## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
2 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone-I (Part-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001346/2022-2023 | 10101/AD | 17/01/2023 | 300 | UCON | 328.79 | 0 | 30
3 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Purba Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000407/2020-2021 | 778/KSD | 14/10/2020 | 45 | M/S KHAJABABA ENTERPRISE | 4.77 | 4.53 | 0
4 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Paschim Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000419/2020-2021 | 796/KSD | 15/10/2020 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 3.86 | 0 | 90
5 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000438/2020-2021 | 824/KSD | 16/10/2020 | 45 | M/S. MOYNA ENTERPRISE | 2.72 | 0 | 0
6 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC at Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000439/2020-2021 | 825/KSD | 16/10/2020 | 45 | ANANDA MAITY | 2.97 | 2.93 | 0
7 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC at Madhya Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000468/2020-2021 | 1046/KSD | 19/12/2020 | 20 | SUDIP KHANRA | 3.16 | 0 | 100
8 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Madhya Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000501/2020-2021 | 1074/KSD | 19/12/2020 | 20 | M/S. PARAMESWAR ENTERPRISE | 4.74 | 4.53 | 0
9 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000709/2023-2024 | 479/AD | 24/01/2024 | 0 | Resource Division | 12.17 | 0 | 0
10 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000702/2023-2024 | 472/AD | 24/01/2024 | 0 | Resource Division | 5.42 | 0 | 0
11 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000078/2020-2021 | 5443/AD | 24/02/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.46 | 54.78 | 90
12 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline for balance portion providing remaining FHTC with allied works at Zone-III of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000373/2022-2023 | 4345/AD | 25/08/2022 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 38.85 | 0 | 50
13 | Alipore Division | Diamond Harbour Sub-Division | Re-laying of distribution pipeline (damaged portion) near Dighirpar Bazar area (in between NP 2-3,NP 5-86,NP 3-186 of Falta (Zone-III) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000826/2022-2023 | 210/DHSD | 02/08/2022 | 45 | SRIJON ENTERPRISE | 4.56 | 0 | 0
14 | Alipore Division | Diamond Harbour Sub-Division | Inter connection between secondary grid and inlet of OHR and restoration of compound area at OHR site of Falta Zone-III for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000828/2022-2023 | 211/DHSD | 02/08/2022 | 45 | SRIJON ENTERPRISE | 2.82 | 0 | 0
15 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000021/2022-2023 | 1198/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
16 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000848/2023-2024 | 786/AD | 03/02/2024 | 0 | Resource Division | 10.26 | 0 | 0
17 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-V including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000020/2021-2022 | 340/AD | 12/05/2021 | 365 | CONCORD ENGINEERING | 309.32 | 65.27 | 90
18 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline due to changing of alignment drawing as per site condition and restoration of distribution pipeline (damaged portion) due to widening of Irrigation canal along with road restoration at Zone-V of Falta Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001113/2022-2023 | 8776/AD | 21/12/2022 | 30 | TIYASHA ENTERPRISE | 33.47 | 0 | 0
19 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000439/2023-2024 | 3621/AD | 30/10/2023 | 0 | Resource Division | 19.73 | 0 | 0
20 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ | AE SWSD-I |  | ORD/000115/2020-2021 | 1464/SWD-I | 21/12/2020 | 120 | M/S. GOUTAM ROY | 66.54 | 27.64 | 0
21 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance work of Providing Functional Household Tap Connection for Bethuabati W/S Scheme & Adjoining Areas under Budge Budge-I block with alied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur under South-24 Pns W/S- Divn-I, PHE Dte. | AE SWSD-I |  | ORD/000328/2022-2023 | 2045/SWD-I | 30/11/2022 | 60 | P.S. AND ASSOCIATES | 20.98 | 0 | 35
22 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ | AE SWSD-I |  | ORD/000329/2020-2021 | 1464/SWD-I JJM | 21/12/2020 | 120 | M/S. GOUTAM ROY | 66.37 | 0 | 100
23 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Dakshin Redokhali Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000057/2022-2023 | 793/AD | 12/05/2022 | 30 | BHATTACHARJEE AND CO. | 17.97 | 0 | 100
24 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000604/2020-2021 | 842/CSD | 12/10/2020 | 45 | ARANYA ENTERPRISE | 4.74 | 0 | 0
25 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000605/2020-2021 | 843/CSD | 12/10/2020 | 45 | TITHI ENTERPRISE | 4.74 | 0 | 0
26 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000606/2020-2021 | 844/CSD | 12/10/2020 | 45 | PROTIVA CONSTRUCTION | 4.74 | 0 | 100
27 | Alipore Division | Canning Sub-division | Relaying of pipeline due to construction of PMGSY road at Dakshin Redokhali W/S Scheme in connection with FHTC work, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (SM/07629) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001017/2023-2024 | 3302/AD | 07/10/2023 | 45 | SAHANA ENTERPRISE | 41.61 | 0 | 90
28 | Alipore Division | Canning Sub-division | Repairing of pipe line and also additional pipe line is required to connect the uncovered habitations at Mouza-Herobhanga, Garkhali, Uttar Rendokhali for FHTC work of Dakshin Rendokhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001062/2021-2022 | 5297/AD | 04/01/2022 | 60 | M/S CHANDIMATA CONSTRUCTION | 33.45 | 0 | 0
29 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001190/2020-2021 | 985/CSD | 13/11/2020 | 45 | GOUTAM HALDAR (I) | 4.65 | 4.64 | 100
30 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001193/2020-2021 | 986/CSD | 13/11/2020 | 45 | SWASTIK CONSTRUCTION | 4.73 | 0 | 0
31 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001382/2020-2021 | 983/CSD | 13/11/2020 | 45 | D.R.CONSTRUCTION | 4.71 | 4.7 | 100
32 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001383/2020-2021 | 984/CSD | 13/11/2020 | 45 | D.R.CONSTRUCTION | 4.62 | 0 | 100
33 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001385/2020-2021 | 987/CSD | 13/11/2020 | 45 | M/S P. B. CONSTRUCTION | 4.79 | 0 | 100
34 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001386/2020-2021 | 988/CSD | 13/11/2020 | 45 | NANDALAL DAS | 4.58 | 0 | 100
35 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001387/2020-2021 | 989/CSD | 13/11/2020 | 45 | P.P. CONCERN | 4.66 | 0 | 0
36 | Alipore Division | Canning Sub-division | roviding Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001389/2020-2021 | 990/CSD | 13/11/2020 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 4.68 | 100
37 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001390/2020-2021 | 991/CSD | 13/11/2020 | 45 | ARANYA ENTERPRISE | 4.78 | 0 | 100
38 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001391/2020-2021 | 992/CSD | 13/11/2020 | 45 | TITHI ENTERPRISE | 4.72 | 0 | 100
39 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001392/2020-2021 | 993/CSD | 13/11/2020 | 45 | TITHI ENTERPRISE | 4.78 | 0 | 0
40 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001406/2021-2022 | 813/CSD | 16/09/2021 | 45 | SHARANYA CONSTRUCTION | 4.78 | 0 | 0
41 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001427/2020-2021 | 994/CSD | 13/11/2020 | 45 | PROTIVA CONSTRUCTION | 4.7 | 0 | 100
42 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001428/2020-2021 | 961/CSD | 07/11/2020 | 45 | ARANYA ENTERPRISE | 4.71 | 0 | 100
43 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001433/2020-2021 | 962/CSD | 07/11/2020 | 45 | TITHI ENTERPRISE | 4.7 | 0 | 100
44 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001435/2020-2021 | 963/CSD | 07/11/2020 | 45 | TITHI ENTERPRISE | 4.69 | 0 | 100
45 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001436/2020-2021 | 964/CSD | 07/11/2020 | 45 | PROTIVA CONSTRUCTION | 4.71 | 0 | 100
46 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001523/2020-2021 | 1191/CSD | 15/12/2020 | 45 | DIPTI ENTERPRISE | 4.74 | 0 | 0
47 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001525/2020-2021 | 1192/CSD | 15/12/2020 | 45 | DIPA CHHETRI | 4.71 | 0 | 95
48 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001527/2020-2021 | 1193/CSD | 15/12/2020 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.65 | 0 | 0
49 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001534/2020-2021 | 1194/CSD | 15/12/2020 | 45 | M/S KALPANA CONSTRUCTION | 4.6 | 0 | 0
50 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001536/2020-2021 | 1195/CSD | 15/12/2020 | 45 | R.G. ENTERPRISE (I) | 4.51 | 0 | 0
51 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001537/2020-2021 | 1196/CSD | 15/12/2020 | 45 | ARANYA ENTERPRISE | 4.74 | 0 | 100
52 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001538/2020-2021 | 1197/CSD | 15/12/2020 | 45 | ARANYA ENTERPRISE | 4.79 | 0 | 100
53 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001539/2020-2021 | 1198/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.74 | 0 | 100
54 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001540/2020-2021 | 1199/CSD | 15/12/2020 | 45 | TITHI ENTERPRISE | 4.7 | 0 | 100
55 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001541/2020-2021 | 1200/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.66 | 0 | 100
56 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001542/2020-2021 | 1201/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.61 | 0 | 100
57 | Alipore Division | Canning Sub-division | Inter connection for TW No. -1 & 2 with reservoir at Dk. Redokhali W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001609/2020-2021 | 1341/CSD | 04/01/2021 | 30 | SUKANTA HALDER | 1.17 | 0 | 90
58 | Alipore Division | Canning Sub-division | Laying of additional pipe line and Protection of pipe line at Dakshin Redokhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002977/2024-2025 | 34./CSD | 09/01/2025 | 30 | BHATTACHARYA ENTERPRISE | 4.63 | 0 | 0
59 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000149/2023-2024 | 840/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
60 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 15 | SUDIP PRADHAN | 11.34 | 0 | 90
61 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000831/2023-2024 | 676/AD | 30/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
62 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 365 | NATURAL RESOURCES CONSORTIUM | 89.65 | 29.55 | 77
63 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Sardarpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000090/2022-2023 | 294/CSD | 20/05/2022 | 40 | NATURAL RESOURCES CONSORTIUM | 4.84 | 0 | 87
64 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 60 | SAHANA ENTERPRISE | 52.81 | 0 | 99
65 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VIII including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based Water Supply Scheme for Falta-Mathurapur" District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000009/2022-2023 | 139/AD | 07/04/2022 | 1080 | TANMAY ROY CHOWDHURY | 277.27 | 0 | 90
66 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Gazipur, Tajpur, Sasan, Pikhira, Purba Gopalpur and Fatepur Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000584/2022-2023 | 5860/AD | 18/10/2022 | 45 | SUPRITI ENTERPRISE | 64.93 | 0 | 55
67 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Rantan, Chaluary, Niogirhat, Durbarat, Kotaldanga, Benapukur, Shibpur, Ramrampur, Mayna and Kalaria Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000585/2022-2023 | 5861/AD | 18/10/2022 | 45 | SUPRITI ENTERPRISE | 63.77 | 0 | 45
68 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000122/2022-2023 | 12048/AD | 27/02/2023 | 0 | Resource Division | 2.61 | 0 | 0
69 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000435/2023-2024 | 3627/AD | 30/10/2023 | 0 | Resource Division | 6.16 | 0 | 0
70 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000437/2023-2024 | 3619/AD | 30/10/2023 | 0 | Resource Division | 33.88 | 0 | 0
71 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Haradhanpur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14159) (SM/09393) (SM/08793) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000450/2025-2026 | 3568/AD | 25/07/2025 | 45 | PALASH HALDAR | 8.12 | 0 | 0
72 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000697/2023-2024 | 467/AD | 24/01/2024 | 0 | Resource Division | 10.8 | 0 | 0
73 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Companirchar W/S Scheme (Phase-A), Haradhanpur W/S Scheme (Phase-A) & Krishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 519/KSD, 24.8.21, T.No. 1784/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | VCH/002604/2021-2022 | BP-2021-22-507 | 22/03/2022 | 0 | LEMNISCATE | 3.53 | 0 | 0
74 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Kakdwip Akshaynagar W/S Scheme (Phase-A), Gobindarampur W/S Scheme (Phase-A), Kashinagar W/S Scheme (Phase-A) & Srikrishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001008/2021-2022 | 514/KSD | 24/08/2021 | 10 | ROY CHOWDHURY ASSOCIATES | 4.7 | 0 | 100
75 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001015/2021-2022 | 533/KSD | 01/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 3.52 | 0 | 100
76 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001016/2021-2022 | 534/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 3.89 | 0 | 100
77 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001017/2021-2022 | 535/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 3.89 | 0 | 100
78 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001038/2021-2022 | 2269/AD | 06/09/2021 | 7 | M/S R.DUTTA & CO. | 2.64 | 0 | 100
79 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001039/2021-2022 | 2270/AD | 06/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.48 | 0 | 100
80 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001042/2021-2022 | 2273/AD | 06/09/2021 | 7 | M/S R.DUTTA & CO. | 2.76 | 0 | 100
81 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000087/2022-2023 | 5590/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
82 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000266/2023-2024 | 3065/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
83 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000379/2023-2024 | 3565/AD | 18/10/2023 | 0 | Resource Division | 5.95 | 0 | 0
84 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000596/2023-2024 | 95/AD | 03/01/2024 | 0 | Resource Division | 27.86 | 0 | 0
85 | Alipore Division | Raidighi Sub-Division | PERMANENT RESTORATION OF TRENCH CUTTING FOR LAYING WATER PIPELINE BY PHE DTE ALONG WITH THE ROAD (HARD CRIST & HARD SHOULDER) AT RIGHT SIDE BETWEEN CH. 0.200 KMP (BISHNUPUR PWD OFFICE) TO CH. 2.600 KMP (LALPUR) & CH. 4.200 KMP (JALGHATA) TO CH. 6.000 KMP (KATANDIGHI) OF PURBA BISHNUPUR-RAIDIGHI ROAD DURING CHEYEAR 2022-23 UNDER JOYNAGAR SUB-DIVISION, PW DTE. | Assistant Engineer, Raidighi sub division |  | BILL/02278/2023-2024 | BP-2023-24-825 | 18/12/2023 | 0 | PUBLIC WORKS DEPARTMENT | 135.47 | 0 | 0
86 | Alipore Division | Raidighi Sub-Division | Laying distribution system for providing FHTC at Zone - VIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000397/2024-2025 | 3160/AD | 30/07/2024 | 30 | KAMALA ENTERPRISE (I) | 20.49 | 0 | 0
87 | Alipore Division | Raidighi Sub-Division | Hydraulic testing and disinfection of laying distribution system including excavation of trial pit of piped water supply at Zone- VIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000995/2023-2024 | 292/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 1.89 | 0 | 100
88 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000011/2022-2023 | 1172/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
89 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000023/2021-2022 | 5660/AD | 27/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
90 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000080/2022-2023 | 5551/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
91 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-D (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000155/2021-2022 | 408/KSD | 07/07/2021 | 15 | M/S KALIPADA JANA | 4.49 | 0 | 100
92 | Alipore Division | Kakdwip Sub-Division | Surging of 2 no. Big dia Tubewell under Debnibus Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000598/2022-2023 | 5923/AD | 19/10/2022 | 15 | S.K.GOLUI | 6.1 | 0 | 100
93 | Alipore Division | Kakdwip Sub-Division | Operation and maintenance of distribution system including rising main for Debnibus Piped Water Supply Scheme of Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [Period from 01.12.2021 to 30.11.2022] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000908/2021-2022 | 768/KSD | 29/11/2021 | 365 | ANANTA KUMAR GIRI | 4.75 | 0 | 100
94 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001031/2021-2022 | 541/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.59 | 0 | 100
95 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block - Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001048/2021-2022 | 2287/AD | 07/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.34 | 0 | 100
96 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000287/2023-2024 | 3083/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
97 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000546/2023-2024 | 10/AD | 02/01/2024 | 0 | Resource Division | 17.88 | 0 | 0
98 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Sankarpur piped water supply scheme ( Mathurapur-I, Zone-XIV) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000571/2021-2022 | 3672/AD | 22/11/2021 | 365 | M/S B.M. CONSTRUCTION | 82 | 0 | 100
99 | Alipore Division |  | Parallel extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Birampur mouza (Node No. 176-177-178-179-180-181-182-184-185) of Sankarpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001586/2021-2022 | 770/RSD | 28/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4.78 | 0 | 100
100 | Alipore Division |  | Extension of pipe line for providing FHTC at Zone-XIV of Mathurapur - I Block (Andharmanik & Sankarpur purba para) under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001767/2021-2022 | 625/RSD | 29/12/2021 | 15 | M/S M. ENTERPRISE | 4.75 | 0 | 100
101 | Alipore Division |  | Dismantling and road restoration in connection with Laying distrubution system of piped water supply at Zone - XIV (Mouza Birampur & Dakhin Janardanpur) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART - A) |  |  | ORD/001793/2022-2023 | 927/RSD | 10/03/2023 | 30 | M/S B.N.ENTERPRISE | 4.82 | 0 | 100
102 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 5658/AD | 27/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
103 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000643/2023-2024 | 247/AD | 15/01/2024 | 0 | Resource Division | 12.06 | 0 | 0
104 | Alipore Division |  | Laying distribution system of piped water supply at Zone-IV of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000480/2021-2022 | 2438/AD | 16/09/2021 | 60 | M/S KALPANA CONSTRUCTION | 50.59 | 0 | 95
105 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Ranaghat piped water supply scheme ( Mathurapur-I, Zone-IV) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) |  |  | ORD/000570/2021-2022 | 3671/AD | 22/11/2021 | 365 | RANADHIR SINHA | 61.42 | 0 | 100
106 | Alipore Division |  | Parallel distribution pipeline to provide FHTC at Purba Ranaghata mouza under Zone-IV of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. |  |  | ORD/001134/2022-2023 | 599/RSD | 23/12/2022 | 30 | SUPER CONSTRUCTION | 4.53 | 0 | 95
107 | Alipore Division |  | Estimate for parallel distribution line for providing FHTC at Purba Ranaghata W/S scheme of Mathurapur - I Block under ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001772/2021-2022 | 630/RSD | 29/12/2021 | 15 | M/S G.M. ASSOCIATES | 4.79 | 0 | 100
108 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 5659/AD | 27/01/2022 | 0 | Resource Division | 1 | 0 | 0
109 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000604/2023-2024 | 234/AD | 11/01/2024 | 0 | Resource Division | 9.69 | 0 | 0
110 | Alipore Division |  | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber under Krishnarampur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000219/2022-2023 | 3060/AD | 13/07/2022 | 30 | KAKALI ENTERPRISE | 8.06 | 0 | 100
111 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/05/2024 to 30/06/2024. |  |  | ORD/000498/2024-2025 | 559A/RSD | 28/04/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
112 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/07/2024 to 31/08/2024. |  |  | ORD/000524/2024-2025 | 612/RSD | 28/06/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
113 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2024 to 31/10/2024. |  |  | ORD/000525/2024-2025 | 685/RSD | 29/08/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
114 | Alipore Division |  | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000658/2024-2025 | 4204/AD | 23/10/2024 | 60 | R.S.CONSTRUCTION CO. | 38.62 | 0 | 0
115 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) |  |  | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 365 | SUPRITI ENTERPRISE | 106.12 | 0 | 100
116 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.03.2023 to 30.04.2023 (Two) Months] |  |  | ORD/002426/2022-2023 | 901/RSD | 28/02/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
117 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2023 to 30/06/2023 (Two) Months] |  |  | ORD/003171/2023-2024 | 48/RSD | 28/04/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
118 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2023 to 31/08/2023 (Two) Months] |  |  | ORD/003172/2023-2024 | 117/RSD | 28/06/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
119 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2023 to 31/10/2023 (Two) Months] |  |  | ORD/003173/2023-2024 | 255/RSD | 29/08/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
120 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/11/2023 to 31/12/2023 (Two) Months] |  |  | ORD/003174/2023-2024 | 335A/RSD | 30/10/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
121 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/01/2024 to 29/02/2024 (Two) Months] |  |  | ORD/003175/2023-2024 | 419/RSD | 22/12/2023 | 62 | SANKAR HALDER | 0.8 | 0 | 0
122 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/03/2024 to 30/04/2024 (Two) Months] |  |  | ORD/003176/2023-2024 | 495A/RSD | 28/02/2024 | 60 | SANKAR HALDER | 0.8 | 0 | 0
123 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 5552/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
124 | Alipore Division |  | HIRE CHARGES BILL FOR VEHICLE NO. WB-19J-6364 |  |  | BILL/02359/2023-2024 | BP-2023-24-867 | 29/12/2023 | 0 | PINTU MONDAL | 1.08 | 0 | 0
125 | Alipore Division |  | HIRE CHARGES BILL OF VEHICLE NO WB-19G-0520 FOR THE MONTH FROM MAY'23 TO AUG'23 |  |  | BILL/02579/2023-2024 | BP-2023-24-698 | 18/11/2023 | 0 | AVIK HALDER | 1.54 | 0 | 0
126 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-XVI (Payla Bhagabanpur PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/001147/2021-2022 | 5535/AD | 20/01/2022 | 365 | FORTUNE ENGINEERING | 18.27 | 0 | 100
127 | Alipore Division |  | Hiring Charges of 1No Motor Cab (Diesel) for the Office fo Assistant Engineer. RWS, Alipore Sub-Division. P.H.E. Dte w.e.f. 01/03/2023 to 31/08/2023) |  |  | ORD/001717/2022-2023 | 757/RWS | 21/02/2023 | 181 | AVIK HALDER | 0.86 | 0 | 20
128 | Alipore Division |  | Remodeling of laying distribution system of piped water supply at Zone- XVI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/002229/2023-2024 | 921/AD | 08/02/2024 | 30 | KARMAKAR CONSTRUCTION | 17.1 | 0 | 90
129 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 5626/AD | 25/01/2022 | 0 | Resource Division | 1.39 | 0 | 0
130 | Alipore Division | Raidighi Sub-Division | Hydraulic testing and disinfection of laying distribution system including excavation of trial pit of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000996/2023-2024 | 293/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 2.44 | 0 | 100
131 | Alipore Division | Raidighi Sub-Division | Protection work for pipe lines at Radhakantapur Abad W/S Scheme (Node point 4-5, 3-4, 6-7, 150-151, 154-155, 73-74, 79-80), modified as Zone- XIV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001906/2023-2024 | 435/RSD | 08/01/2024 | 60 | M/S. M.M. ENTERPRISE | 4.71 | 0 | 0
132 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10534 & SM/15506) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001930/2024-2025 | 109/AD | 08/01/2025 | 60 | A.K. INDUSTRIES | 179.67 | 0 | 0
133 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000655/2023-2024 | 259/AD | 15/01/2024 | 0 | Resource Division | 10.9 | 0 | 0
134 | S24 Pgns Mechanical | Raidighi Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-XIV of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000564/2022-2023 | 580/SMD | 23/02/2023 | 90 | M.S.ENTERPRISE | 26.7 | 0 | 0
135 | Alipore Division | Kakdwip Sub-Division | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Haripur Water Supply Scheme, Block ¿ Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001568/2021-2022 | 6830/AD | 23/03/2022 | 45 | BOSE & CO. | 115.98 | 0 | 80
136 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000795/2023-2024 | 640/AD | 30/01/2024 | 0 | Resource Division | 7.2 | 0 | 0
137 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000103/2021-2022 | 1105/SWD-I JJM | 25/10/2021 | 120 | M/S. S.S. ENTERPRISE | 59.13 | 0 | 100
138 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8296) Part -F | AE SWSD-I |  | ORD/000465/2022-2023 | 2780/SWD-I | 31/01/2023 | 45 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 6.1 | 0 | 100
139 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | VCH/001189/2021-2022 | BP-2021-22-214 | 25/03/2022 | 0 | M/S. S.S. ENTERPRISE | 19.63 | 0 | 0
140 | Alipore Division | Canning Sub-division | Laying of Pipeline to connect the uncovered habitations of Atharabenki W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001577/2022-2023 | 11348/AD | 11/02/2023 | 90 | SAMSUL ENTERPRISE | 130.98 | 0 | 95
141 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001591/2021-2022 | 6962/AD | 29/03/2022 | 120 | SAMSUL ENTERPRISE | 253.28 | 0 | 94
142 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Atharabanki W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001765/2021-2022 | 710/CSD | 24/08/2021 | 365 | MAA LAXMI ENTERPRISE | 4.78 | 0 | 73
143 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000085/2022-2023 | 5548/AD | 29/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
144 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Debnibus, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000274/2023-2024 | 1424/AD | 13/07/2023 | 45 | K.P. CONSTRUCTION | 45.78 | 0 | 100
145 | Alipore Division | Kakdwip Sub-Division | Construction Platform with laying distribution system for providing FHTC, construction of Rising Main, Road Restoration for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000407/2024-2025 | 3190/AD | 31/07/2024 | 75 | K.P. CONSTRUCTION | 89.87 | 0 | 0
146 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 4th tubewell site of Namkhana W/S scheme under JJM, Block : Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000431/2022-2023 | 204/KSD | 01/06/2022 | 7 | SIMPLEX DRILLING CO. | 0.87 | 0 | 100
147 | Alipore Division | Kakdwip Sub-Division | Construction of brick platform, Road Restoration, for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000460/2024-2025 | 3419/AD | 21/08/2024 | 45 | ANANTA KUMAR GIRI | 45.45 | 0 | 60
148 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DEBNIBAS PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000486/2022-2023 | 300/AD | 12/04/2022 | 45 | M/S R.DUTTA & CO. | 8.18 | 0 | 100
149 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. existing big dia Tubewell of Ramtanunagar, Block- Kakdwip and Debnibus W/S Scheme, Block- Namkhana for smooth water supply in existing FHTC under JJM under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000508/2024-2025 | 3608/AD | 06/09/2024 | 30 | S.K.GOLUI | 4.94 | 0 | 100
150 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Debnibus W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000538/2023-2024 | 356/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 100
151 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000767/2022-2023 | 6497/AD | 11/11/2022 | 300 | K.P. CONSTRUCTION | 473.08 | 0 | 25
152 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000773/2022-2023 | 6496/AD | 11/11/2022 | 990 | J.K. CONSTRUCTION | 118.07 | 0 | 70
153 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001605/2021-2022 | 600/KSD | 27/09/2021 | 7 | LEMNISCATE | 4.38 | 0 | 100
154 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Debnibas PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002053/2022-2023 | 731/KSD | 14/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
155 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
156 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 1st Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002137/2024-2025 | 1977/KSD | 23/12/2024 | 20 | COPE ENTERPRISE | 1.79 | 0 | 0
157 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002138/2024-2025 | 1978/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.96 | 0 | 0
158 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 3rd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002139/2024-2025 | 1979/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.95 | 0 | 0
159 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000049/2022-2023 | 3903/AD | 12/08/2022 | 0 | Resource Division | 145.02 | 0 | 0
160 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000801/2023-2024 | 646/AD | 30/01/2024 | 0 | Resource Division | 29.38 | 0 | 0
161 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000974/2023-2024 | 1767/AD | 27/03/2024 | 0 | Resource Division | 1.3 | 0 | 0
162 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/02494/2023-2024 | BP-2023-24-265 | 18/09/2023 | 0 | WBSEDCL | 4.93 | 0 | 0
163 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dosatina water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000540/2022-2023 | 471/SMD | 20/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.92 | 0 | 40
164 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Dosatina Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11503] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002370/2023-2024 | 1378-AE-II-SMD | 14/12/2023 | 15 | AHALYA ENGINEERING WORKS | 0.56 | 0 | 100
165 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supplying and fitting fixing of LED Glow sign board, betterment of external lighting arrangement etc. at P.H. No. 1 under Dosatina Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11503) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002510/2023-2024 | 209-AE-II-SMD | 28/02/2024 | 15 | BHUNIA BUILDERS | 0.75 | 0 | 100
166 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000030/2022-2023 | 914/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 0 | 100
167 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 924] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000187/2022-2023 | 1489/SWD-I | 28/09/2022 | 1001 | NEW STAR CONSTRUCTION | 110.18 | 0 | 70
168 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
169 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, pump house, laying of additional pipeline, and other allied works for DOSATINA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11503] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000258/2024-2025 | 2675/SWD-I | 07/06/2024 | 450 | NEW STAR CONSTRUCTION | 43.67 | 0 | 85
170 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DOSATINA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000385/2023-2024 | 1821/SWD-I | 16/08/2023 | 30 | MOULI CONSTRUCTION | 15.87 | 0 | 70
171 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "DOSTINA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000403/2022-2023 | 457/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 0 | 100
172 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DOSATINA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11503) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000444/2022-2023 | 2663/SWD-I | 18/01/2023 | 60 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 0 | 100
173 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DOSATINA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000506/2022-2023 | 2904/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 100
174 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed DOSATINA Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000807/2022-2023 | 3699/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.96 | 0 | 100
175 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000013/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.69 | 0 | 0
176 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000109/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.65 | 0 | 0
177 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001144/2023-2024 | 556/DHSD | 31/10/2023 | 182 | SUMAN HALDER | 2.4 | 0 | 0
178 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000101/2022-2023 | 7497/AD | 26/11/2022 | 0 | Resource Division | 3.31 | 0 | 0
179 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000123/2022-2023 | 12049/AD | 27/02/2023 | 0 | Resource Division | 3.51 | 0 | 0
180 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000864/2023-2024 | 771/AD | 03/02/2024 | 0 | Resource Division | 16.91 | 0 | 0
181 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000932/2023-2024 | 1274/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
182 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the KALIKAMERYA having village with maximum 34 nos. households, Block - Diamond Harbour -II under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001124/2022-2023 | 8768/AD | 21/12/2022 | 960 | S.S. ENTERPRISE (II) | 26.74 | 0 | 30
183 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | RTOR000885/2023-2024 | 759/AD | 03/02/2024 | 0 | Resource Division | 0.21 | 0 | 0
184 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Payment for new power connection at Kalikamerya PH- I (JL 16, Plot 216/601) under Diamond Harbour- II Block, Dist.- South 24 Pgs. Application No.- 1007639138 Ref. ID- 106542411 | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | BILL/00380/2024-2025 |  | 30/05/2024 | 0 | WBSEDCL | 7.63 | 0 | 0
185 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Quotation payment for new connection at pump house No.-I under Kalikamerya water supply Scheme, South 24 Parganas Mechanical Division, PHE Dte. ( Block- Diamond Harbour-II) Memo No. 1007923539/Quot/03, Dt. 12/07/2024 Ref. ID: 106665830 [ SM/12577 ] | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | BILL/01409/2024-2025 | BP-2024-25-328 | 31/08/2024 | 0 | WBSEDCL | 2.71 | 0 | 0
186 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kalikamerya water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Diamond Harbour-II] | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000546/2022-2023 | 409/SMD | 16/02/2023 | 90 | P.K. ENTERPRISE | 9.25 | 0 | 0
187 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000347/2023-2024 | 1707/AD | 22/07/2023 | 45 | UNITED BUILDERS | 49.55 | 0 | 100
188 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000369/2022-2023 | 4120/AD | 18/08/2022 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 564.7 | 0 | 86
189 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-I), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2023-2024 | 1780/AD | 26/07/2023 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 47.04 | 0 | 100
190 | Alipore Division | Kakdwip Sub-Division | inking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Kamalpur Rudranagar W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000419/2023-2024 | 1908/AD | 01/08/2023 | 30 | FORTUNE ENGINEERING | 25.2 | 0 | 100
191 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAMALPUR RUDRANAGAR) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000476/2022-2023 | 296/AD | 12/04/2022 | 45 | VOYAGER | 8.2 | 0 | 0
192 | Alipore Division | Kakdwip Sub-Division | Sanitary arrangement works and painting works for Pump House No. 4 of Kamalpur Rudranagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000493/2021-2022 | 564/KSD | 10/09/2021 | 45 | PRADIP KUMAR MONDAL | 1.29 | 0 | 100
193 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for augmentation of Kamalpur Rudranagar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000540/2023-2024 | 358/KSD | 09/08/2023 | 62 | S.K.GOLUI | 1.77 | 0 | 100
194 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000289/2023-2024 | 3088/AD | 28/09/2023 | 0 | Resource Division | 20.14 | 0 | 0
195 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000325/2023-2024 | 3140/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
196 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000533/2023-2024 | 17/AD | 02/01/2024 | 0 | Resource Division | 20.14 | 0 | 0
197 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Replacement of TW-1, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000712/2024-2025 | 3420/SMD | 28/10/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.85 | 0 | 0
198 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Replacement of TW-1, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000714/2024-2025 | 3420/SMD | 28/10/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.85 | 0 | 0
199 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at TW-3, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000715/2024-2025 | 3421/SMD | 28/10/2024 | 90 | SMILE | 11.29 | 0 | 0
200 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at TW-3, Zone-II, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000716/2024-2025 | 3422/SMD | 28/10/2024 | 90 | AMIT DAS | 11.25 | 0 | 0
201 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Charges for service connection at Panchagachia-II | Assistant Engineer | Junior Engineer | BILL/00487/2024-2025 | BP-2024-25-115 | 14/06/2024 | 0 | WBSEDCL | 14.23 | 0 | 0
202 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer | Junior Engineer | BILL/04686/2023-2024 | BP-2023-24-513 | 12/02/2024 | 0 | WBSEDCL | 13.25 | 0 | 0
203 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Panch Gachia supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 600/SMD | 27/02/2023 | 855 | AHALYA ENGINEERING WORKS | 23.98 | 0 | 80
204 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 & 2 of Panch Gachia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12240) | Assistant Engineer | Junior Engineer | ORD/002180/2024-2025 | 441/SMSD | 21/03/2025 | 15 | ESENCE ENGINEERING CONCERN | 0.85 | 0 | 0
205 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at PANCH GACHIA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1143] | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 117/SWD-I | 11/04/2023 | 1075 | M/S. GOUTAM ROY | 172.9 | 0 | 60
206 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of boundary walls, platform for FHTC, protection of pipeline, development of land and other allied works for Ground water based PANCH GACHHIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12240) | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 3271/SWD-I | 22/07/2024 | 45 | S. ROY AND ASSOCIATES | 66.2 | 0 | 0
207 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of PANCH GACHHIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000405/2021-2022 | 1940/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0
208 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHGACHIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12240] | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 3060/SWD-I | 21/02/2023 | 30 | AKBAR ALI | 31.75 | 0 | 100
209 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of Pump house cum Chlorine room (Two nos) at PANCH GACHIA piped water supply scheme to accommodate FHTC in BARUIPUR/JOYNAGAR-I BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/12240) | Assistant Engineer | Junior Engineer | ORD/000657/2024-2025 | 4389/SWD-I | 23/10/2024 | 60 | ISHIYA ENTERPRISE | 9.73 | 0 | 100
210 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000185/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 24.23 | 0 | 0
211 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000116/2022-2023 | 1661/AD | 10/06/2022 | 120 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 267.47 | 0 | 71
212 | Alipore Division | Canning Sub-division | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Tube Well No. - 3 at Deuli (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000474/2022-2023 | 5524/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 18.76 | 0 | 0
213 | Alipore Division | Canning Sub-division | Laying of pipe line in place of existing damage line at Deuli Water Supply Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000589/2022-2023 | 5865/AD | 18/10/2022 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 97.22 | 0 | 100
214 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli Water Supply Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001341/2021-2022 | 6020/AD | 15/02/2022 | 365 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 228.74 | 0 | 0
215 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001566/2021-2022 | 6798/AD | 22/03/2022 | 120 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 278.33 | 0 | 72
216 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001655/2021-2022 | 614/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 100
217 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001657/2021-2022 | 615/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.46 | 0 | 100
218 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001658/2021-2022 | 616/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.85 | 0 | 100
219 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001659/2021-2022 | 617/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
220 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001661/2021-2022 | 618/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.54 | 0 | 100
221 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001662/2021-2022 | 619/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.64 | 0 | 100
222 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000062/2022-2023 | 3950/AD | 12/08/2022 | 0 | Resource Division | 11.97 | 0 | 0
223 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000073/2022-2023 | 4850/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
224 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electric bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/00372/2023-2024 | BP-2023-24-27 | 17/05/2023 | 0 | WBSEDCL | 1.98 | 0 | 0
225 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/00394/2023-2024 | BP-2023-24-61 | 09/06/2023 | 0 | WBSEDCL | 1.96 | 0 | 0
226 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Bill for Security Deposit for New Service Connection | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01262/2022-2023 | BP-2022-23-439 | 10/03/2023 | 0 | WBSEDCL | 3.05 | 0 | 0
227 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment for electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01791/2022-2023 | BP-2022-23-459 | 23/03/2023 | 0 | WBSEDCL | 0.76 | 0 | 0
228 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/02559/2023-2024 | BP-2023-24-266 | 18/09/2023 | 0 | WBSEDCL | 0.44 | 0 | 0
229 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/02639/2023-2024 | BP-2023-24-278 | 03/10/2023 | 0 | WBSEDCL | 0.57 | 0 | 0
230 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.1 (Rania) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000269/2022-2023 | 218/SMD | 20/01/2023 | 90 | COOLING CARE CENTER | 11.11 | 0 | 100
231 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.1 (Burul) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000270/2022-2023 | 219/SMD | 20/01/2023 | 90 | SARKAR ELECTRICAL | 11.11 | 0 | 100
232 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.3 (Kashipur Alampur) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000272/2022-2023 | 244/SMD | 27/01/2023 | 90 | S.R. CONCERN | 10.97 | 0 | 100
233 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at OHR Zone No.5 (Chakmanik) water supply scheme under SMD, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000274/2022-2023 | 3918/SMD | 30/12/2022 | 90 | WIZARDTECH SOLUTION | 11.11 | 0 | 100
234 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and fitting fixing additional luminaries, LED glow sign board etc at PH No-1 under OHR Zone No- 5 (Chakmanik) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002101/2023-2024 | 144-AE-II-SMD | 06/02/2024 | 15 | KUNAL ENTERPRISE | 0.75 | 0 | 100
235 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Miscellaneous works in the interest of maintaining proper operational condition at OHR Zone No. 1 (Burul) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002103/2023-2024 | 143-AE-II-SMD | 06/02/2024 | 15 | M/S. GLOBAL POWER CONCERN | 0.75 | 0 | 100
236 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Miscellaneous upliftment works in connection with the external illumination arrangement including other allied works at OHR Zone No. 3 (Kashipur Alampur) Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Budge Budge - II)(SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002104/2023-2024 | 142-AE-II-SMD | 06/02/2024 | 15 | SOHINI ENTERPRISE | 0.75 | 0 | 100
237 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and delivery of Chair, table etc including miscellaneous electrical works at OHR Zone No. 1 (Rania) Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-II) (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002238/2023-2024 | 149-AE-II-SMD | 07/02/2024 | 15 | SUDIP PRADHAN | 0.75 | 0 | 100
238 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 1 (One) no. boundary wall at Burul for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24 Parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000017/2025-2026 | 969/SWD-I | 09/04/2025 | 60 | MS POUSALI ENTERPRISE | 12.01 | 0 | 0
239 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance Upvc Pipeline laying at Burul W/S Scheme for Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs.(TSM/010530) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000045/2023-2024 | 184/SWD-I | 18/04/2023 | 30 | ARKADEEP ENTERPRISE | 19.78 | 0 | 100
240 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Burul Village (Part) to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000054/2022-2023 | 1014/SWD-I | 02/08/2022 | 60 | AHANA ENTERPRISE | 3.81 | 0 | 100
241 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Rania & Kuchigadi Village to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000055/2022-2023 | 1016/SWD-I | 02/08/2022 | 60 | HASIBA ENTERPRISE | 3.81 | 0 | 100
242 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60m X 3.00m) at Burul Village (Part) of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000057/2022-2023 | 1015/SWD-I | 02/08/2022 | 60 | AHANA ENTERPRISE | 3.07 | 0 | 100
243 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60m X 3.00m) at Chakmanik Village (Part) Village of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000059/2022-2023 | 1019/SWD-I | 02/08/2022 | 60 | MS POUSALI ENTERPRISE | 3.06 | 0 | 100
244 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000059/2025-2026 | 1368/SWD-I | 22/05/2025 | 183 | AVIK HALDER | 0.89 | 0 | 0
245 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Burul Village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000108/2022-2023 | 1238/SWD-I | 08/09/2022 | 30 | PADMA ENGINEERING CO. | 20.09 | 0 | 100
246 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Rania & Kuchigadi village of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000109/2022-2023 | 1239/SWD-I | 08/09/2022 | 30 | M/S. S.S. ENTERPRISE | 20.09 | 0 | 100
247 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chakmanik village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000110/2022-2023 | 1240/SWD-I | 08/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 20.08 | 0 | 100
248 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Burul Village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000111/2022-2023 | 1241/SWD-I | 08/09/2022 | 60 | SANJAY MIDDEY | 5.41 | 0 | 100
249 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Rania & Kuchigadi village of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000112/2022-2023 | 1242/SWD-I | 08/09/2022 | 60 | M/S. DAS ENTERPRISE | 8.03 | 0 | 100
250 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipeline for retrofitting of distribution system of Chakmanik Village under South 24-Parganas Water Supply Division-I, P.H.E. Dte. District South 24 Parganas. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000163/2022-2023 | 1408/SWD-I | 22/09/2022 | 90 | M/S. S.S. ENTERPRISE | 77.23 | 0 | 80
251 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of Burul (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000238/2022-2023 | 1713/SWD-I | 02/11/2022 | 120 | M/S. S.S. ENTERPRISE | 165.97 | 0 | 90
252 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of KUCHIGADI (PART) Village & RANIA GOBINDAPUR (PART) under SWD - I, P.H.E. Dte District South 24 Parganas. (No. of FHTC = 632) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000240/2022-2023 | 1727/SWD-I | 03/11/2022 | 90 | FIDERE MARINE SERVICES PVT LTD. | 100.42 | 0 | 80
253 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of Part of Chak Kashipur and Chak Alampur Village under SWD - I, P.H.E. Dte District South 24 Parganas. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000257/2022-2023 | 1698/SWD-I | 01/11/2022 | 90 | TIYASHA ENTERPRISE | 65.45 | 0 | 100
254 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repairing of Pump House and construction of toilet at tubewell site of Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II under South 24-Pgns W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000258/2022-2023 | 1699/SWD-I | 01/11/2022 | 60 | ROYAL CONSTRUCTION | 4.54 | 0 | 100
255 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection of pipeline from proposed Tubewell to Distribution Main for Chak Kashipur (Part) & Chak Alampur(Part) of Budge Budge II Block under South 24 Pgs W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000259/2022-2023 | 1700/SWD-I | 01/11/2022 | 45 | S.R. CONSTRUCTION | 3.94 | 0 | 0
256 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2024 to 30/11/2024] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000288/2024-2025 | 2481/SWD-I | 28/05/2024 | 183 | AVIK HALDER | 0.89 | 0 | 0
257 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chakmanik village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000289/2022-2023 | 1782/SWD-I | 07/11/2022 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 8.54 | 0 | 100
258 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 01 no. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000329/2022-2023 | 2047/SWD-I | 30/11/2022 | 30 | BARI ENTERPRISE | 21.09 | 0 | 100
259 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 0 | 98
260 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 3 (Three) nos. boundary walls for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24- parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000363/2024-2025 | 3505/SWD-I | 07/08/2024 | 45 | MS KRISHNA MONDAL | 44.65 | 0 | 50
261 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (35 Cum capacity) including other allied works at Satgachia village of Budge Budge-II Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000383/2022-2023 | 2362/SWD-I | 22/12/2022 | 150 | RAMASISH ENTERPRISE | 16.78 | 0 | 100
262 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Route Survey and pipeline network design of "RANIA KUCHIGADI & CHAKMANIK Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000535/2022-2023 | 472/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 1.9 | 0 | 100
263 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Route Survey and pipeline network design of "SEKHPARA & BURUL Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000537/2022-2023 | 471/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.01 | 0 | 100
264 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2023 to 31/05/2024] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000664/2023-2024 | 2997/SWD-I | 29/11/2023 | 183 | AVIK HALDER | 0.89 | 0 | 30
265 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at ChakAlampur Village for Zone- 1,3&5 PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000695/2022-2023 | 3498/SWD-I | 16/03/2023 | 15 | BARI ENTERPRISE | 2.2 | 0 | 100
266 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing pipe supporting structures at Burul Water Supply Scheme and other allied works under Providing FHTC with allied works for Zone 1, Zone-3 & Zone-5 of Budge Budge-II under South 24-pgns. Water Supply Division.-I, PHE Dte. Dist- South 24-Pgns. (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000721/2023-2024 | 363/SWD-I | 16/01/2024 | 60 | SOURIK ENTERPRISE | 4.33 | 0 | 100
267 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road crossing of pipeline for interconnection of LDS under Zone-1, 3 & 5 PWSS at 02 locations under Budge Budge-II Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (TSM/10530) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000745/2022-2023 | 3596/SWD-I | 23/03/2023 | 15 | S. ROY AND ASSOCIATES | 7.88 | 0 | 0
268 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000888/2024-2025 | 4875/SWD-I | 29/11/2024 | 182 | AVIK HALDER | 0.88 | 0 | 0
269 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000008/2022-2023 | 1573 | 16/10/2022 | 0 | Resource Division | 16.2 | 0 | 0
270 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 1078 | M/S GHOSH AND CO. | 1160.71 | 0 | 56
271 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000134/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 38.87 | 0 | 0
272 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Arun Nagr Dakshin water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000574/2022-2023 | 599/SMD | 27/02/2023 | 90 | AHALYA ENGINEERING WORKS | 23.98 | 0 | 0
273 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of ARUNNAGAR DAKSHIN Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000207/2021-2022 | 1933/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.03 | 0 | 100
274 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for ARUNNAGAR DAKSHIN PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the arsenic Affected Areas of South 24 Pgs district. [TSM/014830] [2nd Call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000681/2022-2023 | 3481/SWD-I | 15/03/2023 | 30 | KHANDAKAR CONSTRUCTION | 31.75 | 0 | 100
275 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig ground bored 250mm X 150mm dia Tubewell having 66 mtr. housing to achieve 360 mtr. deep Tubewell by Rotary method for ARUN NAGAR DAKSHIN PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/12208] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000710/2024-2025 | 4540/SWD-I | 06/11/2024 | 15 | KHANDAKAR CONSTRUCTION | 4.73 | 0 | 100
276 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, protection wall for laying pipeline and other allied works for Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12208) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000770/2024-2025 | 4746/SWD-I | 20/11/2024 | 180 | S P ENTERPRISE (MURSHIDABAD) | 80.92 | 0 | 40
277 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000141/2022-2023 | 3424/SWD-I | 13/03/2023 | 0 | Resource Division | 7.77 | 0 | 0
278 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000192/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 22.3 | 0 | 0
279 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00005/2023-2024 | BP-2023-24-45 | 18/05/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
280 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KALYANPUR, Khodar Bazar (Khodar Bazar C.T, J.L- 40) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [AFS- GO2223004568PH] [Project ID- PH222355709S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000067/2022-2023 | 1112/SWD-I | 23/08/2022 | 90 | M/S N ISLAM AND CO. | 71.8 | 0 | 25
281 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tubewell by Rotary method for KALYANPUR (Khodar Bazar) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte., within South 24 Parganas District under JJM [AFS- GO2223004568PH] [Project ID- PH222355709S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000070/2022-2023 | 1115/SWD-I | 23/08/2022 | 30 | PADMA ENGINEERING CO. | 20.08 | 0 | 100
282 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KALYANPUR (KHODAR BAZAR), PART-I Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000214/2021-2022 | 1956/SWD-I | 27/01/2022 | 30 | RAMKRISHNA CHAKABORTY | 2.62 | 0 | 100
283 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at KALYANPUR (Khodar Bazar) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns W/S Divn.-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000283/2022-2023 | 1780/SWD-I | 07/11/2022 | 60 | SOMNATH ENTERPRISE | 5.75 | 0 | 100
284 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kalyanpur (Khodar Bazar) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009672] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000792/2022-2023 | 3667/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 2.2 | 0 | 100
285 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000126/2022-2023 | 3329/SWD-I | 09/03/2023 | 0 | Resource Division | 5.01 | 0 | 0
286 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00127/2024-2025 | BP-2024-25-41 | 24/04/2024 | 0 | WBSEDCL | 9.22 | 0 | 0
287 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00285/2023-2024 | BP-2023-24-20 | 15/05/2023 | 0 | WBSEDCL | 5.93 | 0 | 0
288 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Sitakundu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000446/2022-2023 | 3926/SMD | 30/12/2022 | 884 | M/S.UTTAM KUMAR CHATTERJEE | 22.38 | 0 | 40
289 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Sitakundu (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11645) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001592/2024-2025 | 100/SMSD | 21/01/2025 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.91 | 0 | 0
290 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Sitakundu (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11645) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001594/2024-2025 | 98/SMSD | 21/01/2025 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.58 | 0 | 0
291 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for SITAKUNDU ZONE-I Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11645] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000028/2025-2026 | 1061/SWD-I | 22/04/2025 | 30 | MONDAL TUBEWELL | 15.82 | 0 | 0
292 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000080/2022-2023 | 1191/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 0 | 50
293 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at SITAKUNDU (Zone-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1753) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000230/2022-2023 | 1691/SWD-I | 01/11/2022 | 300 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 379.75 | 0 | 80
294 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-I)at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000363/2022-2023 | 2206/SWD-I | 13/12/2022 | 584 | JOY GURU TRADING | 11.52 | 0 | 50
295 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000450/2021-2022 | 1949/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
296 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based SITAKUNDU (ZONE -I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/11645) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000524/2024-2025 | 4017/SWD-I | 13/09/2024 | 60 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 84.63 | 0 | 0
297 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of SITAKUNDU (Zone-I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11645] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000552/2023-2024 | 2500/SWD-I | 06/10/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
298 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000084/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 11.9 | 0 | 0
299 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-VII AT AJODHYANAGAR of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 3427 Nos.) | AE SWSD-II | JE1 | ORD/000515/2022-2023 | 2881/SWD-I | 13/02/2023 | 998 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 379.95 | 0 | 79
300 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000124/2022-2023 | 3365/SWD-I | 09/03/2023 | 0 | Resource Division | 21.11 | 0 | 0
301 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000137/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 21.11 | 0 | 0
302 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00384/2023-2024 | BP-2023-24-59 | 09/06/2023 | 0 | WBSEDCL | 7.37 | 0 | 0
303 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Keshabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000461/2022-2023 | 3938/SMD | 30/12/2022 | 90 | A.K.SIKDAR | 26.02 | 0 | 100
304 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Installation of LED board at P.H No-1 & 2 of Keshbpur water supply scheme under South 24-pgs Mechanical Division PHE Dte. [Block-Sonarpur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/001678/2023-2024 | .1470/SMSD | 01/12/2023 | 15 | A.S.ENTERPRISE | 0.78 | 0 | 100
305 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor illumination arrangement with allied works at Pump House No-2 of Keshabpur W/S Scheme under SMD PHE Dte (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002435/2023-2024 | 1252/SMSD | 22/09/2023 | 15 | A.K.SIKDAR | 0.92 | 0 | 100
306 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work of Laying distribution system for KESHABPUR PWSS to accommodate FHTC in Baruipur Block under South 24 Pgns Water Supply Division-I, PHE. Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Paraganas District (TSM/012609) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000044/2023-2024 | 182/SWD-I | 18/04/2023 | 90 | CREATION CONSTRUCTION | 25.93 | 0 | 50
307 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KESHABPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000093/2022-2023 | 1205/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
308 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at KESHABPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012609] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000119/2022-2023 | 1287/SWD-I | 14/09/2022 | 60 | SUBHRA ENTERPRISE | 10.92 | 0 | 100
309 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KESHABPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000159/2021-2022 | 1919/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
310 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KESHABPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 591) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000219/2022-2023 | 1628/SWD-I | 20/10/2022 | 90 | CREATION CONSTRUCTION | 134.38 | 0 | 85
311 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for KESHABPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/012609] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000452/2023-2024 | 2107/SWD-I | 30/08/2023 | 705 | PADMA ENGINEERING CO. | 4.41 | 0 | 100
312 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for Ground Water based KESABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12059) [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000718/2024-2025 | 4552/SWD-I | 06/11/2024 | 320 | SHAH ENTERPRISE | 71.43 | 0 | 50
313 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000272/2023-2024 | 2419/SWD-I | 30/09/2023 | 0 | Resource Division | 33.16 | 0 | 0
314 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000336/2023-2024 | 264/SWD-I | 10/01/2024 | 0 | Resource Division | 3.64 | 0 | 0
315 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Charges for new service connection at Sahebpur pump house-II | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00216/2024-2025 | BP-2024-25-60 | 16/05/2024 | 0 | WBSEDCL | 15.3 | 0 | 0
316 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00515/2023-2024 | BP-2023-24-78 | 13/06/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
317 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Sahebpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000125/2023-2024 | 1124/SMD | 24/04/2023 | 674 | P.P. CONCERN | 21.75 | 0 | 100
318 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at P.H. No-1 & 2 of Sahebpur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002000/2024-2025 | 427/SMSD | 20/03/2025 | 21 | SHRI KRISHNA ENTERPRISE | 0.79 | 0 | 0
319 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Sahebpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002706/2023-2024 | 1307/SMSD | 03/10/2023 | 15 | P.P. CONCERN | 0.89 | 0 | 100
320 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Sahebpur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015503] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000338/2022-2023 | 2074/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 0 | 100
321 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAHEBPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13675] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000517/2022-2023 | 2914/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.19 | 0 | 50
322 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2108] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000543/2022-2023 | 3032/SWD-I | 20/02/2023 | 300 | SUPER SKILL | 389.1 | 0 | 30
323 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 150.0 Mtr Boundary Wall Temporary approach road and land development at head work site and Eucaliptus Bullah piling work with drum sheet near Sahebpur FP school of Sahebpur PWSS within Sonarpur block SAHEBPUR piped water scheme to accommodate FHTC in Sonarpur Block under South 24-Pgns, W/S Division-I, P.H.E. Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13675] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000758/2023-2024 | 659/SWD-I | 06/02/2024 | 60 | SUPER SKILL | 36.95 | 0 | 30
324 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of SAHEBPUR PWSS within Sonarpur Block "SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13675) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000760/2023-2024 | 661/SWD-I | 06/02/2024 | 45 | NILKANTHA ENTERPRISE | 10.37 | 0 | 100
325 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Temporary approach road, Eucalyptus Bullah piling work with Drumsheet and allied works at SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13675) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001140/2024-2025 | 4652/SWD-I | 14/11/2024 | 30 | S M ENTERPRISE (SANAT MONDAL) | 22.65 | 0 | 0
326 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000029/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 26.26 | 0 | 0
327 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000239/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.99 | 0 | 0
328 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
329 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Kanthalberia, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000673/2023-2024 | 2700/AD | 07/09/2023 | 600 | GHOSH CONSTRUCTION (GOCHARAN) | 539.93 | 0 | 30
330 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Kanthalberia W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - IV) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000746/2024-2025 | 4413/AD | 05/11/2024 | 30 | G.B. CONSTRUCTION (TW) | 19.68 | 0 | 0
331 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. IV) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001225/2024-2025 | 5224/AD | 16/12/2024 | 45 | NEW DAWN POWER & CONSTRUCTION | 6.94 | 0 | 0
332 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Kanthalberia W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.E. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001678/2023-2024 | 1353/CSD | 18/12/2023 | 45 | S.K.GOLUI | 3.72 | 0 | 100
333 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Kanthalberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000014/2023-2024 | 949/SMD | 04/04/2023 | 90 | M/S. BABUSONA ENTERPRISE | 11.7 | 0 | 0
334 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Kathalberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000492/2022-2023 | 294/SMD | 03/02/2023 | 90 | SUPER SKILL | 13.01 | 0 | 0
335 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Bhajna PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/12732) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000190/2024-2025 | 2548/AD | 18/06/2024 | 60 | JAL PRAVAHIKA PVT. LTD. | 55.49 | 0 | 0
336 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Bhajna W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000341/2022-2023 | 6151/AD | 01/11/2022 | 45 | R.K. CONSTRUCTION | 36.69 | 0 | 50
337 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BHAJNA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000483/2022-2023 | 4192/AD | 22/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.3 | 0 | 100
338 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Bhajna W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000583/2023-2024 | 2340/AD | 18/08/2023 | 45 | JAL PRAVAHIKA PVT. LTD. | 42.49 | 0 | 0
339 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Bhajna Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000901/2022-2023 | 7275/AD | 24/11/2022 | 1083 | JAL PRAVAHIKA PVT. LTD. | 344.09 | 0 | 55
340 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bhajna W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000919/2023-2024 | 2972/AD | 26/09/2023 | 45 | M/S KHAJABABA ENTERPRISE | 28.21 | 0 | 100
341 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bhajna W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000920/2023-2024 | 2973/AD | 26/09/2023 | 45 | M/S. MAA MENAKA ENTERPRISE | 9.49 | 0 | 0
342 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bhajna PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002054/2022-2023 | 734/KSD | 16/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
343 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
344 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000084/2023-2024 | 530/AD | 12/05/2023 | 0 | Resource Division | 9 | 0 | 0
345 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000524/2023-2024 | 4933/AD | 22/12/2023 | 0 | Resource Division | 35.87 | 0 | 0
346 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000579/2023-2024 | 51/AD | 03/01/2024 | 0 | Resource Division | 1.56 | 0 | 0
347 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00373/2023-2024 | BP-2023-24-25 | 17/05/2023 | 0 | WBSEDCL | 7.12 | 0 | 0
348 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01887/2023-2024 | BP-2023-24-219 | 23/08/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
349 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Bhajna water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000355/2022-2023 | 3759/SMD | 29/12/2022 | 90 | AHALYA ENGINEERING WORKS | 21.74 | 0 | 65
350 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/01057/2023-2024 | BP-2023-24-124 | 17/07/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
351 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rajak Gohalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000443/2022-2023 | 150/SMD | 16/01/2023 | 90 | STANDARD ENGINEERING | 26.27 | 0 | 50
352 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Rajak Gohalia Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11778] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002239/2023-2024 | 11-AE-II-SMD | 03/01/2024 | 15 | STANDARD ENGINEERING | 0.58 | 0 | 100
353 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Miscellaneous works for the sake of maintaining favourable operating condition by providing No.-1 under Rajak Gohalia Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11778) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002452/2023-2024 | 184-AE-II-SMD | 20/02/2024 | 15 | M. N. ENTERPRISE | 0.75 | 0 | 100
354 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for RAJAK GOHALIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11778] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000177/2022-2023 | 1452/SWD-I | 26/09/2022 | 30 | DIPALI CONSTRUCTION | 14.26 | 0 | 100
355 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
356 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of RAJAK GOHATIA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000227/2021-2022 | 1980/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 0 | 100
357 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Rajakgohalia PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11778) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000256/2024-2025 | 2673/SWD-I | 07/06/2024 | 475 | LAKSHMI NARAYAN SAHOO | 63.98 | 0 | 57
358 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of RAJAK GOHALIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11778) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000443/2022-2023 | 2662/SWD-I | 18/01/2023 | 60 | M/S PANJA ENTERPRISE | 6.02 | 0 | 100
359 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based RAJAK GOHALIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 963 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000472/2022-2023 | 2791/SWD-I | 01/02/2023 | 570 | LAKSHMI NARAYAN SAHOO | 107.44 | 0 | 40
360 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAJAK GOHALIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011742] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000523/2022-2023 | 2913/SWD-I | 14/02/2023 | 15 | DIPALI CONSTRUCTION | 1.57 | 0 | 0
361 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for RAJAK GOHALIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011742] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000589/2022-2023 | 3109/SWD-I | 24/02/2023 | 736 | MOULI CONSTRUCTION | 15.88 | 0 | 70
362 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000114/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.18 | 0 | 0
363 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04093/2023-2024 | BP-2023-24-422 | 16/12/2023 | 0 | WBSEDCL | 8.62 | 0 | 0
364 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandaneswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000573/2022-2023 | 598/SMD | 27/02/2023 | 90 | AHALYA ENGINEERING WORKS | 22.93 | 0 | 90
365 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandaneswar PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011097] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 26/SWD-I | 05/04/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 0 | 100
366 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHANDANESWAR PWSS of Joynagar-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011097] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000213/2022-2023 | 1585/SWD-I | 17/10/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 100
367 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, approach road, development of land and other allied works for Ground water based CHANDANESWAR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/13011) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 2640/SWD-I | 07/06/2024 | 450 | M/S L.P CONSTRUCTION | 62.59 | 0 | 95
368 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHANDANESWAR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000224/2021-2022 | 1928/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
369 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Chandaneswar of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 2213/SWD-I | 13/12/2022 | 60 | ALISHA CONSTRUCTION | 11.52 | 0 | 100
370 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000304/2023-2024 | 2441/SWD-I | 30/09/2023 | 0 | Resource Division | 12.91 | 0 | 0
371 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III A at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4631] | AE BSD |  | ORD/000031/2023-2024 | 115/SWD-I | 11/04/2023 | 120 | SUPRITI ENTERPRISE | 352.02 | 0 | 30
372 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 120 | MANASH GHOSH | 626.38 | 0 | 91
373 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III B at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4773] | AE BSD |  | ORD/000588/2022-2023 | 3123/SWD-I | 24/02/2023 | 120 | MANASH GHOSH | 363.26 | 0 | 50
374 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000074/2022-2023 | 2990/SWD-I | 20/02/2023 | 0 | Resource Division | 57.93 | 0 | 0
375 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Thangara PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000051/2023-2024 | 37/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
376 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000333/2022-2023 | 4063/AD | 18/08/2022 | 30 | MUKHERJEE ENTERPRISE (II) | 17.79 | 0 | 95
377 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000334/2022-2023 | 4064/AD | 18/08/2022 | 30 | M/S. GANGA ENTERPRISE | 11.81 | 0 | 100
378 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000344/2022-2023 | 4071/AD | 18/08/2022 | 45 | AQUATECH ENGINEERS | 37.06 | 0 | 0
379 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary etc. at Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11850) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000464/2024-2025 | 3423/AD | 21/08/2024 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 21.44 | 0 | 0
380 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (THANGARA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000502/2022-2023 | 2495/AD | 27/06/2022 | 45 | LEMNISCATE | 3.94 | 0 | 100
381 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Thangara W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001155/2023-2024 | 3718/AD | 03/11/2023 | 30 | M/S. M.S. ENTERPRISE | 9.51 | 0 | 100
382 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001316/2022-2023 | 9881/AD | 10/01/2023 | 300 | PATHIK PABAN NANDI | 281.34 | 0 | 55
383 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Thangara W/S Scheme, Block: Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001480/2023-2024 | 4683/AD | 18/12/2023 | 275 | M/S IDEAL WORKS | 25.92 | 0 | 100
384 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
385 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000119/2023-2024 | 655/AD | 17/05/2023 | 0 | Resource Division | 5.66 | 0 | 0
386 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000441/2023-2024 | 4709/AD | 18/12/2023 | 0 | Resource Division | 42.17 | 0 | 0
387 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000808/2023-2024 | 653/AD | 30/01/2024 | 0 | Resource Division | 1.02 | 0 | 0
388 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000991/2023-2024 | 1784/AD | 27/03/2024 | 0 | Resource Division | 5.39 | 0 | 0
389 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/01714/2023-2024 | BP-2023-24-203 | 09/08/2023 | 0 | WBSEDCL | 8.38 | 0 | 0
390 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Thangara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000432/2022-2023 | 3828/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE | 21.52 | 0 | 98
391 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of Thangara water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000589/2024-2025 | 746-AE-I-SMD | 28/05/2024 | 15 | M/S. GLOBAL POWER CONCERN | 0.78 | 0 | 0
392 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at , PH-1 of Thangara W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002994/2023-2024 | 443-AE-I-SMD | 20/02/2024 | 15 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0
393 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at , PH-2 of Thangara W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002995/2023-2024 | 444-AE-I-SMD | 20/02/2024 | 15 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0
394 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000198/2024-2025 | 2581/AD | 19/06/2024 | 45 | SHIBU BISWAS | 38.17 | 0 | 0
395 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, construction of 01 no. Pump House Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Lakshmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000360/2023-2024 | 1561/AD | 17/07/2023 | 90 | SHIBU BISWAS | 189.75 | 0 | 92
396 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Laxmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000362/2022-2023 | 4117/AD | 18/08/2022 | 30 | M/S NAIYA & MAITY | 18.12 | 0 | 100
397 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and Road Restoration for Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (PART-II) (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000462/2024-2025 | 3421/AD | 21/08/2024 | 185 | ANANTA KUMAR GIRI | 67.99 | 0 | 20
398 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000469/2022-2023 | 316/HQ-I/AD | 29/08/2022 | 183 | FIROJA KHATUN | 2.4 | 0 | 38
399 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( LASKHMIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000494/2022-2023 | 2493/AD | 27/06/2022 | 45 | LEMNISCATE | 5.79 | 0 | 100
400 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2024 To 28.02.2025) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000648/2024-2025 | 3815/AD | 29/08/2024 | 183 | FIROJA KHATUN | 2.4 | 0 | 100
401 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001043/2023-2024 | 155-/HQ-I/AD | 31/08/2023 | 182 | FIROJA KHATUN | 2.4 | 0 | 20
402 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Laxmipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001159/2023-2024 | 3721/AD | 03/11/2023 | 30 | ANANDA CONSTRUCTION | 9.63 | 0 | 88
403 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including soil investigation including for Laxmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001588/2024-2025 | 100/AD | 08/01/2025 | 270 | KALPANA TRADERS | 134.8 | 0 | 0
404 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Laskhmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001724/2022-2023 | 11750/AD | 21/02/2023 | 30 | MODERN CONSTRUCTION (NEW) | 19.3 | 0 | 20
405 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001836/2022-2023 | 551/HQ-I/AD | 27/02/2023 | 181 | FIROJA KHATUN | 2.4 | 0 | 40
406 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
407 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.03.2024 To 31.08.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002393/2023-2024 | 1195/AD | 28/02/2024 | 182 | FIROJA KHATUN | 2.4 | 0 | 100
408 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000444/2023-2024 | 4711/AD | 18/12/2023 | 0 | Resource Division | 25.6 | 0 | 0
409 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000586/2023-2024 | 85/AD | 03/01/2024 | 0 | Resource Division | 1.49 | 0 | 0
410 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000809/2023-2024 | 654/AD | 30/01/2024 | 0 | Resource Division | 13.01 | 0 | 0
411 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000993/2023-2024 | 1786/AD | 27/03/2024 | 0 | Resource Division | 36.04 | 0 | 0
412 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Laxmipur W/S Scheme PH-1 Application No:- 1007169430 Reference ID:- 106214425 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00966/2024-2025 | BP-2024-25-192 | 23/07/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
413 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Heria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000395/2022-2023 | 3797/SMD | 29/12/2022 | 90 | A.K.SIKDAR | 22.21 | 0 | 0
414 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 144.00m), Approach Road (length = 30.00m) and Construction of Pump House (5.40 Mtr. X 3.60 Mtr.) with water supply & sanitary arrangementat OHR site (1st Tube well Site) for HERIA PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000009/2025-2026 | 933/SWD-I | 07/04/2025 | 60 | SUBHO CONSTRUCTION | 32.33 | 0 | 0
415 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Heria PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014760] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000015/2023-2024 | 39/SWD-I | 06/04/2023 | 15 | DIPALI CONSTRUCTION | 3.13 | 0 | 0
416 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Heria PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000296/2022-2023 | 1876/SWD-I | 16/11/2022 | 30 | DIPALI CONSTRUCTION | 30.03 | 0 | 0
417 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "HERIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000390/2022-2023 | 409/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 0 | 0
418 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 200 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of HERIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1561] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000529/2022-2023 | 2949/SWD-I | 16/02/2023 | 300 | M/S PRADIP KUMAR PAL (EMAIL ID- PRADIPKUMARPAL.CO@GMAIL.COM) | 378.82 | 0 | 0
419 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000788/2023-2024 | 1071/SWD-I | 04/03/2024 | 30 | M/S ARINDAM MONDAL | 29.88 | 0 | 0
420 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12772] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000845/2023-2024 | 1251/SWD-I | 13/03/2024 | 30 | M/S ARINDAM MANDAL | 3.12 | 0 | 0
421 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 57.60m), Development of land, Construction of Service Road (length = 15.00m) and Pump House at 2nd Tubewell site for HERIA PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Divn.-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001160/2024-2025 | 401/SWD-I | 06/02/2025 | 60 | BHANDARY CONSTRUCTION | 15.38 | 0 | 0
422 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000160/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.16 | 0 | 0
423 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Moukhali-Kumarkhali (Part - VI) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000788/2022-2023 | 6643/AD | 14/11/2022 | 929 | MAITY SUPPLIERS | 47.01 | 0 | 80
424 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001902/2022-2023 | 5666/AD. | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.38 | 0 | 100
425 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000171/2023-2024 | 1124/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
426 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00626/2023-2024 | BP-2023-24-89 | 14/06/2023 | 0 | WBSEDCL | 5.37 | 0 | 0
427 | Alipore Division | Canning Sub-division | Laying of pipeline and other allied work of Augmentation of Moukhali-Kumarkhali (Zone-II) RO Plant to Model School (English Medium), Canning-II Tambuldaha GP Office, Bakultala Jr. High Madrasha etc under Moukhali-Kumarkhali W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000220/2023-2024 | 1025/AD | 13/06/2023 | 30 | M/S. TAPAS MONDAL | 16.21 | 0 | 98
428 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - II) having village with maximum 124 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000785/2022-2023 | 6640/AD | 14/11/2022 | 60 | D.N. ENTERPRISE | 47.22 | 0 | 60
429 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001898/2022-2023 | 5662/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.39 | 0 | 0
430 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000167/2023-2024 | 1120/AD | 22/06/2023 | 0 | Resource Division | 0.76 | 0 | 0
431 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00390/2023-2024 | BP-2023-24-53 | 09/06/2023 | 0 | WBSEDCL | 4.75 | 0 | 0
432 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00629/2023-2024 | BP-2023-24-88 | 14/06/2023 | 0 | WBSEDCL | 1.59 | 0 | 0
433 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-II) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000587/2022-2023 | 644/SMD | 02/03/2023 | 760 | SUDIP PRADHAN | 8.83 | 0 | 100
434 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - IX) having village with maximum 173 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000793/2022-2023 | 6682/AD | 14/11/2022 | 60 | UCON | 53.36 | 0 | 35
435 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-IX) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001905/2022-2023 | 5669/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.43 | 0 | 0
436 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000174/2023-2024 | 1127/AD | 22/06/2023 | 0 | Resource Division | 1.07 | 0 | 0
437 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00520/2023-2024 | BP-2023-24-71 | 13/06/2023 | 0 | WBSEDCL | 6.87 | 0 | 0
438 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - XI) having village with maximum 272 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000795/2022-2023 | 6684/AD | 14/11/2022 | 780 | M/S. L.P. CONSTRUCTION | 59.22 | 0 | 65
439 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-XI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001908/2022-2023 | 5671/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.58 | 0 | 0
440 | Alipore Division | Canning Sub-division | Construction of Culvert for canal crossing in front of Khunkhali Part - II, Mini PWSS Scheme, under Canning Sub-Division of Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003333/2024-2025 | 1319/CSD | 22/11/2024 | 30 | M/S. R.M. CONSTRUCTION | 4.49 | 0 | 95
441 | Alipore Division | Canning Sub-division | Laying DI Pipe from Tubewell to Distribution for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Khunkhali (Part - I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003337/2024-2025 | 35./CSD | 09/01/2025 | 30 | M/S. M.M. ENTERPRISE | 4.64 | 0 | 95
442 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000176/2023-2024 | 1129/AD | 22/06/2023 | 0 | Resource Division | 1.68 | 0 | 0
443 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00522/2023-2024 | BP-2023-24-70 | 13/06/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
444 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-IV) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000589/2022-2023 | 650/SMD | 03/03/2023 | 90 | B. P. CONSTRUCTION | 8.85 | 0 | 100
445 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-XI at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/13909] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000010/2025-2026 | 1621/AD | 03/04/2025 | 150 | M/S. J.K. TRIPATHI & SONS | 120.58 | 0 | 10
446 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-XI of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000071/2025-2026 | 2260/AD | 14/05/2025 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 19.56 | 0 | 0
447 | Alipore Division | Diamond Harbour Sub-Division | Restoration of W.B.M damaged due to laying of pipes from Raghunathpur more to Rajarampur F.P School under Kulpi Zone X under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000349/2025-2026 | 3130/AD | 03/07/2025 | 30 | SAMIM AHMED | 11.64 | 0 | 100
448 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4113] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002066/2022-2023 | 12976/AD | 22/03/2023 | 900 | ABDUL HAI | 463.63 | 0 | 20
449 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-XI (Uttar Iswaripur, OHR Size-550) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002102/2022-2023 | 343/DHSD | 18/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
450 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000199/2023-2024 | 1624/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
451 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000214/2023-2024 | 2023/AD | 05/08/2023 | 0 | Resource Division | 14.51 | 0 | 0
452 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000365/2023-2024 | 3229/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
453 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000624/2023-2024 | 285/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
454 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000853/2023-2024 | 760/AD | 03/02/2024 | 0 | Resource Division | 16.1 | 0 | 0
455 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000122/2024-2025 | 2400/AD | 07/06/2024 | 270 | PRADIP KUMAR MONDAL | 11.8 | 0 | 95
456 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000207/2023-2024 | 790/AD | 24/05/2023 | 597 | M/S. S.S. ENTERPRISE | 49.26 | 0 | 100
457 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
458 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001034/2022-2023 | 4153/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.9 | 0 | 100
459 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Gangapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002074/2023-2024 | 770(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
460 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
461 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002154/2023-2024 | 800/AD | 05/02/2024 | 60 | M/S.SREEJIT ENTERPRISE | 33.05 | 0 | 0
462 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000106/2023-2024 | 642/AD | 17/05/2023 | 0 | Resource Division | 7.31 | 0 | 0
463 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000500/2023-2024 | 4950/AD | 22/12/2023 | 0 | Resource Division | 21.84 | 0 | 0
464 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000749/2023-2024 | 584/AD | 29/01/2024 | 0 | Resource Division | 1.31 | 0 | 0
465 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000954/2023-2024 | 1688/AD | 22/03/2024 | 0 | Resource Division | 7.77 | 0 | 0
466 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Gangapur PH-2, W/S Scheme Application No- 1007196380 Reference ID:- 106231315 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02231/2024-2025 | BP-2024-25-504 | 19/12/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
467 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gangapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000378/2022-2023 | 3782/SMD | 29/12/2022 | 90 | SUBHRA ENTERPRISE | 18.5 | 0 | 0
468 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Anduldaha Gopalpur having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001734/2022-2023 | 11764/AD | 21/02/2023 | 60 | M/S S.M. ENTERPRISE | 32.54 | 0 | 0
469 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000871/2023-2024 | 778/AD | 03/02/2024 | 0 | Resource Division | 0.65 | 0 | 0
470 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Anduldaha Gopalpur Village of Karanjali Gram Panchyet Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000608/2022-2023 | 749/SMD | 15/03/2023 | 90 | MEGA SOLAR ENERGY | 8.85 | 0 | 0
471 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sudhanshupur piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1167] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000294/2023-2024 | 1504/AD | 15/07/2023 | 300 | SARDAR ENTERPRISE | 488.97 | 0 | 30
472 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sudhansupur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000490/2023-2024 | 1791/AD | 26/07/2023 | 30 | M/S MODINA ENTERPRISE | 15.27 | 0 | 0
473 | Alipore Division | Canning Sub-division | : Construction of boundary wall at Head Work site for Augmentation of Sudhansupur Piped Water Supply Scheme, Block- Gosaba under Canning Sub-Division of Alipore Division PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000734/2024-2025 | 4392/AD | 05/11/2024 | 30 | SARDAR ENTERPRISE | 29.93 | 0 | 0
474 | Alipore Division | Canning Sub-division | Survey, Design and DPR preparation for Augmentation of ground water based Sudhanshupur Water Supply Scheme to accommodate FHTC in Gosaba Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002065/2022-2023 | 1470/CSD | 28/03/2023 | 15 | TECH VISION | 3.84 | 0 | 95
475 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000042/2023-2024 | 249/AD | 24/04/2023 | 0 | Resource Division | 32.05 | 0 | 0
476 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000163/2023-2024 | 1056/AD | 15/06/2023 | 0 | Resource Division | 7.19 | 0 | 0
477 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/05699/2023-2024 | BP-2023-24-609 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
478 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline (left out portion) and protection works of pipeline as required in Part B and C of Zone-V under Kulpi Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000583/2022-2023 | 5859/AD | 18/10/2022 | 15 | MAA BHABANI CONSTRUCTION (DUM DUM) | 12.04 | 0 | 80
479 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-V at Kulpi block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 4527] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001395/2022-2023 | 10867/AD | 04/02/2023 | 90 | UCON | 340.41 | 0 | 0
480 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000192/2023-2024 | 1632/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
481 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000207/2023-2024 | 2027/AD | 05/08/2023 | 0 | Resource Division | 23.16 | 0 | 0
482 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000363/2023-2024 | 3227/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
483 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000628/2023-2024 | 292/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
484 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000855/2023-2024 | 762/AD | 03/02/2024 | 0 | Resource Division | 3.25 | 0 | 0
485 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000935/2023-2024 | 1277/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
486 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Tajpur Fatepur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 1043/SMD | 17/04/2023 | 90 | M/S. S.S. ENTERPRISE (DOMKAL) | 22.55 | 0 | 0
487 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of TAJPUR FATEPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2497] [TSM/018300] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 587/SWD-I | 16/05/2023 | 300 | DIVINE | 531.16 | 0 | 25
488 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Restoration of Road, and other allied works for "Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to Accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/14861) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000356/2024-2025 | 3456/SWD-I | 02/08/2024 | 45 | DIVINE | 84.28 | 0 | 0
489 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for TAJPUR FATEPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018300] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000613/2022-2023 | 3212/SWD-I | 28/02/2023 | 30 | NAJMUL HAQUE | 31.62 | 0 | 5
490 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000954/2022-2023 | 1305/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.66 | 0 | 100
491 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000096/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 35.84 | 0 | 0
492 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Chak Haradhanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 1050/SMD | 17/04/2023 | 90 | B.T.PROJECTS PVT.LTD. | 22.98 | 0 | 0
493 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of CHAK HARANANDAPUR MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1956] [TSM/018438] | Assistant Engineer | Junior Engineer | ORD/000059/2023-2024 | 276/SWD-I | 24/04/2023 | 90 | M/S. GOUTAM ROY | 237.12 | 0 | 70
494 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK HARANANDAPUR Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14864] | Assistant Engineer | Junior Engineer | ORD/000094/2025-2026 | 1769/SWD-I | 02/07/2025 | 30 | PADMA ENGINEERING CO. | 19.14 | 0 | 0
495 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based CHAK HARANANDAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14864) | Assistant Engineer | Junior Engineer | ORD/000349/2024-2025 | 3443/SWD-I | 02/08/2024 | 90 | M/S. GOUTAM ROY | 201.5 | 0 | 0
496 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for CHAK HARANANDAPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018438][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000689/2022-2023 | 3478/SWD-I | 15/03/2023 | 383 | MUNNA AGROTECH ENTERPRISE | 31.78 | 0 | 50
497 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Chak Haranandapur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000972/2022-2023 | 1406/SWD-I | 21/09/2022 | 30 | GEO SOLUTION | 2.55 | 0 | 100
498 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 16.64 | 0 | 0
499 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - IV) having village with maximum 124 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000786/2022-2023 | 6641/AD | 14/11/2022 | 60 | CAMELIA CONSTRUCTION | 48.44 | 0 | 90
500 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001900/2022-2023 | 5664/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
501 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000169/2023-2024 | 1122/AD | 22/06/2023 | 0 | Resource Division | 0.76 | 0 | 0
502 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00392/2023-2024 | BP-2023-24-54 | 09/06/2023 | 0 | WBSEDCL | 4 | 0 | 0
503 | Alipore Division | Baruipur Sub-Division | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala | AE BSD,Assistant Engineer | Junior Engineer | BILL/01696/2024-2025 | BP-2024-25-785 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0
504 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Purba Begampur (Zone-II) W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000350/2024-2025 | 965/SMSD | 09/07/2024 | 15 | S. DUTTA | 0.89 | 0 | 0
505 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Purba Begampur (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 924/SMSD | 28/06/2024 | 15 | S. DUTTA | 0.58 | 0 | 0
506 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Purba Begampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 235/SMD | 24/01/2023 | 981 | S. DUTTA | 23.29 | 0 | 40
507 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, Pipeline protection, Platform for FHTC, Land development and other allied works for Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns District.(SM/13779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000353/2024-2025 | 3453/SWD-I | 02/08/2024 | 45 | SRIJON ENTERPRISE | 80.58 | 0 | 0
508 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of PURBO BEGAMPUR (ZONE-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1967] [TSM/011437] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 1763/SWD-I | 10/08/2023 | 1021 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 670.09 | 0 | 55
509 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BEGAMPUR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000447/2021-2022 | 1952/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
510 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PURBA BEGAMPUR (Zone-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13779] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 3061/SWD-I | 21/02/2023 | 30 | M/S B.M. INDUSTRIES (BM.INDUSTRY@GMAIL.COM) | 31.76 | 0 | 100
511 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000164/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 27.14 | 0 | 0
512 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bakeswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000511/2022-2023 | 350/SMD | 09/02/2023 | 90 | S.P. CONSTRUCTION | 22.37 | 0 | 0
513 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAKESWAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2430) [TSM/016358]. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000169/2023-2024 | 966/SWD-I | 08/06/2023 | 90 | M/S B.D. ENTERPRISE | 266.82 | 0 | 28
514 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of BAKESWAR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/016358] (2nd call) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000236/2023-2024 | 1419/SWD-I | 17/07/2023 | 593 | NIKHIL SAMADDAR | 18.78 | 0 | 100
515 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of BAKESWAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000422/2021-2022 | 1972/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 0
516 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
517 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BAKESWAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016358] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000579/2022-2023 | 3096/SWD-I | 23/02/2023 | 616 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.87 | 0 | 100
518 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, land development, approach road, pipeline protection and road restoration for BAKESWAR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/13782) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000656/2024-2025 | 4381/SWD-I | 22/10/2024 | 482 | A.K. SIKDAR | 180.08 | 0 | 12
519 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development of OHR / 1st Tubewell site at Bakeswar PWSS in the Arsenic Affected areas South 24-Pgns. Dist in Bishnupur-I Block under South 24-Parganas W/S Division-I, P.H.E. Dte. (SM/13782) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000711/2024-2025 | 4541/SWD-I | 06/11/2024 | 30 | SRIJON ENTERPRISE | 28.8 | 0 | 100
520 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000092/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 41.75 | 0 | 0
521 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying different dia. specials for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000150/2024-2025 | 2488/AD | 14/06/2024 | 60 | UCON (II) | 31.23 | 0 | 0
522 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000425/2024-2025 | 3204/AD | 01/08/2024 | 30 | UCON | 5.36 | 0 | 0
523 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000672/2024-2025 | 984/KSD | 27/05/2024 | 92 | NAMITA PRADHAN | 1.2 | 0 | 0
524 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000673/2024-2025 | 1252/KSD | 28/08/2024 | 91 | NAMITA PRADHAN | 1.2 | 0 | 0
525 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Dhablat (Zone- I & II)) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part - A) (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000761/2024-2025 | 4444/AD | 06/11/2024 | 60 | SUDIP PRADHAN | 25.81 | 0 | 100
526 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dhablat (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000972/2023-2024 | 321/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
527 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DHABLAT (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001058/2022-2023 | 4649/AD | 06/09/2022 | 45 | VOYAGER | 6.21 | 0 | 100
528 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001281/2022-2023 | 9594/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 90
529 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2022 to 30.11.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001754/2022-2023 | 561/KSD | 02/12/2022 | 363 | NAMITA PRADHAN | 4.79 | 0 | 95
530 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001861/2022-2023 | 12414/AD | 09/03/2023 | 300 | UCON (II) | 221.19 | 0 | 72
531 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001985/2023-2024 | 504/AD | 25/01/2024 | 45 | SUDIP PRADHAN | 33.16 | 0 | 80
532 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001986/2023-2024 | 505/AD | 25/01/2024 | 30 | M/S. MOYNA ENTERPRISE | 11.53 | 0 | 100
533 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall, earth filling & approach road at 1st Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002118/2024-2025 | 1967/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.66 | 0 | 100
534 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall, earth filling, approach road at 2nd Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002119/2024-2025 | 1968/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.55 | 0 | 0
535 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhablat Zone - I & II, Kamalpur Rudranagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002164/2023-2024 | 951/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
536 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC after completion of FHTC work for 01 Year for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002452/2023-2024 | 1310/AD | 04/03/2024 | 45 | SUDIP PRADHAN | 0 | 0 | 0
537 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002468/2023-2024 | 1361/AD | 06/03/2024 | 60 | UCON | 0 | 0 | 0
538 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002530/2023-2024 | 712/KSD | 30/11/2023 | 91 | NAMITA PRADHAN | 1.2 | 0 | 0
539 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003037/2023-2024 | 411/KSD | 27/02/2024 | 92 | NAMITA PRADHAN | 1.2 | 0 | 0
540 | Alipore Division | Kakdwip Sub-Division | Continuation order for Carriage of Chlorine from Ganeshpur store to different pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003234/2023-2024 | 380/KSD | 21/02/2024 | 365 | SUDIP PRADHAN | 2.39 | 0 | 0
541 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000335/2023-2024 | 3150/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
542 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000512/2023-2024 | 4830/AD | 20/12/2023 | 0 | Resource Division | 23.39 | 0 | 0
543 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000532/2023-2024 | 16/AD | 02/01/2024 | 0 | Resource Division | 3.97 | 0 | 0
544 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000687/2023-2024 | 457/AD | 24/01/2024 | 0 | Resource Division | 5.88 | 0 | 0
545 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000971/2023-2024 | 1764/AD | 27/03/2024 | 0 | Resource Division | 1.41 | 0 | 0
546 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Dhablat Augmentation W/S Scheme PH-2 Application No:- 1007672480 Reference ID:- 106558453 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/00379/2024-2025 | BP-2024-25-89 | 05/06/2024 | 0 | WBSEDCL | 8.35 | 0 | 0
547 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/05694/2023-2024 | BP-2023-24-644 | 29/03/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
548 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Dhablahat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000794/2022-2023 | 281/SMD | 01/02/2023 | 879 | GLACIER ENGINEERING CO. | 19.61 | 0 | 100
549 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I, PH-2 of Dhablat Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002378/2024-2025 | 1346/AE-II/SMD | 14/11/2024 | 15 | GLACIER ENGINEERING CO. | 0.84 | 0 | 100
550 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indraprastha W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000130/2024-2025 | 2406/AD | 07/06/2024 | 45 | M/S ASCON | 27.58 | 0 | 0
551 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc at Indraprastha PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13804) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000442/2024-2025 | 511/AD | 10/02/2025 | 60 | MAA LAXMI ENTERPRISE | 75.28 | 0 | 0
552 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000940/2023-2024 | 280(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
553 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRAPRASTHA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000980/2022-2023 | 3666/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3 | 0 | 100
554 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indraprastha W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000982/2023-2024 | 3001/AD | 26/09/2023 | 30 | SUJOY SADHUKHAN | 9.55 | 0 | 0
555 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Indraprastha Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 841] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001506/2022-2023 | 11024/AD | 08/02/2023 | 1057 | MAA LAXMI ENTERPRISE | 228.39 | 0 | 40
556 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
557 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000093/2023-2024 | 539/AD | 12/05/2023 | 0 | Resource Division | 4.62 | 0 | 0
558 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000511/2023-2024 | 4942/AD | 22/12/2023 | 0 | Resource Division | 23.91 | 0 | 0
559 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000747/2023-2024 | 582/AD | 29/01/2024 | 0 | Resource Division | 0.83 | 0 | 0
560 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Indraprastha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000363/2022-2023 | 3767/SMD | 29/12/2022 | 90 | UNIVERSAL ENTERPRISES | 18.6 | 0 | 0
561 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Rajrajeshwarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13868) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000076/2025-2026 | 2307/AD | 16/05/2025 | 45 | B.K. ENTERPRISE. | 40.78 | 0 | 0
562 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000123/2024-2025 | 2401/AD | 07/06/2024 | 30 | SHIBSANKAR KAMILA | 9.6 | 0 | 0
563 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary etc at Rajrajeswarpur PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13868) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000236/2024-2025 | 2611/AD | 19/06/2024 | 579 | M/S ASCON | 15.81 | 0 | 80
564 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Raj Rajeshwarpur PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13868) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000396/2024-2025 | 4287/AD | 29/10/2024 | 60 | M/S B.M. CONSTRUCTION | 97.23 | 0 | 0
565 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rajrajeshwarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000932/2023-2024 | 276(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
566 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAJRAJESHWARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000988/2022-2023 | 4149/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.58 | 0 | 100
567 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001744/2022-2023 | 11559/AD | 17/02/2023 | 90 | M/S ASCON | 99.44 | 0 | 90
568 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 838] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002067/2022-2023 | 13006/AD | 23/03/2023 | 800 | M/S B.M. CONSTRUCTION | 263.39 | 0 | 30
569 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
570 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002158/2023-2024 | 803/AD | 05/02/2024 | 60 | M/S ASCON | 26.34 | 0 | 0
571 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000111/2023-2024 | 647/AD | 17/05/2023 | 0 | Resource Division | 4.6 | 0 | 0
572 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000483/2023-2024 | 4755/AD | 19/12/2023 | 0 | Resource Division | 12.71 | 0 | 0
573 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000576/2023-2024 | 60/AD | 03/01/2024 | 0 | Resource Division | 0.8 | 0 | 0
574 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000753/2023-2024 | 588/AD | 29/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
575 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000957/2023-2024 | 1691/AD | 22/03/2024 | 0 | Resource Division | 13.68 | 0 | 0
576 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional / Alternation Work of Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 Zone-II for Augmentation Paschim Surendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000001/2024-2025 | 1440/SMD | 18/04/2024 | 90 | M/S. S.D.CONSTRUCTION | 17.3 | 0 | 0
577 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at P.H. 1&2, of Rajrajeshwarpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000361/2024-2025 | 2664/SMD | 29/08/2024 | 90 | T.S. CONSTRUCTION | 17.44 | 0 | 0
578 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rajrajeshwarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000386/2022-2023 | 3789/SMD | 29/12/2022 | 90 | T.S. CONSTRUCTION | 18.5 | 0 | 0
579 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rajnagar (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 520] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000308/2023-2024 | 1511/AD | 15/07/2023 | 300 | UCON | 381.33 | 0 | 20
580 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Rajnagar W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000537/2023-2024 | 355/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.73 | 0 | 100
581 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAJNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001044/2022-2023 | 3675/AD | 01/08/2022 | 45 | M/S R.DUTTA & CO. | 3.66 | 0 | 100
582 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Rajnagar (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001776/2022-2023 | 12058/AD | 27/02/2023 | 30 | M/S MAITY CONSTRUCTION | 19.27 | 0 | 98
583 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Rajnagar W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002054/2023-2024 | 515/AD | 25/01/2024 | 349 | ROYAL CONSTRUCTION | 9.73 | 0 | 100
584 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
585 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000288/2023-2024 | 3084/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
586 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000493/2023-2024 | 4792/AD | 19/12/2023 | 0 | Resource Division | 30.64 | 0 | 0
587 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000545/2023-2024 | 29/AD | 02/01/2024 | 0 | Resource Division | 3.09 | 0 | 0
588 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000987/2023-2024 | 1780/AD | 27/03/2024 | 0 | Resource Division | 7.29 | 0 | 0
589 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Rajnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000423/2022-2023 | 3819/SMD | 29/12/2022 | 90 | DIPA CHHETRI | 10.75 | 0 | 0
590 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Bagi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000514/2022-2023 | 371/SMD | 13/02/2023 | 1053 | SWAPAN ENTERPRISE | 33.33 | 0 | 10
591 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional laying of pipeline for distribution system due to revision of Laying Distribution System drawing for providing Functional Household Tap Connection (FHTC) for Proposed BAGI PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24 Pgs W/S Sub-Division-I, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000016/2025-2026 | 968/SWD-I | 09/04/2025 | 45 | RAJLAXMI CONSTRUCTION | 43.03 | 0 | 0
592 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAGI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4890) [TSM/017322]. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000159/2023-2024 | 841/SWD-I | 05/06/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 749.97 | 0 | 0
593 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of BAGI PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017322] (2nd call) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000237/2023-2024 | 1420/SWD-I | 17/07/2023 | 60 | MS KRISHNA MONDAL | 18.75 | 0 | 0
594 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BAGI PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000346/2024-2025 | 3345/SWD-I | 25/07/2024 | 60 | M/S B.N. ENTERPRISES | 201.23 | 0 | 0
595 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BAGI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017322] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000580/2022-2023 | 3098/SWD-I | 23/02/2023 | 593 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.87 | 0 | 98
596 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd and 3rd tubewell site for BAGI Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000688/2024-2025 | 4483/SWD-I | 30/10/2024 | 109 | MONDAL TUBEWELL | 31.71 | 0 | 98
597 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Bagi Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000959/2022-2023 | 1138/SWD-I | 25/08/2022 | 30 | GEO SOLUTION | 3.16 | 0 | 100
598 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000088/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 70.75 | 0 | 0
599 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-VI of Mathurapur - I Block in connection with remodeling of existing Batiswar water supply scheme under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000007/2022-2023 | 124/AD | 07/04/2022 | 30 | DEBARATI ENTERPRISE | 94.97 | 0 | 95
600 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
601 | Alipore Division | Raidighi Sub-Division | Miscellaneous work for smooth distribution system of piped water supply at Zone-VI of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000439/2022-2023 | 4353/AD | 25/08/2022 | 60 | DEBARATI ENTERPRISE | 49.88 | 0 | 99
602 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- VI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000880/2024-2025 | 4663/AD | 20/11/2024 | 90 | KARMAKAR CONSTRUCTION | 12.94 | 0 | 0
603 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Botiswar piped water supply Scheme at Zone- VI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001010/2023-2024 | 300/RSD | 29/09/2023 | 60 | DEBARATI ENTERPRISE | 3.86 | 0 | 100
604 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-VI (Batiswar PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001146/2021-2022 | 5534/AD | 20/01/2022 | 365 | DEBARATI ENTERPRISE | 80.58 | 0 | 75
605 | Alipore Division | Raidighi Sub-Division | Laying distribution DI pipeline and allied works to improve functionality Botiswar piped water supply Scheme at Zone- VI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001908/2023-2024 | 436/RSD | 08/01/2024 | 60 | DEBARATI ENTERPRISE | 2.99 | 0 | 100
606 | Alipore Division | Raidighi Sub-Division | Providing 100% Functional Household Tap Connection (FHTC) including Parallel pipeline and other allied works of piped water supply at Zone - VI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface Water Based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001911/2023-2024 | 141/AD | 05/01/2024 | 30 | DEBARATI ENTERPRISE | 12.41 | 0 | 100
607 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-VI, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001961/2022-2023 | 12715/AD | 14/03/2023 | 30 | DEBARATI ENTERPRISE | 37.98 | 0 | 100
608 | Alipore Division | Raidighi Sub-Division | Providing left-out Functional Household Tap Connection (FHTC) at Zone - VI (Mouza: Borasi, Raghabpur, Sadial, Sovanagar) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002269/2023-2024 | 476/RSD | 15/02/2024 | 30 | DEBARATI ENTERPRISE | 3.59 | 0 | 99
609 | Alipore Division | Raidighi Sub-Division | Providing left-out Functional Household Tap Connection (FHTC) at Zone - VI (Mouza : Sarberia, Uttar Joykrishnapur, Narayanpur, Batiswar) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002270/2023-2024 | 477/RSD | 15/02/2024 | 30 | DEBARATI ENTERPRISE | 2.08 | 0 | 90
610 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000639/2023-2024 | 243/AD | 15/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
611 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 592 | TIYASHA ENTERPRISE | 96.43 | 0 | 35
612 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001689/2022-2023 | 11620/AD | 18/02/2023 | 45 | B. ENTERPRISE | 7.07 | 0 | 98
613 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Homrapolta W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001696/2022-2023 | 11627/AD | 18/02/2023 | 30 | TRIMURTI ENTERPRISE | 19.56 | 0 | 0
614 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Homrapolta Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002005/2022-2023 | 12819/AD | 16/03/2023 | 60 | TIYASHA ENTERPRISE | 58.34 | 0 | 51
615 | Alipore Division | Canning Sub-division | Relaying of damaged DI pipe at Homrapolta W/S Scheme due widening of PMGSY Road by Zilla Parishad under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002161/2020-2021 | 1593/CSD | 23/02/2021 | 30 | ARANYA ENTERPRISE | 3.54 | 0 | 99
616 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 2 of Homrapolta W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002453/2023-2024 | 1581/CSD | 22/02/2024 | 30 | SUKANTA HALDER | 3.27 | 0 | 95
617 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000017/2023-2024 | 222/AD | 21/04/2023 | 0 | Resource Division | 39.74 | 0 | 0
618 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000256/2023-2024 | 3048/AD | 28/09/2023 | 0 | Resource Division | 0.92 | 0 | 0
619 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Homrapolta under Canning -II block (REF ID : 106665552) (APP ID: 1007924615) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01004/2024-2025 | BP-2024-25-205 | 30/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
620 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Homrapolta water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000287/2023-2024 | 1147/SMD | 24/04/2023 | 712 | A.S.ENTERPRISE | 10.9 | 0 | 95
621 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Sarberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000044/2023-2024 | 1040/SMD | 17/04/2023 | 90 | A.K.SIKDAR | 22.37 | 0 | 0
622 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sarberia- Dhamua Road,from 0+00 to 6+520 Km Restoration of Damage occurred due to damage caused/ to be caused by laying of pipe line by PHE Dte under Sarberia PWSS, Jaldhapa PWSS, Multi PWSS under South 24 Parganas Highway Division in the District of South 24 Parganas. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00635/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 19.6 | 0 | 0
623 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SARBERIA Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district [No. of FHTC = 2209] [TSM/017755] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000013/2023-2024 | 32/SWD-I | 05/04/2023 | 990 | MILAN GHOSH | 299.38 | 0 | 98
624 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, development of land, pipeline protection work and other allied works for Ground water based SARBERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14874) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000355/2024-2025 | 3455/SWD-I | 02/08/2024 | 45 | MILAN GHOSH | 85.25 | 0 | 0
625 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SARBERIA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000414/2021-2022 | 1967/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 0
626 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for SARBERIA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017755] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000583/2022-2023 | 3068/SWD-I | 21/02/2023 | 690 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 31.79 | 0 | 100
627 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000342/2023-2024 | 261/SWD-I | 10/01/2024 | 0 | Resource Division | 13.61 | 0 | 0
628 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | BILL/05029/2023-2024 | BP-2023-24-563 | 11/03/2024 | 0 | WBSEDCL | 0.58 | 0 | 0
629 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Shyampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000053/2023-2024 | 1049/SMD | 17/04/2023 | 90 | B.T.PROJECTS PVT.LTD. | 34.89 | 0 | 30
630 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Shyampur W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/001293/2024-2025 | 950/SMSD | 02/07/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.74 | 0 | 0
631 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SHYAMPUR Part-I Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 3180] [TSM/018169] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 1609/SWD-I | 01/08/2023 | 90 | UCON | 433.14 | 0 | 25
632 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for SHYAMPUR (PART-I) PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000568/2022-2023 | 3064/SWD-I | 21/02/2023 | 30 | G M ENTERPRISE (19AQFPM3953P1Z3) | 47.4 | 0 | 100
633 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-I) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 1427/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.74 | 0 | 100
634 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000134/2022-2023 | 3393/SWD-I | 10/03/2023 | 0 | Resource Division | 19.59 | 0 | 0
635 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000198/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 57.67 | 0 | 0
636 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00514/2023-2024 | BP-2023-24-77 | 13/06/2023 | 0 | WBSEDCL | 2.85 | 0 | 0
637 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01500/2023-2024 | BP-2023-24-176 | 02/08/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
638 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, delivery stand by submersible pump for Sangur W/S Scheme under SMD PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 1115/SMSD | 06/08/2024 | 15 | BANERJEE ENTERPRISE | 0.86 | 0 | 100
639 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Sangur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000339/2022-2023 | 3743/SMD | 29/12/2022 | 520 | EASTERN INDIA SALES & SERVICE | 23.37 | 0 | 100
640 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-1&2 of Sangur W/S Scheme under South 24-Pgs Mechanical Division PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001650/2023-2024 | .1469/SMSD | 01/12/2023 | 15 | S.B.ENTERPRISE | 0.78 | 0 | 100
641 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no- 2 of Sangur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002656/2023-2024 | 1426/SMSD | 21/11/2023 | 15 | EASTERN INDIA SALES & SERVICE | 0.29 | 0 | 100
642 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Sangur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002662/2023-2024 | 1427/SMSD | 21/11/2023 | 15 | EASTERN INDIA SALES & SERVICE | 0.9 | 0 | 100
643 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 of Sangur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002663/2023-2024 | 1180/SMSD | 05/09/2023 | 15 | EASTERN INDIA SALES & SERVICE | 0.44 | 0 | 100
644 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at pump house no.1 of Sangur W/S Scheme under SMD, PHE Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002972/2023-2024 | ..1172/SMSD | 04/09/2023 | 15 | EASTERN INDIA SALES & SERVICE | 0.9 | 0 | 100
645 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.20] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00479/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 6.93 | 0 | 0
646 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.21] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00480/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 5.39 | 0 | 0
647 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2506] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 30/SWD-I | 05/04/2023 | 1026 | EFFLUENT AND WATER TREATMENT ENGINEERS PRIVATE LIMITED | 633.23 | 0 | 50
648 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Rejuvenation / upgradation of Existing R.C.C. Reservoir of capacity 550 CUM and staging height 20 mtr at 2nd Tubewell site of "SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14545) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 964/SWD-I | 09/04/2025 | 45 | M/S. JAYDEEP DASGUPTA | 10.94 | 0 | 0
649 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & other allied works of " SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/14545). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000234/2024-2025 | 2654/SWD-I | 07/06/2024 | 497 | SAHI MASUM | 42.97 | 0 | 50
650 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR SANGUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/017137) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 3052/SWD-I | 20/02/2023 | 30 | BARI ENTERPRISE | 30.02 | 0 | 100
651 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SANGUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/017137] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 3653/SWD-I | 28/03/2023 | 15 | BARI ENTERPRISE | 3.13 | 0 | 100
652 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Chlorine room, Office room, Land Development, Construction of Pathway & Drain of Sangur PWSS within Sonarpur Block "Sangur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pargnas District under Jal Jeevan Mission. (SM/14545) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001103/2024-2025 | 62/SWD-I | 06/01/2025 | 45 | MIDHAH ENTERPRISE | 22.12 | 0 | 0
653 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000031/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 34.19 | 0 | 0
654 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000255/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 15.44 | 0 | 0
655 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 750 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of piped water supply scheme in Zone-I at Bainchberia Mouza of Mograhat-I Block for augmentation of Mega surface water based water supply scheme and providing Functional Household Tap connection (FHTC) in Zone-I at Bainchberia of Mograhat-I Block within Mega surface water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (No.of FHTC - 5799 Nos.) | AE SWSD-II | JE3 | ORD/000114/2023-2024 | 526/SWD-I | 11/05/2023 | 782 | RADIANT | 911.48 | 0 | 20
656 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-I (Bainchberia) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II | JE3 | ORD/000343/2021-2022 | 2692/SWD-I | 25/03/2022 | 90 | NIKHIL SAMADDAR | 16.45 | 0 | 100
657 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-I (Bainchberia) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14726] | AE SWSD-II | JE3 | ORD/000503/2024-2025 | 3719/SWD-I | 23/08/2024 | 312 | RADIANT | 414.1 | 0 | 15
658 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Carriage of DI (K9) pipes of various diameter from different PHE stores to work site at Mograhat-I block for laying of Secondary Grid pipeline for Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% household in Zone-I at Bainchberia under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Parganas Water Supply Division-I, PHE, Dte. (SM/ 14726) | AE SWSD-II | JE3 | ORD/000554/2023-2024 | 2520/SWD-I | 09/10/2023 | 7 | TIRUPATI ENTERPRISES | 7.85 | 0 | 0
659 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of thrust block, fabricating covers for valve chambers and supply of vent cowl, repairing leakage and construction of valve chamber for G.L.R. - IV at Usthi, Magrahat-I of Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 pgns water supply division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/000763/2024-2025 | 4684/SWD-I | 18/11/2024 | 45 | PROJECT AND MAINTENANCE | 14.36 | 0 | 95
660 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Protection work of Boundary wall along canal inside Magrahat-I GLR under Augmentation of existing laying distribution system including old OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under Magrahat-I block within Mega Surface water based water supply scheme of Falta-Mathurapur dist- South 24-Pgns, Under south 24-Pgns, water supply Division-I, P.H.E. Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/000778/2023-2024 | 806/SWD-I | 16/02/2024 | 15 | PROJECT AND MAINTENANCE | 11.16 | 0 | 95
661 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sludge cleaning including repeated washing with fresh water with allied work disinfection of Magrahat-I (1400 cum) GLRs under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under MAGRAHAT-I block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/000779/2023-2024 | 807/SWD-I | 16/02/2024 | 15 | NIRMAL UDYOG | 3.84 | 0 | 100
662 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for Magrahat-I Block under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under Magrahat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/001074/2024-2025 | 5342/SWD-I | 30/12/2024 | 90 | TIRUPATI ENTERPRISES | 25.7 | 0 | 1
663 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000061/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 3.53 | 0 | 0
664 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution & FHTC for 1 year after completion of FHTC works for Narayanganj Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001424/2023-2024 | 4603/AD | 14/12/2023 | 90 | M/S P. B. CONSTRUCTION | 58.38 | 0 | 50
665 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Narayanganj W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001720/2022-2023 | 11746/AD | 21/02/2023 | 30 | ASMINA MOLLA | 19.26 | 0 | 100
666 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Narayanganj PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001805/2022-2023 | 3696/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 0.67 | 0 | 95
667 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Narayanganj W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002051/2023-2024 | 512/AD | 25/01/2024 | 30 | PALASH HALDAR | 9.71 | 0 | 98
668 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
669 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000485/2023-2024 | 4787/AD | 19/12/2023 | 0 | Resource Division | 1.18 | 0 | 0
670 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000553/2023-2024 | 41/AD | 03/01/2024 | 0 | Resource Division | 2.48 | 0 | 0
671 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000984/2023-2024 | 1777/AD | 27/03/2024 | 0 | Resource Division | 5.23 | 0 | 0
672 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Narayanganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000055/2023-2024 | 1051/SMD | 17/04/2023 | 90 | BHUNIA BUILDERS | 8.92 | 0 | 0
673 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000164/2023-2024 | 608/AD | 15/05/2023 | 30 | KALACHAND DAS | 19.29 | 0 | 0
674 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15050) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000645/2024-2025 | 4141/AD | 05/10/2024 | 117 | S. CHAKRABORTY AND CO. | 20.41 | 0 | 100
675 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution and FHTC for 1 year after completion of FHTC works for Ramchandrapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001426/2023-2024 | 4605/AD | 14/12/2023 | 654 | R.S.CONSTRUCTION CO. | 60.7 | 0 | 50
676 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
677 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000127/2023-2024 | 663/AD | 17/05/2023 | 0 | Resource Division | 1.21 | 0 | 0
678 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000458/2023-2024 | 4721/AD | 18/12/2023 | 0 | Resource Division | 1.42 | 0 | 0
679 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000817/2023-2024 | 662/AD | 30/01/2024 | 0 | Resource Division | 1.24 | 0 | 0
680 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Ramchandrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000050/2023-2024 | 1046/SMD | 17/04/2023 | 90 | PURUSHOTTAM ENTERPRISE | 8.91 | 0 | 0
681 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II Zone-VI including Operation and Maintenance of scheme for 01 (one) year under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas Block Diamond Harbour-II, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000581/2021-2022 | 3646/AD | 22/11/2021 | 365 | ADITYA HAZRA | 83.79 | 0 | 100
682 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000031/2021-2022 | 4349/AD | 04/03/2022 | 0 | Resource Division | 19.81 | 0 | 0
683 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000099/2022-2023 | 7496/AD | 26/11/2022 | 0 | Resource Division | 2.28 | 0 | 0
684 | Alipore Division | Raidighi Sub-Division | Extension of distribution system (Node No. 85-AB) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000037/2022-2023 | 06/RSD | 04/04/2022 | 60 | R.G. ENTERPRISE (I) | 4.72 | 0 | 100
685 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-H) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000042/2022-2023 | 34/RSD | 19/04/2022 | 60 | B.S. CONSTRUCTION | 4.76 | 0 | 100
686 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
687 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART -A) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000114/2023-2024 | 483/AD | 10/05/2023 | 30 | SUTAPA ENTERPRISE | 16.05 | 0 | 98
688 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Ghatbakultala W/S Scheme (Zone-XIII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000434/2023-2024 | 1922/AD | 01/08/2023 | 30 | ALISHA ENTERPRISE | 19.83 | 0 | 100
689 | Alipore Division | Raidighi Sub-Division | Repairing of pump house no.2, including boundary wall and approach road and plinth protection at Ghatbakultala W/S Scheme, modified as Zone- XIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000608/2024-2025 | 748/RSD | 03/10/2024 | 60 | M/S. GANGA ENTERPRISE | 4.74 | 0 | 95
690 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001040/2024-2025 | 4958/AD | 04/12/2024 | 60 | SUKUMAR HALDAR | 31.88 | 0 | 0
691 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 13-12-10-8) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001547/2021-2022 | 713/RSD | 02/03/2022 | 60 | SHEKHAR CHAKRABORTY | 4.79 | 0 | 100
692 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001967/2022-2023 | 12721/AD | 14/03/2023 | 30 | THE TOWER CONSTRUCTION | 39.69 | 0 | 60
693 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Goalar Mal (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002365/2020-2021 | 737/RSD | 12/02/2021 | 60 | DIBYENDU BHATTACHARYA | 4.82 | 0 | 100
694 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000602/2023-2024 | 230/AD | 11/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
695 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05119/2023-2024 | BP-2023-24-577 | 12/03/2024 | 0 | WBSEDCL | 8.7 | 0 | 0
696 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Bagdaha W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15782) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000387/2024-2025 | 486/SMSD | 23/04/2024 | 15 | KARUNAMOY ENGINEERING | 0.92 | 0 | 100
697 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 1 of Bagdaha W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15782) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000388/2024-2025 | 485/SMSD | 23/04/2024 | 15 | KARUNAMOY ENGINEERING | 0.92 | 0 | 100
698 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Bagdaha W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15784) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000389/2024-2025 | 484/SMSD | 23/04/2024 | 15 | KARUNAMOY ENGINEERING | 0.58 | 0 | 100
699 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Installation of LED board at PH No-1 & 2 of Bagdaha water supply scheme under South 24-Pgs Mechanical Division, PHE Dte.[Block-Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000390/2024-2025 | 853/SMSD | 14/06/2024 | 15 | ABHISEK ENGINEERING CONCERN | 0.78 | 0 | 100
700 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Bagdaha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001127/2023-2024 | 4269/SMD | 07/11/2023 | 329 | KARUNAMOY ENGINEERING | 25.81 | 0 | 100
701 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying Distribution System, Rising Main, Functional Household Tap Connection for BAGDAHA PWSS to accommodate FHTC in Baruipur Block under Surface water based water supply scheme in the arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. (TSM/018476) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 469/SWD-I | 04/05/2023 | 90 | M/S ASHIRBAD (INDIA) | 148.94 | 0 | 90
702 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, development of land, pipeline protection work and other allied works for Ground water based BAGDAHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/15782) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000335/2024-2025 | 3273/SWD-I | 22/07/2024 | 495 | KAMALA ENTERPRISE (DIAMOND HARBOUR) | 59.7 | 0 | 100
703 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BAGDAHA PWSS to accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018476) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000708/2022-2023 | 3522/SWD-I | 17/03/2023 | 30 | MURSHID JAHAN | 31.76 | 0 | 100
704 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Bagdah Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000927/2022-2023 | 1175/SWD-I | 31/08/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
705 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000179/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 29.87 | 0 | 0
706 | Alipore Division | Baruipur Sub-Division | Jagita Sarda House to Khalpar Bypass Via Roybahadur Via Projit Mondal To Nikfiil Ranjan Roy House Via Khardhya Math Via Bapi Naskar House | AE BSD,Assistant Engineer | Junior Engineer | BILL/01703/2024-2025 | BP-2024-25-788 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.16 | 0 | 0
707 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04652/2023-2024 | BP-2023-24-489 | 12/02/2024 | 0 | WBSEDCL | 2.31 | 0 | 0
708 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Dhopa Gachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 1065/SMD | 18/04/2023 | 90 | B.T.PROJECTS PVT.LTD. | 21.46 | 0 | 0
709 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DHOPA GACHI Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 917] [TSM/018424] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000084/2023-2024 | 418/SWD-I | 02/05/2023 | 1048 | MONDAL CONSTRUCTION | 168.94 | 0 | 95
710 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of OHR/ 2nd TW site, platform for providing FHTC, restoration of road and other allied works for Augmentation of Ground Water based DHOPAGACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. (SM/15786) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 3551/SWD-I | 09/08/2024 | 225 | MONDAL CONSTRUCTION (BARUIPUR) | 46.21 | 0 | 30
711 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method at Head work site for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/15786] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000385/2024-2025 | 3588/SWD-I | 13/08/2024 | 15 | PADMA ENGINEERING CO. | 15.88 | 0 | 0
712 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018424] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000643/2022-2023 | 3316/SWD-I | 06/03/2023 | 30 | M/S M.S. ENTERPRISE | 31.77 | 0 | 0
713 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DHOPAGACHI Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15786] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000878/2024-2025 | 4976/SWD-I | 05/12/2024 | 30 | M/S. SHYAM CONSTRUCTION | 15.53 | 0 | 0
714 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dhopa Gachhi Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000941/2022-2023 | 1258/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.48 | 0 | 100
715 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000122/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 29.34 | 0 | 0
716 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of different dia. M.S. distribution line for crossing of 10 nos. culvert with allied works at Lakshmipur village road, at Netra stations to Panchagram road and Netra stations to Usthi road under Augmentation scheme of Diamond Harbour-I Zone-II and Zone-VIII within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000097/2025-2026 | 2526/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 93.95 | 0 | 100
717 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VIII Lakshmipur at Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4527] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001015/2023-2024 | 1316/AD | 05/03/2024 | 600 | VISHAL CONSTRUCTION CO. | 858.06 | 0 | 45
718 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001025/2022-2023 | 304/DHSD | 23/09/2022 | 30 | GEO SOLUTION | 2.96 | 0 | 0
719 | Alipore Division | Diamond Harbour Sub-Division | Restoration of laying of distribution system damaged due to construction of PMGSY road at Lakshmipur PWSS in Zone-VIII of Diamond Harbour- I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001616/2022-2023 | 477/DHSD | 03/01/2023 | 21 | M/S B ENTERPRISE | 3.53 | 0 | 100
720 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 600 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-VIII at Lakshmipur of Diamond Harbour -I Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002406/2023-2024 | 1154/AD | 27/02/2024 | 90 | VISHAL CONSTRUCTION CO. | 49.71 | 0 | 80
721 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000129/2022-2023 | 26/AD | 05/04/2023 | 0 | Resource Division | 14.72 | 0 | 0
722 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000237/2023-2024 | 2198/AD | 10/08/2023 | 0 | Resource Division | 21.06 | 0 | 0
723 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000344/2023-2024 | 3208/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
724 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000608/2023-2024 | 270/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
725 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000888/2023-2024 | 742/AD | 03/02/2024 | 0 | Resource Division | 3.25 | 0 | 0
726 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000917/2023-2024 | 1259/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
727 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000006/2024-2025 | 48/DHSD | 30/04/2024 | 184 | GOPAL KUMAR JHA | 2.4 | 0 | 0
728 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000007/2024-2025 | 49/DHSD | 30/04/2024 | 184 | SUMAN HALDER | 2.4 | 0 | 0
729 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 89.87 | 0 | 100
730 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2025 to 31/10/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000209/2025-2026 | 74/DHSD | 29/04/2025 | 184 | SUMAN HALDER | 2.4 | 0 | 0
731 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Kuleswar under Zone- X of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000506/2023-2024 | 1803/AD | 26/07/2023 | 30 | A.S.A.CONSTRUCTION AND CONSULTANT | 27.6 | 0 | 0
732 | Alipore Division | Diamond Harbour Sub-Division | Investigation of soil for the proposed 2(two) nos. R.C.C. Over Head Reservoir i.e. at Zone-X (Kuleswar OHR Size-600) and Zone-XI (Mongrajpur OHR Size-250) within Diamond Harbour-I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000509/2022-2023 | 5530/AD. | 29/09/2022 | 840 | NIRMAN (NEW) | 1.56 | 0 | 50
733 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- X at Kuleswar of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4980]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000674/2023-2024 | 2701/AD | 07/09/2023 | 900 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 983.37 | 0 | 60
734 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-X at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000871/2024-2025 | 4655/AD | 20/11/2024 | 240 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 81.66 | 0 | 73
735 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2024 to 30/11/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000915/2024-2025 | 642/DHSD | 30/10/2024 | 30 | GOPAL KUMAR JHA | 0.4 | 0 | 0
736 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/11/2024 to 30/04/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001039/2024-2025 | 641/DHSD | 30/10/2024 | 181 | SUMAN HALDER | 2.4 | 0 | 0
737 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2024 to 31/03/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001042/2024-2025 | 545/DHSD | 30/09/2024 | 182 | M.P. ENTERPRISE (II) | 2.4 | 0 | 0
738 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-X of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001053/2022-2023 | 306/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.96 | 0 | 0
739 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/12/2024 to 28/02/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001563/2024-2025 | 700/DHSD | 29/11/2024 | 90 | AVIJIT SIL | 1.2 | 0 | 0
740 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-X (Kuleswar OHR Size-600) within Diamond Harbour-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002090/2022-2023 | 324/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 0
741 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000127/2022-2023 | 28/AD | 05/04/2023 | 0 | Resource Division | 14.72 | 0 | 0
742 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000236/2023-2024 | 2197/AD | 10/08/2023 | 0 | Resource Division | 29.99 | 0 | 0
743 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000348/2023-2024 | 3212/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
744 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000894/2023-2024 | 748/AD | 03/02/2024 | 0 | Resource Division | 30.68 | 0 | 0
745 | Alipore Division | Canning Sub-division | Construction of 300 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1161] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000023/2023-2024 | 150/AD | 18/04/2023 | 300 | TANMAY ROY CHOWDHURY | 412.42 | 0 | 30
746 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000098/2023-2024 | 454/AD | 08/05/2023 | 15 | MONDAL ENTERPRISE - 2 (SDK) | 16.47 | 0 | 0
747 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No - I for Gorund Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone - II) , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000386/2025-2026 | 3371/AD | 16/07/2025 | 30 | GANGA TUBEWELL AND HARDWARE | 11.16 | 0 | 0
748 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000387/2025-2026 | 3372/AD | 16/07/2025 | 30 | SOURAV DEBNATH | 10.36 | 0 | 0
749 | Alipore Division | Canning Sub-division | River crossing on the river bed and laying DI pipeline of Augmentation of Sadhupur W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001033/2024-2025 | 4943/AD | 03/12/2024 | 60 | SUBHO CONSTRUCTION | 78.35 | 0 | 0
750 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001890/2022-2023 | 11551/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 6.86 | 0 | 100
751 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001957/2022-2023 | 12693/AD | 14/03/2023 | 45 | BAPAN HALDAR | 8.57 | 0 | 0
752 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001984/2022-2023 | 12645/AD | 13/03/2023 | 45 | RAJ & ENTERPRISE | 8.92 | 0 | 0
753 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000723/2023-2024 | 545/AD | 25/01/2024 | 0 | Resource Division | 111.13 | 0 | 0
754 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/04815/2023-2024 | BP-2023-24-529 | 22/02/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
755 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/05698/2023-2024 | BP-2023-24-607 | 28/03/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
756 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Sadhupur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000274/2023-2024 | 1133/SMD | 24/04/2023 | 90 | DEBJYOTI BASU | 19.55 | 0 | 0
757 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
758 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 903] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000026/2023-2024 | 149/AD | 17/04/2023 | 60 | M/S SUMAN SHIL | 227.54 | 0 | 62
759 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000149/2023-2024 | 694/AD | 18/05/2023 | 15 | BHOLANATH CONSTRUCTION | 13.87 | 0 | 0
760 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Sonakhali (Zone-I) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000290/2025-2026 | 693/CSD | 26/05/2025 | 30 | STARK ENTERPRISE | 2.43 | 0 | 0
761 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000312/2024-2025 | 2693/AD | 24/06/2024 | 45 | SAHANA ENTERPRISE | 7.01 | 0 | 0
762 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Sonakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000885/2024-2025 | 4714/AD | 21/11/2024 | 30 | RAJIB CONSTRUCTION | 19.98 | 0 | 0
763 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001851/2022-2023 | 11817/AD | 23/02/2023 | 45 | TECH VISION | 3.47 | 0 | 0
764 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001920/2022-2023 | 12464/AD | 10/03/2023 | 30 | SANDIP SARKAR | 19.56 | 0 | 0
765 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001985/2022-2023 | 12646/AD | 13/03/2023 | 45 | RAJ & ENTERPRISE | 7.1 | 0 | 0
766 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
767 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000035/2023-2024 | 240/AD | 24/04/2023 | 0 | Resource Division | 24.04 | 0 | 0
768 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000392/2023-2024 | 333/AD | 19/01/2024 | 0 | Resource Division | 5.56 | 0 | 0
769 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04680/2023-2024 | BP-2023-24-503 | 12/02/2024 | 0 | WBSEDCL | 14.59 | 0 | 0
770 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Sonakhali Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000289/2023-2024 | 2126/SMD | 30/05/2023 | 90 | INDIA ENTERPRISE | 9.39 | 0 | 0
771 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the DHURI, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000061/2023-2024 | 311/AD | 26/04/2023 | 810 | SAMSUL ENTERPRISE | 451.63 | 0 | 80
772 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000774/2024-2025 | 4476/AD | 11/11/2024 | 45 | M/S P. B. CONSTRUCTION | 50.82 | 0 | 0
773 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000775/2024-2025 | 4477/AD | 11/11/2024 | 30 | M/S ASHA ENGINEERING | 13.14 | 0 | 0
774 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001818/2022-2023 | 12158/AD | 01/03/2023 | 45 | HI TECH ENTERPRISE | 7.35 | 0 | 0
775 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001819/2022-2023 | 12159/AD | 01/03/2023 | 45 | HI TECH ENTERPRISE | 7.09 | 0 | 100
776 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Dhuri Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001917/2022-2023 | 11776/AD | 21/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 0 | 0
777 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
778 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000074/2023-2024 | 539/AD | 25/01/2024 | 0 | Resource Division | 49.66 | 0 | 0
779 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/03416/2023-2024 | BP-2023-24-371 | 13/11/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
780 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, for Augmentation of Dhuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000495/2022-2023 | 297/SMD | 03/02/2023 | 90 | WEST BENGAL ENGINEERING CO. | 22.21 | 0 | 40
781 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-3 & 4 of of Dhuri W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15834) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002680/2023-2024 | 335/SMSD | 14/03/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.58 | 0 | 0
782 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 4 of Dhuri W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15834) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002682/2023-2024 | 337/SMSD | 14/03/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.89 | 0 | 0
783 | South 24 Pgs W/S Division I | Baruipur Sub-Division | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas | AE BSD |  | BILL/00637/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
784 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional laying of pipeline of secondary grid from Sikirhat to Ghatarnia and allied works for Nolgora of Joynagar-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24 pgns. District under South 24 pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD |  | ORD/000006/2025-2026 | 909/SWD-I | 02/04/2025 | 60 | BISWAS CONSTRUCTION | 47.37 | 0 | 70
785 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Gap Negotiation for Secondary grid of JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD |  | ORD/000015/2025-2026 | 967/SWD-I | 09/04/2025 | 30 | BISWAS CONSTRUCTION | 8.68 | 0 | 80
786 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-III at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/16185) | AE BSD |  | ORD/000277/2024-2025 | 2648/SWD-I | 07/06/2024 | 360 | R.S. CONSTRUCTION CO. | 55.65 | 0 | 40
787 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II block, under Baruipur Sub-Division, for "Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-III at Joynagar-II block within Mega surface water based W/S scheme of Falta-Mathurapur dist. South 24 pgns water supply division-I,PHE Dte.". Erstwhile "Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte." | AE BSD |  | ORD/000339/2021-2022 | 2338/SWD-I | 22/02/2022 | 120 | AJIT PRAMANICK | 416.96 | 0 | 85
788 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-A (Beladurganagar) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000409/2021-2022 | 2337/SWD-I | 22/02/2022 | 120 | MS LOKENATH CONSTRUCTION PROP SILPI DAS | 322.66 | 0 | 0
789 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000066/2022-2023 | 2981/SWD-I | 20/02/2023 | 0 | Resource Division | 326.04 | 0 | 0
790 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipe carrying structure with laying of 508 mm dia M.S. Secondary Rising Main for crossing of Canal at Simana Bazar, 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Path Pukur Bridge and 355.6 mm dia M.S. pipe for Secondary Rising Main for crossing of Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI, Zone-IV and Zone-II respectively within JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16191, 18655 & 18222] | AE BSD |  | ORD/000285/2024-2025 | 3041/SWD-I | 02/07/2024 | 45 | SRIJON ENTERPRISE | 69.41 | 0 | 100
791 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VI (Radha Ballavpur) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000359/2021-2022 | 2599/SWD-I | 15/03/2022 | 1080 | SUPRITI ENTERPRISE | 740.59 | 0 | 88
792 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 900 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (RADHABALLAVPUR) at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur District South 24 Parganas under South 24 parganas water Supply Division-I of PHEDte." [TSM : 014964] | AE BSD |  | ORD/000535/2023-2024 | 2364/SWD-I | 26/09/2023 | 900 | ATCO ENTERPRISE | 364 | 0 | 30
793 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Pipeline at different areas & others ancillary works including Land development of 900 Cu.M. Capacity R.C.C. Over Head Reservoir site for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (Radhaballavpur mouza) at Joynagar-II block within the Mega Surface Water Based Water Supply scheme, District Southy 24 Parganas" under Baruipur Sub Division of South 24 Parganas Water Supply Division-I of PHE Dte. [SM/ 16191] | AE BSD |  | ORD/000620/2023-2024 | 2804/SWD-I | 09/11/2023 | 45 | WALL FORT INDIA | 15.71 | 0 | 50
794 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of additional pipeline for parallel connections from main pipeline to provide FHTC in Zone-VI RADHABALLAVPUR Mouza under Augmentation of laying distribution system to extend the benefit of 100% households in Zone-VI at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur Dist.- South 24-Pgns. under South 24-Pgns W/S Division-I, PHE Dte. (SM/16191) | AE BSD |  | ORD/001157/2024-2025 | 375/SWD-I | 04/02/2025 | 135 | SUPRITI ENTERPRISE | 50.03 | 0 | 50
795 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000068/2022-2023 | 2983/SWD-I | 20/02/2023 | 0 | Resource Division | 30.76 | 0 | 0
796 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000205/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 24.9 | 0 | 0
797 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00123/2024-2025 | BP-2024-25-37 | 24/04/2024 | 0 | WBSEDCL | 12.34 | 0 | 0
798 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Chandanpukur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000084/2023-2024 | 1064/SMD | 18/04/2023 | 805 | B.T.PROJECTS PVT.LTD. | 22.37 | 0 | 40
799 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Chandanpukur W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15785) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000141/2024-2025 | 963/SMSD | 09/07/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 0
800 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chandanpukur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15785) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000213/2024-2025 | 944/SMSD | 28/06/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 0
801 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.27] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00487/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 12.32 | 0 | 0
802 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for CHANDANPUKUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 949] [TSM/018249] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000083/2023-2024 | 417/SWD-I | 02/05/2023 | 700 | PINKI CONSTRUCTION | 163.36 | 0 | 75
803 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDANPUKUR PWSS to accommodate FHTC in Baruipur Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018249) (2nd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2023-2024 | 1401/SWD-I | 14/07/2023 | 30 | P N DASS AND GRANDSON | 31.65 | 0 | 50
804 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Chandanpukur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000942/2022-2023 | 1259/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.49 | 0 | 100
805 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000121/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 26.99 | 0 | 0
806 | Alipore Division | Canning Sub-division | Construction of OHR (550 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Phul Malancha,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001088/2023-2024 | 3605/AD | 30/10/2023 | 300 | JIT CONSTRUCTION | 629.62 | 0 | 60
807 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000160/2023-2024 | 1052/AD | 15/06/2023 | 0 | Resource Division | 13.54 | 0 | 0
808 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2368] [TSM/017349] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 665/SWD-I | 24/05/2023 | 90 | M/S B.N. ENTERPRISE | 284.55 | 0 | 0
809 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000506/2021-2022 | 1905/SWD-I | 27/01/2022 | 30 | RADIANT | 2.62 | 0 | 100
810 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (Four) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLIKPUR (PART-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017349] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 3484/SWD-I | 15/03/2023 | 30 | HUMAYUN KABIR | 63.52 | 0 | 0
811 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000182/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 73.07 | 0 | 0
812 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05709/2023-2024 | BP-2023-24-605 | 28/03/2024 | 0 | WBSEDCL | 3.75 | 0 | 0
813 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Chakar Bar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000083/2023-2024 | 1063/SMD | 18/04/2023 | 836 | B.T.PROJECTS PVT.LTD. | 21.46 | 0 | 40
814 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Chakar Bar W/S Scheme under SMD, P.H.E. Dte.(Block- Baruipur)(SM/15784) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001271/2024-2025 | 76/SMSD | 17/01/2025 | 15 | B.T.PROJECTS PVT.LTD. | 0.91 | 0 | 0
815 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chakar Bar W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15784) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001275/2024-2025 | 74/SMSD | 17/01/2025 | 15 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 0
816 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for CHAKARBAR Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 737] [TSM/018426] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 1735/SWD-I | 10/08/2023 | 669 | J.K. CONSTRUCTION | 134.15 | 0 | 40
817 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Development of Land, and other allied works for "Ground Water Based CHAKAR BAR Piped Water Supply Scheme to Accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15784) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000411/2024-2025 | 3707/SWD-I | 23/08/2024 | 45 | A MONDAL ENTERPRISE | 49.74 | 0 | 0
818 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAKAR BAR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/018426] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000649/2022-2023 | 3321/SWD-I | 06/03/2023 | 30 | AKTARUZZAMAN | 31.76 | 0 | 50
819 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Chakar Bar Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000943/2022-2023 | 1265/SWD-I | 12/09/2022 | 30 | GEO SOLUTION | 2.43 | 0 | 100
820 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000120/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.96 | 0 | 0
821 | Alipore Division | Baruipur Sub-Division | Road restoration of Debipur More to Sonagachi More. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01734/2024-2025 | BP-2024-25-798 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.46 | 0 | 0
822 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04685/2023-2024 | BP-2023-24-501 | 12/02/2024 | 0 | WBSEDCL | 15.85 | 0 | 0
823 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Nor W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16126) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 927/SMSD | 28/06/2024 | 15 | PS & ASSOCIATES | 0.58 | 0 | 0
824 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Nor water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16126) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000303/2024-2025 | 1008/SMSD | 11/07/2024 | 539 | PS & ASSOCIATES | 0.92 | 0 | 100
825 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Nor water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16126) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 1015/SMSD | 11/07/2024 | 15 | PS & ASSOCIATES | 0.92 | 0 | 0
826 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with neither neither allied accessories at P.H. 1 & 2 of Nor water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001624/2023-2024 | 4214/SMD | 31/10/2023 | 883 | PS & ASSOCIATES | 25.9 | 0 | 40
827 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for NOR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 668] [TSM/018252] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 965/SWD-I | 08/06/2023 | 657 | M/S B.N. ENTERPRISE | 140.38 | 0 | 60
828 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Development of Land, and other allied works for "Ground Water Based NOR Piped Water Supply Scheme to Accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." SM/16126 | AE BSD,Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 3315/SWD-I | 23/07/2024 | 45 | MILAN GHOSH | 48.46 | 0 | 0
829 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NOR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018252] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000640/2022-2023 | 3286/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
830 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Nor Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000937/2022-2023 | 1250/SWD-I | 08/09/2022 | 30 | GEO SOLUTION | 2.45 | 0 | 100
831 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000126/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 9.28 | 0 | 0
832 | Alipore Division | Baruipur Sub-Division | Road restoration for Dakhshin Kalyanpur Panchanantala to Uttar Sashan Santali Sangha (Barikpara, Gazipara, Kalyanpur Uttar Railgate, Pashchim Madhabpur) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01730/2024-2025 | BP-2024-25-794 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.6 | 0 | 0
833 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Paschim Madhabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1083/SMD | 18/04/2023 | 90 | S.S. SIGNS | 9.38 | 0 | 0
834 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying distribution, Rising main, Funtional Household Tap Connection (FHTC) for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [TSM/018425] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 346/SWD-I | 26/04/2023 | 90 | S.N. ENTERPRISE | 67.07 | 0 | 60
835 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018425] (3rd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000230/2023-2024 | 1406/SWD-I | 14/07/2023 | 30 | KHAN CONSTRUCTION | 15.87 | 0 | 0
836 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Pachim Madhabpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000936/2022-2023 | 1237/SWD-I | 07/09/2022 | 30 | GEO SOLUTION | 2.37 | 0 | 100
837 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000262/2023-2024 | 2427/SWD-I | 30/09/2023 | 0 | Resource Division | 9.81 | 0 | 0
838 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000331/2023-2024 | 273/SWD-I | 10/01/2024 | 0 | Resource Division | 2.05 | 0 | 0
839 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) WB02435, L046-Mirpur on L045 to Ratanpur 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01669/2024-2025 | BP-2024-25-776 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.74 | 0 | 0
840 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Ratanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 1092/SMD | 18/04/2023 | 806 | SHIVAM ENTERPRISE | 21.75 | 0 | 40
841 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ratanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16133) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001223/2024-2025 | 87/SMSD | 17/01/2025 | 15 | SHIVAM ENTERPRISE | 0.91 | 0 | 0
842 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ratanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16133) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001224/2024-2025 | 85/SMSD | 17/01/2025 | 15 | SHIVAM ENTERPRISE | 0.58 | 0 | 0
843 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RATANPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1004] [TSM/017962]. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 470/SWD-I | 04/05/2023 | 720 | M. MUKHERJEE | 187.27 | 0 | 90
844 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RATANPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/017962] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000647/2022-2023 | 3319/SWD-I | 06/03/2023 | 30 | M/S SABITA ENTERPRISE | 31.72 | 0 | 50
845 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rantanpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000933/2022-2023 | 1225/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
846 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000133/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.6 | 0 | 0
847 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
848 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-VIII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000033/2023-2024 | 127/AD | 13/04/2023 | 300 | M/S. SIKHA ENTERPRISE | 134.28 | 0 | 0
849 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000054/2023-2024 | 146/AD | 17/04/2023 | 60 | M/S ROY TRADING CO. | 207.68 | 0 | 85
850 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1963] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000055/2023-2024 | 147/AD | 17/04/2023 | 60 | M/S ROY TRADING CO. | 111.41 | 0 | 55
851 | Alipore Division | Canning Sub-division | Laying of pipeline at different points of Basanti W/S Scheme (Zone-VIII),Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000091/2023-2024 | 447/AD | 08/05/2023 | 15 | MAA BHABANI CONSTRUCTION (DUM DUM) | 7.91 | 0 | 30
852 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VIII) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000094/2023-2024 | 450/AD | 08/05/2023 | 725 | MAA BHABANI CONSTRUCTION (DUM DUM) | 10.08 | 0 | 100
853 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001870/2022-2023 | 12462/AD | 10/03/2023 | 576 | SOMA ENTERPRISE | 58.79 | 0 | 100
854 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VIII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001938/2022-2023 | 11809/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.67 | 0 | 0
855 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001994/2022-2023 | 12685/AD | 14/03/2023 | 45 | PATRA CONSTRUCTION | 7.21 | 0 | 100
856 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001995/2022-2023 | 12686/AD | 14/03/2023 | 45 | PIU ENTERPRISE | 6.96 | 0 | 100
857 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001996/2022-2023 | 12694/AD | 14/03/2023 | 659 | S.MITRA & CO. | 6.96 | 0 | 100
858 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000028/2023-2024 | 233/AD | 24/04/2023 | 0 | Resource Division | 69.7 | 0 | 0
859 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000157/2023-2024 | 1043/AD | 15/06/2023 | 0 | Resource Division | 12.09 | 0 | 0
860 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at Basanti (Zone-VIII) Pump house no-3 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00524/2024-2025 | BP-2024-25-124 | 24/06/2024 | 0 | WBSEDCL | 7.57 | 0 | 0
861 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/04626/2023-2024 | BP-2023-24-483 | 07/02/2024 | 0 | WBSEDCL | 5.09 | 0 | 0
862 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/04707/2023-2024 | BP-2023-24-519 | 17/02/2024 | 0 | WBSEDCL | 18.35 | 0 | 0
863 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1, 2 & 3 of Basanti (Zone-VIII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15957) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001402/2024-2025 | 31/SMSD | 07/01/2025 | 145 | M/S. S.R. ENTERPRISE | 0.87 | 0 | 0
864 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Basanti (Zone-VIII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15957) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001403/2024-2025 | 34/SMSD | 07/01/2025 | 145 | M/S. S.R. ENTERPRISE | 0.91 | 0 | 0
865 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-VIII of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001510/2022-2023 | 887/SMD | 24/03/2023 | 1195 | M/S. S.R. ENTERPRISE | 31.73 | 0 | 65
866 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Hogolkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000258/2025-2026 | 502/SMSD | 04/04/2025 | 15 | DEBJYOTI BASU | 0.88 | 0 | 0
867 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Hogolkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000260/2025-2026 | 501/SMSD | 04/04/2025 | 15 | DEBJYOTI BASU | 0.58 | 0 | 0
868 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Hogalkuria W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/15771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000262/2025-2026 | 708/SMSD | 08/05/2025 | 15 | DEBJYOTI BASU | 0.88 | 0 | 0
869 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Hogalkuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001222/2023-2024 | 2130/SMD | 31/05/2023 | 90 | DEBJYOTI BASU | 22.79 | 0 | 0
870 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1377) (TSM/017730) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000077/2023-2024 | 391/SWD-I | 28/04/2023 | 888 | M/S MITRA CONSTRUCTION | 357.88 | 0 | 32
871 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HOGALKURIA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017730] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 3408/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 100
872 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Up-gradation of pump house, chlorine room, office room, boundary wall and construction of pathway, drain & others allied works of HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000746/2024-2025 | 4668/SWD-I | 18/11/2024 | 60 | R.K ENTERPRISE | 20.9 | 0 | 0
873 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site "HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission." ( SM/15771). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000818/2023-2024 | 1311/SWD-I | 15/03/2024 | 45 | MS KRISHNA MONDAL | 55.36 | 0 | 0
874 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of HOGOLKURIA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/15771] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001098/2024-2025 | 74/SWD-I | 07/01/2025 | 61 | AQUATECH ENGINEERS | 15.5 | 0 | 100
875 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.47 | 0 | 0
876 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000232/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.48 | 0 | 0
877 | Alipore Division | Kakdwip Sub-Division | Construction of 50 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Iswaripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2023-2024 | 96/AD | 11/04/2023 | 1199 | RELIABLE CONSTRUCTIONS | 103.1 | 0 | 50
878 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002069/2022-2023 | 13219/AD | 31/03/2023 | 30 | JOY ENGINEERING & CONSTRUCTION | 14.48 | 0 | 70
879 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002070/2022-2023 | 13220/AD | 31/03/2023 | 30 | M/S BOSE & CO. | 12.98 | 0 | 100
880 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000129/2023-2024 | 665/AD | 17/05/2023 | 0 | Resource Division | 1.37 | 0 | 0
881 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000469/2023-2024 | 4776/AD | 19/12/2023 | 0 | Resource Division | 1.15 | 0 | 0
882 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000787/2023-2024 | 631/AD | 30/01/2024 | 0 | Resource Division | 0.91 | 0 | 0
883 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/00627/2023-2024 | BP-2023-24-84 | 14/06/2023 | 0 | WBSEDCL | 3.87 | 0 | 0
884 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Iswaripur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001784/2023-2024 | 4767/SMD | 06/12/2023 | 91 | COMBINE ENTERPRISES | 9.42 | 0 | 0
885 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000068/2025-2026 | 2257/AD | 14/05/2025 | 45 | SAHANA ENTERPRISE | 15.98 | 0 | 0
886 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000223/2023-2024 | 1028/AD | 13/06/2023 | 45 | SAHANA ENTERPRISE | 50.78 | 0 | 66
887 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000256/2022-2023 | 3490/AD | 26/07/2022 | 45 | R.G. ENTERPRISE (I) | 6.69 | 0 | 98
888 | Alipore Division | Canning Sub-division | Bamboo pilling and earth work in embankment for protection of boundary wall at head work site of Netra W/S Scheme, under Canning-II Block, South 24 Parganas District of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000326/2022-2023 | 267/CSD | 19/05/2022 | 30 | RSA ENTERPRISE | 4.71 | 0 | 98
889 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000483/2024-2025 | 3542/AD | 02/09/2024 | 45 | ZUBIN CONSTRUCTION | 7.07 | 0 | 0
890 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E.Dte. (SM/09014 & SM/17225) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000762/2024-2025 | 4458/AD | 07/11/2024 | 60 | SAHANA ENTERPRISE | 97.21 | 0 | 98
891 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 2 Site for Augmentation of Netra W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001067/2024-2025 | 5004/AD | 05/12/2024 | 30 | B. ENTERPRISE | 15.68 | 0 | 0
892 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials of Augmentation of Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002491/2023-2024 | 1615/CSD | 29/02/2024 | 30 | SAHANA ENTERPRISE | 4.82 | 0 | 85
893 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000080/2023-2024 | 3054/AD | 28/09/2023 | 0 | Resource Division | 79.38 | 0 | 0
894 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Netra water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000036/2023-2024 | 991/SMD | 06/04/2023 | 90 | SUDIP PRADHAN | 10.76 | 0 | 100
895 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at PH-1 OF Tambuldaha & PH-1 of Netra Augmentation w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000893/2023-2024 | 1O65/SMSD | 10/08/2023 | 10 | T.S. CONSTRUCTION | 0.78 | 0 | 100
896 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service connection at P.H. NO.2 of Mirzapur w/s scheme . Application number:1007729941. | AE RWS, Alipore Division | JE RWS, HQ | BILL/00535/2024-2025 | BP-2024-25-129 | 24/06/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
897 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Allied Electro-Mechanical works at Pump House no-1 of Mirzapur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000684/2024-2025 | 433/SMSD | 09/04/2024 | 15 | M/S. S.S. ENTERPRISE | 0.38 | 0 | 0
898 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Mirzapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division | JE RWS, HQ | ORD/001965/2023-2024 | 2280/SMD | 22/06/2023 | 92 | M/S. S.S. ENTERPRISE | 33.56 | 0 | 31
899 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road edge and Hard shoulder damaged due to laying of pipes by PHE Dte. of Dakshin Barasat Mograhat Usthi Road from 0.00 kmp to 21.0 kmp in different stretched of Diamond Harbour Highway Sub-Division under Diamond Harbour Highway Division in the district of South 24 Parganas | AE RWS, Alipore Division | JE RWS, HQ | BILL/00654/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 6.93 | 0 | 0
900 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MIRZAPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/016565] [2nd Call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000228/2023-2024 | 1404/SWD-I | 14/07/2023 | 30 | M/S SACHIDULAL CHOWDHURY | 47.53 | 0 | 80
901 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 0 | 6
902 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Extension of Boundary wall and development of land at 2nd and 3rd Tubewell site for MIRZAPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/18268) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000291/2024-2025 | 3108/SWD-I | 09/07/2024 | 333 | BISWAS CONSTRUCTION | 23.23 | 0 | 40
903 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Mirzapur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000979/2022-2023 | 1435/SWD-I | 23/09/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
904 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000289/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 50.05 | 0 | 0
905 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000309/2023-2024 | 2736/SWD-I | 06/11/2023 | 0 | Resource Division | 18.66 | 0 | 0
906 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 225 Cum. capacity Over Head Reservoir of Sirakole (Zone-I) Water Supply Scheme (Block - Mograhat-I) under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002463/2023-2024 | 1545/AD | 15/03/2024 | 60 | BKB INFRA PROJECTS PRIVATE LIMITED | 35.5 | 0 | 100
907 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with the allied accessories at newly sunk tube well of P.H. 1 under Basulhat water supply scheme adjacent to Zone-III at Baneswarpur under Mograhat-I Block under South 24 Pgs. Mechanical Division, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/001148/2024-2025 | 4951/SMD | 31/12/2024 | 136 | M/S. S.R. ENTERPRISE | 11.99 | 0 | 100
908 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 705 | PROJECT AND MAINTENANCE | 418.32 | 0 | 95
909 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of balance FHTC platform, Chlorination Room (5.50m X 4.50m) and protection of pipelines for ZONE-III at BANESWARPUR under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist- South 24 pgns. under South 24 pgns W/S Division-I, PHE, Dte. (SM/16184) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000437/2024-2025 | 3882/SWD-I | 03/09/2024 | 411 | PROJECT AND MAINTENANCE | 36.45 | 0 | 35
910 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Surendraganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000208/2023-2024 | 791/AD | 24/05/2023 | 45 | M/S. BOSE CONCERN | 48.89 | 0 | 100
911 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (UTTAR SURENDRAGANJ PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000989/2022-2023 | 4150/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.42 | 0 | 100
912 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002169/2023-2024 | 810/AD | 05/02/2024 | 420 | R.S.CONSTRUCTION CO. | 33.1 | 0 | 100
913 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002281/2023-2024 | 917/AD | 08/02/2024 | 45 | M/S MODINA ENTERPRISE | 11.79 | 0 | 10
914 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000114/2023-2024 | 650/AD | 17/05/2023 | 0 | Resource Division | 6.62 | 0 | 0
915 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000300/2023-2024 | 3095/AD | 28/09/2023 | 0 | Resource Division | 19.51 | 0 | 0
916 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000574/2023-2024 | 72/AD | 03/01/2024 | 0 | Resource Division | 1.15 | 0 | 0
917 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000679/2023-2024 | 445/AD | 24/01/2024 | 0 | Resource Division | 1.43 | 0 | 0
918 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection PHED, Uttar Surendraganj PH-1 W/S Scheme Application No:- 1007907707 Reference ID No:- 106657687 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01207/2024-2025 | BP-2024-25-257 | 12/08/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
919 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Uttar Surendraganj PH-2 W/ S Scheme Application No:- 1007942921 Reference ID: 106676151 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01208/2024-2025 | BP-2024-25-258 | 12/08/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
920 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uttar Surendraganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000799/2022-2023 | 333/SMD | 07/02/2023 | 1035 | NUPUR CHANDRA HALDER | 18.51 | 0 | 30
921 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Baliara W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000117/2024-2025 | 2394/AD | 07/06/2024 | 45 | DEV AND COMPANY | 45.39 | 0 | 30
922 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18392) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000156/2024-2025 | 2507/AD | 15/06/2024 | 60 | PIJUSH KANTI TRIPATHI | 53.71 | 0 | 0
923 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Providing Functional Household Tap Connection (FHTC) to all households for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000344/2023-2024 | 1604/AD | 18/07/2023 | 90 | PIJUSH KANTI TRIPATHI | 110.16 | 0 | 50
924 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block-Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/18392) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000363/2024-2025 | 2912/AD | 10/07/2024 | 60 | AVIK ENTERPRISE | 115.68 | 0 | 0
925 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000366/2023-2024 | 1567/AD | 17/07/2023 | 838 | AVIK ENTERPRISE | 409.79 | 0 | 60
926 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site of Baliara W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18392) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000416/2024-2025 | 3067/AD | 25/07/2024 | 45 | AVIK ENTERPRISE | 44.14 | 0 | 0
927 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000580/2023-2024 | 2267/AD | 14/08/2023 | 657 | TANMAY ROY CHOWDHURY | 64.8 | 0 | 50
928 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kusumtala, Bagdanga, Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002138/2023-2024 | 939/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.54 | 0 | 100
929 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002602/2023-2024 | 227/KSD | 24/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
930 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000476/2023-2024 | 4781/AD | 19/12/2023 | 0 | Resource Division | 15.04 | 0 | 0
931 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000558/2023-2024 | 46/AD | 03/01/2024 | 0 | Resource Division | 16.9 | 0 | 0
932 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000980/2023-2024 | 1773/AD | 27/03/2024 | 0 | Resource Division | 1.17 | 0 | 0
933 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Baliara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000115/2023-2024 | 1022/SMD | 12/04/2023 | 90 | ANJAN ENTERPRISE | 25.43 | 0 | 0
934 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000157/2024-2025 | 2508/AD | 15/06/2024 | 75 | M/S. MIHIR KUMAR NASKAR | 89.74 | 0 | 0
935 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000366/2024-2025 | 2915/AD | 10/07/2024 | 60 | GARGO TRADERS | 98.12 | 0 | 0
936 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000369/2023-2024 | 1570/AD | 17/07/2023 | 624 | GARGO TRADERS | 473.26 | 0 | 50
937 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000391/2024-2025 | 3059/AD | 25/07/2024 | 30 | SK SAKIL AHAMED | 9.6 | 0 | 0
938 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000401/2024-2025 | 3184/AD | 31/07/2024 | 45 | RABIUL GAZI | 28.61 | 0 | 0
939 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000567/2023-2024 | 1807/AD | 26/07/2023 | 30 | FORTUNE ENGINEERING | 16.93 | 0 | 60
940 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000574/2023-2024 | 1828/AD | 27/07/2023 | 45 | MEGA SOLAR ENERGY | 36.66 | 0 | 100
941 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000579/2023-2024 | 2266/AD | 14/08/2023 | 45 | B.S.ENTERPRISE (II) | 60.58 | 0 | 76
942 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =650] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001014/2023-2024 | 3205/AD | 04/10/2023 | 90 | M/S. MIHIR KUMAR NASKAR | 105.31 | 0 | 82
943 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Chandranagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001835/2023-2024 | 123/AD | 05/01/2024 | 45 | SARADA CONSTRUCTION | 39.88 | 0 | 100
944 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
945 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000559/2023-2024 | 47/AD | 03/01/2024 | 0 | Resource Division | 11.33 | 0 | 0
946 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000789/2023-2024 | 633/AD | 30/01/2024 | 0 | Resource Division | 4.74 | 0 | 0
947 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000989/2023-2024 | 1782/AD | 27/03/2024 | 0 | Resource Division | 45.43 | 0 | 0
948 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Dakshin Chandranagar PH-2 W/S Scheme Application No- 1007183473 Reference ID:- 106222546 | Assistant Engineer, Kakdwip Sub Division |  | BILL/00213/2024-2025 | BP-2024-25-61 | 16/05/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
949 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Dakshin chandranagar PH-3 W/ S Scheme Application No:- 1008025333 Reference ID: 106715785 | Assistant Engineer, Kakdwip Sub Division |  | BILL/01765/2024-2025 | BP-2024-25-427 | 07/10/2024 | 0 | WBSEDCL | 8.4 | 0 | 0
950 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer, Kakdwip Sub Division |  | BILL/05392/2023-2024 | BP-2023-24-596 | 28/03/2024 | 0 | WBSEDCL | 8.06 | 0 | 0
951 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Chandranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001511/2022-2023 | 3837/SMD | 29/12/2022 | 90 | BINAPANI ENTERPRISE | 23.4 | 0 | 0
952 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 1no Tube well of Ramchandranagar Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000599/2022-2023 | 5924/AD | 19/10/2022 | 15 | S.K.GOLUI | 3.76 | 0 | 100
953 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Ramchandranagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001144/2021-2022 | 5532/AD | 20/01/2022 | 365 | M/S B.N.ENTERPRISE | 54.95 | 0 | 100
954 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 45 | M/S B. ENTERPRISE | 113.06 | 0 | 94
955 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000017/2021-2022 | 5623/AD | 25/01/2022 | 0 | Resource Division | 4.51 | 0 | 0
956 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000802/2023-2024 | 647/AD | 30/01/2024 | 0 | Resource Division | 2.54 | 0 | 0
957 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Moukhali-Kumarkhali (Part - V) having village with maximum 247 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000787/2022-2023 | 6642/AD | 14/11/2022 | 810 | HARIDAS DUTTA | 56.64 | 0 | 92
958 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-V) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001901/2022-2023 | 5665/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.55 | 0 | 100
959 | Alipore Division | Canning Sub-division | Additional laying of pipeline & FHTC at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - IV) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003329/2024-2025 | 944/CSD | 22/08/2024 | 30 | JOYJIT MUKHERJEE | 3.04 | 0 | 0
960 | Alipore Division | Canning Sub-division | Additional laying of pipeline & FHTC at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - III) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003331/2024-2025 | 945/CSD | 22/08/2024 | 30 | S.S. ENTERPRISE (I) | 3.04 | 0 | 95
961 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000170/2023-2024 | 1123/AD | 22/06/2023 | 0 | Resource Division | 1.52 | 0 | 0
962 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00393/2023-2024 | BP-2023-24-50 | 09/06/2023 | 0 | WBSEDCL | 2.64 | 0 | 0
963 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-V) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000591/2022-2023 | 652/SND | 03/03/2023 | 90 | S.B.ENTERPRISE | 8.84 | 0 | 100
964 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-VI) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000592/2022-2023 | 653/SMD | 03/03/2023 | 90 | M/S. SREEJIT ENTEPRISE | 8.85 | 0 | 100
965 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Baharu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] |  |  | ORD/001634/2023-2024 | 2945/SMD | 05/09/2023 | 91 | DAS ENTERPRISE | 35.08 | 0 | 30
966 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Baharu W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) |  |  | ORD/002479/2024-2025 | 434/SMSD | 09/04/2024 | 15 | DAS ENTERPRISE | 0.63 | 0 | 0
967 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BAHARU PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017335] |  |  | ORD/000365/2023-2024 | 1774/SWD-I | 11/08/2023 | 30 | MATRI ENTERPRISE | 47.62 | 0 | 100
968 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BAHARU MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4292] [TSM/017335] |  |  | ORD/000408/2023-2024 | 1925/SWD-I | 22/08/2023 | 90 | M/S G. C. CONSTRUCTION | 530.53 | 0 | 60
969 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Baharu Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000969/2022-2023 | 1386/SWD-I | 20/09/2022 | 30 | MEASURE LAND | 2.91 | 0 | 100
970 | South 24 Pgs W/S Division I |  | Construction of 02 (two) nos. chlorination rooms for BAHARU Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte., South 24-Pgs. Dist. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/18677) |  |  | ORD/001127/2024-2025 | 190/SWD-I | 17/01/2025 | 300 | S.M. ENTERPRISE (MOGRAHAT) | 11.41 | 0 | 100
971 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 99.15 | 0 | 0
972 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2582] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000194/2023-2024 | 2103/AD | 08/08/2023 | 90 | M/S. JHARNA ENTERPRISE | 259.33 | 0 | 40
973 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000302/2024-2025 | 2709/AD | 24/06/2024 | 60 | M/S. JHARNA ENTERPRISE | 163.39 | 0 | 0
974 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000415/2024-2025 | 3066/AD | 25/07/2024 | 45 | M/S. JHARNA ENTERPRISE | 28.68 | 0 | 0
975 | Alipore Division | Kakdwip Sub-Division | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000421/2023-2024 | 2152/AD | 09/08/2023 | 60 | IQBAL CONSTRUCTION | 57.38 | 0 | 66
976 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000443/2024-2025 | 3294/AD | 09/08/2024 | 30 | KHAN CONSTRUCTION (HASNABAD) | 9.31 | 0 | 0
977 | Alipore Division | Kakdwip Sub-Division | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 2500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000545/2023-2024 | 2211/AD | 10/08/2023 | 900 | M/S. JHARNA ENTERPRISE | 369.23 | 0 | 70
978 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kakdwip PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000643/2023-2024 | 2035/AD | 05/08/2023 | 45 | LEMNISCATE | 12.08 | 0 | 100
979 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001385/2023-2024 | 379/KSD | 17/08/2023 | 184 | ANAMIKA BERA | 2.4 | 0 | 100
980 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
981 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 600 cum. capacity OHR of Kakdwip PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002233/2023-2024 | 719/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
982 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002286/2023-2024 | 1003/AD | 16/02/2024 | 90 | M/S. JHARNA ENTERPRISE | 128.24 | 0 | 60
983 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000454/2023-2024 | 4718/AD | 18/12/2023 | 0 | Resource Division | 40.56 | 0 | 0
984 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000590/2023-2024 | 89/AD | 03/01/2024 | 0 | Resource Division | 14.85 | 0 | 0
985 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000821/2023-2024 | 666/AD | 30/01/2024 | 0 | Resource Division | 15.91 | 0 | 0
986 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000908/2023-2024 | 896/AD | 07/02/2024 | 0 | Resource Division | 0.75 | 0 | 0
987 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | BILL/05173/2023-2024 | BP-2023-24-591 | 13/03/2024 | 0 | WBSEDCL | 6.83 | 0 | 0
988 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Kakdwip water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Kakdwip]. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000026/2025-2026 | 1025/SMD | 16/04/2025 | 90 | NITESH MANAGEMENT | 12.4 | 0 | 0
989 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Kakdwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000366/2024-2025 | 634/AE-I/SMD | 23/04/2024 | 15 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0
990 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Kakdwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000367/2024-2025 | 633/AE-I/SMD | 23/04/2024 | 15 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0
991 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of Kakdwip water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Kakdwip] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000562/2024-2025 | 794-AE-I-SMD | 11/06/2024 | 15 | PS & ASSOCIATES | 0.78 | 0 | 0
992 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Kakdwip water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001623/2023-2024 | 4756/SMD | 06/12/2023 | 738 | KARUNAMOY ENGINEERING | 23.16 | 0 | 95
993 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Durgapur W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000222/2024-2025 | 2605/AD | 19/06/2024 | 225 | M/S KHAJABABA ENTERPRISE | 28.53 | 0 | 95
994 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Durgapur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000223/2024-2025 | 2606/AD | 19/06/2024 | 30 | NEPAL CHANDRA PRADHAN | 9.59 | 0 | 0
995 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000389/2024-2025 | 3057/AD | 25/07/2024 | 30 | M/S BABUSONA ENTERPRISE | 9.58 | 0 | 0
996 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000390/2024-2025 | 3058/AD | 25/07/2024 | 30 | SWASTIK CONSTRUCTION | 9.59 | 0 | 0
997 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000424/2024-2025 | 3202/AD | 01/08/2024 | 240 | H T R CONSTRUCTION | 47.47 | 0 | 30
998 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000573/2023-2024 | 2260/AD | 14/08/2023 | 45 | MEGA SOLAR ENERGY | 36.66 | 0 | 100
999 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000623/2023-2024 | 2432/AD | 22/08/2023 | 863 | H T R CONSTRUCTION | 614.68 | 0 | 75
1000 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000699/2023-2024 | 2527/AD | 28/08/2023 | 30 | ABONTICA ENTERPRISE | 15.52 | 0 | 60
1001 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000700/2023-2024 | 2528/AD | 28/08/2023 | 30 | SWASTIK CONSTRUCTION | 14.73 | 0 | 25
1002 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000702/2023-2024 | 2529/AD | 28/08/2023 | 30 | UNIVERSAL CONSTRUCTION (ULUBERIA) | 13.71 | 0 | 30
1003 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000705/2023-2024 | 2530/AD | 28/08/2023 | 30 | AROMA INC | 13.31 | 0 | 20
1004 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000707/2023-2024 | 2531/AD | 28/08/2023 | 30 | SAB ENGINEERING WORKS | 13.11 | 0 | 20
1005 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000708/2023-2024 | 2532/AD | 28/08/2023 | 30 | SUNIL ENTERPRISE | 8.16 | 0 | 90
1006 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000711/2023-2024 | 2533/AD | 28/08/2023 | 30 | M/S SNEHALATA ENTERPRISE | 7.83 | 0 | 80
1007 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001044/2024-2025 | 4965/AD | 04/12/2024 | 300 | H T R CONSTRUCTION | 74.15 | 0 | 20
1008 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001450/2023-2024 | 4687/AD | 18/12/2023 | 120 | M/S. P. GIRI ENTERPRISE | 91.01 | 0 | 45
1009 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001451/2023-2024 | 4688/AD | 18/12/2023 | 120 | MOINAK POREL | 91.33 | 0 | 40
1010 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001837/2023-2024 | 125/AD | 05/01/2024 | 45 | MEHAI TECHNOLOGY LIMITED | 39.91 | 0 | 40
1011 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
1012 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 400 cum. capacity OHR of Dakshin Durgapur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002217/2023-2024 | 874/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1013 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000475/2023-2024 | 4780/AD | 19/12/2023 | 0 | Resource Division | 26.31 | 0 | 0
1014 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000793/2023-2024 | 638/AD | 30/01/2024 | 0 | Resource Division | 18.6 | 0 | 0
1015 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000910/2023-2024 | 893/AD | 07/02/2024 | 0 | Resource Division | 10.67 | 0 | 0
1016 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000979/2023-2024 | 1772/AD | 27/03/2024 | 0 | Resource Division | 14.69 | 0 | 0
1017 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Dakshin Durgapur PH-1 W/S Scheme JL No- 007, Khatian-2375, Plot-2482, Mouza Dakshin Durgapur Application No:- 1007514926 Reference ID:- 106460089 | Assistant Engineer, Kakdwip Sub Division |  | BILL/00207/2024-2025 | BP-2024-25-65 | 16/05/2024 | 0 | WBSEDCL | 5.31 | 0 | 0
1018 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Dakshin Durgapur PH-2 W/S Scheme Mouza- Dakshin Durgapur, JL No- 007, Khatian- 3270, Plot- 1425 Application No:- 1007551348 Reference ID:- 106484817 | Assistant Engineer, Kakdwip Sub Division |  | BILL/00208/2024-2025 | BP-2024-25-65 | 16/05/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1019 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Dakshin Durgapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002214/2024-2025 | 1347-AE-II-SMD | 14/11/2024 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.9 | 0 | 0
1020 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Dakshin Durgapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002215/2024-2025 | 1348-AE-II-SMD | 14/11/2024 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.9 | 0 | 0
1021 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Dakshin Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/002753/2023-2024 | 4871/SMD | 14/12/2023 | 564 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.19 | 0 | 40
1022 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bansra Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000125/2021-2022 | 1269/AD | 13/07/2021 | 365 | B. MOOKHERJEE | 326.08 | 0 | 80
1023 | Alipore Division | Canning Sub-division | Laying of additional pipe line at Bansra (Zone - I & II) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001031/2024-2025 | 4941/AD | 03/12/2024 | 60 | M/S B.M. CONSTRUCTION | 52.15 | 0 | 0
1024 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-II) Water Supply Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000111/2021-2022 | 1194/AD | 07/07/2021 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.47 | 0 | 51
1025 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-F) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000406/2023-2024 | 1905/AD | 01/08/2023 | 45 | ASHIS ENTERPRISE | 20.52 | 0 | 93
1026 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 0 | 95
1027 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
1028 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary at 2nd Tubewell site of Shibkalinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07399) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002192/2024-2025 | 2073/KSD | 28/12/2024 | 20 | M/S IDEAL WORKS | 1.64 | 0 | 90
1029 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000279/2023-2024 | 3078/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1030 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000835/2023-2024 | 680/AD | 30/01/2024 | 0 | Resource Division | 9.59 | 0 | 0
1031 | Alipore Division |  | Laying pipe line to connect the uncovered habitation of Lot No.-126 W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/000270/2022-2023 | 262/CSD | 19/05/2022 | 30 | K.P. CONSTRUCTION | 4.8 | 0 | 99
1032 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Lot No. - 126 Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year. |  |  | ORD/001375/2020-2021 | 5131/AD | 08/02/2021 | 365 | K.P. CONSTRUCTION | 189.54 | 142.23 | 100
1033 | Alipore Division |  | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] |  |  | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 60 | S.P. CONSTRUCTION (I) | 97.64 | 0 | 80
1034 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Manasadwip Water Supply Scheme, Block - Sagar, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001257/2020-2021 | 2277/AD | 12/10/2020 | 365 | PIKASU BOSE | 128 | 100.03 | 100
1035 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Gurudaspur Water Supply Scheme, Block - Patharpratima South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000499/2020-2021 | 5125/AD | 08/02/2021 | 365 | DHIRENDRA ENGINEERING & CONSTRUCTION | 92.45 | 24.95 | 44
1036 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000772/2023-2024 | 606/AD | 29/01/2024 | 0 | Resource Division | 23.82 | 0 | 0
1037 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [2340/AD, 21-22, T.No. 1603/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | VCH/002610/2021-2022 | BP-2021-22-513 | 23/03/2022 | 0 | LEMNISCATE | 2.67 | 0 | 0
1038 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O NO. 548/KSD, 03.09.21, T.NO. 1783/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | VCH/002611/2021-2022 | BP-2021-22-514 | 23/03/2022 | 0 | M/S R.DUTTA & CO. | 4.26 | 0 | 0
1039 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 141 to 144 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000362/2020-2021 | 1411/SWD-I | 14/12/2020 | 120 | BANIK BROTHERS | 94.35 | 0 | 100
1040 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system by extension of pipeline for Buita W/S Scheme for Booth No - 141 to 144 and adjoining areas under Budge Budge-I Block with allied works unuder South 24-Parganas W/S Divn-I, P.H.E. Dte, South 24-Pgns District. | AE SWSD-I |  | ORD/000586/2021-2022 | 1471/SWD-I | 15/12/2021 | 45 | BANIK BROTHERS | 2.54 | 0 | 100
1041 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for Booth 170 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000116/2020-2021 | 1394/SWD-I | 11/12/2020 | 120 | PROJECT AND MAINTENANCE | 92.1 | 70.07 | 90
1042 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Moukhali W/S Scheme for Durgapur Moukhali and Jagat Ballavpur under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000309/2020-2021 | 1414/SWD- I | 14/12/2020 | 120 | SUPRITI ENTERPRISE | 96.89 | 0 | 100
1043 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6127) Part -H | AE SWSD-I |  | ORD/000470/2022-2023 | 2782/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.51 | 0 | 100
1044 | Alipore Division | Raidighi Sub-Division | Miscellaneous work for smooth distribution system of piped water supply at Zone-VI of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000439/2022-2023 | 4353/AD | 25/08/2022 | 60 | DEBARATI ENTERPRISE | 49.88 | 0 | 99
1045 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000012/2022-2023 | 1170/AD | 27/05/2022 | 0 | Resource Division | 5.97 | 0 | 0
1046 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000019/2021-2022 | 5625/AD | 25/01/2022 | 0 | Resource Division | 9.31 | 0 | 0
1047 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000022/2022-2023 | 1678/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
1048 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000038/2022-2023 | 3585/AD | 29/07/2022 | 0 | Resource Division | 48.96 | 0 | 0
1049 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-V (Raidighi PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001340/2021-2022 | 6034/AD | 16/02/2022 | 365 | TANMAY ROY CHOWDHURY | 171.21 | 0 | 85
1050 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000025/2022-2023 | 1681/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
1051 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000096/2022-2023 | 6202/AD | 02/11/2022 | 0 | Resource Division | 76.28 | 0 | 0
1052 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Narayangar, Sardarpara) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) |  |  | ORD/000111/2022-2023 | 282/CSD | 19/05/2022 | 40 | BABA LOKENATH ENTERPRISE | 4.82 | 0 | 100
1053 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Narayangar) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) |  |  | ORD/000119/2022-2023 | 280/CSD | 19/05/2022 | 40 | M/S BOSE & CO. | 4.78 | 0 | 100
1054 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Sardarpara) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) |  |  | ORD/000120/2022-2023 | 281/CSD | 19/05/2022 | 40 | M/S BOSE & CO. | 4.81 | 0 | 100
1055 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayangarh Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000563/2021-2022 | 3022/AD | 02/11/2021 | 365 | BOSE & CO. | 61.39 | 0 | 100
1056 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
1057 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kashinagar W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001026/2021-2022 | 540/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.59 | 0 | 100
1058 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kashinagar & Srikrishnanagar W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001045/2021-2022 | 2276/AD | 06/09/2021 | 7 | LEMNISCATE | 4.17 | 0 | 100
1059 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000257/2023-2024 | 3062/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1060 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000843/2023-2024 | 689/AD | 30/01/2024 | 0 | Resource Division | 28.25 | 0 | 0
1061 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001151/2021-2022 | 5302/AD | 04/01/2022 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 213.56 | 0 | 0
1062 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000012/2021-2022 | 5618/AD | 25/01/2022 | 0 | Resource Division | 22.69 | 0 | 0
1063 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000396/2023-2024 | 336/AD | 19/01/2024 | 0 | Resource Division | 36.35 | 0 | 0
1064 | Central Drilling | Canning Sub-division | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 350 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR TILKUMAR W/S SCHEME (UNTREATED ZONE), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000015/2022-2023 | 52/CDD | 08/04/2022 | 30 | PADMA ENGINEERING & CO. | 16.79 | 0 | 0
1065 | Central Drilling | Canning Sub-division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE ASSISTANT ENGINEER, STORE & WORKSHOP SUB DIVISION, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000060/2022-2023 | 99/S&WSD | 23/06/2022 | 15 | NAGENDRA PATRA | 0.87 | 0 | 33
1066 | Central Drilling | Canning Sub-division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000061/2022-2023 | 77/ S&WSD | 27/05/2022 | 15 | SUMAN KUMAR DEY | 0.9 | 0 | 0
1067 | Central Drilling | Canning Sub-division | RESISTIVITY SURVEY OF TUBE WELLS AT IRPALA W/S SCHEME, UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000214/2021-2022 | 110/CMSD-I (D) | 20/07/2021 | 7 | EARTH CARE PRODUCTS & SERVICES | 0.52 | 0 | 0
1068 | Central Drilling | Canning Sub-division | ADDITIONAL MOBILIZATION OF ALL MACHINERIES & ACCESSORIES ETC. AND SEALING OF SEALING ZONE AT SITE FOR CONSTRUCTION OF TUBE WELL AT TILKUMAR W/S SCH (UNTREATED ZONE), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000218/2022-2023 | 257/CMSD-I | 23/06/2022 | 3 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0
1069 | Central Drilling | Canning Sub-division | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0 | 0
1070 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000060/2021-2022 | 1206/SWD-I | 09/11/2021 | 120 | STARCO CONSTRUCTION | 288.89 | 0 | 96
1071 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Buita W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM/ 8293 ) PART-VIII | AE SWSD-I |  | ORD/000467/2022-2023 | 2776/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 4.95 | 0 | 100
1072 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance of Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000040/2022-2023 | 978/SWD-I | 27/07/2022 | 892 | CALCON CONSTRUCTIONS | 75.21 | 0 | 100
1073 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000085/2021-2022 | 1162/SWD-I JJM | 02/11/2021 | 120 | UNICON INDIA | 125.43 | 0 | 25
1074 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 8300 ) PART-I | AE BSD |  | ORD/000459/2022-2023 | 2771/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 8.53 | 0 | 100
1075 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000089/2021-2022 | 1163/SWD-I JJM | 02/11/2021 | 120 | CALCON CONSTRUCTIONS | 137.48 | 0 | 10
1076 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Divn. - I P.H.E Dte. (TSM/8301) PART-II | AE SWSD-I |  | ORD/000455/2022-2023 | 2730/SWD-I | 27/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 23.13 | 0 | 100
1077 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for under Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza including Balarampur Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000087/2021-2022 | 1161/SWD-I JJM | 02/11/2021 | 120 | M/S. S.S. ENTERPRISE | 152.75 | 0 | 100
1078 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Atmarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8298) Part -E | AE SWSD-I |  | ORD/000453/2022-2023 | 2727/SWD-I | 27/01/2023 | 45 | MOUMITA ENTERPRISE | 10.71 | 0 | 100
1079 | Alipore Division | Raidighi Sub-Division | Extension of distribution system (Node no. AB-CD) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000043/2022-2023 | 35/RSD | 19/04/2022 | 60 | R.G. ENTERPRISE (I) | 4.77 | 0 | 100
1080 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system (Node No. 16-15-13-14, 16-17-18-19-20-21, 15-23-22-24) at Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000108/2022-2023 | 05/RSD | 04/04/2022 | 60 | KAKALI ENTERPRISE | 4.79 | 0 | 100
1081 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
1082 | Alipore Division | Raidighi Sub-Division | Bamboo pilling walling at Zone-X of Mathurapur - I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Node point -255 - 255A, 255-255E, 255-255D, 255-255C) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000267/2022-2023 | 103/RSD | 13/06/2022 | 60 | SUPRITI ENTERPRISE | 4.65 | 0 | 100
1083 | Alipore Division | Raidighi Sub-Division | Construction of thrust block for D.I. pipe line at Zone - I, Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000426/2022-2023 | 282/RSD | 01/09/2022 | 60 | M/S KUNDU CONSTRUCTION | 0.81 | 0 | 100
1084 | Alipore Division | Raidighi Sub-Division | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 600 | M/S. S.S. ENTERPRISE | 1185.63 | 0 | 10
1085 | Alipore Division | Raidighi Sub-Division | Special repairing work of pipeline and allied works to mitigate water supply problem at Rajapur & adjacent area Uttar Durgapur water supply scheme ( Zone-I of Mathurapur-I Block) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000634/2022-2023 | 95/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.75 | 0 | 100
1086 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line work at Zone-I (Nodal point 354-356-357-359-361-363-367) of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001133/2022-2023 | 598/RSD | 23/12/2022 | 30 | RAIS ALI MOLLA | 1.82 | 0 | 100
1087 | Alipore Division | Raidighi Sub-Division | Construction of culvert at Zone-I of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001804/2022-2023 | 934/RSD | 10/03/2023 | 30 | SUKUMAR HALDAR | 1.07 | 0 | 99
1088 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000637/2023-2024 | 241/AD | 15/01/2024 | 0 | Resource Division | 52.95 | 0 | 0
1089 | S24 Pgns Mechanical | Raidighi Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I of Mega Surface (Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-I] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000559/2022-2023 | 573/SMD | 22/02/2023 | 859 | DEBJYOTI BASU | 13.13 | 0 | 0
1090 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
1091 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.05.2025 to 31.07.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000446/2025-2026 | 72/RSD | 30/04/2025 | 92 | DILIP DHALI | 1.2 | 0 | 0
1092 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.05.2024 to 31.07.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000447/2025-2026 | 73/RSD | 30/04/2025 | 92 | SANKAR HALDER | 1.2 | 0 | 0
1093 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2022 to 31/07/2023. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000850/2022-2023 | 227/RSD | 29/07/2022 | 365 | NITYANANDA MONDAL | 4.8 | 0 | 100
1094 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2022 to 31/10/2022. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001129/2022-2023 | 276/RSD | 31/08/2022 | 61 | BAPPA DAS | 0.8 | 0 | 100
1095 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/11/2022 to 31/12/2022. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001130/2022-2023 | 384/RSD | 28/10/2022 | 61 | BAPPA DAS | 0.8 | 0 | 100
1096 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/01/2023 to 28/02/2023. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001143/2022-2023 | 679/RSD | 29/12/2022 | 2 | BAPPA DAS | 0.8 | 0 | 100
1097 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.11.2024 to 31.01.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002375/2024-2025 | 768E/RSD | 30/10/2024 | 92 | DILIP DHALI | 1.2 | 0 | 10
1098 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2023 to 31/07/2024. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002446/2023-2024 | 212/RSD | 28/07/2023 | 366 | NITYANANDA MONDAL | 4.8 | 0 | 0
1099 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.11.2024 to 31.01.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002473/2024-2025 | 768D/RSD | 30/10/2024 | 92 | SANKAR HALDER | 1.2 | 0 | 100
1100 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.02.2025 to 30.04.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002914/2024-2025 | 1032/RSD | 30/01/2025 | 90 | DILIP DHALI | 1.2 | 0 | 0
1101 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.02.2024 to 30.04.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002916/2024-2025 | 1033/RSD | 30/01/2025 | 90 | SANKAR HALDER | 1.2 | 0 | 0
1102 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000646/2023-2024 | 256/AD | 15/01/2024 | 0 | Resource Division | 47.12 | 0 | 0
1103 | S24 Pgns Mechanical | Raidighi Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-VII of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000563/2022-2023 | 579/SMD | 23/02/2023 | 90 | BARISAL TRADING CO. | 26.11 | 0 | 0
1104 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Charges for new service connection at pump house no-1 of Narayanitala. | Assistant Engineer | Junior Engineer | BILL/01154/2024-2025 | BP-2024-25-235 | 08/08/2024 | 0 | WBSEDCL | 17.87 | 0 | 0
1105 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Charges for new service connection at pump house no-2 of Narayanitala (Baruipur Block) | Assistant Engineer | Junior Engineer | BILL/02035/2024-2025 | BP-2024-25-489 | 09/12/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
1106 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Narayani Tala W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/11495) | Assistant Engineer | Junior Engineer | ORD/000180/2025-2026 | 710/SMSD | 15/05/2025 | 15 | SWAPAN ENTERPRISE | 0.58 | 0 | 0
1107 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Narayani Tala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000537/2022-2023 | 464/SMD | 17/02/2023 | 1139 | SWAPAN ENTERPRISE | 23.3 | 0 | 25
1108 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Improvement of outdoor Illumination arrangement with allied works at PH-1 of Narayani Tala W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11495) | Assistant Engineer | Junior Engineer | ORD/002102/2024-2025 | 391/SMSD | 19/03/2025 | 15 | SWAPAN ENTERPRISE | 0.92 | 0 | 0
1109 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Improvement of outdoor Illumination arrangement with allied works at PH-2 of Narayani Tala W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11495) | Assistant Engineer | Junior Engineer | ORD/002103/2024-2025 | 392/SMSD | 19/03/2025 | 15 | SWAPAN ENTERPRISE | 0.92 | 0 | 0
1110 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Narayanitala PWSS of BaruipurBlock for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011225] | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 28/SWD-I | 05/04/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 0 | 100
1111 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for NARAYANITALA PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2022-2023 | 1189/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 100
1112 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of NARAYANITALA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000216/2021-2022 | 1966/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
1113 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at NARAYANITALA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1527) | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 1800/SWD-I | 09/11/2022 | 900 | PATH MAKERS | 382.32 | 0 | 100
1114 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) nos. chlorination rooms at Narayanitala of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 2212/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 0
1115 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional laying of pipeline for NARAYANITALA Pipe Water Supply Scheme of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (TSM / 011225) | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 1913/SWD-I | 21/08/2023 | 60 | A.B. ASSOCIATES | 19.49 | 0 | 70
1116 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of boundary wall and platform for providing FHTC for Ground water based NARAYANITALA piped water supply scheme to accommodate FHTC in Jaynagar-I & BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11495) | Assistant Engineer | Junior Engineer | ORD/000439/2024-2025 | 3884/SWD-I | 03/09/2024 | 45 | AYUSH ENTERPRISE | 48.14 | 0 | 0
1117 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000263/2023-2024 | 2425/SWD-I | 30/09/2023 | 0 | Resource Division | 44.41 | 0 | 0
1118 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000341/2023-2024 | 262/SWD-I | 10/01/2024 | 0 | Resource Division | 9.41 | 0 | 0
1119 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/01059/2023-2024 | BP-2023-24-125 | 17/07/2023 | 0 | WBSEDCL | 6.17 | 0 | 0
1120 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Lakshmikantapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000539/2022-2023 | 470/SMD | 20/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.92 | 0 | 50
1121 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Lakshmikantapur Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11502] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002374/2023-2024 | 984-AE-II-SMD | 13/09/2023 | 15 | AHALYA ENGINEERING WORKS | 0.58 | 0 | 100
1122 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply & Delivery of Submersible Pumping Machinery for PH No.-1 of Lakshmikantapur Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11502] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002453/2023-2024 | 963-AE-II-SMD | 07/09/2023 | 15 | AHALYA ENGINEERING WORKS | 0.89 | 0 | 100
1123 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000029/2022-2023 | 913/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 0 | 100
1124 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 932] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000149/2022-2023 | 1389/SWD-I | 21/09/2022 | 953 | MS MANABESH ROY | 111.29 | 0 | 95
1125 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2023 to 30.11.2023] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000176/2023-2024 | 778/SWD-I | 31/05/2023 | 183 | PUSPA JAISWAL | 0.87 | 0 | 40
1126 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2024 to 30.11.2024] [Vehicle No- WB-04G-7357] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000198/2024-2025 | 2356/SWD-I | 24/05/2024 | 183 | PUSPA JAISWAL | 0.87 | 0 | 60
1127 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
1128 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of LAKSHMIKANTAPUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000230/2021-2022 | 1979/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 0 | 100
1129 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Lakshikantapur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte, South 24-Pgns disct. (SM/11502) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000270/2024-2025 | 2920/SWD-I | 25/06/2024 | 45 | NIKHIL SAMADDAR | 39.42 | 0 | 31
1130 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of LAKSHMIKANTAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11502) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000442/2022-2023 | 2661/SWD-I | 18/01/2023 | 60 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 0 | 100
1131 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for LAKSHMIKANTAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011195] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000587/2022-2023 | 3108/SWD-I | 24/02/2023 | 210 | MOULI CONSTRUCTION | 15.87 | 0 | 10
1132 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of HDPE pipe from Second Tubewell to distribution network under Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. [SM Code: TSM/011195, SM/11502] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000669/2023-2024 | 3020/SWD-I | 30/11/2023 | 60 | MS MANABESH ROY | 24.39 | 0 | 98
1133 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.12.2023 to 31.05.2024] [Vehicle No- WB-04G-7357] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000700/2023-2024 | 2924/SWD-I | 23/11/2023 | 183 | PUSPA JAISWAL | 0.87 | 0 | 30
1134 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for LAKSHMIKANTAPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11502] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000707/2024-2025 | 4537/SWD-I | 06/11/2024 | 93 | HI-LIGHT ELECTRONICS | 15.9 | 0 | 96
1135 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000860/2022-2023 | 2963/SWD-I | 16/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 0
1136 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000012/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.74 | 0 | 0
1137 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000110/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 25.56 | 0 | 0
1138 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), Construction of boundary fencing, MS grilll type gate, land development, Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Baintala having village with maximum 66 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000953/2022-2023 | 7807/AD | 30/11/2022 | 60 | M/S SEKH ENTERPRISE | 34.11 | 0 | 25
1139 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/04681/2023-2024 | BP-2023-24-512 | 12/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
1140 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, &Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kuler Khonj having village with maximum 85 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000766/2022-2023 | 6495/AD | 11/11/2022 | 60 | SURYA ENTERPRISE | 33.84 | 0 | 88
1141 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Kuler khoj PH-1 Water supply scheme under Canning-II block. Reference ID:-106599046, Application No :-1007775984 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01847/2024-2025 |  | 29/10/2024 | 0 | WBSEDCL | 10.53 | 0 | 0
1142 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01101/2023-2024 | BP-2023-24-151 | 24/07/2023 | 0 | WBSEDCL | 1.3 | 0 | 0
1143 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Danga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000295/2022-2023 | 444/SMD | 17/02/2023 | 90 | A.G.ENTERPRISE | 25.68 | 0 | 50
1144 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Danga W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002208/2023-2024 | 1316/SMSD | 06/10/2023 | 15 | A.G.ENTERPRISE | 0.99 | 0 | 0
1145 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DANGA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12230] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 618/SWD-I | 17/05/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 5
1146 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Repairing and renovation of Pump House, Chlorine Room, Construction of Pathway,Drain, Development of land & others allied works at HW Site of "DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12230). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000235/2024-2025 | 2655/SWD-I | 07/06/2024 | 45 | M/S PIONEER CONSTRUCTION | 22.49 | 0 | 70
1147 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for DANGA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000262/2022-2023 | 1774/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
1148 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1991] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 2882/SWD-I | 13/02/2023 | 1201 | M/S PIONEER CONSTRUCTION | 418.22 | 0 | 50
1149 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12230) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000764/2024-2025 | 4685/SWD-I | 18/11/2024 | 45 | ARASTA ENGINEERING & CO | 10.18 | 0 | 0
1150 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of DANGA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/12230] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001100/2024-2025 | 76/SWD-I | 07/01/2025 | 30 | B.K.ENTERPRISE | 15.68 | 0 | 0
1151 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000014/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 15.6 | 0 | 0
1152 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000251/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.26 | 0 | 0
1153 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V B at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4346] | AE BSD |  | ORD/000155/2023-2024 | 806/SWD-I | 02/06/2023 | 669 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 330.69 | 0 | 40
1154 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V A at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5791] | AE BSD |  | ORD/000156/2023-2024 | 807/SWD-I | 02/06/2023 | 669 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 440.56 | 0 | 50
1155 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000086/2022-2023 | 3002/SWD-I | 20/02/2023 | 0 | Resource Division | 520.49 | 0 | 0
1156 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II A at Mayahauri mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [ No. of FHTC = 5789 ] | AE BSD |  | ORD/000370/2022-2023 | 2314/SWD-I | 19/12/2022 | 840 | SAMIRON GHOSH | 440.83 | 0 | 50
1157 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II B at Mayahauri mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3400] | AE BSD |  | ORD/000534/2022-2023 | 2966/SWD-I | 17/02/2023 | 120 | PRITAM SENGUPTA (EMAIL ID-SENGUPTA408@YAHOO.COM) | 207.24 | 0 | 30
1158 | South 24 Pgs W/S Division I | Baruipur Sub-Division | SupplyofdifferentCIDFspecialsfor layingof DIpipe(250mm dia & 400mm dia)at zone-II B (Mayahauri)of Joynagar-II Blockof BaruipurSub-Division, for "MegaSurface Based water supply schemeforFalta-Mathurapur, DistrictSouth24-Pgns, W/S Division-I, PHE. Dte. | AE BSD |  | ORD/000998/2022-2023 | 1073/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 0.72 | 0 | 0
1159 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF specials for layingof DIpipeat zone-II A (Mayahauri)of Joynagar-II Block of Baruipur Sub-Division, for "Mega Surface Based water supply scheme for Falta-Mathurapur, District South 24-Pgns, W/S Division-I, PHE. Dte. | AE BSD |  | ORD/000999/2022-2023 | 1072/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 3.18 | 0 | 80
1160 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II B (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD |  | ORD/001036/2022-2023 | 1065/SWD-I | 12/08/2022 | 15 | S.K. ENTERPRISE | 0.72 | 0 | 0
1161 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II A (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD |  | ORD/001037/2022-2023 | 1066/SWD-I | 12/08/2022 | 15 | S.K. ENTERPRISE | 3.18 | 0 | 0
1162 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 750 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of piped water supply scheme in Zone-I at Bainchberia Mouza of Mograhat-I Block for augmentation of Mega surface water based water supply scheme and providing Functional Household Tap connection (FHTC) in Zone-I at Bainchberia of Mograhat-I Block within Mega surface water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (No.of FHTC - 5799 Nos.) | AE SWSD-II | JE3 | ORD/000114/2023-2024 | 526/SWD-I | 11/05/2023 | 782 | RADIANT | 911.48 | 0 | 20
1163 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000130/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 35.72 | 0 | 0
1164 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Matsyakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000508/2022-2023 | 343/SMD | 08/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.58 | 0 | 0
1165 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1166 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for MATSYAKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/12045] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000232/2022-2023 | 1682/SWD-I | 01/11/2022 | 30 | ANIK ENTERPRISE | 14.96 | 0 | 1
1167 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of MATSYAKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12045) (3rd Call) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000253/2023-2024 | 1500/SWD-I | 20/07/2023 | 60 | RIDIP ENTERPRISE | 6.04 | 0 | 0
1168 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Matshyakhali PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/12045) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000271/2024-2025 | 2921/SWD-I | 25/06/2024 | 45 | BHOLANATH CONSTRUCTION (PROPRIETOR) | 91.73 | 0 | 0
1169 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "MATSYAKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000398/2022-2023 | 462/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 0 | 100
1170 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based MATSYAKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 750 nos.] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000448/2022-2023 | 2686/SWD-I | 20/01/2023 | 90 | ULTRA CONSTRUCTION | 101.39 | 0 | 60
1171 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011202] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000509/2022-2023 | 2907/SWD-I | 14/02/2023 | 15 | ANIK ENTERPRISE | 1.57 | 0 | 0
1172 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for MATSYAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011202] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000590/2022-2023 | 3110/SWD-I | 24/02/2023 | 675 | DEBASHIS DAS | 15.86 | 0 | 100
1173 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development for 1st Tubewell site at MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgns Dist. under South 24-Pgns W/S-I, PHE Dte. (SM/12045) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000867/2024-2025 | 4925/SWD-I | 03/12/2024 | 30 | SRIJON ENTERPRISE | 32 | 0 | 100
1174 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | RTOR000106/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 30.18 | 0 | 0
1175 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01105/2023-2024 | BP-2023-24-154 | 24/07/2023 | 0 | WBSEDCL | 2.26 | 0 | 0
1176 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chandipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000452/2022-2023 | 3932/SMD | 30/12/2022 | 488 | K.S.P ENTERPRISE | 11.18 | 0 | 100
1177 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Chandipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002846/2023-2024 | 1242/SMSD | 18/09/2023 | 15 | K.S.P ENTERPRISE | 0.29 | 0 | 100
1178 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000087/2022-2023 | 1199/SWD-I | 02/09/2022 | 30 | UMAR ALI KHAN | 20.06 | 0 | 100
1179 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHANDIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 472] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000096/2022-2023 | 1208/SWD-I | 02/09/2022 | 90 | M/S. SUMAN ENTERPRISE | 92.16 | 0 | 60
1180 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHANDIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012519] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000126/2022-2023 | 1294/SWD-I | 14/09/2022 | 60 | JYOTI ENTERPRISE | 5.46 | 0 | 100
1181 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHANDIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000168/2021-2022 | 1911/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
1182 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Chandipur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12046) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000336/2024-2025 | 3310/SWD-I | 23/07/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 41.61 | 0 | 0
1183 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/012519] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000788/2022-2023 | 3676/SWD-I | 29/03/2023 | 15 | UMAR ALI KHAN | 2.2 | 0 | 0
1184 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000265/2023-2024 | 2416/SWD-I | 30/09/2023 | 0 | Resource Division | 4.06 | 0 | 0
1185 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000340/2023-2024 | 269/SWD-I | 10/01/2024 | 0 | Resource Division | 2.91 | 0 | 0
1186 | Alipore Division | Baruipur Sub-Division | Road Restoration of Madarat More Riksha Stand to Najirpur Auto Stand via Kobindapur More to Vurkul Khalpar | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01736/2024-2025 | BP-2024-25-800 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.82 | 0 | 0
1187 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01961/2022-2023 | BP-2022-23-477 | 31/03/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
1188 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kapindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000277/2022-2023 | 3920/SMD | 30/12/2022 | 90 | PERFECT AIRCONDITION | 12.89 | 0 | 100
1189 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at PH-I of Dadpur Dighirpar & Kapindarpur w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000897/2023-2024 | 1O68/SMSD | 17/08/2023 | 10 | DITHI ENTERPRISE | 0.78 | 0 | 100
1190 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KAPINDAPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000089/2022-2023 | 1201/SWD-I | 02/09/2022 | 30 | BENGAL ENTERPRISE | 20.07 | 0 | 100
1191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAPINDAPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000165/2021-2022 | 1913/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
1192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KAPINDAPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 941) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000236/2022-2023 | 1711/SWD-I | 02/11/2022 | 971 | SAKTI ENTERPRISE | 224.76 | 0 | 100
1193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at KAPINDAPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012516] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000288/2022-2023 | 1784/SWD-I | 07/11/2022 | 60 | M/S. FAIZUL HAQUE BISWAS | 5.75 | 0 | 0
1194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Kapindapur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12051) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000359/2024-2025 | 3459/SWD-I | 02/08/2024 | 45 | S R ENTERPRISE (BIRBHUM) | 50.51 | 0 | 0
1195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000101/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.89 | 0 | 0
1196 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - VIII) having village with maximum 247 nos. households, Block - Canning -II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000792/2022-2023 | 6681/AD | 14/11/2022 | 90 | R.S.CONSTRUCTION CO. | 52.9 | 0 | 75
1197 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VIII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001904/2022-2023 | 5668/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.53 | 0 | 0
1198 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000173/2023-2024 | 1126/AD | 22/06/2023 | 0 | Resource Division | 1.52 | 0 | 0
1199 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00628/2023-2024 | BP-2023-24-87 | 14/06/2023 | 0 | WBSEDCL | 7.31 | 0 | 0
1200 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-I) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000586/2022-2023 | 643/SMD | 02/03/2023 | 90 | SUDIP PRADHAN | 8.82 | 0 | 100
1201 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-VIII) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000594/2022-2023 | 658/SMD | 06/03/2023 | 90 | M/S M3 SOLUTION | 8.9 | 0 | 100
1202 | Alipore Division | Canning Sub-division | Improvement & Retrofitting of UPVC pipe line (balance part) in distribution system due to damage of pipe line by widening of road by South 24 Pgs. Zilla Parishad at Improvement & Retrofitting of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000814/2022-2023 | 6809/AD | 16/11/2022 | 30 | TANMAY ROY CHOWDHURY | 60.33 | 0 | 100
1203 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 592 | TIYASHA ENTERPRISE | 96.43 | 0 | 35
1204 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Homrapolta and its adjoining Mouza W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001382/2022-2023 | 1065/CSD | 15/12/2022 | 40 | S.P. CONSTRUCTION (I) | 0.96 | 0 | 90
1205 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Homrapolta Water Supply Scheme Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001458/2021-2022 | 6071/AD | 17/02/2022 | 365 | M/S. BLUE BELL ENTERPRISE | 169.37 | 0 | 75
1206 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001676/2021-2022 | 643/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.42 | 0 | 100
1207 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001677/2021-2022 | 644/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.1 | 0 | 100
1208 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000063/2022-2023 | 3951/AD | 12/08/2022 | 0 | Resource Division | 0.86 | 0 | 0
1209 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Chhoto Banashyamnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000205/2023-2024 | 788/AD | 24/05/2023 | 566 | M/S. S.S. ENTERPRISE | 49.26 | 0 | 100
1210 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
1211 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.07.2024 to 30.09.2024 - 3 months] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000534/2024-2025 | 2523/AD | 18/06/2024 | 92 | PARBATI MONDAL | 1.2 | 0 | 100
1212 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (CHHOTO BANASHYAM NAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001039/2022-2023 | 4154/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.31 | 0 | 100
1213 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Chhoto Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001200/2023-2024 | 4077/AD | 23/11/2023 | 45 | SK SAKIL AHAMED | 33.2 | 0 | 0
1214 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Chhoto Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001201/2023-2024 | 4078/AD | 23/11/2023 | 454 | B. ENTERPRISE | 11.59 | 0 | 98
1215 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 100 cum. capacity OHR of Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002069/2023-2024 | 765(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1216 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1217 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000115/2023-2024 | 651/AD | 17/05/2023 | 0 | Resource Division | 9.93 | 0 | 0
1218 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000471/2023-2024 | 4759/AD | 19/12/2023 | 0 | Resource Division | 53.56 | 0 | 0
1219 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000575/2023-2024 | 73/AD | 03/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
1220 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Choto Banashamnagar PH-2, W/S Scheme Application No- 1007196375 Reference ID:- 106231314 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02227/2024-2025 | BP-2024-25-505 | 19/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1221 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Choto Banashyamnagar W/S Scheme PH-1 Application No:- 1007196386 Reference ID: 106231320 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02228/2024-2025 | BP-2024-25-506 | 19/12/2024 | 0 | WBSEDCL | 7.12 | 0 | 0
1222 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chhoto Banshyam Nagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000377/2022-2023 | 3781/SMD | 29/12/2022 | 90 | RMD TRADING | 19.47 | 0 | 0
1223 | Alipore Division | Canning Sub-division | Construction of OHR (100 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the JELEPARA, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000060/2023-2024 | 310/AD | 26/04/2023 | 300 | ADITYA HAZRA | 244.02 | 0 | 60
1224 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Jelepara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000216/2023-2024 | 956/AD | 06/06/2023 | 269 | INDIA CONSTRUCTION | 43.94 | 0 | 100
1225 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Jelepara Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000736/2024-2025 | 4394/AD | 05/11/2024 | 30 | SARDAR ENTERPRISE | 14.29 | 0 | 0
1226 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001579/2022-2023 | 10683/AD | 01/02/2023 | 45 | SARDAR ENTERPRISE | 8.87 | 0 | 100
1227 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001820/2022-2023 | 12335/AD | 06/03/2023 | 45 | SARDAR ENTERPRISE | 8.59 | 0 | 100
1228 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Jelepara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001884/2022-2023 | 7597/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 3.32 | 0 | 95
1229 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000041/2023-2024 | 248/AD | 24/04/2023 | 0 | Resource Division | 40.56 | 0 | 0
1230 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000162/2023-2024 | 1058/AD | 15/06/2023 | 0 | Resource Division | 4.64 | 0 | 0
1231 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/04081/2023-2024 | BP-2023-24-419 | 16/12/2023 | 0 | WBSEDCL | 7.55 | 0 | 0
1232 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jelepara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000550/2022-2023 | 476/SMD | 20/02/2023 | 865 | P.K. ENGINEERING | 19.27 | 0 | 90
1233 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Jelepara PH-1 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002510/2024-2025 | 1708/SMSD | 27/12/2024 | 15 | P.K. ENGINEERING | 0.99 | 0 | 0
1234 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Jelepara PH-2 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002511/2024-2025 | 1707/SMSD | 27/12/2024 | 15 | P.K. ENGINEERING | 0.99 | 0 | 0
1235 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of valve and UPVC column pipe etc at Jelepara PH-1 water supply scheme under SMD, P.H.E. Dte. [SM/13836] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002512/2024-2025 | 1675/A/SMSD | 20/12/2024 | 15 | P.K. ENGINEERING | 0.7 | 0 | 0
1236 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of valve and UPVC column pipe etc at Jelepara PH-2 water supply scheme under SMD, P.H.E. Dte. [SM/13836] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002513/2024-2025 | 1673-A/SMSD | 20/12/2024 | 15 | P.K. ENGINEERING | 0.7 | 0 | 0
1237 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Pump House-1 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002514/2024-2025 | 1772/SMSD | 31/12/2024 | 15 | P.K. ENGINEERING | 0.31 | 0 | 0
1238 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002515/2024-2025 | 1771/SMSD | 31/12/2024 | 15 | P.K. ENGINEERING | 0.97 | 0 | 0
1239 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Pump House-2 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002516/2024-2025 | 283/SMSD | 25/02/2025 | 15 | P.K. ENGINEERING | 0.31 | 0 | 0
1240 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-2 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002517/2024-2025 | 282/SMSD | 25/02/2025 | 15 | P.K. ENGINEERING | 0.97 | 0 | 0
1241 | Alipore Division | Canning Sub-division | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Pipes W/S Scheme for Biprodaspur Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1466] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000041/2023-2024 | 176/AD | 19/04/2023 | 300 | I.S. ENTERPRISE | 423.65 | 0 | 25
1242 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000296/2024-2025 | 2666/AD | 21/06/2024 | 45 | REZU CONSTRUCTION | 8.92 | 0 | 100
1243 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000297/2024-2025 | 2667/AD | 21/06/2024 | 45 | REZU CONSTRUCTION | 8.61 | 0 | 0
1244 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Biprodaspur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000384/2023-2024 | 1518/AD | 15/07/2023 | 45 | PURKAIT CONSTRUCTION | 43.92 | 0 | 0
1245 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Bipradaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000545/2024-2025 | 3716/AD | 12/09/2024 | 60 | I.S. ENTERPRISE | 76.62 | 0 | 0
1246 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Biprodaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001355/2023-2024 | 4427/AD | 06/12/2023 | 665 | BANGA NIRMAN | 11.91 | 0 | 80
1247 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Biprodaspur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001882/2022-2023 | 7524/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.94 | 0 | 99
1248 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000043/2023-2024 | 250/AD | 24/04/2023 | 0 | Resource Division | 45.11 | 0 | 0
1249 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000164/2023-2024 | 1048/AD | 15/06/2023 | 0 | Resource Division | 9.03 | 0 | 0
1250 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Biprodaspur PH-1 Water supply scheme under Gosaba block. Reference ID:-106763780, Application No :-1008116731 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01844/2024-2025 | BP-2024-25-470 | 18/11/2024 | 0 | WBSEDCL | 7.92 | 0 | 0
1251 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Birprosadpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000809/2022-2023 | 774/SMD | 17/03/2023 | 90 | P.K. ENGINEERING | 19.27 | 0 | 0
1252 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Ganeshnagar Zone-I W/S Scheme, Block - Namkhan for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000165/2024-2025 | 2516/AD | 15/06/2024 | 244 | M/S NAIYA & MAITY | 20.36 | 0 | 100
1253 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1092] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000311/2023-2024 | 1517/AD | 15/07/2023 | 300 | SUJAN KUMAR MISTRY | 242.27 | 0 | 30
1254 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000316/2023-2024 | 191/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
1255 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000317/2023-2024 | 193/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
1256 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000413/2024-2025 | 3064/AD | 25/07/2024 | 45 | LUCKY CONSTRUCTION (HASNABAD) | 28.53 | 0 | 0
1257 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000422/2023-2024 | 1910/AD | 01/08/2023 | 30 | MERAJUL ALAM | 19.95 | 0 | 0
1258 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000592/2024-2025 | 4057/AD | 01/10/2024 | 30 | AZAD RAHAMAN LASKAR | 8.68 | 0 | 0
1259 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-I) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001043/2022-2023 | 4156/AD | 19/08/2022 | 45 | M/S R.DUTTA & CO. | 3.02 | 0 | 100
1260 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001303/2022-2023 | 9885/AD | 10/01/2023 | 45 | MERAJUL ALAM | 38.59 | 0 | 0
1261 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
1262 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000131/2023-2024 | 667/AD | 17/05/2023 | 0 | Resource Division | 6.31 | 0 | 0
1263 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000477/2023-2024 | 4782/AD | 19/12/2023 | 0 | Resource Division | 14.38 | 0 | 0
1264 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000784/2023-2024 | 628/AD | 30/01/2024 | 0 | Resource Division | 0.62 | 0 | 0
1265 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Ganeshnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000424/2022-2023 | 3820/SMD | 29/12/2022 | 90 | M.S.C ENTERPRISE | 19.27 | 0 | 0
1266 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Durga Gobindapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000942/2023-2024 | 281(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1267 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Durga Gobindapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000943/2023-2024 | 281(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
1268 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DURGA GOBINDOPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000982/2022-2023 | 3668/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.16 | 0 | 100
1269 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Durga Gobindapur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000983/2023-2024 | 3002/AD | 26/09/2023 | 30 | BOWEX ENTERPRISE | 9.44 | 0 | 0
1270 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Durga Gobindapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13803) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001046/2024-2025 | 4967/AD | 04/12/2024 | 45 | M/S NAIYA & MAITY | 40.6 | 0 | 100
1271 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durga Gobindapur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001413/2023-2024 | 4466/AD | 08/12/2023 | 45 | SWATHI ENTERPRISE | 27.53 | 0 | 0
1272 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Durga Gobindapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001829/2022-2023 | 12098/AD | 28/02/2023 | 1200 | RELIABLE CONSTRUCTIONS | 171.03 | 0 | 33
1273 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Durga Gobindapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1176] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001830/2022-2023 | 12099/AD | 28/02/2023 | 899 | RELIABLE CONSTRUCTIONS | 162.3 | 0 | 48
1274 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
1275 | Alipore Division | Kakdwip Sub-Division | Laying 125 mm dia. UPVC pipe line for providing FHTC at Durga Gobindapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002570/2023-2024 | 513/KSD | 15/03/2024 | 20 | SOHINI ENTERPRISE | 1.99 | 0 | 100
1276 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000094/2023-2024 | 540/AD | 12/05/2023 | 0 | Resource Division | 8.38 | 0 | 0
1277 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000313/2023-2024 | 3122/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1278 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000510/2023-2024 | 4943/AD | 22/12/2023 | 0 | Resource Division | 34.01 | 0 | 0
1279 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000746/2023-2024 | 581/AD | 29/01/2024 | 0 | Resource Division | 1.5 | 0 | 0
1280 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Durga Gobindopur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000797/2022-2023 | 331/SMD | 07/02/2023 | 90 | ABHISEK ENGINEERING CONCERN | 19.36 | 0 | 0
1281 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Ramanandapur having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001127/2022-2023 | 8771/AD | 21/12/2022 | 60 | JOY GURU TRADING | 32.55 | 0 | 0
1282 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000874/2023-2024 | 781/AD | 03/02/2024 | 0 | Resource Division | 0.65 | 0 | 0
1283 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Ramanandapur Village of Ramnagar Gazipur Gram Panchyet Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000610/2022-2023 | 763/SMD | 15/03/2023 | 90 | M/S. SABITRI ENTERPRISE | 8.93 | 0 | 0
1284 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Padmapukhuria having village with maximum 90 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001125/2022-2023 | 8769/AD | 21/12/2022 | 60 | ARBINA ENTERPRISE | 32.04 | 0 | 0
1285 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000872/2023-2024 | 779/AD | 03/02/2024 | 0 | Resource Division | 0.59 | 0 | 0
1286 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Padmapukhuria Village of Karanjali Gram Panchyet Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000609/2022-2023 | 762/SMD | 15/03/2023 | 90 | SUDIP PRADHAN | 8.83 | 0 | 0
1287 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | RTOR000896/2023-2024 | 750/AD | 03/02/2024 | 0 | Resource Division | 0.53 | 0 | 0
1288 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Radhaballabhpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Diamond Harbour-I] | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000544/2022-2023 | 407/SMD | 16/02/2023 | 90 | M/S. GLOBAL POWER CONCERN | 9.25 | 0 | 0
1289 | Alipore Division | Kakdwip Sub-Division | Laying PVC and UPVC pipe line for providing FHTC at Gobindapur Abad Water Supply Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000225/2022-2023 | 3066/AD | 13/07/2022 | 30 | M/S A.K. GHATAK | 10.71 | 0 | 100
1290 | Alipore Division | Kakdwip Sub-Division | Supply, Delivery & Laying of Specials Required for Laying Rising Main & Inter - Connection Line between Tubewells in Gobindapur Abad Water Supply Scheme at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000350/2022-2023 | 335/KSD | 01/08/2022 | 20 | TANMAY ROY CHOWDHURY | 4.41 | 0 | 100
1291 | Alipore Division | Kakdwip Sub-Division | Construction of deep foundation with earth work protection in connection with construction of boundary wall at 2nd Tubewell Site of Gobindapur Abad W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000354/2022-2023 | 339/KSD | 01/08/2022 | 20 | MOUMITA ENTERPRISE | 4.75 | 0 | 100
1292 | Alipore Division | Kakdwip Sub-Division | Trial Run of distribution system including rising main for Gobindapur Abad Piped Water Supply Scheme under JJM of Pathar Pratima Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [for 3 month] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000427/2022-2023 | 130/KSD | 20/04/2022 | 91 | TANMAY ROY CHOWDHURY | 1.45 | 0 | 92
1293 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary etc for Retrofitting of Gobindapur Abad W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000441/2024-2025 | 3076/AD | 25/07/2024 | 615 | M/S B. ENTERPRISE | 90.93 | 0 | 80
1294 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur Abad W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006)(2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000451/2024-2025 | 3360/AD | 14/08/2024 | 30 | S. CHAKRABORTY AND CO. | 25.94 | 0 | 0
1295 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for retrofitting of Gobindapur Abad W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000530/2023-2024 | 354/KSD | 09/08/2023 | 562 | S.K.GOLUI | 2.17 | 0 | 100
1296 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1297 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000088/2022-2023 | 5595/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
1298 | Alipore Division | Canning Sub-division | nking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Tambuldaha (Part - I) having village with maximum 143 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000658/2022-2023 | 6164/AD | 01/11/2022 | 60 | S.C. ENTERPRISE (I) | 56.82 | 0 | 95
1299 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tambuldaha (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001913/2022-2023 | 5153/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.46 | 0 | 0
1300 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00387/2023-2024 | BP-2023-24-58 | 09/06/2023 | 0 | WBSEDCL | 1.42 | 0 | 0
1301 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Tambul Daha (Part-I) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000598/2022-2023 | 668/SMD | 09/03/2023 | 90 | SOMNATH ENTERPRISE | 8.85 | 0 | 100
1302 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/01723/2023-2024 | BP-2023-24-196 | 09/08/2023 | 0 | WBSEDCL | 5.58 | 0 | 0
1303 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Panchpara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000409/2022-2023 | 3807/SMD | 29/12/2022 | 90 | ALPHA ENTERPRISE | 22.82 | 0 | 0
1304 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
1305 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall Land development & Construction of service road at 2 nd Tube Well site for PANCHPARA PWSS to accommodate FHTC in within Mograhat-II Block for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District. (SM/13919) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000400/2024-2025 | 3689/SWD-I | 22/08/2024 | 225 | M/S UNIQUE ENTERPRISE | 18.87 | 0 | 50
1306 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHPARA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13919] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000573/2022-2023 | 3066/SWD-I | 21/02/2023 | 30 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 0 | 100
1307 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, Construction of Approach Road, Earth Filling, Drum Sheet walling for PANCHPARA Head Work Site to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Div-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/13919) [2nd call] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000771/2024-2025 | 4553/SWD-I | 06/11/2024 | 175 | KANAK GIRI | 35.53 | 0 | 70
1308 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Panchpara Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000975/2022-2023 | 1428/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
1309 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000197/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 30.38 | 0 | 0
1310 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Dhaspara (Zone-I and II) (SM/15221), Ghoramara (SM/14988) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000020/2025-2026 | 2006/AD | 28/04/2025 | 30 | ROY CHOWDHURY ASSOCIATES | 7.24 | 0 | 100
1311 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Ghoramara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14988) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000143/2024-2025 | 2481/AD | 14/06/2024 | 292 | M/S. JHARNA ENTERPRISE | 71.83 | 0 | 100
1312 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Ghoramara W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001000/2023-2024 | 507/KSD | 03/10/2023 | 7 | M/S. JHARNA ENTERPRISE | 3.87 | 0 | 100
1313 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001174/2023-2024 | 1037/AD | 13/06/2023 | 45 | M/S. JHARNA ENTERPRISE | 39.71 | 0 | 100
1314 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001531/2022-2023 | 11021/AD | 08/02/2023 | 45 | HARIDAS DUTTA | 47.07 | 0 | 92
1315 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001745/2022-2023 | 11554/AD | 17/02/2023 | 685 | M/S. JHARNA ENTERPRISE | 197.94 | 0 | 100
1316 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Shibpur Zone - I & II, Ghoramara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002175/2023-2024 | 954/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.61 | 0 | 100
1317 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002180/2023-2024 | 816/AD | 05/02/2024 | 363 | TAPAS KUMAR PRADHAN | 11.71 | 0 | 100
1318 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002428/2023-2024 | 1458/AD | 11/03/2024 | 295 | ADRIJA ENTERPRISE | 31.62 | 0 | 100
1319 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000527/2023-2024 | 12/AD | 02/01/2024 | 0 | Resource Division | 7.67 | 0 | 0
1320 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000973/2023-2024 | 1766/AD | 27/03/2024 | 0 | Resource Division | 30.41 | 0 | 0
1321 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, of Ghoramara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000352/2022-2023 | 3756/SMD | 29/12/2022 | 90 | NITESH MANAGEMENT | 23.19 | 0 | 60
1322 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of submersible pumping machinery for PH-1 of Ghoramara W/S Scheme under South 24Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000550/2023-2024 | 569/AE-I/SMD. | 11/05/2023 | 15 | NITESH MANAGEMENT | 0.65 | 0 | 100
1323 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of automatic chlorinator for PH-2 of Ghoramara W/S Scheme under South 24Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2023-2024 | 568/AE-I/SMD. | 11/05/2023 | 15 | NITESH MANAGEMENT | 1 | 0 | 100
1324 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at PH-1&2 of Ghoramara W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001788/2023-2024 | 1030/AE-I/SMD | 20/09/2023 | 15 | GHOSH ENTERPRISE | 0.82 | 0 | 100
1325 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of pumping accessories at PH-2 of Ghoramara W/S Scheme under JJM under South 24-Pgs Mechanical Division, PHE Dte. [Block- Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002033/2023-2024 | 680-AE-I-SMD | 21/06/2023 | 15 | NITESH MANAGEMENT | 0.23 | 0 | 98
1326 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of pumping accessories at PH-1 of Ghoramara W/S Scheme under JJM under South 24-pgs Mechanical Division, PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002034/2023-2024 | 681-AE-I-SMD | 21/06/2023 | 15 | NITESH MANAGEMENT | 0.23 | 0 | 98
1327 | Alipore Division | Diamond Harbour Sub-Division | Trial Run of existing distribution system (CI/DI/UPVC/HDPE) and other allied works for Falta Zone-IX under Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000823/2024-2025 | 4505/AD | 11/11/2024 | 90 | SRIJON ENTERPRISE | 28.97 | 0 | 0
1328 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IX at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001379/2024-2025 | 5524/AD | 28/12/2024 | 90 | SRIJON ENTERPRISE | 36.85 | 0 | 0
1329 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IX of Falta block | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001392/2022-2023 | 10864/AD | 04/02/2023 | 810 | SRIJON ENTERPRISE | 340.8 | 0 | 85
1330 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IX at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001408/2024-2025 | 5534/AD | 30/12/2024 | 60 | SRIJON ENTERPRISE | 14.92 | 0 | 0
1331 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000434/2023-2024 | 3617/AD | 30/10/2023 | 0 | Resource Division | 3.08 | 0 | 0
1332 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000618/2023-2024 | 279/AD | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
1333 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for New service connection at Dihi Medan Malla-I | AE BSD,Assistant Engineer | Junior Engineer | BILL/00211/2024-2025 | BP-2024-25-67 | 16/05/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
1334 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at Pump house no-2 of Dihi Medan Malla. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00212/2024-2025 | BP-2024-25-67 | 16/05/2024 | 0 | WBSEDCL | 2.95 | 0 | 0
1335 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2for Augmentation of Dehimedan Malla water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000012/2023-2024 | 947/SMD | 04/04/2023 | 90 | SARKAR ELECTRICAL | 22.31 | 0 | 40
1336 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of DEHI MADAN MOLLA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2670] [TSM/018699] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 473/SWD-I | 04/05/2023 | 782 | BISWAS ENTERPRISE | 312.42 | 0 | 70
1337 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, pipeline protection development of land and other allied works for Ground water based DEHI MEDAN MALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14856) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000340/2024-2025 | 3314/SWD-I | 23/07/2024 | 45 | BISWAS ENTERPRISE | 95.68 | 0 | 0
1338 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DEHI MEDAN MALLA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018699] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000622/2022-2023 | 3245/SWD-I | 01/03/2023 | 30 | RUBY ENTERPRISE | 31.65 | 0 | 0
1339 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head Work site for DEHIMEDAN MALLA PWSS to acccommodate FHTC in BARUIPUR block under South 24-Parganas W/S Division-I, South 24-Pgns district for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/14856] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000870/2023-2024 | 1327/SWD-I | 15/03/2024 | 15 | G.M. ENTERPRISE (MURSHIDABAD) | 15.8 | 0 | 100
1340 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dehimedan Malla Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000930/2022-2023 | 1220/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.63 | 0 | 100
1341 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DEHI MEDAN MALLA Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14856] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001151/2024-2025 | 369/SWD-I | 04/02/2025 | 30 | SIMPLEX DRILLING COMPANY | 15.8 | 0 | 0
1342 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000100/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 54.56 | 0 | 0
1343 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Teurhat ( Zone-41) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000008/2023-2024 | 943/SMD | 04/04/2023 | 1184 | DAS ENTERPRISE | 52.78 | 0 | 40
1344 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of TeurhatW/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000083/2025-2026 | 696/SMSD | 15/05/2025 | 15 | DAS ENTERPRISE | 0.93 | 0 | 0
1345 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-4 of TeurhatW/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000084/2025-2026 | 697/SMSD | 15/05/2025 | 15 | DAS ENTERPRISE | 0.93 | 0 | 0
1346 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-2,3 & 4 of Teurhat (Zone-41) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14862) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001829/2024-2025 | 417/SMSD | 20/03/2025 | 15 | DAS ENTERPRISE | 0.88 | 0 | 0
1347 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head Work site for TEURHAT (ZONE-41) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000299/2024-2025 | 3180/SWD-I | 15/07/2024 | 15 | PADMA ENGINEERING CO. | 15.9 | 0 | 100
1348 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (three) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd, 3rd and 4th Tubewell sites at TEURHAT Piped Water Supply Scheme to accommodate FHTC in Baruipur block under South 24-Pgns. W/S Division-I, PHE Dte. for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/14862] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000532/2024-2025 | 4078/SWD-I | 19/09/2024 | 194 | DEV & COMPANY | 47.69 | 0 | 100
1349 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Four nos.) at TEURHAT piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14862) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000683/2024-2025 | 4478/SWD-I | 30/10/2024 | 330 | R.K ENTERPRISE | 19.65 | 0 | 100
1350 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEURHAT PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000719/2023-2024 | 362/SWD-I | 16/01/2024 | 45 | SAIKAT ENTERPRISE | 63.59 | 0 | 0
1351 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEURHAT MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2688] [TSM/018362] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000802/2022-2023 | 3693/SWD-I | 30/03/2023 | 90 | PATHIK PABAN NANDI | 428.89 | 0 | 85
1352 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based TEAUR HAT Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000918/2022-2023 | 1169/SWD-I | 30/08/2022 | 30 | ASTER CONSULTANCY | 3.12 | 0 | 100
1353 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000150/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 21.65 | 0 | 0
1354 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-VII, Ajodhyanagar (OHR Cap-450 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000308/2021-2022 | 2606/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 1.98 | 0 | 100
1355 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-VII AT AJODHYANAGAR of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 3427 Nos.) | AE SWSD-II | JE1 | ORD/000515/2022-2023 | 2881/SWD-I | 13/02/2023 | 998 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 379.95 | 0 | 79
1356 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of chlorination room, land development, repairing and renovation boundary wall and other allied works for Zone-VII (Ajodhyanagar) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | AE SWSD-II | JE1 | ORD/000742/2024-2025 | 4640/SWD-I | 14/11/2024 | 75 | M/S SHIBAM ENTERPRISE | 130.62 | 0 | 2
1357 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000125/2022-2023 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 20.45 | 0 | 0
1358 | Alipore Division | Diamond Harbour Sub-Division | Restoration and Relaying of pipe line (damaged portion) by MS pipe in distribution system (Node Point- 3 to 5, 9 to 12, 12 to 13, 13 to 23) at Falta Zone-III within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000081/2025-2026 | 2422/AD | 23/05/2025 | 30 | SRIJON ENTERPRISE | 6.15 | 0 | 0
1359 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-II at Falta block for providing balance pipe lying works, House Hold Tap connection, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000822/2024-2025 | 780/AD | 25/02/2025 | 225 | M/S PARAMESWAR CHOWDHURY | 80.38 | 0 | 75
1360 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIA at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001375/2024-2025 | 5520/AD | 28/12/2024 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 35.51 | 0 | 0
1361 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-III of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001537/2023-2024 | 438/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
1362 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Zone-III of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001923/2022-2023 | 12712/AD | 14/03/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 138.23 | 0 | 70
1363 | Alipore Division | Diamond Harbour Sub-Division | Additional laying distribution system at Gazipur and Shibanipur Mouza for covering the command area of Falta Zone-III due to avoiding NH crossings of pipelines under Falta Zone-VII for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001974/2022-2023 | 12593/AD | 13/03/2023 | 646 | JOY GURU TRADING | 28.35 | 0 | 100
1364 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000360/2023-2024 | 3224/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1365 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000849/2023-2024 | 787/AD | 03/02/2024 | 0 | Resource Division | 12.32 | 0 | 0
1366 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000926/2023-2024 | 1268/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
1367 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000041/2025-2026 | 2031/AD | 29/04/2025 | 60 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 82 | 0 | 0
1368 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VI of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001051/2022-2023 | 301/DHSD | 15/09/2022 | 30 | MEASURE LAND | 2.83 | 0 | 0
1369 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000345/2023-2024 | 3209/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1370 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000893/2023-2024 | 747/AD | 03/02/2024 | 0 | Resource Division | 20.38 | 0 | 0
1371 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000915/2023-2024 | 1257/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
1372 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Chak Balaibag water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000512/2022-2023 | 351/SMD | 09/02/2023 | 90 | S.P. CONSTRUCTION | 33.46 | 0 | 0
1373 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for initial 50% amount of the estimated cost Rs 17288159.00(Rupees one crore seventy two lakh eighty eight thousand one hundred fifty nine only) i.e. Rs 8644079.50 round off Rs 8644080.00( Rupees eighty six lakh forty four thousand eighty only) toward road restoration work of Keorapukur Julpia, Pailan Nepalgunj & Amgachiya Health Centre Road under Chak Balaibag, Bakeswar, Kismat Karimpur & Kastamahal Pipe Water Supply Scheme in Bishnupur-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/00346/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 86.44 | 0 | 0
1374 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of CHAK BALAIBAG AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000234/2021-2022 | 1974/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 3.1 | 0 | 100
1375 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for CHAK BALAIBAG PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2793) [TSM/016350]. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000719/2022-2023 | 3564/SWD-I | 22/03/2023 | 90 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 414.08 | 0 | 32
1376 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, approach road, land development, protection of pipeline and road restoration for CHAK BALAIBAG Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/13783) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000741/2024-2025 | 4639/SWD-I | 14/11/2024 | 60 | M/S SHIBAM ENTERPRISE | 138.16 | 0 | 0
1377 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000087/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 49.73 | 0 | 0
1378 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Gopalkata W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000124/2023-2024 | 570/AD | 12/05/2023 | 15 | M/S MANGALCHANDI CONSTRUCTION | 7.59 | 0 | 0
1379 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000215/2023-2024 | 955/AD | 06/06/2023 | 57 | SALMAN CONSTRUCTION | 43.94 | 0 | 100
1380 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Gopalkata piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 888] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000295/2023-2024 | 3732/AD | 03/11/2023 | 300 | CHAKRABORTTI ENTERPRISE | 258.61 | 0 | 55
1381 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Sitefor Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000737/2024-2025 | 4395/AD | 05/11/2024 | 45 | SUBHO CONSTRUCTION | 32.48 | 0 | 0
1382 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No- 2 for Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000738/2024-2025 | 4407/AD | 05/11/2024 | 30 | M/S. BISWAS CONSTRUCTION(I) | 19.52 | 0 | 0
1383 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gopalkata New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001883/2022-2023 | 7596/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 3.28 | 0 | 95
1384 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002045/2022-2023 | 13045/AD | 24/03/2023 | 45 | BINAPANI ENTERPRISE | 8.92 | 0 | 0
1385 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002046/2022-2023 | 13046/AD | 24/03/2023 | 708 | BINAPANI ENTERPRISE | 8.61 | 0 | 100
1386 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000062/2023-2024 | 382/AD | 02/05/2023 | 0 | Resource Division | 11.74 | 0 | 0
1387 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gopalkata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000549/2022-2023 | 475/SMD | 20/02/2023 | 90 | P.K. ENGINEERING | 19.27 | 0 | 0
1388 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Additional quotation for new service connection at Rammakhalerchak PWSS P.H. No. I under Bishnupur- I Block. Ref. ID- 860294797, Application ID- 100000102977 Application date- 18/03/2024 | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00393/2024-2025 | BP-2024-25-102 | 10/06/2024 | 0 | WBSEDCL | 0.28 | 0 | 0
1389 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/04615/2023-2024 | BP-2023-24-476 | 02/02/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
1390 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rammakhaler Chak water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000513/2022-2023 | 352/SMD | 09/02/2023 | 90 | S.P. CONSTRUCTION | 23.29 | 0 | 0
1391 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of RAMMAKHALER CHAK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 1749) [TSM/016316]. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000076/2023-2024 | 390/SWD-I | 28/04/2023 | 734 | MALAY KANTI DEY | 261.78 | 0 | 61
1392 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1393 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design, construction of Boundary wall, Pump House for RAMMAKHALER CHAK PWSS of Bishnupur-I Block under South 24 Parganas W/S Division-I, PHE Dte., Dist.-South 24 Parganas. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000275/2024-2025 | 2925/SWD-I | 25/06/2024 | 300 | M/S SUBHODEEP ENTERPRISE | 140.22 | 0 | 0
1394 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional distribution pipeline, Construction of approach road, protection of pipeline and other allied works for Rammakhaler Chak PWSS of Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (SM/13784) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000414/2024-2025 | 3730/SWD-I | 27/08/2024 | 45 | MALAY KANTI DEY | 65.01 | 0 | 4
1395 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of RAMMAKHALER CHAK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000421/2021-2022 | 1973/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.83 | 0 | 0
1396 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000552/2022-2023 | 3041/SWD-I | 20/02/2023 | 30 | PADMA ENGINEERING CO. | 15.9 | 0 | 0
1397 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000601/2022-2023 | 3129/SWD-I | 24/02/2023 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 0 | 98
1398 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 2nd Tubewell site of Rammakhaler Chak Piped Water Supply Scheme under proposed ground water based Rammakhaler Chak PWSS to accommodate FHTC in Bishnupur-I Block, District-South 24-Pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/13784) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000756/2023-2024 | 656/SWD-I | 06/02/2024 | 15 | N ENTERPRISE | 3.97 | 0 | 0
1399 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000119/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 36.66 | 0 | 0
1400 | Alipore Division | Kakdwip Sub-Division | Fuel charges bill for M.V Sidheswari for the month of Dec'22 to March'23. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/03229/2023-2024 | BP-2023-24-1215 | 20/03/2024 | 0 | RAJKUMAR MANNA | 13.72 | 0 | 0
1401 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Piprakhali PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000189/2024-2025 | 924/AD | 05/03/2025 | 60 | M/S PARAMESWAR CHOWDHURY | 55.38 | 0 | 0
1402 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Buraburirtat PWSS, Mouza - Sitarampur, Burabuirtat, Gobardhanpur; Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13801) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000342/2024-2025 | 2754/AD | 27/06/2024 | 90 | GROWING CONCERN | 99.12 | 0 | 0
1403 | Alipore Division | Kakdwip Sub-Division | Laying pipe line for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000617/2023-2024 | 2315/AD | 17/08/2023 | 60 | GROWING CONCERN | 131.1 | 0 | 10
1404 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying D.I. Pipe Line including design & drawing of foundation after soil investigation for Buraburirtat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13801) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000644/2024-2025 | 4147/AD | 05/10/2024 | 270 | GROWING CONCERN | 147.24 | 0 | 18
1405 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000664/2024-2025 | 1176/KSD | 26/07/2024 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
1406 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000671/2024-2025 | 1177/KSD | 26/07/2024 | 184 | PIKASU BOSE | 2.4 | 0 | 0
1407 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Buraburirtat W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000721/2023-2024 | 2538/AD | 28/08/2023 | 30 | ANANTA KUMAR GIRI | 5.32 | 0 | 100
1408 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BURABURIR TAT PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001035/2022-2023 | 3665/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.89 | 0 | 100
1409 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001042/2023-2024 | 325/KSD | 31/07/2023 | 184 | BADSHA ALOM | 2.4 | 0 | 30
1410 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001044/2023-2024 | 326/KSD | 31/07/2023 | 184 | PIKASU BOSE | 2.4 | 0 | 100
1411 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001061/2023-2024 | 3379/AD | 11/10/2023 | 45 | SUDIP PRADHAN | 33.31 | 0 | 0
1412 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001062/2023-2024 | 3380/AD | 11/10/2023 | 30 | M/S BHUNIA ENTERPRISE | 11.77 | 0 | 0
1413 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 03.12.2022 to 30.11.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001085/2022-2023 | 563/KSD | 02/12/2022 | 363 | RUPAK DAS MAHAPATRA | 4.8 | 0 | 20
1414 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001090/2022-2023 | 321/KSD | 26/07/2022 | 184 | PIKASU BOSE | 2.4 | 0 | 95
1415 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 184 | BADSHA ALOM | 2.4 | 0 | 0
1416 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2022 to 30.11.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001092/2022-2023 | 537/KSD | 23/11/2022 | 365 | RAJKUMAR MANNA | 4.36 | 0 | 20
1417 | Alipore Division | Kakdwip Sub-Division | Laboratory Maintenance of Kakdwip Sub - District Water Testing Laboratory under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte.(Period from 08.09.2022 to 07.09.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001093/2022-2023 | 399/KSD | 05/09/2022 | 365 | ANANTA KUMAR GIRI | 0.69 | 0 | 100
1418 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001280/2022-2023 | 9592/AD | 03/01/2023 | 45 | M/S. BOSE CONCERN | 48.69 | 0 | 100
1419 | Alipore Division | Kakdwip Sub-Division | Laying Rising Main and construction of 02 nos. Pump House for providing FHTC for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001423/2023-2024 | 4602/AD | 14/12/2023 | 422 | BISWAJIT SAMANTA | 21.27 | 0 | 100
1420 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001995/2023-2024 | 468/KSD | 22/09/2023 | 30 | M/S R.DUTTA & CO. | 4.34 | 0 | 100
1421 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1422 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002531/2023-2024 | 711/KSD | 30/11/2023 | 91 | RUPAK DAS MAHAPATRA | 1.2 | 0 | 0
1423 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002532/2023-2024 | 260/KSD | 31/01/2024 | 182 | PIKASU BOSE | 2.4 | 0 | 0
1424 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 60 | CHANDAN ROY | 60.06 | 0 | 0
1425 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002898/2024-2025 | 204/KSD | 24/01/2025 | 181 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
1426 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002948/2023-2024 | 325(A)/KSD | 31/07/2023 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
1427 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002958/2024-2025 | 227/KSD | 28/01/2025 | 181 | PIKASU BOSE | 2.4 | 0 | 0
1428 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003030/2023-2024 | 259(A)/KSD | 31/01/2024 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
1429 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000301/2023-2024 | 3096/AD | 28/09/2023 | 0 | Resource Division | 20.07 | 0 | 0
1430 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000678/2023-2024 | 444/AD | 24/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
1431 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000769/2023-2024 | 603/AD | 29/01/2024 | 0 | Resource Division | 9.54 | 0 | 0
1432 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Bura burir Tat W/S Scheme PH-2 Application No:- 1007954078 Reference ID:- 106682238 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01131/2024-2025 | BP-2024-25-228 | 08/08/2024 | 0 | WBSEDCL | 1.14 | 0 | 0
1433 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Bura burir Tat PH-1 W/S Scheme Application No:- 1007911206 Reference ID: 106659346 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01132/2024-2025 | BP-2024-25-229 | 08/08/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
1434 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Buraburir Tat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000360/2022-2023 | 3763/SMD | 29/12/2022 | 90 | BIJAN ENTERPRISE | 21.42 | 0 | 0
1435 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000318/2023-2024 | 195/KSD | 22/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
1436 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000319/2023-2024 | 198/KSD | 23/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
1437 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000414/2024-2025 | 3065/AD | 25/07/2024 | 45 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 28.86 | 0 | 0
1438 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000423/2023-2024 | 1911/AD | 01/08/2023 | 30 | IQBAL CONSTRUCTION | 19.77 | 0 | 92
1439 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000843/2024-2025 | 4578/AD | 15/11/2024 | 30 | M/S DEB ENTERPRISE | 8.56 | 0 | 0
1440 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001304/2022-2023 | 9886/AD | 10/01/2023 | 45 | IQBAL CONSTRUCTION | 38.59 | 0 | 0
1441 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001341/2022-2023 | 3799/AD | 05/08/2022 | 45 | M/S R.DUTTA & CO. | 3.69 | 0 | 100
1442 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1366] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001546/2022-2023 | 11020/AD | 08/02/2023 | 300 | SUJATA CONSTRUCTION | 313.36 | 0 | 48
1443 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Ganeshnagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002077/2023-2024 | 774(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1444 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
1445 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000478/2023-2024 | 4782/AD | 19/12/2023 | 0 | Resource Division | 22.81 | 0 | 0
1446 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000557/2023-2024 | 45/AD | 03/01/2024 | 0 | Resource Division | 8.11 | 0 | 0
1447 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000981/2023-2024 | 1774/AD | 27/03/2024 | 0 | Resource Division | 1.41 | 0 | 0
1448 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01118/2023-2024 | BP-2023-24-160 | 24/07/2023 | 0 | WBSEDCL | 8.32 | 0 | 0
1449 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Ganeshnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000425/2022-2023 | 3821/SMD | 29/12/2022 | 824 | S.K. ENTERPRISE | 19.67 | 0 | 30
1450 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at Zone-II PH No-1 of Ganeshnagar W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000751/2025-2026 | 307-AE-II-SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 100
1451 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at Zone-II PH No-2 of Ganeshnagar W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000806/2025-2026 | 308-AE-II/SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 0
1452 | S24 Pgns Mechanical | Kakdwip Sub-Division | Addditional work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 Zone-II of Ganeshnagar W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001895/2023-2024 | 1182/SMD | 22/03/2024 | 21 | S.K. ENTERPRISE | 16.8 | 0 | 100
1453 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-B) [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000307/2023-2024 | 1510/AD | 15/07/2023 | 90 | M/S ANUBHAB CONSTRUCTION | 117.97 | 0 | 86
1454 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Budhakhali Zone-2 PWSS, Block -Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14123) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000307/2024-2025 | 2681/AD | 24/06/2024 | 285 | ASHOKA ENTERPRISE | 156 | 0 | 80
1455 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-A) [No. of FHTC = 150] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000310/2023-2024 | 1513/AD | 15/07/2023 | 90 | SUNNY ELECTRIC CO. | 124.9 | 0 | 60
1456 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000403/2023-2024 | 1902/AD | 01/08/2023 | 45 | M/S. SONAMONI ENTERPRISE | 11.48 | 0 | 71
1457 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000404/2023-2024 | 1903/AD | 01/08/2023 | 45 | S.MITRA & CO. | 11.16 | 0 | 0
1458 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000405/2023-2024 | 1904/AD | 01/08/2023 | 45 | M/S BABUSONA ENTERPRISE | 14.66 | 0 | 100
1459 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Budhakhali Zone-II (Part- II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001772/2022-2023 | 12045/AD | 27/02/2023 | 45 | M/S MAITY CONSTRUCTION | 38.49 | 0 | 60
1460 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Budhakhali [Zone-II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001811/2022-2023 | 06/AD | 01/04/2022 | 45 | M/S R.DUTTA & CO. | 7.3 | 0 | 95
1461 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone - II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) [No. of FHTC = 645] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001827/2022-2023 | 12100/AD | 28/02/2023 | 763 | ASHOKA ENTERPRISE | 334.36 | 0 | 94
1462 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Budhakhali Zone - II (Part - I & II) W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002052/2023-2024 | 513/AD | 25/01/2024 | 45 | BARUN KANTI PAUL | 27.79 | 0 | 100
1463 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Budhakhali Zone - II (Part - I & II) W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002053/2023-2024 | 514/AD | 25/01/2024 | 310 | R G ENTERPRISE (III) | 9.49 | 0 | 100
1464 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Budhakhali Zone-II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002065/2023-2024 | 759/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1465 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
1466 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Budhakhali Zone-II Part W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14123) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002186/2024-2025 | 2067/KSD | 28/12/2024 | 20 | IMAGINEER VENTURES | 2.43 | 0 | 0
1467 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I and II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002289/2023-2024 | 1027/AD | 19/02/2024 | 45 | M/S. BRINDABAN DAS & SONS | 27.81 | 0 | 51
1468 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000489/2023-2024 | 4788/AD | 19/12/2023 | 0 | Resource Division | 22.85 | 0 | 0
1469 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000551/2023-2024 | 34/AD | 02/01/2024 | 0 | Resource Division | 9.29 | 0 | 0
1470 | S24 Pgns Mechanical | Kakdwip Sub-Division | Budhakhali PH-1 Zone-2 Part-2 Water supply scheme Application No- 1007943437 Reference ID- 106679061 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/01051/2024-2025 | BP-2024-25-209 | 30/07/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
1471 | S24 Pgns Mechanical | Kakdwip Sub-Division | Budhakhali PH-2 Zone-2 Part-2 Water supply scheme Application No- 1007943363 Reference ID- 106679063 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/01052/2024-2025 | BP-2024-25-210 | 30/07/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
1472 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II for Augmentation of Budhakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000803/2022-2023 | 3976/SMD | 30/12/2022 | 90 | SHIVAM ENTERPRISE | 22.25 | 0 | 95
1473 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-II, PH-2 of Budhakhali W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/14123) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002213/2024-2025 | 1360-AE-II-SMD | 20/11/2024 | 15 | SHIVAM ENTERPRISE | 0.9 | 0 | 0
1474 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile cap for OHR etc. at Indranarayanpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13827) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000195/2024-2025 | 4553/AD | 13/11/2024 | 75 | M/S R.K.ENTERPRISE (SALBAGAN) | 86.17 | 0 | 0
1475 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Indranarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000380/2023-2024 | 1773/AD | 26/07/2023 | 45 | SAHANA CO.OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 18.85 | 0 | 30
1476 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRANARAYANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000987/2022-2023 | 3673/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.65 | 0 | 100
1477 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Indranarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001479/2022-2023 | 10987/AD | 07/02/2023 | 300 | M/S R.K.ENTERPRISE (SALBAGAN) | 285.27 | 0 | 40
1478 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indranarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002046/2023-2024 | 528/AD | 25/01/2024 | 45 | SAHANA CO.OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 25.76 | 0 | 0
1479 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indranarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002047/2023-2024 | 529/AD | 25/01/2024 | 30 | DEVAM ENTERPRISE | 9.58 | 0 | 0
1480 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
1481 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000104/2023-2024 | 640/AD | 17/05/2023 | 0 | Resource Division | 6.59 | 0 | 0
1482 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000307/2023-2024 | 3102/AD | 28/09/2023 | 0 | Resource Division | 23.04 | 0 | 0
1483 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000748/2023-2024 | 583/AD | 29/01/2024 | 0 | Resource Division | 2.74 | 0 | 0
1484 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000943/2023-2024 | 1677/AD | 22/03/2024 | 0 | Resource Division | 11.9 | 0 | 0
1485 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Indranarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000796/2022-2023 | 283/SMD | 01/02/2023 | 90 | S.R. CONCERN | 19.27 | 0 | 0
1486 | Alipore Division | Canning Sub-division | Restoration of Kolkata Basanti Road from 59.00 km to 68.00km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01322/2024-2025 | BP-2024-25-626 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 38.98 | 0 | 0
1487 | Alipore Division | Canning Sub-division | Laying damaged pipeline (balance portion) under Atharabeki Water Supply Scheme, due to widening and strengthening of Basanti-Kolkata Road within Dhuri Bus Stop and Fakirtakia, Block-Canning - II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000113/2021-2022 | 1196/AD | 07/07/2021 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 48.88 | 0 | 95
1488 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Atharabeki Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000262/2023-2024 | 1450/AD | 13/07/2023 | 90 | SAMSUL ENTERPRISE | 105.53 | 0 | 0
1489 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Atharabeki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001322/2022-2023 | 9784/AD | 07/01/2023 | 45 | KALPANA BUILDERS (II) | 39.97 | 0 | 100
1490 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Atharabeki W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001667/2022-2023 | 11479/AD | 15/02/2023 | 30 | SATYAM CONSTRUCTION | 19.55 | 0 | 100
1491 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabeki W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001685/2022-2023 | 11492/AD | 15/02/2023 | 315 | RAHUL ENTERPRISE | 7.05 | 0 | 100
1492 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000004/2023-2024 | 119/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
1493 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000139/2023-2024 | 856/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
1494 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000733/2023-2024 | 557/AD | 25/01/2024 | 0 | Resource Division | 73.82 | 0 | 0
1495 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/04678/2023-2024 | BP-2023-24-509 | 12/02/2024 | 0 | WBSEDCL | 4.2 | 0 | 0
1496 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Athrabaki water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000038/2023-2024 | 993/SMD | 06/04/2023 | 90 | MUKHERJEE ART CENTRE | 11.1 | 0 | 95
1497 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Atharabaki PH-5, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001964/2024-2025 | 1086/SMSD | 31/07/2024 | 15 | MUKHERJEE ART CENTRE | 0.88 | 0 | 0
1498 | Alipore Division | Canning Sub-division | Restoration of Jhorer more to Khuribhanga pumping station Road under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01324/2024-2025 | BP-2024-25-621 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 20.08 | 0 | 0
1499 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (449 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Maukhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000222/2023-2024 | 1027/AD | 13/06/2023 | 45 | JAMIRUL CONSTRUCTION | 57.91 | 0 | 50
1500 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation at Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001025/2024-2025 | 4935/AD | 03/12/2024 | 30 | KALIDAS ENTERPRISE | 17.41 | 0 | 0
1501 | Alipore Division | Canning Sub-division | Additional work of construction of concrete road from main road to reservoir site of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001581/2020-2021 | 981/CSD | 09/11/2020 | 20 | RIVER BENZ CONSTRUCTION | 1.93 | 0 | 90
1502 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001691/2022-2023 | 11622/AD | 18/02/2023 | 45 | SRI DURGA ENTERPRISE | 7.05 | 0 | 100
1503 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001692/2022-2023 | 11623/AD | 18/02/2023 | 45 | SRI DURGA ENTERPRISE | 7.05 | 0 | 100
1504 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V & VI of Augmentation of Moukhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001694/2022-2023 | 11625/AD | 18/02/2023 | 45 | M/S MARIYA ENTERPRISES | 39.17 | 0 | 100
1505 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Moukhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002059/2023-2024 | 1305/AD | 04/03/2024 | 30 | GANGA TUBEWELL AND HARDWARE | 2.82 | 0 | 0
1506 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 6 at Ground Water Based Augmentation Piped Water Supply Scheme of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002488/2024-2025 | 770/AD | 25/02/2025 | 30 | SMART SOLUTION | 6.99 | 0 | 0
1507 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000072/2023-2024 | 550/AD | 25/01/2024 | 0 | Resource Division | 79.87 | 0 | 0
1508 | S24 Pgns Mechanical | Canning Sub-division | Quatation for new service (power) connection at Moukhali PH-1 Water supply scheme under Canning-I block Reference ID-106692521, Application No-1007977259 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01362/2024-2025 | BP-2024-25-327 | 31/08/2024 | 0 | WBSEDCL | 13.36 | 0 | 0
1509 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Moukhali , PH-5 under Canning -I block (REF ID : 106673103) (APP ID: 1007938965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01470/2024-2025 | BP-2024-25-365 | 11/09/2024 | 0 | WBSEDCL | 9.9 | 0 | 0
1510 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Laxminarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000046/2023-2024 | 1042/SMD | 17/04/2023 | 1166 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 30
1511 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00664/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
1512 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 106/SWD-I | 10/04/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 0
1513 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/05/2025 to 29/10/2025] [Vehicle No- WB-05-4231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 1153/SWD-I | 28/04/2025 | 182 | PALASH DAS | 0.86 | 0 | 0
1514 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of LAKSHMINARAYANPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2868] [TSM/018292] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000102/2023-2024 | 472/SWD-I | 04/05/2023 | 1080 | M/S A.B. ENTERPRISE | 389.11 | 0 | 60
1515 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for LAKSHMINARAYANPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018292] (2nd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000117/2023-2024 | 529/SWD-I | 11/05/2023 | 30 | N.A. ENTERPRISE | 47.62 | 0 | 30
1516 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14873) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000737/2024-2025 | 4635/SWD-I | 14/11/2024 | 45 | ALISHA CONSTRUCTION | 87.6 | 0 | 0
1517 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/11/2024 to 30/04/2025] [Vehicle No- WB-05-4231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000875/2024-2025 | 4425/SWD-I | 28/10/2024 | 182 | PALASH DAS | 0.86 | 0 | 0
1518 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Lakshminarayanpur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000960/2022-2023 | 1330/SWD-I | 15/09/2022 | 30 | GEO SOLUTION | 2.7 | 0 | 100
1519 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000094/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 71.11 | 0 | 0
1520 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for Initial 50% of Rs 18504950.00 (Rupees One Crore Eighty Five lakh Four Thousand Nine Hu8ndred Fifty only) i.e. Rs. 9252475.00 (Rupees Ninety two lakh Fifty Two Thousand Four Hundred seventy Five only) For road restoration, damaged due to laying of pipeline at Usthi Sirakol, Sirakol Amratala, Usthi Deula roads and road crossings under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (TSM/014912, SM/14729) | AE SWSD-II | JE4 | BILL/00593/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 92.52 | 0 | 0
1521 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
1522 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-VIII (Khelarampur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14729] | AE SWSD-II | JE4 | ORD/000289/2024-2025 | 3105/SWD-I | 09/07/2024 | 241 | M/S. S.S. ENTERPRISE (NODAKHALI) | 426.02 | 0 | 20
1523 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the main road towards the OHR Site (From Sirakole road to Pranab Sardar's house) of Zone-8 of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000340/2021-2022 | 1233/SWD-I | 12/11/2021 | 15 | J. ENTERPRISE | 4.81 | 0 | 100
1524 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the main road towards the OHR Site (From Samsuddin Mondal's house to Zone 8 OHR site) of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000341/2021-2022 | 1234/SWD-I | 12/11/2021 | 15 | J. ENTERPRISE | 4.73 | 0 | 100
1525 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the OHR Site of Zone-8 to Paschim Khelarampur F.P. School of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000342/2021-2022 | 1236/SWD-I | 12/11/2021 | 15 | S.P. ENTERPRISE | 4.8 | 0 | 100
1526 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-VIII (Khelarampur) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II | JE4 | ORD/000344/2021-2022 | 2693/SWD-I | 25/03/2022 | 90 | J. ENTERPRISE | 16.51 | 0 | 100
1527 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 902 | M/S. S.S. ENTERPRISE | 1859.15 | 0 | 52
1528 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000065/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 3.52 | 0 | 0
1529 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service(power) connection at Badi PH-1 Water supply scheme under Bhangar-I Block Reference ID- 106550932, Application No- 1007657894 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00567/2024-2025 | BP-2024-25-140 | 03/07/2024 | 0 | WBSEDCL | 7.9 | 0 | 0
1530 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Badi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 330/SMD | 07/02/2023 | 783 | NITESH MANAGEMENT | 25.8 | 0 | 40
1531 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Badi PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/14487) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001614/2024-2025 | 1543/SMSD | 25/11/2024 | 15 | NITESH MANAGEMENT | 0.9 | 0 | 0
1532 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.41] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00471/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 26.07 | 0 | 0
1533 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Bodra - Champahati Road, from 2.30km to 4.50km(R/S) and 6.00 km to 11.00km (R/S) [ Total Length =7200.00m] . Restoration work damaged during laying of PHE pipe line under Bodra Pipe Line Prpject under South 24 Parganas Highway Division in the District of South 24 Parganas SM/14487 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00643/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 45.04 | 0 | 0
1534 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2842] (TSM/014173) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 2175/SWD-I | 05/09/2023 | 573 | SAMSUL ENTERPRISE | 511.61 | 0 | 35
1535 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/14487] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000557/2024-2025 | 4230/SWD-I | 30/09/2024 | 60 | SAMSUL ENTERPRISE | 81.96 | 0 | 0
1536 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BADI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14487] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000572/2024-2025 | 4271/SWD-I | 01/10/2024 | 30 | PRANTIK DRILLING AGENCY | 15.9 | 0 | 0
1537 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BADI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014173] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000625/2022-2023 | 3238/SWD-I | 01/03/2023 | 30 | SETABUR RAHAMAN | 31.67 | 0 | 50
1538 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000048/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.97 | 0 | 0
1539 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000245/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 17.51 | 0 | 0
1540 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Quotation for new service connection at P.H. NO. 2 of Uttargopinathpur w/s scheme . Application no. 1007730441. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | BILL/00533/2024-2025 | BP-2024-25-131 | 24/06/2024 | 0 | WBSEDCL | 7.15 | 0 | 0
1541 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | BILL/05028/2023-2024 | BP-2023-24-565 | 11/03/2024 | 0 | WBSEDCL | 0.68 | 0 | 0
1542 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Uttar Gopinathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000420/2022-2023 | 3816/SMD | 29/12/2022 | 824 | ASHUTOSH DAS & CO. | 33.54 | 0 | 30
1543 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Uttar Gopinathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/002780/2023-2024 | 115/SMSD | 25/01/2024 | 15 | ASHUTOSH DAS & CO. | 0.62 | 0 | 0
1544 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Uttar Gopinathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/002781/2023-2024 | 116/SMSD | 25/01/2024 | 15 | ASHUTOSH DAS & CO. | 0.62 | 0 | 0
1545 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (two) nos. Boundary walls (48.00mtr each) & Construction of approach Roads at TW-2 & TW-3 sites for UTTAR GOPINATHPUR PWSS to accommodate FHTC in Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14551) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000311/2024-2025 | 3223/SWD-I | 18/07/2024 | 30 | PADMA ENGINEERING CO. | 17.61 | 0 | 0
1546 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR GOPINATHPUR PWSS of MOGRAHAT-II block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017505] [2nd Call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000683/2022-2023 | 3487/SWD-I | 15/03/2023 | 901 | SHAH ENTERPRISE | 47.64 | 0 | 76
1547 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Land development of 2nd Tubewell site for the proposed ground water based UTTAR GOPINATHPUR Piped Water Supply Scheme to accommodate FHTC in Mograhat-II Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14551) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000839/2023-2024 | 1254/SWD-I | 13/03/2024 | 15 | HASIBA ENTERPRISE | 1.02 | 0 | 0
1548 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Gopinathpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000976/2022-2023 | 1429/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.78 | 0 | 100
1549 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000132/2022-2023 | 3391/SWD-I | 10/03/2023 | 0 | Resource Division | 22.83 | 0 | 0
1550 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000154/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 60.07 | 0 | 0
1551 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-III for Zone-I & Head work site to PH-III for Zone-II of Deuli (Zone - I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000291/2023-2024 | 1435/AD | 13/07/2023 | 90 | UNIVERSAL CORPORATION | 236.64 | 0 | 100
1552 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1600 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Deuli (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000324/2023-2024 | 1550/AD | 17/07/2023 | 90 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 105.02 | 0 | 0
1553 | Alipore Division | Canning Sub-division | Laying of pipe line in place of existing damage line at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000338/2023-2024 | 1555/AD | 17/07/2023 | 90 | SOMA CONSTRUCTION | 106.44 | 0 | 0
1554 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Deuli (Zone - I) W/S Scheme under JJM, Block - Canning-II under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000414/2023-2024 | 773/CSD | 02/08/2023 | 40 | S.K.GOLUI | 2.3 | 0 | 99
1555 | Alipore Division | Canning Sub-division | Laying damage pipe line from Akkashia Madrasa to H/O Chandika Show at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001644/2021-2022 | 1512/CSD | 15/02/2022 | 20 | M/S. TAPAS MONDAL | 4.81 | 0 | 0
1556 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 for each zone of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001669/2022-2023 | 11480/AD | 15/02/2023 | 585 | ELECTROMECH | 39.19 | 0 | 100
1557 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Deuli (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001672/2022-2023 | 11483/AD | 15/02/2023 | 1053 | B.K. ENTERPRISE. | 19.99 | 0 | 0
1558 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001688/2022-2023 | 11495/AD | 15/02/2023 | 680 | ARFIN CONSTRUCTION | 7.09 | 0 | 100
1559 | Alipore Division | Canning Sub-division | Laying damage rising main from Panchayat More to PH-II and other distribution lines at Deuli W/S Scheme (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002162/2020-2021 | 1594/CSD | 23/02/2021 | 30 | M/S. TAPAS MONDAL | 3.85 | 0 | 0
1560 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000019/2023-2024 | 225/AD | 22/04/2023 | 0 | Resource Division | 117.02 | 0 | 0
1561 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000259/2023-2024 | 3049/AD | 28/09/2023 | 0 | Resource Division | 0.78 | 0 | 0
1562 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Deuli Zone-II PH-3 Water supply scheme under Canning-II block. Reference ID:-106579689, Application No :-1007690738 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00374/2024-2025 | BP-2024-25-97 | 10/06/2024 | 0 | WBSEDCL | 7.29 | 0 | 0
1563 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Deuli Zone-I PH-3 Water supply scheme under Canning-II block. Reference ID:-106676154, Application No :-1007943446 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01365/2024-2025 | BP-2024-25-294 | 22/08/2024 | 0 | WBSEDCL | 8.18 | 0 | 0
1564 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Deuli (Zone-1 & 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000042/2023-2024 | 1003/SMD | 10/04/2023 | 950 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 22.21 | 0 | 95
1565 | S24 Pgns Mechanical | Canning Sub-division | Supply, delivery and installation of 20 KVA servo motor operated Copper wound line voltage stabilizer at P.H. No. 2, Zone-Ii of Deuli Water Supply Scheme under SMD, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000241/2024-2025 | 2507/SMD | 06/08/2024 | 45 | M/S. S.R. ENTERPRISE | 0 | 0 | 0
1566 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-2 (Zone-II) of Aug of Deuli water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15088) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001961/2024-2025 | 1405/SMSD | 03/10/2024 | 15 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.92 | 0 | 0
1567 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing ) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000032/2023-2024 | 125/AD | 13/04/2023 | 600 | KHAN ENTERPRISE | 314.86 | 0 | 65
1568 | Alipore Division | Canning Sub-division | Laying of pipeline to connect the uncovered habitation at Chimta (Zone-I and II) W/S Scheme, Block - Gosaba, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000280/2024-2025 | 2495/AD | 15/06/2024 | 105 | SWASTIK CONSTRUCTION | 33.27 | 0 | 70
1569 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000296/2023-2024 | 1506/AD | 15/07/2023 | 300 | MAA SANTOSHI ENTERPRISE | 314.54 | 0 | 39
1570 | Alipore Division | Canning Sub-division | Additional work of inter connection & rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000480/2024-2025 | 943/CSD | 22/08/2024 | 30 | CHANDRA ENTERPRISE | 3.28 | 0 | 90
1571 | Alipore Division | Canning Sub-division | Inter c connection and rising main with supply of specials of Augmentation of Chimta (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000733/2023-2024 | 2894/AD | 19/09/2023 | 15 | GANGA TUBEWELL AND HARDWARE | 9.27 | 0 | 0
1572 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 for Ground water Based at Chimta (Zone-I & II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000741/2024-2025 | 4398/AD | 05/11/2024 | 30 | MAA SANTOSHI ENTERPRISE | 15.13 | 0 | 0
1573 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001116/2022-2023 | 11940/AD | 24/02/2023 | 45 | AQUATECH ENGINEERS | 44.82 | 0 | 98
1574 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001117/2022-2023 | 11941/AD | 24/02/2023 | 45 | AQUATECH ENGINEER | 44.84 | 0 | 30
1575 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001353/2023-2024 | 4425/AD | 06/12/2023 | 270 | CHANDRA ENTERPRISE | 7.12 | 0 | 100
1576 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001739/2022-2023 | 11752/AD | 21/02/2023 | 619 | SOHAM ENTERPRISE | 8.92 | 0 | 100
1577 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001740/2022-2023 | 11767/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.61 | 0 | 0
1578 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001741/2022-2023 | 11768/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.92 | 0 | 0
1579 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001742/2022-2023 | 11772/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.61 | 0 | 0
1580 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Chimta (Zone - I & II)New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001887/2022-2023 | 11549/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 7.4 | 0 | 0
1581 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000060/2023-2024 | 380/AD | 02/05/2023 | 0 | Resource Division | 45.96 | 0 | 0
1582 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new electrical connection at Chimta Zone-I, TW-02 Under Gosaba block. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/00377/2024-2025 | BP-2024-25-94 | 10/06/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
1583 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service (Power) connection at Chimta Zone-I PH-1 Water supply scheme under Gosaba block Under SMD PHE dte. (Ref ID:-106609493) (App ID:-1007801321) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/00381/2024-2025 | BP-2024-25-95 | 10/06/2024 | 0 | WBSEDCL | 7.29 | 0 | 0
1584 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Chimta Zone-II PH-1 Water supply scheme under Gosba block Reference ID:-106652148, Application No :-1007883514 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/02063/2024-2025 | BP-2024-25-492 | 09/12/2024 | 0 | WBSEDCL | 5.28 | 0 | 0
1585 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I and P.H. No.1&2, ZoneII of Chimta water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000553/2022-2023 | 498/SMD | 20/02/2023 | 961 | AVINABA ENGINEERING CONCERN | 40.18 | 0 | 45
1586 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000195/2023-2024 | 877/AD | 29/05/2023 | 673 | SUPRITI ENTERPRISE | 1165.66 | 0 | 52
1587 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-III at Kulpi block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000913/2024-2025 | 4757/AD | 25/11/2024 | 60 | SUPRITI ENTERPRISE | 82.23 | 0 | 0
1588 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-III of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001017/2022-2023 | 289/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.45 | 0 | 0
1589 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Ramnagar under Zone- III of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002007/2022-2023 | 12913/AD | 21/03/2023 | 30 | S.S.TRADERS | 25.04 | 0 | 90
1590 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation for the proposed R.C.C. Over Head Reservoir at Zone-III (Ramnagar, OHR Size-700 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002095/2022-2023 | 330/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
1591 | Alipore Division | Diamond Harbour Sub-Division | Laying of pipeline as per revised laying distribution system due to shifting of OHR site under the Augmentation Scheme of Kulpi Zone-III for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002115/2023-2024 | 829/AD | 05/02/2024 | 420 | SUPRITI ENTERPRISE | 85.58 | 0 | 75
1592 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000145/2022-2023 | 12/AD | 05/04/2023 | 0 | Resource Division | 23.55 | 0 | 0
1593 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000190/2023-2024 | 1630/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
1594 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000205/2023-2024 | 2024/AD | 05/08/2023 | 0 | Resource Division | 9.17 | 0 | 0
1595 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000630/2023-2024 | 289/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
1596 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000857/2023-2024 | 764/AD | 03/02/2024 | 0 | Resource Division | 5.84 | 0 | 0
1597 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000933/2023-2024 | 1275/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
1598 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
1599 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply and allied works at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000116/2023-2024 | 485/AD | 10/05/2023 | 30 | KAMALA ENTERPRISE (I) | 8.57 | 0 | 80
1600 | Alipore Division | Raidighi Sub-Division | Restoration of distribution system of piped water supply (N.P. 121-122,109-121, 110-109, 229-232, 228-229, 130-129) at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000265/2022-2023 | 101/RSD | 13/06/2022 | 60 | UNITED BUILDERS | 4.77 | 0 | 100
1601 | Alipore Division | Raidighi Sub-Division | Restoration of distribution system of piped water supply (N.P. 113-114, 128-126, 129-128, 130-129,131-130) at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000266/2022-2023 | 102/RSD | 13/06/2022 | 60 | NITYANANDA MONDAL | 4.2 | 0 | 100
1602 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000875/2024-2025 | 4659/AD | 20/11/2024 | 120 | MONCON INDIA | 27.43 | 0 | 95
1603 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Pump House No. 2 at Nandakumarpur Zone - III W/S Scheme, modified as Zone ¿ XII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001139/2023-2024 | 289/RSD | 29/09/2023 | 60 | MAA KALI ENTERPRISE | 4.29 | 0 | 90
1604 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Nandakumarpur Zone - III W/S Scheme, modified as Zone- XII of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001301/2024-2025 | 5375/AD | 23/12/2024 | 30 | M/S R.K.ENTERPRISE | 4.77 | 0 | 0
1605 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001968/2022-2023 | 12722/AD | 14/03/2023 | 45 | R CONSTRUCTION | 87.48 | 0 | 40
1606 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000651/2023-2024 | 254/AD | 15/01/2024 | 0 | Resource Division | 5.33 | 0 | 0
1607 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000087/2023-2024 | 498/AD | 11/05/2023 | 963 | JAL PRAVAHIKA PVT. LTD. | 569.23 | 0 | 41
1608 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
1609 | Alipore Division | Raidighi Sub-Division | Laying of additional Pipe Line at Zone - V of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000876/2024-2025 | 4660/AD | 20/11/2024 | 90 | HARIDAS DUTTA | 16.64 | 0 | 2
1610 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000244/2023-2024 | 2914/AD | 20/09/2023 | 0 | Resource Division | 13.83 | 0 | 0
1611 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000645/2023-2024 | 249/AD | 15/01/2024 | 0 | Resource Division | 8.36 | 0 | 0
1612 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap connection (FHTC) to all the households in Zone-VII of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000072/2022-2023 | 1036/AD | 23/05/2022 | 30 | S.S. ENTERPRISE (II) | 31.2 | 0 | 95
1613 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Mathurapur W/S Scheme (Zone-VII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000432/2023-2024 | 1920/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 0
1614 | Alipore Division | Raidighi Sub-Division | Construction of steel structure for canal crossing of HDPE pipe (LDS) at at Zone-VII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001137/2022-2023 | 602/RSD | 23/12/2022 | 30 | M/S B ENTERPRISE | 0.98 | 0 | 0
1615 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-VII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001726/2020-2021 | 5315/AD | 18/02/2021 | 120 | S.S. ENTERPRISE (II) | 88.26 | 0 | 100
1616 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-VII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001960/2022-2023 | 12714/AD | 14/03/2023 | 45 | MONDAL ENTERPRISE - 2 (SDK) | 55.92 | 0 | 75
1617 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 7 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000022/2025-2026 | 2008/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.92 | 0 | 0
1618 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.49 | 0 | 0
1619 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V, VI & VII of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000242/2023-2024 | 1394/AD | 12/07/2023 | 30 | ISHAN CONSTRUCTION | 54.94 | 0 | 0
1620 | Alipore Division | Canning Sub-division | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000752/2024-2025 | 4426/AD | 05/11/2024 | 60 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 93.79 | 0 | 0
1621 | Alipore Division | Canning Sub-division | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001060/2024-2025 | 1288/CSD | 20/11/2024 | 30 | A.P. CONSTRUCTION | 4.55 | 0 | 0
1622 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Bijoynagar piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15499) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001099/2024-2025 | 5030/AD | 06/12/2024 | 270 | UNITED BUILDERS | 195.23 | 0 | 0
1623 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 for Ground Water Based at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001241/2024-2025 | 5222/AD | 16/12/2024 | 30 | MAA SANTOSHI ENTERPRISE | 15.05 | 0 | 0
1624 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001699/2022-2023 | 11663/AD | 20/02/2023 | 45 | ESSCON | 8.61 | 0 | 100
1625 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001715/2022-2023 | 11679/AD | 20/02/2023 | 712 | JYOTI ENTERPRISES | 8.4 | 0 | 100
1626 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000114/2022-2023 | 383/AD | 02/05/2023 | 0 | Resource Division | 99.35 | 0 | 0
1627 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Bijoynagar ( TW-1) Water supply scheme under Gosaba block. Reference ID:-106770522, Application No :-1008125225 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01842/2024-2025 | BP-2024-25-467 | 18/11/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
1628 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Bijoynagar PH-2 Water supply scheme under Gosaba block. Reference ID:-106770519, Application No :-1008125182 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01846/2024-2025 | BP-2024-25-468 | 18/11/2024 | 0 | WBSEDCL | 8 | 0 | 0
1629 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Bijoynagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000043/2023-2024 | 1039/SND | 17/04/2023 | 90 | PADMA ENGINEERING CO. | 33.61 | 0 | 0
1630 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
1631 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-III, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC = 807 Nos.) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000117/2023-2024 | 486/AD | 10/05/2023 | 45 | M/S B.M. CONSTRUCTION | 96.3 | 0 | 95
1632 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system and Rising Main system of piped water supply at Zone - III (Koutala PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000277/2024-2025 | 2473/AD | 14/06/2024 | 20 | NITYANANDA MONDAL | 7.42 | 0 | 90
1633 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- III of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000659/2024-2025 | 4205/AD | 23/10/2024 | 90 | NITYANANDA MONDAL | 27.44 | 0 | 0
1634 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 & 3 and approach road and plinth protection at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000990/2023-2024 | 286/RSD | 29/09/2023 | 60 | L.N. ENTERPRISE | 3.48 | 0 | 100
1635 | Alipore Division | Raidighi Sub-Division | Repairing of boundary wall at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000991/2023-2024 | 287/RSD | 29/09/2023 | 60 | M/S R.K.ENTERPRISE | 4.76 | 0 | 100
1636 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - III of Mathurapur - II Block (Koutala PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001969/2022-2023 | 12723/AD | 14/03/2023 | 30 | NITYANANDA MONDAL | 17.09 | 0 | 95
1637 | Alipore Division | Raidighi Sub-Division | Construction of 450 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Mathurapur-II block (zone-III) for Mega surface water based water supply Scheme for Falta Mathurapur, South 24 Parganas under AD PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002154/2019-2020 | 7936/AD | 11/03/2020 | 1826 | PIKASU BOSE | 23.76 | 0 | 100
1638 | Alipore Division | Raidighi Sub-Division | Laying distribution system of damaged pipe line of Koutala piped water supply scheme at Zone- III of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002375/2023-2024 | 1215/AD | 29/02/2024 | 45 | KALIDAS ENTERPRISE | 13.5 | 0 | 100
1639 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000648/2023-2024 | 251/AD | 15/01/2024 | 0 | Resource Division | 4.97 | 0 | 0
1640 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00126/2024-2025 | BP-2024-25-39 | 24/04/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
1641 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gangaduara ( Zone-43) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000010/2023-2024 | 945/SMD | 04/04/2023 | 820 | SARKAR ELECTRICAL | 22.38 | 0 | 40
1642 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gangaduara W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15177) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001639/2024-2025 | 103/SMSD | 21/01/2025 | 15 | SARKAR ELECTRICAL | 0.91 | 0 | 0
1643 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Gangaduara W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15177) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001640/2024-2025 | 101/SMSD | 21/01/2025 | 15 | SARKAR ELECTRICAL | 0.58 | 0 | 0
1644 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GANGADUARA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1426] [TSM/018365] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000012/2023-2024 | 31/SWD-I | 05/04/2023 | 910 | SUN CONSTRUCTION | 330 | 0 | 80
1645 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for GANGADUARA PWSS at Zone-43 of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018365] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000559/2022-2023 | 3051/SWD-I | 20/02/2023 | 30 | DEV & COMPANY (EMAIL ID- DEVANDCOMPANYKOL@GMAIL.COM) | 31.8 | 0 | 100
1646 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based GANGADUARA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000924/2022-2023 | 1177/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 2.68 | 0 | 100
1647 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000146/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.53 | 0 | 0
1648 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 706/SMSD | 15/05/2025 | 15 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0
1649 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 698/SMSD | 15/05/2025 | 15 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0
1650 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kharupatalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15871) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 699/SMSD | 15/05/2025 | 15 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0
1651 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Kharupatalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001125/2023-2024 | 4260/SMD | 06/11/2023 | 90 | JAGANNATH ENTERPRISE | 21.33 | 0 | 0
1652 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for KHARUPATALIA PWSS to accommodate FHTC in Baruipur Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018473) (2nd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 560/SWD-I | 12/05/2023 | 695 | ARUP ENTERPRISE | 31.46 | 0 | 70
1653 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KHARUPATALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 839] [TSM/018473] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 935/SWD-I | 06/06/2023 | 390 | PARAMESWAR CHOWDHURY | 199.89 | 0 | 50
1654 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kharupatalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000938/2022-2023 | 1251/SWD-I | 08/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
1655 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000125/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 24.11 | 0 | 0
1656 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017459) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000018/2023-2024 | 90/AD | 11/04/2023 | 90 | SHEKHAR CHAKRABORTY | 131.1 | 0 | 100
1657 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000027/2025-2026 | 2013/AD | 28/04/2025 | 135 | SAHANA ENTERPRISE | 26.16 | 0 | 0
1658 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kalaria Zone- IIB W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000129/2023-2024 | 489/AD | 10/05/2023 | 30 | ASHIS ENTERPRISE | 17.98 | 0 | 25
1659 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2098] (TSM/017459) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000353/2023-2024 | 1662/AD | 20/07/2023 | 720 | SAHANA ENTERPRISE | 105.65 | 0 | 90
1660 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000465/2023-2024 | 1927/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 90
1661 | Alipore Division | Canning Sub-division | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IIB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000484/2024-2025 | 3543/AD | 02/09/2024 | 45 | SUPRITI ENTERPRISE | 19.63 | 0 | 0
1662 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001084/2023-2024 | 3543/AD | 17/10/2023 | 405 | M/S. ASIRUDDIN SEKH ENTERPRISE | 7.28 | 0 | 100
1663 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kalaria (Zone-IIB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001867/2022-2023 | 12456/AD | 10/03/2023 | 45 | B.K. ENTERPRISE. | 40.76 | 0 | 95
1664 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001950/2022-2023 | 11811/AD | 22/02/2023 | 45 | SIRCON ENGINEERING SERVICES | 5.79 | 0 | 95
1665 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1666 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000067/2023-2024 | 270/AD | 24/04/2023 | 0 | Resource Division | 34.64 | 0 | 0
1667 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/03868/2023-2024 | BP-2023-24-397 | 02/12/2023 | 0 | WBSEDCL | 5.07 | 0 | 0
1668 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/04001/2023-2024 | BP-2023-24-405 | 13/12/2023 | 0 | WBSEDCL | 4.66 | 0 | 0
1669 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II-B for Augmentation of Kalaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000267/2023-2024 | 1127/SMD | 24/04/2023 | 768 | JYOTY SOLAR POWER | 20.92 | 0 | 100
1670 | S24 Pgns Mechanical | Canning Sub-division | Continuation order for Hiring of Motor cab for newly JJM works for the office of the Assistant Engineer, South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000829/2024-2025 | 1573/SMSD | 28/11/2024 | 182 | S.P. CONSTRUCTION | 0.86 | 0 | 0
1671 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-IIB PH-2 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002533/2023-2024 | 164/SMSD | 05/02/2024 | 15 | JYOTY SOLAR POWER | 0.89 | 0 | 100
1672 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1296] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000031/2023-2024 | 124/AD | 13/04/2023 | 400 | M N J ENTERPRISES | 492.25 | 0 | 35
1673 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001929/2022-2023 | 11802/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 4.43 | 0 | 95
1674 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001983/2022-2023 | 12644/AD | 13/03/2023 | 45 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 8.83 | 0 | 0
1675 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002011/2022-2023 | 12917/AD | 21/03/2023 | 772 | MISTRY CONSTRUCTION | 8.61 | 0 | 100
1676 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002032/2022-2023 | 13028/AD | 24/03/2023 | 45 | NILAVA GHOSHAL | 43.98 | 0 | 100
1677 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Purba Radhnagar (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002350/2023-2024 | 1165/AD | 27/02/2024 | 340 | A.K. ENTERPRISE | 6.98 | 0 | 90
1678 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000046/2023-2024 | 253/AD | 23/04/2023 | 0 | Resource Division | 17.55 | 0 | 0
1679 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-II for Augmentation of Purba Radhanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000272/2023-2024 | 1132/SMD | 24/04/2023 | 90 | AMIT DAS | 19.54 | 0 | 0
1680 | S24 Pgns Mechanical | Canning Sub-division | Supply, delivery and installation of 15 KVA servo motor operated Copper wound line voltage stabilizer at P.H. No. 1 of Purba Radhanagar Water Supply Scheme under SMD, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000298/2023-2024 | 2148/SMD | 06/06/2023 | 15 | SHIVAM ENTERPRISE | 2.56 | 0 | 100
1681 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000316/2024-2025 | 2697/AD | 24/06/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0
1682 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000317/2024-2025 | 2698/AD | 24/06/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0
1683 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
1684 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VI) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000728/2023-2024 | 2889/AD | 19/09/2023 | 15 | A.K. ENTERPRISE (II) | 11.16 | 0 | 0
1685 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - II) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000784/2024-2025 | 4485/AD | 11/11/2024 | 231 | SNEHA CONSTRUCTION | 19.59 | 0 | 98
1686 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000786/2024-2025 | 4486/AD | 11/11/2024 | 30 | SNEHA CONSTRUCTION | 19.59 | 0 | 0
1687 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
1688 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001936/2022-2023 | 11807/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 0 | 0
1689 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VI) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001993/2022-2023 | 12684/AD | 14/03/2023 | 45 | NATH CONSTRUCTION | 7.08 | 0 | 1
1690 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000026/2023-2024 | 232/AD | 24/04/2023 | 0 | Resource Division | 63.43 | 0 | 0
1691 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000155/2023-2024 | 1044/AD | 15/06/2023 | 0 | Resource Division | 7.03 | 0 | 0
1692 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 Zone-VI of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001508/2022-2023 | 884/SMD | 24/03/2023 | 90 | BHUNIA BUILDERS | 10.41 | 0 | 0
1693 | Alipore Division | Canning Sub-division | Restoration of Basanti Goran Bose Ganga Mela block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01326/2024-2025 | BP-2024-25-624 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 99.74 | 0 | 0
1694 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -2 of Basanti Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000054/2022-2023 | 790/AD | 12/05/2022 | 30 | G.B. CONSTRUCTION (TW) | 17.99 | 0 | 0
1695 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000109/2023-2024 | 507/AD | 11/05/2023 | 15 | SUPER CONSTRUCTION | 6.22 | 0 | 95
1696 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
1697 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
1698 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-II) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001868/2022-2023 | 12521/AD | 10/03/2023 | 45 | SNEHA CONSTRUCTION | 39.8 | 0 | 81
1699 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001933/2022-2023 | 11805/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.2 | 0 | 99
1700 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001988/2022-2023 | 12679/AD | 14/03/2023 | 706 | M/S KALIPADA JANA | 7.29 | 0 | 98
1701 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-II) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001989/2022-2023 | 12680/AD | 14/03/2023 | 45 | M/S ANNAPURNA ENTERPRISE | 7.03 | 0 | 0
1702 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000022/2023-2024 | 228/AD | 24/04/2023 | 0 | Resource Division | 14.27 | 0 | 0
1703 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000151/2023-2024 | 1046AD | 15/06/2023 | 0 | Resource Division | 9.38 | 0 | 0
1704 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000251/2023-2024 | 3043/AD | 28/09/2023 | 0 | Resource Division | 62.96 | 0 | 0
1705 | S24 Pgns Mechanical | Canning Sub-division | Charges for Service connection at Pump house no- 1 of Basanti Aug (Z-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00445/2024-2025 | BP-2024-25-109 | 14/06/2024 | 0 | WBSEDCL | 7.62 | 0 | 0
1706 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04627/2023-2024 | BP-2023-24-482 | 07/02/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
1707 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Basanti Zone-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000491/2022-2023 | 293/SMD | 03/02/2023 | 820 | SRI KRISHNA NIRMAN | 11.18 | 0 | 100
1708 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001499/2022-2023 | 872/SMD | 23/03/2023 | 802 | JAI BHARAT COMMERCIAL CORPORATION | 20.82 | 0 | 82
1709 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
1710 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bhubannagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000959/2023-2024 | 2991/AD | 26/09/2023 | 45 | M/S SABITRI ENTERPRISE | 27.77 | 0 | 0
1711 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bhubannagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000960/2023-2024 | 2992/AD | 26/09/2023 | 30 | M/S. PARAMESWAR ENTERPRISE | 9.54 | 0 | 0
1712 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Bhubannagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001832/2022-2023 | 12182/AD | 01/03/2023 | 45 | SUNDARBAN SPARK TRADERS | 38.5 | 0 | 50
1713 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
1714 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Bhubannagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002165/2022-2023 | 8338/AD | 12/12/2022 | 45 | LEMNISCATE | 6.05 | 0 | 100
1715 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000126/2023-2024 | 662/AD | 17/05/2023 | 0 | Resource Division | 13.7 | 0 | 0
1716 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000457/2023-2024 | 4720/AD | 18/12/2023 | 0 | Resource Division | 33.36 | 0 | 0
1717 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000820/2023-2024 | 665/AD | 30/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
1718 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000995/2023-2024 | 1788/AD | 27/03/2024 | 0 | Resource Division | 6.44 | 0 | 0
1719 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Bhubannagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000110/2023-2024 | 1004/SMD | 11/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 21.61 | 0 | 0
1720 | Alipore Division | Baruipur Sub-Division | Road restoration for Canning mam to Padma Stopaj Via Kailasbabur Abad Khal Par | AE BSD,Assistant Engineer | Junior Engineer | BILL/01675/2024-2025 | BP-2024-25-780 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.72 | 0 | 0
1721 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01505/2023-2024 | BP-2023-24-173 | 02/08/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
1722 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01717/2023-2024 | BP-2023-24-191 | 09/08/2023 | 0 | WBSEDCL | 2.43 | 0 | 0
1723 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04228/2023-2024 | BP-2023-24-434 | 27/12/2023 | 0 | WBSEDCL | 3.87 | 0 | 0
1724 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Ramnagar (Zone-3) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 939/SMD | 04/04/2023 | 90 | K.S.P ENTERPRISE | 12.96 | 0 | 0
1725 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-III) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000064/2023-2024 | 1058/SMD | 18/04/2023 | 90 | M/S. G.P ENTERPRISE | 21.76 | 0 | 50
1726 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15756) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002695/2023-2024 | 349/SMSD | 19/03/2024 | 15 | M/S. G.P ENTERPRISE | 0.89 | 0 | 0
1727 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 1 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/15756) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002696/2023-2024 | 348/SMSD | 19/03/2024 | 15 | M/S. G.P ENTERPRISE | 0.89 | 0 | 100
1728 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-III) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15756) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002697/2023-2024 | 347/SMSD | 19/03/2024 | 15 | M/S. G.P ENTERPRISE | 0.58 | 0 | 0
1729 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00545/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 62.5 | 0 | 0
1730 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 943] [TSM/018222] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000055/2023-2024 | 274/SWD-I | 24/04/2023 | 918 | MS SARADA UDYOG | 151.16 | 0 | 90
1731 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(III) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000406/2021-2022 | 1947/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0
1732 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, protection work for pipeline and other allied works for "Proposed Ground water based RAMNAGAR ZONE-III piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district". (SM/15756) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000547/2024-2025 | 4135/SWD-I | 23/09/2024 | 45 | MS SARADA UDYOG | 25.01 | 0 | 0
1733 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-III) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018222] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000630/2022-2023 | 3257/SWD-I | 02/03/2023 | 30 | BENGAL ENTERPRISE | 31.76 | 0 | 0
1734 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000110/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 8.72 | 0 | 0
1735 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000166/2023-2024 | 2264/AD | 14/08/2023 | 45 | SARADA CONSTRUCTION | 61.08 | 0 | 60
1736 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Shibnagar Abad W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000230/2024-2025 | 2560/AD | 18/06/2024 | 30 | SUKUMAR HALDAR | 9.6 | 0 | 0
1737 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000231/2024-2025 | 2542/AD | 18/06/2024 | 45 | M/S SAKTI GIRI ENTERPRISE | 5.62 | 0 | 0
1738 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded GravelFilter for Shibnagar Abad W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129)(2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000450/2024-2025 | 3359/AD | 14/08/2024 | 113 | SARADA CONSTRUCTION | 20.39 | 0 | 100
1739 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and Road Restoration for Shibnagar Abad W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000459/2024-2025 | 3418/AD | 21/08/2024 | 30 | SARADA CONSTRUCTION | 18.15 | 0 | 0
1740 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001143/2023-2024 | 3671/AD | 01/11/2023 | 700 | PRINCE INDUSTRIES (INDIA) | 381.91 | 0 | 75
1741 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002050/2023-2024 | 511/AD | 25/01/2024 | 30 | SRI DURGA ENTERPRISE | 9.58 | 0 | 0
1742 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002080/2022-2023 | 13255/AD | 31/03/2023 | 45 | AQUATECH ENGINEERS | 36.97 | 0 | 40
1743 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002129/2023-2024 | 819/AD | 05/02/2024 | 631 | S.M. ENTERPRISE | 30.06 | 0 | 80
1744 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
1745 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002277/2023-2024 | 914/AD | 08/02/2024 | 45 | CAMELIA CONSTRUCTION | 26.92 | 0 | 0
1746 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002573/2023-2024 | 516/KSD | 15/03/2024 | 20 | M/S SANKARI ENTERPRISE (II) | 3.82 | 0 | 0
1747 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibnagar Abad PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002619/2023-2024 | 956/KSD | 19/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1748 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000472/2023-2024 | 4778/AD | 19/12/2023 | 0 | Resource Division | 36.29 | 0 | 0
1749 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000562/2023-2024 | 50/AD | 03/01/2024 | 0 | Resource Division | 8.93 | 0 | 0
1750 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000788/2023-2024 | 632/AD | 30/01/2024 | 0 | Resource Division | 0.43 | 0 | 0
1751 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000977/2023-2024 | 1770/AD | 27/03/2024 | 0 | Resource Division | 3.32 | 0 | 0
1752 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Shibnagarbad PH-1 W/S Scheme JL No-:- 004, Khatian No;- 1714, Plot:- 3348, Mouza:- Shibnagarabad Application No:- 1007514909 Reference ID:- 106460088 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00215/2024-2025 | BP-2024-25-66 | 16/05/2024 | 0 | WBSEDCL | 3.86 | 0 | 0
1753 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Shibnagar Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001464/2023-2024 | 684/SMD | 01/02/2024 | 790 | PS & ASSOCIATES | 22.42 | 0 | 45
1754 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/04816/2023-2024 | BP-2023-24-527 | 22/02/2024 | 0 | WBSEDCL | 6.24 | 0 | 0
1755 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Petua ( Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000091/2023-2024 | 1084/SMD | 18/04/2023 | 90 | ASHIM UDYOG | 22.78 | 0 | 43
1756 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Petua (Part-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/17299) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000779/2024-2025 | 888/SMSD | 19/06/2024 | 15 | ASHIM UDYOG | 0.58 | 0 | 0
1757 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Petua (Part-II) scheme under SMD, P.H.E. Dte.(Block-Baruipur) [SM/17299] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000780/2024-2025 | 935/SMSD | 28/06/2024 | 15 | ASHIM UDYOG | 0.89 | 0 | 0
1758 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Patua (Part-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002844/2023-2024 | 277/SMSD | 29/02/2024 | 15 | ASHIM UDYOG | 0.89 | 0 | 100
1759 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PETUA (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =1306] [TSM/018705] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000079/2023-2024 | 393/SWD-I | 28/04/2023 | 900 | L.N. ENTERPRISE | 214.84 | 0 | 90
1760 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for PETUA (PART-II) PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018705] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000748/2022-2023 | 3610/SWD-I | 24/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
1761 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land of OHR site / 2nd TW site including Construction of approch road and other allied works for Ground Water Based PETUA (Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/17299) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000848/2023-2024 | 1253/SWD-I | 13/03/2024 | 630 | L.N. ENTERPRISE | 27.77 | 0 | 50
1762 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Petua (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000929/2022-2023 | 1198/SWD-I | 02/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
1763 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for PETUA (PART-II) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/17299] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001146/2024-2025 | 327/SWD-I | 29/01/2025 | 30 | M/S MAA TARA ENTERPRISE | 15.57 | 0 | 0
1764 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000112/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 33.22 | 0 | 0
1765 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000178/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 33.22 | 0 | 0
1766 | Alipore Division | Canning Sub-division | Inter connection of Tubewell-1 & Tubewell-2 and laying of pipe line from Chatrakhali PWD Road to Spandan Sishu Academy at Chatrakhali W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000277/2022-2023 | 270/CSD | 19/05/2022 | 30 | M/S. MIHIR KUMAR NASKAR | 1.43 | 0 | 98
1767 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Chatrakhali, Zone-II W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000277/2025-2026 | 682/CSD | 26/05/2025 | 30 | SUDIP DEBNATH | 2.4 | 0 | 0
1768 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000354/2023-2024 | 1663/AD | 20/07/2023 | 90 | RIVER BENZ CONSTRUCTION | 249.56 | 0 | 0
1769 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000371/2023-2024 | 1572/AD | 17/07/2023 | 733 | SUPRITI ENTERPRISE | 308.46 | 0 | 22
1770 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000374/2023-2024 | 1573/AD | 17/07/2023 | 15 | BHOLANATH CONSTRUCTION | 13.56 | 0 | 0
1771 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000387/2023-2024 | 1576/AD | 17/07/2023 | 90 | ANWAR SHAIKH | 77.59 | 0 | 0
1772 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-II) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000388/2023-2024 | 1577/AD | 17/07/2023 | 30 | MAA SARADA ENTERPRISE | 19.57 | 0 | 0
1773 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000391/2023-2024 | 1777/AD | 26/07/2023 | 15 | M/S BABUSONA ENTERPRISE | 13.7 | 0 | 0
1774 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000469/2023-2024 | 1781/AD | 26/07/2023 | 45 | M/S. TAPAS MONDAL | 7.37 | 0 | 0
1775 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000470/2023-2024 | 1782/AD | 26/07/2023 | 45 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0
1776 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000471/2023-2024 | 1783/AD | 26/07/2023 | 45 | M/S. TAPAS MONDAL | 7.11 | 0 | 0
1777 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000472/2023-2024 | 1784/AD | 26/07/2023 | 45 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0
1778 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-II) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000473/2023-2024 | 1785/AD | 26/07/2023 | 45 | SUSHANTA MANDAL | 7.11 | 0 | 0
1779 | Alipore Division | Canning Sub-division | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000474/2023-2024 | 1786/AD | 26/07/2023 | 45 | SABITA INFRASTRUCTURE | 7.11 | 0 | 0
1780 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000475/2023-2024 | 1787/AD | 26/07/2023 | 45 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 0
1781 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Chatrakhali (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000614/2023-2024 | 1832/AD | 27/07/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 15.03 | 0 | 98
1782 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water basedAugmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000755/2024-2025 | 4439/AD | 06/11/2024 | 270 | SUPRITI ENTERPRISE | 309.22 | 0 | 30
1783 | Alipore Division | Canning Sub-division | Sinking of 1 Nos. 200mm x 100mm dia. 420 mtr. deep Tubewell (Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Chatrakhali Water Supply Scheme Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000934/2020-2021 | 4862/AD | 28/01/2021 | 45 | AQUATECH ENGINEERS | 16.7 | 0 | 99
1784 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001147/2023-2024 | 3692/AD | 02/11/2023 | 45 | I.B. ENTERPRISE | 7.36 | 0 | 0
1785 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of the Augmentation Ground Water Based at Chatrakhali (Zone-I, II & III) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (Zone-I, TW No. 1 replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002379/2023-2024 | 1203/AD | 29/02/2024 | 399 | BHATTACHARJEE & CO. | 19.68 | 0 | 99
1786 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1787 | Alipore Division | Canning Sub-division | Supply and delivery of UPVC pipe (CD) for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation Ground Water Based at Chatrakhali (Zone - I, II & III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Zone - I,Tubewell No. - 1, Replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/003677/2024-2025 | 258/CSD | 04/03/2025 | 2 | BHATTACHARJEE & CO. | 1.58 | 0 | 95
1788 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000032/2023-2024 | 237/AD | 24/04/2023 | 0 | Resource Division | 157.26 | 0 | 0
1789 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000387/2023-2024 | 328/AD | 19/01/2024 | 0 | Resource Division | 41.73 | 0 | 0
1790 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000073/2023-2024 | 54/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1791 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gurudaspur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/10486) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000232/2024-2025 | 2607/AD | 19/06/2024 | 60 | UNITED BUILDERS | 87.78 | 0 | 0
1792 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Gurudaspur W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000275/2023-2024 | 1425/AD | 13/07/2023 | 45 | UNITED BUILDERS | 31.2 | 0 | 100
1793 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GURUDASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000441/2022-2023 | 292/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.41 | 0 | 100
1794 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
1795 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Gurudaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000900/2022-2023 | 7274/AD | 24/11/2022 | 300 | UNITED BUILDERS | 411.28 | 0 | 80
1796 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001614/2021-2022 | 613/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 1.92 | 0 | 100
1797 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Gurudaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001996/2023-2024 | 469/KSD | 22/09/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 3.53 | 0 | 100
1798 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
1799 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.07.2024 to 08.10.2024). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002171/2024-2025 | 2889/AD | 08/07/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1800 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 09.10.2024 to 07.01.2025). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002173/2024-2025 | 4157/AD | 05/10/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1801 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 3nos Pump House site of Gurudaspur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10486) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002181/2024-2025 | 2064/KSD | 28/12/2024 | 20 | KANIKA CONSTRUCTION | 3.94 | 0 | 0
1802 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000053/2022-2023 | 3918/AD | 12/08/2022 | 0 | Resource Division | 47.6 | 0 | 0
1803 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000311/2023-2024 | 3120/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1804 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000570/2023-2024 | 77/AD | 03/01/2024 | 0 | Resource Division | 5.22 | 0 | 0
1805 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000739/2023-2024 | 574/AD | 29/01/2024 | 0 | Resource Division | 14.83 | 0 | 0
1806 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Nainan water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 3798/SMD | 29/12/2022 | 90 | ABHISEK ENGINEERING CONCERN | 22.36 | 0 | 0
1807 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of NAINAN PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, PHE Dte. for augmentation of surface water bassed W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/12803) | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1759/SWD-I | 02/07/2025 | 60 | SRI RAM CONSTRUCTION | 12.02 | 0 | 0
1808 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Nainan PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000357/2022-2023 | 2276/SWD-I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 0 | 0
1809 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "NAINAN Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 404/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 0 | 0
1810 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for NAINAN PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12803) | Assistant Engineer | Junior Engineer | ORD/000421/2024-2025 | 3749/SWD-I | 28/08/2024 | 405 | SRI RAM CONSTRUCTION | 43.25 | 0 | 50
1811 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of NAINAN of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1684] | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 3028/SWD-I | 20/02/2023 | 751 | SRI RAM CONSTRUCTION | 382.88 | 0 | 70
1812 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nainan PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014759] | Assistant Engineer | Junior Engineer | ORD/000735/2022-2023 | 3586/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 0
1813 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000175/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 28.49 | 0 | 0
1814 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with soil investigation, Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. for Augmentation of Kusumtala Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/12731) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000304/2024-2025 | 2687/AD | 24/06/2024 | 600 | L.N. ENTERPRISE | 279.17 | 0 | 70
1815 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Kusumtala W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/12731) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000417/2024-2025 | 3068/AD | 25/07/2024 | 30 | M/S. PAPIYA ENTERPRISE | 10.67 | 0 | 0
1816 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KUSUMTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000488/2022-2023 | 4191/AD | 22/08/2022 | 45 | M/S R.DUTTA & CO. | 5.21 | 0 | 100
1817 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kusumtala Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000547/2022-2023 | 5723/AD | 13/10/2022 | 901 | M/S B. ENTERPRISE | 250.59 | 0 | 100
1818 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 1st Tube well of Kusumtala Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000597/2022-2023 | 5922/AD | 19/10/2022 | 15 | S.K.GOLUI | 5.1 | 0 | 100
1819 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Kusumtala W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000922/2023-2024 | 2975/AD | 26/09/2023 | 30 | S. CHAKRABORTY AND CO. | 22.7 | 0 | 0
1820 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kusumtala, Bagdanga, Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002138/2023-2024 | 939/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.54 | 0 | 100
1821 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000291/2023-2024 | 3086/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1822 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000494/2023-2024 | 4793/AD | 19/12/2023 | 0 | Resource Division | 25.9 | 0 | 0
1823 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000544/2023-2024 | 28/AD | 02/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
1824 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000783/2023-2024 | 627/AD | 30/01/2024 | 0 | Resource Division | 0.75 | 0 | 0
1825 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000988/2023-2024 | 1781/AD | 27/03/2024 | 0 | Resource Division | 14.03 | 0 | 0
1826 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Kusumtala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000804/2022-2023 | 267/SMD | 31/01/2023 | 90 | SRI KRISHNA NIRMAN | 10.71 | 0 | 0
1827 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000149/2025-2026 | 2671/AD | 09/06/2025 | 45 | FREEDOM CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.06 | 0 | 0
1828 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 50000 Gallon at Narayanpur W/S Scheme, Block - Namkhana, South 24 Parganas under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000150/2025-2026 | 2672/AD | 09/06/2025 | 400 | SUPREME NIRMAN UDYOG | 131.79 | 0 | 0
1829 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Narayanpur W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000218/2024-2025 | 2601/AD | 19/06/2024 | 30 | CHANDRA ENTERPRISE | 9.59 | 0 | 0
1830 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone II W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000330/2024-2025 | 2733/AD | 25/06/2024 | 60 | M/S B. ENTERPRISE | 117.78 | 0 | 0
1831 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone I W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000403/2024-2025 | 3186/AD | 31/07/2024 | 60 | C L B SYNDICATE | 58.37 | 0 | 0
1832 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001030/2021-2022 | 544/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.57 | 0 | 98
1833 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 Nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 2647] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001142/2023-2024 | 3655/AD | 31/10/2023 | 883 | M/S B. ENTERPRISE | 470.08 | 0 | 92
1834 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAYANPUR )) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001364/2023-2024 | 3437/AD | 12/10/2023 | 45 | M/S R.DUTTA & CO. | 15.05 | 0 | 100
1835 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001419/2023-2024 | 1575/AD | 16/03/2024 | 334 | SAFTI PRIVATE LIMITED | 18.21 | 0 | 0
1836 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001420/2023-2024 | 1576/AD | 16/03/2024 | 334 | SAFTI PRIVATE LIMITED | 13.36 | 0 | 0
1837 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along with Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main & FHTC for 01 year after completion of FHTC work for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001452/2023-2024 | 4690/AD | 18/12/2023 | 90 | M/S SWAPAN KUMAR PRADHAN | 79.34 | 0 | 50
1838 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001453/2023-2024 | 1190/AD | 28/02/2024 | 379 | SAFTI PRIVATE LIMITED | 31.47 | 0 | 0
1839 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001610/2021-2022 | 608/KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 4.57 | 0 | 0
1840 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001619/2021-2022 | 622/KSD | 05/10/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.31 | 0 | 0
1841 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
1842 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at 2nd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002215/2024-2025 | 2110/KSD | 30/12/2024 | 15 | AZAD RAHAMAN LASKAR | 2.58 | 0 | 0
1843 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at 3rd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002216/2024-2025 | 2111/KSD | 30/12/2024 | 15 | AZAD RAHAMAN LASKAR | 2.32 | 0 | 0
1844 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18128) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002525/2024-2025 | 810/AD | 27/02/2025 | 30 | SIMPLEX DRILLING CO. | 20.37 | 0 | 0
1845 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanganj W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15046) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002589/2024-2025 | 921/AD | 05/03/2025 | 30 | M/S P. B. CONSTRUCTION | 7.18 | 0 | 0
1846 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Narayanpur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002617/2023-2024 | 894/KSD | 18/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1847 | Alipore Division | Kakdwip Sub-Division | Continuation order for Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/003232/2023-2024 | 370/KSD | 19/02/2024 | 274 | BIMALENDU GIRI | 0.61 | 0 | 0
1848 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000004/2024-2025 | 5157/AD | 12/12/2024 | 0 | Resource Division | 123.2 | 0 | 0
1849 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000492/2023-2024 | 4791/AD | 19/12/2023 | 0 | Resource Division | 28.85 | 0 | 0
1850 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000547/2023-2024 | 30/AD | 02/01/2024 | 0 | Resource Division | 22.85 | 0 | 0
1851 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000792/2023-2024 | 637/AD | 30/01/2024 | 0 | Resource Division | 24.89 | 0 | 0
1852 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Augmentation of Narayanpur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001481/2023-2024 | 4762/SMD | 06/12/2023 | 91 | R.N.S. TRADING | 19.32 | 0 | 0
1853 | S24 Pgns Mechanical | Kakdwip Sub-Division | Negotiation of price for Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 & 4 of Augmentation of Narayanpur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002552/2023-2024 | 4758/SMD | 06/12/2023 | 731 | DIPA CHHETRI | 19.08 | 0 | 0
1854 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1500 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I PURBO TETULBERIA MOUZA Piped Water Supply Scheme of KULTALI Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 14340] [TSM/011555 & TSM/016360] | AE BSD |  | ORD/000529/2023-2024 | 2344/SWD-I | 22/09/2023 | 558 | MADAN MOHAN MONDAL | 1916.42 | 0 | 60
1855 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000072/2022-2023 | 2988/SWD-I | 20/02/2023 | 0 | Resource Division | 34.13 | 0 | 0
1856 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 315 mm diameter (OD) HDPE pipe by Horizontal Directional Drilling (HDD) process at South Bishnupur More on PWD road in between nodes 17 & 17a within Mandirbazar Block for Secondry Grid of under Providing Functional Household Tap Connection (FHTC) in Zone-VIII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte.(SM/11239) | AE HQ-I |  | ORD/000253/2024-2025 | 2716/SWD-I | 10/06/2024 | 25 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 50.53 | 0 | 100
1857 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-VIII at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5655] | AE HQ-I |  | ORD/000618/2022-2023 | 3218/SWD-I | 28/02/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 377.53 | 0 | 0
1858 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000058/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 34.83 | 0 | 0
1859 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Gangadharpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18697) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000359/2024-2025 | 2872/AD | 08/07/2024 | 75 | SUPER SKILL | 178.53 | 0 | 0
1860 | Alipore Division | Kakdwip Sub-Division | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000532/2023-2024 | 3740/AD | 03/11/2023 | 693 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 489.98 | 0 | 20
1861 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000533/2023-2024 | 2146/AD | 09/08/2023 | 601 | SUPER SKILL | 312.7 | 0 | 30
1862 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000556/2023-2024 | 2238/AD | 11/08/2023 | 493 | S.M. ENTERPRISE | 18.81 | 0 | 100
1863 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000577/2023-2024 | 2263/AD | 14/08/2023 | 30 | M/S. SIKHA ENTERPRISE | 30.66 | 0 | 0
1864 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Gangadharpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000641/2023-2024 | 2033/AD | 05/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 8.84 | 0 | 100
1865 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 700 cum. capacity OHR of Dakshin Gangadharpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002071/2023-2024 | 767(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1866 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1867 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000304/2023-2024 | 3099/AD | 28/09/2023 | 0 | Resource Division | 133.07 | 0 | 0
1868 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000308/2023-2024 | 3117/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1869 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000526/2023-2024 | 4986/AD | 26/12/2023 | 0 | Resource Division | 16.64 | 0 | 0
1870 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000568/2023-2024 | 79/AD | 03/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
1871 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000767/2023-2024 | 601/AD | 29/01/2024 | 0 | Resource Division | 5.56 | 0 | 0
1872 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H-1, Zone- I of Augmentation of Dakshin Gangadarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000758/2023-2024 | 2688/SMD | 16/08/2023 | 90 | MAA TARA CONSTRUCTION | 10.52 | 0 | 0
1873 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01508/2023-2024 | BP-2023-24-180 | 02/08/2023 | 0 | WBSEDCL | 3.18 | 0 | 0
1874 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Mathurapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 321/SMD | 06/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 22.58 | 0 | 45
1875 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Mathurapur PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002427/2023-2024 | 274/SMSD | 28/02/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.89 | 0 | 100
1876 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 of Mathurapur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002464/2024-2025 | 439/SMSD | 09/04/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.29 | 0 | 0
1877 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.43] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00466/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0
1878 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of MATHURAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000561/2024-2025 | 4234/SWD-I | 30/09/2024 | 60 | SUPER CONSTRUCTION | 81.22 | 0 | 0
1879 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for MATHURAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015390] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000627/2022-2023 | 3236/SWD-I | 01/03/2023 | 30 | SABYASACHI CHAKI | 31.6 | 0 | 50
1880 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Mathurapur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1611] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 3612/SWD-I | 24/03/2023 | 300 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 404.21 | 0 | 50
1881 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of MATHURAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2024-2025 | 4674/SWD-I | 18/11/2024 | 45 | BANGA NIRMAN | 12.67 | 0 | 0
1882 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of MATHURAPUR Piped Water Supply Scheme of BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/13500] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001102/2024-2025 | 78/SWD-I | 07/01/2025 | 90 | PRANTIK DRILLING AGENCY | 15.9 | 0 | 50
1883 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 33.04 | 0 | 0
1884 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000256/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 9.92 | 0 | 0
1885 | Alipore Division |  | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000466/2021-2022 | 2414/AD | 15/09/2021 | 45 | PIJUSH KANTI TRIPATHI | 13.41 | 0 | 100
1886 | Alipore Division |  | Surging and repairing of 1st Tube well of Kusumtala Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. |  |  | ORD/000597/2022-2023 | 5922/AD | 19/10/2022 | 15 | S.K.GOLUI | 5.1 | 0 | 100
1887 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households and operation & maintenance for 1(One) year and repairing of distribution main of Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001373/2020-2021 | 5129/AD | 08/02/2021 | 365 | PIJUSH KANTI TRIPATHI | 73.47 | 35.34 | 100
1888 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Andharmanik water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/000754/2023-2024 | 2685/SMD | 16/08/2023 | 90 | NUPUR CHANDRA HALDER | 22.36 | 0 | 0
1889 | South 24 Pgs W/S Division I |  | Construction of 4 (four) nos pipe carrying structures including laying of 150mm dia M.S. distribution Pipe at Node Point 71-101 (27.50mtr), 100mm M.S. distribution Pipe at Node Point 107-111 (44.00mtr) and 80mm M.S. distribution Pipe at Node Point 302-310 (22.00mtr) & Node Point 214-215 (16.50mtr) over Nepalgaunge-Julpia canal and 2 (two) nos Culvert crossing by laying of 150mm dia M.S distribution Pipe at Node point 358-359 (11.00mtr) & Node point 358-359 (11.00mtr) for ANDHARMANIK PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based water supply scheme in arsenic affected areas of South 24 Parganas District. [SM/18680] |  |  | ORD/000127/2025-2026 | 1782/SWD-I | 02/07/2025 | 60 | SRIJON ENTERPRISE | 24.53 | 0 | 0
1890 | South 24 Pgs W/S Division I |  | Laying rising main and additional pipeline for distribution system, construction of boundary wall, approach road, pipeline protection, land development and road restoration for ANDHARMANIK PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/18680) |  |  | ORD/000371/2024-2025 | 3530/SWD-I | 07/08/2024 | 526 | J. D. ENTERPRISE | 204.18 | 0 | 20
1891 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for ANDHARMANIK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3023) [TSM/016562]. |  |  | ORD/000410/2023-2024 | 1937/SWD-I | 22/08/2023 | 90 | TARUN ENTERPRISE | 475.56 | 0 | 40
1892 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of ANDHARMANIK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000463/2021-2022 | 1975/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 3.1 | 0 | 100
1893 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 23.18 | 0 | 0
1894 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment for quotation for new service connection at Bhandaria PWSS, PH No. - I (JL No- 142, Mouza- Chamni) Application No- 1008184995 Reference ID- 106819600 Memo No- 1008184995/Quot/03/945 Quotation Date- 14-11-2024 | AE SWSD-II | JE1 | BILL/01897/2024-2025 | BP-2024-25-480 | 28/11/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
1895 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of Quotation for new service connection at Bhandaria PWSS PH No- 3 under Bishnupur-I Block. Application No- 1008242098 Application Date- 09-12-2024 Reference ID- 106856036 Memo No- 1008242098/Quot/03 | AE SWSD-II | JE1 | BILL/02239/2024-2025 | BP-2024-25-495 | 19/12/2024 | 0 | WBSEDCL | 6.08 | 0 | 0
1896 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3&4, of Bhandaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II | JE1 | ORD/000755/2023-2024 | 2686/SMD | 16/08/2023 | 90 | MAHADEV ENTERPRISE | 52.04 | 0 | 0
1897 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for initial 50% amount of the estimated cost Rs 3983175.00(Rupees thirty nine lakh eighty three thousand one hundred seventy five only) i.e. Rs 1991587.50 round off Rs 1991588.00( Rupees nineteen lakh ninety one thousand five hundred eighty eight only) toward road restoration work of Pailan Nepalgunj (ch from 0.00 km to 1.450 km, left hand side) Road under Doulatpur & Kastamahal Pipe Water Supply Scheme in Bishnupur-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. | AE SWSD-II | JE1 | BILL/00347/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 19.92 | 0 | 0
1898 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall for 2nd & 3rd T/W site for BHANDARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas for Augmentation of Surface Water Based Water Supply Sheme in the Arsenic affected areas of South 24 Parganas District. (51 mtr. For each site) [SM/18681] | AE SWSD-II | JE1 | ORD/000262/2024-2025 | 2677/SWD-I | 07/06/2024 | 524 | S.P. ENTERPRISE | 13.56 | 0 | 93
1899 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Rising Main and additional pipeline as per revised design and drawing of distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in Bishnupur-I block under South 24 Pgs W/S Division-I, South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18681) | AE SWSD-II | JE1 | ORD/000263/2024-2025 | 2678/SWD-I | 07/06/2024 | 505 | M/S. S.S. ENTERPRISE (NODAKHALI) | 91.24 | 0 | 65
1900 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 02 nos. pump houses, approach road, land development and pipeline protection of rising and distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24-Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18681) | AE SWSD-II | JE1 | ORD/000272/2024-2025 | 2922/SWD-I | 25/06/2024 | 556 | M/S. S.S. ENTERPRISE (NODAKHALI) | 76.09 | 0 | 22
1901 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BHANDARIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017323] | AE SWSD-II | JE1 | ORD/000378/2023-2024 | 1812/SWD-I | 16/08/2023 | 472 | MD RUHUL AMIN GOLDER | 15.89 | 0 | 98
1902 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of BHANDARIA PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017323] (2nd call) | AE SWSD-II | JE1 | ORD/000383/2023-2024 | 1819/SWD-I | 16/08/2023 | 60 | KAMALA TRADING COMPANY | 17.64 | 0 | 0
1903 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed BHANDARIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3721] | AE SWSD-II | JE1 | ORD/000406/2023-2024 | 1923/SWD-I | 22/08/2023 | 847 | M/S. S.S. ENTERPRISE | 482.45 | 0 | 78
1904 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd and 3rd tubewell site for BHANDARIA Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/18681) | AE SWSD-II | JE1 | ORD/000687/2024-2025 | 4482/SWD-I | 30/10/2024 | 93 | MONDAL TUBEWELL | 31.71 | 0 | 50
1905 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Bhandaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000955/2022-2023 | 1130/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.89 | 0 | 100
1906 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of temporary approach road and land development for the 2nd Tubewell site of Bhandaria PWSS of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District [SM/18681] | AE SWSD-II | JE1 | ORD/001081/2024-2025 | 5348/SWD-I | 30/12/2024 | 30 | MD RUHUL AMIN GOLDER | 7.8 | 0 | 0
1907 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000093/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 58.78 | 0 | 0
1908 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-I at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9379) | AE HQ-I |  | ORD/000423/2023-2024 | 1970/SWD-I | 24/08/2023 | 1062 | MAA MANASA VYAPAAR | 1837.75 | 0 | 5
1909 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000050/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 57.77 | 0 | 0
1910 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Tambuldaha (Part - II) having village with maximum 143 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000659/2022-2023 | 6165/AD | 01/11/2022 | 60 | G. S. CONSTRUCTION & CO. | 47.99 | 0 | 51
1911 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tambuldaha (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001914/2022-2023 | 5154/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
1912 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Tambul Daha (Part-II) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000599/2022-2023 | 669/SMD | 09/03/2023 | 90 | M/S. SREEJIT ENTEPRISE | 8.85 | 0 | 0
1913 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01822/2022-2023 | BP-2022-23-463 | 23/03/2023 | 0 | WBSEDCL | 1.04 | 0 | 0
1914 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Dakhin Roypur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000649/2022-2023 | 764/SMD | 15/03/2023 | 90 | M/S. S.S. ENTERPRISE | 11.7 | 0 | 55
1915 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 0 | 98
1916 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for water supply at Dakhin Raypur W/S Scheme under South 24 Pgs W/S Division - I, PHE Dte. in the district of South 24 Parganas. [TSM/017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000349/2022-2023 | 2165/SWD-I | 09/12/2022 | 30 | ZINARUL ISLAM | 14.64 | 0 | 100
1917 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Dakhin Raypur Mouza of Budge Budge-II block under South 24 Parganas W/S Divn.-I, PHE Dte. [TSM/ 017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000350/2022-2023 | 2194/SWD-I | 13/12/2022 | 45 | MODERN CONSTRUCTION | 6.92 | 0 | 100
1918 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Dakhin Roypur Village(JL 70) of Budge Budge-II under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000351/2022-2023 | 2195/SWD-I | 13/12/2022 | 60 | JYOTI ENTERPRISE | 6.81 | 0 | 100
1919 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing pipe supporting structures for crossing gaps over newly constructed irrigation culverts with allied works for DAKSHIN RAYPUR PWSS to accommodate FHTC in Budge Budge -II block under South 24 Parganas W/S division-I, P.H.E. Dte of South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas South 24-Pgns District (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000362/2024-2025 | 3504/SWD-I | 07/08/2024 | 45 | SUKUMAR DEBNATH | 13.33 | 0 | 50
1920 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Pipe supporting structure with allied works under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000399/2023-2024 | 1908/SWD-I | 21/08/2023 | 60 | SUKUMAR DEBNATH | 4.08 | 0 | 100
1921 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Constructure of retaining Structure near Pump House under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000413/2023-2024 | 1915/SWD-I | 21/08/2023 | 60 | SOHINI ENTERPRISE | 2.02 | 0 | 100
1922 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for retrofitting of distribution system of Dakhin Raypur Village & providing FHTC under SWD - I, P.H.E. Dte District South 24 Parganas. (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000511/2022-2023 | 2941/SWD-I | 16/02/2023 | 60 | M/S. S.S. ENTERPRISE | 104.69 | 0 | 90
1923 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying HDPE pipeline under Ground Water Based Piped Water Supply Scheme of Dakshin Roypur to accommodate Functional Household Tap Connection (FHTC) in Budge Budge-II block South 24 Pgns. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns Dist. under South 24 Pgns. Water Supply Division-I, PHE Dte. (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000662/2022-2023 | 3378/SWD-I | 10/03/2023 | 45 | S.P. ENTERPRISE | 6.05 | 0 | 100
1924 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at Dakshin Roypur PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13920] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000698/2022-2023 | 3501/SWD-I | 16/03/2023 | 15 | MAHI CONSTRUCTION | 2.17 | 0 | 0
1925 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Development of land at Dakdhin Roypur PWSS Tubewell site (JL No.-70, RS-352/984, LR Dag No.- 495) under Dakshin Roypur PWSS to accomodate FHTC in Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Area of South 24-Pgns. Dist. (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000744/2022-2023 | 3595/SWD-I | 23/03/2023 | 15 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 5.05 | 0 | 0
1926 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Roypur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000992/2022-2023 | 1532/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.42 | 0 | 100
1927 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000122/2022-2023 | 3473/SWD-I | 15/03/2023 | 0 | Resource Division | 2.37 | 0 | 0
1928 | S24 Pgns Mechanical |  | Charges for new service connection at Jagadishpur pump house-I (Sonarpur Block) |  |  | BILL/00394/2024-2025 | BP-2024-25-92 | 10/06/2024 | 0 | WBSEDCL | 10.06 | 0 | 0
1929 | S24 Pgns Mechanical |  | Charges for service connection at Pump house no-II of Jagadishpur (Sonarpur Block) |  |  | BILL/00395/2024-2025 | BP-2024-25-93 | 10/06/2024 | 0 | WBSEDCL | 7.05 | 0 | 0
1930 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Jagadishpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000120/2023-2024 | 1097/SMD | 18/04/2023 | 744 | DEBJYOTI BASU | 22.79 | 0 | 100
1931 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18497) |  |  | ORD/000244/2024-2025 | 2664/SWD-I | 07/06/2024 | 45 | JYOTI ENTERPRISE | 10.26 | 0 | 0
1932 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGADISHPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/017715] |  |  | ORD/000293/2023-2024 | 1658/SWD-I | 03/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
1933 | South 24 Pgs W/S Division I |  | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2503) (TSM/017715) |  |  | ORD/000426/2023-2024 | 1986/SWD-I | 25/08/2023 | 799 | G.B. CONSTRUCTION AND CO. | 703.02 | 0 | 50
1934 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall,Land Development, Pathway,Drain & others allied works of Jagadishpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18497] |  |  | ORD/000842/2023-2024 | 1208/SWD-I | 11/03/2024 | 45 | G.B. CONSTRUCTION AND CO. (DUMDUM) | 46.14 | 0 | 0
1935 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 18.81 | 0 | 0
1936 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 255/SWD-I | 10/01/2024 | 0 | Resource Division | 15.42 | 0 | 0
1937 | S24 Pgns Mechanical |  | Quotation for new service ( power) connection at Serpur PH-1, Water supply scheme under Bhangar-I block Reference ID106663976 Application No-1007921408 |  |  | BILL/01682/2024-2025 | BP-2024-25-395 | 27/09/2024 | 0 | WBSEDCL | 22.96 | 0 | 0
1938 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Serpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001526/2022-2023 | 932/SMD | 30/03/2023 | 732 | S. DUTTA | 25.42 | 0 | 35
1939 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SERPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018414] |  |  | ORD/000362/2023-2024 | 1771/SWD-I | 11/08/2023 | 30 | JSSM CONSTRUCTION | 31.72 | 0 | 50
1940 | South 24 Pgs W/S Division I |  | Construction of 450 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2549) (TSM/018414) |  |  | ORD/000421/2023-2024 | 1968/SWD-I | 24/08/2023 | 300 | SAMSUL ENTERPRISE | 468.39 | 0 | 20
1941 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) |  |  | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 45 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 0 | 100
1942 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18500) |  |  | ORD/001084/2024-2025 | 5212/SWD-I | 20/12/2024 | 60 | SAMSUL ENTERPRISE | 64.9 | 0 | 0
1943 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 17.47 | 0 | 0
1944 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 249/SWD-I | 10/01/2024 | 0 | Resource Division | 15.7 | 0 | 0
1945 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Tardaha Kapasati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001518/2022-2023 | 907/SMD | 28/03/2023 | 90 | S. DUTTA | 25.09 | 0 | 0
1946 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.37] |  |  | BILL/00467/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 65.69 | 0 | 0
1947 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TARDAHA KAPASATI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018470] |  |  | ORD/000301/2023-2024 | 1666/SWD-I | 03/08/2023 | 30 | ASIT PRAMANIK | 31.76 | 0 | 99
1948 | South 24 Pgs W/S Division I |  | Construction of 450 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for TARDAHA KAPASATI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3298) (TSM/018470) |  |  | ORD/000354/2023-2024 | 1740/SWD-I | 10/08/2023 | 300 | MRA NIRMAN UDYOG | 1034.36 | 0 | 35
1949 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) |  |  | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 45 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 0 | 100
1950 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of TARDAH KAPASATI PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18501) |  |  | ORD/000678/2024-2025 | 4467/SWD-I | 29/10/2024 | 75 | MRA NIRMAN UDYOG | 201.31 | 0 | 0
1951 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 44.58 | 0 | 0
1952 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 256/SWD-I | 10/01/2024 | 0 | Resource Division | 20.32 | 0 | 0
1953 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-II) Water Supply Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000111/2021-2022 | 1194/AD | 07/07/2021 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.47 | 0 | 51
1954 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000281/2023-2024 | 3080/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1955 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000794/2023-2024 | 639/AD | 30/01/2024 | 0 | Resource Division | 9.86 | 0 | 0
1956 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Mahishmari Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001243/2020-2021 | 2274/AD | 12/10/2020 | 365 | M. MUKHERJEE | 106.14 | 80.41 | 95
1957 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part B) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000015/2022-2023 | 332/AD | 18/04/2022 | 365 | M/S. ROY CHOWDHURY & CO. | 110.99 | 0 | 68
1958 | Alipore Division | Canning Sub-division | Relaying and repairing of pipeline Daria Water Supply Scheme near PH - 1, 2 and 3 Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000112/2021-2022 | 1195/AD | 07/07/2021 | 45 | DEBARATI ENTERPRISE | 35.86 | 0 | 100
1959 | Alipore Division | Canning Sub-division | Repairing and extension of pipeline for FHTC work for Daria Waster Supply Scheme, Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000197/2022-2023 | 2642/AD | 29/06/2022 | 30 | A.K. SIKDAR | 16.14 | 0 | 100
1960 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. [Part - A] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001136/2021-2022 | 5542/AD | 20/01/2022 | 365 | A.K. SIKDAR | 47.45 | 0 | 100
1961 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000014/2021-2022 | 5620/AD | 25/01/2022 | 0 | Resource Division | 5.4 | 0 | 0
1962 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000017/2022-2023 | 1174/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
1963 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 365 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 0 | 90
1964 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 15 | SUDIP PRADHAN | 11.34 | 0 | 90
1965 | Alipore Division | Kakdwip Sub-Division | Laying D.I. Pipe Line for Rising Main and inter connection in between Tubewell No. 1 & Tubewell No. 2 for Srinagar W/S Scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001935/2020-2021 | 1348/KSD | 23/02/2021 | 10 | SARADA CONSTRUCTION | 4.77 | 0 | 80
1966 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Banibadabelekhali Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000087/2020-2021 | 5123/AD | 08/02/2021 | 365 | DIVINE | 162.5 | 105.59 | 92
1967 | Alipore Division | Canning Sub-division | Construction of concrete road (balanced portion) in OHR premises of Pump House no. - 1 of Banibadabelekhali W/S Scheme, Block - Canning I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000370/2025-2026 | 671/CSD | 26/05/2025 | 30 | A.N.S. ENTERPRISE | 1.71 | 0 | 0
1968 | Alipore Division | Kakdwip Sub-Division | Hire Charges Vehicle bill (June '22 to Oct'22) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03273/2023-2024 |  | 20/03/2024 | 0 | RAJKUMAR MANNA | 6.29 | 0 | 0
1969 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of June'22 to August'22 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03275/2023-2024 | BP-2023-24-1259 | 26/03/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
1970 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Taktipur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000412/2024-2025 | 3063/AD | 25/07/2024 | 45 | RAJ ENTERPRISE | 38.71 | 0 | 0
1971 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Taktipur Zone- II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11876) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000466/2024-2025 | 3461/AD | 23/08/2024 | 45 | GHOSH CONSTRUCTION | 18.54 | 0 | 0
1972 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 29.09.2022 to 30.11.2022 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000776/2022-2023 | 266/HQ-II/AD | 28/09/2022 | 63 | PRIYANKI SADHUKHAN | 0.8 | 0 | 85
1973 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001870/2020-2021 | 1301/KSD | 23/02/2021 | 10 | M/S THREE STAR & CON. | 4.39 | 0 | 93
1974 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001874/2020-2021 | 1303/KSD | 23/02/2021 | 10 | M/S. MAA MENAKA ENTERPRISE | 4.38 | 0 | 93
1975 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001889/2020-2021 | 1311/KSD | 23/02/2021 | 10 | M/S THREE STAR & CON. | 4.38 | 0 | 92
1976 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001907/2020-2021 | 1322/KSD | 23/02/2021 | 10 | M/S. MA LAXMI ENTERPRISE | 4.38 | 0 | 93
1977 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Naskarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001919/2020-2021 | 1329/KSD | 23/02/2021 | 10 | MOUMITA ENTERPRISE | 4.39 | 0 | 93
1978 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Janarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001921/2020-2021 | 1331/KSD | 23/02/2021 | 10 | MOUMITA ENTERPRISE | 4.39 | 0 | 93
1979 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001925/2020-2021 | 1337/KSD | 23/02/2021 | 10 | SUFIA ENTERPRISE | 4.39 | 0 | 93
1980 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001927/2020-2021 | 1339/KSD | 23/02/2021 | 10 | M/S. MA LAXMI ENTERPRISE | 4.39 | 0 | 93
1981 | Alipore Division | Kakdwip Sub-Division | Laying UPVC Pipe Line for Providing House Connection to the Households of Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001929/2020-2021 | 1342/KSD | 23/02/2021 | 15 | SARADA CONSTRUCTION | 3.07 | 0 | 100
1982 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001931/2020-2021 | 1344/KSD | 23/02/2021 | 10 | SUFIA ENTERPRISE | 4.38 | 0 | 86
1983 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001933/2020-2021 | 1346/KSD | 23/02/2021 | 10 | M/S. MAA MENAKA ENTERPRISE | 4.39 | 0 | 91
1984 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001970/2020-2021 | 1335/KSD | 23/02/2021 | 10 | M/S MAA BASANTI ENTERPRISE | 4.38 | 0 | 93
1985 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001972/2020-2021 | 1341/KSD | 23/02/2021 | 10 | M/S MAA BASANTI ENTERPRISE | 4.38 | 0 | 92
1986 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000824/2023-2024 | 669/AD | 30/01/2024 | 0 | Resource Division | 8.82 | 0 | 0
1987 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Maukhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000070/2021-2022 | 867/AD | 21/06/2021 | 365 | TANMAY ROY CHOWDHURY | 203.52 | 59.8 | 44
1988 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Puinjali Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000089/2020-2021 | 5124/AD | 08/02/2021 | 365 | RAMEN GHOSH | 87.24 | 0 | 82
1989 | Alipore Division | Canning Sub-division | Laying of pipeline of uncovered FHTC work area of Puinjali Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001179/2022-2023 | 8775/AD | 21/12/2022 | 30 | RAMEN GHOSH | 18.23 | 0 | 80
1990 | Alipore Division | Canning Sub-division | Providing support service for detail surveying, cross checking of available LOP with making permission drawing for other department by using Survey Instruments at Kolkata-Basanti Road (SH 3A, from chainage 71.000 to 86.790), Basanti-Godkhali Road (SH 3A, from chainage 0.000 to 9.894) and Bharatgar Bazar to Ganga Mela Road (from chainage 5.800 to 11.900) like Remotely Piloted Aircraft System / DGPS / Total Station etc. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000272/2022-2023 | 265/CSD | 19/05/2022 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 1.82 | 0 | 98
1991 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000749/2024-2025 | 4421/AD | 05/11/2024 | 30 | RAKTIM ENTERPRISE | 27.39 | 0 | 0
1992 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000750/2024-2025 | 4422/AD | 05/11/2024 | 30 | RAKTIM ENTERPRISE | 12.56 | 0 | 0
1993 | Alipore Division | Canning Sub-division | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001735/2020-2021 | 1438/CSD | 25/01/2021 | 30 | SRIJON ENTERPRISE | 4.8 | 0 | 100
1994 | Alipore Division | Canning Sub-division | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001736/2020-2021 | 1439/CSD | 25/01/2021 | 30 | SRIJON ENTERPRISE | 4.69 | 0 | 98
1995 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials at TW No. 1 & 5 of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/003338/2024-2025 | 36./CSD | 09/01/2025 | 30 | RAKTIM ENTERPRISE | 2.04 | 0 | 0
1996 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000400/2023-2024 | 358/AD | 19/01/2024 | 0 | Resource Division | 3.39 | 0 | 0
1997 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Jyotishpur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001302/2020-2021 | 2101/AD | 01/10/2020 | 365 | M/S. JAYDEEP DASGUPTA | 108.5 | 66.19 | 100
1998 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nischintipur W/S Scheme for Nischintipur Mouza near Head work Site and ajoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000114/2020-2021 | 1359/SWD-I | 08/12/2020 | 120 | JDJ ENTERPRISE | 91.87 | 80.02 | 0
1999 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/01169/2022-2023 | BP-2023-24-18 | 18/04/2023 | 0 | RAJKUMAR MANNA | 6.51 | 0 | 0
2000 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/01170/2022-2023 | BP-2023-24-31 | 28/04/2023 | 0 | RAJKUMAR MANNA | 6.06 | 0 | 0
2001 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division of Alipore Division, PHE Dte. (01.06.2022 to 31.08.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/03520/2023-2024 | BP-2023-24-1074 | 24/02/2024 | 0 | RAJKUMAR MANNA | 6.51 | 0 | 0
2002 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Bishnupur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000002/2022-2023 | 28/AD | 04/04/2022 | 45 | M. MUKHERJEE | 114.37 | 0 | 98
2003 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Repair and Painting and Approach Road at 1st Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000338/2025-2026 | 3044/AD | 30/06/2025 | 45 | PALASH HALDAR | 5.71 | 0 | 0
2004 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 45 | SWAPAN GUCHHAIT | 3.89 | 0 | 0
2005 | Alipore Division | Kakdwip Sub-Division | Surging of 3 nos. Tubewell for Augmentation of Bishnupur- 1 no., Mahishamari- 1 no., Kamalpur Rudranagar- 1 no. W/S Scheme under JJM, Block - Sagar under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000506/2024-2025 | 3607/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 5.34 | 0 | 100
2006 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000382/2023-2024 | 3568/AD | 18/10/2023 | 0 | Resource Division | 10.38 | 0 | 0
2007 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000694/2023-2024 | 464/AD | 24/01/2024 | 0 | Resource Division | 10.19 | 0 | 0
2008 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - S) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000759/2024-2025 | 4442/AD | 06/11/2024 | 30 | M/S. MANDAL ENTERPRISE | 9.79 | 0 | 100
2009 | Alipore Division | Kakdwip Sub-Division | HIRING OF AN INSPECTION VEHICLE (DIESEL OPERATED WITH LUXURY PERMIT) FOR USE OF ASSISTANT ENGINEER (HQ-II), ALIPORE DIVISION, PHE DTE. (FOR THE PERIOD FROM 01.09.2024 TO 28.02.2025) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000864/2024-2025 | 3534/HQ-II/AD | 30/08/2024 | 182 | BINDU PRASAD DEVI | 2.4 | 0 | 55
2010 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.03.2024 to 30.06.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/003075/2023-2024 | 1142/AD | 27/02/2024 | 121 | M/S P. B. CONSTRUCTION | 1.6 | 0 | 0
2011 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000074/2022-2023 | 4849/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
2012 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000378/2023-2024 | 3517/AD | 16/10/2023 | 0 | Resource Division | 14.31 | 0 | 0
2013 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XVII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000132/2023-2024 | 674/AD | 17/05/2023 | 813 | BALAJI UDDYOG | 553.99 | 0 | 60
2014 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000636/2023-2024 | 240/AD | 15/01/2024 | 0 | Resource Division | 12.62 | 0 | 0
2015 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001057/2021-2022 | 2345/AD | 09/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.42 | 0 | 100
2016 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001083/2021-2022 | 574/KSD | 10/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 0 | 100
2017 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & boundary wall at 3rd Tubewell site for Mandirtala (PH-3, Kuntala) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08805) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001292/2024-2025 | 1925/KSD | 20/12/2024 | 25 | IMAGINEER VENTURES | 3.29 | 0 | 100
2018 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001618/2021-2022 | 618/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.32 | 0 | 100
2019 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000706/2023-2024 | 476/AD | 24/01/2024 | 0 | Resource Division | 21.22 | 0 | 0
2020 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 43 (forty three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sibnagar W/S Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000015/2021-2022 | 3164/AD | 09/11/2021 | 365 | M/S. SAMADDAR CONSTRUCTION | 84.8 | 0 | 80
2021 | Alipore Division | Kakdwip Sub-Division | Surging of 01 no. Big dia Tubewell of Sibnagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000231/2023-2024 | 157/KSD | 01/06/2023 | 20 | S.K.GOLUI | 1.37 | 0 | 95
2022 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2023 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000840/2023-2024 | 688/AD | 30/01/2024 | 0 | Resource Division | 11.37 | 0 | 0
2024 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000323/2022-2023 | 3870/AD | 08/08/2022 | 30 | M/S PIR BABA ENTERPRISE | 5.96 | 0 | 50
2025 | Alipore Division | Kakdwip Sub-Division | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Gangadharpur Water Supply Scheme , Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte.(Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001145/2021-2022 | 5533/AD | 20/01/2022 | 365 | JAI BHARAT COMMERCIAL CORPORATION | 51.59 | 0 | 58
2026 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000018/2021-2022 | 5624/AD | 25/01/2022 | 0 | Resource Division | 4.4 | 0 | 0
2027 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000273/2023-2024 | 3072/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2028 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000803/2023-2024 | 648/AD | 30/01/2024 | 0 | Resource Division | 3.79 | 0 | 0
2029 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 120 | M/S. SUMAN ENTERPRISE | 236.89 | 0 | 95
2030 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000037/2022-2023 | 3584/AD | 29/07/2022 | 0 | Resource Division | 37.95 | 0 | 0
2031 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing for Retrofitting of Bhangankhali W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000817/2022-2023 | 6812/AD | 16/11/2022 | 30 | BANGA NIRMAN | 7.18 | 0 | 0
2032 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Retrofitting of Bhangankhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000854/2022-2023 | 6993/AD | 19/11/2022 | 30 | M/S SEKH ENTERPRISE | 19.48 | 0 | 0
2033 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001836/2021-2022 | 658/CSD | 12/08/2021 | 15 | HORIZEN | 2.81 | 0 | 100
2034 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001837/2021-2022 | 659/CSD | 12/08/2021 | 15 | HORIZEN | 3.33 | 0 | 100
2035 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000389/2023-2024 | 330/AD | 19/01/2024 | 0 | Resource Division | 13.96 | 0 | 0
2036 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte. District South 24 Parganas. | AE SWSD-I |  | ORD/000088/2021-2022 | 1205/SWD-I | 09/11/2021 | 120 | SATYABRATA CHAKRABORTY | 268.77 | 0 | 60
2037 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Buita W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM/ 8292 ) PART-VII | AE SWSD-I |  | ORD/000456/2022-2023 | 2728/SWD-I | 27/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 18.68 | 0 | 100
2038 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000126/2022-2023 | 2029/AD | 21/06/2022 | 30 | M/S BOSE & CO. | 18.21 | 0 | 0
2039 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000127/2022-2023 | 2030/AD | 21/06/2022 | 30 | M/S BOSE & CO. | 16.85 | 0 | 0
2040 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 4 nos Pump House site of Haripur (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18698) (SM/09075) (SM/09076) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000378/2025-2026 | 3253/AD | 09/07/2025 | 45 | SAMANTA AND COMPANY | 4.35 | 0 | 0
2041 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000076/2022-2023 | 5145/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
2042 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000290/2023-2024 | 3085/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2043 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of habitation - Das Para and Majher Para at Companirchar Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001137/2021-2022 | 5529/AD | 20/01/2022 | 365 | SANKAR HALDER | 28.77 | 0 | 96
2044 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of habitation ¿ Companir Char and Uttar Para at Companir Char Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001140/2021-2022 | 5530/AD | 20/01/2022 | 365 | SWAPAN KUMAR PRADHAN | 36.94 | 0 | 94
2045 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000015/2022-2023 | 1171/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
2046 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000025/2021-2022 | 5762/AD | 02/02/2022 | 0 | Resource Division | 206.4 | 0 | 0
2047 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000700/2023-2024 | 470/AD | 24/01/2024 | 0 | Resource Division | 9.29 | 0 | 0
2048 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Damkal mouza (JL No. 133) in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000347/2022-2023 | 4074/AD | 18/08/2022 | 60 | M/S B.M. CONSTRUCTION | 62.36 | 0 | 90
2049 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Purba Sridharpur mouza (JL No. 131) and Nagendrapur Mouza (JL No. 132)in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000348/2022-2023 | 4075/AD | 18/08/2022 | 60 | JAL PRAVAHIKA PVT. LTD. | 84.29 | 0 | 99
2050 | Alipore Division | Raidighi Sub-Division | Land development of OHR site at Zone - IX, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001802/2022-2023 | 932/RSD | 10/03/2023 | 30 | G.B. CONSTRUCTION & CO. | 2.27 | 0 | 10
2051 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000036/2022-2023 | 3583/AD | 29/07/2022 | 0 | Resource Division | 73 | 0 | 0
2052 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000647/2023-2024 | 250/AD | 15/01/2024 | 0 | Resource Division | 21.81 | 0 | 0
2053 | Alipore Division | Raidighi Sub-Division | Repairing of pump house ? 1 & 3 and approach road and plinth protection at Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000993/2023-2024 | 290/RSD | 29/09/2023 | 60 | M/S. BISWAS CONSTRUCTION (II) | 3.95 | 0 | 100
2054 | Alipore Division | Raidighi Sub-Division | Repairing of boundary wall at Head work site of Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000994/2023-2024 | 291/RSD | 29/09/2023 | 60 | SANKAR HALDER | 4.77 | 0 | 100
2055 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-I (Uttar Kashinagar PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001455/2021-2022 | 6070/AD | 17/02/2022 | 365 | SPA ENTERPRISE | 117 | 0 | 70
2056 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000041/2022-2023 | 3582/AD | 29/07/2022 | 0 | Resource Division | 16.52 | 0 | 0
2057 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000078/2022-2023 | 5550/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
2058 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Dakshin Shibganj W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000230/2023-2024 | 156/KSD | 01/06/2023 | 25 | S.K.GOLUI | 3.36 | 0 | 99
2059 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Dakshin Shibganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/10482) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000380/2024-2025 | 3056/AD | 25/07/2024 | 60 | TRIPTI ENTERPRISE | 171.55 | 0 | 0
2060 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 45 | M/S B. ENTERPRISE | 28.74 | 0 | 60
2061 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Shibganj PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000457/2022-2023 | 298/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.29 | 0 | 0
2062 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000789/2023-2024 | 2785/AD | 12/09/2023 | 300 | TRIPTI ENTERPRISE | 191.9 | 0 | 30
2063 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
2064 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002185/2022-2023 | 691/KSD | 23/02/2023 | 365 | M/S B. ENTERPRISE | 1.05 | 0 | 100
2065 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002607/2023-2024 | 293/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2066 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000052/2022-2023 | 3913/AD | 12/08/2022 | 0 | Resource Division | 72.71 | 0 | 0
2067 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000310/2023-2024 | 3119/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2068 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000774/2023-2024 | 608/AD | 29/01/2024 | 0 | Resource Division | 11.08 | 0 | 0
2069 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Alipore water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000468/2022-2023 | 279/SMD | 01/02/2023 | 1065 | NITESH MANAGEMENT | 26.52 | 0 | 40
2070 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for ALIPOREPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000031/2022-2023 | 915/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.18 | 0 | 100
2071 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed ALIPORE PIPE WATER SUPPLY SCHEME Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 1038] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000184/2022-2023 | 1487/SWD-I | 28/09/2022 | 90 | MAA LAXMI ENTERPRISE | 119.84 | 0 | 90
2072 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
2073 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 1st Tubewell site under Alipore PWSS to accommodate FHTC in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000245/2023-2024 | 1487/SWD-I | 19/07/2023 | 15 | MAA LAXMI ENTERPRISE | 2.97 | 0 | 100
2074 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of ALIPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (3rd Call) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000251/2023-2024 | 1498/SWD-I | 20/07/2023 | 361 | RAMASISH ENTERPRISE | 5.91 | 0 | 100
2075 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main & additional pipeline for distribution system, construction of boundary walls for 1st & 2nd Tubewell sites and other allied works for proposed ground water based ALIPORE PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11493) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000274/2024-2025 | 2924/SWD-I | 25/06/2024 | 45 | MAA LAXMI ENTERPRISE | 67.93 | 0 | 0
2076 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "ALIPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000400/2022-2023 | 458/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 0 | 100
2077 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ALIPORE PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000507/2022-2023 | 2905/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 100
2078 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for ALIPORE PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000597/2022-2023 | 3124/SWD-I | 24/02/2023 | 752 | CIVIL CONSULTANT | 15.88 | 0 | 100
2079 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed ALIPORE Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000811/2022-2023 | 3703/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.88 | 0 | 100
2080 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000014/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 6.39 | 0 | 0
2081 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000116/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.09 | 0 | 0
2082 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00003/2024-2025 | BP-2024-25-02 | 05/04/2024 | 0 | WBSEDCL | 4.74 | 0 | 0
2083 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/06297/2023-2024 | BP-2023-24-648 | 30/03/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
2084 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Joykrishnanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000450/2022-2023 | 3930/SMD | 30/12/2022 | 90 | M/S. S.R. ENTERPRISE | 22.37 | 0 | 0
2085 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JOYKRISHNA NAGAR PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 1197/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 100
2086 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JOYKRISHNANAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000217/2021-2022 | 1939/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
2087 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JOYKRISHNANAGAR Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1904) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000341/2022-2023 | 2091/SWD-I | 02/12/2022 | 300 | SUPRITI ENTERPRISE | 534.05 | 0 | 40
2088 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Joykrishnanagar of Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000376/2022-2023 | 2210/SWD-I | 13/12/2022 | 60 | S.M ENTERPRISE | 11.49 | 0 | 0
2089 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JOYKRISHNA NAGAR PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011093] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 2111/SWD-I | 30/08/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.14 | 0 | 0
2090 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000022/2022-2023 | 1983 | 25/11/2022 | 0 | Resource Division | 11.73 | 0 | 0
2091 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000080/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
2092 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - I PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000046/2023-2024 | 31/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2093 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000047/2023-2024 | 32/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2094 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter for Augmentation of Ganeshpur Kalinagar (Zone-I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000119/2024-2025 | 2396AD | 07/06/2024 | 45 | FORTUNE ENGINEERING | 39.72 | 0 | 0
2095 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000129/2021-2022 | 384/KSD | 07/07/2021 | 15 | KHOKAN MONDAL | 4.39 | 0 | 100
2096 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000132/2021-2022 | 387/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.78 | 0 | 100
2097 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000137/2021-2022 | 392/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 100
2098 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000138/2021-2022 | 393/KSD | 07/07/2021 | 15 | KHOKAN MONDAL | 4.39 | 0 | 100
2099 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000150/2021-2022 | 402/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.78 | 0 | 100
2100 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000152/2021-2022 | 404/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.77 | 0 | 100
2101 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000153/2021-2022 | 406/KSD | 07/07/2021 | 15 | TAPAN DAS | 4.77 | 0 | 95
2102 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000164/2024-2025 | 2515/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
2103 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At Head Work Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000202/2024-2025 | 2585/AD | 19/06/2024 | 227 | SOHINI ENTERPRISE | 5.6 | 0 | 0
2104 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000203/2024-2025 | 2586/AD | 19/06/2024 | 45 | GARGO TRADERS | 46.46 | 0 | 0
2105 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Ganeshpur Kalinagar Zone-II W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000233/2023-2024 | 162/KSD | 01/06/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 95
2106 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-I), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000271/2023-2024 | 1421/AD | 13/07/2023 | 45 | ASHIT BARAN BOSE | 61.55 | 0 | 100
2107 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000272/2023-2024 | 1422/AD | 13/07/2023 | 45 | GARGO TRADERS | 65.44 | 0 | 100
2108 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000335/2024-2025 | 2750/AD | 27/06/2024 | 60 | SUDIP PRADHAN | 111.95 | 0 | 0
2109 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000382/2023-2024 | 1775/AD | 26/07/2023 | 45 | SWASTIK CONSTRUCTION | 14.02 | 0 | 100
2110 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000420/2022-2023 | 4346/AD | 25/08/2022 | 60 | G.M. ENTERPRISE | 41.23 | 0 | 20
2111 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000424/2022-2023 | 4347/AD | 25/08/2022 | 30 | ASHIS ENTERPRISE | 16.81 | 0 | 90
2112 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000433/2022-2023 | 4348/AD | 25/08/2022 | 30 | UNIQUE CONSTRUCTION (II) | 16.37 | 0 | 75
2113 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANESHPUR KALINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000490/2022-2023 | 303/AD | 12/04/2022 | 45 | LEMNISCATE | 12.79 | 0 | 100
2114 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000554/2022-2023 | 5728/AD | 13/10/2022 | 880 | GARGO TRADERS | 320.99 | 0 | 40
2115 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Ganeshpur Kalinagar Zone-I W/S Scheme under JJM under Kakdwip Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000635/2023-2024 | 2463/AD | 24/08/2023 | 45 | M/S. BRINDABAN DAS & SONS | 8.5 | 0 | 0
2116 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000669/2022-2023 | 6154/AD. | 01/11/2022 | 90 | S.S. ENTERPRISE (I) | 134.59 | 0 | 80
2117 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000670/2022-2023 | 6155/AD. | 01/11/2022 | 1105 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 168.21 | 0 | 50
2118 | Alipore Division | Kakdwip Sub-Division | Road Restoration for Laying distribution system of Augmentation of Ganeshpur Kalinagar Water Supply Scheme for providing FHTC, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000986/2023-2024 | 3005/AD | 26/09/2023 | 906 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 76.51 | 0 | 100
2119 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001018/2021-2022 | 536/KSD | 01/09/2021 | 20 | LEMNISCATE | 2.82 | 0 | 100
2120 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001023/2021-2022 | 537/KSD | 01/11/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 0 | 100
2121 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001040/2021-2022 | 2271/AD | 06/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 2.58 | 0 | 0
2122 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001041/2021-2022 | 2272/AD | 06/09/2021 | 7 | LEMNISCATE | 4.45 | 0 | 0
2123 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001616/2021-2022 | 615/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 2.62 | 0 | 100
2124 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001617/2021-2022 | 616/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 1.27 | 0 | 100
2125 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001733/2021-2022 | 1006/KSD | 21/02/2022 | 365 | SARADA CONSTRUCTION | 1.46 | 0 | 80
2126 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001782/2020-2021 | 1227/KSD | 23/02/2021 | 10 | M/S. MANIMALA ENTERPRISE | 4.26 | 0 | 100
2127 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001854/2020-2021 | 1285/KSD | 23/02/2021 | 10 | M/S. MANIMALA ENTERPRISE | 4.38 | 0 | 100
2128 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001891/2020-2021 | 1313/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.7 | 0 | 100
2129 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-VI) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001893/2020-2021 | 1315/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 2.91 | 0 | 100
2130 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001896/2020-2021 | 1318/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.74 | 0 | 100
2131 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001905/2020-2021 | 1321/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.3 | 0 | 100
2132 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001914/2020-2021 | 1324/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.61 | 0 | 100
2133 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001916/2020-2021 | 1326/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.74 | 0 | 100
2134 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
2135 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002187/2022-2023 | 689/KSD | 23/02/2023 | 365 | SARADA CONSTRUCTION | 1.54 | 0 | 100
2136 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002536/2023-2024 | 408/KSD | 27/02/2024 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
2137 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000055/2022-2023 | 3905/AD | 12/08/2022 | 0 | Resource Division | 147.3 | 0 | 0
2138 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000090/2022-2023 | 5594/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
2139 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR001001/2023-2024 | 1800/AD | 27/03/2024 | 0 | Resource Division | 18.82 | 0 | 0
2140 | Alipore Division | Baruipur Sub-Division | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01707/2024-2025 | BP-2024-25-792 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
2141 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for New service connection at Pump house no-2 of Belegachi water supply scheme.(Baruipur Block) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01681/2024-2025 | BP-2024-25-397 | 27/09/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
2142 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05703/2023-2024 | BP-2023-24-611 | 28/03/2024 | 0 | WBSEDCL | 8.73 | 0 | 0
2143 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Belegachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000448/2022-2023 | 3928/SMD | 30/12/2022 | 884 | M/S.UTTAM KUMAR CHATTERJEE | 22.36 | 0 | 100
2144 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.34] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00494/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 0.68 | 0 | 0
2145 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for BELEGACHI PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 1196/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 100
2146 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BELGACHHI Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000215/2021-2022 | 1937/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
2147 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BELEGACHI Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1604) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000343/2022-2023 | 2148/SWDI | 08/12/2022 | 300 | M/S. S.S. ENTERPRISE | 524.03 | 0 | 50
2148 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Belegachi at Baruipur Block for under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 2202/SWD-I | 13/12/2022 | 60 | M/S. TORSA ENTERPRISE | 11.51 | 0 | 100
2149 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of BELEGACHI PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011099] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 2110/SWD-I | 30/08/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.14 | 0 | 100
2150 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000082/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 14.96 | 0 | 0
2151 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) | AE HQ-I |  | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 780 | BALAJEE ENTERPRISES | 760.19 | 0 | 75
2152 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000054/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 23.59 | 0 | 0
2153 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kumarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000069/2023-2024 | 50/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2154 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kumarpur, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000283/2023-2024 | 1708/AD | 22/07/2023 | 45 | S & P ENTERPRISE | 34.38 | 0 | 100
2155 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000301/2022-2023 | 3837/AD | 08/08/2022 | 1271 | M/S CHANDIMATA CONSTRUCTION | 60.21 | 0 | 40
2156 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000302/2022-2023 | 3838/AD | 08/08/2022 | 1241 | M/S CHANDIMATA CONSTRUCTION | 12.99 | 0 | 0
2157 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000303/2022-2023 | 3839/AD | 08/08/2022 | 1211 | M/S CHANDIMATA CONSTRUCTION | 7.93 | 0 | 0
2158 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KUMARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000462/2022-2023 | 1707/AD | 14/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.46 | 0 | 100
2159 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Kumarpur Water Supply Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11746) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000469/2024-2025 | 3464/AD | 23/08/2024 | 45 | PRONICON INDIA | 55.66 | 0 | 0
2160 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kumarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000975/2023-2024 | 2994/AD | 06/10/2023 | 45 | M/S KRISHNA MONDAL | 27.73 | 0 | 70
2161 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Kumarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000976/2023-2024 | 2995/AD | 06/10/2023 | 30 | M/S S.DAS ENTERPRISE | 9.65 | 0 | 0
2162 | Alipore Division | Kakdwip Sub-Division | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site for Kumarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001150/2024-2025 | 4506/AD | 11/11/2024 | 60 | MEHAI TECHNOLOGY LIMITED | 19.96 | 0 | 100
2163 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001315/2022-2023 | 9880/AD | 10/01/2023 | 870 | S & P ENTERPRISE | 427.97 | 0 | 50
2164 | Alipore Division | Kakdwip Sub-Division | Hiring of 01 No. Diesel Car / Luxury Taxi for supervision of different works at Gangasagar Point in connection with Gangasagar Mela 2022 under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2021 to 31.03.2022. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001348/2021-2022 | 661/KSD | 23/11/2021 | 120 | SUDIP PRADHAN | 1.6 | 0 | 100
2165 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2022 to 31.07.2022. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001678/2021-2022 | 934/KSD | 31/01/2022 | 181 | BADSHA ALOM | 2.39 | 0 | 100
2166 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
2167 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000067/2022-2023 | 3955/AD | 12/08/2022 | 0 | Resource Division | 13.09 | 0 | 0
2168 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000305/2023-2024 | 3100/AD | 28/09/2023 | 0 | Resource Division | 16.22 | 0 | 0
2169 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000583/2023-2024 | 57/AD | 03/01/2024 | 0 | Resource Division | 8.75 | 0 | 0
2170 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kumarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000126/2023-2024 | 1125/SMD | 24/04/2023 | 90 | S.G.ENTERPRISE | 20.8 | 0 | 0
2171 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00279/2023-2024 |  | 04/05/2023 | 0 | WBSEDCL | 2.9 | 0 | 0
2172 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00619/2023-2024 | BP-2023-24-28 | 17/05/2023 | 0 | WBSEDCL | 2.84 | 0 | 0
2173 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01499/2023-2024 | BP-2023-24-181 | 02/08/2023 | 0 | WBSEDCL | 7.31 | 0 | 0
2174 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01745/2023-2024 | BP-2023-24-181 | 02/08/2023 | 0 | WBSEDCL | 0.05 | 0 | 0
2175 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Garanberia PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000055/2024-2025 | 575/SMSD | 10/05/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
2176 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Garanbearia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 231/SMD | 24/01/2023 | 889 | B.T.PROJECTS PVT.LTD. | 24.06 | 0 | 100
2177 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Garanberia, PH-2 under Bhangar-I Block water supply scheme under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000542/2024-2025 | 830/SMSD | 12/06/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
2178 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.45] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00474/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 53.13 | 0 | 0
2179 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for GARANBERIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000268/2022-2023 | 1779/SWD-I | 07/11/2022 | 30 | MOMINUL BISWAS | 30.03 | 0 | 100
2180 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GARANBERIA PWSS at headwork site & 2nd Tubewell site of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12206] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000480/2022-2023 | 2809/SWD-I | 02/02/2023 | 15 | MOMINUL BISWAS | 3.13 | 0 | 100
2181 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of GARANBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12206) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 4237/SWD-I | 30/09/2024 | 456 | SRI RAM CONSTRUCTION | 81.81 | 0 | 30
2182 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Garanberia Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1146] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000723/2022-2023 | 3566/SWD-I | 22/03/2023 | 853 | SRI RAM CONSTRUCTION | 355.71 | 0 | 60
2183 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000054/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 11.8 | 0 | 0
2184 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000221/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 7.06 | 0 | 0
2185 | Alipore Division | Baruipur Sub-Division | 1) L027-Sagarsangha Math on T03 to Dudhnai(WB/02/480) 2) Construction of Road from Fultala Chow More to Block-A, B.C,D to Ramkrisna Polly to Mohamonilala Greater Kolkata Enginnering College to Ramnagar Bazar via Dhapdhopi road Shakharipukur under Baruipur Block. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01677/2024-2025 | BP-2024-25-782 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.88 | 0 | 0
2186 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, delivery stand by submersible pump for Sitakundu (Zone-II) W/S Scheme under SMD PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000312/2024-2025 | 1117/SMSD | 06/08/2024 | 15 | MAA SARADA CONSTRUCTION | 0.81 | 0 | 100
2187 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Sitakundu water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000447/2022-2023 | 3927/SMD | 30/12/2022 | 90 | M/S.UTTAM KUMAR CHATTERJEE | 22.38 | 0 | 100
2188 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Installation of LED board at P.H. No-1 & 2 of Sitakundu (Zone-II) water supply scheme, under South 24-pgs Mechanical Division PHE Dte. [Block-Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001632/2023-2024 | 1071/SMSD | 17/08/2023 | 10 | M/S.UTTAM KUMAR CHATTERJEE | 0.78 | 0 | 100
2189 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of Outdoor illumination arrangement with allied works at PH-1, Zone-II of Sitakundu water supply scheme under SMD, PHE Dte. (Block- Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002573/2023-2024 | .1060/SMSD | 10/08/2023 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0 | 100
2190 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of Outdoor illumination arrangement with allied works at PH-2, Zone-II of Sitakundu water supply scheme under SMD, PHE Dte. (Block- Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002574/2023-2024 | .1061/SMSD | 10/08/2023 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0 | 100
2191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00759/2024-2025 | BP-2024-25-451 | 06/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 12 | 0 | 0
2192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-II) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000079/2022-2023 | 1190/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 0 | 100
2193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000361/2022-2023 | 2204/SWD-I | 13/12/2022 | 60 | JOY GURU TRADING | 11.52 | 0 | 0
2194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000444/2021-2022 | 1950/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
2195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SITAKUNDU [Zone-II] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11646] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000806/2023-2024 | 1289/SWD-I | 15/03/2024 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
2196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls with land development and other allied works for Ground Water Based SITAKUNDU (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/11646) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000847/2023-2024 | 1252/SWD-I | 13/03/2024 | 609 | BAIDYA ENTERPRISE | 49.19 | 0 | 51
2197 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000085/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 11.9 | 0 | 0
2198 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/04654/2023-2024 | BP-2023-24-493 | 12/02/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
2199 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chakraborty Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000526/2022-2023 | 439/SMD | 17/02/2023 | 90 | A.S ENGINEERING | 13.01 | 0 | 0
2200 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1100) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000185/2022-2023 | 1488/SWD-I | 28/09/2022 | 120 | TANMOY ROY CHOWDHURY | 197.72 | 0 | 77
2201 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAKRABORTY ABAD PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009670] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000241/2022-2023 | 1684/SWD-I | 01/11/2022 | 30 | SIMPLEX DRILLING COMPANY | 21.48 | 0 | 0
2202 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHAKRABORTY ABAD of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009670] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000290/2022-2023 | 1785/SWD-I | 07/11/2022 | 60 | SANJAY ENTERPRISE | 5.8 | 0 | 0
2203 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chakraborty Abad PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000632/2022-2023 | 3261/SWD-I | 02/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 2.24 | 0 | 0
2204 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground Water Based Water Supply Scheme at CHAKRABORTY ABAD (Kalabaru, JL-114) Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11296) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000913/2023-2024 | 1203/SWD-I | 11/03/2024 | 315 | UNI DEVELOPERS AND CONTRACTORS | 23.98 | 0 | 40
2205 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000075/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.78 | 0 | 0
2206 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000277/2023-2024 | 2426/SWD-I | 30/09/2023 | 0 | Resource Division | 1.73 | 0 | 0
2207 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V A at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4150] | AE BSD |  | ORD/000270/2023-2024 | 1550/SWD-I | 25/07/2023 | 120 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 316.11 | 0 | 0
2208 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V B at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3958] | AE BSD |  | ORD/000813/2022-2023 | 3692/SWD-I | 30/03/2023 | 120 | CALCON CONSTRUCTIONS | 299.61 | 0 | 30
2209 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000082/2022-2023 | 2998/SWD-I | 20/02/2023 | 0 | Resource Division | 49.95 | 0 | 0
2210 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-IX at GHOLA NOAPARA Mouza of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-IX at GHOLA NOAPARA of MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 5309 Nos.) | AE SWSD-II | JE4 | ORD/000803/2022-2023 | 3694/SWD-I | 30/03/2023 | 120 | MANASH GHOSH | 603.4 | 0 | 30
2211 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000141/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 32.7 | 0 | 0
2212 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1 (one) no pipe carrying structures for laying of distribution pipeline over Nainpur Deula canal at Node Point 946 - 1205 for the laying of distribution system at Zone-V, Magrahat-I Block within 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME' for Falta-Mathurapur, Dist- South 24 Pgs W/S Division-I, P.H.E. Dte. (SM/11267) | AE SWSD-II | JE3 | ORD/000098/2025-2026 | 1773/SWD-I | 02/07/2025 | 45 | SRIJON ENTERPRISE | 32.96 | 0 | 0
2213 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | 9305 Nos. Functional Household Tap Connection (FHTC) in Zone-V at Barijpur mouza of Mograhat-I block for providing 100% FHTC within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC-9305 Nos.) | AE SWSD-II | JE3 | ORD/000678/2022-2023 | 3457/SWD-I | 14/03/2023 | 840 | M/S. S.S. ENTERPRISE | 554.56 | 0 | 70
2214 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000135/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 57.32 | 0 | 0
2215 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/01748/2023-2024 | BP-2023-24-211 | 11/08/2023 | 0 | WBSEDCL | 4.78 | 0 | 0
2216 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kasthamahal water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000487/2022-2023 | 245/SMD | 27/01/2023 | 90 | KARUNAMOY ENGINEERING | 26.26 | 0 | 50
2217 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Renovation of external illumination arrangement including incorporating LED Glow sign board and other allied works at P.H. No. - 1 under Kasthamahal Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/11733) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002509/2023-2024 | 223-AE-II-SMD | 01/03/2024 | 15 | PURUSHOTTAM ENTERPRISE | 0.75 | 0 | 100
2218 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KASTHAMAHAL Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11733] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000175/2022-2023 | 1450/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.26 | 0 | 100
2219 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
2220 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kasthamahal PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11733) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000264/2024-2025 | 2679/SWD-I | 07/06/2024 | 45 | S.R ENTERPRISE (KARUNAMOYEE) | 50.56 | 0 | 10
2221 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KASTHA MAHAL Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000408/2022-2023 | 465/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 0 | 100
2222 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KASTHAMAHAL Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11733) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000432/2022-2023 | 2576/SWD-I | 10/01/2023 | 60 | R.G ENTERPRISE | 6.04 | 0 | 100
2223 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KASTHAMAHAL PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 985 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000498/2022-2023 | 2866/SWD-I | 09/02/2023 | 90 | S.R ENTERPRISE (EMAIL- SOMENATH.MAJUMDER9874@GMAIL.COM) | 119.6 | 0 | 95
2224 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASTHAMAHAL PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011792] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000524/2022-2023 | 2920/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 0 | 100
2225 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000111/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 36.56 | 0 | 0
2226 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000870/2023-2024 | 777/AD | 03/02/2024 | 0 | Resource Division | 0.55 | 0 | 0
2227 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Mithakundu Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000605/2022-2023 | 696/SMD | 13/03/2023 | 90 | KUNAL ENTERPRISE | 8.84 | 0 | 0
2228 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Digambarpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13764) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000191/2024-2025 | 2550/AD | 18/06/2024 | 75 | MS FIROJA ENTERPRISE | 71.1 | 0 | 0
2229 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000378/2023-2024 | 1771/AD | 26/07/2023 | 60 | SWASTIK ENTERPRISE (NEW) | 9.06 | 0 | 60
2230 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Digambarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000961/2023-2024 | 284(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2231 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DIGAMBERPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000977/2022-2023 | 3662/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.72 | 0 | 100
2232 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Digambarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000980/2023-2024 | 2999/AD | 26/09/2023 | 45 | PRADIP KUMAR MONDAL | 27.46 | 0 | 0
2233 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Digambarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000981/2023-2024 | 3000/AD | 06/11/2023 | 30 | M/S MAA KALI ENTERPRISE | 9 | 0 | 0
2234 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Digambarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13764) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001045/2024-2025 | 4966/AD | 04/12/2024 | 91 | AQUATECH ENGINEERS | 40.73 | 0 | 50
2235 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001495/2022-2023 | 10988/AD | 07/02/2023 | 300 | MUNNA AGROTECH ENTERPRISE | 297.15 | 0 | 30
2236 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 700 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002062/2022-2023 | 13004/AD | 23/03/2023 | 90 | S.P. CONSTRUCTION (I) | 100.07 | 0 | 86
2237 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
2238 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000092/2023-2024 | 538/AD | 12/05/2023 | 0 | Resource Division | 11.15 | 0 | 0
2239 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000517/2023-2024 | 4941/AD | 22/12/2023 | 0 | Resource Division | 28.75 | 0 | 0
2240 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000950/2023-2024 | 1684/AD | 22/03/2024 | 0 | Resource Division | 1.85 | 0 | 0
2241 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Digamberpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000362/2022-2023 | 3765/SMD | 29/12/2022 | 90 | SWAPAN ENTERPRISE | 22.22 | 0 | 0
2242 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I |  | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 0 | 20
2243 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 600 mm dia DI Secondary Grid pipeline including allied works infront of Mandirbazar GLR & Bijoyganj Bazar (gap negotiation) within Mandirbazar Block in connection with Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply scheme for Falta-Mathurapur, Dist. South 24-pgs. under South 24-Pgns W/S Division-I, PHE Dte. (SM/11243) | AE HQ-I |  | ORD/000798/2023-2024 | 1146/SWD-I | 07/03/2024 | 30 | S. ROY AND ASSOCIATES | 39.85 | 0 | 90
2244 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000051/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 59.25 | 0 | 0
2245 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Mastikari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000570/2022-2023 | 589/SMD | 24/02/2023 | 90 | SAIKAT ENTERPRISE | 22.37 | 0 | 0
2246 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia& 300 mtr. deepTubewell by Rotary method for MASTIKARI PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/011743] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 1233/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 28.52 | 0 | 100
2247 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 0 | 30
2248 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land and other allied works for Ground water based MASTIKARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000226/2024-2025 | 2643/SWD-I | 07/06/2024 | 45 | S.C. ENTERPRISE | 16.76 | 0 | 0
2249 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "MASTIKARI Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 470/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.76 | 0 | 100
2250 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000161/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 41.06 | 0 | 0
2251 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II B at Jalaberia mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4835] | AE BSD |  | ORD/000218/2022-2023 | 1627/SWD-I | 20/10/2022 | 1131 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 367.31 | 0 | 40
2252 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II A at Jalaberia mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur district.- South 24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4568] | AE BSD |  | ORD/000524/2023-2024 | 2306/SWD-I | 20/09/2023 | 690 | SPA ENTERPRISE | 365.25 | 0 | 40
2253 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000073/2022-2023 | 2989/SWD-I | 20/02/2023 | 0 | Resource Division | 57.92 | 0 | 0
2254 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VII B at Binodpur (Maipith) mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4614] | AE BSD |  | ORD/000222/2022-2023 | 1640/SWD-I | 20/10/2022 | 960 | K P CONSTRUCTION | 352.6 | 0 | 80
2255 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VII A at Binodpur (Maipith) mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4892] | AE BSD |  | ORD/000306/2022-2023 | 1910/SWD-I | 18/11/2022 | 120 | MRITYUNJOY MUKHERJEE AND CO | 373.71 | 0 | 30
2256 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000077/2022-2023 | 2993/SWD-I | 20/02/2023 | 0 | Resource Division | 58.56 | 0 | 0
2257 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000017/2022-2023 | 3836/AD | 08/08/2022 | 30 | ABONTICA ENTERPRISE | 5.15 | 0 | 100
2258 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000026/2022-2023 | 2926/AD | 07/07/2022 | 30 | AQUATECH ENGINEER | 18.32 | 0 | 98
2259 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 3nos Pump House site of Ramganga Water Supply Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11281) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000132/2025-2026 | 2630/AD | 05/06/2025 | 45 | AZAD RAHAMAN LASKAR | 5.99 | 0 | 0
2260 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Ramganga PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11281) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000186/2024-2025 | 2546/AD | 18/06/2024 | 244 | M/S. S.S. ENTERPRISE | 87.68 | 0 | 80
2261 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramganga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000461/2022-2023 | 295/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.33 | 0 | 100
2262 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000505/2022-2023 | 5091/AD | 20/09/2022 | 902 | M/S. S.S. ENTERPRISE | 494.53 | 0 | 55
2263 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000858/2022-2023 | 6941/AD | 18/11/2022 | 120 | RAMEN GHOSH | 219.32 | 0 | 60
2264 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ramganga W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001077/2021-2022 | 547/KSD | 03/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.6 | 0 | 100
2265 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramganga W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001202/2023-2024 | 4079/AD | 23/11/2023 | 486 | G.M. ENTERPRISE | 9.55 | 0 | 90
2266 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.01.2024 to 09.04.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001870/2023-2024 | 199/AD | 09/01/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
2267 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
2268 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.04.2024 to 09.07.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002155/2024-2025 | 1966/AD | 05/04/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
2269 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000047/2022-2023 | 3910/AD | 12/08/2022 | 0 | Resource Division | 36.27 | 0 | 0
2270 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000309/2023-2024 | 3118/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2271 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000771/2023-2024 | 605/AD | 29/01/2024 | 0 | Resource Division | 21.26 | 0 | 0
2272 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000941/2023-2024 | 1675/AD | 22/03/2024 | 0 | Resource Division | 19.24 | 0 | 0
2273 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | BILL/05696/2023-2024 | BP-2023-24-612 | 28/03/2024 | 0 | WBSEDCL | 4.55 | 0 | 0
2274 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of submersible pumping machinery for PH-1 of Augmentation of Ramganga W/s Scheme under South 24pgs Mechanical Division, PHE. Dte. (Block-Patharpratima) (SM/11281) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000119/2024-2025 | 850-AE-II-SMD | 15/07/2024 | 15 | DITHI ENTERPRISE | 0.78 | 0 | 100
2275 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Ramganga Augmentation water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000567/2022-2023 | 583/SMD | 23/02/2023 | 888 | DITHI ENTERPRISE | 11.27 | 0 | 90
2276 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Ramganga W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima][SM/11281] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001887/2024-2025 | 849-AE-II-SMD | 15/07/2024 | 15 | DITHI ENTERPRISE | 0.9 | 0 | 0
2277 | S24 Pgns Mechanical | Kakdwip Sub-Division | Hiring of Inspection vehicle (Motor Cab) under JJM for the office of the Executive Engineer South 24 Pgs Mechanical Division PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002487/2024-2025 | 1608-AE-II/SMD | 27/12/2024 | 181 | S.P. CONSTRUCTION | 0.86 | 0 | 0
2278 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of DHOPA HAT MOUZA in MANDIRBAZAR (ZONE-IV) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000390/2021-2022 | 1986/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4 | 0 | 100
2279 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-IV at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2270) | AE HQ-I |  | ORD/000712/2022-2023 | 3528/SWD-I | 17/03/2023 | 300 | SUPER SKILL | 458.61 | 0 | 25
2280 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of Zone-IV within Mandirbazar block, Mouza-Dhopahat (JL No-119), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24-Pgns. W/S Division-I, PHE Dte. (Length- 160 mtr.) | AE HQ-I |  | ORD/000727/2022-2023 | 190/SWD-I | 26/04/2022 | 60 | M/S. KALPANA CONSTRUCTION | 21.75 | 0 | 100
2281 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Approach Road for Head Work Site (Dhoparhat) at Zone-IV for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-IV at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District-South 24-Pgns. underSouth 24-Pgns. W/S Division-I, PHE Dte. (SM/12204) | AE HQ-I |  | ORD/000757/2023-2024 | 658/SWD-I | 06/02/2024 | 382 | M/S SUBHODEEP ENTERPRISE | 19.75 | 0 | 100
2282 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Protection of pipe line and other allied work for laying of distribution pipes in between Zone X and Zone IV under Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone IV at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/12204) | AE HQ-I |  | ORD/001131/2024-2025 | 194/SWD-I | 17/01/2025 | 45 | BISWAS CONSTRUCTION | 26.73 | 0 | 0
2283 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000046/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
2284 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 100 Cum. capacity Over Head Reservoir of Zone-IV, Diamond Harbour -II Block (At Sarisha Ramkrishna Mission) Water Supply Scheme under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000131/2023-2024 | 490/AD | 10/05/2023 | 60 | NIVA CONSTRUCTION | 20.82 | 0 | 100
2285 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
2286 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000142/2022-2023 | 15/AD | 05/04/2023 | 0 | Resource Division | 15.11 | 0 | 0
2287 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000182/2023-2024 | 1273/AD | 05/07/2023 | 0 | Resource Division | 15.11 | 0 | 0
2288 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000353/2023-2024 | 3217/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2289 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-V of Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000003/2021-2022 | 341/AD | 12/05/2021 | 180 | M/S. S.S. ENTERPRISE | 189.98 | 0 | 0
2290 | Alipore Division | Diamond Harbour Sub-Division | Interconnection of tubewell, and erection of RBT fencing at Pump House No.-2 of Khandalia W/S Scheme, Block: Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000822/2022-2023 | 206/DHSD | 02/08/2022 | 45 | S.S. ENTERPRISE (II) | 2.66 | 0 | 100
2291 | Alipore Division | Diamond Harbour Sub-Division | Construction of Boundary wall,approach road and renovation of Pump House as per departmental design and drawing at Pump House No. 2 of Khandalia W/S Scheme under Diamond Harbour Sub-Division of Alipore Division, P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001520/2020-2021 | 336/DHSD | 06/01/2021 | 30 | M/S. SUMAN ENTERPRISE | 4.81 | 0 | 100
2292 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000355/2023-2024 | 3219/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2293 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Dhanpota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000408/2022-2023 | 3806/SMD | 29/12/2022 | 90 | ALPHA ENTERPRISE | 22.82 | 0 | 0
2294 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
2295 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DHANPOTA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13918] | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 3241/SWD-I | 01/03/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0
2296 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Dhanpota Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000982/2022-2023 | 1456/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.65 | 0 | 100
2297 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000169/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 29.13 | 0 | 0
2298 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Dakshin Madhusudanpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13977) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000447/2024-2025 | 3324/AD | 12/08/2024 | 60 | MONDAL CONSTRUCTION NEW | 102.17 | 0 | 0
2299 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Madhusudanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000965/2023-2024 | 288(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2300 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Madhusudanpur W/S scheme, Block- Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001057/2023-2024 | 3376/AD | 11/10/2023 | 45 | M/S ANNAPURNA ENTERPRISE | 27.54 | 0 | 0
2301 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Madhusudanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001058/2023-2024 | 3377/AD | 11/10/2023 | 30 | M/S BABUSONA ENTERPRISE | 9.48 | 0 | 0
2302 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN MADHUSUDANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001328/2022-2023 | 3312/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.9 | 0 | 100
2303 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Madhusudanpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001721/2022-2023 | 11747/AD | 21/02/2023 | 45 | MODERN CONSTRUCTION (NEW) | 38.58 | 0 | 80
2304 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Madhusudanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC=1664] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001757/2022-2023 | 11556/AD | 17/02/2023 | 1257 | MONDAL CONSTRUCTION NEW | 299.31 | 0 | 35
2305 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
2306 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000105/2023-2024 | 641/AD | 17/05/2023 | 0 | Resource Division | 9.14 | 0 | 0
2307 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000502/2023-2024 | 4959/AD | 22/12/2023 | 0 | Resource Division | 17.94 | 0 | 0
2308 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000759/2023-2024 | 594/AD | 29/01/2024 | 0 | Resource Division | 1.64 | 0 | 0
2309 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000953/2023-2024 | 1687/AD | 22/03/2024 | 0 | Resource Division | 9.35 | 0 | 0
2310 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01117/2023-2024 | BP-2023-24-159 | 24/07/2023 | 0 | WBSEDCL | 6.64 | 0 | 0
2311 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Madhusudanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000384/2022-2023 | 3787/SMD | 29/12/2022 | 90 | DAS ENTERPRISE | 19.24 | 0 | 90
2312 | S24 Pgns Mechanical | Kakdwip Sub-Division | Hiring of Maxi Cab (BS-III & above) having contract carriage permit along with driver under JJM for the office of the Executive Engineer, South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000758/2025-2026 | 1419-AE-II-SMD | 19/08/2025 | 181 | UJJAL SAHA | 0.86 | 0 | 0
2313 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 of Dakshin Madhusudanpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001902/2023-2024 | 1187/SMD | 22/03/2024 | 21 | DAS ENTERPRISE | 21.03 | 0 | 100
2314 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Dakshin Madhusudanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13977) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002340/2024-2025 | 3095-AE-II-SMD | 21/03/2025 | 15 | DAS ENTERPRISE | 0.67 | 0 | 0
2315 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Dakshin Madhusudanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13977) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002341/2024-2025 | 3094-AE-II-SMD | 21/03/2025 | 15 | DAS ENTERPRISE | 0.67 | 0 | 0
2316 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000253/2023-2024 | 1396/AD | 12/07/2023 | 570 | RAKTIM ENTERPRISE | 8.88 | 0 | 100
2317 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000254/2023-2024 | 1397/AD | 12/07/2023 | 539 | RAKTIM ENTERPRISE | 8.57 | 0 | 100
2318 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Kamarpara piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1443] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000293/2023-2024 | 1503/AD | 15/07/2023 | 1005 | PROJECT INDIA | 354.06 | 0 | 85
2319 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000386/2023-2024 | 1575/AD | 17/07/2023 | 55 | GIASHUDDIN CONSTRUCTION | 43.94 | 0 | 100
2320 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Sitef or Ground water Based at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000388/2025-2026 | 3373/AD | 16/07/2025 | 45 | SWASTIK CONSTRUCTION | 32.27 | 0 | 0
2321 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kamarpara W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000732/2023-2024 | 2893/AD | 19/09/2023 | 15 | M/S. MIHIR KUMAR NASKAR | 13.26 | 0 | 0
2322 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000735/2024-2025 | 4393/AD | 05/11/2024 | 30 | SUKUMAR HALDAR | 14.97 | 0 | 0
2323 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kamarpara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001886/2022-2023 | 7599/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.49 | 0 | 95
2324 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000044/2023-2024 | 251/AD | 24/04/2023 | 0 | Resource Division | 50.79 | 0 | 0
2325 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000165/2023-2024 | 1047/AD | 15/06/2023 | 0 | Resource Division | 8.89 | 0 | 0
2326 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamarpara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000552/2022-2023 | 497/SMD | 20/02/2023 | 90 | AVINABA ENGINEERING CONCERN | 20.09 | 0 | 0
2327 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Dihi Narayani water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000412/2022-2023 | 3810/SMD | 29/12/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 22.29 | 0 | 0
2328 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DIHI NARAYANI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1571] [TSM/014903] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000282/2023-2024 | 1566/SWD-I | 27/07/2023 | 644 | M/S. SUMAN ENTERPRISE | 397.95 | 0 | 50
2329 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Approach Road (length = 25.00m) & Land Development at OHR site for DIHI NARAYANI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/13921) [2nd call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000548/2024-2025 | 4136/SWD-I | 23/09/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 7.28 | 0 | 0
2330 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head work site for DIHI NARAYANI Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13921] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000665/2024-2025 | 4395/SWD-I | 23/10/2024 | 30 | M/S. SHYAM CONSTRUCTION | 18.69 | 0 | 0
2331 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DIHI NARAYANI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13921][2nd Call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000690/2022-2023 | 3479/SWD-I | 15/03/2023 | 30 | BENGAL ENTERPRISE | 31.75 | 0 | 0
2332 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 900mm Dia Double Row Hume Pipe Culvert for DIHI NARAYANI PWSS to accommodate FHTC under Mograhat-II Block in the District of South 24 Parganas for Augmentation of Surfacc Water Based Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. (SM/13921) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000813/2023-2024 | 1149/SWD-I | 07/03/2024 | 30 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 5.77 | 0 | 80
2333 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "DIHINARAYANI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000881/2022-2023 | 412/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 0 | 0
2334 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000203/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 31.74 | 0 | 0
2335 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Rakhalpur W/S scheme, Block - Patharpratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000155/2023-2024 | 677/AD | 17/05/2023 | 30 | JOY ENGINEERING & CONSTRUCTION | 11.79 | 0 | 0
2336 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Rakhalpur W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000156/2023-2024 | 678/AD | 17/05/2023 | 1005 | M/S G.M. ASSOCIATES | 34.25 | 0 | 81
2337 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Rakhalpur (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14987) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000343/2024-2025 | 2755/AD | 27/06/2024 | 75 | BIMALENDU GIRI | 167.27 | 0 | 0
2338 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rakhalpur (Zone-I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000967/2023-2024 | 305/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2339 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rakhalpur (Zone-I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000968/2023-2024 | 306/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2340 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Rakhalpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001794/2022-2023 | 3959/AD | 12/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.06 | 0 | 95
2341 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Rakhalpur W/S Scheme, Block - Pathar PRatima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone- I and II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001961/2023-2024 | 396/AD | 22/01/2024 | 45 | AQUATECH ENGINEERS | 49.26 | 0 | 50
2342 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rakhalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002058/2022-2023 | 13000/AD | 23/03/2023 | 740 | GROWING CONCERN | 253.61 | 0 | 5
2343 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rakhalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002059/2022-2023 | 13001/AD | 23/03/2023 | 740 | GROWING CONCERN | 251.42 | 0 | 5
2344 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sridharnagar Zone - I & II, Rakhalpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002106/2023-2024 | 928/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
2345 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000318/2023-2024 | 3127/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2346 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000442/2023-2024 | 4767/AD | 19/12/2023 | 0 | Resource Division | 40.95 | 0 | 0
2347 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000563/2023-2024 | 84/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
2348 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000763/2023-2024 | 597/AD | 29/01/2024 | 0 | Resource Division | 3.79 | 0 | 0
2349 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000964/2023-2024 | 1698/AD | 22/03/2024 | 0 | Resource Division | 11.49 | 0 | 0
2350 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,&2 for Augmentation of Rakhalpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000392/2022-2023 | 3794/SMD | 29/12/2022 | 90 | M/S. GHOSH ENTERPRISE | 21.42 | 0 | 0
2351 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Multi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000418/2022-2023 | 3814/SMD | 29/12/2022 | 90 | S.P. CONSTRUCTION | 33.56 | 0 | 30
2352 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Allied Electro-Mechanical works at Pump House no-1 of Multi W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | Assistant Engineer | Junior Engineer | ORD/003008/2023-2024 | 235/SMSD | 16/02/2024 | 15 | S.P. CONSTRUCTION | 0.41 | 0 | 0
2353 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sarberia-Dhamua Road from 0+00 to 6+520 km Restoration of Damages occurred due to damages caused/ to be caused by laying of pipe line by PHE Dte. under Sarberia PWSS,Jaldhapa PWSS,Multi PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. | Assistant Engineer | Junior Engineer | BILL/00645/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 106.91 | 0 | 0
2354 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (3 Nos.) for Augmentation of MULTI Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 3314) [TSM/017503] | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 468/SWD-I | 04/05/2023 | 719 | KINGS & CO. | 512.59 | 0 | 87
2355 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall, Box Culvert & Development of Land at TW-2 site and Construction of Service Road at OHR site & TW2 site for MULTI PWSS to accommodate FHTC within Mograhat-II Block underSouth 24-Pgns, W/S Divn-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 3268/SWD-I | 22/07/2024 | 272 | TIYASHA ENTERPRISE | 23.89 | 0 | 40
2356 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional 60mtr. boring of Sinking of 02 (Two ) nos. (for 2nd TW a7 3rd TW) Rig bored 250mm X 150mm dia. & upto 360 mtr. deep Tubewell by Rotary method for MULTI PWSS of Mograhat-II Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000530/2024-2025 | 4076/SWD-I | 19/09/2024 | 194 | TRAYEE DECORATOR | 4.72 | 0 | 30
2357 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MULTI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/017503][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000686/2022-2023 | 3485/SWD-I | 15/03/2023 | 713 | TRAYEE DECORATOR | 47.63 | 0 | 66
2358 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 51.00m), Development of Land at 3rd Tubewell site and Construction of Service Road (length = 25.00m) at 3rd Tubewell site for MULTI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000868/2024-2025 | 4926/SWD-I | 03/12/2024 | 60 | M/S ASHA ENGINEERING | 12.41 | 0 | 0
2359 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Multi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000978/2022-2023 | 1434/SWD-I | 23/09/2022 | 30 | GEO SOLUTION | 2.84 | 0 | 100
2360 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000131/2022-2023 | 3390/SWD-I | 10/03/2023 | 0 | Resource Division | 20.41 | 0 | 0
2361 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000158/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 52.85 | 0 | 0
2362 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Urel Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 1047/SMD | 17/04/2023 | 90 | SUBHRA ENTERPRISE | 22.37 | 0 | 45
2363 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Allied Electro-Mechanical works at Pump House no-1 of Urel Chandpur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/002782/2023-2024 | 117/SMSD | 25/01/2024 | 15 | SUBHRA ENTERPRISE | 0.28 | 0 | 0
2364 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at UREL CHANDPUR Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2247] [TSM/017336] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000063/2023-2024 | 367/SWD-I | 27/04/2023 | 811 | M/S V.P. JAIN | 319.81 | 0 | 95
2365 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14863) | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000323/2024-2025 | 3256/SWD-I | 19/07/2024 | 60 | M/S V.P. JAIN | 41.83 | 0 | 0
2366 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tub-ewell having 66 mtr. housing pipe by Rotary method for UREL CHANDPUR PWSS of Mograhat-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017336] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 3049/SWD-I | 20/02/2023 | 780 | PADMA ENGINEERING CO. | 31.8 | 0 | 100
2367 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Urel Chandpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000970/2022-2023 | 1387/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.7 | 0 | 100
2368 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000133/2022-2023 | 3392/SWD-I | 10/03/2023 | 0 | Resource Division | 13.84 | 0 | 0
2369 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000176/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 39.14 | 0 | 0
2370 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001038/2022-2023 | 3672/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 0 | 100
2371 | Alipore Division | Kakdwip Sub-Division | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Indrapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001270/2022-2023 | 9582/AD | 03/01/2023 | 60 | M/S. BOSE CONCERN | 73.43 | 0 | 100
2372 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002041/2023-2024 | 523/AD | 25/01/2024 | 374 | SK SAKIL AHAMED | 33.48 | 0 | 100
2373 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002042/2023-2024 | 524/AD | 25/01/2024 | 30 | M/S. ASIRUDDIN SEKH ENTERPRISE | 11.8 | 0 | 0
2374 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002043/2023-2024 | 525/AD | 25/01/2024 | 30 | SIMRAN ENTERPRISE | 11.82 | 0 | 100
2375 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 200 cum. capacity OHR of Indrapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002064/2023-2024 | 758/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2376 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
2377 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000102/2023-2024 | 548/AD | 12/05/2023 | 0 | Resource Division | 10.34 | 0 | 0
2378 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000298/2023-2024 | 3093/AD | 28/09/2023 | 0 | Resource Division | 24.37 | 0 | 0
2379 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000744/2023-2024 | 579/AD | 29/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
2380 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/04080/2023-2024 | BP-2023-24-420 | 16/12/2023 | 0 | WBSEDCL | 3.93 | 0 | 0
2381 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/04942/2023-2024 | BP-2023-24-567 | 11/03/2024 | 0 | WBSEDCL | 9.91 | 0 | 0
2382 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Indrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000364/2022-2023 | 3768/SMD | 29/12/2022 | 953 | UNIVERSAL ENTERPRISES | 28.75 | 0 | 85
2383 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Indrapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13798] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001886/2024-2025 | 1019-AE-II-SMD | 09/08/2024 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.83 | 0 | 100
2384 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-2 of Indrapur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001900/2023-2024 | 1185/SMD | 22/03/2024 | 21 | UNIVERSAL ENTERPRISES | 10.63 | 0 | 100
2385 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. | AE BSD |  | BILL/00656/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0
2386 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD |  | BILL/00666/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
2387 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall along with humepipe culvert bridge for the approch road of proposed OHR Site at Nayapukuria Mouza, JL No.43, Khatian No. 1079, Plot No. 661 & 662; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 180.0 mtr.] | AE BSD |  | ORD/000378/2021-2022 | 1581/SWD-I | 27/12/2021 | 90 | SANKAR HALDER | 33.44 | 0 | 0
2388 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-I Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000653/2024-2025 | 4376/SWD-I | 22/10/2024 | 90 | A.P POWER AND CONCRETE | 15.66 | 0 | 0
2389 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000654/2024-2025 | 4377/SWD-I | 22/10/2024 | 90 | BISWAS CONSTRUCTION | 15.58 | 0 | 100
2390 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for application of protective coating on M.S pipe for Railway crossing at Dakshin Bishnupur Rail gate under Mega Surface water Based Water Supply Scheme for Falta-Mathurapur, Dist. South24-Pgns. of South 24-Pgs. Water Supply Divn.-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000756/2024-2025 | 4677/SWD-I | 18/11/2024 | 15 | DIAMOND ENTERPRISE | 3.81 | 0 | 100
2391 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of G.I. Pipe, Collapsible Gate, Laying of 100 mm thick interlocking design concrete paver block (M-15) grade for Mathurapur-I GLR in connection with Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.-South 24-Parganas under Baruipur Sub-Division of SWD-I, PHE Dte. (SM/14140) | AE BSD |  | ORD/000760/2024-2025 | 4681/SWD-I | 18/11/2024 | 30 | DIAMOND ENTERPRISE | 9.4 | 0 | 100
2392 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instrument like Remotely Piloted Aircraft System / DGPS/ Total station etc. and detailed design of pipeline by using watergems Software on the besis of the population density within the zone-I of Joynagar-II block under Mega Surface water based water supply scheme for Falta-Mathurapur, Dist- South 24-Pgns. | AE BSD |  | ORD/000773/2020-2021 | 1038/SWD-I | 05/10/2020 | 14 | DEVELOPMENT CONSULTANTS PVT LTD | 4.75 | 0 | 100
2393 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Raidighi River in between nodes 12 & 13 of Secondary Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/14140) | AE BSD |  | ORD/000775/2024-2025 | 4761/SWD-I | 21/11/2024 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 139.05 | 0 | 0
2394 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000206/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 76.87 | 0 | 0
2395 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000299/2023-2024 | 2438/SWD-I | 30/09/2023 | 0 | Resource Division | 132.42 | 0 | 0
2396 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of JALGHARA in MOGRAHAT-I (ZONE-X/A) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | Assistant Engineer | JE2 | ORD/000305/2021-2022 | 1982/SWD-I | 27/01/2022 | 30 | RADIANT | 3.32 | 0 | 0
2397 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-X/A (Jal Ghara) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 112 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | Assistant Engineer | JE2 | ORD/000379/2021-2022 | 2691/SWD-I | 25/03/2022 | 90 | MS P B CONSTRUCTION | 15.28 | 0 | 100
2398 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, construction of approach road and Chlorination Room under Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/A at JALGHARA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14724) | Assistant Engineer | JE2 | ORD/000442/2024-2025 | 3892/SWD-I | 04/09/2024 | 90 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 333.65 | 0 | 0
2399 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 734 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 0 | 25
2400 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000067/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 298.22 | 0 | 0
2401 | Alipore Division | Canning Sub-division | Earth working embankment at Head work site of Srinagar Water Supply Scheme, Block-canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000003/2022-2023 | 120/AD | 07/04/2022 | 7 | SWASTIK CONSTRUCTION | 8.31 | 0 | 97
2402 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. Store Room (multipurpose) (4.88m x 3.66m) at head work site of Srinagar Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000062/2022-2023 | 843/AD | 13/05/2022 | 30 | BHUNIA BUILDERS | 5.95 | 0 | 80
2403 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 365 | NATURAL RESOURCES CONSORTIUM | 89.65 | 0 | 77
2404 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Banamalipur Khanpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000089/2022-2023 | 293/CSD | 20/05/2022 | 40 | NATURAL RESOURCES CONSORTIUM | 4.83 | 0 | 87
2405 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Mollapara, Sekhpara & Majherpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000112/2022-2023 | 295/CSD | 20/05/2022 | 40 | RAJLAKSHMI ENTERPRISE | 4.81 | 0 | 77
2406 | Alipore Division | Canning Sub-division | Laying of DI pipe to connect OHR with rising main and distribution system at Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000994/2021-2022 | 989/CSD | 26/10/2021 | 30 | K.P. CONSTRUCTION | 4.21 | 0 | 90
2407 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Srinagar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001671/2022-2023 | 11482/AD | 15/02/2023 | 30 | TRIMURTI ENTERPRISE | 19.58 | 0 | 98
2408 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001690/2022-2023 | 11261/AD | 18/02/2023 | 581 | RAHUL ENTERPRISE | 7.05 | 0 | 99
2409 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 60 | SAHANA ENTERPRISE | 52.81 | 0 | 99
2410 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000016/2023-2024 | 221/AD | 21/04/2023 | 0 | Resource Division | 64.05 | 0 | 0
2411 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Srinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000039/2023-2024 | 994/SMD | 06/04/2023 | 999 | A.G.ENTERPRISE | 11.15 | 0 | 95
2412 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Aug of Srinagar water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15095) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002198/2024-2025 | 1522/SMSD | 18/11/2024 | 15 | A.G.ENTERPRISE | 0.92 | 0 | 0
2413 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Pump House-1 of Aug of Srinagar water supply scheme under SMD,PHE Dte. (Block-Canning-II) (SM/15095) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002199/2024-2025 | 1523/SMSD | 18/11/2024 | 15 | A.G.ENTERPRISE | 0.29 | 0 | 0
2414 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000501/2024-2025 | 3604/AD | 06/09/2024 | 360 | SARADA CONSTRUCTION | 80.76 | 0 | 55
2415 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Amarabati W/S Scheme, Namkhana Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000588/2023-2024 | 2345/AD | 18/08/2023 | 45 | SARADA CONSTRUCTION | 42.65 | 0 | 98
2416 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000938/2023-2024 | 278(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2417 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Amrabati PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001784/2022-2023 | 3693/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 9.01 | 0 | 95
2418 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002075/2022-2023 | 12945/AD | 21/03/2023 | 300 | SARADA CONSTRUCTION | 169.37 | 0 | 28
2419 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002076/2022-2023 | 12946/AD | 21/03/2023 | 90 | SARADA CONSTRUCTION | 151.76 | 0 | 77
2420 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002077/2022-2023 | 12947/AD | 21/03/2023 | 90 | SARADA CONSTRUCTION | 169.36 | 0 | 24
2421 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 1st Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002125/2024-2025 | 1972/KSD | 23/12/2024 | 20 | IMAGINEER VENTURES | 1.88 | 0 | 0
2422 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002126/2024-2025 | 1973/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.87 | 0 | 0
2423 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
2424 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 3rd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002133/2024-2025 | 1974/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.33 | 0 | 0
2425 | Alipore Division | Kakdwip Sub-Division | Road restoration and other allied works for laying pipe line to providing Functional Household Tap Connection (FHTC) to all households for Aamarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002565/2023-2024 | 510/KSD | 15/03/2024 | 5 | SARADA CONSTRUCTION | 3.63 | 0 | 90
2426 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000484/2023-2024 | 4786/AD | 19/12/2023 | 0 | Resource Division | 64.94 | 0 | 0
2427 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000554/2023-2024 | 42/AD | 03/01/2024 | 0 | Resource Division | 16.45 | 0 | 0
2428 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000983/2023-2024 | 1776/AD | 27/03/2024 | 0 | Resource Division | 4.9 | 0 | 0
2429 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Amrabati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000805/2022-2023 | 268/SMD | 31/01/2023 | 90 | CINZANO | 32.26 | 0 | 0
2430 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XI of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000025/2023-2024 | 105/AD | 13/04/2023 | 913 | SUJATA CONSTRUCTION | 319.09 | 0 | 85
2431 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000877/2024-2025 | 4661/AD | 20/11/2024 | 45 | L.N. ENTERPRISE | 17.1 | 0 | 0
2432 | Alipore Division | Raidighi Sub-Division | Extension of Pipeline at Gabbati of under Ghoradal Water supply Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001034/2021-2022 | 538/RSD | 30/11/2021 | 60 | UNITED BUILDERS | 4.65 | 0 | 100
2433 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000606/2023-2024 | 236/AD | 11/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
2434 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
2435 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XVII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000132/2023-2024 | 674/AD | 17/05/2023 | 813 | BALAJI UDDYOG | 553.99 | 0 | 60
2436 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works for piped water supply at Zone - XVII of Mathurapur- I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09396 and SM/15467) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000533/2024-2025 | 3639/AD | 09/09/2024 | 315 | BALAJI UDDYOG | 37 | 0 | 10
2437 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XVII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000883/2024-2025 | 4665/AD | 20/11/2024 | 60 | SUPRITI ENTERPRISE | 45.45 | 0 | 0
2438 | Alipore Division | Raidighi Sub-Division | Construction of 1 no. Pump House of size 4.80 Mtr. X 3.66 Mtr. (as per Dept. drawing) at Zone - XVII Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000884/2024-2025 | 4666/AD | 20/11/2024 | 45 | S.S. CONSTRUCTION (NAMKHANA) | 13.11 | 0 | 0
2439 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Raghudevpur W/S Scheme (Zone-XVII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001256/2023-2024 | 4181/AD | 28/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.84 | 0 | 99
2440 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000601/2023-2024 | 229/AD | 11/01/2024 | 0 | Resource Division | 5.78 | 0 | 0
2441 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
2442 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- II of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000120/2023-2024 | 591/AD | 15/05/2023 | 90 | DIPTI ENTERPRISE | 140.01 | 0 | 40
2443 | Alipore Division | Raidighi Sub-Division | Filling in foundation of Overhead Reservoir (Mathurapur - I, Zone -II ) by silver sand filling for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur, South 24 Paraganas under Raidighi Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000241/2022-2023 | 74/RSD | 18/05/2022 | 60 | G.B. CONSTRUCTION & CO. | 2.79 | 0 | 0
2444 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 365 | M/S. JHARNA ENTERPRISE | 101.84 | 0 | 85
2445 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-II of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001339/2021-2022 | 6033/AD | 16/02/2022 | 90 | DIPTI ENTERPRISE | 123.9 | 0 | 95
2446 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - II of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001963/2022-2023 | 12717/AD | 14/03/2023 | 30 | MONCON INDIA | 10.98 | 0 | 95
2447 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 64.12 | 0 | 75
2448 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000632/2023-2024 | 268/AD | 15/01/2024 | 0 | Resource Division | 6.71 | 0 | 0
2449 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 40 m.) and concrete block pavement at proposed OHR site and Land development at Mouza-Kamarpole under Zone- VII of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000072/2025-2026 | 2261/AD | 14/05/2025 | 30 | M/S B ENTERPRISE | 9.12 | 0 | 0
2450 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VII at Diamond Harbour- II block for providing House Hold Tap connection, under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001998/2024-2025 | 317/AD | 27/01/2025 | 30 | YAMUNA CONSTRUCTION | 12.73 | 0 | 0
2451 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002246/2024-2025 | 544/AD | 12/02/2025 | 60 | S.M. ENTERPRISE | 56.88 | 0 | 0
2452 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000612/2023-2024 | 274/AD | 15/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
2453 | Alipore Division | Baruipur Sub-Division | Road restoration of WB024 17, L053 Gudamer Hat to Singher Dari Hugh School | AE BSD,Assistant Engineer | Junior Engineer | BILL/01781/2024-2025 | BP-2024-25-806 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 9.76 | 0 | 0
2454 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,& 3 for Augmentation of Kalikapur Barasat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 1044/SMD | 17/04/2023 | 90 | RELIABLE CONSTRUCTION | 35.5 | 0 | 0
2455 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Functional Household Tap connection(FHTC) for piped water supply scheme at KALIKAPUR BARASAT Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2904] [TSM/018436] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 100/SWD-I | 10/04/2023 | 817 | MILAN GHOSH | 363.92 | 0 | 90
2456 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14872) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000401/2024-2025 | 3681/SWD-I | 22/08/2024 | 322 | MILAN GHOSH | 92.68 | 0 | 50
2457 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for KALIKAPUR BARASAT PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018436] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000582/2022-2023 | 3067/SWD-I | 21/02/2023 | 975 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 47.69 | 0 | 100
2458 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kalikapur Barasat Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000967/2022-2023 | 1384/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.77 | 0 | 100
2459 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000135/2022-2023 | 3394/SWD-I | 10/03/2023 | 0 | Resource Division | 17.89 | 0 | 0
2460 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000283/2023-2024 | 2415/SWD-I | 30/09/2023 | 0 | Resource Division | 52.36 | 0 | 0
2461 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying on distribution system at zone-V, Mograhat-I Block under 'MEGA SURFACE WTER BASED WATER SUPPLY SCHEME" for Falta-Mathurapur, Dist. South 24-Pgs. Under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-II | JE3 | ORD/000140/2022-2023 | 1359/SWD-I | 19/09/2022 | 925 | M/S. S.S. ENTERPRISE | 511.9 | 0 | 75
2462 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-V (Barijpur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14727] | AE SWSD-II | JE3 | ORD/000368/2024-2025 | 3527/SWD-I | 07/08/2024 | 273 | M/S. S.S. ENTERPRISE (NODAKHALI) | 480.15 | 0 | 40
2463 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000257/2023-2024 | 1718/SWD-I | 08/08/2023 | 0 | Resource Division | 188.58 | 0 | 0
2464 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-X/B, Kalikapota (OHR Cap-600 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE2 | ORD/000309/2021-2022 | 2605/SWD-I | 15/03/2022 | 365 | MS R. DUTTA AND CO | 2.08 | 0 | 100
2465 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, upgradation of boundary wall and construction of Chlorination Roomunder Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/B at KALIKAPOTA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14728) | AE SWSD-II | JE2 | ORD/000406/2024-2025 | 3630/SWD-I | 20/08/2024 | 316 | HUMAYUN SK. CONSTRUCTION | 209.98 | 0 | 20
2466 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | AE SWSD-II | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 740 | TARUN ENTERPRISE | 922.07 | 0 | 70
2467 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 1 no. deep Tube well (300mm x 200mm dia. & 360 mtr. deep) with allied works under Zone-VII (Sarisha Ramkrishna Mission water supply scheme ) of Diamond Harbour-II Block of Diamond Harbour Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000213/2023-2024 | 953/AD | 06/06/2023 | 45 | CIVIL CRAFT | 28.55 | 0 | 70
2468 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-VII at Kamarpole of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-950] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000305/2023-2024 | 1508/AD | 15/07/2023 | 1197 | JYOTY SOLAR POWER | 423.33 | 0 | 15
2469 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000141/2022-2023 | 16/AD | 05/04/2023 | 0 | Resource Division | 32.1 | 0 | 0
2470 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000183/2023-2024 | 1274/AD | 05/07/2023 | 0 | Resource Division | 32.1 | 0 | 0
2471 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000117/2022-2023 | 1662/AD | 10/06/2022 | 120 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 369.02 | 0 | 20
2472 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New & Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Nagartala (Zone - I &II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001661/2022-2023 | 11474/AD | 15/02/2023 | 90 | MERAJUL ALAM | 78.41 | 0 | 35
2473 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001676/2022-2023 | 11485/AD | 15/02/2023 | 45 | SAHANA ENTERPRISE | 7.07 | 0 | 100
2474 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001677/2022-2023 | 11486/AD | 15/02/2023 | 45 | SAHANA ENTERPRISE | 7.06 | 0 | 100
2475 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001679/2022-2023 | 11488/AD | 15/02/2023 | 777 | PAL AGENCY | 7.1 | 0 | 98
2476 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000007/2023-2024 | 115/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
2477 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000135/2023-2024 | 842/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2478 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000255/2023-2024 | 3047/AD | 28/09/2023 | 0 | Resource Division | 232.42 | 0 | 0
2479 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Nagartala Zone-II PH-4 Water supply scheme under Canning-II block. Reference ID:-106599060, Application No :-1007776063 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00378/2024-2025 | BP-2024-25-88 | 05/06/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
2480 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/03522/2023-2024 | BP-2023-24-386 | 23/11/2023 | 0 | WBSEDCL | 22.27 | 0 | 0
2481 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04078/2023-2024 | BP-2023-24-424 | 18/12/2023 | 0 | WBSEDCL | 3.69 | 0 | 0
2482 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/06256/2023-2024 | BP-2023-24-643 | 29/03/2024 | 0 | WBSEDCL | 13.27 | 0 | 0
2483 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Nagartala (Zone-1 & 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000041/2023-2024 | 1002/SMD | 10/04/2023 | 840 | ESENCE ENGINEERING CONCERN | 21.57 | 0 | 100
2484 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Zone-II Pump House no- 5 of Aug of Nagartala W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/15081) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000615/2025-2026 | 982/SMSD | 15/07/2025 | 21 | M/S.UTTAM KUMAR CHATTERJEE | 0.29 | 0 | 0
2485 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Zone-II Pump House no- 5 of Aug of Nagartala W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/15081) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000680/2025-2026 | 983/SMSD | 15/07/2025 | 21 | M/S.UTTAM KUMAR CHATTERJEE | 0.66 | 0 | 0
2486 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Augmentation of Nagartala Zone-I and II Piped water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001913/2023-2024 | 1195/SMD | 22/03/2024 | 380 | ROY & BISWAS ENGG. CO. | 12.99 | 0 | 95
2487 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Augmentation of Nagartala Zone-I and II Piped water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001915/2023-2024 | 1196/SMD | 22/03/2024 | 621 | M/S.UTTAM KUMAR CHATTERJEE | 12.99 | 0 | 95
2488 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Belaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000410/2022-2023 | 3808/SMD | 29/12/2022 | 90 | H.K. DAS & CO. | 35.56 | 0 | 0
2489 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BELARIA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016728] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000111/2023-2024 | 518/SWD-I | 10/05/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 47.68 | 0 | 0
2490 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BELARIA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2889] [TSM/016728] | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 1781/SWD-I | 11/08/2023 | 300 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 600.96 | 0 | 0
2491 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary Wall (length=175.00m) & Construction of Service Road (length=300.00m) at OHR Site (1st Tubewell Site) for BELARIA PWSS to accommodate FHTC in Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based WAter Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/14548) | Assistant Engineer | Junior Engineer | ORD/000671/2024-2025 | 4397/SWD-I | 23/10/2024 | 90 | M/S SHIBAM ENTERPRISE | 83.71 | 0 | 0
2492 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "BELARIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 418/SWD-I | 20/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.83 | 0 | 0
2493 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000286/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 41.07 | 0 | 0
2494 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(B) at Kulpi block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-5259]. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000012/2023-2024 | 03/AD | 04/04/2023 | 1080 | S.MISRA INFRADEV PVT. LTD. | 1217.22 | 0 | 60
2495 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from Distribution System under Zone - VIIIB & Zone-X at Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - X/B) [No. of FHTC = 9578] | Assistant Engineer, Diamond Harbour sub division |  | ORD/000342/2023-2024 | 1560/AD | 17/07/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 512.43 | 0 | 0
2496 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(B) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001021/2022-2023 | 294/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.59 | 0 | 100
2497 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-VIIIB at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/15320] | Assistant Engineer, Diamond Harbour sub division |  | ORD/001048/2024-2025 | 4992/AD | 05/12/2024 | 420 | SHYAM DEVELOPER | 113.34 | 0 | 0
2498 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at porposed OHR site at Mouza - Laxmipur under Zone- VIIIB of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001370/2024-2025 | 5499/AD | 27/12/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 22.15 | 0 | 0
2499 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(B) (Lakshmipur, OHR Size-600 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002100/2022-2023 | 339/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2500 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-VIIIB of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002150/2024-2025 | 409/AD | 31/01/2025 | 30 | S.MISRA INFRADEV PVT. LTD. | 21.56 | 0 | 0
2501 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000146/2022-2023 | 11/AD | 05/04/2023 | 0 | Resource Division | 38.18 | 0 | 0
2502 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000196/2023-2024 | 1629/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
2503 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000211/2023-2024 | 2020/AD | 05/08/2023 | 0 | Resource Division | 12.51 | 0 | 0
2504 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000623/2023-2024 | 284/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
2505 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000856/2023-2024 | 763/AD | 03/02/2024 | 0 | Resource Division | 7.76 | 0 | 0
2506 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000939/2023-2024 | 1281/AD | 02/03/2024 | 0 | Resource Division | 1.24 | 0 | 0
2507 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
2508 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- IX of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000123/2023-2024 | 602/AD | 15/05/2023 | 90 | M/S B.M. CONSTRUCTION | 111.14 | 0 | 80
2509 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Uttar Laxminarayanpur W/S Scheme (Zone-IX, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000433/2023-2024 | 1921/AD | 01/08/2023 | 30 | ALISHA ENTERPRISE | 19.83 | 0 | 100
2510 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- IX of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000657/2024-2025 | 4203/AD | 23/10/2024 | 60 | TANMAY ROY CHOWDHURY | 34.45 | 0 | 0
2511 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Uttar Laxminarayanpur W/S Scheme, modified as Zone- IX of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001302/2024-2025 | 5376/AD | 23/12/2024 | 30 | M/S IDEAL WORKS | 4.76 | 0 | 90
2512 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Over Head Reservoir site at Zone IX of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003645/2024-2025 | 1016/RSD | 24/01/2025 | 60 | R. ENTERPRISE (II) | 4.3 | 0 | 100
2513 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000603/2023-2024 | 232/AD | 11/01/2024 | 0 | Resource Division | 4.38 | 0 | 0
2514 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V of Uttar Angadberia W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000243/2023-2024 | 1395/AD | 12/07/2023 | 45 | S.P. CONSTRUCTION (I) | 89.25 | 0 | 0
2515 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (200 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Uttar Angadberia Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001030/2023-2024 | 3314/AD | 07/10/2023 | 45 | SWASTIK ENTERPRISE | 36.08 | 0 | 65
2516 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Uttar Angadberia W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001817/2022-2023 | 12157/AD | 01/03/2023 | 45 | THE TOWER CONSTRUCTION | 7.09 | 0 | 0
2517 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Uttar Angadberia Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001948/2022-2023 | 11507/AD | 15/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 1.52 | 0 | 95
2518 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000070/2023-2024 | 3040/AD | 28/09/2023 | 0 | Resource Division | 57.93 | 0 | 0
2519 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000728/2023-2024 | 551/AD | 25/01/2024 | 0 | Resource Division | 59.7 | 0 | 0
2520 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service connection at P.H. No.5 of Uttar Angadberia w/s scheme . | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01679/2024-2025 | BP-2024-25-396 | 27/09/2024 | 0 | WBSEDCL | 8.55 | 0 | 0
2521 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Uttar Angadberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000031/2023-2024 | 981/SMD | 05/04/2023 | 90 | DURJA ENTERPRISE | 10.76 | 0 | 0
2522 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000704/2023-2024 | 474/AD | 24/01/2024 | 0 | Resource Division | 5.48 | 0 | 0
2523 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 921] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000038/2023-2024 | 173/AD | 19/04/2023 | 804 | SARDAR ENTERPRISE | 354.02 | 0 | 56
2524 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Harishpur W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000187/2025-2026 | 555/CSD | 02/05/2025 | 30 | SANGJOG | 3.1 | 0 | 0
2525 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work for Augmentation of Harishpur (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000732/2024-2025 | 4390/AD | 05/11/2024 | 45 | SARDAR ENTERPRISE | 33.94 | 0 | 0
2526 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001853/2022-2023 | 11819/AD | 23/02/2023 | 45 | TECH VISION | 3.68 | 0 | 0
2527 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002017/2022-2023 | 12923/AD | 21/03/2023 | 560 | M/S. TRIPATHI & CO. | 31.2 | 0 | 95
2528 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002507/2023-2024 | 1602/CSD | 28/02/2024 | 30 | NASKAR ENTERPRISE | 3.59 | 0 | 100
2529 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002508/2023-2024 | 1603/CSD | 28/02/2024 | 30 | KIRON CONSTRUCTION | 2.63 | 0 | 100
2530 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000057/2023-2024 | 264/AD | 24/04/2023 | 0 | Resource Division | 45.85 | 0 | 0
2531 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000419/2023-2024 | 374/AD | 19/01/2024 | 0 | Resource Division | 5.67 | 0 | 0
2532 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-II) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1076] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000039/2023-2024 | 1289/AD | 06/07/2023 | 665 | PATHIK PABAN NANDI | 429.73 | 0 | 56
2533 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000235/2023-2024 | 1388/AD | 12/07/2023 | 386 | S.S.COMSULTANCY & CONSTRUCTION | 21.99 | 0 | 90
2534 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001849/2022-2023 | 11815/AD | 23/02/2023 | 45 | TECH VISION | 3.89 | 0 | 0
2535 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001979/2022-2023 | 12640/AD | 13/03/2023 | 45 | R.G. ENTERPRISE (I) | 8.59 | 0 | 100
2536 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002009/2022-2023 | 12915/AD | 21/03/2023 | 45 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.92 | 0 | 98
2537 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002036/2022-2023 | 13032/AD | 24/03/2023 | 45 | TAPAN DAS (NEW) | 43.96 | 0 | 25
2538 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000052/2023-2024 | 259/AD | 24/04/2023 | 0 | Resource Division | 42.97 | 0 | 0
2539 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000414/2023-2024 | 370/AD | 19/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
2540 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/04079/2023-2024 | BP-2023-24-416 | 16/12/2023 | 0 | WBSEDCL | 3.62 | 0 | 0
2541 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/04682/2023-2024 | BP-2023-24-504 | 12/02/2024 | 0 | WBSEDCL | 8.16 | 0 | 0
2542 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Satjelia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gpsaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000275/2023-2024 | 1135/SMD | 24/04/2023 | 773 | UNIVERSAL ENTERPRISES | 22.53 | 0 | 90
2543 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Satjelia Zone-II PH-1, under Gosaba Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001854/2024-2025 | 1085/SMSD | 31/07/2024 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.88 | 0 | 0
2544 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Satjelia Zone-II PH-2, under Gosaba Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001855/2024-2025 | 1084/SMSD | 31/07/2024 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.88 | 0 | 0
2545 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000035/2023-2024 | 170/AD | 19/04/2023 | 90 | S.R. ENTERPRISE | 104.91 | 0 | 98
2546 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1140] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000036/2023-2024 | 171/AD | 19/04/2023 | 741 | K.B. ENTERPRISE | 113.44 | 0 | 90
2547 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16027) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000155/2024-2025 | 2506/AD | 15/06/2024 | 518 | M/S DEBABRATA DAS | 91.21 | 0 | 25
2548 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000365/2023-2024 | 1566/AD | 17/07/2023 | 899 | M/S DEBABRATA DAS | 298.39 | 0 | 80
2549 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investigation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001349/2023-2024 | 4127/AD | 24/11/2023 | 312 | M/S DEBABRATA DAS | 10.02 | 0 | 100
2550 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001833/2022-2023 | 12183/AD | 01/03/2023 | 45 | GOLDEN GROUPS | 38.57 | 0 | 80
2551 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
2552 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme (Debnagar) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002161/2022-2023 | 8334/AD | 12/12/2022 | 45 | M/S R.DUTTA & CO. | 5.66 | 0 | 100
2553 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Debnagar PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002218/2023-2024 | 875/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2554 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Debnagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002278/2023-2024 | 915/AD | 08/02/2024 | 358 | P & S ASSOCIATES | 9.6 | 0 | 100
2555 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000482/2023-2024 | 4784/AD | 19/12/2023 | 0 | Resource Division | 27.67 | 0 | 0
2556 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000555/2023-2024 | 43/AD | 03/01/2024 | 0 | Resource Division | 15.09 | 0 | 0
2557 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000906/2023-2024 | 894/AD | 07/02/2024 | 0 | Resource Division | 12.81 | 0 | 0
2558 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000982/2023-2024 | 1775/AD | 27/03/2024 | 0 | Resource Division | 3.32 | 0 | 0
2559 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Debnagar W/S Scheme PH-1 Application No:- 1007183483 Reference ID:- 106222545 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00967/2024-2025 | BP-2024-25-186 | 19/07/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
2560 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/05391/2023-2024 | BP-2023-24-597 | 28/03/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
2561 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Debnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000114/2023-2024 | 1021/SMD | 12/04/2023 | 871 | ANJAN ENTERPRISE | 21.62 | 0 | 85
2562 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Debnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/16027) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002431/2024-2025 | 1670/AE-II/SMD | 06/01/2025 | 15 | ANJAN ENTERPRISE | 0.9 | 0 | 0
2563 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Debnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] (SM/16027) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002432/2024-2025 | 1671/AE-II/SMD | 06/01/2025 | 15 | ANJAN ENTERPRISE | 0.9 | 0 | 0
2564 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -3 of Sonakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000056/2022-2023 | 792/AD | 12/05/2022 | 30 | G.B. CONSTRUCTION (TW) | 17.99 | 0 | 94
2565 | Alipore Division | Canning Sub-division | Surging of 03 nos. Big dia Tubewell of Sonakhali (Zone-II) (TW-2) and Harbhangi (TW-3 & 4) W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000241/2025-2026 | 680/CSD | 26/05/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
2566 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1220] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000256/2023-2024 | 1444/AD | 13/07/2023 | 60 | RIVER BENZ CONSTRUCTION | 265.52 | 0 | 81
2567 | Alipore Division | Canning Sub-division | onstruction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000313/2024-2025 | 2694/AD | 24/06/2024 | 45 | SAHANA ENTERPRISE | 7.08 | 0 | 0
2568 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Sonakhali (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000487/2024-2025 | 3546/AD | 02/09/2024 | 122 | MONDAL ENTERPRISE (MURSHIDABAD) | 43.98 | 0 | 95
2569 | Alipore Division | Canning Sub-division | Inter connection in between the replacement tubewell towards distribution system for Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001255/2023-2024 | 1203/CSD | 10/11/2023 | 30 | C.S. CONSTRUCTION | 1.01 | 0 | 0
2570 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001852/2022-2023 | 11818/AD | 23/02/2023 | 45 | TECH VISION | 4.56 | 0 | 0
2571 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
2572 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000036/2023-2024 | 241/AD | 24/04/2023 | 0 | Resource Division | 85.44 | 0 | 0
2573 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000393/2023-2024 | 334/AD | 19/01/2024 | 0 | Resource Division | 7.52 | 0 | 0
2574 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
2575 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Mrinalnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000131/2024-2025 | 2407/AD | 07/06/2024 | 30 | M/S DHIRENDRA ENTERPRISE | 9.53 | 0 | 0
2576 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
2577 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Mrinalnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000956/2023-2024 | 2988/AD | 26/09/2023 | 45 | ANANTA KUMAR GIRI | 27.69 | 0 | 0
2578 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Mrinalnagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/16292) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001364/2024-2025 | 5485/AD | 27/12/2024 | 230 | S. CHAKRABORTY AND CO. | 40.78 | 0 | 100
2579 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Mrinalnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002072/2023-2024 | 768(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2580 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2581 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Mrinalnagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002164/2022-2023 | 8337/AD | 12/12/2022 | 45 | LEMNISCATE | 6.95 | 0 | 100
2582 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000125/2023-2024 | 660/AD | 17/05/2023 | 0 | Resource Division | 15.22 | 0 | 0
2583 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000452/2023-2024 | 4717/AD | 18/12/2023 | 0 | Resource Division | 31.65 | 0 | 0
2584 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000819/2023-2024 | 664/AD | 30/01/2024 | 0 | Resource Division | 2.73 | 0 | 0
2585 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Mrinalnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000112/2023-2024 | 1012/SMD | 11/04/2023 | 90 | SARKAR ELECTRICAL | 21.77 | 0 | 0
2586 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Jamalhati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur, Sonarpur] | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 1113/SMD | 20/04/2023 | 90 | K.S.P ENTERPRISE | 17.99 | 0 | 0
2587 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAMALHATI PWSS of BARUIPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/019799] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 559/SWD-I | 12/05/2023 | 30 | BHATTACHARJEE AND CO | 31.68 | 0 | 90
2588 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for JAMALHATI MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =508] [TSM/019799] | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 718/SWD-I | 29/05/2023 | 90 | MS MANABESH ROY | 132.6 | 0 | 40
2589 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Jamalhati Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000920/2022-2023 | 1171/SWD-I | 30/08/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
2590 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000264/2023-2024 | 2429/SWD-I | 30/09/2023 | 0 | Resource Division | 21.25 | 0 | 0
2591 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000329/2023-2024 | 274/SWD-I | 10/01/2024 | 0 | Resource Division | 3.13 | 0 | 0
2592 | Alipore Division | Baruipur Sub-Division | Road restoration of 1) Conslrucfion Of Biluminous Road From Mirpur School To Matarmaa Veri 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01706/2024-2025 | BP-2024-25-791 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 4.04 | 0 | 0
2593 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00125/2024-2025 | BP-2024-25-35 | 24/04/2024 | 0 | WBSEDCL | 5 | 0 | 0
2594 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Sankarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1093/SMD | 18/04/2023 | 1109 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 0 | 50
2595 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Sankarpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sankarpur)(SM/16134) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000276/2024-2025 | 912/SMSD | 25/06/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0 | 0
2596 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Sankarpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sankarpur)(SM/16134) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000277/2024-2025 | 911/SMSD | 25/06/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0 | 100
2597 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Sankarpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16134) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 892/SMSD | 19/06/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.58 | 0 | 0
2598 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for SANKARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =556] [TSM/017762] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 934/SWD-I | 06/06/2023 | 900 | DIPTI ENTERPRISE | 138.93 | 0 | 80
2599 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKARPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017762] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000652/2022-2023 | 3349/SWD-I | 09/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
2600 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Sankarpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000932/2022-2023 | 1224/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
2601 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000113/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 25.88 | 0 | 0
2602 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad W/S Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000120/2024-2025 | 2398/AD | 07/06/2024 | 208 | S. CHAKRABORTY AND CO. | 39.9 | 0 | 100
2603 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000134/2023-2024 | 606/AD | 15/05/2023 | 60 | SIMPLEX DRILLING CO. | 36.27 | 0 | 0
2604 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Ramnagarabad and Dakshin Durgapur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16759 and 16758) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000329/2024-2025 | 2732/AD | 25/06/2024 | 494 | M/S B. ENTERPRISE | 318.12 | 0 | 25
2605 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. (1 no.) and 300 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000765/2023-2024 | 2911/AD | 20/09/2023 | 300 | M/S B. ENTERPRISE | 547.29 | 0 | 25
2606 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing at 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001164/2023-2024 | 3726/AD | 03/11/2023 | 60 | SUDIP PRADHAN | 5.14 | 0 | 0
2607 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1192] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001214/2023-2024 | 3818/AD | 07/11/2023 | 90 | M/S B. ENTERPRISE | 377.97 | 0 | 30
2608 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
2609 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002162/2023-2024 | 806/AD | 05/02/2024 | 60 | M/S B. ENTERPRISE | 27.51 | 0 | 100
2610 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002163/2023-2024 | 807/AD | 05/02/2024 | 30 | M/S. BABA KAPIL MUNI ENTERPRISE | 9.36 | 0 | 0
2611 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramnagar Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002624/2023-2024 | 881/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2612 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000112/2023-2024 | 648/AD | 17/05/2023 | 0 | Resource Division | 10.14 | 0 | 0
2613 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000480/2023-2024 | 4757/AD | 19/12/2023 | 0 | Resource Division | 42.86 | 0 | 0
2614 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000765/2023-2024 | 599/AD | 29/01/2024 | 0 | Resource Division | 1.82 | 0 | 0
2615 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/03415/2023-2024 | BP-2023-24-370 | 13/11/2023 | 0 | WBSEDCL | 4.06 | 0 | 0
2616 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramnagar Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001274/2024-2025 | 277/SMD | 30/01/2025 | 90 | A.K.SIKDAR | 0 | 0 | 0
2617 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Ramnagar Bazar to Sakhartpur Battafa, Bangal para under ramnagar-2 gp 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01697/2024-2025 | BP-2024-25-786 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.64 | 0 | 0
2618 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01503/2023-2024 | BP-2023-24-174 | 02/08/2023 | 0 | WBSEDCL | 2.88 | 0 | 0
2619 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000062/2023-2024 | 1056/SMD | 18/04/2023 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 25.66 | 0 | 100
2620 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No- 1 & 2 of RAMNAGAR (Zone-I) water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002198/2023-2024 | 354/SMSD | 20/03/2024 | 15 | DITHI ENTERPRISE | 0.78 | 0 | 100
2621 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002345/2023-2024 | 1454/SMSD | 30/11/2023 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 100
2622 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002347/2023-2024 | 134/SMSD | 02/02/2024 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 100
2623 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002381/2023-2024 | 1452/SMSD | 30/11/2023 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.58 | 0 | 100
2624 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.25] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00485/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 5.42 | 0 | 0
2625 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00760/2024-2025 | BP-2024-25-451 | 06/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 48.96 | 0 | 0
2626 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-I) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018210] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 843/SWD-I | 05/06/2023 | 887 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 276.76 | 0 | 88
2627 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000407/2021-2022 | 1945/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0
2628 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based RAMNAGAR (Zone-I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15755) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000523/2024-2025 | 4016/SWD-I | 13/09/2024 | 60 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 95.5 | 0 | 0
2629 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-I) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018210] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000631/2022-2023 | 3258/SWD-I | 02/03/2023 | 30 | MUNNA AGROTECH ENTERPRISE | 31.76 | 0 | 100
2630 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000108/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 19.94 | 0 | 0
2631 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000106/2023-2024 | 1545/AD | 17/07/2023 | 15 | GANGA TUBEWELL AND HARDWARE | 10.68 | 0 | 0
2632 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000107/2023-2024 | 1546/AD | 17/07/2023 | 15 | M/S. MIHIR KUMAR NASKAR | 15.23 | 0 | 0
2633 | Alipore Division | Canning Sub-division | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000312/2023-2024 | 1514/AD | 15/07/2023 | 90 | M/S ROY TRADING CO. | 183.15 | 0 | 60
2634 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2147] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000313/2023-2024 | 1515/AD | 15/07/2023 | 90 | M/S ROY TRADING CO. | 139.14 | 0 | 0
2635 | Alipore Division | Canning Sub-division | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte.(TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000361/2023-2024 | 1562/AD | 17/07/2023 | 546 | M N J ENTERPRISES | 174.43 | 0 | 90
2636 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1909] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000362/2023-2024 | 1563/AD | 17/07/2023 | 90 | M/S GIRIDHARI ENTERPRISE | 125.9 | 0 | 0
2637 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-III), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 715] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000368/2023-2024 | 1569/AD | 17/07/2023 | 763 | S.R.ENTERPRISE | 146.5 | 0 | 50
2638 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-III), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000392/2023-2024 | 1778/AD | 26/07/2023 | 60 | CIVIL CRAFT | 59.88 | 0 | 100
2639 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-I), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000550/2023-2024 | 2082/AD | 07/08/2023 | 60 | BHATTACHARJEE & CO. | 60.27 | 0 | 66
2640 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-II), Block - Canning-II under Canning Sub Division of Alipore Division, P | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000551/2023-2024 | 2083/AD | 07/08/2023 | 165 | G.B. CONSTRUCTION (TW) | 60.27 | 0 | 65
2641 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Matherdighi (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000612/2023-2024 | 1831/AD | 27/07/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 12.1 | 0 | 98
2642 | Alipore Division | Canning Sub-division | Laying of Pipeline and other allied works of AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II and III) PIPED WATER SUPPLY SCHEME , Block ¿ Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Matherdighi, Zone-III) SM/18280 | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001018/2023-2024 | 3303/AD | 07/10/2023 | 30 | M/S. LOKNATH CONSTRUCTION | 6.24 | 0 | 100
2643 | Alipore Division | Canning Sub-division | Laying of washout pipe line with other allied works at Matherdighi RO Plant (Zone -A) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001051/2024-2025 | 1269/CSD | 18/11/2024 | 30 | SUKANTA HALDER | 4.17 | 0 | 100
2644 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-III) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001354/2023-2024 | 4426/AD | 06/12/2023 | 406 | AHANA ENTERPRISE | 8.02 | 0 | 90
2645 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
2646 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002506/2023-2024 | 1561/AD | 16/03/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0
2647 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002510/2023-2024 | 1562/AD | 16/03/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0
2648 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - I) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002515/2023-2024 | 1563/AD | 16/03/2024 | 45 | M/S GIRIDHARI ENTERPRISE | 7.5 | 0 | 0
2649 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - II)(2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002517/2023-2024 | 1564/AD | 16/03/2024 | 260 | M/S GIRIDHARI ENTERPRISE | 7.26 | 0 | 100
2650 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002519/2023-2024 | 1565/AD | 16/03/2024 | 322 | RIDIP ENTERPRISE | 7.26 | 0 | 100
2651 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002566/2024-2025 | 893/AD | 04/03/2025 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
2652 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002569/2024-2025 | 894/AD | 04/03/2025 | 45 | KIRON CONSTRUCTION | 7.05 | 0 | 0
2653 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-III, PH-1 under Canning -II block (REF ID : 106665562) (APP ID: 1007924028) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00997/2024-2025 | BP-2024-25-197 | 30/07/2024 | 0 | WBSEDCL | 2.02 | 0 | 0
2654 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-III PH-3 under Canning -II block | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00998/2024-2025 | BP-2024-25-198 | 30/07/2024 | 0 | WBSEDCL | 13.33 | 0 | 0
2655 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone- I PH-3 under Canning -II block (REF ID : 106665563) (APP ID: 1007924056) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00999/2024-2025 | BP-2024-25-199 | 30/07/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
2656 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-II, PH-1 under Canning -II block (REF ID : 106665564) (APP ID: 1007924727) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/01000/2024-2025 | BP-2024-25-200 | 30/07/2024 | 0 | WBSEDCL | 13 | 0 | 0
2657 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-III PH-2 under Canning -II block (REF ID : 106665555) (APP ID: 1007924044) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/01001/2024-2025 | BP-2024-25-201 | 30/07/2024 | 0 | WBSEDCL | 11.04 | 0 | 0
2658 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-II, PH-2 under Canning -II block (REF ID : 106665559) (APP ID: 1007924629) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/01002/2024-2025 | BP-2024-25-202 | 30/07/2024 | 0 | WBSEDCL | 3.75 | 0 | 0
2659 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Matherdighi Zone-I, PH-2 under Canning -II block (REF ID : 106665560) (APP ID: 1007924076) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/01003/2024-2025 | BP-2024-25-203 | 30/07/2024 | 0 | WBSEDCL | 5.35 | 0 | 0
2660 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Matherdighi and adjoining mouza (inconnction with Kulerkhoj ) PH-1 Water supply scheme under Canning-II block. Reference ID:-106599046, Application No :-1007775984 | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/02038/2024-2025 | BP-2024-25-486 | 09/12/2024 | 0 | WBSEDCL | 10.53 | 0 | 0
2661 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, (Zone-I) , P.H. 1,2 & 3, (Zone-II), P.H. 1,2 & 3, (Zone-III) for Augmentation of Mather Dighi Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000269/2023-2024 | 1129/SMD | 24/04/2023 | 984 | M/S. S.S. ENTERPRISE | 82.02 | 0 | 30
2662 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-III) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000588/2022-2023 | 649/SMD | 03/03/2023 | 90 | B. P. CONSTRUCTION | 8.85 | 0 | 100
2663 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-1 Kuler Khoj water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002195/2024-2025 | 1754/SMSD | 31/12/2024 | 15 | KARUNAMOY ENGINEERING | 0.8 | 0 | 0
2664 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Zone-III Pump House no- 1 & 2,3 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002384/2024-2025 | 465/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0
2665 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-2 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002385/2024-2025 | 456/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.71 | 0 | 0
2666 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-1 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002386/2024-2025 | 457/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.73 | 0 | 0
2667 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Zone-III Pump House no-3 of Aug of Matherdighi W/S Scheme under SMD, P.H.E. Dte.(Block-Canning-II) (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002387/2024-2025 | 458/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.71 | 0 | 0
2668 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-1 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002388/2024-2025 | 464/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0
2669 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-1 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002389/2024-2025 | 463/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0
2670 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-2 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002390/2024-2025 | 462/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0
2671 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-2 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002391/2024-2025 | 461/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0
2672 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of UPVC column pipe, sluice valve non return valve etc. at Zone-III PH-3 Aug of Matherdighi water supply scheme under Canning-II Block under SMD, P.H.E. Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002392/2024-2025 | 460/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.74 | 0 | 0
2673 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type 3 phase actuator operated wafer type butterfly valve at Zone-III PH-3 Aug of Matherdighi water supply scheme under Canning -II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002393/2024-2025 | 459/SMSD | 21/03/2025 | 15 | M/S. S.S. ENTERPRISE | 0.99 | 0 | 0
2674 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-1 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002438/2024-2025 | 409/SMSD | 20/03/2025 | 21 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0
2675 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-3 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002439/2024-2025 | 410/SMSD | 20/03/2025 | 21 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0
2676 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of submersible pump motor at Aug of Matherdighi Zone-III PH-2 water supply scheme under Canning-II block Under SMD PHE Dte. (SM/18280) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002440/2024-2025 | 466/SMSD | 21/03/2025 | 21 | M/S. S.S. ENTERPRISE | 0.57 | 0 | 0
2677 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Baintala water supply scheme adjacent to Augmentation of Ground water based Mather Dighi ( Zone-I,II & III) piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002929/2023-2024 | 2301/SMD | 27/06/2023 | 703 | DITHI ENTERPRISE | 9.39 | 0 | 90
2678 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kuler Khoj water supply scheme adjacent to Augmentation of Ground water based Mather Dighi ( Zone-I,II & III) piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002930/2023-2024 | 2302/SMD | 27/06/2023 | 771 | KARUNAMOY ENGINEERING | 9.25 | 0 | 95
2679 | Alipore Division | Diamond Harbour Sub-Division | Road restoration at an urgent basis at Koutala, Dari Koutala, Shimulberia, Lakshminarayanpur, Kushberia, Kishorepur, Krishnarampur, Nakali, under Dhola G.P under the Augmentation Scheme of Kulpi Zone-VII under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000017/2025-2026 | 1928/AD | 23/04/2025 | 45 | SRINAGAR COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED | 9.01 | 0 | 90
2680 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VII at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-5851]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000340/2023-2024 | 1557/AD | 17/07/2023 | 624 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1417.15 | 0 | 20
2681 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001019/2022-2023 | 292/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.52 | 0 | 99
2682 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-VII under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001368/2024-2025 | 5497/AD | 27/12/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 92.22 | 0 | 0
2683 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VII (Simulberia, OHR Size-900 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002101/2022-2023 | 340/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2684 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000008/2024-2025 | 5160/AD | 12/12/2024 | 0 | Resource Division | 61.6 | 0 | 0
2685 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000194/2023-2024 | 1628/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
2686 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000209/2023-2024 | 2017/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
2687 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000368/2023-2024 | 3232/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2688 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000668/2023-2024 | 421/AD | 22/01/2024 | 0 | Resource Division | 39 | 0 | 0
2689 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000866/2023-2024 | 773/AD | 03/02/2024 | 0 | Resource Division | 36.04 | 0 | 0
2690 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000937/2023-2024 | 1279/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2691 | Alipore Division |  | Road restoration for L036- Gabbria on T01 to Purba paschima para (WB02 403) |  |  | BILL/01735/2024-2025 | BP-2024-25-799 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.64 | 0 | 0
2692 | South 24 Pgs W/S Division I |  | Lakshmikantapur Dhola Road from 1.00KM to 2.00km Restoration of hard shoulder due to laying of pipelinesby PHE Department under Lakshmikantapur Highway Sub Division in the district of South 24 Parganas. (SM/18715) |  |  | BILL/00634/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 4.47 | 0 | 0
2693 | South 24 Pgs W/S Division I |  | Construction of Boundary wall for proposed 500 Cum OHR Site of Zone-V within Mandirbazar block, Mouza-PurbaShrinagar (JL No-98), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 135 mtr.) |  |  | ORD/000021/2022-2023 | 876/SWD-I | 14/07/2022 | 60 | MS P B CONSTRUCTION | 25.37 | 0 | 100
2694 | South 24 Pgs W/S Division I |  | Construction of Hume Pipe Culvert 4.80 Mtr.span with 195 Mtr.Long temporary approach road(Plot No-183,189,189) for proposed Zone -V,OHR Site at Purba Srinagar Mouza(J.L.NO-98,Dag No-80,Khatian No-(60,147&256).at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014532) |  |  | ORD/000381/2023-2024 | 1817/SWD-I | 16/08/2023 | 508 | M/S. KALPANA CONSTRUCTION | 13.51 | 0 | 60
2695 | South 24 Pgs W/S Division I |  | Diversion of Water for "Construction of Hume Pipe Culvert of 10.00 Mtr span for proposed Zone-V OHR Site at Purba Shreenagar Mouza (J.L.NO-132) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18715) |  |  | ORD/000432/2024-2025 | 3874/SWD-I | 03/09/2024 | 30 | M/S. KALPANA CONSTRUCTION | 6.06 | 0 | 100
2696 | South 24 Pgs W/S Division I |  | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) |  |  | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 780 | BALAJEE ENTERPRISES | 760.19 | 0 | 75
2697 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PURBA SRINAGAR MOUZA in MANDIRBAZAR (ZONE-V) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000462/2021-2022 | 1987/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4.42 | 0 | 100
2698 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 58.22 | 0 | 0
2699 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmnetation of Kharamba water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001521/2022-2023 | 917/SMD | 30/03/2023 | 90 | RELIABLE CONSTRUCTION | 25.16 | 0 | 0
2700 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KHARAMBA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018344] |  |  | ORD/000300/2023-2024 | 1665/SWD-I | 03/08/2023 | 745 | ASIT PRAMANIK | 31.76 | 0 | 50
2701 | South 24 Pgs W/S Division I |  | Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) and construction of Pump House cum Chlorine Room (2 Nos.) for KHARAMBA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3153) (TSM/018344) |  |  | ORD/000359/2023-2024 | 1751/SWD-I | 10/08/2023 | 90 | SSN NIRMAN UDYOG | 554.06 | 0 | 40
2702 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) |  |  | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 45 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 0 | 100
2703 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of KHARAMBA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18545) |  |  | ORD/000679/2024-2025 | 4468/SWD-I | 29/10/2024 | 75 | SSN NIRMAN UDYOG | 170.84 | 0 | 0
2704 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 38.49 | 0 | 0
2705 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000325/2023-2024 | 251/SWD-I | 10/01/2024 | 0 | Resource Division | 19.42 | 0 | 0
2706 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01989/2023-2024 | BP-2023-24-239 | 11/09/2023 | 0 | WBSEDCL | 4.84 | 0 | 0
2707 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Jagatipota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000121/2023-2024 | 1103/SMD | 19/04/2023 | 90 | JAGANNATH ENTERPRISE | 21.77 | 0 | 0
2708 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Jagatipota scheme under SMD, P.H.E. Dte.(Block-Sonarpur) |  |  | ORD/000296/2024-2025 | 1013/SMSD | 11/07/2024 | 15 | JAGANNATH ENTERPRISE | 0.89 | 0 | 0
2709 | S24 Pgns Mechanical |  | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Jadatipota W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) |  |  | ORD/000297/2024-2025 | 938/SMSD | 28/06/2024 | 15 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0
2710 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Jagatipota W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) |  |  | ORD/002202/2023-2024 | 264/SMSD | 23/02/2024 | 15 | JAGANNATH ENTERPRISE | 0.89 | 0 | 0
2711 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGATIPOTA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018121] |  |  | ORD/000294/2023-2024 | 1659/SWD-I | 03/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
2712 | South 24 Pgs W/S Division I |  | Construction of 300 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGOTIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1766) (TSM/018121) |  |  | ORD/000420/2023-2024 | 1967/SWD-I | 24/08/2023 | 300 | SAMSUL ENTERPRISE | 617.72 | 0 | 20
2713 | South 24 Pgs W/S Division I |  | Construction of Hume Pipe Culvert 4.80 Mtr.span with 23 Mtr.Long temporary approach road at OHR Site of "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18546) |  |  | ORD/000529/2024-2025 | 4075/SWD-I | 19/09/2024 | 30 | SAMSUL ENTERPRISE | 13.07 | 0 | 0
2714 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain, Development of land & others allied works of JAGATIPOTA PWSS within Sonarpur Block "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18546) |  |  | ORD/000825/2023-2024 | 1299/SWD-I | 15/03/2024 | 45 | SAMSUL ENTERPRISE | 43.64 | 0 | 0
2715 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 17.9 | 0 | 0
2716 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 257/SWD-I | 10/01/2024 | 0 | Resource Division | 10.88 | 0 | 0
2717 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kabasenre having village with maximum 62 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001737/2022-2023 | 11766/AD | 21/02/2023 | 60 | MUNNA AGROTECH ENTERPRISE | 30.53 | 0 | 0
2718 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000868/2023-2024 | 775/AD | 03/02/2024 | 0 | Resource Division | 0.47 | 0 | 0
2719 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kabasenre Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000603/2022-2023 | 681/SMD | 10/03/2023 | 90 | M/S. BABUSONA ENTERPRISE | 8.85 | 0 | 0
2720 | S24 Pgns Mechanical |  | Charges for new service connection at pump house no-1 of Sankharipur water supply scheme (Baruipur Block) |  |  | BILL/01724/2024-2025 | BP-2024-25-409 | 30/09/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
2721 | S24 Pgns Mechanical |  | Charges for new service connection at pump house no-2 of Sankharipur water supply scheme (Baruipur Block) |  |  | BILL/01725/2024-2025 | BP-2024-25-410 | 30/09/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
2722 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Sankharipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000224/2024-2025 | 2455/SMD | 01/08/2024 | 334 | A.G.ENTERPRISE | 12.47 | 0 | 80
2723 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 for Sankharipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000347/2024-2025 | 2125/SMD | 12/07/2024 | 263 | SHRESTHA | 12.59 | 0 | 80
2724 | South 24 Pgs W/S Division I |  | Construction of platform for FHTC, pipeline protection work, development of land and other allied works for "Ground Water Based SANKHARIPUR PWSS Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18870) |  |  | ORD/000358/2024-2025 | 3458/SWD-I | 02/08/2024 | 45 | MOUMITA ENTERPRISE | 58.31 | 0 | 0
2725 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of SANKHARIPUR of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 917] |  |  | ORD/000565/2023-2024 | 2611/SWD-I | 17/10/2023 | 623 | MOUMITA ENTERPRISE | 139.7 | 0 | 94
2726 | South 24 Pgs W/S Division I |  | Sinking of 02 (two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKHARIPUR PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18870] |  |  | ORD/000715/2023-2024 | 3431/SWD-I | 29/12/2023 | 45 | DEV & COMPANY | 31.8 | 0 | 100
2727 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Sankharipur Piped Water Supply Scheme to accommodate FHTC in Baruipuri Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000987/2022-2023 | 1484/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
2728 | Alipore Division | Raidighi Sub-Division | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, boundary wall and other allied works at Zone- XV of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10532 & SM/18872) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000432/2024-2025 | 3275/AD | 07/08/2024 | 300 | PINKI CONSTRUCTION | 129.16 | 0 | 0
2729 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Over Head Reservoir site at Zone ¿ XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000873/2024-2025 | 4657/AD | 20/11/2024 | 45 | L.N. ENTERPRISE | 12.97 | 0 | 100
2730 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000874/2024-2025 | 4658/AD | 20/11/2024 | 60 | M/S. JHARNA ENTERPRISE | 29.11 | 0 | 0
2731 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
2732 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Kashiabad PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000912/2023-2024 | 270(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2733 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( UTTAR KASHIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001050/2022-2023 | 3677/AD | 01/08/2022 | 45 | LEMNISCATE | 4.84 | 0 | 100
2734 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001161/2023-2024 | 3723/AD | 03/11/2023 | 45 | M/S MALI ENTERPRISE | 27.74 | 0 | 60
2735 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001162/2023-2024 | 3724/AD | 03/11/2023 | 30 | KHATEJA CONSTRUCTION | 9.5 | 0 | 0
2736 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Kashiabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001311/2022-2023 | 9894/AD | 10/01/2023 | 45 | BENGAL ENTERPRISE | 38.58 | 0 | 0
2737 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2738 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000121/2023-2024 | 658/AD | 17/05/2023 | 0 | Resource Division | 8.96 | 0 | 0
2739 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000450/2023-2024 | 4715/AD | 18/12/2023 | 0 | Resource Division | 38.71 | 0 | 0
2740 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000814/2023-2024 | 659/AD | 30/01/2024 | 0 | Resource Division | 1.61 | 0 | 0
2741 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/03417/2023-2024 | BP-2023-24-376 | 13/11/2023 | 0 | WBSEDCL | 6.17 | 0 | 0
2742 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uttar Kasiabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000438/2022-2023 | 3834/SMD | 29/12/2022 | 1018 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 19.05 | 0 | 15
2743 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Kashinagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18873) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000215/2024-2025 | 2598/AD | 19/06/2024 | 45 | M/S AINUR ENTERPRISE | 9.73 | 0 | 0
2744 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter at 3rd Tubewell Site of Kashinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000322/2024-2025 | 2397/AD | 07/06/2024 | 30 | S. CHAKRABORTY AND CO. | 19.95 | 0 | 100
2745 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
2746 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( KASINAGAR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001363/2023-2024 | 3259/AD | 05/10/2023 | 45 | LEMNISCATE | 5.75 | 0 | 100
2747 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Kashinagar Water Supply Scheme (Augmentation), Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001410/2023-2024 | 4596/AD | 14/12/2023 | 30 | AQUATECH ENGINEERS | 18.31 | 0 | 0
2748 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
2749 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000999/2023-2024 | 1792/AD | 27/03/2024 | 0 | Resource Division | 33.67 | 0 | 0
2750 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Augmentation of Kashinagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001550/2023-2024 | 4764/SMD | 06/12/2023 | 91 | T.S. CONSTRUCTION | 10.53 | 0 | 0
2751 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IVA at Gardoani mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 6618] | AE BSD |  | ORD/000277/2023-2024 | 1559/SWD-I | 26/07/2023 | 120 | RELIABLE SANITARY AND PLUMBING CO. | 446.56 | 0 | 0
2752 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IVB at Gardoani mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC= 6319] | AE BSD |  | ORD/000371/2022-2023 | 2315/SWD-I | 19/12/2022 | 840 | SAMIRON GHOSH | 426.47 | 0 | 40
2753 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF specials for laying of DI pipe (250mm dia, 400mm dia & 450mm dia) at zone-IV B (Gardoani) of Joynagar-II Block of Baruipur Sub-Division, for "Mega Surface Based water supply scheme for Falta-Mathurapur, District South 24-Pgns, W/S Division-I, PHE. Dte | AE BSD |  | ORD/000997/2022-2023 | 1078/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 3.65 | 0 | 100
2754 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000081/2022-2023 | 2997/SWD-I | 20/02/2023 | 0 | Resource Division | 79.69 | 0 | 0
2755 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Gangasagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-B) (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000423/2024-2025 | 4440/AD | 06/11/2024 | 182 | PIKASU BOSE | 126.64 | 0 | 100
2756 | Alipore Division | Kakdwip Sub-Division | Supply and installation on hire basis Printed Flex Banner for Creating Public Awareness on JJM for different area of Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001334/2024-2025 | 5423/AD | 24/12/2024 | 30 | SHOUMMODIP AND CO. | 11.44 | 0 | 100
2757 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGASAGAR (ZONE - I & II) PWSS (PHASE - B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001362/2023-2024 | 3436/AD | 12/10/2023 | 45 | VOYAGER | 7.61 | 0 | 100
2758 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
2759 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main and FHTC for 1 year after completion of FHTC works for Augmentation of Gangasagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002231/2023-2024 | 904/AD | 08/02/2024 | 783 | ANUP PAUL | 390.45 | 0 | 30
2760 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002622/2023-2024 | 865(A)/KSD | 13/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2761 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000716/2023-2024 | 486/AD | 24/01/2024 | 0 | Resource Division | 13.4 | 0 | 0
2762 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000903/2023-2024 | 889/AD | 07/02/2024 | 0 | Resource Division | 67.34 | 0 | 0
2763 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000968/2023-2024 | 1760/AD | 27/03/2024 | 0 | Resource Division | 29.12 | 0 | 0
2764 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection PHED, Ganga Sagar Mouza Zone-I PH-III W/ Scheme Near Helipad Application No:- 1007971659 Reference ID: 106689505 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/01156/2024-2025 | BP-2024-25-232 | 08/08/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
2765 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Ganga Sagar Mouza Zone-I PH-4 (PHE Campus 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000718/2024-2025 | 3424/SMD | 28/10/2024 | 180 | T.S. CONSTRUCTION | 8.61 | 0 | 95
2766 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Ganga Sagar Mouza Zone-I PH-3 (Near Helipad) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000719/2024-2025 | 3425/SMD | 28/10/2024 | 90 | M/S. BABUSONA ENTERPRISE | 8.22 | 0 | 95
2767 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Dharmatala Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000082/2020-2021 | 5305/AD | 18/02/2021 | 365 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 257.73 | 47.48 | 78
2768 | Alipore Division | Canning Sub-division | Laying pipe line at Badhukulla of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000300/2023-2024 | 187/CSD | 23/05/2023 | 30 | GOUTAM HALDAR (I) | 0.95 | 0 | 100
2769 | Alipore Division | Canning Sub-division | Laying pipe line Badhukulla and Naliakhali of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000588/2022-2023 | 5864/AD | 18/10/2022 | 15 | SAB ENGINEERING WORKS | 9.27 | 0 | 100
2770 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Mouza-Amtala Bhadri, Dakshin Kalikatala, Herobhanga and Basur Chak of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001063/2021-2022 | 5298/AD | 04/01/2022 | 60 | SAHANA ENTERPRISE | 28.74 | 0 | 100
2771 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 60 | B.K. ENTERPRISE. | 59.91 | 0 | 90
2772 | Alipore Division | Canning Sub-division | Laying rising main from tubewell no. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001407/2023-2024 | 1146/CSD | 01/11/2023 | 30 | GOUTAM HALDAR (I) | 1.92 | 0 | 100
2773 | Central Drilling | Canning Sub-division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MMX150MMX 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DHARMATALA W/S SCH (REPLACEMENT TW-IV), CANNING-I BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000315/2022-2023 | 54/CDD | 08/04/2022 | 30 | C.M. ENTERPRISE | 14.55 | 0 | 0
2774 | Central Drilling | Canning Sub-division | ADDITIONAL TRANSPORTATION OF WASHED GRAVELS, SEALING OF SALINE ZONE AND OTHERS FOR CONSTRUCTION OF TUBEWELL IN DHAMATALA W/S SCHEME(REPLACEMENT TW-IV), CANNING -I BLOCK UNDER CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000507/2022-2023 | 42/CMSD-II | 16/02/2023 | 10 | C.M. ENTERPRISE | 0.82 | 0 | 100
2775 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no-3 of Nabagram-3 | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01723/2024-2025 | BP-2024-25-412 | 30/09/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
2776 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no -2 of Nabagram (Baruipur Block) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01981/2024-2025 | BP-2024-25-482 | 03/12/2024 | 0 | WBSEDCL | 15.91 | 0 | 0
2777 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/03275/2023-2024 | BP-2023-24-365 | 04/11/2023 | 0 | WBSEDCL | 3.49 | 0 | 0
2778 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 ,2 & 3 of NABAGRAM W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000344/2024-2025 | 890/SMSD | 19/06/2024 | 15 | SWAPAN ENTERPRISE | 0.87 | 0 | 0
2779 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Nabagram scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000353/2024-2025 | 1003/SMSD | 11/07/2024 | 386 | SWAPAN ENTERPRISE | 0.92 | 0 | 100
2780 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Nabagram scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000354/2024-2025 | 1004/SMSD | 11/07/2024 | 386 | SWAPAN ENTERPRISE | 0.92 | 0 | 100
2781 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Nabagram water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000481/2022-2023 | 234/SMD | 24/01/2023 | 1163 | SWAPAN ENTERPRISE | 39.02 | 0 | 73
2782 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Nabagram W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002473/2023-2024 | 276/SMSD | 29/02/2024 | 15 | SWAPAN ENTERPRISE | 0.92 | 0 | 0
2783 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at NABAGRAM of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 2040] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000024/2023-2024 | 96/SWD-I | 10/04/2023 | 90 | TANMOY ROY CHOWDHURY | 459.09 | 0 | 80
2784 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of NABAGRAM Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000367/2021-2022 | 1944/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 100
2785 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for NABAGRAM PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000564/2022-2023 | 3058/SWD-I | 21/02/2023 | 30 | MD NOOR ALAM | 47.63 | 0 | 100
2786 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (One no.) at 1st Tube well site of NABAGRAM piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [For T/W site-1] (SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000658/2024-2025 | 4388/SWD-I | 23/10/2024 | 60 | SANGJOG | 4.93 | 0 | 100
2787 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based NABAGRAM Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000905/2023-2024 | 1204/SWD-I | 11/03/2024 | 45 | R. UNIQUE CONSTRUCTION | 40.41 | 0 | 0
2788 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000188/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 45.61 | 0 | 0
2789 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electric bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/00371/2023-2024 | BP-2023-24-26 | 17/05/2023 | 0 | WBSEDCL | 7.08 | 0 | 0
2790 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Bill for electricity payment for security deposit for New Service Connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01302/2022-2023 | BP-2022-23-440 | 10/03/2023 | 0 | WBSEDCL | 1.53 | 0 | 0
2791 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Birlapur (CT) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-I] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000517/2022-2023 | 376/SMD | 15/02/2023 | 90 | M/S. S.S. ENTERPRISE | 25.69 | 0 | 80
2792 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, delivery and installation of LED Board and other allied works at P.H. No. - 1 under Birlapur CT Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Budge Budge - I)(SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002371/2023-2024 | 158-AE-II-SMD | 09/02/2024 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.75 | 0 | 100
2793 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of backwash pipe line from newly installed IEP to nearby canal at Birlapur under Birlapur (CT) PWSS to accommodate FHTC in Budge Budge-I block under South 24 Pgns. W/S Division-I, for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000018/2025-2026 | 970/SWD-I | 09/04/2025 | 45 | MONDAL PRECISION PVT. LTD. | 20.63 | 0 | 0
2794 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Engagement of expertise to improve the performance and functionality at the end of consumers (FHTC) of the water supply system using Hydraulic Isolation Structures near Birlapur (CT) under South 24-Parganas Water Supply Division-I, PHE Dte. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000070/2025-2026 | 1509/SWD-I | 03/06/2025 | 45 | AJIVAM WATER PRIVATE LIMITED | 10 | 0 | 100
2795 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Piped Water Supply Scheme at Mayapur Village (JL. - 46) (Sansad III & IV) of Budge Budge - I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. (Route surveying of 40KM) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000194/2022-2023 | 714/SWD-I | 24/06/2022 | 180 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 0 | 100
2796 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Birlapur (CT) Piped Water Supply Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000299/2022-2023 | 1885/SWD-I | 16/11/2022 | 30 | PADMA ENGINEERING CO. | 40.15 | 0 | 100
2797 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 0 | 98
2798 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 2 (Two) nos. boundary walls with allied works for Birlapur CT pipe water supply scheme to accommodate FHTC in Budge Budge-I block under South 24- Parganas. W/S Division-I, PHE Dte. South 24-Pargans District for Augmentation of surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns District. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000366/2024-2025 | 3506/SWD-I | 07/08/2024 | 45 | MS KRISHNA MONDAL | 36.9 | 0 | 0
2799 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of road and providing pipe supporting structures near Mayapur GP Kabarsthan for BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in Budge Budge -I block under South 24 Parganas W/S Division-I, South 24-Pgns District for Augmentation of Surface Based Water Supply Scheme in the affected areas of South 24-Pgns (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000382/2024-2025 | 3573/SWD-I | 12/08/2024 | 45 | MS POUSALI ENTERPRISE | 3.09 | 0 | 100
2800 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection of Tubewell Sites in Mayapur GP "Ground water based BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas". (TSM/013487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000400/2023-2024 | 1909/SWD-I | 21/08/2023 | 45 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.69 | 0 | 100
2801 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 02nos. Pump House (Size 4.80mX3.66m) at tubewell site zone- I & II of Birlapur (CT) PWSS of Budge Budge-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000430/2022-2023 | 2579/SWD-I | 10/01/2023 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 13.69 | 0 | 100
2802 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of distribution pipeline and providing FHTC for BIRLAPUR (CT) PWSS including restoration of roads under South 24-Pgns W/S Division-I, P.H.E. Dte., District South 24 Parganas. [No. of FHTC = 2032] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000510/2022-2023 | 2940/SWD-I | 16/02/2023 | 60 | M/S. S.S. ENTERPRISE | 208.47 | 0 | 60
2803 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 02 (Two) nos. 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Birlapur (CT) PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12214] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000697/2022-2023 | 3500/SWD-I | 16/03/2023 | 15 | PADMA ENGINEERING CO. | 6.1 | 0 | 0
2804 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road Restoration damaged due to laying of pipeline at Booth 116/117 of Mayapur Gp and adjoining areas under command area of Birlapur (CT) piped water supply scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns. W/S Division-I, South 24-Pgns. district for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic afeected areas of South 24-Parganas. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000769/2024-2025 | 4690/SWD-I | 18/11/2024 | 45 | SRIJON ENTERPRISE | 26.65 | 0 | 100
2805 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of additional pipeline for Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns. Water Supply Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in Arsenic Affected Areas of South 24-Pgns. Dist. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000776/2023-2024 | 804/SWD-I | 16/02/2024 | 45 | STAR ENTERPRISE | 43.78 | 0 | 60
2806 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60mX3.00m) Birlapur Piped Water Supply Scheme for Zone-I & Zone-II of Budge Budge-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000834/2023-2024 | 1096/SWD-I | 05/03/2024 | 45 | SANJAY MIDDEY | 7.06 | 0 | 100
2807 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of RIDF Road at Chakatala near Birlapur with allied works under Ground Water Based BIRLAPUR(CT) Piped Water Supply Scheme of South 24 Pargana W/S Supply Division- I, P.H.E Dte. (TSM/013487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000837/2023-2024 | 1151/SWD-I | 07/03/2024 | 45 | PROJECT AND MAINTENANCE | 16.89 | 0 | 100
2808 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply, installation, trail run and commissioning of Pressure Transmitter and display arrangement in connection to Piped water supply scheme for Birlapur CT under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. [SM/12214] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001121/2024-2025 | 115/SWD-I | 10/01/2025 | 7 | B.S. RUBBER INDUSTRIES | 0.53 | 0 | 0
2809 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Fitting of Air Valves and Pressure Gauges to different points of Rising Main towards Mayapur Gp near Birlapur (CT) under Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns W/S Divn.-I, South 24pgns Dist. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001130/2024-2025 | 193/SWD-I | 17/01/2025 | 30 | SRIJON ENTERPRISE | 21.72 | 0 | 0
2810 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Charges for New service connection at Badehoogly Pump house-1 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00214/2024-2025 | BP-2024-25-71 | 16/05/2024 | 0 | WBSEDCL | 4.42 | 0 | 0
2811 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Badehugli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000870/2022-2023 | 363/SMD | 10/02/2023 | 781 | SANKAR PRASAD DUTTA & CO. | 26.54 | 0 | 40
2812 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Badehugli W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/12209) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001173/2024-2025 | 1661/SMSD | 13/12/2024 | 15 | SANKAR PRASAD DUTTA & CO. | 0.91 | 0 | 0
2813 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Badehugli W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/12209) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001174/2024-2025 | 1660/SMSD | 13/12/2024 | 15 | SANKAR PRASAD DUTTA & CO. | 0.58 | 0 | 0
2814 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12209) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000141/2025-2026 | 2247/SWD-I | 02/09/2025 | 45 | RIMON ENTERPRISE | 10.04 | 0 | 0
2815 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BADEHUGLI Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000265/2022-2023 | 1776/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
2816 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall , Pathway, Drain & others allied works at HW Site of " BADEHUGLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/12209) [2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000405/2024-2025 | 3683/SWD-I | 22/08/2024 | 252 | MAJUMDER ENTERPRISE | 40.94 | 0 | 20
2817 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 995] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000514/2022-2023 | 2944/SWD-I | 16/02/2023 | 990 | MAJUMDER ENTERPRISE | 299.69 | 0 | 50
2818 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube-well to achieve 66 mtr. housing pipe by Rotary Method for BADEHUGLI PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12209] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000736/2022-2023 | 3574/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
2819 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at head work site for BADEHUGLI PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12209] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 777/SWD-I | 13/02/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 0 | 100
2820 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Land development at Badehugli Head Work Site within Poleghat Gram Panchayet under Sonarpur Block for "Ground Water Based BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12209) [2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000797/2023-2024 | 1145/SWD-I | 07/03/2024 | 420 | MAJUMDER ENTERPRISE | 11.01 | 0 | 100
2821 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000006/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.62 | 0 | 0
2822 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000227/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.13 | 0 | 0
2823 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road damaged due to laying of pipeline from Post Office More to Kalitala More, Kalitala More to Dharmatala, Rajballabhpur Bazar to Zone-II OHR site,Nilkuthi More to Dharmatala More and Nilkuthi More to Beramara More under the Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II at RAJBALLABHPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 Pgns. under South 24 Pgns Water Supply Division-I, PHE Dte. (SM/18707) | Assistant Engineer | JE1 | ORD/000088/2025-2026 | 1763/SWD-I | 02/07/2025 | 135 | SANJAY ENTERPRISE | 32.4 | 0 | 60
2824 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipeline for distribution system,Protection of distribution pipeline and Construction of FHTC Platform for Zone-II (Rajballabhpur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | Assistant Engineer | JE1 | ORD/000280/2024-2025 | 3004/SWD-I | 28/06/2024 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 206.32 | 0 | 2
2825 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site in Zone-II at Rajballabhpur of Mograhat-I block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II AT RAJBALLABHPUR OF MOGRAHAT-I BLOCK within "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District- South 24-Parganas" under South 24 Parganas W/S Division-I, PHE Dte. (Total Length-114 mtr excluding Gate) (TSM/014908) | Assistant Engineer | JE1 | ORD/000356/2023-2024 | 1742/SWD-I | 10/08/2023 | 594 | SANJAY ENTERPRISE | 19.15 | 0 | 60
2826 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1000 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in Zone-II at Rajballabhpur of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in Zone-II at Rajballabhpur of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 6219 Nos.) | Assistant Engineer | JE1 | ORD/000418/2023-2024 | 1964/SWD-I | 24/08/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1097.7 | 0 | 30
2827 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of chlorination room, approach road, land development and other allied works under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% HouseHold in Zone-II (Rajballabhpur) under Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. (SM/18707) | Assistant Engineer | JE1 | ORD/000431/2024-2025 | 3873/SWD-I | 03/09/2024 | 45 | ROYAL CONSTRUCTION | 29.29 | 0 | 20
2828 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road after laying of pipe line for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in Zone-II at Rajballabhpur under Magrahat-I Block within 'Mega Surface water based water supply scheme for Falta-Mathurapur' under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas. (SM/18707) | Assistant Engineer | JE1 | ORD/000434/2024-2025 | 3876/SWD-I | 03/09/2024 | 45 | SANJAY ENTERPRISE | 26.45 | 0 | 85
2829 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system for Zone-II, Rajballabhpur (OHR Capacity- 1000 cum.) under Mograhat-I Block" under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. District. | Assistant Engineer | JE1 | ORD/000897/2022-2023 | 19/SWD-I | 06/04/2022 | 30 | LEMNISCATE | 2.4 | 0 | 100
2830 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000062/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 149.81 | 0 | 0
2831 | Alipore Division | Baruipur Sub-Division | Road restoration for Shikharbali-I GP lo Dakshin Kalyanpur | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01778/2024-2025 | BP-2024-25-803 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.31 | 0 | 0
2832 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01724/2023-2024 | BP-2023-24-199 | 09/08/2023 | 0 | WBSEDCL | 4.76 | 0 | 0
2833 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Indrapalla water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000460/2022-2023 | 3937/SMD | 30/12/2022 | 90 | JAGANNATH ENTERPRISE | 22.37 | 0 | 100
2834 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No- 1 & 2 of Indrapalla water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002340/2023-2024 | 352/SMSD | 20/03/2024 | 15 | TAMAL ENTERPRISE | 0.78 | 0 | 100
2835 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at INDRAPALLA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000117/2022-2023 | 1285/SWD-I | 14/09/2022 | 60 | S.C. ENTERPRISE | 10.92 | 0 | 100
2836 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of INDRAPALLA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000167/2021-2022 | 1923/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
2837 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for INDRAPALLA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000186/2022-2023 | 1480/SWD-I | 27/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
2838 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at INDRAPALLA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1009) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000308/2022-2023 | 1912\SWD-I | 18/11/2022 | 905 | MANAS CHATTERJEE | 219.29 | 0 | 90
2839 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Platform for providing FHTC, Protection works for pipeline and other allied works for Proposed Ground Water based INDRAPALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12264) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000732/2024-2025 | 4619/SWD-I | 13/11/2024 | 450 | MUNNA AGROTECH ENTERPRISE | 83.18 | 0 | 30
2840 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Indrapalla PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000794/2022-2023 | 3670/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 0 | 100
2841 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000105/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 41.78 | 0 | 0
2842 | Alipore Division | Diamond Harbour Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 360 mtr. deep Tubewell by Direct Rotary method for improvement of water supply at Pump House No. 01 of Birendra Bagaria W/S Scheme Block - Kulpi under Diamond Harbour Sub-Division in the District of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000473/2022-2023 | 5525/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 24.61 | 0 | 100
2843 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of Laying of distribution system at Zone-X of Kulpi Block for providing 100% FHTC under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - A) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000479/2023-2024 | 1992/AD | 04/08/2023 | 697 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1049.75 | 0 | 20
2844 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-X of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001023/2022-2023 | 296/DHSD | 15/09/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 4.14 | 0 | 98
2845 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000213/2023-2024 | 2022/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
2846 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000626/2023-2024 | 287/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
2847 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000665/2023-2024 | 325/AD | 19/01/2024 | 0 | Resource Division | 535.64 | 0 | 0
2848 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000860/2023-2024 | 767/AD | 03/02/2024 | 0 | Resource Division | 49.76 | 0 | 0
2849 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00005/2024-2025 | BP-2024-25-15 | 12/04/2024 | 0 | WBSEDCL | 4.76 | 0 | 0
2850 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Bidyadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000592/2023-2024 | 2616/SMD | 07/08/2023 | 665 | M/S. PS & ASSOCIATES | 25.92 | 0 | 40
2851 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bidyadharpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) |  |  | ORD/002842/2023-2024 | 292/SMSD | 07/03/2024 | 15 | PS & ASSOCIATES | 0.92 | 0 | 100
2852 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.18] |  |  | BILL/00477/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.46 | 0 | 0
2853 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18571)" |  |  | ORD/000232/2024-2025 | 2652/SWD-I | 07/06/2024 | 45 | SUJOY SADHUKHAN | 10.55 | 0 | 10
2854 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BIDYADHARPUR PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/019595] |  |  | ORD/000371/2023-2024 | 1780/SWD-I | 11/08/2023 | 660 | MOULI CONSTRUCTION | 31.76 | 0 | 100
2855 | South 24 Pgs W/S Division I |  | Construction of 500 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2838) (TSM/019595) |  |  | ORD/000447/2023-2024 | 2102/SWD-I | 30/08/2023 | 945 | O.K. CONSTRUCTION | 627.54 | 0 | 20
2856 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bidyadharpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000990/2022-2023 | 1502/SWD-I | 28/09/2022 | 30 | GEO SOLUTION | 2.9 | 0 | 100
2857 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of BIDYADHARPUR PWSS within Sonarpur Block BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18571) |  |  | ORD/001067/2024-2025 | 5219/SWD-I | 20/12/2024 | 132 | MAA GITA ENTERPRISE | 34.7 | 0 | 50
2858 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 23.28 | 0 | 0
2859 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza under Budge Budge I Block with allied works under " Surface water Based Mega water Supply Scheme for Falta Mathurapur" | AE SWSD-I |  | ORD/000111/2020-2021 | 1358/SWD-I | 08/12/2020 | 120 | M/S. S.S. ENTERPRISE | 97.1 | 76.44 | 0
2860 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Atmarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6114) Part -I | AE SWSD-I |  | ORD/000471/2022-2023 | 2783/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.86 | 0 | 100
2861 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
2862 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Budhakhali Zone - I (Part - I & II) W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) (2nd Call) (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000499/2024-2025 | 3602/AD | 06/09/2024 | 45 | M/S MALI ENTERPRISE | 27.79 | 0 | 50
2863 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Budhakhali Zone-1 PWSS, Block -Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14041) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000500/2024-2025 | 3603/AD | 06/09/2024 | 75 | UCON (II) | 92.85 | 0 | 0
2864 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Budhakhali Zone-I Part-II W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2023-2024 | 2350/AD | 18/08/2023 | 45 | UCON | 36.01 | 0 | 0
2865 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Budhakhali Zone-I (Part-II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000939/2023-2024 | 279(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2866 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001096/2022-2023 | 8431/AD | 15/12/2022 | 365 | M/S. J.K. TRIPATHI & SONS | 89.96 | 0 | 91
2867 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001097/2022-2023 | 8432/AD | 15/12/2022 | 60 | B.N.C. CONSTRUCTION | 85.86 | 0 | 90
2868 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001098/2022-2023 | 8433/AD | 15/12/2022 | 60 | M/S. UMA CONSTRUCTION | 88.4 | 0 | 100
2869 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001099/2022-2023 | 8434/AD | 15/12/2022 | 610 | GIRI ENTERPRISE | 88.01 | 0 | 95
2870 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001100/2022-2023 | 8435/AD | 15/12/2022 | 30 | DIPANKAR DUTTA | 20.66 | 0 | 60
2871 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Budhakhali Zone-I (Part- II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001101/2022-2023 | 8436/AD | 15/12/2022 | 45 | SARADA CONSTRUCTION | 36.64 | 0 | 0
2872 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone-I (Part-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001346/2022-2023 | 10101/AD | 17/01/2023 | 300 | UCON | 328.79 | 0 | 30
2873 | Alipore Division | Kakdwip Sub-Division | Sinking of 1 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using PVC Pipe and Pre-packed Resin Bonded Gravel at 2nd Tubewell Site of Budhakhali Zone-I Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001580/2021-2022 | 6960/AD | 29/03/2022 | 30 | SIMPLEX DRILLING CO. | 18.06 | 0 | 100
2874 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Budhakhali [Zone-I] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001810/2022-2023 | 05/AD | 01/04/2022 | 45 | M/S R.DUTTA & CO. | 7.34 | 0 | 95
2875 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (BUDAKHALI ZONE- I PWSS) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [Phase-I]. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001897/2021-2022 | 6921/AD | 28/03/2022 | 45 | M/S R.DUTTA & CO. | 7.34 | 0 | 0
2876 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
2877 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 1st Tubewell site for Budhakhali Zone 1 Part 1 W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002184/2024-2025 | 2065/KSD | 28/12/2024 | 20 | HARAKRISHNA KAMILA | 2.56 | 0 | 100
2878 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Budhakhali Zone - I (Part-1) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002185/2024-2025 | 2066/KSD | 28/12/2024 | 20 | IMAGINEER VENTURES | 2.44 | 0 | 0
2879 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000488/2023-2024 | 4785/AD | 19/12/2023 | 0 | Resource Division | 34.44 | 0 | 0
2880 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000552/2023-2024 | 40/AD | 03/01/2024 | 0 | Resource Division | 5.64 | 0 | 0
2881 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000785/2023-2024 | 629/AD | 30/01/2024 | 0 | Resource Division | 1.36 | 0 | 0
2882 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000907/2023-2024 | 895/AD | 07/02/2024 | 0 | Resource Division | 1.57 | 0 | 0
2883 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/01119/2023-2024 | BP-2023-24-158 | 24/07/2023 | 0 | WBSEDCL | 6.68 | 0 | 0
2884 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I (Part-I&II) for Augmentation of Budhakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000802/2022-2023 | 149/SMD | 16/01/2023 | 896 | DAS ENTERPRISE | 19.63 | 0 | 45
2885 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-2 of Budhakhali Aug (Part-I & II) W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002970/2023-2024 | 1286-AE-I-SMD | 11/12/2023 | 15 | DAS ENTERPRISE | 0.89 | 0 | 0
2886 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Paschim Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000124/2024-2025 | 2402/AD | 07/06/2024 | 272 | GRAVITA ENTERPRISE | 11.58 | 0 | 100
2887 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PASCHIM SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000979/2022-2023 | 3664/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.97 | 0 | 0
2888 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Paschim Sripatinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001278/2022-2023 | 9590/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
2889 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation Water Supply Scheme (PASCHIM SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001325/2022-2023 | 3308/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.97 | 0 | 100
2890 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Paschim Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002038/2023-2024 | 520/AD | 25/01/2024 | 585 | S.S.CONSULTANCY & CONSTRUCTION | 32.87 | 0 | 40
2891 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000098/2023-2024 | 544/AD | 12/05/2023 | 0 | Resource Division | 10.76 | 0 | 0
2892 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000303/2023-2024 | 3098/AD | 28/09/2023 | 0 | Resource Division | 18.47 | 0 | 0
2893 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000676/2023-2024 | 442/AD | 24/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
2894 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000743/2023-2024 | 578/AD | 29/01/2024 | 0 | Resource Division | 1.93 | 0 | 0
2895 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00111/2024-2025 | BP-2024-25-24 | 18/04/2024 | 0 | WBSEDCL | 16.77 | 0 | 0
2896 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Paschim Sripatinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000365/2022-2023 | 3769/SMD | 29/12/2022 | 808 | TAMAL ENTERPRISE | 22.23 | 0 | 90
2897 | Alipore Division | Diamond Harbour Sub-Division | Repairing of boundary wall at Pump House No-2 under Kulpi PWSS under Zone- IV of Kulpi Block for "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000325/2025-2026 | 267/DHSD | 16/06/2025 | 45 | M/S B ENTERPRISE | 4.6 | 0 | 0
2898 | Alipore Division | Diamond Harbour Sub-Division | Repairing of Pump House no-2 under Zone-IV of Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000328/2025-2026 | 268/DHSD | 16/06/2025 | 45 | S.S. ENTERPRISE (II) | 1.11 | 0 | 0
2899 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IV of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001045/2022-2023 | 290/DHSD | 15/09/2022 | 30 | MEASURE LAND | 3.66 | 0 | 98
2900 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-7293]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001136/2023-2024 | 3653/AD | 31/10/2023 | 500 | SAFECO ENTERPRISES | 1446.19 | 0 | 65
2901 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-IV (Sitarampur, OHR Size-1000 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002097/2022-2023 | 332/DHSD | 10/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2902 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000206/2023-2024 | 2024/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
2903 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000622/2023-2024 | 283/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
2904 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000669/2023-2024 | 422/AD | 22/01/2024 | 0 | Resource Division | 222.03 | 0 | 0
2905 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000858/2023-2024 | 765/AD | 03/02/2024 | 0 | Resource Division | 35.68 | 0 | 0
2906 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000934/2023-2024 | 1276/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2907 | S24 Pgns Mechanical |  | Payment of Additional Quotation for new service connection at Makhalia OHR (JL. No. 44) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application ID - 100000099662 Reference ID - 860291532 |  |  | BILL/01177/2024-2025 | BP-2024-25-241 | 12/08/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
2908 | S24 Pgns Mechanical |  | Payment of Additional Quotation for new service connection at Sultangunge OHR (JL. No. 66) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application ID - 100000099751 Reference ID - 860291661 |  |  | BILL/01178/2024-2025 | BP-2024-25-242 | 12/08/2024 | 0 | WBSEDCL | 7.61 | 0 | 0
2909 | S24 Pgns Mechanical |  | Quotation for new power connection at Baratala OHR (JL No-73) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782240 Reference Id- 106600770 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01179/2024-2025 | BP-2024-25-243 | 12/08/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
2910 | S24 Pgns Mechanical |  | Quotation for new power connection at Dhancheberia OHR (JL No-68) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782282 Reference Id- 106600776 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01180/2024-2025 | BP-2024-25-244 | 12/08/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
2911 | S24 Pgns Mechanical |  | Quotation for new power connection at Arjapara OHR (JL-97) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007782206 Reference Id- 106600759 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01181/2024-2025 | BP-2024-25-245 | 12/08/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
2912 | S24 Pgns Mechanical |  | Quotation for new power connection at Sehai OHR (JL-88) under augmentation of Surface Water Based Water Supply Scheme under Budge-budge-II, Bishnupur-II and part of Budge-budge-I Block. Application No- 1007766051 Reference Id- 106592632 Application Type- New Connection. Quotation Date-16/05/2024 |  |  | BILL/01182/2024-2025 | BP-2024-25-246 | 12/08/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
2913 | S24 Pgns Mechanical |  | Payment of Quotation for new service connection at Sultangunge OHR (JL. No. 66) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application No. - 1007514551 Reference ID - 106460076 |  |  | BILL/01183/2024-2025 | BP-2024-25-247 | 12/08/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
2914 | S24 Pgns Mechanical |  | Payment of Quotation for new service connection at Makhalia OHR (JL. No. 44) under Augmentation of Surface Water based Water Supply Scheme of Budge Budge - II, Bishnupur - II and part of Budge Budge - I Block Application No. - 1007514561 Reference ID - 106460075 |  |  | BILL/01185/2024-2025 | BP-2024-25-248 | 12/08/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
2915 | S24 Pgns Mechanical |  | Supply, Installation & commissioning of secondary Gaseous Chlorination arrangement for 14 (Fourteen) Nos. OHR points within Budge Budge-II Block under Improvement of water supply [Phase-I] in Bishnupur-I, Bishnupur-II and Budge Budge-II Block in the District of South 24 Pgs. under SMD PHE Dte. |  |  | ORD/002691/2023-2024 | 2943/SMD | 05/09/2023 | 849 | ORIENTAL ENGINEERING CO. | 400.14 | 0 | 60
2916 | S24 Pgns Mechanical |  | Supply, Installation & commissioning of secondary Gaseous chlorination arrangement for 15 (Fifteen) Nos. OHR points Within Bishnupur-II Block under Improvement of water supply [Phase-i] in Bishnupur-I, Bishnupur-II and Budge Budge- II Block in the district of South 24 Pgs. under SMD, PHE Dte. |  |  | ORD/002692/2023-2024 | 2977/SMD | 12/09/2023 | 366 | MACHINE SUPPLIERS SYNDICATE(PVT.) LTD. | 428.72 | 0 | 70
2917 | S24 Pgns Mechanical |  | Providing Power supply with gaseous chlorination arrangement at Booster Pumping Station GLR of Bishnupur-II Block for the Augmentation of Surface water based water supply scheme of Budge Budge-II, Bishnupur-II and part of Budge Budge-I Blocks in the District of South 24Pgs under South 24Pgs. Mechanical Division PHE Dte. |  |  | ORD/003200/2022-2023 | 694/SMD | 13/03/2023 | 933 | MACHINE SUPPLIERS SYNDICATE(PVT.) LTD. | 391.59 | 0 | 75
2918 | South 24 Pgs W/S Division I |  | Restoration of carriageway and Hard Sholder damaged due to laying of pipes by PHE Dte. Location - Ch.6.584 km to 14.50km along Burul Bowali Road under Diamond Harbour Highway Division in the district of South 24 Parganas. |  |  | BILL/01492/2023-2024 | BP-2023-24-499 | 24/11/2023 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 14.07 | 0 | 0
2919 | South 24 Pgs W/S Division I |  | Providing FHTC in connection to "Augmentation of surface water based water supply scheme for Budge Budge-II, Bishnupur-II and Budge Budge-I Blocks (Mayapur GP only)" under South 24-Pgns. W/S Division-I, PHE Dte., District - South 24-Parganas. [No. of FHTC = 90081] |  |  | ORD/000231/2023-2024 | 1375/SWD-I | 12/07/2023 | 901 | WPIL LTD. | 3016.78 | 0 | 10
2920 | South 24 Pgs W/S Division I |  | Construction of temporary Boundary Wall at Jagat Ballavpur JL 45 Dag No: 834, Kh -1 , Dist. South 24 Paraganas in connection with Augmentation of Budge Budge I/II and Bisnupur II Water Supply Scheme under South 24-Parganas Water Supply Division-I, PHE Dte. |  |  | ORD/000443/2021-2022 | 2608/SWD-I | 15/03/2022 | 60 | MS POUSALI ENTERPRISE | 1.86 | 0 | 100
2921 | South 24 Pgs W/S Division I |  | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] |  |  | ORD/000612/2022-2023 | 519/SWD-I | 30/05/2022 | 365 | AHMED REZA | 1.73 | 0 | 100
2922 | South 24 Pgs W/S Division I |  | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-I (Begampur) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). |  |  | ORD/000765/2022-2023 | 2938/SWD-I | 15/02/2023 | 120 | PEECON | 0.83 | 0 | 0
2923 | South 24 Pgs W/S Division I |  | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-II (Krishnamohan) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). |  |  | ORD/000766/2022-2023 | 2939/SWD-I | 15/02/2023 | 120 | PEECON | 0.83 | 0 | 0
2924 | South 24 Pgs W/S Division I |  | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] |  |  | ORD/000815/2022-2023 | 3720/SWD-I | 31/03/2023 | 365 | M/S. SYSCON | 2.52 | 0 | 90
2925 | South 24 Pgs W/S Division I |  | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] |  |  | ORD/000816/2022-2023 | 3721/SWD-I | 31/03/2023 | 365 | M/S. SYSCON | 2.05 | 0 | 95
2926 | South 24 Pgs W/S Division I |  | Balance work for Laying Distribution System, Rising Main pipe line, gap filling and construction of Approach Road, shifting of DI pipe, road restoration and other allied works in connection with Augmentation of Surface Water Based Water Supply Scheme of Budge Budge II, Bishnupur II and Budge Budge I (Mayapur Part) under South 24 Pgns W/S Division-I, PHE Dte. (SM/08869) |  |  | ORD/000863/2024-2025 | 4909/SWD-I | 02/12/2024 | 151 | WPIL LTD. | 1746.84 | 0 | 60
2927 | South 24 Pgs W/S Division I |  | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] |  |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0 | 50
2928 | South 24 Pgs W/S Division I |  | Acceptance-cum-Work Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] |  |  | ORD/000894/2022-2023 | 515/SWD-I | 30/05/2022 | 365 | AVIK HALDER | 1.77 | 0 | 100
2929 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1522/SWD-I | 29/09/2022 | 0 | Resource Division | 258.14 | 0 | 0
2930 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2119/SWD-I | 06/12/2022 | 0 | Resource Division | 1967.83 | 0 | 0
2931 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 2192/SWD-I | 13/12/2022 | 0 | Resource Division | 530.06 | 0 | 0
2932 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 398/SWD-I | 28/04/2023 | 0 | Resource Division | 2346 | 0 | 0
2933 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 2727/SWD-I | 06/11/2023 | 0 | Resource Division | 129.85 | 0 | 0
2934 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000308/2023-2024 | 2727/SWD-I | 06/11/2023 | 0 | Resource Division | 106.93 | 0 | 0
2935 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Wayleave Facility Charge (Station From-To Lakshmikantapur (LKPR) - Udairampur Halt (URP)) (Revenue Village Lakshmikantapur) | AE HQ-I |  | BILL/00102/2024-2025 | BP-2024-25-85 | 22/05/2024 | 0 | EASTERN RAILWAY SEALDAH DIVISION | 5.38 | 0 | 0
2936 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Permanent Restoration work of probable Black top damage which would caused due to laying of PHED pipe (Falta-Mathurapur Mega surface water supply scheme of PHED) on Purbabishnupur-Lakshmikantapur-Kulpi Road at Dayarampur (Ch. 10.33 kmp.), Raghunathpur (Ch. 11.55 kmp.) Madhusudanpur (Ch. 12.65 kmp.), Tantirhat (Ch.13.15 kmp.) and Mollarchak (Ch. 13.80 kmp.), under Diamond Harbour Division,P.W.Dte. in the district of South 24 Pgs. (SM/12205) | AE HQ-I |  | BILL/00683/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 7.66 | 0 | 0
2937 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of Zone-VI within Mandirbazar block, Mouza-Shibpur (JL No-59), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24 Pgns. Water Supply Division-I, PHE Dte. (Length- 110 mtr.) | AE HQ-I |  | ORD/000072/2022-2023 | 1153/SWD-I | 26/08/2022 | 60 | ARYA ENGINEERS | 15.32 | 0 | 0
2938 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 400 cum capacity Over Head Reservoir as per Departmental Drawing and specifications including RCC bored pile and pile cap within Zone-VI at Shibpur Mouza of Mandirbazar Block, for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24 Pgs District, under South 24 Pgns Water Supply Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I |  | ORD/000308/2023-2024 | 1697/SWD-I | 07/08/2023 | 633 | M/S SUBHODEEP ENTERPRISE | 133.72 | 0 | 20
2939 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of SHIBPUR MOUZA in MANDIRBAZAR (ZONE-VI) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000392/2021-2022 | 2603/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 4.62 | 0 | 100
2940 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Approach Road with Land Development and construction of Boundary Wall gate to facilitate the works within Head Work Site under the Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme Water Based Water Supply Scheme for Falta-Mathurapur, Dist- South 24-Pgns." under South 24-Pgns. W/S Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I |  | ORD/000619/2023-2024 | 2803/SWD-I | 09/11/2023 | 45 | M/S SUBHODEEP ENTERPRISE | 5.82 | 0 | 100
2941 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & laying of 610 mm dia (OD) MS Pipe conduits 85 mtr. in length to be prepared from 12.50 mm thick MS Plate by pipe jacking technique across and underneath the Railway Track at Raipur Dayarampur Railway Gate, LC Gate No. 29/C/E (Lat 22.108613°and Long 88.29267°) near Jame-raipur Dayarampur, Saroya in between 64/6 & 64/7 as per permission to be obtained from Railway Authority for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/12205) | AE HQ-I |  | ORD/000755/2023-2024 | 602/SWD-I | 02/02/2024 | 481 | S. ROY AND ASSOCIATES | 65.96 | 0 | 100
2942 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-VI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (TSM/014544) [5th SLSSC (2022-23)] | AE HQ-I |  | ORD/000771/2022-2023 | 3645/SWD-I | 28/03/2023 | 761 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 328.19 | 0 | 60
2943 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000048/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
2944 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Debipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001520/2022-2023 | 916/SMD | 30/03/2023 | 90 | M/S. S.S. ENTERPRISE (DOMKAL) | 25.09 | 0 | 0
2945 | South 24 Pgs W/S Division I |  | Additional Laying of distribution Network System for different dia HDPE pipe & Road Restoration for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18499) |  |  | ORD/000020/2025-2026 | 972/SWD-I | 09/04/2025 | 45 | THE TEESTA CONSTRUCTION | 71.48 | 0 | 0
2946 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DEBIPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018469] |  |  | ORD/000303/2023-2024 | 1671/SWD-I | 04/08/2023 | 580 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 0 | 50
2947 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 0 | 60
2948 | South 24 Pgs W/S Division I |  | Construction of 400 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2830) (TSM/018469) |  |  | ORD/000534/2023-2024 | 2360/SWD-I | 26/09/2023 | 300 | THE TEESTA CONSTRUCTION | 780.87 | 0 | 25
2949 | South 24 Pgs W/S Division I |  | Development of land, construction of approach road and other allied works at HW site & 2nd Tubewell site of "DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under Jal Jeevan Mission". (SM/18499) |  |  | ORD/000538/2024-2025 | 4095/SWD-I | 20/09/2024 | 60 | M/S SONALI CONSTRUCTION | 39.61 | 0 | 0
2950 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18499] |  |  | ORD/000755/2024-2025 | 4676/SWD-I | 18/11/2024 | 60 | SUJIT KUMAR SHARMA | 31.4 | 0 | 0
2951 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 22.96 | 0 | 0
2952 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 253/SWD-I | 10/01/2024 | 0 | Resource Division | 17.43 | 0 | 0
2953 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000075/2020-2021 | 5352/AD | 19/02/2021 | 365 | SUPRITI ENTERPRISE | 404.97 | 212.18 | 99
2954 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Gondia Raghunathpur village due to Swajal Gram activities under Zone-III of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000581/2022-2023 | 5857/AD | 18/10/2022 | 30 | SRIJON ENTERPRISE | 38.07 | 0 | 100
2955 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001207/2021-2022 | 404/DHSD | 28/12/2021 | 121 | SUMAN HALDER | 1.6 | 0 | 0
2956 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IIIA at Diamond Harbour- II block for providing House Hold Tap connection, under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001403/2024-2025 | 5527/AD | 28/12/2024 | 45 | DURGA ENTERPRISE | 19.3 | 0 | 0
2957 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Akrapanji, OHR Size-1250) within Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002092/2022-2023 | 326/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2958 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000003/2021-2022 | 2022/AD | 01/09/2021 | 0 | Resource Division | 4.07 | 0 | 0
2959 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000121/2022-2023 | 12051/AD | 27/02/2023 | 0 | Resource Division | 4.82 | 0 | 0
2960 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000881/2023-2024 | 755/AD | 03/02/2024 | 0 | Resource Division | 28.59 | 0 | 0
2961 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000920/2023-2024 | 1262/AD | 02/03/2024 | 0 | Resource Division | 0.93 | 0 | 0
2962 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 119.83 | 100
2963 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 152.32 | 100
2964 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution pipe line damaged due to widening and strengthening of Falta PWD main road at Falta Zone-I for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001192/2021-2022 | 5709/AD.. | 31/01/2022 | 60 | S.P. CONSTRUCTION (V) | 50.97 | 0 | 0
2965 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001765/2020-2021 | 1224/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 4.25 | 0
2966 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kali Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001779/2020-2021 | 1226/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 4.25 | 0
2967 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-I), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001787/2020-2021 | 1232/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 4.27 | 0
2968 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Part) & Bamankhali (Part) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001794/2020-2021 | 1239/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.66 | 4.6 | 0
2969 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001804/2020-2021 | 1243/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 4.28 | 0
2970 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001809/2020-2021 | 1247/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.69 | 0
2971 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001810/2020-2021 | 1249/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.75 | 0
2972 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001812/2020-2021 | 1251/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.71 | 0
2973 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001824/2020-2021 | 1258/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 4.24 | 0
2974 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001825/2020-2021 | 1259/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.74 | 0
2975 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001831/2020-2021 | 1262/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.63 | 0
2976 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001832/2020-2021 | 1263/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 4.24 | 0
2977 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001834/2020-2021 | 1265/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.72 | 0
2978 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001852/2020-2021 | 1283/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 4.27 | 0
2979 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001862/2020-2021 | 1293/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.74 | 0
2980 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001866/2020-2021 | 1297/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.73 | 0
2981 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001872/2020-2021 | 1302/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.75 | 0
2982 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001886/2020-2021 | 1308/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 3.39 | 0
2983 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-V) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001888/2020-2021 | 1310/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 2.85 | 0
2984 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001890/2020-2021 | 1312/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.74 | 0
2985 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001892/2020-2021 | 1314/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.72 | 0
2986 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001926/2020-2021 | 1338/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 4.28 | 0
2987 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000020/2022-2023 | 1197/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
2988 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 480 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 51
2989 | Alipore Division |  | HIRING OF AN Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer, DIAMOND HARBOUR SUB-DIVISION under Alipore Division, PHE Dte. (From 01.11.23 to 30.04.2023) |  |  | BILL/03385/2023-2024 | BP-2023-24-954 | 25/01/2024 | 0 | GOPAL KUMAR JHA | 0.7 | 0 | 0
2990 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-II including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000068/2021-2022 | 343/AD | 12/05/2021 | 365 | B. MOOKHERJEE | 310.16 | 0 | 100
2991 | Alipore Division |  | Balance works under the Augmentation scheme of Zone-II at Falta block for providing balance pipe lying works, House Hold Tap connection, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000822/2024-2025 | 780/AD | 25/02/2025 | 225 | M/S PARAMESWAR CHOWDHURY | 80.38 | 0 | 75
2992 | Alipore Division |  | Relaying of distribution pipeline (damaged portion by open cut method) & road restoration near NP 92 & NP 77 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000833/2022-2023 | 213/DHSD | 02/08/2022 | 45 | B. MOOKHERJEE | 3.61 | 0 | 0
2993 | Alipore Division |  | Relaying of distribution pipeline (damaged portion due to widening of road) in between NP 2 to NP 377 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000834/2022-2023 | 214/DHSD | 02/08/2022 | 45 | PEECON | 3.26 | 0 | 0
2994 | Alipore Division |  | Laying of parallel distribution pipeline along opposite flank of Falta main road at Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/001652/2021-2022 | 454/DHSD | 15/03/2022 | 15 | B. MOOKHERJEE | 4.8 | 0 | 100
2995 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 7494/AD | 26/11/2022 | 0 | Resource Division | 2.69 | 0 | 0
2996 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3626/AD | 30/10/2023 | 0 | Resource Division | 6.16 | 0 | 0
2997 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000846/2023-2024 | 784/AD | 03/02/2024 | 0 | Resource Division | 2.03 | 0 | 0
2998 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001421/2023-2024 | 4601/AD | 14/12/2023 | 472 | MAA BHABANI CONSTRUCTION (DUM DUM) | 47.31 | 0 | 70
2999 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000832/2023-2024 | 677/AD | 30/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
3000 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Master Para (Part) & Mali Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000403/2020-2021 | 774/KSD | 14/10/2020 | 45 | M/S. SIKHA ENTERPRISE | 4.77 | 4.68 | 0
3001 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Mahendraganj (Part) & Ghol Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000404/2020-2021 | 775/KSD | 14/10/2020 | 45 | M/S. BABA KAPIL MUNI ENTERPRISE | 4.74 | 4.69 | 0
3002 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhaspara (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000405/2020-2021 | 776/KSD | 14/10/2020 | 45 | AVIJIT MAITY | 2.97 | 2.53 | 0
3003 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Panchayet Bazar Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000417/2020-2021 | 794/KSD | 15/10/2020 | 45 | M/S BHUNIA ENTERPRISE | 4.06 | 0 | 99
3004 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Das Para, Muntan Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000433/2020-2021 | 819/KSD | 16/10/2020 | 45 | SUMAN INDUSTRIES PVT. LTD. | 4.35 | 0 | 90
3005 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 257 (Part), 253 to 264, 264 to 265, 265 to 267, 211 to 223, 221 to 222, 41 to 42 (Part) & 42 to 43 (Part) of Dhaspara W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000436/2020-2021 | 822/KSD | 16/10/2020 | 45 | G.M. ENTERPRISE | 4.78 | 0 | 100
3006 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Purba Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000466/2020-2021 | 1044/KSD | 19/12/2020 | 20 | M/S. JOYGURU ENTERPRISE | 3.52 | 3.45 | 0
3007 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Paschim Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000536/2020-2021 | 793/KSD | 15/10/2020 | 45 | SAB ENGINEERING WORKS | 3.83 | 0 | 0
3008 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000703/2023-2024 | 473/AD | 24/01/2024 | 0 | Resource Division | 12.79 | 0 | 0
3009 | Alipore Division | Kakdwip Sub-Division | Laying of rising main & distribution main and retrofitting of FHTC under JJM for Shibpur Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000199/2022-2023 | 2685/AD | 30/06/2022 | 30 | BIMALENDU GIRI | 19.72 | 0 | 100
3010 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur and adjoining areas of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000215/2020-2021 | 650/KSD | 19/08/2020 | 15 | ANANTA KUMAR GIRI | 4.68 | 4.67 | 0
3011 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Shibpur Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000420/2020-2021 | 797/KSD | 15/10/2020 | 45 | SUMAN INDUSTRIES PVT. LTD. | 4.09 | 0 | 100
3012 | Alipore Division | Kakdwip Sub-Division | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur, Dk Paschim Shibpur and Uttar Purba Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000458/2020-2021 | 846/KSD | 16/10/2020 | 45 | GROWING CONCERN | 4.37 | 4.37 | 0
3013 | Alipore Division | Kakdwip Sub-Division | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Freserganj Dk Shibpur, Shibpur Uttar Majherpara and Uttar Paschim Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000459/2020-2021 | 848/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.56 | 4.56 | 0
3014 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000477/2020-2021 | 1055/KSD | 19/12/2020 | 25 | ANANTA KUMAR GIRI | 4.45 | 4.37 | 0
3015 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000482/2020-2021 | 1060/KSD | 19/12/2020 | 25 | ASHIS ENTERPRISE | 4.72 | 0 | 96
3016 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000488/2020-2021 | 1065/KSD | 19/12/2020 | 25 | GROWING CONCERN | 4.31 | 4.09 | 0
3017 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC to all households for Augmentation of Sibpur (Zone-I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000987/2023-2024 | 3006/AD | 26/09/2023 | 30 | PALCON | 11.99 | 0 | 100
3018 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000797/2023-2024 | 642/AD | 30/01/2024 | 0 | Resource Division | 8.54 | 0 | 0
3019 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000428/2024-2025 | 3258/AD | 06/08/2024 | 360 | M. MUKHERJEE | 150.27 | 0 | 0
3020 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Mahishamari Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000470/2021-2022 | 2418/AD | 15/09/2021 | 45 | M. MUKHERJEE | 14.85 | 0 | 100
3021 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Mahishmari Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001243/2020-2021 | 2274/AD | 12/10/2020 | 365 | M. MUKHERJEE | 106.14 | 6.97 | 95
3022 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000712/2023-2024 | 482/AD | 24/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
3023 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Ananda Abad Water Supply Scheme (Habitation- Ananda Abad), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) |  |  | ORD/000079/2022-2023 | 275/CSD | 19/05/2022 | 40 | M/S. MANABESH ROY | 4.81 | 0 | 100
3024 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Ananda Abad Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year |  |  | ORD/001379/2020-2021 | 5370/AD | 19/02/2021 | 365 | M/S. MANABESH ROY | 61.07 | 17.46 | 100
3025 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Singheswar Water Supply Scheme Block - Canning - II, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001381/2020-2021 | 5371/AD | 19/02/2021 | 365 | M/S. SARADA UDYOG | 68.19 | 42.99 | 96
3026 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (410 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Singheswar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002312/2023-2024 | 1065/AD | 21/02/2024 | 282 | RAKTIM ENTERPRISE | 35.55 | 0 | 93
3027 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Uttar Angadberia Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000084/2020-2021 | 5307/AD | 18/02/2021 | 365 | M/S ROY TRADING CO. | 107.85 | 20.48 | 84
3028 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Makhaltala Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000088/2020-2021 | 5310/AD | 18/02/2021 | 365 | M/S. SUMAN ENTERPRISE | 121.24 | 0 | 100
3029 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghoradal Uttar (Dakshinpara) and Fhatki Paschimpara under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000039/2022-2023 | 08/RSD | 04/04/2022 | 60 | M/S R.K.ENTERPRISE | 4.77 | 0 | 100
3030 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-B) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000270/2021-2022 | 380/RSD | 13/08/2021 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.57 | 100
3031 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Dakshin (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000291/2020-2021 | 376/RSD | 15/10/2020 | 30 | L.N. ENTERPRISE | 4.76 | 4.76 | 0
3032 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Uttar (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000292/2020-2021 | 377/RSD | 15/10/2020 | 30 | L.N. ENTERPRISE | 4.76 | 4.76 | 0
3033 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works for piped water supply at Zone - XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/07751 and SM/15466) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000532/2024-2025 | 3638/AD | 09/09/2024 | 90 | SUJATA CONSTRUCTION | 26.06 | 0 | 0
3034 | Alipore Division | Raidighi Sub-Division | Extension of Pipeline in connection with Functional Household Tap Connection (FHTC) from SI of schools to Dhopapara (node no. 167-172-176) at Ghoradal mouza under Ghoradal Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001156/2021-2022 | 570/RSD | 15/12/2021 | 60 | M/S R.K.ENTERPRISE | 4.68 | 0 | 100
3035 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Ghoradal at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001183/2021-2022 | 536/RSD | 30/11/2021 | 60 | M/S. JHARNA ENTERPRISE | 4.76 | 0 | 100
3036 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza- Istaranpur at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001184/2021-2022 | 537/RSD | 30/11/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
3037 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-A) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001214/2020-2021 | 561/RSD | 30/12/2020 | 60 | L.N. ENTERPRISE | 4.82 | 4.55 | 0
3038 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Ghoradal (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001228/2020-2021 | 563/RSD | 30/12/2020 | 60 | L.N. ENTERPRISE | 4.82 | 4.54 | 0
3039 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Dakshin (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001231/2020-2021 | 565/RSD | 30/12/2020 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.55 | 0
3040 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Uttar (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001235/2020-2021 | 567/RSD | 30/12/2020 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.54 | 0
3041 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001485/2021-2022 | 710/RSD | 02/03/2022 | 60 | L.N. ENTERPRISE | 4.22 | 0 | 100
3042 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001545/2021-2022 | 710/RSD | 02/03/2022 | 60 | L.N. ENTERPRISE | 4.22 | 0 | 100
3043 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000633/2023-2024 | 237/AD | 15/01/2024 | 0 | Resource Division | 11.25 | 0 | 0
3044 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works and Construction of 01 no. Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000626/2022-2023 | 5979/AD | 20/10/2022 | 90 | M/S. JAYDEEP DASGUPTA | 129.4 | 0 | 100
3045 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001731/2020-2021 | 1213/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 0 | 94
3046 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bark Para & Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001742/2020-2021 | 1215/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.71 | 0 | 94
3047 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001758/2020-2021 | 1217/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 3.66 | 98
3048 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sumanta Para & Kaylapara (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001761/2020-2021 | 1220/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.82 | 3.76 | 99
3049 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001763/2020-2021 | 1222/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.1 | 0 | 94
3050 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para (Part) & Purb Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001790/2020-2021 | 1235/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 0 | 94
3051 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - A) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001813/2020-2021 | 1252/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.62 | 94
3052 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - B) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001837/2020-2021 | 1268/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.65 | 97
3053 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001840/2020-2021 | 1271/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.93 | 3.84 | 94
3054 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001842/2020-2021 | 1273/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 0 | 94
3055 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001845/2020-2021 | 1276/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 0 | 99
3056 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001848/2020-2021 | 1279/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.11 | 0 | 94
3057 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001856/2020-2021 | 1287/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 0 | 94
3058 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sk. More for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001894/2020-2021 | 1316/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 0 | 94
3059 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purb Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001908/2020-2021 | 1323/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 0 | 94
3060 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - C) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001915/2020-2021 | 1325/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.66 | 94
3061 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001918/2020-2021 | 1328/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 0 | 94
3062 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001923/2020-2021 | 1334/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 3.65 | 0 | 94
3063 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000715/2023-2024 | 485/AD | 24/01/2024 | 0 | Resource Division | 8.73 | 0 | 0
3064 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Uttar Lakshminarayanpur Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001310/2020-2021 | 2221/AD | 08/10/2020 | 1825 | M/S B.M. CONSTRUCTION | 106 | 0 | 90
3065 | Alipore Division | Raidighi Sub-Division | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP- 148-149-150, ext from 150,144-147,152-153-154, ext from 154-156,ext of 15-16, ext from 144-147,136-138,3-4-6,113-114-115,154-156-157, ext 36-37,ext from34-35,34-36,34-32-33,ext from 35) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001546/2021-2022 | 712/RSD | 02/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4.7 | 0 | 100
3066 | Alipore Division | Raidighi Sub-Division | Additional work (horizontal boring, village road crossing etc.) in connection with Functional Household Tap Connection (FHTCs) at Uttar Laxminarayanpur water supply scheme (Zone-IX of Mathurapur - I Block) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001548/2021-2022 | 714/RSD | 02/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4 | 0 | 100
3067 | Alipore Division | Raidighi Sub-Division | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP-44-45, 43-40, 35-36, ext from 57, 63-65, 64-63, 60-61, 45-53, ext from 50-52, 46-47, 45-53, 60-61, 52-53, etc) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001769/2021-2022 | 627/RSD | 29/12/2021 | 15 | M/S B.M. CONSTRUCTION | 4.28 | 0 | 100
3068 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000642/2023-2024 | 246/AD | 15/01/2024 | 0 | Resource Division | 12.88 | 0 | 0
3069 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 186 to 190 and 192 to 196 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000109/2020-2021 | 1413/SWD-I | 14/12/2020 | 120 | FUTURE | 92.9 | 75.55 | 100
3070 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system by extension of pipeline for Buita W/S Scheme for Booth No- 186 to 190, Booth no- 192 and adjoining areas under Budge Budge-I Block with allied works under South 24-Pgns, W/S Division-I, P.H.E. Dte., DistSouth 24-Pgns. | AE SWSD-I |  | ORD/000585/2021-2022 | 1470/SWD-I | 15/12/2021 | 45 | FUTURE | 2.53 | 0 | 100
3071 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the all habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme, Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000572/2021-2022 | 3673/AD | 22/11/2021 | 365 | SHEKHAR CHAKRABORTY | 53.74 | 0 | 70
3072 | Alipore Division | Kakdwip Sub-Division | Supply and delivery of 6/10 mm NB Gun-metal Ferrule for Providing Functional Household Tap Connection (FHTC) to the households of Nebutala W/S Scheme under JJM Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001751/2021-2022 | 238/KSD/Camp/G.S.Mela 22 | 31/01/2022 | 7 | SHEKHAR CHAKRABORTY | 4.09 | 0 | 100
3073 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000013/2022-2023 | 1168/AD | 27/05/2022 | 0 | Resource Division | 5.97 | 0 | 0
3074 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000823/2023-2024 | 668/AD | 30/01/2024 | 0 | Resource Division | 3.01 | 0 | 0
3075 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000710/2023-2024 | 480/AD | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
3076 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part - F) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000495/2024-2025 | 3571/AD | 04/09/2024 | 90 | GROWING CONCERN | 100.89 | 0 | 100
3077 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000330/2023-2024 | 3145/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3078 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000380/2023-2024 | 3566/AD | 18/10/2023 | 0 | Resource Division | 18.23 | 0 | 0
3079 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000696/2023-2024 | 466/AD | 24/01/2024 | 0 | Resource Division | 7.9 | 0 | 0
3080 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000015/2021-2022 | 5621/AD | 25/01/2022 | 0 | Resource Division | 5.39 | 0 | 0
3081 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000681/2023-2024 | 451/AD | 24/01/2024 | 0 | Resource Division | 3.25 | 0 | 0
3082 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000012/2021-2022 | 3020/AD | 02/11/2021 | 365 | JAYANTA KUMAR DEY | 80.16 | 0 | 40
3083 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000068/2025-2026 | 2257/AD | 14/05/2025 | 45 | SAHANA ENTERPRISE | 15.98 | 0 | 0
3084 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E.Dte. (SM/09014 & SM/17225) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000762/2024-2025 | 4458/AD | 07/11/2024 | 60 | SAHANA ENTERPRISE | 97.21 | 0 | 98
3085 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Netra W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001383/2022-2023 | 1066/CSD | 15/12/2022 | 40 | A.P. CONSTRUCTION | 0.96 | 0 | 95
3086 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000822/2023-2024 | 667/AD | 30/01/2024 | 0 | Resource Division | 5.05 | 0 | 0
3087 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (one) no. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gangacheri Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000010/2021-2022 | 1343/AD | 19/07/2021 | 365 | S.S. ENTERPRISE (II) | 37.06 | 0 | 95
3088 | Alipore Division | Canning Sub-division | Relaying of damage pipeline due to uncovered FHTC work at Amlamethi Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000527/2022-2023 | 5513/AD | 29/09/2022 | 30 | BIMALENDU GIRI | 59.66 | 0 | 0
3089 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Amlamethi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000642/2021-2022 | 3696/AD | 22/11/2021 | 365 | GROWING CONCERN | 205.06 | 0 | 80
3090 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000071/2022-2023 | 5146/AD | 21/09/2022 | 0 | Resource Division | 30.75 | 0 | 0
3091 | Alipore Division | Canning Sub-division | LAUNCH HIRE CHARGES FOR OCT'22 TO DEC'22 UNDER CANNING SUB-DIVISION, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | BILL/00680/2024-2025 | BP-2024-25-224 | 20/06/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
3092 | Alipore Division | Canning Sub-division | HIRE bill for month of JULY-SEP23 | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | BILL/03541/2023-2024 | BP-2023-24-1272 | 27/03/2024 | 0 | RAJKUMAR MANNA | 8.08 | 0 | 0
3093 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV of Bayarsing Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000198/2022-2023 | 2643/AD | 29/06/2022 | 30 | SUDIP PRADHAN | 35.96 | 0 | 0
3094 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000206/2021-2022 | 1423/AD | 27/07/2021 | 1619 | M/S. SAMADDAR CONSTRUCTION | 152.62 | 0 | 83
3095 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Retrofitting of Narayantala W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000816/2022-2023 | 6811/AD | 16/11/2022 | 892 | HARIDAS DUTTA | 19.49 | 0 | 100
3096 | Alipore Division | Canning Sub-division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 23.12.2022 to 30.06.2023 | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001753/2022-2023 | 460/HQ-II/AD | 22/12/2022 | 182 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
3097 | Alipore Division | Canning Sub-division | Survey, Design and DPR preparation for Augmentation of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001844/2021-2022 | 687/CSD | 19/08/2021 | 15 | HORIZEN | 4.12 | 0 | 100
3098 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000390/2023-2024 | 331/AD | 19/01/2024 | 0 | Resource Division | 6.13 | 0 | 0
3099 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing for Retrofitting of Phulmalancha W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000819/2022-2023 | 6814/AD | 16/11/2022 | 30 | BANGA NIRMAN | 7.18 | 0 | 0
3100 | Alipore Division | Canning Sub-division | Construction of OHR (550 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Phul Malancha,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001088/2023-2024 | 3605/AD | 30/10/2023 | 300 | JIT CONSTRUCTION | 629.62 | 0 | 60
3101 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001845/2021-2022 | 691/CSD | 19/08/2021 | 15 | HORIZEN | 3.15 | 0 | 100
3102 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001846/2021-2022 | 692/CSD | 19/08/2021 | 15 | HORIZEN | 3.26 | 0 | 100
3103 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000047/2022-2023 | 600/AD | 28/04/2022 | 1320 | M/S. S.S. ENTERPRISE | 537.16 | 0 | 73
3104 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalikatala (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub- Division of Alipore Division, P.H.E.Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000322/2023-2024 | 1548/AD | 17/07/2023 | 863 | M/S. S.S. ENTERPRISE | 177.08 | 0 | 30
3105 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Kalikatala (Zone - I & II) of Canning-II Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone-II) (SM/10051) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000695/2024-2025 | 4307/AD | 29/10/2024 | 270 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 159.68 | 0 | 0
3106 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001541/2021-2022 | 6708/AD | 16/03/2022 | 120 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.37 | 0 | 86
3107 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001663/2021-2022 | 620/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
3108 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001665/2021-2022 | 621/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.2 | 0 | 100
3109 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001666/2021-2022 | 622/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 1.57 | 0 | 100
3110 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001667/2021-2022 | 632/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.92 | 0 | 100
3111 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001668/2021-2022 | 633/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 0 | 100
3112 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001669/2021-2022 | 634/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 100
3113 | Alipore Division | Canning Sub-division | Additional pipeline for FHTC work of Kalikatala W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001972/2022-2023 | 12591/AD | 13/03/2023 | 45 | M/S. S.S. ENTERPRISE | 90.52 | 0 | 100
3114 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000064/2022-2023 | 3952/AD | 12/08/2022 | 0 | Resource Division | 180.31 | 0 | 0
3115 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000084/2022-2023 | 5547/AD | 29/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
3116 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VIII including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based Water Supply Scheme for Falta-Mathurapur" District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/000009/2022-2023 | 139/AD | 07/04/2022 | 1080 | TANMAY ROY CHOWDHURY | 277.27 | 0 | 90
3117 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 0 | 100
3118 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 0 | 100
3119 | Alipore Division |  | Additional balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe laying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) |  |  | ORD/000389/2025-2026 | 3374/AD | 16/07/2025 | 45 | THE TOWER CONSTRUCTION | 40.87 | 0 | 0
3120 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) in Baidyakhali, Abad Simulgaunge, Pakurtala, Ahamedpur Mouza of Falta Zone-VI under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas Block Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000529/2022-2023 | 5514/AD | 29/09/2022 | 30 | TIYASHA ENTERPRISE | 31.57 | 0 | 50
3121 | Alipore Division |  | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Asta, Chaka,Guthari,Mahadebpur & Padmapur villages due to Swajal Gram activities under Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. |  |  | ORD/000579/2022-2023 | 5855/AD | 18/10/2022 | 15 | BALAJEE ENTERPRISE. | 7.2 | 0 | 100
3122 | Alipore Division |  | Laying of distribution pipeline (leftout portion) over Kantakhali Lock gate and restoration of village concrete road damaged during FHTC work at Zone-VI of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000664/2022-2023 | 6169/AD | 01/11/2022 | 10 | BALAJEE ENTERPRISE. | 3.98 | 0 | 100
3123 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 4346/AD | 04/03/2022 | 0 | Resource Division | 38.31 | 0 | 0
3124 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3616/AD | 30/10/2023 | 0 | Resource Division | 14.78 | 0 | 0
3125 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01060/2023-2024 | BP-2023-24-127 | 17/07/2023 | 0 | CESC LTD | 1.98 | 0 | 0
3126 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/05979/2023-2024 | BP-2023-24-634 | 29/03/2024 | 0 | CESC LTD | 2.9 | 0 | 0
3127 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Asuti-2 of Asuti 1& 2 Gram Panchayet area under Thakupukur Maheshtala Block under South 24-Pgs Mechanical Division PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002721/2021-2022 | 915/SMD. | 09/08/2021 | 90 | A.K.SIKDAR | 6.35 | 0 | 0
3128 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no.1 of Chata Gram Panchayet area under South 24-Pgs Mechanical Division PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/003330/2021-2022 | 914/SMD. | 09/08/2021 | 90 | J.K. ENGINEERING CO. | 5.81 | 0 | 0
3129 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation & Commissioning of 30 KVA voltage stabilizer at Asuti-I&II Gram Panchayet area Block-Thakurpukur Maheshtala under South 24-Pgs Mechanical Division PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/003625/2021-2022 | 868/SMD. | 28/07/2021 | 30 | S.P. CONSTRUCTION | 3.93 | 0 | 0
3130 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Electricity Bill | AE SWSD-I,Assistant Engineer -II | Junior Engineer | VCH/003873/2022-2023 | 65/PFMS | 11/11/2022 | 0 | CESC LTD | 2.78 | 0 | 0
3131 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Ganney Gangadharpur OHR (1250 cum capacity) Head work Site under Asuti I / Asuti II W/S Scheme under South 24 Pgns W/S Div I , PHED. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000041/2022-2023 | 441/SWD-I | 24/05/2022 | 15 | MS POUSALI ENTERPRISE | 4.61 | 0 | 0
3132 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Distribution System, Road Restoration including providing FHTC for Asuti-I & II GP and adjoining areas under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, P.H.E. Dte., District-South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000065/2022-2023 | 1110/SWD-I | 23/08/2022 | 1071 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1559.44 | 0 | 80
3133 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Modification of foundation of awarded 1500 Cum. OHR at Chatta as per sustainability and best engineering practice including site development under ¿Water Supply Arrangement for Asuti I/II and Chatta GP¿ under South 24 Pgns. W/S Divn.-I, PHED. [TSM/005082] [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000074/2022-2023 | 1160/SWD-I | 29/08/2022 | 906 | M/S. S.S. ENTERPRISE | 34.1 | 0 | 90
3134 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of 63mm & 75mm dia pipeline for PWSS of Asuti-I & Asuti-II GP in Thakurpukur-Maheshtala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11160) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000115/2023-2024 | 527/SWD-I | 11/05/2023 | 814 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 122.8 | 0 | 80
3135 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 720 | WATREAT ENGINEERS | 184.41 | 0 | 50
3136 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2023 to 30/11/2023] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000290/2023-2024 | 702/SWD-I | 26/05/2023 | 183 | AVIK HALDER | 0.89 | 0 | 30
3137 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000002/2022-2023 | 560 | 27/07/2022 | 0 | Resource Division | 417.66 | 0 | 0
3138 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000018/2022-2023 | 1660 | 21/10/2022 | 0 | Resource Division | 66.08 | 0 | 0
3139 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000285/2023-2024 | 2008/SWD-I | 28/08/2023 | 0 | Resource Division | 15.6 | 0 | 0
3140 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000125/2022-2023 | 2028/AD | 21/06/2022 | 30 | M/S. GIRI ENTERPRISE | 12.18 | 0 | 20
3141 | Alipore Division | Kakdwip Sub-Division | Road restoration, Y junction and other allied laying works for providing Functional Household Tap Connection (FHTC) for Kachuberia W/S, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000135/2024-2025 | 2472/AD | 14/06/2024 | 30 | SOMBHUNATH BHATTACHARJEE | 6.12 | 0 | 100
3142 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 400] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000406/2022-2023 | 4660/AD | 07/09/2022 | 90 | SOMBHUNATH BHATTACHARJEE | 111.8 | 0 | 100
3143 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KACHUBERIA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000478/2022-2023 | 297/AD | 12/04/2022 | 45 | VOYAGER | 9.73 | 0 | 0
3144 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for augmentation of Kachuberia W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000539/2023-2024 | 357/KSD | 09/08/2023 | 20 | S.K.GOLUI | 1.77 | 0 | 100
3145 | Alipore Division | Kakdwip Sub-Division | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001484/2022-2023 | 10710/AD | 02/02/2023 | 790 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 992.52 | 0 | 65
3146 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002055/2022-2023 | 735/KSD | 16/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3147 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3148 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002184/2022-2023 | 692/KSD | 23/02/2023 | 365 | SUDIP PRADHAN | 2.39 | 0 | 100
3149 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000057/2022-2023 | 3906/AD | 12/08/2022 | 0 | Resource Division | 117.89 | 0 | 0
3150 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000282/2023-2024 | 3057/AD | 28/09/2023 | 0 | Resource Division | 20.5 | 0 | 0
3151 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000320/2023-2024 | 3135/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3152 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000537/2023-2024 | 21/AD | 02/01/2024 | 0 | Resource Division | 15.6 | 0 | 0
3153 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000898/2023-2024 | 884/AD | 07/02/2024 | 0 | Resource Division | 11.9 | 0 | 0
3154 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply and installation of auto cum manual control panel, pumping machinery, voltage stabilizer, automatic chlorinator and related accessories at PH-2, Zone-I of Kachuberia w/s scheme under SMD, PHE Dte.[Block:Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000075/2022-2023 | 907/SMD | 05/09/2022 | 90 | T.S. CONSTRUCTION | 10.48 | 0 | 90
3155 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/03670/2023-2024 | BP-2023-24-392 | 23/11/2023 | 0 | WBSEDCL | 16.78 | 0 | 0
3156 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Deuli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000467/2022-2023 | 278/SMD | 01/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.76 | 0 | 50
3157 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Improvement of external illumination arrangement with other allied works at P.H. No. - 1 under Deuli Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/11498) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000595/2024-2025 | 1036-AE-II-SMD | 13/08/2024 | 15 | KUNAL ENTERPRISE | 0.78 | 0 | 0
3158 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DEULIPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000032/2022-2023 | 916/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 0 | 100
3159 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DEULI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11498) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000094/2023-2024 | 451/SWD-I | 04/05/2023 | 60 | M/S ASHA ENGINEERING | 6.05 | 0 | 100
3160 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
3161 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Deuli PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11498) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000265/2024-2025 | 2680/SWD-I | 07/06/2024 | 45 | SWATHI ENTERPRISE | 76 | 0 | 15
3162 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "DEULI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000404/2022-2023 | 459/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 0 | 100
3163 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DEULI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 822] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000427/2022-2023 | 2565/SWD-I | 10/01/2023 | 60 | TANMOY ROY CHOWDHURY | 123.95 | 0 | 80
3164 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DEULI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011201] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000596/2022-2023 | 3116/SWD-I | 24/02/2023 | 754 | CIVIL CONSULTANT | 15.88 | 0 | 100
3165 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed DEULI Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011201] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000810/2022-2023 | 3702/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.9 | 0 | 100
3166 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000103/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.53 | 0 | 0
3167 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000295/2022-2023 | 5706/AD | 13/10/2022 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 0
3168 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000319/2022-2023 | 5704/AD. | 13/10/2022 | 45 | MOUMITA ENTERPRISE | 56.41 | 0 | 0
3169 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamber, fitting fixing supplying different dia specials etc. for Augmentation of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-D) (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000333/2024-2025 | 2741/AD | 26/06/2024 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 181.12 | 0 | 0
3170 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NAGANDRAGANJ (ZONE - I & II)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000481/2022-2023 | 4190/AD | 22/08/2022 | 45 | VOYAGER | 8.65 | 0 | 100
3171 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 02 nos. Pump House, Functional Household Tap Connection (FHTC) to all households for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000540/2022-2023 | 5705/AD.. | 13/10/2022 | 852 | M/S. DAS BUILDERS | 50.5 | 0 | 70
3172 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Nagendraganj W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000592/2023-2024 | 2349/AD | 18/08/2023 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 52.27 | 0 | 0
3173 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000782/2022-2023 | 6536/AD | 11/11/2022 | 990 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 546.08 | 0 | 20
3174 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nagendraganj (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000971/2023-2024 | 320/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3175 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Nagendraganj W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001003/2023-2024 | 508/KSD | 03/10/2023 | 20 | S.K.GOLUI | 3.54 | 0 | 0
3176 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2024-2025 | 1982/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 3.14 | 0 | 0
3177 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Zone-I of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002143/2024-2025 | 1983/KSD | 23/12/2024 | 20 | M/S. SONAMONI ENTERPRISE | 2.03 | 0 | 90
3178 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Haradhanpur Zone - I & II, Nagendraganj Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002156/2023-2024 | 949/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3179 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Nagendraganj (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002420/2023-2024 | 1347/AD | 06/03/2024 | 45 | M/S KHAJABABA ENTERPRISE | 32.97 | 0 | 90
3180 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Nagendraganj (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002421/2023-2024 | 1348/AD | 06/03/2024 | 389 | RAJLAKSHMI ENTERPRISE | 10.93 | 0 | 100
3181 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000505/2023-2024 | 4828/AD | 20/12/2023 | 0 | Resource Division | 25.17 | 0 | 0
3182 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000718/2023-2024 | 488/AD | 24/01/2024 | 0 | Resource Division | 11.95 | 0 | 0
3183 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000966/2023-2024 | 1759/AD | 27/03/2024 | 0 | Resource Division | 31.52 | 0 | 0
3184 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/01984/2023-2024 | BP-2023-24-243 | 11/09/2023 | 0 | WBSEDCL | 12.83 | 0 | 0
3185 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02641/2023-2024 | BP-2023-24-277 | 03/10/2023 | 0 | WBSEDCL | 2.43 | 0 | 0
3186 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Nagendraganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000347/2022-2023 | 3751/SMD | 29/12/2022 | 90 | AMIT DAS | 22.4 | 0 | 5
3187 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 Zone-I & II for Augmentation of Nagendraganj W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001899/2023-2024 | 1184/SMD | 22/03/2024 | 21 | AMIT DAS | 8.79 | 0 | 100
3188 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00130/2024-2025 | BP-2024-25-42 | 24/04/2024 | 0 | WBSEDCL | 9.43 | 0 | 0
3189 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chitrasali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 440/SMD | 17/02/2023 | 957 | K.S.P ENTERPRISE | 13 | 0 | 80
3190 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHITRASALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 1229/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 20.07 | 0 | 100
3191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Chitrasali ( Chitrasali, J.L-112) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC - 520] [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000113/2022-2023 | 1243/SWD-I | 08/09/2022 | 1080 | KAMALA ENTERPRISE | 65.91 | 0 | 80
3192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHITRASALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000228/2021-2022 | 1957/SWD-I | 27/01/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 2.62 | 0 | 100
3193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHITRASALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000292/2022-2023 | 1786/SWD-I | 07/11/2022 | 840 | SANJAY ENTERPRISE | 5.8 | 0 | 100
3194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chitrasali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 3675/SWD-I | 29/03/2023 | 15 | DIPALI CONSTRUCTION | 2.2 | 0 | 0
3195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHITRASALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000791/2023-2024 | 1131/SWD-I | 06/03/2024 | 345 | BORING HOUSE | 19.97 | 0 | 100
3196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chitrasali PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000792/2023-2024 | 1132/SWD-I | 06/03/2024 | 345 | BORING HOUSE | 2.19 | 0 | 100
3197 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000276/2023-2024 | 2424/SWD-I | 30/09/2023 | 0 | Resource Division | 6.08 | 0 | 0
3198 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000332/2023-2024 | 267/SWD-I | 10/01/2024 | 0 | Resource Division | 3.2 | 0 | 0
3199 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01108/2023-2024 | BP-2023-24-153 | 24/07/2023 | 0 | WBSEDCL | 4.52 | 0 | 0
3200 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bara Gachhia W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002342/2023-2024 | 263/SMSD | 23/02/2024 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 0
3201 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1892] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 524/SWD-I | 11/05/2023 | 967 | M/S R.K. ENTERPRISE | 500.51 | 0 | 50
3202 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000182/2023-2024 | 774/SWD-I | 31/05/2023 | 183 | INDRADEV JHA | 0.87 | 0 | 30
3203 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/06/2024 to 30/11/2024) [Vehicle No- WB-04F-8738] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 2451/SWD-I | 24/05/2024 | 183 | INDRADEV JHA | 0.87 | 0 | 50
3204 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BARAGACHHIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1772/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
3205 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway,Drain, Development of Land & others allied works at HW Site of "BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12211) [2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 3705/SWD-I | 23/08/2024 | 45 | M/S R.K. ENTERPRISE (BARASAT) | 48.08 | 0 | 0
3206 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pump house, Chlorine room, Office room, Construction of Pathway at existing OHR site of Baragachhia Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pargnas District under Jal Jeevan Mission. (SM/12211) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000701/2024-2025 | 4503/SWD-I | 30/10/2024 | 45 | ISHIYA ENTERPRISE | 20.73 | 0 | 0
3207 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/12/2023 to 31/05/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000705/2023-2024 | 3001/SWD-I | 29/11/2023 | 183 | INDRADEV JHA | 0.87 | 0 | 10
3208 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BARAGACHHIA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12211] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000764/2022-2023 | 3603/SWD-I | 24/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
3209 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 19.21 | 0 | 0
3210 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000250/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 11.65 | 0 | 0
3211 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01670/2024-2025 | BP-2024-25-777 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
3212 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no-2 of Harimul water supply scheme (Baruipur Block) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01680/2024-2025 | BP-2024-25-398 | 27/09/2024 | 0 | WBSEDCL | 4.93 | 0 | 0
3213 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04709/2023-2024 | BP-2023-24-520 | 17/02/2024 | 0 | WBSEDCL | 5.39 | 0 | 0
3214 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 707/SMSD | 15/05/2025 | 15 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0
3215 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 504/SMSD | 04/04/2025 | 15 | JAGANNATH ENTERPRISE | 0.88 | 0 | 0
3216 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Harimul W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12635) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000184/2025-2026 | 503/SMSD | 04/04/2025 | 15 | JAGANNATH ENTERPRISE | 0.58 | 0 | 0
3217 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Harimul water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000449/2022-2023 | 3929/SMD | 30/12/2022 | 90 | JAGANNATH ENTERPRISE | 22.34 | 0 | 0
3218 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at HARIMUL Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC= 1433) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 110/SWD-I | 11/04/2023 | 300 | CE INFRASTRUCTURE | 433.03 | 0 | 70
3219 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for HARIMUL PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011095] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2022-2023 | 1584/SWD-I | 17/10/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 0 | 100
3220 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of HARIMUL Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000218/2021-2022 | 1935/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
3221 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at Harimul at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000352/2022-2023 | 2200/SWD-I | 13/12/2022 | 900 | BANGA NIRMAN | 11.51 | 0 | 50
3222 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12635) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000409/2024-2025 | 3706/SWD-I | 23/08/2024 | 45 | C.E. INFRASTRUCTURE | 43.76 | 0 | 0
3223 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for HARIMUL PWSS of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/011095] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000449/2023-2024 | 2104/SWD-I | 30/08/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 0
3224 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for HARIMUL Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12635] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001156/2024-2025 | 374/SWD-I | 04/02/2025 | 30 | G.S. CONSTRUCTION | 15.9 | 0 | 0
3225 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000301/2023-2024 | 2439/SWD-I | 30/09/2023 | 0 | Resource Division | 62.89 | 0 | 0
3226 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI at Radha Ballavpur mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5849] | AE BSD |  | ORD/000633/2022-2023 | 3266/SWD-I | 02/03/2023 | 7320 | SUPRITI ENTERPRISE | 444.62 | 0 | 37
3227 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000083/2022-2023 | 2999/SWD-I | 20/02/2023 | 0 | Resource Division | 36.03 | 0 | 0
3228 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the HAZRABAND having village with maximum 123 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001123/2022-2023 | 8767/AD | 21/12/2022 | 60 | MAMONI ENTERPRISE | 33.66 | 0 | 0
3229 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Hazraband water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Diamond Harbour-I] | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/000545/2022-2023 | 408/SMD | 16/02/2023 | 90 | M/S. GLOBAL POWER CONCERN | 9.25 | 0 | 0
3230 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), boundary fencing, MS grill type gate,, Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Par Kalugachi having village with maximum 82 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000749/2022-2023 | 6410/AD | 10/11/2022 | 60 | GANGA TUBEWELL AND HARDWARE | 34.64 | 0 | 86
3231 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00625/2023-2024 | BP-2023-24-91 | 14/06/2023 | 0 | WBSEDCL | 2.89 | 0 | 0
3232 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Parkalugachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000522/2022-2023 | 391/SMD | 15/02/2023 | 90 | KARUNAMOY ENGINEERING | 9.25 | 0 | 100
3233 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I |  | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 1090 | M/S. S.S. ENTERPRISE | 316.71 | 0 | 80
3234 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I |  | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 720 | WATREAT ENGINEERS | 184.41 | 0 | 50
3235 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata water supply scheme under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I |  | ORD/000152/2022-2023 | 1392/SWD-I | 21/09/2022 | 983 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 309.69 | 0 | 90
3236 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from proposed Tubewell to existing OHR for Zone II with interconnection and bypass arrangement of Asuti W/S Scheme within Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000260/2022-2023 | 1701/SWD-I | 01/11/2022 | 60 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 58.23 | 0 | 65
3237 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1200 m3) site inside Zone no.- II (Mouza-Goney Gangadharpur, JL No.- 25, Plot No.- 694) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000461/2021-2022 | 1222/SWD-I | 12/11/2021 | 30 | G TECH INDIA | 0.54 | 0 | 100
3238 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of 63mm & 75 mm dia balance pipeline for piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/010374) | AE SWSD-I |  | ORD/000661/2022-2023 | 3377/SWD-I | 10/03/2023 | 60 | M/S. S.S. ENTERPRISE | 36.25 | 0 | 95
3239 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road Restoration damaged due to laying of pipeline at CHATTA Gp and adjoining areas under command area of piped water supply scheme including FHTC for CHATTA GP in Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11488) | AE SWSD-I |  | ORD/000768/2024-2025 | 4689/SWD-I | 18/11/2024 | 286 | M/S. S.S. ENTERPRISE (NODAKHALI) | 33.8 | 0 | 80
3240 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall with allied works for Balance Pump House Sites under Chatta Water Supply Scheme of Thakurpukur Mahestala Block, under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11488) | AE SWSD-I |  | ORD/000774/2023-2024 | 801/SWD-I | 16/02/2024 | 60 | RIDIP ENTERPRISE | 26.52 | 0 | 0
3241 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Rameswarpur Pump House 2nd Site with construction of approach road to facilitate the boring of Tubewell under Pipe Water Supply of Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/11488) | AE SWSD-I |  | ORD/000775/2023-2024 | 803/SWD-I | 16/02/2024 | 7 | MS POUSALI ENTERPRISE | 6.86 | 0 | 100
3242 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing pipe supporting and other allied works at Chatta Kalikapur and Rameswarpur under Chatta W/S Scheme of South 24 Pgns W/S Division-I, PHE Dte. (SM/11488) | AE SWSD-I |  | ORD/000777/2023-2024 | 805/SWD-I | 16/02/2024 | 350 | M/S. S.S. ENTERPRISE (NODAKHALI) | 27.24 | 0 | 50
3243 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance interconnection Laying of Rising Main from proposed Tubewell to existing OHR for zone I with interconnection and bypass arrangement for Piped Water Supply Scheme including FHTC for Chatta GP in Thakurpukur-Maheshtala Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/11488) | AE SWSD-I |  | ORD/000780/2023-2024 | 808/SWD-I | 16/02/2024 | 561 | M/S. S.S. ENTERPRISE (NODAKHALI) | 11.24 | 0 | 50
3244 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000023/2022-2023 | 1984/SWD-I | 25/11/2022 | 0 | Resource Division | 45.95 | 0 | 0
3245 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00278/2023-2024 | BP-2023-24-48 | 18/05/2023 | 0 | WBSEDCL | 3.7 | 0 | 0
3246 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00380/2023-2024 | BP-2023-24-62 | 09/06/2023 | 0 | WBSEDCL | 5.03 | 0 | 0
3247 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Satberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000464/2022-2023 | 275/SMD | 01/02/2023 | 90 | DAS ENTERPRISE | 23.38 | 0 | 100
3248 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-1&2 of Satberia under South 24-Pgs Mechanical Division PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000866/2023-2024 | .1013/SMSD | 03/08/2023 | 15 | COOLING CARE CENTER | 0.78 | 0 | 100
3249 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of Outdoor illumination arrangement with allied works at Satberia PH-2 water supply scheme under Bhangar-I Block under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002570/2023-2024 | 1099/SMSD | 21/08/2023 | 15 | DAS ENTERPRISE | 0.88 | 0 | 100
3250 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of Outdoor illumination arrangement with allied works at Satberia PH-1 water supply scheme under Bhangar-I Block under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002571/2023-2024 | 1100/SMSD | 21/08/2023 | 15 | DAS ENTERPRISE | 0.88 | 0 | 100
3251 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Payment of Enhanced GST Rate vide W/O No.1690/SWD-I dt. 01/11/2022 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02031/2023-2024 | BP-2023-24-755 | 13/03/2024 | 0 | MRA NIRMAN UDYOG | 27.18 | 0 | 0
3252 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR SATBERIA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 437, KHATIAN NO. 3227/1, JL. NO. 110, MOUZA - SATBERIA) & 2ND TUBE WELL SITE (DAG NO. 578, KHATIAN NO. 3744, JL NO. 115, MOUZA - KASHINATHPUR), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 1444/SWD-I | 26/09/2022 | 30 | SIMPLEX DRILLING COMPANY | 28.4 | 0 | 100
3253 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Satberia Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000228/2022-2023 | 1690/SWD-I | 01/11/2022 | 300 | MRA NIRMAN UDYOG | 613.53 | 0 | 80
3254 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway at 2nd site of Satberia PWSS within Bhangar-I Block in connetion with" SATBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/11274). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 2597/SWD-I | 16/10/2023 | 757 | MAA CONSTRUCTION | 4.82 | 0 | 100
3255 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing 905 nos. Functional Household Tap connection (FHTC) For Satberia PWSS Under Block:Bhangar-I, District: South 24 parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission[No. of FHTC (1721-816)=905] (SM/11274) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000625/2023-2024 | 2806/SWD-I | 09/11/2023 | 60 | A S BUILDCON | 33.11 | 0 | 100
3256 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of SATBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11274) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000724/2024-2025 | 4601/SWD-I | 12/11/2024 | 60 | MRA NIRMAN UDYOG | 94.4 | 0 | 0
3257 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000021/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 5.03 | 0 | 0
3258 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000032/2022-2023 | 2691/SWD-I | 20/01/2023 | 0 | Resource Division | 11.72 | 0 | 0
3259 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) | AE SWSD-II | JE2 | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 300 | CONCORD ENGINEERING | 1862.26 | 0 | 55
3260 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE2 | RTOR000136/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 56.86 | 0 | 0
3261 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill of security deposit for New service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01482/2022-2023 | BP-2022-23-448 | 17/03/2023 | 0 | WBSEDCL | 4.06 | 0 | 0
3262 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Dadpur Dighirpar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000275/2022-2023 | 3919/SMD | 30/12/2022 | 90 | BISALAXMI ENTERPRISE | 13.04 | 0 | 100
3263 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DADPUR DIGHIRPAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000095/2022-2023 | 1207/SWD-I | 02/09/2022 | 30 | MAMON ENTERPRISE AND CONSTRUCTION | 20.06 | 0 | 100
3264 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at DADPUR DIGHIRPAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012523] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000123/2022-2023 | 1291/SWD-I | 14/09/2022 | 60 | SANJAY ENTERPRISE | 5.47 | 0 | 100
3265 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DADPUR DIGHIRPAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000161/2021-2022 | 1915/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
3266 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DADPUR DIGHIRPAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 911) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000203/2022-2023 | 1559/SWD-I | 13/10/2022 | 90 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 178.64 | 0 | 60
3267 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12053) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000337/2024-2025 | 3311/SWD-I | 23/07/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 62.15 | 0 | 0
3268 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000103/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.7 | 0 | 0
3269 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-XI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2329) (TSM/015099 & TSM/010837) | AE HQ-I |  | ORD/000387/2023-2024 | 1840/SWD-I | 17/08/2023 | 775 | M/S. B.M. CONSTRUCTION | 327.12 | 0 | 80
3270 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000056/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 14.35 | 0 | 0
3271 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Erenda water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 300/SMD | 06/02/2023 | 90 | B.T.PROJECTS PVT.LTD. | 23 | 0 | 40
3272 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/06/2025 to 30/11/2025] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 1367/SWD-I | 22/05/2025 | 183 | GOPAL KUMAR JHA | 0.87 | 0 | 18
3273 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for ERENDA piped water supply scheme at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tubewell site (Dag No. 391, Khatian No. 1321 , JL No. 132, Mouza- Noapara), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000167/2022-2023 | 1441/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.52 | 0 | 0
3274 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 3188] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000428/2023-2024 | 2002/SWD-I | 28/08/2023 | 90 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 347.5 | 0 | 25
3275 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12043) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000676/2024-2025 | 4465/SWD-I | 29/10/2024 | 305 | SUJIT KUMAR SHARMA | 10.53 | 0 | 100
3276 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ERENDA PWSS at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tube-well site (Dag No. 391 Khatian No. 1321, JL No. 132, Mouza- Noapara) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12043] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 3568/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 0
3277 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ERENDA PWSS of Bhangar-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010678] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 562/SWD-I | 31/01/2024 | 15 | TRAYEE DECORATOR | 15.88 | 0 | 100
3278 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for ERENDA Piped Water Supply Scheme in BHANGAR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12043] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000786/2023-2024 | 1069/SWD-I | 04/03/2024 | 30 | ASHIM SHIL | 15.8 | 0 | 100
3279 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/12/2024 to 31/05/2025] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001111/2024-2025 | 4847/SWD-I | 28/11/2024 | 182 | GOPAL KUMAR JHA | 0.86 | 0 | 30
3280 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000053/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 14.98 | 0 | 0
3281 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000246/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 19.64 | 0 | 0
3282 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00512/2023-2024 | BP-2023-24-67 | 13/06/2023 | 0 | WBSEDCL | 9.93 | 0 | 0
3283 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/04076/2023-2024 | BP-2023-24-429 | 19/12/2023 | 0 | WBSEDCL | 1.57 | 0 | 0
3284 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-2 of of Beniabow W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/13774) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 677/SMSD | 04/06/2024 | 15 | DIPALI CONSTRUCTION | 0.29 | 0 | 100
3285 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Beniabow water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000792/2022-2023 | 248/SMD | 27/01/2023 | 567 | DEPALI CONSTRUCTION | 22.37 | 0 | 15
3286 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, Installation and Commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Beniabow W/S Scheme under SMD, PHE Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002295/2022-2023 | .248/SMD | 27/01/2023 | 567 | DIPALI CONSTRUCTION | 22.37 | 0 | 80
3287 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Beniabow W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002707/2023-2024 | 1305/SMSD | 03/10/2023 | 15 | DIPALI CONSTRUCTION | 0.9 | 0 | 100
3288 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development & Road Restoration of "BENIABOW PWSS to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13774 | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000242/2024-2025 | 2662/SWD-I | 07/06/2024 | 315 | SOMNATH ENTERPRISE | 10.52 | 0 | 100
3289 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE BENIABOW PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANASWATER SUPPLY DIV-1, PHE.DTE. (TSM/016028) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 2422/SWD-I. | 27/12/2022 | 30 | SAHI MASUM | 29.69 | 0 | 100
3290 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BENIABOW Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1079] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 2865/SWD-I | 09/02/2023 | 918 | M/S S. C. CIVIL ENTERPRISES | 263.16 | 0 | 30
3291 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BENIABOW PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13774] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000717/2022-2023 | 3554/SWD-I | 21/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 100
3292 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development & Road Restoration of BENIABOW Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13774] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000829/2023-2024 | 1110/SWD-I | 05/03/2024 | 60 | M/S S.C. CIVIL ENTERPRISES | 46.11 | 0 | 0
3293 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000009/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 24.99 | 0 | 0
3294 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000229/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.65 | 0 | 0
3295 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Battali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000125/2023-2024 | 571/AD | 15/05/2023 | 870 | ARFIN CONSTRUCTION | 11.53 | 0 | 80
3296 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Battali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000214/2023-2024 | 954/AD | 06/06/2023 | 65 | SALMAN CONSTRUCTION | 43.94 | 0 | 100
3297 | Alipore Division | Canning Sub-division | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the BATTALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC= 1300] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000544/2023-2024 | 2210/AD | 10/08/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 358.79 | 0 | 34
3298 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000739/2024-2025 | 4396/AD | 05/11/2024 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 33.7 | 0 | 0
3299 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000740/2024-2025 | 4397/AD | 05/11/2024 | 30 | SUBHO CONSTRUCTION | 14.36 | 0 | 0
3300 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001401/2022-2023 | 10926/AD | 06/02/2023 | 634 | ARBINA ENTERPRISE | 8.88 | 0 | 100
3301 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001402/2022-2023 | 10927/AD | 06/02/2023 | 45 | ARBINA ENTERPRISE | 8.57 | 0 | 0
3302 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Battali New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001881/2022-2023 | 7523/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.32 | 0 | 99
3303 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000048/2023-2024 | 255/AD | 24/04/2023 | 0 | Resource Division | 39.04 | 0 | 0
3304 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000409/2023-2024 | 363/AD | 19/01/2024 | 0 | Resource Division | 8.01 | 0 | 0
3305 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Batali PH-1 Water supply scheme under Gosaba block. Reference ID:-106748166, Application No :-1008091231 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01841/2024-2025 | BP-2024-25-469 | 18/11/2024 | 0 | WBSEDCL | 6.72 | 0 | 0
3306 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Battali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000548/2022-2023 | 411/SMD | 16/02/2023 | 90 | P.K. ENGINEERING | 19.27 | 0 | 0
3307 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Chareges for new service connection at Raypur pump house-2 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00217/2024-2025 | BP-2024-25-59 | 16/05/2024 | 0 | WBSEDCL | 17.31 | 0 | 0
3308 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00513/2023-2024 | BP-2023-24-68 | 13/06/2023 | 0 | WBSEDCL | 5.34 | 0 | 0
3309 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Raypur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000305/2022-2023 | 456/SMD | 17/02/2023 | 843 | NEW RANBEE ENGINEERING | 22.22 | 0 | 100
3310 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at P.H. No-1 & 2 of Raypur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002012/2024-2025 | 425/SMSD | 20/03/2025 | 21 | MASSK ENGINEERING WORKS | 0.79 | 0 | 0
3311 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAYPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24- Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1992] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 93/SWD-I | 10/04/2023 | 722 | EQUIPMENTS AND SPARES AGENCIES | 471 | 0 | 75
3312 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE RAYPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016075) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000355/2022-2023 | 2262/SWD-I | 15/12/2022 | 766 | SAHI MASUM | 29.69 | 0 | 100
3313 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAYPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13737] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 2915/SWD-I | 14/02/2023 | 704 | SAHI MASUM | 3.14 | 0 | 100
3314 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Road Restoration & Drumsheet Walling of RAYPUR PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13773] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000771/2023-2024 | 783/SWD-I | 15/02/2024 | 455 | EQUIPMENTS AND SPARES AGENCIES | 50.02 | 0 | 60
3315 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000028/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 23.26 | 0 | 0
3316 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000238/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.27 | 0 | 0
3317 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Bhairabitala having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001121/2022-2023 | 8765/AD | 21/12/2022 | 60 | A.M. ENTERPRISE | 32.19 | 0 | 0
3318 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000873/2023-2024 | 780/AD | 03/02/2024 | 0 | Resource Division | 0.66 | 0 | 0
3319 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Bhairabitala Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000600/2022-2023 | 679/SMD | 10/03/2023 | 90 | A.S.ENTERPRISE | 8.84 | 0 | 0
3320 | Alipore Division | Canning Sub-division | Extension of pipe line for covered the uncovered FHTC area at Luxbagan Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000081/2022-2023 | 1130/AD | 26/05/2022 | 30 | MAA LAXMI ENTERPRISE | 18.44 | 0 | 100
3321 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00160/2024-2025 | BP-2024-25-52 | 10/05/2024 | 0 | WBSEDCL | 9.17 | 0 | 0
3322 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00516/2023-2024 | BP-2023-24-80 | 13/06/2023 | 0 | WBSEDCL | 2.93 | 0 | 0
3323 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Natagachhi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000302/2022-2023 | 454/SMD | 17/02/2023 | 775 | A.K.ENTERPRISE | 23.39 | 0 | 100
3324 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at P.H. No-1 & 2 of Natagahchi water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001926/2024-2025 | 428/SMSD | 20/03/2025 | 21 | PS & ASSOCIATES | 0.79 | 0 | 0
3325 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of Outdoor illumination arrangement with allied works at PH-1 of Natagachi water supply scheme under SMD, PHE Dte. (Block- Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002575/2023-2024 | 1173/SMSD | 04/09/2023 | 15 | A.K.ENTERPRISE | 0.89 | 0 | 100
3326 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & delivery of stand by Automatic star delta stater at PH-1 of Natagachi W/S Scheme under SMD, PHE Dte. (Block-Sonarpur). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002973/2023-2024 | 1174/SMSD | 04/09/2023 | 15 | A.K.ENTERPRISE | 0.26 | 0 | 100
3327 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.19] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00478/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.76 | 0 | 0
3328 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Natagachhi PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015394] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000336/2022-2023 | 2073/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 0 | 100
3329 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for NATAGACHHI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1022] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000542/2022-2023 | 3030/SWD-I | 20/02/2023 | 901 | SAKTI ENTERPRISE (DEBASISH.SAKTI2015@GMAIL.COM) | 306.26 | 0 | 30
3330 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for NATAGACHI PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/015394] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 2975/SWD-I | 21/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.17 | 0 | 100
3331 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling , Land Development, Road Restoration & others allied works of NATAGACHHI PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13499] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000770/2023-2024 | 784/SWD-I | 15/02/2024 | 457 | SAKTI ENTERPRISE | 86.16 | 0 | 20
3332 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000033/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 34.35 | 0 | 0
3333 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000242/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.3 | 0 | 0
3334 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories for replacement of Tube Well at different water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-I] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000611/2022-2023 | 374/SMD | 13/02/2023 | 90 | M/S. S.S. ENTERPRISE | 22.21 | 0 | 60
3335 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Renovation of external illumination arrangement with other allied works at PH No-1 under Nandarampur Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Budge Budge-I) (SM/12884) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002100/2023-2024 | 156-AE-II-SMD | 09/02/2024 | 15 | MAA SUSOMA & COMPANY | 0.75 | 0 | 100
3336 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection for Replacement Tubewell of Buita Water Supply Scheme under "Repair And Replacement of TubeWell Zones of Different Water Supply Scheme under Budge Budge-I Under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/ 013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000243/2023-2024 | 1440/SWD-I | 18/07/2023 | 30 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 4.84 | 0 | 100
3337 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (two) nos. Replacement Rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Nandarampur W/S Scheme and Buita W/S Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000304/2022-2023 | 1884/SWD-I | 16/11/2022 | 30 | SUBHRA ENTERPRISE | 30.03 | 0 | 50
3338 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair / renovation / overhauling of Iron elimination Plant of 100 cum capacity (aprox) for Nischintapur Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/013413] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000327/2022-2023 | 2044/SWD-I | 30/11/2022 | 15 | RAMASISH ENTERPRISE | 12.92 | 0 | 50
3339 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair & Restoration of road damaged due to laying of pipeline for Buita, Jamalpur and Nandarampur Schemes under Repair and Replacement of Tubewell zones of different water supply schemes under Budge Budge-I under South 24-Parganas W/S Division-I, PHE Dte. (SM/12884) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000534/2024-2025 | 4080/SWD-I | 19/09/2024 | 30 | SRIJON ENTERPRISE | 19.32 | 0 | 100
3340 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge -I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000616/2023-2024 | 2800/SWD-I | 09/11/2023 | 45 | SRIJON ENTERPRISE | 10.94 | 0 | 100
3341 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nandarampur&Buita PWSS for repair and replacement of Tubewell zones of different W/S Scheme under Budge Budge-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/013413] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000696/2022-2023 | 3499/SWD-I | 16/03/2023 | 15 | SUBHRA ENTERPRISE | 3.14 | 0 | 0
3342 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road restoration of Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000717/2023-2024 | 360/SWD-I | 16/01/2024 | 30 | SRIJON ENTERPRISE | 7.83 | 0 | 100
3343 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repairing Rising Main from Existing Tubewell to existing OHR for BUITA Distribution Zone for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000746/2022-2023 | 3597/SWD-I | 23/03/2023 | 30 | PEECON | 3.28 | 0 | 0
3344 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Boundary Wall for proposed Pump House Site at Abhirampur for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. Sdouth 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000747/2022-2023 | 3598/SWD-I | 23/03/2023 | 60 | SANJAY MIDDEY | 6.47 | 0 | 100
3345 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from Existing Tubewell to existing OHR for JAMALPUR & MOUKHALI Distribution Zone with interconnection and bypass arrangement including interconnection of Distribution mains for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000780/2022-2023 | 3664/SWD-I | 29/03/2023 | 45 | M/S. S.S. ENTERPRISE | 19.82 | 0 | 75
3346 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road restoration due to laying of pipeline at different nodes under repair and replacement of tubewell zones of different Water Supply Schemes under Budge Budge-I under South 24-Pgns. Water Supply Division-I, PHE Dte. District South 24-Parganas. (SM/12884) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000781/2023-2024 | 809/SWD-I | 16/02/2024 | 366 | PROJECT AND MAINTENANCE | 37.97 | 0 | 70
3347 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/03756/2023-2024 | BP-2023-24-394 | 29/11/2023 | 0 | WBSEDCL | 5.86 | 0 | 0
3348 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Karimpur Kismat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000516/2022-2023 | 373/SMD | 13/02/2023 | 90 | SARKAR ELECTRICAL | 22.21 | 0 | 50
3349 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Miscellaneous renovation works regarding outdoor illumination, LED Board etc. at P.H. No. 1 under Karimpur Kismat Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/13922) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/002454/2023-2024 | 222-AE-II-SMD | 01/03/2024 | 15 | PS & ASSOCIATES | 0.75 | 0 | 100
3350 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply & Delivery of additional materials for PH No.-1 of Karimpur Kismat Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/13922] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/003014/2023-2024 | 85-AE-II-SMD | 18/01/2024 | 15 | SARKAR ELECTRICAL | 0.26 | 0 | 100
3351 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
3352 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Karimpur Kismat PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns district. (SM/13922) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000257/2024-2025 | 2674/SWD-I | 07/06/2024 | 418 | RAJLAXMI CONSTRUCTION | 49.25 | 0 | 40
3353 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of KARIMPUR KISMAT AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000419/2021-2022 | 1969/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 0 | 0
3354 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KARIMPUR KISMAT PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016562] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000600/2022-2023 | 3128/SWD-I | 24/02/2023 | 30 | MRA NIRMAN UDYOG | 15.89 | 0 | 90
3355 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KARIMPUR KISMAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 738) [TSM/016376]. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000722/2022-2023 | 3565/SWD-I | 22/03/2023 | 665 | RAJLAXMI CONSTRUCTION | 117.95 | 0 | 90
3356 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000094/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 4.82 | 0 | 0
3357 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000157/2023-2024 | 679/AD | 17/05/2023 | 30 | M/S S.DAS ENTERPRISE | 11.79 | 0 | 0
3358 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Sridharnagar (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14986) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000362/2024-2025 | 2891/AD | 09/07/2024 | 90 | TANMAY ROY CHOWDHURY | 261.1 | 0 | 30
3359 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000918/2023-2024 | 2971/AD | 26/09/2023 | 45 | ARBINA ENTERPRISE | 34.35 | 0 | 0
3360 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Sridharnagar PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001792/2022-2023 | 3958/AD | 12/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.64 | 0 | 95
3361 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sridharnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001963/2023-2024 | 397AD | 22/01/2024 | 45 | AQUATECH ENGINEERS | 49.26 | 0 | 100
3362 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002026/2022-2023 | 12993/AD | 23/03/2023 | 300 | TANMAY ROY CHOWDHURY | 296.12 | 0 | 30
3363 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002027/2022-2023 | 12994/AD | 23/03/2023 | 300 | TANMAY ROY CHOWDHURY | 290.89 | 0 | 30
3364 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sridharnagar Zone - I & II, Rakhalpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002106/2023-2024 | 928/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3365 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002604/2023-2024 | 290/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3366 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002609/2023-2024 | 304/KSD | 08/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3367 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000446/2023-2024 | 4766/AD | 19/12/2023 | 0 | Resource Division | 38.86 | 0 | 0
3368 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000564/2023-2024 | 83/AD | 03/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
3369 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000762/2023-2024 | 596/AD | 29/01/2024 | 0 | Resource Division | 6.76 | 0 | 0
3370 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000963/2023-2024 | 1697/AD | 22/03/2024 | 0 | Resource Division | 11.88 | 0 | 0
3371 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,&2 for Augmentation of Sridharnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000800/2022-2023 | 772/SMD | 16/03/2023 | 90 | S.G.TECHNICAL SERVICES | 22.15 | 0 | 0
3372 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Mallarchak Ishwaripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 3812/SMD | 29/12/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 22.36 | 0 | 0
3373 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (2 Nos.) for Augmentation of MALLARCHAK ISHWARIPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 1962) [TSM/016725] | Assistant Engineer | Junior Engineer | ORD/000065/2023-2024 | 368/SWD-I | 27/04/2023 | 705 | M/S ROY CHOWDHURY AND CO. | 290.21 | 0 | 50
3374 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOLLARCHAK ISHWARPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016725] | Assistant Engineer | Junior Engineer | ORD/000626/2022-2023 | 3240/SWD-I | 01/03/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0
3375 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Mallarchak Ishwaripur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000995/2022-2023 | 1466\SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.6 | 0 | 100
3376 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall for 2nd Tubewell, land development for OHR and allied works for Mallarchak Iswaripur piped water supply scheme to accomodate FHTC in Mograhat II Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14661) [2nd call] | Assistant Engineer | Junior Engineer | ORD/001122/2024-2025 | 156/SWD-I | 15/01/2025 | 45 | MAMONI ENTERPRISE | 94.94 | 0 | 0
3377 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000130/2022-2023 | 3389/SWD-I | 10/03/2023 | 0 | Resource Division | 12.09 | 0 | 0
3378 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000173/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 27.39 | 0 | 0
3379 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000154/2023-2024 | 676/AD | 17/05/2023 | 30 | DEY ENTERPRISE (III) | 9.62 | 0 | 100
3380 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Madhabnagar Zone-II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000204/2023-2024 | 742/AD | 23/05/2023 | 635 | REALIENCE CONSTRUCTION | 507.58 | 0 | 40
3381 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000917/2023-2024 | 2970/AD | 26/09/2023 | 45 | AALOKRENU | 27.45 | 0 | 100
3382 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001403/2022-2023 | 10333/AD | 25/01/2023 | 795 | A.K. SIKDAR | 61.73 | 0 | 75
3383 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001404/2022-2023 | 10334/AD | 25/01/2023 | 30 | A.S.A.CONSTRUCTION AND CONSULTANT | 16.68 | 0 | 0
3384 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001756/2022-2023 | 11756/AD | 21/02/2023 | 851 | DIPAK ROY | 156.91 | 0 | 70
3385 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001781/2022-2023 | 11758/AD | 21/02/2023 | 45 | S. CHAKRABORTY AND CO. | 36.7 | 0 | 90
3386 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3387 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002295/2023-2024 | 216/AD | 11/01/2024 | 30 | S. CHAKRABORTY AND CO. | 20.41 | 0 | 100
3388 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Indraprastha W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13804) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002528/2024-2025 | 813/AD | 27/02/2025 | 45 | CHANDA ENTERPRISE (KOLKATA) | 40.78 | 0 | 0
3389 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002605/2023-2024 | 291/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3390 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000088/2023-2024 | 534AD | 12/05/2023 | 0 | Resource Division | 14.88 | 0 | 0
3391 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000521/2023-2024 | 4937/AD | 22/12/2023 | 0 | Resource Division | 22.61 | 0 | 0
3392 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000581/2023-2024 | 56/AD | 03/01/2024 | 0 | Resource Division | 2.57 | 0 | 0
3393 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000946/2023-2024 | 1680/AD | 22/03/2024 | 0 | Resource Division | 28.55 | 0 | 0
3394 | S24 Pgns Mechanical | Kakdwip Sub-Division | Madhabnagar PH-2 Water supply scheme Application No- 1007193395 Reference ID- 106229290 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/02034/2024-2025 | BP-2024-25-487 | 09/12/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
3395 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Madhabnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000391/2022-2023 | 3793/SMD | 29/12/2022 | 1005 | JOYSHREE CONCERN | 26.01 | 0 | 40
3396 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-II, PH-1 of Madhabnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002868/2023-2024 | 1228/AE-I/SMD | 04/12/2023 | 15 | JOYSHREE CONCERN | 0.89 | 0 | 0
3397 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of UTTARPARANIJ water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 1045/SMD | 17/04/2023 | 90 | POWER PUMPS & PIPES CO. | 22.37 | 0 | 0
3398 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of UTTAR PARANIJ MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2168] [TSM/018529] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 1709/SWD-I | 08/08/2023 | 816 | M/S SALIM CONSTRUCTION | 478.77 | 0 | 70
3399 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Paranji Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000951/2022-2023 | 1297/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.74 | 0 | 100
3400 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000098/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 41.92 | 0 | 0
3401 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 0 | 100
3402 | Alipore Division | Diamond Harbour Sub-Division | Laying of parallel distribution pipeline along Falta main road at Falta Zone-I under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001193/2021-2022 | 5710/AD. | 31/01/2022 | 60 | M/S. S.S. ENTERPRISE | 42.99 | 0 | 90
3403 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Basulat under Zone-I of Falta Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002022/2022-2023 | 12926/AD | 21/03/2023 | 690 | M/S. S.S. ENTERPRISE | 27.99 | 0 | 80
3404 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-I of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002023/2022-2023 | 12927/AD | 21/03/2023 | 660 | THE TOWER CONSTRUCTION | 30.5 | 0 | 50
3405 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000083/2023-2024 | 405/AD | 03/05/2023 | 0 | Resource Division | 29.8 | 0 | 0
3406 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000185/2023-2024 | 1276/AD | 05/07/2023 | 0 | Resource Division | 29.8 | 0 | 0
3407 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000225/2023-2024 | 2188/AD | 10/08/2023 | 0 | Resource Division | 1.38 | 0 | 0
3408 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000361/2023-2024 | 3225/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3409 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Chandakhali to Dhapdhapi More 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01666/2024-2025 | BP-2024-25-773 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.74 | 0 | 0
3410 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00287/2023-2024 | BP-2023-24-17 | 15/05/2023 | 0 | WBSEDCL | 5.87 | 0 | 0
3411 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no-2 of Alipur water supply scheme.(Baruipur Block) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01722/2024-2025 | BP-2024-25-411 | 30/09/2024 | 0 | WBSEDCL | 7.92 | 0 | 0
3412 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04653/2023-2024 | BP-2023-24-492 | 12/02/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
3413 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Alipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13442) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 939/SMSD | 28/06/2024 | 258 | BARISAL TRADING CO. | 0.58 | 0 | 100
3414 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Alipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000476/2022-2023 | 3947/SMD | 30/12/2022 | 882 | BARISAL TRADING CO. | 21.5 | 0 | 100
3415 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at ALIPUR for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =244] [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 964/SWD-I | 08/06/2023 | 90 | RAJ KUMAR MONDAL | 122.78 | 0 | 40
3416 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at ALIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1752/SWD-I | 04/11/2022 | 8460 | B.M. TRADERS | 10.93 | 0 | 100
3417 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for ALIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000275/2022-2023 | 1838/SWD-I | 11/11/2022 | 30 | UMAR ALI KHAN | 40.12 | 0 | 0
3418 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at ALIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1186) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 2020/SWD-I | 29/11/2022 | 1080 | RAJ KUMAR MONDAL | 190.68 | 0 | 65
3419 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of ALIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000346/2021-2022 | 1908/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.76 | 0 | 100
3420 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, road restoration, protection work for pipeline and other allied works for Ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte, South 24 Parganas district. (SM/13442) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000509/2024-2025 | 3964/SWD-I | 10/09/2024 | 484 | SANDHYA ENTERPRISE | 58.48 | 0 | 60
3421 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Alipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3665/SWD-I | 29/03/2023 | 15 | UMAR ALI KHAN | 4.4 | 0 | 0
3422 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000111/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 14.32 | 0 | 0
3423 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -II | Junior Engineer | BILL/04616/2023-2024 | BP-2023-24-477 | 02/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
3424 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Daulatpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | Assistant Engineer -II | Junior Engineer | ORD/000510/2022-2023 | 349/SMD | 09/02/2023 | 90 | AHALYA ENGINEERING WORKS | 22.87 | 0 | 40
3425 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Miscellaneous works in the interest of maintaining proper operational condition at P.H. No. - 1 under Doulatpur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/13780) | Assistant Engineer -II | Junior Engineer | ORD/000536/2024-2025 | 1037/AE-II-SMD | 13/08/2024 | 15 | SOMNATH ENTERPRISE | 0.78 | 0 | 100
3426 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of boundary wall & other allied works at Head Work Site of DAULATPUR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/016355] | Assistant Engineer -II | Junior Engineer | ORD/000042/2023-2024 | 183/SWD-I | 18/04/2023 | 60 | NIRMAL UDYOG | 18.78 | 0 | 100
3427 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Layiing of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, land development, approach road, protection of pipeline and road restoration for DOULATPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/13780) | Assistant Engineer -II | Junior Engineer | ORD/000290/2024-2025 | 3106/SWD-I | 09/07/2024 | 476 | PROJECT AND MAINTENANCE | 188.62 | 0 | 35
3428 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of DAULATOUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer -II | Junior Engineer | ORD/000420/2021-2022 | 1968/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 0
3429 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | Assistant Engineer -II | Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
3430 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DAULATPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016355] | Assistant Engineer -II | Junior Engineer | ORD/000578/2022-2023 | 3093/SWD-I | 23/02/2023 | 30 | MD RUHUL AMIN GOLDER | 15.89 | 0 | 100
3431 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DAULATPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13780] | Assistant Engineer -II | Junior Engineer | ORD/000689/2024-2025 | 4484/SWD-I | 30/10/2024 | 30 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0
3432 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of DAULATPUR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4918) [TSM/016355]. | Assistant Engineer -II | Junior Engineer | ORD/000763/2022-2023 | 3638/SWD-I | 27/03/2023 | 919 | PROJECT AND MAINTENANCE | 300.71 | 0 | 80
3433 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer -II | Junior Engineer | RTOR000090/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 39.25 | 0 | 0
3434 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Uttar Mohanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000406/2022-2023 | 3804/SMD | 29/12/2022 | 90 | KAMAKHYA ENTERPRISE | 22.35 | 0 | 0
3435 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of UTTAR MOHANPUR MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1742] [TSM/015329] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000051/2023-2024 | 270/SWD-I | 24/04/2023 | 738 | TUMPA ASSOCIATES | 438.46 | 0 | 30
3436 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Approach road, Development of Land at OHR site for UTTAR MOHANPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/13781) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000394/2024-2025 | 3642/SWD-I | 20/08/2024 | 60 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 17.76 | 0 | 40
3437 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR MOHANPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13781] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000623/2022-2023 | 3239/SWD-I | 01/03/2023 | 933 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 50
3438 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "UTTAR MOHANPUR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000883/2022-2023 | 411/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 0 | 0
3439 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000167/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 24.89 | 0 | 0
3440 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/04656/2023-2024 | BP-2023-24-491 | 12/02/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
3441 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Raghunathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000336/2022-2023 | 3740/SMD | 29/12/2022 | 90 | T.S. CONSTRUCTION | 22.36 | 0 | 35
3442 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Raghunathpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002407/2023-2024 | 278/SMSD | 29/02/2024 | 15 | T.S. CONSTRUCTION | 0.9 | 0 | 0
3443 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2025 to 30.11.2025) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000063/2025-2026 | 1372/SWD-I | 22/05/2025 | 183 | MINTU SOMADDAR | 0.87 | 0 | 100
3444 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 787/SWD-I | 04/05/2023 | 183 | DIPAK NASKAR | 0.87 | 0 | 0
3445 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2023 to 30.11.2023) [SM/13785] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 779/SWD-I | 31/05/2023 | 183 | MINTU SOMADDAR | 0.87 | 0 | 20
3446 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2024 to 30.11.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000218/2024-2025 | 2482/SWD-I | 28/05/2024 | 183 | MINTU SOMADDAR | 0.87 | 0 | 18
3447 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR RAGHUNATHPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016318) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000348/2022-2023 | 2168/SWD_I | 09/12/2022 | 30 | PADMA ENGINEERING CO. | 30.07 | 0 | 50
3448 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2039] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 2012/SWD-I | 28/08/2023 | 703 | MILAN GHOSH | 472.62 | 0 | 20
3449 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.12.2023 to 31.05.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000702/2023-2024 | 3000/SWD-I | 29/11/2023 | 183 | MINTU SOMADDAR | 0.87 | 0 | 20
3450 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Cholorine room, Office Room, Construction of Pathway at OHR Site of "RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13785) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000703/2024-2025 | 4505/SWD-I | 30/10/2024 | 60 | M/S UNIQUE ENTERPRISE | 20.87 | 0 | 0
3451 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13785) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000753/2024-2025 | 4675/SWD-I | 18/11/2024 | 45 | MILAN GHOSH | 10.04 | 0 | 0
3452 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAGHUNATHPUR PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13785] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 3643/SWD-I | 28/03/2023 | 15 | PADMA ENGINEERING CO. | 3.14 | 0 | 50
3453 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000876/2022-2023 | 3729/SWD-I | 31/03/2023 | 183 | DIPAK NASKAR | 0.87 | 0 | 0
3454 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.12.2024 to 31.05.2025) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001068/2024-2025 | 4888/SWD-I | 29/11/2024 | 182 | MINTU SOMADDAR | 0.86 | 0 | 15
3455 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000026/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 57.09 | 0 | 0
3456 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000254/2023-2024 | 1006/SWD-1 | 09/06/2023 | 0 | Resource Division | 12.56 | 0 | 0
3457 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000984/2022-2023 | 3669/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.43 | 0 | 100
3458 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002036/2023-2024 | 518/AD | 25/01/2024 | 45 | KALPANA TRADERS | 33.32 | 0 | 100
3459 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002037/2023-2024 | 519/AD | 25/01/2024 | 332 | B.P.R. CONSTRUCTION | 11.6 | 0 | 100
3460 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Purba Sripatinagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002067/2023-2024 | 763(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3461 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3462 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Sripatinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002392/2023-2024 | 1231/AD | 29/02/2024 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
3463 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000097/2023-2024 | 543/AD | 12/05/2023 | 0 | Resource Division | 8.12 | 0 | 0
3464 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000302/2023-2024 | 3097/AD | 28/09/2023 | 0 | Resource Division | 27.56 | 0 | 0
3465 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000677/2023-2024 | 443/AD | 24/01/2024 | 0 | Resource Division | 0.57 | 0 | 0
3466 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Purba Sripatinagar W/S Scheme PH-1 Application No:- 1007193430 Reference ID:- 106229304 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00964/2024-2025 | BP-2024-25-189 | 23/07/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
3467 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Purba Sripatinagar W/S Scheme PH-2 Application No:- 1007193436 Reference ID:- 106229306 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00965/2024-2025 | BP-2024-25-190 | 23/07/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
3468 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Purba Sripatinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000366/2022-2023 | 3770/SMD | 29/12/2022 | 853 | M/S. PS & ASSOCIATES | 19.27 | 0 | 90
3469 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & fixing of main swtch & Bus bar with allied works at PH-1 & 2 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002451/2024-2025 | 1248/A-AE-II-SMD | 30/09/2024 | 15 | PS & ASSOCIATES | 0 | 0 | 0
3470 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & fixing of main swtch & Bus bar with allied works at PH-1 & 2 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002486/2024-2025 | 1248/A/AE-II/SMD | 30/09/2024 | 15 | PS & ASSOCIATES | 0.69 | 0 | 0
3471 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Amtali (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000099/2023-2024 | 468/AD | 08/05/2023 | 15 | KUNDU CONSTRUCTION CO. | 17.56 | 0 | 70
3472 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Piped W/S Scheme for Amtali (Zone-I) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 799] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000168/2023-2024 | 936/AD | 31/05/2023 | 900 | MAA LAXMI ENTERPRISE | 285.43 | 0 | 70
3473 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Piped W/S Scheme for Amtali (Zone-II) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1198] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000260/2023-2024 | 1448/AD | 13/07/2023 | 600 | ADARSH ENTERPRISES | 335.67 | 0 | 80
3474 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Amtali W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001114/2022-2023 | 12059/AD | 27/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.98 | 0 | 0
3475 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Amtali W/S Scheme (Zone - II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001115/2022-2023 | 12060/AD | 27/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.98 | 0 | 0
3476 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Amtali (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001240/2024-2025 | 5221/AD | 16/12/2024 | 45 | ADARSH ENTERPRISES | 36.01 | 0 | 0
3477 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Amtali (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001242/2024-2025 | 5223/AD | 16/12/2024 | 45 | MAA SANTOSHI ENTERPRISE | 31.9 | 0 | 0
3478 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Amtali (Zone-II) W/S Scheme, Block - Gosaba, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001244/2024-2025 | 5242/AD | 17/12/2024 | 240 | NOVELTY CONSTRUCTION | 46.47 | 0 | 45
3479 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Amtali W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001399/2022-2023 | 10924/AD | 06/02/2023 | 45 | A 8 T CONSTRUCTION | 8.59 | 0 | 0
3480 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Amtali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001400/2022-2023 | 10925/AD | 06/02/2023 | 45 | A 8 T CONSTRUCTION | 8.59 | 0 | 0
3481 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Amtali (Zone-I & II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001891/2022-2023 | 12290/AD | 03/01/2023 | 45 | M/S R.DUTTA & CO. | 7.33 | 0 | 100
3482 | Alipore Division | Canning Sub-division | Relaying of HDPE pipe from H/O Dr. Amulya Mondal to Samshanghat at Amtali W/S Scheme (Zone-E), Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002158/2020-2021 | 1590/CSD | 23/02/2021 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 4.17 | 0 | 90
3483 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Amtali W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002546/2023-2024 | 1601/CSD | 28/02/2024 | 30 | DIPA ENTERPRISE | 1.84 | 0 | 100
3484 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000054/2023-2024 | 261/AD | 24/04/2023 | 0 | Resource Division | 110.06 | 0 | 0
3485 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I&II for Augmentation of Amtali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000547/2022-2023 | 410/SMD | 16/02/2023 | 90 | PADMA ENGINEERING CO. | 19.99 | 0 | 0
3486 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Paschim Surendranagar Zone-I W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000166/2024-2025 | 2517/AD | 15/06/2024 | 30 | MUNNA AGROTECH ENTERPRISE | 20.39 | 0 | 100
3487 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- I & II) [No. of FHTC = 160] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000348/2023-2024 | 1658/AD | 20/07/2023 | 300 | BHUWALKA DEVELOPMENTS PVT LTD. | 541.96 | 0 | 50
3488 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Paschim Surendranagar Zone I Part I & II W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000440/2024-2025 | 3075/AD | 25/07/2024 | 60 | CHHETRI ENTERPRISES | 74.62 | 0 | 0
3489 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Paschim Surendranagar Zone-I W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000522/2023-2024 | 350/KSD | 09/08/2023 | 558 | S.K.GOLUI | 2.73 | 0 | 100
3490 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000927/2023-2024 | 273(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3491 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001203/2023-2024 | 4080/AD | 23/11/2023 | 45 | REZU CONSTRUCTION | 27.88 | 0 | 60
3492 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001204/2023-2024 | 4081/AD | 23/11/2023 | 495 | B.B. CONSTRUCTION | 9.38 | 0 | 100
3493 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001205/2023-2024 | 4082/AD | 23/11/2023 | 45 | BANGA NIRMAN | 27.91 | 0 | 0
3494 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001206/2023-2024 | 4083/AD | 23/11/2023 | 30 | M/S A.K. ENTERPRISE | 9.7 | 0 | 50
3495 | Alipore Division | Kakdwip Sub-Division | Sinking of 04 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Paschim Surendranagar (Zone-I) (Part-I, II & III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001275/2022-2023 | 9587/AD | 03/01/2023 | 90 | MUNNA AGROTECH ENTERPRISE | 77.16 | 0 | 100
3496 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Paschim Surendranagar (Zone-I) [Part-I, II & III] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001791/2022-2023 | 3186/AD | 15/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 9.15 | 0 | 95
3497 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- III) [No. of FHTC = 286] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002028/2022-2023 | 12995/AD | 23/03/2023 | 858 | DEEPAK ENTERPRISE | 248.99 | 0 | 40
3498 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 1st Tubewell site for Paschim Surendranagar Zone-I (Part-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002096/2024-2025 | 1929/KSD | 20/12/2024 | 25 | AJMIR ENTERPRISE | 4.08 | 0 | 0
3499 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3500 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone - I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002603/2023-2024 | 273/KSD | 02/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3501 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002608/2023-2024 | 294/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3502 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000456/2023-2024 | 4763/AD | 19/12/2023 | 0 | Resource Division | 84.68 | 0 | 0
3503 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000567/2023-2024 | 80/AD | 03/01/2024 | 0 | Resource Division | 2.65 | 0 | 0
3504 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000760/2023-2024 | 595/AD | 29/01/2024 | 0 | Resource Division | 3.71 | 0 | 0
3505 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000960/2023-2024 | 1694/AD | 22/03/2024 | 0 | Resource Division | 3.69 | 0 | 0
3506 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Paschim Surendranagar PH-1 Zone-I ( Part-I) W/S Scheme Paschim Surendranagar Application No- 1007513251 Reference ID:- 106460080 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/00209/2024-2025 | BP-2024-25-70 | 16/05/2024 | 0 | WBSEDCL | 8.88 | 0 | 0
3507 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Paschim Surendranagar PH-2 Zone-I ( Part-I) W/S Scheme Application No- 1007513394 Reference ID:- 1064600085 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/00210/2024-2025 | BP-2024-25-70 | 16/05/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
3508 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Paschim Surendranagar Zone-I ( Part-III) W/S Scheme PH-1 Application No:- 1007513529 Reference ID:- 106460084 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/00962/2024-2025 | BP-2024-25-187 | 19/07/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
3509 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Paschim Surendranagar PH-2, Zone-I ( Part-III) W/S Scheme Application No:- 1007513563 Reference ID:- 106460079 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/00963/2024-2025 | BP-2024-25-188 | 19/07/2024 | 0 | WBSEDCL | 6.66 | 0 | 0
3510 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1,2,3 &4 Zone-I for Augmentation Paschim Surendranagar water supply scheme under SMD, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000370/2022-2023 | 3774/SMD | 29/12/2022 | 90 | COMBINE ENTERPRISES | 38.52 | 0 | 0
3511 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 Zone-I for Augmentation Paschim Surendranagar W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001929/2024-2025 | 1778/SMD | 29/05/2024 | 90 | COMBINE ENTERPRISES | 33.95 | 0 | 0
3512 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00162/2024-2025 | BP-2024-25-50 | 10/05/2024 | 0 | WBSEDCL | 13.04 | 0 | 0
3513 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Samukhpota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000338/2022-2023 | 3742/SMD | 29/12/2022 | 90 | CMS ENGINEERING CONCERN | 26.76 | 0 | 0
3514 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24- Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1764] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 109/SWD-I | 11/04/2023 | 300 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 533.56 | 0 | 25
3515 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & other allied works of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13787). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000266/2024-2025 | 2681/SWD-I | 07/06/2024 | 45 | M/S SHIBAM ENTERPRISE | 47.6 | 0 | 0
3516 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR SAMUKPOTA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016319) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000347/2022-2023 | 2167/SWD_I | 09/12/2022 | 800 | PADMA ENGINEERING CO. | 30.07 | 0 | 100
3517 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13787) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000747/2024-2025 | 4669/SWD-I | 18/11/2024 | 45 | R.G ENTERPRISE | 10.02 | 0 | 0
3518 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAMUKPOTA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13787] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000768/2022-2023 | 3642/SWD-I | 28/03/2023 | 691 | PADMA ENGINEERING CO. | 3.14 | 0 | 50
3519 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 54.07 | 0 | 0
3520 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000240/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.87 | 0 | 0
3521 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including providing of Functional Household Tap Connection (FHTC) with allied works in Zone-VIII of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 5302] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000372/2023-2024 | 1767/AD | 27/07/2023 | 720 | SPA ENTERPRISE | 1008.05 | 0 | 55
3522 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001026/2022-2023 | 308/DHSD | 23/09/2022 | 30 | GEO SOLUTION | 3.17 | 0 | 0
3523 | Alipore Division | Diamond Harbour Sub-Division | Additional balance Laying Distribution works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing balance pipe lying works, including pipe carrying structure, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002491/2024-2025 | 782/AD | 25/02/2025 | 60 | K.P. CONSTRUCTION | 83.24 | 0 | 0
3524 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
3525 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000140/2022-2023 | 17/AD | 05/04/2023 | 0 | Resource Division | 34.48 | 0 | 0
3526 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000224/2023-2024 | 2207/AD | 10/08/2023 | 0 | Resource Division | 27.63 | 0 | 0
3527 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000429/2023-2024 | 3615/AD | 30/10/2023 | 0 | Resource Division | 0.92 | 0 | 0
3528 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000615/2023-2024 | 276/AD | 15/01/2024 | 0 | Resource Division | 31.72 | 0 | 0
3529 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000738/2023-2024 | 568/AD | 27/01/2024 | 0 | Resource Division | 9.72 | 0 | 0
3530 | Alipore Division | Canning Sub-division | Restoration of Kanthalberia Chunakhali Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01325/2024-2025 | BP-2024-25-625 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 60.02 | 0 | 0
3531 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000336/2023-2024 | 1553/AD | 17/07/2023 | 90 | TIYASHA ENTERPRISE | 140.12 | 0 | 80
3532 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials for each zone of Chunakhali (Zone - I & II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000339/2023-2024 | 3739/AD | 03/11/2023 | 725 | BUILDERS | 67.39 | 0 | 40
3533 | Alipore Division | Canning Sub-division | Protection of pipe line and inter connection in-between existing rising main and TW No. - 3 at Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000995/2021-2022 | 990/CSD | 26/10/2021 | 30 | MODERN CONSTRUCTION | 3.14 | 0 | 54
3534 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Chunakhali Water Supply Scheme (Zone-II) Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001575/2021-2022 | 6956/AD | 30/03/2022 | 30 | AQUATECH ENGINEER | 17.84 | 0 | 54
3535 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Chunakhali (Zone - I & II) W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.E. Dte. (Zon-II, TW-3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001682/2023-2024 | 1359/CSD | 19/12/2023 | 45 | S.K.GOLUI | 3.89 | 0 | 100
3536 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001709/2022-2023 | 11673/AD | 20/02/2023 | 45 | A.K. ENTERPRISE | 7.07 | 0 | 0
3537 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001710/2022-2023 | 11674/AD | 20/02/2023 | 45 | A.K. ENTERPRISE | 7.07 | 0 | 0
3538 | Alipore Division | Canning Sub-division | Surging of 03 (three) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Chunakhali W/S Scheme (Zone-II) TW-1, 2 & 3 under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001746/2020-2021 | 1448/CSD | 27/01/2021 | 15 | AQUATECH ENGINEER | 2.01 | 0 | 54
3539 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. Switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chunakhali W/S Scheme, Block : Basanti under Canning Sub-Division of Alipore Division, PHE Dte.[Pump House-3] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003185/2020-2021 | 322/AD | 08/06/2020 | 0 | M/S. MIHIR KUMAR NASKAR | 5.08 | 0 | 0
3540 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000113/2022-2023 | 245/AD | 24/04/2023 | 0 | Resource Division | 159.84 | 0 | 0
3541 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000398/2023-2024 | 356/AD | 19/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
3542 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Chunakhali Zone1 & 2 water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000015/2023-2024 | 950/SMD | 04/04/2023 | 90 | BARISAL TRADING CO. | 21.4 | 0 | 0
3543 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 90 | KIRON CONSTRUCTION | 126.68 | 0 | 0
3544 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000735/2023-2024 | 2896/AD | 19/09/2023 | 15 | SUPER CONSTRUCTION | 37.51 | 0 | 0
3545 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - VI) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000782/2024-2025 | 4483/AD | 11/11/2024 | 30 | B.K. ENTERPRISE. | 19.35 | 0 | 0
3546 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001666/2022-2023 | 11478/AD | 15/02/2023 | 30 | M.R.ENTERPRISE (II) | 19.52 | 0 | 0
3547 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Budhkhali W/S Scheme under JJM, Block - Canning - I under Canning Sub-Division under Alipore Division P.H.E. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001680/2023-2024 | 1357/CSD | 19/12/2023 | 30 | S.K.GOLUI | 2.85 | 0 | 100
3548 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001704/2022-2023 | 11668/AD | 20/02/2023 | 45 | BABAMONI CONSTRUCTION | 7.09 | 0 | 0
3549 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (TW No. 2 alternative Tubewell) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002377/2023-2024 | 1201/AD | 29/02/2024 | 30 | BHATTACHARJEE & CO. | 19.52 | 0 | 100
3550 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials at Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002551/2024-2025 | 1414/CSD | 10/12/2024 | 25 | ASHIS ENTERPRISE | 0.49 | 0 | 100
3551 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000071/2023-2024 | 272/AD | 24/04/2023 | 0 | Resource Division | 88.67 | 0 | 0
3552 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Budhakhali PH-5 under Canning -I block (REF ID : 106673108) (APP ID: 1007939044) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01157/2024-2025 | BP-2024-25-233 | 08/08/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
3553 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Budhkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000025/2023-2024 | 959/SMD | 04/04/2023 | 90 | JYOTY SOLAR POWER | 11.16 | 0 | 0
3554 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000591/2023-2024 | 2357/SMD | 30/06/2023 | 90 | SRI KRISHNA NIRMAN | 22.37 | 0 | 0
3555 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for GABBARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district, under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000030/2023-2024 | 111/SWD-I | 11/04/2023 | 988 | SHAKUNTALA CONSTRUCTION | 107.41 | 0 | 65
3556 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of GABBERIA PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2259) [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000046/2023-2024 | 242/SWD-I | 20/04/2023 | 1077 | MONDAL PRECISION PVT. LTD. | 311.23 | 0 | 30
3557 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Interconnection of 2 nos. OHRs with existing 1422 mm rising main pipe for Gabberia PWSS under Bishnupur -I District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/14871) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000089/2025-2026 | 1764/SWD-I | 02/07/2025 | 30 | S. ROY AND ASSOCIATES | 8.88 | 0 | 0
3558 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Upgradation of Store including preparation of approach road at GABBERIA PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24-Pgns. W/S Division-I, PHE Dte. for augmentation surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. (SM/14871) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000095/2025-2026 | 1770/SWD-I | 02/07/2025 | 30 | SRIJON ENTERPRISE | 10.5 | 0 | 1
3559 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of approach road, protection work of pipeline, upgradation of existing boundary wall, laying rising mai nand other allied works for GABBARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/14871] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000247/2024-2025 | 2667/SWD-I | 07/06/2024 | 298 | SHAKUNTALA CONSTRUCTION | 82.98 | 0 | 45
3560 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GABBARIA PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000581/2022-2023 | 3095/SWD-I | 23/02/2023 | 30 | MD RUHUL AMIN GOLDER | 15.88 | 0 | 0
3561 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Repairing and renovation of Overhead Reservoir (220 cum. Capacity) for Gabberia P.W.S.S. under South 24-Pgs. W/S Sub-Divn- II under surface water based water supply scheme in the Arsenic affected area of South 24 Pgs. Dist. [SM/14871] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000836/2023-2024 | 1291/SWD-I | 15/03/2024 | 45 | S.P. ENTERPRISE | 6.38 | 0 | 96
3562 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Gabbaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000966/2022-2023 | 1165/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.7 | 0 | 100
3563 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000117/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 67.3 | 0 | 0
3564 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Adhia (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 955] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000029/2023-2024 | 157/AD | 18/04/2023 | 660 | M/S. MIHIR KUMAR NASKAR | 129.78 | 0 | 45
3565 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Adhia W/S Scheme (Part-B), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001764/2022-2023 | 12037/AD | 27/02/2023 | 675 | KRISHNA CONSTRUCTION | 7.06 | 0 | 100
3566 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Adhia (Part B) (Kakradaha) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001839/2022-2023 | 10938/AD | 06/03/2023 | 45 | TECH VISION | 3.88 | 0 | 0
3567 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
3568 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000726/2023-2024 | 548/AD | 25/01/2024 | 0 | Resource Division | 1.76 | 0 | 0
3569 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/03870/2023-2024 | BP-2023-24-398 | 02/12/2023 | 0 | WBSEDCL | 4.82 | 0 | 0
3570 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Adhia ( Part-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000034/2023-2024 | 984/SMD | 05/04/2023 | 90 | M.D ENTERPRISE | 19.35 | 0 | 45
3571 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Adhia Part-B PH-1, under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001928/2024-2025 | 1053/SMSD | 25/07/2024 | 15 | M.D ENTERPRISE | 0.88 | 0 | 0
3572 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed 1250 Cum OHR Site of Zone-II within Mandirbazar block, Mouza-PurbaBishnupur (JL No-23), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 145 mtr.) | AE HQ-I |  | ORD/000023/2022-2023 | 878/SWD-I | 14/07/2022 | 60 | A P POWER AND CONCRETE | 27.53 | 0 | 50
3573 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I |  | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 0 | 20
3574 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PUKURIA MOUZA in MANDIRBAZAR (ZONE-II) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000514/2021-2022 | 1984/SWD-I | 27/01/2022 | 30 | RADIANT | 4.83 | 0 | 100
3575 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fitting & fixing Doors, Windows & allied works in Mandirbazar GLR cum Pump house, Sub-Station Building, Chlorination Building, Office Building, Dormitory Building & Guard Room etc. for Augmentation of existing Laying Distribution System to extend the benefit of 100% households in Zone-II at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/014522) | AE HQ-I |  | ORD/000547/2023-2024 | 2495/SWD-I | 06/10/2023 | 60 | AVIK ENTERPRISE | 33.18 | 0 | 100
3576 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Approach Road with allied for Head Work Site Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 pgns under South-24 pgns W/S Divn-I of South 24-pgns. W/S Circle, Phe Dte. (TSM/14522) | AE HQ-I |  | ORD/000618/2023-2024 | 2802/SWD-I | 09/11/2023 | 45 | A.P POWER AND CONCRETE | 8.99 | 0 | 100
3577 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Piling work for protection of Mandirbazar Hatuganj road near Mandirbazar P.S. damaged due to construction of 1200 mm dia valve chamber for in connection with Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns. W/S Division-I, PHE Dte. (SM/ 15485) [2nd call] | AE HQ-I |  | ORD/000716/2023-2024 | 359/SWD-I | 16/01/2024 | 15 | M/S SUBHODEEP ENTERPRISE | 1.19 | 0 | 100
3578 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land and Construction of Temporary pathway at OHR Site of Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based W/S Scheme for Falta-Mathurapur, Dist- South 24-Pgns. under South 24-Parganas W/S Divn.-I, PHE Dte. (TSM/014522) | AE HQ-I |  | ORD/000744/2023-2024 | 549/SWD-I | 31/01/2024 | 30 | RIVER BENZ CONSTRUCTION | 3.01 | 0 | 100
3579 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000044/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 395.19 | 0 | 0
3580 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000212/2023-2024 | 670 | 24/05/2023 | 0 | Resource Division | 500.47 | 0 | 0
3581 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 120 | M/S. SUMAN ENTERPRISE | 236.89 | 0 | 95
3582 | Alipore Division | Raidighi Sub-Division | Laying of Rising Main (From 2nd Tube Well to Over Head Reservoir) and construction of valve chamber of piped water supply at Zone - XII of Mathurapur - I Block (Abad Bhagabanpur PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000248/2023-2024 | 185/RSD | 14/07/2023 | 30 | SUKUMAR HALDAR | 3.78 | 0 | 100
3583 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001007/2023-2024 | 298/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 4.08 | 0 | 100
3584 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Ramchandrapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001175/2023-2024 | 354/RSD | 21/11/2023 | 60 | S.S. ENTERPRISE (II) | 4.02 | 0 | 100
3585 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Satpukur, Rajarampur, Chakbhagabanpur, Nandapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001176/2023-2024 | 355/RSD | 21/11/2023 | 60 | M/S. SUMAN ENTERPRISE | 4.68 | 0 | 100
3586 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Gadberia) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001177/2023-2024 | 356/RSD | 21/11/2023 | 60 | M/S B ENTERPRISE | 4.7 | 0 | 100
3587 | Alipore Division | Raidighi Sub-Division | Repair and renovation work for 250 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001913/2023-2024 | 143/AD | 05/01/2024 | 45 | MAHALAXMI CONSTRUCTION | 16.13 | 0 | 98
3588 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001959/2022-2023 | 12713/AD | 14/03/2023 | 45 | ADITYA HAZRA | 83.94 | 0 | 65
3589 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000635/2023-2024 | 239/AD | 15/01/2024 | 0 | Resource Division | 4.07 | 0 | 0
3590 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000044/2023-2024 | 179/AD | 19/04/2023 | 60 | G.B. CONSTRUCTION & CO. | 100.29 | 0 | 25
3591 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Jatardeul Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000511/2020-2021 | 5196/AD | 12/02/2021 | 365 | G.B. CONSTRUCTION & CO. | 125.27 | 0 | 98
3592 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- VIII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001043/2024-2025 | 4960/AD | 04/12/2024 | 60 | TIYASHA ENTERPRISE | 28.21 | 0 | 0
3593 | Alipore Division | Raidighi Sub-Division | Restoration of Pipeline (N.P. 70-71, 80-81) at Purba Jatardeul mouza under Purba Jatardeul Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001770/2021-2022 | 628/RSD | 29/12/2021 | 15 | NITYANANDA MONDAL | 2 | 0 | 0
3594 | Alipore Division | Raidighi Sub-Division | Rejuvenation of distribution pipe line and other allied works to Providing Functional Household Tap Connection (FHTC) at Zone- VIII of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002274/2023-2024 | 481/RSD | 15/02/2024 | 60 | M/S KALPANA CONSTRUCTION | 2.4 | 0 | 98
3595 | Alipore Division | Raidighi Sub-Division | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Purba Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002275/2023-2024 | 482/RSD | 15/02/2024 | 121 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 98
3596 | Alipore Division | Raidighi Sub-Division | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Paschim Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002276/2023-2024 | 483/RSD | 15/02/2024 | 60 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 0
3597 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000661/2023-2024 | 265/AD | 15/01/2024 | 0 | Resource Division | 5.21 | 0 | 0
3598 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-IV for Zone-I & Head work site to PH-IV for Zone-II of Bansra (Zone-I & II) W/S Scheme,Block-Canning-I under Canning Sub-Division of Alipore Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000263/2023-2024 | 1451/AD | 13/07/2023 | 538 | M.N. ENTERPRISE | 139.79 | 0 | 95
3599 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bansra W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001705/2022-2023 | 11669/AD | 20/02/2023 | 45 | SAHANA ENTERPRISE | 7.06 | 0 | 0
3600 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bansra W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001706/2022-2023 | 11670/AD | 20/02/2023 | 45 | SAHANA ENTERPRISE | 7.05 | 0 | 0
3601 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 300mm x 200mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Bansra (Zone - I & II) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001812/2022-2023 | 12152/AD | 01/03/2023 | 45 | M.R.ENTERPRISE (II) | 49.69 | 0 | 0
3602 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2000 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Bansra (Zone - I and II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001997/2022-2023 | 12811/AD | 16/03/2023 | 933 | RAMEN GHOSH | 95.95 | 0 | 70
3603 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000077/2023-2024 | 377/AD | 02/05/2023 | 0 | Resource Division | 151.98 | 0 | 0
3604 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000724/2023-2024 | 546/AD | 25/01/2024 | 0 | Resource Division | 65.17 | 0 | 0
3605 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Bansra (Zone-1 & 2) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000030/2023-2024 | 975/SMD | 04/04/2023 | 90 | KARUNAMOY ENGINEERING | 21.49 | 0 | 0
3606 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
3607 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000110/2023-2024 | 508/AD | 11/05/2023 | 661 | SUPER CONSTRUCTION | 5.77 | 0 | 96
3608 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 0 | 35
3609 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti (Zone - III) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000258/2023-2024 | 1446/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 106.47 | 0 | 90
3610 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-III) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000396/2023-2024 | 1496/AD | 14/07/2023 | 300 | SUMAN MONDAL | 101.59 | 0 | 36
3611 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000494/2023-2024 | 1795/AD | 26/07/2023 | 45 | B.S.ENTERPRISE | 7.35 | 0 | 98
3612 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000495/2023-2024 | 1796/AD | 26/07/2023 | 45 | B.S.ENTERPRISE | 7.09 | 0 | 98
3613 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001790/2022-2023 | 12129/AD | 01/03/2023 | 45 | BHATTACHARJEE & CO. | 39.86 | 0 | 95
3614 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001894/2022-2023 | 11553/AD | 17/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 3 | 0 | 100
3615 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000023/2023-2024 | 229/AD | 24/04/2023 | 0 | Resource Division | 14.27 | 0 | 0
3616 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000152/2023-2024 | 1045/AD | 15/06/2023 | 0 | Resource Division | 5.03 | 0 | 0
3617 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04002/2023-2024 | BP-2023-24-406 | 13/12/2023 | 0 | WBSEDCL | 6.17 | 0 | 0
3618 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04676/2023-2024 | BP-2023-24-507 | 12/02/2024 | 0 | WBSEDCL | 17.69 | 0 | 0
3619 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at P.H. No- 1 & 2 of Basanti (Zone-III) water supply scheme, under South 24Pgs Mechanical Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000071/2024-2025 | 852/SMSD | 14/06/2024 | 15 | FORTUNE ENGINEERING | 0.78 | 0 | 100
3620 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001179/2024-2025 | 29/SMSD | 07/01/2025 | 15 | SRI KRISHNA NIRMAN | 0.29 | 0 | 100
3621 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-III of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001502/2022-2023 | 873/SMD | 23/03/2023 | 90 | JAI BHARAT COMMERCIAL CORPORATION | 20.82 | 0 | 100
3622 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15564) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002698/2023-2024 | 374/SMSD | 21/03/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.58 | 0 | 100
3623 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15564) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002699/2023-2024 | 375/SMSD | 21/03/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.73 | 0 | 100
3624 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Basanti (Zone-III) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti)(SM/15564) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002700/2023-2024 | 376/SMSD | 21/03/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.9 | 0 | 100
3625 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional laying & allied works from Ghatarnia to Nolgora of Secondary Grid pipeline for Nolgora of Joynagar-II Block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under South 24 Pgns W/S Division-I, PHE Dte." (SM/16183) | AE BSD |  | ORD/000074/2025-2026 | 1577/SWD-I | 11/06/2025 | 45 | ARASTA ENGINEERING & CO | 48.34 | 0 | 70
3626 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD |  | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 894 | MRA NIRMAN UDYOG | 1590.17 | 0 | 65
3627 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD |  | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 327 | MRA NIRMAN UDYOG | 434.23 | 0 | 40
3628 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000209/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 163.2 | 0 | 0
3629 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000298/2023-2024 | 2435/SWD-I | 30/09/2023 | 0 | Resource Division | 297.49 | 0 | 0
3630 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
3631 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000731/2023-2024 | 2892/AD | 19/09/2023 | 15 | SURYA ENTERPRISE | 9.53 | 0 | 97
3632 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
3633 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001869/2022-2023 | 12522/AD | 10/03/2023 | 60 | G.B. CONSTRUCTION (TW) | 59.73 | 0 | 100
3634 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001934/2022-2023 | 11806/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.33 | 0 | 99
3635 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001990/2022-2023 | 12681/AD | 14/03/2023 | 45 | GOUTAM HALDAR (I) | 7.36 | 0 | 98
3636 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001991/2022-2023 | 12682/AD | 14/03/2023 | 45 | GOUTAM HALDAR (I) | 7.11 | 0 | 99
3637 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001992/2022-2023 | 12683/AD | 14/03/2023 | 90 | NATH CONSTRUCTION | 7.08 | 0 | 98
3638 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000024/2023-2024 | 230/AD | 24/04/2023 | 0 | Resource Division | 32.96 | 0 | 0
3639 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000153/2023-2024 | 1057/AD | 15/06/2023 | 0 | Resource Division | 9.36 | 0 | 0
3640 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at pump house no-1 of Basanti (Zone-IV) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00565/2024-2025 | BP-2024-25-133 | 26/06/2024 | 0 | WBSEDCL | 10.08 | 0 | 0
3641 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04392/2023-2024 | BP-2023-24-441 | 05/01/2024 | 0 | WBSEDCL | 6.52 | 0 | 0
3642 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04393/2023-2024 | BP-2023-24-442 | 05/01/2024 | 0 | WBSEDCL | 4.05 | 0 | 0
3643 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-2 of Basanti (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001283/2024-2025 | 27/SMSD | 07/01/2025 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.29 | 0 | 100
3644 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IV of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001507/2022-2023 | 883/SMD | 24/03/2023 | 739 | M/S. DILIP MITRA | 31.71 | 0 | 100
3645 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-V at Monirtar Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000143/2022-2023 | 1337/SWD-I | 16/09/2022 | 300 | AJIT PRAMANICK | 322.51 | 0 | 45
3646 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VB (Monirtala) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000369/2021-2022 | 2339/SWD-I | 22/02/2022 | 120 | CALCON CONSTRUCTIONS | 267.4 | 0 | 40
3647 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VA (Monirtala) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000676/2022-2023 | 71/SWD-I | 13/04/2022 | 120 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 565.06 | 0 | 40
3648 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipeline protection works, restoration of roads damaged due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-V at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/16190) (2nd call) | AE BSD |  | ORD/000773/2024-2025 | 4758/SWD-I | 21/11/2024 | 405 | MAMONI ENTERPRISE | 89.72 | 0 | 30
3649 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000067/2022-2023 | 2983/SWD-I | 20/02/2023 | 0 | Resource Division | 230.38 | 0 | 0
3650 | Alipore Division | Baruipur Sub-Division | Road restoration of WB02526, L022- Dhosa to Dhosa Chandaneswar irrigation road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01780/2024-2025 | BP-2024-25-805 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 8.36 | 0 | 0
3651 | S24 Pgns Mechanical | Baruipur Sub-Division | Quotation for new service (power) connection at ph no-2 of Tilpi (zone-I) w/s scheme . Application no-1007784239 . | AE BSD,Assistant Engineer | Junior Engineer | BILL/00443/2024-2025 | BP-2024-25-112 | 14/06/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
3652 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000282/2023-2024 | 1142/SMD | 24/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 0
3653 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000602/2023-2024 | 2369/SMD | 30/06/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 45
3654 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Tilpi Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/15781) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002349/2024-2025 | 1463/SMSD | 30/10/2024 | 15 | JAL PRAVAHIKA PVT. LTD. | 0.95 | 0 | 0
3655 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land development and other allied works for "Ground Water Based Tilpi ZONE-I Piped Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15781) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000354/2024-2025 | 3454/SWD-I | 02/08/2024 | 405 | GARAI INFRA PROJECT | 83.17 | 0 | 85
3656 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 0 | 96
3657 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-I PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018024) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000704/2022-2023 | 3513/SWD-I | 17/03/2023 | 30 | MALLICK CONSTRUCTION | 15.82 | 0 | 100
3658 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "TILPI Zone-I Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000756/2022-2023 | 707/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 0 | 100
3659 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method at 2nd Tubewell site for TILPI (Zone-I) Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15781] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000807/2023-2024 | 1286/SWD-I | 15/03/2024 | 30 | M/S BASAK CONSTRUCTION | 18.9 | 0 | 0
3660 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000153/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.28 | 0 | 0
3661 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05120/2023-2024 | BP-2023-24-576 | 12/03/2024 | 0 | WBSEDCL | 7.95 | 0 | 0
3662 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Teka water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1095/SMD | 18/04/2023 | 90 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 0 | 0
3663 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Teka W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16137) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000274/2024-2025 | 1002/SMSD | 11/07/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0
3664 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Teka W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16137) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000275/2024-2025 | 1001/SMSD | 11/07/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 0
3665 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Teka W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16137) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000293/2024-2025 | 891/SMSD | 19/06/2024 | 15 | JAI BHARAT COMMERCIAL CORPORATION | 0.84 | 0 | 0
3666 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEKA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 853] [TSM/017759] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 933/SWD-I | 06/06/2023 | 90 | A.K. INDUSTRIES | 159.51 | 0 | 70
3667 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEKA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017759] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000646/2022-2023 | 3318/SWD-I | 06/03/2023 | 977 | SUMAN ENTERPRISE | 31.72 | 0 | 50
3668 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground Water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/16137) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000716/2024-2025 | 4550/SWD-I | 06/11/2024 | 45 | A.K. INDUSTRIES | 49.41 | 0 | 0
3669 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Teka Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000931/2022-2023 | 1222/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.47 | 0 | 100
3670 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000129/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 26.12 | 0 | 0
3671 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Augmentation for Providing balance FHTC in BUITA, CHINGRIPOTA, NISCHINTIPUR, RAJIBPUR & UTTAR ROYPUR GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. | AE SWSD-I |  | ORD/000564/2023-2024 | 2637/SWD-I | 20/10/2023 | 726 | STAR ENGINEERS CO-OPERATIVE SOCEITY LTD. | 80.22 | 0 | 60
3672 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000317/2023-2024 | 24/SWSD-I | 09/01/2024 | 0 | Resource Division | 15.76 | 0 | 0
3673 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Durgapur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000024/2022-2023 | 13065/AD | 24/03/2023 | 691 | AQUATECH ENGINEERS | 36.6 | 0 | 100
3674 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Ramnagarabad and Dakshin Durgapur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16759 and 16758) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000329/2024-2025 | 2732/AD | 25/06/2024 | 494 | M/S B. ENTERPRISE | 318.12 | 0 | 25
3675 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. (1 no.) and 300 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000765/2023-2024 | 2911/AD | 20/09/2023 | 300 | M/S B. ENTERPRISE | 547.29 | 0 | 25
3676 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1192] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001214/2023-2024 | 3818/AD | 07/11/2023 | 90 | M/S B. ENTERPRISE | 377.97 | 0 | 30
3677 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
3678 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Durgapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002159/2023-2024 | 804/AD | 05/02/2024 | 60 | M/S. SIKHA ENTERPRISE | 27.47 | 0 | 0
3679 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Durgapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002160/2023-2024 | 805/AD | 05/02/2024 | 30 | SANKAR HALDER | 9.55 | 0 | 0
3680 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Durgapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002623/2023-2024 | 880/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
3681 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000481/2023-2024 | 4756/AD | 19/12/2023 | 0 | Resource Division | 46.54 | 0 | 0
3682 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000560/2023-2024 | 48/AD | 03/01/2024 | 0 | Resource Division | 14.52 | 0 | 0
3683 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001272/2024-2025 | 276/SMD | 30/01/2025 | 90 | ASHUTOSH DAS & CO. | 21.42 | 0 | 0
3684 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01099/2023-2024 | BP-2023-24-144 | 24/07/2023 | 0 | WBSEDCL | 9.57 | 0 | 0
3685 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gangajoara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 1111/SMD | 20/04/2023 | 90 | JAGANNATH ENTERPRISE | 21.77 | 0 | 40
3686 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.24] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00483/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 8.08 | 0 | 0
3687 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1683) (TSM/017714) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000233/2023-2024 | 1417/SWD-I | 17/07/2023 | 899 | SAMSUL ENTERPRISE | 487.01 | 0 | 70
3688 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000243/2024-2025 | 2663/SWD-I | 07/06/2024 | 45 | NILKANTHA ENTERPRISE | 10.43 | 0 | 100
3689 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GANGAJOARA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017714] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000666/2022-2023 | 3406/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
3690 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional LDS and Road Restoration of GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000792/2024-2025 | 4843/SWD-I | 27/11/2024 | 60 | SAMSUL ENTERPRISE | 36.02 | 0 | 0
3691 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Protection Wall and Land Development at 2nd Tubewell site GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000804/2023-2024 | 1250/SWD-I | 13/03/2024 | 30 | KALAM ENTERPRISE | 3.85 | 0 | 100
3692 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall,Land Development,Pathway,Drain & others allied works of Gangajoara Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15773] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000843/2023-2024 | 1209/SWD-I | 11/03/2024 | 45 | SAMSUL ENTERPRISE | 41.07 | 0 | 0
3693 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000016/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 58.79 | 0 | 0
3694 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000252/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.37 | 0 | 0
3695 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harekrishnapur W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000238/2023-2024 | 1390/AD | 12/07/2023 | 15 | SUPER CONSTRUCTION | 23.7 | 0 | 80
3696 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000286/2023-2024 | 1539/AD | 17/07/2023 | 45 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0
3697 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000288/2023-2024 | 1540/AD | 17/07/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
3698 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000290/2023-2024 | 1541/AD | 17/07/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
3699 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Harekrishnapur, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2343] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000315/2023-2024 | 1516/AD | 15/07/2023 | 90 | M/S SHIBAM ENTERPRISE | 405.58 | 0 | 40
3700 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harekrishnapur Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002447/2023-2024 | 1513/AD | 13/03/2024 | 45 | M/S APEX ENGINEERING | 7.15 | 0 | 100
3701 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
3702 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000003/2023-2024 | 120/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
3703 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000031/2023-2024 | 235/AD | 24/04/2023 | 0 | Resource Division | 109.7 | 0 | 0
3704 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000140/2023-2024 | 852/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
3705 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3, & 4 for Augmentation of Harekrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001514/2022-2023 | 894/SMD | 27/03/2023 | 90 | S.P. CONSTRUCTION | 41.63 | 0 | 0
3706 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kumirmari (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000239/2023-2024 | 1391/AD | 12/07/2023 | 15 | SWASTIK CONSTRUCTION | 29.2 | 0 | 0
3707 | Alipore Division | Canning Sub-division | Construction of OHR (400 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KUMIRMARI (ZONE-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000309/2023-2024 | 3737/AD | 03/11/2023 | 515 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 780.29 | 0 | 64
3708 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kumirmari W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000560/2023-2024 | 1804/AD | 26/07/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 8.57 | 0 | 0
3709 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kumirmari (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000608/2023-2024 | 1830/AD | 27/07/2023 | 45 | TECH VISION | 8.1 | 0 | 98
3710 | Alipore Division | Canning Sub-division | Name of Work : Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumirmari (Zone - I) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000644/2023-2024 | 1833/AD | 27/07/2023 | 30 | M/S SEKH ENTERPRISE | 21.99 | 0 | 0
3711 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Kumirmari (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000693/2024-2025 | 4298/AD | 29/10/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 97.98 | 0 | 0
3712 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kumirmari W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001677/2023-2024 | 1349/CSD | 18/12/2023 | 30 | SHRESTHA | 2.33 | 0 | 100
3713 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000055/2023-2024 | 262/AD | 24/04/2023 | 0 | Resource Division | 45.19 | 0 | 0
3714 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000417/2023-2024 | 372/AD | 19/01/2024 | 0 | Resource Division | 18.25 | 0 | 0
3715 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Kumirmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001437/2022-2023 | 262/SMD | 30/01/2023 | 90 | CHANDIMATA ELECTRICALS | 11.54 | 0 | 0
3716 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Kumirmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002244/2023-2024 | 2291/SMD | 26/06/2023 | 90 | CHANDIMATA ELECTRICALS | 11.54 | 0 | 0
3717 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall for proposed OHR Site at Purbatetulberia Mouza, JL No.10, Khatian No. 899/1, Plot No. 916 & 918; within Kultali block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 140.0 mtr.] | AE BSD |  | ORD/000418/2021-2022 | 1798/SWD_I | 14/01/2022 | 90 | KHAN ENTERPRISE | 26.92 | 0 | 0
3718 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1500 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I PURBO TETULBERIA MOUZA Piped Water Supply Scheme of KULTALI Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 14340] [TSM/011555 & TSM/016360] | AE BSD |  | ORD/000529/2023-2024 | 2344/SWD-I | 22/09/2023 | 558 | MADAN MOHAN MONDAL | 1916.42 | 0 | 60
3719 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaparpuri & Adjoining Mouzas (Jalghata), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000336/2024-2025 | 2770/AD | 28/06/2024 | 90 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 126.53 | 0 | 0
3720 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000346/2024-2025 | 2787/AD | 01/07/2024 | 241 | AQUATECH ENGINEER | 34.45 | 0 | 100
3721 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] | Assistant Engineer, Canning sub division |  | ORD/002390/2023-2024 | 1213/AD | 29/02/2024 | 407 | J H L CONSTRUCTION | 6.9 | 0 | 100
3722 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Kaparpuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] (SM/18866) | Assistant Engineer, Canning sub division |  | ORD/000062/2025-2026 | 1438/SMD | 21/05/2025 | 135 | M/S. S.S. ENTERPRISE | 18.64 | 0 | 0
3723 | Alipore Division | Diamond Harbour Sub-Division | Construction of Boundary Wall at proposed OHR site of Moukhali Water Supply Scheme (Block: Budge Budge-I) under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000516/2022-2023 | 5537/AD | 29/09/2022 | 45 | M/S. S.S. ENTERPRISE | 16.2 | 0 | 98
3724 | Alipore Division | Diamond Harbour Sub-Division | Construction of Chlorination Room at proposed OHR Site of Moukhali W/S Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000520/2022-2023 | 5507/AD | 29/09/2022 | 45 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 5.46 | 0 | 10
3725 | Alipore Division | Diamond Harbour Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap within Moukhali W/S Scheme of Budge Budge - I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. (SM/18867) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000604/2024-2025 | 4098/AD | 03/10/2024 | 540 | M.M. ENTERPRISE | 144.41 | 0 | 10
3726 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000252/2023-2024 | 3044/AD | 28/09/2023 | 0 | Resource Division | 77.51 | 0 | 0
3727 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- VI of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC =4922 nos) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000121/2023-2024 | 592/AD | 15/05/2023 | 90 | M/S. JHARNA ENTERPRISE | 272.12 | 0 | 0
3728 | Alipore Division | Raidighi Sub-Division | Construction of 900 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap upto pedestal and laying distribution system of piped water supply at Mathurapur - II Block (Zone-VI) for " MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, SOUTH 24 PARGANAS" under Raidighi Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000601/2021-2022 | 3459/AD | 18/11/2021 | 1460 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 501.72 | 0 | 20
3729 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000243/2023-2024 | 2915/AD | 20/09/2023 | 0 | Resource Division | 336.38 | 0 | 0
3730 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000650/2023-2024 | 253/AD | 15/01/2024 | 0 | Resource Division | 9.1 | 0 | 0
3731 | Alipore Division | Raidighi Sub-Division | Construction of 700 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- VII, Mathurapur-II Block (Part-A) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000481/2023-2024 | 1994/AD | 04/08/2023 | 606 | MATRI ENTERPRISE | 1265.16 | 0 | 30
3732 | Alipore Division | Raidighi Sub-Division | Construction of 700 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- VII, Mathurapur-II Block (Part-B) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000670/2023-2024 | 1709/AD | 22/07/2023 | 600 | M/S GHOSH & CO. | 1194.19 | 0 | 30
3733 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 700 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone-VIIA, Mathurapur- II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001049/2023-2024 | 338/RSD | 30/10/2023 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3734 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000247/2023-2024 | 3104/AD | 28/09/2023 | 0 | Resource Division | 342.8 | 0 | 0
3735 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Mograhat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] |  |  | ORD/000599/2023-2024 | 2647/SMD | 11/08/2023 | 90 | B.T.PROJECTS PVT.LTD. | 34.89 | 0 | 0
3736 | South 24 Pgs W/S Division I |  | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based MAGRAHAT piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. |  |  | ORD/000313/2024-2025 | 3245/SWD-I | 19/07/2024 | 90 | CHANDAN ROY | 307.51 | 0 | 0
3737 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOGRAHAT PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018189] |  |  | ORD/000355/2023-2024 | 1741/SWD-I | 10/08/2023 | 30 | JENARUL ISLAM | 47.38 | 0 | 0
3738 | South 24 Pgs W/S Division I |  | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of MOGRAHAT ZONE-33 MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3012] [TSM/018189] |  |  | ORD/000527/2023-2024 | 2340/SWD-I | 22/09/2023 | 300 | M/S R.K. ENTERPRISE | 510.3 | 0 | 0
3739 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Magrahat Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000971/2022-2023 | 1405/SWD-I | 21/09/2022 | 30 | GEO SOLUTION | 2.64 | 0 | 100
3740 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 48.64 | 0 | 0
3741 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 902 | M/S. S.S. ENTERPRISE | 1859.15 | 0 | 52
3742 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000139/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 69.45 | 0 | 0
3743 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13570) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000344/2024-2025 | 2756/AD | 27/06/2024 | 60 | BIMALENDU GIRI | 116.4 | 0 | 0
3744 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur (Part-I) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000547/2024-2025 | 3776/AD | 18/09/2024 | 60 | MOSTAFIZUR HAQUE GAINE | 73.31 | 0 | 0
3745 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-I) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000636/2023-2024 | 2464/AD | 24/08/2023 | 60 | ISHAN CONSTRUCTION | 35.53 | 0 | 100
3746 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-III) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000637/2023-2024 | 2465/AD | 24/08/2023 | 90 | CHANCHAL ENTERPRISE & CO. | 78.12 | 0 | 40
3747 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-I) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000779/2022-2023 | 6650/AD | 14/11/2022 | 45 | M/S. DATTA ENTERPRISE | 36.67 | 0 | 100
3748 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000780/2022-2023 | 6651/AD | 14/11/2022 | 45 | MONDAL & CO. | 36.67 | 0 | 100
3749 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000944/2023-2024 | 282(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3750 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000966/2023-2024 | 289(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3751 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [SRINARAYANPUR (PART I,II & III PWSS)] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001041/2022-2023 | 32/AD | 04/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 11.81 | 0 | 100
3752 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001063/2023-2024 | 3381/AD | 11/10/2023 | 45 | M/S SUNITY ENTERPRISE | 27.67 | 0 | 100
3753 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001064/2023-2024 | 3382/AD | 11/10/2023 | 30 | M/S MODINA ENTERPRISE | 9.49 | 0 | 100
3754 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001065/2023-2024 | 3383/AD | 11/10/2023 | 659 | M/S. SONAMONI ENTERPRISE | 9.53 | 0 | 100
3755 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001213/2023-2024 | 3870/AD | 09/11/2023 | 45 | KIRAN ENTERPRISES | 27.71 | 0 | 50
3756 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001317/2022-2023 | 9882/AD | 10/01/2023 | 300 | MAHMOOD ASSOCIATES PVT LTD | 326.43 | 0 | 25
3757 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001318/2022-2023 | 9883/AD | 10/01/2023 | 300 | KAMIRUL SK AND CO. | 309.53 | 0 | 30
3758 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001746/2022-2023 | 11555/AD | 17/02/2023 | 300 | SUPRITI ENTERPRISE | 309.39 | 0 | 30
3759 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
3760 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Srinarayanpur (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002234/2023-2024 | 720/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
3761 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000316/2023-2024 | 3125/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3762 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000461/2023-2024 | 4762/AD | 19/12/2023 | 0 | Resource Division | 58.24 | 0 | 0
3763 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000572/2023-2024 | 75/AD | 03/01/2024 | 0 | Resource Division | 3.98 | 0 | 0
3764 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000742/2023-2024 | 577/AD | 29/01/2024 | 0 | Resource Division | 2.84 | 0 | 0
3765 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000959/2023-2024 | 1693/AD | 22/03/2024 | 0 | Resource Division | 29.77 | 0 | 0
3766 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/03523/2023-2024 | BP-2023-24-388 | 23/11/2023 | 0 | WBSEDCL | 5.07 | 0 | 0
3767 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/04077/2023-2024 | BP-2023-24-425 | 18/12/2023 | 0 | WBSEDCL | 8.46 | 0 | 0
3768 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3&4, Zone-I of Augmentation of Srinarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000359/2022-2023 | 3762/SMD | 29/12/2022 | 922 | S.S. ENTERPRISES | 44.01 | 0 | 45
3769 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13570) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002433/2024-2025 | 2087/AE-II/SMD | 12/03/2025 | 21 | S.S. ENTERPRISES | 0.9 | 0 | 100
3770 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-3 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002922/2023-2024 | 294-AE-I-SMD | 15/01/2024 | 15 | S.S. ENTERPRISES | 0.89 | 0 | 100
3771 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-4 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002923/2023-2024 | 293-AE-I-SMD | 15/01/2024 | 15 | S.S. ENTERPRISES | 0.89 | 0 | 100
3772 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haripur (Zone-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000531/2023-2024 | 2144/AD | 09/08/2023 | 875 | MALLICK ENTERPRISE | 286.52 | 0 | 80
3773 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 390 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JJM of Haripur (Zone-II) W/S Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000575/2023-2024 | 2261/AD | 14/08/2023 | 45 | AQUATECH ENGINEERS | 39.53 | 0 | 100
3774 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haripur (Zone - I & II)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000642/2023-2024 | 2034/AD | 05/08/2023 | 45 | M/S R.DUTTA & CO. | 7.87 | 0 | 100
3775 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC (Retrofitting) of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002125/2023-2024 | 817/AD | 05/02/2024 | 45 | ASHIS ENTERPRISE | 40.55 | 0 | 50
3776 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002127/2023-2024 | 818/AD | 05/02/2024 | 45 | JOY GURU TRADING | 43.99 | 0 | 0
3777 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
3778 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Haripur (Zone - I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/18698) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002133/2023-2024 | 821/AD | 05/02/2024 | 30 | MEGA SOLAR ENERGY | 19.93 | 0 | 100
3779 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Haripur (Zone - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002232/2023-2024 | 718/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
3780 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000490/2023-2024 | 4789/AD | 19/12/2023 | 0 | Resource Division | 29.51 | 0 | 0
3781 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000550/2023-2024 | 33/AD | 02/01/2024 | 0 | Resource Division | 2.97 | 0 | 0
3782 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000791/2023-2024 | 636/AD | 30/01/2024 | 0 | Resource Division | 4.68 | 0 | 0
3783 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer, Kakdwip Sub Division |  | BILL/03866/2023-2024 | BP-2023-24-395 | 02/12/2023 | 0 | WBSEDCL | 4 | 0 | 0
3784 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at Augmentation PH-1 Zone-I of Haripur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001901/2023-2024 | 1186/SMD | 22/03/2024 | 21 | MASSK ENGINEERING WORKS | 10.74 | 0 | 95
3785 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Haripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/003117/2023-2024 | 2643/SMD | 11/08/2023 | 871 | MASSK ENGINEERING WORKS | 19.27 | 0 | 90
3786 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Kshetra Mohanpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000398/2024-2025 | 3181/AD | 31/07/2024 | 60 | CHAKRABORTTI ENTERPRISE | 54.18 | 0 | 0
3787 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000534/2023-2024 | 2147/AD | 09/08/2023 | 895 | RELIABLE CONSTRUCTIONS | 169.85 | 0 | 20
3788 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-B) [No. of FHTC = 800] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000535/2023-2024 | 2148/AD | 09/08/2023 | 797 | RELIABLE CONSTRUCTIONS | 169.24 | 0 | 55
3789 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [No. of FHTC = 455] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000536/2023-2024 | 3738/AD | 03/11/2023 | 537 | CHAKRABORTTI ENTERPRISE | 128.72 | 0 | 50
3790 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000542/2023-2024 | 3729/AD | 03/11/2023 | 880 | CHAKRABORTTI ENTERPRISE | 168.05 | 0 | 20
3791 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000554/2023-2024 | 2236/AD | 11/08/2023 | 45 | GOLDEN GROUPS | 49.2 | 0 | 90
3792 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000555/2023-2024 | 2237/AD | 11/08/2023 | 407 | GOLDEN GROUPS | 49.2 | 0 | 100
3793 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kshetra mohanpur (Zone - I & II)PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000639/2023-2024 | 2032/AD | 05/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 8.71 | 0 | 100
3794 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
3795 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kshetra Mohanpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division |  | ORD/003207/2023-2024 | 160/KSD | 05/01/2024 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
3796 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000109/2023-2024 | 645/AD | 17/05/2023 | 0 | Resource Division | 10.74 | 0 | 0
3797 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000487/2023-2024 | 4753/AD | 19/12/2023 | 0 | Resource Division | 52.84 | 0 | 0
3798 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000766/2023-2024 | 600/AD | 29/01/2024 | 0 | Resource Division | 4.05 | 0 | 0
3799 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 ( Zone-I & II) of Kshetra Mohanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000117/2023-2024 | 1024/SMD | 12/04/2023 | 90 | NITESH MANAGEMENT | 38.11 | 0 | 0
3800 | Alipore Division | Diamond Harbour Sub-Division | Laying of pipeline as per revised laying distribution system due to shifting of OHR site under the Augmentation Scheme of Kulpi Zone-VI for providing 100% FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18554] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000446/2024-2025 | 3323/AD | 12/08/2024 | 90 | MAHMOOD ASSOCIATES PVT LTD | 150.13 | 0 | 30
3801 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VI at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-7276] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000477/2023-2024 | 2485/AD | 25/08/2023 | 676 | MAHMOOD ASSOCIATES PVT LTD | 1473.09 | 0 | 16
3802 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Gobindapur under Zone- VI of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000505/2023-2024 | 1802/AD | 26/07/2023 | 30 | S.S.TRADERS | 24.17 | 0 | 75
3803 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VI of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001018/2022-2023 | 291/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.6 | 0 | 98
3804 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at Pump House no 1 under Dhola PWSS under Zone- VI of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001371/2024-2025 | 5500/AD | 27/12/2024 | 45 | M/S SEIKH ENTERPRISE | 25.16 | 0 | 0
3805 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-VI at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18554] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001606/2024-2025 | 125/AD | 09/01/2025 | 75 | PINKI CONSTRUCTION | 132.51 | 0 | 0
3806 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VI (Gobindapur, OHR Size-1000 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002098/2022-2023 | 334/DHSD | 14/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
3807 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system by 150 mm dia. HDPE pipe from Pump House No- 1 to Beluni more of Dhola PWSS under Zone-VI of Kulpi Block within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002113/2023-2024 | 825/AD | 05/02/2024 | 364 | M/S.SREEJIT ENTERPRISE | 24.24 | 0 | 100
3808 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000005/2024-2025 | 5159/AD | 12/12/2024 | 0 | Resource Division | 61.6 | 0 | 0
3809 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000208/2023-2024 | 2018/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
3810 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000631/2023-2024 | 290/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
3811 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000861/2023-2024 | 768/AD | 03/02/2024 | 0 | Resource Division | 35.58 | 0 | 0
3812 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000936/2023-2024 | 1278/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3813 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Raghunathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/000589/2023-2024 | 2625/SMD | 08/08/2023 | 602 | MAHAMAYA ENTERPRISE | 38.9 | 0 | 0
3814 | South 24 Pgs W/S Division I |  | Construction of 350 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2835) (TSM/018465) |  |  | ORD/000394/2023-2024 | 1879/SWD-I | 18/08/2023 | 920 | SHIV CONSTRUCTION | 477.4 | 0 | 20
3815 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18569) |  |  | ORD/000563/2024-2025 | 4236/SWD-I | 30/09/2024 | 420 | SUJIT KUMAR SHARMA | 68.52 | 0 | 60
3816 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 20.72 | 0 | 0
3817 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 254/SWD-I | 10/01/2024 | 0 | Resource Division | 17.46 | 0 | 0
3818 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,& 3 for Augmentation of Ramkrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] |  |  | ORD/000597/2023-2024 | 2726/SMD | 22/08/2023 | 90 | RELIABLE CONSTRUCTION | 33.87 | 0 | 0
3819 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for RAMKRISHNAPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018530](3rd call) |  |  | ORD/000374/2023-2024 | 1772/SWD-I | 11/08/2023 | 30 | SNEHA CONSTRUCTION | 46.94 | 0 | 0
3820 | South 24 Pgs W/S Division I |  | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAMKRISHNAPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3080] [TSM/018530] |  |  | ORD/000416/2023-2024 | 1962/SWD-I | 24/08/2023 | 900 | MANASH GHOSH | 659.95 | 0 | 30
3821 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Ramkrishnapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000952/2022-2023 | 1298/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.92 | 0 | 100
3822 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 68.17 | 0 | 0
3823 | S24 Pgns Mechanical | Baruipur Sub-Division | Additional quotation for power connection at Champahat Zone-II P-1 | AE BSD,Assistant Engineer | Junior Engineer | BILL/00285/2024-2025 | BP-2024-25-76 | 22/05/2024 | 0 | WBSEDCL | 1.04 | 0 | 0
3824 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01726/2023-2024 | BP-2023-24-198 | 09/08/2023 | 0 | WBSEDCL | 7.37 | 0 | 0
3825 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Champahati (Zone-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] (SM/12873) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000050/2025-2026 | 1428/SMD | 21/05/2025 | 135 | KARUNAMOY ENGINEERING | 10.97 | 0 | 0
3826 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 (Zone-II) of Champahat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12873) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000219/2024-2025 | 926/SMSD | 28/06/2024 | 15 | NUPUR CHANDRA HALDER | 0.58 | 0 | 0
3827 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Champahati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000534/2022-2023 | 461/SMD | 17/02/2023 | 1139 | NUPUR CHANDRA HALDER | 19.65 | 0 | 70
3828 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Champahati (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002470/2023-2024 | 289/SMSD | 07/03/2024 | 15 | NUPUR CHANDRA HALDER | 0.8 | 0 | 100
3829 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI (ZONE-II) PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/010745] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000214/2022-2023 | 1586/SWD-I | 17/10/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 0 | 100
3830 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Champahati (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 2201/SWD-I | 13/12/2022 | 60 | THE DESIGN IN | 10.72 | 0 | 0
3831 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHAMPAHATI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000446/2021-2022 | 1954/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
3832 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of CHAMPAHATI (Zone-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010745] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000455/2023-2024 | 2112/SWD-I | 30/08/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
3833 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 500 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI (Zone-II) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2991) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000570/2023-2024 | 2667/SWD-I | 31/10/2023 | 518 | RKS ENGINEER & CONTRACTOR | 578.64 | 0 | 65
3834 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000087/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 18.42 | 0 | 0
3835 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000302/2023-2024 | 2440/SWD-I | 30/09/2023 | 0 | Resource Division | 48.26 | 0 | 0
3836 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00004/2023-2024 | BP-2023-24-38 | 18/05/2023 | 0 | WBSEDCL | 2.01 | 0 | 0
3837 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00281/2023-2024 |  | 04/05/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
3838 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00376/2023-2024 | BP-2023-24-38 | 18/05/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
3839 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-2 & 3 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000361/2025-2026 | 709/SMSD | 15/05/2025 | 15 | S.G.ENTERPRISE | 0.58 | 0 | 0
3840 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000362/2025-2026 | 693/SMSD | 15/05/2025 | 15 | S.G.ENTERPRISE | 0.88 | 0 | 0
3841 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Ganeshpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12061) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000363/2025-2026 | 694/SMSD | 15/05/2025 | 15 | S.G.ENTERPRISE | 0.88 | 0 | 0
3842 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, 2 and 3 of Ganeshpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000411/2023-2024 | 2505/SMD | 17/07/2023 | 746 | S.G.ENTERPRISE | 37.83 | 0 | 40
3843 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Ganeshpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000459/2022-2023 | 3936/SMD | 30/12/2022 | 90 | S.G.ENTERPRISE | 29.99 | 0 | 0
3844 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GANESHPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000094/2022-2023 | 1206/SWD-I | 02/09/2022 | 30 | JEWS CONSTRUCTION AND CO | 60.07 | 0 | 67
3845 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 03 (Three) nos. chlorination room at GANESHPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012659] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000118/2022-2023 | 1286/SWD-I | 14/09/2022 | 60 | M/S. SREEJIT ENTERPRISE | 16.38 | 0 | 33
3846 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GANESHPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000160/2021-2022 | 1921/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 3.03 | 0 | 100
3847 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at GANESHPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000223/2022-2023 | 1657/SWD-I | 21/10/2022 | 960 | PATHIK PABAN NANDI | 262.37 | 0 | 100
3848 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for Proposed Ground Water based GANESHPUR piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12061) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000731/2024-2025 | 4618/SWD-I | 13/11/2024 | 427 | PINKI CONSTRUCTION | 91.61 | 0 | 30
3849 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000266/2023-2024 | 2421/SWD-I | 30/09/2023 | 0 | Resource Division | 44.65 | 0 | 0
3850 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000335/2023-2024 | 265/SWD-I | 10/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
3851 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Shyamnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000401/2022-2023 | 3801/SMD | 29/12/2022 | 90 | KUNDU ELECTRICAL ENTERPRISE | 22.25 | 0 | 0
3852 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000324/2024-2025 | 3257/SWD-I | 19/07/2024 | 60 | JAMIRUL CONSTRUCTION | 30.56 | 0 | 0
3853 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "SHYAMNAGAR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 405/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
3854 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of SHYAMNAGAR of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1642] | Assistant Engineer | Junior Engineer | ORD/000513/2022-2023 | 2943/SWD-I | 16/02/2023 | 835 | JAMIRUL CONSTRUCTION | 339.61 | 0 | 10
3855 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 900mm Dia Double Row Hume Pipe Culvert for SHYAMNAGAR PWSS under Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000662/2024-2025 | 4392/SWD-I | 23/10/2024 | 30 | N CONSTRUCTION | 6.18 | 0 | 0
3856 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary Wall (length=175.00m) & Construction of Service Road (length=140.00m) at OHR Site (1st Tubewell Site) for SHYAMNAGAR PWSS within Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based WAter Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000681/2024-2025 | 4476/SWD-I | 30/10/2024 | 90 | R.K ENTERPRISE | 55.77 | 0 | 0
3857 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Shyam Nagar PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014761] | Assistant Engineer | Junior Engineer | ORD/000731/2022-2023 | 3583/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
3858 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000165/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 24.48 | 0 | 0
3859 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including Construction of 1 no. 250cum capcity OHR and 01 no 400 cum capacity OHR to extend the benefit 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Mangarajpur & Zone-V at Atkrishnarampur of Diamond harbour - I block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000487/2023-2024 | 4927/AD | 22/12/2023 | 831 | PRASUN ENTERPRISE | 972.76 | 0 | 10
3860 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-V of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001049/2022-2023 | 300/DHSD | 15/09/2022 | 30 | MEASURE LAND | 2.83 | 0 | 0
3861 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-V (Atkrishnarampur, OHR Size-400 ) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002089/2022-2023 | 323/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
3862 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000130/2022-2023 | 30/AD | 05/04/2023 | 0 | Resource Division | 8.21 | 0 | 0
3863 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000234/2023-2024 | 2195/AD | 10/08/2023 | 0 | Resource Division | 4.64 | 0 | 0
3864 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000343/2023-2024 | 3207/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3865 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000607/2023-2024 | 269/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
3866 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000667/2023-2024 | 420/AD | 22/01/2024 | 0 | Resource Division | 8.26 | 0 | 0
3867 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000887/2023-2024 | 741/AD | 03/02/2024 | 0 | Resource Division | 1.59 | 0 | 0
3868 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000914/2023-2024 | 1256/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3869 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Chandipur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001484/2021-2022 | 6394/AD | 02/03/2022 | 30 | M/S RAKESH ENTERPRISE | 37.72 | 0 | 93
3870 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000833/2023-2024 | 678/AD | 30/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
3871 | Alipore Division |  | Extension distribution system (at Node no. 11) in Zone-X of Mathurapur - II Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000245/2022-2023 | 78/RSD | 18/05/2022 | 60 | BANGA NIRMAN | 4.81 | 0 | 0
3872 | Alipore Division |  | Day to day annual operation and maintenance of Over Head Reservoir, rising main & Distribution System (CI/DI/AC/UPVC of pipeline) of Nandakumarpur (Zone - I) W/S Scheme under Raidighi Sub-Division of Alipore Division P.H.E. Dte. [From 15.12.2021 to 14.12.2022] |  |  | ORD/001187/2021-2022 | 557/RSD | 14/12/2021 | 365 | M/S A.R. CONSTRUCTION | 4.47 | 0 | 100
3873 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Bhuiner Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001234/2020-2021 | 566/RSD | 30/12/2020 | 60 | M/S B.M. CONSTRUCTION | 4.47 | 4.47 | 0
3874 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Janar Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001236/2020-2021 | 568/RSD | 30/12/2020 | 60 | M/S B.M. CONSTRUCTION | 4.48 | 4.47 | 0
3875 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manager Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001237/2020-2021 | 569/RSD | 30/12/2020 | 60 | M/S. M.M. ENTERPRISE | 4.51 | 4.51 | 0
3876 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manger Gheri Purba (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001238/2020-2021 | 570/RSD | 30/12/2020 | 60 | M/S. M.M. ENTERPRISE | 4.47 | 4.3 | 0
3877 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-I) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001333/2020-2021 | 2222/AD | 08/10/2020 | 365 | SUKALPA NIRMAN | 70.74 | 0 | 100
3878 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 18.44 | 100
3879 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Majhi para, Mondal para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000398/2020-2021 | 771/KSD | 14/10/2020 | 45 | BHUNIA BUILDERS | 2.92 | 0 | 0
3880 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (part), Debimathurapur (part) and Barui Para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000399/2020-2021 | 772/KSD | 14/10/2020 | 45 | M/S MODINA ENTERPRISE | 4.79 | 4.77 | 0
3881 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj(part), Jana Para, Khan Para and Gobindapur(Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000402/2020-2021 | 773/KSD | 14/10/2020 | 45 | KHOKAN MONDAL | 4.78 | 4.74 | 0
3882 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Patra Para & Debimathurapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000414/2020-2021 | 790/KSD | 15/10/2020 | 45 | M/S KALIPADA JANA | 3.18 | 2.95 | 0
3883 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (Part) & Gobindapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000415/2020-2021 | 791/KSD | 15/10/2020 | 45 | JOY ENGINEERING & CONSTRUCTION | 3.74 | 0 | 80
3884 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Chokirdar Para & Bar Para of Nagendraganj W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000416/2020-2021 | 792/KSD | 15/10/2020 | 45 | M/S. BRINDABAN DAS & SONS | 3.34 | 0 | 95
3885 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 245 to 246, 245 to 250, 254 to 255 & 255 to 256 of Nagendraganj W/S Scheme under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000431/2020-2021 | 817/KSD | 16/10/2020 | 45 | M/S MODINA ENTERPRISE | 4.59 | 0 | 80
3886 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 258, 258 to 259, 259 to 260 260 to 261, 261 to 262, 262 to 263 & 263 to 264 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000432/2020-2021 | 818/KSD | 16/10/2020 | 45 | SUDIP PRADHAN | 3.42 | 0 | 100
3887 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 11 to 104, 20 to 21, 21 to 23 & 20 to 42 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000470/2020-2021 | 1048/KSD | 19/12/2020 | 20 | M/S. JOYGURU ENTERPRISE | 4.45 | 0 | 100
3888 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000332/2023-2024 | 3147/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3889 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000701/2023-2024 | 471/AD | 24/01/2024 | 0 | Resource Division | 5.71 | 0 | 0
3890 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Nagendraganj W/S Scheme (Phase-A), Dhaspara W/S Scheme (Phase-A), Shibpur W/S Scheme (Phase-A) & Bishnupur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 518/KSD, 24.08.21, T.No. 1792/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | VCH/002607/2021-2022 | BP-2021-22-510 | 22/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 4.7 | 0 | 0
3891 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Booth No: 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000108/2020-2021 | 1360/SWD-I | 08/12/2020 | 120 | CALCON CONSTRUCTIONS | 96.86 | 83.78 | 100
3892 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline of within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6133) PART-V | AE SWSD-I |  | ORD/000464/2022-2023 | 2774/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 2.41 | 0 | 100
3893 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 365 | M/S. DAS BUILDERS | 53.21 | 0 | 96
3894 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
3895 | Alipore Division | Raidighi Sub-Division | Remodeling of pipeline at (Node point - 21-23,23-25,25-26,26-28,28-156,156-158,26-27,28-29,156-157,158-159,30-31,160-161,162-163,63-64) of Chaplarkhop W/S Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001035/2021-2022 | 539/RSD | 30/11/2021 | 60 | SWASTIK ENTERPRISE (NEW) | 4.8 | 0 | 100
3896 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001229/2020-2021 | 564/RSD | 30/12/2020 | 60 | SANKAR HALDER | 4.82 | 0 | 100
3897 | Alipore Division | Raidighi Sub-Division | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 30 | SUKUMAR HALDAR | 7.81 | 0 | 0
3898 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-C) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002363/2020-2021 | 735/RSD | 12/02/2021 | 60 | SWASTIK ENTERPRISE (NEW) | 4.82 | 0 | 100
3899 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002364/2020-2021 | 736/RSD | 12/02/2021 | 60 | M.S. ENTERPRISE | 4.82 | 0 | 100
3900 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000658/2023-2024 | 262/AD | 15/01/2024 | 0 | Resource Division | 5.36 | 0 | 0
3901 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Banshtala Baragheri mouza (JL No. 114) & partly Ghatbakultala mouza (JL No. 116) in Mathurapur-I block, Zone-XIII under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/000391/2022-2023 | 4484/AD | 31/08/2022 | 30 | M/S. L.P. CONSTRUCTION | 28.94 | 0 | 100
3902 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
3903 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-E) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block- Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte |  |  | ORD/000607/2021-2022 | 528/RSD | 18/11/2021 | 60 | L.N. ENTERPRISE | 4.77 | 0 | 100
3904 | Alipore Division |  | Restoration of distribution system of Ghatbakultala W/S scheme (near Ashokenagar-Jgendranagar) at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000635/2022-2023 | 96/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.76 | 0 | 100
3905 | Alipore Division |  | Restoration of distribution system near node no. 139 of Zone-XIII Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000636/2022-2023 | 97/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.75 | 0 | 100
3906 | Alipore Division |  | Restoration of distribution system near jogendranagar more to provide FHTC at Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000637/2022-2023 | 98/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 3.42 | 0 | 100
3907 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-F) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001155/2021-2022 | 569/RSD | 15/12/2021 | 60 | S.P. CONSTRUCTION (II) | 4.77 | 0 | 100
3908 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001307/2020-2021 | 562/RSD | 30/12/2020 | 60 | M/S KALPANA CONSTRUCTION | 4.82 | 0 | 100
3909 | Alipore Division |  | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 27-25-22-16-15-13) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001582/2021-2022 | 711/RSD | 02/03/2022 | 60 | N.B.N CONSTRUCTION | 4.76 | 0 | 100
3910 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-G) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001590/2021-2022 | 774/RSD | 28/03/2022 | 60 | M/S KALIPADA JANA | 4.75 | 0 | 100
3911 | Alipore Division |  | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala water supply scheme (Zone-XIII of Mathurapur-I block for Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001768/2021-2022 | 626/RSD | 29/12/2021 | 15 | L.N. ENTERPRISE | 4.47 | 0 | 100
3912 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/002357/2020-2021 | 734/RSD | 12/02/2021 | 60 | M/S. BISWAS CONSTRUCTION (II) | 4.82 | 0 | 100
3913 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 5661/AD | 27/01/2022 | 0 | Resource Division | 0.7 | 0 | 0
3914 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR MAR'22 TO MAY'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/00681/2024-2025 | BP-2024-25-225 | 20/06/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
3915 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR NOV'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/00683/2024-2025 | BP-2024-25-228 | 20/06/2024 | 0 | RAJKUMAR MANNA | 0.36 | 0 | 0
3916 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001188/2023-2024 | 555/DHSD | 31/10/2023 | 182 | GOPAL KUMAR JHA | 2.4 | 0 | 100
3917 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Koaberia Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001371/2020-2021 | 5128/AD | 08/02/2021 | 365 | M. CHAKRABORTY | 56.38 | 0 | 92
3918 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
3919 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House and boundary wall at 1st Tubewell site for Koaberia W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07579) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002158/2024-2025 | 1986/KSD | 23/12/2024 | 25 | IMAGINEER VENTURES | 2.26 | 0 | 0
3920 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000276/2023-2024 | 3075/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3921 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000838/2023-2024 | 683/AD | 30/01/2024 | 0 | Resource Division | 6.6 | 0 | 0
3922 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 300] [SM/11847] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002288/2023-2024 | 1004/AD | 16/02/2024 | 240 | M/S. JHARNA ENTERPRISE | 172.02 | 0 | 10
3923 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 630 | PUTUL RANI MAITY | 217.06 | 0 | 97
3924 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Kalaria Water Supply Scheme Block - Canning - I, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001378/2020-2021 | 5132/AD | 08/02/2021 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS | 153.65 | 51.27 | 100
3925 | Central Drilling | Canning Sub-division | SALINE ZONE SEALING AND OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN KALARIA W/S SCHEME (REPLACEMENT TW-III, Z-II), UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000508/2022-2023 | 309/CMSD-I | 08/07/2022 | 3 | PADMA ENGINEERING & CO. | 0.58 | 0 | 100
3926 | Central Drilling | Canning Sub-division | Additional Mobilization of all machineries & accessories etc. and Sealing of Saline zone at site for construction of tube well at Kalaria W/S Scheme (untreated zone), South 24 pgs District. under, Central Drilling Division, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000522/2022-2023 | 257/CMSD-I(D) | 23/06/2022 | 3 | PADMA ENGINEERING & CO. | 0.86 | 0 | 100
3927 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation and laying extension pipe line for providing FHTC for Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000595/2022-2023 | 5920/AD | 19/10/2022 | 30 | L.N. ENTERPRISE | 15.68 | 0 | 95
3928 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Srikrishnanagar W/S Scheme, Block Kakdwip and Dakshin Shibganj W/S Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001087/2021-2022 | 578/KSD | 10/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.24 | 0 | 100
3929 | Alipore Division | Kakdwip Sub-Division | Connection of Tubewell with distribution line of Head Work Site of Srikrishnanagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001173/2021-2022 | 761/KSD | 29/11/2021 | 20 | MANDAL ENTERPRISE (JOYNAGAR) | 0.44 | 0 | 95
3930 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000829/2023-2024 | 674/AD | 30/01/2024 | 0 | Resource Division | 7.15 | 0 | 0
3931 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 90 | KIRON CONSTRUCTION | 126.68 | 0 | 0
3932 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000611/2020-2021 | 850/CSD | 12/10/2020 | 45 | DIPA CHHETRI | 4.74 | 4.74 | 0
3933 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000614/2020-2021 | 853/CSD | 12/10/2020 | 45 | SUKANTA HALDER | 4.74 | 0 | 0
3934 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000616/2020-2021 | 855/CSD | 12/10/2020 | 45 | MODERN CONSTRUCTION | 4.74 | 0 | 0
3935 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000617/2020-2021 | 860/CSD | 12/10/2020 | 45 | C.S. CONSTRUCTION | 4.73 | 0 | 95
3936 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000618/2020-2021 | 861/CSD | 12/10/2020 | 45 | SARKAR CONSTRUCTION | 4.75 | 4.72 | 0
3937 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000619/2020-2021 | 862/CSD | 12/10/2020 | 45 | ARFIN CONSTRUCTION | 4.75 | 0 | 100
3938 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000620/2020-2021 | 863/CSD | 12/10/2020 | 45 | KUNDU CONSTRUCTION CO. | 4.74 | 4.72 | 0
3939 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000621/2020-2021 | 864/CSD | 12/10/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.74 | 0 | 100
3940 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000622/2020-2021 | 865/CSD | 12/10/2020 | 45 | M/S. M.K. NASKAR & CONSTRUCTION | 4.73 | 0 | 100
3941 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000623/2020-2021 | 866/CSD | 12/10/2020 | 45 | M/S. MANABESH ROY | 4.74 | 4.74 | 0
3942 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000624/2020-2021 | 867/CSD | 12/10/2020 | 45 | ASHIS ENTERPRISE | 4.72 | 0 | 100
3943 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000625/2020-2021 | 868/CSD | 12/10/2020 | 45 | DEY ENTERPRISE (III) | 4.74 | 0 | 100
3944 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Kripa Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000630/2020-2021 | 869/CSD | 12/10/2020 | 45 | SAHANA ENTERPRISE | 4.74 | 0 | 100
3945 | Alipore Division | Canning Sub-division | Laying pipe line for FHTC work at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000996/2021-2022 | 991/CSD | 26/10/2021 | 30 | MODERN CONSTRUCTION | 3.74 | 0 | 100
3946 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001455/2020-2021 | 1003/CSD | 13/11/2020 | 45 | MONCON INDIA | 4.7 | 4.7 | 100
3947 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001456/2020-2021 | 1005/CSD | 13/11/2020 | 45 | MODERN CONSTRUCTION | 4.74 | 0 | 100
3948 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001457/2020-2021 | 1006/CSD | 13/11/2020 | 45 | SOURAV NASKAR | 4.79 | 0 | 100
3949 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001466/2020-2021 | 1018/CSD | 23/11/2020 | 45 | SUKANTA HALDER | 4.71 | 0 | 100
3950 | Alipore Division | Canning Sub-division | Extension of pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001468/2021-2022 | 1490/CSD | 09/02/2022 | 20 | MITRA ASSOCIATE | 4.6 | 0 | 100
3951 | Alipore Division | Canning Sub-division | Repairing & relaying of damaged pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001469/2021-2022 | 1491/CSD | 09/02/2022 | 20 | ASHIS ENTERPRISE | 4.56 | 0 | 100
3952 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001470/2020-2021 | 1019/CSD | 23/11/2020 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 4.77 | 0 | 100
3953 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001471/2020-2021 | 1020/CSD | 23/11/2020 | 45 | RAKTIM ENTERPRISE | 4.69 | 0 | 100
3954 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001472/2020-2021 | 1021/CSD | 23/11/2020 | 45 | M/S TAMAL CHAKRABORTY | 4.72 | 0 | 0
3955 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001473/2020-2021 | 1022/CSD | 23/11/2020 | 45 | M/S. PROMILA CONSTRUCTION | 4.62 | 0 | 0
3956 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001474/2020-2021 | 1023/CSD | 23/11/2020 | 45 | R.G. ENTERPRISE (I) | 4.78 | 0 | 0
3957 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001475/2020-2021 | 1029/CSD | 24/11/2020 | 45 | BANERJEE ENTERPRISE | 4.73 | 0 | 0
3958 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001476/2020-2021 | 1030/CSD | 24/11/2020 | 45 | MODERN CONSTRUCTION | 4.7 | 0 | 100
3959 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001477/2020-2021 | 1031/CSD | 24/11/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.79 | 0 | 100
3960 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001478/2020-2021 | 1032/CSD | 24/11/2020 | 45 | ASHIS ENTERPRISE | 4.72 | 0 | 100
3961 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001479/2020-2021 | 1033/CSD | 24/11/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.69 | 0 | 100
3962 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001480/2020-2021 | 1034/CSD | 24/11/2020 | 45 | S.C. ENTERPRISE (I) | 4.66 | 0 | 100
3963 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001506/2020-2021 | 1004/CSD | 13/11/2020 | 45 | M/S KRISHNA MONDAL | 4.75 | 4.74 | 100
3964 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001556/2020-2021 | 1211/CSD | 15/12/2020 | 45 | M/S M3 SOLUTION | 4.7 | 4.69 | 100
3965 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001557/2020-2021 | 1212/CSD | 15/12/2020 | 45 | M/S. MANABESH ROY | 4.65 | 0 | 100
3966 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XVI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001558/2020-2021 | 1214/CSD | 15/12/2020 | 45 | D.R.CONSTRUCTION | 4.6 | 0 | 100
3967 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001747/2020-2021 | 1450/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.61 | 0 | 100
3968 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001748/2020-2021 | 1451/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.69 | 0 | 100
3969 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XIX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001751/2020-2021 | 1452/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.57 | 0 | 100
3970 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001754/2020-2021 | 1453/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.65 | 0 | 100
3971 | Alipore Division | Canning Sub-division | Laying of pipeline for providing house connection from H/O Rajkumar Sardar to H/O Bhagyadhar Sardar of Pakhirali habitation under Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002028/2020-2021 | 1517/CSD | 10/02/2021 | 30 | MONCON INDIA | 0.43 | 0.42 | 0
3972 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002039/2020-2021 | 1210/CSD | 15/12/2020 | 45 | M/S ARIYAN ENTERPRISE | 4.72 | 0 | 100
3973 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Sashan Station to Durgapur station connecting road from 0.000 kmp 0.830kmp under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.38,91,559/- x 50% = Rs.19,45,780/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00562/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 19.46 | 0 | 0
3974 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Kalyanpur - Indralala - Durgapur Station Road from 0.000 kmp to 3.15 km (R/S: 230m & L/S: 1520m) under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.73,16,902/- x 50% = Rs.36,58,451/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00563/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 36.58 | 0 | 0
3975 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Improvement of water supply by Interconnection from existing Big dia tube well and laying distribution system with CIDF, UPVC pipes Including providing Functional House Hold Tap Connection by retrofitting of scheme ¿Improvement of water supply [Phase-III] in Baruipur and Mograhat-II block¿ of Sankarpur-II GP within zone-43, covering Nur, Durgo, Balbalia, Surjopur hat mouzas under surface water based water supply scheme for arsenic affected areas of south 24- Parganas district. | AE BSD |  | ORD/000071/2021-2022 | 479 /SWD-I JJM p | 07/07/2021 | 120 | M/S. S.S. ENTERPRISE | 193.14 | 0 | 100
3976 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Interconection including laying distribution system from Big dia Tube well covering Kundarali, Mamudpur & Indraballa for improvement of water supply & Providing Functional House Hold Tap Connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000295/2020-2021 | 2131/SWD-I | 26/02/2021 | 120 | PEECON | 203.09 | 0 | 100
3977 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sitarampur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution system, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000033/2022-2023 | 675/AD | 05/05/2022 | 120 | GROWING CONCERN | 150.83 | 0 | 80
3978 | Alipore Division | Kakdwip Sub-Division | Supply, Delivery & Laying of Specials Required for Laying Rising Main and Inter-Connection Line between Tubewells and other allied works for providing FHTC under JJM at Sitarampur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000224/2022-2023 | 3065/AD | 13/07/2022 | 30 | ANANTA KUMAR GIRI | 7.64 | 0 | 100
3979 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000781/2023-2024 | 615/AD | 29/01/2024 | 0 | Resource Division | 12.81 | 0 | 0
3980 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000825/2023-2024 | 670/AD | 30/01/2024 | 0 | Resource Division | 12.64 | 0 | 0
3981 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001025/2021-2022 | 539/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.58 | 0 | 100
3982 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001044/2021-2022 | 2275/AD | 06/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.04 | 0 | 100
3983 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001609/2021-2022 | 607/KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 4.02 | 0 | 100
3984 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000268/2023-2024 | 3067/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3985 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000830/2023-2024 | 675/AD | 30/01/2024 | 0 | Resource Division | 18.1 | 0 | 0
3986 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Jameson Island & Kali Mandir Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001729/2020-2021 | 1211/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
3987 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001741/2020-2021 | 1214/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
3988 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kamar Para (Part) & Library Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001762/2020-2021 | 1221/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
3989 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mollar Chak & Shivnagar for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001792/2020-2021 | 1237/KSD | 23/02/2021 | 10 | M/S MODINA ENTERPRISE | 4.55 | 0 | 84
3990 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001808/2020-2021 | 1246/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.76 | 0 | 96
3991 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahis Gheri, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001835/2020-2021 | 1266/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 80
3992 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Library Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001839/2020-2021 | 1270/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
3993 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001843/2020-2021 | 1274/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
3994 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001846/2020-2021 | 1277/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.74 | 0 | 100
3995 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Khorimutha for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001849/2020-2021 | 1280/KSD | 23/02/2021 | 10 | M/S MODINA ENTERPRISE | 4.1 | 0 | 91
3996 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.46 | 0 | 87
3997 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001860/2020-2021 | 1291/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
3998 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sitala Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001863/2020-2021 | 1294/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
3999 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para (Part) & Gosta Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001897/2020-2021 | 1319/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
4000 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000775/2023-2024 | 609/AD | 29/01/2024 | 0 | Resource Division | 14.15 | 0 | 0
4001 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000272/2021-2022 | 1719/AD | 17/08/2021 | 1825 | M/S. ROY CHOWDHURY & CO. | 120.85 | 0 | 80
4002 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000143/2023-2024 | 854/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4003 | Central Drilling | Canning Sub-division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DUTTABABUR ABAD W/S SCHEME (TW-II), CANNING-I BLOCK UNDER SOUTH 24PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000064/2022-2023 | 55/CDD | 08/04/2022 | 30 | C.M. ENTERPRISE | 14.55 | 0 | 0
4004 | Central Drilling | Canning Sub-division | ADDITIONAL TRANSPORTATION OF GRAVELS, SEALING OF SALINE ZONE AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN DUTTA BABUR ABAD W/S SCHEME (TW-II), CANNING-I BLOCK UNDER SOUTH 24 PGS DISTRICT CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000221/2022-2023 | 418/CMSD-I | 10/08/2022 | 3 | C.M. ENTERPRISE | 0.66 | 0 | 0
4005 | Central Drilling | Canning Sub-division | RESISTIVITY SURVEY OF TUBE WELLS AT SHIMULTALA W/S SCHEME, UNDER CMSD-I (D), CDD, PHE DTYE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000235/2021-2022 | 109/CMSD-I (D) | 20/07/2021 | 7 | EARTH CARE PRODUCTS & SERVICES | 0.52 | 0 | 0
4006 | Central Drilling | Canning Sub-division | PROVIDING TUBEWELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000366/2022-2023 | 378/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 5 | 0 | 0
4007 | Central Drilling | Canning Sub-division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOT CONSTRUCTION OF TUBE WELL (250MM 150MM X 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000124/2022-2023 | 56/CDD | 08/04/2022 | 30 | PADMA ENGINEERING & CO. | 14.55 | 0 | 0
4008 | Central Drilling | Canning Sub-division | ADDITIONAL TRANSPORTATION OF GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SONAKHALI W/S SCH (ZONE-I, REPLACEMENT TW-III) BASANTI BLOCK, UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000157/2022-2023 | 119/CMSD-I | 06/05/2022 | 5 | PADMA ENGINEERING & CO. | 0.28 | 0 | 0
4009 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000081/2021-2022 | 1106/SWD-I JJM | 25/10/2021 | 120 | M/S. JAYDEEP DASGUPTA | 82.35 | 0 | 100
4010 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nischintipur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8297) Part - A | AE SWSD-I |  | ORD/000468/2022-2023 | 2777/SWD-I | 31/01/2023 | 30 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 8.58 | 0 | 75
4011 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001465/2021-2022 | 6259/AD | 24/02/2022 | 420 | SAJAL KUMAR DAS | 105.31 | 0 | 95
4012 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dwariknagar W/S Scheme, Block - Namkhana for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000345/2022-2023 | 4072/AD | 18/08/2022 | 30 | FORTUNE ENGINEERING | 18.33 | 0 | 100
4013 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, construction of 01 no. 5.40m. x 3.60m Pump House, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000438/2022-2023 | 4352/AD | 25/08/2022 | 60 | M/S KRISHNA MONDAL | 87.53 | 0 | 70
4014 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DWARIKNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000485/2022-2023 | 2492/AD | 27/06/2022 | 45 | M/S R.DUTTA & CO. | 4.61 | 0 | 100
4015 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Namkhana Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001102/2022-2023 | 8485/AD | 16/12/2022 | 837 | BALAJEE ENTERPRISE. | 691.56 | 0 | 100
4016 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Dwariknagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001479/2023-2024 | 4689/AD | 18/12/2023 | 411 | M/S. DAS BUILDERS | 9.51 | 0 | 100
4017 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work and 2nd Tubewell Site of Dwariknagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001836/2023-2024 | 124/AD | 05/01/2024 | 45 | M/S NAIYA & MAITY | 39.81 | 0 | 50
4018 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001841/2023-2024 | 129/AD | 05/01/2024 | 45 | M/S KRISHNA MONDAL | 40.83 | 0 | 60
4019 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
4020 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 300] [SM/11847] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002288/2023-2024 | 1004/AD | 16/02/2024 | 240 | M/S. JHARNA ENTERPRISE | 172.02 | 0 | 10
4021 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000292/2023-2024 | 3060/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4022 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000491/2023-2024 | 4790/AD | 19/12/2023 | 0 | Resource Division | 7.83 | 0 | 0
4023 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000549/2023-2024 | 32/AD | 02/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
4024 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000782/2023-2024 | 626/AD | 30/01/2024 | 0 | Resource Division | 2.74 | 0 | 0
4025 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000985/2023-2024 | 1778/AD | 27/03/2024 | 0 | Resource Division | 2.09 | 0 | 0
4026 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Dwariknagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000375/2022-2023 | 3779/SMD | 29/12/2022 | 90 | KARUNAMOY ENGINEERING | 10.71 | 0 | 0
4027 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Dwarikanagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002074/2023-2024 | 584-A-AE-I-SMD | 22/05/2023 | 15 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0
4028 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of Quotation for new service connection at Julpia PWSS, PH No. - I (Dag No. - 152) Application No. - 1007646826 Reference ID - 106555248 | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00151/2024-2025 | BP-2024-25-47 | 09/05/2024 | 0 | WBSEDCL | 5.28 | 0 | 0
4029 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Julpia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000509/2022-2023 | 348/SMD | 09/02/2023 | 873 | AHALYA ENGINEERING WORKS | 22.78 | 0 | 50
4030 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply & Delivery of the additional materials for PH No.-1 of Julpia Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/12234] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/002351/2024-2025 | 1312-AE-II-SMD | 29/10/2024 | 15 | AHALYA ENGINEERING WORKS | 0.26 | 0 | 0
4031 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for final 50% amount of the estimate value after completion of restoration work near chainage 10 km on Amtala Baruipur road as per minutes of the meeting taken by HMIC, PHED with SE's on 12/09/2022 whose total estimate value Rs.53,10,997/-, Less advance 50% payment Rs.26,55,499/-, So. Payment to be made Rs.26,55,498/- | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00063/2024-2025 | BP-2024-25-52 | 09/05/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0
4032 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of damages due to laying of water supply line of PHE Directorate near chainage 10.00 kmp of Amtala - Baruipur Road in the district of South 24 pgs under South 24 pgs. Division, PWD during the year 2022-2023 (Estimated cost Rs.53,10,997/- x 50% = 2655499/-) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/01314/2023-2024 | BP-2023-24-456 | 03/11/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0
4033 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
4034 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "JULPIA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000420/2022-2023 | 467/SWD-I C | 24/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.62 | 0 | 100
4035 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based JULPIA Pipe Water Supply Scheme for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs. District. [No. of FHTC=901 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000421/2022-2023 | 2566/SWD-I | 10/01/2023 | 90 | RELIABLE CONSTRUCTIONS | 163.03 | 0 | 60
4036 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of JULPIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12234) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000434/2022-2023 | 2578/SWD-I | 10/01/2023 | 60 | BAKSHI ENTERPRISE | 6.05 | 0 | 100
4037 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JULPIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014900] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000634/2022-2023 | 3278/SWD-I | 03/03/2023 | 15 | MOMINUL BISWAS | 1.57 | 0 | 0
4038 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, laying of additional pipeline and other allied works for JULPIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000667/2024-2025 | 4414/SWD-I | 24/10/2024 | 361 | BAKSHI ENTERPRISE | 58.69 | 0 | 12
4039 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for JULPIA Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12234] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000694/2024-2025 | 4489/SWD-I | 30/10/2024 | 151 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 98
4040 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development at JULPIA Piped Water Supply Scheme for 1st Tubewell site in the Arsenic Affected Areas of South 24 Parganas District in Bishnupur-I Block under South 24-Pgns. W/S Sub Division-II, PHE Dte. (SM/12234) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000838/2023-2024 | 1255/SWD-I | 13/03/2024 | 15 | HASIBA ENTERPRISE | 2.65 | 0 | 95
4041 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000121/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 37.13 | 0 | 0
4042 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2022 to 30/04/2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000216/2022-2023 | 45/DHSD | 29/04/2022 | 1 | GOPAL KUMAR JHA | 4.8 | 0 | 71
4043 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Gangadharpur (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000294/2022-2023 | 3831/AD | 08/08/2022 | 45 | M/S AHAMED CONSTRUCTION | 36.53 | 0 | 100
4044 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 2 nos. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000321/2022-2023 | 3868/AD | 08/08/2022 | 30 | SANKAR HALDER | 59.33 | 0 | 85
4045 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000322/2022-2023 | 3869/AD | 08/08/2022 | 30 | MS S.M. ENTERPRISE | 14.79 | 0 | 100
4046 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANGADHARPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000492/2022-2023 | 1750/AD | 15/06/2022 | 45 | LEMNISCATE | 6.22 | 0 | 100
4047 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000543/2023-2024 | 2209/AD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 450.22 | 0 | 60
4048 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gangadharpur (Zone - I &II) PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11805) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000573/2024-2025 | 4027/AD | 30/09/2024 | 458 | M/S PIONEER CONSTRUCTION | 154.01 | 0 | 20
4049 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Gangadharpur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11805) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001330/2024-2025 | 5414/AD | 24/12/2024 | 45 | L G CONSTRUCTION | 39.76 | 0 | 0
4050 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
4051 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002599/2023-2024 | 177/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4052 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002600/2023-2024 | 178/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4053 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002615/2023-2024 | 733/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
4054 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002616/2023-2024 | 864(A)/KSD | 13/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
4055 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000089/2022-2023 | 5596/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
4056 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000459/2023-2024 | 4722/AD | 18/12/2023 | 0 | Resource Division | 33.17 | 0 | 0
4057 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000996/2023-2024 | 1789/AD | 27/03/2024 | 0 | Resource Division | 30.96 | 0 | 0
4058 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00019/2023-2024 | BP-2023-24-04 | 25/04/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
4059 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bills for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01559/2022-2023 | BP-2022-23-452 | 20/03/2023 | 0 | WBSEDCL | 1.42 | 0 | 0
4060 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I&II for Augmentation of Gangadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000372/2022-2023 | 3776/SMD | 29/12/2022 | 90 | BHUNIA BUILDERS | 9.3 | 0 | 0
4061 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2, Zone-I&II for Augmentation of Gangadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000810/2023-2024 | 2925/SMD | 01/09/2023 | 90 | T.S. CONSTRUCTION | 9.08 | 0 | 80
4062 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at Zone-I & II PH-1&2 of Gangadharpur Aug. W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Block-Kakdwip) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001653/2023-2024 | 1026/AE-I/SMD | 20/09/2023 | 15 | DITHI ENTERPRISE | 0.78 | 0 | 100
4063 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000862/2023-2024 | 769/AD | 03/02/2024 | 0 | Resource Division | 20.59 | 0 | 0
4064 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000931/2023-2024 | 1273/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4065 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Companir Char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11748) (SM/09077) (SM/08802) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000021/2025-2026 | 2007/AD | 28/04/2025 | 45 | PALASH HALDAR | 8.27 | 0 | 0
4066 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Companir Char PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000076/2023-2024 | 60/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4067 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Companirchar W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000280/2023-2024 | 1430/AD | 13/07/2023 | 45 | TANMAY ROY CHOWDHURY | 88.41 | 0 | 50
4068 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Companirchar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000296/2022-2023 | 3832/AD | 08/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.93 | 0 | 100
4069 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companir char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000306/2022-2023 | 3842/AD | 08/08/2022 | 30 | DIPA CHHETRI | 11.78 | 0 | 100
4070 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000307/2022-2023 | 3855/AD | 08/08/2022 | 15 | GHOSH CONSTRUCTION | 8.03 | 0 | 100
4071 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC pipe line from Nodal Point 18 to 20, 13 to 48, 13 to 64 of Companirchar W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000390/2020-2021 | 952/KSD | 03/11/2020 | 30 | SK ENTERPRISE | 4.42 | 0 | 100
4072 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000446/2022-2023 | 4645/AD | 06/09/2022 | 120 | RELIABLE CONSTRUCTION | 149.69 | 0 | 100
4073 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (COMPANIR CHAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000480/2022-2023 | 1710/AD | 14/06/2022 | 45 | VOYAGER | 6.12 | 0 | 100
4074 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 1 no. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000671/2022-2023 | 6156/AD | 01/11/2022 | 902 | TANMAY ROY CHOWDHURY | 344.09 | 0 | 95
4075 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Companir Char W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000717/2023-2024 | 2535/AD | 28/08/2023 | 30 | TANMAY ROY CHOWDHURY | 9.03 | 0 | 100
4076 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001206/2021-2022 | 403/DHSD | 28/12/2021 | 4 | MADHUSUDAN MAITY | 1.6 | 0 | 55
4077 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
4078 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Companir char W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002179/2023-2024 | 815/AD | 05/02/2024 | 30 | M/S. MANDAL ENTERPRISE | 11.65 | 0 | 0
4079 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000095/2022-2023 | 5597/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
4080 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000285/2023-2024 | 3087/AD | 28/09/2023 | 0 | Resource Division | 56.81 | 0 | 0
4081 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000333/2023-2024 | 3148/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4082 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000901/2023-2024 | 887/AD | 07/02/2024 | 0 | Resource Division | 3.44 | 0 | 0
4083 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00013/2023-2024 | BP-2023-24-03 | 25/04/2023 | 0 | WBSEDCL | 2.69 | 0 | 0
4084 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Companirchar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000003/2023-2024 | 988/SMD | 06/04/2023 | 90 | ROY & BISWAS ENGG. CO. | 10.14 | 0 | 100
4085 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at P.H. No-1 of Comanirchar Aug & PH-1 of Mrityunjaynagar Aug water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000659/2024-2025 | 764-AE-I-SMD | 03/06/2024 | 15 | MAA SUSOMA & COMPANY | 0.82 | 0 | 0
4086 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Companirchar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002070/2023-2024 | 679-AE-I-SMD | 21/06/2023 | 15 | ROY & BISWAS ENGG. CO. | 0.83 | 0 | 0
4087 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00161/2024-2025 | BP-2024-25-53 | 10/05/2024 | 0 | WBSEDCL | 5.31 | 0 | 0
4088 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Piyali Kolaghata ( Solghoalia CT) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 443/SMD | 17/02/2023 | 90 | RSA ENTERPRISE | 13.01 | 0 | 0
4089 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-I) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009673] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000101/2022-2023 | 1228/SWD-I | 07/09/2022 | 30 | SAIKAT ENTERPRISE | 19.98 | 0 | 0
4090 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at PIYALI KOLAGHATA (Zone-I) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009673] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000155/2022-2023 | 1413/SWD-I | 22/09/2022 | 60 | SHUBHA UDYOG | 5.5 | 0 | 0
4091 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 1001 | M/S. S.S. ENTERPRISE | 285.6 | 0 | 92
4092 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 990 | KARUNAMOYEE ENTERPRISE | 140.23 | 0 | 75
4093 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PiyaliKolaghata-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000729/2022-2023 | 3572/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 2.2 | 0 | 0
4094 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000073/2023-2024 | 293/SWD-I | 24/04/2023 | 0 | Resource Division | 8.71 | 0 | 0
4095 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I |  | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 607 | SUPRITI ENTERPRISE | 1557.57 | 0 | 50
4096 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000052/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 47.52 | 0 | 0
4097 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00010/2023-2024 | BP-2023-24-46 | 18/05/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
4098 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Piyali KOLAGHATA (Part-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000215/2024-2025 | 491/SMSD | 23/04/2024 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 100
4099 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & fixing main switch & Bus Bar at Pump House no-1 of Piyali KOLAGHATA W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000216/2024-2025 | 490/SMSD | 23/04/2024 | 15 | NUPUR CHANDRA HALDER | 0.29 | 0 | 100
4100 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1& 2, of Piyali Kolaghata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000532/2022-2023 | 459/SMD | 17/02/2023 | 90 | NUPUR CHANDRA HALDER | 21.83 | 0 | 100
4101 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Piyali Kolaghat w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000895/2023-2024 | 1O62/SMSD | 10/08/2023 | 15 | NUPUR CHANDRA HALDER | 0.87 | 0 | 100
4102 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000105/2022-2023 | 1231/SWD-I | 07/09/2022 | 30 | BARI ENTERPRISE | 40.12 | 0 | 100
4103 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/07/2025 to 31/12/2025] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 1730/SWD-I | 26/06/2025 | 184 | SUBRAT KUMAR SETHY | 0.87 | 0 | 0
4104 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PIYALI KOLAGHATA (Zone-II) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010734] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000159/2022-2023 | 1412/SWD-I | 22/09/2022 | 60 | M/S. SREEJIT ENTERPRISE | 10.99 | 0 | 100
4105 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 1001 | M/S. S.S. ENTERPRISE | 285.6 | 0 | 92
4106 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 990 | KARUNAMOYEE ENTERPRISE | 140.23 | 0 | 75
4107 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based PIYALI KOLAGHATA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000306/2024-2025 | 3219/SWD-I | 18/07/2024 | 60 | M/S. S.S. ENTERPRISE (NODAKHALI) | 35.48 | 0 | 0
4108 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall including development of land and other allied works for Ground water based PIYALI KOLAGHATA(P-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 3239/SWD-I | 19/07/2024 | 45 | M/S. S.S. ENTERPRISE (NODAKHALI) | 31.32 | 0 | 0
4109 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010734] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 2115/SWD-I | 30/08/2023 | 15 | BARI ENTERPRISE | 4.4 | 0 | 100
4110 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PIYALI KOLAGHATA , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000507/2021-2022 | 1906/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 0 | 100
4111 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/01/2025 to 30/06/2025] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001109/2024-2025 | 5303/SWD-I | 27/12/2024 | 181 | SUBRAT KUMAR SETHY | 0.86 | 0 | 33
4112 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for PIYALI KOLAGHATA (PART-I) Piped Water Supply Scheme of BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/11279] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001154/2024-2025 | 372/SWD-I | 04/02/2025 | 30 | M/S MAA TARA ENTERPRISE | 15.65 | 0 | 0
4113 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000072/2023-2024 | 293/SWD-I | 24/04/2023 | 0 | Resource Division | 38.58 | 0 | 0
4114 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04088/2023-2024 | BP-2023-24-423 | 16/12/2023 | 0 | WBSEDCL | 15.69 | 0 | 0
4115 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000556/2022-2023 | 545/SMD | 21/02/2023 | 831 | DEBJYOTI BASU | 19.37 | 0 | 100
4116 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002273/2024-2025 | 18/SMSD | 06/01/2025 | 15 | DEBJYOTI BASU | 0.59 | 0 | 0
4117 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gobindapur W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11280] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002274/2024-2025 | 1520/SMSD | 18/11/2024 | 15 | DEBJYOTI BASU | 0.59 | 0 | 0
4118 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at GOBINDAPUR of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000157/2022-2023 | 1410/SWD-I | 22/09/2022 | 60 | J H K ENTERPRISE | 11.01 | 0 | 100
4119 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GOBINDAPUR PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010741] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000242/2022-2023 | 1685/SWD-I | 01/11/2022 | 360 | SIMPLEX DRILLING COMPANY | 42.98 | 0 | 100
4120 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GOBINDAPUR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000448/2021-2022 | 1962/SWD-I | 21/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
4121 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000071/2023-2024 | 292/SWD-I | 24/04/2023 | 0 | Resource Division | 45.97 | 0 | 0
4122 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01497/2023-2024 | BP-2023-24-178 | 02/08/2023 | 0 | WBSEDCL | 7.5 | 0 | 0
4123 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-I & 2 of Dari Madhabpur water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Bhangar-I ] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000003/2024-2025 | 1647/SMSD | 05/04/2024 | 15 | KARTICK BAL | 0.78 | 0 | 100
4124 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dari Madhabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000502/2022-2023 | 320/SMD | 06/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 26.02 | 0 | 90
4125 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Dari Madhabpur PH-1 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002283/2023-2024 | 1633/SMSD | 02/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 100
4126 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Dari Madhabpur PH-2 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002284/2023-2024 | 1634/SMSD | 02/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 100
4127 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no- 1 & 2 of Dari Madhabpur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13674) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/003140/2023-2024 | 51/SMSD | 11/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.58 | 0 | 0
4128 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2135] (TSM/014441) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 466/SWD-I | 04/05/2023 | 90 | PROJECT INDIA | 412.54 | 0 | 85
4129 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DARI MADHABPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014441] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 3136/SWD-I | 27/02/2023 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 31.78 | 0 | 100
4130 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of "DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13674) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000677/2024-2025 | 4466/SWD-I | 29/10/2024 | 60 | PROJECT INDIA | 79.05 | 0 | 0
4131 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000902/2023-2024 | 1467/SWD-I | 27/03/2024 | 92 | M/S. SYSCON | 0.51 | 0 | 100
4132 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000903/2023-2024 | 1468/SWD-I | 27/03/2024 | 92 | M/S. SYSCON | 0.41 | 0 | 99
4133 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000052/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 13.13 | 0 | 0
4134 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000220/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.15 | 0 | 0
4135 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | As per Minutes of Hon'ble PHED Minister in Charge 50% advance payment of total estimate value for road restoration work for Mahishot Chattabazar Road which was submitted vide SE memo no.374/6-1391 dt.06/04/2022 | AE SWSD-I |  | BILL/00008/2022-2023 | BP-2022-23-106 | 02/12/2022 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 165.54 | 0 | 0
4136 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of road for laying of water pipeline by PHE Dte, in Mohisgot Chata bazar 0.00 to 5.40 km Under South 24 Parganas Division P.W.D in the Dist of South 24 Pgs During the year 2024-25 | AE SWSD-I |  | BILL/00345/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 165.54 | 0 | 0
4137 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Balance FHTC for ThakurpukurMaheshtala Block (PART) in connection to "Retrofitting of pipeline for FHTC drive including PWD road restoration in connection with pipe water supply scheme including FHTC for CHATTA GP in ThakurpukurMaheshtala Block under South 24 Parganas W/S Division-I, PHE, Dte. [TSM/014924] | AE SWSD-I |  | ORD/000700/2022-2023 | 3509/SWD-I | 17/03/2023 | 60 | M/S. S.S. ENTERPRISE | 40.63 | 0 | 0
4138 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Rameswarpur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000768/2020-2021 | 2064/SWD-I | 19/02/2021 | 90 | SAMPSON INFRA DESIGN LLP | 8.92 | 0 | 100
4139 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Narayantala W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000415/2023-2024 | 774/CSD | 02/08/2023 | 35 | S.K.GOLUI | 2.17 | 0 | 99
4140 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations and pipe protection work at Narayantala W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001029/2024-2025 | 4939/AD | 03/12/2024 | 60 | DIPTI ENTERPRISE | 56.82 | 0 | 0
4141 | Alipore Division | Canning Sub-division | Restoration of pipe line damaged due to flood like situation occurred by breaking of rivers embankment at Choradakatia under Narayantala W/S Scheme of Basanti Block under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001351/2020-2021 | 1259/CSD | 21/12/2020 | 30 | SURYA ENTERPRISE | 4.8 | 0 | 100
4142 | Alipore Division | Canning Sub-division | Construction of OHR (200 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Narayantala,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001641/2022-2023 | 11378/AD | 13/02/2023 | 1200 | DIPTI ENTERPRISE | 319 | 0 | 48
4143 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000073/2023-2024 | 538/AD | 25/01/2024 | 0 | Resource Division | 40.34 | 0 | 0
4144 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Narayantala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000493/2022-2023 | 295/SMD | 03/02/2023 | 90 | SRI KRISHNA NIRMAN | 11.18 | 0 | 0
4145 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bamanagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000049/2023-2024 | 34/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4146 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile & pile cap upto pedestal at Bamanagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000269/2023-2024 | 1419/AD | 13/07/2023 | 446 | GARGO TRADERS | 43.4 | 0 | 70
4147 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000338/2022-2023 | 5707/AD. | 13/10/2022 | 30 | R CONSTRUCTION | 13.63 | 0 | 70
4148 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Bamanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000471/2022-2023 | 5202/AD | 22/09/2022 | 45 | AQUATECH ENGINEER | 37.06 | 0 | 100
4149 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( BAMANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000495/2022-2023 | 4193/AD | 22/08/2022 | 45 | LEMNISCATE | 5.14 | 0 | 100
4150 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000541/2022-2023 | 5708/AD. | 13/10/2022 | 30 | SUMAN ENTERPRISE | 11.89 | 0 | 60
4151 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000552/2022-2023 | 5726/AD | 13/10/2022 | 901 | GARGO TRADERS | 434.79 | 0 | 80
4152 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000575/2022-2023 | 5713/AD | 13/10/2022 | 21 | M/S SAKTI GIRI ENTERPRISE | 9.89 | 0 | 100
4153 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001156/2023-2024 | 3719/AD | 03/11/2023 | 45 | G.M. ENTERPRISE | 27.73 | 0 | 70
4154 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001157/2023-2024 | 3720/AD | 03/11/2023 | 30 | SUKUMAR HALDAR | 9.57 | 0 | 100
4155 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
4156 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000120/2023-2024 | 656/AD | 17/05/2023 | 0 | Resource Division | 11.61 | 0 | 0
4157 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000443/2023-2024 | 4710/AD | 18/12/2023 | 0 | Resource Division | 9.1 | 0 | 0
4158 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000811/2023-2024 | 656/AD | 30/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
4159 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000992/2023-2024 | 1785/AD | 27/03/2024 | 0 | Resource Division | 32.17 | 0 | 0
4160 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00022/2023-2024 | BP-2023-24-06 | 25/04/2023 | 0 | WBSEDCL | 1.09 | 0 | 0
4161 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bills for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01561/2022-2023 | BP-2022-23-449 | 20/03/2023 | 0 | WBSEDCL | 1.42 | 0 | 0
4162 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Bamanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000429/2022-2023 | 3825/SMD | 29/12/2022 | 914 | KUNDU ELECTRICAL ENTERPRISE | 21.88 | 0 | 90
4163 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-1 of Bamanagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000672/2024-2025 | 607-AE-I-SMD | 16/04/2024 | 15 | KUNDU ELECTRICAL ENTERPRISE | 0.89 | 0 | 100
4164 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-2 of Bamanagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/12733] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001797/2024-2025 | 1054-AE-II-SMD | 20/08/2024 | 15 | KUNDU ELECTRICAL ENTERPRISE | 0.9 | 0 | 100
4165 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Bijoyrampur having village with maximum 97 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001718/2022-2023 | 11628/AD | 18/02/2023 | 60 | DEV AND COMPANY | 32.52 | 0 | 0
4166 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000867/2023-2024 | 774/AD | 03/02/2024 | 0 | Resource Division | 0.6 | 0 | 0
4167 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Bijoyrampur Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000602/2022-2023 | 680/SMD | 10/03/2023 | 90 | SARKAR ELECTRICAL | 8.84 | 0 | 0
4168 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Harendragnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000048/2023-2024 | 33/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4169 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile andile cap upto pedestal at Harendranagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000277/2023-2024 | 1427/AD | 13/07/2023 | 45 | SUPRITI ENTERPRISE | 32 | 0 | 0
4170 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000335/2022-2023 | 4065/AD | 18/08/2022 | 30 | M/S MODINA ENTERPRISE | 19.21 | 0 | 40
4171 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000336/2022-2023 | 4066/AD | 18/08/2022 | 867 | M/S. PARAMESWAR ENTERPRISE | 12.68 | 0 | 100
4172 | Alipore Division | Kakdwip Sub-Division | Laying distribution systemfor Providing Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000337/2022-2023 | 4067/AD | 18/08/2022 | 21 | M/S. MOYNA ENTERPRISE | 7.49 | 0 | 100
4173 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Harendranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000343/2022-2023 | 4070/AD | 18/08/2022 | 45 | AQUATECH ENGINEER | 37.06 | 0 | 0
4174 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (HARENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000501/2022-2023 | 2494/AD | 27/06/2022 | 45 | LEMNISCATE | 4.71 | 0 | 100
4175 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000783/2022-2023 | 6537/AD | 11/11/2022 | 300 | SUPRITI ENTERPRISE | 371.44 | 0 | 20
4176 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000945/2023-2024 | 2978/AD | 26/09/2023 | 45 | C L B SYNDICATE | 27.65 | 0 | 0
4177 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000947/2023-2024 | 2979/AD | 26/09/2023 | 30 | DEBIKA CONSTRUCTION | 9.52 | 0 | 0
4178 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Harendranagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001008/2023-2024 | 512/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.72 | 0 | 100
4179 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2021 to 31.01.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001331/2021-2022 | 456/KSD | 29/07/2021 | 184 | PIKASU BOSE | 2.4 | 0 | 100
4180 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2022 to 31.07.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001679/2021-2022 | 935/KSD | 31/01/2022 | 181 | PIKASU BOSE | 2.4 | 0 | 100
4181 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
4182 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000118/2023-2024 | 654/AD | 17/05/2023 | 0 | Resource Division | 7.62 | 0 | 0
4183 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000440/2023-2024 | 4708/AD | 18/12/2023 | 0 | Resource Division | 12.49 | 0 | 0
4184 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000807/2023-2024 | 652/AD | 30/01/2024 | 0 | Resource Division | 1.37 | 0 | 0
4185 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000990/2023-2024 | 1783/AD | 27/03/2024 | 0 | Resource Division | 27 | 0 | 0
4186 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Harendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000430/2022-2023 | 3826/SMD | 29/12/2022 | 90 | RELIABLE CONSTRUCTION | 18.86 | 0 | 0
4187 | Alipore Division | Baruipur Sub-Division | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01729/2024-2025 | BP-2024-25-793 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
4188 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at Harendrapally pump house-I | AE BSD,Assistant Engineer | Junior Engineer | BILL/00218/2024-2025 | BP-2024-25-72 | 16/05/2024 | 0 | WBSEDCL | 13.08 | 0 | 0
4189 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Harendrapally water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000528/2022-2023 | 441/SMD | 17/02/2023 | 90 | K.S.P ENTERPRISE | 13 | 0 | 0
4190 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 1230/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 20.07 | 0 | 0
4191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Harendrapally ( Atniramish, J.L-141) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 910) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000280/2022-2023 | 1842/SWD-I | 11/11/2022 | 900 | A. G. ENTERPRISE | 121.8 | 0 | 75
4192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of BARUIPUR Block for under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 323/SWD-I | 11/01/2024 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 20.07 | 0 | 100
4193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 324/SWD-I | 11/01/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 2.2 | 0 | 100
4194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 3674/SWD-I | 29/03/2023 | 15 | DIPALI CONSTRUCTION | 2.2 | 0 | 0
4195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000074/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 7.02 | 0 | 0
4196 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00386/2023-2024 | BP-2023-24-60 | 09/06/2023 | 0 | WBSEDCL | 4.13 | 0 | 0
4197 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Shifting of HT Line along with DTR at Bausahar(Chandneswar PH-02) Water supply scheme, under Bhangar- I Block | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01868/2024-2025 | BP-2024-25-472 | 18/11/2024 | 0 | WBSEDCL | 2.42 | 0 | 0
4198 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandaneswar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000496/2022-2023 | 298/SMD | 03/02/2023 | 90 | WEST BENGAL ENGINEERING CO. | 22.37 | 0 | 97
4199 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Chandaneswar PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002645/2023-2024 | 259/SMSD | 23/02/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.89 | 0 | 100
4200 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDANESWAR piped water supply scheme at headwork site (Dag No. 514, Khatian No. 1673, 1674, JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003, Khatian No. 1322, JL No. 117, Mouza- Bausahar), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000165/2022-2023 | 1440/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.51 | 0 | 50
4201 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12044) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000560/2024-2025 | 4233/SWD-I | 30/09/2024 | 361 | RAKHI CONSTRUCTION | 90.69 | 0 | 50
4202 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2499] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000714/2022-2023 | 3553/SWD-I | 21/03/2023 | 300 | TRISHA CONSTRUCTION | 434.18 | 0 | 50
4203 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDANESWAR PWSS at headwork site (Dag No. 514, Khatian No. 1673 & 1674 JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003 Khatian No. 1322, JL No. 117, Mouza- Bausahar) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12044] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 3570/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 50
4204 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000050/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 7.08 | 0 | 0
4205 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000218/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 15.39 | 0 | 0
4206 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00002/2023-2024 | BP-2023-24-37 | 18/05/2023 | 0 | WBSEDCL | 6.02 | 0 | 0
4207 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Biraldham Nagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000471/2022-2023 | 3942/SMD | 30/12/2022 | 90 | COOLING CARE CENTER | 9.69 | 0 | 50
4208 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at PH No.-1 of Biraldham Nagar & Jagadishpur water supply scheme under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001181/2023-2024 | 1O69/SMSD | 17/08/2023 | 10 | DITHI ENTERPRISE | 0.78 | 0 | 100
4209 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor illumination arrangement with allied works at Pump House no-1 of BIRALDHAM NAGAR W/S Scheme under SMD, PHE Dte. (Block- Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002567/2023-2024 | 870/SMSD | 11/07/2023 | 15 | COOLING CARE CENTER | 0.99 | 0 | 100
4210 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at BIRALDHAM NAGAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014396] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000127/2022-2023 | 1299/SWD-I | 14/09/2022 | 60 | M/S. ARPAN ENTERPRISE. | 10.91 | 0 | 50
4211 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for BIRALDHAM NAGAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000146/2022-2023 | 1377/SWD-I | 20/09/2022 | 30 | CAPITAL CONSTRUCTION | 40.13 | 0 | 100
4212 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at BIRALDHAM NAGAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 848) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000250/2022-2023 | 1738/SWD-I | 03/11/2022 | 90 | SUJATA CONSTRUCTION | 149.78 | 0 | 90
4213 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BIRALDHAM NAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000357/2021-2022 | 1959/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.62 | 0 | 100
4214 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Biraldham Nagar PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014396] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000790/2022-2023 | 3669/SWD-I | 29/03/2023 | 15 | CAPITAL CONSTRUCTION | 4.4 | 0 | 0
4215 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based BIRALDHAM NAGAR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12213) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000908/2023-2024 | 1207/SWD-I | 11/03/2024 | 45 | S.S. CONSULTANCY & CONSTRUCTION | 26.19 | 0 | 0
4216 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BIRALDHAM NAGAR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12213] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001076/2024-2025 | 5344/SWD-I | 30/12/2024 | 30 | SOURAV GHOSH | 15.54 | 0 | 60
4217 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000007/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 5.22 | 0 | 0
4218 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000183/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 19.84 | 0 | 0
4219 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - X) having village with maximum 198 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000794/2022-2023 | 6683/AD | 14/11/2022 | 805 | M/S. L.P. CONSTRUCTION | 55.83 | 0 | 95
4220 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-X) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001906/2022-2023 | 5670/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.55 | 0 | 0
4221 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000175/2023-2024 | 1128/AD | 22/06/2023 | 0 | Resource Division | 1.22 | 0 | 0
4222 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00521/2023-2024 | BP-2023-24-72 | 13/06/2023 | 0 | WBSEDCL | 7.31 | 0 | 0
4223 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-X) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000596/2022-2023 | 659/SMD | 06/03/2023 | 90 | DITHI ENTERPRISE | 8.94 | 0 | 100
4224 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - IV) having village with maximum 70 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000791/2022-2023 | 6679/AD | 14/11/2022 | 958 | SNEHA CONSTRUCTION | 38.95 | 0 | 80
4225 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001896/2022-2023 | 5660/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.32 | 0 | 0
4226 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000181/2023-2024 | 1134/AD | 22/06/2023 | 0 | Resource Division | 0.43 | 0 | 0
4227 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Khunkhali (Part-IV) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000585/2022-2023 | 642/SND | 02/03/2023 | 90 | KAMAKHYA ENTERPRISE | 8.8 | 0 | 100
4228 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% FHTC household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IV of Diamond Harbour-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 1450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000341/2023-2024 | 3601/AD | 25/10/2023 | 609 | CREATION CONSTRUCTION | 403.02 | 0 | 37
4229 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR with allide works at Zone - IV Diamond Harbour - II Block for Providing 100% FHTC within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Zone - IIIB, Part - A). | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000367/2023-2024 | 1568/AD | 17/07/2023 | 300 | M/S J.T. CONSTRUCTION | 253.06 | 0 | 0
4230 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 25 m.) at proposed OHR site and Land development at Mouza - Sarisha under Zone- IV of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000792/2024-2025 | 4497/AD | 11/11/2024 | 30 | SK SAKIL AHAMED | 7.52 | 0 | 0
4231 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-IV of Diamond Harbour - II Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002024/2022-2023 | 12928/AD | 21/03/2023 | 30 | MAHALAXMI CONSTRUCTION | 30.28 | 0 | 90
4232 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
4233 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000354/2023-2024 | 3218/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
4234 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000882/2023-2024 | 756/AD | 03/02/2024 | 0 | Resource Division | 16.32 | 0 | 0
4235 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
4236 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 200mm x 100mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Ramgopalpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13976) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000596/2024-2025 | 4062/AD | 01/10/2024 | 30 | S.K.GOLUI | 15.8 | 0 | 100
4237 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramgopalpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000952/2023-2024 | 2984/AD | 29/09/2023 | 45 | TIYASHA ENTERPRISE | 27.65 | 0 | 0
4238 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramgopalpur W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000953/2023-2024 | 2985/AD | 26/09/2023 | 30 | BHABASANKAR NAYAK | 9.52 | 0 | 0
4239 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ramgopalpur W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001006/2023-2024 | 511/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.73 | 0 | 100
4240 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramgopalpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001312/2022-2023 | 9895/AD | 10/01/2023 | 45 | KHAIRUL BASAR | 38.55 | 0 | 15
4241 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAMGOPALPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001343/2022-2023 | 3801/AD | 05/08/2022 | 45 | LEMNISCATE | 4.32 | 0 | 100
4242 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
4243 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000122/2023-2024 | 657/AD | 17/05/2023 | 0 | Resource Division | 9.53 | 0 | 0
4244 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000448/2023-2024 | 4714/AD | 18/12/2023 | 0 | Resource Division | 26.47 | 0 | 0
4245 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000815/2023-2024 | 660/AD | 30/01/2024 | 0 | Resource Division | 1.71 | 0 | 0
4246 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01719/2023-2024 | BP-2023-24-195 | 09/08/2023 | 0 | WBSEDCL | 4.97 | 0 | 0
4247 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramgopalpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000437/2022-2023 | 3833/SMD | 29/12/2022 | 90 | M/S. G.P ENTERPRISE | 19.19 | 0 | 0
4248 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00623/2023-2024 | BP-2023-24-86 | 14/06/2023 | 0 | WBSEDCL | 3.87 | 0 | 0
4249 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01749/2023-2024 | BP-2023-24-210 | 11/08/2023 | 0 | WBSEDCL | 12.27 | 0 | 0
4250 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000578/2022-2023 | 607/SMD | 28/02/2023 | 90 | CONCORD ENGINEERING | 19.48 | 0 | 0
4251 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of KAMARIA (ZONE-I) MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2051] [TSM/016158] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 968/SWD-I | 08/06/2023 | 300 | MANASH GHOSH | 397.59 | 0 | 0
4252 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAMARIA (I) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000361/2021-2022 | 1963/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
4253 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for KAMARIA (Zone-I) PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016158] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000504/2022-2023 | 2893/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 0 | 100
4254 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000091/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 82.6 | 0 | 0
4255 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Kuldia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000405/2022-2023 | 3803/SMD | 29/12/2022 | 90 | PADMA ENGINEERING CO. | 22.36 | 0 | 0
4256 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kuldia PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014902] | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 40/SWD-I | 06/04/2023 | 15 | MUNNA AGROTECH ENTERPRISE | 3.13 | 0 | 0
4257 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of KULDIA PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, P.H.E. Dte. (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000083/2025-2026 | 1758/SWD-I | 02/07/2025 | 60 | KALAM ENTERPRISE | 12.03 | 0 | 0
4258 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Kuldia PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 1880-SWD-I | 16/11/2022 | 561 | MUNNA AGROTECH ENTERPRISE | 30.02 | 0 | 38
4259 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "KULDIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 419/SWD-I | 20/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 0 | 0
4260 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for Kuldia PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000422/2024-2025 | 3750/SWD-I | 28/08/2024 | 45 | J. ENTERPRISE | 50.01 | 0 | 0
4261 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of KULDIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1615] (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000583/2024-2025 | 4343/SWD-I | 08/10/2024 | 365 | I.S ENTERPRISE | 372.46 | 0 | 0
4262 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000200/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 18.19 | 0 | 0
4263 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00009/2023-2024 | BP-2023-24-32 | 18/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
4264 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00519/2023-2024 | BP-2023-24-69 | 13/06/2023 | 0 | WBSEDCL | 5.49 | 0 | 0
4265 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01994/2023-2024 | BP-2023-24-225 | 31/08/2023 | 0 | WBSEDCL | 5.98 | 0 | 0
4266 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Khodahati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000304/2022-2023 | 445/SMD | 17/02/2023 | 783 | BARISAL TRADING CO. | 25.92 | 0 | 100
4267 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Installation of LED board at PH No-1&2 of Khodahati water supply scheme under South 24-pgs Mechanical Division, PHE Dte. [Block- Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002564/2023-2024 | .1465/SMSD | 01/12/2023 | 15 | KARTICK BAL | 0.78 | 0 | 100
4268 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Khodahati W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002711/2023-2024 | 1404/SMSD | 17/11/2023 | 15 | BARISAL TRADING CO. | 0.94 | 0 | 100
4269 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Khodahati W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002712/2023-2024 | 1405/SMSD | 17/11/2023 | 15 | BARISAL TRADING CO. | 0.94 | 0 | 100
4270 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR KHODAHATI PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016076) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000356/2022-2023 | 2263/SWD_I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 0 | 100
4271 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KHODAHATI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2039] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 2961/SWD-I | 16/02/2023 | 1050 | G.B. CONSTRUCTION AND CO. | 472.39 | 0 | 20
4272 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Temporary approach road construction for entering H/W Site of KHODAHATI Pipe water supply scheme in Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I,PHE.Dte. (TSM/016076) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000536/2023-2024 | 2141/SWD-I | 31/08/2023 | 7 | SAHI MASUM | 0.97 | 0 | 100
4273 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KHODAHATI PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13772] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000718/2022-2023 | 3560/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 100
4274 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Walls and others allied works at headwork site and 2nd Tubewell site of KHODAHATI PWSS within Sonarpur Block "KHODAHATI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13772) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 1300/SWD-I | 15/03/2024 | 45 | G.B. CONSTRUCTION AND CO. (DUMDUM) | 62.99 | 0 | 0
4275 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000024/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 9.54 | 0 | 0
4276 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000235/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.6 | 0 | 0
4277 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-II of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 2180] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000264/2023-2024 | 3668/AD | 31/10/2023 | 720 | PARAMESWAR CHOWDHURY | 271.31 | 0 | 95
4278 | Alipore Division | Diamond Harbour Sub-Division | Construction of community tank in different Primary and High Schools under Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000825/2022-2023 | 209/DHSD | 02/08/2022 | 45 | B. MOOKHERJEE | 4.22 | 0 | 0
4279 | Alipore Division | Diamond Harbour Sub-Division | Restoration and laying of parallel line by UPVC pipes in distribution system at Falta Zone-II for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Node Point- 223 to 224,305 to 299,249 to 290, 248 to 314, 314 to 335, 290 to 305, 305 to 312, 312 to 337, 337 to 339, 339 to 343, 343 to 345, 345 to 350) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001151/2023-2024 | 3197/AD | 04/10/2023 | 45 | ADITYA HAZRA | 54.35 | 0 | 100
4280 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001536/2023-2024 | 437/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4281 | Alipore Division | Diamond Harbour Sub-Division | Extension of distribution pipeline at Chandpala Anantharampur & Brihaspatipur Mouza under Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001653/2021-2022 | 458/DHSD | 15/03/2022 | 15 | PEECON | 3.72 | 0 | 100
4282 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000438/2023-2024 | 3623/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
4283 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000847/2023-2024 | 785/AD | 03/02/2024 | 0 | Resource Division | 1.11 | 0 | 0
4284 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gayadham PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000187/2024-2025 | 923/AD | 05/03/2025 | 60 | M/S B. ENTERPRISE | 53.26 | 0 | 0
4285 | Alipore Division | Kakdwip Sub-Division | Construction of concrete Y junction for laying pipe line to provide FHTC at Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13802) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000194/2024-2025 | 2554/AD | 18/06/2024 | 45 | M/S B. ENTERPRISE | 37.27 | 0 | 10
4286 | Alipore Division | Kakdwip Sub-Division | Laying D.I. Pipe for providing FHTC, Road Restoration and Y junction for Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. ( (SM/13802) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000502/2024-2025 | 3605/AD | 06/09/2024 | 148 | M/S PARAMESWAR CHOWDHURY | 13.82 | 0 | 100
4287 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAKHASKHALI PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001037/2022-2023 | 3671/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.52 | 0 | 100
4288 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Rakhaskhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001055/2023-2024 | 3374/AD | 11/10/2023 | 45 | KHOKAN MONDAL | 33.28 | 0 | 100
4289 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Rakhaskhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001056/2023-2024 | 3375/AD | 11/10/2023 | 30 | M/S. SONAMONI ENTERPRISE | 11.75 | 0 | 100
4290 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001273/2022-2023 | 9585/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
4291 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Rakhaskhali Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1018] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002061/2022-2023 | 13003/AD | 23/03/2023 | 741 | M/S B. ENTERPRISE | 259.34 | 0 | 100
4292 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
4293 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000101/2023-2024 | 547/AD | 12/05/2023 | 0 | Resource Division | 9.16 | 0 | 0
4294 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000506/2023-2024 | 4946/AD | 22/12/2023 | 0 | Resource Division | 24.05 | 0 | 0
4295 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01114/2023-2024 | BP-2023-24-161 | 24/07/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
4296 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rakhaskhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000368/2022-2023 | 3772/SMD | 29/12/2022 | 90 | SHIVAM ENTERPRISE | 21.42 | 0 | 100
4297 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at PH-1&2 of Rakhaskhali W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.[Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001789/2023-2024 | .1032/AE-I/SMD | 20/09/2023 | 15 | KUNAL ENTERPRISE | 0.78 | 0 | 100
4298 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000011/2025-2026 | 1702/AD | 08/04/2025 | 45 | PRANABANANDA CONSTRUCTION | 5.43 | 0 | 0
4299 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Chandipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13812) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000217/2024-2025 | 2600/AD | 19/06/2024 | 30 | LASKAR ENTERPRISE | 9.1 | 0 | 100
4300 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000398/2023-2024 | 1873/AD | 01/08/2023 | 45 | M/S SUNITY ENTERPRISE | 11.53 | 0 | 70
4301 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000399/2023-2024 | 1874/AD | 01/08/2023 | 45 | C.S. CONSTRUCTION | 11.18 | 0 | 100
4302 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000400/2023-2024 | 1899/AD | 01/08/2023 | 45 | M/S. BRINDABAN DAS & SONS | 10.77 | 0 | 70
4303 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000401/2023-2024 | 1900/AD | 01/08/2023 | 609 | DEV AND COMPANY | 9.51 | 0 | 40
4304 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13812) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000662/2024-2025 | 4211/AD | 23/10/2024 | 218 | SARADA CONSTRUCTION | 92.01 | 0 | 61
4305 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-E) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001031/2023-2024 | 3315/AD | 07/10/2023 | 45 | SARKAR ENTERPRISE | 10 | 0 | 60
4306 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-G) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001032/2023-2024 | 3316/AD | 07/10/2023 | 45 | JHARNA ENTERPRISE | 30.86 | 0 | 80
4307 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (CHANDIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001055/2022-2023 | 4145/AD | 19/08/2022 | 45 | LEMNISCATE | 4.22 | 0 | 100
4308 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001421/2023-2024 | 4601/AD | 14/12/2023 | 472 | MAA BHABANI CONSTRUCTION (DUM DUM) | 47.31 | 0 | 70
4309 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001774/2022-2023 | 12047/AD | 27/02/2023 | 30 | M/S MAITY CONSTRUCTION | 19.26 | 0 | 100
4310 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
4311 | Alipore Division | Kakdwip Sub-Division | Inter connection between two nos. Tubewell for Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002548/2024-2025 | 817/AD | 27/02/2025 | 45 | PAUL CONSTRUCTION | 13.31 | 0 | 0
4312 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002555/2024-2025 | 819/AD | 27/02/2025 | 45 | M/S. GANGA ENTERPRISE | 9.54 | 0 | 0
4313 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000271/2023-2024 | 3070/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4314 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000466/2023-2024 | 4726/AD | 18/12/2023 | 0 | Resource Division | 38.66 | 0 | 0
4315 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000595/2023-2024 | 94/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
4316 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000813/2023-2024 | 658/AD | 30/01/2024 | 0 | Resource Division | 9.62 | 0 | 0
4317 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR001000/2023-2024 | 1799/AD | 27/03/2024 | 0 | Resource Division | 25.73 | 0 | 0
4318 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/01066/2023-2024 | BP-2023-24-147 | 24/07/2023 | 0 | WBSEDCL | 3.59 | 0 | 0
4319 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/05389/2023-2024 | BP-2023-24-599 | 28/03/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
4320 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Chandipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000435/2022-2023 | 3831/SMD | 29/12/2022 | 854 | SEN ENTERPRISE | 11.11 | 0 | 90
4321 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Chandipur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000582/2024-2025 | 632-AE-I-SMD | 23/04/2024 | 15 | SEN ENTERPRISE | 0.89 | 0 | 100
4322 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01107/2023-2024 | BP-2023-24-148 | 24/07/2023 | 0 | WBSEDCL | 8.81 | 0 | 0
4323 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jaykrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000300/2022-2023 | 449/SMD | 17/02/2023 | 90 | S. DUTTA | 23.38 | 0 | 40
4324 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Jaykrishnapur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002349/2023-2024 | 1526/SMSD | 14/12/2023 | 15 | S. DUTTA | 0.89 | 0 | 100
4325 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Jaykrishnapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002383/2023-2024 | 1525/SMSD | 14/12/2023 | 15 | S. DUTTA | 0.58 | 0 | 0
4326 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway,Drain, Development of Land & others allied works at HW Site of " JAYKRISHNAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13514) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 2656/SWD-I | 07/06/2024 | 540 | SUSHANTA MANDAL | 46.28 | 0 | 50
4327 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Jaykrishnapur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015398] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000335/2022-2023 | 2075/SWD-I | 01/12/2022 | 30 | CAPITAL CONSTRUCTION | 30.03 | 0 | 58
4328 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JAYKRISHNAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13514] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 2811/SWD-I | 02/02/2023 | 15 | CAPITAL CONSTRUCTION | 3.13 | 0 | 15
4329 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of JAYKRISHNAPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13514) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001142/2024-2025 | 312/SWD-I | 28/01/2025 | 60 | AFRINA ENTERPRISE | 9.61 | 0 | 0
4330 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 11.94 | 0 | 0
4331 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000233/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.58 | 0 | 0
4332 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Char Baidyarabad W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000855/2022-2023 | 6994/AD | 19/11/2022 | 30 | PAPPU ENTERPRISE | 19.48 | 0 | 95
4333 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001838/2021-2022 | 660/CSD | 12/08/2021 | 15 | HORIZEN | 3.92 | 0 | 100
4334 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001839/2021-2022 | 670/CSD | 17/08/2021 | 15 | HORIZEN | 3.04 | 0 | 100
4335 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000388/2023-2024 | 329/AD | 19/01/2024 | 0 | Resource Division | 12.11 | 0 | 0
4336 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Satyadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000638/2023-2024 | 2466/AD | 24/08/2023 | 90 | PIKASU BOSE | 52.93 | 0 | 100
4337 | Alipore Division | Kakdwip Sub-Division | Construction of Approach Road with Box Culvert and Allied works at Satyadaspur Water Supply OHR Site, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13965) (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000902/2024-2025 | 4751/AD | 23/11/2024 | 182 | PIKASU BOSE | 27.02 | 0 | 100
4338 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Satyadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000934/2023-2024 | 277(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4339 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Satyadaspur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000998/2023-2024 | 505/KSD | 03/10/2023 | 7 | FORTUNE ENGINEERING | 3.37 | 0 | 100
4340 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001184/2023-2024 | 3945/AD | 17/11/2023 | 20 | SARADA CONSTRUCTION | 24.59 | 0 | 0
4341 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001276/2022-2023 | 9588/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
4342 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation Water Supply Scheme (SATYADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001326/2022-2023 | 3309/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.98 | 0 | 100
4343 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 450 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001979/2023-2024 | 438/AD | 24/01/2024 | 30 | SARADA CONSTRUCTION | 30.53 | 0 | 100
4344 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002040/2023-2024 | 522/AD | 25/01/2024 | 45 | A.R.CONSTRUCTION | 33.21 | 0 | 0
4345 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
4346 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002152/2023-2024 | 799/AD | 05/02/2024 | 391 | NARAYAN ENTERPRISE | 11.58 | 0 | 100
4347 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000100/2023-2024 | 546/AD | 12/05/2023 | 0 | Resource Division | 8.14 | 0 | 0
4348 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000296/2023-2024 | 3091/AD | 28/09/2023 | 0 | Resource Division | 23.44 | 0 | 0
4349 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000757/2023-2024 | 592/AD | 29/01/2024 | 0 | Resource Division | 2.59 | 0 | 0
4350 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/03410/2023-2024 | BP-2023-24-375 | 13/11/2023 | 0 | WBSEDCL | 10.4 | 0 | 0
4351 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Satyadaspur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000369/2022-2023 | 3773/SMD | 29/12/2022 | 824 | S.K. ENTERPRISE | 19.67 | 0 | 30
4352 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at PH No-2 of Satyadaspur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13965) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000754/2025-2026 | 304-AE-II-SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 100
4353 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at PH No-1 of Satyadaspur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13965) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000755/2025-2026 | 303-AE-II-SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 100
4354 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 of Satyadaspur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001898/2023-2024 | 1183/SMD | 22/03/2024 | 21 | S.K. ENTERPRISE | 21.68 | 0 | 100
4355 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Hansuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 773/SMD | 16/03/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 22.36 | 0 | 0
4356 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of HANSURI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2556] [TSM/015218] | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 269/SWD-I | 24/04/2023 | 649 | TUMPA ASSOCIATES | 427.98 | 0 | 55
4357 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for HANSURI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13985][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000684/2022-2023 | 3483/SWD-I | 15/03/2023 | 30 | K.P.D. & SONS. | 31.76 | 0 | 0
4358 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | Assistant Engineer | Junior Engineer | ORD/000743/2024-2025 | 4641/SWD-I | 14/11/2024 | 90 | M/S ESSENCE J.V. CONSTRUCTION CO. | 263.03 | 0 | 0
4359 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "HANSURI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000893/2022-2023 | 403/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 100
4360 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [WB04G4525] [SM/13985] [w.e.f. 01/12/2024 to 31/05/2025] | Assistant Engineer | Junior Engineer | ORD/001110/2024-2025 | 4874/SWD-I | 28/11/2024 | 182 | AJAY KUMAR | 0.86 | 0 | 11
4361 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 25.67 | 0 | 0
4362 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - II) having village with maximum 70 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000790/2022-2023 | 6645/AD | 14/11/2022 | 90 | M/S. R.M. CONSTRUCTION | 42.42 | 0 | 80
4363 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001911/2022-2023 | 5151/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.35 | 0 | 0
4364 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000179/2023-2024 | 1132/AD | 22/06/2023 | 0 | Resource Division | 0.43 | 0 | 0
4365 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00388/2023-2024 | BP-2023-24-57 | 09/06/2023 | 0 | WBSEDCL | 6.15 | 0 | 0
4366 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Khunkhali (Part-II) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000583/2022-2023 | 640/SMD | 02/03/2023 | 90 | M/S. BABUSONA ENTERPRISE | 8.81 | 0 | 100
4367 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-VI of Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000564/2021-2022 | 2702/AD | 01/10/2021 | 180 | MALAY KANTI DEY | 125.75 | 0 | 47
4368 | Alipore Division | Diamond Harbour Sub-Division | Functional Household Tap Connection (FHTC) for balance portion in Diamond Harbour-II Zone-VI (Khordanahala) for providing 100% coverage for Swajal Gram activity under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas, Block Falta, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000750/2022-2023 | 6181/AD | 01/11/2022 | 30 | ADITYA HAZRA | 46.66 | 0 | 96
4369 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Marjyada water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000416/2022-2023 | 3813/SMD | 29/12/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 23.38 | 0 | 0
4370 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MARJYADA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/015217] (2nd Call) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000119/2023-2024 | 531/SWD-I | 11/05/2023 | 512 | SHANTI CONSTRUCTION | 47.45 | 0 | 34
4371 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based MARJYADA piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000317/2024-2025 | 3250/SWD-I | 19/07/2024 | 60 | ALOKE KUMAR SARKAR | 46.04 | 0 | 0
4372 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Concrete work for Repairing of Road damaged by Laying of pipe line for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/14662) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000673/2024-2025 | 4399/SWD-I | 23/10/2024 | 60 | ARNAB KUMAR SARKAR | 16.78 | 0 | 100
4373 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "MARJYADA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000880/2022-2023 | 414/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
4374 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000170/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 29.04 | 0 | 0
4375 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. (Phase-II) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001393/2022-2023 | 10865/AD | 04/02/2023 | 90 | TIRUPATI ENTERPRISES | 298.7 | 0 | 85
4376 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000883/2023-2024 | 757/AD | 03/02/2024 | 0 | Resource Division | 11.24 | 0 | 0
4377 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000923/2023-2024 | 1265/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4378 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system with allied works to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III B (Dostipur) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-2330]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000306/2023-2024 | 1509/AD | 15/07/2023 | 720 | M/S A.K. GHATAK | 455.49 | 0 | 70
4379 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone- III(B) (Dostipur) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001000/2022-2023 | 288/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 2.83 | 0 | 0
4380 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IIIB at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002393/2024-2025 | 638/AD | 18/02/2025 | 30 | K.P. CONSTRUCTION | 7.98 | 0 | 0
4381 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIB at Falta block for providing balance pipe lying works, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002472/2024-2025 | 720/AD | 21/02/2025 | 30 | M/S A.K. GHATAK | 20.23 | 0 | 0
4382 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000137/2022-2023 | 20/AD | 05/04/2023 | 0 | Resource Division | 12.74 | 0 | 0
4383 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000184/2023-2024 | 1278/AD | 05/07/2023 | 0 | Resource Division | 12.74 | 0 | 0
4384 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000428/2023-2024 | 3622/AD | 30/10/2023 | 0 | Resource Division | 14.35 | 0 | 0
4385 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000621/2023-2024 | 282/AD | 15/01/2024 | 0 | Resource Division | 0.79 | 0 | 0
4386 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VI at Boria of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-2939] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000090/2023-2024 | 501/AD | 11/05/2023 | 874 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 634.45 | 0 | 70
4387 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc. under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000333/2025-2026 | 270/DHSD | 16/06/2025 | 45 | M/S ROY CONSTRUCTION | 3.39 | 0 | 0
4388 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation of different capacities for the proposed R.C.C. Over Head Reservoir at Diamond Harbour-I Block, (Zone-VI, OHR Size-600 Cum., Mouza - Boria) and (Zone-VIII, OHR Size-600 Cum. Mouza - Paschim Gansingber) under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000361/2022-2023 | 197/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
4389 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000134/2022-2023 | 31/AD | 05/04/2023 | 0 | Resource Division | 7.86 | 0 | 0
4390 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000229/2023-2024 | 2201/AD | 10/08/2023 | 0 | Resource Division | 10.69 | 0 | 0
4391 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000351/2023-2024 | 3215/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
4392 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000424/2023-2024 | 3625/AD | 30/10/2023 | 0 | Resource Division | 15.4 | 0 | 0
4393 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000610/2023-2024 | 272/AD | 15/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
4394 | Alipore Division | Baruipur Sub-Division | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01695/2024-2025 | BP-2024-25-784 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0
4395 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Haral ( Zone-28) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 942/SMD | 04/04/2023 | 90 | M.S.ENTERPRISE | 39.1 | 0 | 0
4396 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Auliapur to Uttarbhag road,Permanent rsetoration work for 13000 mtr of trench (0.00 Km-5.0 Km(L/S),5.00Km-7.75 Km(B/S), 7.75 km-9.30 Km(R/S), 9.30 Km-9.55 Km(B/S) & 9.55 Km-10.0 Km) Total trench length:13000 mtr cause due to pipe laying work of PHED under South 24 Parganas Division, PWD in the district of South 24 Parganas-During the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00541/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 107.89 | 0 | 0
4397 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Three nos.) at HARAL piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14859) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 935/SWD-I | 07/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 13.59 | 0 | 0
4398 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of HARAL MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2089] [TSM/018361] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 98/SWD-I | 10/04/2023 | 90 | SAMSUL ENTERPRISE | 398.11 | 0 | 90
4399 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based HARAL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14859) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000229/2024-2025 | 2646/SWD-I | 07/06/2024 | 45 | SAMSUL ENTERPRISE | 50.8 | 0 | 0
4400 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based HARAL Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000921/2022-2023 | 1173/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 3.08 | 0 | 100
4401 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000147/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 16.72 | 0 | 0
4402 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01103/2023-2024 | BP-2023-24-145 | 24/07/2023 | 0 | WBSEDCL | 2.73 | 0 | 0
4403 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01752/2023-2024 | BP-2023-24-208 | 11/08/2023 | 0 | WBSEDCL | 3.33 | 0 | 0
4404 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at Pump house no-2 of Hariharpur (Part-II) water supply scheme (Baruipur Block). | AE BSD,Assistant Engineer | Junior Engineer | BILL/01807/2024-2025 | BP-2024-25-444 | 07/10/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
4405 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Hariharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 940/SMD | 04/04/2023 | 90 | K.S.P ENTERPRISE | 11.18 | 0 | 0
4406 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Hariharpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14860) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001175/2024-2025 | 73/SMSD | 17/01/2025 | 15 | SRI KRISHNA NIRMAN | 0.89 | 0 | 100
4407 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Augmentation of Hariharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001910/2023-2024 | 1194/SMD | 22/03/2024 | 528 | SRI KRISHNA NIRMAN | 10.9 | 0 | 80
4408 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of HARIHARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2142] [TSM/017835] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 120/SWD-I | 12/04/2023 | 1020 | SRI RAM CONSTRUCTION | 464.05 | 0 | 70
4409 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipeline protection work, platform fo FHTC, restoration of road after laying of pipeline, development of land and other allied works for Ground water based HARIHARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/14860) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000374/2024-2025 | 3547/SWD-I | 09/08/2024 | 495 | SRI RAM CONSTRUCTION | 77.29 | 0 | 30
4410 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of HARIHARPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000508/2021-2022 | 1910\SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 0 | 100
4411 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for HARIHARPUR PWSS of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017835] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000558/2022-2023 | 3050/SWD-I | 20/02/2023 | 30 | DEV & COMPANY (EMAIL ID- DEVANDCOMPANYKOL@GMAIL.COM) | 31.8 | 0 | 100
4412 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Hariharpara Piped Water Supply Scheme to accommodate FHTC in Baruipuri Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district | AE BSD,Assistant Engineer | Junior Engineer | ORD/000988/2022-2023 | 1485/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.99 | 0 | 100
4413 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000138/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 48.41 | 0 | 0
4414 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including Construction of 1 no. 250cum capcity OHR and 01 no 400 cum capacity OHR to extend the benefit 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Mangarajpur & Zone-V at Atkrishnarampur of Diamond harbour - I block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000487/2023-2024 | 4927/AD | 22/12/2023 | 831 | PRASUN ENTERPRISE | 972.76 | 0 | 10
4415 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XI of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001054/2022-2023 | 307/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.62 | 0 | 0
4416 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-XI (Mongrajpur OHR Size-250) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002091/2022-2023 | 325/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
4417 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000126/2022-2023 | 29/AD | 05/04/2023 | 0 | Resource Division | 8.2 | 0 | 0
4418 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000239/2023-2024 | 2200/AD | 10/08/2023 | 0 | Resource Division | 8.21 | 0 | 0
4419 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000349/2023-2024 | 3213/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4420 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000895/2023-2024 | 749/AD | 03/02/2024 | 0 | Resource Division | 10.37 | 0 | 0
4421 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - I) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000655/2022-2023 | 6677/AD | 14/11/2022 | 60 | M/S P. B. CONSTRUCTION | 49.13 | 0 | 88
4422 | Alipore Division | Canning Sub-division | Laying of pipe line at Moukhali High School and Moukhali Jr. High School (Girls) from Moukhali-Kumarkhali (Zone-I) R.O. Plant at Moukhali-Kumarkhali W/S Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000865/2022-2023 | 840/CSD | 12/08/2022 | 30 | SUJIT KUMAR GHOSH | 3.43 | 0 | 0
4423 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Moukhali-Kumarkhali (Zone - I to VI), under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001380/2022-2023 | 1062/CSD | 14/12/2022 | 40 | M/S. M.K. NASKAR & CONSTRUCTION | 0.96 | 0 | 0
4424 | Alipore Division | Canning Sub-division | Surging of 02 (two) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Moukhali-Kumarkhali W/S Scheme (Zone-I, TW-1) & (Zone-II, TW-1) under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001637/2023-2024 | 1048/CSD | 04/10/2023 | 30 | ASHIM SHIL | 0.91 | 0 | 100
4425 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001897/2022-2023 | 5661/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
4426 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000166/2023-2024 | 1119/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
4427 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00382/2023-2024 | BP-2023-24-52 | 09/06/2023 | 0 | WBSEDCL | 3.39 | 0 | 0
4428 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-I) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000586/2022-2023 | 643/SMD | 02/03/2023 | 90 | SUDIP PRADHAN | 8.82 | 0 | 100
4429 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00003/2023-2024 | BP-2023-24-36 | 18/05/2023 | 0 | WBSEDCL | 2.4 | 0 | 0
4430 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01106/2023-2024 | BP-2023-24-149 | 24/07/2023 | 0 | WBSEDCL | 6.21 | 0 | 0
4431 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Jagadishpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000472/2022-2023 | 3943/SMD | 30/12/2022 | 90 | BIDYUT KUMAR MUKHERJEE | 10.7 | 0 | 80
4432 | S24 Pgns Mechanical | South 24Pgs.Mechanical Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2, of Jagadishpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | Assistant Engineer | Junior Engineer | ORD/000929/2023-2024 | 2905/SMD | 29/08/2023 | 90 | KARUNAMOY ENGINEERING | 0 | 0 | 0
4433 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.26] | Assistant Engineer | Junior Engineer | BILL/00486/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.71 | 0 | 0
4434 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for JAGADISHPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000199/2022-2023 | 1547/SWD-I | 12/10/2022 | 30 | M/S SABITA ENTERPRISE | 40.02 | 0 | 100
4435 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of 02 (Two) nos. chlorination room at JAGADISHPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000200/2022-2023 | 1548/SWD-I | 12/10/2022 | 960 | NARAYAN ENTERPRISE | 10.93 | 0 | 50
4436 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at JAGADISHPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 859) | Assistant Engineer | Junior Engineer | ORD/000325/2022-2023 | 2024/SWD-I | 29/11/2022 | 906 | A ONE CONSTRUCTION | 149.52 | 0 | 90
4437 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of JAGADISHPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000356/2021-2022 | 1960/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.62 | 0 | 100
4438 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for JAGADISHPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000450/2023-2024 | 2105/SWD-I | 30/08/2023 | 15 | M/S SABITA ENTERPRISE | 4.4 | 0 | 0
4439 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000106/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 28.97 | 0 | 0
4440 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - VII) having village with maximum 345 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000600/2022-2023 | 6680/AD | 14/11/2022 | 60 | SEKH CONSTRUCTION | 65.01 | 0 | 80
4441 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Moukhali-Kumarkhali (Zone - VII to XII), under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001381/2022-2023 | 1063/CSD | 14/12/2022 | 40 | M/S. MIHIR KUMAR NASKAR | 0.96 | 0 | 0
4442 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001903/2022-2023 | 5667/AD. | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.61 | 0 | 0
4443 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Augmentation of Moukhali-Kumarkhali W/S Scheme (Part-VII), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002110/2023-2024 | 1219/CSD | 21/11/2023 | 30 | S. DAS ENTERPRISE | 4.51 | 0 | 100
4444 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000172/2023-2024 | 1125/AD | 22/06/2023 | 0 | Resource Division | 2.13 | 0 | 0
4445 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01509/2023-2024 | BP-2023-24-179 | 02/08/2023 | 0 | WBSEDCL | 6.22 | 0 | 0
4446 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-VII) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000593/2022-2023 | 657/SMD | 06/03/2023 | 90 | BHUNIA BUILDERS | 8.92 | 0 | 100
4447 | Alipore Division | Diamond Harbour Sub-Division | Inter connection due to increase of additional length from existing Tubewells to OHR site for improvement of water within Zone No-I of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000814/2024-2025 | 4500/AD | 11/11/2024 | 180 | THE TOWER CONSTRUCTION | 11.52 | 0 | 100
4448 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-I of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001535/2023-2024 | 436/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4449 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-I of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 3450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001942/2022-2023 | 12790/AD | 16/03/2023 | 726 | M/S. S.S. ENTERPRISE | 502.63 | 0 | 62
4450 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000436/2023-2024 | 3618/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
4451 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000619/2023-2024 | 280/AD | 15/01/2024 | 0 | Resource Division | 8.93 | 0 | 0
4452 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000735/2023-2024 | 569/AD | 27/01/2024 | 0 | Resource Division | 38.84 | 0 | 0
4453 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000925/2023-2024 | 1267/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4454 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Augmentation of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000151/2024-2025 | 2489/AD | 14/06/2024 | 420 | J.K. CONSTRUCTION | 45.71 | 0 | 0
4455 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Radhakrishnapur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000400/2024-2025 | 3183/AD | 31/07/2024 | 30 | SOMNATH ENTERPRISE | 11.72 | 0 | 0
4456 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000553/2024-2025 | 3782/AD | 18/09/2024 | 360 | J.K. CONSTRUCTION | 73.8 | 0 | 0
4457 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (RADHAKRISHNAPUR) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001340/2022-2023 | 3802/AD | 05/08/2022 | 45 | VOYAGER | 5.03 | 0 | 100
4458 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001476/2023-2024 | 4685/AD | 18/12/2023 | 30 | SARADA CONSTRUCTION | 25.38 | 0 | 100
4459 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Radhakrishnapur Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001578/2021-2022 | 6958/AD | 29/03/2022 | 30 | SIMPLEX DRILLING CO. | 23.04 | 0 | 100
4460 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Radhakrishnapur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 300 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002030/2022-2023 | 12997/AD | 23/03/2023 | 990 | M. MUKHERJEE | 274.08 | 0 | 60
4461 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
4462 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 1st Tubewell site of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002187/2024-2025 | 2068/KSD | 28/12/2024 | 20 | PIJUSH KANTI TRIPATHI | 4.14 | 0 | 0
4463 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000340/2023-2024 | 3155/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4464 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000514/2023-2024 | 4832/AD | 20/12/2023 | 0 | Resource Division | 24.77 | 0 | 0
4465 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000530/2023-2024 | 13/AD | 02/01/2024 | 0 | Resource Division | 1.78 | 0 | 0
4466 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000688/2023-2024 | 458/AD | 24/01/2024 | 0 | Resource Division | 3.12 | 0 | 0
4467 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Radhakrishnapur W/S Scheme PH-3 Application No:- 1007921881 Reference ID:- 106663997 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01134/2024-2025 | BP-2024-25-226 | 08/08/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
4468 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Radhakrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000351/2022-2023 | 3755/SMD | 29/12/2022 | 1185 | BHUNIA BUILDERS | 11.21 | 0 | 90
4469 | Alipore Division | Baruipur Sub-Division | Road restoration for Ramnagar Bazar to Matiar Dhali House. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01694/2024-2025 | BP-2024-25-783 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.08 | 0 | 0
4470 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04625/2023-2024 | BP-2023-24-484 | 07/02/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
4471 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Brindakhali-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000478/2022-2023 | 3949/SMD | 30/12/2022 | 823 | DEBJYOTI BASU | 11.19 | 0 | 80
4472 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (1 No.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-II) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1182) [TSM/015225] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000061/2023-2024 | 365/SWD-I | 27/04/2023 | 888 | M/S V.P. JAIN | 335.23 | 0 | 94
4473 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13310] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000389/2024-2025 | 3607/SWD-I | 14/08/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 0 | 100
4474 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BRINDAKHALI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000510/2021-2022 | 1943/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 0 | 100
4475 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000561/2022-2023 | 3057/SWD-I | 21/02/2023 | 30 | M/S MONDAL ENTERPRISE | 15.88 | 0 | 0
4476 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000128/2022-2023 | 3387/SWD-I | 10/03/2023 | 0 | Resource Division | 7.28 | 0 | 0
4477 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000187/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 1.46 | 0 | 0
4478 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Paschim Surendranagar Zone-II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (Part-B) [No. of FHTC = 90] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000618/2023-2024 | 2316/AD | 17/08/2023 | 60 | L.N. ENTERPRISE | 99.93 | 0 | 100
4479 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-II (Part - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000929/2023-2024 | 274(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4480 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-II (Part - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000931/2023-2024 | 275(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4481 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PASCHIM SURENDRANAGAR (ZONE-II) (PART I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001042/2022-2023 | 3674/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.18 | 0 | 100
4482 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-II (Part- I and II) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001207/2023-2024 | 4084/AD | 23/11/2023 | 405 | M/S KRISHNA MONDAL | 27.88 | 0 | 70
4483 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-II (Part- I and II) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001208/2023-2024 | 4085/AD | 23/11/2023 | 30 | RAJDEEP ENTERPRISE | 9.74 | 0 | 0
4484 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Paschim Surendranagar (Zone-II) (Part-I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001271/2022-2023 | 9583/AD | 03/01/2023 | 45 | PRITI ENTERPRISE | 38.53 | 0 | 100
4485 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 1st Tubewell site for Paschim Surendranagar Zone-II (Part-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13873) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001297/2024-2025 | 1931/KSD | 20/12/2024 | 25 | G.G. PROJECT | 4.33 | 0 | 0
4486 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 2nd Tubewell site for Paschim Surendranagar Zone-II (Part-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13873) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001298/2024-2025 | 1932/KSD | 20/12/2024 | 25 | MANAS INFRA PROJECTS | 4.16 | 0 | 100
4487 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone - II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) [No. of FHTC = 200 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002060/2022-2023 | 13002/AD | 23/03/2023 | 300 | M/S BOSE & CO. | 280.07 | 0 | 78
4488 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
4489 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone - II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (Part-A) [No. of FHTC = 50] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003301/2024-2025 | 1993/AD | 09/04/2024 | 60 | L.N. ENTERPRISE | 28.14 | 0 | 0
4490 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000315/2023-2024 | 3124/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4491 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000453/2023-2024 | 4764/AD | 19/12/2023 | 0 | Resource Division | 49.96 | 0 | 0
4492 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000566/2023-2024 | 81/AD | 03/01/2024 | 0 | Resource Division | 1.78 | 0 | 0
4493 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000756/2023-2024 | 591/AD | 29/01/2024 | 0 | Resource Division | 2.67 | 0 | 0
4494 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000905/2023-2024 | 891/AD | 07/02/2024 | 0 | Resource Division | 0.75 | 0 | 0
4495 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000961/2023-2024 | 1695/AD | 22/03/2024 | 0 | Resource Division | 21.64 | 0 | 0
4496 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/05972/2023-2024 | BP-2023-24-645 | 30/03/2024 | 0 | WBSEDCL | 11.7 | 0 | 0
4497 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at PH1 & 2, Zone-II ( Part-I & II- Phase-B ) of Paschim Surendranagar Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000122/2024-2025 | 2290/SMD | 19/07/2024 | 286 | M/S. S.D.CONSTRUCTION | 22.21 | 0 | 90
4498 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 Zone-II for Augmentation Paschim Surendranagar water supply scheme under SMD, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000371/2022-2023 | 3775/SMD | 29/12/2022 | 90 | T.N. BANERJEE | 19.23 | 0 | 0
4499 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Augmentation of Shibpur (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000147/2024-2025 | 2485/AD | 14/06/2024 | 75 | PALCON | 51.57 | 0 | 0
4500 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying different dia. specials for Augmentation of Shibpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000148/2024-2025 | 2486/AD | 14/06/2024 | 75 | UCON (II) | 51.21 | 0 | 0
4501 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Shibpur (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000554/2024-2025 | 3783/AD | 18/09/2024 | 423 | PALCON | 42.85 | 0 | 60
4502 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000970/2023-2024 | 319/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4503 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC to all households for Augmentation of Sibpur (Zone-I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000987/2023-2024 | 3006/AD | 26/09/2023 | 30 | PALCON | 11.99 | 0 | 100
4504 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001059/2022-2023 | 3678/AD | 01/08/2022 | 45 | VOYAGER | 6.57 | 0 | 100
4505 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sibpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001279/2022-2023 | 9591/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
4506 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Shibpur (Zone- I & II)) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part - B) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001333/2024-2025 | 5417/AD | 24/12/2024 | 480 | NOVELTY CONSTRUCTION | 58.45 | 0 | 70
4507 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 608] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001859/2022-2023 | 12412/AD | 09/03/2023 | 90 | PALCON | 128.51 | 0 | 100
4508 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sibpur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002139/2023-2024 | 798/AD | 05/02/2024 | 30 | M/S BHAGABATI ENTERPRISE | 11.46 | 0 | 0
4509 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Shibpur Zone - I & II, Ghoramara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002175/2023-2024 | 954/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.61 | 0 | 100
4510 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 200 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 608] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002466/2023-2024 | 1360/AD | 06/03/2024 | 60 | UCON | 0 | 0 | 0
4511 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000336/2023-2024 | 3151/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4512 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000513/2023-2024 | 4831/AD | 20/12/2023 | 0 | Resource Division | 24.78 | 0 | 0
4513 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000531/2023-2024 | 14/AD | 02/01/2024 | 0 | Resource Division | 7.22 | 0 | 0
4514 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000685/2023-2024 | 455/AD | 24/01/2024 | 0 | Resource Division | 4.25 | 0 | 0
4515 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Shibpur W/S Scheme PH-1 Application No:- 1007642566 Reference ID:- 106542693 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/00968/2024-2025 | BP-2024-25-191 | 23/07/2024 | 0 | WBSEDCL | 6.62 | 0 | 0
4516 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Shibpur PH-2 W/ S Scheme Application No:- 1007983151 Reference ID: 106694841 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/01341/2024-2025 | BP-2024-25-276 | 22/08/2024 | 0 | WBSEDCL | 6.06 | 0 | 0
4517 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Shibpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000349/2022-2023 | 3753/SMD | 29/12/2022 | 1608 | NITESH MANAGEMENT | 22.41 | 0 | 90
4518 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-1 of Shibpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002216/2024-2025 | 1484-AE-II-SMD | 12/12/2024 | 15 | NITESH MANAGEMENT | 0.91 | 0 | 0
4519 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-2 of Shibpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002217/2024-2025 | 1485-AE-II-SMD | 12/12/2024 | 15 | NITESH MANAGEMENT | 0.91 | 0 | 0
4520 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Manasadwip (Zone-I and II) (SM/13117) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2025-2026 | 2005/AD | 28/04/2025 | 30 | LEMNISCATE | 7.21 | 0 | 100
4521 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone-I & Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000079/2023-2024 | 63/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
4522 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform, Valve Chamber etc. at different household for Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000136/2024-2025 | 2474/AD | 14/06/2024 | 60 | SWAPAN KUMAR PRADHAN | 67.89 | 0 | 0
4523 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I and II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000137/2024-2025 | 2475/AD | 14/06/2024 | 45 | SIMPLEX DRILLING CO. | 49.93 | 0 | 50
4524 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Manasadwip (Zone I & II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000139/2024-2025 | 2477/AD | 14/06/2024 | 30 | M/S. PARAMESWAR ENTERPRISE | 11.66 | 0 | 0
4525 | Alipore Division | Kakdwip Sub-Division | Laying UPVC pipe line between Nodal Point 226 to 227 and 227 to 229 of Manasadwip Water supply scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000444/2020-2021 | 830/KSD | 16/10/2020 | 45 | PIKASU BOSE | 3.55 | 0 | 5
4526 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Manasadwip Zone-II W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000591/2023-2024 | 2348/AD | 18/08/2023 | 45 | BENGAL BUILDERS | 49.7 | 0 | 100
4527 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001422/2022-2023 | 10980/AD | 07/02/2023 | 30 | ANANDA MAITY | 12.91 | 0 | 100
4528 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001461/2023-2024 | 4692/AD | 18/12/2023 | 45 | M/S KHAJABABA ENTERPRISE | 29.61 | 0 | 100
4529 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001462/2023-2024 | 4693/AD | 18/12/2023 | 45 | DIPA CHHETRI | 24.81 | 0 | 100
4530 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001463/2023-2024 | 4694/AD | 18/12/2023 | 30 | P.N. ENTERPRISE | 6.42 | 0 | 100
4531 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-H) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001464/2023-2024 | 4695/AD | 18/12/2023 | 30 | KAMALA ENTERPRISE (I) | 5.78 | 0 | 100
4532 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001465/2023-2024 | 4696/AD | 18/12/2023 | 30 | S.B. ENTERPRISE | 5.65 | 0 | 100
4533 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-J) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001466/2023-2024 | 4697/AD | 18/12/2023 | 30 | SRI DURGA ENTERPRISE | 5.48 | 0 | 100
4534 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-T) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001467/2023-2024 | 4698/AD | 18/12/2023 | 30 | AVIJIT MAITY | 9.41 | 0 | 100
4535 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-U) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001469/2023-2024 | 4699/AD | 18/12/2023 | 30 | M/S BIJALI ENTERPRISE | 15.38 | 0 | 0
4536 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001544/2022-2023 | 10981/AD | 07/02/2023 | 30 | M/S MAA BASANTI ENTERPRISE | 9.62 | 0 | 100
4537 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001545/2022-2023 | 10982/AD | 07/02/2023 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 100
4538 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001689/2023-2024 | 5115/AD | 29/12/2023 | 60 | SHYAM DEVELOPER | 44.93 | 0 | 80
4539 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001690/2023-2024 | 5116/AD | 29/12/2023 | 427 | PALCON | 46.25 | 0 | 100
4540 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-K) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001692/2023-2024 | 5117/AD | 29/12/2023 | 30 | MONDAL ENTERPRISE (JOYNAGAR) | 9.39 | 0 | 100
4541 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-M) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001783/2023-2024 | 920/KSD | 19/12/2023 | 30 | M/S B.S. ENTERPRISE | 4.64 | 0 | 100
4542 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001824/2022-2023 | 12120/AD | 01/03/2023 | 912 | BENGAL BUILDERS | 449.37 | 0 | 34
4543 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Manasadwip [Zone-I & II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001916/2021-2022 | 6554/AD | 10/03/2022 | 45 | VOYAGER | 9.82 | 0 | 95
4544 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Manasadwip (Zone I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001984/2023-2024 | 503/AD | 25/01/2024 | 432 | M/S. PRADHAN ENTERPRISE | 11.64 | 0 | 100
4545 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhaspara Zone - I & II, Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002161/2023-2024 | 950/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
4546 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002188/2024-2025 | 2069/KSD | 28/12/2024 | 20 | P.N. ENTERPRISE | 4.15 | 0 | 0
4547 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 2nd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002189/2024-2025 | 2070/KSD | 28/12/2024 | 20 | SWAPAN KUMAR PRADHAN | 2.89 | 0 | 0
4548 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 3rd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002190/2024-2025 | 2071/KSD | 28/12/2024 | 20 | P.N. ENTERPRISE | 4.21 | 0 | 0
4549 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-L) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002430/2023-2024 | 365/KSD | 19/02/2024 | 30 | M/S DHIRENDRA ENTERPRISE | 4.8 | 0 | 100
4550 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-O) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002431/2023-2024 | 366/KSD | 19/02/2024 | 30 | M/S S.M. CONSTRUCTION | 4.49 | 0 | 100
4551 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-Q) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002432/2023-2024 | 367/KSD | 19/02/2024 | 30 | M/S. MA BHABANI CONSTRUCTION | 3.81 | 0 | 100
4552 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-R) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002433/2023-2024 | 368/KSD | 19/02/2024 | 30 | S. DAS ENTERPRISE | 3.2 | 0 | 100
4553 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-S) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002434/2023-2024 | 369/KSD | 19/02/2024 | 30 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 3.01 | 0 | 100
4554 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002533/2023-2024 | 259/KSD | 31/01/2024 | 182 | BADSHA ALOM | 2.4 | 0 | 10
4555 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of 2 nos. big dia. tubewell at 1st & 2nd Tubewell Site for Augmentation of Manasadwip Zone-II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002571/2023-2024 | 514/KSD | 15/03/2024 | 5 | M/S KHAJABABA ENTERPRISE | 2.96 | 0 | 100
4556 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002626/2023-2024 | 887/KSD | 16/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
4557 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000326/2023-2024 | 3141/AD | 29/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
4558 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000503/2023-2024 | 4827/AD | 20/12/2023 | 0 | Resource Division | 36.98 | 0 | 0
4559 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000540/2023-2024 | 24/AD | 02/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
4560 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000690/2023-2024 | 460/AD | 24/01/2024 | 0 | Resource Division | 10.56 | 0 | 0
4561 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000902/2023-2024 | 888/AD | 07/02/2024 | 0 | Resource Division | 25 | 0 | 0
4562 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Manasadwip Zone-II PH-2 W/ S Scheme Application No:- 1008023799 Reference ID: 106715305 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01516/2024-2025 | BP-2024-25-362 | 11/09/2024 | 0 | WBSEDCL | 5.27 | 0 | 0
4563 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/03669/2023-2024 | BP-2023-24-391 | 23/11/2023 | 0 | WBSEDCL | 8.76 | 0 | 0
4564 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Manasadwip water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000345/2022-2023 | 3749/SMD | 29/12/2022 | 90 | ASHUTOSH DAS & CO. | 22.32 | 0 | 45
4565 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-II, PH-1 of Manasadwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar][SM/14518] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001891/2024-2025 | 954-AE-II-SMD | 31/07/2024 | 15 | ASHUTOSH DAS & CO. | 0.91 | 0 | 0
4566 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Lot No.-126 (Zone-I) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000311/2024-2025 | 2692/AD | 24/06/2024 | 30 | SURYA ENTERPRISE | 8.72 | 0 | 0
4567 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement as per departmental drawing at the site for Augmentation of Lot No. 126 (Zone - I & II) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001070/2024-2025 | 1305/CSD | 22/11/2024 | 60 | A.P. CONSTRUCTION | 2.09 | 0 | 0
4568 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Lot-126 (Zone-I & II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001946/2022-2023 | 10894/AD | 04/02/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 2.6 | 0 | 95
4569 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - A] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002015/2022-2023 | 12921/AD | 21/03/2023 | 30 | JYOTI ENTERPRISES | 14.41 | 0 | 100
4570 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 60 | S.P. CONSTRUCTION (I) | 97.64 | 0 | 80
4571 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002382/2024-2025 | 619/AD | 17/02/2025 | 30 | SURYA ENTERPRISE | 12.58 | 0 | 0
4572 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002383/2024-2025 | 620/AD | 17/02/2025 | 30 | SURYA ENTERPRISE | 11.46 | 0 | 0
4573 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000039/2023-2024 | 244/AD | 24/04/2023 | 0 | Resource Division | 84.63 | 0 | 0
4574 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000397/2023-2024 | 355/AD | 19/01/2024 | 0 | Resource Division | 4.31 | 0 | 0
4575 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00751/2023-2024 | BP-2023-24-100 | 04/07/2023 | 0 | WBSEDCL | 15.67 | 0 | 0
4576 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Lot 126 Zone1 & 2 water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000016/2023-2024 | 951/SMD | 04/04/2023 | 90 | BARISAL TRADING CO. | 22.3 | 0 | 80
4577 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Lot 126 (Zone-I) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002704/2023-2024 | 1189/SMSD | 08/09/2023 | 15 | BARISAL TRADING CO. | 0.9 | 0 | 100
4578 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Lot 126 (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002705/2023-2024 | 1190/SMSD | 08/09/2023 | 15 | BARISAL TRADING CO. | 0.9 | 0 | 100
4579 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV for each zone of Kalikatala (Zone - I and II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000236/2023-2024 | 1324/AD | 07/07/2023 | 60 | JAYANTA KUMAR DEY | 64.08 | 0 | 100
4580 | Alipore Division | Canning Sub-division | Surging of 03 no. Big dia Tubewell of Ramchadrakhali (Zone-II) (TW-3) and Kalikatala (Zone-II) (TW-1 & 3) W/S Scheme under JJM, Block - Basanti & Canning-II, under Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000242/2025-2026 | 681/CSD | 26/05/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
4581 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001686/2022-2023 | 11493/AD | 15/02/2023 | 45 | KUNDU CONSTRUCTION CO. | 7.1 | 0 | 100
4582 | Alipore Division | Canning Sub-division | : Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001687/2022-2023 | 11494/AD | 15/02/2023 | 45 | ARFIN CONSTRUCTION | 7.09 | 0 | 100
4583 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalikatala (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001695/2022-2023 | 11626/AD | 18/02/2023 | 45 | ELECTROMECH | 39.19 | 0 | 100
4584 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000002/2023-2024 | 117/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
4585 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000014/2023-2024 | 219/AD | 21/04/2023 | 0 | Resource Division | 159.84 | 0 | 0
4586 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000137/2023-2024 | 841/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4587 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Kalikatala Zone-II , PH-4 under Canning -II block (REF ID : 106665561) (APP ID: 1007923967) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/00996/2024-2025 | BP-2024-25-204 | 30/07/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
4588 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/04683/2023-2024 | BP-2023-24-508 | 12/02/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
4589 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of submersible pumping machinery for Kalikatala w/s scheme Zone-II PH-1 under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001458/2023-2024 | .1421/SMSD | 21/11/2023 | 15 | S.S.G ENTERPRISE | 0.9 | 0 | 100
4590 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Augmentation of Kalikatala Zone-I and II water supply scheme under SMD, PHE Dte. Block Canning-II | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001917/2023-2024 | 1198/SMD | 22/03/2024 | 90 | MAA TARA ENTERPRISE | 11.42 | 0 | 95
4591 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line and Constriction of an steel structure for khal crossing at Zone-X of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000218/2022-2023 | 3059/AD | 13/07/2022 | 30 | DIPTI ENTERPRISE | 9 | 0 | 100
4592 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000658/2024-2025 | 4204/AD | 23/10/2024 | 60 | R.S.CONSTRUCTION CO. | 38.62 | 0 | 0
4593 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 365 | SUPRITI ENTERPRISE | 106.12 | 0 | 100
4594 | Alipore Division | Raidighi Sub-Division | Repairing of pump house-1 including boundary wall and approach road and plinth protection at Krishnarampur W/S Scheme, modified as Zone- X of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001903/2023-2024 | 434/RSD | 08/01/2024 | 60 | SUKUMAR HALDAR | 4.81 | 0 | 100
4595 | Alipore Division | Raidighi Sub-Division | Providing FHTC including parallel distribution pipeline at Zone- X of Mathurapur -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001966/2022-2023 | 12720/AD | 14/03/2023 | 45 | R.S.CONSTRUCTION CO. | 77.04 | 0 | 60
4596 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000641/2023-2024 | 245/AD | 15/01/2024 | 0 | Resource Division | 5.01 | 0 | 0
4597 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR at Zone - III of Diamond Harbour - II Block to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIA) [No. of FHTC = 2400] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000364/2023-2024 | 1565/AD | 17/07/2023 | 904 | M/S. PROMILA CONSTRUCTION | 433.39 | 0 | 25
4598 | Alipore Division | Diamond Harbour Sub-Division | Road restoration work due to laying of 315 mm dia. distribution line and 315 mm dia. secondary grid from Kalitola more to Khordho FP School Zone No-III (B) of Diamond Harbour - II Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000870/2024-2025 | 4654/AD | 20/11/2024 | 45 | M/S SUBIR GHOSH | 12.61 | 0 | 100
4599 | Alipore Division | Diamond Harbour Sub-Division | Inter connection between secondary grid to distribution system to facilitate direct supply of water under Zone-III (B) of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour Sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000872/2024-2025 | 4656/AD | 20/11/2024 | 30 | S.S. ENTERPRISE (II) | 6.58 | 0 | 0
4600 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIA at Diamond Harbour- II block for providing balance pipe lying works, road restoration works for new laid pipe etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001373/2024-2025 | 5518/AD | 28/12/2024 | 30 | NAZRUL ENTERPRISE | 11.28 | 0 | 0
4601 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIB at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001374/2024-2025 | 5519/AD | 28/12/2024 | 221 | M/S SUBIR GHOSH | 30.79 | 0 | 35
4602 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-IIIA of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001524/2023-2024 | 434/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4603 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-III (Bhaduria, OHR Size-1500 ) within Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002093/2022-2023 | 327/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
4604 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IIIA at Bhadura of Diamond Harbour -II Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002405/2023-2024 | 1153/AD | 27/02/2024 | 60 | M/S. PROMILA CONSTRUCTION | 39.73 | 0 | 0
4605 | Alipore Division | Diamond Harbour Sub-Division | Inter connection of M.S. distribution pipeline and allied works related to Gap Closing at Bhadura Bridge in Diamond Harbour -II Zone - III under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/003146/2020-2021 | 252/DHSD | 25/11/2020 | 30 | SUPER SKILL | 4.71 | 0 | 95
4606 | Alipore Division | Diamond Harbour Sub-Division | Inter connection of M.S. distribution pipeline and allied works related to Gap Closing at Panarpole Bridge in Diamond Harbour -II Zone - III under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/003147/2020-2021 | 255/DHSD | 25/11/2020 | 20 | SUPER SKILL | 3.18 | 0 | 95
4607 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000220/2023-2024 | 2203/AD | 10/08/2023 | 0 | Resource Division | 19.99 | 0 | 0
4608 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000356/2023-2024 | 3220/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4609 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000427/2023-2024 | 3610/AD | 30/10/2023 | 0 | Resource Division | 1.23 | 0 | 0
4610 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000611/2023-2024 | 273/AD | 15/01/2024 | 0 | Resource Division | 16.32 | 0 | 0
4611 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000878/2023-2024 | 752/AD | 03/02/2024 | 0 | Resource Division | 2.46 | 0 | 0
4612 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000025/2025-2026 | 2011/AD | 28/04/2025 | 30 | HALDER & CO. | 8.53 | 0 | 0
4613 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 4 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000026/2025-2026 | 2012/AD | 28/04/2025 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.84 | 0 | 0
4614 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000255/2023-2024 | 1398/AD | 12/07/2023 | 45 | M/S. MA BHABANI CONSTRUCTION | 7.25 | 0 | 100
4615 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2430] (TSM/017473) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000356/2023-2024 | 1686/AD | 21/07/2023 | 810 | NEW STAR CONSTRUCTION | 132.25 | 0 | 25
4616 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017473) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000357/2023-2024 | 1687/AD | 21/07/2023 | 540 | NEW STAR CONSTRUCTION | 137.02 | 0 | 96
4617 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001510/2023-2024 | 4748/AD | 19/12/2023 | 405 | MALANCHA CONSTRUCTION | 7.06 | 0 | 100
4618 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Kalaria (Zone-IIA) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001673/2022-2023 | 11484/AD | 15/02/2023 | 45 | B.K. ENTERPRISE. | 40.73 | 0 | 100
4619 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIA) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001949/2022-2023 | 10893/AD | 04/02/2023 | 45 | SIRCON ENGINEERING SERVICES | 6.76 | 0 | 90
4620 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000066/2023-2024 | 269/AD | 24/04/2023 | 0 | Resource Division | 64.87 | 0 | 0
4621 | S24 Pgns Mechanical | Canning Sub-division | Payment of Electric Bill for new service connection under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00282/2023-2024 | BP-2023-24-15 | 15/05/2023 | 0 | WBSEDCL | 3.53 | 0 | 0
4622 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Kalaria Zone-IIA PH-2 Water supply scheme under Canning-I block. Reference ID:-106599054, Application No :-1007770612 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00376/2024-2025 | BP-2024-25-96 | 10/06/2024 | 0 | WBSEDCL | 5.51 | 0 | 0
4623 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/00748/2023-2024 | BP-2023-24-102 | 04/07/2023 | 0 | WBSEDCL | 3.51 | 0 | 0
4624 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power) connection at kalaria Zone-II A, PH-1 Water supply scheme under canning-I block Reference ID-106621217 Application No-1007825764 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01482/2024-2025 | BP-2024-25-349 | 06/09/2024 | 0 | WBSEDCL | 11.75 | 0 | 0
4625 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Kalaria ( Zone-II A) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000024/2023-2024 | 958/SMD | 04/04/2023 | 729 | ASHUTOSH DAS & CO. | 38.89 | 0 | 60
4626 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Dharmatala (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1544] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000028/2023-2024 | 156/AD | 18/04/2023 | 836 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 244.1 | 0 | 20
4627 | Alipore Division | Canning Sub-division | Laying of pipeline within some uncovered habitation for Functional Household Tap Connection at Augmentation of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000218/2023-2024 | 1023/AD | 13/06/2023 | 630 | GOUTAM HALDAR (I) | 12.65 | 0 | 100
4628 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 60 | B.K. ENTERPRISE. | 59.91 | 0 | 90
4629 | Alipore Division | Canning Sub-division | Construction of Boundary Wall and Renovation of Pump House No. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001406/2023-2024 | 1145/CSD | 01/11/2023 | 30 | GOUTAM HALDAR (I) | 3.8 | 0 | 100
4630 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001582/2022-2023 | 10781/AD | 03/02/2023 | 45 | MAA SOLAR ENTERPRISE | 7.02 | 0 | 100
4631 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001583/2022-2023 | 10782/AD | 03/02/2023 | 45 | MAA SOLAR ENTERPRISE | 7.02 | 0 | 100
4632 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001822/2022-2023 | 12337/AD | 06/03/2023 | 45 | M/S ARIYAN ENTERPRISE | 7.35 | 0 | 100
4633 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Dharmatala (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001840/2022-2023 | 10939/AD | 06/02/2023 | 45 | TECH VISION | 4.2 | 0 | 0
4634 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
4635 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000068/2023-2024 | 271/AD | 24/04/2023 | 0 | Resource Division | 16.49 | 0 | 0
4636 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01727/2023-2024 | BP-2023-24-193 | 09/08/2023 | 0 | WBSEDCL | 22.37 | 0 | 0
4637 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1,2 & 3 for Augmentation of Dharmatala ( Part-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000033/2023-2024 | 983/SMD | 05/04/2023 | 90 | M/S.UTTAM KUMAR CHATTERJEE | 29.05 | 0 | 100
4638 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of standby submersible pump motor at Aug of Dharmatala( Part-B) PH-2 water supply scheme Under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000330/2024-2025 | 1033/SMSD | 15/07/2024 | 15 | ARUSHI CONSTRUCTION | 0.58 | 0 | 0
4639 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Dharmatala PH-2 under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002256/2023-2024 | 1626/SMSD | 29/12/2023 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0 | 100
4640 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Dharmatala PH-3 under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002257/2023-2024 | 1625/SMSD | 29/12/2023 | 15 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0 | 100
4641 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Garan Bose Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001301/2020-2021 | 2275/AD | 12/10/2020 | 365 | M/S. BLUE BELL ENTERPRISE | 136.08 | 0 | 63
4642 | Alipore Division | Canning Sub-division | inking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Goran Bose W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001670/2022-2023 | 11481/AD | 15/02/2023 | 45 | RAHAMAN ENTERPRISE | 39.19 | 0 | 0
4643 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001712/2022-2023 | 11676/AD | 20/02/2023 | 45 | BABAMONI CONSTRUCTION | 7.1 | 0 | 0
4644 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Goranbose Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002003/2022-2023 | 12817/AD | 16/03/2023 | 45 | MS SINHA ROY & CO | 49.13 | 0 | 40
4645 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002043/2022-2023 | 13043/AD | 24/03/2023 | 45 | SUNNY CONSTRUCTION | 42.98 | 0 | 40
4646 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000040/2023-2024 | 246/AD | 24/04/2023 | 0 | Resource Division | 81.96 | 0 | 0
4647 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Goranbose water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000018/2023-2024 | 953/SMD | 04/04/2023 | 90 | KARUNAMOY ENGINEERING | 26.02 | 0 | 0
4648 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001170/2024-2025 | 120/SMSD | 22/01/2025 | 15 | KARUNAMOY ENGINEERING | 0.58 | 0 | 0
4649 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001171/2024-2025 | 121/SMSD | 22/01/2025 | 15 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0
4650 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001172/2024-2025 | 122/SMSD | 22/01/2025 | 15 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0
4651 | Alipore Division | Diamond Harbour Sub-Division | Construction of Pump House at CWR (200 Cumec) within Padmapur Mouza of Zone-VI under Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000096/2025-2026 | 2525/AD | 30/05/2025 | 30 | K.P. CONSTRUCTION | 5.74 | 0 | 0
4652 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe laying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000389/2025-2026 | 3374/AD | 16/07/2025 | 45 | THE TOWER CONSTRUCTION | 40.87 | 0 | 0
4653 | Alipore Division | Diamond Harbour Sub-Division | Construction of 1 no. CWR (200 Cum) at Padmapur Mouza due to improvement of water supply at 5 nos. Mouza i.e. Baidyakhadi, Pakurtala, Padmapur, Abad simulguange and Ahamedpur of Mallickpur G.P. Within Falta Zone-VI Of Falta Block under Diamond Harbour Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001401/2024-2025 | 5525/AD | 28/12/2024 | 450 | M/S B.N.ENTERPRISES | 66.07 | 0 | 0
4654 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001406/2024-2025 | 5551/AD | 30/12/2024 | 45 | SAFTI PRIVATE LIMITED | 35.97 | 0 | 0
4655 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1200] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001456/2023-2024 | 2158/AD | 09/08/2023 | 90 | MANAS CHATTERJEE | 224.55 | 0 | 75
4656 | Alipore Division | Diamond Harbour Sub-Division | Re-layig of damaged distribution pipeline along Falta-Nainan main road due to laying of primary grid pipeline at Falta Zone-VI under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003151/2020-2021 | 263/DHSD | 26/11/2020 | 30 | CONCORD PROJECTS PRIVATE LIMITED | 4.76 | 0 | 100
4657 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000359/2023-2024 | 3223/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
4658 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000851/2023-2024 | 789/AD | 03/02/2024 | 0 | Resource Division | 14.78 | 0 | 0
4659 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Gosaba W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000183/2025-2026 | 546/CSD | 30/04/2025 | 30 | M/S JBL CONSTRUCTION | 2.27 | 0 | 0
4660 | Alipore Division | Canning Sub-division | Laying of additional pipe line at Augmentation of Gosaba W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000309/2024-2025 | 2690/AD | 24/06/2024 | 480 | B.S. CONSTRUCTION | 56.54 | 0 | 30
4661 | Alipore Division | Canning Sub-division | Construction of OHR (250 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000484/2023-2024 | 1997/AD | 04/08/2023 | 390 | DIVINE | 617.63 | 0 | 65
4662 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Gosaba (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001230/2024-2025 | 5211/AD | 16/12/2024 | 45 | SARADA CONSTRUCTION | 32.99 | 0 | 0
4663 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001888/2022-2023 | 10940/AD | 06/02/2023 | 45 | M/S R.DUTTA & CO. | 6.94 | 0 | 0
4664 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000010/2023-2024 | 112/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
4665 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000132/2023-2024 | 843/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4666 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000406/2023-2024 | 360/AD | 19/01/2024 | 0 | Resource Division | 15.52 | 0 | 0
4667 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000720/2023-2024 | 542/AD | 25/01/2024 | 0 | Resource Division | 161.43 | 0 | 0
4668 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 1 of Phulmalancha W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000279/2025-2026 | 684/CSD | 26/05/2025 | 30 | BANERJEE ENTERPRISE | 2.44 | 0 | 0
4669 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Phulmalancha W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000280/2025-2026 | 685/CSD | 26/05/2025 | 30 | BANERJEE ENTERPRISE | 2.45 | 0 | 0
4670 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000030/2023-2024 | 378/AD | 02/05/2023 | 0 | Resource Division | 35.29 | 0 | 0
4671 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Phulmalancha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000013/2023-2024 | 948/SMD | 04/04/2023 | 90 | B. P. CONSTRUCTION | 11.7 | 0 | 0
4672 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Phulmalancha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000494/2022-2023 | 296/SMD | 03/02/2023 | 90 | SRI KRISHNA NIRMAN | 11.18 | 0 | 0
4673 | Alipore Division | Canning Sub-division | Sinking of 300mm x 200mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Adhia Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000059/2022-2023 | 795/AD | 12/05/2022 | 30 | AQUATECH ENGINEERS | 24.68 | 0 | 62
4674 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 270 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0
4675 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001185/2023-2024 | 877/CSD | 31/08/2023 | 182 | SAILEN CHANDRA DAS | 0.86 | 0 | 100
4676 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Adhia W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001347/2022-2023 | 10943/AD | 06/02/2023 | 30 | SNEHA CONSTRUCTION | 19.49 | 0 | 0
4677 | Alipore Division | Canning Sub-division | Bypass arrangement on risingmain, installation of air valve, restoration of damage road & other works at Adhia W/S Scheme,Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001574/2020-2021 | 1062/CSD | 27/11/2020 | 30 | SUKANTA HALDER | 1.48 | 0 | 96
4678 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2023 to 31.08.2023 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002172/2022-2023 | 1370/CSD | 27/02/2023 | 184 | SAILEN CHANDRA DAS | 0.86 | 0 | 0
4679 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002175/2022-2023 | 1354/CSD | 20/02/2023 | 365 | SWAPAN KUMAR MANDAL | 4.8 | 0 | 12
4680 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000118/2022-2023 | 3045/AD | 28/09/2023 | 0 | Resource Division | 51.93 | 0 | 0
4681 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000725/2023-2024 | 547/AD | 25/01/2024 | 0 | Resource Division | 55.77 | 0 | 0
4682 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Adhia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000027/2023-2024 | 972/SMD | 04/04/2023 | 90 | SUPER SKILL | 11.7 | 0 | 0
4683 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.76 | 0 | 85
4684 | Alipore Division | Canning Sub-division | Construction of Sluice Valve Chamber and protection of pipe line work at Augmentation of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000361/2024-2025 | 731/CSD | 28/06/2024 | 30 | A.M. ENTERPRISE | 1.47 | 0 | 99
4685 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002004/2022-2023 | 12818/AD | 16/03/2023 | 45 | RAKTIM ENTERPRISE | 45.51 | 0 | 75
4686 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002044/2022-2023 | 13044/AD | 24/03/2023 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 23.84 | 0 | 0
4687 | Alipore Division | Canning Sub-division | Surging of 03 nos. Big dia Tubewell of Harbhangi W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1, 2 & 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002976/2024-2025 | 32./CSD | 09/01/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
4688 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000115/2022-2023 | 247/AD | 24/04/2023 | 0 | Resource Division | 195.03 | 0 | 0
4689 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000144/2023-2024 | 848/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4690 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00621/2023-2024 | BP-2023-24-85 | 14/06/2023 | 0 | WBSEDCL | 5.61 | 0 | 0
4691 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00750/2023-2024 | BP-2023-24-101 | 04/07/2023 | 0 | WBSEDCL | 2.65 | 0 | 0
4692 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Harbhangi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000019/2023-2024 | 954/SMD | 04/04/2023 | 90 | KARUNAMOY ENGINEERING | 26.02 | 0 | 80
4693 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.4 of Harbhangi W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002702/2023-2024 | 1078/SMSD | 17/08/2023 | 15 | KARUNAMOY ENGINEERING | 0.91 | 0 | 100
4694 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.5 of Harbhangi W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002703/2023-2024 | 1079/SMSD | 17/08/2023 | 15 | KARUNAMOY ENGINEERING | 0.91 | 0 | 100
4695 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000100/2023-2024 | 503/AD | 11/05/2023 | 15 | S.P. CONSTRUCTION (I) | 18.49 | 0 | 0
4696 | Alipore Division | Canning Sub-division | Construction of 200 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-I) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1893] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001071/2023-2024 | 3508/AD | 16/10/2023 | 300 | PATHIK PABAN NANDI | 512.98 | 0 | 60
4697 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001847/2022-2023 | 11814/AD | 23/02/2023 | 45 | TECH VISION | 3.82 | 0 | 0
4698 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001975/2022-2023 | 12638/AD | 13/03/2023 | 45 | M/S. BISWAS CONSTRUCTION(I) | 8.91 | 0 | 100
4699 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001978/2022-2023 | 12639/AD | 13/03/2023 | 507 | M/S. BISWAS CONSTRUCTION(I) | 8.6 | 0 | 100
4700 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002008/2022-2023 | 12914/AD | 21/03/2023 | 499 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.61 | 0 | 100
4701 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002035/2022-2023 | 13031/AD | 24/03/2023 | 120 | SADIKUL ISLAM | 65.92 | 0 | 90
4702 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000051/2023-2024 | 258/AD | 24/04/2023 | 0 | Resource Division | 44.96 | 0 | 0
4703 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000413/2023-2024 | 369/AD | 19/01/2024 | 0 | Resource Division | 11.66 | 0 | 0
4704 | S24 Pgns Mechanical | Canning Sub-division | QUOTATION FOE NEW POWER CONNECTION AT SATJELIA ZONE-I PH-2 UNDER SMD PHE DTE.(Application ID:-1007627508) ( Reference ID:-106535007) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/00131/2024-2025 | BP-2024-25-34 | 24/04/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
4705 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Satjelia Zone-I PH-3 Water supply scheme under Gosaba block. Reference ID:-106770521, Application No :-1008125345 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01840/2024-2025 | BP-2024-25-465 | 18/11/2024 | 0 | WBSEDCL | 4.54 | 0 | 0
4706 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/04814/2023-2024 | BP-2023-24-528 | 22/02/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
4707 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, Zone-I for Augmentation of Satjelia Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000273/2023-2024 | 1134/SMD | 24/04/2023 | 910 | UNIVERSAL ENTERPRISES | 29.32 | 0 | 90
4708 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of valve and UPVC column pipe etc at Satjelia Zone-I PH-2 water supply scheme under SMD, P.H.E. Dte. [SM/16002] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000376/2025-2026 | 567/SMSD | 17/04/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.7 | 0 | 0
4709 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Satjelia Zone-I PH-3 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/16002) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000377/2025-2026 | 569/SMSD | 17/04/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.99 | 0 | 0
4710 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Satjelia Zone-I PH-2 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/16002) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000378/2025-2026 | 564/SMSD | 17/04/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.99 | 0 | 0
4711 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of valve and UPVC column pipe etc at Satjelia Zone-I PH-3 water supply scheme under SMD, P.H.E. Dte. [SM/16002] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000379/2025-2026 | 565/SMSD | 17/04/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.7 | 0 | 0
4712 | S24 Pgns Mechanical | Canning Sub-division | Supply and Installation of Phase Reversal arrangement including all electrical connection complete at PH No 1 & 2, of Satjelia W/S Scheme under South 24-Pgs Mechanical Division, PHE Dte. (Block-Gosaba) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002294/2022-2023 | ..321/SMSD | 31/03/2023 | 21 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.87 | 0 | 100
4713 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Zone-I, Pump House-2, 3 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002492/2024-2025 | 271/SMSD | 24/02/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.61 | 0 | 0
4714 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-2 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002493/2024-2025 | 272/SMSD | 24/02/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.97 | 0 | 0
4715 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-3 Aug of Satjelia water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/16002) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002494/2024-2025 | 273/SMSD | 24/02/2025 | 15 | SARVATAH PROJECTS PRIVATE LIMITED | 0.97 | 0 | 0
4716 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05025/2023-2024 | BP-2023-24-561 | 11/03/2024 | 0 | WBSEDCL | 12.62 | 0 | 0
4717 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, for Augmentation of Dhosa supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000285/2023-2024 | 1145/SMD | 24/04/2023 | 982 | M/S. A.K. BANERJEE | 19.1 | 0 | 50
4718 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 0 | 96
4719 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method for DHOSA Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/16117] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000809/2023-2024 | 1287/SWD-I | 15/03/2024 | 630 | ASHIM SHIL | 38.02 | 0 | 100
4720 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "DHOSA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 706/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 0 | 100
4721 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000151/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 21.79 | 0 | 0
4722 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) L027-Sagarsangha Math on T03 to Dudhnai(WB/02/480) 2) Construction of Road from Fultala Chow More to Block-A, B.C,D to Ramkrisna Polly to Mohamonilala Greater Kolkata Enginnering College to Ramnagar Bazar via Dhapdhopi road Shakharipukur under Baruipur Block. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01676/2024-2025 | BP-2024-25-781 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.78 | 0 | 0
4723 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00129/2024-2025 | BP-2024-25-33 | 24/04/2024 | 0 | WBSEDCL | 6.66 | 0 | 0
4724 | S24 Pgns Mechanical | Baruipur Sub-Division | Additional Charges for service connection at pump house no-I of Dudhnai.(Baruipur Block) | AE BSD,Assistant Engineer | Junior Engineer | BILL/00407/2024-2025 | BP-2024-25-99 | 10/06/2024 | 0 | WBSEDCL | 2.65 | 0 | 0
4725 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04684/2023-2024 | BP-2023-24-502 | 12/02/2024 | 0 | WBSEDCL | 9.99 | 0 | 0
4726 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Dudhnai water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000086/2023-2024 | 1066/SMD | 18/04/2023 | 1079 | B.T.PROJECTS PVT.LTD. | 22.37 | 0 | 100
4727 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Dudhnai W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16118) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 934/SMSD | 28/06/2024 | 400 | B.T.PROJECTS PVT.LTD. | 0.91 | 0 | 0
4728 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Dudhnai W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16118) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2024-2025 | 928/SMSD | 28/06/2024 | 400 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 0
4729 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.32] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00492/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.4 | 0 | 0
4730 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00544/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 20 | 0 | 0
4731 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DUDHNAI Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 661] [TSM/017763] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000305/2023-2024 | 1694/SWD-I | 07/08/2023 | 876 | A.G.S. ENTERPRISE | 151.11 | 0 | 100
4732 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based DUDHNAI Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/16118) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000375/2024-2025 | 3548/SWD-I | 09/08/2024 | 494 | A.G.S. ENTERPRISE | 87.42 | 0 | 90
4733 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DUDHNAI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/017763] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000650/2022-2023 | 3322/SWD-I | 06/03/2023 | 30 | MAHI CONSTRUCTION | 31.77 | 0 | 50
4734 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dudhnai Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000940/2022-2023 | 1257/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.5 | 0 | 100
4735 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000123/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.32 | 0 | 0
4736 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Jamtala Petkulchand Road from 0.20 to 0.35 km, 4.50 to 6.00 km, 8.20 to 8.50 km, 8.80 to 9.00 km & 12.50 to 13.00 km Restoration of Brick top surface & Saucer drain in different chainage due to laying of pipelines by PHE Department under Lakshmikantapur Highway Sub Division of Diamond Harbour Highway Division in the District of South 24 Parganas. | AE BSD |  | BILL/00640/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 13.26 | 0 | 0
4737 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 120 | MANASH GHOSH | 626.38 | 0 | 91
4738 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of 315 mm diameter (OD) HDPE pipe by Horizontal Directional Drilling (HDD) process for crossing Piyali River at Panchuakhali Bridge in between nodes 8 & 8a within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16186) | AE BSD |  | ORD/000252/2024-2025 | 2715/SWD-I | 10/06/2024 | 20 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 67.9 | 0 | 100
4739 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIIA (MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000360/2021-2022 | 2532/SWD-I | 08/03/2022 | 120 | SUPRITI ENTERPRISE | 808.84 | 0 | 85
4740 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipeline protection works restoration of road damaged due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-III at KULTALI block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/16186) | AE BSD |  | ORD/000402/2024-2025 | 3682/SWD-I | 22/08/2024 | 180 | M/S. S.S. ENTERPRISE (NODAKHALI) | 95.58 | 0 | 100
4741 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-III (MONDALER LAT) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM : 015332] | AE BSD |  | ORD/000557/2023-2024 | 2585/SWD-I | 13/10/2023 | 300 | M/S LOKENATH CONSTRUCTION | 439.11 | 0 | 0
4742 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-II & KULTALI Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/16186] | AE BSD |  | ORD/000685/2024-2025 | 4480/SWD-I | 30/10/2024 | 90 | CHANDAN ROY | 30.79 | 0 | 0
4743 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Hume Pipe Culvert bridge for the approach road of proposed OHR Site at Zone-VI (Madhya Gurguria) within KULTALI Block under "Augmentation of Laying Distribution System to extend the benefit of 100% Household in ZONE-III at KULTALI Block within Mega Surface Water Based W/S Scheme of Falta-Mathurapur, South 24-Parganas District under South 24 Pgns W/S Division-I, PHE Dte." (SM/16186) | AE BSD |  | ORD/000700/2024-2025 | 4502/SWD-I | 30/10/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 10.18 | 0 | 100
4744 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000070/2022-2023 | 2986/SWD-I | 20/02/2023 | 0 | Resource Division | 233.8 | 0 | 0
4745 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Dakshin Rajapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001519/2022-2023 | 908/SMD | 28/03/2023 | 90 | GOENKA ENTERPRISE | 22.69 | 0 | 0
4746 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2106) (TSM/017116) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 99/SWD-I | 10/04/2023 | 300 | MILAN GHOSH | 488.23 | 0 | 15
4747 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 4232/SWD-I | 30/09/2024 | 60 | MOLLICK ENTERPRISE | 48.21 | 0 | 0
4748 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for DAKSHIN RAJAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017116] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000637/2022-2023 | 3283/SWD-I | 03/03/2023 | 30 | SAMSUDDIN MANDAL | 31.76 | 0 | 100
4749 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000877/2024-2025 | 4975/SWD-I | 05/12/2024 | 45 | Grafton Tarmac Engineering And Civil | 11.2 | 0 | 0
4750 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000037/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 27.61 | 0 | 0
4751 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000214/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.97 | 0 | 0
4752 | Alipore Division | Baruipur Sub-Division | Road restoration 1) Chandakhali to Dhapdhapi More 2) Ramnagar Bazar to Matiar Dhali House 3) Doctor More to Madanpur Ashok Sangha CIub 4) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01667/2024-2025 | BP-2024-25-774 | 23/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 7.11 | 0 | 0
4753 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01504/2023-2024 | BP-2023-24-175 | 02/08/2023 | 0 | WBSEDCL | 7.34 | 0 | 0
4754 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Ramnagar (Zone-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000063/2023-2024 | 1057/SMD | 18/04/2023 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 25.66 | 0 | 100
4755 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No- 1 & 2 of RAMNAGAR (Zone-II) water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002197/2023-2024 | 355/SMSD | 20/03/2024 | 15 | NITESH MANAGEMENT | 0.78 | 0 | 100
4756 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002343/2023-2024 | 1527/SMSD | 14/12/2023 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 100
4757 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002346/2023-2024 | 1455/SMSD | 30/11/2023 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.92 | 0 | 100
4758 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Ramnagar (Zone-II) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002382/2023-2024 | 1453/SMSD | 30/11/2023 | 15 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.58 | 0 | 100
4759 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 112/SWD-I | 11/04/2023 | 720 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 288.53 | 0 | 100
4760 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000404/2021-2022 | 1946/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0
4761 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providung FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based RAMNAGAR [ZONE-II] piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/15634) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000425/2024-2025 | 3752/SWD-I | 28/08/2024 | 45 | SUPER CONSTRUCTION | 72.09 | 0 | 0
4762 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-II) PWSS to accommodate FHTC in BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 3125/SWD-I | 24/02/2023 | 30 | SARWAR JAMAN | 31.77 | 0 | 50
4763 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000109/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 18.89 | 0 | 0
4764 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1416] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000292/2023-2024 | 1502/AD | 15/07/2023 | 600 | JYOTY SOLAR POWER | 498.31 | 0 | 22
4765 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001928/2022-2023 | 11801/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 3.75 | 0 | 95
4766 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001981/2022-2023 | 12642/AD | 13/03/2023 | 45 | SRI DURGA ENTERPRISE | 8.88 | 0 | 0
4767 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001982/2022-2023 | 12643/AD | 13/03/2023 | 45 | SRI DURGA ENTERPRISE | 8.57 | 0 | 0
4768 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002037/2022-2023 | 13033/AD | 24/03/2023 | 45 | MD JIYAUL HOQUE | 43.95 | 0 | 100
4769 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000045/2023-2024 | 252/AD | 24/04/2023 | 0 | Resource Division | 20.97 | 0 | 0
4770 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-I for Augmentation of Purba Radhanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000276/2023-2024 | 1136/SMD | 24/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 19.55 | 0 | 0
4771 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service (power) connection at Bodra PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663975, Application No- 1007921742 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01468/2024-2025 | BP-2024-25-348 | 06/09/2024 | 0 | WBSEDCL | 5.93 | 0 | 0
4772 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Bodra water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000595/2023-2024 | 2367/SMD | 30/06/2023 | 732 | GOENKA ENTERPRISE | 22.69 | 0 | 25
4773 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BODRA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15757) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 1118/SWD-I | 24/04/2025 | 75 | SARDAR ENTERPRISE | 121 | 0 | 0
4774 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BODRA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2064) (TSM/017117) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 254/SWD-I | 20/04/2023 | 957 | SARDAR ENTERPRISE | 455.71 | 0 | 20
4775 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BODRA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017117] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000638/2022-2023 | 3284/SWD-I | 03/03/2023 | 30 | M/S MONDAL ENTERPRISE | 31.76 | 0 | 0
4776 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BODRA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/15757) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000666/2024-2025 | 4396/SWD-I | 23/10/2024 | 400 | M/S. SHYAM CONSTRUCTION | 31.05 | 0 | 50
4777 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000036/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 35.63 | 0 | 0
4778 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000213/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.71 | 0 | 0
4779 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Dakshin Gouripur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/001430/2022-2023 | 146/SMD | 16/01/2023 | 90 | M/S. S.S. ENTERPRISE | 35.09 | 0 | 0
4780 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed DAKSHIN GOURIPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3883] |  |  | ORD/000315/2023-2024 | 1708/SWD-I | 08/08/2023 | 770 | CE INFRASTRUCTURE | 485.85 | 0 | 80
4781 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, approach road and land development for DAKSHIN GOURIPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/18330) |  |  | ORD/000397/2024-2025 | 3686/SWD-I | 22/08/2024 | 491 | M M ENTERPRISE | 220.68 | 0 | 60
4782 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Gouripur Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000950/2022-2023 | 1129/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.91 | 0 | 100
4783 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 68.93 | 0 | 0
4784 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Rashkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/001432/2022-2023 | 147/SMD | 16/01/2023 | 90 | S.P. CONSTRUCTION | 33.46 | 0 | 0
4785 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Rashkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/001568/2024-2025 | 2029/SMD | 28/06/2024 | 90 | S.P. CONSTRUCTION | 33.46 | 0 | 0
4786 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed RASHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3624] |  |  | ORD/000419/2023-2024 | 1965/SWD-I | 24/08/2023 | 770 | M/S N. H. ENTERPRISE | 448.48 | 0 | 20
4787 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, approach road and land development for RASHKHALI Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/18331) |  |  | ORD/000774/2024-2025 | 4760/SWD-I | 21/11/2024 | 457 | M/S N.H. ENTERPRISE | 208.36 | 0 | 15
4788 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Raskhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000947/2022-2023 | 1128/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.94 | 0 | 100
4789 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 88.83 | 0 | 0
4790 | S24 Pgns Mechanical |  | Supply, delivery and installation of vertical turbine sewage pump with suitable rated vertical Induction motor set at WTP plant of Dakshin Roypur (34 MGD) with starter, cables, valves, pipe connections dismantling joints, and all other accessories & related allied works under SMD, PHE Dte. |  |  | ORD/000722/2024-2025 | 3673/SMD | 21/11/2024 | 540 | S.P. CONSTRUCTION | 106.17 | 0 | 60
4791 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No-WB-09-1333] |  |  | ORD/000060/2025-2026 | 1369/SWD-I | 22/05/2025 | 183 | SUDIP GHOSH | 0.87 | 0 | 0
4792 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No-WB-09-1333] |  |  | ORD/000219/2024-2025 | 2572/SWD-I | 04/06/2024 | 171 | SUDIP GHOSH | 0.81 | 0 | 0
4793 | South 24 Pgs W/S Division I |  | Retrofitting of old recirculation system of 34 MGD WTP (Civil Part) at Budge Budge II Block Under South 24 Pgns W/S Division-I, P.H.E Dte. |  |  | ORD/000339/2023-2024 | 1608/SWD-I | 31/07/2023 | 75 | S. ROY AND ASSOCIATES | 224.5 | 0 | 25
4794 | South 24 Pgs W/S Division I |  | Providing Balance FHTC for Budge Budge-II, Bishnupur-II and Mayapur GP with allied works in connection to Retrofitting and providing FHTC including Special Repair and Rejuvenation of different units of 34 MGD Treatment Plant at Dakshin Roypur for FHTC Drive under Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [No. of FHTC = 23728] (TSM/014925) |  |  | ORD/000567/2023-2024 | 2649/SWD-I | 27/10/2023 | 90 | WPIL LTD. | 1600.01 | 0 | 20
4795 | South 24 Pgs W/S Division I |  | Retrofitting including Special Repair and Rejuvenation of different units of 34 MGD Treatment Plant at Dakshin Roypur for FHTC Drive under Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/014925] |  |  | ORD/000569/2023-2024 | 2666/SWD-I | 31/10/2023 | 450 | VISHVARAJ ENVIRONMENT PRIVATE LIMITED | 515.38 | 0 | 80
4796 | South 24 Pgs W/S Division I |  | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-09-1333] |  |  | ORD/000762/2023-2024 | 3247/SWD-I | 15/12/2023 | 180 | SUDIP GHOSH | 0.86 | 0 | 66
4797 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No-WB-09-1333] |  |  | ORD/000890/2024-2025 | 4877/SWD-I | 29/11/2024 | 182 | SUDIP GHOSH | 0.86 | 0 | 0
4798 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 248/SWD-I | 20/04/2023 | 0 | Resource Division | 146.16 | 0 | 0
4799 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Charges for new service connection at pump house no-II of Bonhugly water supply scheme (Sonarpur Block) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02236/2024-2025 | BP-2024-25-499 | 19/12/2024 | 0 | WBSEDCL | 5.5 | 0 | 0
4800 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bonhoogly water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001419/2022-2023 | 3458/SMD | 23/12/2022 | 1195 | DEY ENTERPRISE | 25.93 | 0 | 45
4801 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE BONHOOGHLY PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I. PHE.DTE. (TSM/016321) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 443/SWD-I | 03/05/2023 | 420 | SARFARAZ CONSTRUCTION | 30.04 | 0 | 50
4802 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BONHOOGHLY PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/016321] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 444/SWD-I | 03/05/2023 | 421 | SARFARAZ CONSTRUCTION | 3.14 | 0 | 50
4803 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Development of land, Pathway, Drain & others allied works of "BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18225) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000418/2024-2025 | 3739/SWD-I | 27/08/2024 | 45 | M/S SANJAY ADHIKARI | 33.99 | 0 | 0
4804 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and other allied works at 2nd Tubewell site of BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18225) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000725/2024-2025 | 4602/SWD-I | 12/11/2024 | 180 | STAR ENTERPRISE | 10.29 | 0 | 100
4805 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000011/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 25.05 | 0 | 0
4806 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000314/2023-2024 | 247/SWD-I | 10/01/2024 | 0 | Resource Division | 18.73 | 0 | 0
4807 | S24 Pgns Mechanical |  | Quotation for new service(power) connection at Narayanpur PH -2 water supply scheme under bhangar-I block Reference ID-106550931, Application No- 1007657658 |  |  | BILL/00983/2024-2025 | BP-2024-25-212 | 30/07/2024 | 0 | WBSEDCL | 17.32 | 0 | 0
4808 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmnetation of Narayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001522/2022-2023 | 929/SMD | 30/03/2023 | 732 | RELIABLE CONSTRUCTION | 25.41 | 0 | 35
4809 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.40] |  |  | BILL/00470/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 39.52 | 0 | 0
4810 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NARAYANPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018316] |  |  | ORD/000302/2023-2024 | 1673/SWD-I | 04/08/2023 | 30 | MOUSUMI DAS SARKAR | 31.72 | 0 | 100
4811 | South 24 Pgs W/S Division I |  | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2308) (TSM/018316) |  |  | ORD/000396/2023-2024 | 1877/SWD-I | 18/08/2023 | 90 | ATCO ENTERPRISE | 380.84 | 0 | 45
4812 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 0 | 60
4813 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18547) |  |  | ORD/000704/2024-2025 | 4506/SWD-I | 30/10/2024 | 60 | ATCO ENTERPRISE | 92.01 | 0 | 0
4814 | South 24 Pgs W/S Division I |  | Protection of pipeline of distribution of N.P-300-348, 39-35, 21-14, 13-08, 20-25, 27-37, 37-49, 52-66, 66-32 & 143-182 of Narayanpur Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18547) |  |  | ORD/000828/2023-2024 | 1109/SWD-I | 05/03/2024 | 15 | ATCO ENTERPRISE | 9.78 | 0 | 0
4815 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 23.63 | 0 | 0
4816 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 258/SWD-I | 10/01/2024 | 0 | Resource Division | 14.22 | 0 | 0
4817 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Sabek Mahisahara and Adjoining Mouzas (Chunpuri), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000279/2024-2025 | 2494/AD | 14/06/2024 | 353 | TARUN KUMAR LAHA | 48.15 | 0 | 15
4818 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Sabek Mahisahara & Adjoining Mouzas (Chunpuri) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] (3rd Call) | Assistant Engineer, Canning sub division |  | ORD/000538/2024-2025 | 3709/AD | 12/09/2024 | 45 | NIJAMUDDIN ENTERPRISE | 6.97 | 0 | 0
4819 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Sabek Mahisahara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] (SM/18863) | Assistant Engineer, Canning sub division |  | ORD/000100/2025-2026 | 1179/SMD | 28/04/2025 | 135 | PS & ASSOCIATES | 11.2 | 0 | 0
4820 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaorakhali & Adjoining Mouzas (Bakultala) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000345/2024-2025 | 2786/AD | 01/07/2024 | 194 | AQUATECH ENGINEERS | 34.47 | 0 | 98
4821 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaorakhali & Adjoining Mouzas (Bakultala), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000372/2024-2025 | 2967/AD | 15/07/2024 | 290 | CREATIVE | 137.23 | 0 | 60
4822 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Kaorakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Canning-II]. (SM/18864) | Assistant Engineer, Canning sub division |  | ORD/000045/2025-2026 | 1430/SMD | 21/05/2025 | 135 | S.S. ENTERPRISES | 19.1 | 0 | 0
4823 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000013/2021-2022 | 3021/AD | 02/11/2021 | 365 | M/S A.K. GHATAK | 83.3 | 0 | 99
4824 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000416/2023-2024 | 775/CSD | 02/08/2023 | 30 | JOY MAA TARA ENTERPRISE | 4.57 | 0 | 0
4825 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001466/2022-2023 | 1285/CSD | 31/01/2023 | 30 | M.P. ENTERPRISE | 4.81 | 0 | 99
4826 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Chak jalsi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000393/2022-2023 | 3795/SMD | 29/12/2022 | 90 | MASSK ENGINEERING WORKS | 22.36 | 0 | 0
4827 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based CHAK JALSI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 3032/SWD-I | 02/07/2024 | 543 | BASIR CONSTRUCTION | 195.85 | 0 | 22
4828 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Chak Jalsi PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2022-2023 | 1879/SWD-I | 16/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
4829 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "CHAK JALASI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 413/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
4830 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell by Rotary method for Ground Water Based at head work site of CHAK JALSI Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/12883) | Assistant Engineer | Junior Engineer | ORD/000444/2024-2025 | 3894/SWD-I | 04/09/2024 | 270 | PADMA ENGINEERING CO. | 19.14 | 0 | 100
4831 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK JALSI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1611] | Assistant Engineer | Junior Engineer | ORD/000598/2022-2023 | 3126/SWD-I | 24/02/2023 | 708 | MD NURNABI CONSTRUCTION (NUMABISK1992@GMAIL.COM) | 435.58 | 0 | 25
4832 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000172/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 22.37 | 0 | 0
4833 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - III) having village with maximum 105 nos. households, Block - Canning -II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000661/2022-2023 | 6166/AD | 01/11/2022 | 105 | SWASTIK CONSTRUCTION | 37.67 | 0 | 79
4834 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001912/2022-2023 | 5152/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.31 | 0 | 0
4835 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000180/2023-2024 | 1133/AD | 22/06/2023 | 0 | Resource Division | 0.65 | 0 | 0
4836 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00389/2023-2024 | BP-2023-24-56 | 09/06/2023 | 0 | WBSEDCL | 4.86 | 0 | 0
4837 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00518/2023-2024 | BP-2023-24-79 | 13/06/2023 | 0 | WBSEDCL | 2.4 | 0 | 0
4838 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Khunkhali (Part-III) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000584/2022-2023 | 641/SMD | 02/03/2023 | 90 | KAMAKHYA ENTERPRISE | 8.8 | 0 | 100
4839 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Crossing Of Culvert and Road Crossing at 9(Nine) Different Locations Within Zone -III At Mandir Bazar Block Under augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-III at Mandirbazar Block within ' Mega surface water based water supply scheme for Falta- Mathurapur, district- South 24 Pgns' under South-24 Pgns w/s Divn-i of south 24-pgns. w/s circle, PHE Dte. (SM/15484) | AE HQ-I |  | ORD/000077/2025-2026 | 1580/SWD-I | 11/06/2025 | 45 | SRIJON ENTERPRISE | 36.06 | 0 | 0
4840 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Boundary wall for proposed OHR Site Uttar Akrabaria within Mandirbazar block, Mouza-Uttar Akrabaria under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 397 mtr.) | AE HQ-I |  | ORD/000111/2021-2022 | 1115/SWD-I | 26/10/2021 | 90 | UNITED BUILDERS | 60.18 | 0 | 100
4841 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of pipe lines for distribution system of Zone-VIII in Mandirbazar Block under under Falta-Mathurapur Mega surface based water supply project under South 24-Pgns. W/S Division-I, P.H.E Dte. (SM/03906) | AE HQ-I |  | ORD/000278/2024-2025 | 2926/SWD-I | 25/06/2024 | 301 | M/S LOKENATH BUILDERS | 243.92 | 0 | 55
4842 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of UTTAR AKRABERIA MOUZA in MANDIRBAZAR (ZONE-III) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000391/2021-2022 | 1985/SWDI | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4.83 | 0 | 100
4843 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I |  | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 607 | SUPRITI ENTERPRISE | 1557.57 | 0 | 50
4844 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/10/2023 to 31/03/2024] | AE HQ-I |  | ORD/000582/2023-2024 | 2389/SWD-I | 27/09/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0 | 25
4845 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Critical gap negotiation in Secondary Grid along with land development at Zone III at Mandir Bazar Block for AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I OF SOUTH 24-PGNS. W/S CIRCLE, PHE DTE. (SM/15484) | AE HQ-I |  | ORD/000762/2024-2025 | 4683/SWD-I | 18/11/2024 | 30 | AVIK ENTERPRISE | 7.7 | 0 | 100
4846 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0 | 50
4847 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-25J-9045] [w.e.f. 01/10/2024 to 31/03/2025] | AE HQ-I |  | ORD/000884/2024-2025 | 4186/SWD-I | 27/09/2024 | 182 | SUBRAT KUMAR SETHY | 0.86 | 0 | 0
4848 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2024 to 30/09/2024] | AE HQ-I |  | ORD/000904/2023-2024 | 1493/SWD-I | 30/03/2024 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0 | 0
4849 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-25J-9045] [w.e.f. 01/04/2025 to 30/09/2025] | AE HQ-I |  | ORD/001206/2024-2025 | 876/SWD-I | 26/03/2025 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0 | 0
4850 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000045/2022-2023 | 3016-SWD-I | 20/02/2023 | 0 | Resource Division | 368.04 | 0 | 0
4851 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01985/2023-2024 | BP-2023-24-244 | 11/09/2023 | 0 | WBSEDCL | 8.05 | 0 | 0
4852 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kalikapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000297/2022-2023 | 447/SMD | 17/02/2023 | 439 | INDIA ENTERPRISE | 26.01 | 0 | 100
4853 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH No.-1&2 of Kalikapur water supply scheme under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001180/2023-2024 | 114O/SMSD | 29/08/2023 | 15 | ARPAN CONSTRUCTION | 0.78 | 0 | 100
4854 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing Bus bar,Cable laying including allied work at Pump House no-1 & 2 of Kalikapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002384/2023-2024 | 1191/SMSD | 08/09/2023 | 15 | INDIA ENTERPRISE | 1 | 0 | 100
4855 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & laying of cable including allied work at Pump House no-1 & 2 of Kalikapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002385/2023-2024 | 1192/SMSD | 08/09/2023 | 15 | INDIA ENTERPRISE | 0.97 | 0 | 100
4856 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Pump House no-2 of Kalikapur W/S Scheme under SMD, PHE Dte. (Block- Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002565/2023-2024 | 1188/SMSD | 08/09/2023 | 15 | INDIA ENTERPRISE | 0.96 | 0 | 100
4857 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Pump House no-1 of Kalikapur W/S Scheme under SMD, PHE Dte. (Block- Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002566/2023-2024 | 1187/SMSD | 08/09/2023 | 15 | INDIA ENTERPRISE | 0.93 | 0 | 100
4858 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.23] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00482/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 12.08 | 0 | 0
4859 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Repairing and Renovation of Pumphouse, Office Room, Boundary Wall & allied works at 2nd TW site of Kalikapur PWSS within Sonarpur Block" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (TSM/014873) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 34/SWD-I | 05/04/2023 | 60 | SUSHANTA MANDAL | 13.21 | 0 | 100
4860 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for OHR site for Sonarpur Block, in support work of Augmentation (part) of balance distribution pipeline (restoration) in different places of Zone-31 (Block-Sonarpur) under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District. [PART-A, Front side (S), Right side (E) & Back side (N) 240 mtr] (SM/05835) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1696/SWD-I | 01/11/2022 | 60 | SUSHANTA MANDAL | 31.72 | 0 | 100
4861 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for KALIKAPUR Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. [SM/014837] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000261/2022-2023 | 1773/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 100
4862 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1717] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000525/2022-2023 | 2959/SWD-I | 16/02/2023 | 836 | HARBAUER INDIA PVT. LTD. | 445.06 | 0 | 50
4863 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway at 2nd site of Kalikapur PWSS within Sonarpur Block in connetion with" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/12207). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000562/2023-2024 | 2603/SWD-I | 16/10/2023 | 30 | NILKANTHA ENTERPRISE | 4.53 | 0 | 100
4864 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fitting, fixing of Barbed wire fencing over existing Boundary wall & Construction of Drain at 2nd Tubewell site of Kalikapur PWSS within Sonarpur Block " KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/12207) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000668/2023-2024 | 3019/SWD-I | 30/11/2023 | 15 | KALAM ENTERPRISE | 1.89 | 0 | 100
4865 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KALIKAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12207] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000773/2022-2023 | 3652/SWD-I | 28/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 100
4866 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway & allied works at Head work site of Kalikapur PWSS within Sonarpur Block "KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (TSM/014873) [ 2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000815/2023-2024 | 1082/SWD-I | 04/03/2024 | 360 | SUSHANTA MANDAL | 44.5 | 0 | 100
4867 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.51 | 0 | 0
4868 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000234/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.58 | 0 | 0
4869 | South 24 Pgs W/S Division I |  | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas |  |  | BILL/00638/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
4870 | South 24 Pgs W/S Division I |  | Payment of Enhanced GST Rate vide W/O No.2484/SWD-I dt. 02/03/2022 |  |  | BILL/01808/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 7.62 | 0 | 0
4871 | South 24 Pgs W/S Division I |  | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/18655) |  |  | ORD/000251/2024-2025 | 2649/SWD-I | 07/06/2024 | 270 | P.L. CONSTRUCTION | 46.65 | 0 | 45
4872 | South 24 Pgs W/S Division I |  | Construction of pipe carrying structure with laying of 508 mm dia M.S. Secondary Rising Main for crossing of Canal at Simana Bazar, 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Path Pukur Bridge and 355.6 mm dia M.S. pipe for Secondary Rising Main for crossing of Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI, Zone-IV and Zone-II respectively within JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16191, 18655 & 18222] |  |  | ORD/000285/2024-2025 | 3041/SWD-I | 02/07/2024 | 45 | SRIJON ENTERPRISE | 69.41 | 0 | 100
4873 | South 24 Pgs W/S Division I |  | Laying distribution system of piped water supply at Zone-IV- B (Gardoani) of Joynagar -II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. |  |  | ORD/000453/2021-2022 | 2484/SWD-I | 02/03/2022 | 1200 | SAMIRON GHOSH | 485.75 | 0 | 95
4874 | South 24 Pgs W/S Division I |  | Construction of 1500 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile and raft foundation within Zone-IV at Gordoani Mouza of Joynagar-II Block for Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. (SM/18655) |  |  | ORD/000695/2023-2024 | 3190\SWD-I | 12/12/2023 | 300 | UNITED BUILDERS | 440.77 | 0 | 0
4875 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2957/SWD-I | 16/02/2023 | 0 | Resource Division | 121.77 | 0 | 0
4876 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 182.71 | 0 | 0
4877 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 2437/SWD-I | 30/09/2023 | 0 | Resource Division | 199.31 | 0 | 0
4878 | South 24 Pgs W/S Division I |  | Balance civil works of Jaynagar-II GLR (Nimpith) under "Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas." under Baruipur Sub-Division of South 24-Parganas Water Supply Division-I, PHE Dte. |  |  | ORD/000018/2022-2023 | 875/SWD-I | 14/07/2022 | 960 | MALLICK ENTERPRISE | 92.73 | 0 | 60
4879 | South 24 Pgs W/S Division I |  | Construction of pipe carrying structure with laying of 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Bakultala Natunhaater Culvert and Nimpith Tulsighata Bridge under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18656] |  |  | ORD/000284/2024-2025 | 3040/SWD-I | 02/07/2024 | 30 | SRIJON ENTERPRISE | 45.72 | 0 | 100
4880 | South 24 Pgs W/S Division I |  | Construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for " Augmentation of laying distribution system to extend the benifit of 100 % Household in ZONE-VIII at JAYNAGAR-II block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist. South 24 Parganas under South 24 Paraganas Water Supply Division-I Division of PHE Dte." (TSM/015336 ) |  |  | ORD/000432/2023-2024 | 2006/SWD-I | 28/08/2023 | 581 | M/S. S.S. ENTERPRISE | 357.14 | 0 | 30
4881 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 126.39 | 0 | 0
4882 | South 24 Pgs W/S Division I |  | Construction of boundary wall & other allied works at Head Work in Zone-VI at Ektara of Mograhat-I block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI AT EKTARA OF MOGRAHAT-I BLOCK within "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District- South 24-Parganas" under South 24 Parganas W/S Division-I, PHE Dte. (Total Length-112 mtr excluding Gate) (TSM/014910) |  |  | ORD/000352/2023-2024 | 1738/SWD-I | 10/08/2023 | 60 | NIKHIL SAMADDAR | 18.85 | 0 | 1
4883 | South 24 Pgs W/S Division I |  | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) |  |  | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 300 | CONCORD ENGINEERING | 1862.26 | 0 | 55
4884 | South 24 Pgs W/S Division I |  | Land development at Head Work site of EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) |  |  | ORD/000412/2024-2025 | 3713/SWD-I | 23/08/2024 | 45 | TIYASHA ENTERPRISE | 20.8 | 0 | 1
4885 | South 24 Pgs W/S Division I |  | Construction of Platform for FHTC, Additional pipelines for distribution system, Protection of pipeline, Approach road and construction of Chlorination Room for Augmentation of existing laying distribution system and allied works to extend the benifit of 100% Household in Zone-VI at Ektara under Magrahat-I Block within Mega surface Water based water supply scheme of Falta-Mathurapur,Dist. S-24 pgns under South 24 parganas W/S Division-I, P.H.E Dte. (SM/18708) |  |  | ORD/000537/2024-2025 | 4093/SWD-I | 20/09/2024 | 90 | CONCORD ENGINEERING | 319.66 | 0 | 0
4886 | South 24 Pgs W/S Division I |  | Supplying, fabrication & laying of 700 mm dia (ID) MS Pipe conduits 72 mtr. in length to be prepared from 12 mm thick MS Plate by pipe jacking technique, including supplying and laying of 250 mm dia (ID) MS water supply pipe line within the conduit 90 mtr. in length to be prepared from 06 mm thick MS Plate across and underneath the Railway Track in between mast no-50/11, 50/13 and mast no-50/12, 56/14 in between Deula Station and Netra Stations on Baruipur - Diamond Harbour Section as per permission obtained from Railway Authority, including construction of Drive Pit & Receiving Pit, as requred, for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mograhat-I Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/03906) |  |  | ORD/000499/2022-2023 | 2868/SWD-I | 09/02/2023 | 60 | S. ROY AND ASSOCIATES | 76.87 | 0 | 100
4887 | South 24 Pgs W/S Division I |  | Providing support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotely Piloted Aircraft System / DGPS / Total station etc. and detailed design of pipeline by using Watergems Software on the besis of the population density within the Zone-VI of Mograhat-I block under Mega surface water based water supply scheme for Falta-Mathurapur, Dist- South 24-Pgns. |  |  | ORD/000770/2020-2021 | 1047/SWD-I | 05/10/2020 | 740 | DEVELOPMENT CONSULTANTS PVT LTD | 4.99 | 0 | 20
4888 | South 24 Pgs W/S Division I |  | Construction of Balance portion of Boundary Wall for EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) [2nd call] |  |  | ORD/001119/2024-2025 | 155/SWD-I | 15/01/2025 | 30 | NIKHIL SAMADDAR | 12.03 | 0 | 0
4889 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 8.27 | 0 | 0
4890 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Kanyanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/000594/2023-2024 | 2692/SMD | 17/08/2023 | 90 | NITESH MANAGEMENT | 34.41 | 0 | 0
4891 | South 24 Pgs W/S Division I |  | Land development at 3rd Tubewell site and approach road of Kannyanagar PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte., for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/18574) |  |  | ORD/000005/2025-2026 | 908/SWD-I | 02/04/2025 | 30 | CHANDAN ROY | 4.71 | 0 | 0
4892 | South 24 Pgs W/S Division I |  | Construction of boundary wall, approach road, laying of rising main and other allied works for KANYANAGAR PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] |  |  | ORD/000250/2024-2025 | 2670/SWD-I | 07/06/2024 | 45 | CHANDAN ROY | 96.96 | 0 | 0
4893 | South 24 Pgs W/S Division I |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KANNYANAGAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018432] |  |  | ORD/000376/2023-2024 | 1802/SWD-I | 14/08/2023 | 522 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.85 | 0 | 98
4894 | South 24 Pgs W/S Division I |  | Construction of boundary wall & other allied works at Head Work Site of KANNYANAGAR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018432] |  |  | ORD/000415/2023-2024 | 1959/SWD-I | 24/08/2023 | 60 | T. K. ENTERPRISE | 18.3 | 0 | 0
4895 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KANNYANAGAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4562) [TSM/018432]. |  |  | ORD/000427/2023-2024 | 1987/SWD-I | 25/08/2023 | 676 | DEBAPRASAD MONDAL | 527.21 | 0 | 45
4896 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Kannyanagar Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000962/2022-2023 | 1166/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.92 | 0 | 100
4897 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 49.9 | 0 | 0
4898 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01991/2023-2024 | BP-2023-24-238 | 11/09/2023 | 0 | WBSEDCL | 9.53 | 0 | 0
4899 | S24 Pgns Mechanical |  | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Bhagabanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/18575) |  |  | ORD/000322/2024-2025 | 948/SMSD | 28/06/2024 | 15 | PS & ASSOCIATES | 0.58 | 0 | 0
4900 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Bhagabanpur scheme under SMD, P.H.E. Dte.(Block-Sonarpur) (SM/18575) |  |  | ORD/000386/2024-2025 | 1012/SMSD | 11/07/2024 | 15 | PS & ASSOCIATES | 0.92 | 0 | 0
4901 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Bhagabanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000601/2023-2024 | 2640/SMD | 10/08/2023 | 90 | M/S. PS & ASSOCIATES | 25.93 | 0 | 0
4902 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bhagabanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) |  |  | ORD/002348/2023-2024 | 326/SMSD | 14/03/2024 | 15 | PS & ASSOCIATES | 0.92 | 0 | 0
4903 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BHAGABANPUR PWSS within Sonarpur Block "BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18575) |  |  | ORD/000231/2024-2025 | 2651/SWD-I | 07/06/2024 | 360 | MOTIONMASS TECHNO OPC PVT LTD | 12.17 | 0 | 50
4904 | South 24 Pgs W/S Division I |  | Construction of Platform for providing FHTC for Ground water based BHAGABANPUR piped water supply scheme to accommadate FHTC in Sonarpur block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18575) |  |  | ORD/000331/2024-2025 | 3269/SWD-I | 22/07/2024 | 60 | KALIPADA JANA | 56.68 | 0 | 0
4905 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BHAGABANPUR PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017739] |  |  | ORD/000370/2023-2024 | 1779/SWD-I | 11/08/2023 | 15 | DEBASHIS DAS | 31.76 | 0 | 100
4906 | South 24 Pgs W/S Division I |  | Construction of 400 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3047) (TSM/017739) |  |  | ORD/000384/2023-2024 | 1820/SWD-I | 16/08/2023 | 685 | GARAI INFRA PROJECT | 628.07 | 0 | 25
4907 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain, development of land & others allied works at headwork site of BHAGABANPUR PWSS within Sonarpur Block "BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18575) |  |  | ORD/000817/2023-2024 | 1310/SWD-I | 15/03/2024 | 405 | TOJO ENTERPRISE | 37.21 | 0 | 20
4908 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 21.59 | 0 | 0
4909 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 248/SWD-I | 10/01/2024 | 0 | Resource Division | 18.77 | 0 | 0
4910 | S24 Pgns Mechanical |  | Quotation for new service connection at PH NO.1 of Biseswarpur w/s scheme . Application no.1008233157 . |  |  | BILL/02235/2024-2025 | BP-2024-25-496 | 19/12/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
4911 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Bishweshwarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] |  |  | ORD/000753/2023-2024 | 2684/SMD | 16/08/2023 | 90 | WEST BENGAL ENGINEERING CO. | 23.38 | 0 | 0
4912 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BISHWESHWAR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017284] |  |  | ORD/000364/2023-2024 | 1773/SWD-I | 11/08/2023 | 30 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 0 | 100
4913 | South 24 Pgs W/S Division I |  | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18678) |  |  | ORD/000384/2024-2025 | 3575/SWD-I | 12/08/2024 | 548 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 241.51 | 0 | 15
4914 | South 24 Pgs W/S Division I |  | Construction of 01 (one) no. 350 Cum capacity 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 02 (two) nos. chlorination room of size 5.0m x 4.0m for BISHWESHWARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2530] [TSM/017284] |  |  | ORD/000507/2023-2024 | 2221/SWD-I | 12/09/2023 | 932 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 646.17 | 0 | 45
4915 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bishweshwarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000981/2022-2023 | 1455/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.8 | 0 | 100
4916 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 3395/SWD-I | 10/03/2023 | 0 | Resource Division | 15.58 | 0 | 0
4917 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 32.9 | 0 | 0
4918 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Mallikput water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000531/2022-2023 | 458/SMD | 17/02/2023 | 90 | BARISAL TRADING CO. | 13.01 | 0 | 0
4919 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tubewell by Rotary method for MALLICKPUR (Part-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte., within South 24 Parganas District under JJM. [AAFS - GO22223004569PH] [Project ID- PH222355766S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000069/2022-2023 | 1114/SWD-I | 23/08/2022 | 1200 | PADMA ENGINEERING CO. | 20.08 | 0 | 100
4920 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR, PART-I Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000222/2021-2022 | 1958/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.62 | 0 | 100
4921 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Mallickpur (Mallickpur C.T, J.L- 10) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (PART-I) (No. of FHTC = 813) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 1799/SWD-I | 09/11/2022 | 90 | DIPALI CONSTRUCTION | 102.68 | 0 | 0
4922 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Mallikpur (I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/009674] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000800/2022-2023 | 3672/SWD-I | 29/03/2023 | 960 | PADMA ENGINEERING CO. | 2.2 | 0 | 100
4923 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000184/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 5.99 | 0 | 0
4924 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Piprakhali PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000070/2023-2024 | 51/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4925 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Piprakhali PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000189/2024-2025 | 924/AD | 05/03/2025 | 60 | M/S PARAMESWAR CHOWDHURY | 55.38 | 0 | 0
4926 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Piprakhali W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000270/2023-2024 | 1420/AD | 13/07/2023 | 45 | M/S PARAMESWAR CHOWDHURY | 39.73 | 0 | 100
4927 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Piprakhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000342/2022-2023 | 4069/AD | 18/08/2022 | 45 | M. R. ENTERPRISE (I) | 36.69 | 0 | 50
4928 | Alipore Division | Kakdwip Sub-Division | Laying of 63 mm dia. UPVC pipe line for providing FHTC to the household under JJM at Piprakhali W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000425/2023-2024 | 1913/AD | 01/08/2023 | 20 | BABUN ENTERPRISE | 4.86 | 0 | 100
4929 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PIPRAKHALI PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000468/2022-2023 | 2491/AD | 27/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.04 | 0 | 100
4930 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Piprakhali Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000679/2022-2023 | 5978/AD | 20/10/2022 | 300 | PARAMESWAR CHOWDHURY | 223.76 | 0 | 52
4931 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Piprakhali W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000979/2023-2024 | 2998/AD | 26/09/2023 | 30 | M/S M.B.ENTERPRISE | 9.02 | 0 | 0
4932 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Piprakhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001047/2024-2025 | 4968/AD | 04/12/2024 | 30 | SIMPLEX DRILLING CO. | 20.37 | 0 | 0
4933 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Piprakhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001054/2023-2024 | 3373/AD | 11/10/2023 | 45 | M/S. TRIPATHI & CO. | 26.76 | 0 | 0
4934 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
4935 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000091/2023-2024 | 537/AD | 12/05/2023 | 0 | Resource Division | 3.86 | 0 | 0
4936 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000518/2023-2024 | 4940/AD | 22/12/2023 | 0 | Resource Division | 9.94 | 0 | 0
4937 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000585/2023-2024 | 59/AD | 03/01/2024 | 0 | Resource Division | 0.67 | 0 | 0
4938 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000949/2023-2024 | 1683/AD | 22/03/2024 | 0 | Resource Division | 23.18 | 0 | 0
4939 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00014/2023-2024 | BP-2023-24-39 | 18/05/2023 | 0 | WBSEDCL | 4.23 | 0 | 0
4940 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01713/2023-2024 | BP-2023-24-204 | 09/08/2023 | 0 | WBSEDCL | 3.89 | 0 | 0
4941 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Pirkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000356/2022-2023 | 3760/SMD | 29/12/2022 | 90 | JAI BHARAT COMMERCIAL CORPORATION | 19.22 | 0 | 0
4942 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Piprakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000358/2022-2023 | 3761/SMD | 29/12/2022 | 90 | JAI BHARAT COMMERCIAL CORPORATION | 19.22 | 0 | 40
4943 | Alipore Division | Baruipur Sub-Division | Road restoration of L023- Shyamnagar F.P. School to Purba Gobindapur PWD Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01783/2024-2025 | BP-2024-25-808 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.73 | 0 | 0
4944 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05024/2023-2024 | BP-2023-24-569 | 12/03/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
4945 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Charaghata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 588/SMD | 24/02/2023 | 90 | SAIKAT ENTERPRISE | 22.37 | 0 | 0
4946 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHARAGHATA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1857) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000273/2022-2023 | 1806/SWD-I | 09/11/2022 | 900 | PATH MAKERS | 485.76 | 0 | 100
4947 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Charaghata of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 2211/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 0
4948 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHARAGHATA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000449/2021-2022 | 1961/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
4949 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of Irrigation embankment road for Ground water based CHARAGHATA Piped Water Based Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns. W/S Division-I, P.H.E Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/11787) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000795/2023-2024 | 1143/SWD-I | 07/03/2024 | 30 | L.N. ENTERPRISE | 24.27 | 0 | 100
4950 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for laying distribution system, at CHARAGHATA PWSS of JOYNAGAR-I Block, for implementation of surface water based W/S scheme in the arsenic affected areas of South 24-Parganas district under Baruipur Sub-Division of South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 1136/SWD-I | 06/03/2024 | 60 | PATH MAKERS | 34.21 | 0 | 100
4951 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 no. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHARAGHATA Piped Water Supply Scheme to accommodate FHTC in JOYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11787] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001123/2024-2025 | 157/SWD-I | 15/01/2025 | 30 | ANCHAR ALI GHORAMI | 19.11 | 0 | 0
4952 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000076/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 142.64 | 0 | 0
4953 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Electricity Bills | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00262/2022-2023 | BP-2022-23-402 | 20/01/2023 | 0 | WBSEDCL | 3.41 | 0 | 0
4954 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of Quotation for new service connection at Jalilpur PWSS PH No- 2 under Bishnupur-I Block. Application No- 1008249626 Application Date- 09-12-2024 Reference ID- 106856015 Memo No- 1008249626/Quot/03 | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/02237/2024-2025 | BP-2024-25-509 | 19/12/2024 | 0 | WBSEDCL | 3.65 | 0 | 0
4955 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jalilpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000281/2022-2023 | 151/SMD | 16/01/2023 | 90 | AHALYA ENGINEERING WORKS | 23.87 | 0 | 60
4956 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 1st Tube well site for Ground water based JALILPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgs Mechanical Division, PHE Dte. South 24 Parganas District. [SM/11988] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/001296/2024-2025 | 365/SMD | 06/02/2025 | 60 | PADMA ENGINEERING CO. | 0 | 0 | 0
4957 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Improvement of external illumination arrangement with other allied works at P.H. No. 1 under Jalilpur Water Supply Scheme, South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I)(SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/002455/2023-2024 | 207-AE-II-SMD | 28/02/2024 | 15 | PS & ASSOCIATES | 0.75 | 0 | 100
4958 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply & delivery of standby submersible pumping machinery at PH-1 of Jalilpur w/s Scheme under south 24 pgs Mechanical Division, PHE Dte.( Block-Bishnupur-I) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/002505/2022-2023 | ..296/AE-II/SMD | 20/03/2023 | 15 | AHALYA ENGINEERING WORKS | 0.54 | 0 | 100
4959 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges on Amtala Baruipur Road due to laying of HDPE of 50% of estimate value i.e. 4357850 x 50% = 217893 as per minutes of meeting with Hon'ble MIC. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00289/2022-2023 | BP-2022-23-223 | 09/03/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 2.18 | 0 | 0
4960 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for Initial 50% Amount of the Estimated cost Rs. 1791575.00 (Seventeen Lakh Ninety One Thousand Five Hundred Seventy Five Only) i.e Rs. 895788.00 ( Eight Lakh Ninty Five Thousand Seven Hundred Eighty Eight only). Towards Road Restoration work for damages due to Laying of HDPE pipe line near Chainage 6.300 kmp to 7.300kmp of Amtala Baruipur road in the district of s24 parganas under ground water based Jalilpur PWSS to accommodate FHTC in Bishnupur I block under SWD-I PHE.Dte (TSM/011226,SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00652/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 8.96 | 0 | 0
4961 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 150mm x 100 mm dia. & 300 mtr. deep Tubewell by Rotary method for JALILPUR PWSS of BISHNUPUR-I Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000166/2022-2023 | 1345/SWD-I | 19/09/2022 | 30 | ANANTA KUMAR GIRI | 9.65 | 0 | 100
4962 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed JALILPUR PWSS in Arsenic affected areas of South 24 Pgs. Dist in BISHNUPUR-I Block, under South 24 Pgs W/S Division - I, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000168/2022-2023 | 1346/SWD-I | 19/09/2022 | 986 | GROWING CONCERN | 53.19 | 0 | 99
4963 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second tubewell site for JALILPUR Piped Water Supply Scheme OF BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011226] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000202/2023-2024 | 1386/SWD-I | 12/07/2023 | 30 | MONA CONSTRUCTION | 15.87 | 0 | 0
4964 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
4965 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for JALILPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, Dist.-South 24-Pgns. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000326/2022-2023 | 2026/SWD-I | 29/11/2022 | 1078 | MONDAL PRECISION PVT. LTD. | 122.11 | 0 | 90
4966 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "JALILPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000401/2022-2023 | 461/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.44 | 0 | 100
4967 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying additional pipeline of distribution system with laying of rising main from 2nd tubewell site for JALILPUR PWSS to accommondate FHTC in BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000512/2024-2025 | 3980/SWD-I | 11/09/2024 | 30 | S.P. ENTERPRISE | 13.77 | 0 | 80
4968 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall and Pump House at 2nd tubewell site for JALILPUR PWSS of BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000518/2024-2025 | 3981/SWD-I | 11/09/2024 | 60 | S. DAS ENTERPRISE | 12.61 | 0 | 1
4969 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd tubewell site for JALILPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11988] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000669/2024-2025 | 4442/SWD-I | 28/10/2024 | 30 | RAJKUMAR MONDAL | 15.9 | 0 | 90
4970 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 150mm x 100mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for JALILPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Divn-I, P.H.E. Dte. [TSM/011226][2nd Call] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000687/2022-2023 | 3486/SWD-I | 15/03/2023 | 30 | MD. IFTIKAR HASAN | 10.6 | 0 | 0
4971 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000016/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 3.34 | 0 | 0
4972 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000105/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 16.97 | 0 | 0
4973 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 219.10 mm dia. (OD) M.S. distribution line for crossing of Karanjali Canal at Karanjali bridge (Node point 249 to 253) for Providing distribution network under the Augmentation scheme of Kulpi Zone-IX within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District-South-24 Parganas under Diamond Harbour Sub- Division, of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000069/2025-2026 | 2258/AD | 14/05/2025 | 30 | SRIJON ENTERPRISE | 39.56 | 0 | 0
4974 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 600 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IX at Krishnachandrapur of Kulpi Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000331/2024-2025 | 2748/AD | 26/06/2024 | 90 | M/S GHOSH & CO. | 60.27 | 0 | 60
4975 | Alipore Division | Diamond Harbour Sub-Division | Restoration of W.B.M damaged due to laying of pipes from Raghunathpur more to Rajarampur F.P School under Kulpi Zone X under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000349/2025-2026 | 3130/AD | 03/07/2025 | 30 | SAMIM AHMED | 11.64 | 0 | 100
4976 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation of different capacities for the proposed R.C.C. Over Head Reservoir at (Zone IX, OHR Size-450 Cum. Mouza - Karanjali ) of Kulpi Block and at Moukhali W/S Scheme (OHR Size-350 Cum., Mouza - Moukhali) of Budge Budge-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000365/2022-2023 | 198/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 30
4977 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IX at Kulpi block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000561/2023-2024 | 3736/AD | 03/11/2023 | 879 | M/S GHOSH & CO. | 905.65 | 0 | 100
4978 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IX of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001022/2022-2023 | 295/DHSD | 15/09/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 3.59 | 0 | 98
4979 | Alipore Division | Diamond Harbour Sub-Division | Repairing of boundary wall at Pump House No-2 under Karanjali PWSS under Zone- IX of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001369/2024-2025 | 5498/AD | 27/12/2024 | 30 | SANKAR HALDER | 5.36 | 0 | 100
4980 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-X of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002490/2024-2025 | 781/AD | 25/02/2025 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 21.59 | 0 | 0
4981 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000212/2023-2024 | 2021/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
4982 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000364/2023-2024 | 3228/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4983 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000629/2023-2024 | 291/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
4984 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000671/2023-2024 | 424/AD | 22/01/2024 | 0 | Resource Division | 24.29 | 0 | 0
4985 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000897/2023-2024 | 791/AD | 03/02/2024 | 0 | Resource Division | 11.21 | 0 | 0
4986 | Alipore Division | Kakdwip Sub-Division | Relaying and repairing of pipe line for FHTC work of Budhkhali, Madhukhali, Golabari Mouza at Budhkhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000029/2022-2023 | 515/AD | 26/04/2022 | 30 | MS SINHA ROY & CO | 38.8 | 0 | 100
4987 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
4988 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001098/2022-2023 | 8433/AD | 15/12/2022 | 60 | M/S. UMA CONSTRUCTION | 88.4 | 0 | 100
4989 | Alipore Division | Kakdwip Sub-Division | Construction of Rising Main, Platform, Road Restoration and Y junction for Augmentation of Rajnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000406/2024-2025 | 3189/AD | 31/07/2024 | 60 | UCON (II) | 45.01 | 0 | 0
4990 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Pulaha and Pulastha of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000453/2020-2021 | 841/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.67 | 3.43 | 0
4991 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Angira and Atri of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte.(Part-1) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000461/2020-2021 | 851/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.69 | 3.75 | 0
4992 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000799/2023-2024 | 644/AD | 30/01/2024 | 0 | Resource Division | 7.78 | 0 | 0
4993 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Majherpara, Laskarpara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000209/2020-2021 | 644/KSD | 19/08/2020 | 15 | SARADA CONSTRUCTION | 4.48 | 0 | 95
4994 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Paschimpara, Panupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000210/2020-2021 | 645/KSD | 19/08/2020 | 15 | G.M. ENTERPRISE | 4.48 | 0 | 0
4995 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Ramtanupara, Tulsitala and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000211/2020-2021 | 646/KSD | 19/08/2020 | 15 | PIJUSH KANTI TRIPATHI | 4.48 | 0 | 0
4996 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Ramtanupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000448/2020-2021 | 834/KSD | 16/10/2020 | 45 | FORTUNE ENGINEERING | 4.45 | 0 | 96
4997 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Madhya Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000452/2020-2021 | 838/KSD | 16/10/2020 | 45 | FORTUNE ENGINEERING | 3.59 | 0 | 97
4998 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Muslim Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000454/2020-2021 | 842/KSD | 16/10/2020 | 45 | SARADA CONSTRUCTION | 3.7 | 0 | 96
4999 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. existing big dia Tubewell of Ramtanunagar, Block- Kakdwip and Debnibus W/S Scheme, Block- Namkhana for smooth water supply in existing FHTC under JJM under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000508/2024-2025 | 3608/AD | 06/09/2024 | 30 | S.K.GOLUI | 4.94 | 0 | 100
5000 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.07.2024 to 30.09.2024 - 3 months] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000534/2024-2025 | 2523/AD | 18/06/2024 | 92 | PARBATI MONDAL | 1.2 | 0 | 100
5001 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for FHTC work of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000902/2021-2022 | 762/KSD | 29/11/2021 | 30 | SARADA CONSTRUCTION | 4.58 | 0 | 100
5002 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.10.2024 to 31.12.2024 - 3 months] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000985/2024-2025 | 4002/AD | 28/09/2024 | 91 | PARBATI MONDAL | 1.2 | 0 | 75
5003 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002176/2022-2023 | 652/KSD | 31/01/2023 | 181 | PIKASU BOSE | 2.39 | 0 | 90
5004 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000827/2023-2024 | 672/AD | 30/01/2024 | 0 | Resource Division | 7.13 | 0 | 0
5005 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000204/2020-2021 | 641/KSD | 19/08/2020 | 15 | AVIRUP CONSTRUCTION | 4.48 | 3.11 | 0
5006 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000206/2020-2021 | 642/KSD | 19/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 90
5007 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000208/2020-2021 | 643/KSD | 19/08/2020 | 15 | M/S B. ENTERPRISE | 4.48 | 0 | 90
5008 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 184 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000447/2020-2021 | 833/KSD | 16/10/2020 | 45 | MAA LAXMI ENTERPRISE | 3.26 | 0 | 90
5009 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000449/2020-2021 | 835/KSD | 16/10/2020 | 45 | M/S B. ENTERPRISE | 4.51 | 4.46 | 0
5010 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 185 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000450/2020-2021 | 836/KSD | 16/10/2020 | 45 | MAA LAXMI ENTERPRISE | 4.01 | 0 | 90
5011 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000455/2020-2021 | 843/KSD | 16/10/2020 | 45 | M/S B. ENTERPRISE | 4.56 | 4.52 | 0
5012 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
5013 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 2no Tube well of Hesamabad Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000596/2022-2023 | 5921/AD | 19/10/2022 | 15 | S.K.GOLUI | 7.37 | 0 | 100
5014 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
5015 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Hesamabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07576) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002159/2024-2025 | 1989/KSD | 23/12/2024 | 25 | IMAGINEER VENTURES | 2.06 | 0 | 0
5016 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002501/2020-2021 | 611/KSD | 12/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.47 | 0 | 90
5017 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002502/2020-2021 | 627/KSD | 13/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 90
5018 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000280/2023-2024 | 3079/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5019 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000839/2023-2024 | 684/AD | 30/01/2024 | 0 | Resource Division | 6.8 | 0 | 0
5020 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Hesamabad W/S Scheme (Phase-A), Chandipur W/S Scheme (Phase-A), Gangadharpur W/S Scheme (Phase-A) & Nebutala W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 512/AD, 24.08.21, T.No. 1761/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | VCH/002606/2021-2022 | BP-2021-22-509 | 22/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 4.71 | 0 | 0
5021 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance of Retrofitting of distribution system for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000039/2022-2023 | 977/SWD-I | 27/07/2022 | 45 | CALCON CONSTRUCTIONS | 15.8 | 0 | 100
5022 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6134 ) PART-VI | AE SWSD-I |  | ORD/000466/2022-2023 | 2775/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 2.72 | 0 | 100
5023 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Dwariknagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001369/2020-2021 | 5367/AD | 19/02/2021 | 365 | M/S. PROMILA CONSTRUCTION | 98.02 | 0 | 75
5024 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000796/2023-2024 | 641/AD | 30/01/2024 | 0 | Resource Division | 5.4 | 0 | 0
5025 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000475/2022-2023 | 5526/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 18.32 | 0 | 0
5026 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000607/2020-2021 | 846/CSD | 12/10/2020 | 45 | SUSHANTA MANDAL | 4.73 | 4.73 | 0
5027 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000608/2020-2021 | 848/CSD | 12/10/2020 | 45 | SUKANTA HALDER | 4.74 | 4.72 | 0
5028 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000631/2020-2021 | 845/CSD | 12/10/2020 | 45 | PRASANTA MONDAL | 4.74 | 0 | 100
5029 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000650/2020-2021 | 847/CSD | 12/10/2020 | 45 | KAMALA ENTERPRISE (I) | 4.72 | 4.71 | 0
5030 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000848/2021-2022 | 3198/AD | 11/11/2021 | 365 | UNITED BUILDERS | 99.47 | 0 | 63
5031 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001429/2020-2021 | 995/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.6 | 4.59 | 100
5032 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001430/2020-2021 | 996/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.64 | 4.62 | 100
5033 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001440/2020-2021 | 965/CSD | 07/11/2020 | 45 | M/S R.K.ENTERPRISE | 4.62 | 4.6 | 100
5034 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001441/2020-2021 | 966/CSD | 07/11/2020 | 45 | L.N. ENTERPRISE | 4.7 | 4.68 | 100
5035 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001443/2020-2021 | 997/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.71 | 0 | 0
5036 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001444/2020-2021 | 1007/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.67 | 4.65 | 100
5037 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001445/2020-2021 | 998/CSD | 13/11/2020 | 45 | M/S M.G.CONSTRUCTION | 4.72 | 4.71 | 100
5038 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001446/2020-2021 | 999/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.79 | 4.78 | 100
5039 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001447/2020-2021 | 1008/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.63 | 4.62 | 100
5040 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001448/2020-2021 | 1000/CSD | 13/11/2020 | 45 | SUKANTA HALDER | 4.75 | 4.74 | 100
5041 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001449/2020-2021 | 1009/CSD | 13/11/2020 | 45 | SUKANTA HALDER | 4.69 | 0 | 0
5042 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001450/2020-2021 | 1010/CSD | 13/11/2020 | 45 | SURYA ENTERPRISE | 4.74 | 4.41 | 100
5043 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001452/2020-2021 | 1001/CSD | 13/11/2020 | 45 | M/S M.G.CONSTRUCTION | 4.72 | 4.71 | 100
5044 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001453/2020-2021 | 1002/CSD | 13/11/2020 | 45 | C.S. CONSTRUCTION | 4.79 | 4.79 | 100
5045 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001454/2020-2021 | 1011/CSD | 13/11/2020 | 45 | NAZRUL ENTERPRISE | 4.72 | 0 | 0
5046 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001458/2020-2021 | 1012/CSD | 13/11/2020 | 45 | JAGANNATH ENTERPRISE | 4.77 | 0 | 100
5047 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001543/2020-2021 | 1202/CSD | 15/12/2020 | 45 | SUKANTA HALDER | 4.78 | 0 | 0
5048 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001544/2020-2021 | 1203/CSD | 15/12/2020 | 45 | SUSHANTA MANDAL | 4.73 | 0 | 0
5049 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001549/2020-2021 | 1204/CSD | 15/12/2020 | 45 | SARKAR ENTERPRISE | 4.78 | 4.76 | 100
5050 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001550/2020-2021 | 1205/CSD | 15/12/2020 | 45 | SUKANTA HALDER | 4.78 | 4.76 | 100
5051 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001551/2020-2021 | 1206/CSD | 15/12/2020 | 45 | C.S. CONSTRUCTION | 4.75 | 4.74 | 100
5052 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001552/2020-2021 | 1207/CSD | 15/12/2020 | 45 | MODERN CONSTRUCTION | 4.73 | 4.71 | 100
5053 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001553/2020-2021 | 1208/CSD | 15/12/2020 | 45 | KUNDU CONSTRUCTION CO. | 4.7 | 0 | 0
5054 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001555/2020-2021 | 1209/CSD | 15/12/2020 | 45 | HALDER & CO. | 4.65 | 0 | 0
5055 | Alipore Division | Canning Sub-division | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 30 | MODERN CONSTRUCTION | 4.82 | 0 | 100
5056 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 30 | MODERN CONSTRUCTION | 4.68 | 0 | 100
5057 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.73 | 0 | 100
5058 | Alipore Division | Canning Sub-division | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.74 | 0 | 100
5059 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 270 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0
5060 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Adhia Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001306/2020-2021 | 2223/AD | 08/10/2020 | 365 | M/S. MIHIR KUMAR NASKAR | 85.78 | 27.8 | 75
5061 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bhaleya Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001217/2020-2021 | 1619/AD | 28/08/2020 | 365 | PUTUL RANI MAITY | 86.44 | 35.93 | 92
5062 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Para (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000406/2020-2021 | 777/KSD | 14/10/2020 | 45 | M/S. M.S. ENTERPRISE | 4.78 | 4.44 | 0
5063 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Khasramkarchar (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000418/2020-2021 | 795/KSD | 15/10/2020 | 45 | M/S BABUSONA ENTERPRISE | 4.79 | 4.46 | 0
5064 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Khas Ramkarchar (Phase-B) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000418/2023-2024 | 1907/AD | 01/08/2023 | 30 | FORTUNE ENGINEERING | 25.22 | 0 | 100
5065 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Muslim Para (Part) of Khasramkarchar W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000437/2020-2021 | 823/KSD | 16/10/2020 | 45 | M/S. PAPIYA ENTERPRISE | 3.93 | 3.56 | 0
5066 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Khas Ramkarchar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000526/2023-2024 | 352/KSD | 09/08/2023 | 470 | S.K.GOLUI | 3.55 | 0 | 100
5067 | Alipore Division | Kakdwip Sub-Division | Construction of approach road, earth work and other allied work of Khas Ramkarchar Water supply scheme, Block-Sagar under Kakdwip Sub division of Alipore Division, P.H.E Dte. (SM/18871) (SM/07756) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002275/2024-2025 | 580/AD | 13/02/2025 | 30 | M/S RELIABLE ENTERPRISE | 12.55 | 0 | 0
5068 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000334/2023-2024 | 3149/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5069 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000713/2023-2024 | 483/AD | 24/01/2024 | 0 | Resource Division | 8.91 | 0 | 0
5070 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Srikrishnanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/09435) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000206/2024-2025 | 2589/AD | 19/06/2024 | 45 | SARADA CONSTRUCTION | 34.89 | 0 | 0
5071 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srikrishnanagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000400/2020-2021 | 3855/AD | 03/12/2020 | 365 | L.N. ENTERPRISE | 27.43 | 0 | 100
5072 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRIKRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000498/2022-2023 | 314/AD | 13/04/2022 | 45 | LEMNISCATE | 1.79 | 0 | 0
5073 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along with rising main for Augmentation of Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001483/2021-2022 | 6393/AD | 02/03/2022 | 60 | SARADA CONSTRUCTION | 71.83 | 0 | 98
5074 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
5075 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000056/2022-2023 | 3915/AD | 12/08/2022 | 0 | Resource Division | 9.19 | 0 | 0
5076 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000267/2023-2024 | 3065/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5077 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000673/2023-2024 | 439/AD | 24/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
5078 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000828/2023-2024 | 673/AD | 30/01/2024 | 0 | Resource Division | 4.19 | 0 | 0
5079 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Haradhanpur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001142/2021-2022 | 5531/AD | 20/01/2022 | 365 | UNIVERSAL CORPORATION | 68.89 | 0 | 97
5080 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002177/2022-2023 | 653/KSD | 31/01/2023 | 181 | BADSHA ALOM | 2.39 | 0 | 70
5081 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000014/2022-2023 | 1169/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
5082 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000016/2021-2022 | 5622/AD | 25/01/2022 | 0 | Resource Division | 6.19 | 0 | 0
5083 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000682/2023-2024 | 452/AD | 24/01/2024 | 0 | Resource Division | 3.06 | 0 | 0
5084 | Alipore Division | Raidighi Sub-Division | Remodeling of Distribution System of Krishnachandrapur PWS Scheme as Zone-III of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000034/2022-2023 | 597/AD | 28/04/2022 | 30 | M/S B.M. CONSTRUCTION | 95.84 | 0 | 50
5085 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - III (Krishnachandrapur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000611/2023-2024 | 242/RSD | 22/08/2023 | 30 | M/S. M.M. ENTERPRISE | 4.49 | 0 | 98
5086 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Dakatmari area under Krishnachandrapur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001589/2021-2022 | 773/RSD | 28/03/2022 | 60 | M/S M. ENTERPRISE | 4.79 | 0 | 98
5087 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000024/2022-2023 | 1680/AD | 13/06/2022 | 0 | Resource Division | 15.38 | 0 | 0
5088 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000034/2021-2022 | 6489/AD | 08/03/2022 | 0 | Resource Division | 32.96 | 0 | 0
5089 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000034/2022-2023 | 3586/AD | 29/07/2022 | 0 | Resource Division | 56.23 | 0 | 0
5090 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
5091 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- II, Mathurapur-II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000345/2023-2024 | 3372/AD | 11/10/2023 | 630 | M/S. TAPAS MONDAL | 114.8 | 0 | 20
5092 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000997/2023-2024 | 294/RSD | 29/09/2023 | 60 | TIYASHA ENTERPRISE | 2.99 | 0 | 100
5093 | Alipore Division | Raidighi Sub-Division | Repairing of pump house ¿ 2 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001001/2023-2024 | 295/RSD | 29/09/2023 | 60 | JOY MAA TARA ENTERPRISE | 3.14 | 0 | 100
5094 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 3 and approach road and plinth protection including boundary wall at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001002/2023-2024 | 296/RSD | 29/09/2023 | 60 | SUKUMAR HALDAR | 3.11 | 0 | 100
5095 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 and approach road and plinth protection at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001004/2023-2024 | 297/RSD | 29/09/2023 | 60 | SUKUMAR HALDAR | 2.26 | 0 | 100
5096 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001912/2023-2024 | 1434/AD | 09/03/2024 | 30 | NITYANANDA MONDAL | 14.82 | 0 | 95
5097 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002254/2024-2025 | 556/AD | 12/02/2025 | 120 | M/S BANERJEE ENGINEERING SYSTEM | 27.31 | 0 | 0
5098 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000075/2022-2023 | 5148/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
5099 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I). | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000409/2024-2025 | 3203/AD | 01/08/2024 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 27.65 | 0 | 0
5100 | Alipore Division | Kakdwip Sub-Division | Surging of 3 nos. Tubewell for Augmentation of Bishnupur- 1 no., Mahishamari- 1 no., Kamalpur Rudranagar- 1 no. W/S Scheme under JJM, Block - Sagar under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000506/2024-2025 | 3607/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 5.34 | 0 | 100
5101 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works and other allied works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/10151) (SM/08795) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000550/2024-2025 | 3779/AD | 18/09/2024 | 179 | NITYANANDA MONDAL | 60.65 | 0 | 100
5102 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Naraharipur W/S Scheme (Phase-A), Purusottampur W/S Scheme (Phase-A), Kamalpur Rudranagar W/S Scheme (Phase-A) & Khasramkar Char W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001011/2021-2022 | 517/KSD | 24/08/2021 | 10 | M/S R.DUTTA & CO. | 4.7 | 0 | 100
5103 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001059/2021-2022 | 2347/AD | 09/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.09 | 0 | 100
5104 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001086/2021-2022 | 577/KSD | 10/09/2021 | 20 | M/S R.DUTTA & CO. | 4.23 | 0 | 100
5105 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001615/2021-2022 | 614/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 2.96 | 0 | 100
5106 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000707/2023-2024 | 477/AD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0
5107 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Gangasagar W/S Scheme (Phase-A), Kachuberia W/S Scheme (Phase-A), Khansaheber Abad W/S Scheme (Phase-A) & Mandirlata W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001010/2021-2022 | 516/KSD | 24/08/2021 | 10 | INDRANIL DUTTA & ASSOCIATES | 4.7 | 0 | 100
5108 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Khansaheber Abad & Naraharipur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001056/2021-2022 | 2344/AD | 09/09/2021 | 7 | LEMNISCATE | 4.48 | 0 | 100
5109 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Khan Saheber Abad W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001082/2021-2022 | 573/KSD | 10/09/2021 | 20 | M/S R.DUTTA & CO. | 3.88 | 0 | 100
5110 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001085/2023-2024 | 3499/AD | 16/10/2023 | 90 | S.P. CONSTRUCTION (V) | 110.29 | 0 | 78
5111 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000321/2023-2024 | 3136/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5112 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000536/2023-2024 | 20/AD | 02/01/2024 | 0 | Resource Division | 11.16 | 0 | 0
5113 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 03 (three) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhuri Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000009/2021-2022 | 3019/AD | 02/11/2021 | 365 | SOMBHUNATH BHATTACHARJEE | 92.97 | 0 | 0
5114 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000161/2023-2024 | 1051/AD | 15/06/2023 | 0 | Resource Division | 17.89 | 0 | 0
5115 | Alipore Division | Canning Sub-division | Laying of pipe line and FHTC work at Hiranmoypur W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000327/2024-2025 | 2731/AD | 25/06/2024 | 371 | R.S.CONSTRUCTION CO. | 197.64 | 0 | 25
5116 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hiranmoypur Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000562/2021-2022 | 3698AD | 22/11/2021 | 365 | G.B. CONSTRUCTION & CO. | 187.36 | 0 | 83
5117 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Retrofitting of Taldi (Zone - I and II) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000602/2023-2024 | 2351/AD | 18/08/2023 | 45 | SUPRITI ENTERPRISE | 53.79 | 0 | 100
5118 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000849/2021-2022 | 4430/AD | 06/12/2021 | 365 | SUPRITI ENTERPRISE | 277.8 | 0 | 32
5119 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000011/2021-2022 | 5617/AD | 25/01/2022 | 0 | Resource Division | 29.69 | 0 | 0
5120 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sambhunagar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000590/2021-2022 | 2984/AD | 29/10/2021 | 365 | M/S. S.S. ENTERPRISE | 160.98 | 0 | 81
5121 | Alipore Division | Canning Sub-division | Hiring Motor launch for Canning Sub Division under Alipore Division, PHE Dte. in connection with execution & maintenance of different piped water supply schemes at different island in the district of South 24 parganas.(Period 01/01/2022 to 30/06/2022) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001462/2021-2022 | 1289/CSD | 17/12/2021 | 181 | RAJKUMAR MANNA | 2.16 | 0 | 0
5122 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000644/2021-2022 | 3697/AD | 22/11/2021 | 365 | SPA ENTERPRISE | 172.91 | 0 | 48
5123 | Alipore Division | Canning Sub-division | Inter connection and rising main works of Retrofitting of Devis Abad W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/09011) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001024/2023-2024 | 3399/AD | 11/10/2023 | 45 | SPA ENTERPRISE | 26.17 | 0 | 75
5124 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001571/2021-2022 | 6834/AD | 23/03/2022 | 365 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 110.82 | 0 | 86
5125 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000383/2024-2025 | 3079/AD | 25/07/2024 | 30 | RANJIT CONSTRUCTION | 11.67 | 0 | 0
5126 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th Tubewell site for Bishnupur (Zone- I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000384/2024-2025 | 3080/AD | 25/07/2024 | 45 | M/S AINUR ENTERPRISE | 7.18 | 0 | 0
5127 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 45 | SWAPAN GUCHHAIT | 3.89 | 0 | 0
5128 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000693/2023-2024 | 463/AD | 24/01/2024 | 0 | Resource Division | 16.99 | 0 | 0
5129 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 4th Tubewell site of Namkhana Water Supply Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000020/2022-2023 | 214/AD | 11/04/2022 | 30 | M/S DAS ENTERPRISE | 5.16 | 0 | 0
5130 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Namkhana PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000059/2023-2024 | 43/KSD | 27/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
5131 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 4th Tubewell site of Namkhana Water Supply Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000064/2022-2023 | 958/AD | 20/05/2022 | 30 | SIMPLEX DRILLING CO. | 18.26 | 0 | 100
5132 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Namkhana W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000282/2023-2024 | 1432/AD | 13/07/2023 | 45 | BALAJEE ENTERPRISE. | 53.48 | 0 | 95
5133 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NAMKHANA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000487/2022-2023 | 301/AD | 12/04/2022 | 45 | M/S R.DUTTA & CO. | 5.91 | 0 | 100
5134 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Namkhana W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001029/2021-2022 | 543/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 4.59 | 0 | 100
5135 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Namkhana Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001102/2022-2023 | 8485/AD | 16/12/2022 | 837 | BALAJEE ENTERPRISE. | 691.56 | 0 | 100
5136 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Namkhana W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001613/2021-2022 | 612/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 2.33 | 0 | 100
5137 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
5138 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002186/2022-2023 | 690/KSD | 23/02/2023 | 365 | BIMALENDU GIRI | 0.81 | 0 | 100
5139 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000043/2022-2023 | 3907/AD | 12/08/2022 | 0 | Resource Division | 32.17 | 0 | 0
5140 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000286/2023-2024 | 3082/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5141 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000548/2023-2024 | 31/AD | 02/01/2024 | 0 | Resource Division | 18.71 | 0 | 0
5142 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000909/2023-2024 | 892/AD | 07/02/2024 | 0 | Resource Division | 1.52 | 0 | 0
5143 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000975/2023-2024 | 1768/AD | 27/03/2024 | 0 | Resource Division | 1.92 | 0 | 0
5144 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/01115/2023-2024 | BP-2023-24-163 | 24/07/2023 | 0 | WBSEDCL | 3.38 | 0 | 0
5145 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Namkhana Augmentation water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000469/2022-2023 | 280/SMD | 01/02/2023 | 90 | GLACIER ENGINEERING CO. | 9.79 | 0 | 80
5146 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Namkhana Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002367/2023-2024 | 911-AE-I-SMD | 11/08/2023 | 15 | GLACIER ENGINEERING CO. | 0.82 | 0 | 100
5147 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 197 to 198) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000157/2021-2022 | 1101/SWD-I | 25/10/2021 | 120 | NIRMAL UDYOG | 38.2 | 0 | 90
5148 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Iswaripur W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000529/2020-2021 | 586/CSD | 27/08/2020 | 365 | SUKANTA HALDER | 2.26 | 0 | 100
5149 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001190/2021-2022 | 5708/AD | 31/01/2022 | 365 | ASHIT BARAN BOSE | 84.89 | 0 | 100
5150 | Alipore Division | Canning Sub-division | Laying pipeline for dispose of waste water from IEP at Head Work Site of Iswaripur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001973/2022-2023 | 12592/AD | 13/03/2023 | 15 | BHUNIA BUILDERS | 5.97 | 0 | 100
5151 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000018/2022-2023 | 1175/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
5152 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000077/2023-2024 | 61/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
5153 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Mandirtala (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000278/2023-2024 | 1428/AD | 13/07/2023 | 630 | SUPRITI ENTERPRISE | 80.97 | 0 | 86
5154 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MANDIRTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000477/2022-2023 | 31/AD | 04/04/2022 | 45 | VOYAGER | 7.71 | 0 | 0
5155 | Alipore Division | Kakdwip Sub-Division | Surging of 01 no. Tubewell for augmentation of Mandirtala W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000524/2023-2024 | 351/KSD | 09/08/2023 | 20 | S.K.GOLUI | 1.77 | 0 | 100
5156 | Alipore Division | Kakdwip Sub-Division | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Mandirtala Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000781/2022-2023 | 6535/AD | 11/11/2022 | 300 | SUPRITI ENTERPRISE | 821.1 | 0 | 78
5157 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000050/2022-2023 | 3902/AD | 12/08/2022 | 0 | Resource Division | 148.87 | 0 | 0
5158 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000094/2022-2023 | 5588/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
5159 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000283/2023-2024 | 3058/AD | 28/09/2023 | 0 | Resource Division | 110.39 | 0 | 0
5160 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000323/2023-2024 | 3138/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5161 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000683/2023-2024 | 453/AD | 24/01/2024 | 0 | Resource Division | 1.44 | 0 | 0
5162 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories for Augmentation of Mandirtala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000568/2022-2023 | 587/SMD | 24/02/2023 | 90 | M/S. S.S. ENTERPRISE | 60.45 | 0 | 0
5163 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap connection (FHTC) to all the households related works in Zone-III of Mathurapur - II Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000071/2022-2023 | 1035/AD | 23/05/2022 | 1363 | UNITED BUILDERS | 45.42 | 0 | 75
5164 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-III (Kautala PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001451/2021-2022 | 6068/AD | 17/02/2022 | 1505 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 107.95 | 0 | 60
5165 | Alipore Division | Raidighi Sub-Division | Laying distribution system of damaged pipe line of Koutala piped water supply scheme at Zone- III of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002375/2023-2024 | 1215/AD | 29/02/2024 | 45 | KALIDAS ENTERPRISE | 13.5 | 0 | 100
5166 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000023/2022-2023 | 1679/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
5167 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000040/2022-2023 | 3581/AD | 29/07/2022 | 0 | Resource Division | 31.31 | 0 | 0
5168 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000077/2022-2023 | 5144/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
5169 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000079/2022-2023 | 5554/AD | 29/09/2022 | 0 | Resource Division | 8.15 | 0 | 0
5170 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000018/2022-2023 | 213/AD | 11/04/2022 | 30 | M/S BABUSONA ENTERPRISE | 5.15 | 0 | 100
5171 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000027/2022-2023 | 411/AD | 20/04/2022 | 30 | AQUATECH ENGINEER | 18.32 | 0 | 100
5172 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Herambagopalpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000066/2023-2024 | 47/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
5173 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Herambagopalpur W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000276/2023-2024 | 1426/AD | 13/07/2023 | 597 | GARGO TRADERS | 42.5 | 0 | 70
5174 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Herambogopalpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000458/2022-2023 | 293/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.27 | 0 | 100
5175 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
5176 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Herambagopalpur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000504/2023-2024 | 349/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.73 | 0 | 100
5177 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Herambagopalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2022-2023 | 5725/AD. | 13/10/2022 | 901 | GARGO TRADERS | 706.06 | 0 | 36
5178 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001076/2021-2022 | 546/KSD | 03/09/2021 | 20 | LEMNISCATE | 4.6 | 0 | 100
5179 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
5180 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001606/2021-2022 | 604/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.56 | 0 | 100
5181 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000044/2022-2023 | 3908/AD | 12/08/2022 | 0 | Resource Division | 19.42 | 0 | 0
5182 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000312/2023-2024 | 3121/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5183 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000571/2023-2024 | 76/AD | 03/01/2024 | 0 | Resource Division | 21.58 | 0 | 0
5184 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000940/2023-2024 | 1674/AD | 22/03/2024 | 0 | Resource Division | 7.49 | 0 | 0
5185 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Kumarkhali, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2968] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000148/2023-2024 | 741/AD | 22/05/2023 | 875 | G.B. CONSTRUCTION & CO. | 553.93 | 0 | 83
5186 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kumarkhali Water Supply Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000263/2022-2023 | 3496/AD | 26/07/2022 | 45 | A 8 T CONSTRUCTION | 6.77 | 0 | 98
5187 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumarkhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001120/2022-2023 | 8847/AD | 22/12/2022 | 30 | G.B. CONSTRUCTION (TW) | 19.51 | 0 | 0
5188 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Kumarkhali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001842/2021-2022 | 681/CSD | 18/08/2021 | 15 | HORIZEN | 3.66 | 0 | 100
5189 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Kumarkhali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001843/2021-2022 | 682/CSD | 18/08/2021 | 15 | HORIZEN | 2.89 | 0 | 100
5190 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Kumarkhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002182/2023-2024 | 833/AD | 05/02/2024 | 90 | ISHAN CONSTRUCTION | 87.63 | 0 | 90
5191 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
5192 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000046/2022-2023 | 3909/AD | 12/08/2022 | 0 | Resource Division | 110.14 | 0 | 0
5193 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000159/2023-2024 | 1054/AD | 15/06/2023 | 0 | Resource Division | 18.28 | 0 | 0
5194 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00749/2023-2024 | BP-2023-24-104 | 04/07/2023 | 0 | WBSEDCL | 2.67 | 0 | 0
5195 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kumarkhali Augmentation water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000538/2022-2023 | 477/SMD | 20/02/2023 | 90 | GOENKA ENTERPRISE | 26.03 | 0 | 40
5196 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kakdwip & Akshaynagar Zone-II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000050/2023-2024 | 36/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
5197 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC and Construction of Platform to all households for Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000200/2024-2025 | 2583/AD | 19/06/2024 | 316 | SWASTIK ENTERPRISE (NEW) | 10.04 | 0 | 100
5198 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for augmentation of Kakdwip Akshaynagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000201/2024-2025 | 2584/AD | 19/06/2024 | 230 | M/S B.N.ENTERPRISES | 37.98 | 0 | 100
5199 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Kakdwip Akshaynagar Zone-I W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000234/2023-2024 | 164/KSD | 02/06/2023 | 20 | S.K.GOLUI | 2.84 | 0 | 95
5200 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kakdwip Akshaynagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000273/2023-2024 | 1423/AD | 13/07/2023 | 45 | M/S. JHARNA ENTERPRISE | 41.66 | 0 | 100
5201 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying specials, etc. for Augmentation of Kakdwip Akshaynagar (Zone- I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-A) (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000303/2024-2025 | 2710/AD | 24/06/2024 | 60 | M/S. JHARNA ENTERPRISE | 144.99 | 0 | 0
5202 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 700 CuM at Kakdwip Akshaynagar Zone I, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000495/2025-2026 | 4426/AD | 09/09/2025 | 400 | SARADA CONSTRUCTION | 148.07 | 0 | 0
5203 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAKDWIP & AKSHOYNAGAR PWSS ) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000497/2022-2023 | 313/AD | 13/04/2022 | 45 | LEMNISCATE | 12.61 | 0 | 0
5204 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000503/2022-2023 | 4930/AD | 15/09/2022 | 1229 | M/S. JHARNA ENTERPRISE | 280.09 | 0 | 90
5205 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kakdwip Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-A) [No. of FHTC = 1782] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000545/2022-2023 | 5721/AD | 13/10/2022 | 1021 | L.N. ENTERPRISE | 215 | 0 | 98
5206 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000628/2022-2023 | 5980/AD | 20/10/2022 | 819 | M/S B.N.ENTERPRISE | 134.44 | 0 | 100
5207 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000665/2024-2025 | 981/KSD | 27/05/2024 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
5208 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000666/2024-2025 | 1254/KSD | 28/08/2024 | 91 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
5209 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) [No. of FHTC = 1220] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000768/2022-2023 | 6498/AD | 11/11/2022 | 90 | A.K. SIKDAR | 109.54 | 0 | 80
5210 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000778/2025-2026 | 968/KSD | 25/11/2025 | 92 | NAMITA PRADHAN | 1.21 | 0 | 0
5211 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [ No. of FHTC = 800] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001110/2022-2023 | 8486/AD | 16/12/2022 | 1001 | M/S KALPANA CONSTRUCTION | 109.65 | 0 | 90
5212 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
5213 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with construction of approach road at 1st Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002204/2024-2025 | 2106/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.2 | 0 | 0
5214 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with construction of approach road at 2nd Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002211/2024-2025 | 2107/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.16 | 0 | 0
5215 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall with construction of approach road at 4th Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002212/2024-2025 | 2108/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.09 | 0 | 0
5216 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall with construction of approach road at 1st Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002213/2024-2025 | 2109/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.18 | 0 | 0
5217 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall at 2nd Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002214/2024-2025 | 258/KSD | 31/01/2025 | 15 | M/S S.M. CONSTRUCTION | 2.98 | 0 | 100
5218 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002566/2023-2024 | 511/KSD | 15/03/2024 | 10 | M/S. R.M. CONSTRUCTION | 2.81 | 0 | 0
5219 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002841/2023-2024 | 380/KSD | 17/08/2023 | 184 | ANANTA KUMAR GIRI | 2.4 | 0 | 0
5220 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002843/2023-2024 | 409/KSD | 27/02/2024 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
5221 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002846/2024-2025 | 1655/KSD | 26/11/2024 | 90 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
5222 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002891/2024-2025 | 1665/KSD | 27/11/2024 | 90 | NAMITA PRADHAN | 1.2 | 0 | 0
5223 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003034/2024-2025 | 349/KSD | 27/02/2025 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
5224 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003682/2024-2025 | 353/KSD | 27/02/2025 | 92 | NAMITA PRADHAN | 1.21 | 0 | 0
5225 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000264/2023-2024 | 3064/AD | 28/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
5226 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000467/2023-2024 | 4727/AD | 18/12/2023 | 0 | Resource Division | 95.8 | 0 | 0
5227 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000836/2023-2024 | 681/AD | 30/01/2024 | 0 | Resource Division | 58.18 | 0 | 0
5228 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01722/2023-2024 | BP-2023-24-205 | 09/08/2023 | 0 | WBSEDCL | 19.62 | 0 | 0
5229 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kuruli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000535/2022-2023 | 462/SMD | 17/02/2023 | 90 | NUPUR CHANDRA HALDER | 23.62 | 0 | 100
5230 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No- 1 & 2 of Kuruli water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Baruipur ] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002195/2023-2024 | 353/SMSD | 20/03/2024 | 15 | SHRI KRISHNA ENTERPRISE | 0.78 | 0 | 100
5231 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kuruli W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002350/2023-2024 | 29/SMSD | 09/01/2024 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 100
5232 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kuruli W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002351/2023-2024 | 30/SMSD | 09/01/2024 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 100
5233 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kuruli W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002352/2023-2024 | 28/SMSD | 09/01/2024 | 15 | NUPUR CHANDRA HALDER | 0.58 | 0 | 100
5234 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning road, permanent restoration work for 5800 mtr of trench(0.00 Km-1.2 Km, 1.70 K.m-2.50 Km & 3.50Km-4.40 Km) Total trench length=5800 Mtr cause due to pipe laying work of PHED under South Parganas Division, PWD in the District of South 24 Parganas-During the year 2024-2025. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00542/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 75 | 0 | 0
5235 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for KURULI PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000077/2022-2023 | 1188/SWD-I | 02/09/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 0 | 100
5236 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KURULI Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000221/2021-2022 | 1938/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
5237 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KURULI Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1516) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000276/2022-2023 | 1807/SWD-I | 09/11/2022 | 300 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 392.81 | 0 | 82
5238 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Kuruli at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000362/2022-2023 | 2205/SWD-I | 13/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 11.52 | 0 | 100
5239 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based KURULI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11500) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000392/2024-2025 | 3640/SWD-I | 20/08/2024 | 45 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 45.6 | 0 | 0
5240 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for KURULI PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011008] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000448/2023-2024 | 2103/SWD-I | 30/08/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 100
5241 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000009/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 9.34 | 0 | 0
5242 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000081/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 4.14 | 0 | 0
5243 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00007/2023-2024 | BP-2023-24-43 | 18/05/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
5244 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jaytala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000536/2022-2023 | 463/SMD | 17/02/2023 | 90 | SWAPAN ENTERPRISE | 23.3 | 0 | 100
5245 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Jaytala scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/11501) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002798/2023-2024 | 384-SMSD | 28/03/2024 | 15 | SWAPAN ENTERPRISE | 0.89 | 0 | 100
5246 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JAYATALA PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000075/2022-2023 | 1186/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 28.52 | 0 | 100
5247 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JOYATALA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000219/2021-2022 | 1941/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
5248 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JAYATALA Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1419) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000272/2022-2023 | 1805/SWD-I | 09/11/2022 | 900 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 415.42 | 0 | 50
5249 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Jayatala at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 2203/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 100
5250 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JAYATALA PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11501] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 2499/SWD-I | 06/10/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
5251 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000010/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 8.74 | 0 | 0
5252 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000083/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.66 | 0 | 0
5253 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III B at Beladurganagar mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC= 3903] | AE BSD |  | ORD/000269/2023-2024 | 1549/SWD-I | 25/07/2023 | 120 | AJIT PRAMANICK | 294.9 | 0 | 40
5254 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III A at Beladurganagar mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3828] | AE BSD |  | ORD/000271/2023-2024 | 1551/SWD-I | 25/07/2023 | 120 | M/S LOKENATH CONSTRUCTION | 289.12 | 0 | 50
5255 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000080/2022-2023 | 2996/SWD-I | 20/02/2023 | 0 | Resource Division | 47.62 | 0 | 0
5256 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD |  | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 894 | MRA NIRMAN UDYOG | 1590.17 | 0 | 65
5257 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD |  | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 327 | MRA NIRMAN UDYOG | 434.23 | 0 | 40
5258 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000084/2022-2023 | 3000/SWD-I | 20/02/2023 | 0 | Resource Division | 73.38 | 0 | 0
5259 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000130/2021-2022 | 385/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 0
5260 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000133/2021-2022 | 388/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 0
5261 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Left Out W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000163/2024-2025 | 2514/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
5262 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Ganeshpur Left Out W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000204/2024-2025 | 2587/AD | 19/06/2024 | 45 | R. UNIQUE CONSTRUCTION | 9.7 | 0 | 0
5263 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 5th tubewell Site for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000205/2024-2025 | 2588/AD | 19/06/2024 | 45 | R. UNIQUE CONSTRUCTION | 5.6 | 0 | 0
5264 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000301/2023-2024 | 1493/AD | 14/07/2023 | 300 | SPA ENTERPRISE | 592.38 | 0 | 20
5265 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( Ganeshpur (Left out Areas) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000489/2022-2023 | 302/AD | 12/04/2022 | 45 | LEMNISCATE | 8.66 | 0 | 0
5266 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000856/2022-2023 | 6939/AD | 18/11/2022 | 929 | M/S PRADIP KUMAR PAL | 104.35 | 0 | 100
5267 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001024/2021-2022 | 538/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 4.59 | 0 | 100
5268 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur (Left Out) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001043/2021-2022 | 2274/AD | 06/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.25 | 0 | 100
5269 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001612/2021-2022 | 611/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 1.55 | 0 | 100
5270 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001798/2020-2021 | 1240/KSD | 23/02/2021 | 10 | UNIQUE CONSTRUCTION (II) | 4.7 | 0 | 0
5271 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001807/2020-2021 | 1245/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.79 | 0 | 0
5272 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001811/2020-2021 | 1250/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.79 | 0 | 0
5273 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001838/2020-2021 | 1269/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.78 | 0 | 0
5274 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001841/2020-2021 | 1272/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.74 | 0 | 0
5275 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001844/2020-2021 | 1275/KSD | 23/02/2021 | 10 | UNIQUE CONSTRUCTION (II) | 4.38 | 0 | 0
5276 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001851/2020-2021 | 1282/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.6 | 0 | 0
5277 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001858/2020-2021 | 1248/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 0 | 0
5278 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001895/2020-2021 | 1317/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.74 | 0 | 0
5279 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
5280 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000054/2022-2023 | 3904/AD | 12/08/2022 | 0 | Resource Division | 348.05 | 0 | 0
5281 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000092/2022-2023 | 5589/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
5282 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000258/2023-2024 | 3063/AD | 28/09/2023 | 0 | Resource Division | 1.2 | 0 | 0
5283 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000674/2023-2024 | 440/AD | 24/01/2024 | 0 | Resource Division | 4.29 | 0 | 0
5284 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000804/2023-2024 | 649/AD | 30/01/2024 | 0 | Resource Division | 10.22 | 0 | 0
5285 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Road Restoration and Bullah Piling work for laying of distribution pipes between node point from 1 to 2, 2 to 59, 59 to 60, 60 to 61, 61 to 62, 62 to 63, 63 to 64, 64 to 65 for Laying Distribution System to extend the benefit of 100% FHTC at Mandirbazar Block in Zone X within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. [SM/11237] | AE HQ-I |  | ORD/000521/2024-2025 | 4014/SWD-I | 13/09/2024 | 136 | BISWAS CONSTRUCTION | 42.19 | 0 | 50
5286 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-X at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5689] | AE HQ-I |  | ORD/000616/2022-2023 | 3216/SWD-I | 28/02/2023 | 763 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 379.55 | 0 | 30
5287 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000060/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 35.04 | 0 | 0
5288 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-IV at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2270) | AE HQ-I |  | ORD/000712/2022-2023 | 3528/SWD-I | 17/03/2023 | 300 | SUPER SKILL | 458.61 | 0 | 25
5289 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000053/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 13.98 | 0 | 0
5290 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Nebutala W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000167/2024-2025 | 2518/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.41 | 0 | 0
5291 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Nebutala W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000216/2024-2025 | 2599/AD | 19/06/2024 | 30 | SWATHI ENTERPRISE | 9.69 | 0 | 0
5292 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Nebutala W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000232/2023-2024 | 161/KSD | 01/06/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 100
5293 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Nebutala, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000268/2023-2024 | 1418/AD | 13/07/2023 | 927 | M/S B.N.ENTERPRISE | 37.36 | 0 | 50
5294 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Nebutala Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000325/2022-2023 | 3872/AD | 08/08/2022 | 30 | M/S M3 SOLUTION | 8.76 | 0 | 100
5295 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 1 no. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Nebutala Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000360/2022-2023 | 3892/AD | 10/08/2022 | 1504 | M/S B.N.ENTERPRISE | 239.96 | 0 | 60
5296 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Nebutala W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-C) (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000392/2024-2025 | 3093/AD | 25/07/2024 | 60 | M/S B.N.ENTERPRISES | 58.8 | 0 | 0
5297 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( NEBUTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000499/2022-2023 | 1751/AD | 15/06/2022 | 45 | LEMNISCATE | 3.76 | 0 | 100
5298 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002052/2022-2023 | 730/KSD | 14/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
5299 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
5300 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002597/2023-2024 | 176/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5301 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000061/2022-2023 | 3947/AD | 12/08/2022 | 0 | Resource Division | 43.58 | 0 | 0
5302 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000269/2023-2024 | 3068/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5303 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000592/2023-2024 | 91/AD | 03/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
5304 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000805/2023-2024 | 650/AD | 30/01/2024 | 0 | Resource Division | 3.96 | 0 | 0
5305 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Nebutala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000427/2022-2023 | 3823/SMD | 29/12/2022 | 90 | KUSHANI ENTERPRISES | 9.28 | 0 | 0
5306 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01674/2024-2025 | BP-2024-25-779 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
5307 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for service connection at Pump house no-I of Jelerhat.(Baruipur Block) | AE BSD,Assistant Engineer | Junior Engineer | BILL/00403/2024-2025 | BP-2024-25-98 | 10/06/2024 | 0 | WBSEDCL | 5.08 | 0 | 0
5308 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jelerhat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000451/2022-2023 | 3931/SMD | 30/12/2022 | 90 | JAGANNATH ENTERPRISE | 22.37 | 0 | 0
5309 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JELERHAT PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011011] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000216/2022-2023 | 1593/SWD-I | 17/10/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 0 | 10
5310 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JELERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000220/2021-2022 | 1936/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 0
5311 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Jelerhat at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000365/2022-2023 | 2208/SWD-I | 13/12/2022 | 60 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 11.52 | 0 | 0
5312 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Jelerhat PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011011] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000724/2022-2023 | 3573/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 0
5313 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JELERHAT Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1675) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000739/2022-2023 | 3592/SWD-I | 23/03/2023 | 300 | THE UNICON ENGINEERS | 422.87 | 0 | 70
5314 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for JELERHAT Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12636] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001155/2024-2025 | 373/SWD-I | 04/02/2025 | 30 | RAJKUMAR MONDAL | 15.9 | 0 | 0
5315 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000333/2023-2024 | 266/SWD-I | 10/01/2024 | 0 | Resource Division | 10.32 | 0 | 0
5316 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Head works site at JALGHARA Zone-X/A of Magrahat-I Block for Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District- South 24-Pgns." under South 24-Pgns W/S Division-I, PHE Dte. (SM/11263) | Assistant Engineer | JE2 | ORD/000531/2024-2025 | 4077/SWD-I | 19/09/2024 | 15 | SRIJON ENTERPRISE | 37.44 | 0 | 90
5317 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 734 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 0 | 25
5318 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000143/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 57.02 | 0 | 0
5319 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05022/2023-2024 | BP-2023-24-571 | 12/03/2024 | 0 | WBSEDCL | 10.24 | 0 | 0
5320 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Purba Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000558/2022-2023 | 572/SMD | 22/02/2023 | 90 | DEBJYOTI BASU | 19.37 | 0 | 0
5321 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-II PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 42/SWD-I | 06/04/2023 | 15 | M/S. S M ENTERPRISE | 4.4 | 0 | 0
5322 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-II) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 1232/SWD-I | 07/09/2022 | 30 | M/S. S M ENTERPRISE | 40.13 | 0 | 12
5323 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-II) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000158/2022-2023 | 1411/SWD-I | 22/09/2022 | 60 | ANANDA MAITY | 11.01 | 0 | 100
5324 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PURBA GABBERIA(II) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000363/2021-2022 | 1930/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
5325 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-II) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2086) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 2316/SWD-I | 19/12/2022 | 900 | M/S. S.S. ENTERPRISE | 662.96 | 0 | 65
5326 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000070/2023-2024 | 292/SWD-I | 24/04/2023 | 0 | Resource Division | 76.13 | 0 | 0
5327 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00163/2024-2025 | BP-2024-25-51 | 10/05/2024 | 0 | WBSEDCL | 4.46 | 0 | 0
5328 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01987/2023-2024 | BP-2023-24-245 | 11/09/2023 | 0 | WBSEDCL | 7.11 | 0 | 0
5329 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Champahati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 460/SMD | 17/02/2023 | 90 | K.P CONSTRUCTION | 19.57 | 0 | 0
5330 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at CHAMPAHATI Zone-I of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000154/2022-2023 | 1407/SWD-I | 22/09/2022 | 60 | M/S P. PURKAIT ENTERPRISE. | 10.95 | 0 | 0
5331 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI Zone-I PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2022-2023 | 1683/SWD-I | 01/11/2022 | 30 | K P CONSTRUCTION | 42.29 | 0 | 100
5332 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHAMPAHATI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000451/2021-2022 | 1953/SWD_I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
5333 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Two nos) at CHAMPAHATI ZONE-I water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/11278) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000661/2024-2025 | 4391/SWD-I | 23/10/2024 | 239 | S D ENTERPRISE | 9.96 | 0 | 100
5334 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI Zone-I Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 918) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000738/2022-2023 | 3591/SWD-I | 23/03/2023 | 300 | M/S SUMAN SHIL | 226.66 | 0 | 30
5335 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Champahati-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 3666/SWD-I | 29/03/2023 | 15 | K P CONSTRUCTION | 4.41 | 0 | 100
5336 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform Development of Land, Pipeline Protection Work and others allied works Ground Water Based CHAMPAHATI ZONE-I PWSS to accommodate FHTC in BARUIPUR Block under South 24 Pgns W/S Divn-I PHE Dte for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District. [SM/11278] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000791/2024-2025 | 4842/SWD-I | 27/11/2024 | 60 | SANKAR MONDAL | 73.66 | 0 | 30
5337 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000181/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 17.75 | 0 | 0
5338 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01716/2023-2024 | BP-2023-24-202 | 09/08/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
5339 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Dhanberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000458/2022-2023 | 3935/SMD | 30/12/2022 | 90 | BIDYUT KUMAR MUKHERJEE | 9.63 | 0 | 100
5340 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Dhanberia W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002469/2023-2024 | 1429/SMSD | 22/11/2023 | 15 | BIDYUT KUMAR MUKHERJEE | 0.81 | 0 | 100
5341 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DHANBERIA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 1202/SWD-I | 02/09/2022 | 30 | PAPPU ENTERPRISE | 20.06 | 0 | 100
5342 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at DHANBERIA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012518] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000122/2022-2023 | 1290/SWD-I | 14/09/2022 | 60 | LAKSHMI IRON | 5.44 | 0 | 100
5343 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DHANBERIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000166/2021-2022 | 1916/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
5344 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DHANBERIA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 209) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000312/2022-2023 | 1953/SWD-I | 22/11/2022 | 90 | M/S ASHIRBAD (INDIA) | 127.29 | 0 | 18
5345 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 01 (One) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for DHANBERIA PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012518] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000453/2023-2024 | 2108/SWD-I | 30/08/2023 | 15 | PAPPU ENTERPRISE | 2.2 | 0 | 100
5346 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000104/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
5347 | Alipore Division | Baruipur Sub-Division | Road restoration for Shikharbali-I GP lo Dakshin Kalyanpur | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01777/2024-2025 | BP-2024-25-802 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.31 | 0 | 0
5348 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01725/2023-2024 | BP-2023-24-201 | 09/08/2023 | 0 | WBSEDCL | 9.09 | 0 | 0
5349 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Sasan water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000455/2022-2023 | 3934/SMD | 30/12/2022 | 90 | M/S. GHOSH ENTERPRISE | 26.1 | 0 | 100
5350 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.30] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00490/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 16.53 | 0 | 0
5351 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DAKSHIN SASAN PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000091/2022-2023 | 1203/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
5352 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at DAKSHIN SASAN of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012622] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000121/2022-2023 | 1289/SWD-I | 14/09/2022 | 60 | M/S. ARPAN ENTERPRISE. | 10.88 | 0 | 100
5353 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DAKSHIN SASAN Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000170/2021-2022 | 1917/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
5354 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DAKSHIN SASAN of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1759) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000239/2022-2023 | 1726/SWD-I | 03/11/2022 | 120 | PRASUN ENTERPRISE | 342.27 | 0 | 60
5355 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Platform for providing FHTC, Protection works for pipeline and other allied works for Proposed Ground Water based DAKSHIN SASAN piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12057) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000730/2024-2025 | 4617/SWD-I | 13/11/2024 | 90 | MUNNA AGROTECH ENTERPRISE | 75.82 | 0 | 40
5356 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Dakshin Sasan PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012622] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000797/2022-2023 | 3679/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 0 | 100
5357 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000268/2023-2024 | 2420/SWD-I | 30/09/2023 | 0 | Resource Division | 112.13 | 0 | 0
5358 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000338/2023-2024 | 263/SWD-I | 10/01/2024 | 0 | Resource Division | 10.84 | 0 | 0
5359 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01110/2023-2024 | BP-2023-24-155 | 24/07/2023 | 0 | WBSEDCL | 4.18 | 0 | 0
5360 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kashinathpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000498/2022-2023 | 316/SMD | 06/02/2023 | 881 | B.T.PROJECTS PVT.LTD. | 22.86 | 0 | 70
5361 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for KASHINATHPUR piped water supply scheme at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tubewell site (Dag No. 1300, Khatian No. 1361 , JL No. 115, Mouza- Kashinathpur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000171/2022-2023 | 1442/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.51 | 0 | 50
5362 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Kashinathpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2255] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000395/2023-2024 | 1878/SWD-I | 18/08/2023 | 300 | SAMSUL ENTERPRISE | 486.03 | 0 | 40
5363 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of KASHINATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12016) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 4238/SWD-I | 30/09/2024 | 60 | SAMSUL ENTERPRISE | 89.07 | 0 | 0
5364 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for KASHINATHPUR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12016] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000709/2024-2025 | 4539/SWD-I | 06/11/2024 | 122 | RAJKUMAR MONDAL | 15.9 | 0 | 100
5365 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASHINATHPUR PWSS at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tube-well site (Dag No. 1300 Khatian No. 1361, JL No. 115, Mouza- Kashinathpur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12016] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000737/2022-2023 | 3567/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 50
5366 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000056/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 47.08 | 0 | 0
5367 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000247/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.89 | 0 | 0
5368 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Kashinagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000266/2023-2024 | 1454/AD | 13/07/2023 | 600 | MITHU BUILDERS | 308.59 | 0 | 60
5369 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Kashinagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000377/2023-2024 | 1770/AD | 26/07/2023 | 60 | B.S. CONSTRUCTION | 62.86 | 0 | 44
5370 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. of Dakshin Kashinagar W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13763) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000512/2024-2025 | 3611/AD | 06/09/2024 | 329 | M/S B. ENTERPRISE | 59.35 | 0 | 60
5371 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN KASHINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000978/2022-2023 | 3663/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.2 | 0 | 100
5372 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Kashinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13763) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001367/2024-2025 | 5496/AD | 27/12/2024 | 210 | CHANDA ENTERPRISE (KOLKATA) | 40.78 | 0 | 100
5373 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Kashinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002034/2023-2024 | 516/AD | 25/01/2024 | 45 | M/S S.DAS ENTERPRISE | 25.46 | 0 | 0
5374 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Kashinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002035/2023-2024 | 517/AD | 25/01/2024 | 360 | SUJOY SADHUKHAN | 9.58 | 0 | 100
5375 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
5376 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000096/2023-2024 | 542/AD | 12/05/2023 | 0 | Resource Division | 9.14 | 0 | 0
5377 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000508/2023-2024 | 4945/AD | 22/12/2023 | 0 | Resource Division | 24.05 | 0 | 0
5378 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000952/2023-2024 | 1686/AD | 22/03/2024 | 0 | Resource Division | 0.57 | 0 | 0
5379 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Kashinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000361/2022-2023 | 3764/SMD | 29/12/2022 | 90 | M/S. S.R. ENTERPRISE | 21.52 | 0 | 0
5380 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road at OHR Site for Augmentation of Kachuberia W/S Scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000471/2024-2025 | 3457/AD | 23/08/2024 | 45 | M/S SOURAV MAHAPATRA | 32.06 | 0 | 0
5381 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001055/2021-2022 | 2343/AD | 09/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.8 | 0 | 100
5382 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001081/2021-2022 | 572/KSD | 10/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.6 | 0 | 100
5383 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001611/2021-2022 | 610KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 2.26 | 0 | 100
5384 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000705/2023-2024 | 475/AD | 24/01/2024 | 0 | Resource Division | 24.87 | 0 | 0
5385 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-VII at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 9193] | AE HQ-I |  | ORD/000053/2023-2024 | 272/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 591.54 | 0 | 35
5386 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supply of various D.I. fittings of different diameters for laying of pipeline in connection Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | AE HQ-I |  | ORD/000348/2024-2025 | 3377/SWD-I | 27/07/2024 | 30 | B.S. RUBBER INDUSTRIES | 11.6 | 0 | 100
5387 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Supply of various D.I. fittings of different diameters for laying of pipeline in connection Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | AE HQ-I |  | ORD/000778/2024-2025 | 4174/SWD-I | 25/09/2024 | 15 | B.S. RUBBER INDUSTRIES | 5.81 | 0 | 100
5388 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000057/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 56.63 | 0 | 0
5389 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00511/2023-2024 | BP-2023-24-74 | 13/06/2023 | 0 | WBSEDCL | 6.42 | 0 | 0
5390 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Padmerhat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000279/2022-2023 | 274/SMD | 01/02/2023 | 790 | SAIKAT ENTERPRISE | 22.37 | 0 | 45
5391 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Padmerhat W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/11780) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002457/2024-2025 | 1533/SMSD | 19/11/2024 | 15 | SAIKAT ENTERPRISE | 0.95 | 0 | 0
5392 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia& 300 mtr. deepTubewell by Rotary method for Padmerhat PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/011744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000102/2022-2023 | 1234/SWD-I | 07/09/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 0 | 100
5393 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 0 | 30
5394 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "PADMERHAT Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 469/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.65 | 0 | 100
5395 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Padmerhat PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000725/2022-2023 | 3571/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 0
5396 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based PADMERHAT Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/11780) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 1200/SWD-I | 11/03/2024 | 45 | BENGAL BUILDERS | 53.81 | 0 | 0
5397 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000157/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 41.81 | 0 | 0
5398 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/02496/2023-2024 | BP-2023-24-264 | 18/09/2023 | 0 | WBSEDCL | 13.97 | 0 | 0
5399 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Saphkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000507/2022-2023 | 342/SMD | 08/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.58 | 0 | 50
5400 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Improvement of working ambience by providing requsite external luminaires, supplying of chair & table etc. at P.H. No. - 1 under Sapkhali Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/11781) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000799/2024-2025 | 1039-AE-II-SMD | 13/08/2024 | 15 | MONOSEBA CONSTRUCTION | 0.78 | 0 | 0
5401 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SAPHKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11781] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000176/2022-2023 | 1451/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.27 | 0 | 100
5402 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
5403 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "SAPKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000399/2022-2023 | 468/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 0 | 100
5404 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SAPHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000418/2022-2023 | 2472/SWD-I | 30/12/2022 | 823 | MERCANTILE HALL | 103.26 | 0 | 90
5405 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SAPHKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11781) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000446/2022-2023 | 2665/SWD-I | 18/01/2023 | 60 | M/S. TORSA ENTERPRISE | 6.04 | 0 | 100
5406 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, pump house, restoration of road, laying of additional pipeline and other allied works for SAPKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11781] [2nd call] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000506/2024-2025 | 3963/SWD-I | 10/09/2024 | 264 | SUKUMAR DEBNATH | 48 | 0 | 80
5407 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAPKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011741] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000522/2022-2023 | 2912/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 0 | 100
5408 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SAPKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011741] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000584/2022-2023 | 3105/SWD-I | 24/02/2023 | 650 | MOULI CONSTRUCTION | 15.88 | 0 | 98
5409 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Repairing of R.C.C. elevated reservoir (1135 Cum capacity) of staging height 20.0 mtr. of ZONE-14 under ground water based SAPKHALI PWSS to Accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte. for augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. [SM/11781] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000622/2023-2024 | 2805/SWD-I | 09/11/2023 | 45 | NIKHIL SAMADDAR | 17.95 | 0 | 98
5410 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Balance portion of LDS at Sapkhali PWSS under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in Bishnupur-I Block within South 24-Pgs. W/S Divn.-I, P.H.E. Dte., South 24-Pgs. Dist. [Scheme code: SM/11781][2nd call] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000724/2023-2024 | 398/SWD-I | 18/01/2024 | 15 | T.T. ENTERPRISE (PANIHATI) | 7.77 | 0 | 99
5411 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000026/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.35 | 0 | 0
5412 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000102/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 25.83 | 0 | 0
5413 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00023/2023-2024 | BP-2023-24-40 | 18/05/2023 | 0 | WBSEDCL | 3.66 | 0 | 0
5414 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chak Nursikdarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000442/2022-2023 | 67/SMD | 11/01/2023 | 90 | M/S. PS & ASSOCIATES | 25.93 | 0 | 50
5415 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Improvement of working ambience by providing requsite external luminaires, supplying of chair & table etc. at P.H. No. 1 under Chak Nursikdarpur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11782) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/002511/2023-2024 | 210-AE-II-SMD | 28/02/2024 | 15 | S.R. CONCERN | 0.75 | 0 | 100
5416 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000181/2023-2024 | 773/SWD-I | 31/05/2023 | 183 | AHMED REZA | 0.87 | 0 | 30
5417 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
5418 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2024 to 30/11/2024) [Vehicle NoWB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000220/2024-2025 | 2449/SWD-I | 24/05/2024 | 183 | AHMED REZA | 0.87 | 0 | 0
5419 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of CHAK NURSHIKDAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000229/2021-2022 | 1978/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 0 | 100
5420 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHAK NURSHIKDAR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11782] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000231/2022-2023 | 1681/SWD-I | 01/11/2022 | 30 | KUNTAL CHOWDHURY | 14.89 | 0 | 100
5421 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump hopuse, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK NURSIKDER PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11782] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000246/2024-2025 | 2666/SWD-I | 07/06/2024 | 586 | SRIJON ENTERPRISE | 71.67 | 0 | 50
5422 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based CHAK NURSHIKDAR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 865 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000415/2022-2023 | 2469/SWD_I | 30/12/2022 | 90 | SANJUKTA ENGINEERS. | 138.64 | 0 | 92
5423 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of CHAK NURSHIKDAR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11782) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000441/2022-2023 | 2660/SWD-I | 18/01/2023 | 60 | M/S. TORSA ENTERPRISE | 6.04 | 0 | 100
5424 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for CHAK NURSHIKDAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011738] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000592/2022-2023 | 3112/SWD-I | 24/02/2023 | 727 | DEBASHIS DAS | 15.87 | 0 | 98
5425 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2023 to 31/05/2024) [Vehicle No- WB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000674/2023-2024 | 2999/SWD-I | 29/11/2023 | 183 | AHMED REZA | 0.87 | 0 | 90
5426 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2024 to 31/05/2025) [Vehicle NoWB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001061/2024-2025 | 4878/SWD-I | 29/11/2024 | 182 | AHMED REZA | 0.86 | 0 | 1
5427 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000028/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.33 | 0 | 0
5428 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000099/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.32 | 0 | 0
5429 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | BILL/03515/2023-2024 | BP-2023-24-381 | 20/11/2023 | 0 | WBSEDCL | 3.59 | 0 | 0
5430 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Krishnarampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000488/2022-2023 | 246/SMD | 27/01/2023 | 1070 | T.S. CONSTRUCTION | 25.93 | 0 | 85
5431 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
5432 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KRISHNARAMPUR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11789] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000229/2022-2023 | 1680/SWD-I | 01/11/2022 | 30 | M/S PURE RENOVATION CONSTRUCTION GROUP | 14.85 | 0 | 100
5433 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KRISHNARAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11789) (3rd Call) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000252/2023-2024 | 1499/SWD-I | 20/07/2023 | 60 | S.P. ENTERPRISE | 6.05 | 0 | 100
5434 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Krishnarampur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11789) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000255/2024-2025 | 2672/SWD-I | 07/06/2024 | 491 | NIKHIL SAMADDAR | 50.05 | 0 | 30
5435 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KRISHNARAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000396/2022-2023 | 464/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.62 | 0 | 100
5436 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KRISHNARAMPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000419/2022-2023 | 2473/SWD-I | 30/12/2022 | 90 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 157.64 | 0 | 98
5437 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KRISHNARAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011787] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000516/2022-2023 | 2908/SWD-I | 14/02/2023 | 15 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0
5438 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KRISHNARAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011787] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000586/2022-2023 | 3107/SWD-I | 24/02/2023 | 30 | MOULI CONSTRUCTION | 15.88 | 0 | 100
5439 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000029/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.35 | 0 | 0
5440 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000101/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 30.22 | 0 | 0
5441 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI A at Madhya Gurguria mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3302] | AE BSD |  | ORD/000183/2022-2023 | 1486/SWD-I | 28/09/2022 | 1200 | MS GOUTAM CHAKRABORTY | 252.19 | 0 | 40
5442 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI B at Madhya Gurguria mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3487] | AE BSD |  | ORD/000460/2023-2024 | 2137/SWD-I | 31/08/2023 | 90 | M/S SARADA CONSTRUCTION | 280.24 | 0 | 0
5443 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000076/2022-2023 | 2992/SWD-I | 20/02/2023 | 0 | Resource Division | 41.82 | 0 | 0
5444 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service connection at P.H. NO.1 of Gokarni w/s scheme . Application no.: 1007730295 . | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/00534/2024-2025 | BP-2024-25-132 | 24/06/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
5445 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Gokarni water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000394/2022-2023 | 3796/SMD | 29/12/2022 | 1099 | M/S. A.K. BANERJEE | 22.35 | 0 | 45
5446 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000918/2025-2026 | 640/SMSD | 30/04/2025 | 15 | M/S. A.K. BANERJEE | 0.85 | 0 | 0
5447 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & laying of submersible cable through non metallic pipes for electrical connection of pumping machinery with Pump House no-1 of Gokorni W/S Scheme under SMD, P.H.E. Dte. (Block-Magrahat-II) (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000919/2025-2026 | 641/SMSD | 30/04/2025 | 15 | M/S. A.K. BANERJEE | 0.82 | 0 | 0
5448 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Gokarni PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014757] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000007/2023-2024 | 29/SWD-I | 05/04/2023 | 15 | KUNTAL CHOWDHURY | 3.13 | 0 | 100
5449 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Hume Pipe culvert for the approach road of proposed "Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block, South 24 Parganas District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE, Dte. (TSM/014757) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000152/2023-2024 | 721/SWD-I | 29/05/2023 | 60 | TOJO ENTERPRISE | 10.17 | 0 | 100
5450 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Gokarni PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000300/2022-2023 | 1878/SWD-I | 16/11/2022 | 30 | KUNTAL CHOWDHURY | 30.03 | 0 | 100
5451 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall & approach Road at 2nd Tube Well site for GOKARNI PWSS to accommodate FHTC in Magrahat-II block under South 24 Parganas W/S division-I, P.H.E. Dte for augmentation of surface water Based Water supply Scheme in the arsenic affected areas of South 24-Pgns district (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000328/2024-2025 | 3265/SWD-I | 22/07/2024 | 90 | SANJAY MIDDEY | 12.19 | 0 | 60
5452 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall at HW site for GOKARNI PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas.(SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000329/2024-2025 | 3267/SWD-I | 22/07/2024 | 45 | M/S. SREEJIT ENTERPRISE | 23.82 | 0 | 50
5453 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Platform for providing FHTC for Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. [No. of FHTC= 1585] (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000344/2024-2025 | 3318/SWD-I | 23/07/2024 | 60 | MONDAL PRECISION PVT. LTD. | 29.5 | 0 | 0
5454 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of "GOKARNEE Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000386/2022-2023 | 406/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
5455 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of chlorination room 5.00mx4.00m(One no) at Head work site of GOKARNI PWSS to accommondate FHTC in MOGRAHAT-II Block under South 24 Pngs Divn-I, PHE Dte for augmentation of surface water based WS scheme in the arsenic affected areas of South 24 Parganas District. (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000413/2024-2025 | 3714/SWD-I | 23/08/2024 | 225 | CHOUDHURY AND ASSOCIATES | 4.86 | 0 | 40
5456 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of GOKARNI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1585] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000487/2022-2023 | 2792/SWD-I | 01/02/2023 | 300 | MONDAL PRECISION PVT. LTD. | 463.13 | 0 | 25
5457 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at GOKARNI Head Work site of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns WS Division-I, P.H.E Dte. (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000541/2024-2025 | 4098/SWD-I | 20/09/2024 | 189 | GLANCE CONSTRUCTION | 5.9 | 0 | 50
5458 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at 2nd Tubewell site of Gokarni PWSS to accommodate FHTC in MOGRAHAT-II Block for augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district, South 24 Pgns WS Division-I, P.H.E Dte. (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000663/2024-2025 | 4393/SWD-I | 23/10/2024 | 280 | SANJAY MIDDEY | 5.89 | 0 | 65
5459 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Balance work for Construction of Humc Pipe culvert for the approach road of proposcd "Ground water bascd GOKARNI piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas Djstnct for Augmentation of Surfacc Water Based Water Supply Scheme In the Arscmc Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dle (TSM/014757) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000794/2023-2024 | 1142/SWD-I | 07/03/2024 | 30 | TOJO ENTERPRISE | 2.41 | 0 | 100
5460 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000196/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.3 | 0 | 0
5461 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chhayani water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000807/2022-2023 | 270/SMD | 31/01/2023 | 90 | SUPER SKILL | 12.65 | 0 | 0
5462 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of CHHAYANI MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 907] [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 373/SWD-I | 27/04/2023 | 90 | M/S SALIM CONSTRUCTION | 162.11 | 0 | 80
5463 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for CHHAYANI PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 3069/SWD-I | 21/02/2023 | 30 | SWASTIK CONSTRUCTION (E-MAIL ID- SIDDHARTHA1978SAMADDER@GMAIL.COM) | 15.46 | 0 | 0
5464 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for CHHAYANI PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 1326/SWD-I | 15/03/2024 | 450 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.46 | 0 | 100
5465 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based CHHAYANI Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under south 24-Pgns W/S Division-I, P.H.E. Dte., for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000916/2022-2023 | 1221/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
5466 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000174/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 6 | 0 | 0
5467 | Alipore Division | Canning Sub-division | Additional laying of pipeline and FHTC work at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - XII) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000563/2024-2025 | 3894/AD | 24/09/2024 | 219 | SUJOY SADHUKHAN | 5.87 | 0 | 65
5468 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - XII) having village with maximum 297 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000796/2022-2023 | 6685/AD | 14/11/2022 | 60 | FIDERE MARINE SERVICES PVT. LTD. | 71.35 | 0 | 77
5469 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-XII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001909/2022-2023 | 5672/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.64 | 0 | 0
5470 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000177/2023-2024 | 1130/AD | 22/06/2023 | 0 | Resource Division | 1.83 | 0 | 0
5471 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00523/2023-2024 | BP-2023-24-75 | 13/06/2023 | 0 | WBSEDCL | 3.19 | 0 | 0
5472 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00524/2023-2024 | BP-2023-24-75 | 13/06/2023 | 0 | WBSEDCL | 0.04 | 0 | 0
5473 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-XII) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000597/2022-2023 | 661/SMD | 06/03/2023 | 90 | MOUMITA ENTERPRISE | 8.9 | 0 | 100
5474 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Chak Parankanta Khali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000403/2022-2023 | 3802/SMD | 29/12/2022 | 90 | M/S.P.P.ELECTRICALS | 22.35 | 0 | 0
5475 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall & land development at 2nd Tubewell site including provision of M.S. gate for CHAK PARANKANTA KHALI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. (SM/12801) [Length - 52.0 mtr. of boundary wall] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000087/2025-2026 | 1762/SWD-I | 02/07/2025 | 45 | MOTIONMASS TECHNO OPC PVT LTD | 9.61 | 0 | 0
5476 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and Approach Road With Drum Sheet walling & Earth filling for CHAK PARANKANTA KHALI PWSS to accommodate FHTC within Mograhat-II Block under South 24 pgs water supply Division-I, PHE Dte. Dist S24 Pgs. (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000295/2024-2025 | 3135/SWD-I | 10/07/2024 | 222 | LASKAR CONSTRUCTION | 38.36 | 0 | 45
5477 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of "CHAK PARANKANTAKHALI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000391/2022-2023 | 410/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
5478 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of chlorination room 5.00mx4.00m(One no) at Head work site of CHAK PARANKANTA KHALI PWSS to accommondate FHTC in MOGRAHAT-II Block under South 24 Pgns Divn-I, (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000440/2024-2025 | 3885/SWD-I | 03/09/2024 | 30 | AHANA ENTERPRISE | 4.87 | 0 | 0
5479 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK PARANKANTA KHALI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1785] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000486/2022-2023 | 2790/SWD-I | 01/02/2023 | 300 | M/S GHOSH AND CO. | 435.23 | 0 | 30
5480 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at CHAK PARANKANTA KHALI Head Work site of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns WS Division-I, P.H.E Dte. (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000542/2024-2025 | 4099/SWD-I | 20/09/2024 | 60 | LASKAR CONSTRUCTION | 5.89 | 0 | 0
5481 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ChakParankanta Khali PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014899] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000734/2022-2023 | 3585/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
5482 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method for CHAK PARANKATA KHALI Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12801] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/001153/2024-2025 | 371/SWD-I | 04/02/2025 | 210 | TITUMIR INTERNATIONAL | 36.84 | 0 | 50
5483 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000204/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 23.83 | 0 | 0
5484 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - I) having village with maximum 105 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000789/2022-2023 | 6644/AD | 14/11/2022 | 120 | M/S M. ENTERPRISE | 45.15 | 0 | 89
5485 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001895/2022-2023 | 5659/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.37 | 0 | 0
5486 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000178/2023-2024 | 1131/AD | 22/06/2023 | 0 | Resource Division | 0.65 | 0 | 0
5487 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00381/2023-2024 | BP-2023-24-49 | 09/06/2023 | 0 | WBSEDCL | 2.72 | 0 | 0
5488 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Khunkhali (Part-I) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000582/2022-2023 | 617/SMD | 02/03/2023 | 90 | M/S. BABUSONA ENTERPRISE | 8.81 | 0 | 100
5489 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Bibir Abad, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1703] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000122/2023-2024 | 158/AD | 18/04/2023 | 895 | NAUTAN DAS AND CO | 300.96 | 0 | 70
5490 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Ground Water Based of Bibir Abad Piped Water Supply Scheme, Block - Canning- II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001065/2024-2025 | 5002/AD | 05/12/2024 | 45 | DEVAM ENTERPRISE | 32.5 | 0 | 0
5491 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 3 Site for Ground Water Based of Bibir Abad Piped Water Supply Scheme, Block - Canning- II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001066/2024-2025 | 5003/AD | 05/12/2024 | 30 | SUBHO CONSTRUCTION | 10.4 | 0 | 0
5492 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001766/2022-2023 | 12039/AD | 27/02/2023 | 45 | GIRI ENTERPRISE (NEW) | 7.33 | 0 | 98
5493 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001767/2022-2023 | 12040/AD | 27/02/2023 | 45 | KRISHNA CONSTRUCTION | 7.07 | 0 | 98
5494 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001821/2022-2023 | 12336/AD | 06/03/2023 | 105 | M/S ARIYAN ENTERPRISE | 7.1 | 0 | 98
5495 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bibir Abad New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001892/2022-2023 | 8036/AD | 02/12/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.72 | 0 | 0
5496 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002021/2022-2023 | 12104/AD | 28/02/2023 | 60 | SNEHA CONSTRUCTION | 59.76 | 0 | 98
5497 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
5498 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000012/2023-2024 | 217/AD | 21/04/2023 | 0 | Resource Division | 103.46 | 0 | 0
5499 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Chelikati bibirabad PH-1 Water supply scheme under Canning-II block. Reference ID:-106554875, Application No :-1007635912 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00385/2024-2025 | BP-2024-25-100 | 10/06/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
5500 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Chelikati Bibirabad PH-2 Water supply scheme under Canning-II block. Reference ID:-106554882, Application No :-1007635920 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00406/2024-2025 | BP-2024-25-101 | 10/06/2024 | 0 | WBSEDCL | 4.48 | 0 | 0
5501 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/04082/2023-2024 | BP-2023-24-418 | 16/12/2023 | 0 | WBSEDCL | 3.68 | 0 | 0
5502 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at P.H. No-3 of Bibir Abad water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000101/2024-2025 | 524/SMSD | 26/04/2024 | 15 | M/S POUSALI ENTERPRISE | 0.39 | 0 | 100
5503 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Bibir Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000519/2022-2023 | 378/SMD | 15/02/2023 | 960 | PADMA ENGINEERING CO. | 27.75 | 0 | 85
5504 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-IX) Mini piped water supply scheme adjacent Bibir Abad W/S Scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000590/2022-2023 | 651/SMD | 03/03/2023 | 791 | S.B.ENTERPRISE | 8.84 | 0 | 100
5505 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-XI) Mini piped water supply scheme adjacent of Bibir Abad W/S Scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000595/2022-2023 | 660/SMD | 06/03/2023 | 90 | MOUMITA ENTERPRISE | 8.9 | 0 | 100
5506 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Chelikati Bibib Abad, PH-3, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002789/2023-2024 | 160/SMSD | 05/02/2024 | 15 | PADMA ENGINEERING CO. | 0.88 | 0 | 100
5507 | Alipore Division | Canning Sub-division | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KAMAKHYAPUR, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000062/2023-2024 | 312/AD | 26/04/2023 | 300 | SAMSUL ENTERPRISE | 432.74 | 0 | 30
5508 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kamakhyapur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000120/2025-2026 | 2583/AD | 03/06/2025 | 45 | JHARNA CONSTRUCTION | 37.41 | 0 | 0
5509 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000217/2023-2024 | 957/AD | 30/05/2023 | 65 | INDIA CONSTRUCTION | 43.94 | 0 | 100
5510 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000542/2024-2025 | 3713/AD | 12/09/2024 | 60 | SAMSUL ENTERPRISE | 60.04 | 0 | 0
5511 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001083/2023-2024 | 3542/AD | 17/10/2023 | 746 | GHOSH CONSTRUCTION | 11 | 0 | 80
5512 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001762/2022-2023 | 11944/AD | 24/02/2023 | 708 | BANGA NIRMAN | 8.61 | 0 | 100
5513 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kamakshyapur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001885/2022-2023 | 7598/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 5.39 | 0 | 95
5514 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002111/2022-2023 | 12877/AD | 17/03/2023 | 656 | JOY GURU BUILDERS | 8.92 | 0 | 100
5515 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000061/2023-2024 | 381/AD | 02/05/2023 | 0 | Resource Division | 30.19 | 0 | 0
5516 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Kamakhyapur TW-02 Water supply scheme under Gosaba block. Reference ID:-106763781, Application No :-1008116807 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01843/2024-2025 | BP-2024-25-471 | 18/11/2024 | 0 | WBSEDCL | 7.57 | 0 | 0
5517 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamakhyapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000551/2022-2023 | 490/SMD | 20/02/2023 | 90 | AVINABA ENGINEERING CONCERN | 20.09 | 0 | 0
5518 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinagar (Zone - I & II) W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000212/2024-2025 | 2595/AD | 19/06/2024 | 45 | KHOKAN MONDAL | 28.76 | 0 | 0
5519 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Sri Nagar PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000378/2024-2025 | 3044/AD | 24/07/2024 | 60 | MAA LAXMI ENTERPRISE | 120.33 | 0 | 0
5520 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000426/2023-2024 | 1914/AD | 01/08/2023 | 30 | HYDROTECH ASSOCIATES | 12.04 | 0 | 90
5521 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000427/2023-2024 | 1915/AD | 01/08/2023 | 30 | M/S.SREEJIT ENTERPRISE | 11.8 | 0 | 60
5522 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 365 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 0 | 90
5523 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000909/2023-2024 | 268(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5524 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001061/2022-2023 | 4650/AD | 06/09/2022 | 45 | LEMNISCATE | 6.13 | 0 | 100
5525 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001775/2022-2023 | 12057/AD | 27/02/2023 | 45 | M/S MAITY CONSTRUCTION | 38.52 | 0 | 100
5526 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 70] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001865/2022-2023 | 12418/AD | 09/03/2023 | 1029 | MAA LAXMI ENTERPRISE | 276.43 | 0 | 90
5527 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone - I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) [No. of FHTC = 70] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002031/2022-2023 | 12998/AD | 23/03/2023 | 830 | PREMANANDA ROY BISWAS | 179.16 | 0 | 100
5528 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
5529 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 1st Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002156/2024-2025 | 1984/KSD | 23/12/2024 | 25 | LASKAR ENTERPRISE | 2 | 0 | 100
5530 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & boundary wall at 2nd Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002157/2024-2025 | 1985/KSD | 23/12/2024 | 25 | M/S IDEAL WORKS | 2 | 0 | 0
5531 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Srinagar Zone-I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002568/2023-2024 | 512/KSD | 15/03/2024 | 10 | MAA LAXMI ENTERPRISE | 2.8 | 0 | 0
5532 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000274/2023-2024 | 3073/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5533 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000465/2023-2024 | 4725/AD | 18/12/2023 | 0 | Resource Division | 24.69 | 0 | 0
5534 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000594/2023-2024 | 93/AD | 03/01/2024 | 0 | Resource Division | 0.83 | 0 | 0
5535 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000812/2023-2024 | 657/AD | 30/01/2024 | 0 | Resource Division | 12.8 | 0 | 0
5536 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Srinagar Aug W/S Scheme PH-1 Application No:- 1007169503 Reference ID: 106214464 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/02225/2024-2025 | BP-2024-25-507 | 19/12/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
5537 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Srinagar Aug W/S Scheme PH-2 Application No:- 1007169511 Reference ID: 106214476 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/02226/2024-2025 | BP-2024-25-508 | 19/12/2024 | 0 | WBSEDCL | 7.34 | 0 | 0
5538 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, for Augmentation of Srinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000436/2022-2023 | 3832/SMD | 29/12/2022 | 90 | KARTICK BAL | 21.78 | 0 | 0
5539 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jangalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001495/2022-2023 | 455/SMD | 17/02/2023 | 90 | DIPALI CONSTRUCTION | 22.37 | 0 | 0
5540 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00667/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
5541 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 0 | 30
5542 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land, and other allied works for Proposed Ground water based JANGALIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/13986) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2024-2025 | 2687/SWD-I | 07/06/2024 | 45 | KAMALA ENTERPRISE (DIAMOND HARBOUR) | 16.7 | 0 | 0
5543 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JANGALIA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017293] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000619/2022-2023 | 3242/SWD-I | 01/03/2023 | 30 | MATRI ENTERPRISE | 31.75 | 0 | 100
5544 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "JANGALIA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000755/2022-2023 | 705/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.63 | 0 | 100
5545 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000159/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 40.81 | 0 | 0
5546 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Bejeorancha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000483/2022-2023 | 236/SMD | 24/01/2023 | 951 | SUPER SKILL | 11.7 | 0 | 100
5547 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Bejeorancha W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13917) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002429/2024-2025 | 123/SMSD | 22/01/2025 | 15 | SUPER SKILL | 0.29 | 0 | 100
5548 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bejeorancha W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13917) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002430/2024-2025 | 124/SMSD | 22/01/2025 | 15 | SUPER SKILL | 0.91 | 0 | 100
5549 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 3182/SWD-I | 15/07/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.46 | 0 | 100
5550 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000577/2022-2023 | 3070/SWD-I | 21/02/2023 | 30 | SWASTIK CONSTRUCTION (E-MAIL ID- SIDDHARTHA1978SAMADDER@GMAIL.COM) | 15.46 | 0 | 80
5551 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (One no.) at 1st Tube well site of BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [For T/W site-1] (SM/13917) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000660/2024-2025 | 4390/SWD-I | 23/10/2024 | 60 | RAJ ENTERPRISE | 4.92 | 0 | 100
5552 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at BEJEORANCHA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 620] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000740/2022-2023 | 3593/SWD-I | 23/03/2023 | 990 | AQUATECH ENGINEERS | 108.64 | 0 | 85
5553 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Bejerancha Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000949/2022-2023 | 1280/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.44 | 0 | 100
5554 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/13917) [3rd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001139/2024-2025 | 242/SWD-I | 22/01/2025 | 45 | R.K ENTERPRISE | 23.83 | 0 | 0
5555 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000191/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 4.04 | 0 | 0
5556 | Alipore Division | Diamond Harbour Sub-Division | Bamboo pilling work due to protection of distribution pipe line in between Node Points 16-17, 25-26, 32-33, 33-34, 35-36, 60-62, 62-63, 94-96 & 98-99 for laying distribution of piped water supply at Zone - III (Part-A) of Diamond Harbour -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, Ditrict South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000823/2022-2023 | 207/DHSD | 02/08/2022 | 45 | BANERJEE ENTERPRISE | 4.37 | 0 | 98
5557 | Alipore Division | Diamond Harbour Sub-Division | Bamboo pilling work due to protection of distribution pipe line in between Node Points 7-8, 8-9, 9-6, 10-12, 9-14, 14-15, 64-66 & 76-78 for laying distribution of piped water supply at Zone - III (Part-A) of Diamond Harbour -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, Ditrict South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000824/2022-2023 | 208/DHSD | 02/08/2022 | 45 | G.M. ENTERPRISE | 4.38 | 0 | 98
5558 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-III at Diamond Harbour- I block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14823] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001102/2024-2025 | 5031/AD | 06/12/2024 | 180 | JAL PRAVAHIKA PVT. LTD. | 100.79 | 0 | 0
5559 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying of distribution system in the left out areas of Part-C at ZONE-III of Diamond Harbour-I Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001153/2023-2024 | 3199/AD | 04/10/2023 | 630 | S.C. ENTERPRISE (I) | 84.6 | 0 | 65
5560 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 6507] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001743/2022-2023 | 11710/AD | 21/02/2023 | 1080 | JAL PRAVAHIKA PVT. LTD. | 477.57 | 0 | 60
5561 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000131/2022-2023 | 25/AD | 05/04/2023 | 0 | Resource Division | 25.43 | 0 | 0
5562 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000215/2023-2024 | 1985/AD | 04/08/2023 | 0 | Resource Division | 20.98 | 0 | 0
5563 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000232/2023-2024 | 2193/AD | 10/08/2023 | 0 | Resource Division | 33.01 | 0 | 0
5564 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000350/2023-2024 | 3214/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
5565 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000423/2023-2024 | 3613/AD | 30/10/2023 | 0 | Resource Division | 18.48 | 0 | 0
5566 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000609/2023-2024 | 271/AD | 15/01/2024 | 0 | Resource Division | 21.56 | 0 | 0
5567 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000912/2023-2024 | 1254/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
5568 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-IX of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000665/2023-2024 | 2599/AD | 31/08/2023 | 757 | BANGA NIRMAN | 30.51 | 0 | 0
5569 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-1) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003148/2020-2021 | 256/DHSD | 25/11/2020 | 45 | ASMIT ENTERPRISE | 4.66 | 0 | 100
5570 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-2) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003149/2020-2021 | 261/DHSD | 26/11/2020 | 45 | SRIJON ENTERPRISE | 4.05 | 0 | 100
5571 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-3) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003150/2020-2021 | 262/DHSD | 26/11/2020 | 45 | SUJOY SADHUKHAN | 4.42 | 0 | 100
5572 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000082/2023-2024 | 406/AD | 03/05/2023 | 0 | Resource Division | 34.5 | 0 | 0
5573 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000186/2023-2024 | 1275/AD | 05/07/2023 | 0 | Resource Division | 29.8 | 0 | 0
5574 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000228/2023-2024 | 2190/AD | 10/08/2023 | 0 | Resource Division | 13.78 | 0 | 0
5575 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000358/2023-2024 | 3222/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
5576 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000736/2023-2024 | 570/AD | 27/01/2024 | 0 | Resource Division | 12.95 | 0 | 0
5577 | Alipore Division | Diamond Harbour Sub-Division | Preparation of re-design, drawing for fundation considering pile cap for group piles of different capacities for the proposed R.C.C. Over Head Reservoir at (Zone-II, OHR Size-600 Cum. Mouza - Paschim Gopal Nagar) of Kulpi Block and (Zone-VIII, OHR Size-1000 Cum. Mouza - Baneshwarpur) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000367/2022-2023 | 201/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
5578 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-II at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-3856] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001922/2022-2023 | 12711/AD | 14/03/2023 | 300 | M/S R.K.ENTERPRISE (SALBAGAN) | 463.56 | 0 | 25
5579 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000189/2023-2024 | 1631/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
5580 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000204/2023-2024 | 2025/AD | 05/08/2023 | 0 | Resource Division | 22.17 | 0 | 0
5581 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000366/2023-2024 | 3230/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
5582 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000865/2023-2024 | 772/AD | 03/02/2024 | 0 | Resource Division | 23.75 | 0 | 0
5583 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00002/2024-2025 | BP-2024-25-01 | 05/04/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
5584 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01750/2023-2024 | BP-2023-24-209 | 11/08/2023 | 0 | WBSEDCL | 20.67 | 0 | 0
5585 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000579/2022-2023 | 608/SMD | 28/02/2023 | 763 | CONCORD ENGINEERING | 19.48 | 0 | 45
5586 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kamaria Zone-II W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/13776) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002357/2024-2025 | 1534/SMSD | 19/11/2024 | 15 | CONCORD ENGINEERING | 0.88 | 0 | 0
5587 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of KAMARIA (ZONE-II) MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2051] [TSM/016159] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 967/SWD-I | 08/06/2023 | 300 | MANASH GHOSH | 359.97 | 0 | 50
5588 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KAMARIA (Zone-II) PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016159] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 2894/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 0 | 100
5589 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000092/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 65.22 | 0 | 0
5590 | Alipore Division | Baruipur Sub-Division | Road restoration for Chandakhali to Dhapdhapi More. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01664/2024-2025 | BP-2024-25-771 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.41 | 0 | 0
5591 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01506/2023-2024 | BP-2023-24-242 | 11/09/2023 | 0 | WBSEDCL | 2.45 | 0 | 0
5592 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/02287/2023-2024 | BP-2023-24-261 | 18/09/2023 | 0 | WBSEDCL | 3.49 | 0 | 0
5593 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/03348/2023-2024 | BP-2023-24-368 | 08/11/2023 | 0 | WBSEDCL | 8.76 | 0 | 0
5594 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/13441) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000278/2024-2025 | 643/SMSD | 29/05/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 0
5595 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-3 of of Chadokhali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13441) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000281/2024-2025 | 675/SMSD | 04/06/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.55 | 0 | 0
5596 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Chadokhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000475/2022-2023 | 3946/SMD | 30/12/2022 | 90 | WEST BENGAL ENGINEERING CO. | 32.24 | 0 | 60
5597 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chadokhali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002708/2023-2024 | 1401/SMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.58 | 0 | 100
5598 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002709/2023-2024 | 1402/SMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 100
5599 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Chadokhali W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002710/2023-2024 | 1403/SMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 100
5600 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.29] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00489/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0
5601 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at CHADOKHALI for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =1517] [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000052/2023-2024 | 271/SWD-I | 24/04/2023 | 708 | J.D. CONSTRUCTION | 221.14 | 0 | 80
5602 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by having 66 mtr. Housing by Rotary method for 3rd tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000229/2023-2024 | 1405/SWD-I | 14/07/2023 | 30 | M/S. S M ENTERPRISE | 21.54 | 0 | 100
5603 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at CHADOKHALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000252/2022-2023 | 1753/SWD-I | 04/11/2022 | 900 | MA TARA CONSTRUCTION | 10.93 | 0 | 100
5604 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHADOKHALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000277/2022-2023 | 1839/SWD-I | 11/11/2022 | 30 | G D S ENTERPRISE | 39.87 | 0 | 100
5605 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHADOKHALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 988) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000282/2022-2023 | 1843/SWD-I | 11/11/2022 | 871 | J.D. CONSTRUCTION | 153.54 | 0 | 100
5606 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHADOKHALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000347/2021-2022 | 1907/SWD-I | 27/01/2022 | 30 | TECH VISION | 3.03 | 0 | 100
5607 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house / chlorination room at 3rd Tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodatte FHTC in Baruipur Block under South 24-Pgns, W/S Divn-I, PHE Dte. within South 24-Pgns district. [TSM/014213] [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000521/2023-2024 | 2268/SWD-I | 14/09/2023 | 60 | MOLLICK ENTERPRISE | 5.68 | 0 | 0
5608 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chadokhali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000786/2022-2023 | 3668/SWD-I | 29/03/2023 | 15 | G.D.S ENTERPRISE | 4.39 | 0 | 100
5609 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000107/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 23.82 | 0 | 0
5610 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Lakhinarayanpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000209/2023-2024 | 860/AD | 27/05/2023 | 557 | DEVAM ENTERPRISE | 38.28 | 0 | 100
5611 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000383/2023-2024 | 1776/AD | 26/07/2023 | 600 | AQUATECH ENGINEERS | 89.3 | 0 | 68
5612 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000619/2023-2024 | 3730/AD | 03/11/2023 | 591 | SYN DEVELOPERS PVT. LTD. | 250.67 | 0 | 30
5613 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN LAKHINARAYANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000986/2022-2023 | 4148/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.24 | 0 | 100
5614 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002044/2023-2024 | 526/AD | 25/01/2024 | 598 | SARADA CONSTRUCTION | 27.89 | 0 | 100
5615 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002045/2023-2024 | 527/AD | 25/01/2024 | 551 | GHOSH CONSTRUCTION | 9.6 | 0 | 0
5616 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
5617 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Lakhinarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002620/2023-2024 | 731(A)/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
5618 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000103/2023-2024 | 549/AD | 12/05/2023 | 0 | Resource Division | 8.49 | 0 | 0
5619 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000504/2023-2024 | 4947/AD | 22/12/2023 | 0 | Resource Division | 38.43 | 0 | 0
5620 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000754/2023-2024 | 589/AD | 29/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
5621 | S24 Pgns Mechanical | Kakdwip Sub-Division | Dakshin Lakshminarayanpur PH-1 Water supply scheme Application No- 1008101139 Reference ID- 106755052 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/02032/2024-2025 | BP-2024-25-490 | 09/12/2024 | 0 | WBSEDCL | 10.26 | 0 | 0
5622 | S24 Pgns Mechanical | Kakdwip Sub-Division | Dakshin Laxminarayanpur PH-2Water supply scheme Application No- 1007545287 Reference ID- 106480850 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/02033/2024-2025 | BP-2024-25-491 | 09/12/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
5623 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Lakhinarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000379/2022-2023 | 3783/SMD | 29/12/2022 | 1005 | MAA TARA CONSTRUCTION | 19.28 | 0 | 90
5624 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-2 of Dakshin Laxminarayanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13869) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000729/2025-2026 | 302-AE-II/SMD | 16/05/2025 | 21 | MAA TARA CONSTRUCTION | 0.81 | 0 | 0
5625 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Dakshin Laxminarayanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. (SM/13869) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000730/2025-2026 | 301-AE-II/SMD | 16/05/2025 | 21 | MAA TARA CONSTRUCTION | 0.81 | 0 | 0
5626 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13871) (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000196/2024-2025 | 2579/AD | 19/06/2024 | 45 | M/S SHIBAM ENTERPRISE | 39.24 | 0 | 0
5627 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Krishnadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000375/2023-2024 | 1769/AD | 26/07/2023 | 60 | TANMAY ROY CHOWDHURY | 55.24 | 0 | 59
5628 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000985/2022-2023 | 4147/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.15 | 0 | 0
5629 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001306/2022-2023 | 9889/AD | 10/01/2023 | 45 | PURE RENOVATION GROUP | 49.2 | 0 | 0
5630 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001327/2022-2023 | 3310/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.5 | 0 | 100
5631 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Krishnadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001825/2022-2023 | 12121/AD | 01/03/2023 | 300 | SHRAYA ROADSLINE | 278.36 | 0 | 10
5632 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Krishnadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002039/2023-2024 | 521/AD | 25/01/2024 | 30 | KUNDU CONSTRUCTION CO. | 11.87 | 0 | 100
5633 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 100 cum. capacity OHR of Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002070/2023-2024 | 766(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5634 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
5635 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002135/2023-2024 | 822/AD | 05/02/2024 | 45 | SARADA CONSTRUCTION | 50.9 | 0 | 50
5636 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/13871) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003200/2023-2024 | 958/KSD | 19/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
5637 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000099/2023-2024 | 545/AD | 12/05/2023 | 0 | Resource Division | 5.14 | 0 | 0
5638 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000297/2023-2024 | 3092/AD | 28/09/2023 | 0 | Resource Division | 24.65 | 0 | 0
5639 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000755/2023-2024 | 590/AD | 29/01/2024 | 0 | Resource Division | 0.92 | 0 | 0
5640 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000904/2023-2024 | 890/AD | 07/02/2024 | 0 | Resource Division | 1.38 | 0 | 0
5641 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/05390/2023-2024 | BP-2023-24-598 | 28/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
5642 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Krishnadaspur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000382/2022-2023 | 3785/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE (DOMKAL) | 19.34 | 0 | 0
5643 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-I W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000153/2023-2024 | 639/AD | 17/05/2023 | 45 | M/S PAUL & CO. | 28.77 | 0 | 0
5644 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gopalnagar Uttar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13870) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000233/2024-2025 | 822/AD | 27/02/2025 | 45 | RELIABLE CONSTRUCTIONS | 64.65 | 0 | 0
5645 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000767/2023-2024 | 2929/AD | 21/09/2023 | 300 | VISHAL CONSTRUCTION CO. | 590.16 | 0 | 45
5646 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001779/2022-2023 | 11503/AD | 15/02/2023 | 958 | JOY GURU TRADING | 15.14 | 0 | 60
5647 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001780/2022-2023 | 11757/AD | 21/02/2023 | 45 | S. CHAKRABORTY AND CO. | 36.7 | 0 | 50
5648 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001782/2022-2023 | 11924/AD | 24/02/2023 | 982 | M/S. JHARNA ENTERPRISE | 62.67 | 0 | 30
5649 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001826/2022-2023 | 12122/AD | 01/03/2023 | 120 | KALPANA BUILDERS (I) | 149.55 | 0 | 0
5650 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
5651 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-I PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002606/2023-2024 | 292/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5652 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Madhavnagar Zone-1 PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/15525) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002852/2024-2025 | 1152/AD | 18/03/2025 | 60 | VISHAL CONSTRUCTION CO. | 110.85 | 0 | 0
5653 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000087/2023-2024 | 533/AD | 12/05/2023 | 0 | Resource Division | 17.51 | 0 | 0
5654 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000522/2023-2024 | 4936/AD | 22/12/2023 | 0 | Resource Division | 28.55 | 0 | 0
5655 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000580/2023-2024 | 55/AD | 03/01/2024 | 0 | Resource Division | 0.18 | 0 | 0
5656 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000945/2023-2024 | 1679/AD | 22/03/2024 | 0 | Resource Division | 27 | 0 | 0
5657 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Madhabnagar PH-1, Zone-I W/S Scheme Application No- 1007523052 Reference ID:- 106465635 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/02223/2024-2025 | BP-2024-25-502 | 19/12/2024 | 0 | WBSEDCL | 6.01 | 0 | 0
5658 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Madhabnagar PH-2, Zone-I W/S Scheme Application No- 1007523116 Reference ID:- 106465710 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/02224/2024-2025 | BP-2024-25-503 | 19/12/2024 | 0 | WBSEDCL | 6.4 | 0 | 0
5659 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/03420/2023-2024 | BP-2023-24-372 | 13/11/2023 | 0 | WBSEDCL | 5.92 | 0 | 0
5660 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Madhabnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000390/2022-2023 | 3792/SMD | 29/12/2022 | 1971 | WESTERN ENGINEERING CO. | 23.46 | 0 | 100
5661 | Alipore Division | Canning Sub-division | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KUMIRMARI (ZONE-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000252/2023-2024 | 1434/AD | 13/07/2023 | 597 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 697.57 | 0 | 65
5662 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kumirmari (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001082/2023-2024 | 3541/AD | 17/10/2023 | 30 | SWASTIK CONSTRUCTION | 44.74 | 0 | 0
5663 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kumirmari Zone-II Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001228/2024-2025 | 5209/AD | 16/12/2024 | 45 | SUDIP PRADHAN | 32.94 | 0 | 0
5664 | Alipore Division | Canning Sub-division | inking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumirmari (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001321/2022-2023 | 11951/AD | 24/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.99 | 0 | 0
5665 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001404/2023-2024 | 1140/CSD | 31/10/2023 | 30 | NASKAR ENTERPRISE | 2.15 | 0 | 100
5666 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001405/2023-2024 | 1144/CSD | 01/11/2023 | 30 | HALDER & CO. | 2.01 | 0 | 100
5667 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kumirmari W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001768/2022-2023 | 12041/AD | 27/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 8.56 | 0 | 0
5668 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kumirmari (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001844/2022-2023 | 11541/AD | 16/02/2023 | 45 | TECH VISION | 7.44 | 0 | 0
5669 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000056/2023-2024 | 263/AD | 24/04/2023 | 0 | Resource Division | 105.54 | 0 | 0
5670 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000418/2023-2024 | 373/AD | 19/01/2024 | 0 | Resource Division | 14.93 | 0 | 0
5671 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-II for Augmentation of Kumirmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000555/2022-2023 | 544/SMD | 21/02/2023 | 90 | CHANDIMATA ELECTRICALS | 11.17 | 0 | 0
5672 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
5673 | Alipore Division | Raidighi Sub-Division | Contruction of 400 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Construction of Boundary wall, Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000631/2023-2024 | 3731/AD | 03/11/2023 | 960 | MONDAL CONSTRUCTION NEW | 366.12 | 0 | 5
5674 | Alipore Division | Raidighi Sub-Division | Protection work at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001178/2023-2024 | 357/RSD | 21/11/2023 | 60 | M/S. GANGA ENTERPRISE | 2.94 | 0 | 100
5675 | Alipore Division | Raidighi Sub-Division | Construction of approach road at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001179/2023-2024 | 358/RSD | 21/11/2023 | 60 | M/S M.B.ENTERPRISE | 3.29 | 0 | 0
5676 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000248/2023-2024 | 3105/AD | 28/09/2023 | 0 | Resource Division | 13.4 | 0 | 0
5677 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1400 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000335/2023-2024 | 1552/AD | 17/07/2023 | 180 | M/S. ROY CHOWDHURY & CO. | 156.75 | 0 | 45
5678 | Alipore Division | Canning Sub-division | Relaying and repairing of pipeline Daria W/S Scheme (NP-11-12,12-14,14-18), Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001565/2020-2021 | 972/CSD | 09/11/2020 | 30 | GANGA TUBEWELL AND HARDWARE | 4.82 | 0 | 0
5679 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Daria W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001693/2022-2023 | 11624/AD | 18/02/2023 | 787 | THE TOWER CONSTRUCTION | 7.09 | 0 | 100
5680 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Daria W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001769/2022-2023 | 12042/AD | 27/02/2023 | 30 | ZINARUL ISLAM | 19.6 | 0 | 100
5681 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000116/2022-2023 | 3041/AD | 28/09/2023 | 0 | Resource Division | 85.12 | 0 | 0
5682 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000730/2023-2024 | 553/AD | 25/01/2024 | 0 | Resource Division | 87.75 | 0 | 0
5683 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01718/2023-2024 | BP-2023-24-192 | 09/08/2023 | 0 | WBSEDCL | 5.41 | 0 | 0
5684 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Daria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000026/2023-2024 | 960/SMD | 04/04/2023 | 90 | M/S. MA KALI ELECTRIC LIGHT CORPORATION | 11.11 | 0 | 0
5685 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of submersible cable & column pipe with adopter for PH No-1 of Daria W/S Scheme (Canning-I Block) under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002520/2024-2025 | 89/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.85 | 0 | 0
5686 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Submersible pumping machinery & Armured cable for PH No-1 of Aug of Daria W/S Scheme (Canning-I Block) under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002521/2024-2025 | 88/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.84 | 0 | 0
5687 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of Butterfly valve with actuator for PH No-1 of Aug of Daria W/s Scheme (Canning-I Block) under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002522/2024-2025 | 90/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.99 | 0 | 0
5688 | S24 Pgns Mechanical | Canning Sub-division | Supply and Installation of Sluice valve, Non return valve for PH No-1 of Aug of Daria W/S Scheme (Canning-I Block) under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002523/2024-2025 | 91/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.53 | 0 | 0
5689 | Alipore Division | Diamond Harbour Sub-Division | Trial Run of existing distribution system (CI/DI/UPVC/HDPE) for Falta Zone-V under Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000818/2024-2025 | 4502/AD | 11/11/2024 | 30 | K.P. CONSTRUCTION | 7.55 | 0 | 0
5690 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001376/2024-2025 | 5521/AD | 28/12/2024 | 360 | MAA BHABANI CONSTRUCTION (DUM DUM) | 49.28 | 0 | 90
5691 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1500] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001391/2022-2023 | 10863/AD | 04/02/2023 | 785 | CONCORD ENGINEERING | 230.24 | 0 | 55
5692 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-V of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001540/2023-2024 | 439/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 0
5693 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 180 | SAB ENGINEERING WORKS | 29.99 | 0 | 0
5694 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional UPVC pipe line for balance portion in the distribution system for Providing balance FHTC to cover 100% household under the Augmentation Scheme of Falta Zone-V within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002403/2023-2024 | 1152/AD | 27/02/2024 | 300 | S.M. ENTERPRISE | 29.8 | 0 | 90
5695 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000850/2023-2024 | 788/AD | 03/02/2024 | 0 | Resource Division | 13.43 | 0 | 0
5696 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000928/2023-2024 | 1270/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
5697 | Alipore Division | Raidighi Sub-Division | Construction of 350 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- XIV of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (No. of FHTC - 100] | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000064/2023-2024 | 344/AD | 28/04/2023 | 975 | A.G.ENTERPRISE | 206.07 | 0 | 50
5698 | Alipore Division | Raidighi Sub-Division | Extension of distibution line (between node no. 3 & 30) for providing FHTC at Sankarpur PWSS of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000246/2022-2023 | 79/RSD | 18/05/2022 | 60 | RSA ENTERPRISE | 4.72 | 0 | 100
5699 | Alipore Division | Raidighi Sub-Division | Parallel distribution line for providing FHTC (Birampur, Dakshin Janardanpur & Andrarmanik) at Zone-XIV of Mathurapur - I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000268/2022-2023 | 104/RSD | 13/06/2022 | 60 | AROMA INC | 4.71 | 0 | 100
5700 | Alipore Division | Raidighi Sub-Division | Protection work to protect Laying distribution system of piped water supply at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/15058) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000656/2024-2025 | 4202/AD | 23/10/2024 | 30 | A.G.ENTERPRISE | 7.76 | 0 | 0
5701 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000881/2024-2025 | 4664/AD | 20/11/2024 | 90 | KARMAKAR CONSTRUCTION | 15.16 | 0 | 0
5702 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-XIV of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000901/2021-2022 | 4943/AD | 16/12/2021 | 90 | M/S B.N.ENTERPRISE | 83.01 | 0 | 100
5703 | Alipore Division | Raidighi Sub-Division | Interconnection between tubewells and Rising Main system of piped water supply at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001965/2022-2023 | 12719/AD | 14/03/2023 | 30 | KARMAKAR CONSTRUCTION | 6.77 | 0 | 98
5704 | Alipore Division | Raidighi Sub-Division | Protection work to protect Rising Main system and other ancillary work at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002271/2023-2024 | 478/RSD | 15/02/2024 | 30 | KARMAKAR CONSTRUCTION | 1.18 | 0 | 98
5705 | Alipore Division | Raidighi Sub-Division | Laying distrubution system (Node point 111-123-110) for providing FHTC at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002272/2023-2024 | 479/RSD | 15/02/2024 | 60 | M/S. M.M. ENTERPRISE | 4.82 | 0 | 100
5706 | Alipore Division | Raidighi Sub-Division | Laying parallel distrubution system for providing FHTC at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002273/2023-2024 | 480/RSD | 15/02/2024 | 60 | M/S. M.M. ENTERPRISE | 4.64 | 0 | 100
5707 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000600/2023-2024 | 228/AD | 11/01/2024 | 0 | Resource Division | 6.24 | 0 | 0
5708 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Shyampur (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000419/2022-2023 | 3815/SMD | 29/12/2022 | 90 | M.S.ENTERPRISE | 34.23 | 0 | 0
5709 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, service road and land development at 2nd and 3rd Tubewell Site for SHYAMPUR PART-II PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000031/2025-2026 | 982/SWD-I | 09/04/2025 | 45 | M/S MJA ENTERPRISE | 15.4 | 0 | 0
5710 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 0 | 6
5711 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall, approach pathway for SHYAMPUR PART- II PWSS to accommodate FHTC in Magrahat-II block under South 24-Pgns W/S Division-I, P.H.E. Dte for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas of South 24-Pgns District (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000381/2024-2025 | 3572/SWD-I | 12/08/2024 | 315 | SWATHI ENTERPRISE | 30.64 | 0 | 75
5712 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of land by filling of silver sand at the head work site for proposed "Ground water waste SHYAMPUR PART-II piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District under South 24-Pgns, Water Supply Division-I, P.H.E. Dte. (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000672/2024-2025 | 4398/SWD-I | 23/10/2024 | 70 | LASKAR CONSTRUCTION | 13.42 | 0 | 40
5713 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method for SHYAMPUR (Part-II) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/14550] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000808/2023-2024 | 1288/SWD-I | 15/03/2024 | 382 | B.K.ENTERPRISE | 57.32 | 0 | 85
5714 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-II) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000973/2022-2023 | 1426/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.73 | 0 | 100
5715 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000201/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 37.72 | 0 | 0
5716 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Haradhanpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000072/2023-2024 | 53/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5717 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for Augmentation of Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (for Zone-I) (SM/14159) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000145/2024-2025 | 2483/AD | 14/06/2024 | 75 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 65.9 | 0 | 0
5718 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) (SM/14159) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000555/2024-2025 | 3784/AD | 18/09/2024 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 12.13 | 0 | 0
5719 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Haradhanpur (Zone-II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000585/2023-2024 | 2342/AD | 18/08/2023 | 45 | UNIQUE AGENCY (PARTNER) | 39.91 | 0 | 100
5720 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Haradhanpur (Zone-II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000713/2023-2024 | 2534/AD | 28/08/2023 | 30 | UNIQUE AGENCY (PARTNER) | 5.05 | 0 | 100
5721 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Haradhanpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001324/2022-2023 | 9246/AD | 29/12/2022 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 100
5722 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001477/2023-2024 | 4686/AD | 18/12/2023 | 30 | SIMPLEX DRILLING CO. | 24.97 | 0 | 100
5723 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haradhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001786/2022-2023 | 3185/AD | 15/07/2022 | 45 | VOYAGER | 7.42 | 0 | 95
5724 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001858/2022-2023 | 12411/AD | 09/03/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 265.34 | 0 | 90
5725 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Haradhanpur Zone - I & II, Nagendraganj Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002156/2023-2024 | 949/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
5726 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002178/2023-2024 | 814/AD | 05/02/2024 | 30 | M/S. NIRODAMAYEE ENTERPRISE | 11.83 | 0 | 0
5727 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002282/2023-2024 | 918/AD | 08/02/2024 | 60 | KHOKAN MONDAL | 33.69 | 0 | 100
5728 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002464/2023-2024 | 1341/AD | 05/03/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 0 | 0 | 0
5729 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000293/2023-2024 | 3089/AD | 28/09/2023 | 0 | Resource Division | 1.15 | 0 | 0
5730 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000329/2023-2024 | 3144/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
5731 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000499/2023-2024 | 4825/AD | 20/12/2023 | 0 | Resource Division | 16.05 | 0 | 0
5732 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000541/2023-2024 | 25/AD | 02/01/2024 | 0 | Resource Division | 5.7 | 0 | 0
5733 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000689/2023-2024 | 459/AD | 24/01/2024 | 0 | Resource Division | 8.24 | 0 | 0
5734 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Haradhanpur Augmentation Z-I PH-1 W/S Scheme Application No:- 1007177572 Reference ID: 106218967 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01209/2024-2025 | BP-2024-25-255 | 12/08/2024 | 0 | WBSEDCL | 4.42 | 0 | 0
5735 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/02640/2023-2024 | BP-2023-24-276 | 03/10/2023 | 0 | WBSEDCL | 5.05 | 0 | 0
5736 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Haradhanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000350/2022-2023 | 3754/SMD | 29/12/2022 | 90 | M.D ENTERPRISE | 22.37 | 0 | 5
5737 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of submersible pumping machinery for PH-I, Zone-I of Augmentation of Haradhanpur W/S Scheme under South 24pgs Mechanical Division, PHE, Dte. (Block- Sagar) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002035/2023-2024 | 1226-AE-I-SMD | 04/12/2023 | 15 | M.D ENTERPRISE | 0.94 | 0 | 100
5738 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-1 Haradhanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002867/2023-2024 | 525/AE-I/SMD | 15/03/2024 | 15 | M.D ENTERPRISE | 0.9 | 0 | 0
5739 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
5740 | Alipore Division | Raidighi Sub-Division | Providing FHTC including laying distribution system and other allied works at Zone- XI of Mathurapur -II Block for ''Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000088/2023-2024 | 499/AD | 11/05/2023 | 813 | M/S B.N.ENTERPRISE | 131.92 | 0 | 60
5741 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line work at Zone-XI of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000222/2022-2023 | 3063/AD | 13/07/2022 | 30 | M/S B.N.ENTERPRISE | 6.13 | 0 | 100
5742 | Alipore Division | Raidighi Sub-Division | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
5743 | Alipore Division | Raidighi Sub-Division | Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part- II) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000580/2020-2021 | 506/RSD | 24/12/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
5744 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XI of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000660/2024-2025 | 4206/AD | 23/10/2024 | 240 | M/S B.N.ENTERPRISES | 38.78 | 0 | 75
5745 | Alipore Division | Raidighi Sub-Division | Laying of distribution pipeline of Zone- XI at Mathurapur - II Block under MEGA SURFACE WATER BASED WATER SUPPLY SCHEME, FALTA-MATHURAPUR, South 24 Parganas by remodeling the existing Nandakumarpur Zone-II water supply scheme under Raidighi Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001727/2020-2021 | 5316/AD | 18/02/2021 | 120 | M/S B.N.ENTERPRISE | 73.83 | 0 | 100
5746 | Alipore Division | Raidighi Sub-Division | Special repairing work of pipeline under Nandakumarpur Zone -II of Nandakumarpur W/S Scheme, Mathurapur -II Block under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002182/2020-2021 | 709/RSD | 08/02/2021 | 60 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.04 | 0 | 100
5747 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000654/2023-2024 | 258/AD | 15/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
5748 | Alipore Division | Raidighi Sub-Division | Providing FHTC including parallel pipeline at Zone- XVI of Mathurapur -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000057/2023-2024 | 194/AD | 19/04/2023 | 30 | B.S. CONSTRUCTION | 15.85 | 0 | 25
5749 | Alipore Division | Raidighi Sub-Division | Surging of Deep Tubewell at different W/S Scheme under Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001233/2022-2023 | 756/RSD | 30/12/2022 | 30 | SIMPLEX DRILLING CO. | 4.72 | 0 | 100
5750 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Payla Bhagabanpur W/S Scheme, modified as Zone- XVI of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001299/2024-2025 | 5373/AD | 23/12/2024 | 30 | SANKAR HALDER | 4.8 | 0 | 100
5751 | Alipore Division | Raidighi Sub-Division | Remodeling of laying distribution system of piped water supply at Zone- XVI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002229/2023-2024 | 921/AD | 08/02/2024 | 30 | KARMAKAR CONSTRUCTION | 17.1 | 0 | 90
5752 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000644/2023-2024 | 248/AD | 15/01/2024 | 0 | Resource Division | 0.63 | 0 | 0
5753 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
5754 | Alipore Division | Raidighi Sub-Division | Construction of 300 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- XIV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000346/2023-2024 | 1606/AD | 18/07/2023 | 923 | A.K. INDUSTRIES | 308.36 | 0 | 20
5755 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000245/2023-2024 | 3066/AD | 28/09/2023 | 0 | Resource Division | 39.42 | 0 | 0
5756 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
5757 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- X of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000355/2023-2024 | 3733/AD | 03/11/2023 | 722 | M/S ASCON | 111.11 | 0 | 50
5758 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Nandakumarpur Zone - I W/S Scheme, modified as Zone- X of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001300/2024-2025 | 5374/AD | 23/12/2024 | 30 | MONDAL ENTERPRISE (JOYNAGAR) | 4.85 | 0 | 0
5759 | Alipore Division | Raidighi Sub-Division | Horizontal boring and allied works for laying of distribution system of piped water supply at Zone-X of Mathurapur-II Block for ?Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001771/2021-2022 | 629/RSD | 29/12/2021 | 15 | M/S B.M. CONSTRUCTION | 3 | 0 | 100
5760 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000656/2023-2024 | 260/AD | 15/01/2024 | 0 | Resource Division | 3.84 | 0 | 0
5761 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Khagra, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 542] (TSM/017752) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000119/2023-2024 | 555/AD | 12/05/2023 | 90 | MAJUMDER ENTERPRISE | 208.66 | 0 | 86
5762 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. 360Mtr. Depth Rig bored Tube wells for the Khagra Mini Piped Water Supply Scheme, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001807/2022-2023 | 12131/AD | 01/03/2023 | 814 | B.K. ENTERPRISE. | 15.65 | 0 | 95
5763 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khagra New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001893/2022-2023 | 11552/AD | 17/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 1.59 | 0 | 0
5764 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000734/2023-2024 | 558/AD | 25/01/2024 | 0 | Resource Division | 1.18 | 0 | 0
5765 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Khagra supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000270/2023-2024 | 1130/SMD | 24/04/2023 | 90 | MOUMITA ENTERPRISE | 9.43 | 0 | 0
5766 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1& 2 for Augmentation of Malayapur (Zone-24) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 941/SMD | 04/04/2023 | 90 | MAA TARA CONSTRUCTION | 22.2 | 0 | 0
5767 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALAYPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 841] [TSM/018360] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 369/SWD-I | 27/04/2023 | 975 | JAI BHARAT COMMERCIAL CORPORATION | 121.47 | 0 | 80
5768 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work, Restoration of road and other allied works for Ground water based MALAYAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15180) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000342/2024-2025 | 3316/SWD-I | 23/07/2024 | 405 | JAI BHARAT COMMERCIAL CORPORATION | 59.41 | 0 | 30
5769 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based MALAYAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000922/2022-2023 | 1174/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 2.57 | 0 | 100
5770 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000148/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 6.56 | 0 | 0
5771 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 24 (twenty four) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chhota Molla Khali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000552/2021-2022 | 2619/AD | 28/09/2021 | 1281 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 445.83 | 0 | 50
5772 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Choto Mollakhali Water Supply Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000940/2021-2022 | 4946/AD | 17/12/2021 | 60 | R.G. ENTERPRISE (I) | 7.66 | 0 | 100
5773 | Alipore Division | Canning Sub-division | Construction of 300 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1153] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000040/2023-2024 | 175/AD | 19/04/2023 | 300 | SAMSUL ENTERPRISE | 483.35 | 0 | 60
5774 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000137/2023-2024 | 692/AD | 18/05/2023 | 15 | HI TECH ENTERPRISE | 10.48 | 0 | 0
5775 | Alipore Division | Canning Sub-division | Sinking of 02 (Two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000141/2023-2024 | 277/AD | 24/04/2023 | 45 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0
5776 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work for Augmentation of Pathakhali (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000731/2024-2025 | 4389/AD | 05/11/2024 | 45 | SAMSUL ENTERPRISE | 44.02 | 0 | 0
5777 | Alipore Division | Canning Sub-division | Development of tube well no-1 at Pathankhali W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000859/2022-2023 | 288/CSD | 19/05/2022 | 40 | S.P. CONSTRUCTION (I) | 0.67 | 0 | 100
5778 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep replacement tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4, Chandipur of Pathankhali Water Supply Scheme Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001574/2021-2022 | 6955/AD | 29/03/2022 | 30 | AQUATECH ENGINEER | 20.64 | 0 | 0
5779 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001927/2022-2023 | 11800/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 5.74 | 0 | 95
5780 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001952/2022-2023 | 12688/AD | 14/03/2023 | 45 | RAJLAKSHMI ENTERPRISE | 8.92 | 0 | 0
5781 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001953/2022-2023 | 12689/AD | 14/03/2023 | 45 | PODDER ENTERPRISE | 8.61 | 0 | 0
5782 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Pathankhali (Zone-III) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002200/2024-2025 | 471/AD | 06/02/2025 | 60 | MOUSUMI ENTERPRISE | 29.17 | 0 | 0
5783 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000011/2023-2024 | 118/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
5784 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000050/2023-2024 | 257/AD | 24/04/2023 | 0 | Resource Division | 48.14 | 0 | 0
5785 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000138/2023-2024 | 857/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
5786 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000411/2023-2024 | 367/AD | 19/01/2024 | 0 | Resource Division | 7.1 | 0 | 0
5787 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-II for Augmentation of Pathankhali supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000278/2023-2024 | 1137/SMD | 24/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 19.55 | 0 | 0
5788 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Purba Radhanagar (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000096/2023-2024 | 452/AD | 08/05/2023 | 15 | M/S ARIYAN ENTERPRISE | 13.19 | 0 | 0
5789 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-III) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1382] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000133/2023-2024 | 757/AD | 23/05/2023 | 710 | M N J ENTERPRISES | 519.69 | 0 | 45
5790 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000139/2023-2024 | 199/AD | 19/04/2023 | 60 | M/S ABDUL BARIK | 65.94 | 0 | 0
5791 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001930/2022-2023 | 11803/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 4.65 | 0 | 95
5792 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002012/2022-2023 | 12918/AD | 21/03/2023 | 45 | M/S JAHANGIR SARDAR | 8.92 | 0 | 0
5793 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002013/2022-2023 | 12919/AD | 21/03/2023 | 45 | M/S JAHANGIR SARDAR | 8.61 | 0 | 0
5794 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002038/2022-2023 | 13034/AD | 24/03/2023 | 45 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 0
5795 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000047/2023-2024 | 254/AD | 24/04/2023 | 0 | Resource Division | 60.78 | 0 | 0
5796 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-III for Augmentation of Purba Radhanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000271/2023-2024 | 1131/SMD | 24/04/2023 | 90 | SHIVAM ENTERPRISE | 19.55 | 0 | 0
5797 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
5798 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000163/2023-2024 | 279/AD | 24/04/2023 | 45 | GOLDEN GROUPS | 38.55 | 0 | 0
5799 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
5800 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000954/2023-2024 | 2986/AD | 26/09/2023 | 45 | M/S.SREEJIT ENTERPRISE | 27.52 | 0 | 0
5801 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000955/2023-2024 | 2987/AD | 26/09/2023 | 30 | M/S. S.B. MANDAL & SONS | 9.58 | 0 | 0
5802 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001834/2022-2023 | 12184/AD | 01/03/2023 | 706 | GOLDEN GROUPS | 38.55 | 0 | 100
5803 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002073/2023-2024 | 769(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
5804 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
5805 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Manmathanagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002163/2022-2023 | 8336/AD | 12/12/2022 | 45 | LEMNISCATE | 6.91 | 0 | 100
5806 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000123/2023-2024 | 659/AD | 17/05/2023 | 0 | Resource Division | 15.46 | 0 | 0
5807 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000451/2023-2024 | 4716/AD | 18/12/2023 | 0 | Resource Division | 32.08 | 0 | 0
5808 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000818/2023-2024 | 663/AD | 30/01/2024 | 0 | Resource Division | 2.77 | 0 | 0
5809 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Manmathanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000111/2023-2024 | 1005/SMD | 11/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 21.61 | 0 | 0
5810 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Initial 50% payment for the amount Rs. 4160934/- (forty-one lakh sixty thousand nine hundred & thirty four) only i.e. Rs. 2080467/- (twenty lakh eighty thousand four hundred & sixty-seven) only for restoration of road edge and hard shoulder damaged due to laying of pipeline of Dakshin Barasat to Usthi Road under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT and Zone -IX at Ghola Noapara under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16187 and SM/14725). | AE SWSD-II | JE4 | BILL/00801/2024-2025 | BP-2024-25-492 | 21/11/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 20.8 | 0 | 0
5811 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Shifting of 2 nos. LT pole for construction of OHR at Alampur under JJM project of PHED | AE SWSD-II | JE4 | BILL/01763/2023-2024 | BP-2023-24-617 | 22/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0
5812 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
5813 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of pipe carrying structure over the canals at village Amtwali Hariharpur GP for the laying of distribution pipeline within Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. [SM/16187] | AE SWSD-II | JE4 | ORD/000097/2025-2026 | 1772/SWD-I | 02/07/2025 | 45 | ADRIK ENTERPRISE | 10.88 | 0 | 0
5814 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 1078 | M/S GHOSH AND CO. | 1160.71 | 0 | 56
5815 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-IV (Hijalhat) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | AE SWSD-II | JE4 | ORD/000495/2024-2025 | 3867/SWD-I | 02/09/2024 | 541 | MILAN GHOSH | 310.34 | 0 | 45
5816 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Design of Route survey of distribution system of Mograhat Zone-IV within Mograhat-I Block for Augmentation of Laying Distribution System, to extend the benefit of 100% households in Zone-IV at HIJALHAT of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns W/S Divn-I, P.H.E. Dte. (Route Surveying of 60 KM) [TSM/015076] | AE SWSD-II | JE4 | ORD/000658/2022-2023 | 3361/SWD-I | 09/03/2023 | 7 | GEO SOLUTION | 2.38 | 0 | 0
5817 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000063/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 5.03 | 0 | 0
5818 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (Two) nos. chlorine room (size 5.90 m x 4.10 m out to out) with sanitary and water supply arrangement at Head work Site at Ghateswar in Zone-X and Achina in Zone-VII for Augmentation of laying distribution system to extend the benefit of 100% house hold in Zone-XI at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta Mathurapur, District-South 24 Parganas under South 24-Pgns W/S Division-I, PHE Dte. (SM/16188) | AE HQ-I |  | ORD/000029/2025-2026 | 980/SWD-I | 09/04/2025 | 60 | SANKAR HALDER | 13.37 | 0 | 0
5819 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-XI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2329) (TSM/015099 & TSM/010837) | AE HQ-I |  | ORD/000387/2023-2024 | 1840/SWD-I | 17/08/2023 | 775 | M/S. B.M. CONSTRUCTION | 327.12 | 0 | 80
5820 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 90mm &160mm dia HDPE Pipe line over Kulpi Road near Uttar Sultanpur Railway Gate, over Dhola Road near Dhola Railway Gate & over Shibpur Road near Polerhat Railway Gate with allied works for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/015099). | AE HQ-I |  | ORD/000548/2023-2024 | 2496/SWD-I | 06/10/2023 | 60 | R.D CONSTRUCTION | 3.39 | 0 | 100
5821 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 600 mm dia (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track at Uttar Sultanpur Railway Gate over Kulpi Road near Lakshmikantapur Railway Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 62/17 - 62/18, as per permission of Railway Authority, for laying of 200 mm dia (ID) 6 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099) [2nd Call] | AE HQ-I |  | ORD/000671/2022-2023 | 3434/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 49.49 | 0 | 0
5822 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & laying of 600 mm dia (ID) MS Pipe conduits 60 mtr. in length to be prepared from 10 mm thick MS Plate by pipe jacking technique, including supplying and laying of 200 mm dia (ID) MS water main within the conduit 90 mtr. in length to be prepared from 06 mm thick MS Plate across and underneath the Railway Track at Shibpur Railway Gate near Polerhat Railway Gate of Lakshmikantapur Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 63/14 - 63/15 as per permission obtained from Railway Authority, including construction of Drive Pit & Receiving Pit, as requred, for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/015099) | AE HQ-I |  | ORD/000664/2022-2023 | 3351/SWD-I | 09/03/2023 | 60 | M/S. GOUTAM ROY | 51.13 | 0 | 100
5823 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 600 mm dia (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track at Dhola Railway Gate over Dhola Road near Lakshmikantapur Railway Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 62/07 - 62/08 as per permission of Railway Authority, for laying of 300 mm dia (ID) 7 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000672/2022-2023 | 3435/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 55.47 | 0 | 0
5824 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 700 mm dia (ID) 12mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track in between Basuldanga station and Gurudasnagar station and in between Mast No.56/27, 56/29 and 56/28, 56/30 as per permission of Railway Authority, for laying of 450 mm dia (ID) 8.6 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000673/2022-2023 | 3436/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 69.23 | 0 | 50
5825 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 700 mm dia (ID) 12mm thick MS casing pipe line 135 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track near Karanjali Railway Station in between Karanjali Halt (KNJI) - Nischindopur Market Halt (NCPM) KM/TP 75/13-75/14 as per permission of Railway Authority, for laying of 500 mm dia (ID) 10 mm thick MS water supply pipe 160 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000674/2022-2023 | 3437/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 134.2 | 0 | 100
5826 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Existing R.C.C. Reservoir of capacity 250 CUM and staging height 20 mtr at Head Work site of Uttar Sultanpur (Zone XI) within Mandir Bazar Block Block " for Mega Surface Water Based Water Supply Scheme for Falta -Mathurapur, South 24 Parganas, under South 24 Pgns. Water Supply Division-I, PHE, Dte. (SM/16188) | AE HQ-I |  | ORD/000699/2024-2025 | 4501/SWD-I | 30/10/2024 | 45 | SRIJON ENTERPRISE | 10.52 | 0 | 100
5827 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Cholorine room, Office Room, Construction of Pathway at Head work site of of Uttar Sultanpur (Zone XI) within Mandir Bazar Block for Mega Surface Water Based Water Supply Scheme for Fakta -Mathurapur, South 24 Parganas, under South 24 Pgns. Water Supply Division-I, PHE, Dte. [SM/16188] | AE HQ-I |  | ORD/000766/2024-2025 | 4687/SWD-I | 18/11/2024 | 30 | G.M. ENTERPRISE (MURSHIDABAD) | 7.85 | 0 | 0
5828 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pump House cum chlorine room (size 5.90 m x 4.10 m) with sanitary and water supply arrangement at Head work sites for various zones of Mandirbazar block under Mega Surface Water Based W/S Scheme for Falta-Mathurapur, South 24-Parganas, under South 24 Parganas W/S Division-I, PHE Dte. [SM/18706, SM/15485, SM/12204, SM/18715, SM/12205] | AE HQ-I |  | ORD/000790/2024-2025 | 4759/SWD-I | 21/11/2024 | 60 | NIKHIL SAMADDAR | 35.04 | 0 | 0
5829 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system for Zone-XI, Uttar Sultanpur (OHR Capacity- 250cum.) under Mandirbazar Block" under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. District. | AE HQ-I |  | ORD/000852/2022-2023 | 18/SWD-I | 06/04/2022 | 30 | LEMNISCATE | 1.98 | 0 | 100
5830 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000049/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
5831 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01751/2023-2024 | BP-2023-24-207 | 11/08/2023 | 0 | WBSEDCL | 7.92 | 0 | 0
5832 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-II for Augmentation of Tilpi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000283/2023-2024 | 1143/SMD | 24/04/2023 | 799 | JAL PRAVAHIKA PVT. LTD. | 21.77 | 0 | 45
5833 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Tilpi Zone-II W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002350/2024-2025 | 11/SMSD | 03/01/2025 | 15 | JAL PRAVAHIKA PVT. LTD. | 0.95 | 0 | 0
5834 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land, Construction of approach road and other allied works for Ground Water Based TILPI (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/15865) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000404/2024-2025 | 3684/SWD-I | 22/08/2024 | 251 | GARAI INFRA PROJECT | 43.89 | 0 | 65
5835 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 0 | 96
5836 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based TILPI (ZONE-II) piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15865) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000575/2024-2025 | 4274/SWD-I | 01/10/2024 | 60 | GARAI INFRA PROJECT | 29.92 | 0 | 0
5837 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-II PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018041) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000709/2022-2023 | 3523/SWD-I | 17/03/2023 | 30 | M/S SUNDARI CONSTRUCTION | 31.76 | 0 | 100
5838 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "TILPI Zone-II Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000757/2022-2023 | 708/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 0 | 100
5839 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000155/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 40.5 | 0 | 0
5840 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road 2) Debipur More to Sonagachi More | AE BSD,Assistant Engineer | Junior Engineer | BILL/01733/2024-2025 | BP-2024-25-797 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.96 | 0 | 0
5841 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/02285/2023-2024 | BP-2023-24-252 | 11/09/2023 | 0 | WBSEDCL | 3.92 | 0 | 0
5842 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Balbalia water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15866) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 961/SMSD | 09/07/2024 | 15 | T.S. CONSTRUCTION | 0.89 | 0 | 0
5843 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Balbalia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 940/SMSD | 28/06/2024 | 15 | T.S. CONSTRUCTION | 0.58 | 0 | 0
5844 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Balbalia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001126/2023-2024 | 4261/SMD | 06/11/2023 | 90 | T.S. CONSTRUCTION | 22.2 | 0 | 40
5845 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BALBALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2078] [TSM/017761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 840/SWD-I | 05/06/2023 | 783 | ASHOKA ENTERPRISE | 480.17 | 0 | 60
5846 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BALBALIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000651/2022-2023 | 3323/SWD-I | 06/03/2023 | 30 | MAHI CONSTRUCTION | 31.77 | 0 | 0
5847 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Balbalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000946/2022-2023 | 1278/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
5848 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000118/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 45.75 | 0 | 0
5849 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
5850 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000102/2023-2024 | 505/AD | 11/05/2023 | 15 | SURYA ENTERPRISE | 7.71 | 0 | 0
5851 | Alipore Division | Canning Sub-division | Laying Distribution system for Augmentation of Basanti W/S Scheme (Zone - VII), Block - Basanti under Canning Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000127/2023-2024 | 145/AD | 17/04/2023 | 849 | ARISTOCON ENGINEERS'CO-OP. SOCIETY LTD. | 161.26 | 0 | 95
5852 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 0 | 35
5853 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000496/2023-2024 | 1797/AD | 26/07/2023 | 45 | MONDAL ENTERPRISE (SALTLAKE) | 7.35 | 0 | 0
5854 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000498/2023-2024 | 1798/AD | 26/07/2023 | 618 | B.S.ENTERPRISE | 7.09 | 0 | 100
5855 | Alipore Division | Canning Sub-division | Construction of 250 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for augmentation of Basanti (Zone-VII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000625/2023-2024 | 4327/AD | 01/12/2023 | 300 | R.S.CONSTRUCTION CO. | 105.35 | 0 | 0
5856 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001919/2022-2023 | 12461/AD | 10/03/2023 | 45 | SANDIP SARKAR | 39.12 | 0 | 0
5857 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001937/2022-2023 | 11808/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 0
5858 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000027/2023-2024 | 232/AD | 24/04/2023 | 0 | Resource Division | 36.13 | 0 | 0
5859 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000156/2023-2024 | 1049/AD | 15/06/2023 | 0 | Resource Division | 5.86 | 0 | 0
5860 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at pump house no- 1 of Basanti (Zone-VII) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01839/2024-2025 | BP-2024-25-466 | 18/11/2024 | 0 | WBSEDCL | 19.02 | 0 | 0
5861 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-VII of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001505/2022-2023 | 874/SMD | 23/03/2023 | 1015 | WESTERN ENGINEERING CO. | 21.14 | 0 | 45
5862 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at PH-1 of Basanti (Zone-VII) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15972) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002225/2024-2025 | 396/SMSD | 19/03/2025 | 15 | WESTERN ENGINEERING CO. | 0.92 | 0 | 0
5863 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Kalayanpur ( Khodar Bazar) Part-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000059/2023-2024 | 1053/SMD | 18/04/2023 | 90 | M/S. S.S. ENTERPRISE | 21.77 | 0 | 0
5864 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kalyanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000529/2022-2023 | 442/SMD | 17/02/2023 | 90 | RSA ENTERPRISE | 13.01 | 0 | 65
5865 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at PH No.-1 of Kalyanpur (Part-II) & Piyali Kolaghata w/s scheme under South 24-Pgs Mechanical Division PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 1070/SMSD | 17/08/2023 | 10 | SHRI KRISHNA ENTERPRISE | 0.78 | 0 | 100
5866 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Kalyanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002688/2023-2024 | 1106/SMSD | 22/08/2023 | 132 | RSA ENTERPRISE | 0.29 | 0 | 100
5867 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump House cum Chlorine Room, Boundary Wall along with Laying Distribution System, Rising Main and providing FHTC for Augmentation of Piped W/S Scheme of KALYANPUR (KHODAR BAZAR) (PART-II) of BARUIPUR Block of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1180] [TSM/018149] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 971/SWD-I | 08/06/2023 | 90 | APORUPA CONSTRUCTION | 151.88 | 0 | 0
5868 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KALYANPUR (KHODAR BAZAR) , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000505/2021-2022 | 1904/SWD-I | 27/01/2022 | 30 | RADIANT | 2.62 | 0 | 100
5869 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing by Rotary method for KALYANPUR KHODARBAZAR (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur block under South 24-Pgns. W/S Division-I, PHE Dte. for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15776] (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000719/2024-2025 | 4577/SWD-I | 11/11/2024 | 30 | RAJKUMAR MONDAL | 31.8 | 0 | 0
5870 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000171/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.37 | 0 | 0
5871 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00122/2024-2025 | BP-2024-25-38 | 24/04/2024 | 0 | WBSEDCL | 3.88 | 0 | 0
5872 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Beralia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15783) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000299/2024-2025 | 928-SMSD | 28/06/2024 | 15 | T.S. CONSTRUCTION | 0.58 | 0 | 0
5873 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Beralia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001128/2023-2024 | 4270/SMD | 07/11/2023 | 90 | T.S. CONSTRUCTION | 22.2 | 0 | 40
5874 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for BERALIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 990] [TSM/018427] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000069/2023-2024 | 370/SWD-I | 27/04/2023 | 790 | SOMA ENTERPRISE | 207.4 | 0 | 93
5875 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BERALIA PWSS to accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018427) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000706/2022-2023 | 3519/SWD-I | 17/03/2023 | 30 | M/S A.M. CONSTRUCTION | 31.76 | 0 | 50
5876 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Beralia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000945/2022-2023 | 1266/SWD-I | 12/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
5877 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000119/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.83 | 0 | 0
5878 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Mahismari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000286/2023-2024 | 1146/SMD | 24/04/2023 | 1168 | SARKAR ELECTRICAL | 21.77 | 0 | 45
5879 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Mahismari W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16125) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002312/2024-2025 | 382/SMSD | 18/03/2025 | 15 | SARKAR ELECTRICAL | 0.95 | 0 | 0
5880 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for MAHISHMARI MOUZA Piped Water Supply Scheme of JAYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1025] [TSM/018296] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 1736/SWD-I | 10/08/2023 | 630 | M. MUKHERJEE | 350.46 | 0 | 40
5881 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for MAHISMARI PWSS to Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018296) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000707/2022-2023 | 3520/SWD-I | 17/03/2023 | 30 | MALLICK CONSTRUCTION | 31.63 | 0 | 100
5882 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, protection wall for laying pipeline, restoraton of damaged roads due to laying of pieline other allied worksand miscelleneous work for Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16125) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000772/2024-2025 | 4757/SWD-I | 21/11/2024 | 45 | B.M. ENTERPRISE | 57.33 | 0 | 0
5883 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Mahishmari Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000958/2022-2023 | 1183/SWD-I | 01/09/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
5884 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000115/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.32 | 0 | 0
5885 | Alipore Division | Baruipur Sub-Division | Road restoration of Jagita Sarda House to Khalpar Bypass Via Roybahadur Via Projit Mondal To Nikfiil Ranjan Roy House Via Khardhya Math Via Bapi Naskar House | AE BSD,Assistant Engineer | Junior Engineer | BILL/01702/2024-2025 | BP-2024-25-787 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.16 | 0 | 0
5886 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Purandapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 1090/SMD | 18/04/2023 | 90 | ASHIM UDYOG | 20.81 | 0 | 0
5887 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PURANDARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 934] [TSM/018251] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 371/SWD-I | 27/04/2023 | 90 | SUJATA CONSTRUCTION | 172.64 | 0 | 80
5888 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, pipeline protection development of land and other allied works for Ground water based PURANDARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/16129) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 3133/SWD-I | 10/07/2024 | 265 | RAJLAXMI CONSTRUCTION | 67.13 | 0 | 30
5889 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PURANDARPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018251] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000648/2022-2023 | 3320/SWD-I | 06/03/2023 | 30 | M/S BASAK CONSTRUCTION | 31.72 | 0 | 64
5890 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Purandarpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000935/2022-2023 | 1227/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.5 | 0 | 100
5891 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000127/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 27.76 | 0 | 0
5892 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05031/2023-2024 | BP-2023-24-560 | 11/03/2024 | 0 | WBSEDCL | 6.04 | 0 | 0
5893 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Rajpur Korabag water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 1144/SMD | 24/04/2023 | 821 | M/S.UTTAM KUMAR CHATTERJEE | 21.6 | 0 | 90
5894 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAJPUR KORABEG MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1692] [TSM/018299] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 1766/SWD-I | 10/08/2023 | 900 | EQUIPMENTS AND SPARES AGENCIES | 411.03 | 0 | 45
5895 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for RAJPUR KORABEG PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018299) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000705/2022-2023 | 3514/SWD-I | 17/03/2023 | 30 | SOURAV GHOSH | 31.75 | 0 | 5
5896 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16131) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000738/2024-2025 | 4636/SWD-I | 14/11/2024 | 45 | EQUIPMENTS AND SPARES AGENCIES | 71.4 | 0 | 0
5897 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rajpur Korabag Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000957/2022-2023 | 1307/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.64 | 0 | 100
5898 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000116/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 32.75 | 0 | 0
5899 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00020/2023-2024 | BP-2023-24-30 | 18/05/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
5900 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/02283/2023-2024 | BP-2023-24-251 | 11/09/2023 | 0 | WBSEDCL | 7.94 | 0 | 0
5901 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of Surjapur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000021/2025-2026 | 536/SMSD | 09/04/2025 | 21 | MONOSEBA CONSTRUCTION | 0.79 | 0 | 100
5902 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Surjapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1094/SMD | 18/04/2023 | 834 | JAI BHARAT COMMERCIAL CORPORATION | 21.77 | 0 | 100
5903 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Surjapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16135) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 488/SMSD | 23/04/2024 | 404 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 100
5904 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Surjapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/16135) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 489/SMSM | 23/04/2024 | 404 | JAI BHARAT COMMERCIAL CORPORATION | 0.89 | 0 | 100
5905 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Surjapur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16135) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 487/SMSD | 23/04/2024 | 404 | JAI BHARAT COMMERCIAL CORPORATION | 0.84 | 0 | 100
5906 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising main,including Funtional Household Tap connection(FHTC) for SURJAPUR piped water supply scheme of BARUIPUR Block, under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under South 24 Pgns. W/S Division-I, P.H.E Dte. (TSM/018700) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 347/SWD-I | 26/04/2023 | 675 | BAIDYA ENTERPRISE | 53.26 | 0 | 76
5907 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall (Two nos) for SURJAPUR PWSS of Baruipur block, under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Paraganas district under South 24 Pgns. W/S Divn-I, PHE, Dte. (TSM/018700) [Length - 50.0 mtr.] (Tube Well site-1 & 2) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000089/2023-2024 | 442/SWD-I | 03/05/2023 | 60 | B.M. TRADERS | 13.85 | 0 | 0
5908 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum chlorination room (Two nos) for SURJAPUR PWSS of Baruipur Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24 Pgns W/S Division-I, PHE, Dte. (TSM/018700) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 569/SWD-I | 15/05/2023 | 60 | BINAPANI ENTERPRISE | 11.28 | 0 | 100
5909 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SURJAPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018700] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000653/2022-2023 | 3350/SWD-I | 09/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 100
5910 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Surjapur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000928/2022-2023 | 1180/SWD-I | 01/09/2022 | 30 | GEO SOLUTION | 2.36 | 0 | 100
5911 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000261/2023-2024 | 2428/SWD-I | 30/09/2023 | 0 | Resource Division | 22.03 | 0 | 0
5912 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000330/2023-2024 | 268/SWD-I | 10/01/2024 | 0 | Resource Division | 2.14 | 0 | 0
5913 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service(power) connection at Jagulgachi PH-1 water supply scheme under bhangar-I block Reference ID- 106492239, Application No-1007561863 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00566/2024-2025 | BP-2024-25-139 | 03/07/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
5914 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Jagulgachhi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001516/2022-2023 | 896/SMD | 27/03/2023 | 90 | GLACIER ENGINEERING CO. | 23.44 | 0 | 40
5915 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Bhangor Bodra Road from 0.00 kmp to 204kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 250mm to 90mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/15754) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00641/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.37 | 0 | 0
5916 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) and construction of Pump House cum Chlorine Room (2 Nos.) for JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2089) (TSM/018474) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 125/SWD-I | 12/04/2023 | 744 | A P POWER AND CONCRETE | 279.5 | 0 | 10
5917 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Upgradation of Pumphouse, Cholorine room, Pathway & other allied works at Head work site of "JAGULGACHHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15754) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000430/2024-2025 | 3872/SWD-I | 03/09/2024 | 30 | TOJO ENTERPRISE | 9.35 | 0 | 100
5918 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for JAGULGACHI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018474] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 3287/SWD-I | 03/03/2023 | 308 | M/S MONDAL ENTERPRISE | 31.76 | 0 | 50
5919 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15754] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000750/2024-2025 | 4672/SWD-I | 18/11/2024 | 60 | A.P POWER AND CONCRETE | 75.42 | 0 | 0
5920 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000046/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 24.11 | 0 | 0
5921 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000216/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.87 | 0 | 0
5922 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00008/2023-2024 | BP-2023-24-31 | 18/05/2023 | 0 | WBSEDCL | 5.89 | 0 | 0
5923 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Hasanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 1036/SMD | 13/04/2023 | 719 | A.K. INDUSTRIES | 25.4 | 0 | 100
5924 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Hasanpur scheme under SMD, P.H.E. Dte.(Block-Sonarpur) (SM/15679) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000691/2024-2025 | 1014/SMSD | 11/07/2024 | 15 | A.K. INDUSTRIES | 0.92 | 0 | 100
5925 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Hasanpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002997/2023-2024 | 261/SMSD | 23/02/2024 | 15 | A.K. INDUSTRIES | 0.92 | 0 | 100
5926 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & laying of 610 mm dia (OD) MS Pipe conduits 50 mtr. in length to be prepared from 12.5 mm thick MS Plate by pipe jacking technique, including supplying and laying of 219 mm dia (OD) MS water main within the conduit 60 mtr. in length to be prepared from 10 mm thick MS Plate, across and underneath the Railway Track at Bidyadharpur Railway Station in between Station Champahati (CHT) - Bidyadharpur (BDYP), OHE Mast No. 20/4C as per permission of Railway Authority for "Hasanpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/15759) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 974/SWD-I | 09/04/2025 | 60 | SRIJON ENTERPRISE | 64.28 | 0 | 0
5927 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design including Laying Rising Main along with providing FHTC for HASANPUR Piped W/S Scheme in Sonarpur Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1435] [TSM/018119] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000071/2023-2024 | 372/SWD-I | 27/04/2023 | 646 | M/S. JAYDEEP DASGUPTA | 156.02 | 0 | 100
5928 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pump House cum Chlorine Room along with Laying Distribution System for HASANPUR Piped W/S Scheme to accommodate FHTC in Sonarpur Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018119] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000074/2023-2024 | 388/SWD-I | 28/04/2023 | 704 | J.D. CONSTRUCTION | 165.4 | 0 | 30
5929 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15759) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000245/2024-2025 | 2665/SWD-I | 07/06/2024 | 184 | J.D. CONSTRUCTION | 10.57 | 0 | 80
5930 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of additional 90mm,75mm dia pipeline work along with Bullah Piling work of "HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". [SM/15759] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000545/2024-2025 | 4102/SWD-I | 20/09/2024 | 122 | J.D. CONSTRUCTION | 25.92 | 0 | 100
5931 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HASANPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018119] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 3407/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
5932 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall and Temporary approach road for Head work of HASANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (Length-166 mtr.) [SM/15759] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 555/SWD-I | 31/01/2024 | 302 | M/S. JAYDEEP DASGUPTA | 27.69 | 0 | 5
5933 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000017/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 6.03 | 0 | 0
5934 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000231/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.84 | 0 | 0
5935 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01111/2023-2024 | BP-2023-24-143 | 24/07/2023 | 0 | WBSEDCL | 10.24 | 0 | 0
5936 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Deara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000348/2024-2025 | 2452/SMD | 01/08/2024 | 90 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 11.32 | 0 | 0
5937 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Deara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/000356/2024-2025 | 2465/SMD | 01/08/2024 | 90 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 11.32 | 0 | 0
5938 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Deara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/001421/2022-2023 | 3460/SMD | 23/12/2022 | 90 | BOSE & CHATTERJEE INDUSTRIES | 22.36 | 0 | 0
5939 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.59] |  |  | BILL/00484/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 31.8 | 0 | 0
5940 | South 24 Pgs W/S Division I |  | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for DEARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2233] |  |  | ORD/000238/2023-2024 | 1435/SWD-I | 18/07/2023 | 898 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 593.7 | 0 | 50
5941 | South 24 Pgs W/S Division I |  | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DEARA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016320] |  |  | ORD/000296/2023-2024 | 1661/SWD-I | 03/08/2023 | 15 | PADMA ENGINEERING CO. | 3.14 | 0 | 100
5942 | South 24 Pgs W/S Division I |  | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR DEARA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016320) |  |  | ORD/000299/2023-2024 | 1664/SWD-I | 03/08/2023 | 30 | PADMA ENGINEERING CO. | 30.07 | 0 | 100
5943 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at Headwork and 2nd Tubewell site of DEARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18329) |  |  | ORD/000823/2023-2024 | 1297/SWD-I | 15/03/2024 | 45 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 52.22 | 0 | 0
5944 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 35.83 | 0 | 0
5945 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000315/2023-2024 | 245/SWD-I | 10/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
5946 | Alipore Division | Diamond Harbour Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 360 mtr. deep Tubewell by Direct Rotary method for improvement of water supply at Pump House No. 01 of Fatepur W/S Scheme Block - Falta under Diamond Harbour Sub-Division in the District of South 24 Parganas under Alipore Division, PHE Dte. (zone-vii) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000472/2022-2023 | 5523/AD | 29/09/2022 | 30 | D.N. ENTERPRISE | 24.51 | 0 | 100
5947 | Alipore Division | Diamond Harbour Sub-Division | Surging of Tube Well No. 01 of Fatepur Water Supply Scheme and Tube Well No. 01 of Birendra Bagaria Water Supply Scheme under Diamond Harbour Sub-Division, of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000959/2021-2022 | 300/DHSD | 08/10/2021 | 10 | SIMPLEX DRILLING CO. | 0.63 | 0 | 100
5948 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001377/2024-2025 | 5522/AD | 28/12/2024 | 30 | SUPRITI ENTERPRISE | 22.69 | 0 | 0
5949 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VI of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001542/2023-2024 | 440/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 0
5950 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VIIIA of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001544/2023-2024 | 441/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
5951 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VIIIB of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001547/2023-2024 | 442/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
5952 | Alipore Division | Diamond Harbour Sub-Division | Extension of distribution pipeline from Shop of Mondal Carry bag & Plastic Wholesaler to House of Binniyani Purkait near Sherpur Bazar area of Sirakol Zone-II W/S Scheme of Mograhat-I Block and installation of different dia Sluice valves at various points of existing distribution pipeline of Fatepur W/S Scheme of Falta Block under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001615/2022-2023 | 478/DHSD | 03/01/2023 | 10 | CHANDRA ENTERPRISE | 4.47 | 0 | 0
5953 | Alipore Division | Diamond Harbour Sub-Division | Surging of Tube Well No. 01 of Fatepur Water Supply Scheme, Block : Falta under Diamond Harbour Sub-Division, of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001749/2022-2023 | 269/DHSD | 02/09/2022 | 15 | SIMPLEX DRILLING CO. | 0.67 | 0 | 95
5954 | Alipore Division | Diamond Harbour Sub-Division | Laying of UPVC pipe line for balance portion in the distribution system for Providing balance FHTC to cover 100 percent household under Falta Zone-VII within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002114/2023-2024 | 828/AD | 05/02/2024 | 90 | SUPRITI ENTERPRISE | 31.02 | 0 | 100
5955 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VII at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002395/2024-2025 | 639/AD | 18/02/2025 | 30 | MAA BHABANI CONSTRUCTION (DUM DUM) | 13.33 | 0 | 0
5956 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000617/2023-2024 | 278/AD | 15/01/2024 | 0 | Resource Division | 15.14 | 0 | 0
5957 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000929/2023-2024 | 1271/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
5958 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
5959 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
5960 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (for Zone-II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000034/2025-2026 | 2020/AD | 28/04/2025 | 30 | SAHANA ENTERPRISE | 14.69 | 0 | 0
5961 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000103/2023-2024 | 1542/AD | 17/07/2023 | 15 | DIPTI ENTERPRISE | 8.34 | 0 | 0
5962 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000104/2023-2024 | 1543/AD | 17/07/2023 | 15 | DIPTI ENTERPRISE | 8.77 | 0 | 0
5963 | Alipore Division | Canning Sub-division | Laying Distribution System for Augmentation of Tilkumar W/S Scheme (Zone-I, Zone-II and Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000483/2023-2024 | 1996/AD | 04/08/2023 | 608 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 556.14 | 0 | 70
5964 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 3 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000772/2024-2025 | 4474/AD | 11/11/2024 | 30 | B.S.ENTERPRISE | 16.16 | 0 | 0
5965 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000773/2024-2025 | 4475/AD | 11/11/2024 | 45 | SUDIP PRADHAN | 42.27 | 0 | 0
5966 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-III] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001306/2024-2025 | 5380/AD | 23/12/2024 | 30 | AAHAN CONSTRUCTION | 11.98 | 0 | 0
5967 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation and Retrofitting of Tilkumar PWSS, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001907/2023-2024 | 221/AD | 11/01/2024 | 45 | M/S ASHA ENGINEERING | 6.65 | 0 | 98
5968 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tilkumar (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002448/2023-2024 | 1514/AD | 15/03/2024 | 45 | M/S APEX ENGINEERING | 22.4 | 0 | 100
5969 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
5970 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3,4,5 & 6 Zone-I for Augmentation of Tilkumar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001513/2022-2023 | 889/SMD | 24/03/2023 | 770 | S.P. CONSTRUCTION | 65.3 | 0 | 80
5971 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Negotiation of gap of Secondary Grid pipeline under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.-South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. (SM/18220) | AE BSD |  | ORD/000092/2025-2026 | 1767/SWD-I | 02/07/2025 | 180 | CHANDAN ROY | 88.79 | 0 | 80
5972 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design with balance work for Augmentation of Laying Distribution System to extend benefit off 100% household in at MADHYA GURUIA (Zone-VI) Mouza in Kultali Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016361] | AE BSD |  | ORD/000459/2023-2024 | 2136/SWD-I | 31/08/2023 | 300 | M/S SARADA CONSTRUCTION | 669.13 | 0 | 30
5973 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Matla-Tribtary between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) | AE BSD |  | ORD/000737/2023-2024 | 495/SWD-I | 25/01/2024 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 84.5 | 0 | 100
5974 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of 475 mm dia (OD) M.S. pipe line for connecting gaps of Secondary grid at both sides of Pet Kulchart Bridge between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) | AE BSD |  | ORD/000761/2024-2025 | 4682/SWD-I | 18/11/2024 | 45 | SRIJON ENTERPRISE | 13.46 | 0 | 99
5975 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000038/2022-2023 | 2955/SWD-I | 16/02/2023 | 0 | Resource Division | 1655.16 | 0 | 0
5976 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/000229/2023-2024 | 1386/AD | 12/07/2023 | 508 | R CONSTRUCTION | 35.33 | 0 | 86
5977 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Char Baidyarabad, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000486/2023-2024 | 1999/AD | 04/08/2023 | 900 | SAMSUL ENTERPRISE | 651.91 | 0 | 71
5978 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/000489/2023-2024 | 1789/AD | 26/07/2023 | 30 | NATURAL RESOURCES CONSORTIUM | 7.17 | 0 | 98
5979 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Char Baidyarabad W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000855/2022-2023 | 6994/AD | 19/11/2022 | 30 | PAPPU ENTERPRISE | 19.48 | 0 | 95
5980 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 06 (six) months from the issuance of work order. | Assistant Engineer, Canning sub division |  | ORD/002429/2023-2024 | 1553/CSD | 19/02/2024 | 182 | SWAPAN KUMAR MANDAL | 2.4 | 0 | 70
5981 | Alipore Division | Canning Sub-division | Laying of additional pipe line to connect the uncovered habitation at Augmentation of Char Baidyarabad, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [SM/18391] | Assistant Engineer, Canning sub division |  | ORD/002489/2024-2025 | 771/AD | 25/02/2025 | 60 | M/S. UMA CONSTRUCTION | 128.86 | 0 | 0
5982 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000033/2023-2024 | 238/AD | 24/04/2023 | 0 | Resource Division | 73.69 | 0 | 0
5983 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer, Canning sub division |  | BILL/01990/2023-2024 | BP-2023-24-240 | 11/09/2023 | 0 | WBSEDCL | 2.51 | 0 | 0
5984 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Char Baidyarabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer, Canning sub division |  | ORD/001548/2023-2024 | 4765/SMD | 06/12/2023 | 91 | D.K.ELECTRIC | 11.43 | 0 | 100
5985 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 3 of Char Baidyarabad W/S Scheme under SMD, P.H.E. Dte. (Block-Basanti )(SM/18391) | Assistant Engineer, Canning sub division |  | ORD/002854/2023-2024 | 346/SMSD | 19/03/2024 | 15 | D.K.ELECTRIC | 0.98 | 0 | 0
5986 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part- B) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000207/2024-2025 | 2590/AD | 19/06/2024 | 248 | ANANTA KUMAR GIRI | 25.16 | 0 | 30
5987 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000208/2024-2025 | 2591/AD | 19/06/2024 | 557 | SARADA CONSTRUCTION | 52.8 | 0 | 30
5988 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000209/2024-2025 | 2592/AD | 19/06/2024 | 45 | MAA BHABANI CONSTRUCTION (DUM DUM) | 42.65 | 0 | 0
5989 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000213/2024-2025 | 2596/AD | 19/06/2024 | 45 | M/S. SUNITY ENTERPRISE | 28.44 | 0 | 0
5990 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000214/2024-2025 | 2597/AD | 19/06/2024 | 30 | JOY ENGINEERING & CONSTRUCTION | 9.66 | 0 | 0
5991 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Suryanagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000470/2022-2023 | 5089/AD | 20/09/2022 | 45 | NIRMAN CONSTRUCTION | 36.67 | 0 | 100
5992 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( SURYANAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000496/2022-2023 | 4189/AD | 22/08/2022 | 45 | LEMNISCATE | 9.6 | 0 | 100
5993 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000496/2024-2025 | 3580/AD | 05/09/2024 | 239 | M/S RAJKUMAR KHAN | 82.06 | 0 | 40
5994 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000570/2022-2023 | 5710/AD | 13/10/2022 | 60 | R.S.CONSTRUCTION CO. | 63.91 | 0 | 0
5995 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000571/2022-2023 | .5711/AD | 13/10/2022 | 30 | TOJO ENTERPRISE | 10.65 | 0 | 95
5996 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000572/2022-2023 | 5712/AD | 13/10/2022 | 21 | THE TOWER CONSTRUCTION | 7.9 | 0 | 100
5997 | Alipore Division | Kakdwip Sub-Division | aying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000576/2022-2023 | 5714/AD | 13/10/2022 | 30 | M/S. L.P. CONSTRUCTION | 16.87 | 0 | 80
5998 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000577/2022-2023 | 5715/AD | 13/10/2022 | 60 | SARADA CONSTRUCTION | 89.01 | 0 | 60
5999 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000578/2022-2023 | 5716/AD | 13/10/2022 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 16.66 | 0 | 100
6000 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Suryanagar Zone - I & II W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000590/2023-2024 | 2347/AD | 18/08/2023 | 45 | KAMIRUL SK AND CO. | 60.02 | 0 | 100
6001 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000669/2024-2025 | 983/KSD | 27/05/2024 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
6002 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000670/2024-2025 | 1256/KSD | 28/08/2024 | 91 | ANAMIKA BERA | 1.2 | 0 | 0
6003 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Suryanagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000908/2023-2024 | 267(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6004 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000913/2022-2023 | 7412/AD | 25/11/2022 | 90 | M/S RAJKUMAR KHAN | 119.67 | 0 | 80
6005 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001319/2022-2023 | 9884/AD | 10/01/2023 | 1233 | KAMIRUL SK AND CO. | 319.24 | 0 | 40
6006 | Alipore Division | Kakdwip Sub-Division | Support services for preparation of documentation in relating to submission to other Department i.e. PWD (NH) for approval of laying rising main and distribution main along / across NH 117 from Nischintapur to Bakkhali for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001997/2023-2024 | 470/KSD | 22/09/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 3.14 | 0 | 100
6007 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
6008 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002847/2024-2025 | 1656/KSD | 26/11/2024 | 90 | ANAMIKA BERA | 1.2 | 0 | 0
6009 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/003035/2024-2025 | 352/KSD | 27/02/2025 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
6010 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000272/2023-2024 | 3071/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6011 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000460/2023-2024 | 4723/AD | 18/12/2023 | 0 | Resource Division | 30.66 | 0 | 0
6012 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000591/2023-2024 | 90/AD | 03/01/2024 | 0 | Resource Division | 5.94 | 0 | 0
6013 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000810/2023-2024 | 655/AD | 30/01/2024 | 0 | Resource Division | 17.57 | 0 | 0
6014 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000997/2023-2024 | 1790/AD | 27/03/2024 | 0 | Resource Division | 25.73 | 0 | 0
6015 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bills for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/01562/2022-2023 | BP-2022-23-450 | 20/03/2023 | 0 | WBSEDCL | 1.42 | 0 | 0
6016 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I&II for Augmentation of Suryanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000374/2022-2023 | 3778/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE | 21.52 | 0 | 75
6017 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at Zone-I & II PH-1&2 of Suryanagar Aug. W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Block-Kakdwip) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001655/2023-2024 | .1031/AE-I/SMD | 20/09/2023 | 15 | MAA SUSOMA & COMPANY | 0.78 | 0 | 100
6018 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-1 of Suryanagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002271/2023-2024 | 841-AE-I-SMD | 31/07/2023 | 15 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0
6019 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-2 of Suryanagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002392/2023-2024 | 842-AE-I-SMD | 31/07/2023 | 15 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0
6020 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01986/2023-2024 | BP-2023-24-241 | 11/09/2023 | 0 | WBSEDCL | 4.52 | 0 | 0
6021 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chakbaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 451/SMD | 17/02/2023 | 835 | GHOSE ENGINEERING SYNDICATE | 22.81 | 0 | 80
6022 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Chakberia W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002380/2023-2024 | 279/SMSD | 29/02/2024 | 398 | GHOSE ENGINEERING SYNDICATE | 0.9 | 0 | 100
6023 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE CHAKBERIA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016026) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000346/2022-2023 | 2164/SWD-I | 09/12/2022 | 754 | ARASTA ENGINEERING & CO | 29.84 | 0 | 100
6024 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1724] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000495/2022-2023 | 2863/SWD-I | 09/02/2023 | 900 | MAHI ENTERPRISE | 372.71 | 0 | 25
6025 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Hume Pipe Culvert 4.80 Mtr.span with 32 Mtr. Long temporary approach road (Plot No-35) for proposed Chakberia OHR Site at Navasan Mouza (JL No-109, Dag No-35, Khatian No-01) at CHAKBERIA PWSS within Sonarpur Block " CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000568/2024-2025 | 4241/SWD-I | 30/09/2024 | 124 | MAHI ENTERPRISE | 13.38 | 0 | 60
6026 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHAKBERIA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13771] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000726/2022-2023 | 3575/SWD-I | 22/03/2023 | 661 | ARASTA ENGINEERING & CO | 3.13 | 0 | 100
6027 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of land at proposed Headwork site of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000726/2024-2025 | 4603/SWD-I | 12/11/2024 | 60 | MAHI ENTERPRISE | 37.97 | 0 | 0
6028 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional laying of pipeline and restoration of road near PROPOSED OHR site of "CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000748/2024-2025 | 4670/SWD-I | 18/11/2024 | 45 | MAHI ENTERPRISE | 21.74 | 0 | 0
6029 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000822/2023-2024 | 1296/SWD-I | 15/03/2024 | 45 | MAHI ENTERPRISE | 44.33 | 0 | 0
6030 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000012/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 23.87 | 0 | 0
6031 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000230/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.62 | 0 | 0
6032 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Nalmuri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/001517/2022-2023 | 905/SMD | 28/03/2023 | 90 | M/S. GHOSH ENTERPRISE | 25.41 | 0 | 0
6033 | South 24 Pgs W/S Division I |  | Land Developement Protection work for pipeline, construction of Boundary Wall with Internal Pavement and others allied works at HW & 2nd Tube-well site of NALMURI PWSS to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18548) |  |  | ORD/000107/2025-2026 | 1869/SWD-I | 14/07/2025 | 75 | SUJIT KUMAR SHARMA | 161.85 | 0 | 0
6034 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NALMURI PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018471] |  |  | ORD/000304/2023-2024 | 1672/SWD-I | 04/08/2023 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 0 | 50
6035 | South 24 Pgs W/S Division I |  | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NALMURI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2582) (TSM/018471) |  |  | ORD/000439/2023-2024 | 2089/SWD-I | 29/08/2023 | 752 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 708.85 | 0 | 30
6036 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 0 | 60
6037 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 28.02 | 0 | 0
6038 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 250/SWD-I | 10/01/2024 | 0 | Resource Division | 15.91 | 0 | 0
6039 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Khan Saheber Abad W/S Scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18874) (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000073/2025-2026 | 2262/AD | 14/05/2025 | 45 | M/S. GIRI ENTERPRISE | 28.4 | 0 | 0
6040 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC, for Augmentation of Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000463/2024-2025 | 3422/AD | 21/08/2024 | 298 | M/S. DAS BUILDERS | 39.16 | 0 | 62
6041 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd Tubewell site for Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000591/2024-2025 | 4056/AD | 01/10/2024 | 45 | M/S. GIRI ENTERPRISE | 7.08 | 0 | 0
6042 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000935/2023-2024 | 3264/AD | 06/10/2023 | 30 | SUDIP PRADHAN | 17.3 | 0 | 80
6043 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000937/2023-2024 | 3265/AD | 06/10/2023 | 30 | SUDIP PRADHAN | 16.16 | 0 | 80
6044 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000 ] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001085/2023-2024 | 3499/AD | 16/10/2023 | 90 | S.P. CONSTRUCTION (V) | 110.29 | 0 | 78
6045 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001086/2023-2024 | 3500/AD | 16/10/2023 | 300 | NIRMAL UDYOG | 174.3 | 0 | 50
6046 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001137/2023-2024 | 3606/AD | 30/10/2023 | 30 | G.M. ENTERPRISE | 15.07 | 0 | 80
6047 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KHAN SAHEBER ABAD PWSS (PHASE-B) ) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001361/2023-2024 | 3258/AD | 05/10/2023 | 45 | VOYAGER | 3.74 | 0 | 100
6048 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 1st Tubewell site for Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002120/2024-2025 | 1969/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.27 | 0 | 100
6049 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 2nd Tubewell site for Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002121/2024-2025 | 1970/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.26 | 0 | 100
6050 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
6051 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th Tubewell site for Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002537/2024-2025 | 815/AD | 27/02/2025 | 45 | M/S. M.S. ENTERPRISE | 7.1 | 0 | 0
6052 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Khansaheber Abad PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002614/2023-2024 | 379/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6053 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Khan Saheber Abad PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002621/2023-2024 | 732/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
6054 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000967/2023-2024 | 1761/AD | 27/03/2024 | 0 | Resource Division | 28.28 | 0 | 0
6055 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Laying distribution system for providing FHTC, construction of Valve Chamber etc. for Augmentation of Purusottampur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/18875) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000354/2024-2025 | 2799/AD | 02/07/2024 | 45 | A.G.ENTERPRISE | 0 | 0 | 0
6056 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURUSOTTAMPUR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001358/2023-2024 | 3255/AD | 05/10/2023 | 45 | VOYAGER | 5.51 | 0 | 100
6057 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Purusottampur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001428/2023-2024 | 4611/AD | 14/12/2023 | 300 | SPA ENTERPRISE | 641.07 | 0 | 50
6058 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Chemaguri, Purusottampur, Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002177/2023-2024 | 955/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.61 | 0 | 100
6059 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000970/2023-2024 | 1763/AD | 27/03/2024 | 0 | Resource Division | 108.57 | 0 | 0
6060 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Naraharipur W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000159/2024-2025 | 2510/AD | 15/06/2024 | 190 | SIMPLEX DRILLING CO. | 51.43 | 0 | 100
6061 | Alipore Division | Kakdwip Sub-Division | Construction, Placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. at Naraharipur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000182/2024-2025 | 2541/AD | 18/06/2024 | 75 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 78.34 | 0 | 0
6062 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd Tubewell site for Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000386/2024-2025 | 3082/AD | 25/07/2024 | 45 | ARUSHI CONSTRUCTION | 7.18 | 0 | 0
6063 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000387/2024-2025 | 3083/AD | 25/07/2024 | 45 | SWAPAN KUMAR PRADHAN | 34.22 | 0 | 0
6064 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 4th Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000388/2024-2025 | 3084/AD | 25/07/2024 | 30 | M/S. DAS BUILDERS | 11.75 | 0 | 0
6065 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 0 | 40
6066 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAHARIPUR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001359/2023-2024 | 3256/AD | 05/10/2023 | 45 | VOYAGER | 6.35 | 0 | 100
6067 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
6068 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Naraharipur PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002610/2023-2024 | 377/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6069 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000969/2023-2024 | 1762/AD | 27/03/2024 | 0 | Resource Division | 43.44 | 0 | 0
6070 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges of damage road due to phed pipe laying between Ch.7.40 km of Thakurpukur Bibirhat Bakhrahat Raipur Road under South 24 pgs. Division, PWD during 2023-24, 50% of estimate cost i.e.1,04,88,089/- in advance as per minutes of the meeting with HMIC, PHED on 12.09.2022 | AE SWSD-II | JE1 | BILL/02110/2023-2024 | BP-2023-24-799 | 22/03/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 52.44 | 0 | 0
6071 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of UTTAR KAZIRHAT PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018475] (2nd call) | AE SWSD-II | JE1 | ORD/000242/2023-2024 | 1439/SWD-I | 18/07/2023 | 60 | UNI DEVELOPERS AND CONTRACTORS | 18.17 | 0 | 100
6072 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II | JE1 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
6073 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed UTTAR KAZIRHAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I & Thakurpukur-Mahestala Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 5617) [TSM/018475]. | AE SWSD-II | JE1 | ORD/000528/2023-2024 | 2345/SWD-I | 22/09/2023 | 526 | SUPRITI ENTERPRISE | 638.94 | 0 | 60
6074 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Rising Main from Zone 9 to Zone 10 for Ground water based UTTAR KAZIRHAT piped water supply scheme to accommodate FHTC in Bishnupur-I block under South 24-Pgns. W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18375) | AE SWSD-II | JE1 | ORD/000751/2023-2024 | 553/SWD-I | 31/01/2024 | 487 | SUKUMAR DEBNATH | 40.63 | 0 | 50
6075 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Kazirhat Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000963/2022-2023 | 1167/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.97 | 0 | 100
6076 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000118/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 43.62 | 0 | 0
6077 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000312/2023-2024 | 3116/SWD-I | 07/12/2023 | 0 | Resource Division | 94.04 | 0 | 0
6078 | Alipore Division | Raidighi Sub-Division | Soil-Investigation work for the proposed 1500 Cum. Capacity Over Head Reservoir for Zone I, Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000133/2025-2026 | 179/RSD | 05/06/2025 | 15 | BOSE ENGINEERS | 0.96 | 0 | 100
6079 | Alipore Division | Raidighi Sub-Division | Supply of Specials, laying DI pipeline including restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000281/2024-2025 | 2629/AD | 20/06/2024 | 90 | M/S B. ENTERPRISE | 127.22 | 0 | 95
6080 | Alipore Division | Raidighi Sub-Division | Restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10218 & SM/18378) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000444/2024-2025 | 3325/AD | 12/08/2024 | 270 | M/S B. ENTERPRISE | 119.73 | 0 | 95
6081 | Alipore Division | Raidighi Sub-Division | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 600 | M/S. S.S. ENTERPRISE | 1185.63 | 0 | 10
6082 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Tentulberia W/S Scheme (Zone-I, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001258/2023-2024 | 4183/AD | 28/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.84 | 0 | 95
6083 | Alipore Division | Raidighi Sub-Division | Supplying, fabrication & insertion of 600 mm dia. (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track in between Node Point No. 442 to 443 of LDS under Zone ¿ I, Mathurapur ¿ I Block. The said location is in between Mathurapur and Madhabpur railway Station (Between mast no. 56/4, 56/6 and 56/5, 56/7 of Baruipur ¿ Lakshikantapur Section of Eastern Railway and comes with Gunjipur mouza as per permission of Railway Authority, for laying of 355.6 (OD) mm dia., 8 mm thick MS Water Supply Pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mathurapur ¿ I Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002290/2023-2024 | 1026/AD | 19/02/2024 | 300 | TELETONE INDIA PVT. LTD. | 60.47 | 0 | 0
6084 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2024 to 30/06/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002722/2024-2025 | 141/RSD | 29/04/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
6085 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2024 to 31/08/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002723/2024-2025 | 613/RSD | 29/06/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
6086 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2024 to 31/10/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002724/2024-2025 | 689C/RSD | 29/08/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
6087 | Alipore Division | Raidighi Sub-Division | Restoration of concrete village road for LDS work at Zone-I (Node point Y-Z) of Mathurapur-I Block under 'Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/003184/2020-2021 | 357/RSD | 13/10/2020 | 30 | M/S. GANGA ENTERPRISE | 4.8 | 0 | 100
6088 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000598/2023-2024 | 233/AD | 11/01/2024 | 0 | Resource Division | 13 | 0 | 0
6089 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000844/2023-2024 | 707/AD | 31/01/2024 | 0 | Resource Division | 137.95 | 0 | 0
6090 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IV at Daskhin Garankathi mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5540] | AE BSD |  | ORD/000429/2023-2024 | 2003/SWD-I | 28/08/2023 | 90 | PATH MAKERS | 444.58 | 0 | 75
6091 | Alipore Division | Kakdwip Sub-Division | Release of fund to PWD towards road restoration work. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/00939/2024-2025 | BP-2024-25-438 | 09/08/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 31.01 | 0 | 0
6092 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Hardwood Point PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14157) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000334/2024-2025 | 2739/AD | 26/06/2024 | 60 | M/S SAMADDAR CONSTRUCTION | 138.26 | 0 | 0
6093 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000399/2024-2025 | 3182/AD | 31/07/2024 | 30 | M/S D.D. INFRASTRUCTURE | 9.03 | 0 | 0
6094 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harwood Point W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000957/2023-2024 | 2989/AD | 26/09/2023 | 45 | M/S SAMADDAR CONSTRUCTION | 27.68 | 0 | 100
6095 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000958/2023-2024 | 2990/AD | 26/09/2023 | 30 | FORTUNE ENGINEERING | 9.53 | 0 | 0
6096 | Alipore Division | Kakdwip Sub-Division | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001152/2024-2025 | 2863/AD | 06/07/2024 | 25 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
6097 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Hardwood Point PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001783/2022-2023 | 3692/AD | 02/08/2022 | 45 | LEMNISCATE | 8.62 | 0 | 95
6098 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2040] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001864/2022-2023 | 12417/AD | 09/03/2023 | 1135 | M/S SAMADDAR CONSTRUCTION | 167.97 | 0 | 50
6099 | Alipore Division | Kakdwip Sub-Division | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002029/2022-2023 | 12996/AD | 23/03/2023 | 1200 | M/S SAMADDAR CONSTRUCTION | 366.95 | 0 | 50
6100 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 450 cum. capacity OHR of Hardwood Point PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002066/2023-2024 | 761(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6101 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
6102 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14157) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003052/2024-2025 | 4087/AD | 03/10/2024 | 150 | GARAI INFRA PROJECT | 19.96 | 0 | 100
6103 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000124/2023-2024 | 661/AD | 17/05/2023 | 0 | Resource Division | 19.45 | 0 | 0
6104 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000455/2023-2024 | 4719/AD | 18/12/2023 | 0 | Resource Division | 89.99 | 0 | 0
6105 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000816/2023-2024 | 661/AD | 30/01/2024 | 0 | Resource Division | 3.49 | 0 | 0
6106 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000994/2023-2024 | 1787/AD | 27/03/2024 | 0 | Resource Division | 6.44 | 0 | 0
6107 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Harwood Point water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000806/2022-2023 | 269/SMD | 31/01/2023 | 90 | M/S. DILIP MITRA | 33.71 | 0 | 0
6108 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02492/2023-2024 | BP-2023-24-262 | 18/09/2023 | 0 | WBSEDCL | 5.63 | 0 | 0
6109 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uspara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 318/SMD | 06/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 23.51 | 0 | 45
6110 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Ushapara PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/13307) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/003108/2023-2024 | 239/SMSD | 16/02/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.9 | 0 | 0
6111 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/13307) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000370/2024-2025 | 3529/SWD-I | 07/08/2024 | 90 | I.S ENTERPRISE | 100.98 | 0 | 45
6112 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for USPARA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015202] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 3135/SWD-I | 27/02/2023 | 30 | SABYASACHI CHAKI | 31.75 | 0 | 50
6113 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of distribution Network System for different dia HDPE pipe under Ushpara PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114]. [SM Code - SM/13307] [2nd Call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000706/2023-2024 | 3403/SWD-I | 28/12/2023 | 60 | I.S ENTERPRISE | 53.48 | 0 | 100
6114 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000713/2022-2023 | 3538/SWD-I | 20/03/2023 | 745 | I.S ENTERPRISE | 429.22 | 0 | 30
6115 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Land development at HW & 2nd tube well site and restoration of road damaged due to laying of pipe line for USHPARA PWSS in Bhangar-I Block under South 24-Parganas, W/S Division-I, P.H.E. Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District under Jal Jeevan Mission (SM/13307) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000871/2024-2025 | 4929/SWD-I | 03/12/2024 | 61 | I.S ENTERPRISE | 60.86 | 0 | 50
6116 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for USHPARA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13307] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001152/2024-2025 | 370/SWD-I | 04/02/2025 | 30 | HI-LIGHT ELECTRONICS | 15.9 | 0 | 0
6117 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
6118 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000224/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.02 | 0 | 0
6119 | Alipore Division | Canning Sub-division | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000488/2024-2025 | 3547/AD | 02/09/2024 | 45 | SUPRITI ENTERPRISE | 34.28 | 0 | 0
6120 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kalaria (Zone- IB) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000492/2023-2024 | 1792/AD | 26/07/2023 | 540 | S.B. ENTERPRISE | 8.75 | 0 | 100
6121 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division |  | ORD/000520/2023-2024 | 2075/AD | 07/08/2023 | 45 | S.M. ENTERPRISE | 7.33 | 0 | 100
6122 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division |  | ORD/000521/2023-2024 | 2076/AD | 07/08/2023 | 45 | ASHIS ENTERPRISE | 7.06 | 0 | 100
6123 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-III) | Assistant Engineer, Canning sub division |  | ORD/000523/2023-2024 | 2077/AD | 07/08/2023 | 45 | ASHIS ENTERPRISE | 7.05 | 0 | 100
6124 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1422] (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000525/2023-2024 | 2141/AD | 09/08/2023 | 630 | SUPRITI ENTERPRISE | 270.46 | 0 | 85
6125 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 630 | PUTUL RANI MAITY | 217.06 | 0 | 97
6126 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2133] (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000528/2023-2024 | 2143/AD | 09/08/2023 | 540 | PUTUL RANI MAITY | 127.34 | 0 | 70
6127 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kalaria (Zone-IB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000558/2023-2024 | 2245/AD | 11/08/2023 | 60 | B.K. ENTERPRISE. | 60 | 0 | 98
6128 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IA & IB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000616/2023-2024 | 2271/AD | 14/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.51 | 0 | 98
6129 | Alipore Division | Canning Sub-division | Construction of street stand post and valve chamber, damaged due to widening of road from Piali Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001029/2022-2023 | 866/CSD | 26/08/2022 | 675 | ASHIS ENTERPRISE | 2.53 | 0 | 100
6130 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
6131 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2024 to 15.03.2024 | Assistant Engineer, Canning sub division |  | ORD/003235/2023-2024 | 1568/CSD | 21/02/2024 | 15 | SAILEN CHANDRA DAS | 0.07 | 0 | 0
6132 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. (Perid from 16.03.2025 to 14.03.2026) | Assistant Engineer, Canning sub division |  | ORD/003373/2024-2025 | 309/CSD | 13/03/2025 | 365 | SAILEN CHANDRA DAS | 4.8 | 0 | 0
6133 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000065/2023-2024 | 268/AD | 24/04/2023 | 0 | Resource Division | 42.51 | 0 | 0
6134 | S24 Pgns Mechanical | Canning Sub-division | Quotation for 25 KVA DTR Shifting at Kalaria Zone-IA, PH-2 Water supply scheme under canning-I block. Reference ID-860304112. Application ID-100000111622. | Assistant Engineer, Canning sub division |  | BILL/00648/2024-2025 | BP-2024-25-154 | 10/07/2024 | 0 | WBSEDCL | 1.81 | 0 | 0
6135 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer, Canning sub division |  | BILL/03869/2023-2024 | BP-2023-24-396 | 02/12/2023 | 0 | WBSEDCL | 4.09 | 0 | 0
6136 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IA & IB for Augmentation of Kalaria Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer, Canning sub division |  | ORD/000268/2023-2024 | 1128/SMD | 24/04/2023 | 90 | PADMA ENGINEERING CO. | 26.98 | 0 | 100
6137 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at Zone-I B PH-I of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- [ Block- Canning-I ] | Assistant Engineer, Canning sub division |  | ORD/002426/2023-2024 | 371/SMSD | 21/03/2024 | 15 | KUSHANI ENTERPRISES | 0.39 | 0 | 100
6138 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at Zone-I A PH-I & 2 of Kalaria water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Canning-I ] | Assistant Engineer, Canning sub division |  | ORD/002428/2023-2024 | 372/SMSD | 21/03/2024 | 15 | S.B.ENTERPRISE | 0.78 | 0 | 100
6139 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-1 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002646/2023-2024 | 195/SMSD | 12/02/2024 | 15 | PADMA ENGINEERING CO. | 0.89 | 0 | 100
6140 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Kalaria Zone-1A PH-2 under Canning-I Block water supply scheme under SMD,PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002647/2023-2024 | 190/SMSD | 09/02/2024 | 15 | PADMA ENGINEERING CO. | 0.89 | 0 | 100
6141 | Alipore Division |  | Road restoration of 070- Atghora on L068 To Tagarberia(WB/02/320) |  |  | BILL/01779/2024-2025 | BP-2024-25-804 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.75 | 0 | 0
6142 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04651/2023-2024 | BP-2023-24-488 | 12/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
6143 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Akna Mirzapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/18573) |  |  | ORD/000217/2024-2025 | 936/SMSD | 28/06/2024 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0
6144 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Akna Mirzapur water supply scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/18573) |  |  | ORD/000218/2024-2025 | 937/SMSD | 28/06/2024 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 0
6145 | S24 Pgns Mechanical |  | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Akna Mirzapur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/18573) |  |  | ORD/000220/2024-2025 | 941/SMSD | 28/06/2024 | 15 | NUPUR CHANDRA HALDER | 0.58 | 0 | 0
6146 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Akna Mirzapur ( Zone-29) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000751/2023-2024 | 2693/SMD | 17/08/2023 | 90 | NUPUR CHANDRA HALDER | 44.46 | 0 | 0
6147 | South 24 Pgs W/S Division I |  | Construction of Platform for providing FHTC for Ground Water Based AKNA MIRZAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/18573) |  |  | ORD/000305/2024-2025 | 3218/SWD-I | 18/07/2024 | 60 | MONDAL AND CO | 79.25 | 0 | 46
6148 | South 24 Pgs W/S Division I |  | Restoration of road after laying of pipeline, protection work for pipeline, development of land and other allied works for Ground water based AKNA MIRZAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18573) |  |  | ORD/000332/2024-2025 | 3270/SWD-I | 22/07/2024 | 45 | MONDAL AND CO | 50.41 | 0 | 0
6149 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of AKNA MIRZAPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4257] [TSM/018363] |  |  | ORD/000407/2023-2024 | 1924/SWD-I | 22/08/2023 | 583 | MONDAL AND CO | 592.29 | 0 | 70
6150 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based AKNA MIRJAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000919/2022-2023 | 1170/SWD-I | 30/08/2022 | 30 | ASTER CONSULTANCY | 3.34 | 0 | 100
6151 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.31 | 0 | 0
6152 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of quotation for new service connection at PH-2 Under Augmentation of Rasapunja PWSS (Shibarampur Road-Sarkarpool) Bill No- 14/24830/24/4/1 Bill Date- 14-11-2024 MR No- 14/24830/24 Unique ID- 14248302441 Bill ID- M141124 | AE SWSD-II | JE1 | BILL/02240/2024-2025 | BP-2024-25-494 | 17/12/2024 | 0 | CESC LTD | 2.46 | 0 | 0
6153 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II | JE1 | BILL/04932/2023-2024 | BP-2023-24-540 | 27/02/2024 | 0 | CESC LTD | 2.75 | 0 | 0
6154 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Rasapunja water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-II | JE1 | ORD/000593/2023-2024 | 2624/SMD | 08/08/2023 | 90 | JAGANNATH ENTERPRISE | 25.93 | 0 | 0
6155 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road for laying of water pipeline by PHE Dte, in Ch- 5.00 Km to Ch - 12.00 km of Thakurpukur Bakrahat Raipur Road Under South 24 Parganas Division P.W.D in the Dist of South 24 Pgs During the year 2024-25 | AE SWSD-II | JE1 | BILL/00263/2024-2025 | BP-2024-25-192 | 16/07/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 133.51 | 0 | 0
6156 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges of damage road due to phed pipe laying between Ch.7.40 km of Thakurpukur Bibirhat Bakhrahat Raipur Road under South 24 pgs. Division, PWD during 2023-24, 50% of estimate cost i.e.1,04,88,089/- in advance as per minutes of the meeting with HMIC, PHED on 12.09.2022 | AE SWSD-II | JE1 | BILL/02110/2023-2024 | BP-2023-24-799 | 22/03/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 52.44 | 0 | 0
6157 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of balance pipeline and road restoration for Raspunja PWSS to accommodate FHTC in Thakurpukur - Maheshtala Block under South 24 Parganas W/S Division-I , PHE Dte. for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/ 18576) | AE SWSD-II | JE1 | ORD/000279/2024-2025 | 3003/SWD-I | 28/06/2024 | 90 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 109 | 0 | 60
6158 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for the stand alone site at SHIBRAMPUR under RASAPUNJA PWSS of Thakurpukur-Maheshtala Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/18576] | AE SWSD-II | JE1 | ORD/000282/2024-2025 | 3038/SWD-I | 02/07/2024 | 30 | K.P CONSTRUCTION | 15.89 | 0 | 100
6159 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and construction of PUMP HOUSE (4.80 Mtr. X 3.66 Mtr.) for Stand alone scheme at Shibrampur under ground water based RASAPUNJA PIPE WATER SUPPLY SCHEME to accomodate FHTC in Thakurpukur-Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (TSM/018477) | AE SWSD-II | JE1 | ORD/000353/2023-2024 | 1739/SWD-I | 10/08/2023 | 640 | JOY GURU TRADING | 38.27 | 0 | 40
6160 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and construction of PUMP HOUSE (4.80 Mtr. X 3.66 Mtr.) for Stand alone scheme at Joka under ground water based RASAPUNJA PIPE WATER SUPPLY SCHEME to accomodate FHTC in Thakurpukur-Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (TSM/018477) | AE SWSD-II | JE1 | ORD/000382/2023-2024 | 1818/SWD-I | 16/08/2023 | 623 | BAIDYA ENTERPRISE | 30.15 | 0 | 30
6161 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for RASAPUNJA PIPE WATER SUPPLY SCHEME in BISHNUPUR-I & Thakurpukur-Mahestala Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 5908) [TSM/018477]. | AE SWSD-II | JE1 | ORD/000417/2023-2024 | 1963/SWD-I | 24/08/2023 | 706 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 744.93 | 0 | 45
6162 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Temporary road repairing at Thakurpukur Bakhrahat Road under Rasapunja W/S Scheme under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/18576] | AE SWSD-II | JE1 | ORD/000713/2024-2025 | 4543/SWD-I | 06/11/2024 | 30 | SRIJON ENTERPRISE | 11.64 | 0 | 100
6163 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for the stand alone site at JOKA under RASAPUNJA PWSS of Thakurpukur-Maheshtala Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018477] | AE SWSD-II | JE1 | ORD/000725/2023-2024 | 391/SWD-I | 17/01/2024 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.89 | 0 | 100
6164 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Boundary wall for proposed pump house site under for Joka and Shibrampur including allied works for Rasapunja Piped Water Supply Schme under Thakurpukur Maheshtala Block, South 24 Pgs W/S Divn-I, P.H.E. Dte. (TSM/018477) | AE SWSD-II | JE1 | ORD/000793/2023-2024 | 1141/SWD-I | 07/03/2024 | 30 | MODERN CONSTRUCTION (DONGARIA) | 17.38 | 0 | 0
6165 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development for construction of Pump house and other civil structures for Ground water based RASAPUNJA Piped Water Supply Scheme to accommodate FHTS in Thakurpukur Maheshtala block under South 24 Parganas W/S Divn-I, P.H.E Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18576) [2nd call] | AE SWSD-II | JE1 | ORD/000796/2023-2024 | 1144/SWD-I | 07/03/2024 | 30 | MODERN CONSTRUCTION (DONGARIA) | 7.3 | 0 | 100
6166 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (7.00 Cum capacity) at Joka including other allied works for Rasapunja Piped Water Supply Scheme to accommodate FHTC in Thakurpukur Mahestala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/18576) | AE SWSD-II | JE1 | ORD/000812/2023-2024 | 1148/SWD-I | 07/03/2024 | 430 | AMRT INDUSTRIES PRIVATE LIMITED | 10.22 | 0 | 100
6167 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (10.00 Cum capacity) at Sibrampur including other allied works for Rasapunja Piped Water Supply Scheme in Thakurpukur Mahestala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/18576) | AE SWSD-II | JE1 | ORD/000864/2024-2025 | 4922/SWD-I | 03/12/2024 | 30 | RAMASISH ENTERPRISE | 10.67 | 0 | 0
6168 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Rashapunja Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000965/2022-2023 | 1168/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 3.11 | 0 | 100
6169 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Design, Supply, installation, trial run, commissioning of necessary pumping assembly including laying of Interconnection of rising main with header line and necessary Civil Works inclusive of 01(One) Year operation and maintenance and DLP for all components during maintenance period in connection to "Pipe Water Supply Scheme for Raspunja PWSS. (SM/18576) [Time of completion for construction and installation 45 days and 12 Months for subsequent O & M] | AE SWSD-II | JE1 | ORD/001097/2024-2025 | 5146/SWD-I | 16/12/2024 | 410 | RELIABLE CONSTRUCTIONS | 91.5 | 0 | 0
6170 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000177/2023-2024 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 36.39 | 0 | 0
6171 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000313/2023-2024 | 3117 | 07/12/2023 | 0 | Resource Division | 48.53 | 0 | 0
6172 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Raynagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] |  |  | ORD/000596/2023-2024 | 2632/SMD | 09/08/2023 | 90 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 0
6173 | South 24 Pgs W/S Division I |  | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00665/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
6174 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for RAYNAGAR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018294] (2nd Call) |  |  | ORD/000369/2023-2024 | 1778/SWD-I | 11/08/2023 | 639 | N.A. ENTERPRISE | 47.65 | 0 | 34
6175 | South 24 Pgs W/S Division I |  | Construction of Platform and for providing FHTC , Construction of approach road and other allied works for Ground water based RAYNAGAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/18577) |  |  | ORD/000396/2024-2025 | 3680/SWD-I | 22/08/2024 | 45 | MILAN GHOSH | 93.83 | 0 | 0
6176 | South 24 Pgs W/S Division I |  | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAYNAGAR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3284] [TSM/018294] |  |  | ORD/000519/2023-2024 | 2263/SWD-I | 14/09/2023 | 779 | M/S GHOSH AND CO. | 734.31 | 0 | 55
6177 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Raynagar Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000956/2022-2023 | 1306/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.95 | 0 | 100
6178 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 45.18 | 0 | 0
6179 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000291/2022-2023 | 3828/AD | 08/08/2022 | 30 | DEVDAS SHAW | 18.26 | 0 | 100
6180 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramtanunagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000324/2022-2023 | 3871/AD | 08/08/2022 | 30 | R.K. CONSTRUCTION | 11.92 | 0 | 45
6181 | Alipore Division | Kakdwip Sub-Division | Construction of Platform, Rising Main and Road Restoration for Augmentation of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11751) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000472/2024-2025 | 3458/AD | 23/08/2024 | 75 | SARADA CONSTRUCTION | 86.58 | 0 | 100
6182 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAMTANUNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000500/2022-2023 | 1978/AD | 20/06/2022 | 45 | LEMNISCATE | 3.3 | 0 | 100
6183 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Construction of Pump House, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramtanunagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC =200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000550/2022-2023 | 5724/AD | 13/10/2022 | 120 | SARADA CONSTRUCTION | 168.05 | 0 | 80
6184 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramtanunagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001163/2023-2024 | 3725/AD | 03/11/2023 | 30 | S.R. CONSTRUCTION | 9.57 | 0 | 80
6185 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11751) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002132/2023-2024 | 820/AD | 05/02/2024 | 30 | S. CHAKRABORTY AND CO. | 19.96 | 0 | 98
6186 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
6187 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000060/2022-2023 | 3949/AD | 12/08/2022 | 0 | Resource Division | 28.82 | 0 | 0
6188 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000277/2023-2024 | 3076/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6189 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000593/2023-2024 | 92/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
6190 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000806/2023-2024 | 651/AD | 30/01/2024 | 0 | Resource Division | 3.42 | 0 | 0
6191 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00021/2023-2024 | BP-2023-24-05 | 25/04/2023 | 0 | WBSEDCL | 1.59 | 0 | 0
6192 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/01563/2022-2023 | BP-2022-23-453 | 20/03/2023 | 0 | WBSEDCL | 0.71 | 0 | 0
6193 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Ramtanunagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000373/2022-2023 | 3777/SMD | 29/12/2022 | 90 | MAA TARA ENTERPRISE | 9.64 | 0 | 80
6194 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Augmentation of Ramtanunagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000717/2024-2025 | 3423/SMD | 28/10/2024 | 90 | SHIVAM ENTERPRISE | 11.22 | 0 | 100
6195 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Ramtanunagar Augmentation W/S Scheme under JJM under South 24-Pgs Mechanical Division, PHE Dte [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002591/2023-2024 | 719-AE-I-SMD | 28/06/2023 | 15 | MAA TARA ENTERPRISE | 0.82 | 0 | 100
6196 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 50.54 | 95
6197 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000834/2023-2024 | 679/AD | 30/01/2024 | 0 | Resource Division | 10.93 | 0 | 0
6198 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Basantapur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000408/2020-2021 | 779/KSD | 14/10/2020 | 45 | M/S. SONAMONI ENTERPRISE | 4.78 | 4.65 | 0
6199 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhablat (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000409/2020-2021 | 780/KSD | 14/10/2020 | 45 | M/S. SUNITY ENTERPRISE | 4.71 | 4.53 | 0
6200 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Lalpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000421/2020-2021 | 798/KSD | 15/10/2020 | 45 | DIPA CHHETRI | 3.11 | 3.02 | 0
6201 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Golakpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000422/2020-2021 | 799/KSD | 15/10/2020 | 45 | JAGANNATH ENTERPRISE | 3.35 | 0 | 98
6202 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Prasadpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000440/2020-2021 | 826/KSD | 16/10/2020 | 45 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 3.41 | 0 | 100
6203 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Laxmibazar area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000441/2020-2021 | 827/KSD | 16/10/2020 | 45 | M/S SNEHALATA ENTERPRISE | 3.64 | 0 | 100
6204 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Bamoner More area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000472/2020-2021 | 1050/KSD | 19/12/2020 | 20 | M/S SAKTI GIRI ENTERPRISE | 3.97 | 0 | 93
6205 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 480 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 51
6206 | Alipore Division | Kakdwip Sub-Division | Laying Rising Main 150 mm dia. D.I. (K9) pipe and inter connection between 1 & 2 for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001930/2020-2021 | 1343/KSD | 23/02/2021 | 10 | UNITED BUILDERS | 3.32 | 0 | 90
6207 | Alipore Division | Kakdwip Sub-Division | Supply of CIDF Sluice Valves and 150 mm dia. CIDF Pipes and Specials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001932/2020-2021 | 1345/KSD | 23/02/2021 | 10 | NITYANANDA MONDAL | 3.68 | 0 | 90
6208 | Alipore Division | Kakdwip Sub-Division | Supply of 250 mm dia. CIDF pipe and sSpecials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001934/2020-2021 | 1347/KSD | 23/02/2021 | 10 | UNITED BUILDERS | 4.71 | 0 | 90
6209 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000708/2023-2024 | 478/AD | 24/01/2024 | 0 | Resource Division | 9.46 | 0 | 0
6210 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Nagartala Water Supply Scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000066/2021-2022 | 708/AD | 10/06/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 223.57 | 0 | 70
6211 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala Water Supply Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000587/2022-2023 | 5863/AD | 18/10/2022 | 30 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 45.64 | 0 | 0
6212 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala (Zone-II) W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [365 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002229/2020-2021 | 2030/CSD | 24/03/2021 | 365 | MODERN CONSTRUCTION | 2.77 | 0 | 100
6213 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala W/S Scheme (Zone-II) under Canning Sub Division of Alipore Division, PHE Dte. [From 01.01.2021 to 23.03.2021] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002421/2020-2021 | 1291/CSD | 30/12/2020 | 82 | MODERN CONSTRUCTION | 1.84 | 0 | 100
6214 | Alipore Division | Canning Sub-division | Construction of day to day annual Operation, repair & Maintenance of CI/DI/AC/UPVC Riising main & distribution system for different zones at Nagartala (zone-II) W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte.. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/003183/2020-2021 | 501/CSD | 05/08/2020 | 0 | MODERN CONSTRUCTION | 1.29 | 0 | 100
6215 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 45 | M/S B. ENTERPRISE | 113.06 | 0 | 94
6216 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000842/2023-2024 | 690/AD | 30/01/2024 | 0 | Resource Division | 24.01 | 0 | 0
6217 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Ramchandranagar W/S Scheme (Phase-A), Srinagar W/S Scheme (Phase-A), Suryanagar W/S Scheme (Phase-A) & Taktipur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 515/KSD, 24.08.21, T.No. 1801/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | VCH/002605/2021-2022 | BP-2021-22-508 | 22/03/2022 | 0 | LEMNISCATE | 4.7 | 0 | 0
6218 | Alipore Division | Kakdwip Sub-Division | Providing Valves for maintaining proper pressure head at dam area in Dakshin Shibganj W/S Scheme, Block - Pathar Pratima in connection with Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) under Jal Swapna under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000395/2020-2021 | 957/KSD | 03/11/2020 | 30 | M/S B. ENTERPRISE | 4.18 | 4.17 | 0
6219 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 45 | M/S B. ENTERPRISE | 28.74 | 0 | 60
6220 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (22-23, 21-25, 19-30, 8-9), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000480/2020-2021 | 1058/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.78 | 4.77 | 0
6221 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (16-17, 11-12, 5-6, 2-3), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000485/2020-2021 | 1062/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.75 | 4.74 | 0
6222 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (30-31, 16-17, 3-3A, 27-28), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000504/2020-2021 | 1076/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.79 | 4.78 | 0
6223 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Dakshin Shibganj & Laxmijanardanpur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001049/2021-2022 | 2332/AD | 09/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
6224 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Sibnagar Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001207/2020-2021 | 2103/AD | 01/10/2020 | 365 | M/S B. ENTERPRISE | 64.82 | 0 | 95
6225 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with approach road at 1st Tubewell site for Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001287/2024-2025 | 1920/KSD | 20/12/2024 | 25 | AZAD RAHAMAN LASKAR | 2.3 | 0 | 0
6226 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 2nd Tubewell site for Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001288/2024-2025 | 1921/KSD | 20/12/2024 | 25 | AZAD RAHAMAN LASKAR | 3.92 | 0 | 0
6227 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 10 | SRI DURGA ENTERPRISE | 4.39 | 0 | 95
6228 | Alipore Division | Kakdwip Sub-Division | Laying UPVC pipe line for maintaining Functional Household Tap Connection at Pathar Pratima Bazar Area for Dakshin Shibganj piped water supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001789/2020-2021 | 1234/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.42 | 4.4 | 100
6229 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000773/2023-2024 | 607/AD | 29/01/2024 | 0 | Resource Division | 7.26 | 0 | 0
6230 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000311/2020-2021 | 328/A/RSD | 30/09/2020 | 15 | TIYASHA ENTERPRISE | 4.73 | 0 | 100
6231 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000312/2020-2021 | 329/A/RSD | 30/09/2020 | 15 | M/S. JHARNA ENTERPRISE | 4.73 | 4.62 | 0
6232 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/000324/2020-2021 | 382/RSD | 16/10/2020 | 30 | TIYASHA ENTERPRISE | 4.73 | 0 | 100
6233 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/000326/2020-2021 | 383/RSD | 16/10/2020 | 30 | TIYASHA ENTERPRISE | 4.74 | 0 | 100
6234 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Uttar Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000348/2020-2021 | 391/RSD | 27/10/2020 | 30 | M/S. JHARNA ENTERPRISE | 4.74 | 4.63 | 0
6235 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) |  |  | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
6236 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part -II) |  |  | ORD/000360/2020-2021 | 427/RSD | 23/11/2020 | 60 | M/S. JHARNA ENTERPRISE | 4.64 | 4.6 | 0
6237 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Manager Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/000361/2020-2021 | 428/RSD | 23/11/2020 | 60 | M/S. JHARNA ENTERPRISE | 4.82 | 4.8 | 0
6238 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Janar Gheri & Sarda Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/000362/2020-2021 | 429/RSD | 23/11/2020 | 60 | M/S. R.M. CONSTRUCTION | 4.82 | 4.8 | 0
6239 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) |  |  | ORD/000579/2020-2021 | 505/RSD | 24/12/2020 | 60 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.39 | 0 | 100
6240 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-B) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001185/2021-2022 | 541/RSD | 30/11/2021 | 60 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 100
6241 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-A) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001205/2021-2022 | 523/RSD | 18/11/2021 | 60 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 100
6242 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000652/2023-2024 | 255/AD | 15/01/2024 | 0 | Resource Division | 11.25 | 0 | 0
6243 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamder etc. for Chemaguri W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/07757) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000339/2024-2025 | 2771/AD | 28/06/2024 | 224 | M. MUKHERJEE | 118.51 | 0 | 2
6244 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Chemaguri, Purusottampur, Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/002177/2023-2024 | 955/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.61 | 0 | 100
6245 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000341/2023-2024 | 3156/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6246 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000714/2023-2024 | 484/AD | 24/01/2024 | 0 | Resource Division | 8.91 | 0 | 0
6247 | Alipore Division |  | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Bahirplot far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000144/2021-2022 | 399/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.77 | 0 | 100
6248 | Alipore Division |  | Laying 25 mm dia. & 15 mm dia. PVC Pipe Line to cover house holds situated at Radhakrishnapur and Bahirplot area which are far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000146/2021-2022 | 401/KSD | 07/07/2021 | 15 | M/S. P. GIRI ENTERPRISE | 4.77 | 0 | 100
6249 | Alipore Division |  | Laying 90 mm dia. (OD) UPVC Pipe Line to cover house holds situated far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000151/2021-2022 | 403/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.78 | 0 | 100
6250 | Alipore Division |  | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Radhakrishnapur far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000154/2021-2022 | 407/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.79 | 0 | 100
6251 | Alipore Division |  | Laying Rising Main and inter connection of Tubewell and Supply and delivery of DI / CI specials for the same works for implementation of JJM of Radhakrishnapur Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division PHE Dte. |  |  | ORD/000353/2022-2023 | 338/KSD | 01/08/2022 | 20 | M/S BABUSONA ENTERPRISE | 2.47 | 0 | 100
6252 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Radhakrishnapur Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001277/2020-2021 | 2003/AD | 26/09/2020 | 365 | M/S. P. GIRI ENTERPRISE | 59.38 | 47.56 | 100
6253 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000711/2023-2024 | 481/AD | 24/01/2024 | 0 | Resource Division | 6.08 | 0 | 0
6254 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/00437/2024-2025 |  | 28/05/2024 | 0 | RAJKUMAR MANNA | 18.72 | 0 | 0
6255 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR SEPT'22-OCT'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/00682/2024-2025 | BP-2024-25-227 | 20/06/2024 | 0 | RAJKUMAR MANNA | 0.73 | 0 | 0
6256 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/03542/2023-2024 | BP-2023-24-1273 | 27/03/2024 | 0 | RAJKUMAR MANNA | 18.72 | 0 | 0
6257 | Alipore Division | Kakdwip Sub-Division | HIRE bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/03543/2023-2024 | BP-2023-24-1274 | 27/03/2024 | 0 | RAJKUMAR MANNA | 1.46 | 0 | 0
6258 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000005/2022-2023 | 122/AD | 07/04/2022 | 15 | FIDERE MARINE SERVICES PVT. LTD. | 12.98 | 0 | 100
6259 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000006/2022-2023 | 123/AD | 07/04/2022 | 15 | FIDERE MARINE SERVICES PVT. LTD. | 12.99 | 0 | 80
6260 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000019/2020-2021 | 2342/AD | 14/10/2020 | 60 | M/S. MA BHABANI CONSTRUCTION | 10.26 | 0 | 100
6261 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Abad Gangadharpur (Part) and Bahirchak (Part) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000139/2021-2022 | 394/KSD | 07/07/2021 | 15 | M/S BHAGABATI ENTERPRISE | 4.48 | 0 | 100
6262 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000162/2021-2022 | 405/KSD | 07/07/2021 | 15 | M/S PIRBABA ENTERPRISE | 4.79 | 0 | 97
6263 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000469/2021-2022 | 2417/AD | 15/09/2021 | 60 | L.N. ENTERPRISE | 37.12 | 0 | 100
6264 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001784/2020-2021 | 1229/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 4.39 | 4.38 | 100
6265 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 10 | SRI DURGA ENTERPRISE | 4.39 | 3.81 | 95
6266 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Taltukuri for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001786/2020-2021 | 1231/KSD | 23/02/2021 | 10 | KHATEJA CONSTRUCTION | 4.39 | 3.82 | 88
6267 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dhutkhali for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001788/2020-2021 | 1233/KSD | 23/02/2021 | 10 | GROWING CONCERN | 4.4 | 4.39 | 100
6268 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kasarir Chak for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001793/2020-2021 | 1238/KSD | 23/02/2021 | 10 | M/S. NIRMAL KUMAR MONDAL | 4.61 | 4.26 | 93
6269 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001799/2020-2021 | 1241/KSD | 23/02/2021 | 10 | M/S. J.K. TRIPATHI & SONS | 4.74 | 4.69 | 99
6270 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001800/2020-2021 | 1242/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 100
6271 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001806/2020-2021 | 1244/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 100
6272 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001814/2020-2021 | 1253/KSD | 23/02/2021 | 10 | L.N. ENTERPRISE | 3.95 | 3.95 | 100
6273 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001823/2020-2021 | 1257/KSD | 23/02/2021 | 10 | M/S. J.K. TRIPATHI & SONS | 4.61 | 0 | 93
6274 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001826/2020-2021 | 1260/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 3.51 | 3.5 | 100
6275 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001830/2020-2021 | 1261/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.6 | 4.53 | 0
6276 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001833/2020-2021 | 1264/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.61 | 0 | 98
6277 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001836/2020-2021 | 1267/KSD | 23/02/2021 | 10 | L.N. ENTERPRISE | 2.63 | 2.46 | 94
6278 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001861/2020-2021 | 1292/KSD | 23/02/2021 | 10 | KRISHNA CONSTRUCTION | 4.74 | 4.47 | 95
6279 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001864/2020-2021 | 1295/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 2.19 | 0 | 96
6280 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001865/2020-2021 | 1296/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.39 | 4.38 | 100
6281 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001867/2020-2021 | 1298/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 3.29 | 0 | 80
6282 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-V) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001869/2020-2021 | 1300/KSD | 23/02/2021 | 10 | MITRA CONSTRUCTION | 3.07 | 2.97 | 97
6283 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001875/2020-2021 | 1304/KSD | 23/02/2021 | 10 | MITRA CONSTRUCTION | 3.51 | 3.41 | 98
6284 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001877/2020-2021 | 1305/KSD | 23/02/2021 | 10 | ANANTA KUMAR GIRI | 4.39 | 4.31 | 99
6285 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001885/2020-2021 | 1307/KSD | 23/02/2021 | 10 | GROWING CONCERN | 3.07 | 3.07 | 100
6286 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.01.2024 to 30.06.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002122/2023-2024 | 5112/AD | 29/12/2023 | 183 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
6287 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 197 to 198 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000107/2020-2021 | 1272/SWD-I | 23/11/2020 | 120 | BANIK BROTHERS | 27.48 | 27.08 | 0
6288 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for ChakNabashan Mouza and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000102/2020-2021 | 1273/SWD-I | 23/11/2020 | 120 | NIRMAL UDYOG | 25.27 | 24.42 | 0
6289 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000422/2024-2025 | 3206/AD | 01/08/2024 | 30 | KHOKAN MONDAL | 14.43 | 0 | 100
6290 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - Q) (SM/11747) (SM/09395) (SM/08803) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2024-2025 | 3780/AD | 18/09/2024 | 30 | KHOKAN MONDAL | 12.86 | 0 | 100
6291 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000698/2023-2024 | 468/AD | 24/01/2024 | 0 | Resource Division | 10 | 0 | 0
6292 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001028/2021-2022 | 542/KSD | 01/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.57 | 0 | 100
6293 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000324/2023-2024 | 3139/AD | 29/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
6294 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000538/2023-2024 | 22/AD | 02/01/2024 | 0 | Resource Division | 18.95 | 0 | 0
6295 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000717/2023-2024 | 487/AD | 24/01/2024 | 0 | Resource Division | 12.34 | 0 | 0
6296 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001058/2021-2022 | 2346/AD | 09/09/2021 | 7 | M/S R.DUTTA & CO. | 2.12 | 0 | 100
6297 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001085/2021-2022 | 576/KSD | 10/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.59 | 0 | 100
6298 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Purusottampur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001428/2023-2024 | 4611/AD | 14/12/2023 | 300 | SPA ENTERPRISE | 641.07 | 0 | 50
6299 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000322/2023-2024 | 3137/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6300 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000534/2023-2024 | 18/AD | 02/01/2024 | 0 | Resource Division | 12.38 | 0 | 0
6301 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001084/2021-2022 | 575/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
6302 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 0 | 40
6303 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001608/2021-2022 | 606/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.55 | 0 | 100
6304 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000327/2023-2024 | 3142/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6305 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000535/2023-2024 | 19/AD | 02/01/2024 | 0 | Resource Division | 16.67 | 0 | 0
6306 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Improvement of water supply by Interconnection from existing Big dia tube well and laying distribution system with CIDF, UPVC pipes Including providing Functional House Hold Tap Connection by retrofitting of scheme ¿Improvement of water supply [Phase-III] in Baruipur and Mograhat-II block¿ of Sankarpur-II GP within zone-43, covering Nur, Durgo, Balbalia, Surjopur hat mouzas under surface water based water supply scheme for arsenic affected areas of south 24- Parganas district. | AE BSD |  | ORD/000061/2021-2022 | 479 /SWD-I JJM | 07/07/2021 | 120 | M/S. S.S. ENTERPRISE | 193.14 | 0 | 0
6307 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Kandalia, Sundarika, Parashurampur and Gopalpur villages due to Swajal Gram activities under Zone-V of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000580/2022-2023 | 5856/AD | 18/10/2022 | 30 | M/S SAMADDAR CONSTRUCTION | 91.55 | 0 | 60
6308 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II Zone-V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas Block Diamond Harbour-II, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001337/2021-2022 | 6018/AD | 15/02/2022 | 365 | M/S A.K. GHATAK | 185.19 | 0 | 100
6309 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000069/2022-2023 | 4969/AD | 16/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
6310 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000097/2022-2023 | 7495/AD | 26/11/2022 | 0 | Resource Division | 3.52 | 0 | 0
6311 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gopalnagar 3 No. for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001744/2020-2021 | 1216/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.19 | 0 | 0
6312 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001759/2020-2021 | 1218/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
6313 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-A | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001796/2020-2021 | 1236/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.5 | 0 | 97
6314 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Part) & Purba Para (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001850/2020-2021 | 1281/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 0 | 0
6315 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.46 | 0 | 87
6316 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-II), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001855/2020-2021 | 1286/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
6317 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block (Part) & 2 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001857/2020-2021 | 1288/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
6318 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 4 no. Block (Part) & 5 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001887/2020-2021 | 1309/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
6319 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001917/2020-2021 | 1327/KSD | 23/02/2021 | 10 | TAPAN DAS | 4.39 | 0 | 100
6320 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-C | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001920/2020-2021 | 1330/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.49 | 0 | 96
6321 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 5 no. Block (Part) & Dakshin Gopalnagar 3 no. (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001922/2020-2021 | 1333/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 0 | 0
6322 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block (Part) & 4 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001924/2020-2021 | 1336/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
6323 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000776/2023-2024 | 610/AD | 29/01/2024 | 0 | Resource Division | 9.27 | 0 | 0
6324 | Alipore Division | Canning Sub-division | Inter connection and rising main for Tubewell No. 1, 2, 3 and 4 with supply of specials at Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000250/2023-2024 | 1393/AD | 12/07/2023 | 15 | ARBINA ENTERPRISE | 16.29 | 0 | 100
6325 | Alipore Division | Canning Sub-division | Laying Distribution system for Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000665/2022-2023 | 6170/AD | 01/11/2022 | 840 | M/S R.K.ENTERPRISE (SALBAGAN) | 227.75 | 0 | 100
6326 | Alipore Division | Canning Sub-division | Relaying and repairing of pipe line for FHTC work at node point no. 124-122-121-120-33-34-36-89-88-87-85-38-40-50-51-52-55-56 of Chunakhali Water Supply Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000031/2022-2023 | 517/AD | 26/04/2022 | 30 | R.S.CONSTRUCTION CO. | 45.81 | 0 | 100
6327 | Alipore Division | Canning Sub-division | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 30 | MODERN CONSTRUCTION | 4.82 | 0 | 100
6328 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 30 | MODERN CONSTRUCTION | 4.68 | 0 | 100
6329 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.73 | 0 | 100
6330 | Alipore Division | Canning Sub-division | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.74 | 0 | 100
6331 | Alipore Division | Canning Sub-division | Continuation order for the work of Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Chunakhali (Zone - I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002438/2024-2025 | 623/AD | 17/02/2025 | 121 | AQUATECH ENGINEER | 19.6 | 0 | 100
6332 | Central Drilling | Canning Sub-division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 350 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHUNAKHALI W/S SCHEME (Z-II, REPLACEMENT TW-III), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000024/2022-2023 | 51/CDD | 08/04/2022 | 30 | PADMA ENGINEERING & CO. | 16.79 | 0 | 0
6333 | Central Drilling | Canning Sub-division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE ASSISTANT ENGINEER, STORE & WORKSHOP SUB DIVISION, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000060/2022-2023 | 99/S&WSD | 23/06/2022 | 15 | NAGENDRA PATRA | 0.87 | 0 | 33
6334 | Central Drilling | Canning Sub-division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION-I, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000217/2021-2022 | 67/CMSD-I (D) | 22/03/2022 | 7 | SUJATA BHOWMICK | 0.87 | 0 | 67
6335 | Central Drilling | Canning Sub-division | ADDITIONAL TRANSPORTATION OF GRAVELS, SEALING AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN CHUNAKHALI W/S SCHEME (REPLACEMENT TW-III, Z-II), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000222/2022-2023 | 309/CMSD-I | 08/07/2022 | 3 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0
6336 | Central Drilling | Canning Sub-division | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0 | 0
6337 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XV of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000111/2023-2024 | 37/AD | 05/04/2023 | 60 | M/S. JHARNA ENTERPRISE | 93.18 | 0 | 80
6338 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XV, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 718 Nos.) [Part - B] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000112/2023-2024 | 38/AD | 05/04/2023 | 45 | BANERJEE ENTERPRISE | 44.3 | 0 | 10
6339 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000242/2023-2024 | 2913/AD | 20/09/2023 | 0 | Resource Division | 1.38 | 0 | 0
6340 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000638/2023-2024 | 242/AD | 15/01/2024 | 0 | Resource Division | 4.42 | 0 | 0
6341 | S24 Pgns Mechanical | Raidighi Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | BILL/02638/2023-2024 | BP-2023-24-279 | 03/10/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
6342 | S24 Pgns Mechanical | Raidighi Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Zone-XV water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Mathgurapur-I] (Phase-I) (SM/10532) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000063/2025-2026 | 1439/SMD | 21/05/2025 | 135 | S.P. CONSTRUCTION | 24.8 | 0 | 0
6343 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
6344 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- VI of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC =4922 nos) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000121/2023-2024 | 592/AD | 15/05/2023 | 90 | M/S. JHARNA ENTERPRISE | 272.12 | 0 | 0
6345 | Alipore Division | Raidighi Sub-Division | Land Development at head work site of Zone-VI, Mathurapur-II block under 'Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000440/2022-2023 | 4354/AD | 25/08/2022 | 30 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 23.26 | 0 | 75
6346 | Alipore Division | Raidighi Sub-Division | Construction of service road for head work site of Zone-VI, Mathurapur-II block under Mega surface water based water supply scheme-FaltaMathurapur under Raidighi Sub-Division of AliporeDivision,P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/001136/2022-2023 | 601/RSD | 23/12/2022 | 30 | M/S M.B.ENTERPRISE | 4.7 | 0 | 20
6347 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000039/2022-2023 | 3587/AD | 29/07/2022 | 0 | Resource Division | 700.28 | 0 | 0
6348 | S24 Pgns Mechanical | Raidighi Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-VI of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000565/2022-2023 | 581/SMD | 23/02/2023 | 90 | M.S.ENTERPRISE | 26.7 | 0 | 0
6349 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Uttar Roypur, Balarampur (Part) and Chak Nabasan (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000080/2021-2022 | 1164/SWD-I JJM | 02/11/2021 | 120 | SRIJON ENTERPRISE | 141.41 | 0 | 100
6350 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte.(TSM / 8302) PART-III | AE SWSD-I |  | ORD/000461/2022-2023 | 2772/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 13.64 | 0 | 100
6351 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000102/2021-2022 | 1103/SWD-I | 25/10/2021 | 120 | PREMANANDA ROY BISWAS | 57.11 | 0 | 100
6352 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Betuabati W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8299) Part -D | AE SWSD-I |  | ORD/000462/2022-2023 | 2779/SWD-I | 31/01/2023 | 45 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.62 | 0 | 0
6353 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000123/2022-2023 | 3472/SWD-I | 15/03/2023 | 0 | Resource Division | 2.21 | 0 | 0
6354 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | VCH/001194/2021-2022 | BP-2021-22-219 | 30/03/2022 | 0 | PREMANANDA ROY BISWAS | 15.5 | 0 | 0
6355 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000078/2021-2022 | 1204/SWD-I JJM | 09/11/2021 | 120 | VISHAL CONSTRUCTION CO. | 254.11 | 0 | 100
6356 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001464/2021-2022 | 6258/AD | 24/02/2022 | 365 | A.G.ENTERPRISE | 145.57 | 0 | 95
6357 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000016/2022-2023 | 1173/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
6358 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000083/2022-2023 | 5549/AD | 29/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
6359 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Madarat More Riksha Stand to Najirpur Auto Stand via Kobindapur More to Vurkul Khalpar 2) L070- Atghora on L068 To Tagarberia(WB/02/320) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01776/2024-2025 | BP-2024-25-801 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 6.57 | 0 | 0
6360 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04004/2023-2024 | BP-2023-24-407 | 13/12/2023 | 0 | WBSEDCL | 6.33 | 0 | 0
6361 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Baruipur W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/12261) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 461/SMSD | 16/04/2024 | 15 | S. DUTTA | 0.72 | 0 | 0
6362 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 1 of Baruipur W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/12261) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 454/SMSD | 16/04/2024 | 15 | S. DUTTA | 0.72 | 0 | 100
6363 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & fixing main switch & Bus Bar at Pump House no-1 & 2 of Baruipur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/12261) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000343/2024-2025 | 453/SMSD | 16/04/2024 | 15 | S. DUTTA | 0.58 | 0 | 0
6364 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Baruipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000484/2022-2023 | 237/SMD | 24/01/2023 | 90 | S. DUTTA | 21.42 | 0 | 40
6365 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.31] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00491/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 18.74 | 0 | 0
6366 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BARUIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000163/2021-2022 | 1922/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
6367 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for BARUIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012660] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 1479/SWD-I | 27/09/2022 | 930 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
6368 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at BARUIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1018) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000217/2022-2023 | 1597/SWD-I | 18/10/2022 | 120 | SHRAYA ROADS LINE. | 330.06 | 0 | 100
6369 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at BARUIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000291/2022-2023 | 1783/SWD-I | 07/11/2022 | 840 | ALISHA CONSTRUCTION | 10.93 | 0 | 100
6370 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for BARUIPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/012660] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 2106/SWD-I | 30/08/2023 | 600 | PADMA ENGINEERING CO. | 4.41 | 0 | 100
6371 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based BARUIPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12261) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000863/2023-2024 | 1199/SWD-I | 11/03/2024 | 45 | M/S SHIBAM ENTERPRISE | 32.54 | 0 | 0
6372 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000267/2023-2024 | 2422/SWD-I | 30/09/2023 | 0 | Resource Division | 58.71 | 0 | 0
6373 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000334/2023-2024 | 271/SWD-I | 10/01/2024 | 0 | Resource Division | 6.27 | 0 | 0
6374 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00024/2023-2024 | BP-2023-24-44 | 18/05/2023 | 0 | WBSEDCL | 4.22 | 0 | 0
6375 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Panakua water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000543/2022-2023 | 474/SMD | 20/02/2023 | 1046 | KARUNAMOY ENGINEERING | 26.42 | 0 | 70
6376 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Upgradation of the outdoor illumination arrangement with other allied works at P.H. No. - 1 under Panakua Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur- I)(SM/11494) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/002456/2023-2024 | 185-AE-II-SMD | 20/02/2024 | 15 | SOHINI ENTERPRISE | 0.75 | 0 | 100
6377 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Providing bullah pilling works and other allied works for the construction of the Boundary Wall at 1st Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000002/2025-2026 | 905/SWD-I | 02/04/2025 | 30 | CONCORD PROJECTS PRIVATE LIMITED | 4.07 | 0 | 99
6378 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000028/2022-2023 | 912/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 0 | 100
6379 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 993] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000148/2022-2023 | 1388/SWD-I | 21/09/2022 | 90 | NIRMAL UDYOG | 139.04 | 0 | 94
6380 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
6381 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of PANAKUA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000223/2021-2022 | 1970/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.69 | 0 | 100
6382 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, additional laying of pipeline and other allied works for PANAKUA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000269/2024-2025 | 2918/SWD-I | 25/06/2024 | 45 | NIRMAL UDYOG | 66.18 | 0 | 0
6383 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/11/2022] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000316/2022-2023 | 1470/SWD-I | 27/09/2022 | 180 | NIRMAL UDYOG | 0.86 | 0 | 50
6384 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PANAKUA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11494) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000428/2022-2023 | 2573/SWD-I | 10/01/2023 | 60 | GOUTAM MAZUMDER | 6.05 | 0 | 100
6385 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for PANAKUA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011229] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000594/2022-2023 | 3114/SWD-I | 24/02/2023 | 646 | DEBASHIS DAS | 15.88 | 0 | 98
6386 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development of Head work site (1st tube well) in connection with Ground Water Based PANAKUA Piped Water Supply Scheme to accomodation FHTC in Bishnupur-I Block under South 24 Pgs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. [TSM/011229] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000808/2022-2023 | 3700/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.96 | 0 | 100
6387 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of temporary approach road, land development and allied works related to the 2nd Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. South 24 Parganas District [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001073/2024-2025 | 5341/SWD-I | 30/12/2024 | 30 | DEBASHIS DAS | 5.13 | 0 | 0
6388 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000011/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 6.06 | 0 | 0
6389 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000115/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 28.03 | 0 | 0
6390 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/01058/2023-2024 | BP-2023-24-126 | 17/07/2023 | 0 | WBSEDCL | 7.84 | 0 | 0
6391 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/04458/2023-2024 | BP-2023-24-452 | 09/01/2024 | 0 | WBSEDCL | 2.36 | 0 | 0
6392 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bharu Ramkrishnapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000541/2022-2023 | 472/SMD | 20/02/2023 | 90 | AHALYA ENGINEERING WORKS | 26.76 | 0 | 0
6393 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000034/2022-2023 | 918/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 0 | 100
6394 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 853] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000151/2022-2023 | 1391/SWD-I | 21/09/2022 | 1720 | ODISSI INNOVATIONS ENGINEERS PVT. LTD. | 132.6 | 0 | 90
6395 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
6396 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BHARU RAMKRISHNAPUR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/11497) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000351/2024-2025 | 3363/SWD-I | 26/07/2024 | 60 | ODISSI INNOVATIONS | 132.11 | 0 | 5
6397 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "BHARU RAMKRISHNAPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000402/2022-2023 | 463/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 0 | 100
6398 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BHARU RAMKRISHNAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11497) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000431/2022-2023 | 2575/SWD-I | 10/01/2023 | 60 | OHAB SK. | 6.05 | 0 | 1
6399 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BHARU RAMKRISHNAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000570/2022-2023 | 2974/SWD-I | 17/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.58 | 0 | 100
6400 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BHARU RAMKRISHNAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000585/2022-2023 | 3106/SWD-I | 24/02/2023 | 800 | MOULI CONSTRUCTION | 15.89 | 0 | 100
6401 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 1st Tubewell site including development of approach road under Bharu Ramkrishnapur Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns Water Supply Division-I, PHE Dte. (TSM/011211) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000730/2023-2024 | 435/SWD-I | 22/01/2024 | 15 | ROYAL CONSTRUCTION | 8.92 | 0 | 50
6402 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed BHARU RAMKRISHNAPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000812/2022-2023 | 3704/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.6 | 0 | 100
6403 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000017/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.25 | 0 | 0
6404 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000108/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 59 | 0 | 0
6405 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00128/2024-2025 | BP-2024-25-40 | 24/04/2024 | 0 | WBSEDCL | 5.05 | 0 | 0
6406 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no-2 of Uttarbhar water supply scheme (Baruipur Block). | AE BSD,Assistant Engineer | Junior Engineer | BILL/01726/2024-2025 | BP-2024-25-413 | 30/09/2024 | 0 | WBSEDCL | 14.69 | 0 | 0
6407 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uttarbhag water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000474/2022-2023 | 3945/SMD | 30/12/2022 | 945 | M.S.C ENTERPRISE | 25.93 | 0 | 40
6408 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Uttarbhag W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12231) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002054/2024-2025 | 393/SMSD | 19/03/2025 | 15 | M.S.C ENTERPRISE | 0.59 | 0 | 0
6409 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at PH-2 of Uttarbhag W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12231) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002056/2024-2025 | 395/SMSD | 19/03/2025 | 15 | M.S.C ENTERPRISE | 0.97 | 0 | 0
6410 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at UTTAR BHAG of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 525/SWD-I | 11/05/2023 | 781 | JAL PRAVAHIKA PVT. LTD. | 527.08 | 0 | 80
6411 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of UTTAR BHAG Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000208/2021-2022 | 1948/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 100
6412 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for UTTAR BHAG Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000573/2024-2025 | 4272/SWD-I | 01/10/2024 | 30 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0
6413 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall including development of land and other allied works for Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/12231) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000856/2023-2024 | 1248/SWD-I | 13/03/2024 | 585 | ARNAB ENTERPRISE | 33.68 | 0 | 50
6414 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Head works site for UTTAR BHAG PWSS to accommodate FHTC in BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000901/2023-2024 | 1328/SWD-I | 15/03/2024 | 15 | ARUP ENTERPRISE | 15.73 | 0 | 100
6415 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000189/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 26.57 | 0 | 0
6416 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000078/2022-2023 | 2994/SWD-I | 20/02/2023 | 0 | Resource Division | 60.86 | 0 | 0
6417 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-IX at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3434] | AE HQ-I |  | ORD/000617/2022-2023 | 3217/SWD-I | 28/02/2023 | 763 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 250.59 | 0 | 15
6418 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000059/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 21.15 | 0 | 0
6419 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Meherpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000158/2023-2024 | 680/AD | 17/05/2023 | 1050 | M/S B. ENTERPRISE | 28.72 | 0 | 60
6420 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Meherpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11745) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000188/2024-2025 | 2549/AD | 18/06/2024 | 60 | TANMAY ROY CHOWDHURY | 65.22 | 0 | 0
6421 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000298/2023-2024 | 1492/AD | 14/07/2023 | 300 | TANMAY ROY CHOWDHURY | 311.15 | 0 | 30
6422 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Meherpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000299/2022-2023 | 3835/AD | 08/08/2022 | 45 | M/S. L.P. CONSTRUCTION | 37.08 | 0 | 100
6423 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000305/2022-2023 | 3841/AD | 08/08/2022 | 30 | KUNDU CONSTRUCTION CO. | 9.96 | 0 | 50
6424 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MEHERPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2022-2023 | 1708/AD | 14/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.77 | 0 | 100
6425 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Meherpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000921/2023-2024 | 2974/AD | 26/09/2023 | 45 | RAMKRISHNA ENTERPRISE | 9.54 | 0 | 0
6426 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
6427 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000065/2022-2023 | 3953/AD | 12/08/2022 | 0 | Resource Division | 13.52 | 0 | 0
6428 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000578/2023-2024 | 52/AD | 03/01/2024 | 0 | Resource Division | 6.41 | 0 | 0
6429 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000942/2023-2024 | 1676/AD | 22/03/2024 | 0 | Resource Division | 14.42 | 0 | 0
6430 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00011/2023-2024 | BP-2023-24-42 | 18/05/2023 | 0 | WBSEDCL | 5.72 | 0 | 0
6431 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Meherpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000353/2022-2023 | 3757/SMD | 29/12/2022 | 90 | ALPHA ENTERPRISE | 19.33 | 0 | 0
6432 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of submersible pumping machinery with allied materials for JJM works at PH-1 of Meherpur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000885/2023-2024 | 2781/SMD | 24/08/2023 | 30 | T.S. CONSTRUCTION | 2.99 | 0 | 100
6433 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Meherpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001893/2023-2024 | 1181/SMD | 22/03/2024 | 21 | ALPHA ENTERPRISE | 8.42 | 0 | 0
6434 | Alipore Division | Kakdwip Sub-Division | VEHICLE BILL FOR ASSISTANT ENGINEER HQ-II | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00787/2022-2023 | BP-2022-23-981 | 21/03/2023 | 0 | DEEPAK KUMAR PRASAD | 0.38 | 0 | 0
6435 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Krishnanagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000144/2023-2024 | 143/KSD | 30/05/2023 | 10 | M/S. P. GIRI ENTERPRISE | 3.38 | 0 | 100
6436 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC, for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-P) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000169/2024-2025 | 2528/AD | 18/06/2024 | 30 | M/S. P. GIRI ENTERPRISE | 7.62 | 0 | 100
6437 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Krishnanagar for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000170/2024-2025 | 2529/AD | 18/06/2024 | 30 | ANANDA MAITY | 7.98 | 0 | 0
6438 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Paschim Gharai Para for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000171/2024-2025 | 2530/AD | 18/06/2024 | 30 | M/S SNEHALATA ENTERPRISE | 7.66 | 0 | 0
6439 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Gholapara South for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000172/2024-2025 | 2531/AD | 18/06/2024 | 30 | M/S. JOYGURU ENTERPRISE | 5.66 | 0 | 0
6440 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Gholapara for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000173/2024-2025 | 2532/AD | 18/06/2024 | 30 | M/S. MOYNA ENTERPRISE | 7.06 | 0 | 0
6441 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000174/2024-2025 | 2533/AD | 18/06/2024 | 30 | M/S B.S. ENTERPRISE | 5.73 | 0 | 0
6442 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000175/2024-2025 | 2534/AD | 18/06/2024 | 30 | PRADIP KUMAR MONDAL | 5.62 | 0 | 0
6443 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000177/2024-2025 | 2536/AD | 18/06/2024 | 30 | M/S MODINA ENTERPRISE | 5.52 | 0 | 0
6444 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000178/2024-2025 | 2537/AD | 18/06/2024 | 30 | M/S. JOYGURU ENTERPRISE | 5.43 | 0 | 0
6445 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000179/2024-2025 | 2538/AD | 18/06/2024 | 30 | M/S. BABA KAPIL MUNI ENTERPRISE | 7.01 | 0 | 0
6446 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000180/2024-2025 | 2539/AD | 18/06/2024 | 30 | M/S PIR BABA ENTERPRISE | 5 | 0 | 0
6447 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000297/2022-2023 | 3833/AD | 08/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.93 | 0 | 99
6448 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 01 No. Pump House for Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000308/2022-2023 | 3856/AD | 08/08/2022 | 45 | MODERN CONSTRUCTION | 59.61 | 0 | 100
6449 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000309/2022-2023 | 3857/AD | 08/08/2022 | 30 | A. K. INDUSTRIES | 13.48 | 0 | 100
6450 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000310/2022-2023 | 3858/AD | 08/08/2022 | 30 | A. K. INDUSTRIES | 13.15 | 0 | 100
6451 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000311/2022-2023 | 3859/AD | 08/08/2022 | 30 | JOY GURU TRADING | 13.82 | 0 | 100
6452 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000312/2022-2023 | 3860/AD | 08/08/2022 | 30 | SARKAR ENTERPRISE | 11.97 | 0 | 100
6453 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000313/2022-2023 | 3861/AD | 08/08/2022 | 30 | DEY ENTERPRISE (III) | 11.47 | 0 | 100
6454 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000314/2022-2023 | 3862/AD | 08/08/2022 | 15 | SRI DURGA ENTERPRISE | 7.2 | 0 | 100
6455 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000315/2022-2023 | 3863/AD | 08/08/2022 | 15 | NARAYAN ENTERPRISE | 6.95 | 0 | 100
6456 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-K) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000316/2022-2023 | 3864/AD | 08/08/2022 | 30 | SWASTIK ENTERPRISE (NEW) | 6.95 | 0 | 100
6457 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-L) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000317/2022-2023 | 3865/AD | 08/08/2022 | 30 | M/S SNEHALATA ENTERPRISE | 5.57 | 0 | 100
6458 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-M) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000318/2022-2023 | 3866/AD | 08/08/2022 | 30 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 5.11 | 0 | 100
6459 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =510] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2022-2023 | 4661/AD | 07/09/2022 | 120 | UNIVERSAL CORPORATION | 148.05 | 0 | 75
6460 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC =510] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000409/2022-2023 | 4678/AD | 07/09/2022 | 120 | M/S. P. GIRI ENTERPRISE | 151.6 | 0 | 100
6461 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000465/2022-2023 | 200/HQ-I/AD | 29/08/2022 | 6 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 60
6462 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000479/2022-2023 | 1709/AD | 14/06/2022 | 45 | VOYAGER | 5.47 | 0 | 100
6463 | Alipore Division | Kakdwip Sub-Division | Inter connection between tubewell no. 1 and 2 to distribution system of Krishnanagar Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001148/2021-2022 | 5536/AD | 20/01/2022 | 15 | JHARNA ENTERPRISE | 6.17 | 0 | 100
6464 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001840/2023-2024 | 128/AD | 05/01/2024 | 54 | KHOKAN MONDAL | 29.23 | 0 | 100
6465 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
6466 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Krishnanagar W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002419/2023-2024 | 1346/AD | 06/03/2024 | 30 | M/S. NAYAK CONSTRUCTION | 11.59 | 0 | 50
6467 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000093/2022-2023 | 5591/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
6468 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000331/2023-2024 | 3146/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6469 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000501/2023-2024 | 4826/AD | 20/12/2023 | 0 | Resource Division | 58.78 | 0 | 0
6470 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00012/2023-2024 | BP-2023-24-41 | 18/05/2023 | 0 | WBSEDCL | 2.38 | 0 | 0
6471 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Krishnanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000344/2022-2023 | 3748/SMD | 29/12/2022 | 90 | KARUNAMOY ENGINEERING | 11.2 | 0 | 5
6472 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of submersible pumping machinery at PH No-1 of Augmentation of Krishnanagar W/S Scheme under south 24 Pgs Mechanical Division PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002360/2023-2024 | 1227-AE-I-SMD | 04/12/2023 | 15 | KARUNAMOY ENGINEERING | 0.94 | 0 | 100
6473 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 Krishnanagar Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002866/2023-2024 | 1217/AE-I/SMD | 24/11/2023 | 15 | KARUNAMOY ENGINEERING | 0.9 | 0 | 0
6474 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramchandranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000132/2024-2025 | 2408/AD | 07/06/2024 | 30 | SUKUMAR HALDAR | 9.51 | 0 | 0
6475 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11749) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000306/2024-2025 | 2680/AD | 24/06/2024 | 361 | AKKRITI CONSTRUCTION | 82.24 | 0 | 0
6476 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 1 no. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000320/2022-2023 | 3867/AD | 08/08/2022 | 45 | S.S. ENTERPRISE (I) | 60.13 | 0 | 0
6477 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000389/2022-2023 | 4483/AD | 31/08/2022 | 30 | M/S BHAGABATI ENTERPRISE | 11.83 | 0 | 100
6478 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( RAMCHANDRANAGAR, PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000491/2022-2023 | 1749/AD | 15/06/2022 | 45 | LEMNISCATE | 5.29 | 0 | 100
6479 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11749) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000560/2024-2025 | 3812/AD | 19/09/2024 | 30 | S. CHAKRABORTY AND CO. | 20.39 | 0 | 0
6480 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
6481 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramchandranagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002601/2023-2024 | 179/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6482 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000058/2022-2023 | 3917/AD | 12/08/2022 | 0 | Resource Division | 43.94 | 0 | 0
6483 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000275/2023-2024 | 3074/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6484 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000675/2023-2024 | 441/AD | 24/01/2024 | 0 | Resource Division | 7.18 | 0 | 0
6485 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000826/2023-2024 | 671/AD | 30/01/2024 | 0 | Resource Division | 13.45 | 0 | 0
6486 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Ramchandranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000428/2022-2023 | 3824/SMD | 29/12/2022 | 90 | K.S.P ENTERPRISE | 11.09 | 0 | 0
6487 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01104/2023-2024 | BP-2023-24-150 | 24/07/2023 | 0 | WBSEDCL | 5.14 | 0 | 0
6488 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/03526/2023-2024 | BP-2023-24-389 | 23/11/2023 | 0 | WBSEDCL | 0.14 | 0 | 0
6489 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kundarali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000462/2022-2023 | 3939/SMD | 30/12/2022 | 90 | A.S.ENTERPRISE | 25.96 | 0 | 53
6490 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Kundarali W/S Scheme under SMD PHE Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/001649/2023-2024 | 1308/SMSD | 03/10/2023 | 15 | A.S.ENTERPRISE | 0.92 | 0 | 100
6491 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at PH-2 of Kundarali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12266) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/001760/2024-2025 | 414/SMSD | 20/03/2025 | 15 | A.S.ENTERPRISE | 0.97 | 0 | 0
6492 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-2 of Kundarali W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12266) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/001761/2024-2025 | 413/SMSD | 20/03/2025 | 15 | A.S.ENTERPRISE | 0.29 | 0 | 0
6493 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at KUNDARALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000116/2022-2023 | 1284/SWD-I | 14/09/2022 | 1080 | MA DURGA ENTERPRISE | 10.93 | 0 | 100
6494 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of additional 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 3rd Tubewell Site for KUNDARALI PWSS to accommodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte. for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [SM/12266] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000128/2025-2026 | 2026/SWD-I | 04/08/2025 | 30 | DEV & COMPANY | 15.9 | 0 | 0
6495 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KUNDALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000162/2021-2022 | 1924/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
6496 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KUNDARALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000188/2022-2023 | 1481/SWD-I | 27/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
6497 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KUNDARALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1571) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000221/2022-2023 | 1639/SWD-I | 20/10/2022 | 1258 | PROJECT AND MAINTENANCE | 333.83 | 0 | 98
6498 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/12266) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000367/2024-2025 | 3507/SWD-I | 07/08/2024 | 495 | PROJECT AND MAINTENANCE | 96.98 | 0 | 30
6499 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kundarali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000798/2022-2023 | 3671/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 0 | 100
6500 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000269/2023-2024 | 2423/SWD-I | 30/09/2023 | 0 | Resource Division | 64.82 | 0 | 0
6501 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000306/2023-2024 | 2443/SWD-I | 30/09/2023 | 0 | Resource Division | 54.51 | 0 | 0
6502 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000071/2023-2024 | 52/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6503 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Roypur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11213)(Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000185/2024-2025 | 2545/AD | 18/06/2024 | 501 | M/S. TAPAS MONDAL | 61.79 | 0 | 0
6504 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000434/2022-2023 | 4349/AD | 25/08/2022 | 30 | M/S KHAJABABA ENTERPRISE | 21.58 | 0 | 60
6505 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000435/2022-2023 | 4350/AD | 25/08/2022 | 30 | M/S. TRIPATHI & CO. | 31.6 | 0 | 70
6506 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000436/2022-2023 | 4351/AD | 25/08/2022 | 30 | KHATEJA CONSTRUCTION | 9.07 | 0 | 0
6507 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Raypur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000459/2022-2023 | 294/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.88 | 0 | 100
6508 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 800] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000546/2022-2023 | 5722/AD | 13/10/2022 | 90 | S.P. CONSTRUCTION (I) | 99.45 | 0 | 84
6509 | Alipore Division | Kakdwip Sub-Division | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000555/2022-2023 | 5729/AD | 13/10/2022 | 1080 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 497.15 | 0 | 20
6510 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 450 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dakshin Roypur W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000582/2023-2024 | 2339/AD | 18/08/2023 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 57.53 | 0 | 0
6511 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 530] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000857/2022-2023 | 6940/AD | 18/11/2022 | 806 | M/S. TAPAS MONDAL | 104.45 | 0 | 92
6512 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Roypur W/S scheme, Block- Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001067/2023-2024 | 3385/AD | 11/10/2023 | 45 | SARADA CONSTRUCTION | 27.64 | 0 | 100
6513 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dakshin Roypur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001068/2023-2024 | 3387/AD | 11/10/2023 | 30 | ANANDA MAITY | 9.55 | 0 | 100
6514 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Dakshin Roypur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001079/2021-2022 | 557/KSD | 08/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.58 | 0 | 100
6515 | Alipore Division | Kakdwip Sub-Division | Construction of 02 nos. Pump House of size 5.40 mtr. x 3.60 mtr. as per departmental drawing and design for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001417/2023-2024 | 4597/AD | 14/12/2023 | 60 | FORTUNE ENGINEERING | 11.18 | 0 | 100
6516 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dakshin Raypur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001725/2022-2023 | 11751/AD | 21/02/2023 | 45 | NATIONAL ENTERPRISE | 38.58 | 0 | 100
6517 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
6518 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 2nos Pump House site of Dakshin Roypur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11213) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002182/2024-2025 | 176/KSD | 11/01/2025 | 20 | KRISHNA CONSTRUCTION | 3.06 | 0 | 0
6519 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000449/2023-2024 | 4765/AD | 19/12/2023 | 0 | Resource Division | 78.58 | 0 | 0
6520 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000565/2023-2024 | 82/AD | 03/01/2024 | 0 | Resource Division | 21.5 | 0 | 0
6521 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000740/2023-2024 | 575/AD | 29/01/2024 | 0 | Resource Division | 8.29 | 0 | 0
6522 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000962/2023-2024 | 1696/AD | 22/03/2024 | 0 | Resource Division | 28.27 | 0 | 0
6523 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/03440/2023-2024 | BP-2023-24-379 | 13/11/2023 | 0 | WBSEDCL | 8.8 | 0 | 0
6524 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/03525/2023-2024 | BP-2023-24-390 | 23/11/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
6525 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-4 of Dakshin Roypur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/11213) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000538/2025-2026 | 372-AE-II/SMD | 26/05/2025 | 21 | T.S. CONSTRUCTION | 0.67 | 0 | 0
6526 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Dakshin Raypur Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000566/2022-2023 | 582/SMD | 23/02/2023 | 90 | SARKAR ELECTRICAL | 11.11 | 0 | 0
6527 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01100/2023-2024 | BP-2023-24-152 | 24/07/2023 | 0 | WBSEDCL | 13.12 | 0 | 0
6528 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Baruli water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000294/2022-2023 | 446/SMD | 17/02/2023 | 638 | NUPUR CHANDRA HALDER | 26.02 | 0 | 100
6529 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-1&2 of Baruli W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001651/2023-2024 | .1468/SMSD | 01/12/2023 | 15 | MAA SUSOMA & COMPANY | 0.78 | 0 | 100
6530 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Pump House no-2 of Baruli W/S Scheme under SMD, PHE Dte. (Block- Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002568/2023-2024 | .1410/SMSD | 17/11/2023 | 15 | NUPUR CHANDRA HALDER | 0.94 | 0 | 100
6531 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump house no-1 & 2 of Baruli W/S Scheme under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002569/2023-2024 | .1409/SMSD | 17/11/2023 | 15 | NUPUR CHANDRA HALDER | 0.58 | 0 | 100
6532 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-11C-6886] "(w.e.f. 01/06/2025 to 30/11/2025) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000061/2025-2026 | 1370/SWD-I | 22/05/2025 | 183 | SRIMANTA MONDAL | 0.87 | 0 | 100
6533 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000183/2023-2024 | 775/SWD-I | 31/05/2023 | 183 | SRIMANTA MONDAL | 0.87 | 0 | 30
6534 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-19E-2060] " (w.e.f. 01/06/2024 to 30/11/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 2355/SWD-I | 24/05/2024 | 183 | SRIMANTA MONDAL | 0.87 | 0 | 18
6535 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of "BARULI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12212) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000237/2024-2025 | 2657/SWD-I | 07/06/2024 | 45 | M/S B.M. INDUSTRIES | 47.54 | 0 | 0
6536 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BARULI Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000263/2022-2023 | 1775/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
6537 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BARULI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1435] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000496/2022-2023 | 2864/SWD-I | 09/02/2023 | 1200 | M/S B.M. INDUSTRIES (BM.INDUSTRY@GMAIL.COM) | 391.4 | 0 | 60
6538 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-19E-2060] " (w.e.f. 01/12/2023 to 31/05/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000673/2023-2024 | 2998/SWD-I | 29/11/2023 | 183 | SRIMANTA MONDAL | 0.87 | 0 | 15
6539 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BARULI PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014838] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000767/2022-2023 | 3604/SWD-I | 24/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
6540 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-11C-6886] "(w.e.f. 01/12/2024 to 31/05/2025) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000889/2024-2025 | 4876/SWD-I | 29/11/2024 | 182 | SRIMANTA MONDAL | 0.86 | 0 | 20
6541 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 7.88 | 0 | 0
6542 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000228/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.84 | 0 | 0
6543 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service(power) connection at Shaksahar PH- 2 water supply scheme under bhangar-I block Reference ID- 106550929, Application No- 1007657683 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00569/2024-2025 | BP-2024-25-141 | 03/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
6544 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01109/2023-2024 | BP-2023-24-156 | 24/07/2023 | 0 | WBSEDCL | 9.73 | 0 | 0
6545 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone- I of Shaksahar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000465/2022-2023 | 276/SMD | 01/02/2023 | 791 | DAS ENTERPRISE | 25.77 | 0 | 95
6546 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Shakasar PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/11275) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001682/2024-2025 | 1696/SMSD | 24/12/2024 | 15 | DAS ENTERPRISE | 0.9 | 0 | 100
6547 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Payment of Enhanced GST Rate vide W/O No.1689/SWD-I dt. 01/11/2022 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02030/2023-2024 | BP-2023-24-756 | 13/03/2024 | 0 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 19.39 | 0 | 0
6548 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR SHAKSAHAR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 882, KHATIAN NO. 843, JL. NO. 104, MOUZA - CHAKBHIKA) & 2ND TUBE WELL SITE (DAG NO. 308, KHATIAN NO. 567, JL NO. 119, MOUZA - SHAKSAHAR), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 757/SWD-I | 29/06/2022 | 30 | SIMPLEX DRILLING CO. | 28.39 | 0 | 50
6549 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of low Land and temporary approach road entering 1st Tubewell site for SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000066/2023-2024 | 90/SWD-I | 06/04/2023 | 15 | CIVILEX COMBINE | 0.61 | 0 | 100
6550 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of low Land and temporary approach road entering 2nd Tubewell site SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000067/2023-2024 | 91/SWD-I | 06/04/2023 | 15 | CIVILEX COMBINE | 0.55 | 0 | 100
6551 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Shaksahar Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000227/2022-2023 | 1689/SWD-I | 01/11/2022 | 300 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 526.17 | 0 | 68
6552 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for Sinking of 01 (One) no. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achive 66 mtr. housing pipe by Rotary method for SHAKSAHAR PWSS at 2nd Tubewell site of Bhangar-I Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/0010765] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000292/2023-2024 | 1398/SWD-I | 13/07/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.57 | 0 | 100
6553 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of SHAKSAHAR Piped Water Suplly Scheme in BHANGAR-I Block in South 24-Pgns West Bengal, under South 24 Paraganas W/S Division-I, P.H.E. Dte. [SM/11275] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000509/2023-2024 | 2247/SWD-I | 13/09/2023 | 30 | MS KRISHNA MONDAL | 29.66 | 0 | 10
6554 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SHAKSAHAR PWSS within Bhangar-I Block "SHAKSAHAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/11275) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000757/2024-2025 | 4678/SWD-I | 18/11/2024 | 60 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 77.5 | 0 | 0
6555 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000020/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 13.92 | 0 | 0
6556 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 2689/SWD-I | 20/01/2023 | 0 | Resource Division | 15.91 | 0 | 0
6557 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05023/2023-2024 | BP-2023-24-570 | 12/03/2024 | 0 | WBSEDCL | 8.55 | 0 | 0
6558 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Purba Gabberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000557/2022-2023 | 546/SMD | 21/02/2023 | 953 | DEBJYOTI BASU | 19.37 | 0 | 91
6559 | S24 Pgns Mechanical | Baruipur Sub-Division | Modified and Allied Electro-Mechanical works at Pump House no-1 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002275/2024-2025 | 1554/SMSD | 26/11/2024 | 15 | DEBJYOTI BASU | 0.94 | 0 | 0
6560 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply and delivery of actuator & Butter fly valve due to some modification held at Pump House no-1 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002276/2024-2025 | 1553/SMSD | 26/11/2024 | 15 | DEBJYOTI BASU | 0.99 | 0 | 0
6561 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Purba Gabberia Zone-I W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I)[SM/11277] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002277/2024-2025 | 17/SMSD | 06/01/2025 | 15 | DEBJYOTI BASU | 0.59 | 0 | 0
6562 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-I PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010747] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 41/SWD-I | 06/04/2023 | 15 | K P CONSTRUCTION | 4.41 | 0 | 100
6563 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-I) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000156/2022-2023 | 1409/SWD-I | 22/09/2022 | 60 | NIRMAN | 11.01 | 0 | 100
6564 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-I) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010747] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000243/2022-2023 | 1686/SWD-I | 01/11/2022 | 30 | K P CONSTRUCTION | 42.29 | 0 | 90
6565 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-I) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1909) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000274/2022-2023 | 1808/SWD-I | 09/11/2022 | 1200 | PASCON | 449.74 | 0 | 65
6566 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PURBA GABBERIA(I) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000364/2021-2022 | 1929/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
6567 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000069/2023-2024 | 291/SWD-I | 24/04/2023 | 0 | Resource Division | 240.21 | 0 | 0
6568 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Tripura Nagar (Ramgopalpur) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000470/2022-2023 | 3941/SMD | 30/12/2022 | 90 | COOLING CARE CENTER | 11.19 | 0 | 100
6569 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Tripura Nagar (Ramgopalpur) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002204/2023-2024 | 1422/SMSD | 21/11/2023 | 15 | COOLING CARE CENTER | 0.9 | 0 | 100
6570 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of of Tripuranagar (Ramgopalpur) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12058) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002793/2023-2024 | 1628/SMSD | 29/12/2023 | 15 | COOLING CARE CENTER | 0.29 | 0 | 100
6571 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for RAMGOPALPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000092/2022-2023 | 1204/SWD-I | 02/09/2022 | 30 | PAPPU ENTERPRISE | 20.06 | 0 | 100
6572 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at RAMGOPALPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 566] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000098/2022-2023 | 1209/SWD-I | 02/09/2022 | 942 | MONDAL CONSTRUCTION | 91.26 | 0 | 98
6573 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at RAMGOPALPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012521] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000120/2022-2023 | 1288/SWD-I | 14/09/2022 | 60 | LAKSHMI IRON | 5.44 | 0 | 100
6574 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMGOPALPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000205/2021-2022 | 1918/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
6575 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 01 (One) no. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for RAMGOPALPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/012521] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000454/2023-2024 | 2109/SWD-I | 30/08/2023 | 15 | PAPPU ENTERPRISE | 2.2 | 0 | 100
6576 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based RAMGOPALPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12058) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000907/2023-2024 | 1206/SWD-I | 11/03/2024 | 630 | S.S. CONSULTANCY & CONSTRUCTION | 21.03 | 0 | 55
6577 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000273/2023-2024 | 2418/SWD-I | 30/09/2023 | 0 | Resource Division | 4.19 | 0 | 0
6578 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000337/2023-2024 | 270/SWD-I | 10/01/2024 | 0 | Resource Division | 3.04 | 0 | 0
6579 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kaikhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000486/2022-2023 | 239/SMD | 24/01/2023 | 90 | M/S. PS & ASSOCIATES | 25.92 | 0 | 0
6580 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
6581 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kaikhali PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11730) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000267/2024-2025 | 2682/SWD-I | 07/06/2024 | 45 | SHRAYA ROADS LINE. | 52.47 | 0 | 10
6582 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KAIKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000409/2022-2023 | 466/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 0 | 100
6583 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KAIKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11730) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000433/2022-2023 | 2577/SWD-I | 10/01/2023 | 60 | N&N ENTERPRISE | 6.04 | 0 | 0
6584 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KAIKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 790 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000447/2022-2023 | 2685/SWD-I | 20/01/2023 | 90 | M/S BIMALENDU BOSE | 122.59 | 0 | 82
6585 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011788] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000521/2022-2023 | 2911/SWD-I | 14/02/2023 | 15 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0
6586 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KAIKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11730] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000585/2023-2024 | 2753/SWD-I | 07/11/2023 | 30 | SAIKAT ENTERPRISE | 15.03 | 0 | 20
6587 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for KAIKHALI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11730] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000691/2024-2025 | 4486/SWD-I | 30/10/2024 | 60 | DEV & COMPANY | 15.9 | 0 | 95
6588 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of BISHNUPUR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11730] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000784/2023-2024 | 1067/SWD-I | 04/03/2024 | 15 | SAIKAT ENTERPRISE | 1.57 | 0 | 0
6589 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000104/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.27 | 0 | 0
6590 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of Quotation for new service connection at Gangrai PWSS PH No- 2 under Bishnupur-I Block. Application No- 1008248827 Application Date- 09-12-2024 Reference ID- 106855997 Memo No- 1008248827/Quot/03 | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/02238/2024-2025 | BP-2024-25-511 | 19/12/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
6591 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/03347/2023-2024 | BP-2023-24-369 | 08/11/2023 | 0 | WBSEDCL | 4.3 | 0 | 0
6592 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/04003/2023-2024 | BP-2023-24-412 | 13/12/2023 | 0 | WBSEDCL | 5.56 | 0 | 0
6593 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Gangarai Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/002237/2023-2024 | 8-AE-II-SMD | 03/01/2024 | 15 | PS & ASSOCIATES | 0.58 | 0 | 100
6594 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Upliftment of operational condition by providing necessary luminaires, LED Board, chair & table etc. at P.H. No. 1 under Gangarai Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-I) (SM/11732) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/002457/2023-2024 | 208-AE-II-SMD | 28/02/2024 | 15 | SOMNATH ENTERPRISE | 0.75 | 0 | 100
6595 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of GANGRAI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000095/2023-2024 | 452/SWD-I | 04/05/2023 | 60 | A.M. ENTERPRISE (BASIRHAT) | 6.04 | 0 | 100
6596 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for GANGARAI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000174/2022-2023 | 1449/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.26 | 0 | 100
6597 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
6598 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of GANGRAL AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000233/2021-2022 | 1976/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
6599 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for GANGARAI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000268/2024-2025 | 2919/SWD-I | 25/06/2024 | 45 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 86.61 | 0 | 0
6600 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based GANGRAI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 882 nos.] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000417/2022-2023 | 2471/SWD-I | 30/12/2022 | 748 | MS BUILDWELL | 125.23 | 0 | 80
6601 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GANGRAI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011791] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000526/2022-2023 | 2921/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 0 | 100
6602 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for GANGRAI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000693/2024-2025 | 4488/SWD-I | 30/10/2024 | 122 | M/S. SHYAM CONSTRUCTION | 15.53 | 0 | 100
6603 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000030/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.43 | 0 | 0
6604 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000113/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.5 | 0 | 0
6605 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000399/2022-2023 | 3800/SMD | 29/12/2022 | 90 | KUNDU ELECTRICAL ENTERPRISE | 17.48 | 0 | 0
6606 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000409/2023-2024 | 2498/SMD | 14/06/2023 | 90 | M/S. G.P ENTERPRISE | 21.62 | 0 | 0
6607 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2 of Ramchandranagar (Part-II) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000410/2023-2024 | 2499/SMD | 14/07/2023 | 90 | M/S. G.P ENTERPRISE | 21.62 | 0 | 0
6608 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 51.00m), Service Road (length = 15.00m), Development of Land, Construction of Pump House (4.80 Mtr. X 3.60 Mtr.) at TW-2 site and Pump House (5.40 Mtr. X 3.60 Mtr.) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000010/2025-2026 | 934/SWD-I | 07/04/2025 | 60 | SUBHO CONSTRUCTION | 19.99 | 0 | 0
6609 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-II) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000297/2022-2023 | 1883/SWD-I | 16/11/2022 | 30 | MERAJUL ALAM | 29.97 | 0 | 0
6610 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Land development, Construction of Boundary wall (length = 204.00m) & Construction of Service Road (length = 140.00m) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000365/2024-2025 | 3510/SWD-I | 07/08/2024 | 45 | PRONICON INDIA | 54.27 | 0 | 0
6611 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-II) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000394/2022-2023 | 408/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 0 | 0
6612 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-II) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1580] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000490/2022-2023 | 2820/SWD-I | 03/02/2023 | 1243 | NEW ALIGNMENT | 384.03 | 0 | 40
6613 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar (II) PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014755] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000629/2022-2023 | 3256/SWD-I | 02/03/2023 | 15 | MERAJUL ALAM | 3.14 | 0 | 0
6614 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Repairing of Damaged road by Laying of pipe line for Ground water based RAMCHANDRANAGAR (Part-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000674/2024-2025 | 4463/SWD-I | 29/10/2024 | 60 | MOTIONMASS TECHNO OPC PVT LTD | 21.67 | 0 | 0
6615 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000195/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 25.52 | 0 | 0
6616 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Uttar Damodarpur having village with maximum 114 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001128/2022-2023 | 8772/AD | 21/12/2022 | 60 | MD. NAZRUL ISLAM GAZI | 32.85 | 0 | 0
6617 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000876/2023-2024 | 783/AD | 03/02/2024 | 0 | Resource Division | 0.7 | 0 | 0
6618 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Uttar Damodarpur Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000606/2022-2023 | 697/SMD | 13/03/2023 | 90 | P.K. ENTERPRISE | 8.81 | 0 | 0
6619 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Durgapur Station Road to Hotor and Mahespur connecting Road from 0.0 Km to 2.4 Km under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.65,08,952/- x 50% = Rs.32,54,476/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00564/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 32.54 | 0 | 0
6620 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Interconnection including laying distribution system from Big dia Tube well covering Chandanpukur, Bagdaha, Dhanberia, Durgapur & Gazipur mouzas for improvement of water supply & Providing functional house hold tap connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000303/2020-2021 | 2132/SWD-I | 26/02/2021 | 120 | ALOK ENTERPRISE | 169.36 | 0 | 100
6621 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Protection work by drum sheet walling on Sal-bullah / Eucaliptus bullah piling for protection of rising main at chandanpukur site of shikharbali-II G.P under Baruipur Sub-Division of South24-Pgns, W/S Division-I, P.H.E.Dte. | AE BSD |  | ORD/000996/2022-2023 | 1079/SWD-I | 16/08/2022 | 15 | MONDAL CONSTRUCTION (BARUIPUR) | 1.18 | 0 | 100
6622 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Alipore RWS Sub-Division, Alipore Division, P.H.E. Dte. for (WB-19G-0520) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/03557/2023-2024 | BP-2023-24-1264 | 27/03/2024 | 0 | AVIK HALDER | 1.87 | 0 | 0
6623 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Ramratanpur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000146/2023-2024 | 145/KSD | 30/05/2023 | 20 | MANDAL ENTERPRISE (JOYNAGAR) | 4.63 | 0 | 89
6624 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Ramratanpur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2022-2023 | 5918/AD | 19/10/2022 | 15 | HARIDAS DUTTA | 3.64 | 0 | 90
6625 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Ramratanpur Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001294/2020-2021 | 2276/AD | 12/10/2020 | 365 | SARADA CONSTRUCTION | 59.73 | 48.32 | 95
6626 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
6627 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000278/2023-2024 | 3077/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6628 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000837/2023-2024 | 682/AD | 30/01/2024 | 0 | Resource Division | 6.26 | 0 | 0
6629 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Ramratanpur W/S Scheme (Phase-A), Koaberia W/S Scheme (Phase-A), Ramtanunagar W/S Scheme (Phase-A) & Shibkalinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[W/O NO. 513/AD, 20.08.21, T.NO. 1755/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | VCH/002608/2021-2022 | BP-2021-22-511 | 22/03/2022 | 0 | M/S R.DUTTA & CO. | 4.7 | 0 | 0
6630 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Zone-VI at Mandirbazar block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. (TSM/010830) [10th SLSSC (2021-22)] | AE HQ-I |  | ORD/000770/2022-2023 | 3644/SWD-I | 28/03/2023 | 825 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 192.73 | 0 | 55
6631 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000055/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 19.44 | 0 | 0
6632 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Mrityunjounagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000145/2023-2024 | 144/KSD | 30/05/2023 | 10 | M/S. JAYDEEP DASGUPTA | 2.16 | 0 | 100
6633 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Mrityunjoynagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000276/2022-2023 | 3688/AD | 02/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.95 | 0 | 100
6634 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MRITYUNJAYNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000482/2022-2023 | 1976/AD | 20/06/2022 | 45 | VOYAGER | 4.86 | 0 | 100
6635 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works and Construction of 01 no. Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000626/2022-2023 | 5979/AD | 20/10/2022 | 90 | M/S. JAYDEEP DASGUPTA | 129.4 | 0 | 100
6636 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001140/2022-2023 | 9079/AD | 27/12/2022 | 90 | M/S RAKESH ENTERPRISE | 129.2 | 0 | 100
6637 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Boundary Wall Painting, Repair and OHR Cat Ladder at 1st Tubewell site for Mritunjaynagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11698) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002161/2024-2025 | 171/KSD | 11/01/2025 | 142 | M/S THREE STAR & CO. | 3.82 | 0 | 100
6638 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
6639 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Mrityunjaynagar W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002284/2023-2024 | 920/AD | 08/02/2024 | 30 | NEPAL CHANDRA PRADHAN | 11.88 | 0 | 100
6640 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works and Construction Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002299/2023-2024 | 898/AD | 07/02/2024 | 45 | M/S. JAYDEEP DASGUPTA | 40.43 | 0 | 100
6641 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000045/2022-2023 | 3911/AD | 12/08/2022 | 0 | Resource Division | 59.91 | 0 | 0
6642 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000091/2022-2023 | 5592/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
6643 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000339/2023-2024 | 3154/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6644 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000900/2023-2024 | 886/AD | 07/02/2024 | 0 | Resource Division | 28.17 | 0 | 0
6645 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01792/2022-2023 | BP-2022-23-458 | 23/03/2023 | 0 | WBSEDCL | 0.76 | 0 | 0
6646 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Mrityunjaynagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000346/2022-2023 | 3750/SMD | 29/12/2022 | 90 | J.K. ENGINEERING CO. | 10.95 | 0 | 100
6647 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Mrityunjaynagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002140/2023-2024 | 995-AE-I-SMD | 13/09/2023 | 15 | J.K. ENGINEERING CO. | 0.9 | 0 | 0
6648 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/04617/2023-2024 | BP-2023-24-478 | 02/02/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
6649 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Salpukuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000506/2022-2023 | 341/SMD | 08/02/2023 | 90 | STANDARD ENGINEERING | 25.69 | 0 | 0
6650 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SALPUKURIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000178/2022-2023 | 1453/SWD-I | 26/09/2022 | 30 | DIPALI CONSTRUCTION | 14.26 | 0 | 5
6651 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/05/2023 to 30/09/2023) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000180/2023-2024 | 333/SWD-I | 25/04/2023 | 153 | NIRMAL UDYOG | 0.73 | 0 | 30
6652 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
6653 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of SALPUKURIA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000226/2021-2022 | 1971/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.69 | 0 | 100
6654 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, Pump house, laying of additional pipeline and other allied works for SALPUKURIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000249/2024-2025 | 2669/SWD-I | 07/06/2024 | 45 | BHASKAR MONDAL | 72.69 | 0 | 5
6655 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SALPUKURIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 910 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000416/2022-2023 | 2470/SWDI | 30/12/2022 | 90 | BHASKAR MONDAL | 179.64 | 0 | 90
6656 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SALPUKURIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11783) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000429/2022-2023 | 2574/SWD-I | 10/01/2023 | 60 | LAKSHMI IRON | 6.04 | 0 | 87
6657 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SALPUKURIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011734] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000520/2022-2023 | 2910/SWD-I | 14/02/2023 | 15 | DIPALI CONSTRUCTION | 1.57 | 0 | 0
6658 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SALPUKURIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011734] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000593/2022-2023 | 3113/SWD-I | 24/02/2023 | 30 | DEBASHIS DAS | 15.87 | 0 | 98
6659 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/10/2023 to 29/02/2024) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000623/2023-2024 | 2388/SWD-I | 27/09/2023 | 152 | NIRMAL UDYOG | 0.72 | 0 | 99
6660 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Salpukuria Piped Water Supply Scheme for 1st Tubewell site in the Arsenic affected areas of South 24-Parganas Water Supply Division-I, PHE Dte. (SM/11783) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000749/2023-2024 | 525/SWD-I | 29/01/2024 | 15 | KALAM ENTERPRISE | 3.35 | 0 | 99
6661 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for SALPUKURIA Piped Water Supply Scheme in BISHNUPUR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000789/2023-2024 | 1072/SWD-I | 04/03/2024 | 271 | MONDAL TUBEWELL | 15.9 | 0 | 98
6662 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2024 to 31/08/2024) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000909/2023-2024 | 917/SWD-I | 21/02/2024 | 184 | NIRMAL UDYOG | 0.87 | 0 | 70
6663 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/09/2024 to 28/02/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001063/2024-2025 | 3766/SWD-I | 28/08/2024 | 181 | NIRMAL UDYOG | 0.86 | 0 | 70
6664 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2025 to 31/08/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001204/2024-2025 | 581/SWD-I | 25/02/2025 | 184 | NIRMAL UDYOG | 0.87 | 0 | 0
6665 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000027/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.61 | 0 | 0
6666 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000100/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.31 | 0 | 0
6667 | Alipore Division | Baruipur Sub-Division | Road restoration Construction of road mom Kanlokhal Bazar lo Begampur Colony Ghalonika Bridge | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01705/2024-2025 | BP-2024-25-790 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.5 | 0 | 0
6668 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00286/2023-2024 | BP-2023-24-19 | 15/05/2023 | 0 | WBSEDCL | 6.66 | 0 | 0
6669 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/04229/2023-2024 | BP-2023-24-435 | 27/12/2023 | 0 | WBSEDCL | 4 | 0 | 0
6670 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/04708/2023-2024 | BP-2023-24-521 | 17/02/2024 | 0 | WBSEDCL | 17.79 | 0 | 0
6671 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Purba Begampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000445/2022-2023 | 3925/SMD | 30/12/2022 | 1279 | M/S. S.R. ENTERPRISE | 22.37 | 0 | 45
6672 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Purba Begampur (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001397/2024-2025 | 78/SMSD | 17/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.91 | 0 | 0
6673 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Purba Begampur (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001398/2024-2025 | 77/SMSD | 17/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.58 | 0 | 0
6674 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for PURBO BEGAMPUR (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000081/2022-2023 | 1192/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 0 | 100
6675 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000302/2024-2025 | 3215/SWD-I | 18/07/2024 | 60 | SRIJON ENTERPRISE | 36.54 | 0 | 0
6676 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BEGAMPUR (ZONE-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1967) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000344/2022-2023 | 2149/SWD-I | 08/12/2022 | 1028 | GHOSH ENTERPRISE | 557.87 | 0 | 90
6677 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Begampur (Zone-I) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000364/2022-2023 | 2207/SWD-I | 13/12/2022 | 60 | PRAGATI CONSTRUCTION AND CO. | 11.51 | 0 | 0
6678 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000445/2021-2022 | 1951/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
6679 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BEGAMPUR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000455/2021-2022 | 1951/SWD_I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
6680 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PURBA BEGAMPUR [Zone-I] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11748] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000805/2023-2024 | 1290/SWD-I | 15/03/2024 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
6681 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000857/2023-2024 | 1249/SWD-I | 13/03/2024 | 45 | SRIJON ENTERPRISE | 43.44 | 0 | 0
6682 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000086/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 12.85 | 0 | 0
6683 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-IV water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000572/2022-2023 | 597/SMD | 27/02/2023 | 90 | AHALYA ENGINEERING WORKS | 22.93 | 0 | 45
6684 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kamaria (Zone-IV) W/S Scheme under SMD, P.H.E. Dte. (Block-Janagar-I) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002406/2023-2024 | 1495/SMSD | 05/12/2023 | 15 | AHALYA ENGINEERING WORKS | 0.48 | 0 | 100
6685 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-IV) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000084/2022-2023 | 1195/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 0 | 100
6686 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-IV) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000278/2022-2023 | 1841/SWD-I | 11/11/2022 | 300 | MANASH GHOSH | 411.42 | 0 | 50
6687 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAMARIA (IV) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000362/2021-2022 | 1964/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
6688 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Kamaria (Zone-IV) of Jaynagar-I Block uunder Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000382/2022-2023 | 2215/SWD-I | 13/12/2022 | 60 | ALISHA CONSTRUCTION | 11.52 | 0 | 50
6689 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-IV PWSS of Joynagar-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011004] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000743/2022-2023 | 3587/SWD-I | 23/03/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
6690 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscelleneous work for KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11788) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000912/2023-2024 | 1202/SWD-I | 11/03/2024 | 630 | BANGA NIRMAN | 16.78 | 0 | 30
6691 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000078/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 13.73 | 0 | 0
6692 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell,construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kamarchak having village with maximum 91 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001736/2022-2023 | 11765/AD | 21/02/2023 | 60 | BARI ENTERPRISE | 32.29 | 0 | 0
6693 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000869/2023-2024 | 776/AD | 03/02/2024 | 0 | Resource Division | 0.56 | 0 | 0
6694 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kamarchak Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000604/2022-2023 | 695/SMD | 13/03/2023 | 90 | M/S. BABUSONA ENTERPRISE | 8.85 | 0 | 0
6695 | Alipore Division | Diamond Harbour Sub-Division | Repairing of Pump House no-1 under Zone-XIII of Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000330/2025-2026 | 269/DHSD | 16/06/2025 | 45 | M.P. ENTERPRISE (II) | 1.2 | 0 | 0
6696 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system with allied works to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XIII at Kulpi block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 3170] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000373/2023-2024 | 1768/AD | 26/07/2023 | 615 | K.P. CONSTRUCTION | 634.65 | 0 | 60
6697 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XIII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001046/2022-2023 | 298/DHSD | 15/09/2022 | 30 | RAMKRISHNA CHAKRABORTY | 3.03 | 0 | 100
6698 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000144/2022-2023 | 14/AD | 05/04/2023 | 0 | Resource Division | 52.38 | 0 | 0
6699 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000201/2023-2024 | 1623/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
6700 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000217/2023-2024 | 2028/AD | 05/08/2023 | 0 | Resource Division | 2.69 | 0 | 0
6701 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000426/2023-2024 | 3614/AD | 30/10/2023 | 0 | Resource Division | 19.53 | 0 | 0
6702 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-XII under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001018/2024-2025 | 4929/AD | 03/12/2024 | 60 | M/S. JHARNA ENTERPRISE | 77.72 | 0 | 0
6703 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001024/2022-2023 | 297/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 2.96 | 0 | 0
6704 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000125/2022-2023 | 12800/AD | 16/03/2023 | 0 | Resource Division | 19.82 | 0 | 0
6705 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000143/2022-2023 | 13/AD | 05/04/2023 | 0 | Resource Division | 21 | 0 | 0
6706 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000627/2023-2024 | 288/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
6707 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000854/2023-2024 | 761/AD | 03/02/2024 | 0 | Resource Division | 3.97 | 0 | 0
6708 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new connection at pump house no-1 of Garia water supply scheme (Baruipur Block) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01898/2024-2025 | BP-2024-25-481 | 28/11/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
6709 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Garia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13443) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000261/2025-2026 | 505/SMSD | 04/04/2025 | 15 | DEBJYOTI BASU | 0.58 | 0 | 0
6710 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Garia W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13443) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000263/2025-2026 | 705/SMSD | 08/05/2025 | 15 | DEBJYOTI BASU | 0.93 | 0 | 0
6711 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Garia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000479/2022-2023 | 232/SMD | 24/01/2023 | 860 | DEBJYOTI BASU | 26.02 | 0 | 40
6712 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13443) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000303/2024-2025 | 3216/SWD-I | 18/07/2024 | 60 | TIRUPATI ENTERPRISES | 36.67 | 0 | 0
6713 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GARIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000311/2021-2022 | 1955/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 100
6714 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for GARIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13443] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000567/2022-2023 | 3063/SWD-I | 21/02/2023 | 30 | M/S MONDAL ENTERPRISE | 31.75 | 0 | 50
6715 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional House Hold Tap Connection (FHTC) alongwith construction of Chlorine Room (two nos.) for Augmentation of GARIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC = 1970] [TSM/015205] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000626/2023-2024 | 20/SWD-I | 05/04/2023 | 1080 | TIRUPATI ENTERPRISES | 360.05 | 0 | 85
6716 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000140/2022-2023 | 3423/SWD-I | 13/03/2023 | 0 | Resource Division | 12.14 | 0 | 0
6717 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000190/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 22.21 | 0 | 0
6718 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Sibnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000126/2024-2025 | 2404/AD | 07/06/2024 | 30 | P & S ASSOCIATES | 11.73 | 0 | 0
6719 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Sibnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000206/2023-2024 | 789/AD | 24/05/2023 | 469 | M/S. BOSE CONCERN | 48.91 | 0 | 50
6720 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
6721 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Sibnagar W/S Scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000593/2024-2025 | 4058/AD | 01/10/2024 | 45 | M/S SOURAV MAHAPATRA | 32.15 | 0 | 0
6722 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Sibnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000831/2025-2026 | 2082/AD | 30/04/2025 | 30 | SARADA CONSTRUCTION | 26.06 | 0 | 0
6723 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SIBNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001040/2022-2023 | 4155/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.14 | 0 | 100
6724 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 200 cum. capacity OHR of Sibnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002068/2023-2024 | 764(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6725 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
6726 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000116/2023-2024 | 652/AD | 17/05/2023 | 0 | Resource Division | 10.98 | 0 | 0
6727 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000464/2023-2024 | 4760/AD | 19/12/2023 | 0 | Resource Division | 16.8 | 0 | 0
6728 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000750/2023-2024 | 585/AD | 29/01/2024 | 0 | Resource Division | 1.97 | 0 | 0
6729 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Sibnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000383/2022-2023 | 3786/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE (DOMKAL) | 19.34 | 0 | 0
6730 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Kedarpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13845) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000456/2024-2025 | 3414/AD | 21/08/2024 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 46.54 | 0 | 0
6731 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KEDARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000990/2022-2023 | 4151/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.59 | 0 | 100
6732 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kedarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001059/2023-2024 | 3378/AD | 11/10/2023 | 45 | DEBASIS JANA | 27.6 | 0 | 0
6733 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kedarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001310/2022-2023 | 9893/AD | 09/01/2023 | 45 | MANDAL CONSTRUCTION | 38.6 | 0 | 90
6734 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kedarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 972] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001879/2022-2023 | 12422/AD | 09/03/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 284.95 | 0 | 25
6735 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
6736 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Kedarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002155/2023-2024 | 801/AD | 05/02/2024 | 45 | M/S SNEHALATA ENTERPRISE | 11.73 | 0 | 100
6737 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kedarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/003144/2023-2024 | 382/KSD | 20/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6738 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000107/2023-2024 | 643/AD | 17/05/2023 | 0 | Resource Division | 5.34 | 0 | 0
6739 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000496/2023-2024 | 4961/AD | 22/12/2023 | 0 | Resource Division | 33.79 | 0 | 0
6740 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000751/2023-2024 | 586/AD | 29/01/2024 | 0 | Resource Division | 0.96 | 0 | 0
6741 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000955/2023-2024 | 1689/AD | 22/03/2024 | 0 | Resource Division | 0.47 | 0 | 0
6742 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Kedarpur PH-2 W/ S Scheme Application No:- 1007977598 Reference ID: 106692950 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/01210/2024-2025 | BP-2024-25-256 | 12/08/2024 | 0 | WBSEDCL | 2.48 | 0 | 0
6743 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03492/2023-2024 | BP-2023-24-378 | 13/11/2023 | 0 | WBSEDCL | 2.47 | 0 | 0
6744 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kedarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000387/2022-2023 | 3790/SMD | 29/12/2022 | 908 | AHALYA ENGINEERING WORKS | 18.75 | 0 | 40
6745 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Kedarpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001907/2023-2024 | 1192/SMD | 22/03/2024 | 21 | AHALYA ENGINEERING WORKS | 10.87 | 0 | 95
6746 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Gobindapur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001160/2023-2024 | 3722/AD | 03/11/2023 | 30 | NEPAL CHANDRA PRADHAN | 9.43 | 0 | 100
6747 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001314/2022-2023 | 9897/AD | 10/01/2023 | 30 | M/S NAIYA & MAITY | 19.06 | 0 | 100
6748 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GOBINDPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001342/2022-2023 | 3800/AD | 05/08/2022 | 45 | LEMNISCATE | 0.6 | 0 | 100
6749 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution & FHTC for 1 year after completion of FHTC works for Gobindapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001425/2023-2024 | 4604/AD | 14/12/2023 | 90 | M/S. LOKNATH CONSTRUCTION | 62.37 | 0 | 0
6750 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000589/2023-2024 | 88/AD | 03/01/2024 | 0 | Resource Division | 1.57 | 0 | 0
6751 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Gobindapur Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000601/2022-2023 | 678/SMD | 10/03/2023 | 90 | M/S. SABITRI ENTERPRISE | 8.93 | 0 | 0
6752 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Jamalpur W/S Scheme for habitations of Jamalpur Mouza and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000113/2020-2021 | 1415/SWD-I | 14/12/2020 | 120 | J.D. CONSTRUCTION | 80.07 | 68.61 | 0
6753 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Jamalpur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6138) Part -G | AE SWSD-I |  | ORD/000469/2022-2023 | 2781/SWD-I | 31/01/2023 | 45 | M/S ASHA ENGINEERING | 2.27 | 0 | 100
6754 | Alipore Division | South 24 Pgs. W/S Division - I | Road restoration of Harishankarpur Bharat Ghosh more to Dakshin Mukundapur Under Magrahal II PS | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/01668/2024-2025 | BP-2024-25-775 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.36 | 0 | 0
6755 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Harisankarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/003028/2022-2023 | 362/SMD | 10/02/2023 | 90 | CINZANO | 33.51 | 0 | 30
6756 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Additional Electro-Mechanical works for PH No-1 of Harisankarpur W/S Scheme under South 24-Pgs Mechanical Division, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/003115/2023-2024 | 166/SMSD | 05/02/2024 | 451 | CINZANO | 0.96 | 0 | 90
6757 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road edge and Hard shoulder damaged due to laying of pipes by PHE Dte. of Dakshin Barasat Mograhat Usthi Road from 0.00 kmp to 21.0 kmp in different stretched of Diamond Harbour Highway Sub-Division under Diamond Harbour Highway Division in the district of South 24 Parganas | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/00653/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 20.8 | 0 | 0
6758 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of Pipeline for distribution system of HARISANKARPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000085/2025-2026 | 1760/SWD-I | 02/07/2025 | 60 | BAIDYA ENTERPRISE | 51.8 | 0 | 0
6759 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method at Harisankarpur 2nd & 3rd Tubewell site for HARISANKARPUR Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/14643] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000093/2025-2026 | 1768/SWD-I | 02/07/2025 | 30 | PADMA ENGINEERING CO. | 38.27 | 0 | 0
6760 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
6761 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Drum Sheet walling on Eucalyptus bullah pilling for laying of HDPE pipeline for HARISANKARPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000261/2024-2025 | 2676/SWD-I | 07/06/2024 | 450 | SOMNATH ENTERPRISE | 12.74 | 0 | 75
6762 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of approach Road inside of the head work site and construction of entrance gate for Harishankarpur PWSS to accommodate FHTC in Magrahat-II block South 24-Parganas district. for augmentation of surface water Based water Supply Scheme in the arsenic Affected areas of South 24-Parganas District. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000427/2024-2025 | 3784/SWD-I | 29/08/2024 | 30 | N & N ENTERPRISE | 6.5 | 0 | 50
6763 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Harisankarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000984/2022-2023 | 1477/SWD-I | 27/09/2022 | 30 | MEASURE LAND | 2.76 | 0 | 100
6764 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional estimate for construction of approach road inside of the Head work site for existing HARISANKARPUR PWSS under MAGRAHAT-II Block, South 24 Parganas Distnct for Augmentation of surfacc water based water supply scheme in the Arsenic affected areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/001078/2024-2025 | 5346/SWD-I | 30/12/2024 | 15 | N & N ENTERPRISE | 3 | 0 | 60
6765 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000199/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 60.24 | 0 | 0
6766 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000311/2023-2024 | 2737/SWD-I | 06/11/2023 | 0 | Resource Division | 18.95 | 0 | 0
6767 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ramdebpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 766] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000265/2023-2024 | 3828/AD | 07/11/2023 | 300 | CHANDAN ROY | 172.49 | 0 | 0
6768 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001060/2023-2024 | 3386/AD | 11/10/2023 | 45 | DEB ASSOCIATE | 27.5 | 0 | 0
6769 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001212/2023-2024 | 3869/AD | 09/11/2023 | 30 | SOMNATH ENTERPRISE | 9.47 | 0 | 70
6770 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramdebpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001722/2022-2023 | 11748/AD | 21/02/2023 | 45 | MODERN CONSTRUCTION (NEW) | 38.59 | 0 | 100
6771 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramdebpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001788/2022-2023 | 3694/AD | 02/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 2.63 | 0 | 95
6772 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
6773 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 60 | CHANDAN ROY | 60.06 | 0 | 0
6774 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000117/2023-2024 | 653/AD | 17/05/2023 | 0 | Resource Division | 4.21 | 0 | 0
6775 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000462/2023-2024 | 4761/AD | 19/12/2023 | 0 | Resource Division | 20.06 | 0 | 0
6776 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000573/2023-2024 | 74/AD | 03/01/2024 | 0 | Resource Division | 0.73 | 0 | 0
6777 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000958/2023-2024 | 1692/AD | 22/03/2024 | 0 | Resource Division | 7.32 | 0 | 0
6778 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/05691/2023-2024 | BP-2023-24-608 | 28/03/2024 | 0 | WBSEDCL | 10.32 | 0 | 0
6779 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramdebpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000871/2022-2023 | 364/SMD | 10/02/2023 | 962 | KAMAKHYA ENTERPRISE | 18.56 | 0 | 20
6780 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/04090/2023-2024 | BP-2023-24-417 | 16/12/2023 | 0 | WBSEDCL | 19.28 | 0 | 0
6781 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Punpo water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000580/2022-2023 | 615/SMD | 02/03/2023 | 90 | CONCORD ENGINEERING | 19.48 | 0 | 45
6782 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Punpo W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | Junior Engineer | ORD/003120/2023-2024 | 237/SMSD | 16/02/2024 | 15 | CONCORD ENGINEERING | 0.78 | 0 | 0
6783 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Punpo W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | Junior Engineer | ORD/003121/2023-2024 | 236/SMSD | 16/02/2024 | 15 | CONCORD ENGINEERING | 0.78 | 0 | 0
6784 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 0 | 15
6785 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PUNPO Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000293/2021-2022 | 1925/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 0
6786 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for PUNPO PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000501/2022-2023 | 2890/SWD-I | 13/02/2023 | 30 | IQBAL CONSTRUCTION (EMAIL ID- AANPI8149M@GMAIL.COM) | 31.77 | 0 | 50
6787 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000088/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 32.55 | 0 | 0
6788 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000139/2022-2023 | 3422/SWD-I | 13/03/2023 | 0 | Resource Division | 10.39 | 0 | 0
6789 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/05030/2023-2024 | BP-2023-24-564 | 11/03/2024 | 0 | WBSEDCL | 0.47 | 0 | 0
6790 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Benipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000411/2022-2023 | 3809/SMD | 29/12/2022 | 90 | ORIENTAL ENGINEERING CO. | 33.43 | 0 | 25
6791 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Benipur W/S Scheme under SMD, P.H.E. Dte. (Block-Mograhat-II) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/002824/2023-2024 | 118/SMSD | 25/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.62 | 0 | 0
6792 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, service road & toilet for pump house at 3rd Tube well site for BENIPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [SM/14659] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000027/2025-2026 | 979/SWD-I | 09/04/2025 | 135 | MAHABUB RAHAMAN LASKAR | 11.79 | 0 | 60
6793 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of Additional Pipeline for distribution system for BENIPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District (SM/14659) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000086/2025-2026 | 1761/SWD-I | 02/07/2025 | 45 | AHANA ENTERPRISE | 13.36 | 0 | 0
6794 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BENIPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017337] (2nd Call) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000093/2023-2024 | 450/SWD-I | 04/05/2023 | 90 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 47.69 | 0 | 66
6795 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
6796 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall, construction of service road and land development with protection work at 2nd Tubewell site for BENIPUR PWSS under Gokarnee G.P within Mograhat-II Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [Length - 43.0 mtr.] (SM/14659) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000684/2024-2025 | 4479/SWD-I | 30/10/2024 | 300 | R.K ENTERPRISE | 12.01 | 0 | 75
6797 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Culvert for the approach road of proposed 2nd Tube well site for "Ground water bascd BENIPUR piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas District for Augmentation of Surface water based water supply scheme In the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dte. (SM/14659) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000714/2024-2025 | 4544/SWD-I | 06/11/2024 | 180 | SAMIR GIRI | 11.52 | 0 | 85
6798 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Benipur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000985/2022-2023 | 1482/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.92 | 0 | 100
6799 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000162/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 64.27 | 0 | 0
6800 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000310/2023-2024 | 2735/SWD-I | 06/11/2023 | 0 | Resource Division | 15.99 | 0 | 0
6801 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Banberia ( Zone-40) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000009/2023-2024 | 944/SMD | 04/04/2023 | 90 | ORIENTAL ENGINEERING CO. | 43.1 | 0 | 0
6802 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Banberia (Zone-40) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000131/2025-2026 | 702/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
6803 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-4 of Banberia (Zone-40) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000132/2025-2026 | 703/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
6804 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Banberia (Zone-40) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000134/2025-2026 | 692/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
6805 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Banberia (Zone-40) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000135/2025-2026 | 691/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
6806 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BANBERA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2949] [TSM/018364] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 842/SWD-I | 05/06/2023 | 90 | RELIABLE CONSTRUCTIONS | 349.93 | 0 | 85
6807 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (four) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BANBERA (Zone-40) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000445/2024-2025 | 3895/SWD-I | 04/09/2024 | 213 | ASIT PRAMANIK | 63.43 | 0 | 50
6808 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground Water based BANBERA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/14858) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000717/2024-2025 | 4551/SWD-I | 06/11/2024 | 45 | SANA ENTERPRISE | 73.31 | 0 | 0
6809 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based BANBERIA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000923/2022-2023 | 1176/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 3.01 | 0 | 100
6810 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000144/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
6811 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000081/2023-2024 | 27/DHSD | 25/04/2023 | 184 | SUMAN HALDER | 2.4 | 0 | 0
6812 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 89.87 | 0 | 100
6813 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2023 to 30/09/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001268/2023-2024 | 449/DHSD | 29/09/2023 | 366 | M.P. ENTERPRISE (II) | 4.8 | 0 | 0
6814 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 2510] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001397/2022-2023 | 10869/AD | 04/02/2023 | 900 | PROJECT & MAINTENANCE | 197.45 | 0 | 80
6815 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000133/2022-2023 | 23/AD | 05/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
6816 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000233/2023-2024 | 2194/AD | 10/08/2023 | 0 | Resource Division | 15.42 | 0 | 0
6817 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000347/2023-2024 | 3211/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
6818 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000892/2023-2024 | 746/AD | 03/02/2024 | 0 | Resource Division | 15.46 | 0 | 0
6819 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000913/2023-2024 | 1255/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
6820 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-I at Diamond Harbour-I block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14476] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000983/2024-2025 | 4854/AD | 29/11/2024 | 180 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 118.31 | 0 | 40
6821 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-I at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 3240] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001396/2022-2023 | 10868/AD | 04/02/2023 | 900 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 252.48 | 0 | 70
6822 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000230/2023-2024 | 2191/AD | 10/08/2023 | 0 | Resource Division | 19.34 | 0 | 0
6823 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000352/2023-2024 | 3216/AD | 04/10/2023 | 0 | Resource Division | 0.52 | 0 | 0
6824 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000889/2023-2024 | 743/AD | 03/02/2024 | 0 | Resource Division | 19.34 | 0 | 0
6825 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000074/2023-2024 | 58/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6826 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-I PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000075/2023-2024 | 59/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6827 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different households for Augmentation of Bishnupur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone- I & II) (SM/13117) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000337/2024-2025 | 2751/AD | 27/06/2024 | 45 | M/S. S.S. ENTERPRISE | 109.19 | 0 | 100
6828 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Bishnupur W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000541/2023-2024 | 359/KSD | 09/08/2023 | 565 | S.K.GOLUI | 3.55 | 0 | 100
6829 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 2 nos. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000621/2023-2024 | 2431/AD | 22/08/2023 | 60 | M/S. S.S. ENTERPRISE | 119.53 | 0 | 50
6830 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000769/2022-2023 | 6524/AD | 11/11/2022 | 90 | M/S. SARADA UDYOG | 104.36 | 0 | 100
6831 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000770/2022-2023 | 6525/AD | 11/11/2022 | 45 | SIMPLEX DRILLING CO. | 45.84 | 0 | 100
6832 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000771/2022-2023 | 6526/AD | 11/11/2022 | 30 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.02 | 0 | 100
6833 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000772/2022-2023 | 6527/AD | 11/11/2022 | 30 | M/S. PAPIYA ENTERPRISE | 6.89 | 0 | 98
6834 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BISHNUPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001056/2022-2023 | 4647/AD | 06/09/2022 | 45 | VOYAGER | 11.73 | 0 | 100
6835 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Bishnupur (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001418/2023-2024 | 4598/AD | 14/12/2023 | 30 | M/S. S.S. ENTERPRISE | 12.53 | 0 | 100
6836 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
6837 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002173/2023-2024 | 811/AD | 05/02/2024 | 45 | M/S SUNITY ENTERPRISE | 33.71 | 0 | 100
6838 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002174/2023-2024 | 812/AD | 05/02/2024 | 30 | M/S SWAPAN KUMAR PRADHAN | 11.77 | 0 | 100
6839 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000328/2023-2024 | 3143/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
6840 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000497/2023-2024 | 4823/AD | 20/12/2023 | 0 | Resource Division | 83.64 | 0 | 0
6841 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000543/2023-2024 | 27/AD | 02/01/2024 | 0 | Resource Division | 6.09 | 0 | 0
6842 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000684/2023-2024 | 454/AD | 24/01/2024 | 0 | Resource Division | 10.97 | 0 | 0
6843 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00017/2023-2024 | BP-2023-24-35 | 18/05/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
6844 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00379/2023-2024 | BP-2023-24-55 | 09/06/2023 | 0 | WBSEDCL | 0.87 | 0 | 0
6845 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Bishnupur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000342/2022-2023 | 3746/SMD | 29/12/2022 | 90 | SIPRA ENTERPRISE | 23.13 | 0 | 80
6846 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at Zone-I&II, PH-1&2 of Bishnupur Augmentation W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001790/2023-2024 | 1027/AE-I/SMD | 20/09/2023 | 15 | M/S. GLOBAL POWER CONCERN | 0.82 | 0 | 100
6847 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-1 of Bishnupur Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002305/2023-2024 | 906-AE-I-SMD | 11/08/2023 | 15 | SIPRA ENTERPRISE | 0.9 | 0 | 100
6848 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-2 of Bishnupur Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002306/2023-2024 | 907-AE-I-SMD | 11/08/2023 | 15 | SIPRA ENTERPRISE | 0.9 | 0 | 100
6849 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - III) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000657/2022-2023 | 6678/AD | 14/11/2022 | 85 | S.S. ENTERPRISE (I) | 43.3 | 0 | 84
6850 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001899/2022-2023 | 5663/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.37 | 0 | 0
6851 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000168/2023-2024 | 1121/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
6852 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00391/2023-2024 | BP-2023-24-51 | 09/06/2023 | 0 | WBSEDCL | 5.83 | 0 | 0
6853 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-III) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000588/2022-2023 | 649/SMD | 03/03/2023 | 90 | B. P. CONSTRUCTION | 8.85 | 0 | 100
6854 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01495/2023-2024 | BP-2023-24-177 | 02/08/2023 | 0 | WBSEDCL | 6.92 | 0 | 0
6855 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Madhabpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000504/2022-2023 | 329/SMD | 07/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 22.58 | 0 | 100
6856 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Madhabpur PH-1 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002281/2023-2024 | 1635/SMSD | 04/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 100
6857 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Madhabpur PH-2 , under Bhangar-I block water supply scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002282/2023-2024 | 1636/SMSD | 04/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 100
6858 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-I & 2 of Madhabpur water supply scheme under South 24 Pgs Mechanical Division PHE Dte.[ Block- Bhangar-I ] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002399/2023-2024 | 22/SMSD | 05/01/2024 | 15 | ARPAN CONSTRUCTION | 0.78 | 0 | 100
6859 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no- 1 & 2 of Madhabpur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13778) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/003141/2023-2024 | 52/SMSD | 11/01/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.58 | 0 | 0
6860 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.38] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00468/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 30.72 | 0 | 0
6861 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1996] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000064/2023-2024 | 243/SWD-I | 20/04/2023 | 300 | ASSOCIATED CONSTRUCTION AND CONSULTANCY | 449.98 | 0 | 35
6862 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for MADHABPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015478] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000628/2022-2023 | 3237/SWD-I | 01/03/2023 | 30 | MRA NIRMAN UDYOG | 31.77 | 0 | 100
6863 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and other allied works at HW & 2nd Tubewell site of "MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13778) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000675/2024-2025 | 4464/SWD-I | 29/10/2024 | 45 | REALIENCE CONSTRUCTION | 91.13 | 0 | 0
6864 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000057/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 9.67 | 0 | 0
6865 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000223/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.3 | 0 | 0
6866 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00620/2023-2024 | BP-2023-24-90 | 14/06/2023 | 0 | WBSEDCL | 0.08 | 0 | 0
6867 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3, & 4 for Augmentation of Mallikpur Part-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000060/2023-2024 | 1054/SMD | 18/04/2023 | 90 | M/S. S.S. ENTERPRISE | 50.65 | 0 | 0
6868 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Mallickpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000480/2022-2023 | 233/SMD | 24/01/2023 | 90 | DEBJYOTI BASU | 33.34 | 0 | 0
6869 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1718] [TSM/012612] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 482/SWD-I | 08/05/2023 | 90 | RANJIT KAR | 161.99 | 0 | 0
6870 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-III Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000204/2021-2022 | 1920/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
6871 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLICKPUR (PART-III) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13444] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 3065/SWD-I | 21/02/2023 | 30 | MD NURUZZUMAN (EMAIL ID- MDNGRPKR@GMAIL.COM) | 47.64 | 0 | 34
6872 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000166/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 42.16 | 0 | 0
6873 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/04675/2023-2024 | BP-2023-24-511 | 12/02/2024 | 0 | WBSEDCL | 11.18 | 0 | 0
6874 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Brindakhali-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000477/2022-2023 | 3948/SMD | 30/12/2022 | 823 | DEBJYOTI BASU | 22.21 | 0 | 40
6875 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Brindakhali (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13309) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001391/2024-2025 | 1691/SMSD | 24/12/2024 | 15 | DEBJYOTI BASU | 0.91 | 0 | 0
6876 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Brindakhali (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/13309) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001392/2024-2025 | 1689/SMSD | 24/12/2024 | 15 | DEBJYOTI BASU | 0.58 | 0 | 0
6877 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.28] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00488/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 11.1 | 0 | 0
6878 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-I) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1773) [TSM/015376] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000062/2023-2024 | 366/SWD-I | 27/04/2023 | 976 | M/S V.P. JAIN | 395.19 | 0 | 98
6879 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BRINDAKHALI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000509/2021-2022 | 1942/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 0 | 100
6880 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BRINDAKHALI-I PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13309] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000562/2022-2023 | 3059/SWD-I | 21/02/2023 | 30 | ABDUL LOTIB MOLLA | 31.76 | 0 | 50
6881 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000127/2022-2023 | 3328/SWD-I | 09/03/2023 | 0 | Resource Division | 10.92 | 0 | 0
6882 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000186/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 28.44 | 0 | 0
6883 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Surendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13799) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000168/2024-2025 | 2519/AD | 15/06/2024 | 45 | SIMPLEX DRILLING CO. | 40.38 | 0 | 0
6884 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Purba Surendranagar W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13799) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000454/2024-2025 | 3412/AD | 21/08/2024 | 60 | FIDERE MARINE SERVICES PVT. LTD. | 65.8 | 0 | 0
6885 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA SURENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000983/2022-2023 | 3667/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.53 | 0 | 100
6886 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Surendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000984/2023-2024 | 3003/AD | 26/09/2023 | 45 | M/S MA BILASINI CONSTRUCTION | 27.16 | 0 | 0
6887 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Surendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000985/2023-2024 | 3004/AD | 26/09/2023 | 30 | NARAYAN ENTERPRISE | 9.49 | 0 | 65
6888 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Purba Surendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001876/2022-2023 | 12419/AD | 09/03/2023 | 90 | M/S. SARADA UDYOG | 129.3 | 0 | 55
6889 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Purba Surendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 910] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001878/2022-2023 | 12421/AD | 09/03/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 251 | 0 | 40
6890 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
6891 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000095/2023-2024 | 541/AD | 12/05/2023 | 0 | Resource Division | 9.94 | 0 | 0
6892 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000509/2023-2024 | 4944/AD | 22/12/2023 | 0 | Resource Division | 44.12 | 0 | 0
6893 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000745/2023-2024 | 580/AD | 29/01/2024 | 0 | Resource Division | 1.79 | 0 | 0
6894 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000951/2023-2024 | 1685/AD | 22/03/2024 | 0 | Resource Division | 0.57 | 0 | 0
6895 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Purba Surendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000367/2022-2023 | 3771/SMD | 29/12/2022 | 90 | GOENKA ENTERPRISE | 22.38 | 0 | 0
6896 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Surendraganj PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13974) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000184/2024-2025 | 2544/AD | 18/06/2024 | 75 | GROWING CONCERN | 91.83 | 0 | 100
6897 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000962/2023-2024 | 285(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6898 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Surendraganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001087/2023-2024 | 3554/AD | 17/10/2023 | 30 | SARADA CONSTRUCTION | 49.21 | 0 | 100
6899 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [DAKSHIN SURENDRAGANJ PWSS] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001329/2022-2023 | 3311/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.53 | 0 | 100
6900 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Dakshin Surendraganj W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001843/2023-2024 | 131/AD | 05/01/2024 | 60 | BIMALENDU GIRI | 36.15 | 0 | 100
6901 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
6902 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002165/2023-2024 | 808/AD | 05/02/2024 | 391 | TANMAY ROY CHOWDHURY | 33.34 | 0 | 100
6903 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002166/2023-2024 | 809/AD | 05/02/2024 | 360 | TIYASHA ENTERPRISE | 11.73 | 0 | 100
6904 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000113/2023-2024 | 649/AD | 17/05/2023 | 0 | Resource Division | 8.43 | 0 | 0
6905 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000299/2023-2024 | 3094/AD | 28/09/2023 | 0 | Resource Division | 18.61 | 0 | 0
6906 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000473/2023-2024 | 4758/AD | 19/12/2023 | 0 | Resource Division | 21.21 | 0 | 0
6907 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000680/2023-2024 | 446/AD | 24/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
6908 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000758/2023-2024 | 593/AD | 29/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
6909 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/03494/2023-2024 | BP-2023-24-377 | 13/11/2023 | 0 | WBSEDCL | 3.37 | 0 | 0
6910 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/03524/2023-2024 | BP-2023-24-387 | 23/11/2023 | 0 | WBSEDCL | 3.36 | 0 | 0
6911 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Surendraganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000376/2022-2023 | 3780/SMD | 29/12/2022 | 926 | R.N.S. TRADING | 19.48 | 0 | 45
6912 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Dakshin Surendraganj W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001903/2023-2024 | 1188/SMD | 22/03/2024 | 408 | R.N.S. TRADING | 8.35 | 0 | 90
6913 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Purba Dwarokapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000381/2023-2024 | 1774/AD | 26/07/2023 | 706 | SUPRITI ENTERPRISE | 54.89 | 0 | 50
6914 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Purba Dwarokapur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13867) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000455/2024-2025 | 3413/AD | 21/08/2024 | 60 | S.S. ENTERPRISE (II) | 65.96 | 0 | 0
6915 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Purba Dwarokapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000964/2023-2024 | 287(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6916 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA DWAROKAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001032/2022-2023 | 4152/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.96 | 0 | 100
6917 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Dwarokapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001723/2022-2023 | 11749/AD | 21/02/2023 | 45 | NATIONAL ENTERPRISE | 38.58 | 0 | 100
6918 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Purba Dwarokapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 900] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001787/2022-2023 | 11558/AD | 17/02/2023 | 1049 | M/S. SUMAN ENTERPRISE | 272.92 | 0 | 60
6919 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
6920 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Dwarokapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002157/2023-2024 | 802/AD | 05/02/2024 | 606 | S.S. ENTERPRISE (II) | 27.9 | 0 | 0
6921 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Dwarokapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002280/2023-2024 | 916/AD | 08/02/2024 | 263 | M/S RADHAKRISHNA CONSTRUCTION | 9.71 | 0 | 96
6922 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000108/2023-2024 | 644/AD | 17/05/2023 | 0 | Resource Division | 6.7 | 0 | 0
6923 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000495/2023-2024 | 4962/AD | 22/12/2023 | 0 | Resource Division | 20.42 | 0 | 0
6924 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000752/2023-2024 | 587/AD | 29/01/2024 | 0 | Resource Division | 1.2 | 0 | 0
6925 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000956/2023-2024 | 1690/AD | 22/03/2024 | 0 | Resource Division | 0.47 | 0 | 0
6926 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/05692/2023-2024 | BP-2023-24-610 | 28/03/2024 | 0 | WBSEDCL | 12.15 | 0 | 0
6927 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Purba Dwarokapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000385/2022-2023 | 3788/SMD | 29/12/2022 | 90 | S.P. CONSTRUCTION | 18.51 | 0 | 95
6928 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Purba Dwarikapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13867] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002210/2024-2025 | 1047-AE-II-SMD | 20/08/2024 | 15 | S.P. CONSTRUCTION | 0.83 | 0 | 0
6929 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Purba Dwarakapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13867] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002211/2024-2025 | 1046-AE-II-SMD | 20/08/2024 | 15 | S.P. CONSTRUCTION | 0.83 | 0 | 0
6930 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gopalnagar Uttar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000159/2023-2024 | 681/AD | 17/05/2023 | 45 | ARBINA ENTERPRISE | 28.27 | 0 | 0
6931 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gopalnagar Uttar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000160/2023-2024 | 682/AD | 17/05/2023 | 30 | CHATTERJEE ENTERPRISES | 9.65 | 0 | 100
6932 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Gopalnagar Uttar W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000314/2023-2024 | 190/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 99
6933 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000379/2023-2024 | 1772/AD | 26/07/2023 | 70 | MOUMITA ENTERPRISE | 39.62 | 0 | 100
6934 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Gopalnagar Uttar W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000586/2023-2024 | 2343/AD | 18/08/2023 | 587 | RELIABLE CONSTRUCTIONS | 34.49 | 0 | 50
6935 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials of Gopalnagar Uttar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000719/2023-2024 | 2536/AD | 28/08/2023 | 60 | RELIABLE CONSTRUCTIONS | 5.5 | 0 | 100
6936 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gopalnagar Uttar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000910/2023-2024 | 269(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6937 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GOPALNAGAR UTTAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000981/2022-2023 | 4146/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.4 | 0 | 100
6938 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Gopalnagar Uttar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001269/2023-2024 | 4214/AD | 29/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.3 | 0 | 100
6939 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Gopalnagar Uttar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001308/2022-2023 | 9891/AD | 10/01/2023 | 45 | MANDAL CONSTRUCTION | 38.6 | 0 | 100
6940 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001507/2022-2023 | 11025/AD | 08/02/2023 | 902 | RELIABLE CONSTRUCTIONS | 174.79 | 0 | 50
6941 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 950] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001541/2022-2023 | 11026/AD | 08/02/2023 | 1059 | RELIABLE CONSTRUCTIONS | 174.69 | 0 | 82
6942 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
6943 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000085/2023-2024 | 531/AD | 12/05/2023 | 0 | Resource Division | 8.79 | 0 | 0
6944 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000525/2023-2024 | 4934/AD | 22/12/2023 | 0 | Resource Division | 18.65 | 0 | 0
6945 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000582/2023-2024 | 54/AD | 03/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
6946 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Uttar Gopalnagar PH-1 W/ S Scheme Application No:- 1007514425 Reference ID: 106460083 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/01813/2024-2025 | BP-2024-25-462 | 29/10/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
6947 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/05021/2023-2024 | BP-2023-24-566 | 11/03/2024 | 0 | WBSEDCL | 5.63 | 0 | 0
6948 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at of Gopalnagar Uttar PH-2 W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000603/2024-2025 | 758-AE-I-SMD | 31/05/2024 | 15 | SAIKAT ENTERPRISE | 0.89 | 0 | 0
6949 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/04622/2023-2024 | BP-2023-24-481 | 07/02/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
6950 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Bhatipota PH-1 under Bhangar-I Block water supply scheme under SMD,PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000082/2024-2025 | 458/SMSD | 16/04/2024 | 15 | ORIENTAL ENGINEERING CO. | 0.89 | 0 | 100
6951 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bhatipota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000501/2022-2023 | 319/SMD | 06/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 23.51 | 0 | 45
6952 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | "ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division." | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00497/2024-2025 |  | 13/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 12.1 | 0 | 0
6953 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | 50% Payment for ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00534/2024-2025 | BP-2024-25-308 | 18/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.05 | 0 | 0
6954 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road Side Flank damaged by PHE Department under Bhojerhat Pipe Line Project from 3,872 km to 4.195 km (Left Side) 3.475 km to 4.095km (RS) [Total Length - 943.00m] under South 24 Parganas Highway Division" | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00546/2024-2025 | BP-2024-25-338 | 25/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.23 | 0 | 0
6955 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Kolkata Basanti Road from 12.427 km to 15.581 km, Permanent restoration work , damaged due to " Pipeline Laying of 90mm,140mm, & 225mm dia HDPE Pipoe Line along road flank by PHE Department " within Alipore Highway Sub-Division under South 24 Parganas Highway Division in the District of South 24 Parganas. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00850/2024-2025 | BP-2024-25-504 | 11/12/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.92 | 0 | 0
6956 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000260/2024-2025 | 2857/SWD-I | 20/06/2024 | 275 | BOSE ENTERPRISES | 164.67 | 0 | 45
6957 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under TARDAH KAPASATI, BHATIPOTA, KHARAMBA & SHERPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18501, SM/13341, SM/18545 & SM/18500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000508/2024-2025 | 3977/SWD-I | 11/09/2024 | 45 | TELETONE INDIA PRIVATE LIMITED | 107.09 | 0 | 100
6958 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of distribution Network System for different dia HDPE pipe under Bhatipota PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000617/2023-2024 | 2801/SWD-I | 09/11/2023 | 60 | K.K. BUILDER. | 34.34 | 0 | 55
6959 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BHATIPOTA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015204] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000621/2022-2023 | 3235/SWD-I | 01/03/2023 | 30 | SETABUR RAHAMAN | 31.67 | 0 | 50
6960 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000710/2022-2023 | 3527/SWD-I | 17/03/2023 | 787 | K.K. BUILDER. | 465.21 | 0 | 70
6961 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (Two) nos. Pipe Carrying Structure- Near Bhatipota OHR Site over 56.0 mtr. width canal and Near Kolkata-Basanti Highway,opp. Kolkata Leather Complex Police Station over 66.0 mtr. width canal within Bhatipota Mouza of Tardaha GP under Bhangar-I Block, BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000738/2023-2024 | 523/SWD-I | 29/01/2024 | 45 | GANAPATI ENTERPRISE | 31.83 | 0 | 100
6962 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000765/2024-2025 | 4686/SWD-I | 18/11/2024 | 60 | K.K. BUILDER | 23.12 | 0 | 52
6963 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000049/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.02 | 0 | 0
6964 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000217/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 11.96 | 0 | 0
6965 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000121/2024-2025 | 2399/AD | 07/06/2024 | 45 | SARADA CONSTRUCTION | 50.92 | 0 | 100
6966 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Upendranagar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13828) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000663/2024-2025 | 4212/AD | 23/10/2024 | 60 | SARADA CONSTRUCTION | 135.89 | 0 | 0
6967 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Upendranagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000963/2023-2024 | 286(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6968 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000977/2023-2024 | 2996/AD | 26/09/2023 | 45 | DEBASIS JANA | 33.33 | 0 | 0
6969 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000978/2023-2024 | 2997/AD | 26/09/2023 | 30 | M/S KHAJABABA ENTERPRISE | 11.7 | 0 | 0
6970 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (UPENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001036/2022-2023 | 3670/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.24 | 0 | 100
6971 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 150] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001505/2022-2023 | 10991/AD | 07/02/2023 | 810 | SARADA CONSTRUCTION | 174.6 | 0 | 80
6972 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001542/2022-2023 | 11027/AD | 08/02/2023 | 90 | SARADA CONSTRUCTION | 173.65 | 0 | 25
6973 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1084] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002063/2022-2023 | 13005/AD | 23/03/2023 | 90 | SARADA CONSTRUCTION | 163.54 | 0 | 50
6974 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002083/2022-2023 | 13256/AD | 31/03/2023 | 45 | PRADIP KUMAR JATI | 46.55 | 0 | 0
6975 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
6976 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000090/2023-2024 | 536/AD | 12/05/2023 | 0 | Resource Division | 9.53 | 0 | 0
6977 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000519/2023-2024 | 4939/AD | 22/12/2023 | 0 | Resource Division | 19.36 | 0 | 0
6978 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000584/2023-2024 | 58/AD | 03/01/2024 | 0 | Resource Division | 1.65 | 0 | 0
6979 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000948/2023-2024 | 1682/AD | 22/03/2024 | 0 | Resource Division | 1.98 | 0 | 0
6980 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Upendranagar PH-2 W/S Scheme Application No:- 1007199954 Reference ID: 106233535 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01205/2024-2025 | BP-2024-25-259 | 12/08/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
6981 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Upendranagar PH-1 W/S Scheme Application No:- 1007199920 Reference ID: 106233519 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/01206/2024-2025 | BP-2024-25-260 | 12/08/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
6982 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Upendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000798/2022-2023 | 332/SMD | 07/02/2023 | 1747 | TRIDENT ENTERPRISE | 21.95 | 0 | 80
6983 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Upendranagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/13828) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002335/2024-2025 | 1822-AE-II-SMD | 28/01/2025 | 15 | TRIDENT ENTERPRISE | 0.9 | 0 | 100
6984 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Upendranagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/13828) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002336/2024-2025 | 1821-AE-II-SMD | 28/01/2025 | 15 | TRIDENT ENTERPRISE | 0.9 | 0 | 100
6985 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gopalnagar Uttar Zone-I W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000151/2023-2024 | 637/AD | 17/05/2023 | 45 | MOUMITA ENTERPRISE | 28.64 | 0 | 0
6986 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gopalnagar Uttar Zone-I W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000152/2023-2024 | 638/AD | 17/05/2023 | 30 | JOY GURU BUILDERS | 9.59 | 0 | 0
6987 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Gopalnagar Uttar Zone I W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000192/2024-2025 | 2552/AD | 18/06/2024 | 45 | MANASH GHOSH | 50.94 | 0 | 0
6988 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Gopalnagar Uttar Zone I W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/15524) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000375/2024-2025 | 3001/AD | 19/07/2024 | 75 | MANASH GHOSH | 240.67 | 0 | 0
6989 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. Pump House for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000420/2024-2025 | 3071/AD | 25/07/2024 | 45 | MONDAL ENTERPRISE (NEW) | 11.18 | 0 | 0
6990 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Gopalnagar Uttar Zone-I W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001005/2023-2024 | 509/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.73 | 0 | 0
6991 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001777/2022-2023 | 11501/AD | 15/02/2023 | 895 | M/S ACME ENTERPRISE | 11.94 | 0 | 50
6992 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar, Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001778/2022-2023 | 11502/AD | 15/02/2023 | 50 | M/S MODINA ENTERPRISE | 16.93 | 0 | 100
6993 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002057/2022-2023 | 12651/AD | 13/03/2023 | 300 | MANASH GHOSH | 466.39 | 0 | 50
6994 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Gopalnagar Uttar Zone-I PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002075/2023-2024 | 772(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
6995 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =325] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002078/2022-2023 | 13127/AD | 27/03/2023 | 905 | M/S CHANDIMATA CONSTRUCTION | 105.76 | 0 | 60
6996 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
6997 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st tubewell site of Gopalnagar Uttar (Zone-I) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15524) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003646/2024-2025 | 3155/AD | 29/07/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0
6998 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000086/2023-2024 | 532/AD | 12/05/2023 | 0 | Resource Division | 11.73 | 0 | 0
6999 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000523/2023-2024 | 4935/AD | 22/12/2023 | 0 | Resource Division | 25.44 | 0 | 0
7000 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000764/2023-2024 | 598/AD | 29/01/2024 | 0 | Resource Division | 6.31 | 0 | 0
7001 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000944/2023-2024 | 1678/AD | 22/03/2024 | 0 | Resource Division | 31.52 | 0 | 0
7002 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Gopalnagar Uttar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000388/2022-2023 | 3791/SMD | 29/12/2022 | 90 | ALPHA ENTERPRISE | 22.35 | 0 | 0
7003 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gopalnagar Uttar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002690/2023-2024 | 1152/SMD | 24/04/2023 | 90 | SAIKAT ENTERPRISE | 21.42 | 0 | 45
7004 | Alipore Division | Raidighi Sub-Division | Payment against "Restoration of Purba Bishnupur Raidighi Road (MDR) 11Km-15.5Km), under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Raidighi Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 264(W)/618G, Dt. 19.02.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | BILL/01576/2024-2025 | BP-2024-25-889 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 71.65 | 0 | 0
7005 | Alipore Division | Raidighi Sub-Division | Remodeling of Distribution System of Krishnachandrapur PWS Scheme as Zone-III of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000034/2022-2023 | 597/AD | 28/04/2022 | 30 | M/S B.M. CONSTRUCTION | 95.84 | 0 | 50
7006 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
7007 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works of piped water supply at Zone - III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2023-2024 | 484/AD | 10/05/2023 | 45 | M/S B.M. CONSTRUCTION | 95.36 | 0 | 40
7008 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Zone-III, Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 255 Nos.) [Part - D] | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000118/2023-2024 | 487/AD | 10/05/2023 | 315 | TIYASHA ENTERPRISE | 70.74 | 0 | 98
7009 | Alipore Division | Raidighi Sub-Division | Construction of 550 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- III of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000343/2023-2024 | 1455/AD | 13/07/2023 | 300 | M/S SUMAN SHIL | 205.1 | 0 | 0
7010 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000879/2024-2025 | 4662/AD | 20/11/2024 | 45 | M/S B.M. CONSTRUCTION | 25.39 | 0 | 0
7011 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001964/2022-2023 | 12718/AD | 14/03/2023 | 30 | M/S B.M. CONSTRUCTION | 30.56 | 0 | 50
7012 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000006/2024-2025 | 5161/AD | 12/12/2024 | 0 | Resource Division | 30.8 | 0 | 0
7013 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000634/2023-2024 | 238/AD | 15/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
7014 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Singheswar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001815/2022-2023 | 12155/AD | 01/03/2023 | 45 | SNEHA CONSTRUCTION | 19.9 | 0 | 0
7015 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Singheswar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001816/2022-2023 | 12156/AD | 01/03/2023 | 45 | GHOSH CONSTRUCTION | 7.09 | 0 | 96
7016 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (410 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Singheswar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002312/2023-2024 | 1065/AD | 21/02/2024 | 282 | RAKTIM ENTERPRISE | 35.55 | 0 | 93
7017 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000020/2023-2024 | 226/AD | 24/04/2023 | 0 | Resource Division | 23.13 | 0 | 0
7018 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/04034/2023-2024 | BP-2023-24-411 | 13/12/2023 | 0 | WBSEDCL | 6.27 | 0 | 0
7019 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Singeshwar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000040/2023-2024 | 1000/SMD | 10/04/2023 | 90 | A.G.ENTERPRISE | 11.15 | 0 | 95
7020 | S24 Pgns Mechanical | Canning Sub-division | Supply & Installation of LED board at PH-1 of Singheswar (Aug) water supply scheme under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000109/2024-2025 | 529/SMSD | 29/04/2024 | 15 | SOHINI ENTERPRISE | 0.39 | 0 | 100
7021 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Augmentation of Singeshwar PH-1, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002254/2023-2024 | 168/SMSD | 05/02/2024 | 15 | A.G.ENTERPRISE | 0.88 | 0 | 0
7022 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- II block for House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002389/2024-2025 | 636/AD | 18/02/2025 | 30 | K.P. CONSTRUCTION | 12.8 | 0 | 0
7023 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000884/2023-2024 | 758/AD | 03/02/2024 | 0 | Resource Division | 4.74 | 0 | 0
7024 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000924/2023-2024 | 1266/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7025 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Dakshin Kashi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000052/2023-2024 | 1048/SMD | 17/04/2023 | 90 | GOENKA ENTERPRISE | 26.03 | 0 | 0
7026 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DAKSHIN KASHI MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2171] [TSM/017968] | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 122/SWD-I | 12/04/2023 | 811 | KUDUCH MOLYA | 388.6 | 0 | 55
7027 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14870) | Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 3199/SWD-I | 16/07/2024 | 259 | KUDUCH MOLYA | 269.02 | 0 | 50
7028 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DAKSHIN KASHI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017968][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000688/2022-2023 | 3477/SWD-I | 15/03/2023 | 30 | MUNNA AGROTECH ENTERPRISE | 31.75 | 0 | 0
7029 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "DAKSHIN KASHI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000882/2022-2023 | 417/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 0 | 0
7030 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000202/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 22.78 | 0 | 0
7031 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Uttar Durgapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Joynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000045/2023-2024 | 1041/SMD | 17/04/2023 | 90 | WEST BENGAL ENGINEERING CO. | 35.49 | 0 | 0
7032 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR DURGAPUR PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017757] [2nd Call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000682/2022-2023 | 3482/SWD-I | 15/03/2023 | 30 | KHANDAKAR CONSTRUCTION | 47.64 | 0 | 100
7033 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14876) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000739/2024-2025 | 4637/SWD-I | 14/11/2024 | 45 | SANJAY ENTERPRISE | 82.6 | 0 | 0
7034 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Durgapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000953/2022-2023 | 1304/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.72 | 0 | 100
7035 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000097/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 45.58 | 0 | 0
7036 | Alipore Division | Sub-Division - II under South 24pgs W/s Division - I | Road restoration of Kesili to Ghola more Under Magrahat I | AE SWSD-II | JE4 | BILL/01704/2024-2025 | BP-2024-25-789 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.37 | 0 | 0
7037 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Initial 50% payment for the amount Rs. 4160934/- (forty-one lakh sixty thousand nine hundred & thirty four) only i.e. Rs. 2080467/- (twenty lakh eighty thousand four hundred & sixty-seven) only for restoration of road edge and hard shoulder damaged due to laying of pipeline of Dakshin Barasat to Usthi Road under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT and Zone -IX at Ghola Noapara under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16187 and SM/14725). | AE SWSD-II | JE4 | BILL/00801/2024-2025 | BP-2024-25-492 | 21/11/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 20.8 | 0 | 0
7038 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of R.C.C. Retaining wall for laying of 1422 mm dia MS Rising Main pipeline at Usthi bridge to extened the benefit of 100% Household in Zone-IX at GHOLANOAPARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist- South 24 Pgns. under South 24 Pgns Water Supply Division-I, PHE Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000004/2023-2024 | 27/SWD-I | 05/04/2023 | 60 | A.M. ENTERPRISE (BASIRHAT) | 8.92 | 0 | 0
7039 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of concrete road from the main road to the OHR Site of Zone-IX Ghola Noapara mouza of Mograhat-I Block under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-IX at GHOLA NOAPARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur district- South 24 Pgns. Under south 24 Pgns Water Supply Division-I, PHE Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000009/2023-2024 | 33/SWD-I | 05/04/2023 | 30 | ROYAL CONSTRUCTION | 16.77 | 0 | 100
7040 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
7041 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for Zone-IX,Ghola Noyapara (OHR Cap-700 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE4 | ORD/000310/2021-2022 | 2604/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 2.15 | 0 | 0
7042 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. (SM/14725) | AE SWSD-II | JE4 | ORD/000350/2024-2025 | 3444/SWD-I | 02/08/2024 | 90 | MANASH GHOSH | 294.26 | 0 | 0
7043 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Pathway, Surface Drain, Balance boundary wall, gate, plinth protection and internal works of G.L.R including necessary grouting & painting with other allied works at G.L.R. at Usthi in connection with Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in MOGRAHAT-I BLOCK within ¿Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District South 24 Parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000492/2022-2023 | 2858/SWD-I | 08/02/2023 | 60 | NIRMAL UDYOG | 45.61 | 0 | 100
7044 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of pipe carrying structure with laying of 355.6 mm dia M.S. Secondary Rising Main and 150 mm dia M.S. Distribution Main for crossing of Karbala Canal for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% household in Zone-IX at Ghola Noapara Usthi mouza of Magrahat-I block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Division-I, P.H.E Dte. (SM/ 14725) | AE SWSD-II | JE4 | ORD/000802/2023-2024 | 1274/SWD-I | 14/03/2024 | 30 | SRIJON ENTERPRISE | 50.64 | 0 | 98
7045 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-IX at GHOLA NOAPARA Mouza of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-IX at GHOLA NOAPARA of MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 5309 Nos.) | AE SWSD-II | JE4 | ORD/000803/2022-2023 | 3694/SWD-I | 30/03/2023 | 120 | MANASH GHOSH | 603.4 | 0 | 30
7046 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000066/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 51.28 | 0 | 0
7047 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01102/2023-2024 | BP-2023-24-146 | 24/07/2023 | 0 | WBSEDCL | 3.24 | 0 | 0
7048 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Tardaha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000340/2022-2023 | 3744/SMD | 29/12/2022 | 90 | MAA KALI ENTERPRISE | 22.34 | 0 | 40
7049 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Tardaha W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur)(SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002794/2023-2024 | 76/SMSD | 19/01/2024 | 15 | MAA KALI ENTERPRISE | 0.58 | 0 | 0
7050 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 1 of Tardaha W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur)(SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002795/2023-2024 | 77/SMSD | 19/01/2024 | 15 | MAA KALI ENTERPRISE | 0.89 | 0 | 100
7051 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no. 2 of Tardaha W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur)(SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002796/2023-2024 | 78/SMSD | 19/01/2024 | 15 | MAA KALI ENTERPRISE | 0.89 | 0 | 0
7052 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Rejuvenation / upgradation of Existing R.C.C. Reservoir of capacity 700 CUM and staging height 20 mtr at 2nd Tubewell site of "TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000013/2025-2026 | 965/SWD-I | 09/04/2025 | 45 | J.D. CONSTRUCTION | 11.09 | 0 | 0
7053 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway, Drain & others allied works at HW Site of " TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000233/2024-2025 | 2653/SWD-I | 07/06/2024 | 45 | MRA NIRMAN UDYOG | 13.19 | 0 | 0
7054 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR TARDAHA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016779) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000457/2022-2023 | 2748/SWD-I | 27/01/2023 | 30 | SAHI MASUM | 29.69 | 0 | 50
7055 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Earthwork in filling in Head Work Site with good earth for proposed TARDAHA Pipe water supply scheme to accommodate FHTC in Sonarpur Block under South 24 parganas, W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. under Jal Jeevan Mission.(SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000667/2023-2024 | 3017/SWD-I | 30/11/2023 | 15 | A S BUILDCON | 11.42 | 0 | 100
7056 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2297] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000675/2022-2023 | 3446/SWD-I | 13/03/2023 | 1025 | MRA NIRMAN UDYOG | 783.17 | 0 | 60
7057 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for TARDAHA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016779] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000720/2022-2023 | 3559/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 50
7058 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Upgradation of Pump house, Chlorine room, Office Room, Boundary wall, Land Development Construction of pathway, drain & other allied work of "TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000745/2024-2025 | 4667/SWD-I | 18/11/2024 | 60 | R.K ENTERPRISE | 19.12 | 0 | 0
7059 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for Head works site of TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (Length-150.0 mtr.) [SM/14488] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 554/SWD-I | 31/01/2024 | 45 | MONDAL ENTERPRISE (SANDESHKHALI-2) | 20.64 | 0 | 0
7060 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000032/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.83 | 0 | 0
7061 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000241/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 14.15 | 0 | 0
7062 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000815/2022-2023 | 6810/AD | 16/11/2022 | 30 | HARIDAS DUTTA | 19.49 | 0 | 95
7063 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000818/2022-2023 | 6813/AD | 16/11/2022 | 30 | M/S BHUNIA ENTERPRISE | 7.18 | 0 | 0
7064 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001840/2021-2022 | 679CSD | 18/08/2021 | 15 | HORIZEN | 1.99 | 0 | 100
7065 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001841/2021-2022 | 680/CSD | 18/08/2021 | 15 | HORIZEN | 3.19 | 0 | 100
7066 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000037/2021-2022 | 7033/AD | 31/03/2022 | 0 | Resource Division | 194.4 | 0 | 0
7067 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000391/2023-2024 | 332/AD | 19/01/2024 | 0 | Resource Division | 13.21 | 0 | 0
7068 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-I at Paschim Gobindapur of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8053]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000017/2023-2024 | 58/AD | 10/04/2023 | 900 | K.P. CONSTRUCTION | 866.96 | 0 | 84
7069 | Alipore Division | Diamond Harbour Sub-Division | Construction of Platform of size 600mm x 600mm (inner dimension) for the FHTC along with road restoration at Zone-I & Zone-III of Diamond Harbour-II Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part-III A / B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000042/2023-2024 | 177/AD | 19/04/2023 | 90 | PRONICON INDIA | 164.18 | 0 | 50
7070 | Alipore Division | Diamond Harbour Sub-Division | Preparation of re-design, drawing for fundation considering pile cap for group piles for the proposed R.C.C. Over Head Reservoir at (Zone-I, OHR Size-1000 Cum., Mouza - Paschim Gobindapur) and (Zone-VII, OHR Size-600 Cum., Mouza - Kamarpole) of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000366/2022-2023 | 199/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
7071 | Alipore Division | Diamond Harbour Sub-Division | Restoration by concreting of village road due to laying of pipeline within Zone-I under Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001180/2022-2023 | 11617/AD | 17/02/2023 | 570 | K.P. CONSTRUCTION | 87.56 | 0 | 90
7072 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000138/2022-2023 | 19/AD | 05/04/2023 | 0 | Resource Division | 96.26 | 0 | 0
7073 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000218/2023-2024 | 2102/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
7074 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000357/2023-2024 | 3221/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
7075 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000613/2023-2024 | 275/AD | 15/01/2024 | 0 | Resource Division | 49.28 | 0 | 0
7076 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000879/2023-2024 | 753/AD | 03/02/2024 | 0 | Resource Division | 0.33 | 0 | 0
7077 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 for Augmentation of Paruldaha (Zone-26) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000061/2023-2024 | 1055/SMD | 18/04/2023 | 90 | M/S. S.S. ENTERPRISE | 21.61 | 0 | 0
7078 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PARULDAHA (ZONE 26) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1030] [TSM/018359] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 963/SWD-I | 08/06/2023 | 927 | M/S B.N. ENTERPRISE | 231.58 | 0 | 80
7079 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based PARULDAHA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000926/2022-2023 | 1182/SWD-I | 01/09/2022 | 30 | ASTER CONSULTANCY | 2.82 | 0 | 100
7080 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000180/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 7.72 | 0 | 0
7081 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000286/2024-2025 | 2657/AD | 21/06/2024 | 45 | RABIUL GAZI | 7.07 | 0 | 0
7082 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000334/2023-2024 | 1551/AD | 17/07/2023 | 805 | M/S. MIHIR KUMAR NASKAR | 122.86 | 0 | 0
7083 | Alipore Division | Canning Sub-division | Additional work inter connection & distribution at Kalugachi W/S Scheme, Block- Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000350/2024-2025 | 722/CSD | 27/06/2024 | 30 | P.S. CONSTRUCTION | 2.26 | 0 | 0
7084 | Alipore Division | Canning Sub-division | Additional work for laying distribution in connection with FHTC work at AUGMENTATION AND RETROFITTING OF KALUGACHHI W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (SM/15478) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001016/2023-2024 | 3301/AD | 07/10/2023 | 30 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 10.97 | 0 | 90
7085 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kaluagachi W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001683/2022-2023 | 11490/AD | 15/02/2023 | 45 | R CONSTRUCTION | 7.11 | 0 | 0
7086 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001770/2022-2023 | 12043/AD | 27/02/2023 | 30 | ZINARUL ISLAM | 19.59 | 0 | 0
7087 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000005/2023-2024 | 116/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
7088 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000136/2023-2024 | 850/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
7089 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000262/2023-2024 | 3052/AD | 28/09/2023 | 0 | Resource Division | 85.12 | 0 | 0
7090 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 of Kalugachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000035/2023-2024 | 985/SMD | 05/04/2023 | 90 | SUDIP PRADHAN | 11.18 | 0 | 0
7091 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-I of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000014/2022-2023 | 211/AD | 11/04/2022 | 1335 | NITYANANDA MONDAL | 173.32 | 0 | 97
7092 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system, making structure for canal crossing and other allied works at Zone- I of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000063/2023-2024 | 343/AD | 28/04/2023 | 90 | SPA ENTERPRISE | 137.27 | 0 | 50
7093 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Mathurapur-II block (zone-I) for Mega surface water based water supply Scheme in 24 pgs (south) under Raidighi Sub Division of AD PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002155/2019-2020 | 7935/AD | 11/03/2020 | 2191 | MANGES INDUSTRIAL CORPORATION | 116.83 | 0 | 80
7094 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000653/2023-2024 | 257/AD | 15/01/2024 | 0 | Resource Division | 5.3 | 0 | 0
7095 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-IV & Head work site to PH-V of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000321/2023-2024 | 1547/AD | 17/07/2023 | 709 | SANKAR MONDAL | 132.1 | 0 | 100
7096 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Mouza-Baluijhaka and Bhaleya of Bhaleya Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001065/2021-2022 | 5300/AD | 04/01/2022 | 60 | M/S CHANDIMATA CONSTRUCTION | 33.22 | 0 | 98
7097 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001707/2022-2023 | 11671/AD | 20/02/2023 | 45 | BARUN KANTI PAUL | 7.09 | 0 | 0
7098 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001708/2022-2023 | 11672/AD | 20/02/2023 | 45 | R.G. ENTERPRISE (I) | 7.07 | 0 | 0
7099 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001813/2022-2023 | 12153/AD | 01/03/2023 | 45 | M.R.ENTERPRISE (II) | 39.03 | 0 | 0
7100 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bhaleya Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001944/2022-2023 | 11504/AD | 15/02/2023 | 45 | M/S. M.K. NASKAR & CONSTRUCTION | 2.6 | 0 | 95
7101 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation (Mondal Para) at Bhaleya Mouza of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002314/2020-2021 | 1520/CSD | 10/02/2021 | 30 | ADITYA SARDAR | 4.83 | 0 | 83
7102 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000249/2023-2024 | 3039/AD | 28/09/2023 | 0 | Resource Division | 81.05 | 0 | 0
7103 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000727/2023-2024 | 549/AD | 25/01/2024 | 0 | Resource Division | 111.53 | 0 | 0
7104 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Bhaleya PH-4 under Canning -I block (REF ID : 106692525) (APP ID: 1007977420) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01366/2024-2025 | BP-2024-25-325 | 31/08/2024 | 0 | WBSEDCL | 6.44 | 0 | 0
7105 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Bhaleya water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000028/2023-2024 | 973/SMD | 04/04/2023 | 90 | ORIENTAL ENGINEERING CO. | 23.45 | 0 | 0
7106 | Alipore Division | Raidighi Sub-Division | Providing FHTC and other allied works at Zone- V of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000065/2023-2024 | 195/AD | 19/04/2023 | 90 | G.B. CONSTRUCTION & CO. | 196.43 | 0 | 62
7107 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 3) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Raidighi W/S Scheme (Zone-V, Mathurapur-II Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000430/2023-2024 | 1918/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 99
7108 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-V of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001249/2021-2022 | 5822/AD | 07/02/2022 | 60 | G.B. CONSTRUCTION & CO. | 252.1 | 0 | 80
7109 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000649/2023-2024 | 252/AD | 15/01/2024 | 0 | Resource Division | 9.17 | 0 | 0
7110 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000097/2023-2024 | 453/AD | 08/05/2023 | 15 | UNIVERSAL CONSTRUCTION | 19.52 | 0 | 0
7111 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000123/2025-2026 | 2586/AD | 03/06/2025 | 30 | KHAN CONSTRUCTION (BASANTI) | 10.27 | 0 | 0
7112 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 2159] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001195/2023-2024 | 4045/AD | 22/11/2023 | 300 | SUPRITI ENTERPRISE | 648.45 | 0 | 30
7113 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001931/2022-2023 | 11804/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 6.53 | 0 | 95
7114 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001956/2022-2023 | 12692/AD | 14/03/2023 | 659 | BAPAN HALDAR | 8.88 | 0 | 100
7115 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sadhupur W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002033/2022-2023 | 13029/AD | 24/03/2023 | 60 | GIASHUDDIN CONSTRUCTION | 65.85 | 0 | 100
7116 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002039/2022-2023 | 13035/AD | 24/03/2023 | 680 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 100
7117 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002040/2022-2023 | 13036/AD | 24/03/2023 | 680 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 100
7118 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000059/2023-2024 | 379/AD | 02/05/2023 | 0 | Resource Division | 67.54 | 0 | 0
7119 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3, Zone-I for Augmentation of Sadhupur Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000293/2023-2024 | 2129/SMD | 31/05/2023 | 947 | SUBHRA ENTERPRISE | 29.32 | 0 | 90
7120 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Zone-I, Pump House-1,2, & 3 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001856/2024-2025 | 105/SMSD | 21/01/2025 | 15 | SUBHRA ENTERPRISE | 0.92 | 0 | 0
7121 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-3 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002419/2024-2025 | 136/SMSD | 22/01/2025 | 15 | SUBHRA ENTERPRISE | 0.97 | 0 | 0
7122 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-1 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002422/2024-2025 | 125/SMSD | 22/01/2025 | 15 | SUBHRA ENTERPRISE | 0.97 | 0 | 0
7123 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Zone-I, Pump House-2 of Aug of Sadhupur water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002423/2024-2025 | 126/SMSD | 22/01/2025 | 15 | SUBHRA ENTERPRISE | 0.97 | 0 | 0
7124 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-3 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002441/2024-2025 | 1726/SMSD | 27/12/2024 | 15 | SUBHRA ENTERPRISE | 0.7 | 0 | 0
7125 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-1 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002442/2024-2025 | 1676-A-SMSD | 20/12/2024 | 15 | SUBHRA ENTERPRISE | 0.7 | 0 | 0
7126 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Valve & UPVC column pipe etc. at Zone-I PH-2 Aug of Sadhupur water supply scheme under Gosaba Block under SMD, P.H.E. Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002443/2024-2025 | 1725/SMSD | 27/12/2024 | 15 | SUBHRA ENTERPRISE | 0.7 | 0 | 0
7127 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-2 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002444/2024-2025 | 1767/SMSD | 31/12/2024 | 15 | SUBHRA ENTERPRISE | 0.99 | 0 | 0
7128 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-3 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002445/2024-2025 | 1768/SMSD | 31/12/2024 | 15 | SUBHRA ENTERPRISE | 0.99 | 0 | 0
7129 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Aug of Sadhupur Zone-I, PH-1 water supply scheme under Gosaba block Under SMD PHE Dte. (SM/15965) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002446/2024-2025 | 1766/SMSD | 31/12/2024 | 15 | SUBHRA ENTERPRISE | 0.99 | 0 | 0
7130 | Alipore Division | Baruipur Sub-Division | Road restoration for L048-Jauhia lo Patpukur. | AE BSD |  | BILL/01732/2024-2025 | BP-2024-25-796 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.48 | 0 | 0
7131 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-IV at Gopalganj Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000015/2022-2023 | 867/SWD-I | 13/07/2022 | 300 | M/S PATH MAKERS | 269.19 | 0 | 90
7132 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipe carrying structure with laying of 323.9 mm dia M.S. Secondary Rising Main for crossing of Canal at Brindaban Kheya Bridge and Raju Vata Culvert under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI Block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S Division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16189] | AE BSD |  | ORD/000283/2024-2025 | 3039/SWD-I | 02/07/2024 | 30 | SRIJON ENTERPRISE | 26.01 | 0 | 100
7133 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Protection work for pipeline restoration of road, construction of approach Road, development of Land for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte." (SM/16189) | AE BSD |  | ORD/000357/2024-2025 | 3457/SWD-I | 02/08/2024 | 180 | ARNAB ENTERPRISE | 89.77 | 0 | 100
7134 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IV (DASKHIN GARANKATHI MOUZA) of Kultali Block, under Raidighi Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000366/2021-2022 | 2533/SWD-I | 08/03/2022 | 1440 | GHOSH BROTHERS | 855.67 | 0 | 85
7135 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Gap Negotiation for Secondary grid of Mathurapur-II block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte." [SM/16189] | AE BSD |  | ORD/001083/2024-2025 | 5350/SWD-I | 30/12/2024 | 60 | CHANDAN ROY | 96.58 | 0 | 75
7136 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quatation for new service (power) connection at Ranigachi PH-1 Water supply scheme under Bhangar-I block Reference ID-106663978, Application No- 1007921419 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01367/2024-2025 | BP-2024-25-324 | 31/08/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
7137 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Ranigachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001524/2022-2023 | 931/SMD | 30/03/2023 | 823 | M/S. S.S. ENTERPRISE (DOMKAL) | 25.09 | 0 | 40
7138 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Ranigachi PH-1 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/15863) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002251/2024-2025 | 1546/SMSD | 25/11/2024 | 15 | M/S. S.S. ENTERPRISE (DOMKAL) | 0.9 | 0 | 0
7139 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for RANIGACHI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1320) (TSM/018478) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 267/SWD-I | 24/04/2023 | 752 | SAMARJIT ENTERPRISE | 303.12 | 0 | 35
7140 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall at HW Site & 2nd Tubewell site of "RANIGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District under Jal Jeevan Mission". (SM/15863) (3rd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000103/2025-2026 | 1816/SWD-I | 07/07/2025 | 60 | SUJIT KUMAR SHARMA | 28.52 | 0 | 0
7141 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of land, drum sheet walling, approach road of HW site & 2nd Tubewell site and allied works of "RANIGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under Jal Jeevan Mission". (SM/15863) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000539/2024-2025 | 4096/SWD-I | 20/09/2024 | 60 | SAMARJIT ENTERPRISE | 52.37 | 0 | 0
7142 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RANIGACHI PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018478] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000670/2022-2023 | 3412/SWD-I | 10/03/2023 | 30 | REALIENCE CONSTRUCTION | 31.79 | 0 | 50
7143 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000039/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 20.91 | 0 | 0
7144 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000215/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 8.13 | 0 | 0
7145 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000101/2023-2024 | 504/AD | 11/05/2023 | 782 | M/S. BISWAS CONSTRUCTION(I) | 23.87 | 0 | 80
7146 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000140/2023-2024 | 276/AD | 24/04/2023 | 75 | GOLDEN ENTERPRISE | 43.97 | 0 | 100
7147 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-III) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1271] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000261/2023-2024 | 1449/AD | 13/07/2023 | 689 | SUBHO CONSTRUCTION | 389.99 | 0 | 71
7148 | Alipore Division | Canning Sub-division | Laying additional pipeline and other allied works at Augmentation of Satjelia (Zone - III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000310/2024-2025 | 2691/AD | 24/06/2024 | 434 | R.S.CONSTRUCTION CO. | 65.49 | 0 | 40
7149 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001850/2022-2023 | 11816/AD | 23/02/2023 | 45 | TECH VISION | 4.2 | 0 | 0
7150 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001980/2022-2023 | 12641/AD | 13/03/2023 | 45 | R.G. ENTERPRISE (I) | 8.9 | 0 | 0
7151 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002010/2022-2023 | 12916/AD | 21/03/2023 | 499 | MISTRY CONSTRUCTION | 8.61 | 0 | 100
7152 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000053/2023-2024 | 260/AD | 24/04/2023 | 0 | Resource Division | 50.2 | 0 | 0
7153 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000415/2023-2024 | 371/AD | 19/01/2024 | 0 | Resource Division | 7.83 | 0 | 0
7154 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Satjelia Zone-III , PH-2 under Gosaba block (REF ID : 106521065) (APP ID: 1007603702) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/01384/2024-2025 | BP-2024-25-347 | 09/09/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
7155 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | BILL/05702/2023-2024 | BP-2023-24-604 | 28/03/2024 | 0 | WBSEDCL | 6.92 | 0 | 0
7156 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-III for Augmentation of Satjelia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gpsaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000277/2023-2024 | 1138/SMD | 24/04/2023 | 1634 | JAL PRAVAHIKA PVT. LTD. | 21.7 | 0 | 45
7157 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Chak Rosanmamud water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000266/2023-2024 | 1126/SMD | 24/04/2023 | 983 | PADMA ENGINEERING CO. | 25.42 | 0 | 25
7158 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000128/2023-2024 | 588/SWD-I | 16/05/2023 | 90 | M/S B.S. CONSTRUCTION | 118.62 | 0 | 0
7159 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 981 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
7160 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK ROSANMAMUD PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/15867] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000287/2024-2025 | 3051/SWD-I | 03/07/2024 | 377 | P ENTERPRISE | 68.52 | 0 | 55
7161 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000292/2024-2025 | 3107/SWD-I | 09/07/2024 | 60 | TIYASHA ENTERPRISE | 118.7 | 0 | 55
7162 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK ROSANMAMUD PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000691/2022-2023 | 3480/SWD-I | 15/03/2023 | 678 | BARI ENTERPRISE | 15.88 | 0 | 98
7163 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Rasanmamud Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000964/2022-2023 | 1164/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
7164 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK ROSANMAMUD Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District in BISHNUPUR-I Block under South 24 Pgns W/S Sub-Division-II, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15867] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001192/2024-2025 | 772/SWD-I | 18/03/2025 | 30 | SATHI ENTERPRISE | 15.88 | 0 | 0
7165 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000120/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 27.73 | 0 | 0
7166 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01507/2023-2024 | BP-2023-24-172 | 02/08/2023 | 0 | WBSEDCL | 2.56 | 0 | 0
7167 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/03276/2023-2024 | BP-2023-24-366 | 04/11/2023 | 0 | WBSEDCL | 10.38 | 0 | 0
7168 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 Zone-I of Rana water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1091/SMD | 18/04/2023 | 744 | SHIVAM ENTERPRISE | 21.76 | 0 | 100
7169 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Rana W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16132) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001220/2024-2025 | 1656/SMSD | 13/12/2024 | 15 | SHIVAM ENTERPRISE | 0.91 | 0 | 100
7170 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Rana W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/16132) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001225/2024-2025 | 1655/SMSD | 13/12/2024 | 15 | SHIVAM ENTERPRISE | 0.87 | 0 | 67
7171 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of Sankharipur water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002105/2024-2025 | 389/SMSD | 19/03/2025 | 21 | NEW RANBEE ENGINEERING | 0.79 | 0 | 0
7172 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of Rana water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/002347/2024-2025 | 388/SMSD | 19/03/2025 | 21 | KARTICK BAL | 0.79 | 0 | 0
7173 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based RANA Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/16132) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 3272/SWD-I | 22/07/2024 | 45 | BAIDYA ENTERPRISE | 91.55 | 0 | 25
7174 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RANA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 998] [TSM/018248] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 2090/SWD-I | 29/08/2023 | 90 | MS BUILDWELL | 181.82 | 0 | 80
7175 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RANA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018248] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000644/2022-2023 | 3285/SWD-I | 03/03/2023 | 30 | M/S SYCHROTECH INDUSTRY | 31.11 | 0 | 100
7176 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rana Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000934/2022-2023 | 1226/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.54 | 0 | 100
7177 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000128/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 11.59 | 0 | 0
7178 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Paschim Chakpanchghora supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000576/2022-2023 | 601/SMD | 27/02/2023 | 764 | CONCORD ENGINEERING | 19.28 | 0 | 45
7179 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Paschim Chak Panchghara W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16930) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002298/2024-2025 | 1447/SMSD | 24/10/2024 | 15 | CONCORD ENGINEERING | 0.59 | 0 | 0
7180 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Paschim Chak Panchghara W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/16930) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002299/2024-2025 | 1528/SMSD | 19/11/2024 | 15 | CONCORD ENGINEERING | 0.59 | 0 | 0
7181 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 0 | 15
7182 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PASCHIM CHAKPANCHGHORA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000388/2021-2022 | 1926/SWD-I NEW | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 0
7183 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well by Rotary method for PASCHIM CHAKPANCHGHORA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012513] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000749/2022-2023 | 3609/SWD-I | 24/03/2023 | 30 | MONDAL ENTERPRISE | 31.77 | 0 | 100
7184 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000089/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 32.55 | 0 | 0
7185 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000138/2022-2023 | 3421/SWD-I | 13/03/2023 | 0 | Resource Division | 7.63 | 0 | 0
7186 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-IX) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000053/2023-2024 | 144/AD | 13/04/2023 | 300 | RIVER BENZ CONSTRUCTION | 141.92 | 0 | 0
7187 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1593] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000056/2023-2024 | 148/AD | 17/04/2023 | 670 | M.T.C. CONSTRUCTION | 91.45 | 0 | 30
7188 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018392] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000167/2023-2024 | 978/AD | 08/06/2023 | 600 | RIVER BENZ CONSTRUCTION | 146.19 | 0 | 100
7189 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 3 (Old)] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000457/2025-2026 | 816/CSD | 17/06/2025 | 30 | M/S NABIBAR BUILDERS | 1.91 | 0 | 0
7190 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000499/2023-2024 | 1799/AD | 26/07/2023 | 45 | PAL ENTERPRISE | 7.35 | 0 | 0
7191 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000500/2023-2024 | 1800/AD | 26/07/2023 | 45 | STRINGS ENGINEERING PVT. LTD. | 7.1 | 0 | 0
7192 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000501/2023-2024 | 1801/AD | 26/07/2023 | 45 | SAMIR GIRI | 7.09 | 0 | 100
7193 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 1 (Old)] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000727/2025-2026 | 815/CSD | 17/06/2025 | 30 | ASIK CONSTRUCTION | 1.91 | 0 | 0
7194 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IX) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000729/2023-2024 | 2890/AD | 19/09/2023 | 15 | SURYA ENTERPRISE | 10.48 | 0 | 90
7195 | Alipore Division | Canning Sub-division | Laying additional pipe line with other allied works at Basanti (Zone-IX) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000829/2024-2025 | 4535/AD | 13/11/2024 | 60 | S.S. CONSTRUCTION | 38.57 | 0 | 0
7196 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. 3 for Augmentation of Basanti (Zone-IX) Piped Water Supply Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001226/2024-2025 | 5225/AD | 16/12/2024 | 376 | NEW DAWN POWER & CONSTRUCTION | 13.34 | 0 | 80
7197 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001871/2022-2023 | 12463/AD | 10/03/2023 | 517 | SOMA ENTERPRISE | 58.76 | 0 | 100
7198 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IX) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001939/2022-2023 | 11810/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.49 | 0 | 0
7199 | Alipore Division | Canning Sub-division | Laying of additional pipe line for Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002181/2023-2024 | 832/AD | 05/02/2024 | 30 | NAZRUL ENTERPRISE | 8.2 | 0 | 100
7200 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000029/2023-2024 | 234/AD | 24/04/2023 | 0 | Resource Division | 74.55 | 0 | 0
7201 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000158/2023-2024 | 1055/AD | 15/06/2023 | 0 | Resource Division | 9.81 | 0 | 0
7202 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at pump house no-3 of Basanti (Zone-IX) water supply scheme.(Basanti Block) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01812/2024-2025 | BP-2024-25-459 | 29/10/2024 | 0 | WBSEDCL | 13.3 | 0 | 0
7203 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/04677/2023-2024 | BP-2023-24-505 | 12/02/2024 | 0 | WBSEDCL | 10.24 | 0 | 0
7204 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 Zone-IX of Basanti water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001515/2022-2023 | 895/SMD | 27/03/2023 | 827 | SINHA ELECTRICALS | 31.38 | 0 | 60
7205 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at P.H. No-1 & 2 of Basanti (Zone-IX) water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001518/2024-2025 | 257/SMSD | 20/02/2025 | 15 | KARTICK BAL | 0.78 | 0 | 0
7206 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti (Zone-IX) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15963) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001524/2024-2025 | 1714/SMSD | 27/12/2024 | 15 | SINHA ELECTRICALS | 0.87 | 0 | 0
7207 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Basanti (Zone-IX) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15963) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001525/2024-2025 | 1715/SMSD | 27/12/2024 | 15 | SINHA ELECTRICALS | 0.91 | 0 | 0
7208 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gopalpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 1112/SMD | 20/04/2023 | 987 | KARUNAMOY ENGINEERING | 22.79 | 0 | 40
7209 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar including allied work at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur )(SM/15775) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 943/SMSD | 28/06/2024 | 15 | KARUNAMOY ENGINEERING | 0.95 | 0 | 100
7210 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar including allied work at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur )(SM/15775) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000304/2024-2025 | 943-SMSD | 28/06/2024 | 15 | KARUNAMOY ENGINEERING | 0.95 | 0 | 0
7211 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Gopalpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002031/2023-2024 | 327-SMSD | 14/03/2024 | 15 | KARUNAMOY ENGINEERING | 0 | 0 | 0
7212 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Gopalpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002200/2023-2024 | 328/SMSD | 14/03/2024 | 15 | KARUNAMOY ENGINEERING | 0.89 | 0 | 0
7213 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOPALPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/019594] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 402/SWD-I | 28/04/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
7214 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1097) (TSM/019594) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000104/2023-2024 | 481/SWD-I | 08/05/2023 | 687 | GUHA CONSTRUCTION | 274.08 | 0 | 27
7215 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land, Construction of Pathway, Drain & others allied works of GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15775) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000824/2023-2024 | 1298/SWD-I | 15/03/2024 | 323 | GUHA CONSTRUCTION | 39.38 | 0 | 50
7216 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Gopalpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000991/2022-2023 | 1503/SWD-I | 28/09/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
7217 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of GOPALPUR Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/15775] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001101/2024-2025 | 77/SWD-I | 07/01/2025 | 145 | B.K.ENTERPRISE | 15.68 | 0 | 100
7218 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000003/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.6 | 0 | 0
7219 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000249/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.76 | 0 | 0
7220 | Alipore Division |  | Bill for way leave/ track crossing proposal with application ID : ER-SHAH-2023-WL-79 in IR/RBCS |  |  | BILL/00436/2024-2025 | BP-2024-25-163 | 04/06/2024 | 0 | EASTERN RAILWAY (SEALDAH DIVISION) | 5.77 | 0 | 0
7221 | Alipore Division |  | DISMANTLING AND RESTORATION OF CONCRETE VILLAGE ROAD FOR LDS WORK AT ZONE-I OF MATHURAPUR-I BLOCK FOR MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA MATHURAPUR UNDER RAIDIGHI SUB DIVISION OF ALIPORE DIVISION, PHE Dte. |  |  | BILL/00985/2024-2025 | BP-2024-25-472 | 17/08/2024 | 0 | M/S RAJU CONSTRUCTION | 1.47 | 0 | 0
7222 | Alipore Division |  | Laying distribution system of piped water supply and allied works at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000116/2023-2024 | 485/AD | 10/05/2023 | 30 | KAMALA ENTERPRISE (I) | 8.57 | 0 | 80
7223 | Alipore Division |  | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000220/2022-2023 | 3061/AD | 13/07/2022 | 30 | UNITED BUILDERS | 13.1 | 0 | 100
7224 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 0 | 100
7225 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 5553/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
7226 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 6th tubewell Site for Achintyanagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000234/2024-2025 | 2609/AD | 19/06/2024 | 266 | M/S A.M. ENTERPRISE | 5.62 | 0 | 100
7227 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 6th Tubewell Site for Achintyanagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000235/2024-2025 | 2610/AD | 19/06/2024 | 266 | M/S A.M. ENTERPRISE | 9.72 | 0 | 100
7228 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Achintyanagar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000999/2023-2024 | 506/KSD | 03/10/2023 | 7 | M/S B. ENTERPRISE | 3.74 | 0 | 100
7229 | Alipore Division | Kakdwip Sub-Division | : Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Achintyanagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001331/2024-2025 | 5415/AD | 24/12/2024 | 189 | AVIJIT ENTERPRISE (64) | 7.93 | 0 | 100
7230 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
7231 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000381/2023-2024 | 3567/AD | 18/10/2023 | 0 | Resource Division | 44.3 | 0 | 0
7232 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000779/2023-2024 | 613/AD | 29/01/2024 | 0 | Resource Division | 8.33 | 0 | 0
7233 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Madhusudanpur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1927] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000143/2023-2024 | 756/AD | 23/05/2023 | 601 | PAUL CONSTRUCTION | 389.27 | 0 | 30
7234 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and other allied works of pipe line protection at Madhusudanpur W/S Scheme for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000199/2024-2025 | 2582/AD | 19/06/2024 | 45 | PAUL CONSTRUCTION | 39.88 | 0 | 20
7235 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000424/2023-2024 | 1912/AD | 01/08/2023 | 45 | G.B. CONSTRUCTION (TW) | 38.38 | 0 | 90
7236 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhusudanpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000948/2023-2024 | 2980/AD | 26/09/2023 | 45 | SARADA CONSTRUCTION | 27.73 | 0 | 0
7237 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Madhusudanpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000949/2023-2024 | 2981/AD | 26/09/2023 | 30 | M/S NAIYA & MAITY | 9.6 | 0 | 0
7238 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
7239 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Madhusudanpur PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002162/2022-2023 | 8335/AD | 12/12/2022 | 45 | LEMNISCATE | 4.16 | 0 | 100
7240 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 350 cum. capacity OHR of Madhusudanpur PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002216/2023-2024 | 873/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
7241 | Alipore Division | Kakdwip Sub-Division | Inter connection between two nos. Tubewell for Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002548/2024-2025 | 817/AD | 27/02/2025 | 45 | PAUL CONSTRUCTION | 13.31 | 0 | 0
7242 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000445/2023-2024 | 4712/AD | 18/12/2023 | 0 | Resource Division | 19.93 | 0 | 0
7243 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000587/2023-2024 | 86/AD | 03/01/2024 | 0 | Resource Division | 11.45 | 0 | 0
7244 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Madhusudanpur W/S Scheme PH-2 Application No:- 1008017613 Reference ID: 106715286 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02229/2024-2025 | BP-2024-25-500 | 19/12/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
7245 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Madhusudanpur W/S Scheme PH-1 Application No:- 1007169493 Reference ID: 106214433 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/02234/2024-2025 | BP-2024-25-501 | 19/12/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
7246 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Madhusudanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001605/2023-2024 | 4757/SMD | 06/12/2023 | 91 | NUPUR CHANDRA HALDER | 23.17 | 0 | 0
7247 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04230/2023-2024 | BP-2023-24-436 | 27/12/2023 | 0 | WBSEDCL | 3.92 | 0 | 0
7248 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] |  |  | ORD/001420/2022-2023 | 3459/SMD | 23/12/2022 | 90 | TRIO CONCERN | 26.99 | 0 | 50
7249 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Chandpur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) |  |  | ORD/002201/2023-2024 | 133/SMSD | 02/02/2024 | 15 | TRIO CONCERN | 0.92 | 0 | 100
7250 | S24 Pgns Mechanical |  | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Chandpur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) |  |  | ORD/002247/2023-2024 | 132/SMSD | 02/02/2024 | 15 | TRIO CONCERN | 0.58 | 0 | 0
7251 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.17] |  |  | BILL/00476/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 14.02 | 0 | 0
7252 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18328) |  |  | ORD/000240/2024-2025 | 2660/SWD-I | 07/06/2024 | 495 | M/S ASHA ENGINEERING | 10.58 | 0 | 60
7253 | South 24 Pgs W/S Division I |  | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 3295] |  |  | ORD/000291/2023-2024 | 1622/SWD-I | 02/08/2023 | 608 | SAFECO ENTERPRISES | 683.19 | 0 | 20
7254 | South 24 Pgs W/S Division I |  | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016315] |  |  | ORD/000297/2023-2024 | 1662/SWD-I | 03/08/2023 | 570 | PADMA ENGINEERING CO. | 3.14 | 0 | 100
7255 | South 24 Pgs W/S Division I |  | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR CHANDPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016315) |  |  | ORD/000298/2023-2024 | 1663/SWD-I | 03/08/2023 | 569 | PADMA ENGINEERING CO. | 30.07 | 0 | 100
7256 | South 24 Pgs W/S Division I |  | Additional Laying Pipeline for 63mm dia (OD) & 75mm dia (OD) HDPE pipe under ¿CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM.¿ [SM/18328] |  |  | ORD/000544/2024-2025 | 4101/SWD-I | 20/09/2024 | 10 | SAFECO ENTERPRISES | 27.53 | 0 | 0
7257 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain and other allied works of CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18328) |  |  | ORD/000887/2024-2025 | 4992/SWD-I | 05/12/2024 | 60 | SAFECO ENTERPRISES | 38.98 | 0 | 0
7258 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 22.24 | 0 | 0
7259 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 246/SWD-I | 10/01/2024 | 0 | Resource Division | 20.3 | 0 | 0
7260 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1474] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000259/2023-2024 | 1447/AD | 13/07/2023 | 300 | SAMSUL ENTERPRISE | 489.25 | 0 | 60
7261 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Augmentation of Harishpur (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000733/2024-2025 | 4391/AD | 05/11/2024 | 45 | SAMSUL ENTERPRISE | 45.41 | 0 | 0
7262 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001227/2024-2025 | 5230/AD | 16/12/2024 | 271 | P.S. CONSTRUCTION | 84.35 | 0 | 0
7263 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002018/2022-2023 | 12924/AD | 21/03/2023 | 986 | MOUMITA ENTERPRISE | 42.77 | 0 | 40
7264 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002112/2022-2023 | 12878/AD | 17/03/2023 | 45 | TECH VISION | 5.24 | 0 | 95
7265 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000058/2023-2024 | 265/AD | 24/04/2023 | 0 | Resource Division | 46.64 | 0 | 0
7266 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000420/2023-2024 | 375/AD | 19/01/2024 | 0 | Resource Division | 9.08 | 0 | 0
7267 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and of 15 KVA servo motor operated copper wound line voltage stabilizer at PH No.-1 (Newly energized converted from DG power to WBSEDCL supply) of Harishpur water supply scheme under SMD, PHE Dte. (Block:-Gosaba). | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000398/2022-2023 | 543/SMD | 10/06/2022 | 30 | SHIVAM ENTERPRISE | 4.12 | 0 | 0
7268 | South 24 Pgs W/S Division I | Baruipur Sub-Division | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas | AE BSD |  | BILL/00639/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
7269 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-II at Jalaberia Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000014/2022-2023 | 866/SWD-I | 13/07/2022 | 300 | M/S PATH MAKERS | 322.19 | 0 | 91
7270 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of boundary wall at Headworks site of Zone-II within kultali block, under Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-II at KULTALI block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Pgns. Water Supply Division-I, PHE Dte. (TSM/ 016053) | AE BSD |  | ORD/000250/2023-2024 | 1492/SWD-I | 19/07/2023 | 60 | A.B. ASSOCIATES | 14.14 | 0 | 100
7271 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIA (JALABERIA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000401/2021-2022 | 2597/SWD-I | 15/03/2022 | 1440 | SPA ENTERPRISE | 631.68 | 0 | 80
7272 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIB (JALABARIA MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000402/2021-2022 | 2600/SWD-I | 15/03/2022 | 1350 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 644.11 | 0 | 65
7273 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000295/2023-2024 | 2433/SWD-I | 30/09/2023 | 0 | Resource Division | 92.47 | 0 | 0
7274 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Jamtala Petkulchand Road from 0.20 to 0.35 km, 4.50 to 6.00 km, 8.20 to 8.50 km, 8.80 to 9.00 km & 12.50 to 13.00 km Restoration of Brick top surface & Saucer drain in different chainage due to laying of pipelines by PHE Department under Lakshmikantapur Highway Sub Division of Diamond Harbour Highway Division in the District of South 24 Parganas. | AE BSD |  | BILL/00636/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 13.26 | 0 | 0
7275 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance civil works of Kultali GLR under the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000006/2022-2023 | 839/SWD-I | 08/07/2022 | 1260 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 113.5 | 0 | 90
7276 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VB of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000037/2022-2023 | 17/SWD-I | 06/04/2022 | 1144 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 589.08 | 0 | 50
7277 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection wall for laying pipeline, restoration of damaged road due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-V at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte. (SM/ 18224) (2nd call) | AE BSD |  | ORD/000740/2024-2025 | 4638/SWD-I | 14/11/2024 | 45 | MOUMITA ENTERPRISE | 89.32 | 0 | 0
7278 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000874/2022-2023 | 16/SWD-I | 06/04/2022 | 1068 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 602.94 | 0 | 65
7279 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000041/2022-2023 | 2956/SWD-I | 16/02/2023 | 0 | Resource Division | 50.12 | 0 | 0
7280 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000064/2022-2023 | 2979/SWD-I | 20/02/2023 | 0 | Resource Division | 37.62 | 0 | 0
7281 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000075/2022-2023 | 2991/SWD-I | 20/02/2023 | 0 | Resource Division | 62.44 | 0 | 0
7282 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000207/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 119.44 | 0 | 0
7283 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000297/2023-2024 | 2432/SWD-I | 30/09/2023 | 0 | Resource Division | 71.69 | 0 | 0
7284 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Abjakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/001434/2022-2023 | 148/SMD | 16/01/2023 | 90 | S.P. CONSTRUCTION | 33.56 | 0 | 0
7285 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Abjakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] |  |  | ORD/001569/2024-2025 | 2030/SMD | 28/06/2024 | 90 | S.P. CONSTRUCTION | 33.56 | 0 | 0
7286 | South 24 Pgs W/S Division I |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ABJAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017506] |  |  | ORD/000226/2023-2024 | 1402/SWD-I | 14/07/2023 | 30 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.86 | 0 | 0
7287 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipelines for distribution system, construction of boundary wall, approach road, land development, pipeline protection and road restoration for ABJAKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/18266] |  |  | ORD/000254/2024-2025 | 2671/SWD-I | 07/06/2024 | 45 | AVIK ENTERPRISE | 96.46 | 0 | 0
7288 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of ABJAKHALI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3239) [TSM/017506]. |  |  | ORD/000306/2023-2024 | 1695/SWD-I | 07/08/2023 | 603 | PRASUN ENTERPRISE | 495.25 | 0 | 70
7289 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Abjakhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000961/2022-2023 | 1139/SWD-I | 25/08/2022 | 30 | GEO SOLUTION | 2.85 | 0 | 100
7290 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 84.26 | 0 | 0
7291 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone - l) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000094/2025-2026 | 2523/AD | 30/05/2025 | 45 | SURYA ENTERPRISE | 19.5 | 0 | 0
7292 | Alipore Division | Canning Sub-division | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the PATHANKHALI (ZONE-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000485/2023-2024 | 1998/AD | 04/08/2023 | 300 | M/S SHIBAM ENTERPRISE | 711.48 | 0 | 25
7293 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000491/2023-2024 | 1931/AD | 01/08/2023 | 45 | NATURAL RESOURCES CONSORTIUM | 51.2 | 0 | 0
7294 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000607/2023-2024 | 1829/AD | 27/07/2023 | 45 | TECH VISION | 7.45 | 0 | 99
7295 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House no.1 for Augmentation of Pathakhali (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000730/2024-2025 | 4388/AD | 05/11/2024 | 30 | KANAN CONSTRUCTION | 28.81 | 0 | 0
7296 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep (Replacement) Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation of Pathankhali (Zone - I) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 4) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000743/2024-2025 | 4417/AD | 05/11/2024 | 30 | MOSTAFIZUR HAQUE GAINE | 22.43 | 0 | 25
7297 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Bipradaspur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002495/2024-2025 | 788/AD | 25/02/2025 | 30 | REZU CONSTRUCTION | 12.42 | 0 | 0
7298 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000049/2023-2024 | 256/AD | 24/04/2023 | 0 | Resource Division | 124.68 | 0 | 0
7299 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000410/2023-2024 | 364/AD | 19/01/2024 | 0 | Resource Division | 14.32 | 0 | 0
7300 | Alipore Division | Canning Sub-division | Laying damaged pipe line due to widening of road by South 24 Parganas Zilla Parishad from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000280/2022-2023 | 273/CSD | 19/05/2022 | 30 | ASHIS ENTERPRISE | 4.18 | 0 | 100
7301 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000683/2024-2025 | 4288/AD | 29/10/2024 | 180 | SAHANA ENTERPRISE | 4.83 | 0 | 0
7302 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000684/2024-2025 | 4289/AD | 29/10/2024 | 30 | ASHIS ENTERPRISE | 10.8 | 0 | 0
7303 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000685/2024-2025 | 4290/AD | 29/10/2024 | 30 | SAHANA ENTERPRISE | 8.33 | 0 | 68
7304 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000686/2024-2025 | 4291/AD | 29/10/2024 | 30 | HARIDAS DUTTA | 8.59 | 0 | 0
7305 | Alipore Division | Canning Sub-division | Land development work at Over Head Reservoir site (balance portion) of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas District of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000867/2022-2023 | 844/CSD | 16/08/2022 | 25 | ASHIS ENTERPRISE | 3.54 | 0 | 100
7306 | Alipore Division | Canning Sub-division | Supply and delivery of DI fittings and construction of Sluice Valve Chamber for the proposed DI line from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000999/2022-2023 | 849/CSD | 18/08/2022 | 30 | ASHIS ENTERPRISE | 4.76 | 0 | 100
7307 | Alipore Division | Canning Sub-division | Land development work at Over Head Reservoir site of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas Distric of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001643/2021-2022 | 1511/CSD | 15/02/2022 | 15 | ASHIS ENTERPRISE | 1.98 | 0 | 100
7308 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000002/2024-2025 | 4550/AD | 13/11/2024 | 0 | Resource Division | 61.6 | 0 | 0
7309 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000003/2024-2025 | 5158/AD | 12/12/2024 | 0 | Resource Division | 123.2 | 0 | 0
7310 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3,4,5,6 & 7 for Augmentation of Kalaria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer, Canning sub division |  | ORD/000108/2023-2024 | 938/SMD | 04/04/2023 | 90 | M/S. S.S. ENTERPRISE | 78.3 | 0 | 0
7311 | S24 Pgns Mechanical | Canning Sub-division | Renovation of Electro-Mechanical works at Zone ¿IB, PH-1 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer, Canning sub division |  | ORD/000137/2024-2025 | 587/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.58 | 0 | 100
7312 | S24 Pgns Mechanical | Canning Sub-division | Installation of submersible pumping machinery along with allied works at Zone -1A, PH No-1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000153/2024-2025 | 591/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.97 | 0 | 100
7313 | S24 Pgns Mechanical | Canning Sub-division | Renevation of auto panel and allied works at Zone-IB, PH- 1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000156/2024-2025 | 593/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.9 | 0 | 100
7314 | S24 Pgns Mechanical | Canning Sub-division | Installation of submersible pumping machinery along with allied works at Zone -1B, PH No-1 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000157/2024-2025 | 590/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.97 | 0 | 100
7315 | S24 Pgns Mechanical | Canning Sub-division | Renovation of Electro-Mechanical works at Zone ¿IA, PH-2 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer, Canning sub division |  | ORD/000158/2024-2025 | 588/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.58 | 0 | 100
7316 | S24 Pgns Mechanical | Canning Sub-division | Renovation of Electro-Mechanical works at Zone ¿IA, PH-1 of Kalaria Augmentation water supply scheme under South 24 pgs. Mechanical Division, PHE Dte. [Canning-I] | Assistant Engineer, Canning sub division |  | ORD/000159/2024-2025 | 589/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.58 | 0 | 100
7317 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IA, PH-2 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000160/2024-2025 | 585/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.99 | 0 | 100
7318 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IB, PH-1 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000161/2024-2025 | 584/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.99 | 0 | 100
7319 | S24 Pgns Mechanical | Canning Sub-division | Installation of submersible pumping machinery along with allied works at Zone -1A, PH No-2 of Kalaria Augmentation water supply scheme under south 24 pgs. Mechanical Division ,PHE Dte.[Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000162/2024-2025 | 581/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.97 | 0 | 100
7320 | S24 Pgns Mechanical | Canning Sub-division | Supply and delivery of wafer type 3 phase actuator operated wafer type butterfly valve at Kalaria Augmentation water supply scheme of Zone -IA, PH-1 under South 24 pgs. Mechanical Division, PHE Dte. [Canning -I] | Assistant Engineer, Canning sub division |  | ORD/000163/2024-2025 | 586/SMSD | 13/05/2024 | 15 | PADMA ENGINEERING CO. | 0.99 | 0 | 100
7321 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Jaldhapa water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division | JE RWS, HQ | ORD/001422/2022-2023 | 3835/SMD | 29/12/2022 | 144 | SINHA ELECTRICALS | 33.56 | 0 | 0
7322 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sarberia-Dhamua Road from 0+00 to 6+520 km Restoration of Damages occurred due to damages caused/ to be caused by laying of pipe line by PHE Dte. under Sarberia PWSS,Jaldhapa PWSS,Multi PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. | AE RWS, Alipore Division | JE RWS, HQ | BILL/00644/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 105.27 | 0 | 0
7323 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JALDHAPA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017282] [2nd call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000227/2023-2024 | 1403/SWD-I | 14/07/2023 | 30 | HOQUE BUILDERS, M/S SEW | 47.65 | 0 | 0
7324 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 0 | 6
7325 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, Construction of Approach Road, Earth Filling, Drum Sheet walling for JALDHAPA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Div-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/18269) [2nd call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000720/2024-2025 | 4554/SWD-I | 06/11/2024 | 45 | VITAE CO INTERNATIONAL | 39.73 | 0 | 0
7326 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Jaldhapa Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000980/2022-2023 | 1436/SWD-I | 23/09/2022 | 30 | MEASURE LAND | 2.89 | 0 | 100
7327 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000288/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 29.61 | 0 | 0
7328 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer, Canning sub division |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
7329 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Bhangankhali,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000352/2023-2024 | 1661/AD | 20/07/2023 | 300 | SPA ENTERPRISE | 636.93 | 0 | 5
7330 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Bhangankhali W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000493/2023-2024 | 1793/AD | 26/07/2023 | 60 | M/S KRISHNA MONDAL | 88.05 | 0 | 0
7331 | Alipore Division | Canning Sub-division | Renovation of Pump House No. 3 and its boundary wall of Bhangankhali W/S Scheme, under Basanti Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/002514/2023-2024 | 1605/CSD | 28/02/2024 | 30 | DIPA CHHETRI | 2.03 | 0 | 95
7332 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000034/2023-2024 | 239/AD | 24/04/2023 | 0 | Resource Division | 142.93 | 0 | 0
7333 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Bhangankhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] (SM/18286) | Assistant Engineer, Canning sub division |  | ORD/000081/2025-2026 | 1442/SMD | 22/05/2025 | 135 | M/S. A.K. BANERJEE | 11.13 | 0 | 0
7334 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
7335 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone - IV, Mathurapur - II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000276/2024-2025 | 593/RSD | 10/06/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 90
7336 | Alipore Division | Raidighi Sub-Division | Laying of additional D.I. (K7) pipes in connection with revised design of laying distribution alongwith supply, delivery and fitting & fixing at site of different dia specials at Zone - IV (Gilarchat PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000326/2024-2025 | 2729/AD | 25/06/2024 | 360 | NITYANANDA MONDAL | 149.16 | 0 | 10
7337 | Alipore Division | Raidighi Sub-Division | Contruction of 1250 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- IV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000482/2023-2024 | 1995/AD | 04/08/2023 | 300 | SPA ENTERPRISE | 818.91 | 0 | 0
7338 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000491/2024-2025 | 629/RSD | 11/07/2024 | 15 | SPA ENTERPRISE | 0.48 | 0 | 100
7339 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-IV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 & SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000790/2024-2025 | 4489/AD | 11/11/2024 | 120 | NITYANANDA MONDAL | 115.08 | 0 | 0
7340 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- IV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001041/2024-2025 | 4959/AD | 04/12/2024 | 60 | S.M. ENTERPRISE | 40.33 | 0 | 0
7341 | Alipore Division | Raidighi Sub-Division | Construction of boundary wall at Zone - IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 and SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001303/2024-2025 | 5377/AD | 23/12/2024 | 30 | BAPAN HALDAR | 6.52 | 0 | 0
7342 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000663/2023-2024 | 267/AD | 15/01/2024 | 0 | Resource Division | 11.41 | 0 | 0
7343 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000845/2023-2024 | 706/AD | 31/01/2024 | 0 | Resource Division | 264.14 | 0 | 0
7344 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 1) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Purba Ranaghat W/S Scheme (Zone-IV, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000429/2023-2024 | 1917/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 95
7345 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-IV, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000557/2023-2024 | 2239/AD | 11/08/2023 | 45 | ISHAN CONSTRUCTION | 59.38 | 0 | 70
7346 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 2, including plinth protection and boundary wall at Purba Ranaghata W/S Scheme, modified as Zone- IV of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001180/2023-2024 | 359/RSD | 21/11/2023 | 60 | MAA TARA ENTERPRISE | 2.96 | 0 | 100
7347 | Alipore Division | Raidighi Sub-Division | Providing 100% Functional Household Tap Connection (FHTC) including Parallel pipeline and other allied works of piped water supply at Zone - IV of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002183/2023-2024 | 834/AD | 05/02/2024 | 60 | M/S. L.P. CONSTRUCTION | 53.03 | 0 | 99
7348 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000640/2023-2024 | 244/AD | 15/01/2024 | 0 | Resource Division | 4.88 | 0 | 0
7349 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Part-B) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000058/2023-2024 | 41/KSD | 27/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
7350 | Alipore Division | Kakdwip Sub-Division | Construction of Platform, rising main and Road Restoration for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/11875) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000461/2024-2025 | 3420/AD | 21/08/2024 | 226 | BIMALENDU GIRI | 58.17 | 0 | 30
7351 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000484/2022-2023 | 1748/AD | 15/06/2022 | 45 | M/S R.DUTTA & CO. | 4.54 | 0 | 100
7352 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Sibpur W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000589/2023-2024 | 2346/AD | 18/08/2023 | 502 | R.P. ENTERPRISE | 45.18 | 0 | 100
7353 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Shibpur W/S Scheme, Block - Namkhana, for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000605/2024-2025 | 4092/AD | 03/10/2024 | 30 | MEHAI TECHNOLOGY LIMITED | 20.27 | 0 | 100
7354 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.06.2024 to 31.08.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000667/2024-2025 | 982/KSD | 27/05/2024 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7355 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.09.2024 to 30.11.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000668/2024-2025 | 1255/KSD | 28/08/2024 | 91 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7356 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 250] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001785/2022-2023 | 11557/AD | 17/02/2023 | 300 | R.P. ENTERPRISE | 176.39 | 0 | 0
7357 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Shibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001994/2023-2024 | 467/KSD | 22/09/2023 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.81 | 0 | 100
7358 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
7359 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Sibpur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002279/2023-2024 | 969/AD | 12/02/2024 | 30 | M/S ASHA ENGINEERING | 9.66 | 0 | 0
7360 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2022 to 30.11.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002423/2022-2023 | 562/KSD | 02/12/2022 | 363 | SARADA CONSTRUCTION | 4.8 | 0 | 0
7361 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2024 to 28.02.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002923/2024-2025 | 1654/KSD | 26/11/2024 | 90 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7362 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2025 to 31.05.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003006/2024-2025 | 350/KSD | 27/02/2025 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7363 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003031/2023-2024 | 713/KSD | 30/11/2023 | 91 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7364 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2024 to 31.05.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003032/2023-2024 | 410/KSD | 27/02/2024 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
7365 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000284/2023-2024 | 3081/AD | 28/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
7366 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000798/2023-2024 | 643/AD | 30/01/2024 | 0 | Resource Division | 3.38 | 0 | 0
7367 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000986/2023-2024 | 1779/AD | 27/03/2024 | 0 | Resource Division | 37.58 | 0 | 0
7368 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Shibpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000422/2022-2023 | 3818/SMD | 29/12/2022 | 90 | MAHAMAYA ENTERPRISE | 9.63 | 0 | 0
7369 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000369/2022-2023 | 4120/AD | 18/08/2022 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 564.7 | 0 | 86
7370 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Khas Ramkarchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 100] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001165/2023-2024 | 3744/AD | 03/11/2023 | 90 | DEBARATI ENTERPRISE | 213.65 | 0 | 100
7371 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (KHAS RAMKARCHAR (Phase - B)) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001360/2023-2024 | 3257/AD | 05/10/2023 | 45 | VOYAGER | 5.58 | 0 | 100
7372 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Augmentation of Khas Ramkarchar (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001838/2023-2024 | 126/AD | 05/01/2024 | 45 | M/S. GIRI ENTERPRISE | 23.17 | 0 | 60
7373 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Augmentation of Khas Ramkarchar (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001839/2023-2024 | 127/AD | 05/01/2024 | 45 | M/S. TRIPATHI & CO. | 21.4 | 0 | 60
7374 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
7375 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000516/2023-2024 | 4834/AD | 20/12/2023 | 0 | Resource Division | 41.76 | 0 | 0
7376 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000528/2023-2024 | 15/AD | 02/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
7377 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000692/2023-2024 | 462/AD | 24/01/2024 | 0 | Resource Division | 9.25 | 0 | 0
7378 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Khas Ramkarchar PH-3 W/ S Scheme Application No:- 1008023779 Reference ID: 106715294 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/01515/2024-2025 | BP-2024-25-361 | 11/09/2024 | 0 | WBSEDCL | 4.26 | 0 | 0
7379 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-3 of Khasramkarchar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/18871) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002283/2024-2025 | 1393-AE-II-SMD | 28/11/2024 | 15 | PS & ASSOCIATES | 0.97 | 0 | 0
7380 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000010/2022-2023 | 65/AD | 06/04/2022 | 120 | DIVINE | 245.35 | 0 | 100
7381 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 4 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000304/2025-2026 | 2957/AD | 25/06/2025 | 30 | M/S KHAJABABA ENTERPRISE | 10.73 | 0 | 0
7382 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 4 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-I) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000305/2025-2026 | 2958/AD | 25/06/2025 | 30 | SUNIL ENTERPRISE | 8.93 | 0 | 0
7383 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials from Head work site to PH - 3, 4 & 5 of Nagartala (Zone I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Nagartala - Z-II] (SM/09935) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000694/2024-2025 | 4295/AD | 29/10/2024 | 180 | RAKHI CONSTRUCTION | 61.46 | 0 | 98
7384 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no. 3 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001054/2024-2025 | 4995/AD | 05/12/2024 | 120 | KUNDU CONSTRUCTION CO. | 11.11 | 0 | 98
7385 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 5 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001056/2024-2025 | 4996/AD | 05/12/2024 | 30 | MAA SOLAR ENTERPRISE | 10.73 | 0 | 0
7386 | Alipore Division | Canning Sub-division | Laying of DI Pipeline form OHR to Distribution line of Augmentation Nagartala (Zone- I & II) W/S Scheme, Block-Canning - II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001267/2023-2024 | 1212/CSD | 17/11/2023 | 30 | SUKANTA HALDER | 2.44 | 0 | 98
7387 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001670/2021-2022 | 635/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.78 | 0 | 100
7388 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001671/2021-2022 | 636/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
7389 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001672/2021-2022 | 637/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.43 | 0 | 100
7390 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001673/2021-2022 | 638/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 100
7391 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001674/2021-2022 | 639/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.67 | 0 | 100
7392 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001675/2021-2022 | 642/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 1.35 | 0 | 100
7393 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001678/2022-2023 | 11487/AD | 15/02/2023 | 45 | PAL AGENCY | 7.1 | 0 | 98
7394 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000068/2022-2023 | 3948/AD | 12/08/2022 | 0 | Resource Division | 16.35 | 0 | 0
7395 | S24 Pgns Mechanical | Canning Sub-division | Supply and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at P.H No. 1, Zone-I of Nagartala w/s Scheme under SMD, PHE. Dte. [Block- Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002504/2022-2023 | ..550/SMD | 10/06/2022 | 30 | DIPALI CONSTRUCTION | 2.69 | 0 | 100
7396 | S24 Pgns Mechanical | Baruipur Sub-Division | Charges for new service connection at pump house no-I of Petua (part-I)(SM/12047) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01466/2024-2025 | BP-2024-25-350 | 06/09/2024 | 0 | WBSEDCL | 5.93 | 0 | 0
7397 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Petua water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000463/2022-2023 | 3940/SMD | 30/12/2022 | 90 | SHIVAM ENTERPRISE | 26.03 | 0 | 0
7398 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PETUA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 1200/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 0 | 100
7399 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PETUA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012604] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 1293/SWD-I | 14/09/2022 | 60 | JHARNA ENTERPRISE | 10.93 | 0 | 100
7400 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PETUA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000164/2021-2022 | 1912/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
7401 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls, platform for providing FHTC, protection works for laying pipeline and other allied works for Ground water based PETUA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12047) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000436/2024-2025 | 3881/SWD-I | 03/09/2024 | 60 | CHANDAN ROY | 91.78 | 0 | 0
7402 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system under ground water based piped water supply scheme at PETUA of BARUIPUR Block, under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12047) (No. of FHTC = 1422) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 2291/SWD-I | 20/09/2023 | 90 | M/S SUKUMAR SINHA | 360.14 | 0 | 0
7403 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PETUA PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012604] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000711/2023-2024 | 2178/SWD-I | 05/09/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 0 | 50
7404 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000270/2023-2024 | 2417/SWD-I | 30/09/2023 | 0 | Resource Division | 39.97 | 0 | 0
7405 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000339/2023-2024 | 272/SWD-I | 10/01/2024 | 0 | Resource Division | 8.76 | 0 | 0
7406 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Kaslas water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] |  |  | ORD/000600/2023-2024 | 2615/SMD | 07/08/2023 | 90 | B.T.PROJECTS PVT.LTD. | 34.71 | 0 | 0
7407 | South 24 Pgs W/S Division I |  | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based DIHI KALAS piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18568) |  |  | ORD/000314/2024-2025 | 3244/SWD-I | 19/07/2024 | 437 | SUPER ENTERPRISES | 286.8 | 0 | 60
7408 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DIHI KALASH PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018231] |  |  | ORD/000367/2023-2024 | 1776/SWD-I | 11/08/2023 | 30 | SAYANDIP CONSTRUCTION | 47.45 | 0 | 34
7409 | South 24 Pgs W/S Division I |  | Construction of 600 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DIHI KALAS MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3846] [TSM/018231] |  |  | ORD/000405/2023-2024 | 1922/SWD-I | 22/08/2023 | 953 | SUPER ENTERPRISES | 702.55 | 0 | 60
7410 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000290/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 32.22 | 0 | 0
7411 | South 24 Pgs W/S Division I |  | Construction of Hume Pipe Culvert of 10.00Mtr.span for proposed Zone-I OHR Site at Mallick Pratap Mouza(J.L.NO-02,Plot No-964) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014517) |  |  | ORD/000380/2023-2024 | 1816/SWD-I | 16/08/2023 | 481 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 16.11 | 0 | 75
7412 | South 24 Pgs W/S Division I |  | Road Restoration and Horizontal Boring for laying of Secondary Grid within Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte.(TSM/014517) |  |  | ORD/000398/2023-2024 | 1891/SWD-I | 18/08/2023 | 45 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 7.01 | 0 | 50
7413 | South 24 Pgs W/S Division I |  | Development of land and construction of approach road for Head Work site (Zone I) at Mallick Pratap Mouja (J.L. No 02) at Mandirbazar Block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under SWD-I, PHE Dte. (SM/18706) |  |  | ORD/000416/2024-2025 | 3736/SWD-I | 27/08/2024 | 45 | MAA MANASA VYAPAAR | 20.12 | 0 | 0
7414 | South 24 Pgs W/S Division I |  | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-I at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9379) |  |  | ORD/000423/2023-2024 | 1970/SWD-I | 24/08/2023 | 1062 | MAA MANASA VYAPAAR | 1837.75 | 0 | 5
7415 | South 24 Pgs W/S Division I |  | Diversion of Water for "Construction of Hume Pipe Culvert infront of 10.00 Mtr span for proposed Zone-I OHR Site at Mallick Pratap Mouza (J.L.NO-02, Plot No-964) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18706) |  |  | ORD/000433/2024-2025 | 3875/SWD-I | 03/09/2024 | 30 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.68 | 0 | 100
7416 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of MALLICKPRATAP MOUZA in MANDIRBAZAR (ZONE-I) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000512/2021-2022 | 1983/SWD-I | 27/01/2022 | 30 | RADIANT | 4.83 | 0 | 100
7417 | South 24 Pgs W/S Division I |  | Laying of 600 mm dia MS Secondary Grid Pipe from Mandirbazar GLR-Pump House to 600mm Dia DI Secondary Grid Pipeline under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.- South 24-Pgns.Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (SM/018706) |  |  | ORD/000549/2023-2024 | 2497/SWD-I | 06/10/2023 | 30 | S. ROY AND ASSOCIATES | 4.91 | 0 | 100
7418 | South 24 Pgs W/S Division I |  | Construction of boundary wall for proposed OHR Site of Zone-I within Mandirbazar block, Mouza-Mallik Protap under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 200.6 mtr.) under South 24-Pgns. W/S Division-I, PHE Dte. |  |  | ORD/000566/2021-2022 | 2694/SWD-I | 25/03/2022 | 90 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD. | 26.82 | 0 | 100
7419 | South 24 Pgs W/S Division I |  | Carriage of K9 DI pipes of various diameters from Dongaria WTP PHE stores to work site at Mandirbazar for laying of Secondary Grid pipeline within Mandirbazar Block under the Augmentation of LDS to extend the benefit of 100% households in Zone-I at Mandirbazar Block within the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas¿ under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/18706) |  |  | ORD/000662/2023-2024 | 2958/SWD-I | 24/11/2023 | 7 | M/S SHIBAM ENTERPRISE | 1.24 | 0 | 0
7420 | South 24 Pgs W/S Division I |  | Gap Negotiation for secondary grid of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18706] |  |  | ORD/000697/2024-2025 | 4499/SWD-I | 30/10/2024 | 60 | S. ROY AND ASSOCIATES | 56.45 | 0 | 0
7421 | South 24 Pgs W/S Division I |  | Three months trial run for secondary grid D.I pipe lines of different diameters of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur District South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/18706) |  |  | ORD/000873/2024-2025 | 4931/SWD-I | 03/12/2024 | 45 | M/S. GOUTAM ROY | 16.98 | 0 | 0
7422 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 276.01 | 0 | 0
7423 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1500 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8848] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000478/2023-2024 | 1991/AD | 04/08/2023 | 882 | M/S. S.S. ENTERPRISE | 2077.27 | 0 | 30
7424 | Alipore Division | Diamond Harbour Sub-Division | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VIII(A) of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000666/2023-2024 | 2600/AD | 31/08/2023 | 15 | GLOBUS CONSULTANCEY | 9.43 | 0 | 0
7425 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(A) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001020/2022-2023 | 293/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 4.41 | 0 | 99
7426 | Alipore Division | Diamond Harbour Sub-Division | Special repairing and restoration of distribution system at different places (Rangafala, Patra para etc.) of Arunnagar Belpukuria PWSS under zone-VIIIA at Kulpi Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001152/2023-2024 | 3198/AD | 04/10/2023 | 30 | M/S. SUMAN ENTERPRISE | 26.48 | 0 | 0
7427 | Alipore Division | Diamond Harbour Sub-Division | Land Developement and other allied works within the head works site under Zone No-VIIIA of Kulpi Block under "Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001397/2024-2025 | 5543/AD | 30/12/2024 | 45 | M/S. S.S. ENTERPRISE | 100.84 | 0 | 30
7428 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-VIIIA for providing 100% FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001456/2024-2025 | 14/AD | 03/01/2025 | 60 | SUBHO CONSTRUCTION | 361.14 | 0 | 0
7429 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(A) (Arunnagar, OHR Size-1500 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002099/2022-2023 | 338/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
7430 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000210/2023-2024 | 2019/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
7431 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000369/2023-2024 | 3233/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
7432 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000625/2023-2024 | 286/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
7433 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000672/2023-2024 | 425/AD | 22/01/2024 | 0 | Resource Division | 244.27 | 0 | 0
7434 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000859/2023-2024 | 766/AD | 03/02/2024 | 0 | Resource Division | 45.26 | 0 | 0
7435 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000938/2023-2024 | 1280/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7436 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Taktipur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000045/2023-2024 | 30/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
7437 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Taktipur Zone- II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/11876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000211/2024-2025 | 2594/AD | 19/06/2024 | 45 | M/S B.M. CONSTRUCTION | 37.59 | 0 | 0
7438 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Taktipur Abad Zone-I W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000279/2023-2024 | 1429/AD | 13/07/2023 | 45 | MAJUMDER ENTERPRISE | 44.25 | 0 | 100
7439 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Taktipur Abad (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000363/2022-2023 | 4118/AD | 18/08/2022 | 45 | SARADA CONSTRUCTION | 36.64 | 0 | 100
7440 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.07.2024 to 31.12.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000374/2024-2025 | 2793/AD | 01/07/2024 | 184 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
7441 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 22.07.2022 to 21.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000377/2022-2023 | 130/HQ-II/AD | 20/07/2022 | 6 | BISWADIP SIKDAR | 2.4 | 0 | 50
7442 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.07.2023 to 31.12.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000397/2023-2024 | 102/HQ-II/AD | 28/06/2023 | 183 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 30
7443 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Taktipur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000412/2024-2025 | 3063/AD | 25/07/2024 | 45 | RAJ ENTERPRISE | 38.71 | 0 | 0
7444 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( TAKTIPUR ABAD (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000493/2022-2023 | 1977/AD | 20/06/2022 | 45 | LEMNISCATE | 6 | 0 | 100
7445 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Taktipur Abad (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000504/2022-2023 | 5090/AD | 20/09/2022 | 300 | MAJUMDER ENTERPRISE | 260.4 | 0 | 100
7446 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 Nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Taktipur Abad (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000553/2022-2023 | 5727/AD | 13/10/2022 | 820 | M/S B.M. CONSTRUCTION | 211.19 | 0 | 85
7447 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Taktipur Abad Zone-II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000634/2023-2024 | 2462/AD | 24/08/2023 | 45 | M/S M. ENTERPRISE | 11.72 | 0 | 60
7448 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.12.2022 to 15.12.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001062/2022-2023 | 384/HQ-II/AD | 29/11/2022 | 15 | PRIYANKI SADHUKHAN | 0.2 | 0 | 85
7449 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Taktipur Zone-II W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001842/2023-2024 | 130/AD | 05/01/2024 | 60 | M/S B.M. CONSTRUCTION | 38.33 | 0 | 100
7450 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
7451 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000086/2022-2023 | 5593/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
7452 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000270/2023-2024 | 3069 | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
7453 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000463/2023-2024 | 4724/AD | 18/12/2023 | 0 | Resource Division | 27.96 | 0 | 0
7454 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000998/2023-2024 | 1791/AD | 27/03/2024 | 0 | Resource Division | 15.78 | 0 | 0
7455 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/00018/2023-2024 | BP-2023-24-02 | 25/04/2023 | 0 | WBSEDCL | 12.24 | 0 | 0
7456 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electric bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/01560/2022-2023 | BP-2022-23-451 | 20/03/2023 | 0 | WBSEDCL | 1.42 | 0 | 0
7457 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03867/2023-2024 | BP-2023-24-399 | 02/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0
7458 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I&II for Augmentation of Taktipur Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000433/2022-2023 | 3829/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE | 19.46 | 0 | 80
7459 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at Zone-I & II PH-2 of Taktipur Abad W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001905/2023-2024 | 1190/SMD | 22/03/2024 | 21 | M/S. S.S. ENTERPRISE | 10.85 | 0 | 0
7460 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH-1 of Taktipur Abad Augmentation W/S Scheme under JJM under south 24 pgs Mechanical Division PHE Dte. [Block- Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002021/2023-2024 | 868-AE-I-SMD | 04/08/2023 | 15 | M/S. S.S. ENTERPRISE | 0.82 | 0 | 0
7461 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Bantra water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] |  |  | ORD/000756/2023-2024 | 2687/SMD | 16/08/2023 | 90 | M/S.UTTAM KUMAR CHATTERJEE | 21.61 | 0 | 0
7462 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BANTRA PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018420) |  |  | ORD/000295/2023-2024 | 1660/SWD-I | 03/08/2023 | 900 | MALLICK CONSTRUCTION | 31.62 | 0 | 25
7463 | South 24 Pgs W/S Division I |  | Construction of platform for providing FHTC, restoration of damaged road due to laying of pipeline for BANTRA PWSS to accommodate FHTC in JAYNAGAR-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM /18498) |  |  | ORD/000423/2024-2025 | 3751/SWD-I | 28/08/2024 | 45 | M/S SALIM CONSTRUCTION | 82.76 | 0 | 0
7464 | South 24 Pgs W/S Division I |  | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BANTRA MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3046] [TSM/018420] |  |  | ORD/000438/2023-2024 | 2088/SWD-I | 29/08/2023 | 300 | M/S SALIM CONSTRUCTION | 659.79 | 0 | 50
7465 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bantra Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000968/2022-2023 | 1385/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.92 | 0 | 100
7466 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 72.16 | 0 | 0
7467 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Rakhalpur Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001595/2020-2021 | 5454/AD | 24/02/2021 | 365 | GROWING CONCERN | 100.46 | 74.33 | 95
7468 | Alipore Division |  | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Rakhalpur (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14987) |  |  | ORD/000343/2024-2025 | 2755/AD | 27/06/2024 | 75 | BIMALENDU GIRI | 167.27 | 0 | 0
7469 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Rakhalpur Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001595/2020-2021 | 5454/AD | 24/02/2021 | 365 | GROWING CONCERN | 100.46 | 0 | 95
7470 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000778/2023-2024 | 612/AD | 29/01/2024 | 0 | Resource Division | 8.18 | 0 | 0
7471 | Alipore Division | Diamond Harbour Sub-Division | HIRING VEHICLE BILL FOR MONTH OF DECEMBER '22 TO FEBRUARY'23 | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01275/2022-2023 | BP-2022-23-1055 | 31/03/2023 | 0 | GOPAL KUMAR JHA | 1.18 | 0 | 0
7472 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-IX including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000081/2020-2021 | 5444/AD | 24/02/2021 | 365 | GHOSH ENTERPRISE | 228.22 | 119.51 | 100
7473 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001188/2023-2024 | 555/DHSD | 31/10/2023 | 182 | GOPAL KUMAR JHA | 2.4 | 0 | 100
7474 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-1) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003148/2020-2021 | 256/DHSD | 25/11/2020 | 45 | ASMIT ENTERPRISE | 4.66 | 0 | 100
7475 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-2) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003149/2020-2021 | 261/DHSD | 26/11/2020 | 45 | SRIJON ENTERPRISE | 4.05 | 0 | 100
7476 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-3) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003150/2020-2021 | 262/DHSD | 26/11/2020 | 45 | SUJOY SADHUKHAN | 4.42 | 0 | 100
7477 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000852/2023-2024 | 790/AD | 03/02/2024 | 0 | Resource Division | 3.84 | 0 | 0
7478 | Alipore Division | Canning Sub-division | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000001/2022-2023 | 01/CSD | 01/04/2022 | 60 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 95
7479 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) at Lahiripur W/S Scheme (uncovered area), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000219/2023-2024 | 1024/AD | 13/06/2023 | 45 | SUPRITI ENTERPRISE | 59.73 | 0 | 99
7480 | Alipore Division | Canning Sub-division | Relaying of pipe line at node point 194-200, 217-209, 207-208 etc. at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000289/2022-2023 | 299/CSD | 23/05/2022 | 30 | S.P. CONSTRUCTION (I) | 3.61 | 0 | 90
7481 | Alipore Division | Canning Sub-division | DI Pipeline protection of Lahiripur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001635/2021-2022 | 1503/CSD | 15/02/2022 | 20 | GANGA TUBEWELL AND HARDWARE | 1.83 | 0 | 98
7482 | Alipore Division | Canning Sub-division | Extension of pipe line for FHTC work at Santigachhi of Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001645/2021-2022 | 1513/CSD | 15/02/2022 | 20 | C.S. CONSTRUCTION | 2.33 | 0 | 100
7483 | Alipore Division | Canning Sub-division | Relaying pipe line for uncovered FHTC work at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001646/2021-2022 | 1514/CSD | 15/02/2022 | 30 | S.P. CONSTRUCTION (I) | 3.24 | 0 | 95
7484 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Bidhan Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001665/2020-2021 | 1367/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 3.6 | 0 | 95
7485 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001666/2020-2021 | 1368/CSD | 08/01/2021 | 45 | GANGA TUBEWELL AND HARDWARE | 4.29 | 0 | 95
7486 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001668/2020-2021 | 1370/CSD | 08/01/2021 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 3.29 | 0 | 95
7487 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001671/2020-2021 | 1371/CSD | 08/01/2021 | 45 | S.C. ENTERPRISE (I) | 3.28 | 0 | 95
7488 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001672/2020-2021 | 1372/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 4.66 | 0 | 95
7489 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001673/2020-2021 | 1373/CSD | 08/01/2021 | 45 | A.P. CONSTRUCTION | 4.71 | 0 | 95
7490 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001674/2020-2021 | 1374/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 4.74 | 0 | 95
7491 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001675/2020-2021 | 1375/CSD | 08/01/2021 | 45 | ADITYA ENTERPRISE | 2.71 | 0 | 95
7492 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001676/2020-2021 | 1377/CSD | 08/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.25 | 0 | 95
7493 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001678/2020-2021 | 1378/CSD | 08/01/2021 | 45 | C.S. CONSTRUCTION | 2.4 | 0 | 95
7494 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001682/2020-2021 | 1379/CSD | 08/01/2021 | 45 | GANGA TUBEWELL AND HARDWARE | 4.47 | 0 | 95
7495 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001683/2020-2021 | 1380/CSD | 08/01/2021 | 45 | M. CHAKRABORTY | 4.47 | 0 | 95
7496 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001684/2020-2021 | 1381/CSD | 08/01/2021 | 45 | MODERN CONSTRUCTION | 4.47 | 0 | 95
7497 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001685/2020-2021 | 1382/CSD | 08/01/2021 | 45 | SUKANTA HALDER | 4.42 | 0 | 95
7498 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001686/2020-2021 | 1383/CSD | 08/01/2021 | 45 | KAYAL ENTERPRISE | 3.47 | 0 | 95
7499 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001687/2020-2021 | 1384/CSD | 08/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.48 | 0 | 95
7500 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001688/2020-2021 | 1387/CSD | 18/01/2021 | 45 | A.P. CONSTRUCTION | 3.41 | 0 | 95
7501 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001689/2020-2021 | 1388/CSD | 18/01/2021 | 45 | M. CHAKRABORTY | 4.01 | 0 | 95
7502 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001690/2020-2021 | 1389/CSD | 18/01/2021 | 45 | SHREEMAA ENTERPRISE | 4 | 0 | 95
7503 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001691/2020-2021 | 1390/CSD | 18/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.99 | 0 | 95
7504 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001692/2020-2021 | 1391/CSD | 18/01/2021 | 45 | BENGAL BUILDERS | 3.98 | 0 | 95
7505 | Alipore Division | Canning Sub-division | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001768/2020-2021 | 1455/CSD | 27/01/2021 | 60 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 98
7506 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002040/2020-2021 | 1376/CSD | 08/01/2021 | 45 | SANTANU GHOSH | 2.94 | 0 | 95
7507 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Uttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000117/2020-2021 | 1396/SWD-I | 11/12/2020 | 120 | SRIJON ENTERPRISE | 86.18 | 42.61 | 60
7508 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme forUttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with alliedworks under SWD - I, P.H.E. Dte District South 24 Parganas | AE SWSD-I |  | ORD/000328/2020-2021 | 1396/SWD-I JJM | 11/12/2020 | 120 | SRIJON ENTERPRISE | 85.74 | 0 | 60
7509 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6136) PART-IV | AE SWSD-I |  | ORD/000463/2022-2023 | 2773/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 3.07 | 0 | 100
7510 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for Booth 170 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000116/2020-2021 | 1394/SWD-I | 11/12/2020 | 120 | PROJECT AND MAINTENANCE | 92.1 | 0 | 90
7511 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Moukhali W/S Scheme for Durgapur Moukhali and Jagat Ballavpur under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000309/2020-2021 | 1414/SWD- I | 14/12/2020 | 120 | SUPRITI ENTERPRISE | 96.89 | 0 | 100
7512 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6127) Part -H | AE SWSD-I |  | ORD/000470/2022-2023 | 2782/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.51 | 0 | 100
7513 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Srinarayanpur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001349/2020-2021 | 5199/AD | 12/02/2021 | 365 | M/S. JHARNA ENTERPRISE | 155.66 | 83.82 | 97
7514 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000770/2023-2024 | 604/AD | 29/01/2024 | 0 | Resource Division | 18.94 | 0 | 0
7515 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Manasadwip Water Supply Scheme, Block - Sagar, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001257/2020-2021 | 2277/AD | 12/10/2020 | 365 | PIKASU BOSE | 128 | 2.21 | 100
7516 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 0 | 95
7517 | Alipore Division |  | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) |  |  | ORD/001422/2022-2023 | 10980/AD | 07/02/2023 | 30 | ANANDA MAITY | 12.91 | 0 | 100
7518 | Alipore Division |  | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) |  |  | ORD/001824/2022-2023 | 12120/AD | 01/03/2023 | 912 | BENGAL BUILDERS | 449.37 | 0 | 34
7519 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000699/2023-2024 | 469/AD | 24/01/2024 | 0 | Resource Division | 4.8 | 0 | 0
7520 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Narayanpur Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000086/2020-2021 | 5309/AD | 18/02/2021 | 1627 | AVIK ENTERPRISE | 118.2 | 26.57 | 90
7521 | Alipore Division | Raidighi Sub-Division | Laying distribution line and construction of masonry valve chamber and others miscellaneous work for providing FHTC at Zone-VIII of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000346/2022-2023 | 4073/AD | 18/08/2022 | 30 | L.N. ENTERPRISE | 14.68 | 0 | 90
7522 | Alipore Division | Raidighi Sub-Division | Horizontally boring for providing FHTC at Zone-VIII of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000425/2022-2023 | 281/RSD | 01/09/2022 | 60 | L.N. ENTERPRISE | 0.84 | 0 | 100
7523 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Jatardeul Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000511/2020-2021 | 5196/AD | 12/02/2021 | 365 | G.B. CONSTRUCTION & CO. | 125.27 | 47.88 | 98
7524 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 13.65 | 100
7525 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000070/2022-2023 | 5147/AD | 21/09/2022 | 0 | Resource Division | 18.45 | 0 | 0
7526 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 137 to 140 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000308/2020-2021 | 1412/SWD-I | 14/12/2020 | 120 | BHOLANATH CONSTRUCTION | 96.19 | 0 | 100
7527 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-IV (Gilarchat PWSS) including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District-South 24-Parganas, Block-Mathurapur-II under Raidighi Sub-Division of Alipore Division, PHE Dte. (Phase-I). | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000013/2022-2023 | 205/AD | 11/04/2022 | 1027 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 251.07 | 0 | 50
7528 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-IV of Mathurapur - II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000016/2022-2023 | 212/AD | 11/04/2022 | 1246 | UNITED BUILDERS | 337.79 | 0 | 70
7529 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000659/2023-2024 | 263/AD | 15/01/2024 | 0 | Resource Division | 33.26 | 0 | 0
7530 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 2nd Tubewell site for Sumatinagar (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13569) (SM/09394) (SM/08792) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000347/2025-2026 | 3103/AD | 02/07/2025 | 45 | M/S. MA BHABANI CONSTRUCTION | 5.58 | 0 | 0
7531 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000778/2022-2023 | 6649/AD | 14/11/2022 | 30 | MONCON INDIA | 10.01 | 0 | 100
7532 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 120 | UCON | 140.93 | 0 | 100
7533 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000695/2023-2024 | 465/AD | 24/01/2024 | 0 | Resource Division | 11.27 | 0 | 0
7534 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Manasadwip W/S Scheme (Phase-A) & Sumatinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[ W/O NO 520/AD, 24.08.21, T.NO. 1791/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | VCH/002609/2021-2022 | BP-2021-22-512 | 22/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 0
7535 | Alipore Division | Kakdwip Sub-Division | HIRE bill for month of MAY-JUL23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | BILL/03539/2023-2024 | BP-2023-24-1270 | 27/03/2024 | 0 | RAJKUMAR MANNA | 4.56 | 0 | 0
7536 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Achintyanagar W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08628) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000162/2024-2025 | 2513/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
7537 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Achintyanagar Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000271/2021-2022 | 1718/AD | 17/08/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 251.54 | 0 | 70
7538 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 4th Tubewell Site of Achintyanagar W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000430/2022-2023 | 203/KSD | 01/06/2022 | 7 | M/S B. ENTERPRISE | 0.61 | 0 | 100
7539 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Achintyanagar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000999/2023-2024 | 506/KSD | 03/10/2023 | 7 | M/S B. ENTERPRISE | 3.74 | 0 | 100
7540 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000317/2023-2024 | 3126/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
7541 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000780/2023-2024 | 614/AD | 29/01/2024 | 0 | Resource Division | 12.28 | 0 | 0
7542 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bagdanga Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000014/2021-2022 | 3163/AD | 09/11/2021 | 365 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 90.17 | 0 | 26
7543 | Alipore Division | Kakdwip Sub-Division | Relaying of DI pipeline with ancillary pipeline protection work for crossing over pond (9 nos.) at Bagbagan of Gosaba W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000287/2023-2024 | 184/CSD | 22/05/2023 | 30 | SUSHANTA MANDAL | 4.74 | 0 | 99
7544 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000294/2023-2024 | 3061/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
7545 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000800/2023-2024 | 645/AD | 30/01/2024 | 0 | Resource Division | 10 | 0 | 0
7546 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000085/2022-2023 | 277/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.77 | 0 | 85
7547 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Narayantala, Naliakhali & Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000086/2022-2023 | 278/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.79 | 0 | 85
7548 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.76 | 0 | 85
7549 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000207/2021-2022 | 1424/AD | 27/07/2021 | 365 | PROJECT & MAINTENANCE | 129.74 | 0 | 97
7550 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000080/2023-2024 | 23/DHSD | 25/04/2023 | 184 | GOPAL KUMAR JHA | 2.4 | 0 | 50
7551 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-VII at Kamarpole of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-950] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000305/2023-2024 | 1508/AD | 15/07/2023 | 1197 | JYOTY SOLAR POWER | 423.33 | 0 | 15
7552 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-VII including Operation and Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001150/2021-2022 | 5301/AD | 04/01/2022 | 1547 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 137.23 | 0 | 25
7553 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000013/2021-2022 | 5619/AD | 25/01/2022 | 0 | Resource Division | 17.45 | 0 | 0
7554 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000614/2023-2024 | 293/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
7555 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% FHTC household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IV of Diamond Harbour-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 1450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000341/2023-2024 | 3601/AD | 25/10/2023 | 609 | CREATION CONSTRUCTION | 403.02 | 0 | 37
7556 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-IV including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001325/2021-2022 | 5934/AD | 11/02/2022 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 366.63 | 0 | 0
7557 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Netra, OHR Size-900) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002369/2022-2023 | 322/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
7558 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
7559 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000120/2022-2023 | 12050/AD | 27/02/2023 | 0 | Resource Division | 3.51 | 0 | 0
7560 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000877/2023-2024 | 751/AD | 03/02/2024 | 0 | Resource Division | 17.38 | 0 | 0
7561 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000922/2023-2024 | 1264/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7562 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00006/2022-2023 | BP-2022-23-503 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 6.59 | 0 | 0
7563 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00007/2022-2023 | BP-2022-23-504 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.41 | 0 | 0
7564 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00039/2022-2023 | BP-2022-23-503 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0
7565 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00040/2022-2023 | BP-2022-23-504 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0
7566 | Alipore Division | Canning Sub-division | Inter connection from TW No. -1, 2 and 3 to distribution line and supply materials at Jibantala Water Supply Scheme (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000073/2022-2023 | 1037/AD | 23/05/2022 | 30 | KAMALA ENTERPRISE (I) | 7.68 | 0 | 95
7567 | Alipore Division | Canning Sub-division | Laying of additional pipeline with other allied works at Jibantala (Zone-I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001030/2024-2025 | 4940/AD | 03/12/2024 | 45 | M/S. JHARNA ENTERPRISE | 20.96 | 0 | 0
7568 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002056/2023-2024 | 572/AD | 29/01/2024 | 425 | VISHAL CONSTRUCTION CO. | 93.43 | 0 | 90
7569 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002057/2023-2024 | 573/AD | 29/01/2024 | 180 | ANKUSH CONSTRUCTION AND CO. | 26.61 | 0 | 70
7570 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 2 for Jibantala (Zone - II) Water Supply Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002131/2024-2025 | 390/AD | 30/01/2025 | 30 | KUNDU CONSTRUCTION CO. | 14.2 | 0 | 0
7571 | Alipore Division | Canning Sub-division | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | VCH/001719/2022-2023 | BP-2022-23-432 | 17/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 5.53 | 0 | 0
7572 | Alipore Division | Canning Sub-division | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | VCH/001720/2022-2023 | BP-2022-23-431 | 17/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.58 | 0 | 0
7573 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 0 | 100
7574 | Alipore Division | Diamond Harbour Sub-Division | Shifting of distribution pipeline due to road widening programme by PWD at Sherpur Sirakole connector and Sherpur Bazar area of existing water supply scheme of Magrahat-I Block and inter connection between 03(three) nos. existing tube well of Fatepur W/S Scheme to the OHR of Falta Zone-VII for providing FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000444/2022-2023 | 4958/AD | 16/09/2022 | 30 | SUPRITI ENTERPRISE | 20.53 | 0 | 100
7575 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VII including Operation and Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001327/2021-2022 | 5935/AD | 11/02/2022 | 365 | SUPRITI ENTERPRISE | 279.46 | 0 | 95
7576 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000019/2022-2023 | 1196/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
7577 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000030/2021-2022 | 4348/AD | 04/03/2022 | 0 | Resource Division | 26.84 | 0 | 0
7578 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000032/2021-2022 | 4347/AD | 04/03/2022 | 0 | Resource Division | 8.65 | 0 | 0
7579 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000033/2021-2022 | 4345/AD | 04/03/2022 | 0 | Resource Division | 14.64 | 0 | 0
7580 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000072/2022-2023 | 4851/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
7581 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000098/2022-2023 | 7493/AD | 26/11/2022 | 0 | Resource Division | 2.69 | 0 | 0
7582 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur piped water supply scheme ( Mathurapur-I, Zone-VII) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) |  |  | ORD/000569/2021-2022 | 3670/AD | 22/11/2021 | 365 | M/S. J.K. TRIPATHI & SONS | 80.12 | 0 | 100
7583 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 6636/AD | 15/03/2022 | 0 | Resource Division | 326.7 | 0 | 0
7584 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000605/2023-2024 | 235/AD | 11/01/2024 | 0 | Resource Division | 11.33 | 0 | 0
7585 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000087/2023-2024 | 498/AD | 11/05/2023 | 963 | JAL PRAVAHIKA PVT. LTD. | 569.23 | 0 | 41
7586 | Alipore Division | Raidighi Sub-Division | Construction of 700M3 capacity 20m straging height R.C.C OHR as per departmental design drawing & specification including R.C.C. bored pile & pile cap upto pedestal at Mathurapur-I block zone- v Site for Mega surface water based water supply scheme for Falta Mathurapur project under Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002152/2019-2020 | 7722/AD | 26/02/2020 | 90 | JAL PRAVAHIKA PVT. LTD. | 128.67 | 0 | 80
7587 | Alipore Division | Raidighi Sub-Division | Protection of pipeline at Zone -V Mathurapur -I block under Raidighi Sub Division of Alipore Division, PHE Dte. (Tender no.- Not found) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002164/2019-2020 | 681/RSD | 03/01/2020 | 0 | M/S MAA ENTERPRISE | 4.63 | 0 | 100
7588 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000599/2023-2024 | 231/AD | 11/01/2024 | 0 | Resource Division | 24.54 | 0 | 0
7589 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000037/2021-2022 | 1102/SWD-I | 25/10/2021 | 120 | SUPRITI ENTERPRISE | 82.25 | 0 | 100
7590 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000079/2021-2022 | 1202/SWD-I JJM | 25/10/2021 | 120 | SUPRITI ENTERPRISE | 82.17 | 0 | 60
7591 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Moukhali W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8295) Part -C | AE SWSD-I |  | ORD/000460/2022-2023 | 2778/SWD-I | 31/01/2023 | 45 | RIDIP ENTERPRISE | 7.14 | 0 | 100
7592 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Laxmi Janardanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000068/2023-2024 | 49/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
7593 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 3rd tubewell site of Laxmi Janardanpur W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000432/2022-2023 | 205/KSD | 01/06/2022 | 7 | AQUATECH ENGINEER | 0.89 | 0 | 100
7594 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Lakshmi Janardhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000464/2022-2023 | 299/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.77 | 0 | 100
7595 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Laxmi Janardanpur W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000584/2023-2024 | 2438/AD | 22/08/2023 | 45 | DEEPAK ENTERPRISE | 31.6 | 0 | 100
7596 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
7597 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 184 | BADSHA ALOM | 2.4 | 0 | 0
7598 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001607/2021-2022 | 605/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.55 | 0 | 100
7599 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Laxmi Janardanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001649/2022-2023 | 11316/AD | 10/02/2023 | 1076 | DEEPAK ENTERPRISE | 603.25 | 0 | 45
7600 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
7601 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000048/2022-2023 | 3901/AD | 12/08/2022 | 0 | Resource Division | 10.09 | 0 | 0
7602 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000306/2023-2024 | 3101/AD | 28/09/2023 | 0 | Resource Division | 12.99 | 0 | 0
7603 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000314/2023-2024 | 3123/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
7604 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000569/2023-2024 | 78/AD | 03/01/2024 | 0 | Resource Division | 14.52 | 0 | 0
7605 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | BILL/00015/2023-2024 | BP-2023-24-47 | 18/05/2023 | 0 | WBSEDCL | 3.74 | 0 | 0
7606 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 of Laxmi Janardanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000058/2023-2024 | 1226/SMD | 04/05/2023 | 90 | J.K. ENGINEERING CO. | 10.86 | 0 | 0
7607 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at P.H. No-3 of Laxmijanardanpur & Zone-I, PH-1 of Bhajna water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Pathar Pratimar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000569/2024-2025 | 815-AE-I-SMD | 18/06/2024 | 15 | SHIVAM ENTERPRISE | 0.78 | 0 | 0
7608 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-3 of Laxmijanardanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/003009/2023-2024 | 590A-AE-I-SMD | 25/05/2023 | 15 | J.K. ENGINEERING CO. | 0.22 | 0 | 0
7609 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00703/2023-2024 | BP-2023-24-103 | 04/07/2023 | 0 | WBSEDCL | 8.18 | 0 | 0
7610 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bijoyrampur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000542/2022-2023 | 473/SMD | 20/02/2023 | 90 | KARUNAMOY ENGINEERING | 26.11 | 0 | 50
7611 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supplying and fitting fixing of LED Glow sign board, betterment of external lighting arrangement etc. at P.H. No. - 1 under Bijoyrampur Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/11496) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000725/2024-2025 | 1035/AE-II/SMD | 13/08/2024 | 15 | PS & ASSOCIATES | 0.78 | 0 | 0
7612 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply & delivery of Submersible Pumping Machinery for Bijoyrampur w/s scheme under SMD, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/001059/2023-2024 | ...789/AE-II/SMD | 17/07/2023 | 15 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0
7613 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BIJOYRAMPURPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000033/2022-2023 | 917/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 0 | 100
7614 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BIJOYRAMPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 821] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000150/2022-2023 | 1390/SWD-I | 21/09/2022 | 90 | JAYANTA KUMAR DEY | 107.26 | 0 | 95
7615 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
7616 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Bijoyrampur PWSS Tubewell site (Bahadurpur) in the Arsenic affected areas of South 24 pgs. Dist in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000244/2023-2024 | 1486/SWD-I | 19/07/2023 | 15 | MAA LAXMI ENTERPRISE | 3.81 | 0 | 100
7617 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Bijoyrampur PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11496) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000248/2024-2025 | 2668/SWD-I | 07/06/2024 | 45 | TIYASHA ENTERPRISE | 81.5 | 0 | 15
7618 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "BIJOYRAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000397/2022-2023 | 460/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 0 | 100
7619 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BIJOYRAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11496) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000445/2022-2023 | 2664/SWD-I | 18/01/2023 | 60 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 6.05 | 0 | 100
7620 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BIJOYRAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000508/2022-2023 | 2906/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 100
7621 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BIJOYRAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000591/2022-2023 | 3111/SWD-I | 24/02/2023 | 708 | DEBASHIS DAS | 15.89 | 0 | 100
7622 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed BIJOYRAMPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000809/2022-2023 | 3701/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.95 | 0 | 100
7623 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000015/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.06 | 0 | 0
7624 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000107/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 26.06 | 0 | 0
7625 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.49 | 0 | 0
7626 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000083/2020-2021 | 5306/AD | 18/02/2021 | 365 | SPA ENTERPRISE | 281.51 | 0 | 85
7627 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Bijoynagar Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000084/2022-2023 | 1131/AD | 26/05/2022 | 30 | M/S. BISWAS CONSTRUCTION(I) | 18.18 | 0 | 91
7628 | Alipore Division | Canning Sub-division | Relaying and extension of pipeline due to FHTC work at Bijoynagar Water Supply Scheme Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001064/2021-2022 | 5299/AD | 04/01/2022 | 60 | ANUP PAUL | 28.3 | 0 | 100
7629 | Alipore Division | Canning Sub-division | Laying of pipeline of uncovered FHTC work area of Bijoynagar Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001178/2022-2023 | 8773/AD | 21/12/2022 | 30 | MONDAL ENTERPRISE - 2 (SDK) | 21.86 | 0 | 0
7630 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households of Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001770/2020-2021 | 1456/CSD | 27/01/2021 | 45 | SUSHANTA MANDAL | 1.26 | 1.25 | 0
7631 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gayadham W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000161/2023-2024 | 683/AD | 17/05/2023 | 686 | M/S B. ENTERPRISE | 28.69 | 0 | 100
7632 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gayadham W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000162/2023-2024 | 684/AD | 17/05/2023 | 30 | M/S. JOYGURU ENTERPRISE | 9.56 | 0 | 0
7633 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gayadham PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000187/2024-2025 | 923/AD | 05/03/2025 | 60 | M/S B. ENTERPRISE | 53.26 | 0 | 0
7634 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Gayadham Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000193/2023-2024 | 945/AD | 05/06/2023 | 667 | M/S B. ENTERPRISE | 297.45 | 0 | 86
7635 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Gayadham Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000304/2022-2023 | 3840/AD | 08/08/2022 | 15 | M/S. MANDAL ENTERPRISE | 7.72 | 0 | 0
7636 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gayadham W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000399/2022-2023 | 4529/AD | 01/09/2022 | 45 | MAMONI ENTERPRISE | 36.34 | 0 | 0
7637 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GAYADHAM PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000466/2022-2023 | 1689/AD | 13/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.77 | 0 | 100
7638 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gayadham W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000558/2024-2025 | 3786/AD | 19/09/2024 | 80 | SARADA CONSTRUCTION | 40.8 | 0 | 100
7639 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gayadham PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003145/2023-2024 | 383/KSD | 22/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
7640 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000066/2022-2023 | 3954/AD | 12/08/2022 | 0 | Resource Division | 37.1 | 0 | 0
7641 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000295/2023-2024 | 3090/AD | 28/09/2023 | 0 | Resource Division | 31.28 | 0 | 0
7642 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000577/2023-2024 | 53/AD | 03/01/2024 | 0 | Resource Division | 6.39 | 0 | 0
7643 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection of Gayadham PH-1 W/S Scheme Application No- 1007193390 Reference ID:- 106229287 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/02232/2024-2025 | BP-2024-25-510 | 19/12/2024 | 0 | WBSEDCL | 6.06 | 0 | 0
7644 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gayadham water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000795/2022-2023 | 282/SMD | 01/02/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 19.4 | 0 | 0
7645 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamaria Zone-III water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000571/2022-2023 | 590/SMD | 24/02/2023 | 797 | AHALYA ENGINEERING WORKS | 22.93 | 0 | 45
7646 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 & 2 of Kamaria Zone-III W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) (SM/11647) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002463/2024-2025 | 1535/SMSD | 19/11/2024 | 15 | AHALYA ENGINEERING WORKS | 0.61 | 0 | 0
7647 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-III) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000083/2022-2023 | 1194/SWD-I | 02/09/2022 | 30 | AYUB KHAN | 37.76 | 0 | 10
7648 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land and other allied works for KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district.(SM/11647) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000224/2024-2025 | 2642/SWD-I | 07/06/2024 | 45 | AYUSH ENTERPRISE | 16.77 | 0 | 0
7649 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-III) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000279/2022-2023 | 1840/SWD-I | 11/11/2022 | 872 | MANASH GHOSH | 391.21 | 0 | 45
7650 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Kamaria (Zone-III) of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000380/2022-2023 | 2214/SWD_I | 13/12/2022 | 720 | ALISHA CONSTRUCTION | 11.52 | 0 | 100
7651 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-III PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011003] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000732/2022-2023 | 3582/SWD-I | 22/03/2023 | 15 | AYUB KHAN | 4.35 | 0 | 10
7652 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000077/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 23.23 | 0 | 0
7653 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-VIII at Nimpith Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000201/2022-2023 | 1557/SWD-I | 13/10/2022 | 300 | RAJ BROTHERS | 268.09 | 0 | 0
7654 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VIII at Nimpith mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 7302] | AE BSD |  | ORD/000345/2022-2023 | 2150/SWD-I | 08/12/2022 | 811 | M/S. S.S. ENTERPRISE | 556.22 | 0 | 75
7655 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000085/2022-2023 | 3001/SWD-I | 20/02/2023 | 0 | Resource Division | 44.98 | 0 | 0
7656 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | Assistant Engineer | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 740 | TARUN ENTERPRISE | 922.07 | 0 | 70
7657 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Three months trial run for Secondary Grid for Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [SM/11262] [w.e.f. 01/02/2025 to 01/05/2025] | Assistant Engineer | JE2 | ORD/001128/2024-2025 | 191/SWD-I | 17/01/2025 | 105 | AVIK ENTERPRISE | 30.87 | 0 | 90
7658 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000068/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 234.99 | 0 | 0
7659 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000145/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 29.44 | 0 | 0
7660 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II | JE2 | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 705 | PROJECT AND MAINTENANCE | 418.32 | 0 | 95
7661 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road from Baneswarpur Bazar to Nabin Sangha for providing 100% FHTC in Zone-III at PRATAPBERIA (Baneswarpur) of Magrahat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.- South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11266) | AE SWSD-II | JE2 | ORD/000732/2023-2024 | 437/SWD-I | 22/01/2024 | 15 | PROJECT AND MAINTENANCE | 7.09 | 0 | 25
7662 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE2 | RTOR000132/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 25.27 | 0 | 0
7663 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Payment for Electricity Bill for New connection under SMD PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/03112/2023-2024 | BP-2023-24-327 | 16/10/2023 | 0 | WBSEDCL | 5.29 | 0 | 0
7664 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Pirkhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000489/2022-2023 | 247/SMD | 27/01/2023 | 1070 | T.S. CONSTRUCTION | 25.93 | 0 | 70
7665 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Incorporation of LED Glow sign board including other allied works at PH No-1 under Pirkhali Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Bishnupur-I) (SM/11731) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/002462/2023-2024 | 186-AE-II-SMD | 21/02/2024 | 15 | KUNAL ENTERPRISE | 0.75 | 0 | 100
7666 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PIRKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11731) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000110/2023-2024 | 517/SWD-I | 10/05/2023 | 60 | DEBAYAN MONDAL | 5.75 | 0 | 100
7667 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for PIRKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11731] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000173/2022-2023 | 1448/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.27 | 0 | 100
7668 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
7669 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of PIRKHALI AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000232/2021-2022 | 1977/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 0 | 100
7670 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, laying of pipeline and other allied works for ground water based PIRKHALI PWSS to accomodate FHTC in Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. for Augmentation of Surface water based water supply scheme in the Arsenic affected areas of South 24 Paraganas District. (SM/11731) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000391/2024-2025 | 3631/SWD-I | 20/08/2024 | 407 | S.C. ENTERPRISE | 107.87 | 0 | 10
7671 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based PIRKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 815 nos.] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000422/2022-2023 | 2583/SWD-I | 10/01/2023 | 903 | LOKENIRMAN | 141.2 | 0 | 100
7672 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PIRKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011789] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000519/2022-2023 | 2909/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 0 | 0
7673 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for PIRKHALI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11731] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000695/2024-2025 | 4490/SWD-I | 30/10/2024 | 147 | B.K.ENTERPRISE | 15.88 | 0 | 100
7674 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000112/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 38.38 | 0 | 0
7675 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 997] (TSM/014717) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000020/2023-2024 | 91/AD | 11/04/2023 | 708 | MODERN CONSTRUCTION | 164.78 | 0 | 100
7676 | Alipore Division | Canning Sub-division | Laying damaged pipe line from PH-1 to Sadanandar More and Hatberia More to House of Chandika Show at Deuli Water Supply Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000105/2021-2022 | 1189/AD | 07/07/2021 | 45 | M/S S AND P CONSTRUCTION | 38.01 | 0 | 100
7677 | Alipore Division | Canning Sub-division | Laying pipe line for uncovered habitation of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli and Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000543/2024-2025 | 3714/AD | 12/09/2024 | 30 | AHANA ENTERPRISE | 8.09 | 0 | 0
7678 | Alipore Division | Canning Sub-division | Bamboo pile walling for protection of pipe line for Ground Water Based of Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000751/2024-2025 | 4425/AD | 05/11/2024 | 180 | AHANA ENTERPRISE | 30.06 | 0 | 100
7679 | Alipore Division | Canning Sub-division | Laying pipeline at Head Work Site for washed of OHR and parallel line of Augmentation of Deuli (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001027/2023-2024 | 1338/AD | 05/03/2024 | 40 | NARAYAN ENTERPRISE | 5.91 | 0 | 100
7680 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001119/2022-2023 | 8848/AD | 22/12/2022 | 45 | BHATTACHARJEE & CO. | 39.02 | 0 | 0
7681 | Alipore Division | Canning Sub-division | Road restoration work for the road damage due to laying of pipe line on Augmentation & Retrofitting of Deuli (Zone-I & II) PWSS, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ at Deuli (Zone-I) ] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001632/2023-2024 | 1139/CSD | 31/10/2023 | 30 | SUKANTA HALDER | 3.06 | 0 | 100
7682 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001760/2022-2023 | 11942/AD | 24/02/2023 | 45 | M/S SEIKH ENTERPRISE | 7.34 | 0 | 95
7683 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001761/2022-2023 | 11943/AD | 24/02/2023 | 45 | M/S SEIKH ENTERPRISE | 7.08 | 0 | 85
7684 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Deuli & adjoining Mouzas (Kaluakhali & Mukhajyapara Mouza) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001943/2022-2023 | 5608/AD | 29/09/2022 | 45 | M/S APEX ENGINEERING | 2.61 | 0 | 80
7685 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 1 of Augmentation of Deuli (Zone - I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002458/2023-2024 | 1588/CSD | 23/02/2024 | 30 | SUKANTA HALDER | 1.59 | 0 | 100
7686 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 2 of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002501/2023-2024 | 1598/CSD | 28/02/2024 | 30 | NAZRUL ENTERPRISE | 2 | 0 | 100
7687 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/04083/2023-2024 | BP-2023-24-421 | 16/12/2023 | 0 | WBSEDCL | 24.65 | 0 | 0
7688 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at P.H. No-1 & 2 of Deuli & Adjoining water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000098/2024-2025 | 930/SMSD | 28/06/2024 | 15 | WIZARDTECH SOLUTION | 0.78 | 0 | 100
7689 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Deuli & Adjoining Mouza water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000523/2022-2023 | 392/SMD | 15/02/2023 | 899 | CHANDIMATA ELECTRICALS | 21.52 | 0 | 100
7690 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Kaluakhali Mukherjee Para, PH-1, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002773/2023-2024 | 140/SMSD | 05/02/2024 | 15 | CHANDIMATA ELECTRICALS | 0.88 | 0 | 100
7691 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Chandakhali to Dhapdhapi More 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01665/2024-2025 | BP-2024-25-772 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.74 | 0 | 0
7692 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00006/2023-2024 | BP-2023-24-33 | 18/05/2023 | 0 | WBSEDCL | 12.09 | 0 | 0
7693 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Padmajala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000808/2022-2023 | 271/SMD | 01/02/2023 | 90 | SARKAR ELECTRICAL | 10.75 | 0 | 100
7694 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Padmajala W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002207/2023-2024 | 1423/SMSD | 21/11/2023 | 15 | SARKAR ELECTRICAL | 0.9 | 0 | 100
7695 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main for piped water supply scheme at PADMAJOLA for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000058/2023-2024 | 275/SWD-I | 24/04/2023 | 90 | N.G. ENGINEERING | 111.21 | 0 | 70
7696 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PADMAJALA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000309/2022-2023 | 1934/SWD-I | 21/11/2022 | 30 | MUNNA AGROTECH ENTERPRISE | 20.07 | 0 | 100
7697 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at PADMAJALA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000310/2022-2023 | 1935-SWD-I | 21/11/2022 | 60 | JYOTI ENTERPRISE | 5.46 | 0 | 100
7698 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at PADMAJALA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1761) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000322/2022-2023 | 2018/SWD-I | 29/11/2022 | 90 | N.G. ENGINEERING | 196.66 | 0 | 70
7699 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PADMOJOLA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000348/2021-2022 | 1909/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.76 | 0 | 100
7700 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall at head work site, platform for providung FHTC, restoration of road and other allied works for Augmentation of Ground Water based PADMAJALA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. (SM/13766) [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000886/2024-2025 | 4991/SWD-I | 05/12/2024 | 135 | G M ENTERPRISE (BERHAMPORE) | 68.43 | 0 | 80
7701 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000194/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 14.59 | 0 | 0
7702 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of December'22 to January'2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00461/2022-2023 | BP-2022-23-791 | 22/02/2023 | 0 | DEEPAK KUMAR PRASAD | 0.79 | 0 | 0
7703 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000067/2023-2024 | 48/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
7704 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000127/2024-2025 | 2405/AD | 07/06/2024 | 30 | SANJIVINI ENTERPRISE | 11.78 | 0 | 0
7705 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BANASHYAM NAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000463/2022-2023 | 2490/AD | 27/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.47 | 0 | 100
7706 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Banashyamnagar W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000587/2023-2024 | 2344/AD | 18/08/2023 | 45 | UNIQUE AGENCY (PARTNER) | 58.37 | 0 | 90
7707 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000668/2022-2023 | 6153/AD. | 01/11/2022 | 1157 | UNIQUE AGENCY | 333.06 | 0 | 50
7708 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 02 nos. Pump House for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000784/2022-2023 | 6538/AD | 11/11/2022 | 120 | M/S A.K. GHATAK | 273.49 | 0 | 55
7709 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000887/2023-2024 | 165/HQ-II/AD | 24/08/2023 | 184 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 45
7710 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000974/2023-2024 | 2993/AD | 06/10/2023 | 45 | M/S RAKESH ENTERPRISE | 33.2 | 0 | 0
7711 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Banashyamnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11848) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001366/2024-2025 | 5495/AD | 27/12/2024 | 131 | SARADA CONSTRUCTION | 52.11 | 0 | 100
7712 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001828/2022-2023 | 520/HQ-II/AD | 27/02/2023 | 181 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 100
7713 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
7714 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.03.2024 to 31.08.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002317/2023-2024 | 1103/AD | 23/02/2024 | 182 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 100
7715 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000089/2023-2024 | 535/AD | 12/05/2023 | 0 | Resource Division | 10.85 | 0 | 0
7716 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000520/2023-2024 | 4938/AD | 22/12/2023 | 0 | Resource Division | 16.27 | 0 | 0
7717 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000741/2023-2024 | 576/AD | 29/01/2024 | 0 | Resource Division | 1.94 | 0 | 0
7718 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000947/2023-2024 | 1681/AD | 22/03/2024 | 0 | Resource Division | 23.18 | 0 | 0
7719 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Banashyam Nagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000354/2022-2023 | 3758/SMD | 29/12/2022 | 90 | M.S.ENTERPRISE | 22.24 | 0 | 0
7720 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/04623/2023-2024 | BP-2023-24-480 | 07/02/2024 | 0 | WBSEDCL | 14.26 | 0 | 0
7721 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Kashiadanga PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000056/2024-2025 | 576/SMSD | 10/05/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
7722 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kashidanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000499/2022-2023 | 317/SMD | 06/02/2023 | 881 | B.T.PROJECTS PVT.LTD. | 26.78 | 0 | 100
7723 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Kashiadanga, PH-1 under Bhangar-I Block water supply scheme under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000543/2024-2025 | 818/SMSD | 11/06/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
7724 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at P.H. No-1 & 2 of Kashiadanga water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[Bhangar-I] [SM/13512] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000868/2024-2025 | 624/SMSD | 21/05/2024 | 15 | SHRI KRISHNA ENTERPRISE | 0.78 | 0 | 100
7725 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kashiadanga W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) (SM/13512) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002405/2024-2025 | 921-SMSD | 26/06/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.58 | 0 | 100
7726 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KASHIA DANGA PWSS of BHANGAR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014455] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 3134/SWD-I | 27/02/2023 | 30 | KUNTAL CHOWDHURY | 31.76 | 0 | 100
7727 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for KASHIADANGA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1406] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2022-2023 | 3619/SWD-I | 24/03/2023 | 790 | BABLU KUMAR MONDAL | 496.35 | 0 | 55
7728 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000055/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 11 | 0 | 0
7729 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000222/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 8.66 | 0 | 0
7730 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Sri Krishnanagar supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000577/2022-2023 | 606/SMD | 28/02/2023 | 90 | CONCORD ENGINEERING | 19.28 | 0 | 0
7731 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 0 | 15
7732 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SRIKRISHNANAGAR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000206/2021-2022 | 1927/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 0 | 100
7733 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for SRIKRISHNANAGAR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012514] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 2892/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 0 | 33
7734 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000090/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 40.8 | 0 | 0
7735 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000137/2022-2023 | 3420/SWD-I | 13/03/2023 | 0 | Resource Division | 8.24 | 0 | 0
7736 | South 24 Pgs W/S Division I |  | Construction of M.S. Manifold of 1000 mm dia 10 mm thickness for Improvement of Water Supply at Zone 9 Head Work Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000245/2022-2023 | 1731/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 4.38 | 0 | 20
7737 | South 24 Pgs W/S Division I |  | Construction of foundation with supporting arrangement including erection of M.S. Manifold and distribution pipeline & some allied works at zone 9 Head Works Site under SWBWSS in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000246/2022-2023 | 1732/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 3.36 | 0 | 100
7738 | South 24 Pgs W/S Division I |  | Laying of 300 mm dia MS & DI distribution pipe line from proposed Manifold to existing distribution pipeline with interconnection at zone 9 Head Works Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000247/2022-2023 | 1733/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 4.09 | 0 | 20
7739 | South 24 Pgs W/S Division I |  | Laying of 250 mm dia MS & DI distribution pipe line from proposed Manifold to existing distribution pipeline with interconnection at zone 9 Head Work Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000248/2022-2023 | 1734/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 3.24 | 0 | 20
7740 | South 24 Pgs W/S Division I |  | Supplying and laying of 450 mm dia 8 mm thickness MS Casing pipe by open cutting method at two (2) places including supplying and laying of 300 mm and 250 mm dia MS Water Distribution pipeline across the PWD road (Bakrahat-Thakurpukur) near zone 9 Head Work Site under SWBWSS in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000249/2022-2023 | 1735/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 6.05 | 0 | 20
7741 | South 24 Pgs W/S Division I |  | Laying a rising main from existing pump house to nearer distribution line of Zone- 8 and Zone - 9 for boosting existing scheme which arise after successfully installation of manifold in connection with Construction and installation of Manifold and allied works at OHR site of Zone-9, Bishnupur-II Block, under surface water based water supply scheme in the arsenic affected areas of South 24 Pgs. district. (TSM/014338) |  |  | ORD/000249/2023-2024 | 1491/SWD-I | 19/07/2023 | 30 | SRIJON ENTERPRISE | 6.56 | 0 | 100
7742 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sumatinagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000078/2023-2024 | 62/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
7743 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000152/2024-2025 | 2490/AD | 14/06/2024 | 75 | COPE ENTERPRISE | 57.99 | 0 | 100
7744 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000153/2024-2025 | 2491/AD | 14/06/2024 | 30 | ANANTA KUMAR GIRI | 26.9 | 0 | 100
7745 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000154/2024-2025 | 2492/AD | 14/06/2024 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 6.12 | 0 | 0
7746 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Sumatinagar (Zone-I & II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000281/2023-2024 | 1431/AD | 13/07/2023 | 45 | GROWING CONCERN | 41.85 | 0 | 100
7747 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Sumatinagar (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13569) (SM/09394) (SM/08792) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000339/2025-2026 | 3045/AD | 30/06/2025 | 45 | PALASH HALDAR | 7.87 | 0 | 0
7748 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell Replacement Tubewell (damaged due to natural calamities) by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000420/2023-2024 | 1909/AD | 01/08/2023 | 30 | SARADA CONSTRUCTION | 24.12 | 0 | 100
7749 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part - F) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000495/2024-2025 | 3571/AD | 04/09/2024 | 90 | GROWING CONCERN | 100.89 | 0 | 100
7750 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Sumatinagar (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000720/2023-2024 | 2537/AD | 28/08/2023 | 30 | ANANTA KUMAR GIRI | 8.71 | 0 | 100
7751 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000774/2022-2023 | 6646/AD | 14/11/2022 | 45 | SARADA CONSTRUCTION | 45.89 | 0 | 100
7752 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000775/2022-2023 | 6647/AD | 14/11/2022 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 12.01 | 0 | 100
7753 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000777/2022-2023 | 6648/AD | 14/11/2022 | 45 | RANJIT CONSTRUCTION | 7.99 | 0 | 100
7754 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 120 | UCON | 140.93 | 0 | 100
7755 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of 02 nos. tubewell for Sumatinagar Zone - II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000989/2023-2024 | 504/KSD | 03/10/2023 | 7 | SARADA CONSTRUCTION | 2.57 | 0 | 100
7756 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SUMATINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001057/2022-2023 | 4648/AD | 06/09/2022 | 45 | VOYAGER | 8.14 | 0 | 100
7757 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mahishamari Zone - I & II, Sumatinagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002153/2023-2024 | 948/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
7758 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002176/2023-2024 | 813/AD | 05/02/2024 | 45 | M/S. MA BHABANI CONSTRUCTION | 11.71 | 0 | 100
7759 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002467/2023-2024 | 1571/AD | 16/03/2024 | 382 | BIMALENDU GIRI | 33.73 | 0 | 68
7760 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000498/2023-2024 | 4824/AD | 20/12/2023 | 0 | Resource Division | 34.63 | 0 | 0
7761 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000542/2023-2024 | 26/AD | 02/01/2024 | 0 | Resource Division | 10.31 | 0 | 0
7762 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000965/2023-2024 | 1758/AD | 27/03/2024 | 0 | Resource Division | 28.55 | 0 | 0
7763 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00016/2023-2024 | BP-2023-24-34 | 18/05/2023 | 0 | WBSEDCL | 5.87 | 0 | 0
7764 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Sumatinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000341/2022-2023 | 3745/SMD | 29/12/2022 | 949 | RELIABLE CONSTRUCTION | 20.25 | 0 | 85
7765 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & installation of LED board at Zone-I & II, P.H. No-1 & 2 of Sumatinagar Aug water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000563/2024-2025 | 795-AE-I-SMD | 11/06/2024 | 15 | PS & ASSOCIATES | 0.82 | 0 | 0
7766 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 694 | SUNNY ELECTRIC CO. | 146 | 0 | 20
7767 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - III B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000363/2023-2024 | 1564/AD | 17/07/2023 | 90 | M/S SUBIR GHOSH | 524.53 | 0 | 84
7768 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-IIIB of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001530/2023-2024 | 435/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
7769 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IIIA at Bhadura of Diamond Harbour -II Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002405/2023-2024 | 1153/AD | 27/02/2024 | 60 | M/S. PROMILA CONSTRUCTION | 39.73 | 0 | 0
7770 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000921/2023-2024 | 1263/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7771 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 of Ramchandranagar (Part-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000397/2022-2023 | 3799/SMD | 29/12/2022 | 90 | KARTICK BAL | 22.21 | 0 | 0
7772 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-I) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000295/2022-2023 | 1882/SWD-I | 16/11/2022 | 30 | BARI ENTERPRISE | 30.03 | 0 | 0
7773 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000319/2024-2025 | 3252/SWD-I | 19/07/2024 | 60 | RELIABLE ENTERPRISE (MURSHIDABAD) | 31.12 | 0 | 0
7774 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-I) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000393/2022-2023 | 407/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 0 | 0
7775 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-I) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1672] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000512/2022-2023 | 2942/SWD-I | 16/02/2023 | 927 | RELIABLE ENTERPRISE | 420.98 | 0 | 15
7776 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar-I PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014752] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000782/2022-2023 | 3673/SWD-I | 29/03/2023 | 15 | BARI ENTERPRISE | 3.13 | 0 | 0
7777 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Service Road (length = 550.00m) and Culvert at OHR site for RAMCHANDRANAGAR (Part-I) PWSS within Mograhat-II under South 24-Pgns, W/S Division-I. P.H.E. Dte. for Augmentation of Surface Water based Water Supply Scheme for Arsenic Affected areas of South 24 Parganas District. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000870/2024-2025 | 4928/SWD-I | 03/12/2024 | 30 | S.M. ENTERPRISE (MOGRAHAT) | 79.56 | 0 | 0
7778 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length= 51.00m), Development of land, Construction of Service Road (Length = 15.00m) and pumphouse (4.80 Mtr x 366 Mtr) at 2nd Tubewell site for RAMCHANDRANAGAR (Part-I) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District South 24-Parganas. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001176/2024-2025 | 502/SWD-I | 18/02/2025 | 60 | SAYAN ENTERPRISE | 14.96 | 0 | 0
7779 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall, Approach Road and Pump house with water supply and sanitary arrangement at Head Work site for RAMCHANDRANAGAR (Part-I) PWSS OHR site of Mograhat-II Block under South 24 Pgs W/S Division -I, P.H.E. Dte. for Augmentation of Surface Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001181/2024-2025 | 607/SWD-I | 27/02/2025 | 45 | M/S LAKHI CONSTRUCTION | 29.15 | 0 | 0
7780 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000140/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.75 | 0 | 0
7781 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-II of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001047/2022-2023 | 299/DHSD | 15/09/2022 | 30 | RAMKRISHNA CHAKRABORTY | 3.24 | 0 | 100
7782 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000342/2023-2024 | 3206/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
7783 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000890/2023-2024 | 744/AD | 03/02/2024 | 0 | Resource Division | 35.24 | 0 | 0
7784 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000911/2023-2024 | 1253 | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7785 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01821/2022-2023 | BP-2022-23-464 | 23/03/2023 | 0 | WBSEDCL | 1.04 | 0 | 0
7786 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/02498/2023-2024 | BP-2023-24-263 | 18/09/2023 | 0 | WBSEDCL | 1.88 | 0 | 0
7787 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Haori water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000297/2023-2024 | 1388/SMD | 25/05/2023 | 90 | M/S. S.S. ENTERPRISE | 10.88 | 0 | 0
7788 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Haori water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Budge Budge-II] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000518/2022-2023 | 377/SMD | 15/02/2023 | 90 | M/S. S.S. ENTERPRISE | 10.76 | 0 | 100
7789 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply & Delivery of additional materials for PH No.-1 of Haori Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Budge Budge - II) [SM/13297] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002999/2023-2024 | 288/AE-II/SMD | 15/03/2024 | 15 | M/S. S.S. ENTERPRISE | 0.26 | 0 | 100
7790 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000011/2023-2024 | 35/SWD-I | 05/04/2023 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 6.79 | 0 | 100
7791 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for water supply at HAORI Piped Water Supply Scheme within Budge Budge-II Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000267/2022-2023 | 1778/SWD-I | 07/11/2022 | 30 | MOMINUL BISWAS | 14.69 | 0 | 100
7792 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000340/2022-2023 | 2071/SWD-I | 01/12/2022 | 60 | UNI DEVELOPERS AND CONTRACTORS | 6.2 | 0 | 0
7793 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 0 | 98
7794 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for distribution system & providing FHTC of HAORI piped water supply scheme for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. under South 24 Pgs W/S Division -I, P.H.E. Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000369/2022-2023 | 2313/SWD-I | 19/12/2022 | 90 | SUKUMAR DEBNATH | 110.48 | 0 | 60
7795 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method HAORI PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Divn- I, P.H.E. Dte. [SM/13297] [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000680/2022-2023 | 3476/SWD-I | 15/03/2023 | 15 | MOMINUL BISWAS | 2.17 | 0 | 100
7796 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Haori Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000993/2022-2023 | 1533/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.45 | 0 | 100
7797 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Khakurdaha water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000581/2022-2023 | 616/SMD | 02/03/2023 | 90 | ROY & BISWAS ENGG. CO. | 22.36 | 0 | 0
7798 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00668/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
7799 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land, Construction of approach road and other allied works for Ground Water Based KHAKURDAHA Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/13923) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000407/2024-2025 | 3685/SWD-I | 22/08/2024 | 296 | GARAI INFRA PROJECT | 56.45 | 0 | 25
7800 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 0 | 96
7801 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KHAKURDAHA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017164] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000620/2022-2023 | 3244/SWD-I | 01/03/2023 | 30 | MATRI ENTERPRISE | 31.75 | 0 | 50
7802 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "KHAKURDAHA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000754/2022-2023 | 711/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.83 | 0 | 100
7803 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000193/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 45.83 | 0 | 0
7804 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 at Ground Water Based Augmentation Piped Water Supply Scheme of Atharabeki W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000028/2025-2026 | 2014/AD | 28/04/2025 | 30 | HIMALAYAN PROPERTY DEALERS AND PROMOTERS PVT LTD | 14.17 | 0 | 0
7805 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection of Ground Water Based Augmentation Piped Water Supply Scheme for Atharabeki (Part - B), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000030/2023-2024 | 169/AD | 19/04/2023 | 60 | SAMSUL ENTERPRISE | 120.51 | 0 | 95
7806 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Atharabeki (Part-B) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000092/2023-2024 | 448/AD | 08/05/2023 | 829 | ASHIS ENTERPRISE | 13.07 | 0 | 65
7807 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabenki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001763/2022-2023 | 11945/AD | 24/02/2023 | 675 | BANGA NIRMAN | 7.36 | 0 | 100
7808 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabeki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001765/2022-2023 | 12038/AD | 27/02/2023 | 675 | BANGA NIRMAN | 7.1 | 0 | 100
7809 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Athara Beki (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001838/2022-2023 | 10937/AD | 06/02/2023 | 45 | TECH VISION | 2.82 | 0 | 0
7810 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
7811 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000013/2023-2024 | 218/AD | 21/04/2023 | 0 | Resource Division | 15.7 | 0 | 0
7812 | S24 Pgns Mechanical | Canning Sub-division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/04679/2023-2024 | BP-2023-24-510 | 12/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
7813 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Atharabeki Part-B water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000524/2022-2023 | 393/SMD | 15/02/2023 | 1142 | CHANDIMATA ELECTRICALS | 21.52 | 0 | 90
7814 | S24 Pgns Mechanical | Sub-Division - II under South 24pgs W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chaknitai water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-I] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000515/2022-2023 | 372/SMD | 13/02/2023 | 90 | NUPUR CHANDRA HALDER | 22.36 | 0 | 0
7815 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000078/2023-2024 | 399/SWD-I | 28/04/2023 | 30 | GEO SOLUTION | 3.05 | 0 | 0
7816 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
7817 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Chak Nitai PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/14657) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000273/2024-2025 | 2923/SWD-I | 25/06/2024 | 45 | DEY ENTERPRISE | 71.64 | 0 | 0
7818 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK NETAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017334] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000494/2022-2023 | 2855/SWD-I | 08/02/2023 | 30 | JINAT CONSTRUCTION | 15.89 | 0 | 1
7819 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
7820 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK NITAI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14657] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000696/2024-2025 | 4491/SWD-I | 30/10/2024 | 30 | BORING HOUSE | 15.83 | 0 | 0
7821 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of CHAK NITAI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2257). | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000715/2022-2023 | 3550/SWD-I | 21/03/2023 | 994 | MAA LAXMI ENTERPRISE | 288.95 | 0 | 10
7822 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000944/2022-2023 | 1127/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 3.05 | 0 | 100
7823 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development work & Protection work for approach road at Headwork site of Chak Netai PWSS for pipe lines at providing 100 % Functional Household Tap Connection (FHTC) for Proposed CHAK NETAI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. (SM/14657) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/001125/2024-2025 | 188/SWD-I | 17/01/2025 | 271 | SRIJON ENTERPRISE | 29.94 | 0 | 80
7824 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000095/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 38.56 | 0 | 0
7825 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Atghara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 1052/SMD | 17/04/2023 | 90 | M.S.ENTERPRISE | 23.44 | 0 | 0
7826 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for ATGHARA Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2247) (TSM/018118) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 268/SWD-I | 24/04/2023 | 300 | TUMPA ASSOCIATES | 421.83 | 0 | 30
7827 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] (2nd Call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000224/2023-2024 | 1400/SWD-I | 14/07/2023 | 30 | G.B. CONSTRUCTION | 31.7 | 0 | 0
7828 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of ATGHARA PWSS within Sonarpur Block "ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14857) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000230/2024-2025 | 2650/SWD-I | 07/06/2024 | 45 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 10.83 | 0 | 100
7829 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Earthwork in filling in Head Work Site with good earth for proposed ATGHARA Pipe water supply scheme to accommodate FHTC in Sonarpur Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. under Jal Jeevan Mission.(SM/14857) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000742/2023-2024 | 524/SWD-I | 29/01/2024 | 330 | SUPER CONSTRUCTION | 7.17 | 0 | 100
7830 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000747/2023-2024 | 561/SWD-I | 31/01/2024 | 15 | MUNNA AGROTECH ENTERPRISE | 15.85 | 0 | 100
7831 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for ATGHARA PWSS of SONARPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/14857] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000787/2023-2024 | 1070/SWD-I | 04/03/2024 | 341 | BORING HOUSE | 15.81 | 0 | 100
7832 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of Head Work Site ATGHARA PWSS within Sonarpur Block ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14857) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001071/2024-2025 | 5339/SWD-I | 30/12/2024 | 315 | RAJ CONSTRUCTION | 39.61 | 0 | 50
7833 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000034/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 18.93 | 0 | 0
7834 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000243/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 13.84 | 0 | 0
7835 | Alipore Division | Diamond Harbour Sub-Division | Payment for "Restoration of Fatepur Falta Road (MDR) near Panchloki to Basulat Battala, damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01188/2024-2025 | BP-2024-25-558 | 11/09/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 0.94 | 0 | 0
7836 | Alipore Division | Diamond Harbour Sub-Division | Payment for "Restoration of Fatepur Falta Road (MDR) (various chainage 465.5 mtr. , damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte., | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01189/2024-2025 | BP-2024-25-559 | 11/09/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 28 | 0 | 0
7837 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VIII of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No of FHTC-700]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000013/2023-2024 | 04/AD | 04/04/2023 | 90 | TANMAY ROY CHOWDHURY | 169.17 | 0 | 80
7838 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 300 | BIDYUT UDYOG | 196.04 | 0 | 1
7839 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(B) at Falta block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000304/2023-2024 | 1507/AD | 15/07/2023 | 900 | SUBRATA GHOSH | 285.95 | 0 | 40
7840 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VII at Falta block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Phase-II). [No of FHTC-1300]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002051/2022-2023 | 12973/AD | 22/03/2023 | 90 | SUPRITI ENTERPRISE | 106.69 | 0 | 70
7841 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000135/2022-2023 | 22/AD | 05/04/2023 | 0 | Resource Division | 101.08 | 0 | 0
7842 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000187/2023-2024 | 1277/AD | 05/07/2023 | 0 | Resource Division | 101.08 | 0 | 0
7843 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 300 | BIDYUT UDYOG | 196.04 | 0 | 1
7844 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone-VIIIB at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000070/2025-2026 | 2259/AD | 14/05/2025 | 180 | SUBRATA GHOSH | 19.47 | 0 | 0
7845 | Alipore Division | Diamond Harbour Sub-Division | Construction of approach WBM Road for Falta Zone-VIIIB OHR site within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001022/2024-2025 | 4933/AD | 03/12/2024 | 360 | SUBRATA GHOSH | 14.19 | 0 | 0
7846 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001378/2024-2025 | 5523/AD | 28/12/2024 | 405 | MONDAL ENTERPRISE (MURSHIDABAD) | 44.51 | 0 | 75
7847 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001407/2024-2025 | 5552/AD | 30/12/2024 | 45 | TANMAY ROY CHOWDHURY | 31.11 | 0 | 0
7848 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000241/2023-2024 | 2780/AD | 12/09/2023 | 0 | Resource Division | 15.19 | 0 | 0
7849 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000620/2023-2024 | 281/AD | 15/01/2024 | 0 | Resource Division | 9.06 | 0 | 0
7850 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000930/2023-2024 | 1272/AD | 02/03/2024 | 0 | Resource Division | 1.24 | 0 | 0
7851 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Diamond Harbour-I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000080/2025-2026 | 2421/AD | 23/05/2025 | 60 | AVIK ENTERPRISE | 87.23 | 0 | 0
7852 | Alipore Division | Diamond Harbour Sub-Division | Construction of Car parking shed by Galvanised corrugated iron sheet at office premiese under Zone VII of Diamond Harbour-I Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas"under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001123/2023-2024 | 518/DHSD | 13/10/2023 | 30 | M/S B ENTERPRISE | 4.8 | 0 | 100
7853 | Alipore Division | Diamond Harbour Sub-Division | R.C.C Roof construction over existing Laboratory building of Office of the Assistant Engineer, Diamond Harbour Sub Division, PHE Dte. under Zone VII of Diamond Harbour-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001146/2023-2024 | 524/DHSD | 13/10/2023 | 30 | SAMIM AHMED | 4.81 | 0 | 100
7854 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 01(One) no.100mm x 50mm dia. having 5 nos. Strainer upto 300 mtr (Average) depth at office of the Assistant Engineer, Diamond Harbour Sub-Division under Zone-VII of Diamond Harbour-I Block under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001158/2023-2024 | 527/DHSD | 13/10/2023 | 7 | M/S B ENTERPRISE | 2.51 | 0 | 0
7855 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VII at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 5140] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001398/2022-2023 | 10870/AD | 04/02/2023 | 990 | AVIK ENTERPRISE | 383.98 | 0 | 95
7856 | Alipore Division | Diamond Harbour Sub-Division | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VII of Diamond Harbour-I Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002025/2022-2023 | 12929/AD | 21/03/2023 | 15 | AVIK ENTERPRISE | 10.47 | 0 | 90
7857 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of UPVC pipe line for balance portion in the distribution system for coverage 100% FHTC in Zone-VII at Diamond Harbour- I block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002116/2023-2024 | 830/AD | 05/02/2024 | 45 | AVIK ENTERPRISE | 23.85 | 0 | 100
7858 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000001/2023-2024 | 33/AD | 05/04/2023 | 0 | Resource Division | 2.3 | 0 | 0
7859 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000132/2022-2023 | 24/AD | 05/04/2023 | 0 | Resource Division | 16.27 | 0 | 0
7860 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000235/2023-2024 | 2196/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
7861 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000240/2023-2024 | 2653/AD | 04/09/2023 | 0 | Resource Division | 30.8 | 0 | 0
7862 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000425/2023-2024 | 3611/AD | 30/10/2023 | 0 | Resource Division | 15.4 | 0 | 0
7863 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000916/2023-2024 | 1258/AD | 02/03/2024 | 0 | Resource Division | 0.93 | 0 | 0
7864 | Alipore Division | Diamond Harbour Sub-Division | Payment against "Restoration of Fatepur Falta Road (MDR) 0.3Km-0.6Km, 9.539Km- 10.05, 13.728Km-14.098Km, 14.098Km-14.418Km, 12.683Km-13.728Km & 9nos points: 5.9-6.1Km) under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Diamond Harbour Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 1118(W)/618G, Dt. 01.08.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01575/2024-2025 | BP-2024-25-890 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 85.83 | 0 | 0
7865 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8074]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000350/2023-2024 | 1660/AD | 20/07/2023 | 438 | S.MISRA INFRADEV PVT. LTD. | 1874.49 | 0 | 87
7866 | Alipore Division | Diamond Harbour Sub-Division | Investigation of soil for the proposed 1(one) no. R.C.C. Over Head Reservoir i.e. at Zone-IV (OHR Size-1250) of Falta Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000515/2022-2023 | 5536/AD. | 21/09/2022 | 10 | RAJIB KUMAR CHAKRABORTY | 0.82 | 0 | 0
7867 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. and 100 mm dia. GI Distribution line for crossing of Bhatheria Canal at Gangadharpur mouza (Node point 297 to 299) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District. South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000529/2024-2025 | 3646/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 38.41 | 0 | 100
7868 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 100 mm dia. GI Distribution line for crossing of Canal at Kantafuli mouza (Node point 103 to 110) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000530/2024-2025 | 3647/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 20.24 | 0 | 100
7869 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 273 mm dia (OD) MS Distribution line for crossing of Canal at Dholtikari mouza (Node point 10 to 11 ) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000531/2024-2025 | 3648/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 23.17 | 0 | 100
7870 | Alipore Division | Diamond Harbour Sub-Division | Land Development and ICBP within the head works site under Zone-IV at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000815/2024-2025 | 4501/AD | 11/11/2024 | 60 | S.MISRA INFRADEV PVT. LTD. | 25.1 | 0 | 100
7871 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IV of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001001/2022-2023 | 284/DHSD | 13/09/2022 | 30 | GEO SOLUTION | 3.72 | 0 | 0
7872 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-IV at Falta block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14680] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001305/2024-2025 | 5379/AD | 23/12/2024 | 75 | S.MISRA INFRADEV PVT. LTD. | 152.39 | 0 | 0
7873 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-IV (OHR Size-1250) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002103/2022-2023 | 344/DHSD | 18/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
7874 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 180 | SAB ENGINEERING WORKS | 29.99 | 0 | 0
7875 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-I at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002390/2024-2025 | 637/AD | 18/02/2025 | 45 | M/S. S.S. ENTERPRISE | 23.13 | 0 | 0
7876 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000136/2022-2023 | 21/AD | 05/04/2023 | 0 | Resource Division | 393.9 | 0 | 0
7877 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000226/2023-2024 | 2189/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
7878 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000362/2023-2024 | 3226/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
7879 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000430/2023-2024 | 3624/AD | 30/10/2023 | 0 | Resource Division | 36.96 | 0 | 0
7880 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000616/2023-2024 | 277/AD | 15/01/2024 | 0 | Resource Division | 12.78 | 0 | 0
7881 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000927/2023-2024 | 1269/AD | 02/03/2024 | 0 | Resource Division | 2.48 | 0 | 0
7882 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of Electric Bill for new service connection under SMD PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00280/2023-2024 | BP-2023-24-16 | 15/05/2023 | 0 | WBSEDCL | 12.04 | 0 | 0
7883 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kantipota water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 457/SMD | 17/02/2023 | 90 | M/S. DILIP MITRA | 22.41 | 0 | 40
7884 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kantipota W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002537/2023-2024 | 32/SMSD | 09/01/2024 | 15 | M/S. DILIP MITRA | 0.89 | 0 | 100
7885 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Kantipota W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002538/2023-2024 | 31/SMSD | 09/01/2024 | 15 | M/S. DILIP MITRA | 0.58 | 0 | 0
7886 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KANTIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1783] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 1373/SWD-I | 12/07/2023 | 600 | ANUP PAUL | 467.02 | 0 | 25
7887 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR KANTIPOTA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016074) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000353/2022-2023 | 2260/SWD-I | 15/12/2022 | 30 | MOUSUMI DAS SARKAR | 29.69 | 0 | 100
7888 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, development of land & others allied works of ¿KANTIPOTA HW site to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13777). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000377/2024-2025 | 3550/SWD-I | 09/08/2024 | 45 | ANUP PAUL | 32.6 | 0 | 0
7889 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KANTIPOTA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13777] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000716/2022-2023 | 3562/SWD-I | 22/03/2023 | 15 | MOUSUMI DAS SARKAR | 3.14 | 0 | 100
7890 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Drum sheet walling, Road Restoration & other allied works of KANTIPOTA 2ND Site to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13777) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001194/2024-2025 | 868/SWD-I | 26/03/2025 | 183 | MAA GITA ENTERPRISE | 41.44 | 0 | 50
7891 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 38.1 | 0 | 0
7892 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000253/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.98 | 0 | 0
7893 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Malipukuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000301/2022-2023 | 450/SMD | 17/02/2023 | 90 | A.S.ENTERPRISE | 22.36 | 0 | 0
7894 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Malipukuria W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/003016/2023-2024 | 280A/SMSD | 29/02/2024 | 15 | A.S.ENTERPRISE | 0.92 | 0 | 0
7895 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Malipukuria PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015504] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 2076/SWD-I | 01/12/2022 | 30 | CAPITAL CONSTRUCTION | 30.03 | 0 | 0
7896 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for MALIPUKURIA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13515] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000481/2022-2023 | 2810/SWD-I | 02/02/2023 | 15 | CAPITAL CONSTRUCTION | 3.13 | 0 | 0
7897 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for MALIPUKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2076] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000545/2022-2023 | 3029/SWD-I | 20/02/2023 | 300 | CE INFRASTRUCTURE | 425.11 | 0 | 20
7898 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall,Land Development,Pathway,Drain & others allied works of Malipukuria Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13515] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 1210/SWD-I | 11/03/2024 | 45 | C.E. INFRASTRUCTURE | 43.91 | 0 | 0
7899 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of MALIPUKURIA Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13515) (2nd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001148/2024-2025 | 333/SWD-I | 29/01/2025 | 60 | GRANTHAM WATFORD | 10.07 | 0 | 0
7900 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000025/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 24.51 | 0 | 0
7901 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000236/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.79 | 0 | 0
7902 | Alipore Division | Canning Sub-division | Restoration of Thunkati Canning Road South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01323/2024-2025 | BP-2024-25-622 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 8.73 | 0 | 0
7903 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augmentation of Canning PWSS Zone-I Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000066/2022-2023 | 5806/AD | 17/10/2022 | 1016 | MAA LAXMI ENTERPRISE | 195.19 | 0 | 70
7904 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000207/2022-2023 | 2994/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 7 | 0 | 98
7905 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000208/2022-2023 | 2995/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 6.78 | 0 | 98
7906 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000209/2022-2023 | 2996/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 6.78 | 0 | 98
7907 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000210/2022-2023 | 2997/AD | 11/07/2022 | 30 | M/S P. B. CONSTRUCTION | 6.98 | 0 | 0
7908 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000211/2022-2023 | 2998/AD | 11/07/2022 | 30 | M/S P. B. CONSTRUCTION | 6.76 | 0 | 0
7909 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000212/2022-2023 | 2999/AD | 11/07/2022 | 30 | SUKALPA NIRMAN | 6.99 | 0 | 95
7910 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000213/2022-2023 | 3000/AD | 11/07/2022 | 30 | SUKALPA NIRMAN | 6.77 | 0 | 0
7911 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000214/2022-2023 | 3001/AD | 11/07/2022 | 30 | M/S. ASIRUDDIN SEKH ENTERPRISE | 6.73 | 0 | 0
7912 | Alipore Division | Canning Sub-division | Additional Laying of pipe line to connect the balance area of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I, under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Zone-III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000278/2024-2025 | 2832/AD | 04/07/2024 | 270 | K.P. CONSTRUCTION | 75.69 | 0 | 80
7913 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation and protection work at Augmentation of Canning (Zone- I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000355/2024-2025 | 2827/AD | 04/07/2024 | 450 | AVIK ENTERPRISE | 141.64 | 0 | 45
7914 | Alipore Division | Canning Sub-division | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000413/2023-2024 | 772/CSD | 02/08/2023 | 30 | JHARNA ENTERPRISE | 2.23 | 0 | 98
7915 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000444/2025-2026 | 3566/AD | 25/07/2025 | 45 | M.P. ENTERPRISE (II) | 29.51 | 0 | 0
7916 | Alipore Division | Canning Sub-division | Dismantling work of Plain Cement Concrete Road and restoration work (Canning Station areas) for laying distribution work of Augmentation of Canning Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-III) ( SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000546/2024-2025 | 3717/AD | 12/09/2024 | 270 | M.P. ENTERPRISE (II) | 41.04 | 0 | 98
7917 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-II Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000556/2022-2023 | 5807/AD | 17/10/2022 | 840 | AVIK ENTERPRISE | 232.69 | 0 | 80
7918 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-III Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000557/2022-2023 | 5808/AD | 17/10/2022 | 120 | K.P. CONSTRUCTION | 268.06 | 0 | 94
7919 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I, Part -C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000560/2022-2023 | 5811/AD | 17/10/2022 | 365 | MAA LAXMI ENTERPRISE | 56.93 | 0 | 0
7920 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - A) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000562/2022-2023 | 5812/AD | 17/10/2022 | 365 | AVIK ENTERPRISE | 59.17 | 0 | 0
7921 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - B) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000563/2022-2023 | 5813/AD | 17/10/2022 | 1095 | AVIK ENTERPRISE | 55.75 | 0 | 0
7922 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000564/2022-2023 | 5814/AD | 17/10/2022 | 1095 | AVIK ENTERPRISE | 49.11 | 0 | 96
7923 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - III, Part - A) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000565/2022-2023 | 5815/AD | 17/10/2022 | 365 | K.P. CONSTRUCTION | 83.63 | 0 | 0
7924 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ B) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000573/2022-2023 | 5816/AD | 17/10/2022 | 896 | K.P. CONSTRUCTION | 50.57 | 0 | 85
7925 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000574/2022-2023 | 5817/AD | 17/10/2022 | 365 | K.P. CONSTRUCTION | 61.49 | 0 | 98
7926 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000687/2024-2025 | 4292/AD | 29/10/2024 | 30 | M/S M.G.CONSTRUCTION | 8.94 | 0 | 0
7927 | Alipore Division | Canning Sub-division | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - I) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000841/2024-2025 | 4576/AD | 15/11/2024 | 270 | JYOTY SOLAR POWER | 220.03 | 0 | 0
7928 | Alipore Division | Canning Sub-division | Construction of 900 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - III) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000842/2024-2025 | 4577/AD | 15/11/2024 | 270 | K.P. CONSTRUCTION | 288.41 | 0 | 0
7929 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-II) (SM/13116 ) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000988/2023-2024 | 3300/AD | 07/10/2023 | 30 | MMS CONSTRUCTIONS PVT. LTD. | 14.05 | 0 | 100
7930 | Alipore Division | Canning Sub-division | Dismantling work of Plain Cement Concrete Road and restoration work up to laying distribution work for Canning (Zone-I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001019/2023-2024 | 3304/AD | 07/10/2023 | 105 | MAA LAXMI ENTERPRISE | 38.83 | 0 | 95
7931 | Alipore Division | Canning Sub-division | Dismantling of existing concrete road and restoration the same (Bahirsona and Kumarsha Chak Part) after laying pipe line at Augmentation of Canning Water Supply Scheme (Zone- I, II & III), Block- Canning- I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001020/2023-2024 | 3305/AD | 07/10/2023 | 540 | AVIK ENTERPRISE | 34.3 | 0 | 0
7932 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-I) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001022/2023-2024 | 3307/AD | 07/10/2023 | 455 | SARKAR ENTERPRISE | 15.95 | 0 | 98
7933 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001023/2023-2024 | 3308/AD | 07/10/2023 | 511 | K.P. CONSTRUCTION | 17.47 | 0 | 95
7934 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 3 Site for Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001059/2024-2025 | 4999/AD | 05/12/2024 | 30 | JOYDEB MANNA | 6.11 | 0 | 0
7935 | Alipore Division | Canning Sub-division | Earth work in filling between proposed Head Work Site and PWD Road at Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001379/2022-2023 | 1061/CSD | 14/12/2022 | 20 | SNEHA CONSTRUCTION | 0.56 | 0 | 100
7936 | Alipore Division | Canning Sub-division | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001408/2023-2024 | 1147/CSD | 01/11/2023 | 30 | JHARNA ENTERPRISE | 2.84 | 0 | 100
7937 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - II), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001436/2021-2022 | 6245/AD | 23/02/2022 | 60 | SNEHA CONSTRUCTION | 63.19 | 0 | 70
7938 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - III), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001440/2021-2022 | 6246/AD | 23/02/2022 | 60 | BHATTACHARJEE AND CO. | 63.16 | 0 | 66
7939 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation of Canning PWSS (Zone-I, II, and III) , Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Canning (Zone-II), Pump House No. - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001909/2023-2024 | 222/AD | 11/01/2024 | 270 | M/S. BABA KAPIL MUNI ENTERPRISE | 6.54 | 0 | 100
7940 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - I), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002413/2022-2023 | 5673/AD | 11/10/2022 | 60 | AQUATECH ENGINEERS | 71.43 | 0 | 90
7941 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002493/2024-2025 | 785/AD | 25/02/2025 | 30 | AVIJIT CONSTRUCTION | 8 | 0 | 0
7942 | Alipore Division | Canning Sub-division | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - II) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002853/2024-2025 | 1153/AD | 18/03/2025 | 270 | RIVER BENZ CONSTRUCTION | 220.05 | 0 | 0
7943 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000731/2023-2024 | 554/AD | 25/01/2024 | 0 | Resource Division | 226.04 | 0 | 0
7944 | S24 Pgns Mechanical | Canning Sub-division | Payment of Electric Bill for new service connection under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/00284/2023-2024 | BP-2023-24-18 | 15/05/2023 | 0 | WBSEDCL | 24.12 | 0 | 0
7945 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service(power) connection at Canning Zone-I PH-3 water supply scheme under Canning -I block PHE dte. (Application ID:-1007778243) (Ref ID:-106599139) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/00396/2024-2025 | BP-2024-25-103 | 10/06/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
7946 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service(power) connection Canning Zone-I ,PH-2 water supply scheme under Canning -I block under SMD PHE dte. (Ref ID:-106606285) (App ID:-1007793877) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/00397/2024-2025 | BP-2024-25-104 | 10/06/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
7947 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service (Power) confection at Canning Zone-I PH-1 water supply scheme under Canning -I block Under SMD PHE dte. (Ref ID:-106606286) (App ID:-1007793891) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/00398/2024-2025 | BP-2024-25-105 | 10/06/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
7948 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01885/2023-2024 | BP-2023-24-224 | 23/08/2023 | 0 | WBSEDCL | 9.33 | 0 | 0
7949 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/04231/2023-2024 | BP-2023-24-437 | 28/12/2023 | 0 | WBSEDCL | 4.79 | 0 | 0
7950 | S24 Pgns Mechanical | Canning Sub-division | Supply, Installation and commissioning of submersible pumping machinery along with allied accessories for Augmentation of Canning Zone-1, Zone-2 & Zone-3 water supply scheme under South 24 Pgs Mechanical Division PHE Dte. [Block:- Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000073/2023-2024 | 1010//SMD | 11/04/2023 | 366 | M/S. S.S. ENTERPRISE | 113.4 | 0 | 70
7951 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 of Dakshin Redokhali water supply scheme Adjacent to Aug. of Canning W/S Sche. under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000123/2024-2025 | 2291/SMD | 19/07/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.82 | 0 | 95
7952 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 of Dakshin Redokhali water supply scheme (Adjacent to Aug. of Canning W/S Sche.) under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000240/2024-2025 | 2483/SMD | 05/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.82 | 0 | 0
7953 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at Zone-I, PH-1 & 2 of Canning (Aug) water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000384/2024-2025 | 1226/SMSD | 30/08/2024 | 15 | SEN ENTERPRISE | 0.78 | 0 | 100
7954 | S24 Pgns Mechanical | Canning Sub-division | Supply & Installation of LED board at Zone-I, PH-3 of Canning (Aug) water supply scheme under South 24-Pgs Mechanical Division, PHE Dte.[SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000397/2024-2025 | 1225/SMSD | 30/08/2024 | 15 | SEN ENTERPRISE | 0.39 | 0 | 100
7955 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-1 water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000643/2024-2025 | 1026/SMSD | 15/07/2024 | 15 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0
7956 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-2 water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000644/2024-2025 | 1025/SMSD | 15/07/2024 | 15 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0
7957 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-3 water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000645/2024-2025 | 1023/SMSD | 15/07/2024 | 15 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0
7958 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at Zone-III, PH-2&3 of Canning w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000892/2023-2024 | 1O64/SMSD | 10/08/2023 | 10 | M/S. PS & ASSOCIATES | 0.78 | 0 | 100
7959 | S24 Pgns Mechanical | Canning Sub-division | Extension of column pipe of Canning Zone-I TW-1&2 and Zone-2 TW-1, Daria TW-2 w/s scheme under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002287/2022-2023 | 135/SMSD | 24/02/2023 | 15 | ROY & BISWAS ENGG. CO. | 0.98 | 0 | 100
7960 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Chak Ruplaskar having village with maximum 77 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001122/2022-2023 | 8766/AD | 21/12/2022 | 60 | SUSHANTA MANDAL | 31.08 | 0 | 0
7961 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000875/2023-2024 | 782/AD | 03/02/2024 | 0 | Resource Division | 0.49 | 0 | 0
7962 | S24 Pgns Mechanical | Diamond Harbour Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Chak Ruplaskar Village of Ramkishore Gram Panchyet Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/000607/2022-2023 | 761/SMD | 15/03/2023 | 90 | SUDIP PRADHAN | 8.83 | 0 | 0
7963 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01113/2023-2024 | BP-2023-24-162 | 24/07/2023 | 0 | WBSEDCL | 7.95 | 0 | 0
7964 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01720/2023-2024 | BP-2023-24-197 | 09/08/2023 | 0 | WBSEDCL | 14.08 | 0 | 0
7965 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/05026/2023-2024 | BP-2023-24-568 | 12/03/2024 | 0 | WBSEDCL | 5.16 | 0 | 0
7966 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Bhabanipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000298/2022-2023 | 448/SMD | 17/02/2023 | 774 | RELIABLE CONSTRUCTION | 26.51 | 0 | 80
7967 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Bhabanipur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/003098/2023-2024 | 329/SMSD | 14/03/2024 | 352 | RELIABLE CONSTRUCTION | 0.92 | 0 | 100
7968 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Bhabanipur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015505] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000334/2022-2023 | 2072/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 0 | 100
7969 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BHABANIPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1292] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000544/2022-2023 | 3031/SWD-I | 20/02/2023 | 300 | CREATION CONSTRUCTION | 282.1 | 0 | 50
7970 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling, Land Development, Road Restoration & others allied works of BHABANIPUR PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13308] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 785/SWD-I | 15/02/2024 | 90 | DUNCON (INDIA) | 54.86 | 0 | 0
7971 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BHABANIPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13308] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3449/SWD-I | 13/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.14 | 0 | 0
7972 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000005/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.21 | 0 | 0
7973 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000226/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 7.96 | 0 | 0
7974 | Alipore Division | Diamond Harbour Sub-Division | Estimate for Re-construction of Boundary wall (Part of North face, length = 27.00 mtr) as per departmental design and drawing at Masat Head Work Site of Diamond Harbour Sub-Division under Alipore Division, P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000835/2022-2023 | 215/DHSD | 12/08/2022 | 45 | M/S M.B.ENTERPRISE | 3.59 | 0 | 0
7975 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IX of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001052/2022-2023 | 305/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.69 | 0 | 0
7976 | Alipore Division | Diamond Harbour Sub-Division | Renovation and reconstruction of existing staff room for the purpose of additional store room at Masat HWS in Zone-IX of Diamond Harbour-I Block for the project of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001181/2022-2023 | 8777/AD | 21/12/2022 | 120 | S.S. ENTERPRISE (II) | 13.97 | 0 | 100
7977 | Alipore Division | Diamond Harbour Sub-Division | Renovation of boundary wall including fencing work with R.B.T (Reinforced Barbed Tape) Concertina fencing at Masat HWS in Zone-IX of Diamond Harbour-I Block for the project of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001182/2022-2023 | 8778/AD | 21/12/2022 | 30 | M/S S.DAS ENTERPRISE | 8.31 | 0 | 100
7978 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including providing (2184 nos) of Functional Household Tap Connection (FHTC) with allied works in Zone-IX of Diamond Harbour-I block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 2184] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001394/2022-2023 | 10866/AD | 04/02/2023 | 900 | BALAJI UDDYOG | 341.01 | 0 | 60
7979 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 272 Cum. capacity Over Head Reservoir of Zone-IX, Diamond Harbour-I Block (At Masat Water Supply Scheme), Block - Diamond Harbour - I under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (3rd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002460/2023-2024 | 1559/AD | 16/03/2024 | 300 | SHARADIYA ENTERPRISE | 32.74 | 0 | 100
7980 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000124/2022-2023 | 12799/AD | 16/03/2023 | 0 | Resource Division | 19.82 | 0 | 0
7981 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000128/2022-2023 | 27/AD | 05/04/2023 | 0 | Resource Division | 9.31 | 0 | 0
7982 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000346/2023-2024 | 3210/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
7983 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000422/2023-2024 | 3612/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
7984 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000886/2023-2024 | 740/AD | 03/02/2024 | 0 | Resource Division | 1.13 | 0 | 0
7985 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000918/2023-2024 | 1260/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
7986 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Charges for New service connection at Pump house no-2 of Ramchandrapur (Sonarpur Block) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00518/2024-2025 | BP-2024-25-125 | 24/06/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
7987 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/04655/2023-2024 | BP-2023-24-490 | 12/02/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
7988 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Ramchandrapur W/S Scheme under SMD, P.H.E. Dte.(Block-Sonarpur) (SM/13786) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000091/2024-2025 | 493/SMSD | 23/04/2024 | 222 | PS & ASSOCIATES | 0.92 | 0 | 100
7989 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramchandrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 3741/SMD | 29/12/2022 | 808 | M/S. PS & ASSOCIATES | 26.01 | 0 | 100
7990 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Ramchandrapur W/S Scheme under SMD, P.H.E. Dte. (Block-Sonarpur) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002341/2023-2024 | 262/SMSD | 23/02/2024 | 15 | PS & ASSOCIATES | 0.92 | 0 | 100
7991 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain and Development of Land & others allied works of ¿RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13786). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000238/2024-2025 | 2658/SWD-I | 07/06/2024 | 45 | BALAJI UDYOG | 67.34 | 0 | 33
7992 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016148) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000354/2022-2023 | 2261/SWD_I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 0 | 100
7993 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road at Publi Garden, Nil Mrittika (NP-1-5, 73-90, 112-90, 90-105, 90-115, 115-120, 151-115, 93-151, 151-154, 122-266, 266-267, 249-266, 27-43, 19-33, 25-50 & 9-18) of RAMCHANDRAPUR Piped Water Supply Scheme, Block- Sonarpur under South 24 Pgns W/S Division-I, PHE Dte. (SM/13786) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000551/2024-2025 | 4224/SWD-I | 30/09/2024 | 211 | BALAJI UDYOG | 19.97 | 0 | 80
7994 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2871] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000665/2022-2023 | 3386/SWD-I | 10/03/2023 | 1008 | BALAJI UDYOG | 455.95 | 0 | 33
7995 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAMCHANDRAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13786] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000721/2022-2023 | 3561/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 50
7996 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of PWD Road damaged due to laying of HDPE pipe line from chainage 0.280Kmp to 1.110 (L/S, R/S, C/L) Kmp of Narendrapur More N.S Road to EM Bye pass, Ramchandrapur, Dhamaitola Payra bagan, Karbala School Road under RAMCHANDRAPUR PWSS to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District (SM/13786) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000744/2024-2025 | 4666/SWD-I | 18/11/2024 | 30 | BALAJI UDYOG | 26.02 | 0 | 0
7997 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of additional pipeline at Ramchandrapur PWSS to accommodate FHTC in Sonarpur Block under south 24 Parganas W/S Division-I under JalJeevan Mission. [SM Code - SM/13786] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000855/2023-2024 | 1325/SWD-I | 15/03/2024 | 407 | BALAJI UDYOG | 21.72 | 0 | 80
7998 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000027/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 21.88 | 0 | 0
7999 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000237/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 17.69 | 0 | 0
8000 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
8001 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000950/2023-2024 | 2982/AD | 26/09/2023 | 45 | M/S. RABIN CON | 27.5 | 0 | 0
8002 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000951/2023-2024 | 2983/AD | 26/09/2023 | 30 | M/S. PAPIYA ENTERPRISE | 9.47 | 0 | 0
8003 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( DAKSHIN KASIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001048/2022-2023 | 3676/AD | 01/08/2022 | 45 | LEMNISCATE | 3.86 | 0 | 100
8004 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
8005 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000447/2023-2024 | 4713/AD | 18/12/2023 | 0 | Resource Division | 14.1 | 0 | 0
8006 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000588/2023-2024 | 87/AD | 03/01/2024 | 0 | Resource Division | 9.3 | 0 | 0
8007 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Kasiabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000434/2022-2023 | 3830/SMD | 29/12/2022 | 90 | M/S. S.S. ENTERPRISE | 19.37 | 0 | 0
8008 | S24 Pgns Mechanical | South 24 Pgs Mechanical Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3 of Jugdia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mograhat-II] | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 3811/SMD | 29/12/2022 | 181 | SINHA ELECTRICALS | 33.56 | 0 | 0
8009 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 500 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (3 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of JUGDIA Mouza of MOGRAHAT-II Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 3406) [TSM/016726] | Assistant Engineer | Junior Engineer | ORD/000081/2023-2024 | 415/SWD-I | 02/05/2023 | 730 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 621.42 | 0 | 45
8010 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional Laying of pipeline for distribution system for Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 1815/SWD-I | 07/07/2025 | 60 | RAJLAXMI CONSTRUCTION | 40.58 | 0 | 0
8011 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JUGDIA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016726] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 530/SWD-I | 11/05/2023 | 539 | SHANTI CONSTRUCTION | 47.45 | 0 | 90
8012 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/08/2025 to 31/01/2026] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000120/2025-2026 | 1941/SWD-I | 23/07/2025 | 184 | AJAY KUMAR | 0.87 | 0 | 17
8013 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000369/2024-2025 | 3508/SWD-I | 07/08/2024 | 45 | TIYASHA ENTERPRISE | 0 | 0 | 0
8014 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000379/2024-2025 | 3571/SWD-I | 12/08/2024 | 45 | TIYASHA ENTERPRISE | 26.83 | 0 | 0
8015 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 25/08/2024 to 31/01/2025] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000428/2024-2025 | 3700/SWD-I | 22/08/2024 | 160 | AJAY KUMAR | 0.76 | 0 | 40
8016 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (TSM/016726) [w.e.f. 25/08/2023 to 23/02/2024] | Assistant Engineer | Junior Engineer | ORD/000665/2023-2024 | 1958/SWD-I | 24/08/2023 | 183 | AJAY KUMAR | 0.87 | 0 | 60
8017 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 24/02/2024 to 24/08/2024] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000811/2023-2024 | 854/SWD-I | 19/02/2024 | 183 | AJAY KUMAR | 0.87 | 0 | 100
8018 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Jugdia Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000983/2022-2023 | 1457/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.77 | 0 | 100
8019 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/02/2025 to 31/07/2025] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/001178/2024-2025 | 299/SWD-I | 27/01/2025 | 181 | AJAY KUMAR | 0.86 | 0 | 19
8020 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000129/2022-2023 | 3388/SWD-I | 10/03/2023 | 0 | Resource Division | 20.98 | 0 | 0
8021 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 28.59 | 0 | 0
8022 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 694 | SUNNY ELECTRIC CO. | 146 | 0 | 20
8023 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-II of Diamond Harbour-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8312] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000086/2023-2024 | 197/AD | 19/04/2023 | 1019 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 1011.34 | 0 | 25
8024 | Alipore Division | Diamond Harbour Sub-Division | Restoration on bituminous road (PWD), protection work due to pipe laying (225 mm. to 350 mm. dia.) and supply of D.I specials within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, DISTRICT SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000445/2022-2023 | 5527/AD | 29/09/2022 | 645 | GHOSH ENTERPRISE (II) | 22.78 | 0 | 100
8025 | Alipore Division | Diamond Harbour Sub-Division | Restoration by concreting of village road due to laying of pipeline dia. varies from 90 mm. to 350 mm. within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000447/2022-2023 | 5528/AD | 29/09/2022 | 840 | GHOSH ENTERPRISE (II) | 94 | 0 | 100
8026 | Alipore Division | Diamond Harbour Sub-Division | Restoration of road and drain of damaged portion due to laying distribution and rising main pipeline from Raichoak more to Singhalganj F.P School under Zone- I of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000528/2024-2025 | 3645/AD | 09/09/2024 | 60 | K.P. CONSTRUCTION | 66.42 | 0 | 100
8027 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 145 m.) at proposed OHR site at Mouza - Akrapunji under Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000869/2024-2025 | 4653/AD | 20/11/2024 | 60 | MOUSUMI ENTERPRISE | 26.73 | 0 | 0
8028 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001459/2021-2022 | 6072/AD | 17/02/2022 | 1194 | SAMIRON GHOSH | 479.57 | 0 | 100
8029 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-I of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001517/2023-2024 | 432/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
8030 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001521/2023-2024 | 433/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
8031 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-II at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002151/2024-2025 | 410/AD | 31/01/2025 | 30 | M/S. S.S. ENTERPRISE | 16.15 | 0 | 0
8032 | Alipore Division | Diamond Harbour Sub-Division | Laying of different dia pipes(DI pipe- 350mm to 400mm, UPVC- 90mm to 225mm) for the balance portion in the distribution system under Diamond Harbour II Block along with the Restoration of subsequent Bitumenous road and concrete road under the jurisdiction of PWD and Diamond Harbour II Panchayat Samiti / Block with the supply of DI specials and allied works of totaling 9453 mtr. under the Augmentation scheme of Diamond Harbour Zone-II within ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Under Jal Jeevan Mission) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002315/2023-2024 | 1092/AD | 22/02/2024 | 720 | SAMIRON GHOSH | 264.14 | 0 | 85
8033 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002492/2024-2025 | 783/AD | 25/02/2025 | 45 | K.P. CONSTRUCTION | 23.55 | 0 | 0
8034 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000139/2022-2023 | 18/AD | 05/04/2023 | 0 | Resource Division | 757.19 | 0 | 0
8035 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000219/2023-2024 | 2202/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
8036 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000737/2023-2024 | 567/ad | 27/01/2024 | 0 | Resource Division | 245.4 | 0 | 0
8037 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000880/2023-2024 | 754/AD | 03/02/2024 | 0 | Resource Division | 51.2 | 0 | 0
8038 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000919/2023-2024 | 1261/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
8039 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Chandipur (Part) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bishnupur-II] |  |  | ORD/001504/2022-2023 | 814/SMD | 17/03/2023 | 90 | JOYSHREE CONCERN | 12.96 | 0 | 100
8040 | S24 Pgns Mechanical |  | Supply, Delivery and Fitting Fixing of the additional materials for PH No.-1 of Augmentation of Chandipur (Part) Water supply scheme under JJM under South 24 Pgs. Mechanical Division, PHE Dte. (Block : Bishnupur-I) [SM/14877] |  |  | ORD/002327/2023-2024 | 1301-AE-II-SMD | 30/11/2023 | 15 | JOYSHREE CONCERN | 0.4 | 0 | 100
8041 | S24 Pgns Mechanical |  | Miscellaneous works in the interest of improvement of outdoor illumination arrangement etc. at P.H. No. 1 under Augmentation of Chandipur (Part) Water Supply Scheme, under South 24 Pgs Mechanical Division, PHE Dte. (Block: Bishnupur-II) (SM/14877) |  |  | ORD/002609/2023-2024 | 224-AE-II-SMD | 01/03/2024 | 15 | DYNATECH SOLUTION | 0.75 | 0 | 100
8042 | South 24 Pgs W/S Division I |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of BUDGE BUDGE-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017980] |  |  | ORD/000599/2022-2023 | 3127/SWD-I | 24/02/2023 | 30 | PROJECT AND MAINTENANCE | 15.88 | 0 | 100
8043 | South 24 Pgs W/S Division I |  | Construction of Pump House at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000654/2022-2023 | 3352/SWD-I | 09/03/2023 | 60 | MODERN CONSTRUCTION | 10.35 | 0 | 100
8044 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000655/2022-2023 | 3353/SWD-I | 09/03/2023 | 45 | S.M ENTERPRISE | 8.02 | 0 | 100
8045 | South 24 Pgs W/S Division I |  | Interconnection from Tubewell to Head Work Site for chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000656/2022-2023 | 3355/SWD-I | 09/03/2023 | 30 | SUJOY SADHUKHAN | 3.97 | 0 | 100
8046 | South 24 Pgs W/S Division I |  | Laying distribution pipeline for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000657/2022-2023 | 3356/SWD-I | 09/03/2023 | 60 | P S CONSTRUCTION | 41.26 | 0 | 100
8047 | South 24 Pgs W/S Division I |  | Land Development of Tubewell site and construction of approach road of Chandipur (Part) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II under South 24-Pgns W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14877) |  |  | ORD/000814/2023-2024 | 1150/SWD-I | 07/03/2024 | 30 | MS KRISHNA MONDAL | 9.6 | 0 | 100
8048 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Chandipur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000994/2022-2023 | 1534/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.37 | 0 | 100
8049 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well No. 4 Site at Narayanpur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000311/2025-2026 | 2964/AD | 25/06/2025 | 30 | CHATTERJEE CONSTRUCTION | 19.11 | 0 | 0
8050 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000734/2023-2024 | 2895/AD | 19/09/2023 | 45 | DIPTI ENTERPRISE | 70.53 | 0 | 60
8051 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Narayanpur W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001663/2022-2023 | 11475/AD | 15/02/2023 | 30 | SARFARAZ CONSTRUCTION | 19.59 | 0 | 90
8052 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001682/2022-2023 | 11489/AD | 15/02/2023 | 45 | R CONSTRUCTION | 7.11 | 0 | 98
8053 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000006/2023-2024 | 121/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
8054 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000015/2023-2024 | 220/AD | 21/04/2023 | 0 | Resource Division | 61.12 | 0 | 0
8055 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000141/2023-2024 | 853/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
8056 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Narayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000288/2023-2024 | 1148/SMD | 24/04/2023 | 834 | NITESH MANAGEMENT | 11.16 | 0 | 95
8057 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Pump House- 1 of Aug of Narayanpur water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15045) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001770/2024-2025 | 70/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.29 | 0 | 0
8058 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House- 1 of Aug of Narayanpur water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15045) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001771/2024-2025 | 71/SMSD | 17/01/2025 | 15 | NITESH MANAGEMENT | 0.92 | 0 | 0
8059 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
8060 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-V) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000093/2023-2024 | 449/AD | 03/05/2023 | 593 | HI TECH ENTERPRISE | 9.12 | 0 | 90
8061 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
8062 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
8063 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001703/2022-2023 | 11667/AD | 20/02/2023 | 45 | SARKAR CONSTRUCTION | 7.36 | 0 | 99
8064 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-V) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001726/2022-2023 | 11763/AD | 21/02/2023 | 80 | B.K. ENTERPRISE. | 60 | 0 | 97
8065 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-V) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001916/2022-2023 | 10942/AD | 06/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.26 | 0 | 99
8066 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002047/2022-2023 | 13047/AD | 24/03/2023 | 45 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 98
8067 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002048/2022-2023 | 13048/AD | 24/03/2023 | 45 | SABITA INFRASTRUCTURE | 7.11 | 0 | 98
8068 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000025/2023-2024 | 231/AD | 24/04/2023 | 0 | Resource Division | 24.45 | 0 | 0
8069 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000154/2023-2024 | 1050/AD | 15/06/2023 | 0 | Resource Division | 13.83 | 0 | 0
8070 | S24 Pgns Mechanical | Canning Sub-division | Charges for service connection at Pump house no-1 of Basant (Zone-V) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00446/2024-2025 | BP-2024-25-114 | 14/06/2024 | 0 | WBSEDCL | 5.46 | 0 | 0
8071 | S24 Pgns Mechanical | Canning Sub-division | Charges for New service connection at Pump house no-3 of Basanti (Zone-V) water supply scheme. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01153/2024-2025 | BP-2024-25-234 | 08/08/2024 | 0 | WBSEDCL | 8.89 | 0 | 0
8072 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at pump house no-2 of Basanti (Zone-V) water supply scheme. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01806/2024-2025 | BP-2024-25-443 | 07/10/2024 | 0 | WBSEDCL | 13.64 | 0 | 0
8073 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Basanti (Zone-5) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000020/2023-2024 | 955/SMD | 04/04/2023 | 789 | A.S.ENTERPRISE | 29.02 | 0 | 100
8074 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Actuator Valve at Pump House no-3 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001202/2024-2025 | 1654/SMSD | 13/12/2024 | 65 | A.S.ENTERPRISE | 0.99 | 0 | 100
8075 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Actuator Valve at Pump House no-1 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001204/2024-2025 | 1652/SMSD | 13/12/2024 | 15 | A.S.ENTERPRISE | 0.99 | 0 | 100
8076 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001208/2024-2025 | 112/SMSD | 22/01/2025 | 15 | A.S.ENTERPRISE | 0.85 | 0 | 100
8077 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-1 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001209/2024-2025 | 1650/SMSD | 13/12/2024 | 15 | A.S.ENTERPRISE | 0.59 | 0 | 100
8078 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-2 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001210/2024-2025 | 110/SMSD | 22/01/2025 | 15 | A.S.ENTERPRISE | 0.59 | 0 | 100
8079 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-3 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001212/2024-2025 | 111/SMSD | 22/01/2025 | 15 | A.S.ENTERPRISE | 0.59 | 0 | 100
8080 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti Aug (Zone-5) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001213/2024-2025 | 1649/SMSD | 13/12/2024 | 65 | A.S.ENTERPRISE | 0.87 | 0 | 100
8081 | Alipore Division | Canning Sub-division | Restoration of Basanti Goran Bose Ganga Mela block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01326/2024-2025 | BP-2024-25-624 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 99.74 | 0 | 0
8082 | Alipore Division | Canning Sub-division | Restoration ofChurchgate Chandur More Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01327/2024-2025 | BP-2024-25-623 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 5.53 | 0 | 0
8083 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000108/2023-2024 | 506/AD | 11/05/2023 | 15 | A.P. CONSTRUCTION | 13.02 | 0 | 0
8084 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
8085 | Alipore Division | Canning Sub-division | Supply of water through pipe line connection at BL & LRO Basanti office from existing pipe line of Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001196/2020-2021 | 1180/CSD | 15/12/2020 | 7 | A.P. CONSTRUCTION | 0.65 | 0 | 0
8086 | Alipore Division | Canning Sub-division | Inter connection in between the replacement tubewell towards distribution system for Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001261/2023-2024 | 1205/CSD | 10/11/2023 | 30 | SUSHANTA MANDAL | 1.06 | 0 | 95
8087 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001349/2022-2023 | 10216/AD | 19/01/2023 | 81 | SNEHA CONSTRUCTION | 58.47 | 0 | 66
8088 | Alipore Division | Canning Sub-division | Pipe line connection from Petrol Pump of Rambabu to basanti Chowmatha TV Relay Centre at Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001397/2023-2024 | 1129/CSD | 30/10/2023 | 30 | KAYAL ENTERPRISE | 1.62 | 0 | 100
8089 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001700/2022-2023 | 11664/AD | 20/02/2023 | 45 | LASKAR CONSTRUCTION | 7.24 | 0 | 98
8090 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001701/2022-2023 | 11665/AD | 20/02/2023 | 650 | SUJOY SADHUKHAN | 7.08 | 0 | 98
8091 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001702/2022-2023 | 11666/AD | 20/02/2023 | 45 | SARKAR CONSTRUCTION | 7.11 | 0 | 0
8092 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001915/2022-2023 | 10941/AD | 06/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.25 | 0 | 99
8093 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000021/2023-2024 | 227/AD | 24/04/2023 | 0 | Resource Division | 110.78 | 0 | 0
8094 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000150/2023-2024 | 1053/AD | 15/06/2023 | 0 | Resource Division | 16.16 | 0 | 0
8095 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000250/2023-2024 | 3042/AD | 28/09/2023 | 0 | Resource Division | 94.19 | 0 | 0
8096 | S24 Pgns Mechanical | Canning Sub-division | Charges for service connection at Pump house no- 2 of Basanti Aug (Z-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/00444/2024-2025 | BP-2024-25-113 | 14/06/2024 | 0 | WBSEDCL | 10.42 | 0 | 0
8097 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Basanti (Zone-1) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000021/2023-2024 | 956/SMD | 04/04/2023 | 90 | M/S. S.R. ENTERPRISE | 29.05 | 0 | 30
8098 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Basanti Zone-I water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000490/2022-2023 | 292/SMD | 03/02/2023 | 90 | SRI KRISHNA NIRMAN | 11.69 | 0 | 0
8099 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001395/2024-2025 | 114/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.59 | 0 | 0
8100 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001396/2024-2025 | 115/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.59 | 0 | 0
8101 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti Aug (Zone-I) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001406/2024-2025 | 1274/SMSD | 12/09/2024 | 15 | M/S. S.R. ENTERPRISE | 0.87 | 0 | 0
8102 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Actuator Valve at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001408/2024-2025 | 118/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.99 | 0 | 0
8103 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001409/2024-2025 | 117/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.85 | 0 | 0
8104 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001410/2024-2025 | 116/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.85 | 0 | 0
8105 | S24 Pgns Mechanical | Canning Sub-division | Supply & delivery of Actuator Valve at Pump House no-3 of Basanti Aug (Zone-I) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15053) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001411/2024-2025 | 119/SMSD | 22/01/2025 | 15 | M/S. S.R. ENTERPRISE | 0.99 | 0 | 0
8106 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Nadabhanga W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000133/2024-2025 | 2470/AD | 14/06/2024 | 45 | M/S MAITY CONSTRUCTION | 27.83 | 0 | 0
8107 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14158) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000404/2024-2025 | 3187/AD | 31/07/2024 | 75 | UCON (II) | 95.23 | 0 | 0
8108 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001305/2022-2023 | 9888/AD | 10/01/2023 | 45 | MONDAL ENTERPRISE (MURSHIDABAD) | 38.59 | 0 | 0
8109 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Nadabhanga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001798/2022-2023 | 3695/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 7.26 | 0 | 95
8110 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Nadabangha Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 2365] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002081/2022-2023 | 12546/AD | 10/03/2023 | 934 | UCON | 385.79 | 0 | 50
8111 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
8112 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Nadabhanga PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002215/2023-2024 | 872/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
8113 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000479/2023-2024 | 4783/AD | 19/12/2023 | 0 | Resource Division | 16.42 | 0 | 0
8114 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000556/2023-2024 | 44/AD | 03/01/2024 | 0 | Resource Division | 14.05 | 0 | 0
8115 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01116/2023-2024 | BP-2023-24-157 | 24/07/2023 | 0 | WBSEDCL | 6.71 | 0 | 0
8116 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01715/2023-2024 | BP-2023-24-194 | 09/08/2023 | 0 | WBSEDCL | 8.4 | 0 | 0
8117 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-2 of Nadabhanga W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000368/2024-2025 | 757/AE-I/SMD | 31/05/2024 | 15 | S.K. ENTERPRISE | 0.89 | 0 | 100
8118 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at PH-1 of Nadabhanga W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000370/2024-2025 | 756/AE-I/SMD | 31/05/2024 | 15 | S.K. ENTERPRISE | 0.89 | 0 | 100
8119 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Nadabhanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000426/2022-2023 | 3822/SMD | 29/12/2022 | 824 | S.K. ENTERPRISE | 22.69 | 0 | 90
8120 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at PH No-2 of Nadabhanga W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/14158) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000752/2025-2026 | 306-AE-II-SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 100
8121 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply & delivery of Electrical accessories with allied items at PH No-1 of Nadabhanga W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/14158) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000753/2025-2026 | 305-AE-II-SMD | 16/05/2025 | 21 | S.K. ENTERPRISE | 0.55 | 0 | 100
8122 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Dhaspara (Zone-I and II) (SM/15221), Ghoramara (SM/14988) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000020/2025-2026 | 2006/AD | 28/04/2025 | 30 | ROY CHOWDHURY ASSOCIATES | 7.24 | 0 | 100
8123 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dhaspara W/S Scheme, Sagar Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000183/2024-2025 | 2543/AD | 18/06/2024 | 45 | MANASH GHOSH | 43.99 | 0 | 0
8124 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dhaspara W/S Scheme, Sagar Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-II) (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000193/2024-2025 | 2553/AD | 18/06/2024 | 45 | MANASH GHOSH | 48.99 | 0 | 0
8125 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamber, fitting fixing supplying different dia specials etc. for Augmentation of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-C) (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001103/2024-2025 | 5034/AD | 06/12/2024 | 60 | MANASH GHOSH | 206.17 | 0 | 0
8126 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dhaspara [Zone-I & II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001917/2021-2022 | 6555/AD | 10/03/2022 | 45 | VOYAGER | 8.94 | 0 | 95
8127 | Alipore Division | Kakdwip Sub-Division | Construction of 2 Nos. 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Dhaspara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002041/2022-2023 | 12999/AD | 23/03/2023 | 300 | MANASH GHOSH | 656.29 | 0 | 20
8128 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site for Augmentation of Dhaspara W/S Scheme (Zone-I & II), Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002056/2022-2023 | 13064/AD | 24/03/2023 | 45 | AQUATECH ENGINEERS | 47.54 | 0 | 0
8129 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Dhaspara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002076/2023-2024 | 773(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
8130 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at Head work site of Zone-I of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002135/2024-2025 | 1975/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 2.72 | 0 | 0
8131 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Zone-I of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2024-2025 | 1976/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 2.59 | 0 | 0
8132 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhaspara Zone - I & II, Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002161/2023-2024 | 950/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
8133 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dhaspara (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002283/2023-2024 | 919/AD | 08/02/2024 | 45 | BHUNIA BUILDERS | 33.71 | 0 | 80
8134 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dhaspara (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002285/2023-2024 | 970/AD | 12/02/2024 | 30 | JAYANTA KUMAR DEY | 11.81 | 0 | 97
8135 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dhaspara (Zone - I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002611/2023-2024 | 378/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
8136 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000337/2023-2024 | 3152/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
8137 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000507/2023-2024 | 4829/AD | 20/12/2023 | 0 | Resource Division | 39.83 | 0 | 0
8138 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000539/2023-2024 | 23/AD | 02/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
8139 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000691/2023-2024 | 461/AD | 24/01/2024 | 0 | Resource Division | 12.17 | 0 | 0
8140 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/03411/2023-2024 | BP-2023-24-374 | 13/11/2023 | 0 | WBSEDCL | 7.12 | 0 | 0
8141 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Dhaspara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000343/2022-2023 | 3747/SMD | 29/12/2022 | 90 | BARMAN ROY TRADERS | 20.56 | 0 | 90
8142 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at Augmentation PH-2 Zone-I & II of Dhaspara W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001906/2023-2024 | 1191/SMD | 22/03/2024 | 21 | BARMAN ROY TRADERS | 10.73 | 0 | 100
8143 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- IX of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000085/2023-2024 | 213/AD | 20/04/2023 | 810 | JAL PRAVAHIKA PVT. LTD. | 144.19 | 0 | 30
8144 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - IX of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000228/2023-2024 | 1385/AD | 12/07/2023 | 30 | R.P. ENTERPRISE (DAKSHINESWAR) | 13.91 | 0 | 100
8145 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000610/2023-2024 | 241/RSD | 22/08/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 4.04 | 0 | 100
8146 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with Interconnection of Tube Well at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000613/2023-2024 | 243/RSD | 22/08/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 2.34 | 0 | 100
8147 | Alipore Division | Raidighi Sub-Division | EARNEST MONEY DEDUCTION. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002114/2019-2020 | 7761/AD | 27/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 23.06 | 0 | 5
8148 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000662/2023-2024 | 266/AD | 15/01/2024 | 0 | Resource Division | 8.13 | 0 | 0
8149 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
8150 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Head Work Site) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Chaplarkhop W/S Scheme (Zone-XIII, Mathurapur-II Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000431/2023-2024 | 1919/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 100
8151 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 365 | M/S. DAS BUILDERS | 53.21 | 0 | 96
8152 | Alipore Division | Raidighi Sub-Division | Extention of pipeline for Providing Functional Household Tap Connection (FHTC) and allied works at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000609/2024-2025 | 749/RSD | 03/10/2024 | 60 | P.L.CONSTRUCTION | 3.03 | 0 | 100
8153 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 83 Nos.) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000610/2024-2025 | 750/RSD | 03/10/2024 | 60 | P.L.CONSTRUCTION | 4.2 | 0 | 100
8154 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 and approach road and plinth protection including boundary wall at Chaplarkhop W/S Scheme, modified as Zone- XIII of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001711/2023-2024 | 301/RSD | 29/09/2023 | 60 | HALDER ENTERPRISE (I) | 2.86 | 0 | 90
8155 | Alipore Division | Raidighi Sub-Division | Construction of boundary wall at Zone - XIII, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface Water Based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001866/2023-2024 | 140/AD | 05/01/2024 | 30 | SUKUMAR HALDAR | 8.63 | 0 | 100
8156 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001962/2022-2023 | 12716/AD | 14/03/2023 | 30 | P.L.CONSTRUCTION | 25.31 | 0 | 100
8157 | Alipore Division | Raidighi Sub-Division | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 30 | SUKUMAR HALDAR | 7.81 | 0 | 0
8158 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000660/2023-2024 | 264/AD | 15/01/2024 | 0 | Resource Division | 1.69 | 0 | 0
8159 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000323/2023-2024 | 1549/AD | 17/07/2023 | 90 | SAJAL KUMAR DAS | 131.07 | 0 | 20
8160 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 & 4 of Augmentation of Mallik Kati W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001665/2022-2023 | 11477/AD | 15/02/2023 | 807 | SATYAM CONSTRUCTION | 39.13 | 0 | 50
8161 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001684/2022-2023 | 11491/AD | 15/02/2023 | 45 | M/S M.B.ENTERPRISE | 7.07 | 0 | 0
8162 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-III and Head work site to PH-IV of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002002/2022-2023 | 12816/AD | 16/03/2023 | 60 | MA KALI CONSTRUCTION | 67.36 | 0 | 50
8163 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 3) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002049/2022-2023 | 13049/AD | 24/03/2023 | 659 | BINAPANI ENTERPRISE | 7.1 | 0 | 100
8164 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000009/2023-2024 | 113/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
8165 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000018/2023-2024 | 223/AD | 21/04/2023 | 0 | Resource Division | 174.21 | 0 | 0
8166 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000133/2023-2024 | 855/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
8167 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Mallikati PH-3 under Canning -II block (REF ID : 106665556) (APP ID: 1007924332) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01005/2024-2025 | BP-2024-25-206 | 30/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
8168 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service ( power ) connection at Mallikati PH-4 under Canning -II block (REF ID : 106665557) (APP ID: 1007923989) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01006/2024-2025 | BP-2024-25-207 | 30/07/2024 | 0 | WBSEDCL | 13.31 | 0 | 0
8169 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 & 2 for Augmentation of Mallik Kati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000037/2023-2024 | 992/SMD | 06/04/2023 | 819 | A.G.ENTERPRISE | 22.21 | 0 | 45
8170 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-2 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002196/2024-2025 | 1785/SMSD | 31/12/2024 | 15 | A.G.ENTERPRISE | 0.92 | 0 | 0
8171 | S24 Pgns Mechanical | Canning Sub-division | Supply & fixing main switch & Bus Bar at Pump House-1, 2 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002197/2024-2025 | 1681/SMSD | 23/12/2024 | 15 | A.G.ENTERPRISE | 0.59 | 0 | 0
8172 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Aug of Mallikkhati water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15196) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002200/2024-2025 | 1673/SMSD | 20/12/2024 | 15 | A.G.ENTERPRISE | 0.92 | 0 | 0
8173 | Alipore Division | Canning Sub-division | Construction of 250 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- III) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1032] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000037/2023-2024 | 172/AD | 19/04/2023 | 743 | SAMSUL ENTERPRISE | 453.31 | 0 | 56
8174 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000138/2023-2024 | 838/AD | 26/05/2023 | 15 | M/S P. B. CONSTRUCTION | 7.5 | 0 | 0
8175 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - III) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000142/2023-2024 | 278/AD | 24/04/2023 | 45 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0
8176 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001889/2022-2023 | 11550/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 4.29 | 0 | 99
8177 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001954/2022-2023 | 12690/AD | 14/03/2023 | 45 | PODDER ENTERPRISE | 8.92 | 0 | 0
8178 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001955/2022-2023 | 12691/AD | 14/03/2023 | 45 | RIYAZ ENTERPRISE | 8.6 | 0 | 0
8179 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000412/2023-2024 | 368/AD | 19/01/2024 | 0 | Resource Division | 6.36 | 0 | 0
8180 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000719/2023-2024 | 540/AD | 25/01/2024 | 0 | Resource Division | 22.19 | 0 | 0
8181 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Augmentation of Pathankhali Zone-III water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] (SM/15561) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000078/2025-2026 | 1441/SMD | 22/05/2025 | 135 | CMS ENGINEERING CONCERN | 10.87 | 0 | 0
8182 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, Zone-III for Augmentation of Pathankhali supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000279/2023-2024 | 1139/SMD | 24/04/2023 | 90 | M/S. S.R. ENTERPRISE | 29.83 | 0 | 0
8183 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01671/2024-2025 | BP-2024-25-778 | 23/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
8184 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 ,3 & 4 for Augmentation of Ramdhari ( Zone-27) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 946/SMD | 04/04/2023 | 90 | ORIENTAL ENGINEERING CO. | 44.52 | 0 | 0
8185 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-4 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000133/2025-2026 | 701/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
8186 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-3 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000136/2025-2026 | 700/SMSD | 15/05/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
8187 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at 2 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002177/2024-2025 | 420/SMSD | 20/03/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.92 | 0 | 0
8188 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-2,3 & 4 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002178/2024-2025 | 399/SMSD | 19/03/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.88 | 0 | 0
8189 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at 1 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002179/2024-2025 | 419/SMSD | 20/03/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.92 | 0 | 0
8190 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Ramdhari (Zone-27) W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002181/2024-2025 | 398/SMSD | 19/03/2025 | 15 | ORIENTAL ENGINEERING CO. | 0.76 | 0 | 0
8191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.33] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00493/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0
8192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00543/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 65 | 0 | 0
8193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMDHARI MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2971] [TSM/018366] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 97/SWD-I | 10/04/2023 | 90 | TANMOY ROY CHOWDHURY | 396.58 | 0 | 80
8194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (Four) nos. Rig Ground bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for RAMDHARI PWSS of Baruipur Block under South 24 Pgns. W/S Division-I, PHE Dte. (SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000426/2024-2025 | 3753/SWD-I | 28/08/2024 | 180 | ASIT PRAMANIK | 63.36 | 0 | 50
8195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based RAMDHARI Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000925/2022-2023 | 1181/SWD-I | 01/09/2022 | 30 | ASTER CONSULTANCY | 3.04 | 0 | 100
8196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000149/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
8197 | Alipore Division | Canning Sub-division | Payment for "Restoration of P.C Sen road Raibaghini to Golabari Kheyaghat(WB/02/ 564) damaged caused due to laying of water pipelines by PHED. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01192/2024-2025 | BP-2024-25-556 | 11/09/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 21 | 0 | 0
8198 | Alipore Division | Canning Sub-division | Laying of pipe line due to widening of roads from P.C. Sen Road (Raibaghini) to Golabari Kheyaghat at Banibadabelekhali Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000030/2022-2023 | 516/AD | 25/04/2022 | 30 | M.T.C. CONSTRUCTION | 46.43 | 0 | 0
8199 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (755 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) of Augmentation of Banibadabelekhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000221/2023-2024 | 1026/AD | 13/06/2023 | 765 | M.T.C. CONSTRUCTION | 58.43 | 0 | 35
8200 | Alipore Division | Canning Sub-division | Rising main with OHR to distribution system at Banibadabelekhali W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000271/2022-2023 | 263/CSD | 19/05/2022 | 30 | R.P. ENTERPRISE | 1.88 | 0 | 87
8201 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Banibadabelekhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001061/2021-2022 | 5296/AD | 04/01/2022 | 60 | S.S. ENTERPRISE (I) | 63.28 | 0 | 81
8202 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V of Augmentation of Banibadabelekhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001808/2022-2023 | 12132/AD | 01/03/2023 | 30 | KUNTAL CHOWDHURY | 19.59 | 0 | 0
8203 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Banibadabelekhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001945/2022-2023 | 11505/AD | 15/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 1.75 | 0 | 95
8204 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Banibadabelekhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 5) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002050/2022-2023 | 13050/AD | 24/03/2023 | 45 | BINAPANI ENTERPRISE | 7.09 | 0 | 0
8205 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000119/2022-2023 | 3046/AD | 28/09/2023 | 0 | Resource Division | 46.38 | 0 | 0
8206 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000729/2023-2024 | 552/AD | 25/01/2024 | 0 | Resource Division | 59.7 | 0 | 0
8207 | S24 Pgns Mechanical | Canning Sub-division | Quatation for new service (power) connection at Banibada belekhali PH-1 Water supply scheme under Canning-I block Reference ID-106692516, Application No-1007977167 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01364/2024-2025 | BP-2024-25-326 | 31/08/2024 | 0 | WBSEDCL | 14.77 | 0 | 0
8208 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Banibada Belekhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000029/2023-2024 | 974/SMD | 04/04/2023 | 90 | SUPER SKILL | 10.76 | 0 | 0
8209 | Alipore Division | Canning Sub-division | Payment for "Restoration of L066-Sibganj To Nol Garanbose Kheyaghat Via Maheshpur H S nd Bharatgarh Market(WB/02/318), damaged caused due to laying of water pipelines by PHED. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01191/2024-2025 | BP-2024-25-557 | 11/09/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 25.5 | 0 | 0
8210 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
8211 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001193/2023-2024 | 3998/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.99 | 0 | 100
8212 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001713/2022-2023 | 11677/AD | 20/02/2023 | 810 | R.G. ENTERPRISE (I) | 7.1 | 0 | 100
8213 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001714/2022-2023 | 11678/AD | 20/02/2023 | 45 | JYOTI ENTERPRISES | 6.93 | 0 | 100
8214 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001814/2022-2023 | 12154/AD | 01/03/2023 | 45 | B.K. ENTERPRISE. | 39.96 | 0 | 100
8215 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bharatgarh Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001947/2022-2023 | 11506/AD | 15/02/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 2.07 | 0 | 95
8216 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (550 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Bharatgarh Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001998/2022-2023 | 12812/AD | 16/03/2023 | 855 | M/S. MIHIR KUMAR NASKAR | 46.27 | 0 | 30
8217 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002001/2022-2023 | 12815/AD | 16/03/2023 | 45 | SUNNY CONSTRUCTION | 46.05 | 0 | 0
8218 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000117/2022-2023 | 3056/AD | 28/09/2023 | 0 | Resource Division | 97.75 | 0 | 0
8219 | S24 Pgns Mechanical | Canning Sub-division | Charges for new service connection at pump house no 4 of Bharatghar water supply scheme (Basanti Block) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01523/2024-2025 | BP-2024-25-364 | 11/09/2024 | 0 | WBSEDCL | 13.71 | 0 | 0
8220 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/03413/2023-2024 | BP-2023-24-373 | 13/11/2023 | 0 | WBSEDCL | 14.74 | 0 | 0
8221 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Bharatgarh water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000017/2023-2024 | 952/SMD | 04/04/2023 | 791 | SHIVAM ENTERPRISE | 23.39 | 0 | 30
8222 | S24 Pgns Mechanical | Canning Sub-division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Bharatghar W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15503) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000920/2025-2026 | 683/SMSD | 15/05/2025 | 15 | SHIVAM ENTERPRISE | 0.58 | 0 | 0
8223 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
8224 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000150/2023-2024 | 695/AD | 18/05/2023 | 15 | KHOKAN MONDAL | 15.59 | 0 | 0
8225 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Sonakhali (Zone-IV) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000284/2025-2026 | 689/CSD | 26/05/2025 | 30 | KIRON CONSTRUCTION | 3.42 | 0 | 0
8226 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000315/2024-2025 | 2696/AD | 24/06/2024 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
8227 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Sonakhali (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000486/2024-2025 | 3545/AD | 02/09/2024 | 105 | RIVER BENZ CONSTRUCTION | 25.36 | 0 | 75
8228 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000745/2024-2025 | 4412/AD | 05/11/2024 | 30 | TRIMURTI ENTERPRISE | 19.95 | 0 | 0
8229 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001795/2022-2023 | 12130/AD | 01/03/2023 | 30 | SAMIR GIRI | 19.56 | 0 | 0
8230 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001842/2022-2023 | 11540/AD | 16/02/2023 | 45 | TECH VISION | 3.08 | 0 | 0
8231 | Alipore Division | Canning Sub-division | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001986/2022-2023 | 12647/AD | 13/03/2023 | 45 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0
8232 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
8233 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000038/2023-2024 | 242/AD | 24/04/2023 | 0 | Resource Division | 38.11 | 0 | 0
8234 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-IV for Augmentation of Sonakhali Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000290/2023-2024 | 2127/SMD | 30/05/2023 | 90 | INDIA ENTERPRISE | 9.39 | 0 | 0
8235 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00124/2024-2025 | BP-2024-25-36 | 24/04/2024 | 0 | WBSEDCL | 7.18 | 0 | 0
8236 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Kanthal Beria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 1067/SMD | 18/04/2023 | 623 | B.T.PROJECTS PVT.LTD. | 22.37 | 0 | 100
8237 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Kathal Beria W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15870) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000144/2024-2025 | 1006/SMSD | 11/07/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
8238 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Kathal Beria W/S scheme under SMD, P.H.E. Dte.(Block-Baruipur) (SM/15870) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000145/2024-2025 | 1005/SMSD | 11/07/2024 | 15 | B.T.PROJECTS PVT.LTD. | 0.89 | 0 | 100
8239 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & installation of LED board at P.H. No-1 & 2 of KANTHALBERIA water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Baruipur][SM/15870] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 1185/SMSD | 21/08/2024 | 15 | KARTICK BAL | 0.78 | 0 | 100
8240 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KANTHALBERIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 634] [TSM/018250] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000082/2023-2024 | 416/SWD-I | 02/05/2023 | 836 | SUJAN KUMAR MISTRY | 149.57 | 0 | 85
8241 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, protection for pipeline and other allied works for Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15870) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000435/2024-2025 | 3879/SWD-I | 03/09/2024 | 60 | SUJAN KUMAR MISTRY | 47.19 | 0 | 0
8242 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KANTHAL BERIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018250] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000641/2022-2023 | 3290/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 100
8243 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kanthal Beria Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000939/2022-2023 | 1256/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.46 | 0 | 100
8244 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000124/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 11.83 | 0 | 0
8245 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service(power) connection at Padmapukuria PH-1 water supply scheme under bhangar-I block Reference ID-106626291, Application No- 1007839611 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00647/2024-2025 | BP-2024-25-155 | 10/07/2024 | 0 | WBSEDCL | 12.7 | 0 | 0
8246 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service(power) connection at Padmapukuria PH -2 water supply scheme under bhangar-I block Reference ID- 106550930, Application No- 1007657634 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00982/2024-2025 | BP-2024-25-215 | 30/07/2024 | 0 | WBSEDCL | 14.05 | 0 | 0
8247 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 of Padmapukuria water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001523/2022-2023 | 930/SMD | 30/03/2023 | 824 | SINHA ELECTRICALS | 22.91 | 0 | 90
8248 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land, Construction of internal service road, pipeline protection, drum sheet walling and others allied works at HW site & 2nd Tubewell site of "PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District under Jal Jeevan Mission." (SM/15772) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000519/2024-2025 | 3982/SWD-I | 11/09/2024 | 488 | D-4 CONSTRUCTION | 77.7 | 0 | 50
8249 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PADMAPUKURIA PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018416] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000669/2022-2023 | 3411/SWD-I | 10/03/2023 | 30 | REALIENCE CONSTRUCTION | 31.79 | 0 | 100
8250 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. Boundary Walls, one at Headwork site & other at 2nd tube-well site, of PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15772] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000827/2023-2024 | 1108/SWD-I | 05/03/2024 | 577 | M.R.U. CONSTRUCTION | 27.66 | 0 | 70
8251 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000044/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.61 | 0 | 0
8252 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000244/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.23 | 0 | 0
8253 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Goalberia water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1141/SMD | 24/04/2023 | 90 | BISALAXMI ENTERPRISE | 17.98 | 0 | 0
8254 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GOALBERIA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 878] [TSM/018461] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 1507/SWD-I | 20/07/2023 | 600 | KALPANA TRADERS | 280.17 | 0 | 35
8255 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GOALBERIA PWSS of JOYNAGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018461] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000645/2022-2023 | 3317/SWD-I | 06/03/2023 | 30 | MOUSUMI DAS SARKAR | 31.72 | 0 | 0
8256 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "GOYALBERIA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000753/2022-2023 | 709/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.77 | 0 | 100
8257 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15774) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000865/2023-2024 | 1201/SWD-I | 11/03/2024 | 45 | MONDAL CONSTRUCTION (BARUIPUR) | 44.48 | 0 | 0
8258 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000305/2023-2024 | 2442/SWD-I | 30/09/2023 | 0 | Resource Division | 21.51 | 0 | 0
8259 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sonarpur] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 1035/SMD | 13/04/2023 | 90 | A.K. INDUSTRIES | 25.4 | 0 | 0
8260 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.16] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00475/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 17.53 | 0 | 0
8261 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.22] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00481/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 1.07 | 0 | 0
8262 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1543) (TSM/017732) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 392/SWD-I | 28/04/2023 | 887 | NIRMAN ENTERPRISE | 370.71 | 0 | 25
8263 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & others allied works of ¿GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/15862). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000239/2024-2025 | 2659/SWD-I | 07/06/2024 | 45 | NIRMAN ENTERPRISE | 59.77 | 0 | 0
8264 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/15862] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000679/2022-2023 | 3465/SWD-I | 15/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 0
8265 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15862) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000754/2024-2025 | 4706/SWD-I | 18/11/2024 | 45 | N. ENTERPRISE | 10 | 0 | 0
8266 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000002/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 30.53 | 0 | 0
8267 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000225/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 9.5 | 0 | 0
8268 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05027/2023-2024 | BP-2023-24-562 | 11/03/2024 | 0 | WBSEDCL | 6.54 | 0 | 0
8269 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Beladanga water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000280/2023-2024 | 1140/SMD | 24/04/2023 | 90 | M/S. DAS ENTERPRISE | 26.01 | 0 | 0
8270 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BELADANGA Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15864] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 911/SWD-I | 02/04/2025 | 30 | ARUP ENTERPRISE | 15.58 | 0 | 0
8271 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall, Pump House cum Chlorine Room and Laying Distribution System, Rising Main and providing FHTC for Augmentation of BELADANGA Piped W/S Scheme of Joynagar-I Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1424] [TSM/020328]. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000075/2023-2024 | 389/SWD-I | 28/04/2023 | 1200 | M/S T.R. CONSTRUCTION | 312.36 | 0 | 5
8272 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BELADANGA PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/020328) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000703/2022-2023 | 3512/SWD-I | 17/03/2023 | 660 | ASIT PRAMANIK | 31.76 | 0 | 75
8273 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Beladanga Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000989/2022-2023 | 1493/SWD-I | 27/09/2022 | 30 | MEASURE LAND | 2.47 | 0 | 100
8274 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000168/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.95 | 0 | 0
8275 | Alipore Division | Canning Sub-division | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-III), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018434] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000034/2023-2024 | 275/AD | 24/04/2023 | 300 | I.S. ENTERPRISE | 325.97 | 0 | 35
8276 | Alipore Division | Canning Sub-division | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001194/2023-2024 | 3999/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 22.45 | 0 | 0
8277 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001926/2022-2023 | 11799/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 3.18 | 0 | 0
8278 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000408/2023-2024 | 362/AD | 19/01/2024 | 0 | Resource Division | 7.37 | 0 | 0
8279 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000722/2023-2024 | 544/AD | 25/01/2024 | 0 | Resource Division | 40.24 | 0 | 0
8280 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Dakhshin Kalyanpur Panchanantala to Uttar Sashan Santali Sangha (Barikpara, Gazipara, Kalyanpur Uttar Railgate, Pashchim Madhabpur) 2) Repairing of Road from Sikharbali- I GP to Dakshin Kalyanpur at Sikhardali-1 GP under Baruipur PS | AE BSD,Assistant Engineer | Junior Engineer | BILL/01731/2024-2025 | BP-2024-25-795 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.86 | 0 | 0
8281 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05122/2023-2024 | BP-2023-24-578 | 12/03/2024 | 0 | WBSEDCL | 7 | 0 | 0
8282 | S24 Pgns Mechanical | Baruipur Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | AE BSD,Assistant Engineer | Junior Engineer | BILL/05708/2023-2024 | BP-2023-24-606 | 28/03/2024 | 0 | WBSEDCL | 4.26 | 0 | 0
8283 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Dakshin Kalayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000079/2023-2024 | 1059/SMD | 18/04/2023 | 90 | MAA TARA ENTERPRISE | 10.89 | 0 | 0
8284 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 of Dakshin Kalyanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001909/2023-2024 | 1193/SMD | 22/03/2024 | 90 | SWAPAN ENTERPRISE | 10.99 | 0 | 0
8285 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Dakshin Kalyanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002289/2024-2025 | 83/SMSD | 17/01/2025 | 15 | MAA TARA ENTERPRISE | 0.91 | 0 | 0
8286 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 of Dakshin Kalyanpur W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/15779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/002290/2024-2025 | 84/SMSD | 17/01/2025 | 15 | MAA TARA ENTERPRISE | 0.29 | 0 | 0
8287 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DAKSHIN KALYANPUR Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 968] [TSM/018483] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000498/2023-2024 | 2156/SWD-I | 04/09/2023 | 850 | RAKESH ENTERPRISE | 155.54 | 0 | 75
8288 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, and other allied works for "Ground Water Based DAKSHIN KALYANPUR Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000525/2024-2025 | 4018/SWD-I | 13/09/2024 | 60 | RAKESH ENTERPRISE (HOWRAH) | 78.26 | 0 | 0
8289 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DAKSHIN KALYANPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018483] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000642/2022-2023 | 3291/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 50
8290 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Kalyanpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000948/2022-2023 | 1279/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.47 | 0 | 100
8291 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DAKSHIN KALYANPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15779] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001190/2024-2025 | 775/SWD-I | 18/03/2025 | 30 | M/S PURNENDU SHEKHAR NASKAR | 15.87 | 0 | 0
8292 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000117/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 35.27 | 0 | 0
8293 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Dongajora water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kultali] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 1013/SMD | 11/04/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 10.81 | 0 | 0
8294 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional House Hold Tap Connection (FHTC) at DONGAJORA of KULTALI Block for Ground Water Based DONGAJORA Piped Water Supply Scheme under South 24 Paragana W/S Division-I, PHE Dte. under South 24 Pgns. Dist. (TSM/020398) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000702/2022-2023 | 3511/SWD-I | 17/03/2023 | 90 | AYUSH ENTERPRISE | 77.23 | 0 | 0
8295 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dongajora Piped Water Supply Scheme to accommodate FHTC in Kultoli Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000986/2022-2023 | 1483/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.4 | 0 | 100
8296 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000077/2021-2022 | 1104/SWD-I JJM | 25/10/2021 | 120 | J.D. CONSTRUCTION | 90.16 | 0 | 100
8297 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Jamalpur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8294) Part - B | AE BSD |  | ORD/000454/2022-2023 | 2729/SWD-I | 27/01/2023 | 45 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 9.53 | 0 | 100
8298 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Narayangar (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1542] (TSM/018335) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000083/2023-2024 | 196/AD | 19/04/2023 | 90 | EQUIPMENTS & SPARES AGENCIES | 255.63 | 0 | 85
8299 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000135/2023-2024 | 690/AD | 18/05/2023 | 60 | SNEHA CONSTRUCTION | 58.66 | 0 | 95
8300 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000466/2023-2024 | 1928/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.35 | 0 | 98
8301 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000467/2023-2024 | 1929/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 98
8302 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000468/2023-2024 | 1930/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 98
8303 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Narayangarh piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15961) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000569/2024-2025 | 3979/AD | 27/09/2024 | 540 | GHOSH ENTERPRISE (II) | 138.78 | 0 | 25
8304 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Narayangar (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001846/2022-2023 | 11813/AD | 23/02/2023 | 45 | TECH VISION | 4.6 | 0 | 0
8305 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Narayangar (Part-B) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002019/2022-2023 | 12925/AD | 16/03/2023 | 45 | SWASTIK CONSTRUCTION | 22.8 | 0 | 81
8306 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
8307 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000008/2023-2024 | 114/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
8308 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000064/2023-2024 | 267/AD | 24/04/2023 | 0 | Resource Division | 27.5 | 0 | 0
8309 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000134/2023-2024 | 849/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
8310 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/02962/2023-2024 | BP-2023-24-292 | 11/10/2023 | 0 | WBSEDCL | 9.54 | 0 | 0
8311 | S24 Pgns Mechanical | Canning Sub-division | Payment of electricity bill for new service connection under SMD, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/03521/2023-2024 | BP-2023-24-385 | 23/11/2023 | 0 | WBSEDCL | 41.14 | 0 | 0
8312 | S24 Pgns Mechanical | Canning Sub-division | Supply & installation of LED board at P.H. No-1 & 2 of Narayangarh (Aug) water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000100/2024-2025 | 523/SMSD | 26/04/2024 | 15 | COOLING CARE CENTER | 0.78 | 0 | 100
8313 | S24 Pgns Mechanical | Canning Sub-division | Supply delivery of standby submersible pump motor at Narayangargh Part-B PH-1 water supply scheme Under SMD PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000385/2024-2025 | 1028/SMSD | 15/07/2024 | 15 | NARAYAN ENTERPRISE | 0.52 | 0 | 100
8314 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Narayangarh Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000598/2023-2024 | 2368/SMD | 30/06/2023 | 704 | A.S.ENTERPRISE | 27 | 0 | 85
8315 | S24 Pgns Mechanical | Canning Sub-division | Improvement of outdoor illumination arrangement with allied works at Narayangarh Part-B, PH-2, under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002947/2023-2024 | 159/SMSD | 05/02/2024 | 15 | A.S.ENTERPRISE | 0.88 | 0 | 100
8316 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of quotation for effecting new service connection at Khanberia under Asuti-I&II and Chatta GP JL No. 32, Khatian No. 1268 Application No. 1007832957 Reference ID - 106623121 | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/00532/2024-2025 | BP-2024-25-130 | 24/06/2024 | 0 | WBSEDCL | 14.33 | 0 | 0
8317 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Bill for Security Deposit for New Service Connection | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/01263/2022-2023 | BP-2022-23-438 | 10/03/2023 | 0 | CESC LTD | 4.35 | 0 | 0
8318 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/04224/2023-2024 | BP-2023-24-433 | 27/12/2023 | 0 | CESC LTD | 4.54 | 0 | 0
8319 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/04687/2023-2024 | BP-2023-24-506 | 12/02/2024 | 0 | WBSEDCL | 10.06 | 0 | 0
8320 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/04926/2023-2024 | BP-2023-24-531 | 26/02/2024 | 0 | CESC LTD | 2.34 | 0 | 0
8321 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | BILL/04933/2023-2024 | BP-2023-24-541 | 27/02/2024 | 0 | CESC LTD | 2.44 | 0 | 0
8322 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000612/2022-2023 | 771/SMD | 16/03/2023 | 90 | CINZANO | 39.14 | 0 | 100
8323 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Renovation of external illumination arrangement with other allied works at P.H. No. - 5 of Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme (Mahisgot), under South 24 Pgs Mechanical Division, PHE Dte. (Block : Bishnupur-I)(SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000726/2024-2025 | 1033/AE-II/SMD | 13/08/2024 | 15 | SUDIP PRADHAN | 0.78 | 0 | 100
8324 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 & 5 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001476/2023-2024 | 683/SMD | 01/02/2024 | 90 | KARUNAMOY ENGINEERING | 25.15 | 0 | 100
8325 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 14 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001482/2023-2024 | 687/SMD | 01/02/2024 | 90 | SHIVAM ENTERPRISE | 12.58 | 0 | 0
8326 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 8 & 9 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001491/2023-2024 | 685/SMD | 01/02/2024 | 484 | DIPA CHHETRI | 25.44 | 0 | 50
8327 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 6 & 7 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001542/2023-2024 | 676/SMD | 01/02/2024 | 700 | P.K. ENTERPRISE | 25.45 | 0 | 40
8328 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 10 & 11 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001544/2023-2024 | 675/SMD | 01/02/2024 | 90 | P.K. ENGINEERING | 25.4 | 0 | 40
8329 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 12 & 13 for Augmentation of Asuti I/II & Chatta GP water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Thakurpukur Maheshtala] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001546/2023-2024 | 674/SMD | 01/02/2024 | 90 | DEBJYOTI BASU | 25.41 | 0 | 0
8330 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Upgradation of external illumination arrangement with other allied works at P.H. No. - 8 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme (Chalkipara), under South 24 Pgs Mechanical Division, PHE Dte. (Block : Thakurpukur Maheshtala) (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001822/2024-2025 | 1377-AE-II-SMD | 26/11/2024 | 15 | STANDARD ENGINEERING | 0.76 | 0 | 0
8331 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Upgradation of external illumination arrangement with other allied works at PH No-1 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Thakurpukur Maheshtala) (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002102/2023-2024 | 146-AE-II-SMD | 07/02/2024 | 15 | M/S POUSALI ENTERPRISE | 0.75 | 0 | 100
8332 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply and installation of LED Glow sign board with allied works at PH No-3 under Augmentation of Asuti-I/II & Chatta GP Water Supply Scheme, under South 24-Pgs Mechanical Division,PHE Dte (Block: Thakurpukur Maheshtala) (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/002368/2023-2024 | 148-AE-II-SMD | 07/02/2024 | 15 | MAA TARA ENTERPRISE | 0.75 | 0 | 0
8333 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation, commissioning and trial run of auto cum manual control panel including pumping machinery and related accessories at Tube Well no.1 of Chata Gram Panchayet area under South 24-Pgs Mechanical Division PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/003266/2021-2022 | 914/SMD | 09/08/2021 | 90 | J.K. ENGINEERING CO. | 5.81 | 0 | 0
8334 | S24 Pgns Mechanical | Sub-Division - I under South 24 W/s Division - I | Supply, installation & Commissioning of 30 KVA voltage stabilizer at Asuti-I&II Gram Panchayet area Block-Thakurpukur Maheshtala under South 24-Pgs Mechanical Division PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/003608/2021-2022 | 868/SMD | 28/07/2021 | 30 | S.P. CONSTRUCTION | 3.93 | 0 | 0
8335 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 1090 | M/S. S.S. ENTERPRISE | 316.71 | 0 | 80
8336 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Sonamukhi Krishnanagar under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000008/2022-2023 | 850/SWD-I | 12/07/2022 | 60 | M/S. TORSA ENTERPRISE | 7.04 | 0 | 100
8337 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 3 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-I under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000009/2022-2023 | 853/SWD-I | 12/07/2022 | 60 | M/S. S.S. ENTERPRISE | 50.84 | 0 | 100
8338 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply and Installation of DI specials with allied works under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte, South 24 Pgns Dist. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000021/2025-2026 | 973/SWD-I | 09/04/2025 | 30 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 18.93 | 0 | 75
8339 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Ganney Gangadharpur Mouza near Asuti II GP under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000068/2022-2023 | 1113/SWD-I | 23/08/2022 | 60 | JYOTI ENTERPRISE | 6.01 | 0 | 0
8340 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of Road (Sonamukhi Chowmatha More, Das Para road, Nandalal Chatterjee road Shibrampur Main road) damaged due to laying of 150 & 200mm dia DI Pipe of KMC Bagpota Road under Asuti I, Asuti - II and Chatta Water Supply scheme of South 24 Pargana W/S Division-I, P.H.E Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000091/2025-2026 | 1766/SWD-I | 02/07/2025 | 45 | GAYATRI CONSTRUCTION | 33.77 | 0 | 0
8341 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 03 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accomodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-I) [TSM/019643] [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000120/2023-2024 | 532/SWD-I | 11/05/2023 | 30 | PADMA ENGINEERING CO. | 64.72 | 0 | 100
8342 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance pipeline laying, road repair with allied works under proposed ground water based Asuti I Asuti II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000131/2025-2026 | 2096/SWD-I | 14/08/2025 | 289 | M/S. S.S. ENTERPRISE (NODAKHALI) | 139.27 | 0 | 20
8343 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from proposed Tubewell to existing OHR for zone I with interconnection and bypass arrangement of Asuti Chatta W/S Scheme under Thakurpukur Maheshtala Block under South 24-Parganas W/S Division-I, PHE Dte | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000175/2021-2022 | 2389/SWD-I | 25/02/2022 | 1131 | M/S. S.S. ENTERPRISE | 67.25 | 0 | 25
8344 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Hiring of 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador/ Indica/ Swift Dezire Car) with driver for official use of the Assistant Engineers, South 24-Pgns. W/S Sub-Division-I, under South 24-Pgns, W/S Divn-I, P.H.E. Dte. (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000179/2023-2024 | 780/SWD-I | 31/05/2023 | 183 | AMARI BHADRA | 0.87 | 0 | 40
8345 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of UPVC pipeline for Zone-I of Chata GP under Thakurpukur-Maheshtala Water Supply Scheme under SWD-I, PHE Dte., District-South 24-Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000205/2022-2023 | 733/SWD-I | 27/06/2022 | 1285 | M/S. S.S. ENTERPRISE | 526.13 | 0 | 65
8346 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Over Head Reservoir of capacity 1500 cum at ZONE - I of Asuti-I/II & Chata water supply scheme under South 24 Pgs Water Supply Divn.-I . PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000206/2022-2023 | 158/SWD-I | 25/04/2022 | 1347 | M/S. S.S. ENTERPRISE | 344.98 | 0 | 100
8347 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000276/2024-2025 | 2683/SWD-I | 07/06/2024 | 171 | SAROJ KUMAR SINGH | 0.81 | 0 | 0
8348 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road restoration from Malangermath to Neemtala damaged due to pipeline under Asuti and Asuti-II Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000293/2024-2025 | 3132/SWD-I | 10/07/2024 | 45 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 21.38 | 0 | 100
8349 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 2 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-II under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000331/2021-2022 | 2388/SWD-I JJM | 25/02/2022 | 60 | M/S. S.S. ENTERPRISE | 34.05 | 0 | 0
8350 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Ganney Gangadharpur (JL-28, Plot-510) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000358/2021-2022 | 2384/SWD-I | 25/02/2022 | 60 | JYOTI ENTERPRISE | 7.57 | 0 | 0
8351 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Chatta Kalikapur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000385/2020-2021 | 2065/SWD-I | 19/02/2021 | 90 | SAMPSON INFRA DESIGN LLP | 8.63 | 0 | 100
8352 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Shankharipota (JL-36, Plot-69) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000389/2021-2022 | 2386/SWD-I | 25/02/2022 | 60 | M/S. DAS ENTERPRISE | 7.57 | 0 | 100
8353 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnections of 04 (Four) nos. pumps for Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000393/2024-2025 | 3641/SWD-I | 20/08/2024 | 30 | M/S. S.S. ENTERPRISE (NODAKHALI) | 22.07 | 0 | 0
8354 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Sonamukhi Krishnanagar (JL-38, Plot-22) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000416/2021-2022 | 2385/SWD-I | 25/02/2022 | 60 | M/S. TORSA ENTERPRISE | 7.56 | 0 | 0
8355 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance Concrete for Over Head Reservoir of capacity 1500 cum at Zone-I of Asuti-I/II & Chata Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000441/2023-2024 | 2097/SWD-I | 30/08/2023 | 30 | M/S. S.S. ENTERPRISE | 4.02 | 0 | 100
8356 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Kh-1) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000459/2021-2022 | 2382/SWD-I | 25/02/2022 | 60 | SNEHA CONSTRUCTION | 5.02 | 0 | 100
8357 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1300 m3) site inside Zone no.- I (Mouza- Kalikapur, JL No.- 22, Plot No.- 4323) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000460/2021-2022 | 1221/SWD-I | 12/11/2021 | 30 | G TECH INDIA | 0.54 | 0 | 100
8358 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Pipeline in uncovered areas of Chatta Kalikapur Mouza under Asuti I/ Asuti II and Chata GP Piped Water Supply Scheme to accommodate FHTC in Thakurpukur Mahestala Block under South 24 Pgns. W/S Division-I, PHE Dte., South 24 Parganas Districts (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000511/2024-2025 | 3979/SWD-I | 11/09/2024 | 30 | M/S. S.S. ENTERPRISE (NODAKHALI) | 23.86 | 0 | 80
8359 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Plot-4350) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000606/2021-2022 | 2383/SWD-I | 25/02/2022 | 60 | M/S. SREEJIT ENTERPRISE | 6.08 | 0 | 0
8360 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accommodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-II) [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000635/2022-2023 | 3259/SWD-I | 02/03/2023 | 30 | PADMA ENGINEERING CO. | 43.15 | 0 | 100
8361 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for ground water based ASUTI I & II and CHATTA GP PWSS in Thakurpukur Maheshtala Block under South 24 Parganas W/S Division-I, PHE, Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000660/2022-2023 | 3376/SWD-I | 10/03/2023 | 60 | STAR ENTERPRISE | 17.94 | 0 | 40
8362 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 05 (Five) nos. Boundary Wall (Length 51 m X 5 nos.) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000663/2022-2023 | 3379/SWD-I | 10/03/2023 | 45 | SIMRAN ENTERPRISE | 42.26 | 0 | 60
8363 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair & Retrofitting of Civil Structures at Chatta Head Work Site with allied Works at ZONE - I of Asuti-I/II & Chatta under Proposed Ground Water Based Asuti-I/II & Chatta GP Piped Water Supply Scheme to accomodates FHTC in Thakurpukur-Maheshtala Block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000677/2023-2024 | 3094/SWD-I | 06/12/2023 | 757 | M/S. S.S. ENTERPRISE (NODAKHALI) | 19.5 | 0 | 60
8364 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 22) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000692/2022-2023 | 3495/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 0 | 100
8365 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 510) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000693/2022-2023 | 3496/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 0 | 100
8366 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 2922, Plot No.- 4350) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000694/2022-2023 | 3497/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 0 | 100
8367 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Balance UPVC pielines within Asuti-I/II GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakur pukur Mahestala Block under South 24 Pgns W/S Div I PHED (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000698/2024-2025 | 4500/SWD-I | 30/10/2024 | 152 | SUPRITI ENTERPRISE | 94.83 | 0 | 40
8368 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Balance FHTC for ThakurpukurMaheshtala Block (Part) in connection to "Piped Water Supply Scheme for ASUTI I & ASUTI II GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. [TSM/010373] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000701/2022-2023 | 3510/SWD-I | 17/03/2023 | 714 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 72.39 | 0 | 10
8369 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 05 (Five) nos. Pump Houses (Size 4.80 m X 3.66 m) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000711/2022-2023 | 3536/SWD-I | 20/03/2023 | 60 | M/S J. ENTERPRISE | 34.14 | 0 | 55
8370 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Chatta Kalikapur Pump House Site to facilitate the boring of Tubewell under Asuti-I / Asuti-II & Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000718/2023-2024 | 361/SWD-I | 16/01/2024 | 30 | MS POUSALI ENTERPRISE | 4.83 | 0 | 100
8371 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Balance UPVC pielines within Chatta GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Mahestala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000728/2024-2025 | 4615/SWD-I | 13/11/2024 | 120 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 174.51 | 0 | 45
8372 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road Restoration of Different pathways excavates for laying of pipeline underground water based ASUTI I/II & Chatta GP PWSS to accommodate FHTC in Thakur Pukur Maheshtala Block under South 24 Parganas W/S Division -I P.H.E. Dte. (SM/ 15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000729/2024-2025 | 4616/SWD-I | 13/11/2024 | 169 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 135.92 | 0 | 45
8373 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Modification of foundation of awarded of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata Piped Water Supply Scheme to accommodate FHTC in Thakurpukur-Maheshtala block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000750/2023-2024 | 552/SWD-I | 31/01/2024 | 20 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 11.88 | 0 | 100
8374 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Development and yield testing of (4 Nos) rig ground bored 300 mm x 200 mm dia & 300 mtr. deep tube-well for Asuti-I, II and Chatta GP PWSS at Rameswarpur, Chatta Head work site, Ganney Gangadharpur and Sarsuna in the Arsenic afeected areas of South 24-Parganas district under South 24-Parganas W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000759/2024-2025 | 4680/SWD-I | 18/11/2024 | 30 | PADMA ENGINEERING CO. | 2.71 | 0 | 0
8375 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000761/2023-2024 | 3246/SWD-I | 15/12/2023 | 180 | SAROJ KUMAR SINGH | 0.86 | 0 | 50
8376 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Ganney Gangadharpur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000767/2020-2021 | 2063/SWD-I | 19/02/2021 | 90 | J. ENTERPRISE | 9.43 | 0 | 100
8377 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land development of tube-well sites at Kalagachia Chalkipara & Sarsuna under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000767/2024-2025 | 4688/SWD-I | 18/11/2024 | 30 | K.P CONSTRUCTION | 8.29 | 0 | 100
8378 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Temporary road repairing at Chata Bazar Moshgot Road under Asuti I / Asuti II and Chatta W/S Scheme under South 24-Pgns, W/S Division-I, P.H.E. Dte. [SM/15660] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000865/2024-2025 | 4923/SWD-I | 03/12/2024 | 393 | M/S. S.S. ENTERPRISE (NODAKHALI) | 60.96 | 0 | 60
8379 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 04 (four) nos. Switching cum control room at Kalikapur, Kalagachia, Khalpar and near Ashuti-I Panchayat office for ASUTI I/II & CHATTA GP Piped Water Supply Scheme to accommondate FHTC in THAKURPUKUR MAHESHTALA Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000879/2024-2025 | 4977/SWD-I | 05/12/2024 | 180 | MOTIONMASS TECHNO OPC PVT LTD | 17.66 | 0 | 50
8380 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/12/2024 to 31/05/2025] [Vehicle NoWB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001062/2024-2025 | 4879/SWD-I | 29/11/2024 | 182 | SAROJ KUMAR SINGH | 0.86 | 0 | 50
8381 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply, installation, trail run, commissioning of Full Bore Electromagnetic Flow Meter in connection to PWS Scheme of proposed ground water based ASUTI- I /II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 Parganas W/S Division-I, PHE Dte., South 24-Parganas District. [SM/15660] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001129/2024-2025 | 192/SWD-I | 17/01/2025 | 15 | B.S. RUBBER INDUSTRIES | 4.77 | 0 | 0
8382 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection pipeline for 04 nos. tube-well with rising main under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) (2nd call) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001144/2024-2025 | 314/SWD-I | 28/01/2025 | 30 | SRIJON ENTERPRISE | 11.69 | 0 | 100
8383 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000284/2023-2024 | 2007/SWD-I | 28/08/2023 | 0 | Resource Division | 3.73 | 0 | 0
8384 | Alipore Division | Kakdwip Sub-Division | Construction of 60 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Durganagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000022/2023-2024 | 97/AD | 11/04/2023 | 1199 | ADITYA HAZRA | 108.12 | 0 | 30
8385 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durganagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002048/2023-2024 | 509/AD | 25/01/2024 | 406 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 27.8 | 0 | 80
8386 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002071/2022-2023 | 13221/AD | 31/03/2023 | 30 | G.M. ENTERPRISE | 15.94 | 0 | 100
8387 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002072/2022-2023 | 13222/AD | 31/03/2023 | 30 | KHOKAN MONDAL | 15.16 | 0 | 100
8388 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002073/2022-2023 | 13223/AD | 31/03/2023 | 30 | BHUNIA BUILDERS | 7.25 | 0 | 82
8389 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002074/2022-2023 | 13224/AD | 31/03/2023 | 30 | BHOLANATH CONSTRUCTION | 8.23 | 0 | 50
8390 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
8391 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000128/2023-2024 | 664/AD | 17/05/2023 | 0 | Resource Division | 1.65 | 0 | 0
8392 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000468/2023-2024 | 4775/AD | 19/12/2023 | 0 | Resource Division | 0.71 | 0 | 0
8393 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000786/2023-2024 | 630/AD | 30/01/2024 | 0 | Resource Division | 1.16 | 0 | 0
8394 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Durganagar Water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001782/2023-2024 | 4766/SMD | 06/12/2023 | 183 | COMBINE ENTERPRISES | 9.42 | 0 | 0
8395 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - II (Debipur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000609/2023-2024 | 240/RSD | 22/08/2023 | 30 | DIPTI ENTERPRISE | 0.96 | 0 | 99
8396 | Alipore Division | Raidighi Sub-Division | Parallel distribution pipeline to provide FHTC at Debipur moza under Zone-II of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001135/2022-2023 | 600/RSD | 23/12/2022 | 30 | SANKAR HALDER | 4.76 | 0 | 99
8397 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 365 | M/S. JHARNA ENTERPRISE | 101.84 | 0 | 85
8398 | Alipore Division | Raidighi Sub-Division | Protection and other ancillary work (Node No. 2-30, 28-26, 25-23, 21-22, 17-19) for laying distribution system and providing FHTC at Zone - II Block of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under under Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001799/2022-2023 | 930/RSD | 10/03/2023 | 30 | DIPTI ENTERPRISE | 4.27 | 0 | 99
8399 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 64.12 | 0 | 75
8400 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000033/2022-2023 | 3450/AD | 25/07/2022 | 0 | Resource Division | 45.51 | 0 | 0
8401 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000035/2022-2023 | 3588/AD | 29/07/2022 | 0 | Resource Division | 3.28 | 0 | 0
8402 | Alipore Division | Baruipur Sub-Division | Road restoration of Nolgora to Sonartikari | AE BSD |  | BILL/01782/2024-2025 | BP-2024-25-807 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.42 | 0 | 0
8403 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VIIB (BINODPUR) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000399/2021-2022 | 2534/SWD-I | 08/03/2022 | 120 | M/S. S.S. ENTERPRISE | 739.71 | 0 | 0
8404 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VIIA (BINODPUR MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000873/2022-2023 | 72/SWD-I | 13/04/2022 | 120 | MRITYUNJOY MUKHERJEE AND CO | 518.85 | 0 | 60
8405 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-VII (Binodpur) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [SM / 18221] | AE BSD |  | ORD/001182/2024-2025 | 629/SWD-I | 28/02/2025 | 300 | PATH MAKERS | 436.4 | 0 | 0
8406 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000042/2022-2023 | 2958/SWD-I | 16/02/2023 | 0 | Resource Division | 1067.77 | 0 | 0
8407 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000063/2022-2023 | 2978/SWD-I | 20/02/2023 | 0 | Resource Division | 443.48 | 0 | 0
8408 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000071/2022-2023 | 2987/SWD-I | 20/02/2023 | 0 | Resource Division | 29.22 | 0 | 0
8409 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000296/2023-2024 | 2434/SWD-I | 30/09/2023 | 0 | Resource Division | 33.95 | 0 | 0
8410 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. | AE BSD |  | BILL/00655/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0
8411 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Payment of Enhanced GST Rate vide W/O No.2336/SWD-I dt. 22/02/2022 | AE BSD |  | BILL/01807/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 20.95 | 0 | 0
8412 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Payment of Enhanced GST Rate vide W/O No.2483/SWD-I dt. 02/03/2022 | AE BSD |  | BILL/01809/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 4.66 | 0 | 0
8413 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Making arrangements for laying of 406.4 mm dia M.S. pipe of Tertiary Grid over Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II Block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24 pgns Water Supply Division-I, PHE Dte. [SM/18222] | AE BSD |  | ORD/000075/2025-2026 | 1578/SWD-I | 11/06/2025 | 45 | SRIJON ENTERPRISE | 32.71 | 0 | 0
8414 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipe carrying structure with laying of 508 mm dia M.S. Secondary Rising Main for crossing of Canal at Simana Bazar, 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Path Pukur Bridge and 355.6 mm dia M.S. pipe for Secondary Rising Main for crossing of Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VI, Zone-IV and Zone-II respectively within JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16191, 18655 & 18222] | AE BSD |  | ORD/000285/2024-2025 | 3041/SWD-I | 02/07/2024 | 45 | SRIJON ENTERPRISE | 69.41 | 0 | 100
8415 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-II-B (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000400/2021-2022 | 2483/SWD-I | 02/03/2022 | 1200 | SAMIRON GHOSH | 385.01 | 0 | 95
8416 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-II-A (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000408/2021-2022 | 2336/SWD-I | 22/02/2022 | 1320 | SAMIRON GHOSH | 579.07 | 0 | 95
8417 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap For " Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.(TSM/016052) | AE BSD |  | ORD/000431/2023-2024 | 2005/SWD-I | 28/08/2023 | 300 | M/S. S.S. ENTERPRISE | 435.92 | 0 | 0
8418 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of restoration of road, pipeline protection works and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-II at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/18222) (2nd call) | AE BSD |  | ORD/000736/2024-2025 | 4634/SWD-I | 14/11/2024 | 225 | P.L. CONSTRUCTION | 83.92 | 0 | 45
8419 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000065/2022-2023 | 2980/SWD-I | 20/02/2023 | 0 | Resource Division | 28.62 | 0 | 0
8420 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000293/2023-2024 | 2431/SWD-I | 30/09/2023 | 0 | Resource Division | 709.28 | 0 | 0
8421 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kachukhali W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000189/2025-2026 | 629/CSD | 21/05/2025 | 30 | HALDER & CO. | 2.93 | 0 | 100
8422 | Alipore Division | Canning Sub-division | Laying additional pipeline and other allied works at Augmentation of Kachukhali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000282/2024-2025 | 2639/AD | 20/06/2024 | 315 | MS SINHA ROY & CO | 39.38 | 0 | 80
8423 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000385/2023-2024 | 1574/AD | 17/07/2023 | 30 | MAA SANTOSHI ENTERPRISE | 21.96 | 0 | 0
8424 | Alipore Division | Canning Sub-division | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KACHUKHALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000630/2023-2024 | 2434/AD | 22/08/2023 | 300 | UNITED BUILDERS | 588.5 | 0 | 70
8425 | Alipore Division | Canning Sub-division | Sinking of 200mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001190/2023-2024 | 3995/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 20.46 | 0 | 0
8426 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001237/2024-2025 | 5218/AD | 16/12/2024 | 30 | UNITED BUILDERS | 6.91 | 0 | 0
8427 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001238/2024-2025 | 5219/AD | 16/12/2024 | 40 | NITYANANDA MONDAL | 32.8 | 0 | 0
8428 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000063/2023-2024 | 541/AD | 25/01/2024 | 0 | Resource Division | 26.47 | 0 | 0
8429 | S24 Pgns Mechanical | Canning Sub-division | Quotation for new service( power) connection at Kachukhali PH- 1 Water supply scheme under Gosaba block. Reference ID:-106770520, Application No :-1008125133 | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | BILL/01845/2024-2025 | BP-2024-25-464 | 18/11/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
8430 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Kachukhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Gosaba] (SM/18267) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000048/2025-2026 | 1429/SMD | 21/05/2025 | 135 | DIPALI CONSTRUCTION | 10.34 | 0 | 0
8431 | Alipore Division | Diamond Harbour Sub-Division | Payment against "Restoration of Hatuganj Basuldanga Road (MDR) 0Km-12.2Km), under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Raidighi Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 264(W)/618G, Dt. 19.02.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | BILL/01577/2024-2025 | BP-2024-25-891 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 54.41 | 0 | 0
8432 | Alipore Division | Diamond Harbour Sub-Division | Erection of 20 nos scheme information display board at different headwork site of falta,Diamond Harbour I ,Diamond Harbour II and Kulpi Block under Diamond Harbour Sub Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000065/2025-2026 | 35/DHSD | 08/04/2025 | 7 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.75 | 0 | 100
8433 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of different dia. M.S. distribution line for crossing of 10 nos. culvert with allied works at Lakshmipur village road, at Netra stations to Panchagram road and Netra stations to Usthi road under Augmentation scheme of Diamond Harbour-I Zone-II and Zone-VIII within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000097/2025-2026 | 2526/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 93.95 | 0 | 100
8434 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Netra under Zone- II of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000130/2023-2024 | 1790/AD | 26/07/2023 | 30 | MAYA CONSTRUCTION | 25.02 | 0 | 0
8435 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- II at Netra of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC=6323] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000740/2023-2024 | 2908/AD | 20/09/2023 | 622 | TARUN ENTERPRISE | 1223.41 | 0 | 55
8436 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000231/2023-2024 | 2192/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
8437 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000666/2023-2024 | 419/AD | 22/01/2024 | 0 | Resource Division | 315.41 | 0 | 0
8438 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000891/2023-2024 | 745/AD | 03/02/2024 | 0 | Resource Division | 38.95 | 0 | 0
8439 | Alipore Division | Diamond Harbour Sub-Division | Construction of Chlorination Room at OHR Site of Jamalpur Water Supply Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000060/2022-2023 | 841/AD | 13/05/2022 | 30 | BANGA NIRMAN | 5.15 | 0 | 98
8440 | Alipore Division | Diamond Harbour Sub-Division | Construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing and specification including R.C.C. Bored Pile & Pile Cap upto pedestal at JAMALPUR Water Supply Scheme, Block - Budge-Budge-I under Diamond Harbour Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000069/2021-2022 | 834/AD | 18/06/2021 | 365 | M/S. S.S. ENTERPRISE | 63.1 | 0 | 5
8441 | Alipore Division | Diamond Harbour Sub-Division | Development and strengthening of earthen approach road from Jamalpur Health Centre to proposed OHR site of Jamalpur W/S Scheme and allied works in Budge Budge-I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000215/2022-2023 | 3002/AD | 11/07/2022 | 15 | M/S. S.S. ENTERPRISE | 10.89 | 0 | 95
8442 | S24 Pgns Mechanical |  | Charges for New service connection at Pump house no-2 of Hariharpur (Part-II) water supply scheme (Baruipur Block) |  |  | BILL/01802/2024-2025 | BP-2024-25-438 | 07/10/2024 | 0 | WBSEDCL | 3.75 | 0 | 0
8443 | S24 Pgns Mechanical |  | Charges for new service connection at Pump house no-3 of Hariharpur (Part-II) water supply scheme (Baruipur Block) |  |  | BILL/01803/2024-2025 | BP-2024-25-439 | 07/10/2024 | 0 | WBSEDCL | 14.09 | 0 | 0
8444 | S24 Pgns Mechanical |  | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04084/2023-2024 | BP-2023-24-415 | 16/12/2023 | 0 | WBSEDCL | 2.61 | 0 | 0
8445 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000166/2024-2025 | 2124/SMD | 12/07/2024 | 385 | KARUNAMOY ENGINEERING | 12.62 | 0 | 80
8446 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 3 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000171/2024-2025 | 2305/SMD | 22/07/2024 | 90 | P.P. CONCERN | 12.57 | 0 | 0
8447 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000222/2024-2025 | 2453/SMD | 01/08/2024 | 90 | SAIKAT ENTERPRISE | 12.62 | 0 | 0
8448 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2 for Hariharpur ( Part-II ) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] |  |  | ORD/000223/2024-2025 | 2454/SMD | 01/08/2024 | 90 | RMD TRADING | 12.76 | 0 | 0
8449 | South 24 Pgs W/S Division I |  | Construction of platfrom for FHTC, restoration of road, Protection of Pipeline and other allied works for "Ground Water Based Hariharpur(Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18869) |  |  | ORD/000522/2024-2025 | 4015/SWD-I | 13/09/2024 | 60 | MODERN CONSTRUCTION (MURSHIDABAD) | 79.26 | 0 | 0
8450 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of HARIHARPUR (PART-II) of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 1763] |  |  | ORD/000566/2023-2024 | 2639/SWD-I | 20/10/2023 | 523 | MODERN CONSTRUCTION (MURSHIDABAD) | 216.74 | 0 | 60
8451 | South 24 Pgs W/S Division I |  | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HARIHARPUR (Part-II) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18869] |  |  | ORD/000714/2023-2024 | 3430/SWD-I | 29/12/2023 | 45 | PADMA ENGINEERING CO. | 63.59 | 0 | 75
8452 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000747/2024-2025 | 4419/AD | 05/11/2024 | 30 | S.S. CONSTRUCTION | 29.61 | 0 | 0
8453 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000748/2024-2025 | 4420/AD | 05/11/2024 | 30 | MODERN CONSTRUCTION | 20.83 | 0 | 0
8454 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001711/2022-2023 | 11675/AD | 20/02/2023 | 720 | A 8 T CONSTRUCTION | 7.09 | 0 | 100
8455 | Alipore Division | Canning Sub-division | Construction of 600 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Goranbose piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/05716) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002095/2024-2025 | 351/AD | 28/01/2025 | 300 | MS SINHA ROY & CO | 181.43 | 0 | 0
8456 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000399/2023-2024 | 357/AD | 19/01/2024 | 0 | Resource Division | 3.82 | 0 | 0
8457 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Patibania W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000161/2024-2025 | 2512/AD | 15/06/2024 | 270 | DEV AND COMPANY | 40.82 | 0 | 50
8458 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000219/2024-2025 | 2602/AD | 19/06/2024 | 45 | M/S MALI ENTERPRISE | 28.95 | 0 | 0
8459 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000220/2024-2025 | 2603/AD | 19/06/2024 | 30 | KRISHNA CONSTRUCTION | 9.56 | 0 | 0
8460 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000226/2024-2025 | 2525/AD | 18/06/2024 | 30 | RIYANA ENTERPRISE | 9.66 | 0 | 0
8461 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000227/2024-2025 | 2557/AD | 18/06/2024 | 45 | M/S MALI ENTERPRISE | 5.62 | 0 | 0
8462 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Patibania W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. [Part-I] (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000340/2024-2025 | 2772/AD | 28/06/2024 | 60 | PROJECT INDIA | 99.02 | 0 | 0
8463 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000359/2023-2024 | 1558/AD | 17/07/2023 | 838 | SYN DEVELOPERS PVT. LTD. | 437.8 | 0 | 15
8464 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000510/2024-2025 | 4570/AD | 14/11/2024 | 30 | AZAD RAHAMAN LASKAR | 8.9 | 0 | 0
8465 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000566/2023-2024 | 1806/AD | 26/07/2023 | 30 | ABONTICA ENTERPRISE | 17.93 | 0 | 0
8466 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000572/2023-2024 | 1809/AD | 26/07/2023 | 45 | AQUATECH ENGINEER | 36.71 | 0 | 80
8467 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000578/2023-2024 | 2265/AD | 14/08/2023 | 45 | SUPRITI ENTERPRISE | 63.53 | 0 | 20
8468 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patabania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =950] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000716/2023-2024 | 2661/AD | 04/09/2023 | 120 | PROJECT INDIA | 161.87 | 0 | 40
8469 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
8470 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Patibania PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002625/2023-2024 | 882/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
8471 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000130/2023-2024 | 666/AD | 17/05/2023 | 0 | Resource Division | 15.23 | 0 | 0
8472 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000470/2023-2024 | 4777/AD | 19/12/2023 | 0 | Resource Division | 29.79 | 0 | 0
8473 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000841/2023-2024 | 634/AD | 30/01/2024 | 0 | Resource Division | 7.87 | 0 | 0
8474 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000976/2023-2024 | 1769/AD | 27/03/2024 | 0 | Resource Division | 28.97 | 0 | 0
8475 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Patibunia Zone-2 PH-2 W/S Scheme Application No:- 1007183453 Reference ID: 106222544 | Assistant Engineer, Kakdwip Sub Division |  | BILL/02230/2024-2025 | BP-2024-25-497 | 19/12/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
8476 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Patibunia Zone-2, PH-1W/S Scheme Application No:- 1007183440 Reference ID: 106222543 | Assistant Engineer, Kakdwip Sub Division |  | BILL/02233/2024-2025 | BP-2024-25-498 | 19/12/2024 | 0 | WBSEDCL | 8.05 | 0 | 0
8477 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Patibania water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000744/2023-2024 | 2633/SMD | 09/08/2023 | 90 | S.K. ENTERPRISE | 27.18 | 0 | 0
8478 | Alipore Division | Raidighi Sub-Division | Construction of 900 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- II of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000480/2023-2024 | 3670/AD | 01/11/2023 | 900 | M/S GHOSH & CO. | 1045.49 | 0 | 28
8479 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 900 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone-II, Mathurapur- II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001712/2023-2024 | 421/RSD | 02/01/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
8480 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000007/2024-2025 | 5162/AD | 12/12/2024 | 0 | Resource Division | 30.8 | 0 | 0
8481 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000246/2023-2024 | 3103/AD | 28/09/2023 | 0 | Resource Division | 43.57 | 0 | 0
8482 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000657/2023-2024 | 261/AD | 15/01/2024 | 0 | Resource Division | 8.95 | 0 | 0
8483 | Alipore Division |  | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Sridharnagar (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14986) |  |  | ORD/000362/2024-2025 | 2891/AD | 09/07/2024 | 90 | TANMAY ROY CHOWDHURY | 261.1 | 0 | 30
8484 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 3128/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
8485 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000777/2023-2024 | 611/AD | 29/01/2024 | 0 | Resource Division | 9.2 | 0 | 0
8486 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000376/2023-2024 | 3501/AD | 16/10/2023 | 60 | PIJUSH KANTI TRIPATHI | 77.26 | 0 | 20
8487 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. at Brojaballavpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-I) (SM/18718) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000435/2024-2025 | 3074/AD | 25/07/2024 | 546 | SHYAM DEVELOPER | 60.73 | 0 | 0
8488 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000552/2023-2024 | 2234/AD | 11/08/2023 | 45 | KANAN CONSTRUCTION | 49.16 | 0 | 90
8489 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000553/2023-2024 | 2235/AD | 11/08/2023 | 45 | KANAN CONSTRUCTION | 49.14 | 0 | 90
8490 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000564/2023-2024 | 2256/AD | 14/08/2023 | 1171 | M/S B.N.ENTERPRISE | 249.59 | 0 | 35
8491 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1145] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000565/2023-2024 | 2257/AD | 14/08/2023 | 748 | TANMAY ROY CHOWDHURY | 217.83 | 0 | 20
8492 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Brojaballavpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000640/2023-2024 | 2272/AD | 14/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 9.35 | 0 | 100
8493 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000790/2023-2024 | 3734/AD | 03/11/2023 | 901 | M/S B.N.ENTERPRISES | 266.67 | 0 | 41
8494 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
8495 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000110/2023-2024 | 646/AD | 17/05/2023 | 0 | Resource Division | 14.14 | 0 | 0
8496 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000486/2023-2024 | 4754/AD | 19/12/2023 | 0 | Resource Division | 43.79 | 0 | 0
8497 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000768/2023-2024 | 602/AD | 29/01/2024 | 0 | Resource Division | 2.54 | 0 | 0
8498 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 ( Zone-I & II) of Brojaballavpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000604/2023-2024 | 1023/SMD | 12/04/2023 | 90 | M.S.ENTERPRISE | 35.47 | 0 | 0
8499 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1000 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in Zone-II at Rajballabhpur of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in Zone-II at Rajballabhpur of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 6219 Nos.) | Assistant Engineer | JE1 | ORD/000418/2023-2024 | 1964/SWD-I | 24/08/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1097.7 | 0 | 30
8500 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000131/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 38.31 | 0 | 0
8501 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01721/2023-2024 | BP-2023-24-200 | 09/08/2023 | 0 | WBSEDCL | 4.73 | 0 | 0
8502 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/05121/2023-2024 | BP-2023-24-579 | 12/03/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
8503 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.3 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur)(SM/12237) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000279/2024-2025 | 644/SMSD | 29/05/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 100
8504 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-3 of of Majherhat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur)(SM/12237) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000280/2024-2025 | 676/SMSD | 04/06/2024 | 15 | WEST BENGAL ENGINEERING CO. | 0.29 | 0 | 100
8505 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Majherhar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Baruipur] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000473/2022-2023 | 3944/SMD | 30/12/2022 | 823 | WEST BENGAL ENGINEERING CO. | 38.89 | 0 | 100
8506 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Majherhat W/S Scheme under SMD, P.H.E. Dte.(Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002713/2023-2024 | 1406/SMMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.58 | 0 | 100
8507 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.1 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002714/2023-2024 | 1407/SMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 100
8508 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no.2 of Majherhat W/S Scheme under SMD, P.H.E. Dte. (Block-Baruipur) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/002715/2023-2024 | 1408/SMSD | 17/11/2023 | 15 | WEST BENGAL ENGINEERING CO. | 0.9 | 0 | 100
8509 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work of Laying distribution system for MAJHERHAT PWSS to accommodate FHTC in Baruipur Block under South 24 Pgns Water Supply Division-I, PHE. Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Paraganas District (TSM/012625) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000043/2023-2024 | 181/SWD-I | 18/04/2023 | 90 | K P CONSTRUCTION | 31.15 | 0 | 0
8510 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for MAJERHAT PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000115/2022-2023 | 1276/SWD-I | 13/09/2022 | 30 | M/S S R ENTERPRISE | 60.19 | 0 | 100
8511 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 03 (Three) nos. chlorination room at MAJERHAT of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012625] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000124/2022-2023 | 1292/SWD-I | 14/09/2022 | 961 | SWASTIK CONSTRUCTION | 16.4 | 0 | 100
8512 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MAJERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000169/2021-2022 | 1914/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 0 | 100
8513 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at MAJERHAT of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000202/2022-2023 | 1558/SWD-I | 13/10/2022 | 120 | K P CONSTRUCTION | 358.83 | 0 | 100
8514 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 03 (Three) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for MAJHERHAT PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012625] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000782/2023-2024 | 810/SWD-I | 16/02/2024 | 30 | M/S S.R ENTERPRISE | 6.6 | 0 | 100
8515 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000102/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 108.14 | 0 | 0
8516 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different households, fitting fixing supplying of different dia. specials for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000146/2024-2025 | 2484/AD | 14/06/2024 | 450 | M. MUKHERJEE | 73.02 | 0 | 0
8517 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000428/2024-2025 | 3258/AD | 06/08/2024 | 360 | M. MUKHERJEE | 150.27 | 0 | 0
8518 | Alipore Division | Kakdwip Sub-Division | Surging of 01 No. Tubewell for augmentation of Mahishamari (Zone - I & II) W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000529/2023-2024 | 353/KSD | 09/08/2023 | 25 | S.K.GOLUI | 2.18 | 0 | 100
8519 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mahishmari (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000969/2023-2024 | 307/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
8520 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mahishmari (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000973/2023-2024 | 322/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
8521 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MAHISMARI(ZONE- I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001060/2022-2023 | 4651/AD | 06/09/2022 | 45 | VOYAGER | 6.89 | 0 | 100
8522 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Mahishamari (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001277/2022-2023 | 9589/AD | 03/01/2023 | 698 | SARADA CONSTRUCTION | 49.18 | 0 | 50
8523 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Mahishamari (Zone-I) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001474/2023-2024 | 4684/AD | 18/12/2023 | 30 | M. MUKHERJEE | 39.65 | 0 | 100
8524 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Mahishamari (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 80] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001862/2022-2023 | 12415/AD | 09/03/2023 | 1050 | M. MUKHERJEE | 252.54 | 0 | 88
8525 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Mahishamari (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 80] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001863/2022-2023 | 12416/AD | 09/03/2023 | 1052 | M. MUKHERJEE | 234.69 | 0 | 70
8526 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Mahishamari (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001988/2023-2024 | 507/AD | 25/01/2024 | 45 | M/S SWAPAN KUMAR PRADHAN | 33.09 | 0 | 0
8527 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Mahishamari (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001989/2023-2024 | 508/AD | 25/01/2024 | 30 | ANANDA MAITY | 11.74 | 0 | 100
8528 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mahishamari Zone - I & II, Sumatinagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002153/2023-2024 | 948/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
8529 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000338/2023-2024 | 3153/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
8530 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000515/2023-2024 | 4833/AD | 20/12/2023 | 0 | Resource Division | 56.08 | 0 | 0
8531 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000529/2023-2024 | 11/AD | 02/01/2024 | 0 | Resource Division | 0.95 | 0 | 0
8532 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000686/2023-2024 | 456/AD | 24/01/2024 | 0 | Resource Division | 5.38 | 0 | 0
8533 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000972/2023-2024 | 1765/AD | 27/03/2024 | 0 | Resource Division | 8.34 | 0 | 0
8534 | S24 Pgns Mechanical | Kakdwip Sub-Division | Payment for New Service connection Mahishmari augmentation Zone-I PH-1 W/S Scheme Application No:- 1007503605 Reference ID:- 106454748 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/01133/2024-2025 | BP-2024-25-227 | 08/08/2024 | 0 | WBSEDCL | 6.3 | 0 | 0
8535 | S24 Pgns Mechanical | Kakdwip Sub-Division | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | BILL/05971/2023-2024 | BP-2023-24-646 | 30/03/2024 | 0 | WBSEDCL | 7.45 | 0 | 0
8536 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Mahishmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000348/2022-2023 | 3752/SMD | 29/12/2022 | 914 | JAGANNATH ENTERPRISE | 20.15 | 0 | 20
8537 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional / Alternation Work of Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2, Zone - I for Augmentation of Mahishmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000359/2024-2025 | 2657/SMD | 29/08/2024 | 90 | JAGANNATH ENTERPRISE | 17.43 | 0 | 0
8538 | S24 Pgns Mechanical | Kakdwip Sub-Division | Additional / Alternation Work of Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2, Zone - I for Augmentation of Mahishmari water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000702/2024-2025 | 1390/SMD | 15/04/2024 | 914 | JAGANNATH ENTERPRISE | 17.43 | 0 | 45
8539 | S24 Pgns Mechanical | Kakdwip Sub-Division | Improvement of outdoor illumination arrangement with allied works at Zone-II PH-2 of Mahismari W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13872) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002338/2024-2025 | 1425-AE-II-SMD | 04/12/2024 | 15 | JAGANNATH ENTERPRISE | 0.67 | 0 | 0
8540 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00385/2023-2024 | BP-2023-24-63 | 09/06/2023 | 0 | WBSEDCL | 14.73 | 0 | 0
8541 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone- I of Jhungri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000466/2022-2023 | 277/SMD | 01/02/2023 | 90 | DAS ENTERPRISE | 26.01 | 0 | 100
8542 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply & installation of LED board at PH-1&2 of Jhungri w/s scheme under South 24-Pgs Mechanical Division PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000867/2023-2024 | 1075/SMSD | 17/08/2023 | 15 | M/S. S.R. ENTERPRISE | 0.78 | 0 | 100
8543 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of outdoor illumination arrangement with allied works at Jhungri PH 1 w/s scheme under Bhangar-I under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001962/2023-2024 | 1O97/SMSD | 21/08/2023 | 15 | DAS ENTERPRISE | 0.88 | 0 | 100
8544 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of Outdoor illumination arrangement with allied works at Satberia PH-1 water supply scheme under Bhangar-I Block under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002572/2023-2024 | 1098/SMSD | 21/08/2023 | 15 | DAS ENTERPRISE | 0.88 | 0 | 100
8545 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Improvement of Outdoor illumination arrangement with allied works at Jhungri PH-2 water supply scheme under Bhangar-I Block under SMD, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/002971/2023-2024 | ..1098/SMSD | 21/08/2023 | 15 | DAS ENTERPRISE | 0.88 | 0 | 100
8546 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR JHUNGRI PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 26, KHATIAN NO. 743, JL. NO. 118, MOUZA - GHUMRI) & 2ND TUBE WELL SITE (DAG NO. 116/1166, KHATIAN NO. 743, JL NO. 118, MOUZA - GHUMRI), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 756/SWD-I | 29/06/2022 | 30 | SIMPLEX DRILLING CO. | 28.38 | 0 | 100
8547 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 400 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Jhungri Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000307/2022-2023 | 1911/SWD-I | 18/11/2022 | 1019 | STARCO CONSTRUCTION | 660.5 | 0 | 85
8548 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000562/2024-2025 | 4235/SWD-I | 30/09/2024 | 60 | TOJO ENTERPRISE | 36.45 | 0 | 0
8549 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd TW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000751/2024-2025 | 4673/SWD-I | 18/11/2024 | 45 | GANAPATI ENTERPRISE | 11.47 | 0 | 0
8550 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000019/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 16.4 | 0 | 0
8551 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000031/2022-2023 | 2690/SWD-I | 20/01/2023 | 0 | Resource Division | 14.98 | 0 | 0
8552 | S24 Pgns Mechanical | Baruipur Sub-Division | Payment of electricity bill for new service connection under SMD, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00624/2023-2024 | BP-2023-24-92 | 14/06/2023 | 0 | WBSEDCL | 6.73 | 0 | 0
8553 | S24 Pgns Mechanical | Baruipur Sub-Division | Quotation for new service connection at P.H. No. 2 of Dewanganj w/s scheme . Application no. 1008175066 . | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/02036/2024-2025 | BP-2024-25-488 | 09/12/2024 | 0 | WBSEDCL | 10.33 | 0 | 0
8554 | S24 Pgns Mechanical | Baruipur Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 and 2, of Dewanganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Jaynagar-I] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000732/2023-2024 | 2915/SMD | 31/08/2023 | 762 | JAGANNATH ENTERPRISE | 18.87 | 0 | 50
8555 | S24 Pgns Mechanical | Baruipur Sub-Division | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Dewanganj W/S Scheme under SMD, P.H.E. Dte. (Block-Jaynagar-I) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/002783/2023-2024 | 112/SMSD | 25/01/2024 | 493 | JAGANNATH ENTERPRISE | 0.5 | 0 | 70
8556 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for DEWANGANJ PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000076/2022-2023 | 1187/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 28.52 | 0 | 50
8557 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at DEWANGANJ Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1095) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000220/2022-2023 | 1629/SWD-I | 20/10/2022 | 1108 | SRIJON ENTERPRISE | 308.29 | 0 | 100
8558 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DEWANGANJ Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000225/2021-2022 | 1965/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.62 | 0 | 100
8559 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Dewanganj at Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000375/2022-2023 | 2209/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 100
8560 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of approach road in front of OHR site and construction of Boundary Walls at Tubewell site- 1 & 2 under Ground Water Based DEWANGANJ Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11499) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000666/2023-2024 | 3026/SWD-I | 30/11/2023 | 60 | SRIJON ENTERPRISE | 49.36 | 0 | 80
8561 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Dewanganj PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011007] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000733/2022-2023 | 3584/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 50
8562 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based DEWANGANJ Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11499) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000906/2023-2024 | 1205/SWD-I | 11/03/2024 | 360 | M/S THE BASU ENTERPRISE | 16.06 | 0 | 70
8563 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000079/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 46.39 | 0 | 0
8564 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 9 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000024/2025-2026 | 2010/AD | 28/04/2025 | 30 | SUBHASISH SAU | 12.97 | 0 | 0
8565 | Alipore Division | Canning Sub-division | Laying pipe line from C.W.R. - 2 to O.H.R. point of Augmentation of Ground Water Based at Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000092/2025-2026 | 2521/AD | 30/05/2025 | 45 | S.P. CONSTRUCTION (I) | 25.17 | 0 | 0
8566 | Alipore Division | Canning Sub-division | Construction of 02 (two) nos. 100 Cum. Clear Water Reservoir (CWR) at Gosaba (Zone-II) Water Supply Scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000299/2024-2025 | 2679AD | 24/06/2024 | 311 | SWASTIK CONSTRUCTION | 67.49 | 0 | 40
8567 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000507/2023-2024 | 2062/AD | 07/08/2023 | 544 | S.B. ENTERPRISE | 8.64 | 0 | 100
8568 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000508/2023-2024 | 2063/AD | 07/08/2023 | 45 | S.B. ENTERPRISE | 8.64 | 0 | 0
8569 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000509/2023-2024 | 2064/AD | 07/08/2023 | 45 | M/S. GANGA ENTERPRISE | 8.64 | 0 | 0
8570 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000510/2023-2024 | 2065/AD | 07/08/2023 | 45 | M/S. GANGA ENTERPRISE | 8.63 | 0 | 0
8571 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-V) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000511/2023-2024 | 2066/AD | 07/08/2023 | 360 | JYOTI ENTERPRISES | 8.64 | 0 | 100
8572 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-VI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000512/2023-2024 | 2067/AD | 07/08/2023 | 360 | JYOTI ENTERPRISES | 8.64 | 0 | 100
8573 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.VII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000513/2023-2024 | 2068/AD | 07/08/2023 | 513 | SUPER CONSTRUCTION | 8.59 | 0 | 100
8574 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No.VIII] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000514/2023-2024 | 2069/AD | 07/08/2023 | 45 | SUPER CONSTRUCTION | 8.59 | 0 | 0
8575 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IX) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000515/2023-2024 | 2070/AD | 07/08/2023 | 45 | A.M.ENTERPRISE (I) | 8.64 | 0 | 0
8576 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-X) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000516/2023-2024 | 2071/AD | 07/08/2023 | 452 | A.M.ENTERPRISE (I) | 8.64 | 0 | 100
8577 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000517/2023-2024 | 2072/AD | 07/08/2023 | 45 | B.S.ENTERPRISE | 8.62 | 0 | 100
8578 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.XII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000518/2023-2024 | 2073/AD | 07/08/2023 | 45 | RAJLAKSHMI ENTERPRISE | 8.64 | 0 | 0
8579 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000519/2023-2024 | 2074/AD | 07/08/2023 | 45 | KAMALA ENTERPRISE (I) | 8.64 | 0 | 0
8580 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 1, 2, 3) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000546/2023-2024 | 2078/AD | 07/08/2023 | 60 | DOLY CONSTRUCTION | 67.35 | 0 | 0
8581 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 4, 5, 6) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000547/2023-2024 | 2079/AD | 07/08/2023 | 937 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 90
8582 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 7, 8, 9) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000548/2023-2024 | 2080/AD | 07/08/2023 | 756 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 100
8583 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 10, 11, 12, 13) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000549/2023-2024 | 2081/AD | 07/08/2023 | 90 | SETABUR RAHAMAN | 89.78 | 0 | 0
8584 | Alipore Division | Canning Sub-division | Construction of OHR (250 Cum), Construction of OHR (600 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018435] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000563/2023-2024 | 2255/AD | 14/08/2023 | 745 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 2050.6 | 0 | 25
8585 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000615/2023-2024 | 2270/AD | 14/08/2023 | 45 | M/S R.DUTTA & CO. | 35.42 | 0 | 98
8586 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000676/2024-2025 | 4249/AD | 26/10/2024 | 30 | S.B. ENTERPRISE | 14.29 | 0 | 0
8587 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000677/2024-2025 | 4250/AD | 26/10/2024 | 30 | NEPAL CHANDRA PRADHAN | 11.97 | 0 | 0
8588 | Alipore Division | Canning Sub-division | Construction of boundary wall at CWR for Augmentation of Ground water Based at Gosaba (Zone- II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000742/2024-2025 | 4399/AD | 05/11/2024 | 45 | SWASTIK CONSTRUCTION | 37.17 | 0 | 0
8589 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 12 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000767/2024-2025 | 4468/AD | 11/11/2024 | 30 | A 8 T CONSTRUCTION | 13.68 | 0 | 0
8590 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 11 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000768/2024-2025 | 4469/AD | 11/11/2024 | 30 | BANGA NIRMAN | 13.35 | 0 | 0
8591 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 10 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000769/2024-2025 | 4470/AD | 11/11/2024 | 30 | BANGA NIRMAN | 13.35 | 0 | 0
8592 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 7 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000770/2024-2025 | 4471/AD | 11/11/2024 | 30 | SUBHO CONSTRUCTION | 14.16 | 0 | 0
8593 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000771/2024-2025 | 4472/AD | 11/11/2024 | 30 | CHATTERJEE ENTERPRISES | 13.85 | 0 | 0
8594 | Alipore Division | Canning Sub-division | Laying pipe line at the Augmentation of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001032/2024-2025 | 4942/AD | 03/12/2024 | 90 | SURYA ENTERPRISE | 27.22 | 0 | 100
8595 | Alipore Division | Canning Sub-division | Survey, Soil Investigation/Geo-technical survey, preparation of design and drawing, making service corridor for installation of 315 mm (Nominal OD) HDPE Pipe by HDD method under the river bed of Durga Doani River at Gosaba Island for Gosaba Zone -II WS Scheme. The works include transportation of machineries and mobilization, supply of 315 mm (Nominal OD) HDPE pipe (PE80, PN10) including laying / installation, pressure testing of laid pipe, hire charges of all machine and tools, expenses of consumables (Bentonite /Polymer, Diesel, hydraulic machine, water etc.) including transportation all type of man power, HDD operation cost, Electric / Lighting arrangement at site, insurance for staff, labour, materials and machine including GST @18%, cess @1% and riverine @22.50% and all other charges including site clearance. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001033/2023-2024 | 3188/AD | 03/10/2023 | 75 | ATINDRA CONSTRUCTION PRIVATE LIMITED | 449.89 | 0 | 100
8596 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 8 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001243/2024-2025 | 5241/AD | 17/12/2024 | 30 | ASHIS ENTERPRISE | 14.16 | 0 | 0
8597 | Alipore Division | Canning Sub-division | Hiring Motor launch for Canning Sub Division under Alipore Division,PHE Dte. in connection with execution and maintenance of different piped water supply schemes at different island in the district of South 24 Parganas. (for 365 days) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001336/2024-2025 | 5442/AD | 26/12/2024 | 365 | RAJKUMAR MANNA | 40.7 | 0 | 0
8598 | Alipore Division | Canning Sub-division | Laying DI pipe line and other allied works at Kalir Khal of Pond Based Surface Water Supply Scheme of Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001929/2023-2024 | 1173/CSD | 06/11/2023 | 10 | MOHANA ENTERPRISES | 0.97 | 0 | 100
8599 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000407/2023-2024 | 361/AD | 19/01/2024 | 0 | Resource Division | 60.32 | 0 | 0
8600 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000721/2023-2024 | 543/AD | 25/01/2024 | 0 | Resource Division | 1057.58 | 0 | 0
8601 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at 13 Nos Pump House of Gosaba Zone-II water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000807/2023-2024 | 2997/SMD | 14/09/2023 | 366 | M/S. S.S. ENTERPRISE | 172.29 | 0 | 0
8602 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 1 of Sonakhali (Zone-III) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000287/2025-2026 | 690/CSD | 26/05/2025 | 30 | ARANYA ENTERPRISE | 2.92 | 0 | 0
8603 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000314/2024-2025 | 2695/AD | 24/06/2024 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
8604 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000502/2023-2024 | 2060/AD | 07/08/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
8605 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000559/2023-2024 | 2246/AD | 11/08/2023 | 30 | SAMIR GIRI | 19.56 | 0 | 0
8606 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000606/2023-2024 | 2269/AD | 14/08/2023 | 45 | TECH VISION | 6.39 | 0 | 99
8607 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1981] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000632/2023-2024 | 2156/AD | 09/08/2023 | 90 | M/S SHIBAM ENTERPRISE | 450.06 | 0 | 65
8608 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001081/2023-2024 | 3540/AD | 17/10/2023 | 15 | ARBINA ENTERPRISE | 27.69 | 0 | 0
8609 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
8610 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000037/2023-2024 | 243/AD | 24/04/2023 | 0 | Resource Division | 82.44 | 0 | 0
8611 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000394/2023-2024 | 335/AD | 19/01/2024 | 0 | Resource Division | 12.2 | 0 | 0
8612 | S24 Pgns Mechanical | Canning Sub-division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-III for Augmentation of Sonakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001512/2022-2023 | 888/SMD | 24/03/2023 | 90 | MAA TARA ENTERPRISE | 10.41 | 0 | 0
8613 | S24 Pgns Mechanical |  | Quotation for new service (power) connection at Gobindapur PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663977, Application No- 1007921431 |  |  | BILL/01464/2024-2025 | BP-2024-25-345 | 09/09/2024 | 0 | WBSEDCL | 5.42 | 0 | 0
8614 | S24 Pgns Mechanical |  | Quotation for new service (power) connection at Gobindapur PH-2 , Water supply scheme under Bhangar-I Block. Reference ID-106663974, Application No- 1007921442 |  |  | BILL/01469/2024-2025 | BP-2024-25-346 | 09/09/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
8615 | S24 Pgns Mechanical |  | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Gobindapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] |  |  | ORD/000590/2023-2024 | 2648/SMD | 11/08/2023 | 600 | SRI KRISHNA NIRMAN | 25.68 | 0 | 70
8616 | S24 Pgns Mechanical |  | Improvement of outdoor Illumination arrangement with allied works at Gobindapur PH-2 under Bhangar-I Block W/S Scheme under SMD, P.H.E. Dte.(SM/18572) |  |  | ORD/001621/2024-2025 | 1541/SMSD | 21/11/2024 | 15 | SRI KRISHNA NIRMAN | 0.9 | 0 | 100
8617 | S24 Pgns Mechanical |  | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Gobindapur W/S Scheme under SMD, P.H.E. Dte.(Block-Bhangar-I) |  |  | ORD/002270/2024-2025 | 62/SMSD | 17/01/2025 | 15 | SRI KRISHNA NIRMAN | 0.59 | 0 | 100
8618 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.44] |  |  | BILL/00473/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 47.79 | 0 | 0
8619 | South 24 Pgs W/S Division I |  | Bhangor Kulti Canal from 0.00 kmp to 2.00kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 90mm to 280mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/18572) |  |  | BILL/00642/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 14.93 | 0 | 0
8620 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018472] (2nd Call) |  |  | ORD/000366/2023-2024 | 1775/SWD-I | 11/08/2023 | 30 | M/S SUNDARI CONSTRUCTION | 31.61 | 0 | 50
8621 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 22.96 | 0 | 0
8622 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 252/SWD-I | 10/01/2024 | 0 | Resource Division | 17.59 | 0 | 0
8623 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Uttar Chandanpiri W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000160/2024-2025 | 2511/AD | 15/06/2024 | 45 | DEV AND COMPANY | 40.82 | 0 | 0
8624 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000221/2024-2025 | 2604/AD | 19/06/2024 | 45 | MODERN CONSTRUCTION | 28.84 | 0 | 0
8625 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000228/2024-2025 | 2558/AD | 18/06/2024 | 30 | M/S R.K.ENTERPRISE | 9.66 | 0 | 0
8626 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000229/2024-2025 | 2559/AD | 18/06/2024 | 30 | PRADIP KUMAR MONDAL | 9.65 | 0 | 0
8627 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Uttar Chandanpiri PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000357/2024-2025 | 2841/AD | 05/07/2024 | 635 | SOMA CONSTRUCTION | 117.46 | 0 | 50
8628 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2024-2025 | 3462/AD | 23/08/2024 | 45 | M/S R.K.ENTERPRISE | 5.62 | 0 | 0
8629 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000468/2024-2025 | 3463/AD | 23/08/2024 | 45 | M/S. TARA MAA CONSTRUCTION | 5.6 | 0 | 0
8630 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000509/2024-2025 | 3609/AD | 06/09/2024 | 30 | KAMALA ENTERPRISE | 9.61 | 0 | 0
8631 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000568/2023-2024 | 2258/AD | 14/08/2023 | 60 | M/S ARPAN ENTERPRISE | 16.9 | 0 | 70
8632 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000569/2023-2024 | 2084/AD | 07/08/2023 | 30 | AROMA INC | 12.09 | 0 | 50
8633 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000571/2023-2024 | 2259/AD | 14/08/2023 | 45 | AQUATECH ENGINEERS | 36.71 | 0 | 50
8634 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000581/2023-2024 | 2268/AD | 14/08/2023 | 45 | NATURAL RESOURCES CONSORTIUM | 60.84 | 0 | 0
8635 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1577] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000633/2023-2024 | 2451/AD | 23/08/2023 | 952 | SOMA CONSTRUCTION | 486 | 0 | 60
8636 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
8637 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002618/2023-2024 | 895/KSD | 18/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
8638 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000474/2023-2024 | 4779/AD | 19/12/2023 | 0 | Resource Division | 16.05 | 0 | 0
8639 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000561/2023-2024 | 49/AD | 03/01/2024 | 0 | Resource Division | 13.23 | 0 | 0
8640 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000790/2023-2024 | 635/AD | 30/01/2024 | 0 | Resource Division | 0.5 | 0 | 0
8641 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000978/2023-2024 | 1771/AD | 27/03/2024 | 0 | Resource Division | 38.31 | 0 | 0
8642 | S24 Pgns Mechanical | Kakdwip Sub-Division | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 &2 of Uttar Chandanpiri water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001964/2023-2024 | 4870/SMD | 14/12/2023 | 91 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.2 | 0 | 0
8643 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Chandpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 229/SMD | 24/01/2023 | 90 | WEST BENGAL ENGINEERING CO. | 22.37 | 0 | 0
8644 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Chandpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2810] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 419/SWD-I | 02/05/2023 | 300 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 581.79 | 0 | 50
8645 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tubewell site (Dag No. 12, Khatian No. 359, JL No. 126, Mouza- Srirampur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/010665] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000458/2022-2023 | 2749/SWD-I | 27/01/2023 | 30 | ABUTALEB MONDAL | 28.51 | 0 | 0
8646 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of CHANDPUR PWSS within Bhangar-I Block CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/14419). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000556/2024-2025 | 4229/SWD-I | 30/09/2024 | 60 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 96.12 | 0 | 0