8647 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/10/2023 to 31/03/2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000663/2023-2024 | 2387/SWD-I | 27/09/2023 | 183 | AJAY KUMAR | 0.89 | 0 | 30
8648 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDPUR PWSS at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tube-well site (Dag No. 12 Khatian No. 359, JL No. 126, Mouza- Srirampur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010665] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000741/2022-2023 | 3569/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 0
8649 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site under Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [SM/14419] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000783/2023-2024 | 853/SWD-I | 19/02/2024 | 15 | M/S SABITA ENTERPRISE | 15.84 | 0 | 0
8650 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 3730/SWD-I | 31/03/2023 | 183 | AJAY KUMAR | 0.89 | 0 | 60
8651 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2024 to 30/09/2024] [Vehicle No- WB-09-1725] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000914/2023-2024 | 1496/SWD-I | 30/03/2024 | 183 | AJAY KUMAR | 0.89 | 0 | 0
8652 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of CHANDPUR PWSS within Bhangar-I Block "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14419) (2nd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001149/2024-2025 | 334/SWD-I | 29/01/2025 | 45 | MAHABUB RAHAMAN LASKAR | 11.37 | 0 | 0
8653 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000051/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 14.98 | 0 | 0
8654 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000219/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 17.31 | 0 | 0
8655 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new power(service) connection at Naora PH-2 Water Supply Scheme under Bhangar- I Block Reference ID-106663973, Application No- 1007921578. | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01465/2024-2025 | BP-2024-25-351 | 06/09/2024 | 0 | WBSEDCL | 17.9 | 0 | 0
8656 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Quotation for new service (power) connection at Nowra PH-1 , Water supply scheme under Bhangar-I Block. Reference ID-106663979, Application No- 1007921564 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/01467/2024-2025 | BP-2024-25-352 | 09/09/2024 | 0 | WBSEDCL | 4.91 | 0 | 0
8657 | S24 Pgns Mechanical | South 24 Pgs. W/S Division - I | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Naora water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Bhangar-I] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000440/2022-2023 | 230/SMD | 24/01/2023 | 1073 | B.T.PROJECTS PVT.LTD. | 23 | 0 | 30
8658 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.39] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00469/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0
8659 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.42] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00472/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 31.04 | 0 | 0
8660 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for NAORA piped water supply scheme at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152,160,161,166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 1443/SWD-I | 26/09/2022 | 30 | MUNNA AGROTECH ENTERPRISE | 28.51 | 0 | 100
8661 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2739] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000430/2023-2024 | 2004/SWD-I | 28/08/2023 | 300 | M/S SALIM CONSTRUCTION | 501.09 | 0 | 35
8662 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for NAORA PWSS at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152, 160, 161, 166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12017] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000488/2022-2023 | 2808/SWD-I | 02/02/2023 | 15 | MUNNA AGROTECH ENTERPRISE | 3.13 | 0 | 100
8663 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12017) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000558/2024-2025 | 4231/SWD-I | 30/09/2024 | 60 | M/S SALIM CONSTRUCTION | 93.92 | 0 | 0
8664 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 46.1 | 0 | 0
8665 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000248/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 16.87 | 0 | 0
8666 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Karimnagar under Zone- I of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000503/2023-2024 | 2061/AD | 07/08/2023 | 30 | ESSCON | 25.16 | 0 | 0
8667 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-I at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-6682] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000562/2023-2024 | 2254/AD | 14/08/2023 | 300 | DIVINE | 712.58 | 0 | 0
8668 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-I (Karimnagar, OHR Size-900 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002094/2022-2023 | 329/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 0
8669 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000203/2023-2024 | 2026/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
8670 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000367/2023-2024 | 3231/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
8671 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000670/2023-2024 | 423/AD | 22/01/2024 | 0 | Resource Division | 19.18 | 0 | 0
8672 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000863/2023-2024 | 770/AD | 03/02/2024 | 0 | Resource Division | 41.16 | 0 | 0
Total | [10 empty] | 591431.79 | 3141.65