## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC under JJM within Barasubarnanagar PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000031/2020-2021 | 2107/TD | 05/11/2020 | 180 | PRANAB KUMAR DAS | 96.08 | 31.17 | 100
2 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM Bara Subarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001254/2020-2021 | 992/W | 27/03/2021 | 0 | PRANAB KUMAR DAS | 56.48 | 0 | 0
3 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IXA Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000121/2020-2021 | 2630/TD | 05/01/2021 | 60 | RAJ KUMAR SINGHA | 96.85 | 193.4 | 100
4 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Purba Bakulda PWSS Block Panskura-I in the District of Purba Medinipur. |  |  | ORD/000033/2020-2021 | 2110/TD | 05/11/2020 | 180 | BIDHAN MONDAL | 72.9 | 0 | 100
5 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000145/2021-2022 | 70/W | 24/06/2021 | 0 | BIDHAN MONDAL | 20.84 | 0 | 0
6 | Tamluk Division |  | Re-laying of D.I./G.I./UPVC pipe line under Purba Bakulda W/S Scheme within Panskura Block damaged due to upgradation of moorum road under Tamluk Division, PHE Dte. |  |  | VCH/000214/2021-2022 | 100/W | 05/07/2021 | 0 | BIDHAN MONDAL | 12.56 | 0 | 0
7 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001041/2020-2021 | 724/W | 18/02/2021 | 0 | BIDHAN MONDAL | 33.98 | 0 | 0
8 | Tamluk Division |  | Charges of entry of Household data in J.J.M website alongwith Household Addhar Details entry in J.J.M. website under Tamluk Division, PHE Dte. |  |  | VCH/001053/2020-2021 | 816/W | 25/02/2021 | 0 | MISHRA ENTERPRISE | 4.85 | 0 | 0
9 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Srirampur PWSS (Part-I) Block -Tamluk in the District of Purba Medinipur. |  |  | ORD/000223/2020-2021 | 2835/TD | 05/02/2021 | 45 | ARABINDA GHOSH | 113.61 | 0 | 100
10 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000348/2021-2022 | BP-2021-22-117 | 05/10/2021 | 0 | ARABINDA GHOSH | 13.82 | 0 | 0
11 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001099/2020-2021 |  | 12/03/2021 | 0 | ARABINDA GHOSH | 100.73 | 0 | 0
12 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001264/2020-2021 | 1079/W | 30/03/2021 | 0 | ARABINDA GHOSH | 100.54 | 0 | 0
13 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Majna Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000166/2021-2022 | 1170/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.34 | 4.04 | 100
14 | Tamluk Division | Contai Sub-Division | Repair and Renovation of Pump House and others allied works for OHR & 2nd Tube well site at Majna Water Supply Scheme in Contai - Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000369/2024-2025 | 3398/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.92 | 0 | 100
15 | Tamluk Division | Contai Sub-Division | Augmentation of ground water based Majna Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir of Capacity 250 cum. And staging height 20.00 mtr. With allied work including Sub Soil Investigation within Contai-I Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000403/2021-2022 | 1845/TD | 15/02/2022 | 180 | DAS ENTERPRISE | 324.35 | 303.34 | 100
16 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site( Mouza- Nayabasan ,J.L. No-294, Plot No- 319), for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for West side & North Side) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000412/2022-2023 | 344/TD | 13/05/2022 | 28 | PARTHA CONSTRUCTION | 4.84 | 3.82 | 100
17 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Majna BPHC Premises for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side & South Side) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000415/2022-2023 | 373/TD | 17/05/2022 | 28 | BIBEKANANDA DAS | 3.85 | 3.5 | 100
18 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Majna Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000661/2021-2022 | 2216/TD | 22/03/2022 | 15 | BIBEKANANDA DAS | 4.06 | 4.06 | 100
19 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by UPVC pipes with allied works due to Construction of drain by Local Panchayet of Majna and its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000748/2023-2024 | 1714/CSD | 31/08/2023 | 30 | SUBRATA KUMAR BERA | 2.66 | 2.65 | 100
20 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Majna PWSS within Contai -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Laying rising main and other allied works Augmentation of Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000861/2022-2023 | 3217/TD | 14/03/2023 | 40 | SUBRATA KUMAR BERA | 19.54 | 0 | 0
21 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000002/2022-2023 | 82/TD | 08/04/2022 | 0 | Resource Division | 20.19 | 0 | 0
22 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000022/2021-2022 | 1264/TD | 13/12/2021 | 0 | Resource Division | 13.16 | 0 | 0
23 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000057/2021-2022 | 1902/TD | 23/02/2022 | 0 | Resource Division | 13.73 | 0 | 0
24 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000086/2021-2022 | 2217/TD | 24/03/2022 | 0 | Resource Division | 20.19 | 0 | 0
25 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Majna W/S Scheme (T/W-III) , Contai-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000106/2023-2024 | 855/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 14.61 | 0 | 0
26 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MAJNA Water Supply Scheme T/W-III, (Ref. ID-204068438) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01930/2023-2024 | BP-2023-24-235 | 08/09/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
27 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Supply Scheme for Majna, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001912/2022-2023 | 813/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.34 | 4.67 | 58
28 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 150 nos] under JJM in Dariapur PWSS [Pratappur(507,part),Haripur(508,part),Ramchak Gopalchak(509,part),Purba Bamunia(511,part), Dariapur(512,part),Daulatpur(513,part),Kazichak(514,part),Chhota Subarnanagar(515,part),Nankar Gopinathpur(516,part),Durgapur Part-IV(608,part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000268/2020-2021 | 2921/TD | 22/02/2021 | 20 | SK. NUR ISLAM | 10.94 | 0 | 100
29 | Tamluk Division |  | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000366/2021-2022 |  | 30/09/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0
30 | Tamluk Division |  | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000422/2021-2022 | BP-2021-22-98 | 05/10/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0
31 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block- Egra-I in the District of Purba Medinipur.(Phase-II). | Assistant Engineer | Junior Engineer | ORD/000033/2021-2022 | 239/TD | 23/06/2021 | 60 | FIROZ KHAN | 172.05 | 214.65 | 100
32 | Tamluk Division | Digha Sub-Division | Laying distribution system of Chirulia-Chatla & its adjoining moujas Water Supply Scheme within Egra-I Dev. Block under Digha sub-division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000261/2021-2022 | 1453/TD | 31/12/2021 | 30 | AJIT KUMAR SOM | 29.22 | 29.22 | 100
33 | Tamluk Division |  | Retrofitting to accomodate FHTC (250 nos.) under JJM in Kanakpur PWSS under Potashpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PHASE-II) |  |  | ORD/000006/2021-2022 | 684/TD | 10/09/2021 | 20 | SRIMANTA KUMAR MAITY | 22.38 | 21.15 | 100
34 | Tamluk Division |  | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Kanakpur Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000356/2024-2025 | 3319/TD | 22/10/2024 | 30 | THE GODFATHER TRADING COMPANY | 1.45 | 0 | 0
35 | Tamluk Division |  | Retrofitting to accomodate FHTC (899 nos.) under JJM in Dona Zone-II PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | ORD/000014/2021-2022 | 690/TD | 10/09/2021 | 30 | TARUN KOLEY | 41.48 | 0 | 100
36 | Tamluk Division |  | Retrofitting to accomodate FHTC (899 Nos.) under JJM in Dona Zone - II PWSS (Balance Work) Block-Moyna under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000353/2021-2022 | BP-2021-22-106 | 05/10/2021 | 0 | TARUN KOLEY | 41.31 | 0 | 0
37 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Amtalia PWSS Block- Contai-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000018/2021-2022 | 85/TD | 11/05/2021 | 30 | ARABINDA GHOSH | 90.23 | 65.29 | 80
38 | Tamluk Division |  | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline within Nodal point 160-161, 196-197, 196-199, 161-172 & 172-174 in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-A) |  |  | ORD/000125/2021-2022 | 1005/TD | 02/11/2021 | 30 | PULAK KUMAR SAMANTA | 11.81 | 11.81 | 100
39 | Tamluk Division |  | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-B) |  |  | ORD/000126/2021-2022 | 1006/TD | 02/11/2021 | 30 | ZENITH CONSTRUCTION | 28.92 | 28.84 | 100
40 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in KUDI PWSS Block - Egra-I in the District of Purba Medinipur |  |  | ORD/000139/2021-2022 | 1022/TD | 02/11/2021 | 20 | KESHOB ENTERPRISE | 12.26 | 12.22 | 100
41 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Dwariberia Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000034/2022-2023 | 133/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
42 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (456 FHTC) of Dwariberia Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000110/2024-2025 | 1904/TD | 07/06/2024 | 367 | SK. NUR ISLAM | 56.28 | 5.91 | 50
43 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Dwariberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000253/2022-2023 | 1045/TD | 16/08/2022 | 45 | TARUN KHATUA | 4.09 | 3.82 | 100
44 | Tamluk Division | Haldia Sub-Division | Work Order for Laying of UPVC pipe line at Dwariberia Water supply Scheme (Node point 182-182A) within Haldia Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000262/2022-2023 | 571/HSD | 17/08/2022 | 15 | TAPAN BERA | 1.57 | 1.57 | 100
45 | Tamluk Division | Haldia Sub-Division | Work order for Make approach road to access Rig Machine for Boring of Tube well at Head work site of Dwariberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000263/2022-2023 | 572/HSD | 17/08/2022 | 7 | TAPAN BERA | 1.36 | 1.36 | 100
46 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dwariberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000390/2021-2022 | 1606/TD | 14/01/2022 | 20 | RADIANT | 3.58 | 3.56 | 100
47 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (1003 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000392/2021-2022 | 1851/TD | 16/02/2022 | 40 | SUDIPTA ROY | 75.32 | 73.42 | 100
48 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (927 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000393/2021-2022 | 1852/TD | 16/02/2022 | 40 | PALCON | 74.59 | 69.74 | 100
49 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (737 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000394/2021-2022 | 1853/TD | 16/02/2022 | 40 | JAI BHARAT COMMERCIAL CORPORATION | 74.58 | 74.45 | 100
50 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000395/2021-2022 | 1854/TD | 16/02/2022 | 20 | BUNBA CONSTRUCTION | 10.38 | 10.26 | 100
51 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. " (Part-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000396/2021-2022 | 1855/TD | 16/02/2022 | 20 | TAPAN BERA | 10.79 | 10.79 | 100
52 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000397/2021-2022 | 1860/TD | 17/02/2022 | 20 | SAYAN MAITY | 4.85 | 4.82 | 100
53 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000398/2021-2022 | 1861/TD | 17/02/2022 | 20 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.8 | 4.8 | 100
54 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000399/2021-2022 | 1862/TD | 17/02/2022 | 20 | MAHAPRABHU ENTERPRISE | 4.83 | 4.63 | 100
55 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000400/2021-2022 | 1863/TD | 17/02/2022 | 20 | MODERN CONSTRUCTION | 4.85 | 4.81 | 100
56 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000401/2021-2022 | 1864/TD | 17/02/2022 | 20 | TARUN KHATUA | 4.85 | 4.84 | 100
57 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Dwariberia & its adjoining moujas Water Supply Scheme within Haldia Block including supply of all labour & materials under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000482/2022-2023 | 1887/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 131.54 | 96.5 | 98
58 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (101 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000526/2021-2022 | 2000/TD | 08/03/2022 | 20 | A. K. SIKDAR | 35.52 | 35.15 | 100
59 | Tamluk Division | Haldia Sub-Division | Boundary wall including land development at Headwork site of Dwariberia Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000644/2023-2024 | 2596/TD | 10/10/2023 | 506 | ELITE CONSTRUCTION | 18.69 | 7.13 | 1
60 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000063/2021-2022 | 1874/TD | 18/02/2022 | 0 | Resource Division | 16 | 0 | 0
61 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000082/2021-2022 | 2069/TD | 16/03/2022 | 0 | Resource Division | 16.85 | 0 | 0
62 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000127/2024-2025 | 804/TD | 18/03/2025 | 0 | Resource Division | 2.81 | 0 | 0
63 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dwariberia water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001140/2022-2023 | 2121/W/MMD | 28/11/2022 | 120 | PRANAB KUMAR DAS | 11.12 | 9.38 | 100
64 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-B) |  | Junior Engineer | ORD/000005/2022-2023 | 59/TD | 05/04/2022 | 60 | UCON | 164.31 | 161.84 | 100
65 | Tamluk Division | RWS Tamluk Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Muradpur Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000187/2021-2022 | 1196/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 6.38 | 6.38 | 100
66 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-A) |  | Junior Engineer | ORD/000423/2022-2023 | 1597/TD | 18/10/2022 | 30 | G. S. CONSTRUCTION | 25.21 | 24.82 | 100
67 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-B) |  | Junior Engineer | ORD/000424/2022-2023 | 1598/TD | 18/10/2022 | 25 | TARUN KHATUA | 10.28 | 10.16 | 100
68 | Tamluk Division | RWS Tamluk Sub-Division | Pilling with Bamboo & bullah, retaining of OHR & laying leftout portion for Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Dist. Purba Medinipur. |  | Junior Engineer | ORD/000453/2023-2024 | 1471/TD | 13/07/2023 | 40 | G. S. CONSTRUCTION | 34.18 | 0 | 50
69 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-A) |  | Junior Engineer | ORD/000631/2021-2022 | 2214/TD | 22/03/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 237.6 | 236 | 100
70 | Tamluk Division | RWS Tamluk Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000046/2021-2022 | 2346/TD | 31/03/2022 | 0 | Resource Division | 10.33 | 0 | 0
71 | Tamluk Division | RWS Tamluk Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000196/2023-2024 | 1096/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
72 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Chandibhetti Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000115/2022-2023 | 593/TD | 17/06/2022 | 60 | RAJ KUMAR SINGHA | 585.56 | 564.09 | 95
73 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Chandibhetti Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000127/2022-2023 | 627/TD | 23/06/2022 | 15 | SRIMANTA KUMAR MAITY | 4.59 | 4.59 | 100
74 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur,Basudevberia,Chandivety & Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II).(Supply at Mukutshila Store). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000171/2022-2023 | 775/TD | 08/07/2022 | 15 | SRIMANTA KUMAR MAITY | 3.49 | 3.49 | 100
75 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Chandibhetti Water Supply Scheme (Mouza - Banamaliberya, JL No. - 458, Plot No. - 8) within Contai-II (Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000237/2022-2023 | 978/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.38 | 100
76 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chandiveti Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2021-2022 | 1608/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.99 | 4.29 | 100
77 | Tamluk Division | Haldia Electrical Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2, Head Work site Boundary Wall and Boundary Wall of 2nd Tubewell Site under JJM with allied work of Chandivetty PWSS within Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000344/2024-2025 | 3329/TD | 22/10/2024 | 40 | SUBHENDU HAZRA | 18.38 | 0 | 0
78 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Rising Main including interconnection of Chandibhetty PWSS in Deshapran Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000360/2023-2024 | 928/TD | 01/06/2023 | 30 | SUDIP MANNA | 6.09 | 3.05 | 100
79 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (Boundary Wall(as per Departmental Design & Drawing) at 3rd TW Site for Augmentation of Chandibhetty PWSS in Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Length 65.00 mtr.) For Low Land. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000471/2023-2024 | 1497/TD | 17/07/2023 | 60 | SUBHENDU HAZRA | 10.3 | 8.31 | 100
80 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Chandibhetti W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000725/2023-2024 | 2970/TD | 28/11/2023 | 60 | BISWA NIRMAN ENTERPRISE. | 3.73 | 3.72 | 100
81 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000017/2022-2023 | 405/TD | 25/05/2022 | 0 | Resource Division | 42.06 | 0 | 0
82 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000080/2022-2023 | 1268/TD | 12/09/2022 | 0 | Resource Division | 23.08 | 0 | 0
83 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for Chandiveti PWSS Tube Well- III in connection Mukundapur CCC (2004186280) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00163/2022-2023 | BP-2022-23-131 | 14/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
84 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chandibhetti, Block Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001906/2022-2023 | 807/W/MMD | 24/03/2023 | 720 | SUJOY RANJAN BHOWMICK | 13.58 | 9.65 | 100
85 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000132/2022-2023 | 693/TD | 27/06/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 736.14 | 725.08 | 98
86 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tubewell of Augmentation of Junbani Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000209/2023-2024 | 473/TD | 10/05/2023 | 60 | SUBHENDU HAZRA | 3.68 | 3.32 | 100
87 | Tamluk Division | Contai Sub-Division | Continuation W/O for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2024 to 30/06/2025. (12 Months), Vehicle no.-WB-31/6974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000215/2024-2025 | 1788/CSD | 28/06/2024 | 365 | SABITA PRADHAN | 1.49 | 0 | 0
88 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Junbani Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000221/2022-2023 | 493/CSD | 02/08/2022 | 15 | GIRI CONSTRUCTION | 2.47 | 2.47 | 100
89 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional (3rd) Tubewell of Augmentation of Junbani Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000238/2022-2023 | 979/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.12 | 100
90 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Junbani Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000313/2021-2022 | 1547/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.58 | 4.76 | 100
91 | Tamluk Division | Contai Sub-Division | Repairing of 1st, 2nd, 3rd Pump House, under JJM with allied work for Augmentation of Junbani PWSS in Contai-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 3472/TD | 06/11/2024 | 60 | BISWA NIRMAN ENTERPRISE. | 4.35 | 0 | 98
92 | Tamluk Division | Contai Sub-Division | Repairing of R.C.C. Elevated Reservoir of capacity with allied works of Junbani PWSS within Contai - I Block including supply of all labour & materials under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000447/2024-2025 | 3614/TD | 27/11/2024 | 40 | CHARUBALA ENTERPRISE | 11.14 | 0 | 97
93 | Tamluk Division | Contai Sub-Division | Left Out pipeline, Piling and Road Restoration work for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000638/2024-2025 | 850/TD | 19/03/2025 | 30 | BASANTA KUMAR MAITY | 41.02 | 0 | 0
94 | Tamluk Division | Contai Sub-Division | Boundary wall and Rising Main and under JJM with allied work for Jubani PWSS within Contai-I Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000753/2023-2024 | 3224/TD | 13/12/2023 | 40 | MAHAPRABHU ENTERPRISE | 35.37 | 5.22 | 16
95 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000010/2022-2023 | 102/TD | 11/04/2022 | 0 | Resource Division | 51.5 | 0 | 0
96 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000083/2022-2023 | 1270/TD | 12/09/2022 | 0 | Resource Division | 32.32 | 0 | 0
97 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Junboni PWSS Tube Well-IV WS Scheme (Ref. ID-203911303) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00318/2022-2023 | BP-2022-23-137 | 20/03/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
98 | Midnapore Mechanical | Contai Sub-Division | Solar quotation for JUNBONI PWSS P.H-I under MMD PHE Dte PICHABONI CCC, WBSEDCL Consumer Id- 200433206 Application No- 2004857954 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02462/2025-2026 |  | 02/09/2025 | 0 | WBSEDCL | 0.24 | 0 | 0
99 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill for T/W NO-IV Of JUNBONI W/S Scheme under MMD, PHE, Dte. Block- Contai-I, PICHABANI C.C.C. Ref. Memo No- 2004620649/QUOT/03 DT. 27-02-2024 Application NO- 2004620649 Reference Id- 204229267 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04304/2023-2024 | BP-2023-24-798 | 07/03/2024 | 0 | WBSEDCL | 6.88 | 0 | 0
100 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000202/2023-2024 | 1482/W/MMD | 21/06/2023 | 467 | MAA KALI ENTERPRISE | 11.4 | 9.96 | 25
101 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money of Pump House No. ¿ III of Khejuri Zone-I PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01305/2023-2024 | BP-2023-24-583 | 22/11/2023 | 0 | WBSEDCL | 2.88 | 0 | 0
102 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 0 | 99
103 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 159.66 | 95
104 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 15.76 | 100
105 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-S) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000469/2023-2024 | 1450/TD | 13/07/2023 | 30 | DEBABRATA DAS | 9.42 | 6.64 | 70
106 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Khejuri Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000480/2024-2025 | 3769/TD | 10/12/2024 | 40 | GIRI CONSTRUCTION | 3.96 | 0 | 0
107 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Barka saria Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000854/2023-2024 | 67/TD | 05/01/2024 | 7 | AMITAVA MONDAL | 0.96 | 0.95 | 100
108 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Khejuri Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000855/2023-2024 | 68/TD | 05/01/2024 | 7 | TECHNO ENTERPRISE. | 0.96 | 0.95 | 100
109 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-O) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000893/2023-2024 | 247/TD | 11/01/2024 | 20 | GITA ENTERPRISE | 9.75 | 6.62 | 90
110 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line and Rising main, construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000539/2023-2024 | 1838/TD | 08/08/2023 | 40 | SK. SARFARAJ | 16.93 | 13.3 | 100
111 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (1557 Nos)with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000744/2022-2023 | 2551/TD | 24/01/2023 | 920 | TARUN KOLEY | 289.69 | 203.04 | 70
112 | Tamluk Division | Haldia Electrical Sub-Division | Repairing of existing Store Room with Guard Room with sanitary & water supply arrangements including Plinth Protection of OHR Site under Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000767/2022-2023 | 2770/TD | 09/02/2023 | 30 | GIRI CONSTRUCTION | 9.94 | 9.82 | 100
113 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-L) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000891/2023-2024 | 246/TD | 11/01/2024 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.96 | 42.14 | 100
114 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000897/2023-2024 | 244/TD | 11/01/2024 | 348 | ROY BISWAS CONSTRUCTION | 37.4 | 34.37 | 100
115 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 12.63 | 95
116 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
117 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 61.6 | 94
118 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 539.28 | 70
119 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 2898/TD | 21/11/2023 | 0 | Resource Division | 4.92 | 0 | 0
120 | Tamluk Division | Haldia Electrical Sub-Division | Quotation money payment to WBSEDCL for Simulia Water Supply Scheme of Tube Well No. - III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00537/2023-2024 | BP-2023-24-283 | 17/08/2023 | 0 | WBSEDCL | 4.34 | 0 | 0
121 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Simulia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000165/2021-2022 | 1169/TD | 01/12/2021 | 7 | RADIANT | 9.35 | 9.24 | 100
122 | Tamluk Division | Haldia Electrical Sub-Division | Pump House & Boundary Wall for Augmentation of Simulia Water Supply Scheme under Tamluk Development Block withen Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000470/2023-2024 | 1451/TD | 13/07/2023 | 413 | SK. SAHALAM | 12.36 | 10.04 | 40
123 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000499/2022-2023 | 1971/TD | 01/12/2022 | 1276 | SANKHA ENTERPRISE | 707.13 | 463.32 | 65
124 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Boundary wall , Pump Hose at Head Work site of Simulia Water Supply Scheme underTamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Length 402 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000625/2024-2025 | 737/TD | 07/03/2025 | 45 | M J A ENTERPRISE | 44.35 | 0 | 0
125 | Tamluk Division | Haldia Electrical Sub-Division | Laying of proposed Rising main line and supply & delivery of DI Specials M.S Structure for Canal crossing, Road crossing and Drum Sheet Piling at Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000710/2023-2024 | 2871/TD | 17/11/2023 | 25 | SANKHA ENTERPRISE | 58.27 | 0 | 0
126 | Tamluk Division | Haldia Electrical Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.10.2023 to 31.12.2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000824/2023-2024 | 1341/TSD | 27/09/2023 | 50 | DEBNATH MAITY | 0.24 | 1.18 | 100
127 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000020/2022-2023 | 408/TD | 25/05/2022 | 0 | Resource Division | 42.01 | 0 | 0
128 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000082/2022-2023 | 1262/TD | 12/09/2022 | 0 | Resource Division | 7.78 | 0 | 0
129 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000219/2023-2024 | 1118/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
130 | Central Drilling | Haldia Electrical Sub-Division | RESISTIVITY SURVEY AND OTHER WORKS OF SIMULIA W/S SCH (TW-III), TAMLUK BLOCK, PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000402/2022-2023 | 1539/CDD | 08/12/2022 | 30 | PADMA ENGINEERING & CO. | 12.67 | 10.25 | 0
131 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SIMULIA W/S SCH (TW-III), TAMLUK BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000403/2022-2023 | 416/CMSD-I | 10/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 0
132 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001965/2022-2023 | 864/W/MMD | 27/03/2023 | 180 | SWAPAN ENTERPRISE | 13.66 | 12.85 | 35
133 | Tamluk Division | Haldia Sub-Division | Continuation Work Order for Operation and Maintenance of distribution system including rising main, FHTC, OHR of Manoharpur & its adjoining mouzas Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. {For 12 Months} [i.e. 01/09/2024 to 31/08/2025] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000325/2024-2025 | 2786/TD | 30/08/2024 | 365 | G. S. CONSTRUCTION | 4.53 | 0 | 100
134 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Monoharpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000436/2021-2022 | 1512/TD | 06/01/2022 | 20 | RADIANT | 3.55 | 3.45 | 100
135 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Pump House No. "1" & Pump House No.- "2" at Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000652/2023-2024 | 2617/TD | 11/10/2023 | 470 | ANIRBAN BHOWMIK | 6.15 | 3.18 | 50
136 | Tamluk Division | Haldia Sub-Division | Laying of distribution pipe line to accommodate FHTC(2729 Nos) with new construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000777/2022-2023 | 2861/TD | 17/02/2023 | 865 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.9 | 410.36 | 85
137 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line with inter connection at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000981/2023-2024 | 395/TD | 30/01/2024 | 274 | G. S. CONSTRUCTION | 9.36 | 5 | 50
138 | Tamluk Division | Haldia Sub-Division | Surging of Deep Tube well at different W/S Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001164/2023-2024 | 739/HSD, | 19/02/2024 | 15 | BUNBA CONSTRUCTION | 2.3 | 2.3 | 100
139 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall, Protection work ,Earth Filling, Laying of left-out & Parallal Distribution line at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001208/2023-2024 | 966/TD | 12/03/2024 | 693 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 112.45 | 85.97 | 10
140 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000024/2022-2023 | 412/TD | 25/05/2022 | 0 | Resource Division | 47.71 | 0 | 0
141 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000072/2022-2023 | 1266/TD | 12/09/2022 | 0 | Resource Division | 16.78 | 0 | 0
142 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2023-2024 | 1224/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 24.79 | 0 | 0
143 | Tamluk Division | Digha Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Narandiha W/S Scheme within Ramnagar -II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-146 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000194/2023-2024 | 395/TD | 27/04/2023 | 40 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.72 | 0 | 100
144 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Narandiha Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000325/2021-2022 | 1618/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.06 | 3.05 | 100
145 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house - II at 2nd tube well site of Narandiha W/S Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000530/2024-2025 | 1315/DSD | 13/01/2025 | 7 | PURNENDU MAITY | 0.94 | 0 | 100
146 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of NARANDIA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000554/2022-2023 | 2182/TD | 20/12/2022 | 180 | MAITY CONSTRUCTION | 299.31 | 120.84 | 42
147 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of Pump House for Augmentation of NARANDIHA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000555/2022-2023 | 2181/TD | 20/12/2022 | 60 | MAITY CONSTRUCTION | 112.72 | 88.63 | 80
148 | Tamluk Division | Digha Sub-Division | Soil Investigation work in Connection of Construction of R.C.C. Over Head Reservoir (Capacity - 400 Cum) due to change of land with Laying of Balance Distribution Pipe Line for Provided balance FHTC and other allied works of Narandiha Piped Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000639/2024-2025 | 851/TD | 19/03/2025 | 30 | MAITY CONSTRUCTION | 48.33 | 0 | 0
149 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000280/2022-2023 | 2619/TD | 02/02/2023 | 0 | Resource Division | 41.76 | 0 | 0
150 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000285/2022-2023 | 2638/TD | 02/02/2023 | 0 | Resource Division | 19.64 | 0 | 0
151 | Central Drilling | Digha Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 220 mtrs. Depth) by utilising Departmental machineries for Narandiha W/S Scheme (TW-III), Ramnagar-II block under Purba Midnapore District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000011/2023-2024 | 14/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 17.39 | 13.88 | 100
152 | Central Drilling | Digha Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 220 Mtrs. Depth) by utilising Departmental Machineries for Narandiha W/S Scheme (T/W-I) , Ramangar-II Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000182/2023-2024 | 13/CDD | 04/04/2023 | 574 | MENAKA ENTERPRISE | 17.39 | 16.28 | 100
153 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for NARANDIHA Water Supply Scheme T/W-III, (Ref. ID-204068440) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01931/2023-2024 | BP-2023-24-236 | 08/09/2023 | 0 | WBSEDCL | 3.76 | 0 | 0
154 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NARANDIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005010859/QUOT/03 DT. 17-12-2024 Application NO- 2005010859 Application type-New connection Consumer Id- 204475187 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03866/2024-2025 | C012539028066 | 21/01/2025 | 0 | WBSEDCL | 3.71 | 0 | 0
155 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001978/2022-2023 | 817/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 22.74 | 40
156 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Shwnia PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000472/2024-2025 | 3761/TD | 10/12/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
157 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 145.8 | 51
158 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000020/2025-2026 | 2078/TD | 12/08/2025 | 0 | Resource Division | 4.52 | 0 | 0
159 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000129/2022-2023 | 2413/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0
160 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-I of Shwina W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746256 Consumer ID.-204316922 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01138/2024-2025 | BP-2024-25-253 | 06/06/2024 | 0 | WBSEDCL | 3.74 | 0 | 0
161 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SHWNIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2005013627/QUOT/03/2472 DT. 18-12-2024 Application NO- 2005013627 Application type-New connection Consumer Id- 204476587 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03863/2024-2025 | C012539030169 | 21/01/2025 | 0 | WBSEDCL | 4.28 | 0 | 0
162 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHWNIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001598/2022-2023 | 502/W/MMD | 20/03/2023 | 864 | SRI KRISHNA NIRMAN | 21.57 | 0 | 53
163 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Boundary Wall, Soil investigation & Accommodate FHTC (1623 nos) including 2 years of Operation Maintenance under JJM with allied work for Chauddha Chuli & its adjoining moujas PWSS in Khajuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000851/2023-2024 | 74/TD | 05/01/2024 | 720 | SRIMANTA KUMAR MAITY | 501.66 | 90.39 | 40
164 | Tamluk Division | Contai Sub-Division | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Khejuri-I, Khejuri-II, Patashpur-I & Patashpur-II ) | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001291/2023-2024 | 563/CSD | 14/03/2024 | 10 | SAURAV HAZRA | 0.54 | 0.27 | 100
165 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000333/2022-2023 | 2982/TD | 27/02/2023 | 0 | Resource Division | 32.13 | 0 | 0
166 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAUDDHA CHULI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001629/2022-2023 | 513/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 17.58 | 50
167 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000243/2023-2024 | 511/TD | 11/05/2023 | 30 | MANAS KUMAR SAHA | 93.6 | 57.08 | 30
168 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (300 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2023-2024 | 583/TD | 16/05/2023 | 634 | RAJ KUMAR SINGHA | 172.52 | 34.27 | 22
169 | Tamluk Division | Haldia Sub-Division | Land development at HW site, boundary wall at HW site & 2nd TW site of ground water based Erekhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000511/2024-2025 | 3945/TD | 23/12/2024 | 518 | CHANDA AGENCIES | 14.78 | 0 | 45
170 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site & 2nd TW site ,Canal crossing & Approach Road of ground water based Erekhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000735/2023-2024 | 2987/TD | 29/11/2023 | 484 | A. R. CONSTRUCTION | 18 | 11.6 | 70
171 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000811/2022-2023 | 3080/TD | 28/02/2023 | 648 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.86 | 8.05 | 100
172 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000812/2022-2023 | 3081/TD | 28/02/2023 | 20 | HYDROTECH ASSOCIATES | 10.01 | 8.28 | 85
173 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (470nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000900/2022-2023 | 3349/TD | 22/03/2023 | 824 | SUNNY ELECTRIC CO | 72.51 | 49.13 | 52
174 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (483nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000901/2022-2023 | 3350/TD | 22/03/2023 | 630 | DILIP KUMAR GHOSH | 73.45 | 51.32 | 70
175 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000164/2022-2023 | 2472/TD | 16/01/2023 | 0 | Resource Division | 18.44 | 0 | 0
176 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000189/2023-2024 | 638/W | 20/02/2024 | 0 | Resource Division | 10.55 | 0 | 0
177 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Erekhali W/S Scheme (T/W-I & II) , Sutahata Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000121/2023-2024 | 1388/CDD | 19/09/2023 | 269 | MENAKA ENTERPRISE | 31.41 | 29.24 | 100
178 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Eriakhali w/s scheme,Block-Sutahata under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695183 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-8500W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00649/2024-2025 | BP-2024-25-108 | 06/05/2024 | 0 | WBSEDCL | 6.26 | 0 | 0
179 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-II Of Erekhali w/s scheme, Block-Sutahata in the Dist. of purba medinipur under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004923436 Application Type-New Connection Reference ID-204414482 Quotation Date-01/10/2024 Quotation Due Date-01/10/2025 Contract Demand-8344W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02676/2024-2025 | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 6.17 | 0 | 0
180 | Midnapore Mechanical | Haldia Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
181 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for EREKHALI and ADJOINING MOUJAS, Block Sutahata, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001325/2022-2023 | 2327/W/MMD | 29/12/2022 | 976 | M/S. SAJAHAN CHOWDHURY | 23.69 | 15.21 | 60
182 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000016/2022-2023 | 50/TD | 05/04/2022 | 20 | RADIANT | 5.44 | 5.36 | 100
183 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.47 | 75
184 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 507.95 | 65
185 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000093/2022-2023 | 1375/TD | 23/09/2022 | 0 | Resource Division | 52.31 | 0 | 0
186 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000235/2022-2023 | 2617/TD | 02/02/2023 | 0 | Resource Division | 139.61 | 0 | 0
187 | Midnapore Mechanical | Haldia Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of JUNE"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/11470 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/06213/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.14 | 0 | 0
188 | Midnapore Mechanical | Haldia Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
189 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001472/2022-2023 | 210/W/MMD | 10/02/2023 | 180 | M/S S.G. ENTERPRISE | 27.26 | 0 | 0
190 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2095 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SARBERYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000227/2023-2024 | 453/TD | 04/05/2023 | 847 | TARUN KOLEY | 640.74 | 375.92 | 40
191 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000171/2023-2024 | 111/TD | 05/01/2024 | 0 | Resource Division | 12.91 | 0 | 0
192 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000174/2023-2024 | 289/TD | 17/01/2024 | 0 | Resource Division | 11.04 | 0 | 0
193 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000250/2022-2023 | 2719/TD | 06/02/2023 | 0 | Resource Division | 16.76 | 0 | 0
194 | Central Drilling | Contai Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Sar Berya W/S Scheme(TW-IV), Bhagawanpur-I block under Purba medinipur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 55/CDD | 06/04/2023 | 30 | ASHUTOSH DAS & CO | 13.27 | 11.68 | 100
195 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 300Mtrs. Depth ) by utilising Departmental machineries for Sarberya W/S Scheme (TW-I) Block Bhagwanpur, under Purba Midnapur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 549/CDD | 02/06/2023 | 30 | CHANDA ENTERPRISE | 21.55 | 6.4 | 100
196 | Central Drilling | Contai Sub-Division | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000061/2023-2024 | 854/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 31.45 | 12.17 | 100
197 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Sar Berya W/S Scheme (T/W-III) , Bhagawanpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000142/2023-2024 | 56/CDD | 06/04/2023 | 390 | ASHUTOSH DAS & CO | 13.27 | 10.78 | 100
198 | Central Drilling | Contai Sub-Division | PROVIDING DRIILING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 200 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SARBERYA W/S SCHEME (TW-I), UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2022-2023 | 1726/CDD | 29/12/2022 | 30 | MENAKA ENTERPRISE | 11.86 | 5.71 | 100
199 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SARBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818488/QUOT/03 DT. 12-07-2024 Application NO- 2004818488 Application type-New connection Consumer Id- 204355506 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01888/2024-2025 | BP-2024-25-553 | 08/08/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
200 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERYA Water Supply Scheme T/W-I, (Ref. ID-204090827) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02894/2023-2024 | BP-2023-24-315 | 01/11/2023 | 0 | WBSEDCL | 3.24 | 0 | 0
201 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERIYA Water Supply Scheme T/W-I, (Ref. ID-204147803) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03135/2023-2024 | BP-2023-24-411 | 09/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0
202 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERIYA Water Supply Scheme T/W-II, (Ref. ID-204147802) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03136/2023-2024 | BP-2023-24-410 | 09/12/2023 | 0 | WBSEDCL | 3.12 | 0 | 0
203 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SARBERYA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001361/2022-2023 | 2372/W/MMD | 31/12/2022 | 974 | DIPALI CONSTRUCTION | 23.68 | 13.17 | 85
204 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000043/2025-2026 | 432/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
205 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000044/2025-2026 | 433/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.94 | 0 | 100
206 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000045/2025-2026 | 434/HSD, | 23/04/2025 | 10 | BHOWMIK ENTERPRISE | 0.97 | 0 | 100
207 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000046/2025-2026 | 435/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.96 | 0 | 100
208 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000047/2025-2026 | 436/HSD, | 23/04/2025 | 10 | M/S RAJ CONSTRUCTION | 0.92 | 0 | 100
209 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000048/2025-2026 | 437/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.96 | 0 | 100
210 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000049/2025-2026 | 438/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.95 | 0 | 100
211 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000050/2025-2026 | 439/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.59 | 0 | 100
212 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd Tube well site of Chaitanyapur (Zone-II) Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-48mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000231/2024-2025 | 2534/TD | 07/08/2024 | 21 | M/S SOURAV MAHAPATRA | 4.51 | 3.87 | 100
213 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000327/2023-2024 | 625/TD | 17/05/2023 | 30 | SOUVIK GHOSAL | 4.16 | 3.73 | 100
214 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2022-2023 | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 58.29 | 100
215 | Tamluk Division | Haldia Sub-Division | Laying Left Out Distribution System for Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part Work Order I of II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000361/2024-2025 | 3814/TD | 13/12/2024 | 385 | DEBASIS SAMADDAR | 58.86 | 0 | 70
216 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000460/2021-2022 | 1725/TD | 01/02/2022 | 20 | RADIANT | 4.02 | 3.64 | 100
217 | Tamluk Division | Haldia Sub-Division | Laying Rising main work & construction of Approach Road of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000645/2023-2024 | 2591/TD | 10/10/2023 | 20 | A. R. CONSTRUCTION | 24.5 | 17.72 | 70
218 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rd Tube Well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000849/2022-2023 | 3169/TD | 10/03/2023 | 60 | MAITY TRADING | 4.6 | 4.49 | 85
219 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (4374 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000902/2022-2023 | 3458/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 625.57 | 267.79 | 32
220 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000052/2022-2023 | 1203/TD | 06/09/2022 | 0 | Resource Division | 49.51 | 0 | 0
221 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000061/2022-2023 | 1202/TD | 06/09/2022 | 0 | Resource Division | 26.9 | 0 | 0
222 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-III, Zone-II, (Ref. ID-204076090) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02203/2023-2024 | BP-2023-24-242 | 12/09/2023 | 0 | WBSEDCL | 9.52 | 0 | 0
223 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-I, Zone-II, (Ref. ID-204076083) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02204/2023-2024 | BP-2023-24-241 | 12/09/2023 | 0 | WBSEDCL | 3.63 | 0 | 0
224 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2024 to 31/12/2024. (12 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000992/2023-2024 | 623/HSD, | 28/12/2023 | 366 | SANTANU PATTANAYAK | 1.5 | 4.67 | 20
225 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District Block ¿Sutahata, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001718/2022-2023 | 631/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 37.88 | 36.99 | 60
226 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(764 nos), Laying Rising Main under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000141/2023-2024 | 282/TD | 20/04/2023 | 951 | NARAYAN MANDAL | 92.86 | 61.98 | 65
227 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(700 nos),Construction of switch room cum cholorine room(2nd T/W site) , Construction of Boundary Wall (2nd t/w site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000288/2023-2024 | 581/TD | 16/05/2023 | 892 | NARAYAN MANDAL | 139.9 | 99.14 | 76
228 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & Construction of RCC over Head Reservoir of capacity 300 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), under JJM with allied work for Harshankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000295/2023-2024 | 584/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.97 | 26.5 | 2
229 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(500 nos),Construction of switch room cum cholorine room(H/W site) , Construction of Boundary Wall (H/W site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000298/2023-2024 | 590/TD | 17/05/2023 | 803 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 88.84 | 52.65 | 30
230 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 150 mm DI (K9) Rising main and 200 mm DI (K7) pipes ( Nodal 379-382 ) of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Canal Length- = 20.00 mtr. ,Number of crossing -2 nos | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000300/2024-2025 | 3059/TD | 19/09/2024 | 400 | NARAYAN MANDAL | 8.28 | 0 | 0
231 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of 90 mm OD HDPE pipe line at Harasankar village ( Booth no -72 ) as per revised drawing of Harasankar PWSS under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000593/2024-2025 | 565/TD | 17/02/2025 | 60 | MMS CONSTRUCTIONS PVT. LTD. | 29.77 | 0 | 100
232 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 110 mm OD uPVC pipe of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001197/2023-2024 | 825/TD | 05/03/2024 | 20 | NARAYAN MANDAL | 4.21 | 3.02 | 10
233 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC construction of switch room cum chlorine room (2nd T/W site), construction of Boundary wall (2nd T/W site), under JJM with allied work for Harasankar PWSS within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001206/2023-2024 | 887/TD | 06/03/2024 | 35 | NARAYAN MANDAL | 4.09 | 4.09 | 100
234 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000301/2022-2023 | 3005/TD | 27/02/2023 | 0 | Resource Division | 16.42 | 0 | 0
235 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Harashankar W/S Scheme, Tamluk Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000521/2022-2023 | 2114/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 15.45 | 100
236 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Harasankar W/S scheme H/W site Application No.-2004562746 Ref.-204191037 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03465/2023-2024 | BP-2023-24-588 | 02/02/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
237 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001705/2022-2023 | 626/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 23.7 | 11.01 | 35
238 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 127.31 | 51
239 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000035/2024-2025 | 1631/TD | 18/06/2025 | 0 | Resource Division | 5.37 | 0 | 0
240 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000186/2022-2023 | 2445/TD | 16/01/2023 | 0 | Resource Division | 55.25 | 0 | 0
241 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743736/QUOT/03 DT. 20-05-2024 Application NO- 2004743736 Application type-New connection Consumer Id- 204312608 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01203/2024-2025 | BP-2024-25-320 | 24/06/2024 | 0 | WBSEDCL | 6.24 | 0 | 0
242 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004924431/QUOT/03 DT. 01-10-2024 MEMO NO: AMR/NS/436 DT. 01-10-2024 Application NO- 2004924431 Application type-New connection Consumer Id- 204415334 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03273/2024-2025 | C122406880068 | 06/12/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
243 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PAHARPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001400/2022-2023 | 2411/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 45
244 | Tamluk Division | Contai Sub-Division | Sinking of Tube well, Pump House , OHR (Intze type with pile foundation), Rising main, Head work site pipe connection, Laying distribution pipe line,Rigid Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2953 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dakshin Kalamdan, Katari, and its adjoing Mouzas- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000430/2023-2024 | 1417/TD | 12/07/2023 | 992 | TAPAS SANTRA | 1109.38 | 553.91 | 75
245 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000087/2024-2025 | 2955/TD | 12/09/2024 | 0 | Resource Division | 13.47 | 0 | 0
246 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000334/2022-2023 | 2981/TD | 27/02/2023 | 0 | Resource Division | 22.62 | 0 | 0
247 | Central Drilling | Contai Sub-Division | Providing Drilling Crew and other allied works for construction of Tube Well (250mm x 150mm x280 Mtrs. Depth) by utilising Departmental machineries for Dakshin Kalamdan and Sarberya (T/W-I & II) under Purba Medinipur District, CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000061/2023-2024 | 854/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 31.45 | 13.69 | 100
248 | Midnapore Mechanical | Contai Sub-Division | Dakshin Kalamadan W/S scheme Application No.-2004527976 Ref.-204160990 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03265/2023-2024 | BP-2023-24-515 | 09/01/2024 | 0 | WBSEDCL | 13.12 | 0 | 0
249 | Midnapore Mechanical | Contai Sub-Division | Quotation for Dakhin Kalamdan w/s scheme PH II under MMD PHE Dte in the district of Purba Medinipur. (Ref 204221089 App No. 2004606720) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04146/2023-2024 | BP-2023-24-757 | 01/03/2024 | 0 | WBSEDCL | 2.81 | 0 | 0
250 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005096379/QUOT/03 DT. 19-02-2025 Application NO- 2005096379 Application type-New connection Consumer Id- 204535464 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04462/2024-2025 | C032580117860 | 26/03/2025 | 0 | WBSEDCL | 0.14 | 0 | 0
251 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALAMDAN and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001416/2022-2023 | 2427/W/MMD | 31/12/2022 | 543 | DEY ENTERPRISE | 23.7 | 22.1 | 48
252 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1806 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KHAGA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000326/2023-2024 | 698/TD | 23/05/2023 | 801 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 581.3 | 242.94 | 40
253 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-J-1 To J-2) of pipe line and its allied works for KHAGA water supply scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (As per Revised LDS Drawing) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001245/2023-2024 | 1080/TD | 16/03/2024 | 487 | S.S. ENTERPRISE | 23.86 | 17.47 | 80
254 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000153/2023-2024 | 89/TD | 05/01/2024 | 0 | Resource Division | 11.12 | 0 | 0
255 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000245/2022-2023 | 2722/TD | 06/02/2023 | 0 | Resource Division | 37.4 | 0 | 0
256 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686929/QUOT/03 DT. 19-04-2024 Application NO- 2004686929 Application type-New connection Consumer Id- 204277584 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00707/2024-2025 | BP-2024-25-140 | 09/05/2024 | 0 | WBSEDCL | 2.87 | 0 | 0
257 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004739171/QUOT/03 DT. 16-05-2024 Application NO- 2004739171 Application type-New connection Consumer Id- 204309281 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01135/2024-2025 | BP-2024-25-244 | 06/06/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
258 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001584/2022-2023 | 467/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 85
259 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (163 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000128/2023-2024 | 259/TD | 19/04/2023 | 30 | BADAL CHANDRA GOLE | 41.58 | 31.33 | 77
260 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Rajendrachak PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2024-2025 | 2071/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
261 | Tamluk Division | Digha Sub-Division | Land Development at Head Works site of Rajendrachak W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000280/2024-2025 | 3471/TD | 06/11/2024 | 7 | LAXMEE ENTERPRISE | 4.6 | 0 | 100
262 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 500 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.. (PART- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000281/2023-2024 | 553/TD | 12/05/2023 | 889 | SK. NUR ISLAM | 114.81 | 81.88 | 80
263 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 997 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000345/2023-2024 | 849/TD | 31/05/2023 | 784 | JAGANNATH MAKAR | 256.07 | 178.54 | 85
264 | Tamluk Division | Digha Sub-Division | Soil investigation, 250 cum OHR (Intze type with pile foundation) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000631/2023-2024 | 2439/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 104.2 | 0 | 0
265 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000028/2025-2026 | 2087/TD | 12/08/2025 | 0 | Resource Division | 10.23 | 0 | 0
266 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000322/2022-2023 | 2975/TD | 27/02/2023 | 0 | Resource Division | 18.5 | 0 | 0
267 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.31 | 11
268 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732464/QUOT/03/212 DT. 13-05-2024 Application NO- 2004732464 Application type-New connection Consumer Id- 204305461 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01132/2024-2025 | BP-2024-25-248 | 06/06/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
269 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004940316/QUOT/03/770 DT. 25-10-2024 Application NO- 2004940316 Application type-New connection Consumer Id- 204428743 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03021/2024-2025 | C112429700471 | 25/11/2024 | 0 | WBSEDCL | 6.29 | 0 | 0
270 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAJENDRA CHAK and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001407/2022-2023 | 2418/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.73 | 0 | 0
271 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 110.17 | 51
272 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000054/2024-2025 | 1665/TD | 29/04/2024 | 0 | Resource Division | 7.01 | 0 | 0
273 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000152/2022-2023 | 2458/TD | 16/01/2023 | 0 | Resource Division | 40.42 | 0 | 0
274 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657850/QUOT/03/1514 DT. 28-03-2024 Application NO- 2004657850 Application type-New connection Consumer Id- 204257679 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00259/2024-2025 | BP-2024-25-31 | 15/04/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
275 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889798/QUOT/03 DT. 12-09-2024 Application NO- 2004889798 Application type-New connection Consumer Id- 204393534 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02499/2024-2025 | C092445096068 | 30/09/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
276 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TUPCHIBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001581/2022-2023 | 464/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 0 | 80
277 | Tamluk Division | Tamluk Sadar Sub-Division | Work Order for Land development at Head Work Site of Mirikpur Water Supply Scheme within Tamluk Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000181/2024-2025 | 2252/TD | 15/07/2024 | 98 | GHOSH ENTERPRISE | 4.07 | 0 | 100
278 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000211/2023-2024 | 433/TD | 03/05/2023 | 1000 | ARABINDA GHOSH | 1233.42 | 0 | 65
279 | Tamluk Division | Tamluk Sadar Sub-Division | Canal crossing for laying HDPE pipes of Mirikpur PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Nodal Point J-512 to J-517 ) Canal Length- =30.00 mtr. Number of crossing -1 nos | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000582/2024-2025 | 459/TD | 04/02/2025 | 25 | GHOSH ENTERPRISE | 6.25 | 0 | 0
280 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000221/2022-2023 | 2678/TD | 06/02/2023 | 0 | Resource Division | 38.97 | 0 | 0
281 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Mirikpur W/S scheme H/W site Tw-I Application.-2004547150 Ref.-204177955 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03299/2023-2024 | BP-2023-24-545 | 15/01/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
282 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Mirikpur W/S scheme H/W site Tw-II Application.-2004547153 Ref.-204177965 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03300/2023-2024 | BP-2023-24-546 | 15/01/2024 | 0 | WBSEDCL | 4.21 | 0 | 0
283 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRIKPUR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001750/2022-2023 | 644/W/MMD | 20/03/2023 | 749 | SOUMEN ELECTRIC | 27.17 | 23.4 | 80
284 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Anantapur Zone-I PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00611/2022-2023 | BP-2022-23-819 | 24/03/2023 | 0 | WBSEDCL | 2.38 | 0 | 0
285 | Tamluk Division | Haldia Electrical Sub-Division | Construction of new boundary wall around OHR and Repair and Renovation of Existing boundary wall , Pump house and chlorine room at Head work site and 2nd tube well site of Anantapur Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000386/2024-2025 | 3449/TD | 30/10/2024 | 40 | M J A ENTERPRISE | 9.09 | 0 | 0
286 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000397/2023-2024 | 1081/TD | 08/06/2023 | 45 | SK. SAHALAM | 5.1 | 4.79 | 100
287 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000461/2021-2022 | 1739/TD | 03/02/2022 | 20 | RADIANT | 3.86 | 3.83 | 100
288 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC(6217 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000480/2022-2023 | 1889/TD | 24/11/2022 | 859 | TARUN KOLEY | 622.31 | 336.89 | 90
289 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 400 mm dia. Additional length distribution pipe line with supply of DI specials under Anantapur Zone- I PWSS with in Tamluk Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000582/2023-2024 | 2203/TD | 01/09/2023 | 20 | TARUN KOLEY | 10.96 | 9.95 | 100
290 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 200 /250/300mm dia DI (K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of boundary wall & approach 3rd tube well site under Anantapur Zone- I PWSS with in Tamluk Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000584/2023-2024 | 2204/TD | 01/09/2023 | 368 | TARUN KOLEY | 13.81 | 9.91 | 95
291 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000031/2023-2024 | 1923/TD | 14/08/2023 | 0 | Resource Division | 33.23 | 0 | 0
292 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000047/2022-2023 | 1017/TD | 08/08/2022 | 0 | Resource Division | 67.14 | 0 | 0
293 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000056/2022-2023 | 1208/TD | 06/09/2022 | 0 | Resource Division | 38.23 | 0 | 0
294 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000224/2023-2024 | 1123/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
295 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR ANANTAPUR W/S SCH (ZONE-I) (TW-III), TAMLUK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000396/2022-2023 | 2120/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 17.75 | 16.09 | 0
296 | Midnapore Mechanical | Haldia Electrical Sub-Division | Additional quatation for Tulia Anantapur Zone-I, TW-III , Tamluk Block Application ID.-100000099975 Reference ID.-860292305 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03782/2023-2024 | BP-2023-24-716 | 20/02/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
297 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001722/2022-2023 | 633/W/MMD | 20/03/2023 | 180 | DEBJYOTI BASU | 40.78 | 25.63 | 50
298 | Tamluk Division | Contai Sub-Division | Payment to WBSEDCL for Shifting of LTOH Line at Siulipur for Ilashpur PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00810/2024-2025 | BP-2024-25-382 | 29/08/2024 | 0 | WBSEDCL | 0.81 | 0 | 0
299 | Tamluk Division | Contai Sub-Division | Laying Distribution System (NP-2-27,27-38,38-45,45-47,47-53,53-57,57-61,61-63,63-65,65-67 & 67-71) of pipe line and its allied works for Ilashpur Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000140/2024-2025 | 1923/TD | 07/06/2024 | 25 | MMS CONSTRUCTIONS PVT. LTD. | 12.61 | 12.14 | 90
300 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2038 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of ILASHPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000217/2023-2024 | 448/TD | 04/05/2023 | 942 | TAPAS SANTRA | 657.13 | 356.42 | 58
301 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000142/2023-2024 | 88/TD | 05/01/2024 | 0 | Resource Division | 12.55 | 0 | 0
302 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000196/2022-2023 | 2385/TD | 16/01/2023 | 0 | Resource Division | 20.13 | 0 | 0
303 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for ILASHPUR Water Supply Scheme T/W-I, (Ref. ID-204086226) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02895/2023-2024 | BP-2023-24-314 | 01/11/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
304 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ILASHPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2005011980/QUOT/03 DT. 18-12-2024 Application NO- 2005011980 Application type-New connection CONSUMER ID: 204475791 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03864/2024-2025 | C012539026306 | 21/01/2025 | 0 | WBSEDCL | 3.58 | 0 | 0
305 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ILASHPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001357/2022-2023 | 2368/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.18 | 50
306 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (1841 nos.) under JJM in Chandibenia Zone- II PWSS Block - Moyna in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000391/2022-2023 | 1424/TD | 26/09/2022 | 25 | HARIPADA PATTANAYAK | 69.06 | 69.04 | 100
307 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000201/2023-2024 | 1101/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
308 | Tamluk Division | Tamluk Sadar Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00709/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.38 | 0 | 0
309 | Tamluk Division | Tamluk Sadar Sub-Division | Bill for damage of Moyna Bridge approach road at 1.90 Km. Due to laying of water pipe line for Moyna Zone-II PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00992/2024-2025 | BP-2024-25-496 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.41 | 0 | 0
310 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Retaining Wall cun Guard wall and Approach Road beside pond at 3rd Tube well for Augmentation of Moyna Zone-II PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Divisionin the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2024-2025 | 2678/TD | 22/08/2024 | 25 | GHOSH ENTERPRISE | 6.98 | 0 | 0
311 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (3870 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-II Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000443/2022-2023 | 1651/TD | 02/11/2022 | 1080 | ARABINDA GHOSH | 571.76 | 481.85 | 80
312 | Tamluk Division | Tamluk Sadar Sub-Division | Pump House , Boundary Wall, Rising Main, Dramsheet Pilling for Augmentation of Moyna Zone-II Water Supply Scheme under Moyna Development Block within Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000465/2023-2024 | 1445/TD | 13/07/2023 | 820 | GHOSH ENTERPRISE | 89.23 | 36.26 | 81
313 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000860/2021-2022 | 1469/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.37 | 3.98 | 100
314 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000051/2022-2023 | 1206/TD | 06/09/2022 | 0 | Resource Division | 109.03 | 0 | 0
315 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000059/2022-2023 | 1204/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0
316 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-IV) Moyna Block under Purba Medinipur District CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000037/2023-2024 | 540/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.14 | 100
317 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-III) Moyna Block under Purba Medinipur District CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000038/2023-2024 | 539/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 15.47 | 100
318 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Moyna W/S Scheme (Z-II,T/W-V ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000129/2023-2024 | 541/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 15.8 | 100
319 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-I,Zone-II, (Ref. ID-204143547) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03133/2023-2024 | BP-2023-24-409 | 09/12/2023 | 0 | WBSEDCL | 5.37 | 0 | 0
320 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Moyna W/S scheme T/W-III, Z-II Ref.-204143545 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03164/2023-2024 | BP-2023-24-436 | 18/12/2023 | 0 | WBSEDCL | 2.74 | 0 | 0
321 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Moyna W/S scheme PH.-II, Zone-II Application No.-2004557342 Ref.-204187844 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03367/2023-2024 | BP-2023-24-577 | 18/01/2024 | 0 | WBSEDCL | 8.84 | 0 | 0
322 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Moyna (Zone-II) PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001715/2022-2023 | 630/W/MMD | 20/03/2023 | 530 | ALPHA ENTERPRISE | 37.86 | 35.46 | 70
323 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1155 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Silampur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000488/2023-2024 | 1565/TD | 19/07/2023 | 720 | ORIENT CONSTRUCTION | 431.66 | 224.96 | 60
324 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000032/2025-2026 | 2095/TD | 12/08/2025 | 0 | Resource Division | 7.11 | 0 | 0
325 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000256/2022-2023 | 2711/TD | 06/02/2023 | 0 | Resource Division | 42.6 | 0 | 0
326 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672028/QUOT/03/45 DT. 05-04-2024 Application NO- 2004672028 Application type-New connection Consumer Id- 204266730 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00503/2024-2025 | BP-2024-25-94 | 24/04/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
327 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672007/QUOT/03/46 DT. 05-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204266731 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00511/2024-2025 | BP-2024-25-93 | 24/04/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
328 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SILAMPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001579/2022-2023 | 462/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 20.72 | 80
329 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 153.74 | 20
330 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000027/2024-2025 | 1636/TD | 18/06/2025 | 0 | Resource Division | 8.09 | 0 | 0
331 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000324/2022-2023 | 2992/TD | 27/02/2023 | 0 | Resource Division | 26.09 | 0 | 0
332 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743815/QUOT/03 DT. 20-05-2024 Application NO- 2004743815 Application type-New connection Consumer Id- 204312604 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01205/2024-2025 | BP-2024-25-321 | 24/06/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
333 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607668/QUOT/03 DT. 21-02-2024 Application NO- 2004607668 Application type-New connection Consumer Id- 204222374 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04387/2023-2024 | BP-2023-24-825 | 13/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
334 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DHANKAR and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001634/2022-2023 | 515/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 10.38 | 51
335 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
336 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 51
337 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000092/2024-2025 | 2957/TD | 12/09/2024 | 0 | Resource Division | 10.46 | 0 | 0
338 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000121/2022-2023 | 2401/TD | 16/01/2023 | 0 | Resource Division | 41.93 | 0 | 0
339 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DURMUT AND ADJOINING MOUJAS PWSS, Block Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001913/2022-2023 | 815/W/MMD | 24/03/2023 | 180 | TAPAN KUMAR DEY | 22.78 | 9.45 | 35
340 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 371.25 | 75
341 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gokulnagar PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000871/2023-2024 | 193/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
342 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000007/2024-2025 | 1565/TD | 23/04/2024 | 0 | Resource Division | 14.91 | 0 | 0
343 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000179/2022-2023 | 2425/TD | 16/01/2023 | 0 | Resource Division | 6.8 | 0 | 0
344 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gokulnagar w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631965, Ref ID 204238451) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04745/2023-2024 | BP-2023-24-909 | 28/03/2024 | 0 | WBSEDCL | 7.06 | 0 | 0
345 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gokulnagar w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No 2004635309, Ref ID 204240956) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04747/2023-2024 | BP-2023-24-910 | 28/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
346 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOKULNAGAR and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001365/2022-2023 | 2376/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 20.03 | 50
347 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharui PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000165/2024-2025 | 2077/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
348 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000154/2023-2024 | 136/TD | 05/01/2024 | 0 | Resource Division | 15.86 | 0 | 0
349 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000273/2022-2023 | 2685/TD | 06/02/2023 | 0 | Resource Division | 73.85 | 0 | 0
350 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Quotation for Kharui Water Supply Scheme T/W-I Kolaghat CCC, Block-Sahaid Matangini Reference ID=860298136 Application ID=100000106136 Quotation Date=23.04.2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00694/2024-2025 | BP-2024-25-144 | 09/05/2024 | 0 | WBSEDCL | 0.62 | 0 | 0
351 | Midnapore Mechanical | Tamluk Sadar Sub-Division | ADDITIONAL CHARGE (ESCAL CHARGE-5%) FOR PO MODIFICATION TO REMOVE ROW AT THE TIME OF EXECUTATION THE Quotation bill for T/W NO-I OF KHARUI W/S SCHEME under MMD,PHE,Dte. WBSEDCL SUPPLY OFFICE: Kolaghat C.C.C Ref. Memo No- KCCC/T-08/DATED-29.11.2024/265 DT. 29/11/2024 APPLICATION ID: 100000124382 REFERENCE Id- 860319442 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03373/2024-2025 | C122421497101 | 16/12/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
352 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kharui W/S Scheme T/W-II Application No=2004614098 Reference ID=204225097 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04335/2023-2024 | BP-2023-24-802 | 11/03/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
353 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kharui W/S Scheme H/W Site Application No=2004624417 Reference ID=204231697 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04336/2023-2024 | BP-2023-24-801 | 11/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
354 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARUI AND ADJOINING MOUZAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001703/2022-2023 | 625/W/MMD | 20/03/2023 | 743 | DEBJYOTI BASU | 23.7 | 15.07 | 90
355 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 123.85 | 51
356 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000043/2024-2025 | 1645/TD | 18/06/2025 | 0 | Resource Division | 7.18 | 0 | 0
357 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000145/2022-2023 | 2449/TD | 16/01/2023 | 0 | Resource Division | 32.88 | 0 | 0
358 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004834992/QUOT/03 DT. 26-07-2024 Application NO- 2004834992 MEMO NO: AMR/PHE/284 DT.26/7/2024 Application type-New connection Consumer Id- 204365754 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01861/2024-2025 | BP-2024-25-537 | 07/08/2024 | 0 | WBSEDCL | 6.84 | 0 | 0
359 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835302/QUOT/03 DT. 26-07-2024 Application NO- 2004835302 MEMO NO: AMR/PHE/285 DT.26/7/2024 Application type-New connection Consumer Id- 204365759 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01862/2024-2025 | BP-2024-25-536 | 07/08/2024 | 0 | WBSEDCL | 1.98 | 0 | 0
360 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAPINDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001345/2022-2023 | 2356/W/MMD | 31/12/2022 | 974 | SOUMEN ELECTRIC | 21.61 | 15.29 | 61
361 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Alangiri PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000473/2024-2025 | 3762/TD | 10/12/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
362 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 196.57 | 51
363 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000007/2025-2026 | 2081/TD | 12/08/2025 | 0 | Resource Division | 9.22 | 0 | 0
364 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000159/2022-2023 | 2422/TD | 16/01/2023 | 0 | Resource Division | 39.03 | 0 | 0
365 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674870/QUOT/03 DT. 09-04-2024 Application NO- 2004674870 Application type-New connection Consumer Id- 204269908 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00507/2024-2025 | BP-2024-25-84 | 24/04/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
366 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674883/QUOT/03 DT. 09-04-2024 Application NO- 2004674883 Application type-New connection Consumer Id- 204269736 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00509/2024-2025 | BP-2024-25-85 | 24/04/2024 | 0 | WBSEDCL | 6.04 | 0 | 0
367 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ALANGIRI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001406/2022-2023 | 2417/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 10.72 | 80
368 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barnan PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000164/2024-2025 | 2076/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
369 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd T/W site Barnan W/S Scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000178/2024-2025 | 2182/TD | 08/07/2024 | 14 | S.D. CONSTRUCTION | 3.91 | 3.91 | 100
370 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 1(One) nos M.S. Structure over irrigation canal to support 200 mm dia. DI K-7 distribution pipe under Barnan Water Supply Scheme at NP 7-10 under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte.(Each length=24.00 Mtr ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000401/2025-2026 | 2147/TD | 18/08/2025 | 30 | GLOBAL TRADE | 3.74 | 0 | 100
371 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000120/2023-2024 | 82//TD | 05/01/2024 | 0 | Resource Division | 6.85 | 0 | 0
372 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000274/2022-2023 | 2684/TD | 06/02/2023 | 0 | Resource Division | 19.64 | 0 | 0
373 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Barnan Water supply Scheme Tubewell No-II Application No=2004756795 Reference ID=204319871 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01163/2024-2025 | BP-2024-25-267 | 12/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
374 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Barnan Water supply Scheme Tubewell No-I Application No=2004754441 Reference ID=204318380 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01164/2024-2025 | BP-2024-25-266 | 12/06/2024 | 0 | WBSEDCL | 8.5 | 0 | 0
375 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARNAN AND ITS ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001699/2022-2023 | 624/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 23.7 | 15.07 | 50
376 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna Block under Tamluk Division, PHE Dte. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000227/2024-2025 | 2428/TD | 30/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
377 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -2) , 2. GOURANGA CHAK PWSS( PUMP HOUSE 1 & 2), 3.GHOJINA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000257/2025-2026 | 63/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
378 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 245.75 | 75
379 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000873/2023-2024 | 195/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
380 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2024-2025 | 1566/TD | 23/04/2024 | 0 | Resource Division | 8.79 | 0 | 0
381 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000169/2022-2023 | 2437/TD | 16/01/2023 | 0 | Resource Division | 25.43 | 0 | 0
382 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gouranga chak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709475, Ref ID 204293707) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01074/2024-2025 | BP-2024-25-189 | 24/05/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
383 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gouranga chak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709436, Ref ID 204293706) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01075/2024-2025 | BP-2024-25-188 | 24/05/2024 | 0 | WBSEDCL | 7.81 | 0 | 0
384 | Midnapore Mechanical | Haldia Electrical Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
385 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOURANGA CHAK and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001682/2022-2023 | 558/W/MMD | 20/03/2023 | 709 | DIPALI CONSTRUCTION | 22.63 | 20.32 | 80
386 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
387 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Syamraibar PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000154/2024-2025 | 2065/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
388 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 286.45 | 75
389 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000067/2024-2025 | 2978/TD | 12/09/2024 | 0 | Resource Division | 6.44 | 0 | 0
390 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000168/2022-2023 | 2391/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0
391 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SHYAMRAIBAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005011621/QUOT/03 DT. 17-12-2024 Application NO- 2005011621 Application type-New connection Consumer Id- 204475366 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03861/2024-2025 | C012539048842 | 21/01/2025 | 0 | WBSEDCL | 3.94 | 0 | 0
392 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SYAMRAIBAR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001399/2022-2023 | 2410/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 7.35 | 35
393 | Tamluk Division | Digha Sub-Division | Leftout pipeline to accommodate FHTC under JJM of Jumki Water Supply Scheme within Egra I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000312/2024-2025 | 3156/TD | 27/09/2024 | 149 | SOM CONSTRUCTION | 27.41 | 0 | 100
394 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well , Laying distribution system, Pump House at Head work site & 2nd tube well site, Soil Test, OHR ( 250 Cum ) FHTC ( (1636 nos ) Boundary wall and Rising Main and 2 Years Maintenance under JJM with allied work for Jumki PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000639/2023-2024 | 2485/TD | 26/09/2023 | 1008 | AJIT KUMAR SOM | 442.63 | 241.06 | 65
395 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000014/2025-2026 | 2079/TD | 12/08/2025 | 0 | Resource Division | 10.08 | 0 | 0
396 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000316/2022-2023 | 2971/TD | 27/02/2023 | 0 | Resource Division | 19.96 | 0 | 0
397 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674807/QUOT/03 DT. 09-04-2024 Application NO- 2004674807 Application type-New connection Consumer Id- 204269878 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00504/2024-2025 | BP-2024-25-87 | 24/04/2024 | 0 | WBSEDCL | 4.9 | 0 | 0
398 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674743/QUOT/03 DT. 09-04-2024 Application NO- 2004674743 Application type-New connection Consumer Id- 204269918 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00505/2024-2025 | BP-2024-25-86 | 24/04/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
399 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JUMKI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001360/2022-2023 | 2371/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 17.21 | 85
400 | Tamluk Division | Haldia Sub-Division | Trial boring of 2 (two) nos. 100 mm x 50 mm dia x 270 mtr (av.) depth Tube well & sinking upto 200 mtr. depth with PVC pipes including cost of all materials for Sarberya PWSS ( Head Work Site & 2nd T/W Site) under Haldia Sub Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000210/2024-2025 | 2384/TD | 26/07/2024 | 98 | DIPANKAR MAITY | 4.09 | 0 | 100
401 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2023-2024 | 1468/TD | 13/07/2023 | 777 | JAGANNATH MAKAR | 80.39 | 33.31 | 3
402 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000807/2022-2023 | 3076/TD | 28/02/2023 | 30 | PULAK KUMAR SAMANTA | 55.08 | 45.84 | 62
403 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000808/2022-2023 | 3077/TD | 28/02/2023 | 941 | J.M. CONSTRUCTION | 59.34 | 45.12 | 35
404 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000809/2022-2023 | 3078/TD | 28/02/2023 | 447 | R CONSTRUCTION | 42.52 | 39.94 | 100
405 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000810/2022-2023 | 3079/TD | 28/02/2023 | 20 | MADAN MOHAN MAITY | 36.48 | 35.3 | 100
406 | Tamluk Division | Haldia Sub-Division | Installation of display board at 2 (two) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) [Sarberia PWSS & Urddhabmal PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000832/2023-2024 | 620/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.42 | 0.41 | 100
407 | Tamluk Division | Haldia Sub-Division | Orientation Programme under Haldia Sub-Division of Tamluk Division, PHE Dte. (For 5 nos Blocks, i.e. - i) Sutahata Dev. Block, ii) Mahishadal Dev. Block, iii) Haldia Dev. Block, iv) Nandigram - I Dev. Block & v) Nandigram - II Dev. Block) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001169/2023-2024 | 621/HSD, | 21/12/2023 | 2 | TAPAN BERA | 0.94 | 0.94 | 100
408 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site & Construction of Retaining wall of ground water based Sarberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001241/2023-2024 | 1083/TD | 16/03/2024 | 40 | JAGANNATH MAKAR | 13.42 | 0 | 0
409 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000137/2022-2023 | 2424/TD | 16/01/2023 | 0 | Resource Division | 39.36 | 0 | 0
410 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000170/2023-2024 | 112/TD | 05/01/2024 | 0 | Resource Division | 5.39 | 0 | 0
411 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAR BERYA and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001659/2022-2023 | 544/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 21.56 | 21.13 | 100
412 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (845 nos) under JJM with allied work of KAPASDA PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000279/2023-2024 | 554/TD | 12/05/2023 | 868 | PATHIK PABAN NANDI | 453.18 | 136.77 | 50
413 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000093/2024-2025 | 2963/TD | 12/09/2024 | 0 | Resource Division | 9.09 | 0 | 0
414 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000313/2022-2023 | 2969/TD | 27/02/2023 | 0 | Resource Division | 34.67 | 0 | 0
415 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAPASDA and ADJOINING MOUJAS, Block ¿ contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001677/2022-2023 | 556/W/MMD | 20/03/2023 | 180 | SHIVAM ENTERPRISE | 22.78 | 0 | 0
416 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
417 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (672 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of GHANTA SHALA PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000350/2023-2024 | 852/TD | 31/05/2023 | 940 | GHOSH CONSTRUCTION | 288.84 | 184.54 | 75
418 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000135/2023-2024 | 105/TD | 05/01/2024 | 0 | Resource Division | 4.14 | 0 | 0
419 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000266/2022-2023 | 2694/TD | 06/02/2023 | 0 | Resource Division | 26.6 | 0 | 0
420 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for GHATASHALA Water Supply Scheme T/W-I, (Ref. ID-204135822) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03002/2023-2024 | BP-2023-24-359 | 24/11/2023 | 0 | WBSEDCL | 4.07 | 0 | 0
421 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-2 of Ghantashala ws scheme under MMD PHE DTE, Ref Application no-2004577503, Con ID-204203251 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03568/2023-2024 | BP-2023-24-651 | 09/02/2024 | 0 | WBSEDCL | 8.39 | 0 | 0
422 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GHANTA SHALA AND IT'S ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001708/2022-2023 | 593/W/MMD | 20/03/2023 | 713 | ASHUTOSH DAS & CO. | 21.53 | 0 | 80
423 | Tamluk Division | Contai Sub-Division | Schedule for Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Chistipur PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000174/2024-2025 | 2086/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
424 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall,Rigid Pavment CC road Soil investigation & Accommodate FHTC (2004 nos) including 2 years Operation & Maintenance under JJM with allied work for Chistipur & its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000497/2023-2024 | 1673/TD | 25/07/2023 | 1067 | HALDIA DEVELOPMENT CONSTRUCTION | 523.91 | 0 | 60
425 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000025/2024-2025 | 1638/TD | 18/06/2025 | 0 | Resource Division | 12.34 | 0 | 0
426 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000321/2022-2023 | 2994/TD | 27/02/2023 | 0 | Resource Division | 17.01 | 0 | 0
427 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of CHISTIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835430/QUOT/03 DT. 26-07-2024 Application NO- 2004835430 MEMO NO: AMR/PHE/280 DT.26/7/2024 Application type-New connection Consumer Id- 204365756 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01859/2024-2025 | BP-2024-25-540 | 07/08/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
428 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of CHISTIPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005031537/QUOT/03 DT. 02-01-2025 MEMO NO: AMR/PHE/594 DT. 02-01-2025 Application NO- 2005031537 Application type-New connection Consumer Id- 204487553 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04002/2024-2025 | C022509402799 | 05/02/2025 | 0 | WBSEDCL | 5.98 | 0 | 0
429 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHISTIPUR AND ITS ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002041/2022-2023 | 949/W/MMD | 28/03/2023 | 887 | M/S B.M. ELECTRICAL | 22.78 | 0 | 62
430 | Tamluk Division | Contai Sub-Division | Shifting of 11kv HT Line (Junput feeder) at BAGURAN JALPAI WS SCHEME, BLOCK-Contai-1,CCC-CONTAI. Ref memono.-CD-322 Dated-14.05.2024 Ref. ID-860299651 Application ID-100000107869 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00421/2024-2025 | BP-2024-25-142 | 27/05/2024 | 0 | WBSEDCL | 2.06 | 0 | 0
431 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
432 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baguran Jalpai PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000230/2024-2025 | 2427/TD | 30/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
433 | Tamluk Division | Contai Sub-Division | Installation of display Board of Augmentation of Contai Saline Area Zone-IV PWSS (Part-1) (Kalikapur) at 1st & 2nd TW site in Contai-II (Deshpran) Block, Paschim Rasulpur PWSS (1st TW site), Baguran Jalpai PWSS (2nd TW site), Potapukuria PWSS ( 2nd TW site) in Contai-I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000323/2025-2026 | 1623/CSD | 19/06/2025 | 7 | BHARAT NIRMAN ENTERPRISE | 0.83 | 0 | 100
434 | Tamluk Division | Contai Sub-Division | Construction of Retaining wall for Protection of OHR site from Soil erosion and Land filling at Baguran Jalpai and its adjoing Mouzas- PWSS in Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. (For Low Land and existance of natural channel nearby) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000387/2024-2025 | 3448/TD | 30/10/2024 | 200 | BISWA NIRMAN ENTERPRISE. | 11.77 | 0 | 72
435 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 430.99 | 75
436 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000071/2024-2025 | 2948/TD | 12/09/2024 | 0 | Resource Division | 8.06 | 0 | 0
437 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000173/2022-2023 | 2396/TD | 16/01/2023 | 0 | Resource Division | 35.66 | 0 | 0
438 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAGURANJALPAI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004689899/QUOT/03 DT. 19-04-2024 Application NO- 2004689899 Application type-New connection Consumer Id- 204279763 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00664/2024-2025 | BP-2024-25-111 | 06/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
439 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGURAN JALPAI AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001721/2022-2023 | 596/W/MMD | 20/03/2023 | 712 | T.S.CONSTRUCTION | 22.75 | 0 | 51
440 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Nonakourda PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000156/2024-2025 | 2068/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
441 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1018 nos) under JJM with allied work for Nonakourda- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000683/2023-2024 | 2684/TD | 16/10/2023 | 893 | RELIABLE CONSTRUCTIONS | 352.4 | 62.22 | 30
442 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000034/2024-2025 | 1661/TD | 29/04/2024 | 0 | Resource Division | 6.27 | 0 | 0
443 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000342/2022-2023 | 2997/TD | 27/02/2023 | 0 | Resource Division | 8.93 | 0 | 0
444 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of Nonakourda W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760157/QUOT/03 DT. 04-06-2024 Application NO- 2004760157 Application type-New connection Consumer Id- 204322028 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01238/2024-2025 | BP-2024-25-288 | 18/06/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
445 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NONAKOURDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2005010804/QUOT/03 DT. 31-12-2024 Application NO- 2005010804 Application type-New connection Consumer Id- 204475790 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04001/2024-2025 | C022509408281 | 05/02/2025 | 0 | WBSEDCL | 4.83 | 0 | 0
446 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NONAKOURDA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001669/2022-2023 | 552/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 0 | 55
447 | Tamluk Division | Tamluk Sadar Sub-Division | Shifting of Existing Electrical Installation from Baragachia PWSS Under Sahid Matangini Development Block Under Tamluk Sadar Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01318/2024-2025 | BP-2024-25-659 | 22/03/2025 | 0 | WBSEDCL | 5.21 | 0 | 0
448 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (785 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BARAGECHA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000223/2023-2024 | 458/TD | 04/05/2023 | 1080 | TAPAS SANTRA | 308.25 | 12.73 | 50
449 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000118/2023-2024 | 97//TD | 05/01/2024 | 0 | Resource Division | 4.84 | 0 | 0
450 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000209/2022-2023 | 2469/TD | 16/01/2023 | 0 | Resource Division | 54.65 | 0 | 0
451 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for Bargachia W/S scheme TW-II Block-Kolaghat Kolaghat CCC Application ID-2005220089 Ref ID-204621582 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00772/2025-2026 | 42156W | 07/08/2025 | 0 | WBSEDCL | 3.43 | 0 | 0
452 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for T/W NO-I OF Bargachia W/S SCHEME under MMD,PHE,Dte. WBSEDCL SUPPLY OFFICE: Kolaghat C.C.C Ref. Memo No- 2004891704/Quot/03 DT. 09/09/2024 APPLICATION ID: 2004891704 REFERENCE Id- 204394386 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03374/2024-2025 | C122421492088 | 16/12/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
453 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAGECHA and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001664/2022-2023 | 547/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 21.58 | 6.57 | 40
454 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 93.52 | 75
455 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000220/2022-2023 | 2674/TD | 06/02/2023 | 0 | Resource Division | 13.79 | 0 | 0
456 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connection at Uttar Sautanchak water supply scheme tube well no.-II Tamluk CCC Block-Tamluk Application No.-2004785533 Consumer ID.-204336033 Date.-21-06-2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01329/2024-2025 | BP-2024-25-356 | 01/07/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
457 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for Uttat Sautanchak Water Supply scheme H/W site. Quotation Bill Date.-20/03/2024 Tamluk Block Tamluk CCC Application No.-2004648593 Ref. ID-204250592 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04735/2023-2024 | BP-2023-24-919 | 28/03/2024 | 0 | WBSEDCL | 0.87 | 0 | 0
458 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SAUTANCHAK PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002038/2022-2023 | 946/W/MMD | 28/03/2023 | 719 | M/S. S.R. ENTERPRISE | 21.55 | 12.49 | 75
459 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Shifting of LT line of Purba Nukha PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01993/2023-2024 | BP-2023-24-937 | 06/03/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
460 | Tamluk Division | Tamluk Sadar Sub-Division | Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2260 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2024 to 31.01.2025.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000249/2024-2025 | 1110/TSD | 31/07/2024 | 184 | KISHORE KUMAR SEN | 0.87 | 1.85 | 80
461 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well , Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 350 Cum OHR (Intze type with pile foundation) and Accommodate FHTC 2344 nos including 02(Two) Years Operation & Maintanance for Two years including supply of all labour & materials with allied work under JJM for Purbanukha and Adjoining Moujas Piped Water Supply Scheme under Tamluk Block withen Tamluk Sub-Division under Tamluk Division, PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000485/2023-2024 | 1567/TD | 19/07/2023 | 180 | TARUN KOLEY | 549.36 | 145.4 | 65
462 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.02.2025 to 31.07.2025.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000687/2024-2025 | 222/TSD | 28/01/2025 | 181 | KISHORE KUMAR SEN | 0.86 | 0 | 0
463 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000295/2022-2023 | 3009/TD | 27/02/2023 | 0 | Resource Division | 27.4 | 0 | 0
464 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Purbaanukha W/S scheme H/W site Application No.-2004603682 Ref.-204218679 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04060/2023-2024 | BP-2023-24-748 | 27/02/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
465 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA NUKHA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001726/2022-2023 | 598/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 23.7 | 11.62 | 35
466 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004966048/QUOT/03 DT. 22-11-2024 Application NO- 2004966048 Application type-New connection Consumer Id- 204446057 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/01295/2024-2025 |  | 16/12/2024 | 0 | WBSEDCL | 2.54 | 0 | 0
467 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005019326/QUOT/03 DT. 23-12-2024 Application NO- 2005019326 Application type-New connection Consumer Id- 204480239 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/01502/2024-2025 |  | 06/03/2025 | 0 | WBSEDCL | 2.59 | 0 | 0
468 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000145/2023-2024 | 124/TD | 05/01/2024 | 0 | Resource Division | 0.97 | 0 | 0
469 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000350/2022-2023 | 3016/TD | 27/02/2023 | 0 | Resource Division | 15.15 | 0 | 0
470 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at JHAUGERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000044/2023-2024 | 1215/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 12.05 | 0 | 0
471 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at tw no.-1 of Kanpur Zone-2 w/s scheme under MMD,PHE Dte, Block-Ramnagar -2 under Digha CCC Application no-2005040494 CON ID-204494116 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01503/2024-2025 |  | 06/03/2025 | 0 | WBSEDCL | 26.37 | 0 | 0
472 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR & Accommodate FHTC ( 238 Nos) under JJM with allied work for KANPUR (Z-II) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000705/2023-2024 | 2819/TD | 08/11/2023 | 180 | BASANTA KUMAR MAITY | 278.75 | 80.94 | 35
473 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000968/2022-2023 | 1058/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 3.06 | 100
474 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000037/2023-2024 | 2082/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
475 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000108/2023-2024 | 3011/TD | 29/11/2023 | 0 | Resource Division | 1.47 | 0 | 0
476 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-2, TW-2 OF KANPUR WS SCHEME UNDER MMD PHE DTE,BLOCK-RAMNAGAR-II, DIGHA CCC APPLCATION NO-2004746438, CON ID-204313992 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01139/2024-2025 | BP-2024-25-252 | 06/06/2024 | 0 | WBSEDCL | 6.19 | 0 | 0
477 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
478 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VII). Name of sites:- i) Gopalpur PWSS's 4th Tube well Site, ii) Rangibasan PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. iii) Betkundu PWSS 1st Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000389/2024-2025 | 1072/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
479 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VIII). Name of sites:- i) Betkundu PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Rajarampur PWSS's 1st Tube well Site and 2nd Tube well Site iii) Natshal Lakshya (Z-I) 1st Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000390/2024-2025 | 1073/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
480 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IX). Name of sites: - i) Natshal Lakshya (Z-1) PWSS's 2nd Tube well Site, 3rd Tube well site, 4th Tube well site, 5th Tube well site ii) Natshal Lakshya (Z-II) PWSS's 1st Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000391/2024-2025 | 1074/HSD, | 05/11/2024 | 57 | SANTANU PATTANAYAK | 0.83 | 0 | 100
481 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-X) Name of sites:- i) Baramrit Bere PWSS's 1st Tube well Site, 2nd Tube well site, ii) Amritberya PWSS 1st Tube well Site, 2nd Tube well Site iii) Bamanpur 1st Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000392/2024-2025 | 1075/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
482 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XI) Name of sites:- i) Bamanpur PWSS's 1st Tube well Site, ii) Kanchanpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Sarberya 1st Tube well Site and 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000393/2024-2025 | 1076/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
483 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XII) Name of sites: - i) Madhya Hingli PWSS's 1st Tube well Site, 2nd Tube well site, ii) Baksichak PWSS's 1st Tube well Site, iii) Mayachar 1st Tube well Site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000394/2024-2025 | 1077/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
484 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIII) Name of sites: - i) Lakshya PWSS¿s 1st Tube well Site, 2nd Tube well site, 3rd Tube well site ii) Keshabpur jalpai PWSS's 1st Tube well Site, 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000395/2024-2025 | 1078/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100
485 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIV) Name of sites: - i) Bar Sundara PWSS's 3rd Tube well Site, ii) Simulberya PWSS's 1st Tube well site iii) Natshal Lakshya (Z-II) PWSS's 2nd Tube well Site and 3rd Tube well site. iv) Kesabpur Jalpai PWSS's 3rd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2024-2025 | 1079/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
486 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XV) Name of sites:- i) Dwariberia PWSS's 1st Tube well Site, and 2nd Tube well site, ii) Barbasudevpur PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000397/2024-2025 | 1080/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100
487 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVI) Name of sites: - i) Manoharpur PWSS¿s 1st Tube well site and 2nd Tube well Site. ii) Solat PWSS's 1st Tube well site and 2nd Tube well site, iii) Dakshinchak PWSS's 1st Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000398/2024-2025 | 1081/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100
488 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVII) Name of sites: - i) Dakshinchak (Z-I) PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Dakshinchak (Z-II) PWSS's 1st Tube well Site (iii) Barsundara PWSS 1st Tube well site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000399/2024-2025 | 1082/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100
489 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVIII) Name of sites:- i) Gholpukuria PWSS's (Z-1) 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Gholpukuria PWSS's (Z-II) PWSS's 1st Tube well Site, 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000402/2024-2025 | 1083/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
490 | Tamluk Division | Haldia Sub-Division | Installation of 3 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIX) Name of sites: - i) Jalpai Part -II PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2024-2025 | 1084/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.5 | 0 | 100
491 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XX) Name of sites:- i) Manikpur PWSS's 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Tajpur PWSS's 1st Tube well Site and 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000404/2024-2025 | 1085/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
492 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXI) Name of sites: - i) Tajpur PWSS's 3rd Tube well Site ii) Mahammadpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Sonachura PWSS 1st Tube well Site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2024-2025 | 1086/HSD | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
493 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXII) Name of sites: - i) Solat Headwork site. ii) Chaitanyapur (Zone-II) 2nd Tube well site, 3rd Tube well site and 4th Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2024-2025 | 1087/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.67 | 0 | 100
494 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXIII) Name of sites:- i) Nandigram PWSS 1st Tube well site and 2nd Tube well site. ii) Reyapara PWSS 1st Tube well site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000408/2024-2025 | 1088/HSD | 05/11/2024 | 57 | SANTANU PATTANAYAK | 0.67 | 0.67 | 100
495 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) Name of sites- i) Dhenuka PWSS's Head Work Site and 2nd Tube well Site. ii) Tabakhali PWSS's Head Work site and 3rd Tube well site, iii) Begunberia PWSS's, Head Work site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000424/2024-2025 | 1108/HSD, | 13/11/2024 | 49 | SINGHA ENTERPRISE | 0.83 | 0 | 100
496 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) Name of sites: i) Begunberia PWSS's, 2nd Tube well site and 3rd Tube well site, ii) Chaitanyapur PWSS (Zone-I)'s 1st Tube well Site, 2nd Tube well site and 3rd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000425/2024-2025 | 1109/HSD, | 13/11/2024 | 49 | SINGHA ENTERPRISE | 0.83 | 0 | 100
497 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) Name of sites: i) Chaitanyapur (Z-I) PWSS's 3rd Tube well site. ii) Chaitanyapur (Z-II) PWSS's 3rd Tube well site, iii) Asadtalia PWSS's, 1st Tube well Site, and 2nd Tube well site and 3rd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000426/2024-2025 | 1110/HSD, | 13/11/2024 | 49 | SINGHA ENTERPRISE | 0.83 | 0 | 100
498 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) Name of sites: - i) Urddhabmal PWSS¿s 1st Tube well Site, 2nd Tube well site, ii) Jaynagar PWSS's 1st Tube well Site, 2nd Tube well Site iii) Erakhali PWSS 1st Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000427/2024-2025 | 1111/HSD, | 13/11/2024 | 49 | SINGHA ENTERPRISE | 0.83 | 0 | 100
499 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-V) Name of sites: - i) Erakhali PWSS¿s 2nd Tube well Site, ii) Mohanpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Hariballbhpur PWSS 1st Tube well Site, 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000428/2024-2025 | 1112/HSD, | 13/11/2024 | 49 | SINGHA ENTERPRISE | 0.83 | 0 | 100
500 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VI) Name of sites:- i) Kapaseria PWSS's 1st Tube well Site, 2nd Tube well site, ii) Gopalpur PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000429/2024-2025 | 1113/HSD, | 13/11/2024 | 7 | SINGHA ENTERPRISE | 0.83 | 0 | 100
501 | Tamluk Division | Haldia Sub-Division | Ground water based Amritberya Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (450 cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000500/2023-2024 | 1688/TD | 26/07/2023 | 583 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 580.82 | 341.56 | 40
502 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-1) Location:- 1) Dwariberiyarchak of Lakshya - I G.P. within Lakshya PWSS, 2) Rajchak of Natshal - 2 G.P. within Gopalpur PWSS, 3) Ghagra of Kishmat Naikundi G.P. within Rangibasan PWSS, 4) Sarberia of Kishmat Naikundi within Sarberia PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000520/2024-2025 | 20/HSD, | 09/01/2025 | 10 | SANTANU PATTANAYAK | 0.83 | 0 | 100
503 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-2) Location:- 1) Anantapur of Asadtalia G.P. within Asathalia PWSS, 2) Jamalchak of Asadtalia G.P. within Asadtalia PWSS, 3) Dakshin Gobindapur of Asadtalia G.P. within Asadtalia PWSS, 4) Dundipur of Horkhali G.P. within Begunberya PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000522/2024-2025 | 21/HSD | 09/01/2025 | 10 | SINGHA ENTERPRISE | 0.83 | 0 | 100
504 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-3) Location:- 1) Finga of Horkhali G.P. within Begunberia PWSS, 2) Ataphala of Horkhali G.P. within Begunberia PWSS, 3) Horkhali of Horkhali G.P. within Begunberia PWSS, 4) Begunbere of Horkhali G.P. within Begunberya PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000523/2024-2025 | 22/HSD, | 09/01/2025 | 10 | SNEHASIS BERA | 0.83 | 0 | 100
505 | Tamluk Division | Haldia Sub-Division | Installation of 3 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-4) Location:- 1) Asathtalya of Asataliya G.P. within Asathtalya PWSS, 2) Barotala of Asataliya G.P. within Asathtalya PWSS, 3) Gopalpur of Kismat Naikundi G.P. within Gopalpur PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2024-2025 | 23/HSD, | 09/01/2025 | 10 | G. S. A. CONSTRUCTION | 0.62 | 0 | 100
506 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2025 to 31/12/2025. (12 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000564/2024-2025 | 1285/HSD, | 27/12/2024 | 365 | SANTANU PATTANAYAK | 1.5 | 1.2 | 40
507 | Tamluk Division | Haldia Sub-Division | Supply and delivery of 3 nos Chairs (with arm rest), 11 nos Chairs (without arm rest) and 1 nos stainless steel Rack (72inch X 36inch X 15 inch with 5 selves) (all articles should be of Godrej Interio Brand) under Office of the Assistant Engineer, Haldia Sub-Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001013/2023-2024 | 689/HSD, | 31/01/2024 | 343 | MALLIK TRADERS | 0.97 | 0 | 100
508 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Amritberya PWSS at Mahisadal Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001043/2023-2024 | 373/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 0
509 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site & Construction of Retaining wall of ground water based Amritberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001242/2023-2024 | 1082/TD | 16/03/2024 | 350 | G. S. CONSTRUCTION | 10.83 | 0 | 100
510 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000113/2023-2024 | 77/TD | 05/01/2024 | 0 | Resource Division | 21.19 | 0 | 0
511 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000331/2022-2023 | 2984/TD | 27/02/2023 | 0 | Resource Division | 27.61 | 0 | 0
512 | Central Drilling | Haldia Sub-Division | : Providing drilling crew and other allied works for construction of Tube Well ( 200mm X150mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Amrit Berya W/S Scheme (T/W-II) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000181/2023-2024 | 58/CDD | 06/04/2023 | 30 | MENAKA ENTERPRISE | 16.22 | 0 | 0
513 | Midnapore Mechanical | Haldia Sub-Division | Quotation of new service connection at Amritberiya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004714253, Ref ID 204295221) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01142/2024-2025 | BP-2024-25-243 | 06/06/2024 | 0 | WBSEDCL | 4.8 | 0 | 0
514 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004760250, Ref ID 204322037) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01334/2024-2025 | BP-2024-25-362 | 01/07/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
515 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMRITBERYA and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000086/2023-2024 | 1270/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 21.2 | 60
516 | Midnapore Mechanical | Haldia Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
517 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 432/TD | 27/05/2022 | 90 | JAGANNATH MAKAR | 234.25 | 229.76 | 95
518 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rasikachak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2021-2022 | 1194/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 4.62 | 100
519 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000243/2024-2025 | 2695/TD | 22/08/2024 | 30 | HARIPADA PATTANAYAK | 38.26 | 0 | 0
520 | Tamluk Division | Tamluk Sadar Sub-Division | Piling work and pond crossing of Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining mouzas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2344/TD | 10/01/2023 | 25 | JAGANNATH MAKAR | 29.39 | 28.47 | 0
521 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000195/2023-2024 | 1095/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
522 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BANCHBERIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671953/QUOT/03/49 DT. 05-04-2024 Application NO- 2004671953 Application type-New connection Consumer Id- 204266734 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01293/2024-2025 | BP-2024-25-653 | 06/02/2025 | 0 | WBSEDCL | 2.96 | 0 | 0
523 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BANCHBERIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672038/QUOT/03/51 DT. 05-04-2024 Application NO- 2004672038 Application type-New connection Consumer Id- 204266721 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01294/2024-2025 | BP-2024-25-654 | 06/02/2025 | 0 | WBSEDCL | 5.11 | 0 | 0
524 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , & Accommodate FHTC (147 nos) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000123/2023-2024 | 256/TD | 19/04/2023 | 857 | CHANDIMATA CONSTRUCTION | 84.7 | 26.51 | 70
525 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Boundary Wall & Rising main pipe line under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000125/2023-2024 | 257/TD | 19/04/2023 | 60 | SOUMYA ENTERPRISE | 49.45 | 20.51 | 45
526 | Tamluk Division | Digha Sub-Division | Soil investigation, 50 cum OHR ( type with pile foundation) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000416/2023-2024 | 1085/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.56 | 31.16 | 50
527 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2025-2026 | 2085/TD | 12/08/2025 | 0 | Resource Division | 0.91 | 0 | 0
528 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000352/2022-2023 | 3015/TD | 27/02/2023 | 0 | Resource Division | 16.09 | 0 | 0
529 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 57.54 | 11
530 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIII (Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000103/2021-2022 | 729/TD | 15/09/2021 | 180 | ARABINDA GHOSH | 342.78 | 471.5 | 100
531 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Surface Water Based W/S Scheme for Zone - VIII under Tamluk Division, PHE Dte. in the district of Purba Medinipur. |  |  | VCH/000375/2021-2022 | BP-2021-22-125 | 07/10/2021 | 0 | ARABINDA GHOSH | 106.46 | 0 | 0
532 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (190 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XI Block - Kolaghat in the District of Purba Medinipur.(Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000121/2023-2024 | 252/TD | 19/04/2023 | 20 | MISHRA ENTERPRISE | 9.69 | 9.69 | 100
533 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (990 nos.) and laying of left-out portion UPVC pipeline due to uncovered area at different nodel point under JJM in Surface water based Water Supply Scheme for Zone-XI, Block- Kolaghat in the District of Purba Medinipur. (Phase-III) [PART-A) | Assistant Engineer | Junior Engineer | ORD/000247/2023-2024 | 512/TD | 11/05/2023 | 40 | TAPAS SANTRA | 81.84 | 69.61 | 85
534 | Tamluk Division | Digha Sub-Division | Payment to WBSEDCL for Shifting of 33 KV FEEDER HT Line at Sabitrapur for Kanpur Water Supply Scheme for Zone-V under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02086/2023-2024 | BP-2023-24-957 | 14/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
535 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000459/2022-2023 | 1858/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.13 | 100
536 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 184 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000509/2023-2024 | 1731/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 284.7 | 166.43 | 5
537 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (215 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000591/2024-2025 | 491/TD | 06/02/2025 | 120 | GHOSH CONSTRUCTION | 87.4 | 0 | 80
538 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone-V PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000868/2023-2024 | 190/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
539 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000042/2023-2024 | 2067/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
540 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000094/2023-2024 | 2997/TD | 29/11/2023 | 0 | Resource Division | 1.13 | 0 | 0
541 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme TW no.-II, Z-V Ref.-204156068 Application ID-2004521673 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03154/2023-2024 | BP-2023-24-445 | 19/12/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
542 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I,ZONE-V of KANPUR WS SCHEME under MMD,PHE Dte, Block-Ramnagar-II, DIGHA CCC, Application no-2004644488, CON ID-204246837 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04741/2023-2024 | BP-2023-24-913 | 28/03/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
543 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
544 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation works for the purpose of Geotagging at different PWSS under CHANDIPUR, MAHISHADAL and KHEJURI Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000182/2024-2025 | 725/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.7 | 0 | 100
545 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002149/2022-2023 | 1083/W/MMD | 30/03/2023 | 180 | S.S.GHORAI | 11.86 | 0 | 0
546 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
547 | Tamluk Division | Contai Sub-Division | Bill for payment to WBSEDCL for New Pipe Construction at Panchgachia new Sawsahan for Fuleshwar PWSS under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02050/2023-2024 | BP-2023-24-962 | 14/03/2024 | 0 | WBSEDCL | 0.27 | 0 | 0
548 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 167.92 | 51
549 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000095/2024-2025 | 2958/TD | 12/09/2024 | 0 | Resource Division | 7.81 | 0 | 0
550 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000122/2022-2023 | 2403/TD | 16/01/2023 | 0 | Resource Division | 34.22 | 0 | 0
551 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of FULESWAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767027/QUOT/03 DT. 07-06-2024 Application NO- 2004767027 Application type-New connection Consumer Id- 204325420 | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01222/2024-2025 | BP-2024-25-301 | 18/06/2024 | 0 | WBSEDCL | 12.7 | 0 | 0
552 | Midnapore Mechanical | Contai Sub-Division | Quotation bill for Fuleswar W/S scheme T/W. No.-I, P.S- Contai, Block.-Contai-II Application No.-2004626938 Ref ID.-204233452 Date.-01/03/2024 Quotation Date.-01-03-2024 Mukundapur CCC | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04337/2023-2024 | BP-2023-24-808 | 11/03/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
553 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FULESHWAR and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001622/2022-2023 | 508/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 22.77 | 9.98 | 60
554 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 255.59 | 51
555 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000039/2024-2025 | 1628/TD | 18/06/2025 | 0 | Resource Division | 17.99 | 0 | 0
556 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000142/2022-2023 | 2442/TD | 16/01/2023 | 0 | Resource Division | 19.52 | 0 | 0
557 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790353/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/211 DT. 24-06-2024 Application NO- 2004790353 Application type-New connection Consumer Id- 204339004 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01367/2024-2025 | BP-2024-25-375 | 08/07/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
558 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790382/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/212 DT. 24-06-2024 Application NO- 2004790382 Application type-New connection Consumer Id- 204339027 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01368/2024-2025 | BP-2024-25-374 | 08/07/2024 | 0 | WBSEDCL | 2.17 | 0 | 0
559 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHOULA BHERI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001660/2022-2023 | 529/W/MMD | 20/03/2023 | 889 | BHABANI PRASAD MANNA | 25.26 | 0 | 50
560 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 327.94 | 60
561 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000097/2024-2025 | 2959/TD | 12/09/2024 | 0 | Resource Division | 14.85 | 0 | 0
562 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000230/2022-2023 | 2709/TD | 06/02/2023 | 0 | Resource Division | 14.75 | 0 | 0
563 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Jahanabad W/S Scheme (T/W-I), Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000101/2023-2024 | 851/CDD | 10/07/2023 | 300 | UNIVERSAL ENTERPRISES | 15.71 | 13.39 | 100
564 | Midnapore Mechanical | Contai Sub-Division | New service connection at Jahanabad PH I in the District of Pruba Medinipur under MMD PHE Dte.( App No.- 2004920946, Ref ID : 204412267) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03263/2024-2025 | C122405703685 | 05/12/2024 | 0 | WBSEDCL | 5.47 | 0 | 0
565 | Midnapore Mechanical | Contai Sub-Division | Quotation for new application at Jahanabad w/s scheme PH II in the district of Purba Medinipur MMD PHE Dte. (App No. 2005025902, Ref Id 204483776) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03939/2024-2025 | C012539045649 | 21/01/2025 | 0 | WBSEDCL | 7.34 | 0 | 0
566 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAHANABAD and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000089/2023-2024 | 1267/W/MMD | 04/05/2023 | 697 | MENAKA ENTERPRISE | 25.14 | 0 | 0
567 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
568 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 92.45 | 94
569 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 359.75 | 70
570 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 2896/TD | 21/11/2023 | 0 | Resource Division | 14.27 | 0 | 0
571 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000283/2020-2021 | 2974/TD | 25/02/2021 | 70 | SANKHA ENTERPRISE | 164.85 | 0 | 100
572 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000243/2021-2022 | BP-2021-22-66 | 18/08/2021 | 0 | SANKHA ENTERPRISE | 70.63 | 0 | 0
573 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000895/2021-2022 | BP-2021-22-297 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0
574 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000896/2021-2022 | BP-2021-22-298 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 14.19 | 0 | 0
575 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Gogras Keshab bar,J.L. No-328 and Village-Gogras Kottaluk,J.L. No-329 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000104/2020-2021 | 2460/TD | 18/12/2020 | 30 | TARUN KOLEY | 37.07 | 0 | 100
576 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Beraberia,J.L. No-330 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000105/2020-2021 | 2461/TD | 18/12/2020 | 20 | TARUN KOLEY | 17.22 | 0 | 100
577 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Purushottampur,J.L. No-331 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000106/2020-2021 | 2462/TD | 18/12/2020 | 25 | TARUN KOLEY | 26.29 | 0 | 100
578 | Tamluk Division |  | Survey and data collection through mobile application regarding availability of drinking water, Sanitation facility, Rain water harvesting, greywater management and others parameters in High School, upper Primary School, Primary School, Sisu Siksha Kendra of 25 blocks areas under Tamluk Division PHE Dte within Purba Medinipur District. |  |  | ORD/000429/2022-2023 | 1618/TD | 20/10/2022 | 20 | SUDIP MANNA | 3.67 | 3.52 | 100
579 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Gogas Keshab Bar and Gogras Kottaluk Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001027/2020-2021 | 700/W | 02/02/2021 | 0 | TARUN KOLEY | 36.85 | 0 | 0
580 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Beraberia Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001028/2020-2021 | 701/W | 02/02/2021 | 0 | TARUN KOLEY | 17.09 | 0 | 0
581 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Purushottampur Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001029/2020-2021 | 702/W | 02/02/2021 | 0 | TARUN KOLEY | 25.18 | 0 | 0
582 | Tamluk Division |  | Annual Maintenance of Computer and Peripherals for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. (Period from 01/11/20 to 28/02/2021) |  |  | VCH/000074/2021-2022 | 08/W | 05/05/2021 | 0 | MISHRA ENTERPRISE | 0.78 | 0 | 0
583 | Tamluk Division |  | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000165/2020-2021 | 05 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 9.82 | 0 | 0
584 | Tamluk Division |  | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000166/2020-2021 | 06 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 8.25 | 0 | 0
585 | Tamluk Division |  | Contigency Bill of NGO managed laboratory for the period from October, 2020 to March, 2021. under Tamluk Division, PHE Dte. |  |  | VCH/000215/2021-2022 | 161/W | 30/07/2021 | 0 | TAMRALIPTA GUCHHA SAMITY AND OTHERS | 2.45 | 0 | 0
586 | Tamluk Division |  | THIS BILL HAS BEEN RAISED FOR SURRENDER OF UNSPENT FUND TO THE SINGLE NODAL ACCOUNT AS PER CLAUSE 2(III) OF D.O. NO. F.1(13)PFMS/FCD/2020, DTD. 12TH APRIL, 2021 BY SECRETARY, EXPENDITURE, GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE AND CLAUSE 13 OF OFFICE MEMORANDUM. NO. F.I. (13) PFMS FCD / 2020 DTD. 23/03/2021 BY THE DIRECTOR (FCD), GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE, PFMS DIVISION, AND VIDE MEMO NO. 2724/PHE-13011/7/2021-BUDGET CELL-DEPT. OF PHE Dte. |  |  | VCH/000706/2021-2022 | 452/W | 22/12/2021 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 7.13 | 0 | 0
587 | Tamluk Division |  | Instrument / Equipment for Digha Sub-Divisional Water Testing Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. |  |  | VCH/001059/2020-2021 | 1115/W | 30/03/2021 | 0 | LABARD INSTRUCHEM PVT. LTD. | 8.06 | 0 | 0
588 | Tamluk Division |  | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in TAMALDA piped water supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. |  |  | ORD/000132/2025-2026 | 145/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0
589 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Tamalda PWSS Block -Egra-I in the District of Purba Medinipur. |  |  | ORD/000235/2020-2021 | 2866/TD | 10/02/2021 | 25 | AJIT KUMAR SOM | 44.61 | 0 | 100
590 | Tamluk Division |  | Laying distribution system of Tamalda & its adjoining moujas Water Supply Scheme to support the ongoing FHTC Connection within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000457/2021-2022 | 1930/TD | 28/02/2022 | 15 | SOM CONSTRUCTION | 4.84 | 4.84 | 100
591 | Tamluk Division |  | Functional Household Tap Connection for completion of 100 percent house hold coverage at Tamalda & Sonapada Mouza of Tamalda PWSS, GP-Panchroll, Block - Egra - I under Digha Sub-Division, within Tamluk Division, P.H.E.Dte. Purba Medinipur. |  |  | ORD/001217/2023-2024 | 981/TD | 13/03/2024 | 348 | SAURAV HAZRA | 3.16 | 0 | 100
592 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000436/2021-2022 | BP-2021-22-149 | 09/11/2021 | 0 | AJIT KUMAR SOM | 8.58 | 0 | 0
593 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Tamalda Piped Water Supply Scheme |  |  | VCH/001121/2020-2021 |  | 15/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0
594 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001261/2020-2021 | 1089/W | 30/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0
595 | Tamluk Division |  | Retrofitting to accommodate FHTC (387 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II )_within Rankinipur JL-135(P) - (Rankinipur Uttar) &Gholepukuria JL-134(P) - (Madhya Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-A |  |  | ORD/000182/2020-2021 | 2748/TD | 27/01/2021 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.48 | 0 | 100
596 | Tamluk Division |  | Retrofitting to accommodate FHTC (397 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur - (Rankinipur Purba) JL-135(P) &Gholepukuria - (Gholepukuria Purba Uttar Para) JL-134(P) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B |  |  | ORD/000183/2020-2021 | 2749/TD | 27/01/2021 | 20 | ADHIKARY CONSTRUCTION | 20.1 | 0 | 100
597 | Tamluk Division |  | Retrofitting to accommodate FHTC (424 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Paschim) & GholepukuriaJL-134(P) - (Gholepukuria Dakshin Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-C |  |  | ORD/000184/2020-2021 | 2750/TD | 27/01/2021 | 20 | FARID UDDIN AHMED | 21.27 | 4.5 | 100
598 | Tamluk Division |  | Retrofitting to accommodate FHTC (395 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Dakshin) & Gholepukuria JL-134(P) - (Gholepukuria Uttar Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-D |  |  | ORD/000185/2020-2021 | 2751/TD | 27/01/2021 | 20 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 20.37 | 11.38 | 100
599 | Tamluk Division |  | Retrofitting to accommodate FHTC (121 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Gholepukuria JL-134(P) - (Gholepukuria Dakshin Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-E |  |  | ORD/000186/2020-2021 | 2752/TD | 27/01/2021 | 20 | PULAK KUMAR SAMANTA | 6.33 | 0 | 100
600 | Tamluk Division |  | Retrofitting to accomodate FHTC 121 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-E) |  |  | VCH/000130/2021-2022 | BP-2021-22-49 | 29/07/2021 | 0 | PULAK KUMAR SAMANTA | 0.97 | 0 | 0
601 | Tamluk Division |  | Retrofitting to accomodate FHTC 387 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000191/2021-2022 | BP-2021-22-56 | 13/08/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.11 | 0 | 0
602 | Tamluk Division |  | Retrofitting to accomodate FHTC 397 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000354/2021-2022 | BP-2021-22-116 | 05/10/2021 | 0 | ADHIKARY CONSTRUCTION | 9.55 | 0 | 0
603 | Tamluk Division |  | Retrofitting to accomodate FHTC 424 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000416/2021-2022 | BP-2021-22-146 | 03/11/2021 | 0 | FARID UDDIN AHMED | 16.5 | 0 | 0
604 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001103/2020-2021 | 1101/W | 30/03/2021 | 0 | ADHIKARY CONSTRUCTION | 10.54 | 0 | 0
605 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001104/2020-2021 | 1094/W | 30/03/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.1 | 0 | 0
606 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001106/2020-2021 | 1114/W | 30/03/2021 | 0 | PULAK KUMAR SAMANTA | 5.34 | 0 | 0
607 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001133/2020-2021 | 1100/W | 30/03/2021 | 0 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 8.89 | 0 | 0
608 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- A (Mouza-Guria JL-45.) |  |  | ORD/000176/2020-2021 | 2742/TD | 27/01/2021 | 20 | MADAN MOHAN MAITY | 9.51 | 4.07 | 100
609 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- B (Mouza-GuriaJL-45). |  |  | ORD/000177/2020-2021 | 2743/TD | 27/01/2021 | 20 | G. S. CONSTRUCTION | 9.5 | 0 | 100
610 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- C (Mouza-Guria JL-45). |  |  | ORD/000178/2020-2021 | 2744/TD | 27/01/2021 | 20 | SUDIP MANNA | 9.5 | 1.78 | 100
611 | Tamluk Division |  | Functional Household Tap connection to the 531 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- D (Mouza-Betalbasan & Ghatual (282+249= 531 nos), JL-47 & 50. |  |  | ORD/000179/2020-2021 | 2745/TD | 27/01/2021 | 25 | BHOLANATH DEY | 25.08 | 4.72 | 100
612 | Tamluk Division |  | Functional Household Tap connection to the 140 nos. Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- E (Mouza-Narayanpur,JL-46). |  |  | ORD/000180/2020-2021 | 2746/TD | 27/01/2021 | 20 | SK. NUR ISLAM | 6.64 | 0.34 | 100
613 | Tamluk Division |  | Functional Household Tap connection to the 300 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- F (Mouza-Narayanpur,JL-46). |  |  | ORD/000181/2020-2021 | 2747/TD | 27/01/2021 | 20 | MAA KALI CONSTRUCTION | 14.3 | 2.16 | 100
614 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1107/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
615 | Tamluk Division |  | Functional Household Tap Connection for Guria W/S Scheme within Nandakumar Block Tamluk Division, PHE Dte. |  |  | VCH/001063/2020-2021 | 1106/W | 30/03/2021 | 0 | G. S. CONSTRUCTION | 9.28 | 0 | 0
616 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001110/2020-2021 | 1112/W | 30/03/2021 | 0 | SUDIP MANNA | 8.61 | 0 | 0
617 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001111/2020-2021 | 1098/W | 30/03/2021 | 0 | MAA KALI CONSTRUCTION | 12.11 | 0 | 0
618 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001112/2020-2021 | 1108/W | 30/03/2021 | 0 | SK. NUR ISLAM | 6.01 | 0 | 0
619 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001134/2020-2021 |  | 17/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0
620 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001135/2020-2021 | 1096/W | 30/03/2021 | 0 | BHOLANATH DEY | 22.75 | 0 | 0
621 | Tamluk Division |  | Retrofitting to accomodate FHTC 200 Nos. connection under JJM Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/001259/2020-2021 | 1105/W | 30/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0
622 | Tamluk Division |  | valve operator (one no) in head work site at Paya(Mahaprabhu) & its adjoining mouzas water supply scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division PHE Dte. (For 12 months or 365 days) w.e.f from 01.09.2024 |  |  | ORD/000248/2024-2025 | 873/DSD | 27/08/2024 | 365 | MAITY CONSTRUCTION | 2.14 | 0 | 100
623 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Paya(Mahaprabhu) PWSS Block- Ramnagar-I in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000280/2020-2021 | 2996/TD | 25/02/2021 | 30 | MAITY CONSTRUCTION | 99.11 | 72.39 | 100
624 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Paya (Mahaprabhu) W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001108/2020-2021 | 1087/W | 30/03/2021 | 0 | MAITY CONSTRUCTION | 24.87 | 0 | 0
625 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bheribaranga PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000044/2021-2022 | 694/TD | 10/09/2021 | 60 | DAS CONSTRUCTION | 97.49 | 60.11 | 80
626 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bheribharanga PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000414/2021-2022 | BP-2021-22-144 | 03/11/2021 | 0 | DAS CONSTRUCTION | 37.37 | 0 | 0
627 | Tamluk Division |  | Retrofitting to accomodate FHTC (1100 nos.) under JJM in Alinan -I & II PWSS(Balance Work) Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District . (Phase- II). |  |  | ORD/000002/2021-2022 | 692/TD | 10/09/2021 | 45 | TAPAS SANTRA | 58.58 | 0 | 100
628 | Tamluk Division |  | Retrofitting to accomodate FHTC (1100 Nos.) under JJM in Alinan Zone - I & II PWSS (Balance Work) Block - Sahid Matangini under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000357/2021-2022 | BP-2021-22-107 | 05/10/2021 | 0 | TAPAS SANTRA | 56.73 | 0 | 0
629 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 300 nos] under JJM in Uttar Khasda PWSS [Kulbaria(119,part),DakshinKhasda(120,part), Harichak(121,part),Akgerya(123,part), Palta Beria(128,part), Paschim Teghari(129,part), Tedubi(184,part), Uttar Khasda(185,part), Ulu Bere(186,part), Naraharichak(187,part), Dhangan(188,part),Paschim Jagannathchak(189,part), Rautara(193,part)] within Contai-I Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000270/2020-2021 | 2923/TD | 22/02/2021 | 20 | SRIMANTA KUMAR MAITY | 26.25 | 0 | 100
630 | Tamluk Division |  | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000254/2021-2022 |  | 24/08/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0
631 | Tamluk Division |  | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000312/2021-2022 | BP-2021-22-71 | 04/09/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0
632 | Tamluk Division | Contai Sub-Division | Laying Distribution pipe line to accommodate FHTC with allied works for Retrofitting in Baharchandberya Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000227/2022-2023 | 969/TD | 03/08/2022 | 786 | DIPAK KUMAR BAKLY | 92.52 | 71.22 | 70
633 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0.5 | 100
634 | Tamluk Division | Contai Sub-Division | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 350 Cum at Contai-II Block within Baharchandberya W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000253/2021-2022 | 516 / CSD | 29/11/2021 | 21 | LAKSHMI NARAYAN ENTERPRISE | 0.55 | 0 | 0
635 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Baharchandberya PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000343/2024-2025 | 3328/TD | 22/10/2024 | 40 | S R TRADING CORPORATION | 12.55 | 0 | 0
636 | Tamluk Division | Contai Sub-Division | Land Development for approach road for entry of Rig Machine for Replacement of 2nd Tube Well of Baharchandberya W/S Scheme within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000609/2023-2024 | 1583/CSD | 16/08/2023 | 15 | ABHIJIT BERA | 0.49 | 0.48 | 100
637 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002025/2022-2023 | 884/W/MMD | 27/03/2023 | 180 | UTTAM KUMAR CHATTERJEE | 12.39 | 0 | 0
638 | Tamluk Division |  | Retrofitting to accommodate FHTC (335 Nos.) under JJM in Manikpur PWSS & Jalpai Part-II PWSS (Balance Part) Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000153/2021-2022 | 1124/TD | 22/11/2021 | 20 | SANKHA ENTERPRISE | 36.47 | 26.1 | 100
639 | Tamluk Division |  | Work order for laying of left out HDPE pipe line at Manikpur & Champainagar mouja for Manikpur & its Adjoining Mouzas W/S Scheme within Nandigram - I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000297/2022-2023 | 599/HSD | 30/08/2022 | 10 | SANKHA ENTERPRISE | 2.46 | 2.46 | 100
640 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of ground water based Bahichberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir 900 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000003/2022-2023 | 56/TD | 05/04/2022 | 922 | JAYANTA KUMAR MONDAL | 952.26 | 917.45 | 99
641 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Baichberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000104/2022-2023 | 480/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 0 | 0
642 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bahichberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000135/2023-2024 | 270/TD | 20/04/2023 | 630 | S.K. MONDAL | 29.92 | 4.51 | 80
643 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bainchberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000159/2021-2022 | 1163/TD | 01/12/2021 | 7 | HORIZEN | 9.35 | 9.23 | 100
644 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection of 400 DI(K 7)Distribution pipe line and 300 mm dia DI(K 9) pipe line including supply of DI specials for to OHR under Bainchberia PWSS with in Nandakumar Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000277/2024-2025 | 2905/TD | 10/09/2024 | 219 | SOUVIK GHOSAL | 9.33 | 0 | 100
645 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe line ( 3991.00 mtr ) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000289/2024-2025 | 3054/TD | 19/09/2024 | 25 | HYDROTECH ASSOCIATES | 17.58 | 0 | 0
646 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe line ( 4227.0 mtr) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000290/2024-2025 | 3055/TD | 19/09/2024 | 173 | MISHRA ENTERPRISE | 19.13 | 0 | 100
647 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000323/2022-2023 | 1232/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.61 | 3.61 | 100
648 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000324/2022-2023 | 1231/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.14 | 3.14 | 100
649 | Tamluk Division | Tamluk Sadar Sub-Division | Dismentling of existing damaged godown at Bainchberia and its adj mouzas Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000569/2024-2025 | 195/TSD | 22/01/2025 | 545 | SUDIP MANNA | 2.12 | 0 | 0
650 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000615/2022-2023 | 79/TSD | 13/01/2023 | 690 | J.S. CONSTRUCTION | 2.61 | 0 | 100
651 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing Vehicle No-WB-29F-4919 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 07.08.2025 to 06.02.2026.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000404/2025-2026 | 2671/TSD | 06/08/2025 | 184 | KHOKAN SAMANTA | 0.87 | 0 | 10
652 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bahichberia Water Supply Scheme under Tamluk Sub Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000632/2022-2023 | 2482/TD | 16/01/2023 | 30 | SK. NUR ISLAM | 4.85 | 4.85 | 25
653 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000639/2022-2023 | 2483/TD | 16/01/2023 | 30 | S.K. MONDAL | 3.53 | 3.52 | 0
654 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 01.11.2024 upto 31.10.2025 i.e 12 (Twelve) Months. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000657/2024-2025 | 1636/TSD | 30/10/2024 | 239 | TAPAS SANTRA | 1.14 | 0.8 | 0
655 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling work for entrance approach & 3rd tube well site of Bahichberia Water Supply Scheme for augmentation of Bahichberia pwss under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000746/2022-2023 | 1086/TSD | 22/08/2022 | 15 | J.S. CONSTRUCTION | 1.72 | 1.54 | 100
656 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of pump houseof 4th tube well , laying of /150 mm dia DI (K9) rising main in between OHR to T/W-4, T/W-3, T/W-3 to OHR under Bainchberia PWSS under Tamluk Sub Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001243/2023-2024 | 1081/TD | 16/03/2024 | 415 | A. R. CONSTRUCTION | 13.71 | 0 | 96
657 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000012/2022-2023 | 84/TD | 08/04/2022 | 0 | Resource Division | 53.93 | 0 | 0
658 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000034/2022-2023 | 650/TD | 27/06/2022 | 0 | Resource Division | 39.34 | 0 | 0
659 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000055/2024-2025 | 2002/TD | 14/06/2024 | 0 | Resource Division | 2.64 | 0 | 0
660 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000202/2023-2024 | 1103/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
661 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERYA W/S SCH (REPLACEMENT TW-II) NANDAKUMAR BLOCK PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000010/2022-2023 | 433/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 13.86 | 12.78 | 100
662 | Central Drilling | Tamluk Sadar Sub-Division | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.72 | 0
663 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAICHBERIA W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000269/2022-2023 | 1231/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.95 | 16.13 | 100
664 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries at Baichberia , Nandakumar Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000529/2022-2023 | 1229/CDD | 16/11/2022 | 390 | MENAKA ENTERPRISE | 18.61 | 15.55 | 100
665 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Baichberya PWSS Tube Well- III (Ref. ID - 203911567) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00159/2022-2023 | BP-2022-23-129 | 13/03/2023 | 0 | WBSEDCL | 8.28 | 0 | 0
666 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Qoutation bill for T/W -IV of Baichberia water supply scheme | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03565/2023-2024 | BP-2023-24-608 | 07/02/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
667 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000046/2023-2024 | 1219/W/MMD | 25/04/2023 | 860 | BHABANI PRASAD MANNA | 27.19 | 12.79 | 50
668 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-II under Baichberia w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000069/2024-2025 | 570/HESD | 27/06/2024 | 7 | RITESH ENTERPRISE | 0.26 | 0.07 | 90
669 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well - II of Baichberiya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001137/2022-2023 | 2118/W/MMD | 28/11/2022 | 458 | RITESH ENTERPRISE | 12.17 | 11.3 | 90
670 | Tamluk Division | Tamluk Sadar Sub-Division | Quotation money payment to WBSEDCL for GobindanagarZone-II Water Supply Scheme of Tube Well No. - IV | Assistant Engineer | Junior Engineer | BILL/00599/2023-2024 | BP-2023-24-324 | 29/08/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
671 | Tamluk Division | Tamluk Sadar Sub-Division | Charges for entry of Household data in J.J.M. website along with House hold Addhar detai1s and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. The work should be taken up as per direction of Engineer-In-Charge. N.B. This item should be exclusively used for IMIS entry through J.J.M. | Assistant Engineer | Junior Engineer | ORD/000029/2022-2023 | 90/TD | 11/04/2022 | 30 | MISHRA ENTERPRISE | 4.85 | 4.85 | 100
672 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 424/TD | 27/05/2022 | 15 | TARUN KOLEY | 4.32 | 4.32 | 100
673 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000089/2022-2023 | 425/TD | 27/05/2022 | 15 | TARUN KOLEY | 3.65 | 3.65 | 100
674 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gobindanagar (Zone-I & Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000183/2021-2022 | 1192/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 9.26 | 9.26 | 100
675 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, and providing of FHTC for Rejuvenation of GOBINDANAGAR & its adjoining moujas Water Supply Scheme within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000409/2021-2022 | 1899/TD | 23/02/2022 | 180 | TARUN KOLEY | 554.16 | 519.2 | 100
676 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 62.84 | 100
677 | Tamluk Division | Tamluk Sadar Sub-Division | Land development and making approach road of 3 (three) nos. Boosting Tube Well site at Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000729/2023-2024 | 2980/TD | 29/11/2023 | 20 | M/S. S. A. CONSTRUCTION | 5.11 | 0 | 0
678 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2021-2022 | 1259/TD | 13/12/2021 | 0 | Resource Division | 4.42 | 0 | 0
679 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000027/2022-2023 | 417/TD | 25/05/2022 | 0 | Resource Division | 2.19 | 0 | 0
680 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000049/2021-2022 | 1954/TD | 04/03/2022 | 0 | Resource Division | 23.84 | 0 | 0
681 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR GOBINDANAGAR W/S SCH (ZONE-I, TW-III), PANSKURA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000410/2022-2023 | 2119/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 15.08 | 0
682 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Gobindanagar W/S Scheme (Z-II) panskura block under purba medinipur district, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 2112/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 13.68 | 0
683 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
684 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 825.55 | 94
685 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 2901/TD | 21/11/2023 | 0 | Resource Division | 13.69 | 0 | 0
686 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money at 3rd Pump House of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00192/2023-2024 | BP-2023-24-95 | 07/06/2023 | 0 | WBSEDCL | 1.74 | 0 | 0
687 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with sand filling and jhama -metal consolidation of link road to NH-41 along the bank of Sankarara Khal Road due to cutting of hard shoulder for laying water pipeliones by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00230/2023-2024 | BP-2023-24-115 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.05 | 0 | 0
688 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. - 2 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00366/2022-2023 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
689 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. ¿ 1 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00367/2022-2023 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0
690 | Tamluk Division | Tamluk Sadar Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division, P.W.(Roads) Directorate. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00697/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.05 | 0 | 0
691 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of Souther Eastern Railway Track for Application ID SER-KGP-2021-WL-01 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01199/2023-2024 | BP-2023-24-567 | 07/11/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.22 | 0 | 0
692 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Chapbasan Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000133/2022-2023 | 692/TD | 27/06/2022 | 180 | TARUN KOLEY | 724.76 | 531.29 | 75
693 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000157/2021-2022 | 1161/TD | 01/12/2021 | 7 | HORIZEN | 9.49 | 9.05 | 100
694 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2022 to 31.12.2022. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000330/2022-2023 | 783/TSD | 29/06/2022 | 183 | KRISHNA MONDAL | 1.09 | 1.97 | 100
695 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & Renovation work of Boundary wall, Staff Quarter, Godown & approach Road at Chapbassan Store of Tamluk Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000330/2025-2026 | 1725/TD | 30/06/2025 | 45 | GOUTAM DEY | 44.99 | 0 | 0
696 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000375/2022-2023 | 1339/TD | 16/09/2022 | 25 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.77 | 100
697 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000376/2022-2023 | 1340/TD | 16/09/2022 | 25 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.98 | 100
698 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2453 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.07.2024 to 31.12.2024.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000245/2024-2025 | 949/TSD | 28/06/2024 | 183 | DEBNATH MAITY | 0.87 | 2.31 | 0
699 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) (Bharat stage-IV) bearing vehicle no- WB-29B-2278 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte. under Tamluk Division for the period from 01.08.2022 to30.09.2022. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000255/2022-2023 | 991/TSD | 27/07/2022 | 62 | DEBNATH MAITY | 0.19 | 0.4 | 100
700 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000377/2022-2023 | 1341/TD | 16/09/2022 | 25 | SWAPAN KUMAR MAITY | 4.55 | 1.93 | 100
701 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division ,PHE Dte. under Tamluk Division for the period from 01.10.2022 to 30.09.2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000501/2022-2023 | 1297/TSD | 29/09/2022 | 239 | DEBNATH MAITY | 1.14 | 4.69 | 100
702 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 1(one) nos M.S. Structure over irrigation canal to support 200 mm dia. DI K9 Rising Main under Chapbasan Water Supply Scheme at Pipulberia under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000528/2024-2025 | 38/TSD | 08/01/2025 | 20 | PULAK KUMAR SAMANTA | 1.58 | 0 | 100
703 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one Diesel motor cabs & Maxi cab with Engine capacity more than 2000 C.C. with (Air Condition) on monthly hiring (Per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2023 to 31.12.2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000559/2023-2024 | 913/TSD | 30/06/2023 | 184 | KRISHNA MONDAL | 1.09 | 2.4 | 100
704 | Tamluk Division | Tamluk Sadar Sub-Division | New construction of Boundaty wall at Chapbasan Water Supply Scheme 3rd (52 mtr) & 4th(47 mtr) T/W site under Tamluk Sub-Division P.H.E. Dte. of Tamluk Division, P.H.E.Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000617/2024-2025 | 674/TD | 03/03/2025 | 360 | SUDIP MANNA | 9.68 | 0 | 0
705 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main From 3rd Tube Well & 4 th Tube Well Site to O.H.R. Site and other allied works at Chapbasan Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000666/2022-2023 | 2351/TD | 10/01/2023 | 330 | PULAK KUMAR SAMANTA | 9.84 | 0 | 100
706 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.01.2023 to 30.06.2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000753/2022-2023 | 1675/TSD | 30/12/2022 | 182 | KRISHNA MONDAL | 1.09 | 2.39 | 100
707 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000005/2022-2023 | 100/TD | 11/04/2022 | 0 | Resource Division | 56.47 | 0 | 0
708 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte under Tamluk Division for the period from 01.04.2024 to 30.06.2024. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001287/2023-2024 | 551/TSD | 28/03/2024 | 50 | DEBNATH MAITY | 0.24 | 1.13 | 100
709 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000065/2021-2022 | 643/TD | 27/06/2022 | 0 | Resource Division | 44.53 | 0 | 0
710 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000221/2023-2024 | 1120/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
711 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAPBASAN W/S SCHEME (TW-IV), TAMLUK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000021/2022-2023 | 386/ CDD | 18/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 13.31 | 100
712 | Central Drilling | Tamluk Sadar Sub-Division | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTRS) FOR IIEST (TW-I), MELLOK, HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000120/2022-2023 | 400/CDD | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 10.05 | 0 | 0
713 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN PWSS (TW-IV) BLOCK- TAMLUK UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000172/2022-2023 | 125/CMSD-I | 17/05/2022 | 7 | PADMA ENGINEERING & CO. | 0.53 | 0.15 | 100
714 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE JOHN/1000 UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000200/2021-2022 | 1016/CDD | 15/12/2021 | 30 | MENAKA ENTERPRISE | 13.81 | 12.72 | 100
715 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN BLOCK TAMLUK UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000246/2021-2022 | 66/CMSD-I (D) | 22/03/2022 | 7 | MENAKA ENTERPRISE | 0.84 | 0.84 | 100
716 | Central Drilling | Tamluk Sadar Sub-Division | ADDITIONAL WORK FOR CONSTRUCTION OF TUBE WELL AT CHAPBASAN, BLOCK - TAMLUK BY UTILIZING SKILLED DRILLING CREW & DEPRTMENTAL MACHINERIES UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000247/2021-2022 | 69/CMSD-I (D) | 29/03/2022 | 7 | MENAKA ENTERPRISE | 0.4 | 0.4 | 100
717 | Central Drilling | Tamluk Sadar Sub-Division | CONTINUATION OF MAXI CAB (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE SEMC-II, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000367/2019-2020 | 26/ S&WSD | 18/03/2020 | 15 | MITALI DAS | 0.29 | 0.84 | 100
718 | Central Drilling | Tamluk Sadar Sub-Division | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTR) FOR IIEST (TW-I), SHIBPUR, HOWRAH DISTRICT BY UTILISING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000373/2022-2023 | 400/CDD (P-II) | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 10.05 | 5.2 | 0
719 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCH (TW-I) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000394/2022-2023 | 1076/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 0.72 | 0
720 | Central Drilling | Tamluk Sadar Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT HARIPAL (Z-I) PWSS, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000404/2022-2023 | 574/CMSD-I (D) (P-II) | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.7 | 0.64 | 0
721 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Gourangapur/Chapbasan PWSS Tube Well-I in connection Tamluk CCC (2004170186) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00054/2022-2023 |  | 09/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0
722 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Chapbasan PWSS Tube Well-II in connection Tamluk CCC (2004150121) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00055/2022-2023 |  | 09/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
723 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme Block - Tamluk under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001468/2022-2023 | 206/W/MMD | 10/02/2023 | 180 | UNITED TRADERS | 27.3 | 26.8 | 60
724 | Tamluk Division | Digha Sub-Division | Repaire of Pump House , Boundary Wall construction of boundary wall & Land development approch road under JJM with allied work for Madhabpur (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2023-2024 | 1023/TD | 07/06/2023 | 40 | KAMAL KUMAR ROY | 41.68 | 0 | 0
725 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2022-2023 | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 0 | 100
726 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000553/2022-2023 | 2183/TD | 20/12/2022 | 180 | GUPTA ENTERPRISE. | 638.56 | 82.65 | 15
727 | Tamluk Division | Digha Sub-Division | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Madhakhali Zone-I & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000587/2023-2024 | 2189/TD | 01/09/2023 | 45 | SWARUPANANDA DAS | 95.53 | 93.29 | 100
728 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline to accommodate FHTC for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000604/2023-2024 | 2197/TD | 01/09/2023 | 25 | DEBABRATA DAS | 16.53 | 0 | 0
729 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000111/2022-2023 | 1665/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0
730 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000283/2022-2023 | 2636/TD | 02/02/2023 | 0 | Resource Division | 18.68 | 0 | 0
731 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000077/2023-2024 | 1279/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 0 | 0
732 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Electric Quotation money of Dakshin Gumai Water Supply Scheme for Tube Well No.- III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00434/2023-2024 | BP-2023-24-218 | 02/08/2023 | 0 | WBSEDCL | 3.12 | 0 | 0
733 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000156/2021-2022 | 1160/TD | 01/12/2021 | 7 | HORIZEN | 8.24 | 8.12 | 100
734 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Rising Mains for Agumentation of Dakshin Gumai Water Supply Scheme under Nandakumar Block, under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000242/2024-2025 | 2682/TD | 22/08/2024 | 125 | GHOSH ENTERPRISE | 10.8 | 0 | 100
735 | Tamluk Division | Tamluk Sadar Sub-Division | Left out FHTC 402 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk SubDivision of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000279/2024-2025 | 2895/TD | 10/09/2024 | 360 | ARABINDA GHOSH | 91.84 | 0 | 56
736 | Tamluk Division | Tamluk Sadar Sub-Division | Dismantling of existing OHR (Capacity 61550 Gallons or 341000 Ltr.) at Head work site of Dakshin Gumai Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000376/2023-2024 | 1029/TD | 07/06/2023 | 45 | BISWAJIT BAG | 9.42 | 9.42 | 100
737 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Distribution pipe line to accommodate FHTC (5547 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000387/2022-2023 | 1420/TD | 26/09/2022 | 979 | ARABINDA GHOSH | 944.7 | 805.94 | 85
738 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st & 2nd tube well site of Dakshin Gumai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000421/2024-2025 | 3477/TD | 06/11/2024 | 30 | GLOBAL TRADE | 4.06 | 0 | 100
739 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 3.6 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for water supply scheme with Boundary Wall (as per Deptt. drawing) at 3rd Tube well site of Dakshin Gumai Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000732/2023-2024 | 2983/TD | 29/11/2023 | 45 | BHOWMIK & SONS | 11.41 | 8.07 | 72
740 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000043/2022-2023 | 1016/TD | 08/08/2022 | 0 | Resource Division | 232.04 | 0 | 0
741 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000073/2022-2023 | 1257/TD | 12/09/2022 | 0 | Resource Division | 34.11 | 0 | 0
742 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000208/2023-2024 | 1108/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
743 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTALMACHINERIES FOR DAKSHIN GUMAI W/S SCHEME (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000397/2022-2023 | 2118/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 18.26 | 15.62 | 0
744 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxary Taxi) (standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Executive Engineer, Tamluk Division, PHE Dte. under Tamluk Division for the period from 12 (twelve) months, w.e.f. 01/11/2022 to 31/10/2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001001/2022-2023 | 1344/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 2.4 | 75
745 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme Block - Nandakumar under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001964/2022-2023 | 863/W/MMD | 27/03/2023 | 180 | PRANAB KUMAR DAS | 13.47 | 0 | 70
746 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004720948/QUOT/03 DT. 07-05-2024 Application NO- 2004720948 Application type-New connection Consumer Id- 204298864 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00444/2024-2025 | BP-2024-25-171 | 07/06/2024 | 0 | WBSEDCL | 36.92 | 0 | 0
747 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 294.07 | 40
748 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000164/2023-2024 | 118/TD | 05/01/2024 | 0 | Resource Division | 7.8 | 0 | 0
749 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000275/2022-2023 | 2699/TD | 06/02/2023 | 0 | Resource Division | 20.82 | 0 | 0
750 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920/QUOT/03 DT. 17-05-2024 Application NO- LY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920 Application type-New connection Consumer Id- 204309716 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01096/2024-2025 | BP-2024-25-225 | 31/05/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
751 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001638/2022-2023 | 518/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 8.42 | 85
752 | Tamluk Division | Haldia Sub-Division | Land Development work at Head work site of Jaynagar Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000006/2025-2026 | 1082/TD | 07/04/2025 | 315 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 3.29 | 0 | 0
753 | Tamluk Division | Haldia Sub-Division | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 1st & 2nd Tube well of Jaynagar Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000142/2024-2025 | 2015/TD | 14/06/2024 | 232 | PRANTIK DRILLING AGENCY | 30.07 | 7.48 | 100
754 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000245/2023-2024 | 524/TD | 11/05/2023 | 1044 | ZENITH CONSTRUCTION | 141.93 | 45.73 | 30
755 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000324/2023-2024 | 686/TD | 23/05/2023 | 1130 | RELIABLE CONSTRUCTIONS | 172.01 | 21.99 | 20
756 | Tamluk Division | Haldia Sub-Division | Construction of Box Culvert (5.00Mtr. X 3.50Mtr.) at 2nd Tube Well site of Jaynagar W/S Scheme within Sutahata Dev. Block under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000721/2023-2024 | 2943/TD | 23/11/2023 | 600 | M/S SOURAV MAHAPATRA | 5.33 | 3.77 | 50
757 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000791/2022-2023 | 3042/TD | 27/02/2023 | 1029 | RELIABLE CONSTRUCTIONS | 90.11 | 51.54 | 68
758 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (774 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000792/2022-2023 | 3043/TD | 27/02/2023 | 951 | ZENITH CONSTRUCTION | 89.68 | 45.99 | 55
759 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) [Jaynagar PWSS, Mohanpur PWSS, Erekhali PWSS & Hariballavpur PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000829/2023-2024 | 617/HSD, | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100
760 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jaynagar PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001046/2023-2024 | 376/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
761 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000163/2022-2023 | 2473/TD | 16/01/2023 | 0 | Resource Division | 30.03 | 0 | 0
762 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000190/2023-2024 | 639/W | 20/02/2024 | 0 | Resource Division | 13.39 | 0 | 0
763 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-II of Joynagar w/s scheme,Block-Sutahata under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818887 Application type-new connection Reference ID-204355766 Quotation Date-12/7/2024 Quotation Due Date-14/7/2025 Contract Demand-8344 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01695/2024-2025 | BP-2024-25-495 | 29/07/2024 | 0 | WBSEDCL | 4.61 | 0 | 0
764 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Joynagar w/s scheme Block-sutahata in the Dist. of Purba Medinipur under MMD ,PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004839280 Application type-new connection Reference ID-204366525 Quotation Date-26/07/2024 Quotation due Date-28/07/2025 Contract Demand-8344W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01858/2024-2025 | C082408702219 | 07/08/2024 | 0 | WBSEDCL | 7.89 | 0 | 0
765 | Tamluk Division | Haldia Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000895/2022-2023 | 3345/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.84 | 0 | 0
766 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAYNAGAR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001586/2022-2023 | 469/W/MMD | 20/03/2023 | 1183 | BHABANI PRASAD MANNA | 23.7 | 0 | 35
767 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges (SER-KGP-2024-WL-47) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00135/2024-2025 | BP-2024-25-78 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0
768 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility(SER-KGP-2024-WL-48) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00136/2024-2025 | BP-2024-25-79 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.25 | 0 | 0
769 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
770 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000633/2022-2023 | 2314/TD | 05/01/2023 | 995 | DAS CONSTRUCTION | 456.2 | 0 | 0
771 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000670/2022-2023 | 2311/TD | 05/01/2023 | 983 | DAS CONSTRUCTION | 230.47 | 0 | 0
772 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000025/2023-2024 | 610/TD | 17/05/2023 | 0 | Resource Division | 23.76 | 0 | 0
773 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000104/2022-2023 | 1660/TD | 03/11/2022 | 0 | Resource Division | 143.41 | 0 | 0
774 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-I, Part-A, Zone-I (Ref. ID-204050258) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01686/2023-2024 | BP-2023-24-164 | 04/08/2023 | 0 | WBSEDCL | 2.34 | 0 | 0
775 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-II, Part-A, Zone-I (Ref. ID-204050190) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01687/2023-2024 | BP-2023-24-163 | 04/08/2023 | 0 | WBSEDCL | 2.48 | 0 | 0
776 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A),under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000158/2023-2024 | 1393/W/MMD | 01/06/2023 | 180 | P.K.ENGINEERING | 27.18 | 10.43 | 30
777 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Baghadanri, JL No. - 246, Plot No. -495/1489) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000036/2022-2023 | 135/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 11.83 | 100
778 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1st Tubewell of Head Works site (Mouza - Baghadanri, JL No. - 246, Plot No. - 1029) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000037/2022-2023 | 136/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 11.76 | 100
779 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate 1933 nos FHTC with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000079/2022-2023 | 384/TD | 20/05/2022 | 45 | DAS ENTERPRISE | 223.21 | 223.66 | 98
780 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000099/2022-2023 | 475/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
781 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate 1900 nos FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000199/2022-2023 | 817/TD | 12/07/2022 | 180 | DAS ENTERPRISE | 477.83 | 472.5 | 98
782 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000243/2022-2023 | 1003/TD | 08/08/2022 | 180 | DAS ENTERPRISE | 512.49 | 431.94 | 90
783 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site at Madhakhali Zone-I Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000269/2022-2023 | 1092/TD | 25/08/2022 | 60 | SWARUPANANDA DAS | 6.34 | 0 | 100
784 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW (Head Work) site at Madhakhali Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000270/2022-2023 | 1093/TD | 25/08/2022 | 60 | BIBEKANANDA DAS | 6.63 | 0 | 100
785 | Tamluk Division | Contai Sub-Division | Land Development at Head Work Site of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000399/2023-2024 | 1097/CSD | 07/06/2023 | 15 | BIBEKANANDA DAS | 0.97 | 0.97 | 100
786 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000402/2022-2023 | 1178/TD | 05/09/2022 | 840 | SWARUPANANDA DAS | 3.81 | 0 | 100
787 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2022-2023 | 1177/TD | 05/09/2022 | 60 | PARTHA CONSTRUCTION | 3.81 | 3.13 | 100
788 | Tamluk Division | Contai Sub-Division | i) Laying Rising main and other allied works Augmentation of Madhakhali Zone-II W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iv) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000349/2023-2024 | 878/TD | 01/06/2023 | 880 | M/S. PRADIP PRADHAN | 49.33 | 0 | 70
789 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-I W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000404/2022-2023 | 1179/TD | 05/09/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 3.53 | 3.25 | 100
790 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000452/2021-2022 | 1696/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.15 | 4.15 | 100
791 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000453/2021-2022 | 1697/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 3.42 | 3.27 | 100
792 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000489/2022-2023 | 1929/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.64 | 7.64 | 100
793 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000490/2022-2023 | 1930/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.42 | 5.42 | 100
794 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 16.19 | 44
795 | Tamluk Division | Contai Sub-Division | M.S. Structures and allied works under Madhakhali Zone-I Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001178/2023-2024 | 722/TD | 28/02/2024 | 30 | DAS ENTERPRISE | 17.77 | 0 | 0
796 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC pipes with allied works due to uncovered area under of Madhakhali Zone-II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part - A + B + C + D). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001209/2023-2024 | 965/TD | 12/03/2024 | 40 | DAS ENTERPRISE | 100.28 | 82.34 | 90
797 | Tamluk Division | Contai Sub-Division | Land Development at HeadWorks site of Madhakhali Zone-II W/S Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001293/2023-2024 | 375/CSD | 23/02/2024 | 15 | PARTHA CONSTRUCTION | 0.97 | 0.96 | 100
798 | Tamluk Division | Contai Sub-Division | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-I PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Laying Rising main and other allied works Augmentation of Madhakhali Zone-I W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000893/2022-2023 | 3393/TD | 24/03/2023 | 532 | SWARUPANANDA DAS | 19.31 | 0 | 100
799 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2022-2023 | 99/TD | 11/04/2022 | 0 | Resource Division | 53.75 | 0 | 0
800 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000068/2021-2022 | 646/TD | 27/06/2022 | 0 | Resource Division | 23.67 | 0 | 0
801 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000069/2021-2022 | 647/TD | 27/06/2022 | 0 | Resource Division | 20.06 | 0 | 0
802 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCHEME (REPLACEMENT TW, ZONE-I, TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000029/2022-2023 | 385/CDD | 18/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 12.58 | 100
803 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHAKHALI W/S SCH (REPLACEMENT TW, ZONE-I, TW-II) BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHD DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2022-2023 | 432/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 12.83 | 100
804 | Central Drilling | Contai Sub-Division | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000126/2022-2023 | 171/CMSD-I (D) | 06/06/2022 | 7 | MENAKA ENTERPRISE | 0.49 | 0.49 | 100
805 | Central Drilling | Contai Sub-Division | PROVIDING ADDITIONAL TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADHAKHALI PWSS, TW-II, BLOCK-BHAGAWANPUR-II UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2022-2023 | 269/CMSD-II (D) | 31/05/2022 | 10 | MENAKA ENTERPRISE | 0.69 | 0.69 | 100
806 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 20mm x 250 mtrs depth) by utilising Departmental Machineries for Madhakhali W/S scheme(TW-III) ,Bhagawanpur- II Block under Purba Midnapore Dristict ,CDD,P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000447/2022-2023 | 1232/CDD | 16/11/2022 | 30 | MENAKA ENTERPRISE | 19.35 | 15.45 | 100
807 | Midnapore Mechanical | Contai Sub-Division | Electric Quotiaton for Madhakhali Water Supply Scheme Zone-II, T/W-I (Ref. ID-204004293) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00381/2023-2024 | BP-2023-24-67 | 06/06/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
808 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MADHAKHALI Water Supply Scheme Z-II, T/W-II (Ref. ID-204049127 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01632/2023-2024 | BP-2023-24-138 | 27/07/2023 | 0 | WBSEDCL | 2.39 | 0 | 0
809 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of MADHAKHALI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004826940/QUOT/03 DT. 25-07-2024 Application NO- 2004826940 Application type-New connection Consumer Id- 204360840 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01887/2024-2025 | BP-2024-25-551 | 08/08/2024 | 0 | WBSEDCL | 3.35 | 0 | 0
810 | Midnapore Mechanical | Contai Sub-Division | Madhakhali W/S scheme PH-III, Zone-I Application no-2004427213 Ref.-204078346 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03236/2023-2024 | BP-2023-24-501 | 05/01/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
811 | Midnapore Mechanical | Contai Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of AUGUST"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/09920 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/06212/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
812 | Midnapore Mechanical | Contai Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of APRIL"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/09920 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/06215/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.09 | 0 | 0
813 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
814 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I of Zone - I Madhakhali water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001013/2022-2023 | 1862/W/MMD | 22/09/2022 | 120 | M/S B.M. ELECTRICAL | 11.68 | 10.76 | 70
815 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001515/2022-2023 | 359/W/MMD | 09/03/2023 | 180 | AHALYA ENGINEERING WORKS | 27.16 | 25.59 | 20
816 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001516/2022-2023 | 360/W/MMD | 09/03/2023 | 875 | SOUMEN ELECTRIC | 40.74 | 35.76 | 75
817 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
818 | Tamluk Division | Tamluk Sadar Sub-Division | Additional Cost towards mofication of PO to effect NSC, PHE by insatallation of DTR inside the boundary of PHE at Jamitta PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01350/2024-2025 | BP-2024-25-655 | 06/02/2025 | 0 | WBSEDCL | 7.64 | 0 | 0
819 | Tamluk Division | Tamluk Sadar Sub-Division | Additional Quotation Bill For Jamitta W/S Scheme T/W-II Kolaghat CCC Application No=100000125821 Reference ID=860320961 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01655/2024-2025 |  | 24/12/2024 | 0 | WBSEDCL | 7.64 | 0 | 0
820 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (653 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000884/2022-2023 | 3241/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.26 | 31.59 | 80
821 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall, Rising Main & Accommodate FHTC (400 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000885/2022-2023 | 3242/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.03 | 20.77 | 70
822 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (110 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000889/2022-2023 | 3243/TD | 15/03/2023 | 992 | MISHRA ENTERPRISE | 9.53 | 3.16 | 100
823 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & construction of 200 cum OHR (Intze type with pile foundation) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000892/2022-2023 | 3394/TD | 24/03/2023 | 1013 | TAPAS SANTRA | 99.27 | 0 | 70
824 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd. T/W site at Jamitta Water Supply scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001194/2023-2024 | 829/TD | 05/03/2024 | 24 | S.D. CONSTRUCTION | 4.77 | 4.77 | 100
825 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000144/2023-2024 | 123/TD | 05/01/2024 | 0 | Resource Division | 7.16 | 0 | 0
826 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000303/2022-2023 | 3002/TD | 27/02/2023 | 0 | Resource Division | 19.42 | 0 | 0
827 | Central Drilling | Tamluk Sadar Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 59.71 | 11
828 | Central Drilling | Tamluk Sadar Sub-Division | Hiring of Diesel Driven Motor cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000008/2024-2025 | 139/S&WSD | 26/06/2024 | 182 | ASHUTOSH DAS & CO | 0.86 | 0.91 | 0
829 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for New connection Jamitya water supply scheme Tube Well-II. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662461 Ref no.-204260852 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00254/2024-2025 | BP-2024-25-27 | 15/04/2024 | 0 | WBSEDCL | 10.19 | 0 | 0
830 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connection at Jamitya water supply scheme H/W site Kolaghat CCC Block- Kolaghat Application No.-2004803550 Consumer ID.-204346513 Date.-02-07-2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01469/2024-2025 | BP-2024-25-416 | 15/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
831 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jerthan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000474/2024-2025 | 3763/TD | 10/12/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
832 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 406.93 | 51
833 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000013/2025-2026 | 2084/TD | 12/08/2025 | 0 | Resource Division | 13.75 | 0 | 0
834 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000136/2022-2023 | 2420/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0
835 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004812325/QUOT/03/814 DT. 09-07-2024 Application NO- 2004812325 Application type-New connection Consumer Id- 204352202 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01587/2024-2025 | BP-2024-25-450 | 23/07/2024 | 0 | WBSEDCL | 6.77 | 0 | 0
836 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847107/QUOT/03/1183 DT. 13-08-2024 Application NO- 2004847107 Application type-New connection Consumer Id- 204372867 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02121/2024-2025 | C082448274884 | 02/09/2024 | 0 | WBSEDCL | 10.86 | 0 | 0
837 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JERTHAN and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001371/2022-2023 | 2382/W/MMD | 31/12/2022 | 1247 | ECO ENTERPRISE | 25.26 | 13.35 | 40
838 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 212.88 | 30
839 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000032/2024-2025 | 1658/TD | 29/04/2024 | 0 | Resource Division | 14.83 | 0 | 0
840 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000198/2022-2023 | 2454/TD | 16/01/2023 | 0 | Resource Division | 39.75 | 0 | 0
841 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MALLIKPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004971321/QUOT/03 DT. 20-11-2024 Application NO- 2004971321 Application type-New connection Consumer Id- 204450413 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03664/2024-2025 | C012524037997 | 09/01/2025 | 0 | WBSEDCL | 3.66 | 0 | 0
842 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MALIKPUR and ADJOINING MOUJAS, Block Potashpur II District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001327/2022-2023 | 2329/W/MMD | 29/12/2022 | 180 | DAS ENTERPRISE | 23.64 | 0 | 0
843 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (725nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000069/2023-2024 | 139/TD | 10/04/2023 | 720 | S. B. ASSOCIATES | 83.67 | 30.56 | 55
844 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000238/2023-2024 | 499/TD | 11/05/2023 | 844 | BARH CONSTRUCTION | 131.4 | 68.59 | 70
845 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000240/2023-2024 | 503/TD | 11/05/2023 | 590 | SUDIP MANNA | 20.62 | 19.41 | 75
846 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000241/2023-2024 | 504/TD | 11/05/2023 | 594 | TAPAN BERA | 20.43 | 17.71 | 100
847 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (300 nos) and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000285/2023-2024 | 566/TD | 12/05/2023 | 1078 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 167.34 | 65.25 | 70
848 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000813/2022-2023 | 3103/TD | 02/03/2023 | 604 | MUKHERJEE ENTERPRISE | 19.22 | 14.6 | 26
849 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (25 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000814/2022-2023 | 3104/TD | 02/03/2023 | 1188 | MODERN CONSTRUCTION | 10.75 | 3.17 | 36
850 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000815/2022-2023 | 3105/TD | 02/03/2023 | 15 | DEBDUT CONSTRUCTION | 16.69 | 11.31 | 68
851 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000816/2022-2023 | 3106/TD | 02/03/2023 | 665 | TAPAN BERA | 21.6 | 21.23 | 90
852 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000817/2022-2023 | 3107/TD | 02/03/2023 | 662 | ELECTIVA ENTERPRISE | 4.53 | 4.14 | 50
853 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000827/2022-2023 | 3120/TD | 02/03/2023 | 20 | TAPAN BERA | 20.42 | 0 | 0
854 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. approach road at Head work site of Hariballabhpur & its adjoining mouzas Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte.(Length of Approach Road-45mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000863/2023-2024 | 240/TD | 11/01/2024 | 20 | G. S. CONSTRUCTION | 4.78 | 0 | 0
855 | Tamluk Division | Haldia Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000896/2022-2023 | 3346/TD | 22/03/2023 | 25 | PRANTIK DRILLING AGENCY | 30.88 | 30.47 | 100
856 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000162/2022-2023 | 2471/TD | 16/01/2023 | 0 | Resource Division | 18.07 | 0 | 0
857 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000188/2023-2024 | 637/W | 20/02/2024 | 0 | Resource Division | 10.66 | 0 | 0
858 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for new service connection at TW-I & II of Hariballavpur w/s scheme under MMD,PHE, Dte. Block-Sutahata,Chaitanyapur C.C.C Memo No.-2004632082/Quot/03 Date-05/03/2024 Application No.-2004632082 Application Type-New Connection Reference ID-204237950 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04382/2023-2024 | BP-2023-24-826 | 13/03/2024 | 0 | WBSEDCL | 13.11 | 0 | 0
859 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for New Service Connection at PH-II of Hariballavpur pwss,Block-Sutahata, under MMD,PHE Dte. Name of C.C.C.- Chaitanyapur Application no.-2004644794 Application Type-New Connection Quotation Date-15/03/2024 Quotation Due Date-17/03/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04750/2023-2024 | BP-2023-24-920 | 28/03/2024 | 0 | WBSEDCL | 0.28 | 0 | 0
860 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARIBALLABHPUR and ADJOINING MOUJAS, Block Sutahata District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001328/2022-2023 | 2330/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.65 | 0 | 80
861 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1870 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PURBA RADHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2023-2024 | 1090/TD | 08/06/2023 | 754 | DAS ENTERPRISE | 595.42 | 251.29 | 65
862 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Purba Radhapur at Bhagwanpur - I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000585/2024-2025 | 461/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
863 | Tamluk Division | Contai Sub-Division | Wideing of approach road of Head work Site of Purba Radhapur PWSS under Bhagabanpur-I. Block under Contai Sub-Division of Tamluk Division , P.H.E. Dte Dist- Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000739/2023-2024 | 3066/TD | 30/11/2023 | 20 | PARTHA CONSTRUCTION | 3.89 | 3.64 | 100
864 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000165/2023-2024 | 86/TD | 05/01/2024 | 0 | Resource Division | 11.52 | 0 | 0
865 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000197/2022-2023 | 2383/TD | 16/01/2023 | 0 | Resource Division | 47.81 | 0 | 0
866 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835493 Application type-New connection Consumer Id- 204365530 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02118/2024-2025 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 7.35 | 0 | 0
867 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835536 Application type-New connection Consumer Id- 204365524 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02120/2024-2025 | C082448207124 | 02/09/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
868 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA RADHAPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001334/2022-2023 | 2339/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.63 | 0 | 0
869 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
870 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 961 | SANKHA ENTERPRISE | 1144 | 201.16 | 30
871 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000028/2024-2025 | 1635/TD | 18/06/2025 | 0 | Resource Division | 9.75 | 0 | 0
872 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000201/2022-2023 | 2438/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0
873 | Midnapore Mechanical | Contai Sub-Division | Goyalda W/S scheme, TW-II, site tarat(near Tower) application no-2004515995 id-204153075 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03148/2023-2024 | BP-2023-24-456 | 21/12/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
874 | Midnapore Mechanical | Contai Sub-Division | Goyalda W/S scheme, TW-I, site tarat(near swasan) application no-2004515964 id-204153046 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03149/2023-2024 | BP-2023-24-457 | 21/12/2023 | 0 | WBSEDCL | 3.74 | 0 | 0
875 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOYALDA and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001319/2022-2023 | 2321/W/MMD | 29/12/2022 | 824 | S.S.GHORAI | 22.81 | 17.99 | 100
876 | Tamluk Division | Contai Sub-Division | Sinking tube well ,Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1418 nos), Including 2 years of Operation & Maintenance under JJM with allied work of Abas Berya PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000425/2023-2024 | 1414/TD | 12/07/2023 | 180 | SUDHAMAY MAJUMDAR | 462.29 | 101.03 | 45
877 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Abas Beriya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2024-2025 | 3479/TD | 06/11/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
878 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000111/2023-2024 | 75/TD | 05/01/2024 | 0 | Resource Division | 9.71 | 0 | 0
879 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000238/2022-2023 | 2729/TD | 06/02/2023 | 0 | Resource Division | 19.06 | 0 | 0
880 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818449/QUOT/03 DT. 12-07-2024 Application NO- 2004818449 Application type-New connection Consumer Id- 204355505 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01889/2024-2025 | BP-2024-25-552 | 08/08/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
881 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004940081/QUOT/03 DT. 24-10-2024 Application NO- 2004940081 Application type-New connection CONSUMER ID: 204426079 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03001/2024-2025 | C112423541900 | 19/11/2024 | 0 | WBSEDCL | 14.89 | 0 | 0
882 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ABAS BERYA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001341/2022-2023 | 2346/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 25.25 | 0 | 0
883 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Natshal Lakshya (Zone-I) Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000051/2025-2026 | 441/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
884 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Natshal Lakshya (Zone-I) Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000052/2025-2026 | 442/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
885 | Tamluk Division | Haldia Sub-Division | Construction of 2 nos (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site & 5th Tube well site, Laying of Rising main with interconnection, and Supplying of D.I. Specials for Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2024-2025 | 1924/TD | 07/06/2024 | 679 | TAPAN BERA | 22.25 | 0 | 50
886 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 4th & 5th Tube well of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000196/2024-2025 | 2321/TD | 23/07/2024 | 40 | MANNA COMPUTER | 39.77 | 0 | 0
887 | Tamluk Division | Haldia Sub-Division | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000338/2023-2024 | 803/TD | 30/05/2023 | 30 | BARH CONSTRUCTION | 25.52 | 12.05 | 40
888 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya (Zone-I) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000339/2023-2024 | 804/TD | 30/05/2023 | 990 | TAPAN BERA | 5.92 | 0 | 60
889 | Tamluk Division | Haldia Sub-Division | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & Rising main & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000340/2023-2024 | 805/TD | 30/05/2023 | 640 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 92.32 | 64.02 | 100
890 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 1st tube well site of Natshal Lakshya (Zone-I) Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000419/2024-2025 | 3475/TD | 06/11/2024 | 210 | BHOWMIK & SONS | 5.93 | 0 | 100
891 | Tamluk Division | Haldia Sub-Division | G.I pipe column with M.S. Structure for laying of Rising main pipe line at Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= (33+13+18+13+10+67)=154 mtr, | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000455/2024-2025 | 3703/TD | 03/12/2024 | 30 | TAPAN BERA | 18.16 | 2.96 | 100
892 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2022-2023 | 1877/TD | 22/11/2022 | 30 | MODERN CONSTRUCTION | 4.06 | 4.01 | 100
893 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000492/2022-2023 | 1878/TD | 22/11/2022 | 60 | M/S SOURAV MAHAPATRA | 5.03 | 4.99 | 100
894 | Tamluk Division | Haldia Sub-Division | Construction of (5.40 Mtr. X 3.60 Mtr.) Chlorine Room including Plinth Protection at Natshal Lakshya Store within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000542/2024-2025 | 204/TD | 15/01/2025 | 160 | BHOWMIK & SONS | 6.18 | 0 | 80
895 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 20.45 | 45
896 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in OHR site of Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-155mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000610/2023-2024 | 2254/TD | 05/09/2023 | 45 | PRAMANIK AND ROY CONSTRUCTION | 13.18 | 11 | 100
897 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2022-2023 | 3459/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 609.47 | 0 | 25
898 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000046/2022-2023 | 1013/TD | 08/08/2022 | 0 | Resource Division | 106.84 | 0 | 0
899 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-I, T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000214/2023-2024 | 1391/CDD | 19/09/2023 | 204 | DEV AND COMPANY | 21.16 | 19.89 | 100
900 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation for Natshallakhya PWSS Tube Well- III, Zone-I in connection Mukundapur CCC (2004197468) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00160/2022-2023 | BP-2022-23-128 | 13/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
901 | Midnapore Mechanical | Haldia Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
902 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001473/2022-2023 | 211/W/MMD | 10/02/2023 | 180 | S.B.ENTERPRISE | 13.65 | 13.41 | 75
903 | Midnapore Mechanical | Haldia Sub-Division | Replacement of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Tube Well-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur Districtunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002727/2023-2024 | 1072/W/MMD | 14/03/2024 | 180 | ECO ENTERPRISE | 10.85 | 10.61 | 90
904 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 900 cum RCC OHR at Betkundu PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000175/2024-2025 | 2087/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
905 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Betkundu Water Supply Scheme by providing Laying of Distribution pipe line, FHTC work, Construction of R.C.C. Over Head Reservoir of capacity 900 cum and staging height 20.00 mtr. and Sub-Soil Investigation within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000417/2022-2023 | 1577/TD | 14/10/2022 | 930 | RAJ KUMAR SINGHA | 1014.31 | 744.56 | 68
906 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bethkundu Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000440/2021-2022 | 1543/TD | 11/01/2022 | 20 | HORIZEN | 4.88 | 4.88 | 100
907 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 4th Tube well Site of Betkundu Water Supply Scheme within mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000565/2023-2024 | 2051/TD | 25/08/2023 | 25 | DEV & COMPANY | 20.17 | 18.97 | 100
908 | Tamluk Division | Haldia Sub-Division | Culvert, Approach Road and Guard wall cum Boundery wall including land development at Headwork site of Betkundu Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000625/2023-2024 | 2367/TD | 12/09/2023 | 60 | BABUL DAS | 55.26 | 22.24 | 41
909 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube well site of BETKUNDU Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001155/2023-2024 | 731/HSD, | 15/02/2024 | 273 | NASIR ENTERPRISE | 2.81 | 0 | 100
910 | Tamluk Division | Haldia Sub-Division | Laying of Leftout Pipeline, Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement at 4th Tube Well site, Construction new Boundary Wall at 4th Tube well site and Laying of proposed Rising main line and inter connection at Betkundu Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001215/2023-2024 | 979/TD | 13/03/2024 | 45 | RAJ KUMAR SINGHA | 111.15 | 98.53 | 10
911 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000109/2022-2023 | 1673/TD | 03/11/2022 | 0 | Resource Division | 48.38 | 0 | 0
912 | Midnapore Mechanical | Haldia Sub-Division | Quotation for net billing meter at Betkundu w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 222016853 & Application No.- 2004450537) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03722/2023-2024 | BP-2023-24-674 | 15/02/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
913 | Midnapore Mechanical | Haldia Sub-Division | QUATATION BILL FOR BETKUNDU Water Supply scheme Tube Well no.-III Mahishadal CCC Application No.-2004625358 Ref ID.-204232822 Block-Mahishadal | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04573/2023-2024 | BP-2023-24-889 | 22/03/2024 | 0 | WBSEDCL | 4.84 | 0 | 0
914 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground water Based Betkundu Water Supply Scheme, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001928/2022-2023 | 847/W/MMD | 24/03/2023 | 896 | MAA BHABOTARINE ENTERPRISE | 27.18 | 0 | 60
915 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
916 | Tamluk Division | Contai Sub-Division | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1808 nos) under JJM with allied work for Barahat & its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000638/2023-2024 | 2481/TD | 26/09/2023 | 977 | MAA ANANDAMAYEE | 547.32 | 149.65 | 35
917 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000020/2024-2025 | 1641/TD | 18/06/2025 | 0 | Resource Division | 11.14 | 0 | 0
918 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000323/2022-2023 | 2993/TD | 27/02/2023 | 0 | Resource Division | 2.69 | 0 | 0
919 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769741/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769741 Application type-New connection Consumer Id- 204327215 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01281/2024-2025 | BP-2024-25-336 | 25/06/2024 | 0 | WBSEDCL | 5 | 0 | 0
920 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769769/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/170 DT. 10-06-2024 Application NO- 2004769769 Application type-New connection Consumer Id- 204327222 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01282/2024-2025 | BP-2024-25-335 | 25/06/2024 | 0 | WBSEDCL | 1.2 | 0 | 0
921 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAHAT and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001414/2022-2023 | 2425/W/MMD | 31/12/2022 | 882 | DEY ENTERPRISE | 22.8 | 0 | 85
922 | Tamluk Division | Digha Sub-Division | Surging of existing 2nd Tube site of Padima W/S Scheme within Ramnagar-I Block under Digha Sub-Division, of Tamluk Diision P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000041/2025-2026 | 41/DSD | 11/04/2025 | 7 | ONKAR ENTERPRISE | 0.61 | 0 | 100
923 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Rising main ,Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 150Cum OHR ( Intze type with pile foundatio ) Pipe Carrying canal crossing Structure & Accommodate FHTC ( 960 Nos) Including 2 years of Operation & Maintenance under JJM with allied work for Padima & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000548/2023-2024 | 1987/TD | 21/08/2023 | 864 | ONKAR ENTERPRISE | 339.12 | 210.05 | 50
924 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Padima PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000883/2023-2024 | 205/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
925 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000161/2023-2024 | 99/TD | 05/01/2024 | 0 | Resource Division | 5.91 | 0 | 0
926 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000311/2022-2023 | 2998/TD | 27/02/2023 | 0 | Resource Division | 23.63 | 0 | 0
927 | Midnapore Mechanical | Digha Sub-Division | PADIMA W/S SCHEME T/W-I Application No.-2004566513 Ref.-204194520 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03532/2023-2024 | BP-2023-24-613 | 07/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0
928 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PADIMA W/S Scheme under MMD, PHE, Dte. Block- Ramnagar-I, DIGHA C.C.C. Ref. Memo No- 2004626606/QUOT/03 DT. 04-03-2024 Application NO- 2004626606 Application type-New connection CONSUMMER ID- 204233354 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04338/2023-2024 | BP-2023-24-804 | 11/03/2024 | 0 | WBSEDCL | 7.74 | 0 | 0
929 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PADIMA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001665/2022-2023 | 548/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 19.87 | 100
930 | Tamluk Division | Contai Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00708/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.17 | 0 | 0
931 | Tamluk Division | Contai Sub-Division | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Itaberia Mugberia Road from 1.25 Km. To 3.10 Km. for laying water pipe line of Dakshin Patherbaria PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00991/2024-2025 | BP-2024-25-494 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.12 | 0 | 0
932 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
933 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1373 nos) under JJM with allied work of DAKSHIN PATHAR BERYA AND IT'S ADJOINING MOUJAS PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000278/2023-2024 | 555/TD | 12/05/2023 | 1080 | PATHIK PABAN NANDI | 460.76 | 167.47 | 50
934 | Tamluk Division | Contai Sub-Division | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Dakshin Patharberya PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000579/2024-2025 | 457/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.35 | 0 | 0
935 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000184/2023-2024 | 633/W | 20/02/2024 | 0 | Resource Division | 8.46 | 0 | 0
936 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000340/2022-2023 | 2967/TD | 27/02/2023 | 0 | Resource Division | 35.37 | 0 | 0
937 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
938 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
939 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1816 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GATHRA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000107/2023-2024 | 218/TD | 17/04/2023 | 1080 | TAPAS SANTRA | 495.61 | 270.77 | 75
940 | Tamluk Division | Tamluk Sadar Sub-Division | Land development work at Headwork Site of Gathra Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000127/2024-2025 | 1925/TD | 07/06/2024 | 14 | S. P. ENTERPRISE (GSTIN- 19FLFPR7861R1ZS) | 4.23 | 4.18 | 100
941 | Tamluk Division | Tamluk Sadar Sub-Division | Work order for installation of 18 nos Dispaly Board at different PWSS works site under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000197/2024-2025 | 2279/TD | 18/07/2024 | 7 | GLOBAL TRADE | 3.95 | 3.78 | 100
942 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000134/2023-2024 | 129/TD | 05/01/2024 | 0 | Resource Division | 11.19 | 0 | 0
943 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000210/2022-2023 | 2468/TD | 16/01/2023 | 0 | Resource Division | 17.41 | 0 | 0
944 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOTHRA Water Supply Scheme , (Ref. ID-204075850) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02187/2023-2024 | BP-2023-24-238 | 12/09/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
945 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Gathra W/S scheme H/W site. Application No.-100000094421 Ref.-860286461 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03303/2023-2024 | BP-2023-24-544 | 15/01/2024 | 0 | WBSEDCL | 0.34 | 0 | 0
946 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Gathra W/S Scheme T/W-II Application No=2005003708 Reference ID=204470377 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03670/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
947 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GATHRA and ADJOINING MOUJAS, Block Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001355/2022-2023 | 2366/W/MMD | 31/12/2022 | 180 | ABHIJIT BASU | 23.69 | 11.08 | 35
948 | Tamluk Division | Contai Sub-Division | Quotation money for shifting of 11 KV OH Henria Feeder at Bajkul for Bajukl Zone-I PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01686/2023-2024 | BP-2023-24-744 | 04/01/2024 | 0 | WBSEDCL | 2.08 | 0 | 0
949 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC(2596 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - I Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000486/2022-2023 | 1892/TD | 24/11/2022 | 1103 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 440.22 | 264.92 | 78
950 | Tamluk Division | Contai Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000560/2022-2023 | 2243/TD | 29/12/2022 | 40 | R K CONSTRUCTION | 39.67 | 12.07 | 0
951 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-I Water Supply Scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000575/2023-2024 | 2184/TD | 01/09/2023 | 1056 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.41 | 0 | 70
952 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000888/2021-2022 | 1802/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.3 | 100
953 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2023-2024 | 607/TD | 17/05/2023 | 0 | Resource Division | 15.99 | 0 | 0
954 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000115/2022-2023 | 1670/TD | 03/11/2022 | 0 | Resource Division | 95.79 | 0 | 0
955 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF NOVEMBER'2023 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04351/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.19 | 0 | 0
956 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/W/MMD DATED-28.08.2024. FOR THE MONTH OF OCT'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04362/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.16 | 0 | 0
957 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
958 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001915/2022-2023 | 818/W/MMD | 24/03/2023 | 180 | EMCON | 11.83 | 11 | 100
959 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone I Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002728/2023-2024 | 1077/W/MMD | 15/03/2024 | 180 | SOUMEN ELECTRIC | 24.86 | 8.41 | 35
960 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-G ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000071/2023-2024 | 173/TD | 11/04/2023 | 1020 | AYSAN KHAN | 19.97 | 0 | 60
961 | Tamluk Division | Digha Sub-Division | Canal crossing Structure for laying of Distribution line and 2nd TW Land filling for Islampur & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000272/2024-2025 | 2900/TD | 10/09/2024 | 120 | LOKENATH ENTERPRISE | 16.49 | 0 | 100
962 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 238 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000284/2023-2024 | 563/TD | 12/05/2023 | 1079 | LOKENATH ENTERPRISES | 119.04 | 87.21 | 60
963 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundatio ) & Accommodate FHTC ( 414 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000412/2023-2024 | 1098/TD | 08/06/2023 | 992 | FIROZ KHAN | 199.26 | 0 | 30
964 | Tamluk Division | Digha Sub-Division | Canal crossing Structure for laying of Distribution line from Sapua Bridge towards Chaulkhola parallel of NH-116B for Islampur & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000442/2024-2025 | 3538/TD | 13/11/2024 | 450 | AYSAN KHAN | 21.61 | 0 | 100
965 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000536/2023-2024 | 1839/TD | 08/08/2023 | 40 | MRINAL KANTI PRADHAN | 84.49 | 52.16 | 65
966 | Tamluk Division | Digha Sub-Division | Laying of Balance Distribution HDPE Pipe Line(225 mm dia) for Islampur Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000706/2023-2024 | 2872/TD | 17/11/2023 | 20 | A. K. SIKDAR | 9.42 | 9.36 | 99
967 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000865/2022-2023 | 3179/TD | 10/03/2023 | 1157 | LOKENATH ENTERPRISES | 84.26 | 54.11 | 65
968 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000866/2022-2023 | 3180/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.85 | 12.06 | 62
969 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-F ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000868/2022-2023 | 3181/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.87 | 12.08 | 60
970 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-H ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000869/2022-2023 | 3182/TD | 10/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 6.81 | 5.92 | 95
971 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000143/2023-2024 | 103/TD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0
972 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000157/2022-2023 | 2464/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
973 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 50.75 | 11
974 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW no-2 of Islampur ws scheme, Block-Ramnagar-2, Pichaboni CCC Ref. Application no-2005007319 Con ID-204472431 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03683/2024-2025 | C012524064766 | 09/01/2025 | 0 | WBSEDCL | 2.55 | 0 | 0
975 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ISLAMPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005010810/QUOT/03 DT. 17-12-2024 Application NO- 2005010810 Application type-New connection Consumer Id- 204475188 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03865/2024-2025 | C012552561112 | 31/01/2025 | 0 | WBSEDCL | 5.22 | 0 | 0
976 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000105/2023-2024 | 170/TD | 10/04/2023 | 30 | SK MAIDUL ISLAM | 40.83 | 32.18 | 78
977 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000145/2024-2025 | 2061/TD | 24/06/2024 | 20 | KISHORE GHOSH | 14.87 | 0 | 0
978 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (450 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000248/2023-2024 | 526/TD | 11/05/2023 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 172.54 | 37 | 22
979 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) (Balance Part) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000275/2024-2025 | 2902/TD | 10/09/2024 | 520 | TARUN KHATUA | 68.16 | 0 | 50
980 | Tamluk Division | Tamluk Sadar Sub-Division | Land Development work at Head work site & 2nd Tube well site of Urddhabmal Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000381/2024-2025 | 1008/HSD, | 04/10/2024 | 480 | TARUN KHATUA | 4.85 | 0 | 50
981 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000784/2022-2023 | 3035/TD | 27/02/2023 | 60 | R K CONSTRUCTION | 97.19 | 26.22 | 30
982 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000785/2022-2023 | 3036/TD | 27/02/2023 | 30 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 39 | 22.77 | 65
983 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(137 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000786/2022-2023 | 3037/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.92 | 0 | 0
984 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000787/2022-2023 | 3038/TD | 27/02/2023 | 20 | SAYAN MAITY | 20.13 | 17.36 | 87
985 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000788/2022-2023 | 3039/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.99 | 13.44 | 85
986 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (120nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000789/2022-2023 | 3040/TD | 27/02/2023 | 20 | SUDIP MANNA | 15.47 | 9.32 | 65
987 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(130nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000790/2022-2023 | 3041/TD | 27/02/2023 | 20 | SAYAN MAITY | 19.92 | 14.14 | 72
988 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000894/2022-2023 | 3344/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.86 | 0 | 50
989 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000913/2022-2023 | 3559/TD | 29/03/2023 | 632 | S. B. ASSOCIATES | 57.43 | 46.53 | 85
990 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (230nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000914/2022-2023 | 3560/TD | 29/03/2023 | 1022 | S. B. ASSOCIATES | 67.13 | 40.57 | 65
991 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000160/2022-2023 | 2475/TD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0
992 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000192/2023-2024 | 641/W | 20/02/2024 | 0 | Resource Division | 11.07 | 0 | 0
993 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for URDHABMAL Water Supply Scheme T/W-I, (Ref. ID-204076039) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02197/2023-2024 | BP-2023-24-244 | 12/09/2023 | 0 | WBSEDCL | 15.45 | 0 | 0
994 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for URDHABMAL Water Supply Scheme T/W-II, (Ref. ID-204076027) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02199/2023-2024 | BP-2023-24-243 | 12/09/2023 | 0 | WBSEDCL | 3.36 | 0 | 0
995 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for URDDHABMAL and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001686/2022-2023 | 562/W/MMD | 20/03/2023 | 895 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 70
996 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (850 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000258/2023-2024 | 536/TD | 12/05/2023 | 1048 | GIRI CONSTRUCTION | 191.14 | 78.24 | 42
997 | Tamluk Division | Contai Sub-Division | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (511 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000391/2023-2024 | 1050/TD | 07/06/2023 | 180 | TARUN KOLEY | 222.99 | 45.72 | 22
998 | Tamluk Division | Contai Sub-Division | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Manikjore PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000580/2024-2025 | 458/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.18 | 0 | 0
999 | Tamluk Division | Contai Sub-Division | Laying Distribution pipe line & Accommodate FHTC (330 nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000910/2022-2023 | 3465/TD | 27/03/2023 | 45 | SUBHENDU HAZRA | 76.59 | 47.28 | 60
1000 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 180nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000911/2022-2023 | 3466/TD | 27/03/2023 | 302 | SUBRATA KUMAR BERA | 28.31 | 16.28 | 60
1001 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000176/2023-2024 | 625/W | 20/02/2024 | 0 | Resource Division | 12.23 | 0 | 0
1002 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000296/2022-2023 | 2961/TD | 27/02/2023 | 0 | Resource Division | 33.37 | 0 | 0
1003 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1004 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1005 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1006 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line,Pump House, Accommodate FHTC & Boundary Wall (400 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000064/2023-2024 | 134/TD | 10/04/2023 | 719 | JAI BHARAT COMMERCIAL CORPORATION | 78.91 | 0 | 65
1007 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Pump House & Accommodate FHTC (315 nos), Boundary Wall under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000065/2023-2024 | 135/TD | 10/04/2023 | 45 | SOUMYA ENTERPRISE | 53.18 | 34.5 | 67
1008 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (100 nos) under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000066/2023-2024 | 136/TD | 10/04/2023 | 1065 | SUDIP MANNA | 19.43 | 10.36 | 60
1009 | Tamluk Division | Contai Sub-Division | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (200 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000522/2023-2024 | 1755/TD | 01/08/2023 | 964 | DIPAK ROY | 159.88 | 49.25 | 50
1010 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Panch Bajari, Manikjor, Bahadurpur, Kayemgerya, & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001166/2023-2024 | 2327/CSD | 29/12/2023 | 15 | M/S. NEW DINDA ENTERPRISE | 0.83 | 0.83 | 100
1011 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000175/2023-2024 | 624/W | 20/02/2024 | 0 | Resource Division | 6.25 | 0 | 0
1012 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000294/2022-2023 | 2960/TD | 27/02/2023 | 0 | Resource Division | 33.17 | 0 | 0
1013 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 50.2 | 11
1014 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of Panchbajari W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601878/QUOT/03 DT. 15-02-2024 Quotation due date-14.02.2025 Application NO- 2004601878 Application type-New connection Reference Id- 204217833 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04263/2023-2024 | BP-2023-24-793 | 06/03/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
1015 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PANCH BAJARI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2005049006/QUOT/03 DT. 10-02-2025 Application NO- 2005049006 Application type-New connection Consumer Id- 204499364 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04415/2024-2025 | C032554751081 | 17/03/2025 | 0 | WBSEDCL | 7.75 | 0 | 0
1016 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1017 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at 5 nos {1. TILKHOJA PWSS,( PUMP HOUSE -1 &2) 2. RADHABALLAVCHAK PWSS ( PUMP HOUSE -1 &2), 3. GOBARDHAN PWSS( PUMP HOUSE -1), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2025-2026 | 61/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
1018 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 299.32 | 75
1019 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Tilkhoja PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000876/2023-2024 | 198/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1020 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000014/2024-2025 | 1570/TD | 23/04/2024 | 0 | Resource Division | 14.36 | 0 | 0
1021 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000180/2022-2023 | 2432/TD | 16/01/2023 | 0 | Resource Division | 27.95 | 0 | 0
1022 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Tlkhoja w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004685657, Con ID 204277587) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00646/2024-2025 | BP-2024-25-123 | 05/05/2024 | 0 | WBSEDCL | 9.91 | 0 | 0
1023 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Tilkhoja w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608980, Ref ID-204222618) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04498/2023-2024 | BP-2023-24-852 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
1024 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Tilkhoja and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001322/2022-2023 | 2324/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 60
1025 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000015/2022-2023 | 49/TD | 05/04/2022 | 20 | RADIANT | 5.76 | 5.75 | 100
1026 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.25 | 75
1027 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000336/2022-2023 | 1278/TD | 12/09/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 416.22 | 307.87 | 80
1028 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000338/2022-2023 | 1288/TD | 13/09/2022 | 60 | BARH CONSTRUCTION | 205.99 | 124.95 | 65
1029 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2022-2023 | 3459/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 609.47 | 117.91 | 25
1030 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000045/2022-2023 | 1014/TD | 08/08/2022 | 0 | Resource Division | 15.11 | 0 | 0
1031 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000071/2022-2023 | 1255/TD | 12/09/2022 | 0 | Resource Division | 50.47 | 0 | 0
1032 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new application at Natshallakhya Zone I PH IV in the district of Purba Medinipur under MMD PHE Dte. ( App No. 20046922155, Ref ID 204281189) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01077/2024-2025 | BP-2024-25-191 | 24/05/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
1033 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001935/2022-2023 | 854/W/MMD | 24/03/2023 | 180 | SUBHASIS ROY | 27.33 | 0 | 0
1034 | Tamluk Division | Haldia Sub-Division | Quotation payment for shifting of 11 KV line at Gobindapur on Full deposit of scheme of Asadtalia PWSS of Sutathat Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00538/2023-2024 | BP-2023-24-282 | 17/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0
1035 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Asadtalia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000188/2021-2022 | 1197/TD | 02/12/2021 | 20 | RADIANT | 3.95 | 3.82 | 100
1036 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2nd tube well site of Asadtalia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000257/2022-2023 | 1068/TD | 22/08/2022 | 45 | BUNBA CONSTRUCTION | 3.95 | 3.51 | 100
1037 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Asadtalia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000374/2021-2022 | 1815/TD | 11/02/2022 | 1145 | HARIPADA PATTANAYAK | 303.25 | 242.47 | 85
1038 | Tamluk Division | Haldia Sub-Division | Laying Rising main, laying left out pipe line, canal crossing and supporting work with Drum Sheet walling and Earth filling in Asadtalia Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000550/2022-2023 | 2168/TD | 19/12/2022 | 768 | HARIPADA PATTANAYAK | 64.43 | 54.65 | 100
1039 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Asadtalia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000625/2021-2022 | 2186/TD | 17/03/2022 | 20 | BAGLAMUKHI SECURITY SERVICE | 3.61 | 3.61 | 100
1040 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000021/2021-2022 | 1263/TD | 13/12/2021 | 0 | Resource Division | 11.63 | 0 | 0
1041 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000055/2021-2022 | 1868/TD | 17/02/2022 | 0 | Resource Division | 10.22 | 0 | 0
1042 | Central Drilling | Haldia Sub-Division | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR ASADTALIA W/S SCHEME (TW-I), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000007/2022-2023 | 15/CDD | 04/04/2022 | 30 | MENAKA ENTERPRISE | 18.53 | 17.39 | 100
1043 | Central Drilling | Haldia Sub-Division | Providing Drilling crew and other allied works for construction of TW (300mm x 200mm x280mtrs) by utilising Departmental machinery for Sutahata Block under Purba Midnapur, CDD,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000095/2022-2023 | 106/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.7 | 18.33 | 100
1044 | Central Drilling | Haldia Sub-Division | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, HE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000152/2022-2023 | 224/CMSD-I (D) | 20/06/2022 | 15 | MENAKA ENTERPRISE | 4.96 | 4.63 | 100
1045 | Central Drilling | Haldia Sub-Division | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000153/2022-2023 | 225/CMSD-I | 20/06/2022 | 15 | MENAKA ENTERPRISE | 5 | 5 | 100
1046 | Central Drilling | Haldia Sub-Division | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER MATERIALS & WORKS FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA PWSS, SUTAHATA BLOCK UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000154/2022-2023 | 226/CMSD-I | 20/06/2022 | 15 | MENAKA ENTERPRISE | 4.98 | 4.44 | 100
1047 | Central Drilling | Haldia Sub-Division | PROVIDING TUBE WELL MATERIALS WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ASADTALIA W/S SCH (TW-II) UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000249/2022-2023 | 254/CMSD-I | 23/06/2022 | 10 | MENAKA ENTERPRISE | 0.93 | 0.3 | 100
1048 | Central Drilling | Haldia Sub-Division | PROVIDING TUBEWELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000366/2022-2023 | 378/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 5 | 2.23 | 0
1049 | Central Drilling | Haldia Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.01 | 0
1050 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-I under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000415/2023-2024 | 579/HESD | 04/08/2023 | 7 | BALAJI CONSTRUCTION | 0.19 | 0 | 0
1051 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-II under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000416/2023-2024 | 578/HESD | 04/08/2023 | 7 | SHOVAN KUMAR DAS | 0.13 | 0 | 0
1052 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well I under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001135/2022-2023 | 2116/W/MMD | 28/11/2022 | 120 | BALAJI CONSTRUCTION | 11.24 | 10.54 | 100
1053 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001136/2022-2023 | 2117/W/MMD | 28/11/2022 | 120 | SHOVAN KUMAR DAS | 11.37 | 10.65 | 100
1054 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (82 Nos) under JJM with allied work for FATEPUR PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000466/2024-2025 | 3722/TD | 04/12/2024 | 30 | MAITY CONSTRUCTION | 14.16 | 0 | 0
1055 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000132/2023-2024 | 107/TD | 05/01/2024 | 0 | Resource Division | 2.32 | 0 | 0
1056 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000269/2022-2023 | 2697/TD | 06/02/2023 | 0 | Resource Division | 4.51 | 0 | 0
1057 | Midnapore Mechanical | Digha Sub-Division | Fatepur W/S scheme PH-I Application no.-2004511512 ref.-204147631 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03193/2023-2024 | BP-2023-24-468 | 27/12/2023 | 0 | WBSEDCL | 0.86 | 0 | 0
1058 | Midnapore Mechanical | Digha Sub-Division | Fatepur W/S scheme TW-II Application No.-2004521 Ref.-204156067 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03363/2023-2024 | BP-2023-24-574 | 18/01/2024 | 0 | WBSEDCL | 0.26 | 0 | 0
1059 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for LOAD ENHANCEMENT at T/W NO-I Of FATEPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005045654/QUOT/03 DT. 14-01-2025 Application NO- 2005045654 Application type-LOAD ENHANCEMENT Consumer Id- 204156067 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04114/2024-2025 | C022539974995 | 18/02/2025 | 0 | WBSEDCL | 0.15 | 0 | 0
1060 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FATEPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001673/2022-2023 | 570/W/MMD | 20/03/2023 | 539 | DEY ENTERPRISE | 11.98 | 10.88 | 100
1061 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 210 Nos) under JJM with allied work for Chirulia-Chatla (Zone-III) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000407/2023-2024 | 1089/TD | 08/06/2023 | 1208 | AJIT KUMAR SOM | 233.68 | 78.46 | 85
1062 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000495/2022-2023 | 1931./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100
1063 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000034/2023-2024 | 2063/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
1064 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000091/2023-2024 | 2994/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0
1065 | Midnapore Mechanical | Digha Sub-Division | Chirulia Chatla W/S scheme Zone-III, T/W-I Application.-2004553660 Ref.-204183515 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03362/2023-2024 | BP-2023-24-575 | 18/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
1066 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at Zone-III,TW-II of Chirulia Chatla ws scheme under MMD, PHE Dte. Block-Egra-I, Chopalia CCC. App. no-2004635402, Con ID-204242995 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04742/2023-2024 | Bp-2023-24-915 | 28/03/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
1067 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Chirulia-Chatla Zone-3 Egra I Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001984/2022-2023 | 892/W/MMD | 27/03/2023 | 888 | SHREE BISHNU CONSTRUCTION | 23.68 | 0 | 52
1068 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000228/2023-2024 | 474/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 3.67 | 100
1069 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000229/2023-2024 | 475/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 3.69 | 100
1070 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000230/2023-2024 | 476/TD | 10/05/2023 | 60 | GIRI CONSTRUCTION | 3.71 | 3.7 | 100
1071 | Tamluk Division | Contai Sub-Division | Laying of 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 1(One) no. Boosting Tubewell for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000233/2023-2024 | 477/TD | 10/05/2023 | 300 | KOUSHIK MALLICK | 3.22 | 0 | 100
1072 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000317/2023-2024 | 663/TD | 19/05/2023 | 30 | GIRI CONSTRUCTION | 6.94 | 5.89 | 100
1073 | Tamluk Division | Contai Sub-Division | Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000318/2023-2024 | 664/TD | 19/05/2023 | 30 | DAS ENTERPRISE | 6.91 | 5.07 | 100
1074 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00106/2023-2024 | BP-2023-24-25 | 04/05/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
1075 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00418/2022-2023 |  | 25/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
1076 | Tamluk Division | Contai Sub-Division | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000394/2023-2024 | 1083/TD | 08/06/2023 | 20 | M/S. NEW DINDA ENTERPRISE | 5.07 | 3.28 | 100
1077 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000438/2023-2024 | 1421/TD | 12/07/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 6.93 | 0 | 0
1078 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000456/2023-2024 | 1501/TD | 17/07/2023 | 20 | THE GODFATHER TRADING COMPANY | 5.24 | 3.2 | 65
1079 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001471/2022-2023 | 209/W/MMD | 10/02/2023 | 180 | SUBHASIS ROY | 11.84 | 9.44 | 70
1080 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000124/2023-2024 | 106/TD | 05/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1081 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000268/2022-2023 | 2695/TD | 06/02/2023 | 0 | Resource Division | 4.13 | 0 | 0
1082 | Midnapore Mechanical | Contai Sub-Division | Biswanathpur W/S scheme TW-I Application no.-2004496775 Ref no.-204135775 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03194/2023-2024 | BP-2023-24-469 | 27/12/2023 | 0 | WBSEDCL | 1.54 | 0 | 0
1083 | Midnapore Mechanical | Contai Sub-Division | Biswanathpur W/S scheme PH no.-II Application No.-2004521756 Ref.-204156072 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03244/2023-2024 | BP-2023-24-498 | 05/01/2024 | 0 | WBSEDCL | 2.56 | 0 | 0
1084 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
1085 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BISWANATHPUR PWSS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001728/2022-2023 | 600/W/MMD | 20/03/2023 | 499 | M/S S M ELECTRICAL | 5.98 | 5.42 | 100
1086 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 26.15 | 75
1087 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000082/2024-2025 | 2970/TD | 12/09/2024 | 0 | Resource Division | 6.11 | 0 | 0
1088 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000171/2022-2023 | 2395/TD | 16/01/2023 | 0 | Resource Division | 25.23 | 0 | 0
1089 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of POTAPUKURIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005367965/QUOT/03 DT. 31-07-2025 Application NO- 2005367965 Application type-New connection Consumer Id- 204682905 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01875/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 3.8 | 0 | 0
1090 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PASCHIM RASULPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005048465/QUOT/03 DT. 16-01-2025 Application NO- 2005048465 Application type-New connection Consumer Id- 204498741 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04504/2024-2025 | C032587408156 | 27/03/2025 | 0 | WBSEDCL | 9.75 | 0 | 0
1091 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001711/2022-2023 | 594/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 0 | 0
1092 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (291 nos) under JJM with allied work for ASTICHAK (ZONE-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000635/2023-2024 | 2444/TD | 19/09/2023 | 984 | HALDIA DEVELOPMENT CONSTRUCTION | 446.88 | 0 | 55
1093 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000856/2021-2022 | 1472/TD | 03/01/2022 | 20 | APEX ENGINEERING | 3.99 | 3.99 | 100
1094 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Astichak Zone-I PWSS at Egra-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001048/2023-2024 | 378/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1095 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000044/2023-2024 | 2078/TD | 28/08/2023 | 0 | Resource Division | 24.42 | 0 | 0
1096 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000106/2023-2024 | 3009/TD | 29/11/2023 | 0 | Resource Division | 7.95 | 0 | 0
1097 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671988/QUOT/03/47 DT. 05-04-2024 Application NO- 2004671988 Application type-New connection Consumer Id- 204266732 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00502/2024-2025 | BP-2024-25-91 | 24/04/2024 | 0 | WBSEDCL | 7.72 | 0 | 0
1098 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, ZONE- I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626968/QUOT/03/1610 DT. 01-03-2024 Application NO- 2004626968 Application type-New connection Consumer Id- 204233764 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04882/2023-2024 | C122421523282 | 16/12/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
1099 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-I) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001981/2022-2023 | 889/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 0 | 0
1100 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001730/2022-2023 | 602/W/MMD | 20/03/2023 | 712 | BHABANI PRASAD MANNA | 11.98 | 0 | 40
1101 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1102 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 236.48 | 48
1103 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2025-2026 | 2093/TD | 12/08/2025 | 0 | Resource Division | 25.05 | 0 | 0
1104 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000320/2022-2023 | 2974/TD | 27/02/2023 | 0 | Resource Division | 49.63 | 0 | 0
1105 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1106 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DUBDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005020296/QUOT/03 DT. 23-12-2024 Application NO- 2005020296 Application type-New connection Consumer Id- 204480414 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03946/2024-2025 | C012553116780 | 31/01/2025 | 0 | WBSEDCL | 4.24 | 0 | 0
1107 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DUBDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005050848/QUOT/03/962 DT. 20-01-2025 Application NO- 2005050848 Application type-New connection Consumer Id- 204501203 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04272/2024-2025 | C032554781201 | 17/03/2025 | 0 | WBSEDCL | 19.21 | 0 | 0
1108 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DUBDA and ADJOINING MOUJAS, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2023-2024 | 1269/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0
1109 | Midnapore Mechanical | Digha Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1110 | Tamluk Division | Tamluk Sadar Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00704/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.55 | 0 | 0
1111 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. and repairing as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kaktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000135/2022-2023 | 690/TD | 27/06/2022 | 1368 | TAPAS SANTRA | 965.88 | 929.87 | 86
1112 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 16.11 | 100
1113 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000367/2021-2022 | 1631/TD | 18/01/2022 | 20 | HORIZEN | 5.27 | 5.25 | 100
1114 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 15 | 80
1115 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of boundary wall (Length-150 m With Double Tie Beam at 01 Longer & 01 Shorter Side) with R.C.C structures including provision of M.S. gate at H/W site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000619/2024-2025 | 696/TD | 05/03/2025 | 100 | A. R. CONSTRUCTION | 21.69 | 0 | 100
1116 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 2nd. tube well site under Kanktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000642/2024-2025 | 945/TD | 27/03/2025 | 40 | MRITYUNJOY PARIA | 5.31 | 0 | 100
1117 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000657/2022-2023 | 2342/TD | 10/01/2023 | 40 | TARUN KHATUA | 5.11 | 5.1 | 0
1118 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000658/2022-2023 | 2343/TD | 10/01/2023 | 40 | SUDIP MANNA | 5.11 | 5.11 | 100
1119 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2025 to 31.01.2026.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000480/2025-2026 | 2632/TSD | 30/07/2025 | 181 | KISHORE KUMAR SEN | 0.86 | 0 | 0
1120 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Left out pipe line with FHTC (200 nos.) work for Kanktia PWSS in Sahid Matangini Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000854/2022-2023 | 3208/TD | 14/03/2023 | 1024 | TAPAS SANTRA | 68.55 | 46.63 | 72
1121 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000037/2022-2023 | 653/TD | 27/06/2022 | 0 | Resource Division | 26.13 | 0 | 0
1122 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000077/2022-2023 | 1260/TD | 12/09/2022 | 0 | Resource Division | 44.52 | 0 | 0
1123 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Kaktia PWSS Tube Well--III WS Scheme (Ref. ID - 203931856) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00319/2022-2023 | BP-2022-23-138 | 20/03/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
1124 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Kaktia PWSS Tube Well--IV WS Scheme (Ref. ID - 203931902) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00320/2022-2023 | BP-2022-23-139 | 20/03/2023 | 0 | WBSEDCL | 2.94 | 0 | 0
1125 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotiaton for KAKTIA Water Supply Scheme T/W-III (Ref. ID-860272167) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01616/2023-2024 | BP-2023-24-134 | 27/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
1126 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001474/2022-2023 | 212/W/MMD | 10/02/2023 | 180 | WEST BENGAL ENGINEERING CO. | 40.35 | 25.37 | 35
1127 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (130Nos) under JJM with allied work for KANPUR (Zone -IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000316/2024-2025 | 3183/TD | 30/09/2024 | 240 | GHOSH CONSTRUCTION | 95.27 | 0 | 85
1128 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000458/2022-2023 | 1857/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.38 | 100
1129 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 209 Nos) under JJM with allied work for KANPUR (Zone-IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000508/2023-2024 | 1730/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 308.34 | 222.32 | 40
1130 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone- IV PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000869/2023-2024 | 191/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1131 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000043/2023-2024 | 2068/TD | 28/08/2023 | 0 | Resource Division | 13.67 | 0 | 0
1132 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000102/2023-2024 | 3005/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0
1133 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme T/W-I, Zone-IV Application No.-2004536085 Ref.-204168169 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03290/2023-2024 | BP-2023-24-542 | 11/01/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1134 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme PH-II, Zone-IV Application No.-2004565701 Ref no.-204193734 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03521/2023-2024 | BP-2023-24-587 | 02/02/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
1135 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
1136 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at KANPUR zone IV Water supply scheme, RAMNAGAR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002723/2023-2024 | 1068/W/MMD | 14/03/2024 | 180 | M/S SREEJIT ENTERPRISE | 12.52 | 11.68 | 85
1137 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 34.96 | 100
1138 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Habichak Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000305/2023-2024 | 602/TD | 17/05/2023 | 45 | SOUMEN KUMAR GHOSH | 25.91 | 25.89 | 100
1139 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side of 2 (Two) nos Boosting T/W site at Habichak W/S scheme of Chandipur Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000375/2024-2025 | 1607/TSD | 28/10/2024 | 20 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.82 | 0 | 100
1140 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000003/2023-2024 | 352/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
1141 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HABICHAK Water Supply SchemeT/W-III (Ref. ID-204049767) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01633/2023-2024 | BP-2023-24-142 | 27/07/2023 | 0 | WBSEDCL | 3.76 | 0 | 0
1142 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HABICHAK Water Supply SchemeT/W-IV (Ref. ID-204049766) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01634/2023-2024 | BP-2023-24-141 | 27/07/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
1143 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotiaton for HABICHAK Water Supply Scheme, T/W- II, (Ref. ID-860281634) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02879/2023-2024 | BP-2023-24-322 | 01/11/2023 | 0 | WBSEDCL | 2.27 | 0 | 0
1144 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 25.33 | 55
1145 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for MAHISHADAL BETKUNDU Water Supply Scheme T/W-, (Ref. ID-222016853) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02680/2023-2024 | BP-2023-24-268 | 10/10/2023 | 0 | WBSEDCL | 0.01 | 0 | 0
1146 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation works for the purpose of Geotagging at different PWSS under CHANDIPUR, MAHISHADAL and KHEJURI Block under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000182/2024-2025 | 725/HESD | 30/07/2024 | 15 | SOUMEN ELECTRIC | 3.7 | 0 | 100
1147 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001849/2022-2023 | 766/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.24 | 0 | 100
1148 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001850/2022-2023 | 768/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.65 | 10.44 | 75
1149 | Tamluk Division | Contai Sub-Division | Laying distribution System, Construction of Pump House Accommodate FHTC (1100 nos) & Rising Main including interconnection for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000432/2023-2024 | 1407/TD | 12/07/2023 | 80 | BARH CONSTRUCTION | 205.81 | 99.87 | 50
1150 | Tamluk Division | Contai Sub-Division | Laying distribution System & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000433/2023-2024 | 1408/TD | 12/07/2023 | 80 | UCON | 204.9 | 82.81 | 25
1151 | Tamluk Division | Contai Sub-Division | Laying distribution System & Accommodate FHTC (897 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000434/2023-2024 | 1409/TD | 12/07/2023 | 786 | SWADHIN KUMAR CHAKRABORTY | 211.86 | 70.39 | 40
1152 | Tamluk Division | Contai Sub-Division | Laying distribution System, Construction of Pump House, Construction of Boundary Wall & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000435/2023-2024 | 1410/TD | 12/07/2023 | 796 | NARAYAN CHANDRA DAS | 200.01 | 74.62 | 45
1153 | Tamluk Division | Contai Sub-Division | Soil investigation, R.C.C. Elevated Reservoir of capacity 550cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000633/2023-2024 | 2441/TD | 19/09/2023 | 529 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 178.22 | 0 | 0
1154 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000159/2023-2024 | 133/TD | 05/01/2024 | 0 | Resource Division | 27.7 | 0 | 0
1155 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000293/2022-2023 | 2959/TD | 27/02/2023 | 0 | Resource Division | 54.95 | 0 | 0
1156 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 81.51 | 11
1157 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004698092/QUOT/03 DT. 23-04-2024 Application NO- 2004698092 Application type-New connection Consumer Id- 204285056 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00706/2024-2025 | BP-2024-25-139 | 09/05/2024 | 0 | WBSEDCL | 10.71 | 0 | 0
1158 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638854/QUOT/03 DT. 13-03-2024 Application NO- 2004638854 Application type-New connection CONSUMER ID: 204243849 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04739/2023-2024 | BP-2023-24-911 | 28/03/2024 | 0 | WBSEDCL | 2.77 | 0 | 0
1159 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638811/QUOT/03 DT. 13-03-2024 Application NO- 2004638811 Application type-New connection CONSUMER ID: 204243848 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04748/2023-2024 | BP-2023-24-912 | 28/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
1160 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1161 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well, Construction of Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (314 nos.), Installation of display Board, under JJM with allied work including 02 (two) Years Operation & Maintenance of Ajangechhya PWSS within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000077/2023-2024 | 208/TD | 13/04/2023 | 899 | RELIABLE CONSTRUCTIONS | 135.23 | 26.21 | 45
1162 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000224/2022-2023 | 2675/TD | 06/02/2023 | 0 | Resource Division | 4.96 | 0 | 0
1163 | Midnapore Mechanical | Tamluk Sadar Sub-Division | AJANGECHIA w/s SCHEME Application No.-2004568912 Ref.-204196601 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03528/2023-2024 | BP-2023-24-586 | 02/02/2024 | 0 | WBSEDCL | 5.6 | 0 | 0
1164 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJANGECHHYA, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001661/2022-2023 | 545/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 9.75 | 45
1165 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1670 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 250 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Putputia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 130/TD | 10/04/2023 | 1051 | TARUN KOLEY | 483.49 | 237.21 | 70
1166 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000222/2022-2023 | 2677/TD | 06/02/2023 | 0 | Resource Division | 23.37 | 0 | 0
1167 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for PUTPUTIA Water Supply Scheme , T/W-II (Ref. ID-204075888) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02182/2023-2024 | BP-2023-24-240 | 12/09/2023 | 0 | WBSEDCL | 4.59 | 0 | 0
1168 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for PUTPUTIA Head Work Water Supply Scheme T/W-I, (Ref. ID-204094476) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02679/2023-2024 | BP-2023-24-270 | 10/10/2023 | 0 | WBSEDCL | 5.52 | 0 | 0
1169 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
1170 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PUTPUTIA PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001691/2022-2023 | 620/W/MMD | 20/03/2023 | 896 | M/S B.M. ELECTRICAL | 22.81 | 19.81 | 35
1171 | Tamluk Division |  | Functional Household Tap Connection to the 1174 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Srirampur(118) Bagmari(116)] |  |  | ORD/000229/2020-2021 | 2864/TD | 09/02/2021 | 30 | SWARUPANANDA DAS | 57.51 | 0 | 100
1172 | Tamluk Division |  | Functional Household Tap Connection to the 836 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [Dwarakapur(115) Rannagarpur(119) Dhusurda(239) Kashimpur(240) Joykrishnapur(114)PART] |  |  | ORD/000230/2020-2021 | 2865/TD | 09/02/2021 | 30 | S.K. MONDAL | 38.92 | 25.89 | 100
1173 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000371/2021-2022 | BP-2021-22-114 | 05/10/2021 | 0 | SWARUPANANDA DAS | 7.5 | 0 | 0
1174 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000429/2021-2022 | 302/W | 05/10/2021 | 0 | SWARUPANANDA DAS | 2.87 | 0 | 0
1175 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001142/2020-2021 | 1118/W | 30/03/2021 | 0 | S.K. MONDAL | 25.94 | 0 | 0
1176 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001219/2020-2021 | 965/W | 22/03/2021 | 0 | SWARUPANANDA DAS | 47.13 | 0 | 0
1177 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Basudevpur PWSS Block Egra-II in the District of Purba Medinipur. |  |  | ORD/000125/2020-2021 | 2629/TD | 05/01/2021 | 60 | SNEHESH SEN | 87.4 | 87.39 | 100
1178 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0.8 | 65
1179 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Bamunia PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000030/2020-2021 | 2106/TD | 05/11/2020 | 180 | JAYANTA KR. MONDAL | 74.72 | 0 | 100
1180 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000374/2021-2022 | BP-2021-22-121 | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 3.99 | 0 | 0
1181 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000430/2021-2022 | 303/W | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 5 | 0 | 0
1182 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000601/2020-2021 | 639/W | 13/01/2021 | 0 | JAYANTA KUMAR MONDAL | 54.64 | 0 | 0
1183 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001242/2020-2021 | 995/W | 26/03/2021 | 0 | JAYANTA KUMAR MONDAL | 10.33 | 0 | 0
1184 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -II(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000122/2020-2021 | 2631/TD | 05/01/2021 | 60 | MAA ANANDAMAYEE | 96.97 | 192 | 100
1185 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XII Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000192/2020-2021 | 2769/TD | 28/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 96.7 | 0 | 100
1186 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000132/2021-2022 | BP-2021-22-51 | 29/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 0.73 | 0 | 0
1187 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000223/2021-2022 | 133/W | 15/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 4.15 | 0 | 0
1188 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001216/2020-2021 | 943/W | 19/03/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 91.85 | 0 | 0
1189 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XIII(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000119/2020-2021 | 2632/TD | 05/01/2021 | 60 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 96.92 | 195.77 | 100
1190 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS (Zone-I)Block -Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000118/2020-2021 | 2503/TD | 23/12/2020 | 60 | M/S. CHANDI CHARAN MISHRA & CO. | 76.13 | 31.88 | 100
1191 | Tamluk Division |  | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 1.64 | 100
1192 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000464/2021-2022 | 296/W | 07/10/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 21.89 | 0 | 0
1193 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001207/2020-2021 | 936/W | 18/03/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 22.35 | 0 | 0
1194 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (409 nos) under JJM in Tajpur PWSS within Dijam Talya - JL No.-149 (Dijam Talya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000211/2020-2021 | 2823/TD | 05/02/2021 | 20 | MRITYUNJOY PARIA | 19.4 | 12.43 | 100
1195 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (429 nos) under JJM in Tajpur PWSS within Bar Jamtalya - JL No.-148 (Bar Jamtalya) & Nandanayak Bar - J.L. - 179 (Nandanayak Bar) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000212/2020-2021 | 2824/TD | 05/02/2021 | 20 | SK. NUR ISLAM | 20.36 | 8.35 | 100
1196 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Bartalya - JL No.-209 (Bartalya) & Chargalya (P) - J.L. - 150 (Chargalya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000213/2020-2021 | 2825/TD | 05/02/2021 | 25 | KRISHNENDU SEKHAR DAS | 27.98 | 0 | 100
1197 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Chargalya (P) - J.L. - 150 (Chargalya) & Tajpur (P) - J.L. - 210 (Tajpur & Tajpur Paschim Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000214/2020-2021 | 2826/TD | 05/02/2021 | 25 | DEBASIS DAS | 27.75 | 0 | 100
1198 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (100 nos) under JJM in Mahammadpur PWSS within Khariberia JL No.-183 (Khariberia) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000261/2020-2021 | 2877/TD | 11/02/2021 | 20 | TAPAN BERA | 4.84 | 0 | 100
1199 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (102 nos) under JJM in Tajpur PWSS within Tajpur (P) J.L.- 210 (Tajpur Dakshin Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000262/2020-2021 | 2878/TD | 11/02/2021 | 20 | BUNBA CONSTRUCTION | 4.85 | 0 | 100
1200 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (673 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185 (Dakshin Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-C) [2nd Call] | Assistant Engineer | Junior Engineer | ORD/000273/2020-2021 | 2926/TD | 22/02/2021 | 25 | TARUN KOLEY | 31.71 | 0 | 100
1201 | Tamluk Division | Haldia Sub-Division | Earth filling at Boosting Tubewell site of Tajpur PWSS within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000409/2024-2025 | 1071/HSD, | 05/11/2024 | 10 | M/S SOURAV MAHAPATRA | 2.46 | 0 | 100
1202 | Tamluk Division | Haldia Sub-Division | Laying Left Out UPVC pipe line of Mouza- Di-jamtalya for Tajpur & its adjoinin Mouzas Water Supply Scheme within Nandigram - I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000527/2021-2022 | 1944/TD | 03/03/2022 | 15 | MRITYUNJOY PARIA | 4.85 | 4.64 | 100
1203 | Tamluk Division | Haldia Sub-Division | Construction of Approach Road for Mahammadpur PWSS RCC Elevated Reservoir of Capacity 350 Cum. Within Nandigram-I Block under Haldia Sub-Division of Tamluk Division., P.H.E. Dte.Length = 150.00 Mtr Width = 3.0 Mtr. Thickness = 150 mm | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 983/TD | 13/03/2024 | 40 | SATYABRATA BHAUMIK | 5.74 | 5.74 | 100
1204 | Tamluk Division | Haldia Sub-Division | Retrofitting of accommodate FHTC 100 Nos. under JJM in Mahammadpur W/S Scheme within Nandigram - I Block. | Assistant Engineer | Junior Engineer | VCH/000192/2021-2022 | BP-2021-22-60 | 13/08/2021 | 0 | TAPAN BERA | 4.84 | 0 | 0
1205 | Tamluk Division | Haldia Sub-Division | Sinking of 1(one) nos. 100 mm X 50 mm dia. X 280.0 m(av.) depth, Tube well with PVC Pipes including cost of all materials near Sahid Bedi Ashwini Mal house S/O of Bhupendranath Pal Dag No.3261 & 3262 JL No.241 Mouza Gokulnagar at Gokulnagar Gram Panchayat within Nandigram-I Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000478/2024-2025 | 1250/HSD, | 16/12/2024 | 10 | S.D. CONSTRUCTION | 2.79 | 0 | 100
1206 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC for Tajpur W/S Scheme | Assistant Engineer | Junior Engineer | VCH/000201/2021-2022 | BP-2021-22-62 | 13/08/2021 | 0 | BUMBA CONSTRUCTION | 4.84 | 0 | 0
1207 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC 741 Nos. connection under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | VCH/000253/2021-2022 | BP-2021-22-72 | 04/09/2021 | 0 | NARAYAN CHANDRA DAS | 16.12 | 0 | 0
1208 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate for 409 Nos. FHTC connection under JJM in Tajpur W/S Scheme within Nandigram - I Dev. Block Block under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | VCH/000255/2021-2022 | BP-2021-22-69 | 04/09/2021 | 0 | MRITYUNJOY PARIA | 6.98 | 0 | 0
1209 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC (673 Nos.) under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000322/2021-2022 | BP-2021-22-88 | 05/10/2021 | 0 | TARUN KOLEY | 32.35 | 0 | 0
1210 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC 590 Nos. connection under JJM Tajpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer | Junior Engineer | VCH/000349/2021-2022 | BP-2021-22-118 | 05/10/2021 | 0 | KRISHNENDU SEKHAR DAS | 13.48 | 0 | 0
1211 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001097/2020-2021 | 1102/W | 30/03/2021 | 0 | SK. NUR ISLAM | 12 | 0 | 0
1212 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001098/2020-2021 | 1095/W | 30/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 14.5 | 0 | 0
1213 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Mahammadpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001109/2020-2021 | 1093/W | 30/03/2021 | 0 | NARAYAN CHANDRA DAS | 19.15 | 0 | 0
1214 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM in Tajpur W/S Scheme within Nandigram ¿ I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001136/2020-2021 | 1097/W | 30/03/2021 | 0 | DEBASIS DAS | 13.78 | 0 | 0
1215 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. |  |  | ORD/000225/2020-2021 | 2843/TD | 08/02/2021 | 70 | RAJ KUMAR SINGHA | 222.76 | 0 | 100
1216 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000107/2021-2022 |  | 23/06/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0
1217 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000240/2021-2022 | BP-2021-22-34 | 23/07/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0
1218 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000310/2021-2022 |  | 16/09/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0
1219 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000423/2021-2022 | BP-2021-22-105 | 05/10/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0
1220 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001137/2020-2021 | 1090/W | 30/03/2021 | 0 | RAJ KUMAR SINGHA | 28.06 | 0 | 0
1221 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sankarpur PWSS Block - Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000124/2020-2021 | 2637/TD | 05/01/2021 | 60 | MAITY CONSTRUCTION | 94.92 | 186.18 | 100
1222 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 65
1223 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block-Ramnagar-II in the District of Purba Medinipur. |  |  | ORD/000123/2020-2021 | 2634/TD | 05/01/2021 | 60 | BASANTA KUMAR MAITY | 96.58 | 3.47 | 100
1224 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 2.67 | 65
1225 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001037/2020-2021 | 715/W | 09/02/2021 | 0 | BASANTA KUMAR MAITY | 59.24 | 0 | 0
1226 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001160/2020-2021 | BP-2021-22-29 | 19/07/2021 | 0 | BASANTA KUMAR MAITY | 13.32 | 0 | 0
1227 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001244/2020-2021 | 991/W | 26/03/2021 | 0 | BASANTA KUMAR MAITY | 20.5 | 0 | 0
1228 | Tamluk Division |  | Rejuvenation to accommodate FHTC (670 nos.) under JJM in BADHIA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( Phase -II ) |  |  | ORD/000098/2021-2022 | 691/TD | 10/09/2021 | 20 | AJIT KUMAR SOM | 94.24 | 89.52 | 100
1229 | Tamluk Division |  | Supply of C.I D.F sluice valve to accommodate FHTC under JJM in BADHYA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( phase -II ) |  |  | ORD/000349/2021-2022 | 617/DSD | 31/01/2022 | 15 | AJIT KUMAR SOM | 1.03 | 1.03 | 100
1230 | Tamluk Division |  | Laying ( Left Out ) UPVC pipe line to accommodate FHTC under JJM in Badhya PWSS within Ramnagar-I Block ( To support Phase-I FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. ( Mouza- Kachum, Bakharpur, Khandagram, Badhya) |  |  | ORD/000543/2021-2022 | 2003/TD | 08/03/2022 | 25 | R CONSTRUCTION | 10.79 | 10.79 | 100
1231 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 1234/TD | 09/12/2021 | 0 | Resource Division | 0.08 | 0 | 0
1232 | Tamluk Division |  | Retrofitting to accomodate FHTC (1487 nos.) under JJM in Paschim Kamarda PWSS Block - Contai-III under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) |  |  | ORD/000010/2021-2022 | 688/TD | 10/09/2021 | 50 | RAJ KUMAR SINGHA | 96.99 | 170.64 | 100
1233 | Tamluk Division |  | Sinking of 2 (two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Tubewell Site (Mouza- Panbhuni, JL No. - 163, Plot No. 551) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube Tubewell Site (Mouza- Nilpur, JL No. - 160, Plot No. 318) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000271/2022-2023 | 1095/TD | 25/08/2022 | 21 | M/S SYCHROTECH INDUSTRY | 26.31 | 0 | 0
1234 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block - Contai-II in the District of Purba Medinipur. Mouza- Sofiabad(497),Dholmari(498),Kultalia(500),(Phase-II) |  |  | ORD/000129/2021-2022 | 1009/TD | 02/11/2021 | 30 | RELIABLE CONSTRUCTIONS | 35.54 | 35.66 | 100
1235 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 2162/TD | 05/07/2024 | 0 | Resource Division | 0.81 | 0 | 0
1236 | Tamluk Division |  | Supply & Delivery of different dia C.I.D.F. Sluice Valve for Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the district of Purba Medinipur (Phase-II) under Contai Sub- Division, of Tamluk Division, PHE Dte. |  |  | ORD/000046/2022-2023 | 12/A/CSD | 05/04/2022 | 15 | SRIMANTA KUMAR MAITY | 1.89 | 1.89 | 100
1237 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Haipur PWSS Block-Contai-I in the district of Purba Medinipur.(Phase-II) |  |  | ORD/000296/2021-2022 | 1637/TD | 19/01/2022 | 60 | SRIMANTA KUMAR MAITY | 118.38 | 105.84 | 100
1238 | Central Drilling |  | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000082/2021-2022 | 429/CMSD-II (D) | 30/09/2021 | 15 | S B S ENTERPRISE | 0.41 | 0.41 | 100
1239 | Central Drilling |  | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAZIPUR PWSS TW-I, GOGHAT-II, BLOCK HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000083/2021-2022 | 428/CMSD-II (D) | 30/09/2021 | 15 | S B S ENTERPRISE | 0.96 | 0.79 | 100
1240 | Central Drilling |  | Supply & Delivery of 12 1/4" dia RR Bit for Drilling work at haipur PWSS, Dist. Purba Midnapore under CDD,PHE Dte. |  |  | ORD/000133/2022-2023 | 253/CMSD-I(D) | 23/06/2022 | 15 | DAS ENTERPRISE | 4.65 | 4.65 | 100
1241 | Central Drilling |  | SEALING BORE- HOLE ANNULAR SPACE AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HAIPUR PWSS UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000202/2021-2022 | 188/CMSD-I (D) | 30/09/2021 | 7 | MENAKA ENTERPRISE | 0.6 | 0.6 | 100
1242 | Central Drilling |  | SUPPLY & DELIBVERY OF 9 7/8'' DIA RR BIT FOR DRILLING WORK AT HAIPUR PWSS, DISTRICT PURBA MEDINIPUR AND OTHER PWSS UNDER CDD, PHE DTE. |  |  | ORD/000248/2022-2023 | 249/CMSD-I | 22/06/2022 | 15 | M.S. ENTERPRISE | 4.21 | 4.21 | 100
1243 | Central Drilling |  | SUPPLY & DELIVERY OF COMPRESSOR PIPE AND HOSE AT SITE FOR COMPRESSOR UNIT ATTACHED WITH RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000274/2021-2022 | 65/CMSD-I (D) | 22/03/2022 | 7 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100
1244 | Central Drilling |  | REPAIRING OF DAMAGE TRUCK DRIVER CABIN, STEEL BODY, CHEQUER PLATE, CHASSIS AND TRUCK BODY PAINTING OF GOVT VEHICLE NO. WMK 6422 (TATA) UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000276/2022-2023 | 77/CMSD-I | 01/04/2022 | 15 | M/S B.P.TRADING CORPORATION | 2.36 | 0.79 | 0
1245 | Central Drilling |  | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. |  |  | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.35 | 0
1246 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC (245 nos.) at Jashdumbur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000022/2022-2023 | 64/TD | 05/04/2022 | 20 | PULAK KUMAR SAMANTA | 28.02 | 23.63 | 100
1247 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-1) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000095/2022-2023 | 455/TD | 01/06/2022 | 15 | GRAND CONSTRUCTION | 4.84 | 4.78 | 100
1248 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-2) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000096/2022-2023 | 456/TD | 01/06/2022 | 15 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.84 | 4.82 | 100
1249 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-3) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000097/2022-2023 | 457/TD | 01/06/2022 | 15 | MISHRA ENTERPRISE | 4.84 | 4.83 | 100
1250 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-4) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000098/2022-2023 | 458/TD | 01/06/2022 | 15 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100
1251 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-A(PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000177/2023-2024 | 334/TD | 25/04/2023 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 58.58 | 54.39 | 100
1252 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-C-B(PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000178/2023-2024 | 335/TD | 25/04/2023 | 20 | PULAK KUMAR SAMANTA | 6.91 | 5.83 | 100
1253 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with earth of approach road and other side of 3rd T/W site at Bishnubar Water Supply scheme of Tamluk Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000206/2022-2023 | 857/TD | 21/07/2022 | 7 | KRISHNENDU SEKHAR DAS | 4.82 | 4.8 | 100
1254 | Tamluk Division | Tamluk Sadar Sub-Division | Repair & renovation of exisiting pump house and boundary wall at OHR site & 2nd tube well site of Bishnubar PWSS Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000366/2023-2024 | 934/TD | 01/06/2023 | 30 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 18.32 | 0 | 100
1255 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000368/2021-2022 | 1632/TD | 18/01/2022 | 20 | HORIZEN | 3.35 | 3.35 | 100
1256 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Purbakola Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- G ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000380/2022-2023 | 1364/TD | 22/09/2022 | 25 | SOUMYA ENTERPRISE | 30.53 | 30.43 | 30
1257 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Bishnubar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000546/2022-2023 | 2164/TD | 19/12/2022 | 60 | SK. SAHALAM | 5.11 | 5.1 | 100
1258 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Bishnubar & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000447/2022-2023 | 1820/TD | 14/11/2022 | 870 | HARIPADA PATTANAYAK | 163.96 | 116.5 | 100
1259 | Tamluk Division | Tamluk Sadar Sub-Division | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 3nd tube well site under Bishnubar Water Supply Scheme. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000547/2022-2023 | 2165/TD | 19/12/2022 | 45 | SK. SAHALAM | 5.83 | 5.81 | 0
1260 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-A-5) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000606/2021-2022 | 2194/TD | 21/03/2022 | 20 | MADAN MOHAN MAITY | 23.06 | 22.96 | 100
1261 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000607/2021-2022 | 2195/TD | 21/03/2022 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 39.96 | 39.89 | 100
1262 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000608/2021-2022 | 2196/TD | 21/03/2022 | 20 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.98 | 20.77 | 100
1263 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jashdumber Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000609/2021-2022 | 2197/TD | 21/03/2022 | 30 | GHOSH ENTERPRISE | 45.02 | 44.98 | 85
1264 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Maishali Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000610/2021-2022 | 2198/TD | 21/03/2022 | 35 | BIDHAN MONDAL | 74.98 | 60.06 | 100
1265 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Melahait & Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- E & I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000611/2021-2022 | 2199/TD | 21/03/2022 | 35 | KRISHNENDU SEKHAR DAS | 74.87 | 74.82 | 85
1266 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Naikuri Jagannath Chak-I & Khas Panchpukhuria Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- F & J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000612/2021-2022 | 2200/TD | 21/03/2022 | 35 | S.K. MONDAL | 77.9 | 77.77 | 100
1267 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Hirapur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-A ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000613/2021-2022 | 2201/TD | 21/03/2022 | 20 | G. S. CONSTRUCTION | 20.87 | 11.62 | 100
1268 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000614/2021-2022 | 2202/TD | 21/03/2022 | 20 | DEBDUT CONSTRUCTION | 20.89 | 20.57 | 100
1269 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000003/2022-2023 | 80/TD | 08/04/2022 | 0 | Resource Division | 38.98 | 0 | 0
1270 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000059/2021-2022 | 2350/TD | 31/03/2022 | 0 | Resource Division | 23.8 | 0 | 0
1271 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000217/2023-2024 | 1117/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1272 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BISHNUBAR W/S SCH (TW-III), TAMLIK BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000168/2022-2023 | 431/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 5.58 | 100
1273 | Central Drilling | Tamluk Sadar Sub-Division | SUPPLY & DELIVERY OF CONSUMABLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR, NANDAKUMAR BLOCK, DIST : PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000174/2022-2023 | 145/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.97 | 90
1274 | Central Drilling | Tamluk Sadar Sub-Division | ADDITIONAL DEVELOPMENT OF TUBE WELL BY AIR COMPRESSOR WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR SCHEME (TW-III) UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000175/2022-2023 | 360/CMSD-II | 15/07/2022 | 10 | PADMA ENGINEERING & CO. | 0.99 | 0.97 | 0
1275 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BISHNUBAR W/S SCH, NANDAKUMAR BLOCK, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000181/2022-2023 | 144/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.98 | 100
1276 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Bishnubar PWSS Tube Well-III WS Scheme Additional TW (Ref. ID - 203930212) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00321/2022-2023 | BP-2022-23-140 | 20/03/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
1277 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001547/2022-2023 | 405/W/MMD | 16/03/2023 | 180 | DAS ENTERPRISE | 35.46 | 11.06 | 61
1278 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (2488 nos.) under JJM in MUKUNDAPUR PWSS Block- Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000041/2022-2023 | 172/TD | 25/04/2022 | 30 | M/S EL-CON | 90.6 | 0 | 60
1279 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to damaged by the construction of connecting Road & to Accommodate balance FHTC (290 Nos) with allied work for Mukundapur Piped Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 3065/TD | 19/09/2024 | 30 | BASANTA KUMAR MAITY | 35.18 | 0 | 0
1280 | Tamluk Division |  | Retrofitting to accommodate FHTC (300 Nos.) under JJM in Srirampur PWSS (PART-I) Block - Tamluk in the District of Purba Medinipur. |  |  | ORD/000154/2021-2022 | 1125/TD | 22/11/2021 | 40 | GHOSH ENTERPRISE | 19.58 | 18.98 | 100
1281 | Tamluk Division | Contai Sub-Division | Renovation and new Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Bhagabanpur Zone-II Water Supply Scheme in Bhagabanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2025-2026 | 1077/TD | 07/04/2025 | 40 | RAI CONSTRUCTION | 18.27 | 0 | 0
1282 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000140/2022-2023 | 691/TD | 27/06/2022 | 180 | TAPAS SANTRA | 597.73 | 567.16 | 82
1283 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-II Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000151/2022-2023 | 726/TD | 04/07/2022 | 180 | TARUN KOLEY | 595.09 | 532.66 | 83
1284 | Tamluk Division | Contai Sub-Division | Laying of 200 mm dia & 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well & 2nd Tube well to 3rd Tube Well (Additional) of Augmentation of Bhagwanpur Zone II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000166/2023-2024 | 297/TD | 20/04/2023 | 30 | BARH CONSTRUCTION | 11.04 | 8.14 | 100
1285 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000228/2022-2023 | 893/TD | 25/07/2022 | 15 | SRIMANTA KUMAR MAITY | 4.8 | 4.8 | 100
1286 | Tamluk Division | Contai Sub-Division | Construction and Commissioning of R.C.C. Over Head Reservoir of capacity 500 cum and staging height 20.00 mtr, as per Departmental Drawing no-PC-1/O.H.R./5/2012 for Rejuvination of Bhagwanpur Zone-I Water Supply Scheme under Bhagwanpur-I Block of Contai sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000238/2020-2021 | 2839/TD | 05/02/2021 | 200 | DAS CONSTRUCTION | 118.1 | 15.5 | 90
1287 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia UPVC pipe lines with allied works to accommodate Total 5666 nos FHTC of Augmentation of Bhagwanpur Zone-I & its adjoining mouzas W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2023-2024 | 623/TD | 17/05/2023 | 30 | TAPAS SANTRA | 67.97 | 55.64 | 85
1288 | Tamluk Division | Contai Sub-Division | Repairing of Boundary Wall, and Pump House (1st & 2nd) under JJM with allied work for Augmentation of Bhagabanpur Zone -II PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000317/2024-2025 | 3216/TD | 01/10/2024 | 120 | SAMIT KUMAR MONDAL | 8.34 | 0 | 100
1289 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, Approach Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000333/2024-2025 | 3293/TD | 05/10/2024 | 160 | SAMIT KUMAR MONDAL | 31.76 | 0 | 60
1290 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 857 | B. K. ENTERPRISE | 34.31 | 0 | 0
1291 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-II W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000348/2022-2023 | 1281/TD | 12/09/2022 | 60 | BISWA NIRMAN ENTERPRISE. | 3.82 | 3.73 | 100
1292 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-II Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) 2nd Call. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000357/2022-2023 | 1299/TD | 13/09/2022 | 15 | NANDY UDYOG | 4.83 | 4.83 | 100
1293 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-I piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000358/2022-2023 | 1297/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.41 | 3.41 | 100
1294 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tube Well site for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000400/2022-2023 | 1344/TD | 19/09/2022 | 60 | M/S SOURAV MAHAPATRA | 3.82 | 0 | 0
1295 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-I W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2022-2023 | 1345/TD | 19/09/2022 | 60 | GIRI CONSTRUCTION | 3.82 | 3.68 | 100
1296 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-II piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2022-2023 | 1300/TD | 13/09/2022 | 15 | PARTHA CONSTRUCTION | 3.23 | 3.23 | 100
1297 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000445/2021-2022 | 1676/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.46 | 4.46 | 100
1298 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000446/2021-2022 | 1677/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.19 | 4.19 | 100
1299 | Tamluk Division | Contai Sub-Division | Interconection work Between 2nd pump and 3rd pump , of Augementation of Bhagabanpur Zone-II water supply scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000568/2024-2025 | 2445/CSD | 22/10/2024 | 21 | BARH CONSTRUCTION | 0.52 | 0 | 0
1300 | Tamluk Division | Contai Sub-Division | Construction of Approach Road at 4th TW site for Augmentation of Bhagabanpur Zone-I PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur.(Length-58 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000598/2024-2025 | 570/TD | 17/02/2025 | 25 | CHANDA AGENCIES | 4.92 | 0 | 0
1301 | Tamluk Division | Contai Sub-Division | Laying of Rising Main DI(K9) pipe line with CIDF Pipe & Speacials for interconnection in between 3rd TW & OHR of Augmentation of Bhagabanpur Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000647/2023-2024 | 2597/TD | 10/10/2023 | 20 | TAPAS SANTRA | 9.63 | 0 | 100
1302 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Bhagabanpur Zone-II PWSS in Bhagwanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-50.00 mtr.)For Low Land. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000686/2023-2024 | 2696/TD | 17/10/2023 | 30 | BHOWMIK & SONS | 8.66 | 6.39 | 100
1303 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia UPVC Pipe Lines With allied works to accommodate Total 4010 nos FHTC of Augementation of Bhagabanpur Zone -II Water Supply Scheme within Bhagabanpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000708/2023-2024 | 2874/TD | 17/11/2023 | 30 | TARUN KOLEY | 79.77 | 78.53 | 100
1304 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, Approch Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001180/2023-2024 | 725/TD | 28/02/2024 | 40 | M/S. PRADIP PRADHAN | 32.11 | 0 | 0
1305 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000015/2022-2023 | 403/TD | 25/05/2022 | 0 | Resource Division | 102.66 | 0 | 0
1306 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000016/2022-2023 | 404/TD | 25/05/2022 | 0 | Resource Division | 28.11 | 0 | 0
1307 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000090/2022-2023 | 1272/TD | 12/09/2022 | 0 | Resource Division | 59.54 | 0 | 0
1308 | Central Drilling | Contai Sub-Division | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL FOR BHAGAWANPUR W/S SCHEME TW-III, ZONE-I, PURBA MEDINIPU DISTRICT BY UTILISING SKILLED CREW & DEPARTMENTAL MACHINERRIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000113/2023-2024 | 92/CMSD-II | 17/04/2023 | 15 | PADMA ENGINEERING & CO. | 1 | 0.32 | 100
1309 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCH (TW-III), BHAGAWANPUR-II BLOCK UNDER PURBA MEDNAIPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000314/2022-2023 | 1347/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.77 | 17.45 | 100
1310 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION F TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BHAGWANPUR W/S SCHEME, TW-III, Z-I, BLOCK BHAGAWANPUR-I, UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000411/2022-2023 | 2115/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 16.63 | 0
1311 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Bhagwanpur Zone-II, TW - III (Ref. ID - 203964030) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00108/2023-2024 | BP-2023-24-30 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
1312 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BHAGWANPUR Water Supply Scheme Z-I, T/W-III (Ref. ID-204049532 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01631/2023-2024 | BP-2023-24-137 | 27/07/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
1313 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-IV Of BHAGWANPUR, ZONE-I W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-I, WBSEDCL : BHAGWANPUR C.C.C. Ref. Memo No- 2005615115/QUOT/03 DT. 16-02-2026 Application NO- 2005615115 Application type-New connection Reference Id- 204813268 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/06148/2025-2026 |  | 11/03/2026 | 0 | WBSEDCL | 5.31 | 0 | 0
1314 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
1315 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001929/2022-2023 | 848/W/MMD | 24/03/2023 | 180 | BHABANI PRASAD MANNA | 59.25 | 18.74 | 35
1316 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Kapaseria Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000050/2022-2023 | 269/TD | 02/05/2022 | 1520 | MONDAL PRECISION PRIVATE LIMITED | 222.44 | 119.87 | 60
1317 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kapasberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000163/2021-2022 | 1167/TD | 01/12/2021 | 7 | HORIZEN | 3.42 | 3.31 | 100
1318 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.52 | 100
1319 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kapaseria Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000387/2023-2024 | 1051/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.73 | 3.73 | 100
1320 | Tamluk Division | Haldia Sub-Division | Construction of New Boundary Wall at H/W site & 2nd TW Site of Kapasaria Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall- 80mtr at H/W Site & 50mtr at 2nd TW Site) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000514/2024-2025 | 3948/TD | 23/12/2024 | 190 | ANIRBAN BHOWMIK | 15.18 | 0 | 0
1321 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection including repairing & renovation of switch room cum chlorine room at Head work site of Kapasaria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000697/2023-2024 | 2737/TD | 01/11/2023 | 20 | R CONSTRUCTION | 8.2 | 6.06 | 10
1322 | Tamluk Division | Haldia Sub-Division | Construction Temporary Approach road by Brick Bats & Carried Earth over Nayanjuli of PWD Roads for H/W Site of Kapasaria W/S Scheme for accessibility of Rig Machine and removal of road materials from Nayanjuli of PWD Roads under Haldia Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000812/2023-2024 | 576/HSD, | 08/12/2023 | 7 | SNEHASIS BERA | 0.8 | 0.8 | 100
1323 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Kapaseria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000822/2023-2024 | 3286/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.41 | 1.04 | 30
1324 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000012/2021-2022 | 1254/TD | 13/12/2021 | 0 | Resource Division | 10.46 | 0 | 0
1325 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000043/2021-2022 | 639/TD | 27/06/2022 | 0 | Resource Division | 5.6 | 0 | 0
1326 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme, Block Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001908/2022-2023 | 809/W/MMD | 24/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 12.86 | 90
1327 | Tamluk Division | Digha Sub-Division | Repairing of Existing pipe line with allied works for non functional to functional FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000042/2025-2026 | 42/DSD | 11/04/2025 | 7 | ABHIJIT BERA | 0.97 | 0 | 100
1328 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000172/2021-2022 | 1181/TD | 02/12/2021 | 20 | HORIZEN | 6.91 | 5.92 | 100
1329 | Tamluk Division | Digha Sub-Division | Supply of 125 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000211/2022-2023 | 323/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 1.32 | 1.32 | 100
1330 | Tamluk Division | Digha Sub-Division | Supply of 80 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000371/2022-2023 | 1049/TD | 17/08/2022 | 7 | BASANTA KUMAR MAITY | 4.72 | 4.72 | 100
1331 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house I & II, Boundary Wall at head works & 2nd tube well site of Kalindi Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000372/2024-2025 | 3401/TD | 28/10/2024 | 40 | DAS ENTERPRISE. | 9.65 | 0 | 0
1332 | Tamluk Division | Digha Sub-Division | Supply & delevary of 100 mm,200mm,150mm & 250mm dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000445/2022-2023 | 1155/TD | 31/08/2022 | 7 | BASANTA KUMAR MAITY | 4.28 | 4.28 | 100
1333 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line by UPVC pipes with allied works for complete balance FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000468/2023-2024 | 1449/TD | 13/07/2023 | 30 | BASANTA KUMAR MAITY | 24.44 | 23.58 | 100
1334 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Kalindi Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000605/2021-2022 | 2185/TD | 17/03/2022 | 180 | BASANTA KUMAR MAITY | 533.41 | 376.04 | 50
1335 | Tamluk Division | Digha Sub-Division | Laying Rising Main Pipe Line With allied Works For Augmentation Of KALINDI Water Supply Scheme In Ramnagar-II Block Of Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000872/2022-2023 | 3223/TD | 14/03/2023 | 20 | ABHIJIT BERA | 6.86 | 6.34 | 100
1336 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000018/2021-2022 | 1260/TD | 13/12/2021 | 0 | Resource Division | 21.19 | 0 | 0
1337 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000051/2021-2022 | 2348/TD | 31/03/2022 | 0 | Resource Division | 16.82 | 0 | 0
1338 | Central Drilling | Digha Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 240 mtrs. Depth) by utilising Departmental machineries for Kalindi W/S Scheme(TW-I), Ramnagar-II block under Purba medinipur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000016/2023-2024 | 857/CDD | 10/07/2023 | 30 | MENAKA ENTERPRISE | 18.74 | 14.63 | 100
1339 | Central Drilling | Digha Sub-Division | Providing drilling crews Including Allied Materials for construction of Tube Well at Kalindi within Ramnagar-II Block, District Purba Medinipur under Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000125/2023-2024 | 1536/CDD | 06/10/2023 | 180 | MENAKA ENTERPRISE | 8.73 | 5.11 | 100
1340 | Central Drilling | Digha Sub-Division | Resistivity Survey and other works of Kalindi WS Scheme (TW-Il) , Ramnagar-ll Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000512/2022-2023 | 1540/CDD | 08/12/2022 | 480 | MENAKA ENTERPRISE | 12.67 | 9.92 | 100
1341 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 53/TD | 05/04/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 150.85 | 99.71 | 90
1342 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 137/TD | 19/04/2022 | 90 | ASIS KUMAR SARANGI | 192.27 | 114.53 | 90
1343 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Haur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2021-2022 | 1191/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.95 | 5.95 | 100
1344 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Left out portion of pipe line Rejuvenation & Retrofitting of of HAUR PWSS under Tamluk Sub Division, PHE Dte. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 3064/TD | 19/09/2024 | 25 | KAMALA ENTERPRISE | 14.42 | 0 | 100
1345 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of Boundary Wall ( 1mtr height) & Painting Pump House and Boundary wall & other allied works at 1 st TW site, Dismantling of Existing B/W & Construction of Boundary Wall with Gate and along PCC road & other allied works at 2nd TW site of Haur Pipe Water Supply Scheme, within Panskura-I Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000632/2024-2025 | 736/TD | 07/03/2025 | 40 | SINHA BUILDERS | 9.71 | 0 | 0
1346 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2021-2022 | 2343/TD | 31/03/2022 | 0 | Resource Division | 11.07 | 0 | 0
1347 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000211/2023-2024 | 1111/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1348 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -X(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000117/2020-2021 | 2504/TD | 23/12/2020 | 60 | JAYANTA KUMAR MONDAL | 96.37 | 192.59 | 100
1349 | Tamluk Division | Contai Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00707/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.18 | 0 | 0
1350 | Tamluk Division | Contai Sub-Division | Bill for Restoration of damage of Heria Mugberia Road at 1.80 KM caused due to lying of PHE water pipe line across the road under Tamluk Highway Division of Mukutshilla Zone-II PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00989/2024-2025 | BP-2024-25-495 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.19 | 0 | 0
1351 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000245/2022-2023 | 1002/TD | 08/08/2022 | 1302 | GIRI CONSTRUCTION | 106.79 | 92.03 | 88
1352 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -B). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000248/2022-2023 | 1039/TD | 16/08/2022 | 45 | I. S. ENTERPRISE. | 154.56 | 102.85 | 70
1353 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000258/2022-2023 | 1079/TD | 23/08/2022 | 1196 | RELIABLE CONSTRUCTIONS | 130.52 | 103.15 | 80
1354 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 60.86 | 18
1355 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000365/2022-2023 | 1332/TD | 16/09/2022 | 20 | PULAK KUMAR SAMANTA | 28 | 23.39 | 85
1356 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000366/2022-2023 | 1333/TD | 16/09/2022 | 20 | SUBRATA KUMAR BERA | 35.6 | 23.71 | 70
1357 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000367/2022-2023 | 1334/TD | 16/09/2022 | 25 | THREE MAA ENTERPRISE | 41.22 | 29.45 | 85
1358 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000368/2022-2023 | 1335/TD | 16/09/2022 | 25 | ANUSKA ENTERPRISE | 51.96 | 38.82 | 75
1359 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000374/2022-2023 | 1338/TD | 16/09/2022 | 30 | A. K. SIKDAR | 69.34 | 36.22 | 60
1360 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2022-2023 | 1387/TD | 23/09/2022 | 25 | NEW STAR CONSTRUCTION | 76.73 | 68.22 | 85
1361 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000529/2022-2023 | 2100/TD | 13/12/2022 | 1193 | M/S. NEW DINDA ENTERPRISE | 41.85 | 39.6 | 85
1362 | Tamluk Division | Contai Sub-Division | Land Filling & allied works for Boosting Tube Well (5Th TW) site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000546/2023-2024 | 1488/A/CSD | 03/08/2023 | 15 | KAMAL KUMAR BERA | 0.72 | 0.71 | 100
1363 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000564/2022-2023 | 2241/TD | 29/12/2022 | 20 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LIMITED | 32.16 | 19.73 | 65
1364 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000668/2022-2023 | 2341/TD | 10/01/2023 | 25 | MRINAL KANTI PRADHAN | 44.01 | 32.43 | 0
1365 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000055/2022-2023 | 1195/TD | 06/09/2022 | 0 | Resource Division | 186.74 | 0 | 0
1366 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000065/2022-2023 | 1197/TD | 06/09/2022 | 0 | Resource Division | 47.95 | 0 | 0
1367 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MUKUTSHILA, Water Supply Scheme T/W-V, Zone-II (Ref. ID-204049558) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01672/2023-2024 | BP-2023-24-162 | 04/08/2023 | 0 | WBSEDCL | 2.26 | 0 | 0
1368 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, MUKUTSHILA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049562) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01680/2023-2024 | BP-2023-24-160 | 04/08/2023 | 0 | WBSEDCL | 1.51 | 0 | 0
1369 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2)under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000149/2023-2024 | 1377/W/MMD | 30/05/2023 | 180 | MENAKA ENTERPRISE | 35.5 | 31.24 | 75
1370 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID ¿ SER-KGP-2023-WL-33 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00373/2023-2024 | BP-2023-24-204 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
1371 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-31 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00374/2023-2024 | BP-2023-24-202 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
1372 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-32 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00375/2023-2024 | BP-2023-24-203 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
1373 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-30 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00376/2023-2024 | BP-2023-24-201 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
1374 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID-SER-KGP-2023-WL-34 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00493/2023-2024 | BP-2023-24-256 | 10/08/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0
1375 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000012/2022-2023 | 46/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 100
1376 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-B for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000131/2024-2025 | 1911/TD | 07/06/2024 | 25 | DEBABRATA DAS | 14.72 | 14.31 | 90
1377 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-D for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000137/2024-2025 | 1948/TD | 10/06/2024 | 244 | DEBABRATA DAS | 10.35 | 2.68 | 80
1378 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of (PART M) for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri I Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000281/2024-2025 | 3036/TD | 18/09/2024 | 543 | M/S. NEW DINDA ENTERPRISE | 4.18 | 0 | 0
1379 | Tamluk Division | Contai Sub-Division | Laying Distribution pipe line by HDPE pipes with allied works for Left Out Area of PART-K for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000286/2024-2025 | 3051/TD | 19/09/2024 | 542 | M/S. NEW DINDA ENTERPRISE | 49.94 | 0 | 0
1380 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorine Room & Boundary Wall at 2nd TW site & 1st TW site for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000354/2024-2025 | 3317/TD | 22/10/2024 | 40 | M/S. NEW DINDA ENTERPRISE | 7.08 | 0 | 100
1381 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 0 | 18
1382 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 49.28 | 48
1383 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-J for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000417/2024-2025 | 2184/CSD | 05/09/2024 | 150 | GIRI ENTERPRISE | 1.85 | 0 | 0
1384 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-A) In between OHE MAST NO 35/9 & 35/10, Nodal Point 255 TO 293. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000552/2024-2025 | 135/CSD | 16/01/2025 | 20 | BIBEKANANDA DAS | 1.16 | 0 | 100
1385 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-C) In between OHE MAST NO 33/17 & 33/18, Nodal Point 55 to 58. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000555/2024-2025 | 137/CSD | 16/01/2025 | 20 | JASODA ENTERPRISE | 1.16 | 0 | 100
1386 | Tamluk Division | Contai Sub-Division | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 4th Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000600/2024-2025 | 590/TD | 19/02/2025 | 30 | M/S. NEW DINDA ENTERPRISE | 4.09 | 0 | 0
1387 | Tamluk Division | Contai Sub-Division | Land Filling & allied works for 3rd TW site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000606/2023-2024 | 1490/CSD | 04/08/2023 | 15 | GIRI ENTERPRISE | 0.96 | 0.96 | 100
1388 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000723/2023-2024 | 0 | 28/11/2023 | 45 | GIRI CONSTRUCTION | 0 | 0 | 0
1389 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000842/2023-2024 | 2157/CSD | 04/12/2023 | 136 | GIRI CONSTRUCTION | 2.26 | 0 | 100
1390 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-D) In between OHE MAST NO 33/1 & 33/2 , Nodal Point 5 to 109. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000556/2024-2025 | 138/CSD | 16/01/2025 | 20 | DEBABRATA DAS | 1.16 | 0 | 100
1391 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-E) In between OHE MAST NO 31/13 & 31/14, Nodal Point 64 to 68. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000557/2024-2025 | 139/CSD | 16/01/2025 | 20 | M/S SREE DURGA ENTERPRISE | 1.16 | 0 | 100
1392 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-F) In between OHE MAST NO 32/4 & 32/5, Nodal Point 18 to 19. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000558/2024-2025 | 140/CSD | 16/01/2025 | 20 | DEBABRATA DAS | 1.16 | 0 | 100
1393 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO 32/4 & 32/5 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =46 Mtr) Nodal Point 18 to 19. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000713/2023-2024 | 2945/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 64.87 | 59.78 | 100
1394 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 31/13 & 31/14 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =38 Mtr) Nodal Point 64 to 68. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000714/2023-2024 | 2946/TD | 23/11/2023 | 25 | JOY GURU TRADING | 65.18 | 62.73 | 100
1395 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/1 & 33/2 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 5 to 109. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000716/2023-2024 | 2947/TD | 23/11/2023 | 25 | BISWAJIT BAG | 71.16 | 71.07 | 100
1396 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District.(PART Work Order - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000847/2023-2024 | 58/TD | 05/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 8.43 | 8.43 | 100
1397 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART Work Order- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000848/2023-2024 | 59/TD | 05/01/2024 | 20 | MAJI ENGINEERING WORKS | 0.96 | 0 | 0
1398 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-G for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001149/2023-2024 | 569/TD | 15/02/2024 | 20 | NEW STAR CONSTRUCTION | 9.63 | 9.52 | 100
1399 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/17 & 33/18 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 55 to 58. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000717/2023-2024 | 2948/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 68.36 | 67.46 | 100
1400 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 34/2 & 34/3 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =54 Mtr) Nodal Point 253 to 182. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000718/2023-2024 | 2949/TD | 23/11/2023 | 25 | ZENITH CONSTRUCTION | 69.67 | 64.84 | 100
1401 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-H for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001150/2023-2024 | 570/TD | 15/02/2024 | 20 | PULAK KUMAR SAMANTA | 6.98 | 0 | 80
1402 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-C for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001151/2023-2024 | 577/TD | 15/02/2024 | 20 | RELIABLE CONSTRUCTIONS | 13.64 | 9.1 | 100
1403 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 150 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 35/9 & 35/10 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =48Mtr) Nodal Point 255 TO 293. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001244/2023-2024 | 1078/TD | 16/03/2024 | 156 | R. B. ENTERPRISE | 62.73 | 0 | 100
1404 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 1000 cum RCC OHR at Mukutshila Z-II Water Supply Scheme at Khejuri-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001274/2023-2024 | 1048/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1405 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-L for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001280/2023-2024 | 726/TD | 28/02/2024 | 30 | ROY BISWAS CONSTRUCTION | 4.8 | 0 | 0
1406 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000069/2022-2023 | 1193/TD | 06/09/2022 | 0 | Resource Division | 97.03 | 0 | 0
1407 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000252/2022-2023 | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 0 | 32
1408 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000020/2023-2024 | 358/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
1409 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001759/2022-2023 | 639/W/MMD | 20/03/2023 | 180 | A.M.S. ENTERPRISE | 13.59 | 0 | 0
1410 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
1411 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000013/2022-2023 | 47/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 100
1412 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000014/2022-2023 | 48/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 8.67 | 0 | 100
1413 | Tamluk Division | Contai Sub-Division | Installation of display Board of Contai Saline Area Zone III (Zone-A) Augmentation PWSS at 4 nos. TW Site, Contai Saline Area Zone III (Zone-B) Augmentation PWSS at 1 no TW site in Contai-I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipurDistrict. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000286/2025-2026 | 1587/CSD | 19/06/2025 | 7 | M/S SREE DURGA ENTERPRISE | 0.83 | 0 | 0
1414 | Tamluk Division | Contai Sub-Division | Installation of display Board of Contai State Welfare Home PWSS at 1 nos TW site , Contai Municipalty PWSS at 1 nos TW site , Contai S.A. ZONE - III (Ghatua store ) PWSS at 1 nos TW site in Contai - I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000301/2025-2026 | 1600/CSD | 19/06/2025 | 7 | BISWA NIRMAN ENTERPRISE. | 0.5 | 0 | 0
1415 | Tamluk Division | Contai Sub-Division | Laying of Damaged HDPE Pipe line of 180 mm dia with allied works under Augmentation of Contai Saline area Zone-III( Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(N.P.-1074 -1084 Part) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000358/2025-2026 | 1342/CSD | 02/06/2025 | 21 | JASODA ENTERPRISE | 0.88 | 0 | 100
1416 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC (4893 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000513/2022-2023 | 2063/TD | 09/12/2022 | 841 | TARUN KOLEY | 1059.62 | 828.04 | 80
1417 | Tamluk Division | Contai Sub-Division | Renovation work of Spiral Staircase, Support UC Post For Raising Main line , Shutter Gate of Office Cum Godown at Contai Saline Area Zone -III ( Phase-A) W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000570/2024-2025 | 2447/CSD | 22/10/2024 | 21 | M/S SREE DURGA ENTERPRISE | 0.96 | 0 | 100
1418 | Tamluk Division | Contai Sub-Division | Pump House and Rising main, under Augmentation of Contai Saline Area Zone-III (Phase-B) PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000605/2023-2024 | 2199/TD | 01/09/2023 | 40 | S B ENTERPRISE | 25.16 | 19.96 | 100
1419 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000029/2023-2024 | 614/TD | 17/05/2023 | 0 | Resource Division | 30.14 | 0 | 0
1420 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between NACHINDA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I (Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (TD-46/09-10) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000559/2024-2025 | 141/CSD | 16/01/2025 | 20 | SUBHENDU HAZRA | 1.16 | 0 | 0
1421 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000667/2022-2023 | 2340/TD | 10/01/2023 | 40 | M/S SYCHROTECH INDUSTRY | 57.41 | 30.27 | 60
1422 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000108/2022-2023 | 1664/TD | 03/11/2022 | 0 | Resource Division | 325.57 | 0 | 0
1423 | Midnapore Mechanical | Contai Sub-Division | Contai S.A Zone -III W/S scheme PH-II Application no.-2004474775 ref.-204117777 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03195/2023-2024 |  | 15/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
1424 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of CONTAI S.A.REJ.(PHASE-B) W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005120731/QUOT/03 DT. 07-03-2025 Application NO- 2005120731 Application type-New connection Consumer Id- 204554509 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04973/2024-2025 |  | 20/03/2025 | 0 | WBSEDCL | 3.26 | 0 | 0
1425 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001918/2022-2023 | 822/W/MMD | 24/03/2023 | 720 | P.K.ENGINEERING | 40.78 | 28.91 | 80
1426 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia Janka Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000011/2022-2023 | 45/TD | 05/04/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 0 | 100
1427 | Tamluk Division | Contai Sub-Division | Repair and renovation of of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Length-78.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000199/2024-2025 | 2324/TD | 23/07/2024 | 40 | S.D. CONSTRUCTION | 10.42 | 0 | 0
1428 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000202/2023-2024 | 396/TD | 27/04/2023 | 20 | MA SARADA ENTERPRISE | 8.14 | 8.14 | 100
1429 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000203/2023-2024 | 397/TD | 27/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.02 | 2.02 | 100
1430 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works, Repair and renovation of Pump House, Toilet and others allied works at OHR's site under Shillaberia Zone-I Water Supply scheme (Augmentation) in Khjuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000236/2024-2025 | 2696/TD | 22/08/2024 | 240 | TAPAS SANTRA | 57.33 | 0 | 100
1431 | Tamluk Division | Contai Sub-Division | Land Development at 4th Tube Well site of Shillaberia Jhanka Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000416/2024-2025 | 2002/CSD | 06/08/2024 | 15 | GIRI CONSTRUCTION | 1.8 | 0 | 100
1432 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 251.77 | 70
1433 | Tamluk Division | Contai Sub-Division | Land Development at 3rd Tube Well site of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001285/2023-2024 | 369/CSD | 23/02/2024 | 15 | ABHIJIT BERA | 0.51 | 0 | 100
1434 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000102/2022-2023 | 1657/TD | 03/11/2022 | 0 | Resource Division | 106.02 | 0 | 0
1435 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-I (Ref. ID-204049557) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01674/2023-2024 | BP-2023-24-154 | 04/08/2023 | 0 | WBSEDCL | 2.55 | 0 | 0
1436 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Shilaberia Zone-I-1 no, Shilaberia Zone-II-1 no, Durmuth-1 no, Amarshikasba Zone-I-1 no, Amarshikasba Zone-II-1 no, Golaranij-1 no & Mukutshila Zone-I-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000509/2022-2023 | 809 / CSD | 21/10/2022 | 15 | THE GODFATHER TRADING COMPANY | 0.81 | 0.81 | 100
1437 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000825/2022-2023 | 3144/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 35.19 | 33.45 | 100
1438 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000862/2022-2023 | 3218/TD | 14/03/2023 | 843 | BARH CONSTRUCTION | 46.11 | 7.76 | 80
1439 | Midnapore Mechanical | Contai Sub-Division | ADDITIONAL QUOTATION FOR SHILSBERIA, ZONE-I W/S PH-IV UNDER JJM UNDER MIDNAPORE MECHANICAL DIVISION,PHE DTE. WBSEDCL CUSTOMER CARE OFFICE: KHEJURI C.C.C. BLOCK- KHEJURI-II MEMO NO: KJR/QI/392 Dated:18.12.2025 Reference ID: 860358767 DT.18.12.2025 Application ID:100000155107 DT.18.12.2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04138/2025-2026 |  | 23/12/2025 | 0 | WBSEDCL | 3.49 | 0 | 0
1440 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001911/2022-2023 | 812/W/MMD | 24/03/2023 | 714 | DEBJYOTI BASU | 54.33 | 28.88 | 25
1441 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000134/2023-2024 | 271/TD | 20/04/2023 | 906 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 97.2 | 56.76 | 60
1442 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-V) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000144/2023-2024 | 272/TD | 20/04/2023 | 60 | MRINAL KANTI PRADHAN | 61.5 | 41.07 | 60
1443 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VI) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000146/2023-2024 | 273/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 38.1 | 23.31 | 65
1444 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000147/2023-2024 | 274/TD | 20/04/2023 | 25 | DEBABRATA DAS | 10.89 | 7.92 | 74
1445 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VIII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000148/2023-2024 | 275/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 46.77 | 39.65 | 85
1446 | Tamluk Division | Contai Sub-Division | Trial boring of 100 mm x 50 mm dia x 280 mtr (av.) depth Tube well & sinking upto 200 mtr. depth with PVC pipes including cost of all materials for Tikashi PWSS ( 2nd TW Site) under Contai Sub Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000209/2024-2025 | 2383/TD | 26/07/2024 | 15 | BISWA NIRMAN ENTERPRISE. | 2.16 | 2.03 | 100
1447 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IV) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000242/2023-2024 | 509/TD | 11/05/2023 | 45 | B M ENTERPRISE | 81.75 | 40.93 | 60
1448 | Tamluk Division | Contai Sub-Division | Pump House , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000257/2023-2024 | 537/TD | 12/05/2023 | 1047 | GIRI CONSTRUCTION | 139.39 | 111.43 | 80
1449 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IX) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000383/2023-2024 | 1007/TD | 05/06/2023 | 25 | DEBABRATA DAS | 14.02 | 9.94 | 73
1450 | Tamluk Division | Contai Sub-Division | Pump House,350 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000385/2023-2024 | 1043/TD | 07/06/2023 | 1115 | TAPAS SANTRA | 245.15 | 134.79 | 85
1451 | Tamluk Division | Contai Sub-Division | Balance portion of dismantling, cement concrete and construction of sluice valve including supply of 100 mm dia GI pipe for laying of Distribution pipe line by HDPE pipes with allied works of TIKASHI- PWSS in Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-VIII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000460/2024-2025 | 2444/CSD | 22/10/2024 | 21 | ROZE SEKH | 0.94 | 0 | 100
1452 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Tikashi & Adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001175/2023-2024 | 2330/CSD | 29/12/2023 | 7 | M/S. NEW DINDA ENTERPRISE | 0.21 | 0.21 | 100
1453 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000065/2024-2025 | 2979/TD | 12/09/2024 | 0 | Resource Division | 15.26 | 0 | 0
1454 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000337/2022-2023 | 2978/TD | 27/02/2023 | 0 | Resource Division | 42.38 | 0 | 0
1455 | Central Drilling | Contai Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 280 mtrs. Depth) by utilising Departmental machineries for Tikashi W/S Scheme (TW-III), Khejuri-I block under Purba Midnapore District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000009/2023-2024 | 21/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 15.48 | 12.17 | 100
1456 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250 mm X 150mm X 280mm Depth) by utilising Departmental Machineries for Tikashi W/S Scheme(TW-I), Khejuri-I Block under Purba Medinipur District, CDD,P.H.E.Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000025/2023-2024 | 850/CDD | 10/07/2023 | 30 | UNIVERSAL ENTERPRISES | 15.71 | 12.88 | 100
1457 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for TIKASHI, Water Supply Scheme T/W-II, (Ref. ID-204049560) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01681/2023-2024 | BP-2023-24-161 | 04/08/2023 | 0 | WBSEDCL | 2.41 | 0 | 0
1458 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for TIKASHI Water Supply Scheme T/W-I, (Ref. ID-204134790) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03185/2023-2024 | BP-2023-24-440 | 19/12/2023 | 0 | WBSEDCL | 5.13 | 0 | 0
1459 | Midnapore Mechanical | Contai Sub-Division | Additional quotation for Tkashi w/s swcheme PH I at Khejuri I Block in the District of Purba Medinipur under MMD PHE Dte. (Application ID 100000100192 Dated 12.02.2024 Ref ID 860292212) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03783/2023-2024 | BP-2023-24-715 | 20/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
1460 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TIKASHI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000090/2023-2024 | 1266/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 22.33 | 88
1461 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Simulya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000193/2024-2025 | 2203/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
1462 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SIMULYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000221/2023-2024 | 451/TD | 04/05/2023 | 876 | TARUN KOLEY | 663.05 | 209.12 | 35
1463 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000242/2022-2023 | 2725/TD | 06/02/2023 | 0 | Resource Division | 58.93 | 0 | 0
1464 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686956/QUOT/03 DT. 19-04-2024 Application NO- 2004686956 Application type-New connection Consumer Id- 204277583 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00703/2024-2025 | BP-2024-25-143 | 09/05/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
1465 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004691120/QUOT/03 DT. 19-04-2024 Application NO- 2004691120 Application type-New connection Consumer Id- 204280540 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00704/2024-2025 | BP-2024-25-142 | 09/05/2024 | 0 | WBSEDCL | 11.94 | 0 | 0
1466 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULYA and ADJOINING MOUJAS, Block - Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001653/2022-2023 | 525/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.94 | 80
1467 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2039 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KAKRA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000219/2023-2024 | 450/TD | 04/05/2023 | 897 | TARUN KOLEY | 666.45 | 467.04 | 85
1468 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000148/2023-2024 | 126/TD | 05/01/2024 | 0 | Resource Division | 12.56 | 0 | 0
1469 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000240/2022-2023 | 2727/TD | 06/02/2023 | 0 | Resource Division | 18.4 | 0 | 0
1470 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KAKRA Water Supply Scheme T/W-I, (Ref. ID-204090826) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02889/2023-2024 | BP-2023-24-318 | 01/11/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
1471 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KAKRA Water Supply Scheme T/W-II, (Ref. ID-204090825) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02890/2023-2024 | BP-2023-24-317 | 01/11/2023 | 0 | WBSEDCL | 2.85 | 0 | 0
1472 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAKRA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001324/2022-2023 | 2326/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 23.69 | 23.22 | 95
1473 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Accommodate FHTC (1012 nos) Construction of Switch Room cum Chlorine Room I & II and Interconnection of Risisng main with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A,MOUZA-RAMCHANDRAPUR) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2023-2024 | 498/TD | 11/05/2023 | 837 | S.K. MONDAL | 138.29 | 78.3 | 80
1474 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Accommodate FHTC (700 Nos) & Construction of Boundary Wall with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B,MOUZA-UTTAMPUR) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000244/2023-2024 | 523/TD | 11/05/2023 | 911 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 136.15 | 90.38 | 65
1475 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 350cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000857/2023-2024 | 170/TD | 09/01/2024 | 180 | SATYABRATA BHAUMIK | 133.51 | 45.78 | 10
1476 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System & Accommodate FHTC (520 nos) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C,MOUZA-SHRI BRINDABAN CHAK) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000879/2022-2023 | 3215/TD | 14/03/2023 | 1083 | MAA KALI CONSTRUCTION | 71.8 | 40.8 | 55
1477 | Tamluk Division | Tamluk Sadar Sub-Division | Retaining wall cum guard wall , Approach road, Earth filling at 2nd Tube Site under Ramchandrapur and Its adjoing Mouzas PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Division PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2023-2024 | 245/TD | 11/01/2024 | 343 | ANIRBAN MONDAL | 6.79 | 5.34 | 25
1478 | Tamluk Division | Tamluk Sadar Sub-Division | Earth work in filling by carried earth and Construction of link Road for Ramchandrapur and its adjoining mouzas new Piped Water Supply Scheme at Head Work Site within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001111/2023-2024 | 563/TD | 15/02/2024 | 20 | KIRON CONSTRUCTION | 5.66 | 0 | 11
1479 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000012/2024-2025 | 1570/TD | 23/04/2024 | 0 | Resource Division | 13.75 | 0 | 0
1480 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000188/2022-2023 | 2429/TD | 16/01/2023 | 0 | Resource Division | 23.04 | 0 | 0
1481 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other works for construction of Tube Well (300 mm X 200 mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W-III), Moyna Block under Purba Medinipur Distrct, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000058/2023-2024 | 543/CDD | 02/06/2023 | 30 | WIZARDTECH SOLUTION | 17.72 | 15.95 | 100
1482 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W -II ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000100/2023-2024 | 542/CDD | 02/06/2023 | 374 | UNIVERSAL ENTERPRISES | 17.74 | 14.87 | 100
1483 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Ramchandrapur W/S scheme PH No.-I Application No.-2004543119 Ref.-204175235 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03266/2023-2024 | BP-2023-24-512 | 09/01/2024 | 0 | WBSEDCL | 2.95 | 0 | 0
1484 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connetion at Ramchandrapur PH II in the district of Purba Medinipur under MMD PHE Dte. (App No: 2004962417, Con ID 204443611) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03274/2024-2025 | C122406882987 | 06/12/2024 | 0 | WBSEDCL | 8.89 | 0 | 0
1485 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001326/2022-2023 | 2328/W/MMD | 29/12/2022 | 853 | SOUMEN ELECTRIC | 23.68 | 20.23 | 85
1486 | Tamluk Division | Haldia Sub-Division | Quotation bill for new service connection at TW-III of solat w/s scheme under Haldia block in the Dist. of purba medinipur under MMD,PHE Dte. Name of C.C.C.-Brajalalchak Application no.-2004898781 Reference ID-204397568 Contract Demand-12074watt Quotation Date-12/09/2024 Quotation Due Date-12/09/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00955/2024-2025 | BP-2024-25-632 | 26/11/2024 | 0 | WBSEDCL | 10.59 | 0 | 0
1487 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Solat Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000298/2022-2023 | 1113/TD | 29/08/2022 | 1370 | ARUP KUMAR DEY | 454.08 | 289.11 | 90
1488 | Tamluk Division | Haldia Sub-Division | Additional Laying of Distribution pipeline,Drum Sheet Walling,G.I. Casing & Laying Rising Main of Solat Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000364/2023-2024 | 932/TD | 01/06/2023 | 1004 | SANKHA ENTERPRISE | 68.51 | 0 | 75
1489 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 19.05 | 63
1490 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -1) Name of Work site :- 1) Asadtalia PWSS, 2) Rangibasan PWSS, 3) Kapaseria PWSS, 4) Rajarampur PWSS, 5) Begunberia PWSS, 6) Dhenkua PWSS, 7) Solat PWSS & 8) Gopalpur PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000438/2022-2023 | 721/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
1491 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Solat Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000459/2021-2022 | 1723/TD | 01/02/2022 | 20 | RADIANT | 3.65 | 3.58 | 100
1492 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Solat Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000473/2023-2024 | 1499/TD | 17/07/2023 | 520 | ELECTIVA ENTERPRISE | 5.1 | 0 | 100
1493 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000049/2022-2023 | 1019/TD | 08/08/2022 | 0 | Resource Division | 12.18 | 0 | 0
1494 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000066/2022-2023 | 1201/TD | 06/09/2022 | 0 | Resource Division | 16.27 | 0 | 0
1495 | Central Drilling | Haldia Sub-Division | Providing Tube Well materials Conforming to IS: 12818:2010 at site for construction of Tube Well at Solat PWSS, Purba Medinipur district under CDD, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000020/2024-2025 | 145/CMSD-II | 22/07/2024 | 7 | PADMA ENGINEERING & CO. | 0.97 | 0.97 | 100
1496 | Central Drilling | Haldia Sub-Division | Additional drilling works & other materials at site for construction of Tube Well at Solat W/S Scheme, Haldia Block, Purba MedinipurDist. under CDD, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000021/2024-2025 | 146/CMSD-II | 22/07/2024 | 10 | PADMA ENGINEERING & CO. | 0.99 | 0.79 | 100
1497 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s at TW II for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000074/2023-2024 | 1243/W/MMD | 28/04/2023 | 644 | M/S EMMESS | 13.59 | 6.63 | 60
1498 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001517/2022-2023 | 361/W/MMD | 09/03/2023 | 180 | AMIT DAS | 13.56 | 12.85 | 0
1499 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Selmabad PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000451/2024-2025 | 3480/TD | 06/11/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.5 | 100
1500 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 143.9 | 51
1501 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000038/2024-2025 | 1629/TD | 18/06/2025 | 0 | Resource Division | 16.74 | 0 | 0
1502 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000141/2022-2023 | 2443/TD | 16/01/2023 | 0 | Resource Division | 14.54 | 0 | 0
1503 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-20048335913/QUOT/03 DT. 26-07-2024 Application NO- 20048335913 MEMO NO: AMR/PHE/282 DT.26/7/2024 Application type-New connection Consumer Id- 204365755 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01857/2024-2025 | BP-2024-25-539 | 07/08/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
1504 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835826/QUOT/03 DT. 26-07-2024 Application NO- 2004835826 MEMO NO: AMR/PHE/288 DT.26/7/2024 Application type-New connection Consumer Id- 204365757 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01863/2024-2025 | BP-2024-25-538 | 07/08/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
1505 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SELMABAD and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001650/2022-2023 | 522/W/MMD | 20/03/2023 | 1317 | S.S.ENTERPRISES | 23.7 | 2.91 | 51
1506 | Tamluk Division | Digha Sub-Division | Canal crossing structure for Distribution pipe line with allied works of Nijmaitana & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. N.P-From 1193 towards Kathmundi 45.0M & N.P 1190 to N.P 1191 15.0 M. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000126/2024-2025 | 1926/TD | 07/06/2024 | 15 | SNEHESH SEN | 4.87 | 4.03 | 100
1507 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 700 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000283/2023-2024 | 564/TD | 12/05/2023 | 718 | SNEHESH SEN | 199.62 | 158.45 | 100
1508 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 56 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000334/2023-2024 | 808/TD | 30/05/2023 | 762 | M/S. PRADIP PRADHAN | 9.31 | 5.52 | 100
1509 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 1050 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED , Purba Medinipur ( Part - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000517/2023-2024 | 1753/TD | 01/08/2023 | 853 | SUSIL KUMAR HAZRA | 254.73 | 77.56 | 32
1510 | Tamluk Division | Digha Sub-Division | Laying Balance distribution pipe line,with balance FHTC and allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000597/2024-2025 | 569/TD | 17/02/2025 | 25 | R CONSTRUCTION | 36.35 | 0 | 0
1511 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (123 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000917/2022-2023 | 3554/TD | 29/03/2023 | 876 | SUBRATA KUMAR BERA | 39.9 | 31.5 | 100
1512 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (42 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000918/2022-2023 | 3555/TD | 29/03/2023 | 889 | DEBABRATA DAS | 9.94 | 6.57 | 100
1513 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (19 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000919/2022-2023 | 3556/TD | 29/03/2023 | 799 | DEBABRATA DAS | 11.2 | 9.64 | 100
1514 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000157/2023-2024 | 134/TD | 05/01/2024 | 0 | Resource Division | 12.26 | 0 | 0
1515 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000215/2022-2023 | 2693/TD | 06/02/2023 | 0 | Resource Division | 54.53 | 0 | 0
1516 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 48.99 | 11
1517 | Midnapore Mechanical | Digha Sub-Division | Nij-Maitana W/S scheme T/W-I Application No.-2004550686 Ref.-204181243 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03291/2023-2024 | BP-2023-24-540 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0
1518 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Nijmaitana ws scheme under MMD,PHE, Dte. Ref. Application no-2004579831. Con ID-204204430. PICHABONI CCC, BLOCK-RAMNAGAR-II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03654/2023-2024 | BP-2023-24-680 | 15/02/2024 | 0 | WBSEDCL | 3.07 | 0 | 0
1519 | Tamluk Division | Contai Sub-Division | Shifting of HTOH line at Palpara PWSS, OHR Site under Patashpur-I Dev. Block. Memo No: AMR/SHIFTING/HTOH/.....Date: 05.04.2024 Reference ID: 860297135 Application ID: 100000104915 Application Date: 05.04.2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00129/2024-2025 | BP-2024-25-66 | 26/04/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
1520 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 961 | SANKHA ENTERPRISE | 1144 | 121.46 | 30
1521 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000036/2024-2025 | 1630/TD | 18/06/2025 | 0 | Resource Division | 17.62 | 0 | 0
1522 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000202/2022-2023 | 2446/TD | 16/01/2023 | 0 | Resource Division | 19.77 | 0 | 0
1523 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835399/QUOT/03 DT. 26-07-2024 Application NO- 2004835399 MEMO NO: AMR/PHE/281 DT.26/7/2024 Application type-New connection Consumer Id- 204365758 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01860/2024-2025 | BP-2024-25-541 | 07/08/2024 | 0 | WBSEDCL | 4.98 | 0 | 0
1524 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004895165/QUOT/03 DT. 10-09-2024 MEMO NO: AMR/PHE/377 DT. 10-09-2024 Application NO- 2004895165 Application type-New connection Consumer Id- 204395918 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02451/2024-2025 | BP-2024-25-718 | 30/09/2024 | 0 | WBSEDCL | 3.34 | 0 | 0
1525 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PALPARA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001589/2022-2023 | 472/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 25.24 | 17.6 | 53
1526 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at TW-II of Mahabishra ws scheme under MMD,PHE Dte, Block-Egra-I, EGRA CCC Application no-2004823398 Consumer ID-204358386 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00729/2024-2025 | BP-2024-25-380 | 29/08/2024 | 0 | WBSEDCL | 17.31 | 0 | 0
1527 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Mahabisra PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000169/2024-2025 | 2081/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1528 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 199.43 | 51
1529 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000016/2025-2026 | 2074/TD | 12/08/2025 | 0 | Resource Division | 12.32 | 0 | 0
1530 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000133/2022-2023 | 2417/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
1531 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MAHABISHRA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004667051/QUOT/03 DT. 15-04-2024 Application NO- 2004667051 Application type-New connection Consumer Id- 204275715 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00577/2024-2025 | BP-2024-25-101 | 26/04/2024 | 0 | WBSEDCL | 6.36 | 0 | 0
1532 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHABISHRA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001582/2022-2023 | 465/W/MMD | 20/03/2023 | 803 | DEY ENTERPRISE | 23.7 | 0 | 90
1533 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 1423/TD | 26/09/2022 | 30 | SANKHA ENTERPRISE | 86.77 | 68.76 | 100
1534 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000216/2023-2024 | 1115/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1535 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline for Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000664/2023-2024 | 2672/TD | 16/10/2023 | 602 | M/S. CHANDI CHARAN MISHRA & CO. | 51.03 | 0 | 1
1536 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 2859/TD | 17/02/2023 | 45 | DAS CONSTRUCTION | 80.73 | 54.34 | 70
1537 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000290/2022-2023 | 2646/TD | 02/02/2023 | 0 | Resource Division | 14.41 | 0 | 0
1538 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 11.46 | 100
1539 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000016/2023-2024 | 361/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
1540 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-III of Baharchandberia ws scheme under MMD, PHE Dte, Block-Conai-II, MARISHDA CCC Application no-2004763702 Con ID-204323627 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01232/2024-2025 | BP-2024-25-286 | 18/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
1541 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF JULY'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04359/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.21 | 0 | 0
1542 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF JUNE'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04370/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
1543 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF MAY'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04373/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.21 | 0 | 0
1544 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1545 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block ¿ Deshopran under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001747/2022-2023 | 643/W/MMD | 20/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 11.31 | 85
1546 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 97.49 | 48
1547 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000026/2025-2026 | 2094/TD | 12/08/2025 | 0 | Resource Division | 6.58 | 0 | 0
1548 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000317/2022-2023 | 2972/TD | 27/02/2023 | 0 | Resource Division | 65.15 | 0 | 0
1549 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAGDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852019/QUOT/03/563 DT. 07-08-2024 Application NO- 2004852019 Application type-New connection Consumer Id- 204373372 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02124/2024-2025 | C082449401206 | 02/09/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
1550 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHAGDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005064753/QUOT/03/992 DT. 30-01-2025 Application NO- 2005064753 Application type-New connection Consumer Id- 204512553 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04463/2024-2025 | C032554736961 | 17/03/2025 | 0 | WBSEDCL | 3.16 | 0 | 0
1551 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001398/2022-2023 | 2409/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 45
1552 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 17.72 | 48
1553 | Tamluk Division | Contai Sub-Division | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Sherkhanchak Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000356/2023-2024 | 924/TD | 01/06/2023 | 40 | S.D. CONSTRUCTION | 98.88 | 94.52 | 95
1554 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2021-2022 | 1477/TD | 03/01/2022 | 20 | SANTRA ENTERPRISE. | 4.97 | 4.97 | 100
1555 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000398/2022-2023 | 1447/TD | 27/09/2022 | 1068 | TAPAS SANTRA | 896.61 | 774.33 | 70
1556 | Tamluk Division | Contai Sub-Division | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-342) iv) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-2543) v) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000439/2023-2024 | 1422/TD | 12/07/2023 | 802 | M/S. NEW DINDA ENTERPRISE | 41.06 | 13.22 | 75
1557 | Tamluk Division | Contai Sub-Division | Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001211/2023-2024 | 977/TD | 13/03/2024 | 25 | B. K. ENTERPRISE | 19.16 | 0 | 100
1558 | Tamluk Division | Contai Sub-Division | Rising main (Balance Portion) with laying of 200mm dia & 150 mm dia DI (K-9) From 2nd Tube Well & 4th Tube Well Site to O.H.R. Site and other allied works for Sherkhanchak Zone-I Water Supply Scheme in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001212/2023-2024 | 978/TD | 13/03/2024 | 329 | M/S. NEW DINDA ENTERPRISE | 7.34 | 0 | 100
1559 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2022-2023 | 1200/TD | 06/09/2022 | 0 | Resource Division | 292.79 | 0 | 0
1560 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000062/2022-2023 | 1199/TD | 06/09/2022 | 0 | Resource Division | 44.01 | 0 | 0
1561 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Serkhanchak Zone I w/s scheme PH IV Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004675042, Ref ID 204268872) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00291/2024-2025 | BP-2024-25-50 | 18/04/2024 | 0 | WBSEDCL | 8.33 | 0 | 0
1562 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SHERKHANCHAK Water Supply Scheme Z-I, T/W-III (Ref. ID-204040417 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01637/2023-2024 | BP-2023-24-139 | 27/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
1563 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001514/2022-2023 | 358/W/MMD | 09/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 29.45 | 70
1564 | Tamluk Division | Contai Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00705/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.14 | 0 | 0
1565 | Tamluk Division | Contai Sub-Division | Bill or Damage of road flank / hard shoulder due to cutting of hard shoulder and road flank on Egra-Bajkul Road from 5.30 Km. To 7.00 Km. For laying water pipe line of Kekai PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00988/2024-2025 | BP-2024-25-492 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.03 | 0 | 0
1566 | Tamluk Division | Contai Sub-Division | Charges for WBSEDCL for Shifting of Rail Pole of 33 KV OH Line at Kekai, Junpukur under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01216/2024-2025 | BP-2024-25-633 | 30/11/2024 | 0 | WBSEDCL | 0.87 | 0 | 0
1567 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kekai PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000157/2024-2025 | 2069/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
1568 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 136.54 | 51
1569 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000047/2024-2025 | 1654/TD | 29/04/2024 | 0 | Resource Division | 11.04 | 0 | 0
1570 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000149/2022-2023 | 2453/TD | 16/01/2023 | 0 | Resource Division | 37.57 | 0 | 0
1571 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657831/QUOT/03/1513 DT. 28-03-2024 Application NO- 2004657831 Application type-New connection Consumer Id- 204257680 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00260/2024-2025 | BP-2024-25-30 | 15/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1572 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760163/QUOT/03 DT. 04-06-2024 Application NO- 2004760163 Application type-New connection Consumer Id- 204322029 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01231/2024-2025 | BP-2024-25-287 | 18/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1573 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KEKAI and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001366/2022-2023 | 2377/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 5.85 | 51
1574 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1588 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Rukminipur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000232/2023-2024 | 460/TD | 04/05/2023 | 1063 | FIROZ KHAN | 483.49 | 204.95 | 70
1575 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000029/2025-2026 | 2086/TD | 12/08/2025 | 0 | Resource Division | 9.78 | 0 | 0
1576 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000253/2022-2023 | 2716/TD | 06/02/2023 | 0 | Resource Division | 34.45 | 0 | 0
1577 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004701293/QUOT/03/98 DT. 25-04-2024 Application NO- 2004701293 Application type-New connection Consumer Id- 204287569 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00856/2024-2025 | BP-2024-25-162 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
1578 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792717/QUOT/03/381 DT. 02/07/2024 Application NO- 2004792717 Application type-New connection Consumer Id- 204345882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01699/2024-2025 | BP-2024-25-493 | 29/07/2024 | 0 | WBSEDCL | 4.04 | 0 | 0
1579 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RUKMINIPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001354/2022-2023 | 2365/W/MMD | 31/12/2022 | 974 | ABHIJIT BASU | 23.69 | 14.81 | 80
1580 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 444.54 | 85
1581 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000123/2023-2024 | 83/TD | 05/01/2024 | 0 | Resource Division | 9.34 | 0 | 0
1582 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000279/2022-2023 | 2688/TD | 06/02/2023 | 0 | Resource Division | 24.43 | 0 | 0
1583 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BHUIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004950601/QUOT/03 DT. 30-10-2024 Application NO- 2004950601 Application type-New connection Consumer Id- 204434656 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03006/2024-2025 | C112423559210 | 20/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
1584 | Midnapore Mechanical | Digha Sub-Division | Shifting of Electric line at pump house no-1 of Bhuniajibar w/s scheme. Block-Ramnagar-2. Pichaboni ccc Con ID-204229268 Ref ID-860320499 Application ID-100000126319 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03977/2024-2025 | C012539098687 | 21/01/2025 | 0 | WBSEDCL | 0.69 | 0 | 0
1585 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BHUNIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004620665/QUOT/03 DT. 27-02-2024 Application NO- 2004620665 Application type-New connection Reference Id- 204229268 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04331/2023-2024 | BP-2023-24-807 | 11/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
1586 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BHUIANJIBAR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001685/2022-2023 | 563/W/MMD | 20/03/2023 | 803 | SUBHRA ENTERPRISE | 22.78 | 16.52 | 100
1587 | Tamluk Division | Haldia Electrical Sub-Division | Continuation for Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2025 to 31.12.2025 i.e. 06 (Six) months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000423/2025-2026 | 169/RWS/TSD | 26/06/2025 | 184 | SADHAN CHANDRA SAMANTA | 0.87 | 0 | 50
1588 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 355.87 | 75
1589 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gojina PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000878/2023-2024 | 200/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
1590 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000006/2024-2025 | 1564/TD | 23/04/2024 | 0 | Resource Division | 15.01 | 0 | 0
1591 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000174/2022-2023 | 2435/TD | 16/01/2023 | 0 | Resource Division | 46.71 | 0 | 0
1592 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Gojina w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619845, Ref ID-204229480) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04499/2023-2024 | BP-2023-24-862 | 16/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
1593 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Gojina w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619919, Ref ID-204229478) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04500/2023-2024 | BP-2023-24-861 | 16/03/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
1594 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOJINA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001654/2022-2023 | 526/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 5.65 | 60
1595 | Tamluk Division | Contai Sub-Division | Sinking of Tube well, Pump House , OHR (Intze type with pile foundation), Rising main, Head work site pipe connection, Laying distribution pipe line,Rigid Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2953 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dakshin Kalamdan, Katari, and its adjoing Mouzas- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000430/2023-2024 | 1417/TD | 12/07/2023 | 992 | TAPAS SANTRA | 1109.38 | 124.19 | 75
1596 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000089/2024-2025 | 2965/TD | 12/09/2024 | 0 | Resource Division | 4.72 | 0 | 0
1597 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000335/2022-2023 | 2980/TD | 27/02/2023 | 0 | Resource Division | 17.68 | 0 | 0
1598 | Central Drilling | Contai Sub-Division | Providing drliing crew and other allied works for construction of Tube Well (250 mm x 150mm x 280 Mtrs Depth) by utilising Departmental Machineries for katari W/S Scheme (T/W-III), khejuri-I Block under Purba Mednipur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000057/2023-2024 | 59/CDD | 06/04/2023 | 30 | PADMA ENGINEERING & CO. | 15.48 | 12.9 | 100
1599 | Central Drilling | Contai Sub-Division | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000059/2024-2025 | 11/S&WSD | 15/01/2025 | 197 | SULEKHA PAUL | 0.94 | 1.9 | 0
1600 | Central Drilling | Contai Sub-Division | Provicjing drilling crew and other allied works for construction of Tube Well (250mm Xi50mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Katari W/S Scheme (T/W-l) , Khejuri-l Block under Purba IVedinipur District, CentralDrilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000177/2023-2024 | 853/CDD | 10/07/2023 | 30 | C.M. ENTERPRISE | 15.47 | 12.9 | 100
1601 | Midnapore Mechanical | Contai Sub-Division | Katari W/S scheme PH.-I Application No.-2004565589 Ref No.-204193626 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03478/2023-2024 | BP-2023-24-590 | 02/02/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
1602 | Midnapore Mechanical | Contai Sub-Division | Katari W/S scheme PH.-II Application No.-2004565602 Ref No.-204193624 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03479/2023-2024 | BP-2023-24-591 | 02/02/2024 | 0 | WBSEDCL | 5.2 | 0 | 0
1603 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KATARI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001612/2022-2023 | 505/W/MMD | 20/03/2023 | 180 | AMIT DAS | 21.57 | 20.26 | 50
1604 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
1605 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Potapukuria PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2024-2025 | 2066/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
1606 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 163.12 | 75
1607 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000078/2024-2025 | 2972/TD | 12/09/2024 | 0 | Resource Division | 6.04 | 0 | 0
1608 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000175/2022-2023 | 2397/TD | 16/01/2023 | 0 | Resource Division | 22.13 | 0 | 0
1609 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of POTA PUKURIA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670768/QUOT/03 DT. 05-04-2024 Application NO- 2004670768 Application type-New connection Consumer Id- 204266388 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00295/2024-2025 | BP-2024-25-45 | 18/04/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
1610 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PASCHIM RASULPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005368246/QUOT/03 DT. 31-07-2025 Application NO- 2005368246 Application type-New connection Consumer Id- 204682902 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01876/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 5.72 | 0 | 0
1611 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for POTA PAKURIA and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001668/2022-2023 | 551/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 9.99 | 80
1612 | Tamluk Division | Digha Sub-Division | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (248nos) under JJM with allied work of BADALPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000300/2023-2024 | 603/TD | 17/05/2023 | 685 | AYSAN KHAN | 63.14 | 26.03 | 60
1613 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (635 nos) including 02(two) Years Operation & Maintenance under JJM with allied work of Badalpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000351/2023-2024 | 853/TD | 31/05/2023 | 1031 | GHOSH CONSTRUCTION | 320.45 | 214.44 | 52
1614 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000114/2023-2024 | 78/TD | 05/01/2024 | 0 | Resource Division | 3.91 | 0 | 0
1615 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000260/2022-2023 | 2686/TD | 06/02/2023 | 0 | Resource Division | 8.88 | 0 | 0
1616 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BADALPUR Water Supply Scheme T/W-I, (Ref. ID-204134593) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02999/2023-2024 | BP-2023-24-360 | 24/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
1617 | Midnapore Mechanical | Digha Sub-Division | Badalpur W/S scheme PH-II Application no.-2004522472 ref.-204156771 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03196/2023-2024 | BP-2023-24-470 | 27/12/2023 | 0 | WBSEDCL | 4.53 | 0 | 0
1618 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BADALPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001662/2022-2023 | 546/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 19.98 | 100
1619 | Tamluk Division | Contai Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Murisai & its adjoining moujas Water Supply Scheme within Contai-III Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000512/2023-2024 | 1741/TD | 01/08/2023 | 180 | ANUSKA ENTERPRISE | 130.06 | 0 | 0
1620 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-I] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000453/2022-2023 | .1853/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.2 | 100
1621 | Tamluk Division | Contai Sub-Division | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1807 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-I PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000852/2023-2024 | 897/TD | 11/03/2024 | 360 | SRIMANTA KUMAR MAITY | 428.55 | 0 | 0
1622 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000055/2023-2024 | 2093/TD | 29/08/2023 | 0 | Resource Division | 69.1 | 0 | 0
1623 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme Deshopran Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001983/2022-2023 | 891/W/MMD | 27/03/2023 | 180 | GANGULY ENGINEERING CO. | 23.69 | 0 | 0
1624 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (1718 nos.) under JJM in Baranalgeria Zone -II PWSS Block - EGRA -II in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000042/2022-2023 | 173/TD | 25/04/2022 | 30 | FIROZ KHAN | 82.65 | 82.65 | 100
1625 | Tamluk Division | Digha Sub-Division | Laying ( Left out ) HDPE pipe lineto accommodated FHTC under JJM in Baranalgeria (Zone-II) PWSS within Egra-II Block( to Support Phase -I FHTC ( part -B ) under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2023-2024 | 402/TD | 27/04/2023 | 30 | DEBDUT CONSTRUCTION | 32.43 | 35.41 | 100
1626 | Tamluk Division | Digha Sub-Division | Land development at 1st tube well site of Baranalgeria ( Zone-II ) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000426/2022-2023 | 1595/TD | 18/10/2022 | 20 | PULAK KUMAR SAMANTA | 3.51 | 3.5 | 100
1627 | Tamluk Division | Digha Sub-Division | TRIAL RUN work of distribution system and rising main pipe line etc. of Baranalgeriya (Zone - II) W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. For the period of 90 (Ninety) Days. (01/04/2022 to 29/06/2022 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000660/2021-2022 | 778/DSD | 31/03/2022 | 90 | BIBEKANANDA DAS | 0.72 | 0 | 100
1628 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte.[PART-II] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000454/2022-2023 | .1854/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.09 | 3.49 | 100
1629 | Tamluk Division | Contai Sub-Division | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1636 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-II PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000680/2023-2024 | 2709/TD | 30/10/2023 | 540 | TAPAS SANTRA | 480.26 | 0 | 0
1630 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000056/2023-2024 | 2094/TD | 29/08/2023 | 0 | Resource Division | 15.65 | 0 | 0
1631 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000103/2023-2024 | 3006/TD | 29/11/2023 | 0 | Resource Division | 10.08 | 0 | 0
1632 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (851 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 253/TD | 19/04/2023 | 30 | CHANDIMATA CONSTRUCTION | 56.02 | 50.36 | 100
1633 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of DI Specials for Zone-XII under Surface Water based Water Supply Scheme of Panskura-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000825/2023-2024 | 1528/TSD | 10/11/2023 | 10 | KRISHNENDU SEKHAR DAS | 0.73 | 0.73 | 100
1634 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Purba Teghari & its adjoining Moujas New PWSS in Deshpran Block & Augmentation of Contai Saline Area Zone-I (Phase-A) & Augmentation of Contai Saline Area Zone-I (Phase-B) PWSS in Contai-III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000565/2024-2025 | 2442/CSD | 22/10/2024 | 7 | AMIT PAYRA | 0.62 | 0 | 100
1635 | Tamluk Division | Contai Sub-Division | Tube well, Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (227 nos) under JJM with allied work for Purba Teghari and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000694/2023-2024 | 2706/TD | 20/10/2023 | 719 | CHANDIMATA CONSTRUCTION | 183.69 | 40.89 | 70
1636 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000072/2024-2025 | 2975/TD | 12/09/2024 | 0 | Resource Division | 1.4 | 0 | 0
1637 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000349/2022-2023 | 3013/TD | 27/02/2023 | 0 | Resource Division | 14.09 | 0 | 0
1638 | Central Drilling | Contai Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-III), Deshpran block under Purba Medinipur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000014/2023-2024 | 12/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 13.29 | 12.08 | 100
1639 | Central Drilling | Contai Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Purba Teghari W/S Scheme(TW-II), Deshpran block under Purba Medinipur District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000015/2023-2024 | 19/CDD | 04/04/2023 | 30 | MENAKA ENTERPRISE | 13.29 | 12.01 | 100
1640 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-I, (Ref. ID-204072720) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02536/2023-2024 | BP-2023-24-308 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
1641 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-II, (Ref. ID-204072721) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02537/2023-2024 | BP-2023-24-307 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
1642 | Midnapore Mechanical | Contai Sub-Division | Additional Electric Quotiaton for PURBA TEGHARI Water Supply Scheme, T/W- I, (Ref. ID-860281573) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02878/2023-2024 | BP-2023-24-339 | 10/11/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
1643 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000049/2023-2024 | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 53
1644 | Tamluk Division | Contai Sub-Division | Payment of WBSEDCL for Quotation money for New Service Connection at Tube Well No. - II of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00336/2024-2025 | BP-2024-25-113 | 10/05/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
1645 | Tamluk Division | Contai Sub-Division | Quotation bill of WBSEDCL for New Service Connection at Tube Well No.-1 of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02147/2023-2024 | BP-2023-24-995 | 20/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
1646 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (40 Nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000126/2023-2024 | 262/TD | 19/04/2023 | 15 | PARTHA CONSTRUCTION | 9.59 | 6.69 | 70
1647 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (40 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000259/2023-2024 | 540/TD | 12/05/2023 | 750 | CHANDA AGENCIES | 19.28 | 7.04 | 60
1648 | Tamluk Division | Contai Sub-Division | Pump House ,50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (20 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000527/2023-2024 | 1776/TD | 02/08/2023 | 180 | SUSIL KUMAR HAZRA | 68.66 | 0 | 35
1649 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line & Accommodate FHTC (50 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000839/2022-2023 | 3183/TD | 10/03/2023 | 180 | BADAL CHANDRA GOLE | 18.58 | 12.06 | 70
1650 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000187/2023-2024 | 636/W | 20/02/2024 | 0 | Resource Division | 0.92 | 0 | 0
1651 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000345/2022-2023 | 3010/TD | 27/02/2023 | 0 | Resource Division | 16.31 | 0 | 0
1652 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47 | 11
1653 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601950/QUOT/03 DT. 15-02-2024 Application NO- 2004601950 Application type-New connection Reference Id- 204217839 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04265/2023-2024 |  | 01/03/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
1654 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, MADHAKHALI C.C.C. Ref. Memo No- 2004625653/QUOT/03 DT. 01-03-2024 Application NO- 2004625653 Application type-New connection Consumer Id- 204232821 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04339/2023-2024 |  | 06/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
1655 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 162 Nos) under JJM with allied work for Chirulia-Chatla (Zone-I) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000408/2023-2024 | 1088/TD | 08/06/2023 | 1118 | AJIT KUMAR SOM | 269.22 | 117.58 | 60
1656 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000965/2022-2023 | 1055/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100
1657 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000033/2023-2024 | 2062/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
1658 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000090/2023-2024 | 2993/TD | 29/11/2023 | 0 | Resource Division | 1 | 0 | 0
1659 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-I of Chirulia Chalta, Zone-I W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746276 Consumer ID.-204313776 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01137/2024-2025 | BP-2024-25-254 | 06/06/2024 | 0 | WBSEDCL | 13.67 | 0 | 0
1660 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
1661 | Tamluk Division | Haldia Electrical Sub-Division | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 0 | 94
1662 | Tamluk Division | Haldia Electrical Sub-Division | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 52
1663 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000055/2023-2024 | 1227/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 12.14 | 0 | 0
1664 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line, Rising main pipe line with allied works of Pratapdighi & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000531/2023-2024 | 1826/TD | 07/08/2023 | 509 | GIRI CONSTRUCTION | 55.97 | 0 | 45
1665 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
1666 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Pratapdighi Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000779/2025-2026 | 3042/TD | 18/12/2025 | 60 | MAHARAJ NAYAK | 3.61 | 0 | 0
1667 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of PRATAPDIGHI W/S Scheme under MMD, PHE, Dte. Block- Patashpur-II, wbsedcl office: PATASHPUR C.C.C. Ref. Memo No- 2005628515/QUOT/03/2292 DT.10-02-2026 Application NO- 2005628515 Application type-New connection Reference Id- 204823137 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/05692/2025-2026 |  | 19/02/2026 | 0 | WBSEDCL | 3.2 | 0 | 0
1668 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2023-2024 | 1222/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 11.76 | 0 | 0
1669 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001852/2022-2023 | 770/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0
1670 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001851/2022-2023 | 769/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0
1671 | Tamluk Division | Haldia Electrical Sub-Division | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 284.36 | 94
1672 | Tamluk Division | Haldia Electrical Sub-Division | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 26.01 | 52
1673 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000089/2023-2024 | 2902/TD | 21/11/2023 | 0 | Resource Division | 2.26 | 0 | 0
1674 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-F ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000072/2023-2024 | 174/TD | 11/04/2023 | 15 | AURGHA BHATTACHARYA | 9.97 | 9.12 | 100
1675 | Tamluk Division | Digha Sub-Division | Land development of 2nd T/W Site at Dakshin Shitala & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000247/2024-2025 | 872/DSD | 27/08/2024 | 7 | ABHIJIT BERA | 0.91 | 0.9 | 100
1676 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000370/2023-2024 | 1006/TD | 05/06/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 9.96 | 9.56 | 96
1677 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, & Accommodate FHTC ( 500Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000410/2023-2024 | 1096/TD | 08/06/2023 | 1112 | ABHIJIT BERA | 119.92 | 69.06 | 48
1678 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, soil investigation, 150 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 392 Nos) under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000629/2023-2024 | 2437/TD | 19/09/2023 | 720 | EVEREST INFRATECH INC | 119.98 | 0 | 30
1679 | Tamluk Division | Digha Sub-Division | Laying of Balance Distribution HDPE Pipe Line(180 mm dia) for Dakshin Shitala Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000707/2023-2024 | 2873/TD | 17/11/2023 | 20 | HYDROTECH ASSOCIATES | 11.34 | 11.26 | 99
1680 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 128Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000855/2022-2023 | 3173/TD | 10/03/2023 | 1148 | DHANANJOY DAS | 39.79 | 0 | 60
1681 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000857/2022-2023 | 3174/TD | 10/03/2023 | 1074 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.84 | 18.87 | 97
1682 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000858/2022-2023 | 3175/TD | 10/03/2023 | 1074 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.83 | 18.92 | 97
1683 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-H ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000859/2022-2023 | 3176/TD | 10/03/2023 | 15 | CHARUBALA ENTERPRISE | 9.93 | 0 | 0
1684 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000860/2022-2023 | 3177/TD | 10/03/2023 | 15 | DAS ENTERPRISE. | 9.58 | 0 | 0
1685 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-J ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000863/2022-2023 | 3178/TD | 10/03/2023 | 15 | M/S SOURAV MAHAPATRA | 2.72 | 0 | 0
1686 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000127/2023-2024 | 92/TD | 05/01/2024 | 0 | Resource Division | 6.28 | 0 | 0
1687 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000156/2022-2023 | 2463/TD | 16/01/2023 | 0 | Resource Division | 60.63 | 0 | 0
1688 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 44.83 | 11
1689 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670651/QUOT/03 DT. 05-04-2024 Application NO- 2004670651 Application type-New connection Consumer Id- 204266386 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00296/2024-2025 | BP-2024-25-49 | 18/04/2024 | 0 | WBSEDCL | 7.85 | 0 | 0
1690 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004905806/QUOT/03 DT. 18-09-2024 Application NO- 2004905806 Application type-New connection Consumer Id- 204402411 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02498/2024-2025 | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 7.48 | 0 | 0
1691 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 144.34 | 85
1692 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000158/2023-2024 | 100/TD | 05/01/2024 | 0 | Resource Division | 3.57 | 0 | 0
1693 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000277/2022-2023 | 2696/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0
1694 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I of Nilkanthapur ws scheme under MMD,PHE Dte , Block-Ramnagar-I, DIGHA CCC Application no-2004764563 Con ID-204324292 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01233/2024-2025 | BP-2024-25-289 | 18/06/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
1695 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000165/2023-2024 | 1407/W/MMD | 02/06/2023 | 700 | SOUMEN ELECTRIC | 21.56 | 0 | 55
1696 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 306.53 | 60
1697 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000022/2023-2024 | 351/TD | 26/04/2023 | 0 | Resource Division | 14.49 | 0 | 0
1698 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000037/2024-2025 | 1663/TD | 29/04/2024 | 0 | Resource Division | 16.25 | 0 | 0
1699 | Midnapore Mechanical | Contai Sub-Division | Satsatamal W/S scheme PH-I Application.-2004536916 Ref.-204169242 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03296/2023-2024 | BP-2023-24-533 | 11/01/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
1700 | Midnapore Mechanical | Contai Sub-Division | Satsatamal W/S scheme PH-II Application no.-2004544493 Ref.-204176804 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03456/2023-2024 | BP-2023-24-578 | 18/01/2024 | 0 | WBSEDCL | 9.26 | 0 | 0
1701 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATSATMAL and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001364/2022-2023 | 2375/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 18.31 | 90
1702 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kotbar(CT),J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000107/2020-2021 | 2463/TD | 18/12/2020 | 30 | RAJ KUMAR SINGHA | 43.46 | 0 | 100
1703 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kulapara,J.L. No-9 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000108/2020-2021 | 2464/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 22.74 | 0 | 100
1704 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kotbar(CT) of Kotbar Purba & Paschim Para,J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000109/2020-2021 | 2465/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 24.58 | 0 | 100
1705 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000289/2021-2022 | 217/W | 27/08/2021 | 0 | RAJ KUMAR SINGHA | 0.41 | 0 | 0
1706 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000383/2021-2022 | 222/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.23 | 0 | 0
1707 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000402/2021-2022 | 223/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.16 | 0 | 0
1708 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000589/2020-2021 | 683/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 21.58 | 0 | 0
1709 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000613/2020-2021 | 682/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 42.23 | 0 | 0
1710 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001042/2020-2021 | 726/W | 18/02/2021 | 0 | RAJ KUMAR SINGHA | 24.17 | 0 | 0
1711 | Tamluk Division |  | Functional Household Tap Connection to the 311 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Payrakola (609) ii) Bargolia (610) iii) Hajrakola (611) iv) Bhogpur (624) v) Kalichar (626) vi) Kalidasbar (627). |  |  | ORD/000095/2020-2021 | 2451/TD | 18/12/2020 | 20 | AHINDRA BARIK | 15.31 | 0 | 100
1712 | Tamluk Division |  | Functional Household Tap Connection to the 232 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bankipur(629) ii ) Tiakola (630). |  |  | ORD/000096/2020-2021 | 2452/TD | 18/12/2020 | 20 | JASODA ENTERPRISE | 11.46 | 0 | 100
1713 | Tamluk Division |  | Functional Household Tap Connection to the 202 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bhupatichak (628) ii ) Kaluraybar (631) iii) Kanaichatta (632). |  |  | ORD/000097/2020-2021 | 2453/TD | 18/12/2020 | 20 | SUBHENDU HAZRA | 10 | 0 | 100
1714 | Tamluk Division |  | Construction of 3.60 mtr. x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well of Source Augmentation of Bankiput W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte. |  |  | ORD/000355/2023-2024 | 1001/TD | 05/06/2023 | 60 | GITA ENTERPRISE | 3.97 | 0 | 0
1715 | Tamluk Division |  | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bankiput & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000369/2023-2024 | 1000/TD | 05/06/2023 | 30 | GITA ENTERPRISE | 3.39 | 0 | 0
1716 | Tamluk Division |  | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000818/2021-2022 | BP-2021-22-279 | 25/02/2022 | 0 | JASODA ENTERPRISE | 0.66 | 0 | 0
1717 | Tamluk Division |  | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000868/2021-2022 | 603/W | 24/02/2022 | 0 | JASODA ENTERPRISE | 0.85 | 0 | 0
1718 | Tamluk Division |  | Retrofitting to accomodate for 232 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001044/2020-2021 | 729/W | 18/02/2021 | 0 | JASODA ENTERPRISE | 11.46 | 0 | 0
1719 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001049/2020-2021 | 802/W | 24/02/2021 | 0 | SUBHENDU HAZRA | 9.68 | 0 | 0
1720 | Tamluk Division |  | Retrofitting to accomodate for 311 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001200/2020-2021 | 861/W | 16/03/2021 | 0 | AHINDRA BARIK | 15.01 | 0 | 0
1721 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IX Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000131/2020-2021 | 2657/TD | 11/01/2021 | 60 | BARH CONSTRUCTION | 54.91 | 0.22 | 100
1722 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001047/2020-2021 | 1122/W | 30/03/2021 | 0 | BARH CONSTRUCTION | 0.69 | 0 | 0
1723 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001195/2020-2021 | 824/W | 10/03/2021 | 0 | BARH CONSTRUCTION | 54 | 0 | 0
1724 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Lakshya PWSS Block- Mahishadal in the District of Purba Medinipur. |  |  | ORD/000222/2020-2021 | 2844/TD | 08/02/2021 | 70 | HARIPADA PATTANAYAK | 160.74 | 138.8 | 100
1725 | Tamluk Division |  | Retrofitting to accomodate FHTC of Lakshya W/S Scheme within Mahishadal under Tamluk Division, PHE Dte. |  |  | VCH/000129/2021-2022 | BP-2021-22-39 | 23/07/2021 | 0 | HARIPADA PATTANAYAK | 60.72 | 0 | 0
1726 | Central Drilling |  | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Lakshya W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000139/2023-2024 | 1392/CDD | 19/09/2023 | 517 | MENAKA ENTERPRISE | 21.16 | 0 | 100
1727 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 1783 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District.[Mouza-Mahammadpur(07) - Part] Part-A. | Assistant Engineer | Junior Engineer | ORD/000015/2021-2022 | 108/TD | 17/05/2021 | 60 | DAS CONSTRUCTION | 83.89 | 82.45 | 100
1728 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 588 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Mahammadpur (07) - Part, Durbba Chakri (14),Manoharpur (10) - Part] Part-B. | Assistant Engineer | Junior Engineer | ORD/000016/2021-2022 | 109/TD | 17/05/2021 | 25 | JASODA ENTERPRISE | 27.79 | 27.79 | 100
1729 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 510 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Manoharpur (10) - Part, Tiraipur (11),Chapal Ghata (13) - Part] Part-C. | Assistant Engineer | Junior Engineer | ORD/000017/2021-2022 | 110/TD | 17/05/2021 | 25 | MRINAL KANTI PRADHAN | 24.1 | 20.98 | 100
1730 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 411 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Chapal Ghata (13) - Part, Parial Chak (15),Benauda (16) - Part] Part-D. | Assistant Engineer | Junior Engineer | ORD/000023/2021-2022 | 111/TD | 17/05/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 19.33 | 18.1 | 100
1731 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 370 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Benauda (16) - Part,Mabarakpur (20)] Part-E. | Assistant Engineer | Junior Engineer | ORD/000024/2021-2022 | 112/TD | 17/05/2021 | 20 | SUBHENDU HAZRA | 17.49 | 15.92 | 100
1732 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC (741 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185- (Uttar Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000210/2020-2021 | 2822/TD | 05/02/2021 | 30 | NARAYAN CHANDRA DAS | 35.29 | 0 | 100
1733 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haldia PWSS Block - Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000136/2020-2021 | 2662/TD | 11/01/2021 | 60 | SANKHA ENTERPRISE | 96.1 | 10.96 | 100
1734 | Tamluk Division |  | Laying of Distribution pipe line by UPVC pipes with allied works for jointing of Existing line( N.P-55A-55B, N.P-56A-56B, 58A-58B) under Haldia & its adjoining mouzas W/S Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. |  |  | ORD/000975/2023-2024 | 986/DSD | 17/01/2024 | 7 | LOKENATH ENTERPRISES | 0.97 | 0.94 | 100
1735 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Haldia PWSS within Ramnagar ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001132/2020-2021 | 1113/W | 30/03/2021 | 0 | SANKHA ENTERPRISE | 3.98 | 0 | 0
1736 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Haldia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001240/2020-2021 | 966/W | 25/03/2021 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0
1737 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. |  |  | ORD/000112/2020-2021 | 2468/TD | 18/12/2020 | 25 | MAA ANANDAMAYEE | 20.9 | 0 | 0
1738 | Tamluk Division |  | Construction of approach road at head work site of Kolsar PWSS under Tamluk Sub-division of Tamluk Division PHE Dte.( 20.0 mtr) |  |  | ORD/000400/2025-2026 | 2733/TSD | 13/08/2025 | 15 | M/S MONDAL CONSTRUCTION & CO. | 1.2 | 0 | 0
1739 | Tamluk Division |  | Functional Household Tap Connection (FHTC-11 nos)) of Kolsar water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. |  |  | ORD/000527/2024-2025 | 39/TSD | 08/01/2025 | 15 | M/S MONDAL CONSTRUCTION & CO. | 0.4 | 0 | 100
1740 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Engineer-In-Chief, Govt. of West Bengal, PHE Dte. for the month of May, 2022, June, 2022 and July, 2022 |  |  | VCH/000791/2022-2023 | BP-2022-23-578 | 30/12/2022 | 0 | KRISHNA MONDAL | 1.2 | 0 | 0
1741 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division, PHE Dte. for the period from November, 2021 to March, 2022. |  |  | VCH/000793/2022-2023 | BP-2022-23-452 | 25/11/2022 | 0 | TAPAS SANTRA | 1.97 | 0 | 0
1742 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte. for the period from June, 2022 to August, 2022. |  |  | VCH/000794/2022-2023 | BP-2022-23-455 | 01/12/2022 | 0 | DEBNATH MAITY | 1.2 | 0 | 0
1743 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. |  |  | VCH/000991/2021-2022 | BP-2021-22-385 | 31/03/2022 | 0 | MAA ANANDAMAYEE | 3.38 | 0 | 0
1744 | Tamluk Division |  | Functional Household Tap connection to the 750 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Shirui, JL-74.)PART- A. |  |  | ORD/000215/2020-2021 | 2827/TD | 05/02/2021 | 30 | DILIP KUMAR GHOSH | 35.45 | 6.34 | 100
1745 | Tamluk Division |  | unctional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- B |  |  | ORD/000216/2020-2021 | 2828/TD | 05/02/2021 | 20 | DEBDUT CONSTRUCTION | 9.69 | 0.44 | 100
1746 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- C |  |  | ORD/000217/2020-2021 | 2829/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.69 | 0 | 100
1747 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- D |  |  | ORD/000218/2020-2021 | 2830/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.7 | 0 | 100
1748 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- E. |  |  | ORD/000219/2020-2021 | 2831/TD | 05/02/2021 | 20 | J.M. CONSTRUCTION | 9.7 | 0.32 | 100
1749 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri, JL-76.)PART-F |  |  | ORD/000220/2020-2021 | 2832/TD | 05/02/2021 | 20 | SHAKEEL KHAN | 9.71 | 0 | 100
1750 | Tamluk Division |  | Functional Household Tap connection to the 205 nos(Barsuri-28 nos + Belun-140nos,Soyadighi-37) Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri , Belun & Soyadighi, JL-76 , 75 & 36.) PART-G. |  |  | ORD/000221/2020-2021 | 2833/TD | 05/02/2021 | 20 | TARUN KOLEY | 9.71 | 0 | 100
1751 | Tamluk Division |  | Left out of ( 90 mm & 75 mm) OD pvc laying distribution system of pipe line and its allied works for Alinan zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000300/2022-2023 | 1150/TD | 31/08/2022 | 15 | TARUN KOLEY | 3.39 | 3.39 | 100
1752 | Tamluk Division |  | Left out of 110 mm OD pvc laying distribution system of pipe line and its allied works for Alinan Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000301/2022-2023 | 1151/TD | 31/08/2022 | 15 | TARUN KOLEY | 4.52 | 0.41 | 100
1753 | Tamluk Division |  | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 2.28 | 100
1754 | Tamluk Division |  | Retrofitting to accomodate FHTC 205 Nos. connection under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000106/2021-2022 | BP-2021-22-54 | 05/08/2021 | 0 | DEBDUT CONSTRUCTION | 9.25 | 0 | 0
1755 | Tamluk Division |  | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | VCH/001064/2020-2021 | 1111/W | 30/03/2021 | 0 | J.M. CONSTRUCTION | 9.37 | 0 | 0
1756 | Tamluk Division |  | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | VCH/001065/2020-2021 | 1107/W | 30/03/2021 | 0 | SHAKEEL KHAN | 9.41 | 0 | 0
1757 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001100/2020-2021 | 1110/W | 30/03/2021 | 0 | TARUN KOLEY | 9.48 | 0 | 0
1758 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001101/2020-2021 | 1109/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.26 | 0 | 0
1759 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001102/2020-2021 | 1099/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.36 | 0 | 0
1760 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Block under Tamluk Division, PHE Dte. |  |  | VCH/001140/2020-2021 | 1117/W | 30/03/2021 | 0 | DILIP KUMAR GHOSH | 29.1 | 0 | 0
1761 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 206 nos] under JJM in Barasubarnanagar PWSS [Prakash Kultalia 1st Part(500,part),Chaitanyapur(501, part),Bara Subarnanagar(502, part),Rupnagar(503, part),Krishnalal Chak(504, part),Sikdar Chak(505,part),DahaShonamui(506,part),Bamunia Nankar(510,part),Purba Bhagabanpur(517, part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | VCH/000075/2021-2022 |  | 08/06/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0
1762 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Barasubarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000241/2021-2022 | BP-2021-22-35 | 23/07/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0
1763 | Tamluk Division |  | Laying left out pipe line and Retrofitting to accommodate FHTC (1600 Nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-X (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte (Phase-III) . |  |  | ORD/000101/2021-2022 | 1066/TD | 08/11/2021 | 30 | JAYANTA KUMAR MONDAL | 84.04 | 84.01 | 100
1764 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur. (PART- A) |  |  | ORD/000137/2021-2022 | 1019/TD | 02/11/2021 | 20 | ABHIJIT BERA | 21.29 | 21.29 | 100
1765 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur ( PART - B ) |  |  | ORD/000138/2021-2022 | 1020/TD | 02/11/2021 | 30 | UNIQUE AGENCY | 52.71 | 52.71 | 100
1766 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- A) |  |  | ORD/000133/2021-2022 | 1015/TD | 02/11/2021 | 20 | MAA KALI CONSTRUCTION | 20.35 | 20.34 | 100
1767 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- B) |  |  | ORD/000134/2021-2022 | 1016/TD | 02/11/2021 | 20 | LOKENATH ENTERPRISES | 20.29 | 20.28 | 100
1768 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- C) |  |  | ORD/000135/2021-2022 | 1017/TD | 02/11/2021 | 20 | SHAKEEL KHAN | 22.37 | 22.37 | 100
1769 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- D) |  |  | ORD/000136/2021-2022 | 1018/TD | 02/11/2021 | 20 | NARAYAN CHANDRA DAS | 22.37 | 22.37 | 100
1770 | Tamluk Division |  | Laying ( Left out ) UPVC pipe line to accommodate FHTC under JJM in PANCHROL PWSS within EGRA -I BLOCK ( to Support phase I FHTC ) (part -B )under Digha Sub Division of Tamluk Division PHE Dte. |  |  | ORD/000285/2021-2022 | 1541/TD | 11/01/2022 | 15 | LOKENATH ENTERPRISES | 4.76 | 0 | 100
1771 | Tamluk Division |  | Laying distribution pipe line to accommodate FHTC of Panchrol Water Supply Scheme within Egra - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Within (Panchrol West part ). |  |  | ORD/000348/2021-2022 | 1781/TD | 08/02/2022 | 20 | SHAKEEL KHAN | 11.26 | 0 | 100
1772 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in DULALPUR PWSS Block - Egra-II in the District of Purba Medinipur |  |  | ORD/000130/2021-2022 | 1012/TD | 02/11/2021 | 30 | BIDHAN MONDAL | 57.42 | 57.41 | 100
1773 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-II & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000119/2022-2023 | 622/TD | 22/06/2022 | 1193 | TARUN KOLEY | 570.24 | 337.16 | 85
1774 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - II) Water Supply under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000169/2021-2022 | 1178/TD | 02/12/2021 | 20 | HORIZEN | 6.26 | 6.26 | 100
1775 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site for Mohisda (Zone-II) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000851/2022-2023 | 3205/TD | 14/03/2023 | 30 | TARUN KOLEY | 16.19 | 0 | 100
1776 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2021 to 30.11.2022 i.e. 01 (One) year for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001000/2021-2022 | 309/RWS/TSD | 01/12/2021 | 365 | SRIMANTA PANJA | 1.48 | 2.35 | 100
1777 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000036/2022-2023 | 652/TD | 27/06/2022 | 0 | Resource Division | 10.05 | 0 | 0
1778 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000050/2021-2022 | 641/TD | 27/06/2022 | 0 | Resource Division | 23.01 | 0 | 0
1779 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000214/2023-2024 | 1114/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1780 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000035/2022-2023 | 134/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 0 | 0
1781 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Golaranji Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000322/2021-2022 | 1615/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.46 | 3.04 | 100
1782 | Tamluk Division | Contai Sub-Division | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site and 2nd Tube Well site at Golaranij Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000355/2024-2025 | 3318/TD | 22/10/2024 | 30 | BADAL CHANDRA GOLE | 4.92 | 0 | 100
1783 | Tamluk Division | Contai Sub-Division | Augmentation of ground water based Golaranij Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Potashpur-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000381/2022-2023 | 1370/TD | 23/09/2022 | 795 | KISHORE GHOSH | 392.47 | 262.56 | 70
1784 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000534/2023-2024 | 1835/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 4.2 | 4.2 | 100
1785 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000714/2022-2023 | 1212/TD | 06/09/2022 | 60 | BADAL CHANDRA GOLE | 3.81 | 3.28 | 100
1786 | Tamluk Division | Contai Sub-Division | Name of Work: i) Laying Rising main and other allied works Augmentation of Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Golaranij PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Golaranij PWSS within Patashpur -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000870/2022-2023 | 3221/TD | 14/03/2023 | 1007 | M/S. PRADIP PRADHAN | 35.86 | 4.46 | 80
1787 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line With allied Works of Left Out Area for Augmentation Of Golaranij Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001201/2023-2024 | 738/TD | 28/02/2024 | 275 | KISHORE GHOSH | 44.24 | 0 | 100
1788 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2021-2022 | 1249/TD | 13/12/2021 | 0 | Resource Division | 10.87 | 0 | 0
1789 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000060/2021-2022 | 1273/TD | 12/09/2022 | 0 | Resource Division | 18.08 | 0 | 0
1790 | Central Drilling | Contai Sub-Division | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Golaranji W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000179/2023-2024 | 1412/CDD | 20/09/2023 | 149 | MENAKA ENTERPRISE | 11.26 | 9.61 | 100
1791 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of GOLARANIJ W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609771/QUOT/03 DT. 21-02-2024 Application NO- 2004609771 Application type-New connection Reference Id- 204223235 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04385/2023-2024 | BP-2023-24-823 | 13/03/2024 | 0 | WBSEDCL | 5.82 | 0 | 0
1792 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001914/2022-2023 | 816/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.79 | 0 | 85
1793 | Tamluk Division |  | Retrofitting to accommodate FHTC (410 Nos.) under JJM in Keshabpur Jalpai PWSS (Balance Part : Phase-II) Block - Mahisadal in the District of Purba Medinipur |  |  | ORD/000546/2021-2022 | 2006/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 23.33 | 19.06 | 100
1794 | Tamluk Division |  | Balance work for Retrofitting to accommodate FHTC (750 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface water based water supply scheme for Zone-XI, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000360/2021-2022 | 1800/TD | 08/02/2022 | 40 | TAPAS SANTRA | 92.64 | 92.89 | 100
1795 | Tamluk Division | Digha Sub-Division | Providing FHTC under JJM in Negua PWSS within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000300/2021-2022 | 1641/TD | 19/01/2022 | 120 | M/S CARE | 137.35 | 84.49 | 85
1796 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (Phase-II) of Negua PWSS, Egra - I Block under Digha Sub-Division PHE Dte. of Tamluk Division PHE Dte. in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 621/TD | 17/05/2023 | 25 | SOM CONSTRUCTION | 15.44 | 15.44 | 100
1797 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2021-2022 | 1748/TD | 08/02/2022 | 0 | Resource Division | 15.3 | 0 | 0
1798 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Thenkuachak PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00394/2022-2023 | BP-2022-23-755 | 28/02/2023 | 0 | WBSEDCL | 4.07 | 0 | 0
1799 | Tamluk Division | Haldia Electrical Sub-Division | Additional laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000071/2022-2023 | 292/TD | 06/05/2022 | 15 | MALLICK CONSTRUCTION | 3.91 | 3.91 | 100
1800 | Tamluk Division | Haldia Electrical Sub-Division | Laying of DI (K7) ( Nodal point 167 to 627) ,UPVC pipe (Nodal 167-623) & Supply of of DI (Specials) under Thekuachak Zone-I Water Supply Scheme under Tamluk Division, Purba Medinipur, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000111/2024-2025 | 1905/TD | 07/06/2024 | 20 | GHOSH ENTERPRISE | 12.87 | 0 | 100
1801 | Tamluk Division | Haldia Electrical Sub-Division | Drum sheet walling in different nodal point under Thekuachak Zone-I water supply scheme under Tamluk Division, Purba Medinipur,PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000123/2024-2025 | 1920/TD | 07/06/2024 | 20 | GHOSH ENTERPRISE | 13.39 | 0 | 100
1802 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-II PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000175/2023-2024 | 332/TD | 25/04/2023 | 60 | GHOSH ENTERPRISE | 17.82 | 10.35 | 70
1803 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-I PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000176/2023-2024 | 333/TD | 25/04/2023 | 480 | GHOSH ENTERPRISE | 15.05 | 5.78 | 70
1804 | Tamluk Division | Haldia Electrical Sub-Division | Laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub- Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000196/2021-2022 | 1228/TD | 08/12/2021 | 40 | ANUSKA ENTERPRISE | 17.87 | 17.85 | 100
1805 | Tamluk Division | Haldia Electrical Sub-Division | Pilling work & casing pipe (GI/MS)over khal and Road crossing of various junction of Thekuachak Zone-II water supply scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000341/2023-2024 | 806/TD | 30/05/2023 | 30 | GHOSH ENTERPRISE | 14.63 | 5.86 | 50
1806 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Thenkuachak (Zone - I & II) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000391/2021-2022 | 1607/TD | 14/01/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 8.64 | 8.59 | 100
1807 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well site for Thekuachak Zone-II Water Supply Scheme in Nandakumar Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000464/2024-2025 | 3724/TD | 04/12/2024 | 120 | GHOSH ENTERPRISE | 7.83 | 0 | 100
1808 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Concrete road for Kharar Pool ( Mansa Mandir) (Nodal Point -38) to Head work site of Thekuachak Zone -I(Nodal point 1158 )( Length - 350 mtr, width 2.10 mte , Depth of cincrete 150 mm ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000734/2023-2024 | 2988/TD | 29/11/2023 | 30 | KRISHNENDU SEKHAR DAS | 9.63 | 9.11 | 100
1809 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr. and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000241/2022-2023 | 1020/TD | 08/08/2022 | 1080 | ARABINDA GHOSH | 705.19 | 617.42 | 90
1810 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000242/2022-2023 | 1021/TD | 08/08/2022 | 1318 | ARABINDA GHOSH | 1009.34 | 650.99 | 70
1811 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2024 to 14/07/2025 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000262/2024-2025 | 2227/TD | 11/07/2024 | 365 | THREE MAA ENTERPRISE | 1.24 | 3.77 | 0
1812 | Tamluk Division | Haldia Electrical Sub-Division | Additional works of Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur .( Low Land ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000466/2023-2024 | 1446/TD | 13/07/2023 | 40 | TARUN KHATUA | 1.86 | 1.83 | 100
1813 | Tamluk Division | Haldia Electrical Sub-Division | Cannel crossing for DI and uPVC pipes of Thekua chak Zone-II PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. (Nodal Point 139-140, 410-528, 165-164, 636-448, 675-381, 783-789, 665-214 and 55-221= 8 nos) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000736/2023-2024 | 2986/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 33.58 | 17.04 | 100
1814 | Tamluk Division | Haldia Electrical Sub-Division | Canel crossing for DI and uPVC pipes of Thekua chak Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. ( Nodal 167-112, 585-327,33-98,337-401 and 213-109 )= 5 nos | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000737/2023-2024 | 2985/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 20.97 | 20.44 | 100
1815 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000831/2022-2023 | 3171/TD | 10/03/2023 | 60 | ANIRBAN MONDAL | 4.59 | 4.57 | 100
1816 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000832/2022-2023 | 3172/TD | 10/03/2023 | 60 | TARUN KHATUA | 5.11 | 5.11 | 100
1817 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000025/2022-2023 | 413/TD | 25/05/2022 | 0 | Resource Division | 121.31 | 0 | 0
1818 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000026/2022-2023 | 414/TD | 25/05/2022 | 0 | Resource Division | 46.43 | 0 | 0
1819 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2023 to 14/07/2024 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001289/2023-2024 | 1489/TD | 14/07/2023 | 366 | THREE MAA ENTERPRISE | 1.24 | 4.56 | 0
1820 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000074/2022-2023 | 1267/TD | 12/09/2022 | 0 | Resource Division | 59.51 | 0 | 0
1821 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000194/2023-2024 | 670/W | 22/02/2024 | 0 | Resource Division | 16.44 | 0 | 0
1822 | Central Drilling | Haldia Electrical Sub-Division | Fuel Charges for the month of November 2022 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00039/2022-2023 | BP-2022-23-280 | 21/12/2022 | 0 | MIRA SERVICE STATION | 0.22 | 0 | 0
1823 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH (TW-II), MOYNA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, [PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000138/2022-2023 | 387/CDD | 18/05/2022 | 30 | PADMA ENGINEERING & CO. | 14.26 | 8.65 | 100
1824 | Central Drilling | Haldia Electrical Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, BLOCK-NANDAKUMAR, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000139/2022-2023 | 410/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.93 | 0.91 | 100
1825 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL DEPARTMENTAL RIG MACHINE AT NANDAKUMAR BLOCK, DIST. PURBA MEDINIPUR UNDER CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000140/2022-2023 | 143/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.4 | 100
1826 | Central Drilling | Haldia Electrical Sub-Division | SUPPLY & DELIVERY OF TUBE WELL MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK PWSS, ZONE-II, TW-II, BLOCK- NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000141/2022-2023 | 411/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100
1827 | Central Drilling | Haldia Electrical Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN THENKUA CHAK [PWSS, TW-II, ZONE-II, BLOCK - NANDAKUMAR, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000142/2022-2023 | 409/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.98 | 0.98 | 100
1828 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAK W/S SCH (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000226/2022-2023 | 1228/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.84 | 17.18 | 100
1829 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR THENKUACHAUK W/S SCH UNDER PURBA MIDNAPORE DISREICT, CDD, PHE DTE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000320/2022-2023 | 1382/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.39 | 16.46 | 100
1830 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Tube Well-III, Z-II of Thenkuachak W/S Scheme at Nandakumar CCC (2004173196) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00060/2022-2023 | BP-2022-23-110 | 01/03/2023 | 0 | WBSEDCL | 8.3 | 0 | 0
1831 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Tube Well-III, Z-I of Thenkuachak W/S Scheme at Nandakumar CCC (2004172999) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00061/2022-2023 | BP-2022-23-111 | 01/03/2023 | 0 | WBSEDCL | 1.11 | 0 | 0
1832 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District., under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001475/2022-2023 | 213/W/MMD | 10/02/2023 | 180 | DAS ENTERPRISE | 40.3 | 37.84 | 60
1833 | Tamluk Division | Tamluk Sadar Sub-Division | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Mohisda Zone-I PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01193/2023-2024 | BP-2023-24-566 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.6 | 0 | 0
1834 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000067/2022-2023 | 338/TD | 12/05/2022 | 1080 | TAPAS SANTRA | 331.77 | 315.84 | 95
1835 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 700 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000075/2022-2023 | 337/TD | 12/05/2022 | 1054 | TAPAS SANTRA | 417.56 | 274.52 | 70
1836 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well at OHR Site of Mahisda Zone-I Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000103/2022-2023 | 479/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 15.97 | 100
1837 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000168/2021-2022 | 1177/TD | 02/12/2021 | 20 | HORIZEN | 7.73 | 7.73 | 100
1838 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Mahisda Zone-I Water Supply Scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000249/2023-2024 | 513/TD | 11/05/2023 | 30 | TAPAS SANTRA | 58.58 | 55.7 | 90
1839 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia DI(K-9) & 200 mm dia DI (K-9) rising main from 1st.,2nd. & 3rd. T/W to OHR at Mohisda Zone-I PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000454/2023-2024 | 1494/TD | 17/07/2023 | 20 | TAPAS SANTRA | 3.84 | 0 | 0
1840 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of Retaining wall and approach concrete road at OHR site at Mohisda Zone-I Water Supply scheme of Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000617/2023-2024 | 2282/TD | 07/09/2023 | 420 | TAPAS SANTRA | 27.97 | 0 | 100
1841 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000035/2022-2023 | 651/TD | 27/06/2022 | 0 | Resource Division | 22.79 | 0 | 0
1842 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000072/2021-2022 | 640/TD | 27/06/2022 | 0 | Resource Division | 31.83 | 0 | 0
1843 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000215/2023-2024 | 1113/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1844 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Net-Metering Solar Power Plant quotation at Mohisda water supply scheme Zone-I, Tube Well-I Matangini CCC Block-Sahid Matangini Application No.-2004795833 Consumer ID.-222091158 Quotation Date.-26/06/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01450/2024-2025 | BP-2024-25-446 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0
1845 | Tamluk Division | Tamluk Sadar Sub-Division | Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2022 to 14/07/2023 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000703/2022-2023 | 821/TD | 15/07/2022 | 365 | THREE MAA ENTERPRISE | 1.24 | 4.76 | 100
1846 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room at 1 st.T.W. Site and Construction of switch room cum Chlorine room with water supply & sanitary arrangement at 3 rd. Tube Well Site and Repairing & renovation of existing Boundary Wall at 1 st.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000852/2022-2023 | 3206/TD | 14/03/2023 | 30 | TAPAS SANTRA | 17.08 | 16.83 | 100
1847 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site and Construction of Pump House at 3 rd Tube Well site &New construction of Boundary Wall at 3 rd.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000853/2022-2023 | 3207/TD | 14/03/2023 | 30 | TAPAS SANTRA | 19.48 | 19.29 | 100
1848 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Mahisda Water Supply Scheme zone-I, T/W-III (Ref. ID-204015583) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01669/2023-2024 | BP-2023-24-173 | 04/08/2023 | 0 | WBSEDCL | 8.05 | 0 | 0
1849 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Net Billing Mahisda Zone-I,T/W-I Matangini CCC Application No=2004795833 Consumer ID=222091158 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02430/2024-2025 | BP-2024-25-773 | 28/10/2024 | 0 | WBSEDCL | 0.22 | 0 | 0
1850 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotation for MAHISDA Water Supply Scheme, T/W- III, Zone- I (Ref. ID-860281848) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02908/2023-2024 | BP-2023-24-320 | 01/11/2023 | 0 | WBSEDCL | 4.8 | 0 | 0
1851 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001931/2022-2023 | 850/W/MMD | 24/03/2023 | 180 | MUKHERJEE ART CENTRE | 12.37 | 11.32 | 65
1852 | Tamluk Division | Haldia Sub-Division | Electric Quotation Bill for Rangibasan PWSS | Assistant Engineer | Junior Engineer | BILL/00226/2022-2023 | BP-2022-23-637 | 20/01/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
1853 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Mahishadal-Geonkhali road from Ch.0.20 km to 1.10 km under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer | Junior Engineer | BILL/00235/2023-2024 | BP-2023-24-120 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.98 | 0 | 0
1854 | Tamluk Division | Haldia Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer | Junior Engineer | BILL/00701/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.96 | 0 | 0
1855 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000053/2025-2026 | 416/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
1856 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000054/2025-2026 | 417/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.94 | 0 | 100
1857 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 418/HSD, | 23/04/2025 | 10 | BHOWMIK ENTERPRISE | 0.97 | 0 | 100
1858 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- D) | Assistant Engineer | Junior Engineer | ORD/000056/2025-2026 | 419/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.96 | 0 | 100
1859 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- E) | Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 420/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
1860 | Tamluk Division | Haldia Sub-Division | Restoration of cement concrete pavements of dismantling road for laying of distribution pipeline for Augmentation of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division PHE Dte. (Part- F) | Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 421/HSD, | 23/04/2025 | 10 | ANIRBAN BHOWMIK | 0.97 | 0 | 100
1861 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 2013/TD | 14/06/2024 | 313 | A. R. CONSTRUCTION | 56.76 | 0 | 20
1862 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2021-2022 | 1180/TD | 02/12/2021 | 20 | HORIZEN | 5.56 | 5.56 | 100
1863 | Tamluk Division | Haldia Sub-Division | Renovation of Boundary Wall and land development at Head Work Site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Length - 212.00 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000244/2024-2025 | 2693/TD | 22/08/2024 | 360 | BHOWMIK & SONS | 21.73 | 0 | 30
1864 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Rangibasan Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000375/2021-2022 | 1814/TD | 11/02/2022 | 1265 | DAS CONSTRUCTION | 481.17 | 376.05 | 65
1865 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District (PART-A) | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1052/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.9 | 5.9 | 100
1866 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000389/2023-2024 | 1053/TD | 07/06/2023 | 20 | MA SARADA ENTERPRISE | 0.73 | 0.73 | 100
1867 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Rangibasan Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000459/2023-2024 | 1496/TD | 17/07/2023 | 45 | PULAK KUMAR SAMANTA | 4.81 | 4.6 | 60
1868 | Tamluk Division | Haldia Sub-Division | Laying of supply & delivery of different dia D.I specials for Rising main line and inter connection at Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1493/TD | 17/07/2023 | 895 | S.D. CONSTRUCTION | 7.32 | 1.95 | 10
1869 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube Well site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000655/2023-2024 | 2620/TD | 11/10/2023 | 30 | PULAK KUMAR SAMANTA | 5.98 | 0 | 3
1870 | Tamluk Division | Haldia Sub-Division | Sinking of 300 mm x 200 mm dia x 280 mtr. deep tube well by direct rotary rig method at 3rd Tubewell site of Rangibasan Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 51/TD | 04/01/2024 | 45 | AQUATECH ENGINEER | 20.68 | 19.69 | 100
1871 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2021-2022 | 1258/TD | 13/12/2021 | 0 | Resource Division | 11.32 | 0 | 0
1872 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2021-2022 | 1867/TD | 17/02/2022 | 0 | Resource Division | 19.09 | 0 | 0
1873 | Central Drilling | Haldia Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 280 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RANGIBASAN W/S SCHEME (TW-III), MAHISBADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000111/2022-2023 | 109/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.7 | 17.85 | 100
1874 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 240 Mtrs. Depth) by utilising Departmental Machineries for Solat/Rangibasan W/S Scheme (T/W-II) , under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000196/2023-2024 | 858/CDD | 10/07/2023 | 386 | PADMA ENGINEERING & CO. | 18.74 | 17.81 | 100
1875 | Tamluk Division | Haldia Sub-Division | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001006/2021-2022 | 476/HSD, | 27/12/2021 | 365 | SANTANU PATTANAYAK | 1.5 | 1.91 | 100
1876 | Central Drilling | Haldia Sub-Division | SEALING OF SALINE ZONEAT SITE FOR CONSTRUCTION OF TUBE WELL AT RANGIBASAN W/S SCHEME (TW-III), MAHISHADAL BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000224/2022-2023 | 454/CMSD-I | 01/09/2022 | 7 | MENAKA ENTERPRISE | 0.47 | 0 | 100
1877 | Tamluk Division | Contai Sub-Division | payment Wayleave plan & survey charges SER-KGP-2024-WL-103 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00486/2024-2025 | BP-2024-25-189 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.1 | 0 | 0
1878 | Tamluk Division | Contai Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-103) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00694/2024-2025 | BP-2024-25-301 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.75 | 0 | 0
1879 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-I PWSS for Application ID-SER-KGP-2023-WL-57 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01830/2023-2024 | BP-2023-24-824 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0
1880 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 125.16 | 50
1881 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes with allied works of Mukutshila Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000519/2024-2025 | 113/TD | 09/01/2025 | 25 | GEE BEE NIRMAN CO PVT LTD. | 36.64 | 0 | 0
1882 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-B) In between OHE MAST NO 34/2 & 34/3, Nodal Point 253 to 182. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000554/2024-2025 | 136/CSD | 16/01/2025 | 20 | BIBEKANANDA DAS | 1.16 | 0 | 100
1883 | Tamluk Division | Contai Sub-Division | Rising main and other allied works Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000589/2023-2024 | 2190/TD | 01/09/2023 | 720 | GRAND CONSTRUCTION | 11.85 | 0 | 90
1884 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-I PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. (Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000615/2023-2024 | 2277/TD | 07/09/2023 | 796 | SAMIT KUMAR MONDAL | 8.63 | 0 | 100
1885 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000068/2022-2023 | 1194/TD | 06/09/2022 | 0 | Resource Division | 108.25 | 0 | 0
1886 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x 3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Mukutshila Zone-I water supply scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000724/2023-2024 | 2968/TD | 28/11/2023 | 60 | ABHIJIT BERA | 3.72 | 3.37 | 100
1887 | Tamluk Division | Contai Sub-Division | Temporary water supply arrangement through pipe line & PVC tank connection from distribution pipe line of Mukutshila Zone-I W/S Scheme for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-A), Date of Mela :- 20.03.2023 to 23.03.2023, (4 days) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000998/2022-2023 | 394/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.7 | 0.51 | 100
1888 | Tamluk Division | Contai Sub-Division | Construction of Temporary 25(twenty five) nos. Latrine & Urinal for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-B) Date of Mela :- 20.03.2023 to 23.03.2023,(4 days) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000999/2022-2023 | 395/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.62 | 0 | 100
1889 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001957/2022-2023 | 860/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 23.7 | 0 | 0
1890 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chirulia PWSS Block Egra-II in the District of Purba Medinipur. |  |  | ORD/000190/2020-2021 | 2768/TD | 28/01/2021 | 60 | FIROZ KHAN | 56.35 | 6.8 | 100
1891 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000153/2021-2022 | 62/W | 08/06/2021 | 0 | FIROZ KHAN | 24.5 | 0 | 0
1892 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001236/2020-2021 | 977/W | 25/03/2021 | 0 | FIROZ KHAN | 21.3 | 0 | 0
1893 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
1894 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 102.85 | 94
1895 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 708.05 | 70
1896 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 2892/TD | 21/11/2023 | 0 | Resource Division | 19.46 | 0 | 0
1897 | Tamluk Division |  | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Jagati(244 ) part,] |  |  | ORD/000171/2020-2021 | 2721/TD | 21/01/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 10.43 | 0 | 100
1898 | Tamluk Division |  | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Jagati(244 ) part,] |  |  | ORD/000172/2020-2021 | 2722/TD | 21/01/2021 | 20 | GIRI ENTERPRISE | 10.43 | 0 | 100
1899 | Tamluk Division |  | Functional Household Tap Connection to the 1400 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Pratap Dighi (245), Mangalpur (249)] |  |  | ORD/000173/2020-2021 | 2809/TD | 04/02/2021 | 50 | GIRI CONSTRUCTION | 64.82 | 0 | 100
1900 | Tamluk Division |  | Renovation of existing pump house at head works & 2nd tube well site of Pratapdighi W/S Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000193/2022-2023 | 409 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 1.36 | 1.35 | 100
1901 | Tamluk Division |  | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000283/2021-2022 | 159/W | 02/08/2021 | 0 | GIRI CONSTRUCTION | 13.24 | 0 | 0
1902 | Tamluk Division |  | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000387/2021-2022 | 225/W | 01/09/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 0.63 | 0 | 0
1903 | Tamluk Division |  | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000469/2021-2022 | 315/W | 08/10/2021 | 0 | GIRI ENTERPRISE | 0.38 | 0 | 0
1904 | Tamluk Division |  | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/001052/2020-2021 | 815/W | 24/02/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 9.64 | 0 | 0
1905 | Tamluk Division |  | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001222/2020-2021 | 980/W | 23/03/2021 | 0 | GIRI ENTERPRISE | 9.77 | 0 | 0
1906 | Tamluk Division |  | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001237/2020-2021 | 972/W | 25/03/2021 | 0 | GIRI CONSTRUCTION | 21.89 | 0 | 0
1907 | Tamluk Division | Haldia Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01480/2023-2024 | BP-2023-24-665 | 15/12/2023 | 0 | WBSEDCL | 5.18 | 0 | 0
1908 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000136/2023-2024 | 277/TD | 20/04/2023 | 25 | TARUN KHATUA | 19.88 | 14.27 | 60
1909 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (240 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-G+H+I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000137/2023-2024 | 278/TD | 20/04/2023 | 45 | BHOLANATH DEY | 90.98 | 76.65 | 76
1910 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J+K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000138/2023-2024 | 279/TD | 20/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.8 | 25.84 | 80
1911 | Tamluk Division | Haldia Sub-Division | Construction of Box Culvert (5.00Mtr. X 3.50Mtr.) at H/W site of Bamanpur Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2024-2025 | 2382/TD | 26/07/2024 | 160 | M/S SOURAV MAHAPATRA | 5.3 | 0 | 100
1912 | Tamluk Division | Haldia Sub-Division | Land development of Head work site at Bamanpur Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, PEH Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000294/2025-2026 | 638/HSD, | 12/06/2025 | 10 | M/S SOURAV MAHAPATRA | 2.27 | 0 | 60
1913 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (480 nos.) work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000411/2023-2024 | 1097/TD | 08/06/2023 | 180 | SUSIL KUMAR HAZRA | 104.34 | 38.53 | 10
1914 | Tamluk Division | Haldia Sub-Division | Canal Crossing Structure for Laying Distribution (Nodal Point -161-163, 378-382, R1 - 1, 12-16) Pipe line of Bamanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000649/2023-2024 | 2615/TD | 11/10/2023 | 30 | TARUN KHATUA | 8.77 | 6.05 | 100
1915 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (425 nos.)work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D+E+F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000665/2023-2024 | 2678/TD | 16/10/2023 | 649 | SK. SARFARAJ | 93.13 | 35.37 | 10
1916 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000117/2023-2024 | 81/TD | 05/01/2024 | 0 | Resource Division | 8.39 | 0 | 0
1917 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000330/2022-2023 | 2986/TD | 27/02/2023 | 0 | Resource Division | 15.66 | 0 | 0
1918 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new connection at Bamanpur w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004732591, Ref ID 204305895) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01366/2024-2025 | BP-2024-25-376 | 08/07/2024 | 0 | WBSEDCL | 10.38 | 0 | 0
1919 | Midnapore Mechanical | Haldia Sub-Division | New service connection at Bamanpur w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No 2004732540, Con ID 204305894) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03660/2024-2025 | C012524055154 | 09/01/2025 | 0 | WBSEDCL | 8.49 | 0 | 0
1920 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAMANPUR and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001600/2022-2023 | 504/W/MMD | 20/03/2023 | 895 | SUJOY RANJAN BHOWMICK | 21.62 | 10.07 | 50
1921 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 0 | 100
1922 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH line at Moyna Zone-I Water Supply Scheme | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01475/2023-2024 | BP-2023-24-663 | 15/12/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
1923 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of left out pipe line by 90 mm OD UPVC pipes with allied works of Moyna Zone-I & its adjoining mouzas Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000108/2024-2025 | 1902/TD | 07/06/2024 | 200 | GHOSH ENTERPRISE | 70.24 | 0 | 0
1924 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well 2nd tube well site of Moyna Zone-I Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000430/2024-2025 | 3547/TD | 18/11/2024 | 60 | SANDIP MAITI | 3.06 | 0 | 100
1925 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (4679 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-I Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000442/2022-2023 | 1652/TD | 02/11/2022 | 903 | ARABINDA GHOSH | 612.74 | 336.18 | 85
1926 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000597/2023-2024 | 2211/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 4.9 | 10
1927 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000598/2023-2024 | 2212/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 5.01 | 70
1928 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of 300/250/200/150 mm dia DI (K9) rising main in between OHR to T/W-I, T/W-2, T/W-3 and T/W-4 including canel crossing and dram Sheet Walling and DI specials of Moyna Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000653/2023-2024 | 2618/TD | 11/10/2023 | 600 | KRISHNENDU SEKHAR DAS | 24.68 | 3.4 | 100
1929 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000859/2021-2022 | 1470/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.08 | 3.93 | 100
1930 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.01.2024 to 31.03.2024. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001226/2023-2024 | 1756/TSD | 29/12/2023 | 50 | DEBNATH MAITY | 0.24 | 1.11 | 100
1931 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001259/2023-2024 | 1468/TSD | 31/10/2023 | 239 | TAPAS SANTRA | 1.14 | 3.97 | 0
1932 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000032/2023-2024 | 1922/TD | 14/08/2023 | 0 | Resource Division | 9.63 | 0 | 0
1933 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2022-2023 | 1209/TD | 06/09/2022 | 0 | Resource Division | 131.09 | 0 | 0
1934 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000058/2022-2023 | 1205/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0
1935 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000200/2023-2024 | 1099/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1936 | Central Drilling | Tamluk Sadar Sub-Division | Providing Drilling crew and other allied works for construction of Tube Well (300mm x 200mmx 230 Mtrs. Depth) by utilising Departmental Mechineries for Moyna W/S Scheme (Z-I,T/W-I)block under Purba Medinipur District CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000028/2023-2024 | 537/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.24 | 100
1937 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 230 Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-I, T/W-I), Moyna Block under Purba Medinipur District , Central Drilling Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000033/2023-2024 | 538/CDD | 02/06/2023 | 30 | MENAKA ENTERPRISE | 17.76 | 16.24 | 100
1938 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-III, Zone-I, (Ref. ID-204143546) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03134/2023-2024 | BP-2023-24-408 | 09/12/2023 | 0 | WBSEDCL | 4.7 | 0 | 0
1939 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-IV, Zone-I, (Ref. ID-204136064) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03186/2023-2024 | BP-2023-24-437 | 18/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
1940 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Augmentation of Moyna (Zone-I) PWSS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001752/2022-2023 | 645/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 27.17 | 26.82 | 60
1941 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kshetrapal PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000158/2024-2025 | 2070/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
1942 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 255.57 | 51
1943 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2024-2025 | 1657/TD | 29/04/2024 | 0 | Resource Division | 11.58 | 0 | 0
1944 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000150/2022-2023 | 2456/TD | 16/01/2023 | 0 | Resource Division | 19.2 | 0 | 0
1945 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004686002/QUOT/03 DT. 16-04-2024 Application NO- 2004686002 Application type-New connection Consumer Id- 204277214 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00574/2024-2025 | BP-2024-25-104 | 26/04/2024 | 0 | WBSEDCL | 5.44 | 0 | 0
1946 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004685984/QUOT/03 DT. 16-04-2024 Application NO- 2004685984 Application type-New connection Consumer Id- 204277213 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00575/2024-2025 | BP-2024-25-103 | 26/04/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
1947 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF MARCH'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04355/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.15 | 0 | 0
1948 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF MAY'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04357/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.25 | 0 | 0
1949 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF MARCH'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04367/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.25 | 0 | 0
1950 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1951 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KSHETRAPAL and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001637/2022-2023 | 517/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 0 | 70
1952 | Tamluk Division |  | Retrofitting to accommodate FHTC [180 nos.] under JJM in Uttar Charaikhia PWSS Block - Contai-I in the District of Purba Medinipur. Mouza- Saheb Khankeranibar(101),Kanchra Gerya(122),Dakshin Charai Khia(124),Uttar Charai Khia(125) (Phase-II) |  |  | ORD/000127/2021-2022 | 1007/TD | 02/11/2021 | 20 | M/S SREE DURGA ENTERPRISE | 17.26 | 17.26 | 100
1953 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Rautari to Terapara Jalpai road from Ch.8.5 KM to 9.85 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer | Junior Engineer | BILL/00237/2023-2024 | BP-2023-24-122 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.76 | 0 | 0
1954 | Tamluk Division | Haldia Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer | Junior Engineer | BILL/00702/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.92 | 0 | 0
1955 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 514/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.81 | 4.81 | 100
1956 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 515/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.7 | 3.7 | 100
1957 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2021-2022 | 1165/TD | 01/12/2021 | 7 | HORIZEN | 5.74 | 5.61 | 100
1958 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.28 | 100
1959 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Rajarampur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1069/TD | 22/08/2022 | 45 | TAPAN BERA | 3.96 | 3.93 | 100
1960 | Tamluk Division | Haldia Sub-Division | Laying Rising main, laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Rajarampur Water Supply Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 2167/TD | 19/12/2022 | 1170 | SANKHA ENTERPRISE | 78.54 | 23.06 | 35
1961 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 3289/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 8.69 | 1.22 | 25
1962 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2021-2022 | 1253/TD | 13/12/2021 | 0 | Resource Division | 40.29 | 0 | 0
1963 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 465/W | 02/06/2022 | 0 | Resource Division | 55.01 | 0 | 0
1964 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Rajarampur Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.. | Assistant Engineer | Junior Engineer | ORD/000528/2021-2022 | 2021/TD | 08/03/2022 | 1334 | SANKHA ENTERPRISE | 549.46 | 437.5 | 90
1965 | Tamluk Division | Haldia Sub-Division | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001005/2021-2022 | 476/HSD | 27/12/2021 | 365 | SUSANTA PATTANAYAK | 1.5 | 0 | 100
1966 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2021-2022 | 2344/TD | 31/03/2022 | 0 | Resource Division | 16.03 | 0 | 0
1967 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000136/2023-2024 | 104/TD | 05/01/2024 | 0 | Resource Division | 5.61 | 0 | 0
1968 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000278/2022-2023 | 2682/TD | 06/02/2023 | 0 | Resource Division | 14.87 | 0 | 0
1969 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For Gobindapur W/S Scheme T/W-I Matangini CCC Application No=2005012098 Reference ID=204475906 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03880/2024-2025 | C012552555934 | 31/01/2025 | 0 | WBSEDCL | 4.53 | 0 | 0
1970 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For Gobindapur W/S Scheme T/W-II Matangini CCC Application No=2005012102 Reference ID=204475934 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03881/2024-2025 | C012552557436 | 31/01/2025 | 0 | WBSEDCL | 3.83 | 0 | 0
1971 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - IV at GOBINDAPUR Zone-II Water supply scheme,Block : Shahid Matangini, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001176/2023-2024 | 2612/W/MMD | 19/09/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.17 | 0 | 0
1972 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOBINDAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002197/2022-2023 | 454/W/MMD | 20/03/2023 | 540 | S.S.ENTERPRISES | 21.62 | 0 | 20
1973 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2060 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of HARINAN PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000222/2023-2024 | 455/TD | 04/05/2023 | 1057 | TAPAS SANTRA | 585.56 | 309.39 | 80
1974 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of pipe line and its allied works for Harinan water supply scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000700/2023-2024 | 2736/TD | 01/11/2023 | 792 | TAPAS SANTRA | 85.07 | 76.45 | 100
1975 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000140/2023-2024 | 90/TD | 05/01/2024 | 0 | Resource Division | 12.69 | 0 | 0
1976 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000207/2022-2023 | 2465/TD | 16/01/2023 | 0 | Resource Division | 18.6 | 0 | 0
1977 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HARINAN Water Supply Scheme , (Ref. ID-204069690) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01871/2023-2024 | W/23-24/224 | 01/09/2023 | 0 | WBSEDCL | 3.04 | 0 | 0
1978 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HARINAN, Water Supply Scheme T/W-II , (Ref. ID-204069696) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01872/2023-2024 | W/23-24/225 | 01/09/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
1979 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
1980 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 15 | S.S.GHORAI | 2.13 | 0 | 70
1981 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
1982 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARINAN PWSS and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001333/2022-2023 | 2338/W/MMD | 29/12/2022 | 180 | DEY ENTERPRISE | 23.7 | 22.63 | 85
1983 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
1984 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at T/W-I of Barada under MMD,PHE DTE, Block-Egra-I, Chorpalia CCC Application no-2004811995 CON ID-204352240 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00635/2024-2025 | BP-2024-25-312 | 02/08/2024 | 0 | WBSEDCL | 20.24 | 0 | 0
1985 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2024-2025 | 2082/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
1986 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 93.47 | 51
1987 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000010/2025-2026 | 2083/TD | 12/08/2025 | 0 | Resource Division | 8.6 | 0 | 0
1988 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000135/2022-2023 | 2419/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0
1989 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARADA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847092/QUOT/03/1184 DT. 13-08-2024 Application NO- 2004847092 Application type-New connection Consumer Id- 204372857 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02122/2024-2025 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1990 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARDA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001402/2022-2023 | 2413/W/MMD | 31/12/2022 | 180 | ECO ENTERPRISE | 22.8 | 9.45 | 35
1991 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 23.24 | 30
1992 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000029/2024-2025 | 1651/TD | 29/04/2024 | 0 | Resource Division | 7.38 | 0 | 0
1993 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000200/2022-2023 | 2462/TD | 16/01/2023 | 0 | Resource Division | 17.76 | 0 | 0
1994 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004781161/QUOT/03 DT. 19-06-2024 Application NO- 2004781161 Application type-New connection Consumer Id- 204333913 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01330/2024-2025 | BP-2024-25-358 | 01/07/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
1995 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886291/QUOT/03/582 DT. 06-09-2024 Application NO- 2004886291 Application type-New connection Consumer Id- 204391659 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02450/2024-2025 | C092443181197 | 27/09/2024 | 0 | WBSEDCL | 3.46 | 0 | 0
1996 | Midnapore Mechanical | Digha Sub-Division | ADDITIONAL Quotation OF MODIFIED WORK FOR NSC OF PHE KALYANPUR T/W NO-II W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- PTP/QUOT DT. 09-01-2025 REF.ID-860322918 Application ID- 100000127608 DT. 09-01-2025 Application type-ADDITIONAL QUOTATION Consumer Id- 204391659 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04113/2024-2025 | C022539938524 | 18/02/2025 | 0 | WBSEDCL | 0.22 | 0 | 0
1997 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALYANPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001348/2022-2023 | 2359/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 80
1998 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 326.87 | 75
1999 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Basanta Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000877/2023-2024 | 199/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2000 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000002/2024-2025 | 1560/TD | 23/04/2024 | 0 | Resource Division | 12.76 | 0 | 0
2001 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000182/2022-2023 | 2431/TD | 16/01/2023 | 0 | Resource Division | 21.73 | 0 | 0
2002 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Basantachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756260, Ref ID 204319518) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01700/2024-2025 | BP-2024-25-492 | 29/07/2024 | 0 | WBSEDCL | 5.19 | 0 | 0
2003 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Basantachak w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608977, Ref ID-204222619) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04497/2023-2024 | BP-2023-24-853 | 16/03/2024 | 0 | WBSEDCL | 2.96 | 0 | 0
2004 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001330/2022-2023 | 2335/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 23.68 | 21.94 | 80
2005 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 389.78 | 75
2006 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Radhaballabh Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000875/2023-2024 | 197/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
2007 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000011/2024-2025 | 1569/TD | 23/04/2024 | 0 | Resource Division | 12.48 | 0 | 0
2008 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000184/2022-2023 | 2428/TD | 16/01/2023 | 0 | Resource Division | 32.13 | 0 | 0
2009 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Radhaballavchak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631522, Ref ID 204237226) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04736/2023-2024 | BP-2023-24-907 | 28/03/2024 | 0 | WBSEDCL | 7.1 | 0 | 0
2010 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Radhaballavchak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631928, Ref ID 204238450) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04746/2023-2024 | BP-2023-24-908 | 28/03/2024 | 0 | WBSEDCL | 11.33 | 0 | 0
2011 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RADHABALLAV CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001335/2022-2023 | 2340/W/MMD | 29/12/2022 | 914 | S.G.TECHNICAL SERVICE | 23.58 | 0 | 80
2012 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Telami PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000161/2024-2025 | 2073/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2013 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 94.37 | 51
2014 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000021/2025-2026 | 2080/TD | 12/08/2025 | 0 | Resource Division | 4.46 | 0 | 0
2015 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000125/2022-2023 | 2409/TD | 16/01/2023 | 0 | Resource Division | 35.73 | 0 | 0
2016 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674624/QUOT/03 DT. 09-04-2024 Application NO- 2004674624 Application type-New connection Consumer Id- 204269445 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00506/2024-2025 | BP-2024-25-88 | 24/04/2024 | 0 | WBSEDCL | 7.55 | 0 | 0
2017 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674680/QUOT/03 DT. 09-04-2024 Application NO- 2004674680 Application type-New connection Consumer Id- 204269489 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00508/2024-2025 | BP-2024-25-89 | 24/04/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
2018 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TELAMI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001344/2022-2023 | 2355/W/MMD | 31/12/2022 | 180 | SOUMEN ELECTRIC | 21.56 | 15.29 | 70
2019 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000437/2022-2023 | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 220.41 | 85
2020 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia-Janka Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000441/2021-2022 | 1647/TD | 19/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.95 | 100
2021 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000095/2022-2023 | 1376/TD | 23/09/2022 | 0 | Resource Division | 13.06 | 0 | 0
2022 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000103/2022-2023 | 1659/TD | 03/11/2022 | 0 | Resource Division | 186.64 | 0 | 0
2023 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049361) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01675/2023-2024 | BP-2023-24-155 | 04/08/2023 | 0 | WBSEDCL | 2.97 | 0 | 0
2024 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-I, Zone-II (Ref. ID-204049345) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01676/2023-2024 | BP-2023-24-156 | 04/08/2023 | 0 | WBSEDCL | 0.97 | 0 | 0
2025 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-II, Zone-II (Ref. ID-204049556) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01677/2023-2024 | BP-2023-24-157 | 04/08/2023 | 0 | WBSEDCL | 2.4 | 0 | 0
2026 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049047) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01678/2023-2024 | BP-2023-24-158 | 04/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
2027 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA JANKA, Water Supply Scheme T/W-IV, Zone-I (Ref. ID-204049555) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01679/2023-2024 | BP-2023-24-159 | 04/08/2023 | 0 | WBSEDCL | 2.8 | 0 | 0
2028 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2023-2024 | 1274/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 50.28 | 34.45 | 70
2029 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 860 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000249/2022-2023 | 1040/TD | 16/08/2022 | 1313 | M/S SREE DURGA ENTERPRISE | 110.9 | 105.16 | 96
2030 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 814 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. ( Part -C ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000259/2022-2023 | 1077/TD | 23/08/2022 | 45 | J. K. BUILDERS | 109.37 | 107.91 | 95
2031 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000439/2021-2022 | 1542/TD | 11/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.71 | 4.44 | 100
2032 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000444/2022-2023 | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 165.5 | 40
2033 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for the work of Hiring of one Diesel Motor cabs & Maxi cabs with Engine capacity More than 2000 C.C. with ( Air Condition) on monthly Hiring (Per day) ( including Govt. Holidays as and when required ) having contract carriage permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. Govt. of West Bengal. For the Period from 01/07/2023 to 30/06/2024 i.e.12 Months. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000560/2023-2024 | 1204/A/CSD | 21/06/2023 | 366 | SABITA PRADHAN | 1.49 | 0 | 0
2034 | Tamluk Division | Haldia Electrical Sub-Division | Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2021 to 30/06/2022. (12 Months) Vehicle No-WB-31/6974 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000979/2021-2022 | 157/CSD | 29/06/2021 | 12 | SABITA PRADHA | 1.49 | 4.53 | 100
2035 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000076/2022-2023 | 1259/TD | 12/09/2022 | 0 | Resource Division | 24.85 | 0 | 0
2036 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Khejuri Zone II w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640039, Ref ID - 204244094) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04493/2023-2024 | BP-2023-24-850 | 16/03/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
2037 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Khejuri Zone II w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004639938, Ref ID - 204243679) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04494/2023-2024 | BP-2023-24-851 | 16/03/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
2038 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II)under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000091/2023-2024 | 1280/W/MMD | 04/05/2023 | 719 | DEBJYOTI BASU | 40.2 | 25.05 | 25
2039 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Sahara PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000228/2024-2025 | 2423/TD | 29/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
2040 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 172.72 | 51
2041 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000018/2025-2026 | 2096/TD | 12/08/2025 | 0 | Resource Division | 7.11 | 0 | 0
2042 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000127/2022-2023 | 2411/TD | 16/01/2023 | 0 | Resource Division | 12.32 | 0 | 0
2043 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769073/QUOT/03/443 DT. 11-06-2024 Application NO- 2004769073 Application type-New connection Consumer Id- 204327178 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01277/2024-2025 | BP-2024-25-334 | 25/06/2024 | 0 | WBSEDCL | 4.79 | 0 | 0
2044 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769176/QUOT/03/442 DT. 11-06-2024 Application NO- 2004769176 Application type-New connection Consumer Id- 204327965 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01279/2024-2025 | BP-2024-25-333 | 25/06/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
2045 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHARA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002032/2022-2023 | 940/W/MMD | 28/03/2023 | 856 | SUJOY RANJAN BHOWMICK | 27.69 | 16.57 | 60
2046 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 13.07 | 98
2047 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Barasubarnanagar W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000210/2023-2024 | 472/TD | 10/05/2023 | 60 | JASODA ENTERPRISE | 3.83 | 3.58 | 100
2048 | Tamluk Division | Contai Sub-Division | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 1st Tube Well & 1(One) no. Boosting Tube Well of Barasubarnanagar & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000234/2023-2024 | 471/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 4.01 | 1.62 | 100
2049 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 13.05 | 100
2050 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000015/2023-2024 | 345/TD | 26/04/2023 | 0 | Resource Division | 9.11 | 0 | 0
2051 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Barasubarnanagar PWSS Tube Well- III in connection Mukundapur CCC (2004188348) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00059/2022-2023 | BP-2022-23-109 | 01/03/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
2052 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Boosting Tube Well No. III for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District.under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000133/2023-2024 | 1354/W/MMD | 24/05/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 12.5 | 40
2053 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001343/2022-2023 | 36/W/MMD | 04/01/2023 | 360 | SOUMEN ELECTRIC | 13.57 | 12.8 | 80
2054 | Tamluk Division | Digha Sub-Division | Land development of 2nd T/W Site at Ramnagar Zone-II & Its Adjoining Mouzas water Supply Scheme within Ramnagar-I BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000366/2024-2025 | 905/DSD | 03/09/2024 | 7 | SRIYA CONSTRUCTION | 2.86 | 0 | 100
2055 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Ramnagar Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000638/2022-2023 | 741/TD | 04/07/2022 | 20 | SANTRA ENTERPRISE. | 4.52 | 2.45 | 100
2056 | Tamluk Division | Digha Sub-Division | Laying of Distribution System to accomodate FHTC(2941 Nos), Construction of Boundary Wall,Pump House ,R.C.C. Overhead Reservoir of Capacity 350 Cum and staging height 20 meter for Augmentation of Ramnagar Water Supply Scheme (Zone-II) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000743/2022-2023 | 2532/TD | 19/01/2023 | 803 | BASANTA KUMAR MAITY | 476.59 | 191.35 | 66
2057 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000237/2022-2023 | 2614/TD | 02/02/2023 | 0 | Resource Division | 65.04 | 0 | 0
2058 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000287/2022-2023 | 2640/TD | 02/02/2023 | 0 | Resource Division | 18.12 | 0 | 0
2059 | Central Drilling | Digha Sub-Division | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (TW-I, Z-II) Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000031/2023-2024 | 454/CDD | 02/06/2023 | 30 | UNIVERSAL ENTERPRISES | 20.47 | 16.54 | 100
2060 | Central Drilling | Digha Sub-Division | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II(D),CDD P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000091/2023-2024 | 227/CMSD-II(D) | 10/10/2023 | 61 | DILIP KAR | 0.29 | 0.53 | 50
2061 | Central Drilling | Digha Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Ramnagar W/S Scheme (Z- II,T/W-II) , Ramnagar-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000133/2023-2024 | 544/CDD | 02/06/2023 | 416 | UNIVERSAL ENTERPRISES | 20.47 | 17.32 | 100
2062 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of RAMNAGAR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004923160/QUOT/03 DT. 01-10-2024 Application NO- 2004923160 Application type-New connection Consumer Id- 204414480 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03271/2024-2025 | C122406874783 | 06/12/2024 | 0 | WBSEDCL | 3.88 | 0 | 0
2063 | Midnapore Mechanical | Digha Sub-Division | Ramnagar W/S scheme T/W-I, Zone-II Application-2004536109 Ref.-204168170 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03289/2023-2024 | BP-2023-24-541 | 11/01/2024 | 0 | WBSEDCL | 5.06 | 0 | 0
2064 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-II) PWSS, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001917/2022-2023 | 821/W/MMD | 24/03/2023 | 180 | M/S SWAPAN BANERJEE | 27.17 | 12.76 | 45
2065 | Tamluk Division | Contai Sub-Division | Payment of WBSEDCL for Quotation of Shifting of LTOH line at Haludbari Water Supply Scheme for Construction of New OHR. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01889/2023-2024 | BP-2023-24-844 | 07/02/2024 | 0 | WBSEDCL | 1.52 | 0 | 0
2066 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Rising main,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works, with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (4781 Nos), including 2 years Operation & Maintenance For Halud Bari, Dekhali, Pipe water supply Scheme within Khejuri-II Block, within Contai Sub-Division Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000287/2023-2024 | 454/TD | 04/05/2023 | 1092 | TAPAS SANTRA | 1701.13 | 482.25 | 78
2067 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000228/2022-2023 | 2708/TD | 06/02/2023 | 0 | Resource Division | 20.18 | 0 | 0
2068 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Haludbari w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004785778, Ref ID 204336496) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01365/2024-2025 | BP-2024-25-377 | 08/07/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
2069 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for Haludbari Water Supply scheme Tube well no.-I Khejuri CCC Block-Khejuri Application No.-2004645013 Ref ID.-204247115 Quatation Bill Date.-14/03/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04572/2023-2024 | BP-2023-24-888 | 22/03/2024 | 0 | WBSEDCL | 4.93 | 0 | 0
2070 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HALUD BARI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001652/2022-2023 | 524/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 15.86 | 48
2071 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
2072 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
2073 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000017/2024-2025 | 1643/TD | 18/06/2025 | 0 | Resource Division | 4.88 | 0 | 0
2074 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000272/2022-2023 | 2703/TD | 06/02/2023 | 0 | Resource Division | 15.41 | 0 | 0
2075 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of AYMABAR BERYA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004775224/QUOT/03 DT. 14-06-2024 Application NO- 2004775224 Application type-New connection Consumer Id- 204330602 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01331/2024-2025 | BP-2024-25-355 | 01/07/2024 | 0 | WBSEDCL | 10.56 | 0 | 0
2076 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of AYMABAR BARIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878127/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/350 DT. 30/08/2024 Application NO- 2004878127 Application type-New connection Consumer Id- 204387570 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02448/2024-2025 | C102415716055 | 05/10/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
2077 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AYMABAR BARYA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001649/2022-2023 | 542/W/MMD | 20/03/2023 | 1017 | SOUMEN ELECTRIC | 21.56 | 15.29 | 60
2078 | Tamluk Division | Contai Sub-Division | Emergent repairing of Right Embankment of Kallaghal River in between ch 46.0 to 51.50 km within G.P.-Mahammadpur-I, Block-Bhagwanpur-I at Mouza- Uttarbar & Paschimber and P.S.-Bhagwanpur, Dist.-Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00007/2025-2026 |  | 04/04/2025 | 0 | EXECUTIVE ENGINEER, CONTAI IRRIGATION DIVISION | 8.95 | 0 | 0
2079 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3181 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PASCHIM BAR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000220/2023-2024 | 447/TD | 04/05/2023 | 942 | TAPAS SANTRA | 872.64 | 595.67 | 40
2080 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-1-2,2-4,4-19,19-20,20-50,50-84,84-109,109-167 & 167-89) of pipe line and its allied works for PASCHIM BAR Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001258/2023-2024 | 1072/TD | 16/03/2024 | 25 | MISHRA ENTERPRISE | 23.45 | 21.38 | 80
2081 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000163/2023-2024 | 128/TD | 05/01/2024 | 0 | Resource Division | 19.59 | 0 | 0
2082 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000246/2022-2023 | 2720/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0
2083 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PASCHIMBAR Water Supply Scheme T/W-I, (Ref. ID-204104644) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03057/2023-2024 | BP-2023-24-390 | 02/12/2023 | 0 | WBSEDCL | 1.05 | 0 | 0
2084 | Midnapore Mechanical | Contai Sub-Division | Paschimbarh W/S scheme T/W No.-II (Laxmi Mandir) Applicatiot No.-2004522520 Ref.-204156806 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03179/2023-2024 | BP-2023-24-479 | 27/12/2023 | 0 | WBSEDCL | 4.86 | 0 | 0
2085 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
2086 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM BAR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001676/2022-2023 | 568/W/MMD | 20/03/2023 | 468 | DEY ENTERPRISE | 25.26 | 23.59 | 75
2087 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kasba Patashpur PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000153/2024-2025 | 2064/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2088 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 13.52 | 51
2089 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000045/2024-2025 | 1652/TD | 29/04/2024 | 0 | Resource Division | 11.55 | 0 | 0
2090 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000148/2022-2023 | 2451/TD | 16/01/2023 | 0 | Resource Division | 32.56 | 0 | 0
2091 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KASBA PATASHPUR W/S Scheme under MMD, PHE, Dte. Block- Patashpur-II, wbsedcl office: PATASHPUR C.C.C. Ref. Memo No- 2005628552/QUOT/03/2291 DT.10-02-2026 Application NO- 2005628552 Application type-New connection Reference Id- 204823135 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/05690/2025-2026 |  | 19/02/2026 | 0 | WBSEDCL | 3.21 | 0 | 0
2092 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of KASBA PATASHPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL OFFICE: PATASHPUR C.C.C. Ref. Memo No- 2005628535/QUOT/03/2293 DT. 12-02-2026 Application NO- 2005628535 Application type-New connection Reference Id- 204823136 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/05691/2025-2026 |  | 19/02/2026 | 0 | WBSEDCL | 5.82 | 0 | 0
2093 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KASBAPATASHPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2005088004/QUOT/03/1057 DT. 20-02-2025 Application NO- 2005088004 Application type-New connection Consumer Id- 204528861 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/05696/2025-2026 |  | 08/05/2025 | 0 | WBSEDCL | 4.59 | 0 | 0
2094 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASBAPATASHPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001353/2022-2023 | 2364/W/MMD | 31/12/2022 | 180 | JAL PRAVAHIKA PVT. LTD. | 23.44 | 0 | 0
2095 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000016/2024-2025 | 1644/TD | 18/06/2025 | 0 | Resource Division | 7.99 | 0 | 0
2096 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000226/2022-2023 | 2706/TD | 06/02/2023 | 0 | Resource Division | 24.84 | 0 | 0
2097 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743549/QUOT/03 DT. 25-05-2024 Application NO- 2004743549 Application type-New connection Consumer Id- 204312620 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01202/2024-2025 | BP-2024-25-318 | 24/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
2098 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004793608/QUOT/03 DT. 25-06-2024 MEMO NO: AMR/PHE/223 DT. 25-06-2024 Application NO- 2004793608 Application type-New connection Consumer Id- 204340910 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01369/2024-2025 | BP-2024-25-373 | 08/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
2099 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMARPUR and ADJOINING MOUJAS, Block potaspur- I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002029/2022-2023 | 937/W/MMD | 28/03/2023 | 710 | MENAKA ENTERPRISE | 22.77 | 13.33 | 50
2100 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2022-2023 | 816/TD | 12/07/2022 | 1185 | SRIMANTA KUMAR MAITY | 406.75 | 278.03 | 70
2101 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000363/2021-2022 | 1511/TD | 06/01/2022 | 20 | SANTRA ENTERPRISE. | 3.71 | 3.33 | 100
2102 | Tamluk Division | Contai Sub-Division | Name of Work: i) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000871/2022-2023 | 3222/TD | 14/03/2023 | 650 | SRIMANTA KUMAR MAITY | 7.4 | 0 | 100
2103 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site under Sherkhanchak Zone-II Water Supply Scheme (Augmentation) in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001218/2023-2024 | 982/TD | 13/03/2024 | 480 | BIPLAB GUHA | 86.79 | 0 | 60
2104 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000054/2022-2023 | 1198/TD | 06/09/2022 | 0 | Resource Division | 15.39 | 0 | 0
2105 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000063/2022-2023 | 1210/TD | 06/09/2022 | 0 | Resource Division | 15.91 | 0 | 0
2106 | Central Drilling | Contai Sub-Division | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000018/2023-2024 | 74/S&WSD | 30/06/2023 | 30 | NAGENDRA PATRA | 0.15 | 0.4 | 100
2107 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHERKHANCHAK W/S SCH, BHAGAWANPUR-I BLOCK UNDER MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000155/2022-2023 | 435/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 8.86 | 100
2108 | Central Drilling | Contai Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, BLOCK-KHEJURI -II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000156/2022-2023 | 133/CMSD-II | 12/08/2022 | 15 | MENAKA ENTERPRISE | 5 | 4.83 | 100
2109 | Central Drilling | Contai Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, ZONE-II, BLOCK-KHEJURI-II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000176/2022-2023 | 146/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.38 | 4.22 | 100
2110 | Central Drilling | Contai Sub-Division | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, S&WSD,CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000341/2022-2023 | 232/S&WSD | 20/12/2022 | 7 | NAGENDRA PATRA | 0.86 | 2.27 | 100
2111 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SERKHAN CHAK W/S SCHEME, ZONE-I, TW-III, KHEJURI-II BLOCK, UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000375/2022-2023 | 1381/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 22.11 | 17.48 | 0
2112 | Central Drilling | Contai Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 300 mtrs. Depth) by utilising Departmental machineries for Serkhanchak W/S Scheme (TW-III), Khejuri-II block under Purba Midnapore District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000453/2022-2023 | 1346/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 22.2 | 16.22 | 100
2113 | Central Drilling | Contai Sub-Division | providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Serkhan Chawk W/S Scheme (TW-¦V) , Khejuri-ll Block under Purba Midnapore Dlstrict, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000517/2022-2023 | 1536/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 22.23 | 16.07 | 100
2114 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well No I of Zone II under Sherkhan Chack water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001134/2022-2023 | 2115/W/MMD | 28/11/2022 | 120 | BHABANI PRASAD MANNA | 11.56 | 0 | 0
2115 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001476/2022-2023 | 214/W/MMD | 10/02/2023 | 445 | EMCON | 11.83 | 10.96 | 85
2116 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gabardhanpur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000191/2024-2025 | 2201/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2117 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 126.18 | 51
2118 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000044/2024-2025 | 1650/TD | 29/04/2024 | 0 | Resource Division | 10.35 | 0 | 0
2119 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000185/2022-2023 | 2455/TD | 16/01/2023 | 0 | Resource Division | 15.86 | 0 | 0
2120 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of GOBARDHANPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004595917/QUOT/03 DT. 12-02-2024 Application NO- 2004595917 Application type-New connection Consumer Id- 204213656 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01134/2024-2025 | BP-2024-25-250 | 06/06/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
2121 | Midnapore Mechanical | Contai Sub-Division | ADDITIONAL Quotation Bill for NSC of GOBARDHANPUR W/S Scheme, T/W NO-I under JJM Under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No-PTP/QOT/856 DT. 05-08-2025 Application NO- 100000145046 DT. 05-08-2025 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860345026 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01904/2025-2026 |  | 18/08/2025 | 0 | WBSEDCL | 0.26 | 0 | 0
2122 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of Gabardhanpur W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004595896/QUOT/03 DT. 12-03-2024 Application NO- 2004595896 Application type-New connection CONSUMER ID: 204213657 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04738/2023-2024 | BP-2023-24-921 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
2123 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GABARDHANPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001639/2022-2023 | 519/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 0 | 0
2124 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, renovation of Pump House, Boundary Wall 400 Cum OHR & Accommodate balance FHTC ( 42 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000118/2024-2025 | 1914/TD | 07/06/2024 | 181 | GHOSH CONSTRUCTION | 38.32 | 0.43 | 100
2125 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 79 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000145/2023-2024 | 287/TD | 20/04/2023 | 20 | BUNBA CONSTRUCTION | 16.35 | 14.59 | 90
2126 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000329/2023-2024 | 739/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.41 | 100
2127 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Sankarpur Zone-II Ramnagar I Blockunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/002046/2022-2023 | 887/W/MMD | 27/03/2023 | 180 | R.S. ENTERPRISE | 11.4 | 0 | 0
2128 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 13.01 | 75
2129 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai- II ( Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000111/2023-2024 | 241/TD | 19/04/2023 | 30 | GITA ENTERPRISE | 7.54 | 0 | 0
2130 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Bamunia W/S Scheme within Contai - II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000367/2023-2024 | 998/TD | 05/06/2023 | 660 | GIRI CONSTRUCTION | 3.72 | 0 | 100
2131 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bamunia & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000368/2023-2024 | 999/TD | 05/06/2023 | 30 | GIRI CONSTRUCTION | 3.39 | 0 | 0
2132 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000012/2023-2024 | 340/TD | 26/04/2023 | 0 | Resource Division | 5.21 | 0 | 0
2133 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of BAMUNIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2005061859/QUOT/03 DT. 28-01-2025 Application NO- 2005061859 Application type-New connection Consumer Id- 204509581 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04505/2024-2025 | C032587407652 | 27/03/2025 | 0 | WBSEDCL | 7.18 | 0 | 0
2134 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001988/2022-2023 | 895/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 0 | 0
2135 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 12.84 | 75
2136 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Silampur & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000213/2023-2024 | 480/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 3.27 | 1.05 | 100
2137 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Silampur W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000214/2023-2024 | 481/TD | 10/05/2023 | 60 | THE GODFATHER TRADING COMPANY | 3.67 | 3.56 | 100
2138 | Tamluk Division | Contai Sub-Division | Constrution of Boundary wall (as per Departmental Desigh & Drawing) And,Augmentation of Silampur Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000303/2023-2024 | 600/TD | 17/05/2023 | 30 | M/S SOURAV MAHAPATRA | 7.01 | 4.5 | 100
2139 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Silampur, Uttar Khasda, Barchunfali, Uttar Charaikhia Retrofitting PWSS in Contai - I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001176/2023-2024 | 2331/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0.83 | 100
2140 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000013/2023-2024 | 341/TD | 26/04/2023 | 0 | Resource Division | 4.77 | 0 | 0
2141 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SILAMPUR Water Supply Scheme T/W-III, (Ref. ID-204134606) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02997/2023-2024 | BP-2023-24-361 | 24/11/2023 | 0 | WBSEDCL | 3.71 | 0 | 0
2142 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001986/2022-2023 | 894/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 11.09 | 85
2143 | Tamluk Division | Digha Sub-Division | Land Development at HeadWorks site of Baincha Water Supply Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2025-2026 | 1575/TD | 13/06/2025 | 7 | M/S JOY | 4.75 | 0 | 0
2144 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (880nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Baincha PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000481/2023-2024 | 1566/TD | 19/07/2023 | 709 | M/S JOY | 322.5 | 136.69 | 45
2145 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000022/2025-2026 | 2091/TD | 12/08/2025 | 0 | Resource Division | 4.31 | 0 | 0
2146 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000255/2022-2023 | 2712/TD | 06/02/2023 | 0 | Resource Division | 32.92 | 0 | 0
2147 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAINCHA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005006522/QUOT/03 DT. 13-12-2024 Application NO- 2005006522 Application type-New connection Consumer Id- 204472411 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03682/2024-2025 | C012524065878 | 09/01/2025 | 0 | WBSEDCL | 3.96 | 0 | 0
2148 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAINCHA W/S Scheme under MMD, PHE, Dte. Block- Egra-II, BALIGHAI C.C.C. Ref. Memo No- 2004626460/QUOT/03 DT. 01-03-2024 Application NO- 2004626460 Application type-New connection Consumer Id- 204233927 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04507/2023-2024 | BP-2023-24-864 | 16/03/2024 | 0 | WBSEDCL | 5.54 | 0 | 0
2149 | Midnapore Mechanical | Digha Sub-Division | "Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAINCHA AND ITS ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. ¿" | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002040/2022-2023 | 948/W/MMD | 28/03/2023 | 887 | A.S.ENTERPRISE | 21.57 | 9.57 | 90
2150 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Katnadighi PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000187/2024-2025 | 2197/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2151 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 32.79 | 51
2152 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000046/2024-2025 | 1653/TD | 29/04/2024 | 0 | Resource Division | 3.51 | 0 | 0
2153 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000155/2022-2023 | 2461/TD | 16/01/2023 | 0 | Resource Division | 21.8 | 0 | 0
2154 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KATNADIGHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760145/QUOT/03 DT. 04-06-2024 Application NO- 2004760145 Application type-New connection Consumer Id- 204322030 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01237/2024-2025 | BP-2024-25-296 | 18/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
2155 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KATNADIGHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004971258/QUOT/03 DT. 20-11-2024 Application NO- 2004971258 Application type-New connection Consumer Id- 204450411 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03663/2024-2025 | C012524067307 | 09/01/2025 | 0 | WBSEDCL | 3.33 | 0 | 0
2156 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KATNADIGHI AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001742/2022-2023 | 606/W/MMD | 20/03/2023 | 884 | RITESH AGARWALL | 11.98 | 0 | 90
2157 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000019/2023-2024 | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100
2158 | Tamluk Division | Tamluk Sadar Sub-Division | 3(Three) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Gobindanagar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000133/2023-2024 | 269/TD | 20/04/2023 | 600 | M/S. S. A. CONSTRUCTION | 49.64 | 10.88 | 100
2159 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 9.62 | 100
2160 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000010/2023-2024 | 344/TD | 26/04/2023 | 0 | Resource Division | 13.24 | 0 | 0
2161 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and allied works for construction of Tube Well (300mm x 200mm x 230mtrs. Depth) by utilising Departmental Machineries for Gobindanagar PWSS 1ST Boosting TW, Z-I, Panskura - I Block under Purba Medinipur District, CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000461/2022-2023 | 2113/CDD | 02/03/2023 | 30 | PADMA ENGINEERING & CO. | 17.76 | 14.72 | 100
2162 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR, Water Supply Scheme T/W-I, Zone-I (Ref. ID-204056032) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01754/2023-2024 | BP-2023-24-177 | 08/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0
2163 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048353) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01814/2023-2024 | BP-2023-24-197 | 18/08/2023 | 0 | WBSEDCL | 12.55 | 0 | 0
2164 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR (ALALPARA)Water Supply Scheme Z-II, T/W-II (Ref. ID-204048367) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01815/2023-2024 | BP-2023-24-198 | 18/08/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
2165 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotation for GOBINDANAGAR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048353) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03182/2023-2024 | C032434121398 | 01/01/2025 | 0 | WBSEDCL | 0 | 0 | 0
2166 | Midnapore Mechanical | Tamluk Sadar Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF JANUARY'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04353/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.23 | 0 | 0
2167 | Midnapore Mechanical | Tamluk Sadar Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF JANUARY'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04365/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.19 | 0 | 0
2168 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional service connection charge at Gobindanagar, Zone-II, TW-IV Chiara, Chiara, Gobindanagar, Golghat Panskura Ref ID-860294542 Application ID-100000102262 Panskura CCC | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04383/2023-2024 | BP-2023-24-827 | 13/03/2024 | 0 | WBSEDCL | 1.83 | 0 | 0
2169 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
2170 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
2171 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1(One)) No. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001395/2023-2024 | 3042/W/MMD | 17/11/2023 | 501 | SHIVAM ENTERPRISE | 13.68 | 2.95 | 80
2172 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002000/2022-2023 | 902/W/MMD | 27/03/2023 | 180 | M/S EMMESS | 40.78 | 40.07 | 70
2173 | Tamluk Division | Tamluk Sadar Sub-Division | Quotation bill for T/W NO-II OF Tulia W/S SCHEME under MMD,PHE,Dte. WBSEDCL SUPPLY OFFICE: Gourangapur C.C.C Ref. Memo No- 2004981451/Quot/03/4281 DT. 27-11-2024 APPLICATION NO: 2004981451 Consumer Id- 204457141 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01264/2024-2025 | BP-2024-25-656 | 06/02/2025 | 0 | WBSEDCL | 14.15 | 0 | 0
2174 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube well ,Laying distribution pipe line, laying Rising main ,Pump House , Boundary Wall, Soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC 2059 nos) including Operation & Maintanance for Two years under JJM with allied work including supply of all labour & materials for Tulia and Adjoining Moujas Piped Water Supply Scheme in Tamluk Dev. Block within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000354/2023-2024 | 908/TD | 01/06/2023 | 998 | HARIPADA PATTANAYAK | 492.6 | 51.07 | 50
2175 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000344/2022-2023 | 3018/TD | 27/02/2023 | 0 | Resource Division | 24.12 | 0 | 0
2176 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Tulia W/S scheme Application no.-2004555235 Ref.-204184819 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03534/2023-2024 | BP-2023-24-621 | 07/02/2024 | 0 | WBSEDCL | 16.04 | 0 | 0
2177 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TULIA AND ADJOINING MOUJAS PWSS Tamluk Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001977/2022-2023 | 888/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 11.02 | 35
2178 | Midnapore Mechanical | Haldia Electrical Sub-Division | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001487/2022-2023 | 266/W/MMD | 20/02/2023 | 180 | SOUMEN ELECTRIC | 41.28 | 0 | 0
2179 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2022-2023 | 1932./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 2.89 | 100
2180 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 173 Nos) under JJM with allied work for Chirulia-Chatla (Zone-IV) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000523/2023-2024 | 1759/TD | 01/08/2023 | 180 | SUSIL KUMAR HAZRA | 262.49 | 0 | 0
2181 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000051/2023-2024 | 2076/TD | 28/08/2023 | 0 | Resource Division | 15.05 | 0 | 0
2182 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000093/2023-2024 | 2996/TD | 29/11/2023 | 0 | Resource Division | 1.07 | 0 | 0
2183 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
2184 | Tamluk Division | Digha Sub-Division | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-IV) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000299/2024-2025 | 3069/TD | 19/09/2024 | 20 | GHOSH ENTERPRISE | 4.62 | 0 | 100
2185 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000463/2022-2023 | 1866/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.98 | 100
2186 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (48 nos) under JJM with allied work for Bathuari (Zone-IV) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000526/2023-2024 | 1762/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 278.74 | 26.66 | 20
2187 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2023-2024 | 2073/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0
2188 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000099/2023-2024 | 3002/TD | 29/11/2023 | 0 | Resource Division | 0.3 | 0 | 0
2189 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004714304/QUOT/03/142 DT. 03-05-2024 Application NO- 2004714304 Application type-New connection Consumer Id- 204294967 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01278/2024-2025 | BP-2024-25-337 | 25/06/2024 | 0 | WBSEDCL | 4.73 | 0 | 0
2190 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004941929/QUOT/03/769 DT. 25-10-2024 Application NO- 2004941929 Application type-New connection Consumer Id- 204428742 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03020/2024-2025 | C112429746394 | 25/11/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
2191 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
2192 | Tamluk Division | Contai Sub-Division | Quotation for new service connection at Dekhali w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004783456, Ref ID 204336497) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00590/2024-2025 | BP-2024-25-288 | 29/07/2024 | 0 | WBSEDCL | 12.1 | 0 | 0
2193 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Rising main,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works, with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (4781 Nos), including 2 years Operation & Maintenance For Halud Bari, Dekhali, Pipe water supply Scheme within Khejuri-II Block, within Contai Sub-Division Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000287/2023-2024 | 454/TD | 04/05/2023 | 1092 | TAPAS SANTRA | 1701.13 | 815.02 | 78
2194 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000227/2022-2023 | 2707/TD | 06/02/2023 | 0 | Resource Division | 20.88 | 0 | 0
2195 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Dekhali w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640113, Ref ID - 204244140) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04492/2023-2024 | BP-2023-24-865 | 16/03/2024 | 0 | WBSEDCL | 8.79 | 0 | 0
2196 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEKHALI and ADJOINING MOUJAS, Block ¿ Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001590/2022-2023 | 474/W/MMD | 20/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 27.04 | 23.1 | 60
2197 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC(Balance work) (579 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-IV, Block-Kolaghat in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000021/2022-2023 | 62/TD | 05/04/2022 | 30 | CONCORD ENGINEERING | 91.47 | 65.2 | 100
2198 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
2199 | Tamluk Division | Haldia Sub-Division | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Tajpur W/S Scheme within Nandigram-I Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000174/2023-2024 | 331/TD | 25/04/2023 | 617 | M/S SOURAV MAHAPATRA | 12.42 | 10.79 | 100
2200 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000002/2023-2024 | 354/TD | 26/04/2023 | 0 | Resource Division | 1.14 | 0 | 0
2201 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for TAJPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063651) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01823/2023-2024 | BP-2023-24-202 | 24/08/2023 | 0 | WBSEDCL | 3.86 | 0 | 0
2202 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.71 | 35
2203 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Badalpur PWSS at Ramnagar - II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000889/2023-2024 | 208/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2204 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000069/2024-2025 | 2947/TD | 12/09/2024 | 0 | Resource Division | 1.53 | 0 | 0
2205 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000346/2022-2023 | 3011/TD | 27/02/2023 | 0 | Resource Division | 6.62 | 0 | 0
2206 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-1 of Badalpur ws scheme under MMD,PHE Dte. Block-Contai-I, Pichaboni CCC. Application no-2004641194. Con ID-204244743. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00009/2024-2025 | BP-2024-25-1 | 04/04/2024 | 0 | WBSEDCL | 0.86 | 0 | 0
2207 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
2208 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
2209 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
2210 | Tamluk Division | Haldia Sub-Division | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Jalpai Part-II W/S Scheme within Nandigram-II Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000172/2023-2024 | 329/TD | 25/04/2023 | 608 | M/S SOURAV MAHAPATRA | 13.12 | 8.41 | 100
2211 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000006/2023-2024 | 360/TD | 26/04/2023 | 0 | Resource Division | 0.35 | 0 | 0
2212 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for JALPAI PART-II, Water Supply Scheme , T/W-III, (Ref. ID-204076620) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02190/2023-2024 | BP-2023-24-257 | 26/09/2023 | 0 | WBSEDCL | 5.72 | 0 | 0
2213 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.64 | 35
2214 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 17.82 | 100
2215 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Saripur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000442/2023-2024 | 1425/TD | 12/07/2023 | 60 | SK. NUR ISLAM | 13.01 | 12.98 | 100
2216 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (42 nos) under JJM within Saripur PWSS (Balance work) within Chandipur Block under Tamluk Sub Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000546/2024-2025 | 147/TSD | 20/01/2025 | 126 | NARAYAN MANDAL | 2.48 | 0 | 100
2217 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000005/2023-2024 | 350/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
2218 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for SARIPUR Water Supply Scheme T/W-I, (Ref. ID-204064849) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02888/2023-2024 | BP-2023-24-309 | 01/11/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
2219 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 8.1 | 55
2220 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate under JJM with allied work for Dariapur PWSS within Contai-II (Deshpran) Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. Part-A | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000143/2023-2024 | 286/TD | 20/04/2023 | 60 | BUNBA CONSTRUCTION | 28.63 | 0 | 0
2221 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Haipur, Damodarpur Retrofitting PWSS in Contai - I Block, Dariapur & Bankiput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001167/2023-2024 | 2332/CSD | 29/12/2023 | 15 | JASODA ENTERPRISE | 0.83 | 0.83 | 100
2222 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000004/2025-2026 | 1648/TD | 18/06/2025 | 0 | Resource Division | 8.9 | 0 | 0
2223 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000014/2023-2024 | 343/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
2224 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000049/2023-2024 | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 53
2225 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001856/2022-2023 | 767/W/MMD | 23/03/2023 | 1 | M/S SWAPAN BANERJEE | 12.24 | 0 | 0
2226 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001854/2022-2023 | 772/W/MMD | 23/03/2023 | 1015 | SOUMEN ELECTRIC | 12.65 | 10.53 | 82
2227 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001844/2022-2023 | 761/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.22 | 9.89 | 60
2228 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001843/2022-2023 | 760/W/MMD | 23/03/2023 | 180 | RAJIB COMPANY | 12.24 | 7.15 | 35
2229 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001853/2022-2023 | 771/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.66 | 6.77 | 30
2230 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at BARBASUDEBPUR and adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2024-2025 | 535/HESD | 10/06/2024 | 15 | KOLEY ENTERPRISE | 1.23 | 0.18 | 75
2231 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001855/2022-2023 | 757/W/MMD | 23/03/2023 | 180 | M/S SWAPAN BANERJEE | 11.35 | 0 | 0
2232 | Tamluk Division | Digha Sub-Division | Drum sheet piling work, Canal Crossing Structure for Distribution pipe line, Supply and delivery of different dia D.I. specials, Repairing & renovation of OHR (350 CUM), Repairing & renovation of existing H/W site Pump House & 2nd TW site Pump house with allied works under JJM for Augmentation of Astichak Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000640/2024-2025 | 852/TD | 19/03/2025 | 40 | ONKAR ENTERPRISE | 78.51 | 0 | 100
2233 | Tamluk Division | Digha Sub-Division | Proposed Rising main and interconnection with OHR of ASTICHAK (Z-II ) & its adjoining moujas Water Supply Scheme within Egra-II Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000834/2023-2024 | 3326/TD | 27/12/2023 | 789 | ONKAR ENTERPRISE | 515.99 | 401.82 | 98
2234 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000858/2021-2022 | 1471/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.75 | 4.75 | 100
2235 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000041/2023-2024 | 2079/TD | 28/08/2023 | 0 | Resource Division | 49.99 | 0 | 0
2236 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000104/2023-2024 | 3007/TD | 29/11/2023 | 0 | Resource Division | 13.53 | 0 | 0
2237 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of ASTICHAK ZII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004749715/QUOT/03 DT. 05-06-2024 Application NO- 2004749715 Application type-New connection Consumer Id- 204317619 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01229/2024-2025 | BP-2024-25-299 | 18/06/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
2238 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-IV, ZONE-II Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005050851/QUOT/03/963 DT. 20-01-2025 Application NO- 2005050851 Application type-New connection Consumer Id- 204501207 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04253/2024-2025 | C032554613786 | 17/03/2025 | 0 | WBSEDCL | 4.19 | 0 | 0
2239 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-II) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001982/2022-2023 | 890/W/MMD | 27/03/2023 | 857 | M/S B.M. ELECTRICAL | 23.7 | 15.94 | 40
2240 | Tamluk Division | Contai Sub-Division | Quotation bill for Kanthi Bari Water supply scheme PH-II, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711606 Reference ID.-204294517 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00448/2024-2025 | BP-2024-25-169 | 10/06/2024 | 0 | WBSEDCL | 10.12 | 0 | 0
2241 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1582 nos) under JJM with allied work for Kanthi Bari & its adjoining moujas PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000475/2023-2024 | 1516/TD | 17/07/2023 | 987 | TAPAS SANTRA | 565.57 | 349.77 | 70
2242 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000094/2024-2025 | 2962/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0
2243 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000338/2022-2023 | 2977/TD | 27/02/2023 | 0 | Resource Division | 33.32 | 0 | 0
2244 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 29.37 | 11
2245 | Midnapore Mechanical | Contai Sub-Division | Quotation bill for Kanthi Bari Water supply scheme PH-I, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711599 Reference ID.-204294533 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00857/2024-2025 | BP-2024-25-161 | 15/05/2024 | 0 | WBSEDCL | 15.76 | 0 | 0
2246 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANTHI BARI and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001347/2022-2023 | 2358/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0
2247 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 102.22 | 30
2248 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000073/2024-2025 | 2974/TD | 12/09/2024 | 0 | Resource Division | 10.48 | 0 | 0
2249 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000203/2022-2023 | 2405/TD | 16/01/2023 | 0 | Resource Division | 20.41 | 0 | 0
2250 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001409/2022-2023 | 2420/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 51
2251 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 1080 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
2252 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000088/2024-2025 | 2966/TD | 12/09/2024 | 0 | Resource Division | 2.62 | 0 | 0
2253 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000213/2022-2023 | 2408/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0
2254 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MAHISHAGOAT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004963932/QUOT/03 DT. 22-11-2024 Application NO- 2004963932 Application type-New connection Consumer Id- 204444763 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03363/2024-2025 | C122421452693 | 16/12/2024 | 0 | WBSEDCL | 7.32 | 0 | 0
2255 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MAHISHAGOAT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004965980/QUOT/03 DT. 22-11-2024 Application NO- 2004965980 Application type-New connection Consumer Id- 204446012 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03364/2024-2025 | C122421449766 | 16/12/2024 | 0 | WBSEDCL | 7.31 | 0 | 0
2256 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001737/2022-2023 | 601/W/MMD | 20/03/2023 | 180 | SHAKEEL KHAN | 11.98 | 0 | 0
2257 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Basudevpur ( Phase-II ) PWSS Block-Egra-II in the District Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000131/2021-2022 | 1013/TD | 02/11/2021 | 30 | SNEHESH SEN | 69.11 | 67.16 | 100
2258 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 237.07 | 75
2259 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gobradan PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000874/2023-2024 | 196/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
2260 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000005/2024-2025 | 1563/TD | 23/04/2024 | 0 | Resource Division | 8.75 | 0 | 0
2261 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000181/2022-2023 | 2426/TD | 16/01/2023 | 0 | Resource Division | 21.84 | 0 | 0
2262 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gobradan w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No. 2004631559, Ref ID 204237227) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04737/2023-2024 | BP-2023-24-905 | 28/03/2024 | 0 | WBSEDCL | 9.24 | 0 | 0
2263 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gobradan w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631550, 204237224) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04743/2023-2024 | BP-2024-25-16 | 08/04/2024 | 0 | WBSEDCL | 10.25 | 0 | 0
2264 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOBRADAN and ADJOINING MOUJAS, Block Moyna, District Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002198/2022-2023 | 455/W/MMD | 20/03/2023 | 711 | JOYSHREE CONCERN | 23.64 | 4.78 | 80
2265 | Tamluk Division | Haldia Electrical Sub-Division | SHIFTING OF LT POLE AT - DHITAIBASAN | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01362/2024-2025 | BP-2024-25-657 | 06/02/2025 | 0 | WBSEDCL | 0.8 | 0 | 0
2266 | Tamluk Division | Haldia Electrical Sub-Division | Design & Construction of GSLR (4900 Cum) at Nandakumar Block & GSLR (3800 Cum ) at Chandipur Block including High lift Pump House, Chlorine room, Store room, Sub Station Building, Administrative Building, Guard Room, Staff quarter and other allied Structures and Construction of Zonal Overhead Reservior (27 Nos) including Soil Investigation of Different Capacity along with CW Rising Main ,Laying of Distribution Pipeline and FHTC (51946 Nos) including sinking of Big Dia Tube Wells and its connections and other allied works as per direction of EIC including 1 years Operation and Maintenance after successful Trail Run(180 Days) for Surface water based Water supply scheme for Nandakumar Block and Chandipur Block under Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000246/2024-2025 | 2707/TD | 23/08/2024 | 646 | R SANDESH INFRACONTRACTS PRIVATE LIMITED | 16926.01 | 313.53 | 15
2267 | Tamluk Division | Haldia Electrical Sub-Division | Route survey and all releated field works for preparation and submission of zone wise Geo tagged reference drawing with desinged pipe network system at Chandipur Development Block and Nandakumar Development Block within Purba Medinipur District Under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000344/2023-2024 | 844/TD | 31/05/2023 | 40 | ENVIROTECH SOLUTIONS | 85.01 | 68.61 | 100
2268 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-II (Bhagaban Khali) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000392/2025-2026 | 2132/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2269 | Tamluk Division | Haldia Electrical Sub-Division | Laying UPVC pipe line 90 ( OD ) for left out portion at village Bhandarberia Jalpai under Jalpai PWSS Tamluk Sub-Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000402/2025-2026 | 2148/TD | 18/08/2025 | 30 | FARID UDDIN AHMED | 4.18 | 0 | 90
2270 | Tamluk Division | Haldia Electrical Sub-Division | Dismantling of existing damaged godown staff quarter, Guard room and Go-Down at Jalpai PWSS under Tamluk Sub Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000403/2025-2026 | 2149/TD | 18/08/2025 | 30 | ENGINEERS CONSULTANT (INDIA) | 3.37 | 0 | 100
2271 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-III (Jaukti Basan) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000407/2025-2026 | 2133/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2272 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-IV (Barneturia) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000408/2025-2026 | 2134/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2273 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VI (Balibar) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000409/2025-2026 | 2135/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2274 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XI (Bamunara) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000410/2025-2026 | 2136/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2275 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XIV (Barabanki) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000411/2025-2026 | 2137/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2276 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XV (Usmanpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000412/2025-2026 | 2138/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2277 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVI (Rasik Chak) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000413/2025-2026 | 2139/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2278 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVII (Kulbari) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000414/2025-2026 | 2140/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2279 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XX (Dibakarpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000415/2025-2026 | 2141/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2280 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-XXI (Baraghuni) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000416/2025-2026 | 2142/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2281 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XXII (Khagda) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000417/2025-2026 | 2143/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2282 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-XXIII (Jalpai Part - II) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000418/2025-2026 | 2144/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
2283 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Chandipur Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-D) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000476/2025-2026 | 2437/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 100
2284 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000477/2025-2026 | 2438/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 100
2285 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Sahid Matangini & Nandakumar Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000478/2025-2026 | 2439/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 100
2286 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (29 nos) at different work site within Sahid Matangini Block for P.H.E. Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000479/2025-2026 | 2440/TD | 18/09/2025 | 14 | GLOBAL TRADE | 4.83 | 0 | 100
2287 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE- I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000483/2025-2026 | 2359/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
2288 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000484/2025-2026 | 2360/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
2289 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District .(PHASE-III) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000485/2025-2026 | 2361/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
2290 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work( ZONE-XI,XXII) site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District.(PHASE-IV) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000486/2025-2026 | 2362/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.42 | 0 | 100
2291 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XII (Kulup) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000620/2024-2025 | 668/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
2292 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VIII (Atattar) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000621/2024-2025 | 669/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
2293 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-V (Narandanri) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000622/2024-2025 | 670/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
2294 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-IX (Baroj) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000623/2024-2025 | 671/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
2295 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Zone-XIII (Sultanpur) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000624/2024-2025 | 672/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
2296 | Tamluk Division | Haldia Electrical Sub-Division | Repair of existing brick bats roads after laying of 600 mm dia DI-K9 pipe from Calcutta public school to Griha Lakshmi Brick Field under Nandakumar Surface based water supply scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000768/2025-2026 | 3699/TSD | 21/11/2025 | 15 | PRASANTA MONDAL | 0.94 | 0 | 100
2297 | Tamluk Division | Haldia Electrical Sub-Division | Repair of existing brick bats roads after laying of 600 mm dia DI-K9 pipe from Banbhera to Calcutta public school under Nandakumar Surface based water supply scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000769/2025-2026 | 3700/TSD | 21/11/2025 | 15 | PRASANTA MONDAL | 0.94 | 0 | 100
2298 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-IV (Mouza- Karak) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000948/2025-2026 | 2708/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2299 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Zone-V (Mouza- Sandalpur) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000949/2025-2026 | 2709/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2300 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-VII (Mouza- Bagmari) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000950/2025-2026 | 2710/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2301 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Zone-VIII (Mouza- Dhitaibasan) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000951/2025-2026 | 2711/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2302 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-X (Mouza- Kalidahi) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000952/2025-2026 | 2712/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2303 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 500 cum RCC OHR at Zone-XI (Mouza- Hatgechiya Dakshin) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000953/2025-2026 | 2713/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2304 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 500 cum RCC OHR at Zone-XIII (Mouza- Bargodagudar) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000954/2025-2026 | 2714/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2305 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-XIV (Mouza- Kumarchak) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000955/2025-2026 | 2715/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2306 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at Zone XVI (Mouza Tarageria) Nandakumar Surface based PWSS at Nandakumar Block under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000956/2025-2026 | 2716/TSD | 12/08/2025 | 20 | ENGINEERS CONSULTANT (INDIA) | 0.95 | 0 | 100
2307 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | RTOR000005/2025-2026 | 1985/TD | 29/07/2025 | 0 | Resource Division | 6341.96 | 0 | 0
2308 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | RTOR000033/2025-2026 | 2611/TD | 13/10/2025 | 0 | Resource Division | 319.99 | 0 | 0
2309 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | RTOR000121/2024-2025 | 48/TD | 06/01/2025 | 0 | Resource Division | 146.53 | 0 | 0
2310 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | RTOR000124/2024-2025 | 805/TD | 18/03/2025 | 0 | Resource Division | 44.15 | 0 | 0
2311 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for new power connection at Karak , within Nandakumar block .Application No : 2005358103 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01873/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 11.76 | 0 | 0
2312 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for new power connection at Dhitaibasan , within Nandakumar block .Application No : 2005136791 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01874/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 6.33 | 0 | 0
2313 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for new power connection at majnaberiachak , OHR ZONE - III , within Chandipur block .Application No : 2005327907 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01877/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 5.8 | 0 | 0
2314 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for new power connection at Kumarchak , within Nandakumar block .Application No : 2005358038 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01878/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 18.04 | 0 | 0
2315 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for new power connection at Hatgachiya , within Nandakumar block .Application No : 2005358145 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/01879/2025-2026 |  | 14/08/2025 | 0 | WBSEDCL | 13.39 | 0 | 0
2316 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Kulup PWSS within Chandipur Block ,Application No - 2005015711 , Ref ID- 204478036 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04003/2024-2025 | C022509341382 | 05/02/2025 | 0 | WBSEDCL | 5.34 | 0 | 0
2317 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Sultanpur PWSS within Chandipur Block ,Application No - 2005015716 , Ref ID- 204478037 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04004/2024-2025 | C022509328157 | 05/02/2025 | 0 | WBSEDCL | 3.73 | 0 | 0
2318 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Atattar PWSS within Chandipur Block ,Application No - 2005015013 , Ref ID- 204478032 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04005/2024-2025 | C032554591547 | 17/03/2025 | 0 | WBSEDCL | 3.41 | 0 | 0
2319 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Jalpai Part - II PWSS within Chandipur Block ,Application No - 2005015706 , Ref ID- 204478033 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04006/2024-2025 | C022509332396 | 04/02/2025 | 0 | WBSEDCL | 3.86 | 0 | 0
2320 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Burunda PWSS within Chandipur Block ,Application No - 2005015699 , Ref ID- 204478035 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04007/2024-2025 | C022509338458 | 05/02/2025 | 0 | WBSEDCL | 4.47 | 0 | 0
2321 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Narandari PWSS within Chandipur Block ,Application No - 2005015718 , Ref ID- 204478031 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/04008/2024-2025 | C022509346213 | 05/02/2025 | 0 | WBSEDCL | 4.57 | 0 | 0
2322 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new power connection at Uttar Iswarpur , Application No- 2005244109, reference Id- 204635106 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05487/2025-2026 |  | 13/02/2026 | 0 | WBSEDCL | 5.73 | 0 | 0
2323 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new power connection at Barneturia , Zone-IV, Application No- 2005015692, Reference Id- 204478034 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05488/2025-2026 |  | 13/02/2026 | 0 | WBSEDCL | 10.28 | 0 | 0
2324 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Barbanki , Application No- 2005015680 and Reference Id- 204478030 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05489/2025-2026 |  | 13/02/2026 | 0 | WBSEDCL | 12.68 | 0 | 0
2325 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new power connection at Nandapur, Zone -21 under Chandipur Block, Application No-2005262607, Reference Id- 204642211 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05490/2025-2026 |  | 13/02/2026 | 0 | WBSEDCL | 6.6 | 0 | 0
2326 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new power connection at Brajalalchak, Application Id- 2005292161, Reference Id- 204655325 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05491/2025-2026 |  | 13/02/2026 | 0 | WBSEDCL | 10.29 | 0 | 0
2327 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new power connection at Bhagwankhali, Zone-II, Chandipur, Application No- 2005325190, Reference id:- 204669239 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | BILL/05694/2025-2026 |  | 19/02/2026 | 0 | WBSEDCL | 4.48 | 0 | 0
2328 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipment's at Newly sunk Tube well within NANDAKUMAR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001559/2023-2024 | 3174/W/MMD | 18/12/2023 | 180 | SOUMEN ELECTRIC | 96.15 | 55.59 | 20
2329 | Midnapore Mechanical | Haldia Electrical Sub-Division | 11/0.433 KV, 1600 KVA Electrical Substation allied Electrical works at Chandipur GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001636/2023-2024 | 41/W/MMD | 10/01/2024 | 540 | THE MARKET ELECTRICAL ENGINEERING WORKS | 532.18 | 97.17 | 20
2330 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-mechanical works for Nandakumar and Chandipur WTP SITE under Midnapore Mechanical Division, PHE Dte. under JJM in Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001638/2023-2024 | 42/W/MMD | 10/01/2024 | 733 | MACHINE SUPPLIERS SYNDICATE (P) LTD | 734.46 | 0 | 10
2331 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-Mechanical works for Chandipur GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001641/2023-2024 | 43/W/MMD | 10/01/2024 | 528 | WEST BENGAL ENGINEERING CO. | 1578.72 | 0 | 20
2332 | Midnapore Mechanical | Haldia Electrical Sub-Division | 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Nandakumar GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001642/2023-2024 | 44/W/MMD | 10/01/2024 | 540 | APEX ENGINEERING & PROJECT CO | 533.06 | 115.61 | 20
2333 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-Mechanical works for Nandakumar GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001718/2023-2024 | 92/W/MMD | 24/01/2024 | 540 | ORIENTAL ENGINEERING CO. | 1405.35 | 0 | 20
2334 | Midnapore Mechanical | Haldia Electrical Sub-Division | Hiring Vehicle for Site inspection of Nandakumar Chnadipur Surface based Project and Pingla Panskura Surface based Project under Midnapore Mechanical Division , P.H.E.Dte (Vehical No. WB-31A-3738) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001868/2024-2025 | 781//WMMD | 24/02/2025 | 365 | SUDIP KUMAR ROY | 7.78 | 0 | 70
2335 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well within CHANDIPUR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001875/2023-2024 | 903/W/MMD | 21/02/2024 | 180 | DEBJYOTI BASU | 192.31 | 102.72 | 20
2336 | Midnapore Mechanical | Haldia Electrical Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
2337 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VI(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000120/2020-2021 | 2633/TD | 05/01/2021 | 60 | JAGANNATH MAKAR | 96.81 | 193.59 | 100
2338 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000231/2021-2022 | 158/W | 30/07/2021 | 0 | MAA ANANDAMAYEE | 0.34 | 0 | 0
2339 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS(Zone-II) Block -Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000127/2020-2021 | 2635/TD | 05/01/2021 | 60 | SWADHIN KUMAR CHAKRABORTY | 76.69 | 0 | 100
2340 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000260/2021-2022 | BP-2021-22-77 | 17/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 6.78 | 0 | 0
2341 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000395/2021-2022 | 245/W | 13/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 9 | 0 | 0
2342 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001185/2020-2021 | 825/W | 02/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 35.94 | 0 | 0
2343 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001210/2020-2021 | 933/W | 18/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 24.96 | 0 | 0
2344 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VII(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000195/2020-2021 | 2779/TD | 29/01/2021 | 120 | TARUN KOLEY | 253.33 | 506.67 | 100
2345 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-III(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000196/2020-2021 | 2780/TD | 29/01/2021 | 120 | JAYANTA KUMAR MONDAL | 259.53 | 512.89 | 100
2346 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-V(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000198/2020-2021 | 2785/TD | 01/02/2021 | 120 | M/S EL-CON | 241.65 | 450.27 | 100
2347 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000209/2020-2021 | 2821/TD | 05/02/2021 | 100 | M/S A.R. ENTERPRISE | 216.86 | 433.43 | 100
2348 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-IV(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000240/2020-2021 | 2845/TD | 08/02/2021 | 120 | CONCORD ENGINEERING | 267.73 | 375.47 | 100
2349 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Habichak PWSS Block Chandipur in the District of Purba Medinipur. |  |  | ORD/000035/2020-2021 | 2112/TD | 05/11/2020 | 180 | TAPAS SANTRA | 96.73 | 0 | 100
2350 | Tamluk Division |  | Left out portion for laying distribution system of pipe line and its allied works for Habichak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. |  |  | ORD/000108/2021-2022 | 790/TD | 28/09/2021 | 20 | TAPAS SANTRA | 6.59 | 0 | 0
2351 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000227/2021-2022 | 142/W | 22/07/2021 | 0 | TAPAS SANTRA | 1.52 | 0 | 0
2352 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000593/2020-2021 | 638/W | 14/01/2021 | 0 | TAPAS SANTRA | 48.82 | 0 | 0
2353 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001045/2020-2021 | 698/W | 02/02/2021 | 0 | TAPAS SANTRA | 46.39 | 0 | 0
2354 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Jagatpur PWSS Block Panskura-I in the District of Purba Medinipur. |  |  | ORD/000034/2020-2021 | 2111/TD | 05/11/2020 | 180 | ARUP KUMAR DEY | 88.18 | 12.62 | 100
2355 | Tamluk Division |  | Repairing & partly re-laying of 100 dia DI(K-9) of Rising main line from T/W-1 to OHR under Jagatpur PWSS with in Panskura Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. |  |  | ORD/000947/2025-2026 | 225/TSD | 09/02/2026 | 30 | GLOBAL TRADE | 0.96 | 0 | 0
2356 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Jagatpur W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001033/2020-2021 | 711/W | 09/02/2021 | 0 | ARUP KUMAR DEY | 74.34 | 0 | 0
2357 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS Block - Ramnagar-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000138/2020-2021 | 2688/TD | 20/01/2021 | 60 | UNIQUE AGENCY | 60.84 | 60.84 | 100
2358 | Tamluk Division |  | Laying (Left Out) UPVC pipe line to accommodate FHTC under JJM in Kudi PWSS within Egra-I Block (to support phase-1 FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. (Mouza- Naraharipur, Usma, Kudi) |  |  | ORD/000023/2022-2023 | 76/TD | 08/04/2022 | 25 | MONDAL PRECISION PRIVATE LIMITED | 16.72 | 0 | 0
2359 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kudi PWSS Block-Egra-I in the District of Purba Medinipur. |  |  | ORD/000137/2020-2021 | 2667/TD | 14/01/2021 | 60 | MONDAL PRECISION PRIVATE LIMITED | 70.47 | 0 | 75
2360 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000399/2021-2022 | 246/W | 14/09/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 10.18 | 0 | 0
2361 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001233/2020-2021 | 983/W | 25/03/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 37.11 | 0 | 0
2362 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Argoal PWSS Block -Potashpur-II in the District of Purba Medinipur. |  |  | ORD/000202/2020-2021 | 2803/TD | 04/02/2021 | 45 | DAS ENTERPRISE | 125.99 | 38.39 | 100
2363 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000259/2021-2022 |  | 06/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0
2364 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000314/2021-2022 | BP-2021-22-79 | 17/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0
2365 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Argoal Piped Water Supply Scheme |  |  | VCH/001113/2020-2021 | 1091/W | 30/03/2021 | 0 | DAS ENTERPRISE | 40.02 | 0 | 0
2366 | Tamluk Division |  | Retrofitting to accomodate FHTC (700 nos.) under JJM IN Silampur PWSS under CONTAI-I BLOCK of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) |  |  | ORD/000008/2021-2022 | 686/TD | 10/09/2021 | 30 | BASANTA KUMAR MAITY | 58.45 | 48.98 | 90
2367 | Tamluk Division |  | Laying of different dia UPVC pipe line to accommodate 86 nos FHTC to make Betgerya,Eryafetepur, Khalisabhanga,, Betbani, Paryadwip, Silampur, Sitalpur & Sujulpur Mouza as Swajal Gram of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000522/2022-2023 | 2094 /TD | 13/12/2022 | 20 | ROY & ROY CONSTRUCTION. | 5.73 | 5.63 | 100
2368 | Tamluk Division |  | Re-laying of 140 mm dia UPVC pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000576/2022-2023 | 877 / CSD | 22/11/2022 | 21 | JASODA ENTERPRISE | 0.84 | 0.84 | 100
2369 | Tamluk Division |  | Re-laying of 125 mm dia UPVC & 100 mm dia DI (K-7) pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000577/2022-2023 | 885 / CSD | 23/11/2022 | 21 | PAL ENTERPRISE. | 0.82 | 0.81 | 100
2370 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000279/2020-2021 | 2997/TD | 25/02/2021 | 60 | SRIMANTA KUMAR MAITY | 197.96 | 119.39 | 100
2371 | Tamluk Division |  | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Haipur Water Supply Scheme in Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000338/2024-2025 | 3336/TD | 22/10/2024 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.06 | 0 | 0
2372 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block Contai - I in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000377/2021-2022 | BP-2021-22-132 | 18/10/2021 | 0 | SRIMANTA KUMAR MAITY | 78.57 | 0 | 0
2373 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM at Santeswarpur J.L No-8(Part), Purushottampur J.L. No-11(Part), Kholaberia J.L. No-36(part), Ranisai J.L. No-40(Part) in Ranisai PWSS within Block - Ramnagar under Digha Sub-Division of Tamluk Division, P.H.E. Dte. in the District of Purba Medinipur. ( PHASE-II) |  |  | ORD/000269/2020-2021 | 2922/TD | 22/02/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.9 | 0 | 100
2374 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000379/2021-2022 |  | 04/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0
2375 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000424/2021-2022 | BP-2021-22-136 | 18/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0
2376 | Tamluk Division |  | Balance Work for Retrofitting to accommodate FHTC (907 Nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water based water supply scheme for Zone-VII ,Block-Kolaghat in the District of Purba Medinipur under tamluk Division. (Phase-II) |  |  | ORD/000142/2021-2022 | 1069/TD | 08/11/2021 | 60 | TARUN KOLEY | 119.62 | 115.86 | 100
2377 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bar Basudevpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000189/2021-2022 | 1198/TD | 02/12/2021 | 20 | RADIANT | 4.28 | 4.21 | 100
2378 | Tamluk Division | Haldia Sub-Division | Additional Laying Distribution System of 200 mm dia upvc pipe line and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia(sec 2-14) and 180 mm dia(sec-20-23) of pipe line of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000307/2022-2023 | 1147/TD | 31/08/2022 | 20 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.88 | 24.11 | 100
2379 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (646 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000335/2021-2022 | 1769/TD | 08/02/2022 | 680 | ZENITH CONSTRUCTION | 84.54 | 50.24 | 75
2380 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (446 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2021-2022 | 1770/TD | 08/02/2022 | 40 | SHAKEEL KHAN | 53.9 | 17.85 | 55
2381 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection at Barbasudevpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2023-2024 | 802/TD | 30/05/2023 | 20 | PULAK KUMAR SAMANTA | 6.22 | 4.72 | 100
2382 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part- III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000338/2021-2022 | 1771/TD | 08/02/2022 | 30 | MAA KALI CONSTRUCTION | 47.34 | 46.29 | 100
2383 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-IV) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000339/2021-2022 | 1772/TD | 08/02/2022 | 30 | FARID UDDIN AHMED | 47.43 | 43.13 | 80
2384 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Barbasudevpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000382/2022-2023 | 1383/TD | 23/09/2022 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.13 | 3.88 | 100
2385 | Tamluk Division | Haldia Sub-Division | Laying of additional 90mm dia. distribution pipe line and cannel crossing by M.S. structure for 140mm dia. distribution pipe laying of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. (Phase - II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000663/2022-2023 | 2348/TD | 10/01/2023 | 20 | MAA KALI CONSTRUCTION | 13.75 | 13.66 | 0
2386 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (for Barbasudevpur PWSS, Lakshya PWSS, Chaitanyapur Zone-II PWSS, Manoharpur PWSS) (Phase-VI) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001171/2023-2024 | 767/HSD | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100
2387 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000027/2021-2022 | 1300/TD | 20/12/2021 | 0 | Resource Division | 19.51 | 0 | 0
2388 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Barbasudebpur Water Supply Scheme,with in Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000484/2022-2023 | 1886/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 104.61 | 74.3 | 96
2389 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000056/2021-2022 | 1834/TD | 15/02/2022 | 0 | Resource Division | 9.79 | 0 | 0
2390 | Central Drilling | Haldia Sub-Division | Fuel Charges bill | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00100/2022-2023 | BP-2022-23-326 | 06/02/2023 | 0 | MIRA SERVICE STATION | 0.46 | 0 | 0
2391 | Central Drilling | Haldia Sub-Division | Fuel Charges for the month of January 2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00142/2022-2023 | BP-2022-23-353 | 09/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0
2392 | Central Drilling | Haldia Sub-Division | FUEL CHARGE MONTH OF FEBRUARY 2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00194/2022-2023 | BP-2022-23-387 | 29/03/2023 | 0 | MIRA SERVICE STATION | 0.2 | 0 | 0
2393 | Central Drilling | Haldia Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-II), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000053/2022-2023 | 108/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.28 | 17.82 | 100
2394 | Central Drilling | Haldia Sub-Division | PROVIDING DRILLING CREW AND ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 270 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), SUTAHATA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000167/2022-2023 | 107/CDD | 12/04/2022 | 30 | MENAKA ENTERPRISE | 18.28 | 17.62 | 100
2395 | Central Drilling | Haldia Sub-Division | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCH (REPLACEMENT TW-I), IN HALDIA BLOCK UNDER PURRBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000215/2022-2023 | 154/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 3.17 | 2.07 | 100
2396 | Central Drilling | Haldia Sub-Division | ADDITIONAL DRILLING (DEPTH 270 MTR TO 320 MTR) AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL FOR BARBASUDEVPUR W/S SCHEME (REPLACEMENT TW-II), IN HALDIA BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000216/2022-2023 | 402/CMSD-II | 01/08/2022 | 15 | MENAKA ENTERPRISE | 3.17 | 2.01 | 100
2397 | Central Drilling | Haldia Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000283/2022-2023 | 217/S&WSD | 23/11/2022 | 30 | SUMAN KUMAR DEY | 0.89 | 0.35 | 100
2398 | Central Drilling | Haldia Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000364/2022-2023 | 379/CMSD-II | 01/08/2022 | 15 | C.M. ENTERPRISE | 3.44 | 2.56 | 0
2399 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Barbasudebpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001138/2022-2023 | 2119/W/MMD | 28/11/2022 | 120 | M/S B.M. ELECTRICAL | 11.26 | 10.32 | 100
2400 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Augumentation of ground water based Barbasudebpur PWSS to accommodate FHTC in Haldia block under Haldia Sub Division of Tamluk Division in purba medinipur district under JJM program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000426/2023-2024 | 623/HESD | 17/08/2023 | 15 | SHIVAM ENTERPRISE | 3.5 | 3.24 | 75
2401 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001518/2022-2023 | 362/W/MMD | 09/03/2023 | 180 | SHIVAM ENTERPRISE | 12.63 | 11.88 | 0
2402 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Baghaput Water Supply Scheme within Deshpran ( Contai- II)Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000188/2022-2023 | 813/TD | 12/07/2022 | 1147 | G. B. CONSTRUCTION & CO. | 378.59 | 267.34 | 70
2403 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baghaput Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000314/2021-2022 | 1548/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.62 | 3.26 | 100
2404 | Tamluk Division | Contai Sub-Division | Repairing Of Boundary Wall of Head Work site and Pump House No - II under Augmentation of Baghaput Water Supply Scheme within Deshpran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000424/2023-2024 | 493/TD | 10/05/2023 | 30 | SUBHENDU HAZRA | 3.73 | 0 | 0
2405 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Baghaput Water Supply Scheme in Contai II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000488/2022-2023 | 1928/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.35 | 5.35 | 100
2406 | Tamluk Division | Contai Sub-Division | Repair and Renovation of 136 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Baghaput Water Supply Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000733/2022-2023 | 2563/TD | 24/01/2023 | 60 | NARAYAN CHANDRA DAS | 11.29 | 7.54 | 0
2407 | Tamluk Division | Contai Sub-Division | Repair And renovation Of Pump House No. I & II under Augmentation of Baghaput Water Supply Scheme within Deshpran( Contai- II) Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000958/2022-2023 | 421/CSD | 17/03/2023 | 30 | THE GODFATHER TRADING COMPANY | 2.24 | 1.23 | 100
2408 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000018/2022-2023 | 406/TD | 25/05/2022 | 0 | Resource Division | 22.79 | 0 | 0
2409 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000089/2022-2023 | 1269/TD | 12/09/2022 | 0 | Resource Division | 11.27 | 0 | 0
2410 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000066/2023-2024 | 1225/W/MMD | 25/04/2023 | 180 | M/S. JIT ENTERPRISE | 26.93 | 0 | 0
2411 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Durmut Water Supply Scheme within Despran & Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2022-2023 | 394/TD | 23/05/2022 | 1306 | MAHAVIR PUMPS MFG. PVT. LTD. | 430.39 | 344.05 | 81
2412 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Durmut Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2021-2022 | 1612/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.09 | 3.09 | 100
2413 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of over head reservoir in Durmuth Water Supply Scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2024-2025 | 3771/TD | 10/12/2024 | 294 | BISWA NIRMAN ENTERPRISE. | 7.05 | 0 | 100
2414 | Tamluk Division | Haldia Electrical Sub-Division | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 150 mm dia MS Carrier Pipe in between Mast NO 54/9 TO Mast NO 54/8 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =45 M) Section 482 TO 486. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000514/2023-2024 | 1744/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 72.22 | 46 | 64
2415 | Tamluk Division | Haldia Electrical Sub-Division | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 100 mm dia MS Carrier Pipe in between Mast NO 55/17 TO Mast NO 55/16 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =127M) Section 209 TO 231. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000515/2023-2024 | 1745/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 75.01 | 51.79 | 71
2416 | Tamluk Division | Haldia Electrical Sub-Division | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 4.26 | 100
2417 | Tamluk Division | Haldia Electrical Sub-Division | Balance work for Construction of Boundary Wall (as per Departmental Design & Drawing) at Tube Well (2nd Tube Well) site for Durmuth W/S Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000633/2024-2025 | 191/CSD | 27/01/2025 | 30 | BISWA NIRMAN ENTERPRISE. | 2.39 | 0 | 100
2418 | Tamluk Division | Haldia Electrical Sub-Division | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000744/2023-2024 | 3133/TD | 07/12/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.6 | 3.6 | 100
2419 | Tamluk Division | Haldia Electrical Sub-Division | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000746/2023-2024 | 3134/TD | 07/12/2023 | 20 | ABHIJIT BERA | 3.85 | 3.85 | 100
2420 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Hade work site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000901/2023-2024 | 248/TD | 11/01/2024 | 450 | ANIRBAN MONDAL | 11.93 | 0 | 100
2421 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Tube Well (2nd Tube Well) site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000904/2023-2024 | 249/TD | 11/01/2024 | 30 | BISWA NIRMAN ENTERPRISE. | 5.73 | 5.7 | 100
2422 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Pump House , Tube well , Boundary Wall, Rising main for Durmuth PWSS in Deshpran & Contai III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001109/2023-2024 | 559/TD | 15/02/2024 | 40 | DEVEN ENTERPRISES | 33.8 | 0 | 0
2423 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 6.11 | 100
2424 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of pump house 1 and boundary wall in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001372/2023-2024 | 240/CSD | 07/02/2024 | 45 | BISWA NIRMAN ENTERPRISE. | 0.71 | 0.69 | 100
2425 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of pump house 2 in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001373/2023-2024 | 241/CSD | 07/02/2024 | 180 | RABINDRANATH DAS | 0.92 | 0 | 100
2426 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000013/2022-2023 | 91/TD | 11/04/2022 | 0 | Resource Division | 210.65 | 0 | 0
2427 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000084/2022-2023 | 1271/TD | 12/09/2022 | 0 | Resource Division | 23.95 | 0 | 0
2428 | Tamluk Division | Haldia Electrical Sub-Division | Payment for Railway Application Fees. for Durmut PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | VCH/000450/2022-2023 |  | 01/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 17.19 | 0 | 0
2429 | Tamluk Division | Haldia Electrical Sub-Division | Charges for Way Leave Permission under railway track permission for Durmut PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | VCH/000520/2022-2023 | BP-2022-23-271 | 29/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 3.15 | 0 | 0
2430 | Central Drilling | Haldia Electrical Sub-Division | Car Oil Bill for the month of October 2022 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00009/2022-2023 | BP-2022-23-246 | 29/11/2022 | 0 | MIRA SERVICE STATION | 0.13 | 0 | 0
2431 | Central Drilling | Haldia Electrical Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000023/2022-2023 | 77/S&WSD | 27/05/2022 | 7 | SUMAN KUMAR DEY | 0.9 | 0.15 | 67
2432 | Central Drilling | Haldia Electrical Sub-Division | CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (REPLACEMENT TW-II), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000044/2022-2023 | 410/CDD | 20/05/2022 | 30 | M/S B.P.TRADING CORPORATION | 14.69 | 5.56 | 100
2433 | Central Drilling | Haldia Electrical Sub-Division | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DURMUT W/S SCHEME (TW-III), DESHPRAN BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000045/2022-2023 | 411/CDD | 20/05/2022 | 30 | ASHUTOSH DAS & CO | 14.67 | 5.36 | 100
2434 | Central Drilling | Haldia Electrical Sub-Division | SUPPLY & DELIVERY OF CONSUMABLES AT SITE FOR CONSTRUCTION OF TUBE WELL WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000046/2022-2023 | 227/CMSD-I (D) | 20/06/2022 | 15 | M/S B.P.TRADING CORPORATION | 5 | 1.63 | 100
2435 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE WITHIN CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2022-2023 | 228/CMSD-I (D) | 20/06/2022 | 15 | M/S B.P.TRADING CORPORATION | 4.05 | 3.87 | 100
2436 | Central Drilling | Haldia Electrical Sub-Division | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000065/2022-2023 | 301/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 0 | 50
2437 | Central Drilling | Haldia Electrical Sub-Division | SUPPLY & DELIVERY OF BATS AT SITE FOR MAKING APPROACH ROAD FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT DURMUT PWSS CONTAI-III BLOCK, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000197/2022-2023 | 296/CMSD-I | 08/07/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.81 | 0.59 | 100
2438 | Central Drilling | Haldia Electrical Sub-Division | LOADING UNLOADING & SHIFTING DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM DURMUT PWSS, BLOCK-CONTAI-III, PURBA MEDINIPUR DISTRICT TO PANCHLA STORE, HOWRAH UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000200/2022-2023 | 371/CMSD-I | 04/08/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.47 | 0 | 100
2439 | Central Drilling | Haldia Electrical Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000216/2021-2022 | 55/CMSD-II (D) | 31/01/2022 | 7 | ASHUTOSH PAL | 0.86 | 0.15 | 64
2440 | Central Drilling | Haldia Electrical Sub-Division | Loading unloading & Shifting of Drilling Accessories, Supporting Vehicles along with rig machine JOHN/DR/1500-I from Durmut PWSS, block Contai-III, Purba Medinipur dist. to Panchla store, Howrah under CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000302/2022-2023 | 371/CMSD-I(D) | 04/08/2022 | 7 | M/S B.P.TRADING CORPORATION | 0.47 | 0.43 | 100
2441 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply & delivery of submersible pump motor set & other electromechanical accessories at P/H No-I, under DURMUT Water Supply Scheme under MMD , P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000174/2023-2024 | 462/HESD | 13/06/2023 | 15 | DEBJYOTI BASU | 7.25 | 7.25 | 60
2442 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under durmut water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001220/2022-2023 | 2162/W/MMD | 08/12/2022 | 120 | DEBJYOTI BASU | 11.13 | 4.81 | 70
2443 | Tamluk Division | Contai Sub-Division | Repairing of inlet, outlet, washout pipe and allied works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for PASHIM KAMARDA W/S Scheme in Contai- III Block Of Purba Medinipur District under Contai Sub Division within Tamluk division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 394 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 2.26 | 2.22 | 100
2444 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM in PASCHIM KAMARDA PWSS ( Phase- II) Block - Contai-III in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000545/2021-2022 | 2005/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 39.32 | 0 | 100
2445 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valves for Paschim Kamarda Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000659/2021-2022 | 889 / CSD | 23/03/2022 | 15 | PARTHA CONSTRUCTION | 1.3 | 1.3 | 100
2446 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000031/2022-2023 | 130/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 18.87 | 100
2447 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000032/2022-2023 | 131/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
2448 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000170/2021-2022 | 1179/TD | 02/12/2021 | 20 | HORIZEN | 9.54 | 9.54 | 100
2449 | Tamluk Division | Haldia Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 900 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2022-2023 | 832/TD | 15/07/2022 | 1082 | RAJ KUMAR SINGHA | 838.35 | 739.61 | 62
2450 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000302/2022-2023 | 1152/TD | 31/08/2022 | 45 | RAI CONSTRUCTION | 4.12 | 4.09 | 0
2451 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with Water Supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000316/2022-2023 | 1227/TD | 07/09/2022 | 60 | M/S SOURAV MAHAPATRA | 4.84 | 4.42 | 100
2452 | Tamluk Division | Haldia Sub-Division | Cannel crossing, Road crossing and Drum sheet pilling of Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000449/2023-2024 | 1470/TD | 13/07/2023 | 40 | RAJ KUMAR SINGHA | 71.38 | 68.31 | 60
2453 | Tamluk Division | Haldia Sub-Division | Boundery wall including land development at 4th tube well site of Gopalpur Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000462/2023-2024 | 1492/TD | 17/07/2023 | 30 | GUCHHAIT ENTERPRISE | 8.53 | 4.69 | 100
2454 | Tamluk Division | Haldia Sub-Division | New Construction of boundary wall at 3rd T/W site (50mt) of Gopalpur Water Supply Scheme under Haldia Sub-Division PHE Dte.. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000641/2022-2023 | 2352/TD | 10/01/2023 | 45 | M/S SOURAV MAHAPATRA | 6.48 | 5.01 | 0
2455 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000644/2022-2023 | 2353/TD | 10/01/2023 | 60 | GUCHHAIT ENTERPRISE | 4.63 | 3.67 | 100
2456 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000740/2023-2024 | 3067/TD | 30/11/2023 | 481 | RAJ KUMAR SINGHA | 14.06 | 0 | 100
2457 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2023 to 31/12/2023. (12 Months) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000563/2022-2023 | 815/HSD | 29/12/2022 | 365 | SANTANU PATTANAYAK | 1.5 | 4.58 | 100
2458 | Tamluk Division | Haldia Sub-Division | Laying Distribution System at GOPALPUR PWSS with in MAHISADAL Dev. Block under Haldia Sub-Division Of Tamluk Division PHE DTE under AMAR PARA AMAR SAMADHAN. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000959/2025-2026 | 253/TD | 17/02/2026 | 60 | BHOWMIK & SONS | 3.57 | 0 | 100
2459 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) and construction of new Boundary wall at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001216/2023-2024 | 980/TD | 13/03/2024 | 456 | RAJ KUMAR SINGHA | 128.78 | 51.24 | 30
2460 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000092/2022-2023 | 1373/TD | 23/09/2022 | 0 | Resource Division | 37.63 | 0 | 0
2461 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000110/2022-2023 | 1674/TD | 03/11/2022 | 0 | Resource Division | 96.09 | 0 | 0
2462 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000180/2022-2023 | 2003987573/QUOT/03 | 11/07/2022 | 365 | WBSEDCL | 0.7 | 0 | 0
2463 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No III under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001141/2022-2023 | 2122/W/MMD | 28/11/2022 | 120 | SOUMEN ELECTRIC | 13.1 | 0.55 | 100
2464 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No IV under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001142/2022-2023 | 2123/W/MMD | 28/11/2022 | 120 | MANORANJAN DEY | 13.12 | 12.89 | 75
2465 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | VCH/001780/2022-2023 | BP-2022-23-26 | 10/08/2022 | 0 | WBSEDCL | 0.7 | 0 | 0
2466 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation MAHISHADAL CCC at Gopalpur, Manashathan Water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | VCH/002769/2022-2023 | BP-2022-23-61 | 23/11/2022 | 0 | WBSEDCL | 0.5 | 0 | 0
2467 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhanghara Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000167/2021-2022 | 1171/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.76 | 10.07 | 100
2468 | Tamluk Division | Contai Sub-Division | Supply & Delivery 80 mm dia Sluice Valve for Dhanghara W/S Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-I) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000359/2022-2023 | 1298/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.9 | 3.9 | 100
2469 | Tamluk Division | Contai Sub-Division | Augmentation of Dhanghara Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block Of Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000472/2021-2022 | 1947/TD | 03/03/2022 | 150 | M/S S. S. ENTERPRISE | 547.65 | 468.64 | 90
2470 | Tamluk Division | Contai Sub-Division | Rising main 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Dhanghara W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000472/2023-2024 | 1498/TD | 17/07/2023 | 622 | SUDIP MANNA | 5.27 | 2.03 | 100
2471 | Tamluk Division | Contai Sub-Division | Re-laying of Distribution pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Dhanghara PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000615/2024-2025 | 667/TD | 03/03/2025 | 40 | SRIMANTA KUMAR MAITY | 23.42 | 0 | 0
2472 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000772/2022-2023 | 105 / CSD | 19/01/2023 | 15 | BIBEKANANDA DAS | 0.95 | 0 | 0
2473 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000886/2022-2023 | 439 / CSD | 20/03/2023 | 15 | SAURAV HAZRA | 0.95 | 0.95 | 0
2474 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorine Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E .Dte. Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001152/2023-2024 | 560/TD | 15/02/2024 | 240 | GITA ENTERPRISE | 3.72 | 0 | 100
2475 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2021-2022 | 1250/TD | 13/12/2021 | 0 | Resource Division | 10.79 | 0 | 0
2476 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000035/2021-2022 | 1952/TD | 04/03/2022 | 0 | Resource Division | 18.66 | 0 | 0
2477 | Central Drilling | Contai Sub-Division | Construction of TW (300m x 200mm x 250mtr. depth) for Dhanghara WS Scheme (Rep TW-I), Contai-III Block within purba Medinipurr Dist. by utilising skilled Departmental crew and Departmental machineries of CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000300/2022-2023 | 412/CDD | 20/05/2022 | 30 | KARTICK BAL | 14.67 | 5.45 | 100
2478 | Central Drilling | Contai Sub-Division | RESISTIVITY SURVEY AND OTHER WORKS OF Dhanghara W/S SCH (TW-I), PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000326/2022-2023 | 1537/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 12.67 | 9.5 | 100
2479 | Central Drilling | Contai Sub-Division | RESISTIVITY SURVEY AND OTHER WORKS OF DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000398/2022-2023 | 1538/CDD | 08/12/2022 | 30 | MENAKA ENTERPRISE | 12.67 | 9.71 | 0
2480 | Central Drilling | Contai Sub-Division | CONSTRUCTION OF TUBE WELL (300MM X 200MM X DEPTH 250 MTR) FOR DHANGHARA W/S SCHEME (TW-III), CONTAI-III BLOCK WITHIN PURBA MEDINIPUR DISTRICT BY UTILISING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000399/2022-2023 | 413/CDD | 20/05/2022 | 30 | KARTICK BAL | 14.67 | 5.44 | 0
2481 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for DHANGHARA Water Supply Scheme T/W-III, (Ref. ID-204049566) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01685/2023-2024 | BP-2023-24-165 | 04/08/2023 | 0 | WBSEDCL | 1.35 | 0 | 0
2482 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at DHANYAGARAHA Water supply scheme, contai - III block, District -Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000968/2024-2025 | 2338/W/MMD | 16/12/2024 | 180 | P.K.ENGINEERING | 24.97 | 0 | 65
2483 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001466/2022-2023 | 204/W/MMD | 10/02/2023 | 180 | M/S SREEJIT ENTERPRISE | 13.52 | 13.29 | 55
2484 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000141/2022-2023 | 715/TD | 28/06/2022 | 20 | SANTANU PATTANAYAK | 4.27 | 4.21 | 100
2485 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (840 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000152/2022-2023 | 727/TD | 04/07/2022 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 70.64 | 64.02 | 95
2486 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (460 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000153/2022-2023 | 728/TD | 04/07/2022 | 25 | NARAYAN MANDAL | 80.94 | 77.3 | 100
2487 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (500 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000154/2022-2023 | 729/TD | 04/07/2022 | 25 | ZENITH CONSTRUCTION | 80.53 | 78.32 | 100
2488 | Tamluk Division | Haldia Sub-Division | Work: Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part- F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000155/2022-2023 | 730/TD | 04/07/2022 | 1314 | SK. NUR ISLAM | 49.38 | 39.62 | 85
2489 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (370 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000156/2022-2023 | 731/TD | 04/07/2022 | 1101 | MAA KALI CONSTRUCTION | 39.79 | 35.78 | 75
2490 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000157/2022-2023 | 733/TD | 04/07/2022 | 1380 | R CONSTRUCTION | 20.34 | 15.02 | 78
2491 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000158/2022-2023 | 734/TD | 04/07/2022 | 1072 | TAPAN BERA | 20.46 | 18.17 | 100
2492 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (210 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000159/2022-2023 | 735/TD | 04/07/2022 | 887 | SUDIP MANNA | 20.03 | 18.82 | 95
2493 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (96 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000160/2022-2023 | 736/TD | 04/07/2022 | 15 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 10 | 9.57 | 100
2494 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (82 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000161/2022-2023 | 737/TD | 04/07/2022 | 15 | MAHAPRABHU ENTERPRISE | 10.01 | 9.87 | 100
2495 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (104 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000162/2022-2023 | 738/TD | 04/07/2022 | 1432 | MODERN CONSTRUCTION | 10 | 6.81 | 100
2496 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (115 nos) work within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-O) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000163/2022-2023 | 739/TD | 04/07/2022 | 15 | CANVAS | 9.54 | 4.82 | 55
2497 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (110 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-P) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000164/2022-2023 | 740/TD | 04/07/2022 | 15 | TARUN KHATUA | 10.01 | 10 | 100
2498 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (350 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000165/2022-2023 | 732/TD | 04/07/2022 | 20 | SK MAIDUL ISLAM | 40.03 | 32.28 | 85
2499 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (850 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000244/2022-2023 | 1004/TD | 08/08/2022 | 1242 | HARIPADA PATTANAYAK | 212.75 | 87.96 | 80
2500 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2022-2023 | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 20.05 | 100
2501 | Tamluk Division | Haldia Sub-Division | Canal Crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I W/S Scheme under Haldia Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000359/2023-2024 | 927/TD | 01/06/2023 | 30 | NARAYAN MANDAL | 7.82 | 5.07 | 100
2502 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000409/2022-2023 | 1563/TD | 12/10/2022 | 720 | KRISHNENDU SEKHAR DAS | 4.78 | 0 | 100
2503 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chaitanyapur Zone -I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000410/2022-2023 | 1564/TD | 12/10/2022 | 45 | SAYAN MAITY | 3.95 | 3.93 | 0
2504 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase - 2) Name of Work site :- 1) Chaitanyapur Zone-I (Part-A) PWSS, 2) Chaitanyapur Zone-I (Part-B) PWSS, 3) Chaitanyapur Zone-I (Part-C) PWSS, 4) Chaitanyapur Zone-I (Part-D) PWSS, 5) Chaitanyapur Zone-I (Part-E) PWSS, 6) Chaitanyapur Zone-I (Part-F) PWSS, 7) Chaitanyapur Zone-I (Part-G) PWSS & 8) Chaitanyapur Zone-I (Part-H) PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000439/2022-2023 | 724/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
2505 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -3) Name of Work site :- 1) Chaitanyapur Zone-I (Part-I) PWSS, 2) Chaitanyapur Zone-I (Part-J) PWSS, 3) Chaitanyapur Zone-I (Part-K) PWSS, 4) Chaitanyapur Zone-I (Part-L) PWSS, 5) Chaitanyapur Zone-I (Part-M) PWSS, 6) Chaitanyapur Zone-I (Part-N) PWSS, 7) Chaitanyapur Zone-I (Part-O) PWSS & 8) Chaitanyapur Zone-I (Part-P) PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000440/2022-2023 | 725/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
2506 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000458/2021-2022 | 1662/TD | 21/01/2022 | 20 | RADIANT | 4.13 | 4.13 | 100
2507 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 4th tubewell site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-13mtr) & (length of Approach road-20mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000572/2023-2024 | 2163/TD | 31/08/2023 | 30 | TAPAN BERA | 13.62 | 9.27 | 100
2508 | Tamluk Division | Haldia Sub-Division | Laying Rising main work of ground water based Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000580/2023-2024 | 2202/TD | 01/09/2023 | 20 | ELECTIVA ENTERPRISE | 6.04 | 1.1 | 40
2509 | Tamluk Division | Haldia Sub-Division | Earth filling and Making approach road at OHR site at Chaitanyapur (Zone-I) Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -45mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000593/2023-2024 | 2208/TD | 01/09/2023 | 490 | BAGLAMUKHI SECURITY SERVICE | 8.55 | 0 | 0
2510 | Tamluk Division | Haldia Sub-Division | Construction of Damaged bitumen road from PHE office to Rampur more at Chaitanyapur (zone-1) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -330mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000616/2023-2024 | 2281/TD | 07/09/2023 | 20 | RAI CONSTRUCTION | 9.04 | 9.01 | 100
2511 | Tamluk Division | Haldia Sub-Division | Laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000636/2023-2024 | 2448/TD | 20/09/2023 | 854 | S.D. CONSTRUCTION | 69.7 | 31.16 | 40
2512 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000660/2022-2023 | 2345/TD | 10/01/2023 | 40 | TAPAN BERA | 5.08 | 5.06 | 100
2513 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000801/2022-2023 | 909/HSD | 23/02/2023 | 10 | RAI CONSTRUCTION | 0.95 | 0.92 | 0
2514 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000802/2022-2023 | 910/HSD | 23/02/2023 | 10 | MODERN CONSTRUCTION | 0.95 | 0.92 | 100
2515 | Tamluk Division | Haldia Sub-Division | Canal crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte (PART - J). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000856/2022-2023 | 3209/TD | 14/03/2023 | 20 | TAPAN BERA | 8.74 | 8.72 | 100
2516 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000030/2022-2023 | 467/TD | 02/06/2022 | 0 | Resource Division | 10.8 | 0 | 0
2517 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000031/2022-2023 | 466/W | 02/06/2022 | 0 | Resource Division | 40.61 | 0 | 0
2518 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000032/2022-2023 | 468/W | 02/06/2022 | 0 | Resource Division | 30.41 | 0 | 0
2519 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000040/2022-2023 | 829/TD | 15/07/2022 | 0 | Resource Division | 55.98 | 0 | 0
2520 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilizing Departmental Machineries for Chaitanyapur W/S Scheme (Z-I, T/W-IV), SutahataBlock underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000225/2023-2024 | 1390/CDD | 19/09/2023 | 255 | MENAKA ENTERPRISE | 21.16 | 20.24 | 100
2521 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at Z-I of TW-III of Chaitanyapur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695240 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-11900W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00650/2024-2025 | BP-2024-25-114 | 06/05/2024 | 0 | WBSEDCL | 7.14 | 0 | 0
2522 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-IV, zone- I, (Ref. ID-204078116) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02605/2023-2024 | BP-2023-24-249 | 19/09/2023 | 0 | WBSEDCL | 10.52 | 0 | 0
2523 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at CHAITANYAPUR Zone-I Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001174/2023-2024 | 2611/W/MMD | 19/09/2023 | 439 | THE GODFATHER TRADING COMPANY | 14.94 | 10.16 | 40
2524 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001932/2022-2023 | 851/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.46 | 13.19 | 40
2525 | Tamluk Division | Haldia Electrical Sub-Division | Laying Rising main and other allied works Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000199/2023-2024 | 400/TD | 27/04/2023 | 499 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 12.14 | 4.63 | 75
2526 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution system by HDPE pipes with allied works of Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000288/2024-2025 | 3053/TD | 19/09/2024 | 180 | M/S. NEW DINDA ENTERPRISE | 48.21 | 0 | 5
2527 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000289/2023-2024 | 591/TD | 17/05/2023 | 40 | M/S SOURAV MAHAPATRA | 9.2 | 3.76 | 45
2528 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000321/2022-2023 | 591/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.71 | 100
2529 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3rd Pump House & Boundary wall of Amarshi Kasba Zone-I & its adjoining moujas PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000329/2025-2026 | 1716/TD | 30/06/2025 | 40 | GOUTAM DEY | 9.9 | 0 | 0
2530 | Tamluk Division | Haldia Electrical Sub-Division | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site at Amarshi Kasba Zone-I Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000359/2024-2025 | 3322/TD | 22/10/2024 | 30 | M/S. NEW DINDA ENTERPRISE | 2.76 | 0 | 0
2531 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (4400 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-I Water Supply Scheme within Patashpur-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000751/2022-2023 | 2592/TD | 30/01/2023 | 1121 | SANKHA ENTERPRISE | 567.28 | 198.8 | 70
2532 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000068/2023-2024 | 2644/TD | 13/10/2023 | 0 | Resource Division | 27.1 | 0 | 0
2533 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000117/2022-2023 | 1668/TD | 03/11/2022 | 0 | Resource Division | 90.44 | 0 | 0
2534 | Central Drilling | Haldia Electrical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-II,T/W-II) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000514/2022-2023 | 2117/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 15.74 | 14.1 | 100
2535 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE- I Of AMARSHI KASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775131/QUOT/03 DT. 14-06-2024 Application NO- 2004775131 MEMO NO: AMR/PHE/175 DT.14/06/2024 Application type-New connection Consumer Id- 204330575 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01335/2024-2025 | BP-2024-25-361 | 01/07/2024 | 0 | WBSEDCL | 4.79 | 0 | 0
2536 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001904/2022-2023 | 805/W/MMD | 24/03/2023 | 880 | RITESH AGARWALL | 12.63 | 0 | 45
2537 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshinchak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2022-2023 | 51/TD | 05/04/2022 | 20 | HORIZEN | 6.01 | 6 | 0
2538 | Tamluk Division | Haldia Sub-Division | Sinking of Tube well, Reparing & Renovation of 1st & 2nd Pump House, Construction of New 3rd Tube well site Pump House, Construction of 2 nos Pump House, Soil Investigation Test, Construction of Different Capacity OHR, Laying of Rising main, Laying of Distribution pipe line & FHTC(6512 Nos) works for Augmentation of Dakshinchak Zone- I and Dakshinchak Zone-II Water Supply Scheme under Haldia Sub-Division,of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000428/2023-2024 | 1411/TD | 12/07/2023 | 1053 | M/S S. S. ENTERPRISE | 1432.04 | 320.92 | 6
2539 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-I Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000820/2023-2024 | 3288/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.38 | 2.76 | 30
2540 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-II Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000821/2023-2024 | 3287/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 10.9 | 2.76 | 30
2541 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000062/2023-2024 | 2638/TD | 13/10/2023 | 0 | Resource Division | 43.18 | 0 | 0
2542 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000233/2022-2023 | 2616/TD | 02/02/2023 | 0 | Resource Division | 349.36 | 0 | 0
2543 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000288/2022-2023 | 2641/TD | 02/02/2023 | 0 | Resource Division | 204.6 | 0 | 0
2544 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I,Z-II of Dakshinchak w/s scheme, Block-Haldia under MMD,PHE Dte. Name of CCC-Brajalalchak Application no.-2005036411 Application Type-New Connection Reference ID-204491647 Quotation Date-07/01/2025 Quotation Due Date-07/01/2026 Contract Demand-12074 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04000/2024-2025 | C022508972809 | 04/02/2025 | 0 | WBSEDCL | 6.43 | 0 | 0
2545 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-III,Z-I of Dakshinchak w/s scheme, Block-Haldia under MMD,PHE Dte. Name of CCC-Brajalalchak Application no.-2005036298 Application Type-New Connection Reference ID-204490776 Quotation Date-07/01/2025 Quotation Due Date-07/01/2026 Contract Demand-10209 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04009/2024-2025 | C022508807571 | 04/02/2025 | 0 | WBSEDCL | 15 | 0 | 0
2546 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Zone- II of Tube well-I and II at Dakshin Chak Water supply scheme, Haldia block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001684/2023-2024 | 63/W/MMD | 15/01/2024 | 180 | SUJOY RANJAN BHOWMICK | 28.21 | 16.58 | 30
2547 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001723/2022-2023 | 635/W/MMD | 20/03/2023 | 799 | P.K.ENGINEERING | 27.18 | 19.11 | 30
2548 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of T/W- III, Zone-I for Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002726/2023-2024 | 1071/W/MMD | 14/03/2024 | 180 | DEBSANKER BHATTACHARYA | 13.59 | 0 | 0
2549 | Tamluk Division | Contai Sub-Division | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division P.H.E. DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000112/2024-2025 | 1906/TD | 07/06/2024 | 361 | SK. NUR ISLAM | 45.39 | 0 | 35
2550 | Tamluk Division | Contai Sub-Division | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai Saline Area Zone-II PWSS under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000232/2024-2025 | 2487/TD | 02/08/2024 | 105 | S R TRADING CORPORATION | 3.45 | 0 | 100
2551 | Tamluk Division | Contai Sub-Division | Renovation work of Spiral stair and related works for R.C.C. Over Head Reservoir of capacity 60000 Gallons at Keshurkunda mouza within Contai S.A. Zone-II W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur.( 2nd Part) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2021-2022 | 497 / CSD | 18/11/2021 | 21 | SRIMANTA KUMAR MAITY | 2.06 | 0 | 0
2552 | Tamluk Division | Contai Sub-Division | Installation of display Board of Contai Saline Area Zone III (Zone-B) Augmentation PWSS at 2 nos. TW Site, Contai Saline Area Zone II Augmentation PWSS at 3 no TW site in Contai-I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000267/2025-2026 | 1568/CSD | 19/06/2025 | 7 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0 | 0
2553 | Tamluk Division | Contai Sub-Division | Installation of display Board of Contai Saline Area Zone II Augmentation PWSS at 2 no TW site , Sapai Augmentation PWSS at 1 no TW site in Contai-I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000268/2025-2026 | 1569/CSD | 19/06/2025 | 7 | BISWA NIRMAN ENTERPRISE. | 0.5 | 0 | 0
2554 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
2555 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000449/2021-2022 | 1684/TD | 28/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.86 | 4.85 | 100
2556 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000027/2023-2024 | 612/TD | 17/05/2023 | 0 | Resource Division | 37.05 | 0 | 0
2557 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000106/2022-2023 | 1663/TD | 03/11/2022 | 0 | Resource Division | 315.36 | 0 | 0
2558 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai-I & III Dev. Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000500/2022-2023 | 1972/TD | 01/12/2022 | 1244 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 938.66 | 272.74 | 45
2559 | Tamluk Division |  | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. |  |  | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 98
2560 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000278/2020-2021 | 2994/TD | 25/02/2021 | 60 | BASANTA KUMAR MAITY | 210.56 | 172.89 | 100
2561 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000196/2023-2024 | 306/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 11.41 | 11.41 | 100
2562 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 307/TD | 24/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.3 | 0.3 | 100
2563 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works of Shillaberia Jhanka Zone-II & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000238/2024-2025 | 2677/TD | 22/08/2024 | 156 | TARUN KOLEY | 79.64 | 20.21 | 95
2564 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 612.99 | 85
2565 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) with Approach road at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000594/2024-2025 | 566/TD | 17/02/2025 | 40 | DAS ENTERPRISE | 9.15 | 0 | 0
2566 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i)300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at Head Works Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 2nd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2022-2023 | 3145/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 70.37 | 53.19 | 75
2567 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) ii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Laying Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000864/2022-2023 | 3219/TD | 14/03/2023 | 962 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.37 | 13.14 | 90
2568 | Tamluk Division | Contai Sub-Division | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1023 nos) under JJM with allied work of BRINDABANPUR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000381/2023-2024 | 1017/TD | 06/06/2023 | 901 | DAS ENTERPRISE | 305.41 | 201.72 | 60
2569 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000181/2023-2024 | 630/W | 20/02/2024 | 0 | Resource Division | 6.3 | 0 | 0
2570 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000308/2022-2023 | 2965/TD | 27/02/2023 | 0 | Resource Division | 23.38 | 0 | 0
2571 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Brindabanpur W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000110/2023-2024 | 1395/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 28.62 | 0 | 0
2572 | Midnapore Mechanical | Contai Sub-Division | BRINDABANPUR w/s SCHEME PH.-I APPLICATION NO.-2004567517 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03536/2023-2024 | BP-2023-24-610 | 07/02/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
2573 | Midnapore Mechanical | Contai Sub-Division | BRINDABANPUR w/s SCHEME PH.-II APPLICATION NO.-2004570658 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03537/2023-2024 | BP-2023-24-609 | 07/02/2024 | 0 | WBSEDCL | 4.06 | 0 | 0
2574 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BRINDABANPUR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001316/2022-2023 | 2318/W/MMD | 29/12/2022 | 180 | AHALYA ENGINEERING WORKS | 21.61 | 19.67 | 75
2575 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000167/2023-2024 | 114/TD | 05/01/2024 | 0 | Resource Division | 11.32 | 0 | 0
2576 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000212/2022-2023 | 2467/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0
2577 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for RAMCHANDRAPUR Water Supply Scheme , (Ref. ID-204075844) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02185/2023-2024 | BP-2023-24-239 | 12/09/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
2578 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For Ramchandrapur W/S Scheme T/W-II Kolaghat CCC Application No=2005024015 Reference ID=204482671 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03943/2024-2025 | C012539022843 | 21/01/2025 | 0 | WBSEDCL | 3.36 | 0 | 0
2579 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001332/2022-2023 | 2337/W/MMD | 29/12/2022 | 1068 | DEY ENTERPRISE | 23.7 | 11.09 | 65
2580 | Tamluk Division | Haldia Sub-Division | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000129/2023-2024 | 260/TD | 19/04/2023 | 617 | MADAN MOHAN MAITY | 24.93 | 17.53 | 75
2581 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Mayachar PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000151/2024-2025 | 2062/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2582 | Tamluk Division | Haldia Sub-Division | Ground water based Mayachar Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000286/2023-2024 | 576/TD | 16/05/2023 | 596 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 139.9 | 104.51 | 90
2583 | Tamluk Division | Haldia Sub-Division | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000630/2023-2024 | 2438/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 165.66 | 28.45 | 30
2584 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) [Chaitanyapur Zone-I PWSS, Dwariberia PWSS, Natshal Lakshya Zone-I PWSS & Mayachar PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000831/2023-2024 | 619/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.83 | 0.83 | 100
2585 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000897/2022-2023 | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 28.82 | 50
2586 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000156/2023-2024 | 135/TD | 05/01/2024 | 0 | Resource Division | 8.04 | 0 | 0
2587 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000332/2022-2023 | 2983/TD | 27/02/2023 | 0 | Resource Division | 12.88 | 0 | 0
2588 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Mayachar w/s scheme PH II in the district of Purba Medinipur (Application no 1007525986, Ref ID 106467535) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03780/2023-2024 | BP-2023-24-712 | 20/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
2589 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Mayachar w/s scheme PH I in the district of Purba Medinipur (Application no 1007526112, Ref ID 106467554) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03781/2023-2024 | BP-2023-24-711 | 20/02/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
2590 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAYACHAR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001397/2022-2023 | 2408/W/MMD | 31/12/2022 | 721 | S.G.ENTERPRISE | 21.6 | 21.27 | 100
2591 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 211.9 | 51
2592 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000026/2024-2025 | 1637/TD | 18/06/2025 | 0 | Resource Division | 8.3 | 0 | 0
2593 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000190/2022-2023 | 2441/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0
2594 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DANGARTULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004706844/QUOT/03 DT. 29-04-2024 Application NO- 2004706844 MEMO NO: AMR/PHE/91 DT.29/04/2024 Application type-New connection Consumer Id- 204291543 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00854/2024-2025 | BP-2024-25-164 | 15/05/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
2595 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DANGAR TULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004862083/QUOT/03 DT. 16-08-2024 MEMO NO: AMR/PHE/330 DT. 16-08-2024 Application NO- 2004862083 Application type-New connection Consumer Id- 204378443 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02119/2024-2025 | C082448267203 | 02/09/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
2596 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DANGAR TULSI and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001401/2022-2023 | 2412/W/MMD | 31/12/2022 | 882 | SUJOY RANJAN BHOWMICK | 22.8 | 9.04 | 35
2597 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Sofiabad W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000235/2023-2024 | 483/TD | 10/05/2023 | 60 | BABA LOKNATH CONSTRUCTION | 4.03 | 0 | 0
2598 | Tamluk Division | Contai Sub-Division | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 2nd Tube Well & 1(One) no. Boosting Tube Well of Sofiabad & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000236/2023-2024 | 482/TD | 10/05/2023 | 600 | KAMAL KUMAR BERA | 3.92 | 0 | 0
2599 | Tamluk Division | Contai Sub-Division | Retrofitting to Accommodate 30 nos FHTC under JJM in Sofiabad PWSS Block- Contai-II ( Deshpran) of Tamluk Division, PHE Dte,in the districtof Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000394/2022-2023 | 1427/TD | 26/09/2022 | 15 | RELIABLE CONSTRUCTIONS | 1.28 | 1.28 | 100
2600 | Tamluk Division | Contai Sub-Division | Replacement of Damaged UPVC Pipe Line , FHTC with allied works of Sofiabad PWSS within Contai-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000797/2025-2026 | 3071/TD | 19/12/2025 | 120 | BISWA NIRMAN ENTERPRISE. | 3.89 | 0 | 0
2601 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Bamunia, Barasubarnagar, Sofiabad, Aladarput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001185/2023-2024 | 2333/CSD | 29/12/2023 | 15 | ABHIJIT BERA | 0.83 | 0.83 | 100
2602 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Sofiabad W/S Scheme (T/W-I & II) , Deshpran Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000114/2023-2024 | 856/CDD | 10/07/2023 | 398 | MENAKA ENTERPRISE | 29.23 | 0 | 50
2603 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001731/2022-2023 | 637/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 60
2604 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-49) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00137/2024-2025 | BP-2024-25-80 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.59 | 0 | 0
2605 | Tamluk Division | Contai Sub-Division | Payment of wayleave charges(SER-KGP-2024-WL-50) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00138/2024-2025 | BP-2024-25-81 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 9.38 | 0 | 0
2606 | Tamluk Division | Contai Sub-Division | payment of way leave facility cahrges(SER-KGP-2024-WL-51) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00139/2024-2025 | BP-2024-25-82 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.3 | 0 | 0
2607 | Tamluk Division | Contai Sub-Division | Payment of Wayleave facility charges (SER-KGP-2024-WL-52) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00140/2024-2025 | BP-2024-25-83 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.28 | 0 | 0
2608 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-53) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00141/2024-2025 | BP-2024-25-84 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0
2609 | Tamluk Division | Contai Sub-Division | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00570/2024-2025 | BP-2024-25-236 | 12/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.25 | 0 | 0
2610 | Tamluk Division | Contai Sub-Division | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01940/2023-2024 | BP-2023-24-894 | 22/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.65 | 0 | 0
2611 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-B) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (2nd Call) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000147/2024-2025 | 1735/CSD | 20/06/2024 | 20 | ABHIJIT BERA | 2.31 | 2.31 | 100
2612 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000149/2024-2025 | 1732/CSD | 20/06/2024 | 20 | GIRI CONSTRUCTION | 1.16 | 1.16 | 100
2613 | Tamluk Division | Contai Sub-Division | Construction Boundary Wall & Repairing and renovation of Pump House and others allied works for 2nd Tube well site under Contai Saline Area Zone-I (Phase-B) Water Supply scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000241/2024-2025 | 2680/TD | 22/08/2024 | 280 | BISWA NIRMAN ENTERPRISE. | 10.08 | 0 | 0
2614 | Tamluk Division | Contai Sub-Division | Construction of Pump House & Boundary Wall and others allied works for 1st Tube well site under Contai Saline Area Zone-I (Phase-A) Water Supply Scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 3063/TD | 19/09/2024 | 40 | GUCHHAIT ENTERPRISE | 14.07 | 0 | 0
2615 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000697/2022-2023 | 2312/TD | 05/01/2023 | 739 | DAS CONSTRUCTION | 180.42 | 14.77 | 45
2616 | Tamluk Division | Contai Sub-Division | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai S.A. Zone I (Phase B) PWSS under Contai Sub Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000282/2024-2025 | 3035/TD | 18/09/2024 | 21 | SUBHENDU HAZRA | 3.53 | 0 | 0
2617 | Tamluk Division | Contai Sub-Division | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Reservoir (OHR) Site under Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000334/2024-2025 | 3292/TD | 05/10/2024 | 280 | DEBANANDA CONSTRUCTION | 21.34 | 0 | 35
2618 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
2619 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000634/2022-2023 | 2313/TD | 05/01/2023 | 966 | DAS CONSTRUCTION | 439.86 | 171.68 | 42
2620 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- I within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001238/2023-2024 | 1086/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.4 | 0 | 0
2621 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000026/2023-2024 | 611/TD | 17/05/2023 | 0 | Resource Division | 31.42 | 0 | 0
2622 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000105/2022-2023 | 1661/TD | 03/11/2022 | 0 | Resource Division | 239.21 | 0 | 0
2623 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A. RAJ (PHASE-B) Water Supply Scheme T/W-II,Zone-III, (Ref. ID-204114270) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02907/2023-2024 | BP-2023-24-321 | 01/11/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
2624 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- II within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001239/2023-2024 | 1085/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.24 | 0 | 0
2625 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II), under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001513/2022-2023 | 357/W/MMD | 09/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 0 | 60
2626 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B), under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001744/2022-2023 | 642/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.58 | 0 | 0
2627 | Tamluk Division | Contai Sub-Division | Drum Sheet Walling & allied works of Pachhari PWSS (PART-A) in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2024-2025 | 3222/TD | 01/10/2024 | 25 | THREE MAA ENTERPRISE | 9.45 | 0 | 0
2628 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for PACHHARI PWSS (PART-B) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000533/2024-2025 | 211/TD | 15/01/2025 | 501 | SAURAV HAZRA | 12.27 | 0 | 0
2629 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (357 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000634/2023-2024 | 2443/TD | 19/09/2023 | 682 | THREE MAA ENTERPRISE | 226.83 | 107.43 | 32
2630 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line & Accommodate FHTC (420 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000873/2022-2023 | 3210/TD | 14/03/2023 | 1226 | ABHIJIT BERA | 82.33 | 57.41 | 50
2631 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (170 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000875/2022-2023 | 3211/TD | 14/03/2023 | 1179 | KAMAL KUMAR BERA | 19.49 | 5.93 | 45
2632 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (75nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000876/2022-2023 | 3212/TD | 14/03/2023 | 20 | PARTHA CONSTRUCTION | 9.77 | 4.15 | 45
2633 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 430 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000912/2022-2023 | 3561/TD | 29/03/2023 | 785 | OM ENTERPRISE | 80.86 | 42.25 | 55
2634 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000183/2023-2024 | 632/W | 20/02/2024 | 0 | Resource Division | 8.94 | 0 | 0
2635 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000189/2022-2023 | 2388/TD | 16/01/2023 | 0 | Resource Division | 34.82 | 0 | 0
2636 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.54 | 11
2637 | Midnapore Mechanical | Contai Sub-Division | Pachahari W/S scheme PH-I Application.-2004537390 Ref.-204168886 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03297/2023-2024 | BP-2023-24-531 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
2638 | Midnapore Mechanical | Contai Sub-Division | Pachahari W/S scheme PH-II Application.-2004537398 Ref.-204168891 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03298/2023-2024 | BP-2023-24-532 | 11/01/2024 | 0 | WBSEDCL | 3.16 | 0 | 0
2639 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
2640 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2023-2024 | 417/TD | 02/05/2023 | 719 | ARABINDA GHOSH | 113.16 | 90.05 | 46
2641 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary wall at 1st. & 2nd. Tube well site, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room, interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main and Accommodate FHTC (638 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000212/2023-2024 | 416/TD | 02/05/2023 | 660 | KRISHNENDU SEKHAR DAS | 140.04 | 117.64 | 74
2642 | Tamluk Division | Tamluk Sadar Sub-Division | Earth work in filling by carried earth and Construction of link Road for Naichanpur and its adjoining mouzas new Piped Water Supply Scheme within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000654/2023-2024 | 2619/TD | 11/10/2023 | 25 | KRISHNENDU SEKHAR DAS | 9.57 | 6.35 | 69
2643 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Pump House & Accommodate FHTC (375 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000890/2022-2023 | 3244/TD | 15/03/2023 | 660 | GHOSH ENTERPRISE | 90.18 | 84.46 | 65
2644 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System & Accommodate FHTC (500 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000891/2022-2023 | 3245/TD | 15/03/2023 | 854 | ADHIKARY CONSTRUCTION | 64.64 | 32.51 | 60
2645 | Tamluk Division | Tamluk Sadar Sub-Division | Surging of existing 2nd Tube well with using air compressor of Naichhanpur water supply scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000946/2025-2026 | 70/TSD | 15/01/2026 | 15 | KRISHNENDU SEKHAR DAS | 0.61 | 0 | 0
2646 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000010/2024-2025 | 1568/TD | 23/04/2024 | 0 | Resource Division | 9.32 | 0 | 0
2647 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000327/2022-2023 | 2989/TD | 27/02/2023 | 0 | Resource Division | 16.3 | 0 | 0
2648 | Central Drilling | Tamluk Sadar Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 47.62 | 11
2649 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Naichanpur W/S scheme Ph-I Application No.-204543058 Ref.-204175259 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03267/2023-2024 | BP-2023-24-514 | 09/01/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
2650 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Naichanpur W/S scheme PH-II Application No.-2004543088 Ref.-204175260 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03268/2023-2024 | BP-2023-24-513 | 09/01/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
2651 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NAICHHANPUR AND ADJOINING MOUJAS PWSS, Block Moyna, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000168/2023-2024 | 1411/W/MMD | 02/06/2023 | 180 | P.K.ENGINEERING | 27.53 | 0 | 0
2652 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SAHAJADAPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004772844/QUOT/03 DT. 14-06-2024 Application NO- 2004772844 Application type-New connection Consumer Id- 204329286 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00591/2024-2025 | BP-2024-25-289 | 29/07/2024 | 0 | WBSEDCL | 14.1 | 0 | 0
2653 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 97.06 | 75
2654 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Sahajadapur PWSS at Contai-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000881/2023-2024 | 203/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 0
2655 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000068/2024-2025 | 2977/TD | 12/09/2024 | 0 | Resource Division | 3.28 | 0 | 0
2656 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000166/2022-2023 | 2392/TD | 16/01/2023 | 0 | Resource Division | 34.34 | 0 | 0
2657 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-I of Sahajadapur ws scheme under MMD,PHE Dte. Ref. Application no-2004579826, CON ID-204204429, under PICHABONI CCC, Block-CONTAI-I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03655/2023-2024 | BP-2023-24-679 | 15/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
2658 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHAJADAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001657/2022-2023 | 543/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 21.56 | 16.07 | 100
2659 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Amtalia W/S Scheme within Contai- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000437/2023-2024 | 1420/TD | 12/07/2023 | 30 | PARIA ENTERPRISE | 9.47 | 0 | 0
2660 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Amtalia W/S Scheme (TW-III) , Deshpran Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000516/2022-2023 | 1230/CDD | 16/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.11 | 0 | 0
2661 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001729/2022-2023 | 636/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 60
2662 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Dakshin Utaspur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000166/2024-2025 | 2078/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
2663 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of M.S. Structure over irrigation canal to support 200 mm dia. DI(K-7) distribution pipe under Dakshin Utaspur Water Supply Scheme at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=30.00 Mtr ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000311/2024-2025 | 3139/TD | 26/09/2024 | 40 | TARUN KHATUA | 5.19 | 5.18 | 100
2664 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000128/2023-2024 | 91/TD | 05/01/2024 | 0 | Resource Division | 8.11 | 0 | 0
2665 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000276/2022-2023 | 2681/TD | 06/02/2023 | 0 | Resource Division | 15.32 | 0 | 0
2666 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Dakshin Usutpur Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004690463 Reference ID=204279652 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00665/2024-2025 | BP-2024-25-166 | 15/05/2024 | 0 | WBSEDCL | 4.65 | 0 | 0
2667 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Dakshin Usutpur Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004690460 Reference ID=204279646 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00667/2024-2025 | BP-2024-25-167 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
2668 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000084/2023-2024 | 1272/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 25
2669 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
2670 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 15 | S.S.GHORAI | 2.13 | 0 | 70
2671 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
2672 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1959 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KALABERIA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000850/2023-2024 | 73/TD | 05/01/2024 | 696 | SRIMANTA KUMAR MAITY | 584.3 | 43.7 | 15
2673 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000191/2022-2023 | 2384/TD | 16/01/2023 | 0 | Resource Division | 19.89 | 0 | 0
2674 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KALABERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL C.C.C. : BHAGWANPUR C.C.C. Ref. Memo No- 2005232856/QUOT/03 DT. 21-05-2025 Application NO- 2005232856 Application type-New connection CONSUMER ID: 204628888 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/01391/2025-2026 |  | 12/06/2025 | 0 | WBSEDCL | 6.87 | 0 | 0
2675 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALABERIA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001338/2022-2023 | 2343/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 25.24 | 0 | 0
2676 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 155.3 | 30
2677 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Purba Mahammadpur PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001275/2023-2024 | 1049/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
2678 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000075/2024-2025 | 2973/TD | 12/09/2024 | 0 | Resource Division | 6.99 | 0 | 0
2679 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000205/2022-2023 | 2407/TD | 16/01/2023 | 0 | Resource Division | 18.82 | 0 | 0
2680 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURBA MAHAMMADPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2005246718/QUOT/03 DT. 02-06-2024 Application NO- 2005246718 Application type-New connection Consumer Id- 204639831 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01390/2025-2026 |  | 12/06/2025 | 0 | WBSEDCL | 5.95 | 0 | 0
2681 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA MAHAMMADPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877670/QUOT/03 DT. 12-09-2024 Application NO- 2004877670 Application type-New connection Consumer Id- 204397980 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02497/2024-2025 | C092445105167 | 30/09/2024 | 0 | WBSEDCL | 12.11 | 0 | 0
2682 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MAHAMMADPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001667/2022-2023 | 550/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 11.03 | 55
2683 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
2684 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 193.47 | 51
2685 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000022/2024-2025 | 1640/TD | 18/06/2025 | 0 | Resource Division | 14.69 | 0 | 0
2686 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000144/2022-2023 | 2447/TD | 16/01/2023 | 0 | Resource Division | 22.75 | 0 | 0
2687 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BELDA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005009762/QUOT/03 DT. 16-12-2024 MEMO NO: AMR/PHE/562 DT. 16-12-2024 Application NO- 2005009762 Application type-New connection Consumer Id- 204474220 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03681/2024-2025 | C012524057410 | 09/01/2025 | 0 | WBSEDCL | 4.37 | 0 | 0
2688 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BELDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607449/QUOT/03 DT. 21-02-2024 Application NO- 2004607449 Application type-New connection Consumer Id- 204223207 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04386/2023-2024 | BP-2023-24-824 | 13/03/2024 | 0 | WBSEDCL | 3.03 | 0 | 0
2689 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BELDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001349/2022-2023 | 2360/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 23.67 | 0 | 50
2690 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 1080 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
2691 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000098/2024-2025 | 2960/TD | 12/09/2024 | 0 | Resource Division | 1.92 | 0 | 0
2692 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000214/2022-2023 | 2400/TD | 16/01/2023 | 0 | Resource Division | 30.7 | 0 | 0
2693 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAMUASHANKARPUR PWSS, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001743/2022-2023 | 603/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.94 | 0 | 0
2694 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 113.39 | 75
2695 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000218/2022-2023 | 2673/TD | 06/02/2023 | 0 | Resource Division | 19.08 | 0 | 0
2696 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Satkalua W/S scheme H/W site. Application No.-2004547137 Ref.-204177910 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03302/2023-2024 | BP-2023-24-548 | 15/01/2024 | 0 | WBSEDCL | 4.11 | 0 | 0
2697 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATKALUA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001716/2022-2023 | 595/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 10.61 | 35
2698 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Barchunfali PWSS Block Contai-I in the District of Purba Medinipur. |  |  | ORD/000026/2020-2021 | 2102/TD | 05/11/2020 | 180 | DAS CONSTRUCTION | 96.5 | 1.82 | 100
2699 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000466/2021-2022 | 311/W | 08/10/2021 | 0 | DAS CONSTRUCTION | 16.22 | 0 | 0
2700 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000612/2020-2021 | 686/W | 27/01/2021 | 0 | DAS CONSTRUCTION | 59.4 | 0 | 0
2701 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001266/2020-2021 | 1040/W | 30/03/2021 | 0 | DAS CONSTRUCTION | 18.19 | 0 | 0
2702 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2843 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chakbhabani PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000489/2023-2024 | 1564/TD | 19/07/2023 | 180 | TARUN KOLEY | 947.78 | 606.52 | 35
2703 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2024-2025 | 1649/TD | 29/04/2024 | 0 | Resource Division | 17.51 | 0 | 0
2704 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000343/2022-2023 | 2996/TD | 27/02/2023 | 0 | Resource Division | 22.46 | 0 | 0
2705 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill of Erection for the Service connection at T/W NO-II Of CHAKBHABANI W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-PTP/QOT/HT/151 DT. 14-05-2024 Application NO- 100000107893 DT. 14-05-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860299943 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01129/2024-2025 | BP-2024-25-245 | 06/06/2024 | 0 | WBSEDCL | 0.37 | 0 | 0
2706 | Midnapore Mechanical | Contai Sub-Division | Chakbhabani W/S scheme PH-I Application no.-2004520839 ref.-204155241 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03190/2023-2024 | BP-2023-24-484 | 27/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
2707 | Midnapore Mechanical | Contai Sub-Division | Chakbhabani W/S scheme PH-II Application no.-2004520828 ref.-204155254 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03191/2023-2024 | BP-2023-24-483 | 27/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
2708 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAK BHABANI & ADJOINING MOUJAS PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001712/2022-2023 | 629/W/MMD | 20/03/2023 | 718 | ALPHA ENTERPRISE | 25.24 | 23.52 | 100
2709 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at t/w no.-II of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753851 Con ID-204322327 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00593/2024-2025 | BP-2024-25-293 | 29/07/2024 | 0 | WBSEDCL | 4.56 | 0 | 0
2710 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at TW-1 of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753843 CON ID-204318364 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00595/2024-2025 | BP-2024-25-292 | 29/07/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
2711 | Tamluk Division | Digha Sub-Division | Soil investigation, Construction of 50 cum OHR (tourch type with pile foundation) under JJM with allied work for Bhatsalia PWSS within Egra-I Block including Supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000417/2023-2024 | 1086/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.57 | 0 | 30
2712 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (337 nos) under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000445/2023-2024 | 1453/TD | 13/07/2023 | 643 | R CONSTRUCTION | 78.02 | 38.07 | 85
2713 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Boundary Wall under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000446/2023-2024 | 1454/TD | 13/07/2023 | 45 | MAHAPRABHU ENTERPRISE | 14.4 | 0 | 0
2714 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000012/2025-2026 | 2070/TD | 12/08/2025 | 0 | Resource Division | 2.08 | 0 | 0
2715 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000351/2022-2023 | 3014/TD | 27/02/2023 | 0 | Resource Division | 9.41 | 0 | 0
2716 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.63 | 11
2717 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (105 nos) under JJM with allied work for CHIRULIA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000299/2023-2024 | 589/TD | 17/05/2023 | 743 | SK MAIDUL ISLAM | 53.24 | 13.24 | 30
2718 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of CHIRULIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004692025/QUOT/03/97 DT. 25-04-2024 Application NO- 2004692025 Application type-New connection Consumer Id- 204287568 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00853/2024-2025 | BP-2024-25-165 | 15/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
2719 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF OCTOBER'2023 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04350/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.17 | 0 | 0
2720 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF AUGUST'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04360/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
2721 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF SEPT'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04361/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.24 | 0 | 0
2722 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
2723 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001989/2022-2023 | 896/W/MMD | 27/03/2023 | 1667 | ECO ENTERPRISE | 12.63 | 8.53 | 85
2724 | Tamluk Division | Contai Sub-Division | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (250 nos) under JJM with allied work of DESHHDUTTABARH PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000440/2023-2024 | 1424/TD | 12/07/2023 | 570 | JASODA ENTERPRISE | 64.31 | 41.51 | 70
2725 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000090/2024-2025 | 2956/TD | 12/09/2024 | 0 | Resource Division | 1.54 | 0 | 0
2726 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000348/2022-2023 | 3012/TD | 27/02/2023 | 0 | Resource Division | 19.16 | 0 | 0
2727 | Midnapore Mechanical | Contai Sub-Division | Deshduttabar W/S scheme T/W-I Application-no.-2004523550 Ref.-204157344 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03167/2023-2024 | BP-2023-24-446 | 19/12/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
2728 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
2729 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block- Egra-II in the District of Purba Medinipur.(Phase-II) |  | Junior Engineer | ORD/000066/2021-2022 | 693/TD | 10/09/2021 | 60 | SATYABRATA BHAUMIK | 137.67 | 137.67 | 100
2730 | Tamluk Division | Digha Sub-Division | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 1.79 | 100
2731 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000006/2021-2022 | 1235/TD | 09/12/2021 | 0 | Resource Division | 6.01 | 0 | 0
2732 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
2733 | Tamluk Division | Haldia Sub-Division | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Manikpur W/S Scheme within Nandigram-I Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000306/2023-2024 | 624/TD | 17/05/2023 | 499 | DEEP ENTERPRISE | 12.11 | 10.51 | 100
2734 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000001/2023-2024 | 353/TD | 26/04/2023 | 0 | Resource Division | 0.63 | 0 | 0
2735 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for MANIKPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063673) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01822/2023-2024 | BP-2023-24-203 | 24/08/2023 | 0 | WBSEDCL | 4.87 | 0 | 0
2736 | Midnapore Mechanical | Haldia Sub-Division | Additional Quotation of Manikpur Boosting Tube Well Application ID-100000095367 Referance ID- 860287817 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03181/2023-2024 | BP-2023-24-467 | 27/12/2023 | 0 | WBSEDCL | 0.29 | 0 | 0
2737 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 35
2738 | Midnapore Mechanical | Haldia Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
2739 | Midnapore Mechanical | Haldia Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 15 | S.S.GHORAI | 2.13 | 0 | 70
2740 | Midnapore Mechanical | Haldia Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
2741 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 17.82 | 100
2742 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2023-2024 | 355/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
2743 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for new service connection at Kotbar w/s scheme Boosting T/W I in the district of Purba Medinipur under MMD PHE Dte. (App No 2004689061, Ref ID 204279764) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01165/2024-2025 | BP-2024-25-275 | 12/06/2024 | 0 | WBSEDCL | 6.09 | 0 | 0
2744 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 5.95 | 55
2745 | Tamluk Division | Haldia Electrical Sub-Division | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 0 | 94
2746 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at 55 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000330/2024-2025 | 3289/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9.16 | 9.16 | 100
2747 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Hajipur, 2.Tangabani, under Haldia-i Panchyat 3. Saripur, 4. Mirjapur, 5. Somaibasan, Panchayat :Padima-ii- all are under Ramnagar-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000338/2025-2026 | 114/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2748 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Nata Gechhia, 2 .Uttar Khas Mulda, under Boroj Panchyat, 3. Jagamohanpur, 4. Uttar Nara Basan, under Mugberia Panchyat 5. vill- Hinari, Panchayat :- Basantapur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000339/2025-2026 | 115/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2749 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Bisha Dangar, 2. Dhangharibar, 3. Kunja Para, 4. Uttar Sukhmajhi, under Itaberia Panchyat 5. vill- Binanda Chak, Panchayat :- Basudevberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000340/2025-2026 | 116/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2750 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Mirchak , Panchayat : -Basudevberia 2. Dakshin Baroj-part-i,Panchayat :- Boroj, 3. Lochananda Chak, 4. Uttar Gobinda Chak, under Garbari-ii Panchyat 5. vill- Bargopal, Panchayat :- Itaberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000341/2025-2026 | 117/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2751 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1.Tikar Maisali, 2.Agar Mulda, 3. Gora Mulda, 4. Kalikapur, 5. Kalu Rautbar all are under Bhagwanpur-II Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000355/2025-2026 | 132/RWS/TSD | 04/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2752 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000292/2022-2023 | 2910/TD | 21/11/2023 | 0 | Resource Division | 10.62 | 0 | 0
2753 | Midnapore Mechanical | Haldia Electrical Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
2754 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Haturia, 2. Haturia Dalbari, 3. Kalika Danri, under Arjunnagar Panchyat 4.. vill- Jagamohan Chak, 5.Kuchai Dighi Panchayat :- Basudevberia all are under Bhagawanpur-ii Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000346/2025-2026 | 121RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2755 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Haripur , 2. Chak Sibrampur, 3. Danaipur , 4. Tiraipur Jalpal, under Mahammadpur-i Panchyat 5. vill- Gopal Chak, Panchayat :- Simulia all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000347/2025-2026 | 122/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2756 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Bar Kasimpur, 2. Dhaka Chora, under Kakra Panchayat 3. Bhairabi Chak, 4. Nishkini, 5. Ramchak, Panchayat :- Kotebash all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000349/2025-2026 | 123/RWS/TSD | 02/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2757 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Ghoshpur, 2.Raygange,under Gurgram Panchyat 3. Kotbar, Panchayat :- Simulia, 4. Baman Chak, 5. Bhabani Chak Panchayat :- Kajlagarh, all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000351/2025-2026 | 126/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2758 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Nata Talya, 2. Nona Birampur, 3. Nunbar, 4. Dihi Jhanjrar, under Bhagabanpur Panchyat 5. vill- Brahmattar Bar, Panchayat :- Bibhisanpur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000352/2025-2026 | 127/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2759 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1. Bhabanipur, 2.Digha Nagar, 3.Jamalpur , 4. Kalupur, 5, Kismat Arajibar under Gurgram Panchyat & all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000353/2025-2026 | 128/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2760 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos ( Vill:- 1.Gopal Dasbar, 2.Shyampur, 3. Subodhpur, 4. Uttar Shibarampur, under Bhagabanpur Panchyat 5. vill- Harma Shani, Panchayat :- Bibhisanpur all are under Bhagawanpur-i Development Block) work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000354/2025-2026 | 129/RWS/TSD | 03/06/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2761 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different on going Solarization works for the purpose of Geotagging at different PWSS under Khejuri block under Midnapore Mechanical Division, P.H.E. Dte. in the Dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2024-2025 | 648/HESD | 08/07/2024 | 7 | THE GODFATHER TRADING COMPANY | 0.35 | 0.3 | 100
2762 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001848/2022-2023 | 765/W/MMD | 23/03/2023 | 720 | M/S EMMESS | 12.24 | 9.08 | 70
2763 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100
2764 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001845/2022-2023 | 762/W/MMD | 23/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 90
2765 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100
2766 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001846/2022-2023 | 763/W/MMD | 23/03/2023 | 718 | UNITED TRADERS | 12.24 | 7.15 | 45
2767 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different on going Solarization works for the purpose of Geotagging at different PWSS under Khejuri block under Midnapore Mechanical Division, P.H.E. Dte. in the Dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000135/2024-2025 | 648/HESD | 08/07/2024 | 7 | THE GODFATHER TRADING COMPANY | 0.35 | 0.3 | 100
2768 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001847/2022-2023 | 764/W/MMD | 23/03/2023 | 1678 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 60
2769 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 368.95 | 85
2770 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000147/2023-2024 | 102/TD | 05/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
2771 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000270/2022-2023 | 2698/TD | 06/02/2023 | 0 | Resource Division | 65.99 | 0 | 0
2772 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KAINARA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738882/QUOT/03 DT. 17-05-2024 Application NO-2004738882 Application type-New connection Consumer Id- 204309127 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01097/2024-2025 | BP-2024-25-226 | 31/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
2773 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for Shifting of LT POLE AT KAINARA T/W NO-I , BLOCK: RAMNAGRA -I WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. MEMO No- DGA/QT/1042 Dt. 17.09.2024 Application NO- 100000119117 Dt. 17/09/2024 Reference Id- 860313097 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02500/2024-2025 | C102415728122 | 05/10/2024 | 0 | WBSEDCL | 0.33 | 0 | 0
2774 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I of KAINARA WS SCHEME under MMD,PHE Dte, Block-Ramnagar-I, DIGHA CCC, Application no-2004644445, CON ID-204246842 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04740/2023-2024 | BP-2023-24-914 | 28/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0
2775 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAINARA and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001656/2022-2023 | 527/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 75
2776 | Tamluk Division | Tamluk Sadar Sub-Division | payment of Wayleave plan & survey charges SER-KGP-2024-WL-104 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00488/2024-2025 | BP-2024-25-190 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
2777 | Tamluk Division | Tamluk Sadar Sub-Division | payment of Wayleave plan & survey charges SER-KGP-2024-WL-105 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00489/2024-2025 | BP-2024-25-191 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
2778 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-105) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00692/2024-2025 | BP-2024-25-299 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.27 | 0 | 0
2779 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-104) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00693/2024-2025 | BP-2024-25-300 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.21 | 0 | 0
2780 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Sub-Soil investigation, Construction of OHR - 50 Cum, Laying of Distribution pipe line and FHTC work (477 nos) Including 2 years of Operation & Maintenance under JJM with alied work for ground water based Simulberya Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000352/2023-2024 | 881/TD | 01/06/2023 | 914 | BARH CONSTRUCTION | 177.2 | 44.07 | 30
2781 | Tamluk Division | Tamluk Sadar Sub-Division | Installation of 1 Nos. Display Board at Simulberya PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase -VIII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001173/2023-2024 | 769/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.21 | 0.21 | 100
2782 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000193/2023-2024 | 642/W | 20/02/2024 | 0 | Resource Division | 2.94 | 0 | 0
2783 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000302/2022-2023 | 3004/TD | 27/02/2023 | 0 | Resource Division | 5.27 | 0 | 0
2784 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Simulberia W/S Scheme (T/W-I & II) , Sutahatal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000118/2023-2024 | 1397/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 13.38 | 0 | 0
2785 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at TW-I of Simulberia w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695156 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6000W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00648/2024-2025 | BP-2024-25-109 | 06/05/2024 | 0 | WBSEDCL | 8.39 | 0 | 0
2786 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULBERYA and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001670/2022-2023 | 553/W/MMD | 20/03/2023 | 684 | DEBJYOTI BASU | 21.62 | 8.99 | 46
2787 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Amtalia PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000028/2020-2021 | 2104/TD | 05/11/2020 | 180 | ARABINDA GHOSH | 96.58 | 40.55 | 100
2788 | Tamluk Division |  | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 90
2789 | Tamluk Division |  | Instalation of display Board at different work site of Amtalia PWSS (Retrofitting) in Deshpran Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/001189/2023-2024 | 2337/CSD | 29/12/2023 | 7 | AMIT PAYRA | 0.21 | 0.21 | 100
2790 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000591/2020-2021 | 635/W | 13/01/2021 | 0 | ARABINDA GHOSH | 54.93 | 0 | 0
2791 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004874714/QUOT/03/296 DT. 03-09-2024 Application NO- 2004874714 Application type-New connection Consumer Id- 204386343 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01002/2024-2025 | BP-2024-25-631 | 26/11/2024 | 0 | WBSEDCL | 14.38 | 0 | 0
2792 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barttana PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000162/2024-2025 | 2074/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2793 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 270.06 | 51
2794 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000011/2025-2026 | 2072/TD | 12/08/2025 | 0 | Resource Division | 10.1 | 0 | 0
2795 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000134/2022-2023 | 2418/TD | 16/01/2023 | 0 | Resource Division | 43.87 | 0 | 0
2796 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004660093/QUOT/03 DT. 01-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204261081 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00521/2024-2025 | BP-2024-25-96 | 24/04/2024 | 0 | WBSEDCL | 5.33 | 0 | 0
2797 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTANA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001681/2022-2023 | 565/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 22.8 | 0 | 55
2798 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Puronda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000184/2024-2025 | 2194/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2799 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 229.97 | 51
2800 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000017/2025-2026 | 2075/TD | 12/08/2025 | 0 | Resource Division | 8.19 | 0 | 0
2801 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000130/2022-2023 | 2414/TD | 16/01/2023 | 0 | Resource Division | 25.18 | 0 | 0
2802 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674845/QUOT/03 DT. 09-04-2024 Application NO- 2004674845 Application type-New connection Consumer Id- 204269900 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00500/2024-2025 | BP-2024-25-83 | 24/04/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
2803 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674832/QUOT/03 DT. 09-04-2024 Application NO- 2004674832 Application type-New connection Consumer Id- 204269889 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00510/2024-2025 | BP-2024-25-82 | 24/04/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
2804 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURANDA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001627/2022-2023 | 512/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.25 | 100
2805 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3076 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Barttan PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000226/2023-2024 | 452/TD | 04/05/2023 | 876 | TARUN KOLEY | 782.24 | 344.73 | 45
2806 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000121/2023-2024 | 95/TD | 05/01/2024 | 0 | Resource Division | 18.95 | 0 | 0
2807 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000244/2022-2023 | 2724/TD | 06/02/2023 | 0 | Resource Division | 35.45 | 0 | 0
2808 | Midnapore Mechanical | Contai Sub-Division | Barttan W/S scheme T/W no.-II(Tower) Application-2004521219 Ref.-204156075 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03177/2023-2024 | BP-2023-24-477 | 27/12/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
2809 | Midnapore Mechanical | Contai Sub-Division | Barttan W/S scheme T/W no.-I(Tower) Application-2004521240 Ref.-204156076 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03178/2023-2024 | BP-2023-24-478 | 27/12/2023 | 0 | WBSEDCL | 2.93 | 0 | 0
2810 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTAN and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001578/2022-2023 | 473/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 25.26 | 18.96 | 100
2811 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block-Contai-II (Deshpran) in the District of Purba Medinipur. |  |  | ORD/000224/2020-2021 | 2792/TD | 01/02/2021 | 60 | RELIABLE CONSTRUCTIONS | 70.61 | 34.76 | 100
2812 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 1308/TD | 13/05/2025 | 0 | Resource Division | 0.48 | 0 | 0
2813 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Sofiabad W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001243/2020-2021 | 993/W | 26/03/2021 | 0 | RELIABLE CONSTRUCTIONS | 35.85 | 0 | 0
2814 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block Egra-I in the District of Purba Medinipur. |  |  | ORD/000191/2020-2021 | 2770/TD | 28/01/2021 | 60 | FIROZ KHAN | 96.97 | 0 | 100
2815 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000077/2021-2022 | BP-2021-22-40 | 23/07/2021 | 0 | FIROZ KHAN | 3.74 | 0 | 0
2816 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000261/2021-2022 | BP-2021-22-80 | 17/09/2021 | 0 | FIROZ KHAN | 15.36 | 0 | 0
2817 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000393/2021-2022 | 229/W | 07/09/2021 | 0 | FIROZ KHAN | 35.28 | 0 | 0
2818 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001229/2020-2021 | 970/W | 23/03/2021 | 0 | FIROZ KHAN | 44.72 | 0 | 0
2819 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Dariapur PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000032/2020-2021 | 2108/TD | 05/11/2020 | 180 | RAJ KUMAR SINGHA | 79.23 | 0 | 100
2820 | Tamluk Division |  | Land Development at Head Work Site of Dariapur PWSS within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. |  |  | ORD/000643/2023-2024 | 1584/CSD | 16/08/2023 | 15 | JASODA ENTERPRISE | 0.53 | 0.53 | 100
2821 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000599/2020-2021 | 636/W | 13/01/2021 | 0 | RAJ KUMAR SINGHA | 76.24 | 0 | 0
2822 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Aladarput PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000029/2020-2021 | 2105/TD | 05/11/2020 | 180 | TARUN KOLEY | 96.5 | 188.57 | 100
2823 | Tamluk Division |  | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 90
2824 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Uttar Khasda PWSS Block Contai-I in the District of Purba Medinipur. |  |  | ORD/000027/2020-2021 | 2103/TD | 05/11/2020 | 180 | SRIMANTA KUMAR MAITY | 96.46 | 0 | 100
2825 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Uttar Khasda W/S Scheme within Contai - I Block under Tamluk Division, PHE Dte. |  |  | VCH/000609/2020-2021 | 649/W | 25/01/2021 | 0 | SRIMANTA KUMAR MAITY | 87.27 | 0 | 0
2826 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS Block -Contai-II (Deshpran) in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000206/2020-2021 | 2802/TD | 04/02/2021 | 45 | DIPAK KUMAR BAKLY | 111.16 | 39.05 | 70
2827 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Baharchandberya W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 484/TD | 10/05/2023 | 60 | END POINT STRUCTURAL DEPARTMENT | 3.58 | 0 | 0
2828 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM Baharchand Berya W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001141/2020-2021 | 1119/W | 30/03/2021 | 0 | DIPAK KUMAR BAKLY | 23.16 | 0 | 0
2829 | Tamluk Division |  | Retrofitting to accomodate FHTC (400 nos.) under JJM in Argoal PWSS Block - Potashpur-II under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase - II) |  |  | ORD/000004/2021-2022 | 682/TD | 10/09/2021 | 20 | DAS ENTERPRISE | 44.39 | 35.17 | 100
2830 | Central Drilling |  | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ARGOAL W/S SCHEME 2ND TW-II SITE UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000188/2020-2021 | 51 /CMSD-I (D) | 25/02/2021 | 7 | ASHUTOSH DAS & CO | 0.95 | 0.95 | 100
2831 | Central Drilling |  | COMPRESSOR DEVELOPMENT OF THE NEWLY CONSTRUCTION TUBE WELL AT ARGOAL W/S SCHEMW 2ND TW SITE, BLOCK-PATASHPUR-II UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000189/2020-2021 | 54/ CMSD-I (D) | 01/03/2021 | 7 | WEST BENGAL ENGINEERING CO. | 0.32 | 0.32 | 100
2832 | Central Drilling |  | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000191/2020-2021 | 63/CMSD-I | 18/03/2021 | 3 | ASHUTOSH DAS & CO | 0.49 | 0.12 | 100
2833 | Central Drilling |  | ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MX200MMX250 MTRS DEPTH) WITH UPVC PIPE BY DIRECT ROTARY RIG MACHINES JOHN-1000 UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000213/2021-2022 | 1402/CDD | 10/02/2022 | 30 | ASHUTOSH DAS & CO | 11.32 | 4.77 | 100
2834 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block- Contai-III in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000021/2021-2022 | 82/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 96.02 | 59.46 | 100
2835 | Tamluk Division |  | Repair and Renovation of Pump House & R.C.C. Elevated Reservoir of capacity 350 cum with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site and Boundary Wall at 2nd TW Site at Kanaidighi Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000339/2024-2025 | 3337/TD | 22/10/2024 | 40 | PARTHA CONSTRUCTION | 10.87 | 0 | 0
2836 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block Contai - III in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000378/2021-2022 | BP-2021-22-131 | 18/10/2021 | 0 | DAS ENTERPRISE | 27.23 | 0 | 0
2837 | Tamluk Division | Contai Sub-Division | Dismantling of existing OHR (Capacity 55000 Gallons) at Head work Site of Murisai Water Supply Scheme including carriage of old materials to store under Contai Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000067/2021-2022 | 453/TD | 06/08/2021 | 30 | M/S B. N. ENTERPRISES | 7.62 | 6.4 | 100
2838 | Tamluk Division | Contai Sub-Division | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000083/2022-2023 | 436-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 6.67 | 6.67 | 100
2839 | Tamluk Division | Contai Sub-Division | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000093/2022-2023 | 450/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.31 | 0.31 | 100
2840 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000102/2022-2023 | 478/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 13.41 | 0 | 0
2841 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 98
2842 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Murisai PWSS at Contai-III Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000152/2024-2025 | 2063/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2843 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main under JJM with allied work for Augmentation of Murisai Water Supply Scheme in Contai III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000269/2024-2025 | 2898/TD | 10/09/2024 | 319 | MRINAL KANTI PRADHAN | 53.73 | 0 | 40
2844 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Murisai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000317/2021-2022 | 1610/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.67 | 100
2845 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Augmentation of Murisai W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000347/2022-2023 | 1283/TD | 12/09/2022 | 827 | MRINAL KANTI PRADHAN | 3.82 | 0 | 100
2846 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 620 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000350/2021-2022 | 1790/TD | 08/02/2022 | 30 | MAITY CONSTRUCTION | 89.06 | 82.85 | 100
2847 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 570 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000351/2021-2022 | 1791/TD | 08/02/2022 | 30 | SNEHESH SEN | 86.32 | 64.26 | 100
2848 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 419 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000352/2021-2022 | 1792/TD | 08/02/2022 | 30 | LOKENATH ENTERPRISES | 64.86 | 61.94 | 100
2849 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 210 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000353/2021-2022 | 1793/TD | 08/02/2022 | 25 | MRINAL KANTI PRADHAN | 35.66 | 34.09 | 100
2850 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 260 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000354/2021-2022 | 1794/TD | 08/02/2022 | 25 | AHINDRA BARIK | 30.12 | 19.73 | 70
2851 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000355/2021-2022 | 1795/TD | 08/02/2022 | 25 | ABHIJIT BERA | 25.4 | 24.03 | 100
2852 | Tamluk Division | Contai Sub-Division | Canal crossing of Distribution pipe line for Augmentation of Murisai & its adjoining mouzas W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (N.P.-410-415 & N.P.-181-190) (Length = 2nos x15.00 Mtr.= 30.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000355/2022-2023 | 1282/TD | 12/09/2022 | 21 | AHINDRA BARIK | 3.63 | 0 | 0
2853 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 180 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000356/2021-2022 | 1796/TD | 08/02/2022 | 1335 | JASODA ENTERPRISE | 25.5 | 24.33 | 100
2854 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 155 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000357/2021-2022 | 1797/TD | 08/02/2022 | 1177 | PARIA ENTERPRISE | 22.19 | 21.33 | 100
2855 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 110 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000358/2021-2022 | 1798/TD | 08/02/2022 | 20 | S.A. ENTERPRISE | 11.89 | 9.44 | 100
2856 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 75 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART- J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000359/2021-2022 | 1799/TD | 08/02/2022 | 1343 | LAKSHMI NARAYAN ENTERPRISE | 9.86 | 7.96 | 100
2857 | Tamluk Division | Contai Sub-Division | Laying Distribution main for Augmentation of Murisai Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. N.P. 4-8, & 8-12 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000393/2022-2023 | 1426/TD | 26/09/2022 | 15 | CHANDA AGENCIES | 4.18 | 4.18 | 100
2858 | Tamluk Division | Contai Sub-Division | Drum Sheet walling at Murisai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000405/2025-2026 | 1338/CSD | 02/06/2025 | 15 | MRINAL KANTI PRADHAN | 0.97 | 0 | 100
2859 | Tamluk Division | Contai Sub-Division | Drum Sheet walling at Murisai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000406/2025-2026 | 1339/CSD | 02/06/2025 | 15 | MRINAL KANTI PRADHAN | 0.96 | 0 | 100
2860 | Tamluk Division | Contai Sub-Division | Repairing of Pump Houses and Boundary Wall with allied work of Murisai PWSS in Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000448/2024-2025 | 3615/TD | 27/11/2024 | 30 | MRINAL KANTI PRADHAN | 3.4 | 0 | 100
2861 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Murisai-3 nos., Junbani-1 no., Bhagwanpur Zone-I- 1 no.,Bhagwanpur Zone-II- 1 no., Contai Saline Area Zone-III (Phase-A)- 1no. & Contai Saline Area Zone-III (Phase-B)- 1no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000511/2022-2023 | 811 / CSD | 21/10/2022 | 15 | MRINAL KANTI PRADHAN | 0.93 | 0.93 | 100
2862 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 0 | 40
2863 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Baharchandberia Retrofitting PWSS in Contai - II (Deshopran) Block, Kanaidighi, Paschim Kamarda, Murisai Retrofitting PWSS in Contai - III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001186/2023-2024 | 2334/CSD | 29/12/2023 | 15 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0.83 | 100
2864 | Tamluk Division | Contai Sub-Division | Land Filling at Replacement of 2nd Tube well site for Augmentation of Murisai Water Supply Scheme in Contai-III Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Dist-Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001279/2024-2025 | 2467/CSD | 25/10/2024 | 7 | MRINAL KANTI PRADHAN | 0.96 | 0 | 100
2865 | Tamluk Division | Contai Sub-Division | Strengthening of existing approach road for Replacement of 2nd Tube Well at Murisai Water Supply Scheme within Contai-III Block within Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001280/2024-2025 | 2468/CSD | 25/10/2024 | 7 | GANAPATI CONSTRUCTION | 0.97 | 0 | 100
2866 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000029/2021-2022 | 1345/TD | 23/12/2021 | 0 | Resource Division | 20.82 | 0 | 0
2867 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000061/2021-2022 | 1835/TD | 15/02/2022 | 0 | Resource Division | 14.73 | 0 | 0
2868 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW NO-II of Murisai ws scheme. Block-CONTAI-III, MARISHDA CCC APPLICATION NO-2005156460 CON ID-204579889 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00516/2025-2026 | 42156 | 07/08/2025 | 0 | WBSEDCL | 3.54 | 0 | 0
2869 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-III of Murisai w/s scheme under MMD, PHE Dte. Block-Contai-III, MARISHDA CCC Application n0-2004764433 Con ID-204324522 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01234/2024-2025 | BP-2024-25-285 | 18/06/2024 | 0 | WBSEDCL | 5.67 | 0 | 0
2870 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at Murisai Water supply scheme, Contai - III block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001859/2024-2025 | 782/W/MMD | 24/02/2025 | 180 | PADMA ENGINEERING CO. | 14.81 | 0 | 0
2871 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001910/2022-2023 | 811/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.75 | 8.29 | 60
2872 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (345 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-A] | Assistant Engineer | Junior Engineer | ORD/000121/2022-2023 | 614/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 30.95 | 30.93 | 100
2873 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (620 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000123/2022-2023 | 615/TD | 21/06/2022 | 25 | MAA ANANDAMAYEE | 65.39 | 65.43 | 100
2874 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting of FHTC (200 nos.) and Laying of Left-Out portion HDPE Pipe line under Surface Water Based Water Supply Scheme at Zone-V due to uncovered area of this Zone and damaged pipe line at different Nodal Point under Tamluk Sub-Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000020/2022-2023 | 61/TD | 05/04/2022 | 20 | MRITYUNJOY PARIA | 17.51 | 16.09 | 100
2875 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-46) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00134/2024-2025 | BP-2024-25-77 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.35 | 0 | 0
2876 | Tamluk Division | Contai Sub-Division | Draning out of washout & over flow water from 500 Cum Capacity Over Head Reservoir to the near by natural ditch of Augmentation of Kumirda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000033/2025-2026 | 1162/TD | 22/04/2025 | 60 | SAURAV HAZRA | 4.34 | 0 | 0
2877 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line And FHTC ( Functional Household tap connection ) with allied works including all for Augmentation of Kumirda Water Supply Scheme within Contai- III under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2022-2023 | 601/TD | 20/06/2022 | 1260 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 799.74 | 517.9 | 70
2878 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track from station henria and nachinda of augmentation of Kumirda Piped Water Supply scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 44/15 to mast no 44/16 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000120/2024-2025 | 1916/TD | 07/06/2024 | 179 | ROY CONSTRUCTION | 61.73 | 0 | 100
2879 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Kumirda Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000150/2024-2025 | 1736/CSD | 20/06/2024 | 20 | M/S. NEW DINDA ENTERPRISE | 1.16 | 1.16 | 100
2880 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for Additional Tube well site J.L no. -155, Plot no. -1245, Mouza -Panichiary under Augmentation of Kumirda W/S Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000311/2023-2024 | 490/TD | 10/05/2023 | 60 | PARIA ENTERPRISE | 4.09 | 3.58 | 100
2881 | Tamluk Division | Contai Sub-Division | Rising main with laying of 150 mm dia DI (K-9) from 4th Tube Well site to OHR site and other allied works for Kumirda in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000313/2024-2025 | 2357/CSD | 26/09/2024 | 30 | BISWA NIRMAN ENTERPRISE. | 1.61 | 0 | 100
2882 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kumirda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000320/2021-2022 | 1613/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.66 | 5.64 | 100
2883 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kumirda Water Supply Scheme in Contai III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000565/2022-2023 | 2262/TD | 30/12/2022 | 20 | CASTING CORPORATION OF INDIA | 8.5 | 8.5 | 100
2884 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir ( OHR) & 1st.Tube Well , 2nd , 3rd , Additional Tube Well Site, Mouza -kumirda under Augmentation of Kumirda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 230.00 mtr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000732/2022-2023 | 2562/TD | 24/01/2023 | 60 | M/S. PRADIP PRADHAN | 32.65 | 20.96 | 90
2885 | Tamluk Division | Contai Sub-Division | Repairing and Renovation Of Pump House No. I , II & III under Augmentation of Kumirda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000960/2022-2023 | 422/CSD | 17/03/2023 | 30 | PARIA ENTERPRISE | 2.89 | 0 | 0
2886 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000011/2022-2023 | 98/TD | 11/04/2022 | 0 | Resource Division | 40.13 | 0 | 0
2887 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000081/2022-2023 | 1274/TD | 12/09/2022 | 0 | Resource Division | 33.04 | 0 | 0
2888 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000265/2022-2023 | 156/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.99 | 100
2889 | Central Drilling | Contai Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000266/2022-2023 | 157/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.98 | 4.98 | 100
2890 | Central Drilling | Contai Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL IN KUMIRDA PWSS, PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000267/2022-2023 | 158/S&WSD | 12/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.99 | 4.95 | 100
2891 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KUMIRDA Water Supply Scheme T/W-IV, (Ref. ID-204050266) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01684/2023-2024 | BP-2023-24-166 | 04/08/2023 | 0 | WBSEDCL | 5.19 | 0 | 0
2892 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kumirda, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001930/2022-2023 | 849/W/MMD | 24/03/2023 | 720 | SUJOY RANJAN BHOWMICK | 13.58 | 9.63 | 60
2893 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 286.59 | 50
2894 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000447/2021-2022 | 1678/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.72 | 4.71 | 100
2895 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 17.48 | 100
2896 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000064/2022-2023 | 1196/TD | 06/09/2022 | 0 | Resource Division | 29.7 | 0 | 0
2897 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Mukutshila Zone I w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671631, Ref ID 204266595) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03075/2024-2025 | C112443271348 | 02/12/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
2898 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001926/2022-2023 | 845/W/MMD | 24/03/2023 | 180 | DEBJYOTI BASU | 35.54 | 24.61 | 50
2899 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money of Pump House No. - 4 of Khejurberia PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00002/2023-2024 | BP-2023-24-12 | 17/04/2023 | 0 | WBSEDCL | 3.87 | 0 | 0
2900 | Tamluk Division | Haldia Electrical Sub-Division | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00466/2023-2024 | BP-2023-24-238 | 09/08/2023 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 5.94 | 0 | 0
2901 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Khejurberia PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00610/2022-2023 | BP-2022-23-818 | 24/03/2023 | 0 | WBSEDCL | 2.61 | 0 | 0
2902 | Tamluk Division | Haldia Electrical Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00710/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.37 | 0 | 0
2903 | Tamluk Division | Haldia Electrical Sub-Division | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00892/2024-2025 | BP-2024-25-454 | 24/09/2024 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 1.31 | 0 | 0
2904 | Tamluk Division | Haldia Electrical Sub-Division | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Khejurberia PWSS | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01192/2023-2024 | BP-2023-24-565 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.37 | 0 | 0
2905 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejurberia Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000164/2021-2022 | 1168/TD | 01/12/2021 | 7 | RADIANT | 8.76 | 8.65 | 100
2906 | Tamluk Division | Haldia Electrical Sub-Division | Left out pipe line of Providing Functional Household Tap Connection of Khejurberia water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000308/2023-2024 | 622/TD | 17/05/2023 | 30 | TAPAS SANTRA | 77.24 | 77.23 | 100
2907 | Tamluk Division | Haldia Electrical Sub-Division | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 4.96 | 100
2908 | Tamluk Division | Haldia Electrical Sub-Division | Restoration work at Panskura Durgachak road from Ch. 38.400 km to Ch. 38.404 Km (length-4.40 m) after laying pipe line by PHE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000712/2023-2024 | 1280/TSD | 15/09/2023 | 20 | MIHIR SAMANTA | 2.99 | 2.99 | 100
2909 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000724/2022-2023 | 2554/TD | 24/01/2023 | 60 | RAI CONSTRUCTION | 2.8 | 2.8 | 100
2910 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000725/2022-2023 | 2555/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 2.79 | 2.08 | 0
2911 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line to accommodate FHTC (8284 nos) with new construction of R.C.C. Elevated Reservoir of capacity 1000cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000335/2022-2023 | 1279/TD | 12/09/2022 | 1146 | TAPAS SANTRA | 956.75 | 865.39 | 90
2912 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 29.84 | 80
2913 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Khejurberia Water Supply Scheme under Tamluk-Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000726/2022-2023 | 2556/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 5.09 | 5.09 | 0
2914 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well sites of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000735/2022-2023 | 2553/TD | 24/01/2023 | 60 | ANIRBAN MONDAL | 4.79 | 4.19 | 100
2915 | Tamluk Division | Haldia Electrical Sub-Division | Water supply & sanitary arrangement for Switch Room cum chlorine Room (pump House no-II) at Khejurberia PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000770/2023-2024 | 1688/TSD | 15/12/2023 | 24 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 100
2916 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall & fencing work over boundary work with allied work for Khejurberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000850/2022-2023 | 3204/TD | 14/03/2023 | 630 | TAPAS SANTRA | 29.62 | 0 | 30
2917 | Tamluk Division | Haldia Electrical Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-41 of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001181/2023-2024 | 740/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.48 | 0 | 0
2918 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000044/2022-2023 | 1015/TD | 08/08/2022 | 0 | Resource Division | 69.9 | 0 | 0
2919 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000070/2022-2023 | 1256/TD | 12/09/2022 | 0 | Resource Division | 50.95 | 0 | 0
2920 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001519/2022-2023 | 363/W/MMD | 09/03/2023 | 180 | UNITED TRADERS | 23.68 | 22.93 | 60
2921 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
2922 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 443.6 | 94
2923 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 87.75 | 70
2924 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 2900/TD | 21/11/2023 | 0 | Resource Division | 5.49 | 0 | 0
2925 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
2926 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 84.19 | 94
2927 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 686.09 | 70
2928 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 2895/TD | 21/11/2023 | 0 | Resource Division | 1.9 | 0 | 0
2929 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
2930 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 245.24 | 94
2931 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 460.99 | 70
2932 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 2899/TD | 21/11/2023 | 0 | Resource Division | 12.28 | 0 | 0
2933 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Retaining wall cum Gurad Wall at Head work site under Dakshin Anukha and its Adjoning mouzas PWSS under Moyna Block Development Block under Tamluk Sub Division in Tamluk Division, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000139/2024-2025 | 1928/TD | 07/06/2024 | 30 | M J A ENTERPRISE | 3.33 | 3.32 | 100
2934 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000183/2023-2024 | 373/TD | 27/04/2023 | 20 | ACHINTA KUMAR HALDER | 9.86 | 6 | 71
2935 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000184/2023-2024 | 374/TD | 27/04/2023 | 20 | BAGLAMUKHI SECURITY SERVICE | 10 | 6.05 | 56
2936 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000185/2023-2024 | 375/TD | 27/04/2023 | 20 | MRITYUNJOY PARIA | 9.97 | 5.98 | 60
2937 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary wall at 1st. Tube well site & Accommodate FHTC (385 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000250/2023-2024 | 514/TD | 11/05/2023 | 1078 | MAA KALI CONSTRUCTION | 77.96 | 22.14 | 3
2938 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary Wall at 2nd. Tube well site , & Accommodate FHTC (500 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2023-2024 | 515/TD | 11/05/2023 | 60 | SHAKEEL KHAN | 89.3 | 60.12 | 31
2939 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Switch Room cum Chlorine Room I & II , Accommodate FHTC (550 nos) & Rising Main under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000293/2023-2024 | 582/TD | 16/05/2023 | 896 | NARAYAN MANDAL | 138.66 | 104.99 | 80
2940 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of M.S. Structure over irrigation canal to support 100 mm dia. GI distribution pipe under Dakhin Anukha and its Adjoining Mouzas PWSS at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=20.00 Mtr 4 nos and L= 16 mtr 6 nos ,Total 10 nos Stracture. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2024-2025 | 3141/TD | 26/09/2024 | 90 | NARAYAN MANDAL | 29.63 | 7.81 | 100
2941 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000528/2023-2024 | 1777/TD | 02/08/2023 | 851 | NEW STAR CONSTRUCTION | 108.73 | 54.87 | 90
2942 | Tamluk Division | Tamluk Sadar Sub-Division | Development of low land and construction of Link Road by carried earth at H/W Site for Dakshin Anukha PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000698/2023-2024 | 2738/TD | 01/11/2023 | 890 | MAA KALI CONSTRUCTION | 6.92 | 5.02 | 25
2943 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000702/2023-2024 | 2813/TD | 07/11/2023 | 20 | CHANDA AGENCIES | 9.93 | 6.52 | 81
2944 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed retaining wall cum guard wall , approach road, earth filling at 2nd tube site under Dakshin Anukha and its adjoining mouzas PWSS under Moyna development block under Tamluk Sub-Division in Tamluk Division ,Dist-Pruba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000719/2023-2024 | 2941/TD | 23/11/2023 | 25 | NARAYAN MANDAL | 8.22 | 8.21 | 60
2945 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2024-2025 | 1562/TD | 23/04/2024 | 0 | Resource Division | 10.07 | 0 | 0
2946 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000326/2022-2023 | 2990/TD | 27/02/2023 | 0 | Resource Division | 46.28 | 0 | 0
2947 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crews Including Allied Materials for construction of Tube Well (300mm X200mm) at Dakshin Ankha PWSS within Moyna Block under Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000176/2023-2024 | 1469/CDD | 27/09/2023 | 210 | PADMA ENGINEERING & CO. | 14.74 | 0 | 100
2948 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Dakshin Ankha W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000178/2023-2024 | 1414/CDD | 20/09/2023 | 210 | MENAKA ENTERPRISE | 11.26 | 9.95 | 100
2949 | Central Drilling | Tamluk Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Dakshin Ankha W/S Scheme ( TW- II) , Moyna Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000221/2023-2024 | 1844//CDD | 18/12/2023 | 120 | PADMA ENGINEERING & CO. | 14.69 | 12.26 | 100
2950 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional quotation for Dakhin Anukha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 100000112312, Ref ID 860303992) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01721/2024-2025 | BP-2024-25-496 | 30/07/2024 | 0 | WBSEDCL | 0.99 | 0 | 0
2951 | Midnapore Mechanical | Tamluk Sadar Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF JUNE'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04358/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.23 | 0 | 0
2952 | Midnapore Mechanical | Tamluk Sadar Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF APRIL'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04369/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.15 | 0 | 0
2953 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for Dakhin Ankha w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608987, Ref ID-204222617) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04496/2023-2024 | BP-2023-24-859 | 16/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0
2954 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for Dakhin Ankha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608983, Ref ID-204222616) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04501/2023-2024 | BP-2023-24-858 | 16/03/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
2955 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
2956 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DKSHIM ANKHA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001636/2022-2023 | 516/W/MMD | 20/03/2023 | 683 | KARUNAMOY ENGINEERING | 22.75 | 15.69 | 100
2957 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000127/2023-2024 | 258/TD | 19/04/2023 | 25 | MENAKA ENTERPRISE | 13.21 | 0 | 0
2958 | Tamluk Division | Digha Sub-Division | Soil investigation, 150 cum OHR (Torch type with pile foundation) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000254/2023-2024 | 522/TD | 11/05/2023 | 1147 | SASWATA CONSTRUCTION | 86.46 | 0 | 98
2959 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Mirjapur PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000463/2024-2025 | 3463/TD | 06/11/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2960 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall , Laying rising main pipe line & Accommodate FHTC (835 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000518/2023-2024 | 1754/TD | 01/08/2023 | 708 | BARH CONSTRUCTION | 211.44 | 0 | 70
2961 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline for distribution pipeline due to revised drawing for Mirjapur PWSS under JJM within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001179/2023-2024 | 723/TD | 28/02/2024 | 718 | ELECTIVA ENTERPRISE | 6.28 | 0 | 0
2962 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000027/2025-2026 | 2088/TD | 12/08/2025 | 0 | Resource Division | 6.38 | 0 | 0
2963 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000319/2022-2023 | 2973/TD | 27/02/2023 | 0 | Resource Division | 37.6 | 0 | 0
2964 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 64.14 | 11
2965 | Central Drilling | Digha Sub-Division | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000006/2024-2025 | 253/CMSD-I | 26/06/2024 | 182 | SUJATA BHOWMICK | 0.86 | 2.11 | 0
2966 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MIRJAPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671915/QUOT/03/50 DT. 05-04-2024 Application NO- 2004671915 Application type-New connection Consumer Id- 204266735 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00514/2024-2025 | BP-2024-25-92 | 24/04/2024 | 0 | WBSEDCL | 4.49 | 0 | 0
2967 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MIRZAPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005008543/QUOT/03 DT. 16-12-2024 Application NO- 2005008543 Application type-New connection Consumer Id- 204473364 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03876/2024-2025 | C012552559475 | 31/01/2025 | 0 | WBSEDCL | 3.63 | 0 | 0
2968 | Midnapore Mechanical | Digha Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
2969 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block - Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001615/2022-2023 | 506/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 21.59 | 0 | 0
2970 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 598.73 | 70
2971 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2022-2023 | 1372/TD | 23/09/2022 | 0 | Resource Division | 38.75 | 0 | 0
2972 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000101/2022-2023 | 1658/TD | 03/11/2022 | 0 | Resource Division | 180.08 | 0 | 0
2973 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIA Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000022/2021-2022 | 81/TD | 11/05/2021 | 60 | TITAS CONSTRUCTION | 53.3 | 51.1 | 100
2974 | Tamluk Division | Haldia Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01479/2023-2024 | BP-2023-24-666 | 15/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
2975 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000070/2023-2024 | 140/TD | 10/04/2023 | 30 | THREE MAA ENTERPRISE | 69.26 | 69.25 | 75
2976 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000296/2023-2024 | 585/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.37 | 0 | 0
2977 | Tamluk Division | Haldia Sub-Division | Canal Crossing Structure for Laying Distribution (Nodal Point - 17 - 18) & Rising Main Pipeline of Madhya Hingly Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000651/2023-2024 | 2609/TD | 11/10/2023 | 30 | SOUVIK GHOSAL | 7.39 | 4.72 | 100
2978 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000818/2022-2023 | 3108//TD | 02/03/2023 | 1149 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 67.57 | 44.7 | 55
2979 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000819/2022-2023 | 3109/TD | 02/03/2023 | 30 | SK SANAMAJ | 59.34 | 44.1 | 40
2980 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000820/2022-2023 | 3110/TD | 02/03/2023 | 30 | S. N. A. CONSTRUCTION | 58.38 | 50.43 | 35
2981 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000821/2022-2023 | 3111/TD | 02/03/2023 | 30 | SOUMYA ENTERPRISE | 49.53 | 38.52 | 80
2982 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000822/2022-2023 | 3112/TD | 02/02/2023 | 20 | PULAK KUMAR SAMANTA | 31.14 | 19.16 | 62
2983 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000138/2022-2023 | 2423/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0
2984 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000155/2023-2024 | 101/TD | 05/01/2024 | 0 | Resource Division | 10.82 | 0 | 0
2985 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for MADHYA HINGLI Water Supply Scheme T/W-I, (Ref. ID-204136074) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03184/2023-2024 | BP-2023-24-441 | 19/12/2023 | 0 | WBSEDCL | 5.95 | 0 | 0
2986 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Madhya Hingli w/s scheme PH II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03665/2023-2024 | BP-2023-24-682 | 15/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
2987 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MADHYA HINGLI and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001625/2022-2023 | 510/W/MMD | 20/03/2023 | 652 | SHOVAN KUMAR DAS | 22.81 | 10.54 | 45
2988 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 25.35 | 100
2989 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at 5 nos { 1. GOBARDAN PWSS( PUMP HOUSE -2) , 2. UTTAR CHONGRA CHAK PWSS( PUMP HOUSE 1 & 2), 3.BAKCHA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000253/2025-2026 | 58/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
2990 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 301.79 | 75
2991 | Tamluk Division | Haldia Electrical Sub-Division | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.01.2025 to 31.06.2025 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000573/2024-2025 | 344/RWS/TSD | 30/12/2024 | 181 | SADHAN CHANDRA SAMANTA | 0.86 | 1.08 | 0
2992 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Bakcha PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000879/2023-2024 | 201/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
2993 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000001/2024-2025 | 1559/TD | 23/04/2024 | 0 | Resource Division | 12.6 | 0 | 0
2994 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000183/2022-2023 | 2430/TD | 16/01/2023 | 0 | Resource Division | 26.3 | 0 | 0
2995 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Bakcha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004620130, Ref ID-204229481) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04502/2023-2024 | BP-2023-24-854 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
2996 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Bakcha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631507, Ref ID 204237228) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04744/2023-2024 | BP-2023-24-906 | 28/03/2024 | 0 | WBSEDCL | 6.12 | 0 | 0
2997 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKCHA and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001331/2022-2023 | 2336/W/MMD | 29/12/2022 | 180 | PRANAB KUMAR DAS | 23.69 | 22.11 | 90
2998 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2305 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of MIRJAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000225/2023-2024 | 456/TD | 04/05/2023 | 900 | TAPAS SANTRA | 719.36 | 478.77 | 66
2999 | Tamluk Division | Contai Sub-Division | Construction boundary wall & Accommodate FHTC (200 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000444/2023-2024 | 1452/TD | 13/07/2023 | 30 | HYDROTECH ASSOCIATES | 13.65 | 0 | 0
3000 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000149/2023-2024 | 87/TD | 05/01/2024 | 0 | Resource Division | 14.2 | 0 | 0
3001 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000193/2022-2023 | 2380/TD | 16/01/2023 | 0 | Resource Division | 19.37 | 0 | 0
3002 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-I, (Ref. ID-204086227) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02892/2023-2024 | BP-2023-24-313 | 01/11/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
3003 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-II, (Ref. ID-204090824) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02893/2023-2024 | BP-2023-24-316 | 01/11/2023 | 0 | WBSEDCL | 1.14 | 0 | 0
3004 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001350/2022-2023 | 2361/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 23.67 | 23.13 | 100
3005 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House , Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2138 nos), Including 2 years of operation maintance under JJM with allied work for Balgobindapur- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000613/2023-2024 | 2272/TD | 05/09/2023 | 965 | DAS ENTERPRISE | 693.39 | 0 | 40
3006 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000018/2024-2025 | 1648/TD | 29/04/2024 | 0 | Resource Division | 13.17 | 0 | 0
3007 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000261/2022-2023 | 2702/TD | 06/02/2023 | 0 | Resource Division | 14.6 | 0 | 0
3008 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BALGOBINDAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004675882/QUOT/03 DT. 12-04-2024 Application NO- 2004675882 Application type-New connection Consumer Id- 204270815 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00578/2024-2025 | BP-2024-25-100 | 26/04/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
3009 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BALGOBINDAPUR and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001329/2022-2023 | 2334/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 55
3010 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 165.13 | 60
3011 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2023-2024 | 349/TD | 26/04/2023 | 0 | Resource Division | 51.9 | 0 | 0
3012 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000042/2024-2025 | 1664/TD | 29/04/2024 | 0 | Resource Division | 7.61 | 0 | 0
3013 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TANIABILA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004971307/QUOT/03 DT. 20-11-2024 Application NO- 2004971307 Application type-New connection Consumer Id- 204450412 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03665/2024-2025 | C012524041808 | 09/01/2025 | 0 | WBSEDCL | 3.26 | 0 | 0
3014 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TANIABILA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004971271/QUOT/03 DT. 20-11-2024 Application NO- 2004971271 Application type-New connection Consumer Id- 204450410 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03666/2024-2025 | C012524040713 | 09/01/2025 | 0 | WBSEDCL | 4.52 | 0 | 0
3015 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TANIA BILA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001318/2022-2023 | 2320/W/MMD | 29/12/2022 | 180 | M/S. SAJAHAN CHOWDHURY | 22.79 | 16.65 | 65
3016 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Augmentation of Bijaynagar & adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000318/2024-2025 | 3221/TD | 01/10/2024 | 168 | TARUN KOLEY | 30.63 | 0 | 100
3017 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1750 nos) under JJM with allied work for BIJAYNAGAR PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000480/2023-2024 | 1553/TD | 19/07/2023 | 652 | TARUN KOLEY | 555.04 | 265.45 | 70
3018 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Bijaynagar & adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000485/2024-2025 | 3753/TD | 06/12/2024 | 50 | BHOWMIK & SONS | 10.64 | 0 | 100
3019 | Tamluk Division | Contai Sub-Division | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Contai-I, Deshpran(Contai-II), Contai-III, Bhagwanpur-I & Bhagwanpur-II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001290/2023-2024 | 562/CSD | 14/03/2024 | 10 | BISWA NIRMAN ENTERPRISE. | 0.68 | 0 | 100
3020 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000180/2023-2024 | 629/W | 20/02/2024 | 0 | Resource Division | 10.78 | 0 | 0
3021 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000307/2022-2023 | 2964/TD | 27/02/2023 | 0 | Resource Division | 16.56 | 0 | 0
3022 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well(250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Bijaynagar W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000108/2023-2024 | 1394/CDD | 19/09/2023 | 30 | MENAKA ENTERPRISE | 27.2 | 0 | 0
3023 | Midnapore Mechanical | Contai Sub-Division | Bijoynagar W/S scheme T/W-II Application.-2004537378 Ref.-204168879 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03294/2023-2024 | BP-2023-24-529 | 11/01/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
3024 | Midnapore Mechanical | Contai Sub-Division | Bijoynagar W/S scheme T/W-I Application.-2004537086 Ref.-204168733 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03295/2023-2024 | BP-2023-24-530 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
3025 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
3026 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIJAYNAGAR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001320/2022-2023 | 2322/W/MMD | 29/12/2022 | 723 | GOENKA ENTERPRISE | 22.8 | 21.04 | 100
3027 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1594 nos) under JJM with allied work of GARBERHA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000074/2023-2024 | 131/TD | 10/04/2023 | 782 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 454.99 | 308.41 | 75
3028 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000133/2023-2024 | 120/TD | 05/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
3029 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000195/2022-2023 | 2382/TD | 16/01/2023 | 0 | Resource Division | 23.95 | 0 | 0
3030 | Midnapore Mechanical | Contai Sub-Division | Gar Bhera W/S scheme T/W-V Application No.-2004553977 Ref.-204184071 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03358/2023-2024 | BP-2023-24-573 | 18/01/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
3031 | Midnapore Mechanical | Contai Sub-Division | Garbhera W/S scheme T/W-II Application No.-2004554001 Ref.-204184072 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03359/2023-2024 | BP-2023-24-580 | 18/01/2024 | 0 | WBSEDCL | 7.59 | 0 | 0
3032 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GAR BHERA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001336/2022-2023 | 2341/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 22.14 | 85
3033 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
3034 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000019/2024-2025 | 1642/TD | 18/06/2025 | 0 | Resource Division | 6.84 | 0 | 0
3035 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000199/2022-2023 | 2444/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0
3036 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004870409/QUOT/03 DT. 23-08-2024 MEMO NO: AMR/PHE/338 DT. 23-08-2024 Application NO- 2004870409 Application type-New connection Consumer Id- 204383603 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02398/2024-2025 | BP-2024-25-648 | 06/09/2024 | 0 | WBSEDCL | 5.91 | 0 | 0
3037 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878231/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/351 DT. 30-08-2024 Application NO- 2004878231 Application type-New connection Consumer Id- 204387577 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02453/2024-2025 | C102415714404 | 05/10/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
3038 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARA BHAGIA and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001626/2022-2023 | 511/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.26 | 60
3039 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1669 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NILKANTHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000076/2023-2024 | 129/TD | 10/04/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 486.76 | 127.04 | 25
3040 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000160/2023-2024 | 127/TD | 05/01/2024 | 0 | Resource Division | 10.28 | 0 | 0
3041 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000247/2022-2023 | 2721/TD | 06/02/2023 | 0 | Resource Division | 19.28 | 0 | 0
3042 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818541/QUOT/03 DT. 12-07-2024 Application NO- 2004818541 Application type-New connection Consumer Id- 204355510 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01890/2024-2025 | BP-2024-25-555 | 08/08/2024 | 0 | WBSEDCL | 12.51 | 0 | 0
3043 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004942161/QUOT/03 DT. 24-10-2024 Application NO- 2004942161 Application type-New connection CONSUMER ID: 204427729 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03004/2024-2025 | C112423542425 | 20/11/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
3044 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005116348/QUOT/03 DT. 06-03-2025 Application NO- 2005116348 Application type-New connection Consumer Id- 204551421 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04968/2024-2025 | 42156 | 07/08/2025 | 0 | WBSEDCL | 0.88 | 0 | 0
3045 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001412/2022-2023 | 2423/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 17.44 | 62
3046 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Shipur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000173/2024-2025 | 2085/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3047 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 220.85 | 51
3048 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000019/2025-2026 | 2077/TD | 12/08/2025 | 0 | Resource Division | 9.14 | 0 | 0
3049 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000132/2022-2023 | 2416/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0
3050 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SHIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004976541/QUOT/03/2033 DT. 26-11-2024 Application NO- 2004976541 Application type-New connection Consumer Id- 204456613 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03269/2024-2025 | C122406884240 | 06/12/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
3051 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SHIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2005060926/QUOT/03/2887 DT. 27-01-2025 Application NO- 2005060926 Application type-New connection Consumer Id- 204508298 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04506/2024-2025 | C032587407420 | 27/03/2025 | 0 | WBSEDCL | 4.98 | 0 | 0
3052 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHIPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001413/2022-2023 | 2424/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 51
3053 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Amdai PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000172/2024-2025 | 2084/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3054 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 97.31 | 51
3055 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000008/2025-2026 | 2082/TD | 12/08/2025 | 0 | Resource Division | 6.54 | 0 | 0
3056 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000158/2022-2023 | 2421/TD | 16/01/2023 | 0 | Resource Division | 16.01 | 0 | 0
3057 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of Amdai w/s scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia CCC,Application no-2004635540.Con ID-204242882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04574/2023-2024 | BP-2023-24-886 | 22/03/2024 | 0 | WBSEDCL | 5.55 | 0 | 0
3058 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of AMDAI WS Scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia ccc . Application no-2004635643. CON ID-204240383. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04576/2023-2024 | BP-2023-24-887 | 22/03/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
3059 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMDAI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001405/2022-2023 | 2416/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 0 | 80
3060 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 02 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000169/2023-2024 | 296/TD | 20/04/2023 | 40 | SPG ENTERPRISES | 37.92 | 34.74 | 100
3061 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000323/2021-2022 | 1616/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.16 | 6.16 | 100
3062 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000407/2022-2023 | 1449/TD | 27/09/2022 | 1372 | AJIT KUMAR SOM | 351.09 | 231.59 | 90
3063 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000408/2022-2023 | 1448/TD | 27/09/2022 | 1214 | SNEHESH SEN | 170.64 | 99.16 | 0
3064 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000521/2022-2023 | 2093/TD | 13/12/2022 | 1106 | LOKENATH ENTERPRISES | 79.14 | 47.5 | 95
3065 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2022-2023 | 2096/TD | 13/12/2022 | 15 | M/S. PRADIP PRADHAN | 4.18 | 4.18 | 100
3066 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000525/2022-2023 | 2011/TD | 06/12/2022 | 25 | DHANANJOY DAS | 38.53 | 9.09 | 25
3067 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000526/2022-2023 | 2012/TD | 06/12/2022 | 25 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.56 | 3.16 | 0
3068 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000527/2022-2023 | 2013/TD | 06/12/2022 | 25 | CHARUBALA ENTERPRISE | 10.76 | 2.41 | 0
3069 | Tamluk Division | Digha Sub-Division | Repairing & renovation of Pump House, construction of boundary wall , Land development, Supply & delivery of different dia D.I. Specials with allied works under JJM for Paniparul (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000601/2023-2024 | 2195/TD | 01/09/2023 | 571 | AJIT KUMAR SOM | 48.26 | 0 | 90
3070 | Tamluk Division | Digha Sub-Division | Site cleaning at Head work site of Paniparul (zone-I ) W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000917/2023-2024 | 859/DSD | 01/12/2023 | 3 | SOM CONSTRUCTION | 0.36 | 0.36 | 100
3071 | Tamluk Division | Digha Sub-Division | Laying distribution of pipe line, Pump House at 2nd TW site, construction of boundary wall & FHTC -100nos. (Phase-II) with allied works under JJM for Paniparul( Z-I) PWSS within Egra- II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001145/2023-2024 | 565/TD | 15/02/2024 | 40 | AJIT KUMAR SOM | 39.83 | 35.73 | 100
3072 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000114/2022-2023 | 1667/TD | 03/11/2022 | 0 | Resource Division | 128.58 | 0 | 0
3073 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000281/2022-2023 | 2634/TD | 02/02/2023 | 0 | Resource Division | 24.04 | 0 | 0
3074 | Midnapore Mechanical | Digha Sub-Division | Paniparul W/S scheme TW-2 Memo No.-2004516165/Quot/03/1650 application no-2004516165 ref. id-204151594 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03146/2023-2024 | BP-2023-24-447 | 19/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
3075 | Midnapore Mechanical | Digha Sub-Division | Paniparul W/S scheme TW-2 Memo No.-2004516174/Quot/03/1649 application no-2004516174 ref. id-204151561 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03147/2023-2024 | BP-2023-24-448 | 19/12/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
3076 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - I Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001680/2023-2024 | 58/W/MMD | 15/01/2024 | 360 | POLYCON ENGINEERS | 13.92 | 12.32 | 100
3077 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001933/2022-2023 | 852/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.47 | 13.3 | 100
3078 | Tamluk Division | Contai Sub-Division | Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (124 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000382/2023-2024 | 1018/TD | 06/06/2023 | 936 | DAS ENTERPRISE | 201.92 | 70.87 | 37
3079 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, & Accommodate FHTC (270 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000840/2022-2023 | 3184/TD | 10/03/2023 | 25 | SUBHENDU HAZRA | 48.38 | 23.1 | 50
3080 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 250 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000841/2022-2023 | 3185/TD | 10/03/2023 | 1110 | M/S. NEW DINDA ENTERPRISE | 48.13 | 23.7 | 50
3081 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (300nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000843/2022-2023 | 3186/TD | 10/03/2023 | 25 | BADAL CHANDRA GOLE | 37.34 | 16.56 | 48
3082 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000844/2022-2023 | 3187/TD | 10/03/2023 | 15 | SUSANTA KUMAR KAR | 9.8 | 4.36 | 45
3083 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Basudeb Berya PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001052/2023-2024 | 382/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3084 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of BASUDEVBERIA PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001148/2023-2024 | 568/TD | 15/02/2024 | 264 | PARTHA CONSTRUCTION | 6.83 | 0 | 90
3085 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000120/2022-2023 | 2389/TD | 16/01/2023 | 0 | Resource Division | 33.31 | 0 | 0
3086 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000185/2023-2024 | 634/W | 20/02/2024 | 0 | Resource Division | 6.55 | 0 | 0
3087 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 25.77 | 11
3088 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill cost due to Modification for NSC of PHE AT Site- BASUDEVBERIA W/S SCHEME, T/W NO-I Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/253 DT. 16-05-2024 Application NO- 100000108115 DT. 16-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300165 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01128/2024-2025 | BP-2024-25-241 | 06/06/2024 | 0 | WBSEDCL | 0.59 | 0 | 0
3089 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558723/QUOT/03 DT. 10-01-2024 Application NO- 2004558723 Application type-New connection Consumer Id- 204187848 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04388/2023-2024 | BP-2023-24-829 | 13/03/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
3090 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558731/QUOT/03 DT. 27-02-2024 Application NO- 2004558731 Application type-New connection Consumer Id- 204187847 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04390/2023-2024 | BP-2023-24-828 | 13/03/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
3091 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
3092 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
3093 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
3094 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Nijkasba W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side, North & South Side) | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 487/TD | 10/05/2023 | 45 | BIPLAB BAHNI GUCHHAIT | 4.5 | 3.79 | 100
3095 | Tamluk Division | Contai Sub-Division | Providing FHTC with allied works of Nijkasba & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000544/2022-2023 | 2163/TD | 19/12/2022 | 25 | HARIPADA PATTANAYAK | 35.25 | 33.89 | 70
3096 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works of distribution system of Nijkasba W/S Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000765/2025-2026 | 2275/CSD | 09/10/2025 | 30 | SAVORIO REALITY LLP | 0.96 | 0 | 0
3097 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 609/TD | 17/05/2023 | 0 | Resource Division | 4.7 | 0 | 0
3098 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000252/2022-2023 | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 16.89 | 32
3099 | Tamluk Division | Contai Sub-Division | Laying Rising Main, Construction of Boundary wall at 3rd Tube Well Boosting Site of Damudarpur PWSS in Contai-I within Contai Sub-Division of Tamluk Division,PHE Dte. {Length-44.00 mtr.} (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000486/2023-2024 | 1576/TD | 19/07/2023 | 30 | M/S MONDAL CONSTRUCTION & CO. | 14.04 | 11.85 | 100
3100 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000019/2023-2024 | 356/TD | 26/04/2023 | 0 | Resource Division | 11.65 | 0 | 0
3101 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Damodarpur PWSS Tube Well-III WS Scheme (Ref. ID - 203911304) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00317/2022-2023 | BP-2022-23-136 | 20/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
3102 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well and 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai I,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2023-2024 | 1413/W/MMD | 02/06/2023 | 180 | RUBY ENTERPRISE | 27.17 | 13.44 | 80
3103 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3104 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 233.38 | 75
3105 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Raghusardarbar Jalpai PWSS at Contai-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000882/2023-2024 | 204/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0.96 | 100
3106 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000070/2024-2025 | 2976/TD | 12/09/2024 | 0 | Resource Division | 5.96 | 0 | 0
3107 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000170/2022-2023 | 2394/TD | 16/01/2023 | 0 | Resource Division | 45.39 | 0 | 0
3108 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of RAGHUSARDARBAR JALPAI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004950694/QUOT/03 DT. 30-10-2024 Application NO- 2004950694 Application type-New connection Consumer Id- 204434651 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03022/2024-2025 | C122406886493 | 06/12/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
3109 | Midnapore Mechanical | Contai Sub-Division | Quotation for New service connection at TW-I of Raghu Sardarbar Jalpai ws scheme under MMD,PHE ,Dte. Ref Application no-2004579837, CON ID-204204431, under PICHABONI CCC, Block-Contai-I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03659/2023-2024 | BP-2023-24-662 | 12/02/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
3110 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAGHUSARDAR BAR JALPAI and ADJOINING MOUJAS, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001666/2022-2023 | 549/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 10.04 | 80
3111 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2024-2025 | 1639/TD | 18/06/2025 | 0 | Resource Division | 8.37 | 0 | 0
3112 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000225/2022-2023 | 2704/TD | 06/02/2023 | 0 | Resource Division | 22.02 | 0 | 0
3113 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of CHANDPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005076157/QUOT/03 DT. 05-02-2024 MEMO NO: AMR/PHE/686 DT. 05-02-2024 Application NO- 2005076157 Application type-New connection Consumer Id- 204520898 | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04276/2024-2025 | C032554600635 | 17/03/2025 | 0 | WBSEDCL | 5.23 | 0 | 0
3114 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of CHANDPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005076216/QUOT/03 DT. 05-02-2024 MEMO NO: AMR/PHE/687 DT. 05-02-2024 Application NO- 2005076216 Application type-New connection Consumer Id- 204520908 | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04277/2024-2025 | C032554598872 | 17/03/2025 | 0 | WBSEDCL | 3.7 | 0 | 0
3115 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHANDPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001679/2022-2023 | 566/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 22.8 | 0 | 0
3116 | Tamluk Division | Digha Sub-Division | Payment to WBSEDCL for Shifting of 11KV HT maithana feeder for Kalapunja PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01994/2023-2024 | BP-2023-24-938 | 06/03/2024 | 0 | WBSEDCL | 2.16 | 0 | 0
3117 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 238.18 | 60
3118 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000150/2023-2024 | 119/TD | 05/01/2024 | 0 | Resource Division | 8.41 | 0 | 0
3119 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000263/2022-2023 | 2690/TD | 06/02/2023 | 0 | Resource Division | 39.36 | 0 | 0
3120 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670828/QUOT/03 DT. 05-04-2024 Application NO- 2004670828 Application type-New connection Consumer Id- 204266383 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00301/2024-2025 | BP-2024-25-43 | 18/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
3121 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749309/QUOT/03 DT. 28-05-2024 Application NO- 2004749309 Application type-New connection Consumer Id- 204316972 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01146/2024-2025 | BP-2024-25-258 | 06/06/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
3122 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALAPUNJA and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000150/2023-2024 | 1376/W/MMD | 30/05/2023 | 701 | MENAKA ENTERPRISE | 23.67 | 17.84 | 100
3123 | Tamluk Division | Digha Sub-Division | Relaying the Distribution pipe line (Damaged during the construction of RIDF road from Dakshin Purushottampur Khal Parh to House of Jugal Giri House) of Ranisai PWSS, Ramnagar- I Block under Digha Sub-Division of Tamluk Division , PHE Dte. in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000369/2022-2023 | 1336/TD | 16/09/2022 | 25 | SUKOMAL BERA | 27.06 | 27.05 | 0
3124 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Ranisai & its adjoining mouzas W/S Scheme within Ramnagar - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000378/2023-2024 | 1027/TD | 07/06/2023 | 842 | SWASTIK ENTERPRISE | 62.09 | 12.77 | 21
3125 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000036/2023-2024 | 2064/TD | 28/08/2023 | 0 | Resource Division | 17.51 | 0 | 0
3126 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000092/2023-2024 | 2995/TD | 29/11/2023 | 0 | Resource Division | 2.24 | 0 | 0
3127 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at tw-III of Ranisai ws scheme under MMD PHE Dte,Block-Ramnagar-I, Digha CCC Application no-2004764426 Con ID-204324285 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01226/2024-2025 | C062416826632 | 18/06/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
3128 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001997/2022-2023 | 885/W/MMD | 27/03/2023 | 1259 | SUDIKSHA CONSTRUCTION | 12.37 | 3.05 | 10
3129 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at PATNA PWSS at Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000376/2025-2026 | 1375/CSD | 03/06/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
3130 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 437.25 | 60
3131 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Patna, Jahanabad & its adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000567/2024-2025 | 2443/CSD | 22/10/2024 | 7 | M/S. NEW DINDA ENTERPRISE | 0.42 | 0 | 100
3132 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000079/2024-2025 | 2971/TD | 12/09/2024 | 0 | Resource Division | 18.05 | 0 | 0
3133 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000229/2022-2023 | 2710/TD | 06/02/2023 | 0 | Resource Division | 6.86 | 0 | 0
3134 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Patna W/S Scheme (T/W-I) ,Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000104/2023-2024 | 852/CDD | 10/07/2023 | 30 | C.M. ENTERPRISE | 15.47 | 0 | 0
3135 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Patna w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640160, Ref ID - 204244152) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04491/2023-2024 | BP-2023-24-855 | 16/03/2024 | 0 | WBSEDCL | 7.46 | 0 | 0
3136 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PATNA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001372/2022-2023 | 2383/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 19.5 | 60
3137 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004768458/QUOT/03 DT. 11-06-2024 Application NO- 2004768458 Application type-New connection Consumer Id- 204327319 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00596/2024-2025 | BP-2024-25-294 | 29/07/2024 | 0 | WBSEDCL | 10.84 | 0 | 0
3138 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3139 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (940 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000266/2023-2024 | 532/TD | 12/05/2023 | 1120 | M/S SREE DURGA ENTERPRISE | 196.73 | 93.53 | 49
3140 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 700nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000270/2023-2024 | 531/TD | 12/05/2023 | 1143 | M/S SREE DURGA ENTERPRISE | 138.34 | 71.13 | 80
3141 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000390/2023-2024 | 1049/TD | 07/06/2023 | 694 | TARUN KOLEY | 266.16 | 56.41 | 65
3142 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (370 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000447/2023-2024 | 1466/TD | 13/07/2023 | 446 | R CONSTRUCTION | 69.75 | 44.91 | 60
3143 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works for Left Out Area due to Revised Drawing of BAHADURPUR PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000709/2023-2024 | 2875/TD | 17/11/2023 | 681 | M/S SREE DURGA ENTERPRISE | 33.75 | 32.61 | 97
3144 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000177/2023-2024 | 626/W | 20/02/2024 | 0 | Resource Division | 15.22 | 0 | 0
3145 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000298/2022-2023 | 2962/TD | 27/02/2023 | 0 | Resource Division | 65.74 | 0 | 0
3146 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 51.53 | 11
3147 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill cost for Diversion of route due to RAW at the PHE Site-BAHADURPUR W/S SCHEME,T/W NO-II, MADHABPUR Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/260 DT. 17-05-2024 Application NO- 100000108126 DT. 17-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300546 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01144/2024-2025 | BP-2024-25-242 | 06/06/2024 | 0 | WBSEDCL | 1.41 | 0 | 0
3148 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601928/QUOT/03 DT. 15-02-2024 Application NO- 2004601928 Application type-New connection Reference Id- 204217837 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04266/2023-2024 | BP-2023-24-794 | 06/03/2024 | 0 | WBSEDCL | 4 | 0 | 0
3149 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
3150 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Panchet PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000192/2024-2025 | 2202/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3151 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 210.59 | 51
3152 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000053/2024-2025 | 1662/TD | 29/04/2024 | 0 | Resource Division | 11.82 | 0 | 0
3153 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000147/2022-2023 | 2452/TD | 16/01/2023 | 0 | Resource Division | 24.44 | 0 | 0
3154 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649232/QUOT/03 DT. 20-03-2024 Application NO- 2004649232 Application type-New connection Consumer Id- 204250589 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00007/2024-2025 | BP-2024-25-3 | 04/04/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
3155 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004626644/QUOT/03 DT. 01-03-2024 Application NO- 2004626644 Application type-New connection Consumer Id- 204234144 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04391/2023-2024 | BP-2023-24-820 | 13/03/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
3156 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PANCHET and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001367/2022-2023 | 2378/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 0 | 45
3157 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3158 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 150.73 | 51
3159 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000033/2024-2025 | 1632/TD | 18/06/2025 | 0 | Resource Division | 9.7 | 0 | 0
3160 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000139/2022-2023 | 2439/TD | 16/01/2023 | 0 | Resource Division | 27.79 | 0 | 0
3161 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775287/QUOT/03 DT. 14-06-2024 Application NO- 2004775287 MEMO NO: AMR/PHE/176 DT.14/06/2024 Application type-New connection Consumer Id- 204330587 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01332/2024-2025 | BP-2024-25-354 | 01/07/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
3162 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609871/QUOT/03 DT. 21-02-2024 Application NO- 2004609871 Application type-New connection Reference Id- 204223251 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04392/2023-2024 | BP-2023-24-821 | 13/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
3163 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAIPUR and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001317/2022-2023 | 2319/W/MMD | 29/12/2022 | 824 | SOUMEN ELECTRIC | 22.78 | 16.14 | 90
3164 | Tamluk Division | Tamluk Sadar Sub-Division | Estimate for against damage of road flank/hard shoulder due to cutting of hard shoulder and road flank on Bhabanipur-Thekuabazar Road from 5.00 km to 7.00 km for laying of water pipe kline by PHE Department. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00232/2023-2024 | BP-2023-24-117 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.76 | 0 | 0
3165 | Tamluk Division | Tamluk Sadar Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00699/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.52 | 0 | 0
3166 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-57 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01499/2023-2024 | BP-2023-24-661 | 15/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.28 | 0 | 0
3167 | Tamluk Division | Tamluk Sadar Sub-Division | Way Leave permission from South Eastern Railway for Jalpai PWSS for Application ID-SER-KGP-2023-WL-59 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01829/2023-2024 | BP-2023-24-823 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 4.98 | 0 | 0
3168 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Jalpai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000018/2022-2023 | 52/TD | 05/04/2022 | 20 | HORIZEN | 5.57 | 5.56 | 100
3169 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 5th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000068/2023-2024 | 137/TD | 10/04/2023 | 40 | GRAND CONSTRUCTION | 5.1 | 0 | 0
3170 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai Sater Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000278/2022-2023 | 1114/TD | 29/08/2022 | 25 | SUDIPTA ROY | 75.72 | 48.16 | 65
3171 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000279/2022-2023 | 1115/TD | 29/08/2022 | 778 | CHANDIMATA CONSTRUCTION | 72.07 | 48.92 | 90
3172 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000280/2022-2023 | 1116/TD | 29/08/2022 | 25 | SHAKEEL KHAN | 74.47 | 51.09 | 80
3173 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(260 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000281/2022-2023 | 1117/TD | 29/08/2022 | 20 | ADHIKARY CONSTRUCTION | 42.21 | 23.02 | 60
3174 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000283/2022-2023 | 1118/TD | 29/08/2022 | 25 | NARAYAN CHANDRA DAS | 76.58 | 72.03 | 80
3175 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000284/2022-2023 | 1119/TD | 29/08/2022 | 25 | S.D. CONSTRUCTION | 70.82 | 43.92 | 70
3176 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000285/2022-2023 | 1120/TD | 29/08/2022 | 999 | FARID UDDIN AHMED | 65.7 | 41.04 | 91
3177 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(200 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000286/2022-2023 | 1121/TD | 29/08/2022 | 25 | KRISHNENDU SEKHAR DAS | 78.19 | 64.98 | 85
3178 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000287/2022-2023 | 1122/TD | 29/08/2022 | 20 | SK SANAMAJ | 56.8 | 53.04 | 100
3179 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000288/2022-2023 | 1123/TD | 29/08/2022 | 840 | BHOLANATH DEY | 57.72 | 52.02 | 96
3180 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-O) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000289/2022-2023 | 1124/TD | 29/08/2022 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.12 | 55.6 | 100
3181 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-Q) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000290/2022-2023 | 1125/TD | 29/08/2022 | 20 | S. N. A. CONSTRUCTION | 46.55 | 41.84 | 99
3182 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-R) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000291/2022-2023 | 1126/TD | 29/08/2022 | 15 | SAYAN MAITY | 9.94 | 7.85 | 80
3183 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-S) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000292/2022-2023 | 1127/TD | 29/08/2022 | 15 | OM UDYOG | 9.85 | 7.78 | 100
3184 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-P) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000293/2022-2023 | 1128/TD | 29/08/2022 | 20 | AQUATECH ENGINEERS | 45.31 | 35.25 | 85
3185 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2022-2023 | 1129/TD | 29/08/2022 | 1356 | S.K. MONDAL | 72.41 | 53.12 | 75
3186 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(330 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000295/2022-2023 | 1130/TD | 29/08/2022 | 25 | RELIABLE CONSTRUCTIONS | 72.71 | 51.83 | 75
3187 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000296/2022-2023 | 1131/TD | 29/08/2022 | 25 | DILIP KUMAR GHOSH | 73.9 | 50.08 | 99
3188 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000664/2022-2023 | 2349/TD | 10/01/2023 | 40 | RAI CONSTRUCTION | 5.06 | 2.88 | 10
3189 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Distribution pipe line to accommodate FHTC(3600 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Jalpai Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000385/2022-2023 | 1386/TD | 23/09/2022 | 180 | M/S. CARE | 454 | 191.81 | 30
3190 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 15.9 | 45
3191 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000665/2022-2023 | 2350/TD | 10/01/2023 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 5.06 | 0 | 0
3192 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000091/2022-2023 | 1374/TD | 23/09/2022 | 0 | Resource Division | 48.52 | 0 | 0
3193 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000113/2022-2023 | 1672/TD | 03/11/2022 | 0 | Resource Division | 373.53 | 0 | 0
3194 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000205/2023-2024 | 1104/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
3195 | Central Drilling | Tamluk Sadar Sub-Division | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Driller in charge, CMSD-II(D), CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000003/2023-2024 | 107/CMSD-II | 27/04/2023 | 184 | ASHUTOSH PAL | 0.87 | 2.21 | 33
3196 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR JAIPAI W/S SCHEME (TW-I), NANDAKUMAR BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000414/2022-2023 | 1637/CDD | 20/12/2022 | 30 | DEY ENTERPRISE | 19.2 | 17.23 | 0
3197 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For New Service Connection at TW-IV of Jalpai PWSS under MMD PHE Dte.,Block-Nandakumar C.C.C.-Na Contract Demand-12000Wndakumar Application no.-2004653153 Application Type-New Connection Quotation Date-28/03/2024 Quotation Due Date-28/03/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00252/2024-2025 | BP-2024-25-26 | 15/04/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
3198 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Jalpai W/S scheme TW-III Application No.-2004554813 Ref.-204184634 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03346/2023-2024 | BP-2023-24-576 | 18/01/2024 | 0 | WBSEDCL | 3.46 | 0 | 0
3199 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at JALPAI Water supply scheme,T/W - V, NANDAKUMAR block, District ¿ Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000390/2024-2025 | 2006/W/MMD | 30/08/2024 | 180 | M/S EMMESS | 14.12 | 0 | 0
3200 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipment's for augmentation of ground water based Jaipai w/s scheme under JJM Program under Medinipur Mechanical Division P.H.E Dte. In the dist of PurbaMedinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000427/2023-2024 | 580/HESD | 04/08/2023 | 7 | BHABANI PRASAD MANNA | 0.39 | 0 | 0
3201 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water based Jalpai Water Supply Scheme, Block ¿ Nanda Kumar, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001512/2022-2023 | 356/W/MMD | 09/03/2023 | 180 | BHABANI PRASAD MANNA | 40.78 | 25.4 | 60
3202 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC (400 nos),Construction of switch room cum cholorine room , Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000139/2023-2024 | 280/TD | 20/04/2023 | 1176 | S.K. MONDAL | 87.98 | 45.71 | 55
3203 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & Construction of RCC Over Head of capacity 200 cum and staging height 20.00 mtr as per Deptt. Drawing ( Intze type with pile foundation), under JJM with allied work for Nilkanthia_PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division,PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000140/2023-2024 | 281/TD | 20/04/2023 | 180 | HARIPADA PATTANAYAK | 93.35 | 0 | 0
3204 | Tamluk Division | Tamluk Sadar Sub-Division | Land development at Head work site of Nilkunthia water supply scheme within Tamluk Block under Tamluk Sub-Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000374/2024-2025 | 1608/TSD | 28/10/2024 | 42 | TARUN KHATUA | 2.07 | 0 | 100
3205 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC (877 nos),Construction of switch room cum cholorine room , Laying of rising main, Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000392/2023-2024 | 1065/TD | 08/06/2023 | 1012 | SUDIPTA ROY | 123.48 | 27.8 | 26
3206 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 250 x 150 mm Dia and 230m deep tubewell ( at 2nd tube well site) Drilling by Direct Rotary method with 150 dia. UPVC. Strainer of 30m.length all complete including cost of materials for Nilkunthia Water Supply Scheme under Tamluk Block under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000578/2024-2025 | 456/TD | 04/02/2025 | 20 | PRANTIK DRILLING AGENCY | 12.58 | 0 | 0
3207 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000300/2022-2023 | 3006/TD | 27/02/2023 | 0 | Resource Division | 16.01 | 0 | 0
3208 | Central Drilling | Tamluk Sadar Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 36.48 | 11
3209 | Central Drilling | Tamluk Sadar Sub-Division | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000009/2024-2025 | 138/S&WSD | 26/06/2024 | 182 | NAGENDRA PATRA | 0.86 | 2.15 | 0
3210 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Nilkunthia W/S Scheme T/W-I Application No=2004684512 Reference ID=204275851 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00576/2024-2025 | BP-2024-25-102 | 26/04/2024 | 0 | WBSEDCL | 4.02 | 0 | 0
3211 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For Nilkanthia W/S Scheme T/W-II Tamluk CCC Application No=2005063385 Reference ID=204509892 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04507/2024-2025 | C032587405841 | 27/03/2025 | 0 | WBSEDCL | 5.97 | 0 | 0
3212 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHIA AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001695/2022-2023 | 622/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 0 | 0
3213 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mathura PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2024-2025 | 2200/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3214 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 162.33 | 51
3215 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000051/2024-2025 | 1659/TD | 29/04/2024 | 0 | Resource Division | 13.37 | 0 | 0
3216 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000154/2022-2023 | 2460/TD | 16/01/2023 | 0 | Resource Division | 41.71 | 0 | 0
3217 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MATHURA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2005088012/QUOT/03/1056 DT. 20-02-2025 Application NO- 2005088012 Application type-New connection Consumer Id- 204528860 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00706/2025-2026 | W/267/25-26 | 07/08/2025 | 0 | WBSEDCL | 4.76 | 0 | 0
3218 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MATHURA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811805/QUOT/03 DT. 11-07-2024 Application NO- 2004811805 Application type-New connection Consumer Id- 204351926 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01978/2024-2025 | C082420136916 | 14/08/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
3219 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MATHURA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001688/2022-2023 | 561/W/MMD | 20/03/2023 | 180 | M/S B.M. ELECTRICAL | 22.81 | 3.13 | 62
3220 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 840 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000256/2023-2024 | 538/TD | 12/05/2023 | 1007 | GIRI CONSTRUCTION | 199.43 | 0 | 90
3221 | Tamluk Division | Digha Sub-Division | Land development of 2nd T/W Site at Kadua & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000307/2024-2025 | 892/DSD | 02/09/2024 | 7 | GIRI CONSTRUCTION | 1.85 | 0 | 0
3222 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 70 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part - E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000483/2023-2024 | 1533/TD | 18/07/2023 | 20 | HYDROTECH ASSOCIATES | 9.99 | 5.4 | 60
3223 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 81 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - D ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000624/2023-2024 | 2363/TD | 12/09/2023 | 463 | KESHOB ENTERPRISE | 19.96 | 15 | 100
3224 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( Intze type with pile foundation ) & Accommodate FHTC ( 900Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000628/2023-2024 | 2436/TD | 19/09/2023 | 1011 | BIDHAN MONDAL | 246.91 | 67.82 | 45
3225 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (261Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000916/2022-2023 | 3553/TD | 29/03/2023 | 808 | MRINAL KANTI PRADHAN | 84.53 | 69.26 | 100
3226 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000146/2023-2024 | 125/TD | 05/01/2024 | 0 | Resource Division | 13.24 | 0 | 0
3227 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000216/2022-2023 | 2691/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0
3228 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 58.13 | 11
3229 | Central Drilling | Digha Sub-Division | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000032/2024-2025 | 124/CMSD-II(D) | 27/06/2024 | 182 | DILIP KAR | 0.86 | 2.06 | 0
3230 | Central Drilling | Digha Sub-Division | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000053/2024-2025 | 294/CMSD-II(D) | 30/12/2024 | 182 | DILIP KAR | 0.86 | 2.08 | 0
3231 | Central Drilling | Digha Sub-Division | Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000190/2023-2024 | 264/CMSD-II(D) | 15/12/2023 | 183 | DILIP KAR | 0.86 | 2.08 | 70
3232 | Midnapore Mechanical | Digha Sub-Division | Kadua W/S scheme PH-I Application No.-2004550666 Ref.-204181244 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03292/2023-2024 | BP-2023-24-539 | 11/01/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
3233 | Midnapore Mechanical | Digha Sub-Division | Kadua W/S scheme PH-II Application No.-2004550634 Ref.-204181242 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03293/2023-2024 | BP-2023-24-538 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0
3234 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC (7 Nos) under JJM with allied work for Chirulia-Chatla (Zone-II) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000262/2023-2024 | 542/TD | 12/05/2023 | 60 | SUBHENDU HAZRA | 71.29 | 60.07 | 93
3235 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house at 2nd T/W site of Chirulia Chatla Zone-II Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000613/2024-2025 | 463/TD | 04/02/2025 | 120 | RADHAKRISHNA TRADERS | 7.79 | 0 | 100
3236 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000966/2022-2023 | 1056/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100
3237 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
3238 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 125.85 | 51
3239 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000030/2024-2025 | 1634/TD | 18/06/2025 | 0 | Resource Division | 6.41 | 0 | 0
3240 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000143/2022-2023 | 2448/TD | 16/01/2023 | 0 | Resource Division | 26.2 | 0 | 0
3241 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743601/QUOT/03 DT. 20-05-2024 Application NO- 2004743601 Application type-New connection Consumer Id- 204312616 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01204/2024-2025 | BP-2024-25-322 | 24/06/2024 | 0 | WBSEDCL | 5.12 | 0 | 0
3242 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769788/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769788 Application type-New connection Consumer Id- 204327232 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01280/2024-2025 | BP-2024-25-339 | 25/06/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
3243 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KULRAKHI AND IT'S ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001706/2022-2023 | 592/W/MMD | 20/03/2023 | 180 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0
3244 | Tamluk Division | Haldia Sub-Division | Land development of ditch and Approach Road with Box Culvert at 3rd T.W. site of Barsundra Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000104/2023-2024 | 214/TD | 17/04/2023 | 30 | BISWANATH BHUNIA | 16.31 | 0 | 0
3245 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line with inter connection ,Supply of DI Specials, at Head Work Site at Barsundara Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000234/2024-2025 | 2698/TD | 22/08/2024 | 25 | ANIRBAN BHOWMIK | 10.21 | 0 | 0
3246 | Tamluk Division | Haldia Sub-Division | Construction new Boundary Wall at Head Work Site of BARSUNDRA Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Length - 225.00 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000235/2024-2025 | 2697/TD | 22/08/2024 | 191 | ANIRBAN BHOWMIK | 19.92 | 10.54 | 50
3247 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room without water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000255/2024-2025 | 2841/TD | 05/09/2024 | 240 | PRASANTA MONDAL | 5.11 | 0 | 90
3248 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 40.74 | 75
3249 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Barsundra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000437/2021-2022 | 1518/TD | 07/01/2022 | 20 | RADIANT | 4.5 | 4.5 | 100
3250 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Pump House No. "1" & Pump House No.- "2" at Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000650/2023-2024 | 2616/TD | 11/10/2023 | 444 | GUCHHAIT ENTERPRISE | 6 | 4.69 | 80
3251 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000823/2023-2024 | 3285/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.93 | 3.64 | 30
3252 | Tamluk Division | Haldia Sub-Division | New Construction of boundary wall at 3rd T/W site (50mt) of Barsundra water supply scheme under Haldia Sub-Division PHE Dte.. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000829/2022-2023 | 3168/TD | 10/03/2023 | 749 | M/S SOURAV MAHAPATRA | 6.26 | 0 | 100
3253 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Barsundra PWSS, Betkundu PWSS, Baramrit Beria PWSS, Amritberya PWSS) (Phase-VII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001172/2023-2024 | 768/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100
3254 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barsundra Water Supply Scheme by providing Laying of Distribution to accommodate FHTC (5920 Nos),construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. with allied works within Haldia Dev.Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000776/2022-2023 | 2860/TD | 17/02/2023 | 865 | TAPAS SANTRA | 900.87 | 651.29 | 73
3255 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000067/2023-2024 | 2643/TD | 13/10/2023 | 0 | Resource Division | 36.47 | 0 | 0
3256 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000231/2022-2023 | 2611/TD | 02/02/2023 | 0 | Resource Division | 118.88 | 0 | 0
3257 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for shifting of PHE meter room with allied works at PH-I of Barsundra w/s scheme under MMD PHE Dte. Name of C.C.C.-Brajalalchak Reference ID-860311526 Application ID-100000117246 Quotation Date-27/08/2024 Quotation Due Date-25/11/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02393/2024-2025 | C092404597616 | 05/09/2024 | 0 | WBSEDCL | 1.38 | 0 | 0
3258 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical Equipments for Augmentation of Ground Water Based BarSundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000124/2023-2024 | 1344/W/MMD | 24/05/2023 | 712 | THE GODFATHER TRADING COMPANY | 26.94 | 20.24 | 60
3259 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme, Block ¿ Haldia, District - Purba Medinipur under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001545/2022-2023 | 396/W/MMD | 15/03/2023 | 180 | BALAJI CONSTRUCTION | 12.4 | 11.59 | 60
3260 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Rejuvenation of elctro-mechanical components of Barsundra PWSS in the district of purba medinipur district under JJM program,Block-Haldia,under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001560/2023-2024 | 951/HESD | 30/11/2023 | 7 | BALAJI CONSTRUCTION | 0.69 | 0.54 | 100
3261 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges (SER-KGP-2024-WL-45) | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00133/2024-2025 | BP-2024-25-76 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0
3262 | Tamluk Division | Contai Sub-Division | Quotation money for shifting of 11 KV OH Henria Feeder at Najir Bazar for Bajukl Zone-III PWSS under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01685/2023-2024 | BP-2023-24-743 | 04/01/2024 | 0 | WBSEDCL | 2.63 | 0 | 0
3263 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track from station deshpran and henria of augmentation of Bajkul Zone-III piped Water Supply Scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 29/18 to mast no 29/19 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000119/2024-2025 | 1915/TD | 07/06/2024 | 208 | ROY CONSTRUCTION | 61.73 | 0 | 100
3264 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between DESHPRAN-HENRIA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Bajkul Zone-III Piped Water Supply Scheme in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000148/2024-2025 | 1730/CSD | 20/06/2024 | 20 | BIBEKANANDA DAS | 1.16 | 0 | 100
3265 | Tamluk Division | Contai Sub-Division | Pump House, Boundary Wall and others allied works for 3rd Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000198/2024-2025 | 2322/TD | 23/07/2024 | 320 | M/S S M H CONSTRUCTION | 10.68 | 0 | 100
3266 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Bajkul Zone-III Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000240/2024-2025 | 2679/TD | 22/08/2024 | 160 | SWARUPANANDA DAS | 83.59 | 0 | 0
3267 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000318/2022-2023 | 598/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.72 | 4.71 | 100
3268 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC (4683 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - III Water Supply Scheme within Bhagabanpur- I &II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000540/2023-2024 | 1887/TD | 09/08/2023 | 1051 | DAS ENTERPRISE | 779.24 | 266.54 | 50
3269 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 600 cum RCC OHR at Bajkul Zone-III PWSS at Bhagwanpur-I & II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001053/2023-2024 | 383/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3270 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 225 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube well of Bajkul Zone-III Water Supply Scheme within Bhagwanpur-I & II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001157/2023-2024 | 608/TD | 16/02/2024 | 20 | B. K. ENTERPRISE | 17.8 | 0 | 0
3271 | Tamluk Division | Contai Sub-Division | Repair and renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001184/2023-2024 | 724/TD | 28/02/2024 | 40 | PARTHA CONSTRUCTION | 10.65 | 0 | 0
3272 | Tamluk Division | Contai Sub-Division | Repair and renovation and others allied works of Pump House, Boundary Wall for 2nd. Tube well site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001246/2023-2024 | 1077/TD | 16/03/2024 | 529 | M/S. S. A. CONSTRUCTION | 9.84 | 0 | 100
3273 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 32.14 | 90
3274 | Tamluk Division | Contai Sub-Division | Pump House, Boundary Wall and others allied works for 4th Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001248/2023-2024 | 1076/TD | 16/03/2024 | 556 | M/S. S. A. CONSTRUCTION | 11.22 | 0 | 90
3275 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000065/2023-2024 | 2641/TD | 13/10/2023 | 0 | Resource Division | 28.85 | 0 | 0
3276 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000234/2022-2023 | 2612/TD | 02/02/2023 | 0 | Resource Division | 210.83 | 0 | 0
3277 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-IV, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606750/QUOT/03/424 DT. 19-02-2024 Application NO- 2004606750 Application type-New connection Reference Id- 204221087 | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04140/2023-2024 | BP-2023-24-761 | 01/03/2024 | 0 | WBSEDCL | 2.62 | 0 | 0
3278 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606772/QUOT/03/426 DT. 19-02-2024 Application NO- 2004606772 Application type-New connection Reference Id- 204221105 | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04141/2023-2024 | BP-2023-24-760 | 01/03/2024 | 0 | WBSEDCL | 2.86 | 0 | 0
3279 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III, Block Bhagawanpur II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000081/2023-2024 | 1275/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 37.71 | 22.94 | 76
3280 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone III Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002722/2023-2024 | 1067/W/MMD | 14/03/2024 | 360 | DEBJYOTI BASU | 25.9 | 0 | 55
3281 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 11.35 | 75
3282 | Tamluk Division | Contai Sub-Division | Re- Laying od different dia. UPVC Pipe and Constrution of Boundary wall (as per Departmental Design & Drawing),Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000112/2023-2024 | 242/TD | 19/04/2023 | 45 | SUBRATA KUMAR BERA | 30.48 | 17.76 | 60
3283 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Augmentation of Barchunfali W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000215/2023-2024 | 479/TD | 10/05/2023 | 60 | SAURAV HAZRA | 3.6 | 0 | 0
3284 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well for Augmentatuion of Barchunfali & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000216/2023-2024 | 478/TD | 10/05/2023 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.38 | 0 | 0
3285 | Tamluk Division | Contai Sub-Division | Laying of different dia UPVC pipe line to accommodate 70 Nos FHTC to make Benipur Mouza, Chuaphali, Ghata, Hugli, Khikina & Subdi mouzas as Swajal Gram of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000523/2022-2023 | 2095/TD | 13/12/2022 | 20 | M/S UNIQUE. | 7.92 | 6.38 | 100
3286 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000011/2023-2024 | 342/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
3287 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of BARCHUNFALI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004877553/QUOT/03 DT. 29-08-2024 Application NO- 2004877553 Application type-New connection Consumer Id- 204387021 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02397/2024-2025 | C092406568982 | 06/09/2024 | 0 | WBSEDCL | 6.02 | 0 | 0
3288 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001998/2022-2023 | 893/W/MMD | 27/03/2023 | 180 | SUDIKSHA CONSTRUCTION | 11.83 | 0 | 0
3289 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (80 Nos) under JJM with allied work for Dakshin Kalyanpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000423/2024-2025 | 3474/TD | 06/11/2024 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.7 | 0 | 0
3290 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 50 Cum OHR & Accommodate FHTC ( 236 Nos) under JJM with allied work for DAKSHIN KALYANPUR & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000521/2023-2024 | 1758/TD | 01/08/2023 | 1033 | PREMANANDA ROY BISWAS | 164.16 | 75.61 | 40
3291 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 50 cum RCC OHR at Dakshin Kalyanpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001049/2023-2024 | 379/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3292 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000126/2023-2024 | 132/TD | 05/01/2024 | 0 | Resource Division | 1.45 | 0 | 0
3293 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000304/2022-2023 | 3001/TD | 27/02/2023 | 0 | Resource Division | 9.75 | 0 | 0
3294 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004671005/QUOT/03 DT. 05-04-2024 Application NO- 2004671005 Application type-New connection Consumer Id- 204268105 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00297/2024-2025 | BP-2024-25-47 | 18/04/2024 | 0 | WBSEDCL | 2.16 | 0 | 0
3295 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005055401/QUOT/03 DT. 20-05-2025 Application NO- 2005055401 Application type-New connection Consumer Id- 204268105 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00896/2025-2026 |  | 30/05/2025 | 0 | WBSEDCL | 2.43 | 0 | 0
3296 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001749/2022-2023 | 604/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.95 | 5.39 | 45
3297 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 98 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000109/2024-2025 | 1903/TD | 07/06/2024 | 25 | SOUMYA ENTERPRISE | 53.79 | 0 | 65
3298 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000330/2023-2024 | 740/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.49 | 3.48 | 100
3299 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 267 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000519/2023-2024 | 1756/TD | 01/08/2023 | 910 | SUSIL KUMAR HAZRA | 193.96 | 0 | 40
3300 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-III PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001044/2023-2024 | 374/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3301 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000045/2023-2024 | 2075/TD | 28/08/2023 | 0 | Resource Division | 14.02 | 0 | 0
3302 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000095/2023-2024 | 2998/TD | 29/11/2023 | 0 | Resource Division | 1.64 | 0 | 0
3303 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-3, TW-II OF SHANKARPUR WS SCHEME UNDER MMD, PHE DTE, BLOCK-RAMNAGAR -1, DIGHA CCC APP. NO-2004746394 CON ID-204313991 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01143/2024-2025 | BP-2024-25-257 | 06/06/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
3304 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I , ZONE-III Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-I, DIGHA C.C.C. Ref. Memo No- 2004626526/QUOT/03 DT. 04-03-2024 Application NO- 2004626526 Application type-New connection Consumer Id- 204233340 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04341/2023-2024 | BP-2023-24-809 | 11/03/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
3305 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF FEBRUARY'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04354/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.16 | 0 | 0
3306 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF FEBRUARY '2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04366/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.17 | 0 | 0
3307 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000040/2023-2024 | 1211/W/MMD | 25/04/2023 | 1660 | S.S.GHORAI | 23.52 | 14.1 | 75
3308 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
3309 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (172 nos) under JJM with allied work for Panchrol PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000113/2023-2024 | 243/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 61.6 | 28.15 | 50
3310 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-III of Panchrol W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746343 Consumer ID.-204313789 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01140/2024-2025 | BP-2024-25-251 | 06/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
3311 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF DECEMBER'2023 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04352/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.24 | 0 | 0
3312 | Midnapore Mechanical | Digha Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF DECEMBER'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04364/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.22 | 0 | 0
3313 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
3314 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001994/2022-2023 | 899/W/MMD | 27/03/2023 | 720 | M/S EMMESS | 12.63 | 8.28 | 90
3315 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (239 nos) under JJM with allied work for Bheribaranga PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2023-2024 | 247/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 66.11 | 11.35 | 75
3316 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at tw-III of Bheribaranga ws under MMD,PHE Dte ,Block-Ramnagar-II. Digha CCC Application no-2004764489 CON ID-204324289 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01225/2024-2025 | BP-2024-25-290 | 18/06/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
3317 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001990/2022-2023 | 897/W/MMD | 27/03/2023 | 720 | A.S.ENTERPRISE | 12.62 | 0 | 75
3318 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (Phase-II) under JJM in DULALPUR PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 245/TD | 19/04/2023 | 30 | AYSAN KHAN | 25.68 | 25.66 | 100
3319 | Tamluk Division | Digha Sub-Division | Schedule for retrofitting to accommodate FHTC under JJM in DULALPUR PWSS within Egra-II Block under DighaSub-Division of Tamluk Division,P HE Dte. in the District of Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 246/TD | 19/04/2023 | 560 | AYSAN KHAN | 5.16 | 0 | 100
3320 | Tamluk Division | Digha Sub-Division | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-III) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000274/2024-2025 | 2901/TD | 10/09/2024 | 20 | GHOSH ENTERPRISE | 8.84 | 0 | 100
3321 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000462/2022-2023 | 1861./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.89 | 100
3322 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (55 nos) under JJM with allied work for Bathuari (Zone-III) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000525/2023-2024 | 1761/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 261.16 | 58.13 | 80
3323 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000049/2023-2024 | 2072/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0
3324 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000100/2023-2024 | 3003/TD | 29/11/2023 | 0 | Resource Division | 0.34 | 0 | 0
3325 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARHUARY ZIII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004737554/QUOT/03 DT. 16-05-2024 Application NO- 2004737554 Application type-New connection Consumer Id- 204309058 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01227/2024-2025 | BP-2024-25-292 | 18/06/2024 | 0 | WBSEDCL | 3.27 | 0 | 0
3326 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, Zone-III Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004793307/QUOT/03/380 DT. 02-07-2024 Application NO- 2004793307 Application type-New connection Consumer Id- 204346846 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01698/2024-2025 | BP-2024-25-497 | 31/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
3327 | Midnapore Mechanical | Digha Sub-Division | Additional Quotation Bill for Extension of LTOH Line with Additional 2 nos PCC POLES for shifting the meter to meter room at T/W NO-I, ZONE-III Of BATHUARY W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No-BLG CCC/QUOTATION/1186 DT. 12-03-2025 Application NO- 100000132257 DT. 12-03-2025 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860328257 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04972/2024-2025 | 42156 | 07/08/2025 | 0 | WBSEDCL | 0.54 | 0 | 0
3328 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
3329 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000331/2023-2024 | 741/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100
3330 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 294 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000510/2023-2024 | 1732/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 216.84 | 69.71 | 55
3331 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line Due to Re-design & Accommodate Balance FHTC ( 125 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000513/2024-2025 | 3943/TD | 23/12/2024 | 80 | ONKAR ENTERPRISE | 32.85 | 0 | 100
3332 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Z-IV PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001281/2023-2024 | 1053/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3333 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000047/2023-2024 | 2070/TD | 28/08/2023 | 0 | Resource Division | 14.46 | 0 | 0
3334 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000096/2023-2024 | 2999/TD | 29/11/2023 | 0 | Resource Division | 1.81 | 0 | 0
3335 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme TW no.-I, Z-IV Ref.-204156071 Application ID-2004521698 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03156/2023-2024 | BP-2023-24-442 | 19/12/2023 | 0 | WBSEDCL | 2.63 | 0 | 0
3336 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme PH.-II, zone-IV Application No.-2004565718 Ref.-204193727 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03540/2023-2024 | BP-2023-24-622 | 07/02/2024 | 0 | WBSEDCL | 7.26 | 0 | 0
3337 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-IV in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000041/2023-2024 | 1212/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 23.93 | 22.24 | 90
3338 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001842/2022-2023 | 759/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.23 | 5.82 | 35
3339 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 15.68 | 100
3340 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side of 1st. Boosting T/W site at Paramanandapur W/S scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000136/2024-2025 | 858/TSD | 05/06/2024 | 20 | ANIRBAN BHOWMIK | 1.69 | 0.45 | 100
3341 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2023-2024 | 359/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
3342 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connetion at Paramanadapur w/s scheme additional TW No.- III in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004979492, Con ID 204456223) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03661/2024-2025 | C012525524697 | 10/01/2025 | 0 | WBSEDCL | 13.8 | 0 | 0
3343 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000039/2023-2024 | 1208/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.44 | 7.08 | 50
3344 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,400 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2897 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GURGRAM PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000501/2023-2024 | 1689/TD | 26/07/2023 | 717 | TARUN KOLEY | 894.96 | 603.82 | 69
3345 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000139/2023-2024 | 121/TD | 05/01/2024 | 0 | Resource Division | 17.85 | 0 | 0
3346 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000192/2022-2023 | 2381/TD | 16/01/2023 | 0 | Resource Division | 75.63 | 0 | 0
3347 | Midnapore Mechanical | Contai Sub-Division | Gurgram W/S scheme PH-II,(River Side) Application No.-2004523993 Ref.-204157866 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03175/2023-2024 | BP-2023-24-475 | 27/12/2023 | 0 | WBSEDCL | 9.17 | 0 | 0
3348 | Midnapore Mechanical | Contai Sub-Division | Gurgram W/S scheme PH-I,(Primary School) Application No.-2004523960 Ref.-204157826 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03176/2023-2024 | BP-2023-24-476 | 27/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
3349 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GURGRAM & ADJOINING MOUZAS, Block- Bhagwanpur I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2023-2024 | 1628/W/MMD | 25/07/2023 | 180 | ALPHA ENTERPRISE | 23.68 | 23.17 | 80
3350 | Tamluk Division | Contai Sub-Division | Pump House , Laying distribution pipe line, Boundary Wall & Accommodate FHTC (1170 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000325/2023-2024 | 687/TD | 23/05/2023 | 1214 | RELIABLE CONSTRUCTIONS | 241.87 | 121.98 | 52
3351 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000845/2022-2023 | 00/TD | 10/03/2023 | 180 | SRIMANTA KUMAR MAITY | 0 | 0 | 0
3352 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 480 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000846/2022-2023 | 3189/TD | 10/03/2023 | 997 | SRIMANTA KUMAR MAITY | 67.29 | 30.57 | 50
3353 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (83 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000847/2022-2023 | 3190/TD | 10/03/2023 | 1177 | KAMAL KUMAR BERA | 19.35 | 11.42 | 75
3354 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000853/2023-2024 | 139/TD | 05/01/2024 | 661 | SRIMANTA KUMAR MAITY | 242.35 | 53.69 | 45
3355 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of URURI- PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001147/2023-2024 | 567/TD | 15/02/2024 | 835 | KAMAL KUMAR BERA | 5.66 | 4.02 | 80
3356 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Ururi, Garabar, Itaberia & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001168/2023-2024 | 2328/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0.62 | 100
3357 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000119/2022-2023 | 2387/TD | 16/01/2023 | 0 | Resource Division | 23.22 | 0 | 0
3358 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000179/2023-2024 | 628/W | 20/02/2024 | 0 | Resource Division | 13.76 | 0 | 0
3359 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 53.38 | 11
3360 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of URURI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004570649/QUOT/03 DT. 22-01-2024 Application NO- 2004570649 Application type-New connection Consumer Id- 204198017 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01133/2024-2025 | BP-2024-25-249 | 06/06/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
3361 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Under URURI W/S Scheme under MMD,PHE,Dte. Ref. Quotation no- 2004558742/Quot/03 dt. 10- Jan-24 quotation Due date- 09-Jan-25 Application NO- 2004558742 Application type-New connection Reference Id- 204188975 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03657/2023-2024 | BP-2023-24-676 | 15/02/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
3362 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
3363 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3364 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House , Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1324 nos), Including 2 years of operation maintance under JJM with allied work for Taladiha PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2023-2024 | 1093/TD | 08/06/2023 | 1056 | SUJATA CONSTRUCTION | 373.7 | 66.61 | 21
3365 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000040/2024-2025 | 1627/TD | 18/06/2025 | 0 | Resource Division | 8.16 | 0 | 0
3366 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000258/2022-2023 | 2705/TD | 06/02/2023 | 0 | Resource Division | 51.54 | 0 | 0
3367 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TALADIHA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004969351/QUOT/03 DT. 18-11-2024 MEMO NO: AMR/PHE/512 DT. 18-11-2024 Application NO- 2004969351 Application type-New connection Consumer Id- 204448691 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03064/2024-2025 | C112433888301 | 27/11/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
3368 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALADIHA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001403/2022-2023 | 2414/W/MMD | 31/12/2022 | 1924 | ECO ENTERPRISE | 22.8 | 11.71 | 40
3369 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Gopinathpur PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000224/2023-2024 | 457/TD | 04/05/2023 | 822 | TAPAS SANTRA | 588.58 | 387.98 | 85
3370 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000137/2023-2024 | 130/TD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
3371 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000239/2022-2023 | 2728/TD | 06/02/2023 | 0 | Resource Division | 36.99 | 0 | 0
3372 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-I, (Ref. ID-204089465) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02886/2023-2024 | BP-2023-24-310 | 01/11/2023 | 0 | WBSEDCL | 3.57 | 0 | 0
3373 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-II, (Ref. ID-204089466) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02887/2023-2024 | BP-2023-24-319 | 01/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
3374 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOPINATHPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002031/2022-2023 | 939/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 23.67 | 21.89 | 100
3375 | Tamluk Division | Contai Sub-Division | Sinking of Big dia Tube Well, Laying distribution System, Construction of Pump House, Construction of Boundary Wall, Soil investigation, R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation), Accommodate FHTC (1656 nos) & Two years Operation & Maintenance with allied works under JJM for Dwarikapur & It's Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000075/2023-2024 | 128/TD | 10/04/2023 | 628 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 407.28 | 0 | 0
3376 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000131/2023-2024 | 85/TD | 05/01/2024 | 0 | Resource Division | 10.2 | 0 | 0
3377 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000194/2022-2023 | 2386/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0
3378 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DWARIKAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL C.C.C. : BHAGWANPUR C.C.C. Ref. Memo No- 2005232943/QUOT/03 DT. 21-05-2025 Application NO- 2005232943 Application type-New connection CONSUMER ID: 204628898 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/01392/2025-2026 |  | 12/06/2025 | 0 | WBSEDCL | 7.77 | 0 | 0
3379 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DWARIKAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001408/2022-2023 | 2419/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.76 | 0 | 0
3380 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line (Left out), Repair and Renovation Pump House, Boundary Wall , 450 Cum OHR & Accommodate Balance FHTC ( 65 Nos) under JJM with allied work for KANPUR (Zone-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000237/2024-2025 | 2676/TD | 22/08/2024 | 45 | MAITY CONSTRUCTION | 87.84 | 0 | 0
3381 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Accommodate FHTC ( 69 Nos) under JJM with allied work for KANPUR (Z-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000611/2023-2024 | 2255/TD | 05/09/2023 | 60 | BASANTA KUMAR MAITY | 85.65 | 60.27 | 60
3382 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000967/2022-2023 | 1057/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 2.95 | 100
3383 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000039/2023-2024 | 2081/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
3384 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000110/2023-2024 | 3013/TD | 29/11/2023 | 0 | Resource Division | 0.43 | 0 | 0
3385 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
3386 | Midnapore Division | Kharagpur Sub-Division | Supplying, laying of 9 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 9 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination &Sanitary Arrangement, Boundary Wall, Service Road for 50 M length, Improvement of Land for each site, Renovation of 4 nos. Existing OHRs. surface Drain, Campus lighting & other provisional works etc for Pingla Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation& Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000837/2023-2024 | 801/MD | 15/03/2024 | 915 | G B CONSTRUCTION & UMWELT JV | 7243.56 | 895.75 | 10
3387 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | RTOR000002/2024-2025 | 2240/MD | 22/07/2024 | 0 | Resource Division | 237.7 | 0 | 0
3388 | Tamluk Division | Kharagpur Sub-Division | Payment of Way leave plan & Survey Charges for Application ID SER-KGP-2025-WL-13 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | BILL/00207/2025-2026 | 142/W | 18/07/2025 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.02 | 0 | 0
3389 | Tamluk Division | Kharagpur Sub-Division | Payment of Way leave plan & Survey Charges for Application ID SER-KGP-2025-WL-14 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | BILL/00208/2025-2026 | 142/W | 18/07/2025 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.85 | 0 | 0
3390 | Tamluk Division | Kharagpur Sub-Division | Supplying, laying of 22 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 25 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination & Sanitary Arrangement, Boundary Wall, Service Road for 50 M length & Improvement of Land for each site, surface Drain, Campus lighting & other provisional works etc for Panskura Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000183/2024-2025 | 2258/TD | 16/07/2024 | 1826 | M/S ANAND SINGH | 18090.51 | 0 | 5
3391 | Tamluk Division | Kharagpur Sub-Division | Surveying, Designing, Engineering, Supplying, Construction, Erectioning, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House connected by RCC carriageway with the river bank, 70 MLD capacity conventional type Water Treatment Plant, Raw Water Rising Mains, Bank protection, Substation Building for Intake and WTP, Clear Water Reservoir, High Lift Pump House, Clear Water Rising Mains, 1000 Cum capacity UGR cum Booster Pumping Station at Pingla block , Chlorine room & Guard room at UGR site with necessary sanitary arrangements including plinth protection work with surface drain, Administrative Building with centralized SCADA system, Bunglow & Staff Quarter including furniture at WTP & other necessary all Civil and Electro-Mechanical works [excluding substation equipments] etc on EPC turnkey basis as per direction of the EIC including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Purba & Paschim Medinipur (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/001219/2023-2024 | 1012/TD | 14/03/2024 | 730 | G. B. CONSTRUCTION | 28900 | 0 | 12
3392 | Tamluk Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | RTOR000120/2024-2025 | 40/TD | 03/01/2025 | 0 | Resource Division | 5271.92 | 0 | 0
3393 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for Earnest Money Deposition for bulk power supply for proposed premises at Vill-Naskardighi & Janabar, Block-Panskura-I, for an Ultimate contract Demand of 3000KVA. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | BILL/06261/2025-2026 |  | 18/03/2026 | 0 | WBSEDCL | 0.2 | 0 | 0
3394 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 33/0.433 KV, 3000 KVA Electrical Substation with allied Electrical works at WTP at Panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000163/2024-2025 | 1659/W/MMD | 29/07/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 747.99 | 0 | 0
3395 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 11/0.433 KV, 800 KVA Electrical Substation with allied Electrical works at Pingla Boosting at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/002705/2023-2024 | 1057/W/MMD | 13/03/2024 | 180 | APEX ENGINEERING & PROJECT CO | 338.92 | 0 | 0
3396 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Intake point (River bank) at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/002717/2023-2024 | 1058/W/MMD | 13/03/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 485.76 | 0 | 0
3397 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (1165 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000272/2023-2024 | 530/TD | 12/05/2023 | 591 | SWARUPANANDA DAS | 240.51 | 160.38 | 70
3398 | Tamluk Division | Contai Sub-Division | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (475 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000632/2023-2024 | 2440/TD | 19/09/2023 | 861 | S.S.T ENGINEERING | 231.87 | 72.32 | 60
3399 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 325nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000905/2022-2023 | 3460/TD | 27/03/2023 | 633 | GIRI ENTERPRISE | 37.99 | 16.12 | 45
3400 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000178/2023-2024 | 627/W | 20/02/2024 | 0 | Resource Division | 12.66 | 0 | 0
3401 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000306/2022-2023 | 2963/TD | 27/02/2023 | 0 | Resource Division | 35.87 | 0 | 0
3402 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Kayemgeria W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000105/2023-2024 | 1393/CDD | 19/09/2023 | 210 | PADMA ENGINEERING & CO. | 27.2 | 22.74 | 100
3403 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004570684/QUOT/03 DT. 22-01-2024 Application NO- 2004570684 Application type-New connection Consumer Id- 204198020 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04389/2023-2024 | BP-2023-24-819 | 13/03/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
3404 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558744/QUOT/03 DT. 10-01-2024 Application NO- 2004558744 Application type-New connection Consumer Id- 204188974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04393/2023-2024 | BP-2023-24-818 | 13/03/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
3405 | Midnapore Mechanical | Contai Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
3406 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAYEMGERYA and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001321/2022-2023 | 2323/W/MMD | 29/12/2022 | 1077 | MAA TARA ENTERPRISE | 22.75 | 9.67 | 45
3407 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [536 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-E) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000164/2020-2021 | 2714/TD | 21/01/2021 | 30 | PALCON | 25.95 | 0.39 | 70
3408 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-D) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000165/2020-2021 | 2715/TD | 21/01/2021 | 20 | ANUPAM CONSTRUCTION | 9.99 | 0 | 40
3409 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-C),Bamaniabar(228), Narubhunya Chak(229). |  | Junior Engineer | ORD/000166/2020-2021 | 2716/TD | 21/01/2021 | 20 | DHANANJOY DAS | 9.99 | 0 | 100
3410 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [740 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.( Part-A), Nalbar(227),Dhalgoda (231) part, .Uttar Padma(233), Kashmali(234), .Kumbha Dharbar(235), |  | Junior Engineer | ORD/000167/2020-2021 | 2717/TD | 21/01/2021 | 35 | LOKENATH ENTERPRISES | 35.86 | 0 | 100
3411 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [126 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 2B ]. |  | Junior Engineer | ORD/000271/2020-2021 | 2924/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.1 | 0 | 0
3412 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [181 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 1B ]. |  | Junior Engineer | ORD/000272/2020-2021 | 2925/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.77 | 0 | 0
3413 | Tamluk Division | Digha Sub-Division | Laying 150mm. dia. D.I. (K-9) Rising main pipe line in between 1st Tube Well to pump house & O.H.R. to Distribution Main including construction of masonry pillar and Thrust concrete block for Astichak Water supply Scheme under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. |  | Junior Engineer | ORD/000370/2022-2023 | 834/TD | 18/07/2022 | 7 | ANUPAM CONSTRUCTION | 3.14 | 0 | 100
3414 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000232/2021-2022 | 160/W | 30/07/2021 | 0 | PALCON | 4.33 | 0 | 0
3415 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000233/2021-2022 | 97/W | 07/07/2021 | 0 | DHANANJOY DAS | 4.68 | 0 | 0
3416 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000290/2021-2022 | 209/W | 18/08/2021 | 0 | DHANANJOY DAS | 5.2 | 0 | 0
3417 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000394/2021-2022 | 233/W | 07/09/2021 | 0 | LOKENATH ENTERPRISES | 25.14 | 0 | 0
3418 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC (206 Nos.) under JJM of Astichak W/S Scheme within Egra-II Block under Tamluk Division, PHE Dte. (Part-D) |  | Junior Engineer | VCH/000539/2021-2022 | 397/W | 25/11/2021 | 0 | ANUPAM CONSTRUCTION | 2.65 | 0 | 0
3419 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001234/2020-2021 | 982/W | 25/03/2021 | 0 | PALCON | 10.68 | 0 | 0
3420 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001238/2020-2021 | 971/W | 25/03/2021 | 0 | LOKENATH ENTERPRISES | 10.64 | 0 | 0
3421 | Tamluk Division |  | Functional Household Tap Connection to the 275 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Damudarpur (357) ii) Hamirpur (545). |  |  | ORD/000098/2020-2021 | 2454/TD | 18/12/2020 | 20 | ABHIJIT BERA | 13.49 | 0 | 100
3422 | Tamluk Division |  | Functional Household Tap Connection to the 237 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Chandanpur (422) ii) Dakshin Rampur ( 539). |  |  | ORD/000099/2020-2021 | 2455/TD | 18/12/2020 | 20 | PARIA ENTERPRISE | 11.6 | 0 | 100
3423 | Tamluk Division |  | Functional Household Tap Connection to the 233 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Baliapur (358) ii) Jamna Madhusudhanbar (365). |  |  | ORD/000100/2020-2021 | 2456/TD | 18/12/2020 | 20 | BADAL CHANDRA GOLE | 11.46 | 0 | 100
3424 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000386/2021-2022 | 224/W | 01/09/2021 | 0 | ABHIJIT BERA | 1.3 | 0 | 0
3425 | Tamluk Division |  | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000475/2021-2022 | 325/W | 08/10/2021 | 0 | BADAL CHANDRA GOLE | 0.81 | 0 | 0
3426 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001043/2020-2021 | 728/W | 18/02/2021 | 0 | ABHIJIT BERA | 11.81 | 0 | 0
3427 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001048/2020-2021 | 801/W | 24/02/2021 | 0 | PARIA ENTERPRISE | 11.27 | 0 | 0
3428 | Tamluk Division |  | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001214/2020-2021 | 956/W | 19/03/2021 | 0 | BADAL CHANDRA GOLE | 10.24 | 0 | 0
3429 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Kanaidighi PWSS Block Contai-III in the District of Purba Medinipur. |  |  | ORD/000036/2020-2021 | 2109/TD | 05/11/2020 | 180 | DAS ENTERPRISE | 96.3 | 26.7 | 100
3430 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/000594/2020-2021 | 640/W | 13/01/2021 | 0 | DAS ENTERPRISE | 52.63 | 0 | 0
3431 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/001208/2020-2021 | 935/W | 18/03/2021 | 0 | DAS ENTERPRISE | 16.93 | 0 | 0
3432 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Alisuli,J.L. No-42 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000101/2020-2021 | 2457/TD | 18/12/2020 | 20 | KRISHNENDU SEKHAR DAS | 16.12 | 0.59 | 100
3433 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Bet Kalla,J.L. No-41 and Village-Dakshin Dhalhara,J.L No-39 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000102/2020-2021 | 2458/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 33.51 | 1.43 | 100
3434 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Hariharpur,J.L. No-43 and Village-Uttar Rautori,J.L No-40 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000103/2020-2021 | 2459/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 38.54 | 0.88 | 100
3435 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000595/2020-2021 | 642/W | 13/01/2021 | 0 | ARABINDA GHOSH | 21.06 | 0 | 0
3436 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000600/2020-2021 | 641/W | 13/01/2021 | 0 | ARABINDA GHOSH | 23.24 | 0 | 0
3437 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000607/2020-2021 | 647/W | 25/01/2021 | 0 | KRISHNENDU SEKHAR DAS | 12.09 | 0 | 0
3438 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001253/2020-2021 | 1032/W | 27/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 3.44 | 0 | 0
3439 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001269/2020-2021 | 1034/W | 30/03/2021 | 0 | ARABINDA GHOSH | 11.02 | 0 | 0
3440 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001270/2020-2021 | 1033/W | 30/03/2021 | 0 | ARABINDA GHOSH | 14.42 | 0 | 0
3441 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Uttar Charaikhia PWSS Block -Contai-l in the District of Purba Medinipur. |  |  | ORD/000204/2020-2021 | 2804/TD | 04/02/2021 | 25 | M/S SREE DURGA ENTERPRISE | 45.73 | 0 | 100
3442 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000256/2021-2022 | BP-2021-22-73 | 04/09/2021 | 0 | M/S SREE DURGA ENTERPRISE | 0.69 | 0 | 0
3443 | Tamluk Division |  | Functional Household Tap Connection for Uttar Charaikhia W/S Scheme within Contai - I Block Tamluk Division, PHE Dte. |  |  | VCH/001062/2020-2021 |  | 08/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0
3444 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001262/2020-2021 | 1088/W | 30/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0
3445 | Tamluk Division | Digha Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00706/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.11 | 0 | 0
3446 | Tamluk Division | Digha Sub-Division | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Alamgiri Birbara Khosbagola Road from 5.80 Km. to 6.20 Km., 6.40 Km. to 6.50 Km. & 6.80 Km. to 7.00 Km. for laying water pipe line of Kasbagola PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00990/2024-2025 | BP-2024-25-493 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.24 | 0 | 0
3447 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kasbagola Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000191/2021-2022 | 1200/TD | 02/12/2021 | 20 | RADIANT | 3.78 | 3.78 | 100
3448 | Tamluk Division | Digha Sub-Division | Repairing of Pump house, Construction of Boundary Wall, Laying Rising main pipe line & Supply under JJM with allied work for Kasbagola PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000200/2023-2024 | 401/TD | 27/04/2023 | 789 | ANUSKA ENTERPRISE | 26.15 | 14.62 | 95
3449 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, of 3rd Tube Well site with allied works of Kasbagola & its adjoining mouzas W/S Scheme within Egra -I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000292/2023-2024 | 594/TD | 17/05/2023 | 60 | CHAKRABORTY CONSTRUCTION | 13.42 | 5.07 | 90
3450 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Kasbagola Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Egra-I Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000426/2021-2022 | 1910/TD | 23/02/2022 | 180 | KISHORE GHOSH | 287.79 | 156.81 | 70
3451 | Tamluk Division | Digha Sub-Division | Sinking of 300 mm. x 200 mm. dia. x 230 mtr. deep tube well by direct rotary rig method using UPVC pipe and UPVC Deep Well Screen (RDS) at Kasbagola PWSS, Block- EGRA-I under Digha Sub-Division of Tamluk Division Dist- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000575/2021-2022 | 2048/TD | 14/03/2022 | 21 | KISHORE GHOSH | 13.75 | 10.69 | 100
3452 | Tamluk Division | Digha Sub-Division | Supply of CIDF sluice valve for Augmentation of Kasbagola PWSS within Egra-I Block under Digha Sub Division of Tamluk division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000620/2023-2024 | 2334/TD | 08/09/2023 | 10 | KISHORE GHOSH | 3.38 | 3.38 | 100
3453 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline to accommodate FHTC under JJM for Augmentation of Kasbagola PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 3191/TD | 11/12/2023 | 25 | KISHORE GHOSH | 31.07 | 29.75 | 95
3454 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2021-2022 | 1955/TD | 04/03/2022 | 0 | Resource Division | 11.7 | 0 | 0
3455 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000085/2021-2022 | 2189/TD | 21/03/2022 | 0 | Resource Division | 14.39 | 0 | 0
3456 | Tamluk Division | Digha Sub-Division | Construction of Pump House (3.6mx 3.0m), Boundary Wall, Proposed Rising & Interconnection, Supply and delivery of different dia D.I. specials & fittings with allied works under JJM at 4th TW site for Augmentation of Kasbagola Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000592/2024-2025 | 490/TD | 06/02/2025 | 360 | AYSAN KHAN | 15.06 | 0 | 0
3457 | Central Drilling | Digha Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Kasbagola W/S Scheme (T/W-I) , Egra-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000130/2023-2024 | 859/CDD | 10/07/2023 | 287 | PADMA ENGINEERING & CO. | 18.23 | 15.33 | 100
3458 | Midnapore Mechanical | Digha Sub-Division | Electric Quotiaton for Kasbagola Water Supply Scheme T/W-III (Ref. ID-204005246) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00380/2023-2024 | BP-2023-24-66 | 06/06/2023 | 0 | WBSEDCL | 0.61 | 0 | 0
3459 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-4 of Kasbagola ws scheme under MMD, PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004773721 Con ID-204332518 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01328/2024-2025 | BP-2024-25-359 | 01/07/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
3460 | Midnapore Mechanical | Digha Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
3461 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001925/2022-2023 | 844/W/MMD | 24/03/2023 | 840 | ECO ENTERPRISE | 35.55 | 13.97 | 25
3462 | Tamluk Division |  | Retrofitting to accomodate FHTC (1575 nos.) under JJM in Palduhi PWSS Block - RAMNAGAR-II under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) |  |  | ORD/000007/2021-2022 | 685/TD | 10/09/2021 | 45 | BASANTA KUMAR MAITY | 95.95 | 61.88 | 100
3463 | Tamluk Division |  | Retrofitting to accommodate FHTC 1575 Nos. under JJM in Palduhi PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000382/2021-2022 | BP-2021-22-135 | 18/10/2021 | 0 | BASANTA KUMAR MAITY | 34.05 | 0 | 0
3464 | Tamluk Division |  | Retrofitting to accomodate FHTC (548 nos.) under JJM in Habichak PWSS(Balance Work) Block - Chandipur in the District of Purba Medinipur. (Phase- II) |  |  | ORD/000003/2021-2022 | 681/TD | 10/09/2021 | 50 | S.D. CONSTRUCTION | 24.29 | 0 | 100
3465 | Tamluk Division |  | Retrofitting to accomodate FHTC (548 Nos.) under JJM in Habichak PWSS (Balance Work) Block-Chandipur under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000351/2021-2022 | BP-2021-22-87 | 05/10/2021 | 0 | S.D. CONSTRUCTION | 24 | 0 | 0
3466 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC (220 nos.) under JJM IN Damudarpur PWSS under Contai-I Block of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000009/2021-2022 | 687/TD | 10/09/2021 | 20 | MAA ANANDAMAYEE | 16.62 | 15.68 | 96
3467 | Tamluk Division |  | Retrofitting to accomodate FHTC (1050 nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte . (Phase-II) |  |  | ORD/000128/2021-2022 | 1008/TD | 02/11/2021 | 45 | M/S A.R. ENTERPRISE | 60.36 | 59.87 | 100
3468 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM in Chirulia PWSS Block - Egra-II in the District of Purba Medinipur. (PHASE- II) | Assistant Engineer | Junior Engineer | ORD/000132/2021-2022 | 1014/TD | 02/11/2021 | 30 | FIROZ KHAN | 44.75 | 43.55 | 100
3469 | Tamluk Division | Digha Sub-Division | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 3 | 100
3470 | Tamluk Division |  | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless AWC under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Dakshin Badhia AWC, G.P- Badhia, Mouza - Badhia, J.L. No.- 06 |  |  | ORD/000129/2022-2023 | 135/RWS/TSD | 14/06/2022 | 7 | GRAND CONSTRUCTION | 2.98 | 2.59 | 100
3471 | Tamluk Division |  | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless School under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Ghersai SSK, G.P- Padima-II, Mouza - Ghersai, J.L. No.- 88 |  |  | ORD/000131/2022-2023 | 138/RWS/TSD | 14/06/2022 | 7 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.97 | 2.62 | 100
3472 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Benagolisa Tapas Mandal House (19345200609), G.P- Gobindanagar, (ii) Ratulia Jr. Basic School (19345200501), G.P- Gobindanagar, (iii) Paschim Arjunda Pry. (19345200502), G.P- Gobindanagar,, (iv) Paschim Nekra Pry. School (19345200505), G.P- Gobindanagar, (v) Joykrishnapur I.C.J.C.K. (19345200507),G.P- Gobindanagar, (vi) Dharmapore Asharam (19345200508), G.P- Gobindanagar, (vii) Manur Pry. School (19345200611), (viii) Golghat Pry. School (19345200613), G.P- Gobindanagar. |  |  | ORD/000225/2021-2022 | 1356/TD | 24/12/2021 | 45 | MADAN MOHAN MAITY | 22.79 | 22.56 | 100
3473 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Tamluk Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) HOUSE OF SADHAN KUILA,JASADUMBUR (19345281114). G.P- Bishnubarh-I, (ii) MAISALI MAHILA SAMITY HOUSE (19345281118), G.P- Bishnubarh-I, (iii) GHOLECHAK VIJOY PRY. SCH. (19345281119),G.P- Bishnubarh-I, (iv) AMGECHHIA SITALA AWC (19345280915),G.P- Bishnubarh-I, (v) BAHICHARD DAKSHIN PALLI AWC (19345280917),G.P- Bishnubarh-I. |  |  | ORD/000226/2021-2022 | 1357/TD | 24/12/2021 | 35 | BHOLANATH DEY | 14.22 | 14.09 | 100
3474 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Moyna Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Moyna Badurtala (19345140202), G.P- Moyna-II,(ii) Dakshin Moyna Dangisai (19345140215), G.P- Moyna-II, (iii) P D Moyna (19345140216), G.P- Moyna-II, (iv) Radhaballabh Chak (19345140509), G.P- Gokulnagar. |  |  | ORD/000227/2021-2022 | 1358/TD | 24/12/2021 | 30 | JAGANNATH MAKAR | 12.4 | 12.4 | 100
3475 | Tamluk Division |  | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2024 to 31.12.2024 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. |  |  | ORD/000251/2024-2025 | 104/RWS/TSD | 28/06/2024 | 184 | HALADHAR SAMANTA | 0.87 | 2.03 | 50
3476 | Tamluk Division |  | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. |  |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 1.91 | 100
3477 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 270 mt.) along with stand post at different Sourceless AWC under Nandigram-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Amdabad Uttar AWC (19345160504), G.P- Amdabad-I, (ii) Amdabad Purba chara AWC (19345160618), G.P- Amdabad-I, (iii) Amdabad Madhya AWC (19345160502), G.P- Amdabad-I, (iv) Subdi N. State Plan AWC (19345160514), G.P- Amdabad-I, (v) Amdabad 2 N0.AWC (19345160516), G.P- Amdabad-I, (vi) Hanubhuiya Uttar AWC (19345160420),G.P- Birulia, (vii) Sibrampur AWC (19345160422), G.P- Birulia, (viii) Gholpukur Dakshin AWC (19345160409), G.P- Birulia. |  |  | ORD/000228/2021-2022 | 1359/TD | 24/12/2021 | 45 | NARAYAN CHANDRA DAS | 26.82 | 25.2 | 100
3478 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakkhin Amtalia Anathbandhu A.W.C. (19345050907), G.P- Amtalia, (ii) Kasafalia A.W.C. (19345050105), G.P- Amtalia, (iii) Aurai Kacharibari A.W.C. (19345050301), G.P- Aurai, (iv) Chhanberya A.W.C. (19345050121), G.P- Aurai, (v) Uttar Basudebberya Bramhanarayan A.W.C. (19345050307), G.P- Aurai, (vi) Namaldiha Mother Teresa A.W.C. (19345050302), G.P- Aurai, (vii) Uttar Karpura Keshabchandra A.W.C. (19345050315), G.P- Aurai, (viii) Sarsa A.W.C. (19345050610), G.P- Bamunia. |  |  | ORD/000229/2021-2022 | 1360/TD | 24/12/2021 | 45 | PARIA ENTERPRISE | 24.53 | 23.27 | 100
3479 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 250 mt.) along with stand post at different Sourceless AWC under Contai-III Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Khalsiberia AWC (19345060125), (ii) Marishda AWC (19345060524), G.P- Marishda, (iii) Dakhsin Sukunia (19345060310), (iv) Sukunia Uttar (19345060312), (v) Jagudasbar AWC (19345060413). |  |  | ORD/000230/2021-2022 | 1361/TD | 24/12/2021 | 35 | JASODA ENTERPRISE | 16.04 | 14.11 | 100
3480 | Tamluk Division |  | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bakshishpur AWC (19345250519), G.P- Maitana, (ii) Dakshin Tentultala AWC (19345250522), G.P- Maitana, (iii) Dakshin Maitana AWC (19345250525), G.P- Maitana, (iv) Satilapur AWC (19345250604), G.P- Sitalapur, (v) Purba Satilapur AWC (19345250605), G.P- Sitalapur, (vi) Purba Ghole AWC (19345250622), G.P- Sitalapur, (vii) Bararankua Harijan AWC (19345250716), G.P- Balisai. |  |  | ORD/000231/2021-2022 | 1362/TD | 24/12/2021 | 45 | MRINAL KANTI PRADHAN | 20.96 | 19.36 | 100
3481 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 17,Batashpur FP School 15 (19345070115), G.P- Barida, (ii) 10, Barida Banikishor Sangha 11, (19345070111), G.P- Barida, (iii) 11, Khalina ICJCK 17 (19345070117), G.P- Barida, (iv) 12,Khalina Own Awc 13 (19345070113), G.P- Barida, (v) 13, Madhabpur FP School 16 (19345070116), G.P- Barida, (vi) 194,Sekhpara,Jerthan 08 (19345070408), G.P- Jerthan, (vii) 2, Swarrang Narayan Das'House 06 (19345070106), G.P- Barida, (viii) 190,Sannihari Dhananjoy Patra 15 (19345070315). G.P- Chhatri. |  |  | ORD/000232/2021-2022 | 1364/TD | 24/12/2021 | 45 | S.D. CONSTRUCTION | 22.23 | 22.14 | 100
3482 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rasulpur A.W.C. (19345050911), G.P- Basantia, (ii) Tengorerya Ma Ballavi A.W.C. (19345051007), G.P- Basantia, (iii) Kultalia Paschimpara A.W.C. (19345050915), G.P- Basantia, (iv) Dakkhin Deulpota Subhashchandra A.W.C. (19345051009), G.P- Basantia, (v) Gokulnagar A.W.C. ( 19345050916), G.P- Basantia, (vi) Kalikakumari Vivekananda A.W.C. (19345051010), G.P- Basantia, (vii) Purba Mahammadpur Jana Para A.W.C. (19345051005), G.P- Basantia, (viii) Kultalia Purba Para A.W.C. (19345050914), G.P- Basantia. |  |  | ORD/000239/2021-2022 | 1394/TD | 28/12/2021 | 45 | M/S SREE DURGA ENTERPRISE | 24.51 | 24.23 | 100
3483 | Tamluk Division |  | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Kusbani A.W.C. (19345050919), G.P- Basantia, (ii) Baghaghole Vivekananda A.W.C. (19345050620), G.P- Chalti, (iii) Dakkhin Kalikapur A.W.C. (19345050619), G.P- Chalti, (iv) Nanker Gopinathpur A.W.C. ( 19345050804) G.P- Dariapur, (v) Chitanyapur A.W.C. (19345050818), G.P- Dariapur, (vi) Haripur A.W.C. (19345050812), G.P- Dariapur, (vii) Uttar Deulpota Padmabati A.W.C. (19345050202), G.P- Dhobaberya. |  |  | ORD/000240/2021-2022 | 1395/TD | 28/12/2021 | 45 | SUBRATA KUMAR BERA | 21.46 | 21.14 | 100
3484 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Block: (i) Sukrasoni (19345240211), G.P- Haldia-I, (ii) Dikshal (19345240216), G.P- Haldia-I, (iii) Khairanda-3 (19345240218), G.P- Haldia-I, (iv) Bandhmuri (19345240219), G.P- Haldia-I, (v) Gangra-1 (19345240312), G.P-Haldia-II, (vi) Gangra-2 (19345240315), G.P- Haldia-II, (vii) Ranisai-2 (19345240322), G.P- Haldia-II, (viii) Koniora-3 (19345240323), G.P- Haldia-II. |  |  | ORD/000241/2021-2022 | 1396/TD | 28/12/2021 | 45 | PALCON | 24.7 | 21.07 | 100
3485 | Tamluk Division |  | Installation of 03 (Three) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Gopalpur (19345240720), G.P- Talgachari-II, (ii) Nariha-2 (19345240802), G.P- Talgachari-I, (iii) Jamra (19345240819), G.P- Talgachari-II. |  |  | ORD/000242/2021-2022 | 1397/TD | 28/12/2021 | 25 | SAYAN MAITY | 9.31 | 8.34 | 100
3486 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Jinandapur AWC (19345250319), G.P- Badalpur, (ii) Balarampur AWC (19345250323), G.P- Maitana, (iii) Uttar Kalindi AWC (19345250401), G.P- Kalindi, (iv) Kalindi Basti AWC (19345250405), G.P- Kalindi, (v) Purbabarh Manodamoyee AWC (19345250406), G.P- Kalindi, (vi) Teghari ICDS Centre (19345250409), G.P- Kalindi, (vii) Demuria Paikbar AWC (19345250510), G.P- Maitana, (viii) Mandarpur Pry. School(OWN) (19345250516), G.P- Maitana. |  |  | ORD/000243/2021-2022 | 1398/TD | 28/12/2021 | 45 | MAITY CONSTRUCTION | 23.94 | 22.03 | 100
3487 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 39,Rasan Chakbandi FpSchool 23 (19345070323), G.P- Chhatri, (ii) 40,Rasan Own AWC 25 (19345070325), G.P-G.P- Chhatri. |  |  | ORD/000244/2021-2022 | 1400/TD | 28/12/2021 | 20 | GRAND CONSTRUCTION | 5.55 | 5.53 | 100
3488 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rukminipur ICDS Centre (19345080302), G.P- Deshbandhu, (ii) Eranda Binapani Club (19345080306), G.P- Deshbandhu, (iii) Kirtipur Bhai Bhai Sangha (19345080307), G.P- Deshbandhu, (iv) Rajendrachak Matsya Jibi Yuva Kalyan Sangha (19345080501), G.P- Deshbandhu, (v) Urijalkar Martri Sakti Sangha (19345080310), G.P- Deshbandhu, (vi) Sarisa Jagrata Yuva Sangha (19345080203), G.P- Deshbandhu, (vii) Hurkuchia Sourav Club (19345080503), G.P- Deshbandhu, (viii) Eranda Haripriya Seba Sangha (19345080309), G.P- Deshbandhu. |  |  | ORD/000245/2021-2022 | 1401/TD | 28/12/2021 | 45 | ABHIJIT BERA | 23.38 | 23.29 | 100
3489 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Narubhuiachak ICDS (19345080410), G.P- Bathuary, (ii) Jaganathkarbar Sunrise ICDS ( 193450805414), G.P- Bathuary, (iii) Bhatda Haripur Youth Club (19345080101), G.P- Manjushree, (iv) Bhatda Palli Mongal ICDS (19345080102), G.P- Manjushree. |  |  | ORD/000246/2021-2022 | 1402/TD | 28/12/2021 | 30 | DEBABRATA DAS | 11.69 | 11.63 | 100
3490 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kaijuddin para-06 (19345220406), G.P- Amarshi 7/1, (ii) Amarshi Kasba-08 (19345220408), G.P- Amarshi 7/1, (iii) Amarshi(e)muslimpara-12 (19345220412), G.P- Amarshi 7/1, (iv) Barsankar-01 (19345220501), (v) Sanamginga-03 (19345220503), G.P- Amarshi 7/2, (vi) Bantitaka-06 (19345220506), (vii) Gumraveri-07 (19345220507), G.P- Amarshi 7/2, (viii) Taladiha-2-08 (19345220508), G.P- Amarshi 7/2. |  |  | ORD/000247/2021-2022 | 1403/TD | 28/12/2021 | 45 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.23 | 21 | 100
3491 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Muradpur AWC (19345230101), G.P- Khar, (ii) Manpur AWC (19345230102), G.P- Khar, (iii) Girisha AWC (19345230104), G.P- Khar, (iv) Gangasagar AWC (19345230105), G.P- Khar, (v) Mustafapur Dakshin AWC (19345230107), G.P- Khar, (vi) Bar Mustafapur AWC (19345230108), G.P- Khar, (vii) Panchet Uttar AWC (19345230206), G.P- Panchet-04, (viii) Panchet Daksin AWC (19345230207) |  |  | ORD/000248/2021-2022 | 1404/TD | 28/12/2021 | 45 | GIRI CONSTRUCTION | 25.08 | 24 | 100
3492 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Nimja AWC (19345230213), G.P- Panchet-04, (ii) Bamunda-II AWC (19345230307), G.P- Panchet-04, (iii) Etachana AWC (19345230309), G.P- Panchet-04, (iv) Motirampur AWC (19345230310), G.P- Patashpur-05. |  |  | ORD/000249/2021-2022 | 1405/TD | 28/12/2021 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.55 | 11.45 | 100
3493 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Uttar Tiraipur AWC (19345010201), G.P- Mahammadpur-II, (ii) Benauda 1 No. ICDS (19345010203), G.P- Mahammadpur-II, (iii) Goalapukur AWC (19345010208), G.P- Mahammadpur-II, (iv) Garbhera South ICDS (19345010214), G.P- Gurgram (v) Purba Gurgram-1 No. ICDS (19345010302), G.P- Gurgram, (vi) Dakshin Gurgram ICDS (19345010304), G.P- Gurgram, (vii) Fatepur ICDS (19345010312), G.P- Gurgram, (viii) Buraburi-2 No.ICDS (19345010313), G.P- Gurgram. |  |  | ORD/000250/2021-2022 | 1406/TD | 28/12/2021 | 45 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.23 | 23.51 | 100
3494 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Gurgram-2 No. ICDS (19345010314), G.P- Gurgram, (ii) Amratala AWC (19345010213), G.P- Gurgram. |  |  | ORD/000252/2021-2022 | 1407/TD | 28/12/2021 | 20 | BADAL CHANDRA GOLE | 6.06 | 5.99 | 100
3495 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dhelua AWC (19345020309), G.P- Jukhia, (ii) Bani Mandir AWC (19345020312), G.P- Jukhia. |  |  | ORD/000256/2021-2022 | 1363/TD | 24/12/2021 | 20 | DHANANJOY DAS | 6.05 | 5.61 | 100
3496 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 64,Kiya Nonformal School 22 (19345070422), G.P- Jerthan, (ii) 66, Ashada 19 (19345070419), G.P- Jerthan, (iii) 59, Satkhanda FP School 02 (19345070402), G.P- Jerthan, (iv) 38,Chhatri Bhatgeria 06 (19345070306), G.P- Chhatri. |  |  | ORD/000257/2021-2022 | 1365/TD | 24/12/2021 | 30 | M/S. S. A. CONSTRUCTION | 11.1 | 11.07 | 100
3497 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Shilampur Swamiji Seba Sangha ( 19345080519), G.P- Vivekananda, (ii) Uttar Eranda Tapsili Sangha (19345080315), G.P- Deshbandhu, (iii) Nijdant Tarun Sangha (19345080316), G.P- Bathuary, (iv) Dakshin Chowmukh ICDS ( 19345080507), G.P- Bathuary, (v) Gangadharbar ICDS Center (19345080508), G.P- Bathuary. |  |  | ORD/000258/2021-2022 | 1366/TD | 24/12/2021 | 35 | ANUPAM CONSTRUCTION | 14.59 | 14.3 | 100
3498 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Mahapur Pry. School G.P. Gobindanagar. (ii) Bijaharpur Nabarun Sangha ( 19345200604), G.P- Gobindanagar, (iii) Rajnagar Pry. School (19345200605), G.P- Gobindanagar, (iv) Anupganj Pry. School (19345200606), G.P- Gobindanagar, (v) Gobindanagar Pry. School(19345200607), G.P- Gobindanagar. |  |  | ORD/000268/2021-2022 | 1502/TD | 06/01/2022 | 35 | BARH CONSTRUCTION | 14.25 | 13.5 | 100
3499 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Saiadpur (19345240701), G.P- Talgachari-I, (ii) Uttar Bagpura (19345240712), G.P- Talgachari-I, (iii) Bagpura-2 (19345240714), G.P- Talgachari-I, (iv) Ramnagar (19345240718), G.P- Talgachari-I. |  |  | ORD/000269/2021-2022 | 1503/TD | 06/01/2022 | 30 | SWADHIN KUMAR CHAKRABORTY | 12.43 | 11.57 | 100
3500 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250102), G.P- Paldhui, (ii) Kanwa ICDS (19345250105), G.P- Paldhui, (iii) Purba Paldhui AWC (19345250108), G.P- Paldhui, (iv) Uttar Sabitrapur AWC (19345250116), G.P- Paldhui. |  |  | ORD/000270/2021-2022 | 1504/TD | 06/01/2022 | 30 | SUDIP MANNA | 11.98 | 11.05 | 100
3501 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250122), G.P- Paldhui, (ii) Uttar Kanpur Awc (19345250206), G.P- Depal, (iii) Tajpur AWC (19345250307), G.P- Badalpur, (iv) Badalpur Tarun Sangha Awc (19345250313), G.P- Badalpur. |  |  | ORD/000271/2021-2022 | 1505/TD | 06/01/2022 | 30 | TAPAN BERA | 11.98 | 11.5 | 100
3502 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschimbarh-2 No. ICDS (19345010102), G.P- Mahammadpur-I, (ii) Paschimbarh-3 No. ICDS (19345010103), G.P- Mahammadpur-I, (iii) Uttarbarh-1 No ICDS (19345010104), G.P- Mahammadpur-I, (iv) Sekbarh ICDS (19345010105), G.P- Mahammadpur-I, (v) Mahammadpur-2 No. ICDS (19345010107), G.P- Mahammadpur-I, (vi) Sribachhipur-1 No. ICDS (19345010108), G.P- Mahammadpur-I, (vii) Nimakbarh-2 No. ICDS (19345010113),G.P- Mahammadpur-I, (viii) Uttarbarh-3 No. ICDS (19345010114), G.P- Mahammadpur-I. |  |  | ORD/000272/2021-2022 | 1506/TD | 06/01/2022 | 45 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.25 | 23.52 | 100
3503 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 28,Baranihari Ramkrishna Seba Sangha 05 (19345070305), G.P- Chhatri, (ii) 30,Ramkrishnapur AWC 03 (19345070303), G.P- Chhatri, (iii) 31, Sannihari Own AWC 14 (19345070314), G.P- Chhatri, (iv) 133, Arjuni ICJCK 21 (19345070821), G.P- Jumki, (v) 134, Hansaria AWC (19345070725), G.P- Jumki, (vi) 136, Chaulda AWC (19345070727), G.P- Jumki,, (vii) 137, Nischinta AWC 27 (19345070827), G.P- Jumki, (viii) 62, Benachakri Mandalpara 24 (19345070424), G.P- Jerthan. |  |  | ORD/000294/2021-2022 | 1399/TD | 28/12/2021 | 45 | AJIT KUMAR SOM | 22.24 | 22.15 | 100
3504 | Tamluk Division |  | Sinking of 1(One) nos. 100 mm X 50 mm dia. X 220.0 m(av.) depth Indian Mark-II tube well with PVC pipes including cost of all materials and construction of Platform (as per Departtl. approved drawing) at ''Tamralipta Mahavidyalaya'' due to scarcity of drinking water in a newly constructed three- storied building under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. |  |  | ORD/000328/2023-2024 | 626/TD | 17/05/2023 | 15 | GLOBAL TRADE | 2.29 | 2.16 | 100
3505 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Panchuria-2-12 (19345220512), G.P- Amarshi-7/2, (ii) Taladiha-3-13 (19345220513), G.P- Amarshi-7/2. |  |  | ORD/000388/2021-2022 | 1848/TD | 16/02/2022 | 20 | SK. SAHALAM | 5.55 | 5.19 | 100
3506 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kamalpur AWC (19345230311), G.P- Patashpur-05, (ii) Shikhoda AWC (19345230319), G.P- Patashpur-05, (iii) Morirampur Uttar Awc (19345230322), G.P- Patashpur-05, (iv) Tupchibarh- III AWC (19345230327), G.P- G.P- Patashpur-05. |  |  | ORD/000389/2021-2022 | 1849/TD | 16/02/2022 | 30 | ELECTIVA ENTERPRISE | 12.43 | 11.24 | 100
3507 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bikra Khan Para (19345200216), G.P- Mysora, (ii) Sahalajpur (Chotto Bhim Para) (19345200218), G.P- Mysora, (iii) Mysora Paschim Muslim Para (19345200124), G.P- Mysora, (iv) Gobindanagar Kali Mandir (19345200603), G.P- Gobindanagar. |  |  | ORD/000404/2021-2022 | 1896/TD | 23/02/2022 | 30 | TARUN KHATUA | 11.39 | 11.29 | 100
3508 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Sikarput A.W.C. (19345050705), G.P- Bamunia, (ii) Choudhuribar A.W.C. (19345051011), G.P- Basantia, (iii) Mukundapur Paschim Para A.W.C. (19345051018), G.P- Basantia, (iv) Basantia Mago Mandir A.W.C. (19345051012), G.P- Basantia. |  |  | ORD/000405/2021-2022 | 1897/TD | 23/02/2022 | 30 | FARID UDDIN AHMED | 12.26 | 12.16 | 100
3509 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Charaput A.W.C. (19345050612), G.P- Bamunia, (ii) Murabenia Maktab A.W.C. (19345050617), G.P- Bamunia, (iii) Dakshin Kadua A.W.C. (19345050706), G.P- Bamunia (iv) Uttar Kadua Vivekananda A.W.C. (19345050708), G.P- Bamunia. |  |  | ORD/000406/2021-2022 | 1898/TD | 23/02/2022 | 30 | SUBHRANGSHU SEKHAR GIRI | 12.25 | 11.62 | 100
3510 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschim Bakulda Dashibard AWC (19345200204), G.P- Mysora, (ii) Radhaballavpur P.L.C. (19345200208), G.P- Mysora, (iii) Bikra Pry. School (19345200209), G.P- Mysora, (iv) Rajshar AWC (19345200113), G.P- Mysora, (v) Paschim Shyampur (19345200115), G.P- Mysora, (vi) Purba Mysora Club (19345200117), G.P- Mysora, (vii) Balarampur S.S.K. (19345200211), G.P- Mysora, (viii) Gopal Hazra SSK (19345200213),G.P- Mysora. |  |  | ORD/000454/2021-2022 | 1937/TD | 02/03/2022 | 45 | BIDHAN MONDAL | 22.81 | 21.39 | 100
3511 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Chandanpur-1 (19345240116), G.P- Badhia, (ii) South Badhia-3 (19345240121), G.P- Badhia, (iii) Dangri Patna (19345240125), G.P- Badhia, (iv) Damodarpur Paschim (19345240203), G.P- Badhia, (v) Sadi (19345240207), G.P- Haldia-I, (vi) Kholaberia (19345240208), G.P- Haldia-I, (vii) Nilkanthapur (19345240209), G.P- Haldia-I, (viii) Rania (19345240210), G.P- Haldia-I. |  |  | ORD/000455/2021-2022 | 1938/TD | 02/03/2022 | 45 | AYSAN KHAN | 24.8 | 21.96 | 100
3512 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Porachingra AWC (19345020102), G.P- Garbari-I, (ii) Jhinuk-khali Madhyapally AWC (19345020117), G.P- Garbari-I, (iii) Paschim Garbari AWC (19345020216), G.P- Garbari-II, (iv) Kutubuddinpur AWC (19345020302), G.P- Jukhia, (v) Madhakhali Primary School (19345020303), G.P- Jukhia, (vi) Sitadighi Primary School (19345020305), G.P- Jukhia, (vii) Jukhia AWC (19345020307), G.P- Jukhia, (viii) Jukhia Sitadhighi Primary School (19345020308), G.P- Jukhia. |  |  | ORD/000456/2021-2022 | 1939/TD | 02/03/2022 | 45 | DAS ENTERPRISE | 24.24 | 23.02 | 100
3513 | Tamluk Division |  | Continuation work order for hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily rate basis (as and when required including Govt. Holiday) for the period from 01.06.2023 to 30.06.2023 i.e. 01 (one) month only, having contract carriage permit from Regional Transport Authority for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. (Ref:- Memo No.- 375/RWS/TSD Dated, 30/11/2022 |  |  | ORD/000703/2023-2024 | 54/RWS/TSD | 19/05/2023 | 30 | SRIMANTA PANJA | 0.14 | 0.38 | 100
3514 | Tamluk Division |  | Construction of M.S. Structure over drainage canal to support different dia DI(K-7) distribution pipe & 150 mm dia. DI(K-9) rising main pipe under Shyampur Water Supply Scheme at different Nodal Point within Moyna Block under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. |  |  | ORD/000048/2022-2023 | 271/TD | 02/05/2022 | 30 | RAJ KUMAR SINGHA | 17.62 | 15.54 | 100
3515 | Tamluk Division |  | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. with allied work under Shyampur & its adjoining mouzas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000152/2021-2022 | 1092/TD | 17/11/2021 | 210 | RAJ KUMAR SINGHA | 521.85 | 484.18 | 100
3516 | Tamluk Division |  | Laying Distribution system of Left-out portion of pipe line and Retrofitting to accommodate FHTC (775 Nos.) under JJM at Shyampur Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000250/2024-2025 | 2801/TD | 03/09/2024 | 160 | RAJ KUMAR SINGHA | 113.63 | 0 | 100
3517 | Tamluk Division |  | Interconnection with laying of 150 mm dia DI (K-9) Rising main From 1st & 2nd Tube Well Site to O.H.R. and other allied works at Shyampur PWSS Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000392/2022-2023 | 1425/TD | 26/09/2022 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 3.91 | 3.04 | 100
3518 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Shyampur Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000520/2021-2022 | 1995/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.07 | 100
3519 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 1284/TD | 15/12/2021 | 0 | Resource Division | 33.3 | 0 | 0
3520 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 1474/TD | 03/01/2022 | 0 | Resource Division | 14.11 | 0 | 0
3521 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 1680/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
3522 | Central Drilling |  | PROVIDING TUBE WELL MATERIALS OF 200 MM NOMINAL DIA, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000040/2022-2023 | 244/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 3.85 | 2.77 | 100
3523 | Central Drilling |  | SINKING OF 300 MM X 200 MM DIA X 240 MTRS DEPTH TUBE WELL IN PURBA MEDINPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000041/2022-2023 | 242/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 3.18 | 3.05 | 100
3524 | Central Drilling |  | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DIST. UNDER CDD, PHE DTE. |  |  | ORD/000042/2022-2023 | 241/CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 2.42 | 1.74 | 100
3525 | Central Drilling |  | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN PURBA MEDINIPUR DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000043/2022-2023 | 243/ CMSD-II (D) | 20/05/2022 | 15 | MENAKA ENTERPRISE | 4.9 | 4.9 | 100
3526 | Central Drilling |  | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0.55 | 0
3527 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000172/2022-2023 | 2003984006/QUOT/1017 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0
3528 | Midnapore Mechanical |  | New Service Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000173/2022-2023 | MNA/QUT/22-23/NSC/PHE/201 | 08/07/2022 | 365 | WBSEDCL | 1.86 | 0 | 0
3529 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000174/2022-2023 | 2003984015/QUOT/1016 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0
3530 | Midnapore Mechanical |  | New service connection PHE Full deposite scheme for T/W -II of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000176/2022-2023 | MNA/QUT/22-23/NSC/PHE/101 | 08/07/2022 | 365 | WBSEDCL | 1.42 | 0 | 0
3531 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001014/2022-2023 | 1863/W/MMD | 22/09/2022 | 120 | PRANAB KUMAR DAS | 12.66 | 11.9 | 100
3532 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001130/2022-2023 | 2111/W/MMD | 28/11/2022 | 120 | ECO ENTERPRISE | 12.68 | 12.42 | 100
3533 | Midnapore Mechanical |  | New Servic Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001775/2022-2023 | BP-2022-23-29 | 10/08/2022 | 0 | WBSEDCL | 1.86 | 0 | 0
3534 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001776/2022-2023 | BP-2022-23-32 | 11/08/2022 | 0 | WBSEDCL | 1.42 | 0 | 0
3535 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001777/2022-2023 | BP-2022-23-30 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0
3536 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001778/2022-2023 | BP-2022-23-28 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0
3537 | Tamluk Division |  | Laying of Distribution pipe line , Construction of Pump House & Boundary Wall, Construction of RCC Over Head Reservoir of Capacity 450 Cum, Sub -Soil Investigation with allied works of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000151/2021-2022 | 1091/TD | 17/11/2021 | 210 | TAPAS SANTRA | 526.12 | 429.67 | 95
3538 | Tamluk Division |  | Laying of 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000168/2023-2024 | 295/TD | 20/04/2023 | 30 | SUBHENDU HAZRA | 3.71 | 2.91 | 100
3539 | Tamluk Division |  | Supply & Delivery of 80 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000311/2021-2022 | 1687/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 4.01 | 4.01 | 100
3540 | Tamluk Division |  | Supply & Delivery of 125 mm, 150 mm,200 mm & 250 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000312/2021-2022 | 1688/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 3.81 | 3.81 | 100
3541 | Tamluk Division |  | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 1st TW / Head Work Site ( Mouza- Kalmichhabar ,J.L. No-317, Plot No- 599), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur,PHE Dte. |  |  | ORD/000372/2021-2022 | 1682/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100
3542 | Tamluk Division |  | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 2nd TW Site ( Mouza- Jethaibari ,J.L. No-307, Plot No- 106), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur, PHE Dte. |  |  | ORD/000373/2021-2022 | 1683/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100
3543 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Baharampur Water Supply Scheme within under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000513/2021-2022 | 1994/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 14.76 | 10.39 | 100
3544 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Baharampur PWSS Block - Bhagwanpur-II in the District of Purba Medinipur. |  |  | ORD/000715/2023-2024 | 2959/TD | 24/11/2023 | 25 | S.D. CONSTRUCTION | 51.79 | 37.96 | 85
3545 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 81/TD | 08/04/2022 | 0 | Resource Division | 21.16 | 0 | 0
3546 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 1283/TD | 15/12/2021 | 0 | Resource Division | 3.37 | 0 | 0
3547 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 1475/TD | 03/01/2022 | 0 | Resource Division | 12.61 | 0 | 0
3548 | Central Drilling |  | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAHARAMPUR W/S SCH (TW-I), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000054/2022-2023 | 380/CDD | 17/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.64 | 100
3549 | Central Drilling |  | SUPPLY AND DELIVERY OF BRICKS BATS WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. |  |  | ORD/000159/2022-2023 | 246/CMSD-II | 23/05/2022 | 10 | MENAKA ENTERPRISE | 0.57 | 0.57 | 100
3550 | Central Drilling |  | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT BAHARAMPUR PWSS, BLOCK-BHAGAWANPUR-II BY UTILIZING DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. |  |  | ORD/000160/2022-2023 | 303/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 3.76 | 1.51 | 100
3551 | Central Drilling |  | Providing Tube Well Materials conforming to IS : 12818:2010 with other works at site for construction of tube well at Baharampur PWSS, Block - Bhagawanpur-II under CDD, PHE Dte. |  |  | ORD/000162/2022-2023 | 305/CMSD-I(D) | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.89 | 0.08 | 100
3552 | Central Drilling |  | ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL & OTHER MATERIALS AT SITE FOR BAHARAMPUR PWSS, BLOCK BHAGAWANPUR-II BY UTILIZING SKILLED DRILLING CREW & DEPARTMENTAL MACHINERIES UNDER CDD, PHE DTE. |  |  | ORD/000169/2022-2023 | 304/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.9 | 3.68 | 100
3553 | Central Drilling |  | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BAHARAMPUR PWSS, BLOCK- BHAGAWANPUR-II UNDER CDD, PHE DTE. |  |  | ORD/000170/2022-2023 | 305/CMSD-I | 08/07/2022 | 15 | MENAKA ENTERPRISE | 4.89 | 4.18 | 100
3554 | Midnapore Mechanical |  | Electric quotation for Baharampur PWSS Tube Well- I in connection Madhakhali CCC (2004185409) |  |  | BILL/00062/2022-2023 | BP-2022-23-105 | 27/02/2023 | 0 | WBSEDCL | 0.47 | 0 | 0
3555 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-2 under Baharampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001131/2022-2023 | 2112/W/MMD | 28/11/2022 | 120 | ALPHA ENTERPRISE | 10.92 | 8.34 | 100
3556 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baharampur Piped Water Supply Scheme., Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. |  |  | ORD/001342/2022-2023 | 35/W/MMD | 04/01/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 11.58 | 100
3557 | Midnapore Mechanical |  | Supply delivery of Voltage Stabilizer and submersible pump motor set at PH No. II of Baharampur Water Supply Scheme under H.E.S.D. under Midnapore Mechanical Division, P.H.E. Dte. |  |  | ORD/002188/2022-2023 | 291/MMSD-I | 23/03/2023 | 10 | ALPHA ENTERPRISE | 3.06 | 3.06 | 100
3558 | Midnapore Mechanical |  | Electric quotation MADHAKHALI CCC at Baharampur T/W-II Pin-721444 |  |  | VCH/002772/2022-2023 | BP-2022-23-60 | 23/11/2022 | 0 | WBSEDCL | 0.61 | 0 | 0
3559 | Tamluk Division | Contai Sub-Division | Quotation for new service connection at TW-III of Basudebberia ws scheme under MMD,PHE Dte, Block-Contai-III, Marishda CCC Application no-2004765941 Con ID-204324592 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00592/2024-2025 | BP-2024-25-290 | 29/07/2024 | 0 | WBSEDCL | 6.15 | 0 | 0
3560 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000101/2022-2023 | 477/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
3561 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia. Sluice Valve for Augmentation of Basudebberia Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000126/2022-2023 | 630/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.82 | 4.82 | 100
3562 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Basudebberya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2021-2022 | 1185/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.84 | 9.56 | 100
3563 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2023-2024 | 541/TD | 12/05/2023 | 508 | GRAND CONSTRUCTION | 9.36 | 4.6 | 60
3564 | Tamluk Division | Contai Sub-Division | Laying of Washout pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Basudebberiya PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000292/2024-2025 | 3057/TD | 19/09/2024 | 640 | ABHIJIT BERA | 19.56 | 0 | 100
3565 | Tamluk Division | Contai Sub-Division | Relaying of Existing Damaged Distribution Pipe Line With allied Works for Augmentation Of Basudebberiya Water Supply Scheme in Deshpran Block Of Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000333/2023-2024 | 807/TD | 30/05/2023 | 30 | A-PLUS | 20.92 | 20.92 | 100
3566 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line and providing of FHTC for Augmentation of Basudebberiya Water Supply Scheme In Deshpran Block in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000471/2021-2022 | 1946/TD | 03/03/2022 | 180 | M/S A.R. ENTERPRISE | 490.93 | 393.51 | 90
3567 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Basudebberiya Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000636/2024-2025 | 849/TD | 19/03/2025 | 60 | SMMD | 3.59 | 0 | 0
3568 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Basudebberiya Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000887/2022-2023 | 440 / CSD | 20/03/2023 | 15 | GIRI ENTERPRISE | 0.91 | 0.91 | 0
3569 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000010/2021-2022 | 1252/TD | 13/12/2021 | 0 | Resource Division | 19.67 | 0 | 0
3570 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000037/2021-2022 | 1953/TD | 04/03/2022 | 0 | Resource Division | 16.73 | 0 | 0
3571 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR Basudebberya W/S SCH (TW-I), DESHPRAN BLOCK UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000247/2022-2023 | 1344/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 17.25 | 100
3572 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 30.04 | 40
3573 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya in Block - Deshopran under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001449/2022-2023 | 159/W/MMD | 02/02/2023 | 180 | MUKHERJEE ART CENTRE | 25.26 | 12.02 | 54
3574 | Tamluk Division |  | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied work under Narikeldaha & its adjoining moujas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000155/2021-2022 | 1154/TD | 30/11/2021 | 210 | ARABINDA GHOSH | 523.45 | 518.48 | 100
3575 | Tamluk Division |  | Land filling with earth at 2nd. T/W site at Narikeldaha W/S scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. |  |  | ORD/000166/2022-2023 | 712/TSD | 16/06/2022 | 7 | GHOSH ENTERPRISE | 1.43 | 1.43 | 100
3576 | Tamluk Division |  | Land filling with earth at H/W site at Narikeldaha Water Supply scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division. PHE Dte. |  |  | ORD/000207/2022-2023 | 860/TD | 21/07/2022 | 7 | GHOSH ENTERPRISE | 4.79 | 4.79 | 100
3577 | Tamluk Division |  | Interconnection with laying of 150 mm dia DI (K-9) rising main from H/W site tube well to 2nd T/W site at Narikeldaha PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. |  |  | ORD/000231/2022-2023 | 972/TD | 03/08/2022 | 15 | GHOSH ENTERPRISE | 5.7 | 3.7 | 100
3578 | Tamluk Division |  | Additional work of Plinth protection, surface drain, septic tank, soak well, plumbing work, brick work,water arrangement of Toilet at 2nd T/W site for Narikeldaha Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000350/2022-2023 | 1172/TSD | 07/09/2022 | 25 | GHOSH ENTERPRISE | 2.27 | 2.27 | 100
3579 | Tamluk Division |  | Construction of M.S. Structure over irrigation canal to support 200 mm dia. DI (K-7) distribution pipe under Narikeldaha Water Supply Scheme at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=40.00 Mtr ) |  |  | ORD/000395/2022-2023 | 1429/TD | 26/09/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.48 | 4.48 | 100
3580 | Tamluk Division |  | Installation of display Board (80 nos.) at different work site for PHE Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000445/2024-2025 | 3544/TD | 14/11/2024 | 25 | MISHRA ENTERPRISE | 13.33 | 5.91 | 100
3581 | Tamluk Division |  | Functional Household Tap Connection (FHTC=798 nos)at Narikeldaha water supply scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000467/2023-2024 | 1447/TD | 13/07/2023 | 30 | GHOSH ENTERPRISE | 31.51 | 31.45 | 100
3582 | Tamluk Division |  | Laying Distribution system of Left-out portion of pipe line at Narikeldaha Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000566/2023-2024 | 2046/TD | 25/08/2023 | 30 | GHOSH ENTERPRISE | 88.3 | 88.28 | 100
3583 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000578/2021-2022 | 2049/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.32 | 100
3584 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000580/2021-2022 | 2050/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.1 | 100
3585 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 1685/TD | 31/01/2022 | 0 | Resource Division | 12.47 | 0 | 0
3586 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 1681/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
3587 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000076/2021-2022 | 1832/TD | 15/02/2022 | 0 | Resource Division | 36.27 | 0 | 0
3588 | Tamluk Division |  | Bill for WBSEDCL for Quotation charges of Narikeldaha PWSS under Moyna Block under Tamluk Division, PHE Dte. |  |  | VCH/000572/2022-2023 | BP-2022-23-272 | 29/08/2022 | 0 | WBSEDCL | 9.17 | 0 | 0
3589 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/001258/2022-2023 | 2188/W/MMD | 12/12/2022 | 120 | S.S.GHORAI | 13.09 | 12.3 | 75
3590 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/001259/2022-2023 | 2189/W/MMD | 12/12/2022 | 120 | MENAKA ENTERPRISE | 13.09 | 12.32 | 100
3591 | Tamluk Division |  | Retrofitting to accommodate .FHTC (152 nos.)(Balance work) and laying of left-out portion with uPVC pipeline due to uncovered area of Dona Zone-II Water Supply Scheme and its adjoining mouzas Water Supply Scheme at different nodal point under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000204/2021-2022 | 1267/TD | 13/12/2021 | 25 | TARUN KOLEY | 46.72 | 45.8 | 100
3592 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3593 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000125/2022-2023 | 628/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.21 | 4.21 | 100
3594 | Tamluk Division | Contai Sub-Division | Renovation work of spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum for Augmentation of Sankarpur Water Supply Scheme within Block Contai- III under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000172/2022-2023 | 392 / CSD | 12/07/2022 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.43 | 2.34 | 100
3595 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd Tube Well site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2024-2025 | 2323/TD | 23/07/2024 | 120 | DIPANKAR MAITY | 4.96 | 0 | 100
3596 | Tamluk Division | Contai Sub-Division | Continuation work order for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2022 to 30/06/2023. (12 Months) Vehicle No-WB-31/6974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000222/2022-2023 | 357/CSD | 30/06/2022 | 365 | SABITA PRADHA | 1.49 | 4.57 | 100
3597 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Shankarpur Water Supply Scheme (Mouza - Kukraul, JL No. - 468, Plot No. - 66) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2022-2023 | 980/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.67 | 100
3598 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Sankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000276/2024-2025 | 2903/TD | 10/09/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 11.57 | 0 | 100
3599 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,P.H.E. Dte., Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000313/2022-2023 | 1226/TD | 07/09/2022 | 45 | PATHIK PABAN NANDI | 359.47 | 356.17 | 99
3600 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shankarpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000316/2021-2022 | 1609/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 3.54 | 100
3601 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Augmentation of Shankarpur & adjoining mouzas Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000418/2024-2025 | 3476/TD | 06/11/2024 | 40 | KOUSHIK MALLICK | 7.56 | 0 | 100
3602 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000427/2023-2024 | 717/TD | 24/05/2023 | 60 | JASODA ENTERPRISE | 3.73 | 3.67 | 100
3603 | Tamluk Division | Contai Sub-Division | Rising main and other allied works Augmentation of Shankarpur W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000494/2023-2024 | 1092/CSD | 06/06/2023 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.58 | 0.68 | 100
3604 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-104.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001199/2023-2024 | 820/TD | 05/03/2024 | 180 | S R TRADING CORPORATION | 12.57 | 0 | 100
3605 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2022-2023 | 411/TD | 25/05/2022 | 0 | Resource Division | 18.52 | 0 | 0
3606 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000088/2022-2023 | 1265/TD | 12/09/2022 | 0 | Resource Division | 13.3 | 0 | 0
3607 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SHANKARPUR Water Supply Scheme T/W-III, (Ref. ID-204049544) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01682/2023-2024 | BP-2023-24-168 | 04/08/2023 | 0 | WBSEDCL | 4.93 | 0 | 0
3608 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
3609 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000064/2023-2024 | 1223/W/MMD | 25/04/2023 | 180 | THE GODFATHER TRADING COMPANY | 11.96 | 11.75 | 100
3610 | Tamluk Division |  | Retrofitting to accommodate FHTC (Balance work) (951 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-III, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000407/2021-2022 | 1907/TD | 23/02/2022 | 40 | JAYANTA KUMAR MONDAL | 82.25 | 77.04 | 100
3611 | Tamluk Division | Digha Sub-Division | Providing FHTC under JJM in Gobra PWSS within Ramnagar-II Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000299/2021-2022 | 1640/TD | 19/01/2022 | 100 | M/S CARE | 122.42 | 92.17 | 80
3612 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2021-2022 | 1749/TD | 08/02/2022 | 0 | Resource Division | 14.03 | 0 | 0
3613 | Tamluk Division |  | Providing 1412 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000143/2022-2023 | 719/TD | 29/06/2022 | 40 | S.D. CONSTRUCTION | 64.5 | 64.48 | 100
3614 | Tamluk Division |  | Providing 1450 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur |  |  | ORD/000615/2021-2022 | 2203/TD | 21/03/2022 | 35 | TAPAS SANTRA | 78.78 | 78.78 | 100
3615 | Tamluk Division |  | Instalation of display Board at different work site of Paschimbetiya Retrofitting PWSS in Contai - III Block, Mahammadpur Retrofitting PWSS in Bhagwanpur - I Block, Baharampur, Arjunnagar Retrofitting PWSS in Bhagwanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/001187/2023-2024 | 2335/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0.83 | 100
3616 | Tamluk Division |  | Retrofitting to accommodate FHTC (2753 nos) and laying of left-out uPVC pipeline due to uncovered area of this zone at different nodal point under JJM in Uttar Dhalhara Zone-II Water Supply Scheme for Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in the District of Purba medinipur. |  |  | ORD/000298/2021-2022 | 1634/TD | 19/01/2022 | 120 | M/S CARE | 135.49 | 63.79 | 80
3617 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000073/2021-2022 | 2349/TD | 31/03/2022 | 0 | Resource Division | 15.14 | 0 | 0
3618 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1116/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
3619 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandibeniya Zone-I PWSS within Moyna Dev. Block .in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000297/2021-2022 | 1633/TD | 19/01/2022 | 90 | ARABINDA GHOSH | 105.61 | 104.47 | 100
3620 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000199/2023-2024 | 1100/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
3621 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Dakshin Mechogram PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2022-2023 | 442/TD | 31/05/2022 | 15 | SWADHIN KUMAR CHAKRABORTY | 3.34 | 3.34 | 100
3622 | Tamluk Division | Tamluk Sadar Sub-Division | 1(One) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Dakshin Mechogram Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 267/TD | 20/04/2023 | 45 | TARUN KHATUA | 13.06 | 12.52 | 96
3623 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Mechogram Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2021-2022 | 1190/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.28 | 5.28 | 100
3624 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000306/2021-2022 | 1667/TD | 25/01/2022 | 120 | SWADHIN KUMAR CHAKRABORTY | 135.54 | 135.32 | 100
3625 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system of pipe line and its allied works for Dakshin Mechogram & its adjoining mouzas Water Supply Scheme at Panskura-I Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 1146/TD | 31/08/2022 | 20 | M/S. CHANDI CHARAN MISHRA & CO. | 14.56 | 14.4 | 100
3626 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000307/2021-2022 | 1668/TD | 25/01/2022 | 120 | M/S. CHANDI CHARAN MISHRA & CO. | 134.86 | 123.22 | 100
3627 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation Of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000734/2022-2023 | 2552/TD | 24/01/2023 | 60 | FARID UDDIN AHMED | 43.27 | 25.35 | 100
3628 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2021-2022 | 1256/TD | 13/12/2021 | 0 | Resource Division | 0.59 | 0 | 0
3629 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2022-2023 | 419/TD | 25/05/2022 | 0 | Resource Division | 1.16 | 0 | 0
3630 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2021-2022 | 1730/TD | 02/02/2022 | 0 | Resource Division | 12.11 | 0 | 0
3631 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00015/2023-2024 | BP-2023-24-1 | 13/04/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
3632 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money for Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00645/2022-2023 | BP-2022-23-934 | 30/03/2023 | 0 | WBSEDCL | 4.34 | 0 | 0
3633 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000158/2021-2022 | 1162/TD | 01/12/2021 | 7 | HORIZEN | 7.18 | 7.16 | 100
3634 | Tamluk Division | Tamluk Sadar Sub-Division | Leftout FHTC- 15 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Uttar Sonamui Water Supply Scheme under Uttar Sonamui Gram Panchayat Area within Tamluk-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000200/2024-2025 | 1061/TSD | 19/07/2024 | 84 | DIPANKAR MALAKAR | 0.97 | 0.72 | 100
3635 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2022-2023 | 904/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.84 | 100
3636 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000219/2022-2023 | 905/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.53 | 100
3637 | Tamluk Division | Tamluk Sadar Sub-Division | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000229/2022-2023 | 970/TD | 03/08/2022 | 15 | NARAYAN MANDAL | 10.6 | 10.59 | 100
3638 | Tamluk Division | Tamluk Sadar Sub-Division | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000230/2022-2023 | 971/TD | 03/08/2022 | 15 | KRISHNENDU SEKHAR DAS | 8.3 | 8.29 | 100
3639 | Tamluk Division | Tamluk Sadar Sub-Division | Supply & Delivery of different dia DI Specials for Laying of Distribution Main (K-7) of Different works for providing functional house hold tap connection(FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000331/2022-2023 | 1175/TSD | 09/09/2022 | 15 | SK. NUR ISLAM | 1.92 | 1.77 | 100
3640 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 810 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000340/2021-2022 | 1773/TD | 08/02/2022 | 1336 | NARAYAN MANDAL | 74.62 | 68.32 | 95
3641 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 388 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000341/2021-2022 | 1774/TD | 08/02/2022 | 30 | ADHIKARY CONSTRUCTION | 42.02 | 31.98 | 95
3642 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 533 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Bhandarberya) (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000342/2021-2022 | 1775/TD | 08/02/2022 | 30 | S.D. CONSTRUCTION | 58 | 32.49 | 100
3643 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 510 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-I) (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000343/2021-2022 | 1776/TD | 08/02/2022 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 76.98 | 67.75 | 95
3644 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 858 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Chak Srikrishnapur &Uttar Narikelda) (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000344/2021-2022 | 1777/TD | 08/02/2022 | 40 | NARAYAN CHANDRA DAS | 86.75 | 81.26 | 100
3645 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 484 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme''(Mouza-Payrachali) (PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000345/2021-2022 | 1778/TD | 08/02/2022 | 1467 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 43.68 | 39.07 | 100
3646 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 586 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Ganapatinagar) (PART-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000346/2021-2022 | 1779/TD | 08/02/2022 | 40 | BHOLANATH DEY | 57.93 | 47 | 95
3647 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000556/2022-2023 | 2214/TD | 22/12/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.56 | 0 | 0
3648 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000557/2022-2023 | 2215/TD | 22/12/2022 | 25 | ADHIKARY CONSTRUCTION | 4.46 | 3.93 | 0
3649 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 204 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-II) (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000588/2021-2022 | 2061/TD | 15/03/2022 | 30 | J.M. CONSTRUCTION | 29.04 | 24.61 | 95
3650 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 374 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Kulberya) (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000589/2021-2022 | 2062/TD | 15/03/2022 | 30 | SK. NUR ISLAM | 51.1 | 48.35 | 100
3651 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for Water Supply (as per Deptt. drawing) at 2nd. Tube well site. of Uttar Sonamui Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000731/2023-2024 | 2982/TD | 29/11/2023 | 45 | KRISHNENDU SEKHAR DAS | 7.81 | 4.3 | 100
3652 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia DI(K-9) Rising main From 3 rd Tube Well & 2 nd Tube Well Site to O.H.R. Site and other allied works at Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000842/2022-2023 | 3196/TD | 14/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 5.48 | 0 | 0
3653 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Uttar Sonamui & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000745/2022-2023 | 2550/TD | 24/01/2023 | 738 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 149.76 | 120.36 | 80
3654 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000054/2021-2022 | 1833/TD | 15/02/2022 | 0 | Resource Division | 26.06 | 0 | 0
3655 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000083/2021-2022 | 2191/TD | 21/03/2022 | 0 | Resource Division | 30.92 | 0 | 0
3656 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000222/2023-2024 | 1121/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
3657 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 23.84 | 60
3658 | Tamluk Division | Contai Sub-Division | Payment to WBSEDCL for Quotation Money of Ramchak PWSS from Sapai PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00016/2023-2024 | BP-2023-24-2 | 13/04/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
3659 | Tamluk Division | Contai Sub-Division | Providing FHTC( Functional Household tap connection )For implementation of Har Ghar Jhal Gram / Sajal Gram under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000058/2023-2024 | 133/TD | 10/04/2023 | 20 | MRINAL KANTI PRADHAN | 10.72 | 8.12 | 60
3660 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sapai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000178/2021-2022 | 1187/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.13 | 4.11 | 100
3661 | Tamluk Division | Contai Sub-Division | Repairing Of Pump House and Boundary Wall of Pump House No-I & II under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000313/2023-2024 | 486/TD | 10/05/2023 | 30 | SADDAM DIN | 4.19 | 1.94 | 100
3662 | Tamluk Division | Contai Sub-Division | Augmentation of Sapai Water Supply Scheme by Providing Laying Distribution System and FHTC in Conati-III Block of Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2021-2022 | 1653/TD | 21/01/2022 | 90 | ARUP KUMAR DEY | 223.76 | 205.92 | 100
3663 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development for Additional Tube Well at J.L. No.-171, PLot no.-65/215, Mouza-Chandrikalapunja under Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000343/2022-2023 | 1294/TD | 13/09/2022 | 60 | GITA ENTERPRISE | 4.85 | 3.81 | 100
3664 | Tamluk Division | Contai Sub-Division | Rising main and other allied works for connecting Additional Tube well of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000346/2022-2023 | 1295/TD | 13/09/2022 | 30 | AMIT PAYRA | 4.57 | 3.48 | 100
3665 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional Tubewell Site (JL no. 171, Plot no. 65/215, Mouza-Chandrikalapunja) of Sapai Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2021-2022 | 1993/TD | 07/03/2022 | 21 | PRANTIK DRILLING AGENCY | 12.08 | 8.76 | 100
3666 | Tamluk Division | Contai Sub-Division | Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method with 150 dia. uPVC Steiner of 30 m length for replacement of 1st Tube Well for Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000577/2024-2025 | 455/TD | 04/02/2025 | 40 | PRANTIK DRILLING AGENCY | 13.3 | 0 | 0
3667 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir (OHR)Site, Mouza -Sapai, J.L no - 176, under Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 76.00 mtr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000661/2022-2023 | 2346/TD | 10/01/2023 | 30 | JASODA ENTERPRISE | 10.32 | 8.76 | 100
3668 | Tamluk Division | Contai Sub-Division | Supply & Delivery of CIDF Sluice Valve for laying of distribution pipe line by UPVC pipes with allied works for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000662/2021-2022 | 2224/TD | 24/03/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.31 | 4.31 | 100
3669 | Tamluk Division | Contai Sub-Division | Repairing of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000662/2022-2023 | 2347/TD | 10/01/2023 | 60 | BARH CONSTRUCTION | 14.41 | 8.54 | 0
3670 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2021-2022 | 1251/TD | 13/12/2021 | 0 | Resource Division | 0.35 | 0 | 0
3671 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000036/2021-2022 | 1866/TD | 17/02/2022 | 0 | Resource Division | 5.42 | 0 | 0
3672 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation bill of Sapai T/W-III ,P.O.-Bahitrakunda under Marishda CCC (Memo No. 2004155106) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00050/2022-2023 | BP-2022-23-100 | 10/01/2023 | 0 | WBSEDCL | 0.47 | 0 | 0
3673 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2023-2024 | 1394/W/MMD | 01/06/2023 | 180 | BHABANI PRASAD MANNA | 11.59 | 0 | 80
3674 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well I under Sapai water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001143/2022-2023 | 2124/W/MMD | 28/11/2022 | 120 | DEBKUMAR BASU | 11.15 | 10.8 | 0
3675 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village- Saripur,J.L. No-92 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000110/2020-2021 | 2466/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.85 | 0 | 100
3676 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village- Damodarpur,J.L. No-93 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000111/2020-2021 | 2467/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.46 | 0 | 100
3677 | Tamluk Division |  | Retrofitting to accommodate FHTC (53 nos) under JJM within Saripur PWSS(Balance Work), Block- Chandipur in the District of Purba Medinipur |  |  | ORD/000222/2021-2022 | 639/TSD | 26/10/2021 | 20 | NARAYAN MANDAL | 2.52 | 1.69 | 100
3678 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000216/2021-2022 | 123/W | 07/07/2021 | 0 | NARAYAN MANDAL | 1.54 | 0 | 0
3679 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000217/2021-2022 | 124/W | 07/07/2021 | 0 | NARAYAN MANDAL | 2 | 0 | 0
3680 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000597/2020-2021 | 644/W | 13/01/2021 | 0 | NARAYAN MANDAL | 26.31 | 0 | 0
3681 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000608/2020-2021 | 648/W | 25/01/2021 | 0 | NARAYAN MANDAL | 25.46 | 0 | 0
3682 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767136/QUOT/03 DT. 07-06-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204325528 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00594/2024-2025 | BP-2024-25-291 | 29/07/2024 | 0 | WBSEDCL | 21.24 | 0 | 0
3683 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 26.98 | 51
3684 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Chalti PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001279/2023-2024 | 1052/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
3685 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000080/2024-2025 | 2952/TD | 12/09/2024 | 0 | Resource Division | 6.76 | 0 | 0
3686 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000123/2022-2023 | 2404/TD | 16/01/2023 | 0 | Resource Division | 49.91 | 0 | 0
3687 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004945784/QUOT/03 DT. 05-11-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204429932 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03007/2024-2025 | C112423558564 | 19/11/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
3688 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHALTI and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001411/2022-2023 | 2422/W/MMD | 31/12/2022 | 882 | P.K.ENGINEERING | 22.8 | 17.61 | 90
3689 | Tamluk Division | Contai Sub-Division | Ancillary Work of Reinforcement for reinforced cement concrete work for Constrution of R.C.C Elevated Reservoir of Capacity 900 cum and staging height 20.00mtr. With allied work including supply of all labour & material of Augmentation of Contai Saline Area Zone-III (PHASE-A) & its adjoining maujas water supply scheme within Contai-I Block under Contai sub- Division of Tamluk Division, P.H.E.Dte. Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000192/2023-2024 | 393/TD | 27/04/2023 | 40 | TAPAS SANTRA | 48.63 | 47.68 | 60
3690 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC (7341 Nos) with construction of R.C.C. Elevated Reservoir of capacity 900cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000514/2022-2023 | 2062/TD | 09/12/2022 | 935 | TAPAS SANTRA | 1130.28 | 941.81 | 80
3691 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000701/2023-2024 | 3115/TD | 05/12/2023 | 40 | TAPAS SANTRA | 115.73 | 115.64 | 100
3692 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augmentation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000856/2023-2024 | 00/TD | 09/01/2024 | 40 | TAPAS SANTRA | 0 | 0 | 0
3693 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, and Pump House, under JJM with allied work for Augmentation of Contai Saline area Zone-III( Phase-B) in Contai-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001153/2023-2024 | 561/TD | 15/02/2024 | 481 | PULAK KUMAR SAMANTA | 46.1 | 3.51 | 25
3694 | Tamluk Division | Contai Sub-Division | Replacement of Damaged Existing DI/CI pipe line with HPPE Pipe line With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001198/2023-2024 | 849/TD | 06/03/2024 | 30 | TAPAS SANTRA | 52.89 | 37.93 | 100
3695 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000028/2023-2024 | 613/TD | 17/05/2023 | 0 | Resource Division | 45.22 | 0 | 0
3696 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000107/2022-2023 | 1662/TD | 03/11/2022 | 0 | Resource Division | 263.84 | 0 | 0
3697 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at CONTAI SALINE AREA ZONE-III, T/W NO-I, PHASE-B W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004696671/QUOT/03 DT. 24-04-2024 Application NO- 2004696671 Application type-New connection Consumer Id- 204284086 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00705/2024-2025 | BP-2024-25-146 | 09/05/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
3698 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001909/2022-2023 | 810/W/MMD | 24/03/2023 | 180 | SUBHAM ENTERPRISE | 13.59 | 6.32 | 47
3699 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 14.62 | 100
3700 | Tamluk Division | Contai Sub-Division | Laying Rising Main DI(K-9) pipe line with interconnection, Construction of 3.60 mtr. X 3.00 mtr. Size Switch Room cum Chlorine Room & Boundary Wall at 3rd Boosting TW site (Mouza-Jabda, J.L No-225, Plot No-887) of Argoal PWSS in Patashpur-II within Contai Sub-Division of Tamluk Division,PHE Dte.(Length-50.00 mtr.) (for Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2023-2024 | 1521/TD | 18/07/2023 | 30 | SK. SARFARAJ | 33.57 | 9.68 | 90
3701 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000018/2023-2024 | 357/TD | 26/04/2023 | 0 | Resource Division | 17.67 | 0 | 0
3702 | Central Drilling | Contai Sub-Division | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000191/2020-2021 | 63/CMSD-I | 18/03/2021 | 3 | ASHUTOSH DAS & CO | 0.49 | 0 | 100
3703 | Midnapore Mechanical | Contai Sub-Division | Electric quotation bill for WBSEDCL at TW III of Argoal WS Scheme (Ref. ID - 203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00060/2023-2024 | BP-2023-24-7 | 18/04/2023 | 0 | WBSEDCL | 0.74 | 0 | 0
3704 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. Block ¿ Potashpur II within the Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001738/2022-2023 | 640/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.57 | 13.27 | 100
3705 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC (2244 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - II Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000494/2022-2023 | 1891/TD | 24/11/2022 | 1283 | MAA ANANDAMAYEE | 407.46 | 227.81 | 50
3706 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 23.98 | 90
3707 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-II Water Supply scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000577/2023-2024 | 2185/TD | 01/09/2023 | 830 | MAA ANANDAMAYEE | 84.88 | 37.42 | 60
3708 | Tamluk Division | Contai Sub-Division | Brick bats road due to smoothly carring Rig Machine and soil testing equipment for Head Works site at Mouza-Pora Chingra, J.L. NO.-155, under Bajkul Zone-II W/S Scheme (Augmentation) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000841/2023-2024 | 1705/CSD | 31/08/2023 | 15 | M/S MONDAL CONSTRUCTION & CO. | 0.8 | 0 | 100
3709 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000889/2021-2022 | 1803/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.32 | 100
3710 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2023-2024 | 608/TD | 17/05/2023 | 0 | Resource Division | 13.82 | 0 | 0
3711 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000116/2022-2023 | 1671/TD | 03/11/2022 | 0 | Resource Division | 39.54 | 0 | 0
3712 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill for the Service connection at T/W NO-I , ZONE-II Of BAJKUL W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Ref. Memo No-KJR/QTN/200 DT. 25-06-2024 Application NO- 100000111551 DT. 25-06-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860303091 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01400/2024-2025 | BP-2024-25-379 | 08/07/2024 | 0 | WBSEDCL | 0.53 | 0 | 0
3713 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAJKUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204114262) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03058/2023-2024 | BP-2023-24-374 | 01/12/2023 | 0 | WBSEDCL | 3.48 | 0 | 0
3714 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAJKUL Water Supply Scheme T/W-II, Zone- II, (Ref. ID-204114267) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03059/2023-2024 | BP-2023-24-375 | 02/12/2023 | 0 | WBSEDCL | 4.77 | 0 | 0
3715 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill for the Service connection at T/W NO-I Of BAJKUL,ZONE-II W/S Scheme AT PORACHINGRA(NEAR CHURCH) under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Ref. Memo No-KJR/QT/479 DT. 10-02-2026 Application NO- 100000158771 DT. 10-02-2026 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860363881 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/05693/2025-2026 |  | 19/02/2026 | 0 | WBSEDCL | 0.73 | 0 | 0
3716 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001980/2022-2023 | 819/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 23.7 | 21.81 | 85
3717 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3718 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- D [Bamania Jangal(62) part, Chhota Sijua(64) part, Parihara(65), Panchberya(67) part, Dhandali Bar(139) part, Bhaja Chauli(140)]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000054/2022-2023 | 322/TD | 11/05/2022 | 45 | SRIMANTA KUMAR MAITY | 287.16 | 264.06 | 92
3719 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- B [Dhandi Bar (139) part]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000080/2022-2023 | 385/TD | 20/05/2022 | 30 | SWARUPANANDA DAS | 120.93 | 117.93 | 100
3720 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART - A [ Bamania(74), Ugalpur(73), Kajli(70), Katmuri(69), Amratalia(68), Panchberya(67) part]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000081/2022-2023 | 395/TD | 23/05/2022 | 30 | PRANAB KUMAR DAS | 118.3 | 93.84 | 65
3721 | Tamluk Division | Contai Sub-Division | Augmentation Of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART-C [Bamania Jangal (62) part, Sijua (63), Chhota Sijua (64) part.] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000086/2022-2023 | 433/TD | 27/05/2022 | 981 | SNEHESH SEN | 113.07 | 89.13 | 100
3722 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000128/2022-2023 | 629/TD | 23/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.44 | 4.44 | 100
3723 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhajachauli Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000177/2021-2022 | 1186/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.34 | 9.91 | 100
3724 | Tamluk Division | Contai Sub-Division | Washout pipeline, Repairing of OHR, Pump House no 1 under JJM with allied work of Bhajachauli PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000291/2024-2025 | 3056/TD | 19/09/2024 | 186 | SUBHENDU HAZRA | 31.12 | 0 | 50
3725 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr. x 3.00 mtr. size switch Room cum chlorine room without sanitary & water supply arrangements including plinth protection at 3rd TW site for Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000361/2023-2024 | 929/TD | 01/06/2023 | 25 | DEBABRATA DAS | 3.53 | 3.53 | 100
3726 | Tamluk Division | Contai Sub-Division | Rising main and other allied works of 3rd Tube Well for Augmentation of BHAJACHAULI W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2023-2024 | 930/TD | 01/06/2023 | 25 | DEBABRATA DAS | 4.31 | 2.81 | 100
3727 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for BHAJACHAULI PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-160.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000363/2023-2024 | 931/TD | 01/06/2023 | 40 | DEBABRATA DAS | 22.69 | 21.07 | 100
3728 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line & Accommodate FHTC (146 nos) under JJM with allied work for Left out Areas of BHAJACHAULI- PWSS in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000576/2023-2024 | 2198/TD | 01/09/2023 | 30 | SUBHENDU HAZRA | 19.54 | 18.3 | 100
3729 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 857 | B. K. ENTERPRISE | 34.31 | 16.53 | 0
3730 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room at 2nd TW site at Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000726/2023-2024 | 2971/TD | 28/11/2023 | 45 | SUBHENDU HAZRA | 3.53 | 3.34 | 100
3731 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000843/2023-2024 | 2128/CSD | 24/11/2023 | 20 | SAURAV HAZRA | 1.22 | 1.22 | 100
3732 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000006/2022-2023 | 101/TD | 11/04/2022 | 0 | Resource Division | 21.75 | 0 | 0
3733 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000066/2021-2022 | 644/TD | 27/06/2022 | 0 | Resource Division | 23.79 | 0 | 0
3734 | Central Drilling | Contai Sub-Division | Construction of TW (300mm x 200mm x Depth 250 Mtr.) for Bhajachauli WS Scheme (TW-II), Contai-III block within Purba Midnapur District by utilising Skilled Departmental crew & machineries of CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000332/2022-2023 | 414/CDD | 20/05/2022 | 30 | M/S B.P.TRADING CORPORATION | 14.69 | 5.48 | 45
3735 | Central Drilling | Contai Sub-Division | Resistivity Survey & other works of Bhajachauli WS Scheme (TW-III), Contai-III Block under Purba Midnapur District, CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000335/2022-2023 | 1640/CDD | 20/12/2022 | 30 | M/S B.P.TRADING CORPORATION | 12.62 | 10.21 | 100
3736 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BHAJACHAULI Water Supply Scheme T/W-III, (Ref. ID-204050249) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01683/2023-2024 | BP-2023-24-167 | 04/08/2023 | 0 | WBSEDCL | 1.74 | 0 | 0
3737 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001905/2022-2023 | 806/W/MMD | 24/03/2023 | 536 | DEBKUMAR BASU | 13.58 | 12.76 | 100
3738 | Tamluk Division | Contai Sub-Division | Restoration of Hard shoulder at Heria-Mugberia and Itaberia-Mugberia Road after laying pipe line by PHE under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00236/2023-2024 | BP-2023-24-121 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.16 | 0 | 0
3739 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3740 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000100/2022-2023 | 476/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
3741 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 1st Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1228) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000105/2022-2023 | 481/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
3742 | Tamluk Division | Contai Sub-Division | Left-out portion of uncovered area of different dia. uPVC pipeline within Suadighi Zone-II Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000132/2024-2025 | 1910/TD | 07/06/2024 | 717 | SETH ENTERPRISE | 48.35 | 0 | 0
3743 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2022-2023 | 815/TD | 12/07/2022 | 1265 | JAYANTA KUMAR MONDAL | 565.34 | 490.77 | 88
3744 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2022-2023 | 814/TD | 12/07/2022 | 1323 | JAYANTA KUMAR MONDAL | 584.44 | 426.54 | 80
3745 | Tamluk Division | Contai Sub-Division | Boundary Wall Repair at 2nd TW Site and Construction of Toilet at 1st TW site of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000341/2024-2025 | 3339/TD | 22/10/2024 | 40 | BIBEKANANDA DAS | 7.03 | 0 | 0
3746 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-I Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2022-2023 | 1435/TD | 27/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.34 | 7.34 | 100
3747 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements at 1st TW (Head Work) site at Suadighi Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000425/2022-2023 | 1594/TD | 18/10/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 6.94 | 6.32 | 100
3748 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2021-2022 | 1694/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.2 | 4.02 | 100
3749 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000451/2021-2022 | 1695/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.47 | 4.47 | 100
3750 | Tamluk Division | Contai Sub-Division | Laying Rising Main, Earth work filling & Construction of Boundary wall at OHR (1st), 2nd & 3rd Tube Well Site Mouza- Bhupatinagar & Keshaidighi, J.L No.-253,262 for Augmentation of Suadighi Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000490/2023-2024 | 1599/TD | 24/07/2023 | 570 | JAYANTA KUMAR MONDAL | 45.98 | 0 | 0
3751 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for 3rd Tube well J.L no. -257,Plot no. -240, Mouza -Kasba under Suadighi Zone-I Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000530/2022-2023 | 2097/TD | 13/12/2022 | 60 | SMMD | 3.4 | 3.16 | 100
3752 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 2nd Tube well site J.L no. -262,Plot no. -272, Mouza -Keshaidighi under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000531/2022-2023 | 2098/TD | 13/12/2022 | 60 | SMMD | 3.46 | 3.45 | 100
3753 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 3rd Tube well site J.L no. -253,Plot no. -1498, Mouza -Bhupatinagar under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000532/2022-2023 | 2099/TD | 13/12/2022 | 60 | SMMD | 3.4 | 0 | 0
3754 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 0 | 44
3755 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000574/2022-2023 | 2261/TD | 30/12/2022 | 20 | SWASTIK ENTERPRISE | 6.18 | 6.18 | 100
3756 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000575/2022-2023 | 2266/TD | 30/12/2022 | 20 | MAKALI ENGINEERING CORPORATION | 1.01 | 0 | 0
3757 | Tamluk Division | Contai Sub-Division | Rising main, Boundary Wall under JJM with allied work at 3rd TW site for Augmentation of SUADIGHI ZONE-I PWSS in Bhagwanpur-II Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000646/2023-2024 | 2598/TD | 10/10/2023 | 40 | A. R. CONSTRUCTION | 14.76 | 9.66 | 100
3758 | Tamluk Division | Contai Sub-Division | Left out Portion of uncovered area with upvc pipes with allied works of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001225/2023-2024 | 1038/TD | 15/03/2024 | 350 | S.D. CONSTRUCTION | 43.4 | 9.08 | 50
3759 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2022-2023 | 95/TD | 11/04/2022 | 0 | Resource Division | 58.97 | 0 | 0
3760 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000070/2021-2022 | 648/TD | 27/06/2022 | 0 | Resource Division | 21.41 | 0 | 0
3761 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000071/2021-2022 | 649/TD | 27/06/2022 | 0 | Resource Division | 21.19 | 0 | 0
3762 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Suadighi W/S Scheme( TW-III) , Bhagawanpur-II Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000147/2023-2024 | 1453/CDD | 30/11/2023 | 120 | MENAKA ENTERPRISE | 18.35 | 15.83 | 100
3763 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, BLOCK BHAGAWANPUR-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000250/2022-2023 | 151/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.99 | 4.97 | 100
3764 | Central Drilling | Contai Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL INSUADIGHI PWSS, ZONE-II, TW-II, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 149/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.98 | 4.95 | 100
3765 | Central Drilling | Contai Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SUADIGHI PWSS, ZONE-I, TW-I, BLOCK - KHEJURI, DIST PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000252/2022-2023 | 152/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.99 | 4.97 | 100
3766 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN SUADIGHI PWSS, ZONE-II, TW-II, BLOCK-KHEJURI, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000253/2022-2023 | 150/S&WSD | 12/08/2022 | 15 | MENAKA ENTERPRISE | 4.91 | 4.88 | 100
3767 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-I, TW-I, BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000254/2022-2023 | 430/CDD | 23/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.65 | 100
3768 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI PWSS, ZONE-II, TW-II, BHAGAWANPUR -II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2022-2023 | 375/CDD | 13/05/2022 | 30 | MENAKA ENTERPRISE | 14.69 | 5.66 | 100
3769 | Central Drilling | Contai Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 260 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUADIGHI W/S SCH (TW-II), BHAGAWANPUR-II BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1349/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 19.77 | 16.95 | 100
3770 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260mtrs. depth) by utilising Departmental Machineries for Suadighi WS Scheme (TW-I) Bhagwanpur-II block under Purba midnapore Dist., CDD,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000299/2022-2023 | 1348/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 17.03 | 100
3771 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00102/2023-2024 | BP-2023-24-26 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
3772 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme Zone-I, TW-III (Ref. Id-203950247) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00107/2023-2024 | BP-2023-24-38 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
3773 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00111/2023-2024 |  | 28/04/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
3774 | Midnapore Mechanical | Contai Sub-Division | quotation for new power connection at newly sunk t/w at Madhakhali w/s scheme zone -II , T/W - I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00270/2023-2024 |  | 23/05/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
3775 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of SUADIGHI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004740459/QUOT/03 DT. 17-05-2024 Application NO- 2004740459 Application type-New connection Consumer Id- 204309985 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01130/2024-2025 | BP-2024-25-246 | 06/06/2024 | 0 | WBSEDCL | 7.11 | 0 | 0
3776 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SUADIGHI Water Supply Scheme T/W-II, Zone-II (Ref. ID-204020001) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01825/2023-2024 | BP-2023-24-201 | 24/08/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
3777 | Midnapore Mechanical | Contai Sub-Division | Suadighi W/S scheme TW no.-III, Z-I Ref.-860286948 ID-100000094898 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03153/2023-2024 | BP-2023-24-449 | 19/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
3778 | Midnapore Mechanical | Contai Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of MaY"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/09919 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/06210/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.13 | 0 | 0
3779 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001467/2022-2023 | 205/W/MMD | 10/02/2023 | 180 | BALAJI CONSTRUCTION | 40.78 | 34.24 | 70
3780 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001470/2022-2023 | 208/W/MMD | 10/02/2023 | 180 | NIRMAN | 27.16 | 25.53 | 75
3781 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
3782 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3783 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Biramput PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000155/2024-2025 | 2067/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3784 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 215.14 | 75
3785 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000077/2024-2025 | 2951/TD | 12/09/2024 | 0 | Resource Division | 5.79 | 0 | 0
3786 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000167/2022-2023 | 2390/TD | 16/01/2023 | 0 | Resource Division | 43.89 | 0 | 0
3787 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005011642/QUOT/03 DT. 17-12-2024 Application NO- 2005011642 Application type-New connection Consumer Id- 204475405 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03862/2024-2025 | C012539035678 | 21/01/2025 | 0 | WBSEDCL | 3.52 | 0 | 0
3788 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, CONTAI C.C.C. Ref. Memo No-2004614786/QUOT/03 DT. 23-02-2024 Application NO- 2004614786 Application type-New connection Reference Id- 204225082 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04264/2023-2024 | BP-2023-24-792 | 06/03/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
3789 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIRAMPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001599/2022-2023 | 503/W/MMD | 20/03/2023 | 864 | SUJOY RANJAN BHOWMICK | 21.62 | 10.07 | 100
3790 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2046 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NARAYAN DANRI PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000849/2023-2024 | 72/TD | 05/01/2024 | 540 | SRIMANTA KUMAR MAITY | 519.29 | 23.48 | 25
3791 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000243/2022-2023 | 2723/TD | 06/02/2023 | 0 | Resource Division | 15.86 | 0 | 0
3792 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NARAYAN DANRI and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001585/2022-2023 | 468/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 23.68 | 16.85 | 30
3793 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iv)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2023-2024 | 521/TD | 11/05/2023 | 1029 | PRASANTA MONDAL | 8.09 | 3.41 | 35
3794 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(i)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000347/2023-2024 | 876/TD | 01/06/2023 | 45 | TARUN KHATUA | 11.03 | 10.07 | 100
3795 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(ii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000348/2023-2024 | 877/TD | 01/06/2023 | 30 | TARUN KHATUA | 28.18 | 27.54 | 85
3796 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000414/2023-2024 | 1099/TD | 08/06/2023 | 1028 | MAA ANANDAMAYEE | 139.46 | 0 | 2
3797 | Tamluk Division | Haldia Sub-Division | Construction of Retaining wall, Approach road & Earth filling Work in Head work site of Kanchanpur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(length of Retaining wall-120mtr) & (length of Approach road- 60 mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000459/2024-2025 | 3705/TD | 03/12/2024 | 200 | TARUN KHATUA | 17.55 | 0 | 90
3798 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (280 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000877/2022-2023 | 3213/TD | 14/03/2023 | 654 | SK MAIDUL ISLAM | 39.57 | 25.63 | 60
3799 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (200 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000878/2022-2023 | 3214/TD | 14/03/2023 | 30 | G. S. CONSTRUCTION | 34.87 | 26.93 | 79
3800 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000880/2022-2023 | 3216/TD | 14/03/2023 | 60 | THREE MAA ENTERPRISE | 64.69 | 39.91 | 50
3801 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (115 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(i)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000881/2022-2023 | 3238/TD | 15/03/2023 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.62 | 9.32 | 100
3802 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(ii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000882/2022-2023 | 3239/TD | 15/03/2023 | 45 | MAHAPRABHU ENTERPRISE | 9.86 | 2.02 | 21
3803 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000883/2022-2023 | 3240/TD | 15/03/2023 | 1176 | MODERN CONSTRUCTION | 9.69 | 4.86 | 43
3804 | Tamluk Division | Haldia Sub-Division | "G.I pipe column with M.S. Structure for laying of HDPE pipe line with Casing at Kanchanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. " (Total Length= 60.00 mtr, {i) NP-21 to 27= 30.00 mtr + ii) NP-44 to 50= 30.00 mtr .} | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001200/2023-2024 | 727/TD | 28/02/2024 | 30 | TARUN KHATUA | 8.88 | 8.71 | 100
3805 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000152/2023-2024 | 115/TD | 05/01/2024 | 0 | Resource Division | 10.5 | 0 | 0
3806 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000329/2022-2023 | 2987/TD | 27/02/2023 | 0 | Resource Division | 29.7 | 0 | 0
3807 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilizing Departmental Machineries for Kanchanpur W/S Scheme (T/W-I & II), Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000107/2023-2024 | 1389/CDD | 19/09/2023 | 560 | PADMA ENGINEERING & CO. | 31.41 | 12.37 | 100
3808 | Midnapore Mechanical | Haldia Sub-Division | Quotation for Kanchanpur w/s scheme PH II in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216165, App No 2004599558) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04142/2023-2024 | BP-2023-24-756 | 01/03/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
3809 | Midnapore Mechanical | Haldia Sub-Division | Quotation for Kanchanpur w/s scheme PH I in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216166, App No 2004599555) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04143/2023-2024 | BP-2023-24-755 | 01/03/2024 | 0 | WBSEDCL | 5.06 | 0 | 0
3810 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANCHANPUR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001583/2022-2023 | 466/W/MMD | 20/03/2023 | 914 | DEY ENTERPRISE | 23.7 | 11.15 | 45
3811 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 30
3812 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000084/2024-2025 | 2954/TD | 12/09/2024 | 0 | Resource Division | 5.5 | 0 | 0
3813 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000204/2022-2023 | 2406/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0
3814 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KADUA and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002033/2022-2023 | 941/W/MMD | 28/03/2023 | 180 | S.G.ENTERPRISE | 21.6 | 0 | 0
3815 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (325 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000186/2023-2024 | 376/TD | 27/04/2023 | 60 | A. K. SIKDAR | 73.19 | 35.95 | 52
3816 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (322 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000187/2023-2024 | 377/TD | 27/04/2023 | 668 | SWARUPANANDA DAS | 73.44 | 36.55 | 50
3817 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (140 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000188/2023-2024 | 378/TD | 27/04/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 38.62 | 22.81 | 65
3818 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (200 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2023-2024 | 379/TD | 27/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.51 | 22.02 | 60
3819 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (150 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2023-2024 | 380/TD | 27/04/2023 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.52 | 14.8 | 58
3820 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (170 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000191/2023-2024 | 381/TD | 27/04/2023 | 25 | M/S. NEW DINDA ENTERPRISE | 19.14 | 7.88 | 45
3821 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (160 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000252/2023-2024 | 516/TD | 11/05/2023 | 60 | NEW STAR CONSTRUCTION | 84.23 | 60.35 | 73
3822 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Pump House & Accommodate FHTC (375 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000253/2023-2024 | 517/TD | 11/05/2023 | 1178 | S.S.T ENGINEERING | 77.56 | 47.05 | 65
3823 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (195 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000377/2023-2024 | 1016/TD | 06/06/2023 | 1080 | DAS ENTERPRISE | 189.43 | 0 | 10
3824 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Panushi PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001051/2023-2024 | 381/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3825 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Pachahari, Basudevberya,Panusi & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001174/2023-2024 | 2329/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0.62 | 100
3826 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000186/2023-2024 | 635/W | 20/02/2024 | 0 | Resource Division | 12.55 | 0 | 0
3827 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000312/2022-2023 | 2968TD | 27/02/2023 | 0 | Resource Division | 21.55 | 0 | 0
3828 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 75.69 | 11
3829 | Central Drilling | Contai Sub-Division | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000007/2024-2025 | 254/CMSD-I | 26/06/2024 | 182 | SIDDHARTHA CHATTERJEE | 0.89 | 0.97 | 0
3830 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PANUSI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004615668/QUOT/03 DT. 23-02-2024 Application NO- 2004615668 Application type-New connection Consumer Id- 204225684 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02553/2024-2025 | C102412615985 | 04/10/2024 | 0 | WBSEDCL | 11.08 | 0 | 0
3831 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PANSUI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601802/QUOT/03 DT. 15-02-2024 Application NO- 2004601802 Application type-New connection Reference Id- 204217830 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04342/2023-2024 | BP-2023-24-811 | 11/03/2024 | 0 | WBSEDCL | 6.85 | 0 | 0
3832 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
3833 | Tamluk Division | Contai Sub-Division | Shifting of hanging electrical cable of adjacent public building over Talchitkini 2nd pump hose site, Ref. ID : 860325204 Application ID: 100000129374, Date-31.01.2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00087/2025-2026 |  | 08/04/2025 | 0 | WBSEDCL | 0.17 | 0 | 0
3834 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
3835 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 20
3836 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000041/2024-2025 | 1626/TD | 18/06/2025 | 0 | Resource Division | 11.29 | 0 | 0
3837 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000325/2022-2023 | 2991/TD | 27/02/2023 | 0 | Resource Division | 14.06 | 0 | 0
3838 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TALCHITKINI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005238766/QUOT/03 DT. 23-05-2025 MEMO NO: AMR/PHE/261 DT. 23-05-2025 Application NO- 2005238766 Application type-New connection Consumer Id- 204631508 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00901/2025-2026 | W/267/25-26 | 07/08/2025 | 0 | WBSEDCL | 5.57 | 0 | 0
3839 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TALCHITKINI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005238834/QUOT/03 DT. 23-05-2025 MEMO NO: AMR/PHE/260 DT. 23-05-2025 Application NO- 2005238834 Application type-New connection Consumer Id- 204631502 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00902/2025-2026 |  | 02/06/2025 | 0 | WBSEDCL | 9.07 | 0 | 0
3840 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALCHITKINI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001643/2022-2023 | 520/W/MMD | 20/03/2023 | 180 | BIJAN ENTERPRISE | 22.72 | 0 | 0
3841 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0 | 100
3842 | Tamluk Division | Contai Sub-Division | Dismantling & Re-Construction of Boundary Wall and Land Filling at 2nd TW site for Site Preparation for Lowering of Replacement Tube Well at Paschimbetya PWSS for within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000458/2023-2024 | 1495/TD | 17/07/2023 | 15 | PULAK KUMAR SAMANTA | 4.84 | 0 | 30
3843 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000017/2023-2024 | 347/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
3844 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF APRIL'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04356/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.27 | 0 | 0
3845 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF JULY'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04371/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.23 | 0 | 0
3846 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF AUGUST'2025 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04374/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
3847 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
3848 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001907/2022-2023 | 808/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 8.29 | 60
3849 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house - II at 2nd tube well site of Ramnagar Zone-I W/S Scheme within Ramnagar-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000531/2024-2025 | 1316/DSD | 13/01/2025 | 7 | PURNENDU MAITY | 0.94 | 0 | 100
3850 | Tamluk Division | Digha Sub-Division | Laying of Distribution System to accomodate FHTC (3086 Nos) for Augmentation of Ramnagar Water Supply Scheme (Zone-I) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000742/2022-2023 | 2533/TD | 19/01/2023 | 90 | BASANTA KUMAR MAITY | 287.99 | 125.94 | 45
3851 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying of Rising main with distribution pipe line & Accommodate FHTC ( 500 Nos) under JJM with allied work for Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000858/2023-2024 | 169/TD | 09/01/2024 | 45 | BASANTA KUMAR MAITY | 104.58 | 38.48 | 41
3852 | Tamluk Division | Digha Sub-Division | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P-72-74(P)=18.0M, 53-72=298.0M, 34-53(P)=53.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001221/2023-2024 | 1032/TD | 15/03/2024 | 45 | APARNA CONSTRUCTION | 4.72 | 4.72 | 100
3853 | Tamluk Division | Digha Sub-Division | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P- 34-53(P)=233.0M, 26-34=136.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001223/2023-2024 | 1033/TD | 15/03/2024 | 45 | BASANTI ENTERPRISE | 4.69 | 4.67 | 100
3854 | Tamluk Division | Digha Sub-Division | Sinking of 300 mm. x 200 mm. dia. x 270 mtr. deep tube well by direct rotary rig method for 3rd tubewell Site of Ramnagar Zone-I Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001247/2023-2024 | 1079/TD | 16/03/2024 | 212 | PRANTIK DRILLING AGENCY | 19.83 | 3.27 | 100
3855 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000236/2022-2023 | 2613/TD | 02/02/2023 | 0 | Resource Division | 75.91 | 0 | 0
3856 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000286/2022-2023 | 2639/TD | 02/02/2023 | 0 | Resource Division | 19.01 | 0 | 0
3857 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-I Of RAMNAGAR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004957544/QUOT/03 DT. 06-11-2024 Application NO- 2004957544 Application type-New connection Consumer Id- 204440003 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03008/2024-2025 | C112423558120 | 19/11/2024 | 0 | WBSEDCL | 2.66 | 0 | 0
3858 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-I) PWSS, Block Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001916/2022-2023 | 820/W/MMD | 24/03/2023 | 860 | M/S SWAPAN BANERJEE | 27.17 | 0 | 52
3859 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000211/2023-2024 | 433/TD | 03/05/2023 | 1000 | ARABINDA GHOSH | 1233.42 | 423.27 | 65
3860 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000223/2022-2023 | 2676/TD | 06/02/2023 | 0 | Resource Division | 35.6 | 0 | 0
3861 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Chawrakalganda W/S scheme T/W-I Application No.-2004520328 Ref:-204154822 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03168/2023-2024 | BP-2023-24-438 | 18/12/2023 | 0 | WBSEDCL | 8.99 | 0 | 0
3862 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Changrakalganda T/W-II Gourangapur CCC Application No=2005011150 Reference ID=204475173 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03878/2024-2025 | C012539020054 | 21/01/2025 | 0 | WBSEDCL | 3.34 | 0 | 0
3863 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001710/2022-2023 | 627/W/MMD | 20/03/2023 | 957 | P.K.ENGINEERING | 23.7 | 18.1 | 35
3864 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1988 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BETULYA CHAKLAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000206/2023-2024 | 413/TD | 02/05/2023 | 728 | DAS CONSTRUCTION | 517.7 | 0 | 7
3865 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Betula Chaklalpur Water Supply Scheme at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001276/2023-2024 | 1050/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3866 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000122/2023-2024 | 94/TD | 05/01/2024 | 0 | Resource Division | 12.25 | 0 | 0
3867 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000241/2022-2023 | 2726/TD | 06/02/2023 | 0 | Resource Division | 59.37 | 0 | 0
3868 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BETULIACHAKLALPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818516/QUOT/03 DT. 12-07-2024 Application NO- 2004818516 Application type-New connection Consumer Id- 204355509 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01891/2024-2025 | C082410083941 | 08/08/2024 | 0 | WBSEDCL | 13.02 | 0 | 0
3869 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BETULYA CHAKLALPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001323/2022-2023 | 2325/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 55
3870 | Tamluk Division | Haldia Electrical Sub-Division | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -1) , 2. BASANTA CHAK PWSS( PUMP HOUSE 1 & 2), 3. GOKUL NAGAR PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000212/2025-2026 | 57/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.83 | 0 | 100
3871 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 287.31 | 75
3872 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Chongra PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000880/2023-2024 | 202/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
3873 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000003/2024-2025 | 1561/TD | 23/04/2024 | 0 | Resource Division | 11.88 | 0 | 0
3874 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000176/2022-2023 | 2434/TD | 16/01/2023 | 0 | Resource Division | 39.7 | 0 | 0
3875 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation of New service connection at Chongra w/s scheme PH I at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653990 Con ID 204255037) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00235/2024-2025 | BP-2024-25-32 | 15/04/2024 | 0 | WBSEDCL | 15.26 | 0 | 0
3876 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation of New service connection at Chongra w/s scheme PH II at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653966 Con ID 204255035) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00240/2024-2025 | BP-2024-25-33 | 15/04/2024 | 0 | WBSEDCL | 8.93 | 0 | 0
3877 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHONGRA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001362/2022-2023 | 2373/W/MMD | 31/12/2022 | 720 | DIPALI CONSTRUCTION | 23.68 | 13.53 | 50
3878 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chatra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2021-2022 | 1189/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 3.53 | 100
3879 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000302/2021-2022 | 1648/TD | 20/01/2022 | 90 | MAITY ENTERPRISE | 165.08 | 51.25 | 70
3880 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing and Renovation of the Elevated Water Reservoir, Renovation of Switch Room cum Chlorine Room with water supply & sanitary arrangement at 2nd. T/W Site Along with Renovation of Existing Boundary Wall and Renovation of Switch Room cum Chlorine Room with sanitary arrangement at 1st. Tube well site i.c.w Rejuvenation of Ground Water Based Chatra PWSS by Providing Laying Distribution System and FHTC in Sahid Matangini Block under Tamluk Sub Division of Tamluk Division in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000336/2024-2025 | 3335/TD | 22/10/2024 | 436 | TAPAS SANTRA | 14.99 | 0 | 100
3881 | Tamluk Division | Tamluk Sadar Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Chatra Water Supply Scheme in Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000535/2023-2024 | 1836/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 3.13 | 3.13 | 100
3882 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer | Junior Engineer | ORD/000619/2022-2023 | 1345/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 2.39 | 100
3883 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2021-2022 | 1731/TD | 02/02/2022 | 0 | Resource Division | 8.76 | 0 | 0
3884 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000212/2023-2024 | 1112/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
3885 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1914 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SOYA DIGHI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000205/2023-2024 | 412/TD | 02/05/2023 | 1121 | JAYANTA KUMAR MONDAL | 418.27 | 73.15 | 40
3886 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Soya Dighi PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000229/2024-2025 | 2424/TD | 29/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3887 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000172/2023-2024 | 110/TD | 05/01/2024 | 0 | Resource Division | 11.79 | 0 | 0
3888 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000257/2022-2023 | 2680/TD | 06/02/2023 | 0 | Resource Division | 20.04 | 0 | 0
3889 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quatation bill for Swadighi H/W Site W/S SCHEME under MMD,PHE,Dte. BLOCK- Sahid Matangini WBSEDCL SUPPLY OFFICE: Matangini C.C.C Ref. Memo No- 2004992438/Quot/03/1203 DT. 05-12-2024 APPLICATION NO: 2004992438 Consumer Id- 204463808 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03680/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 8.06 | 0 | 0
3890 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Swadighi T/W-II Matangini CCC Application No=2005106565 Consumer ID=204544607 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04967/2024-2025 | W/267/25-26 | 07/08/2025 | 0 | WBSEDCL | 5.18 | 0 | 0
3891 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SOYA DIGHI and ADJOINING MOUJAS, Block - Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002035/2022-2023 | 943/W/MMD | 28/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.79 | 0 | 0
3892 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1376 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GULURI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000108/2023-2024 | 219/TD | 17/04/2023 | 1080 | TAPAS SANTRA | 384.71 | 87.95 | 60
3893 | Tamluk Division | Tamluk Sadar Sub-Division | Land Development work at Headwork Site of Guluria Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000285/2024-2025 | 3050/TD | 19/09/2024 | 15 | S.D. CONSTRUCTION | 5.82 | 5.82 | 100
3894 | Tamluk Division | Tamluk Sadar Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116B of Guluri PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001183/2023-2024 | 742/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.53 | 0 | 0
3895 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000138/2023-2024 | 131/TD | 05/01/2024 | 0 | Resource Division | 8.48 | 0 | 0
3896 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000211/2022-2023 | 2470/TD | 16/01/2023 | 0 | Resource Division | 25.32 | 0 | 0
3897 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for New connection GULARI water supply scheme Head Work Site. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662586 Ref no.-204260849 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00257/2024-2025 | BP-2024-25-28 | 15/04/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
3898 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New electric Quotation as per bill for Guluri water supply scheme, T/W-II Matangini CCC Block- Sahid Matangini Application No.-2004770105 Consumer ID.-204328454 Date.-12/06/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01283/2024-2025 | BP-2024-25-340 | 25/06/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
3899 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GULURI and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001680/2022-2023 | 557/W/MMD | 20/03/2023 | 720 | SHIVAM ENTERPRISE | 22.78 | 10.61 | 75
3900 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kia PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000171/2024-2025 | 2083/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3901 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 261.62 | 51
3902 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000015/2025-2026 | 2073/TD | 12/08/2025 | 0 | Resource Division | 11.69 | 0 | 0
3903 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000128/2022-2023 | 2412/TD | 16/01/2023 | 0 | Resource Division | 35.2 | 0 | 0
3904 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II of KIA W/S Scheme under MMD, PHE, Dte. Block- Egra-I, Egra CCC Ref. Memo no- 2004607232/QUOT/03/3197 Dt. 20-Feb-2024 Application NO- 2004607232 Application type-New connection Reference Id- 204221796 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04144/2023-2024 | bp-2023-24-759 | 01/03/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
3905 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of KIA ws scheme under MMD, PHE DTE, Block-Egra-1, under EGRA CCC. Application no-2004607227, CON ID-204221794. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04145/2023-2024 | BP-2023-24-758 | 01/03/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
3906 | Midnapore Mechanical | Digha Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 0
3907 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002034/2022-2023 | 942/W/MMD | 28/03/2023 | 709 | ORIENTAL ENGINEERING CO. | 22.79 | 7.34 | 90
3908 | Tamluk Division | Contai Sub-Division | Sinking of Tube well, Pump House, 300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Soil investigation & Accommodate FHTC (1581 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Basantia and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000421/2023-2024 | 1412/TD | 12/07/2023 | 180 | JAYANTA KUMAR MONDAL | 413.14 | 102.11 | 85
3909 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000074/2024-2025 | 2949/TD | 12/09/2024 | 0 | Resource Division | 9.74 | 0 | 0
3910 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000314/2022-2023 | 2970/TD | 27/02/2023 | 0 | Resource Division | 21.24 | 0 | 0
3911 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BASANTIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877659/QUOT/03 DT. 12-09-2024 Application NO- 2004877659 Application type-New connection Consumer Id- 204397982 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02496/2024-2025 | C092445108283 | 30/09/2024 | 0 | WBSEDCL | 7.85 | 0 | 0
3912 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTIA AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001725/2022-2023 | 597/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 22.8 | 0 | 0
3913 | Tamluk Division | Digha Sub-Division | Construction of boundary wall, repairing & renovation of Switch Room , existing boundary wall, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (145 Nos) under JJM with allied work for Digha Augmentation (Central Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000322/2024-2025 | 3218/TD | 01/10/2024 | 45 | ONKAR ENTERPRISE | 50.13 | 0 | 100
3914 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Central Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000444/2021-2022 | 1665/TD | 24/01/2022 | 20 | HORIZEN | 3.52 | 3.46 | 100
3915 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2069 nos) under JJM with allied work for Digha Augmentation (Central Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000612/2023-2024 | 2271/TD | 05/09/2023 | 808 | ORIENT CONSTRUCTION | 477.25 | 166.99 | 22
3916 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000054/2023-2024 | 2077/TD | 28/08/2023 | 0 | Resource Division | 38.59 | 0 | 0
3917 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000066/2023-2024 | 2642/TD | 13/10/2023 | 0 | Resource Division | 12.75 | 0 | 0
3918 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-III of Digha Central zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812635 CON ID-204351924 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01584/2024-2025 | C072438487551 | 23/07/2024 | 0 | WBSEDCL | 0.43 | 0 | 0
3919 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Digha Central zone under MMD, PHE Dte, Block-Ramnagar-I, DIGHA CCC Application no-2004812648 CON ID-204351925 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01585/2024-2025 | C072438486724 | 23/07/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
3920 | Midnapore Mechanical | Digha Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of JULY"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/14837 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/06211/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.14 | 0 | 0
3921 | Midnapore Mechanical | Digha Sub-Division | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of March"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/06214/2025-2026 |  | 12/03/2026 | 0 | S.S.GHORAI | 0.13 | 0 | 0
3922 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme in Block Ramnagar I under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000071/2023-2024 | 1241/W/MMD | 28/04/2023 | 180 | SOUMEN ELECTRIC | 33.56 | 33.15 | 100
3923 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
3924 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Augmentation of Digha ( Central Zone) Water supply scheme, Ramnagar - I block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002718/2023-2024 | 1063/W/MMD | 14/03/2024 | 412 | S.S.GHORAI | 29.05 | 17.81 | 100
3925 | Tamluk Division | Digha Sub-Division | Repairing & renovation of Switch Room , existing boundary wall, Store Room, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (125 Nos) under JJM with allied work for Digha Augmentation (Eastern Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000323/2024-2025 | 3219/TD | 01/10/2024 | 426 | M/S. NEW DINDA ENTERPRISE | 28.09 | 0 | 65
3926 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Eastern Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000442/2021-2022 | .1651/TD | 20/01/2022 | 20 | HORIZEN | 4.21 | 4.15 | 100
3927 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2052 nos) under JJM with allied work for Digha Augmentation (Eastern Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000493/2023-2024 | 1591/TD | 21/07/2023 | 1044 | ATCO ENTERPRISE | 642.85 | 185.21 | 40
3928 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000040/2023-2024 | 2066/TD | 28/08/2023 | 0 | Resource Division | 106.76 | 0 | 0
3929 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000064/2023-2024 | 2640/TD | 13/10/2023 | 0 | Resource Division | 13.39 | 0 | 0
3930 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-III of Digha Eastern zone under MMD, PHE Dte, Block-Ramnagar-I,DIGHA CCC Application no-2004812582 CON ID-204351921 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01586/2024-2025 | C072438488216 | 23/07/2024 | 0 | WBSEDCL | 0.88 | 0 | 0
3931 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001996/2022-2023 | 900/W/MMD | 27/03/2023 | 765 | S.S.GHORAI | 25.26 | 14.86 | 100
3932 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 203.47 | 75
3933 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at KASHIBHUIAN BAR PWSS at Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000608/2024-2025 | 189/CSD | 27/01/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
3934 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000091/2024-2025 | 2964/TD | 12/09/2024 | 0 | Resource Division | 3.78 | 0 | 0
3935 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000177/2022-2023 | 2398/TD | 16/01/2023 | 0 | Resource Division | 34.37 | 0 | 0
3936 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KASHI BHUINABAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004804684/QUOT/03 DT. 03-07-2024 Application NO- 2004804684 Application type-New connection Consumer Id- 204347452 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01468/2024-2025 | BP-2024-25-417 | 15/07/2024 | 0 | WBSEDCL | 0.51 | 0 | 0
3937 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KASHI BHUNIABAR W/S Scheme under MMD, PHE, Dte. Block-CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005078216/QUOT/03 DT. 07-02-2025 Application NO- 2005078216 Application type-New connection Consumer Id- 204522790 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04275/2024-2025 | C032555241732 | 17/03/2025 | 0 | WBSEDCL | 12.48 | 0 | 0
3938 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001702/2022-2023 | 591/W/MMD | 20/03/2023 | 180 | S.S.GHORAI | 21.58 | 13.15 | 62
3939 | Tamluk Division | Haldia Sub-Division | New Service connection at Baksichak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004980445, Ref ID 204456236) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01265/2024-2025 | BP-2024-25-648 | 17/01/2025 | 0 | WBSEDCL | 12.43 | 0 | 0
3940 | Tamluk Division | Haldia Sub-Division | Ground water based Bakshichak Water Supply Scheme by providing Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000149/2023-2024 | 276/TD | 20/04/2023 | 1046 | NARAYAN CHANDRA DAS | 84.8 | 52.91 | 39
3941 | Tamluk Division | Haldia Sub-Division | Ground water based Bakshichak Water Supply Scheme by Sub-Soil investigation, Construction of OHR - 50 Cum, within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000384/2023-2024 | 1008/TD | 05/06/2023 | 900 | ZENITH CONSTRUCTION | 45.79 | 0 | 5
3942 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) [Bakshichak PWSS, Bamanpur PWSS, Kanchanpur PWSS & Madhyahingli PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000830/2023-2024 | 618/HSD | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100
3943 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000116/2023-2024 | 80/TD | 05/01/2024 | 0 | Resource Division | 1.53 | 0 | 0
3944 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000328/2022-2023 | 2988/TD | 27/02/2023 | 0 | Resource Division | 4.55 | 0 | 0
3945 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Bakshi Chak W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000119/2023-2024 | 1396/CDD | 19/09/2023 | 30 | DEV AND COMPANY | 13.38 | 0 | 0
3946 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKSHI CHAK, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001671/2022-2023 | 571/W/MMD | 20/03/2023 | 895 | DEY ENTERPRISE | 5.99 | 0 | 95
3947 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (172 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2024-2025 | 3182/TD | 30/09/2024 | 40 | MAITY CONSTRUCTION | 91.37 | 0 | 0
3948 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000457/2022-2023 | 1856/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.22 | 100
3949 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 99 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000704/2023-2024 | 2820/TD | 08/11/2023 | 510 | BASANTA KUMAR MAITY | 282.99 | 0 | 55
3950 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000035/2023-2024 | 2083/TD | 28/08/2023 | 0 | Resource Division | 13.95 | 0 | 0
3951 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000107/2023-2024 | 3010/TD | 29/11/2023 | 0 | Resource Division | 0.61 | 0 | 0
3952 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II , zone-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927974/QUOT/03 DT. 04-10-2024 Application NO- 2004927974 Application type-New connection Consumer Id- 204417444 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02973/2024-2025 | BP-2024-25-779 | 05/11/2024 | 0 | WBSEDCL | 4.94 | 0 | 0
3953 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, ZONE-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927967/QUOT/03 DT. 04-10-2024 Application NO- 2004927967 Application type-New connection Consumer Id- 204417441 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02988/2024-2025 | C112422744521 | 18/11/2024 | 0 | WBSEDCL | 4.99 | 0 | 0
3954 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
3955 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 300 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2022-2023 | 784/TD | 12/07/2022 | 25 | JASODA ENTERPRISE | 63.98 | 63.98 | 100
3956 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-D) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000173/2022-2023 | 785/TD | 12/07/2022 | 1171 | ABHIJIT BERA | 45.02 | 41.98 | 100
3957 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 67 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-E) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000174/2022-2023 | 786/TD | 12/07/2022 | 15 | KAMAL KUMAR BERA | 9.5 | 9.49 | 100
3958 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 217 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-F) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2022-2023 | 787/TD | 12/07/2022 | 1071 | PARIA ENTERPRISE | 42.11 | 34.27 | 100
3959 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 112 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-G) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000177/2022-2023 | 788/TD | 12/07/2022 | 15 | LAKSHMI NARAYAN ENTERPRISE | 19.61 | 19.61 | 100
3960 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 198 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-H) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000178/2022-2023 | 789/TD | 12/07/2022 | 1104 | SUBHENDU HAZRA | 39.49 | 29.43 | 75
3961 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 85 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-J) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000179/2022-2023 | 790/TD | 12/07/2022 | 15 | GIRI ENTERPRISE | 20.05 | 16.08 | 70
3962 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 60 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-K) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000180/2022-2023 | 791/TD | 12/07/2022 | 15 | M/S BLUE BIRD | 10.57 | 7.28 | 80
3963 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-L) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000181/2022-2023 | 792/TD | 12/07/2022 | 20 | AHINDRA BARIK | 44.27 | 0 | 0
3964 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 69 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-N) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000182/2022-2023 | 793/TD | 12/07/2022 | 15 | GITA ENTERPRISE | 8.33 | 4.78 | 75
3965 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-O) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000183/2022-2023 | 794/TD | 12/07/2022 | 15 | S.A. ENTERPRISE | 9.73 | 0 | 0
3966 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-P) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000184/2022-2023 | 795/TD | 12/07/2022 | 998 | HYDROTECH ASSOCIATES | 9.05 | 4.57 | 98
3967 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 6.88 | 99
3968 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-R) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000186/2022-2023 | 797/TD | 12/07/2022 | 1034 | DEBABRATA DAS | 9.59 | 6.14 | 100
3969 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 81 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000209/2022-2023 | 861/TD | 21/07/2022 | 15 | R K CONSTRUCTION | 11.52 | 6.6 | 75
3970 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 67.26 | 95
3971 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 80 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-M) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000272/2022-2023 | 1082/TD | 24/08/2022 | 15 | MUKHERJEE ENTERPRISE | 18.87 | 15.4 | 80
3972 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 70 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-T) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2022-2023 | 1083/TD | 24/08/2022 | 15 | GITA ENTERPRISE | 8.99 | 4.96 | 80
3973 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 99 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-U) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000274/2022-2023 | 1084/TD | 24/08/2022 | 15 | SUBHRANGSHU SEKHAR GIRI | 7.86 | 2.73 | 70
3974 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 150mm, 200mm & 250mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000361/2022-2023 | 1285/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.37 | 4.37 | 100
3975 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 80 mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2022-2023 | 1286/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.79 | 3.79 | 100
3976 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 100 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000363/2022-2023 | 1296/TD | 13/09/2022 | 15 | NANDY UDYOG | 3.62 | 3.62 | 100
3977 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 125 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-A) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000364/2022-2023 | 597 / CSD | 06/09/2022 | 15 | ABHIJIT BERA | 2.46 | 2.46 | 100
3978 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000438/2021-2022 | 1519/TD | 07/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.92 | 100
3979 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000041/2022-2023 | 827/TD | 15/07/2022 | 0 | Resource Division | 210.14 | 0 | 0
3980 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000075/2022-2023 | 1258/TD | 12/09/2022 | 0 | Resource Division | 31.77 | 0 | 0
3981 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 0 | 95
3982 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, with allied works of MANDARMANI & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000342/2023-2024 | 842/TD | 31/05/2023 | 40 | DILIP KUMAR GHOSH | 94.7 | 0 | 0
3983 | Tamluk Division | Digha Sub-Division | Pipe crossing for laying Distribution pipe line to provide FHTC (9 nos.) of Mondarmoni W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (NP- 8 - 6, NP- 48 - 50, NP-50 - 52) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000373/2023-2024 | 1010/TD | 05/06/2023 | 20 | UNIQUE AGENCY | 7.52 | 7.52 | 100
3984 | Tamluk Division | Digha Sub-Division | Sinking of 250mm. X 150mm dia. X 250 mtr. Deep tube well by direct rotary rig method for 3rd Tubewell at Ramnagar-II Block of Mandarmoni Water Supply Scheme under Digha Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000564/2023-2024 | 2050/TD | 25/08/2023 | 401 | PADMA ENGINEERING CO. | 14.21 | 0 | 100
3985 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of MANDARMONI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004957283/QUOT/03 DT. 20-11-2024 Application NO- 2004957283 Application type-New connection Consumer Id- 204450783 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03243/2024-2025 | C122406894909 | 05/12/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
3986 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001999/2022-2023 | 901/W/MMD | 27/03/2023 | 1336 | S.S.GHORAI | 12.63 | 0 | 100
3987 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (176 nos) under JJM with allied work for Palduhi PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000302/2023-2024 | 599/TD | 17/05/2023 | 45 | BASANTA KUMAR MAITY | 61.68 | 27.05 | 45
3988 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of PALDHUI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004851530/QUOT/03 DT. 07-08-2024 Application NO- 2004851530 Application type-New connection Consumer Id- 204372989 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03272/2024-2025 | C122406876082 | 06/12/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
3989 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001992/2022-2023 | 898/W/MMD | 27/03/2023 | 180 | A.S.ENTERPRISE | 12.62 | 0 | 0
3990 | Tamluk Division | Haldia Sub-Division | Way Leave permission from South Eastern Railway for Lakshya PWSS for Application ID-SER-KGP-2023-WL-66 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01827/2023-2024 | BP-2023-24-821 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.52 | 0 | 0
3991 | Tamluk Division | Haldia Sub-Division | Laying of Distribution pipe line for FHTC (920 nos), Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Lakshya & its adjoining mouzas Water Supply Scheme within Mahisadal Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000124/2023-2024 | 254/TD | 19/04/2023 | 30 | HARIPADA PATTANAYAK | 64.14 | 0 | 0
3992 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002001/2022-2023 | 903/W/MMD | 27/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 0 | 0
3993 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for retrofitting to accommodate FHTC (545 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-VII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 251/TD | 19/04/2023 | 25 | MRITYUNJOY PARIA | 32.97 | 30.37 | 100
3994 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to Re- design of pipe line & Accommodate Balance FHTC ( 110 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000254/2024-2025 | 2840/TD | 05/09/2024 | 200 | ONKAR ENTERPRISE | 57.51 | 0 | 100
3995 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000498/2022-2023 | 1934/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.3 | 100
3996 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 321 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000507/2023-2024 | 1729/TD | 31/07/2023 | 936 | ONKAR ENTERPRISE | 194.4 | 62.64 | 55
3997 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-V PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000866/2023-2024 | 189/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
3998 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000046/2023-2024 | 2069/TD | 28/08/2023 | 0 | Resource Division | 14.56 | 0 | 0
3999 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000097/2023-2024 | 3000/TD | 29/11/2023 | 0 | Resource Division | 1.98 | 0 | 0
4000 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme TW no.-I, Z-V Ref.-204156069 Application ID-2004521724 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03157/2023-2024 | BP-2023-24-443 | 19/12/2023 | 0 | WBSEDCL | 3.08 | 0 | 0
4001 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme T/W-II, Z-V Application-no.-2004522973 Ref.-204157003 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03166/2023-2024 | BP-2023-24-444 | 19/12/2023 | 0 | WBSEDCL | 3 | 0 | 0
4002 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-V in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000042/2023-2024 | 1213/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 21.6 | 19.98 | 90
4003 | Tamluk Division | Digha Sub-Division | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-II) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000297/2024-2025 | 3066/TD | 19/09/2024 | 20 | GHOSH ENTERPRISE | 9.46 | 0 | 100
4004 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000461/2022-2023 | 1860./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.1 | 100
4005 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (24 nos) under JJM with allied work for Bathuari (Zone-II) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2023-2024 | 1760/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 294.32 | 102.26 | 50
4006 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000048/2023-2024 | 2071/TD | 28/08/2023 | 0 | Resource Division | 15.21 | 0 | 0
4007 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000101/2023-2024 | 3004/TD | 29/11/2023 | 0 | Resource Division | 0.07 | 0 | 0
4008 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, Zone-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732398/QUOT/03/213 DT. 15-05-2024 Application NO- 2004732398 Application type-New connection Consumer Id- 204305458 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01131/2024-2025 | BP-2024-25-247 | 06/06/2024 | 0 | WBSEDCL | 6.88 | 0 | 0
4009 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2005007909/QUOT/03 DT. 14-12-2024 Application NO- 2005007909 Application type-New connection Consumer Id- 204472925 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03684/2024-2025 | C012524069662 | 09/01/2025 | 0 | WBSEDCL | 7.1 | 0 | 0
4010 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
4011 | Tamluk Division | Digha Sub-Division | Additional boundary wall, repairing & renovation of Switch Room, existing boundary wall, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (105 Nos) under JJM with allied work for Digha Augmentation (Western Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000365/2024-2025 | 3355/TD | 23/10/2024 | 135 | SAHA CONSTRUCTION & CO | 31.05 | 0 | 100
4012 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Western Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000443/2021-2022 | .1652/TD | 20/01/2022 | 20 | HORIZEN | 3.2 | 3.15 | 100
4013 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (782 nos) under JJM with allied work for Digha Augmentation (Western Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000484/2023-2024 | 1569/TD | 19/07/2023 | 1073 | GUHA CONSTRUCTION | 355.55 | 143.04 | 16
4014 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000038/2023-2024 | 2065/TD | 28/08/2023 | 0 | Resource Division | 29.47 | 0 | 0
4015 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000063/2023-2024 | 2639/TD | 13/10/2023 | 0 | Resource Division | 4.82 | 0 | 0
4016 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-IV of Digha western zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812623 CON ID-204351922 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01583/2024-2025 | BP-2024-25-457 | 23/07/2024 | 0 | WBSEDCL | 0.92 | 0 | 0
4017 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Augmentation of Digha ( Western Zone) Water supply scheme, Ramnagar - I block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002719/2023-2024 | 1064/W/MMD | 14/03/2024 | 412 | MENAKA ENTERPRISE | 29.12 | 18.1 | 100
4018 | Tamluk Division | Contai Sub-Division | Withdrawing and Relaying of different dia D.I pipe line at Contai Saline Area Zone-IV PART-III Water Supply Scheme due to Widening and Strengthening along existing alignment of Contai-Rasulpur Road under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000114/2024-2025 | 1907/TD | 07/06/2024 | 25 | TARUN KHATUA | 43.11 | 0 | 0
4019 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1 and Head Works Boundary Wall under JJM with allied work of Contai Saline Area Zone-IV Part-III PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000293/2024-2025 | 3058/TD | 19/09/2024 | 40 | SOUMEN KUMAR GHOSH | 29.17 | 0 | 100
4020 | Tamluk Division | Contai Sub-Division | Installation of display Board of Haipur Retrofitting PWSS at 2 nos TW site in Contai - I Block , Contai S.A. ZONE - IV (PART- I ) PWSS at 1 nos TW site , Contai S.A. ZONE - IV (PART-III) PWSS at 2 nos TW site, in Deshpran Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipurDistrict. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000300/2025-2026 | 1599/CSD | 19/06/2025 | 7 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0 | 100
4021 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room at 2nd TW site for Augmentation of Contai Saline Area Zoner-IV Part-III Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000370/2024-2025 | 3399/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.8 | 0 | 0
4022 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (1427 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-III PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2023-2024 | 1091/TD | 08/06/2023 | 1109 | SUJATA CONSTRUCTION | 214.81 | 84.58 | 50
4023 | Tamluk Division | Contai Sub-Division | Relaying of Damaged Distribution Pipe Line due to Paka Drain work by PWD with allied Works for Contai Saline Area Zone-IV Water Supply Scheme within Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000407/2024-2025 | 3468/TD | 06/11/2024 | 20 | FARID UDDIN AHMED | 3.19 | 3.03 | 100
4024 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-III] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000455/2022-2023 | 1855./TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.23 | 100
4025 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000057/2023-2024 | 2095/TD | 29/08/2023 | 0 | Resource Division | 156.45 | 0 | 0
4026 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000061/2023-2024 | 2637/TD | 13/10/2023 | 0 | Resource Division | 8.79 | 0 | 0
4027 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
4028 | Tamluk Division | Digha Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV line of Bagmari Water Supply Scheme within Egra-II Block | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01476/2023-2024 | BP-2023-24-664 | 15/12/2023 | 0 | WBSEDCL | 4.64 | 0 | 0
4029 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Accommodate FHTC (70 nos)(Phase-II), proposed Rising main and interconnection ,Supply & Delivery of different dia D.I. Specials under JJM with allied works for Augmentation of Bagmari & its adjoining mouzas Water Supply Scheme within Egra- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000115/2024-2025 | 1912/TD | 07/06/2024 | 246 | SOM CONSTRUCTION | 30.97 | 0 | 100
4030 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 100cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bagmari Water Supply Scheme within Egra-I Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000237/2023-2024 | 459/TD | 04/05/2023 | 1241 | AJIT KUMAR SOM | 241.82 | 161.5 | 70
4031 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house H/W site and 2nd TW Site of Bagmari Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000449/2024-2025 | 3616/TD | 27/11/2024 | 519 | SOM CONSTRUCTION | 11.36 | 0 | 0
4032 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bagmari Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000692/2021-2022 | 1741/TD | 03/02/2022 | 20 | HORIZEN | 3.67 | 3.14 | 0
4033 | Tamluk Division | Digha Sub-Division | Instalation of display Board at different work site of Kanakpur Retrofitting PWSS in Potashpur - I Block, Argoal, Bagmari, Pratapdighi Retrofitting PWSS in Potashpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001188/2023-2024 | 2336/CSD | 29/12/2023 | 15 | THE GODFATHER TRADING COMPANY | 0.83 | 0.83 | 100
4034 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000059/2023-2024 | 2635/TD | 13/10/2023 | 0 | Resource Division | 5.72 | 0 | 0
4035 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000105/2023-2024 | 3008/TD | 29/11/2023 | 0 | Resource Division | 5.72 | 0 | 0
4036 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bagmari Water Supply Scheme, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001753/2022-2023 | 632/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 0.64 | 90
4037 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site( Mouza- Bagmari ,J.L. No-116, Plot No- 189), for Bagmari Water Supply Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000067/2023-2024 | 138/TD | 10/04/2023 | 60 | GRAND CONSTRUCTION | 3.99 | 3.58 | 100
4038 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 15.62 | 100
4039 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line, Rising main pipe line with allied works of Bagmari & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PHASE-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000530/2023-2024 | 1825/TD | 07/08/2023 | 576 | DAS ENTERPRISE | 63.16 | 35.49 | 100
4040 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAGMARI Water Supply Scheme T/W-III, (Ref. ID-204067663) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01870/2023-2024 | W/23-24/223 | 01/09/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
4041 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000062/2023-2024 | 1221/W/MMD | 25/04/2023 | 180 | RISHAV ENTERPRISE | 11.94 | 11.49 | 100
4042 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000268/2024-2025 | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 100
4043 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001840/2022-2023 | 756/W/MMD | 23/03/2023 | 720 | UNITED TRADERS | 11.34 | 6.7 | 100
4044 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at SRIKANTHA PWSS at MOYNA Block under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000028/2025-2026 | 07/RWS/TSD | 04/04/2025 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
4045 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at 4 nos {1. SRIKHANTA PWSS,( PUMP HOUSE 1 & 2) 2. KIYARANA PWSS ( PUMP HOUSE -1 &2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000256/2025-2026 | 62/RWS/TSD | 06/05/2025 | 7 | SUDIP MANNA | 0.69 | 0 | 100
4046 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II under Tamluk Division,P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000467/2024-2025 | 3379/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.88 | 0 | 0
4047 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division, P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000468/2024-2025 | 3380/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.88 | 0 | 0
4048 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division, P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000469/2024-2025 | 3381/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.88 | 0 | 0
4049 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2024-2025 | 3385/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.88 | 0 | 0
4050 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Chandipur Block under Tamluk Division,P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000500/2024-2025 | 3390/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.88 | 0 | 0
4051 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patshpur-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000501/2024-2025 | 3391/TD | 28/10/2024 | 10 | TECHNO ENTERPRISE. | 0.88 | 0 | 0
4052 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000502/2024-2025 | 3392/TD | 28/10/2024 | 10 | TECHNO ENTERPRISE. | 0.88 | 0 | 0
4053 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000504/2024-2025 | 3395/TD | 28/10/2024 | 18 | AMITAVA MONDAL | 0.88 | 0 | 0
4054 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000505/2024-2025 | 3383/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.79 | 0 | 0
4055 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II & Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000507/2024-2025 | 3388/TD | 28/10/2024 | 10 | TECHNO ENTERPRISE. | 0.62 | 0 | 0
4056 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-V) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000508/2024-2025 | 3389/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.79 | 0 | 0
4057 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II & Chandipur Block under Tamluk Division,P.H.E Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000509/2024-2025 | 3394/TD | 28/10/2024 | 10 | AMITAVA MONDAL | 0.79 | 0 | 0
4058 | Tamluk Division | Haldia Electrical Sub-Division | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-IV) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000516/2024-2025 | 3396/TD | 28/10/2024 | 10 | TECHNO ENTERPRISE. | 0.88 | 0 | 0
4059 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 115.91 | 75
4060 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000013/2024-2025 | 1571/TD | 23/04/2024 | 0 | Resource Division | 15.86 | 0 | 0
4061 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000172/2022-2023 | 2436/TD | 16/01/2023 | 0 | Resource Division | 23.09 | 0 | 0
4062 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Srikanta w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707397, Ref ID 204292174) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01073/2024-2025 | BP-2024-25-192 | 24/05/2024 | 0 | WBSEDCL | 8.38 | 0 | 0
4063 | Midnapore Mechanical | Haldia Electrical Sub-Division | New service connection at Srikantha w/s scheme PH I ind the district of Purba Medinipur under MMD PHE Dte.(App No 2005056297, Con ID 2045505102) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04274/2024-2025 | C032554814129 | 17/03/2025 | 0 | WBSEDCL | 5.55 | 0 | 0
4064 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SRIKANTHA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001588/2022-2023 | 471/W/MMD | 20/03/2023 | 955 | SOUMEN ELECTRIC | 25.24 | 19.29 | 60
4065 | Tamluk Division | Digha Sub-Division | Canal crossing Structure for laying of Rising main line for Deuli & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. ( Length of Rising main structure-1104.0m ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000302/2024-2025 | 2867/TD | 05/09/2024 | 30 | TAPAS SANTRA | 38.23 | 0 | 100
4066 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 405.43 | 85
4067 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000130/2023-2024 | 84/TD | 05/01/2024 | 0 | Resource Division | 9.77 | 0 | 0
4068 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000262/2022-2023 | 2689/TD | 06/02/2023 | 0 | Resource Division | 43.3 | 0 | 0
4069 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670691/QUOT/03 DT. 05-04-2024 Application NO- 2004670691 Application type-New connection Consumer Id- 204266384 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00298/2024-2025 | BP-2024-25-44 | 18/04/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
4070 | Midnapore Mechanical | Digha Sub-Division | ADDITIONAL Quotation Bill for DEULI W/S SCHEME T/W NO- I , RAMNAGRA -II BLOCK . Ref. MEMO No- PBN/NS/36 Dt. 25.04.2024 Application NO- 100000106413 Dt. 25.04.2024 Reference Id- 860299003 REF CONSUMER ID: 204244736 WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00708/2024-2025 | BP-2024-25-147 | 09/05/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
4071 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004641295/QUOT/03 DT. 12-03-2024 Application NO- 2004641295 Application type-New connection Consumer Id- 204244736 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04495/2023-2024 | BP-2023-24-863 | 16/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
4072 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEULI and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001683/2022-2023 | 564/W/MMD | 20/03/2023 | 1487 | DEY ENTERPRISE | 22.8 | 10.63 | 85
4073 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 286.82 | 75
4074 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Chandra Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000872/2023-2024 | 194/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
4075 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000015/2024-2025 | 1573/TD | 23/04/2024 | 0 | Resource Division | 12.71 | 0 | 0
4076 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000187/2022-2023 | 2427/TD | 16/01/2023 | 0 | Resource Division | 41.87 | 0 | 0
4077 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Uttar Chandrachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707437, Ref ID 204292173) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01076/2024-2025 | BP-2024-25-190 | 24/05/2024 | 0 | WBSEDCL | 4.89 | 0 | 0
4078 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Uttar chandrachak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756265, Ref ID 204319510) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01696/2024-2025 | BP-2024-25-485 | 30/07/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
4079 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR CHANDRA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001337/2022-2023 | 2342/W/MMD | 29/12/2022 | 823 | SOUMEN ELECTRIC | 23.68 | 18.26 | 60
4080 | Tamluk Division |  | Functional Household Tap Connection to the 172 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Bara Rasulpur(635)] |  |  | ORD/000168/2020-2021 | 2718/TD | 21/01/2021 | 20 | SUKOMAL BERA | 8.15 | 1.3 | 100
4081 | Tamluk Division |  | Functional Household Tap Connection to the 355 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Aluan(78 ) part,Paschimbatya(79)] |  |  | ORD/000169/2020-2021 | 2719/TD | 21/01/2021 | 25 | MRINAL KANTI PRADHAN | 16.73 | 0.64 | 100
4082 | Tamluk Division |  | Functional Household Tap Connection to the 190 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [(Balagerya(77 ) ,Aluan(78) ,Part)] |  |  | ORD/000170/2020-2021 | 2720/TD | 21/01/2021 | 20 | SUBRATA KUMAR BERA | 9 | 1.52 | 100
4083 | Tamluk Division |  | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000471/2021-2022 | 329/W | 08/10/2021 | 0 | MRINAL KANTI PRADHAN | 2.08 | 0 | 0
4084 | Tamluk Division |  | Retrofitting to accomodate FHTC 172 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001057/2020-2021 | 823/W | 26/02/2021 | 0 | SUKOMAL BERA | 6.61 | 0 | 0
4085 | Tamluk Division |  | Functional Household Tap Connection to the 190 Nos. Household of Paschimbetya W/S Scheme within Contai - III Block Tamluk Division, PHE Dte. (PART-A) |  |  | VCH/001194/2020-2021 | 843/W | 08/03/2021 | 0 | SUBRATA KUMAR BERA | 7.26 | 0 | 0
4086 | Tamluk Division |  | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001218/2020-2021 | 967/W | 22/03/2021 | 0 | MRINAL KANTI PRADHAN | 14.01 | 0 | 0
4087 | Tamluk Division | Contai Sub-Division | Sinking Tube well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (958 nos), Including 2 years of Operation maintance under JJM with allied work of BATIPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000404/2023-2024 | 1092/TD | 08/06/2023 | 1110 | SUJATA CONSTRUCTION | 368.76 | 47.72 | 30
4088 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000076/2024-2025 | 2950/TD | 12/09/2024 | 0 | Resource Division | 5.9 | 0 | 0
4089 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000249/2022-2023 | 2717/TD | 06/02/2023 | 0 | Resource Division | 42.25 | 0 | 0
4090 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BATIPUR AND ITS ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002039/2022-2023 | 947/W/MMD | 28/03/2023 | 180 | A.S.ENTERPRISE | 21.57 | 0 | 0
4091 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Erenda PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2023-2024 | 1592/TD | 21/07/2023 | 856 | MUKHERJEE CONSTRUCTION | 504.12 | 221.63 | 62
4092 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000025/2025-2026 | 2092/TD | 12/08/2025 | 0 | Resource Division | 10.77 | 0 | 0
4093 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000254/2022-2023 | 2713/TD | 06/02/2023 | 0 | Resource Division | 29.89 | 0 | 0
4094 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ERENDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792956/QUOT/03/379 DT. 02-07-2024 Application NO- 2004792956 Application type-New connection Consumer Id- 204345868 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01701/2024-2025 | BP-2024-25-494 | 29/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
4095 | Midnapore Mechanical | Digha Sub-Division | Erenda W/S scheme PH-I Application no.-2004523042 ref.-204156895 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03192/2023-2024 | BP-2023-24-482 | 27/12/2023 | 0 | WBSEDCL | 4.3 | 0 | 0
4096 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ERENDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001356/2022-2023 | 2367/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 10.96 | 45
4097 | Tamluk Division | Digha Sub-Division | Leftout pipeline & Drum Sheet Walling to accommodate FHTC under JJM of Tajpur Water Supply Scheme within Egra II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000068/2025-2026 | 1167/TD | 22/04/2025 | 40 | R CONSTRUCTION | 103.69 | 0 | 0
4098 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at Tajpur PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000160/2024-2025 | 2072/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4099 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2785 nos) under JJM with allied work for Tajpur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000423/2023-2024 | 1415/TD | 12/07/2023 | 994 | FIROZ KHAN | 607.63 | 296.14 | 70
4100 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000030/2025-2026 | 2089/TD | 12/08/2025 | 0 | Resource Division | 17.16 | 0 | 0
4101 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000251/2022-2023 | 2715/TD | 06/02/2023 | 0 | Resource Division | 32.5 | 0 | 0
4102 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626691/QUOT/03/1613 DT. 01/03/2024 Application NO- 2004626691 Application type-New connection Consumer Id- 204233925 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04504/2023-2024 | BP-2023-24-857 | 16/03/2024 | 0 | WBSEDCL | 4.05 | 0 | 0
4103 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626737/QUOT/03/1611 DT. 01-03-2024 Application NO- 2004626737 Application type-New connection Consumer Id- 204233924 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04505/2023-2024 | BP-2023-24-856 | 16/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
4104 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAJPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001587/2022-2023 | 470/W/MMD | 20/03/2023 | 744 | SOUMEN ELECTRIC | 25.24 | 23.66 | 100
4105 | Tamluk Division | Tamluk Sadar Sub-Division | payment for Wayleave plan & survey charges SER-KGP-2024-WL-95 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00487/2024-2025 | BP-2024-25-188 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
4106 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-95) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00691/2024-2025 | BP-2024-25-298 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.08 | 0 | 0
4107 | Tamluk Division | Tamluk Sadar Sub-Division | Canal crossing, land development, dismentling concrete and restoration work,dram sheet walling of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub- Division of Tamluk division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000310/2024-2025 | 3140/TD | 26/09/2024 | 30 | BAGLAMUKHI SECURITY SERVICE | 17.81 | 0 | 100
4108 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 90 mm dia pipe of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Nodal Point 242-243, 314-315,356-343 & 88A-128 ) Canal Length- = 14.00 mtr. Number of crossing -4 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000331/2024-2025 | 3290/TD | 05/10/2024 | 30 | BAGLAMUKHI SECURITY SERVICE | 9.39 | 0 | 100
4109 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1435 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Harashankar Khamarchak PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000372/2023-2024 | 907/TD | 01/06/2023 | 970 | HARIPADA PATTANAYAK | 371.31 | 201.64 | 50
4110 | Tamluk Division | Tamluk Sadar Sub-Division | Jack Pushing of Railway Track Between Raghunathbari to Rajgoda Railway Station on Panskura Tamluk Section of Kharagpur S.E. Railway Division of Purba Medinipur for Harasankar Khamarchak Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 150 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 13/5 & 13/7 and 13/6 & 13/8 within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =60.0 Mtr) Nodal Point 176 TO 183. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001256/2023-2024 | 1070/TD | 16/03/2024 | 262 | HARIPADA PATTANAYAK | 73.77 | 0 | 100
4111 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000299/2022-2023 | 3007/TD | 27/02/2023 | 0 | Resource Division | 18.84 | 0 | 0
4112 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Harasankarpur Khamarchak W/S scheme T/W-II Application No.-2004586186, Ref ID.-204209423 Date of quotation .-06/02/2024 New connection. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03701/2023-2024 | BP-2023-24-683 | 15/02/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
4113 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Harasankar Khamarchak H/W Site Block=Sahid Matangini Application No=2004626478 Reference ID=204233282 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04340/2023-2024 | BP-2023-24-803 | 11/03/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
4114 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001693/2022-2023 | 621/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 21.15 | 35
4115 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 385.99 | 75
4116 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Kiarana PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000870/2023-2024 | 192/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
4117 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2024-2025 | 1567/TD | 23/04/2024 | 0 | Resource Division | 8.77 | 0 | 0
4118 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000178/2022-2023 | 2433/TD | 16/01/2023 | 0 | Resource Division | 36.03 | 0 | 0
4119 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Kiarana w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004686357, Con ID 204277586) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00645/2024-2025 | BP-2024-25-110 | 06/05/2024 | 0 | WBSEDCL | 13.89 | 0 | 0
4120 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Kiarana w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.(App No.- 2004620100, Ref ID 204229479) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04503/2023-2024 | BP-2023-24-860 | 16/03/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
4121 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIARANA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001415/2022-2023 | 2426/W/MMD | 31/12/2022 | 670 | DEY ENTERPRISE | 23.7 | 19.45 | 100
4122 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block-Egra-II in the District of Purba Medinipur. |  | Junior Engineer | ORD/000135/2020-2021 | 2661/TD | 11/01/2021 | 60 | SATYABRATA BHAUMIK | 96.25 | 53.35 | 100
4123 | Tamluk Division | Digha Sub-Division | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 2.67 | 65
4124 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000226/2021-2022 | 141/W | 22/07/2021 | 0 | SATYABRATA BHAUMIK | 22.86 | 0 | 0
4125 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001235/2020-2021 | 981/W | 25/03/2021 | 0 | SATYABRATA BHAUMIK | 20.03 | 0 | 0
4126 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Badhia PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000126/2020-2021 | 2636/TD | 05/01/2021 | 60 | AJIT KUMAR SOM | 96.85 | 21.21 | 100
4127 | Tamluk Division |  | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in BADHIA piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. |  |  | ORD/000130/2025-2026 | 144/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.76 | 0 | 100
4128 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000392/2021-2022 | 230/W | 07/09/2021 | 0 | AJIT KUMAR SOM | 21.1 | 0 | 0
4129 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001246/2020-2021 | 978/W | 26/03/2021 | 0 | AJIT KUMAR SOM | 54.53 | 0 | 0
4130 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XI (Balance Work) Block ¿ Panskura-II in the District of Purba Medinipur. |  |  | ORD/000208/2020-2021 | 2820/TD | 05/02/2021 | 70 | TAPAS SANTRA | 196.75 | 6.19 | 100
4131 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000295/2021-2022 |  | 09/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0
4132 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000313/2021-2022 | BP-2021-22-78 | 17/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0
4133 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Zone ¿ XI (Balance Work) Piped Water Supply Scheme |  |  | VCH/001122/2020-2021 | 1081/W | 30/03/2021 | 0 | TAPAS SANTRA | 56.32 | 0 | 0
4134 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chandanpur PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000115/2020-2021 | 2481/TD | 21/12/2020 | 60 | TAPAS SANTRA | 96.74 | 2.45 | 100
4135 | Tamluk Division |  | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in CHANDANPUR piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division,Purba Medinipur District. |  |  | ORD/000135/2025-2026 | 147/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0
4136 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Chandanpur W/S Scheme |  |  | VCH/000892/2020-2021 | 827/W | 03/03/2021 | 0 | TAPAS SANTRA | 16.22 | 0 | 0
4137 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chandanpur W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001036/2020-2021 | 714/W | 09/02/2021 | 0 | TAPAS SANTRA | 78 | 0 | 0
4138 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Silampur PWSS Block -Contai-I in the District of Purba Medinipur. |  |  | ORD/000245/2020-2021 | 2876/TD | 11/02/2021 | 30 | BASANTA KUMAR MAITY | 77.79 | 21.22 | 100
4139 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Silampur PWSS within Contai ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001131/2020-2021 |  | 17/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0
4140 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Silampur W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001260/2020-2021 | 1092/W | 30/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0
4141 | Tamluk Division |  | Retrofitting to accommodate FHTC (520 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Baishnab Chak (JL-136) - (Baishnab Chak Uttar Paschim Para, Baishnab Chak Purba Dakshin Para &Gholepukuria [JL134(P)] - (Jaykhali Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. ,PART-A |  |  | ORD/000187/2020-2021 | 2753/TD | 27/01/2021 | 25 | ZENITH CONSTRUCTION | 26.93 | 0 | 100
4142 | Tamluk Division |  | Retrofitting to accommodate FHTC (480 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Gholepukuria [JL-134(P)] - (Purba Dakshin Para & Madhya Jana Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B |  |  | ORD/000188/2020-2021 | 2754/TD | 27/01/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.38 | 0 | 100
4143 | Tamluk Division |  | Retrofitting to accomodate FHTC 520 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000097/2021-2022 | BP-2021-22-44 | 29/07/2021 | 0 | ZENITH CONSTRUCTION | 3.86 | 0 | 0
4144 | Tamluk Division |  | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000200/2021-2022 | BP-2021-22-59 | 13/08/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.49 | 0 | 0
4145 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001105/2020-2021 | 1103/W | 30/03/2021 | 0 | ZENITH CONSTRUCTION | 23.02 | 0 | 0
4146 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001107/2020-2021 |  | 12/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0
4147 | Tamluk Division |  | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/001257/2020-2021 | 1104/W | 30/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0
4148 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Alinan Zone-I PWSS Block -Sahid Matangini in the District of Purba Medinipur. |  |  | ORD/000207/2020-2021 | 2819/TD | 05/02/2021 | 45 | TAPAS SANTRA | 97.45 | 193.36 | 100
4149 | Tamluk Division |  | Retrofitting to accommodate (175) nos FHTC under JJM of Balarampur & Joyrampur village in Alinan Zone-I PWSS Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District . |  |  | ORD/000332/2021-2022 | 1717/TD | 01/02/2022 | 20 | MUKHERJEE ENTERPRISE | 10.37 | 0 | 100
4150 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanakpur PWSS Block -Potashpur-I in the District of Purba Medinipur. |  |  | ORD/000203/2020-2021 | 2801/TD | 04/02/2021 | 45 | SRIMANTA KUMAR MAITY | 114.41 | 41.4 | 100
4151 | Tamluk Division |  | Providing Balance FHTC with allied works of Kanakpur mouzas under Kanakpur water supply scheme of Contai Sub Division under Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000456/2022-2023 | 1301/TD | 13/09/2022 | 30 | THE GODFATHER TRADING COMPANY | 3.52 | 3.51 | 100
4152 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kanakpur Piped Water Supply Scheme |  |  | VCH/001114/2020-2021 | 1085/W | 30/03/2021 | 0 | SRIMANTA KUMAR MAITY | 41.89 | 0 | 0
4153 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia. Sluice Valve for Augmentation of Anurai Water Supply Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2022-2023 | 426/TD | 27/05/2022 | 15 | PARTHA CONSTRUCTION | 4.59 | 4.59 | 100
4154 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anurai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000175/2021-2022 | 1184/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 8.21 | 6.31 | 100
4155 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Additional Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000265/2022-2023 | 1088/TD | 25/08/2022 | 40 | ABHIJIT BERA | 5.47 | 5.31 | 100
4156 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000278/2024-2025 | 2906/TD | 10/09/2024 | 40 | RAI CONSTRUCTION | 12.9 | 0 | 100
4157 | Tamluk Division | Contai Sub-Division | Augmentation of Anurai Water Supply Scheme by Providing Laying Distribution System and FHTC in In Contai-III & Deshpran Block Of in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000301/2021-2022 | 1639/TD | 19/01/2022 | 1415 | MAHAVIR PUMPS MFG. PVT. LTD. | 391.92 | 332.51 | 90
4158 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additiona Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai - III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000329/2022-2023 | 843/TD | 20/07/2022 | 30 | ABHIJIT BERA | 3.63 | 3.57 | 100
4159 | Tamluk Division | Contai Sub-Division | Supply & delivery D.I. Specials for Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000401/2022-2023 | 690 / CSD | 22/09/2022 | 15 | SUBRATA KUMAR BERA | 0.76 | 0 | 100
4160 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Anurai W/S Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-136 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000477/2023-2024 | 1535/TD | 18/07/2023 | 410 | DEBABRATA DAS | 21.39 | 11.3 | 100
4161 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 1st Tube well Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1407) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2021-2022 | 1991/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.65 | 100
4162 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tube well (Additional) Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1289) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000497/2021-2022 | 1992/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.85 | 100
4163 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Anurai- 1 no, Bhajachauli- 1 no, Dhanghara- 1 no, Basudebberiya- 1 no, Shankarpur- 1 no, Mukutshila Zone-II- 1 no. & Chandibhetti- 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000510/2022-2023 | 810 / CSD | 21/10/2022 | 15 | SAURAV HAZRA | 0.81 | 0.81 | 100
4164 | Tamluk Division | Contai Sub-Division | Renovation work of Spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum at Anurai Mouza within Anurai W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000602/2021-2022 | 493 / CSD | 16/11/2021 | 21 | SUBRATA KUMAR BERA | 2.43 | 2.26 | 100
4165 | Tamluk Division | Contai Sub-Division | Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000699/2022-2023 | 1992/TD | 01/12/2022 | 30 | SUBRATA KUMAR BERA | 4.49 | 0 | 100
4166 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for providing FHTC for Augmentation of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000764/2025-2026 | 2262/CSD | 09/10/2025 | 60 | ANJANI ENTERPRISE | 0.94 | 0 | 100
4167 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Anurai Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000888/2022-2023 | 441 / CSD | 20/03/2023 | 15 | KAMAL KUMAR BERA | 0.95 | 0.95 | 0
4168 | Tamluk Division | Contai Sub-Division | Land Filling & Construction of Approch Road for 3rd TW site of Anurai W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000904/2022-2023 | 307/CSD | 27/02/2023 | 15 | ABHIJIT BERA | 1.25 | 1.23 | 0
4169 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2021-2022 | 1265/TD | 13/12/2021 | 0 | Resource Division | 42.96 | 0 | 0
4170 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000058/2021-2022 | 1729/TD | 02/02/2022 | 0 | Resource Division | 13.95 | 0 | 0
4171 | Midnapore Mechanical | Contai Sub-Division | Electric quotation Bill of T/W-III of Anurai water suplly scheme under MMD PHE Dte. under Marishda CCC | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000228/2022-2023 | 2004006184/QUOT/03 | 30/07/2022 | 365 | WBSEDCL | 0.7 | 0.7 | 0
4172 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001012/2022-2023 | 1861/W/MMD | 22/09/2022 | 120 | SUBHAM ENTERPRISE | 11.67 | 8.29 | 20
4173 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional 3rd Tube well under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001272/2022-2023 | 2201/W/MMD | 14/12/2022 | 837 | A G ENTERPRISE | 12.25 | 11.41 | 100
4174 | Tamluk Division |  | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | ORD/000013/2021-2022 | 689/TD | 10/09/2021 | 60 | ARABINDA GHOSH | 88.68 | 0 | 100
4175 | Tamluk Division |  | Retrofitting to accomodate FHTC 1125 Nos. connection under JJM under Dona Zone - I W/S Scheme within Moyna Block under Tamluk Division, PHE Dte. (Phase - I) |  |  | VCH/000435/2021-2022 | BP-2021-22-148 | 09/11/2021 | 0 | ARABINDA GHOSH | 21.94 | 0 | 0
4176 | Tamluk Division |  | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | VCH/000996/2021-2022 | BP-2021-22-391 | 31/03/2022 | 0 | ARABINDA GHOSH | 75.2 | 0 | 0
4177 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bagmari PWSS Block- Potashpur-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000020/2021-2022 | 83/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 88.69 | 115.43 | 100
4178 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Ranisai PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000116/2020-2021 | 2480/TD | 21/12/2020 | 60 | TARUN KOLEY | 94.35 | 0 | 100
4179 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Ranisai W/S Scheme |  |  | VCH/000891/2020-2021 | 828/W | 02/03/2021 | 0 | TARUN KOLEY | 4.71 | 0 | 0
4180 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Ranisai W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001034/2020-2021 | 712/W | 09/02/2021 | 0 | TARUN KOLEY | 80 | 0 | 0
4181 | Tamluk Division | Contai Sub-Division | Providing FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-01) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000049/2022-2023 | 287/TD | 05/05/2022 | 60 | DAS CONSTRUCTION | 124.25 | 89.94 | 95
4182 | Tamluk Division | Contai Sub-Division | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000084/2022-2023 | 437-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.88 | 7.88 | 100
4183 | Tamluk Division | Contai Sub-Division | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000094/2022-2023 | 451/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.24 | 0.24 | 100
4184 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Talda,Murisai & Anurai Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000112/2022-2023 | 278 / CSD | 14/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.34 | 2.34 | 100
4185 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Talda Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000118/2022-2023 | 613/TD | 21/06/2022 | 21 | M/S BISWANATH CONSTRUCTION | 13.38 | 10.35 | 100
4186 | Tamluk Division | Contai Sub-Division | Laying of of HDPE Pipe line & DI Pipe Line and allied works due to Damage partion under Augmentation of Talda Water Supply Scheme and its adjoining mouzas at different Nodal Point in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000127/2025-2026 | 783/CSD | 09/04/2025 | 7 | M/S SREE DURGA ENTERPRISE | 0.97 | 0 | 100
4187 | Tamluk Division | Contai Sub-Division | Construction of Pump House & Boundary Wall and others allied works for 3rd Tube well site under Talda Water Supply Scheme (Augmentation) in Contai III Block within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000268/2024-2025 | 2897/TD | 10/09/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 11.34 | 0 | 0
4188 | Tamluk Division | Contai Sub-Division | Repairing Of Pump House ( House No-I & II) and Boundary Wall of Pump House No- II under Augmentation of Talda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000280/2023-2024 | 485/TD | 10/05/2023 | 30 | M/S SREE DURGA ENTERPRISE | 3.65 | 0 | 100
4189 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Talda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000318/2021-2022 | 1611/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.97 | 100
4190 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000361/2021-2022 | 1816/TD | 11/02/2022 | 45 | M/S SREE DURGA ENTERPRISE | 95.89 | 89.58 | 100
4191 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000377/2021-2022 | 1817/TD | 11/02/2022 | 40 | AJIT KUMAR SOM | 77.52 | 75.76 | 100
4192 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000378/2021-2022 | 1818/TD | 11/02/2022 | 40 | GIRI CONSTRUCTION | 58.08 | 56.04 | 100
4193 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2021-2022 | 1819/TD | 11/02/2022 | 20 | SUBHENDU HAZRA | 24.07 | 23.63 | 100
4194 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000380/2021-2022 | 1820/TD | 11/02/2022 | 20 | M/S. NEW DINDA ENTERPRISE | 23.24 | 23.09 | 100
4195 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. . (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000381/2021-2022 | 1821/TD | 11/02/2022 | 20 | BADAL CHANDRA GOLE | 19.35 | 19.13 | 100
4196 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000382/2021-2022 | 1822/TD | 11/02/2022 | 20 | GIRI ENTERPRISE | 19.36 | 19.19 | 100
4197 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000383/2021-2022 | 1823/TD | 11/02/2022 | 20 | SUBRATA KUMAR BERA | 18.89 | 18.64 | 100
4198 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000384/2021-2022 | 1824/TD | 11/02/2022 | 20 | DHANANJOY DAS | 19.35 | 18.93 | 100
4199 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000385/2021-2022 | 1825/TD | 11/02/2022 | 20 | SUKOMAL BERA | 14.52 | 14.44 | 100
4200 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2021-2022 | 1826/TD | 11/02/2022 | 20 | ANUPAM CONSTRUCTION | 9.6 | 9.53 | 100
4201 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District.(PART- M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000387/2021-2022 | 1827/TD | 11/02/2022 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.62 | 9.54 | 100
4202 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Talda- 1 no, Sapai- 1 no, Baghaput- 1 no & Kumirda - 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2022-2023 | 812 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.46 | 0.46 | 100
4203 | Tamluk Division | Contai Sub-Division | Washout Pipe line by UPVC Pipe for Augmentation of Talda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000643/2024-2025 | 697/CSD | 25/03/2025 | 180 | BHARAT NIRMAN ENTERPRISE | 1.91 | 0 | 0
4204 | Tamluk Division | Contai Sub-Division | Rising main with laying of 150 mm dia DI(K-9) From 3rd Tube Well Site to O.H.R. Site and other allied works for Augmentation of Talda water supply scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000644/2024-2025 | 698/CSD | 25/03/2025 | 30 | BISWA NIRMAN ENTERPRISE. | 1.47 | 0 | 100
4205 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-36-89,89-131 & 131-139A,Part) of pipe line and its allied works for Talda water supply scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000741/2023-2024 | 3068/TD | 30/11/2023 | 25 | ACHINTA KUMAR HALDER | 10.08 | 8.42 | 80
4206 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube well of Talda Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001156/2023-2024 | 607/TD | 16/02/2024 | 20 | KALPANA BUILDERS | 14.29 | 0 | 0
4207 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000062/2021-2022 | 1875/TD | 18/02/2022 | 0 | Resource Division | 17.42 | 0 | 0
4208 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000084/2021-2022 | 2190/TD | 21/03/2022 | 0 | Resource Division | 39.93 | 0 | 0
4209 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of TALDA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-III, WBSEDCL SUPPLY OFFICE: MARISHDA C.C.C. Ref. Memo No- 2004815942/QUOT/03 DT. 10-07-2024 Application NO-2004815942 Application type-New connection Consumer Id- 204353932 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01697/2024-2025 | C072443922958 | 29/07/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
4210 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Talda, Block Contai III, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000169/2023-2024 | 1412/W/MMD | 02/06/2023 | 718 | SHIVAM ENTERPRISE | 12.63 | 0 | 90
4211 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kamarda Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000195/2023-2024 | 305/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 4.15 | 4.15 | 100
4212 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kamarda Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000260/2022-2023 | 1076/TD | 23/08/2022 | 1398 | HARIPADA PATTANAYAK | 499.3 | 405.37 | 86
4213 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kamarda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000321/2021-2022 | 1614/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.2 | 3.6 | 100
4214 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Kamarda-1 no, Sherkhanchak Zone-I-1 no, Sherkhanchak Zone-II-1 no, Majna-1 no, Madhakhali Zone-I-1 no , Madhakhali Zone-I-1 no, Arjunnagar-1 no & Nijkasba-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000508/2022-2023 | 808 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.93 | 0.93 | 100
4215 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 17.72 | 100
4216 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Kamarda PWSS within Khejuri -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Rising main and other allied works Augmentation of Kamarda W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Kamarda W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000867/2022-2023 | 3220/TD | 14/03/2023 | 880 | GIRI CONSTRUCTION | 20.1 | 0 | 70
4217 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes and FHTC works under Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001257/2023-2024 | 1071/TD | 16/03/2024 | 25 | TARUN KHATUA | 34.31 | 23.75 | 30
4218 | Tamluk Division | Contai Sub-Division | Land Development at 3rd Tube Well site of Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001294/2023-2024 | 162/CSD | 29/01/2024 | 15 | GIRI CONSTRUCTION | 0.97 | 0 | 100
4219 | Tamluk Division | Contai Sub-Division | Land Development at 3rd Tube Well site of Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001465/2023-2024 | 222/CSD | 06/02/2024 | 15 | GIRI CONSTRUCTION | 0.97 | 0 | 0
4220 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000019/2022-2023 | 407/TD | 25/05/2022 | 0 | Resource Division | 50.49 | 0 | 0
4221 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000079/2022-2023 | 1261/TD | 12/09/2022 | 0 | Resource Division | 19.4 | 0 | 0
4222 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Kamarda w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671499, Ref ID 204266596) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00288/2024-2025 | BP-2024-25-48 | 18/04/2024 | 0 | WBSEDCL | 3.07 | 0 | 0
4223 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at Kamarda Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001187/2023-2024 | 2610/W/MMD | 19/09/2023 | 712 | M/S SREEJIT ENTERPRISE | 14.77 | 10.79 | 50
4224 | Tamluk Division | Tamluk Sadar Sub-Division | Laying damage portion of different dia. UPVC pipes within Surface Water Based Water Supply Scheme for Zone- VIII of Kolaghat Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 63/TD | 05/04/2022 | 20 | CONCORD ENGINEERING | 12.59 | 12.58 | 100
4225 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC(Balance work) (200 nos.) and laying of left-out portion with uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone- VIII, Block-Kolaghat in the District of Purba Medinipur(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000124/2022-2023 | 616/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 78.41 | 67.03 | 100
4226 | Tamluk Division | Digha Sub-Division | Quotation money payment to WBSEDCL for Mandar Water Supply Scheme of Tube Well No. - III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/00468/2023-2024 | BP-2023-24-237 | 09/08/2023 | 0 | WBSEDCL | 3.54 | 0 | 0
4227 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line, Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Mandar & its adjoining mouzas Water Supply Scheme within RAMNAGAR -II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000114/2023-2024 | 244/TD | 19/04/2023 | 45 | BASANTA KUMAR MAITY | 59.1 | 28.91 | 50
4228 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000173/2021-2022 | 1182/TD | 02/12/2021 | 20 | HORIZEN | 2.94 | 2.94 | 100
4229 | Tamluk Division | Digha Sub-Division | Supply of C.I D.F Sluice valve for Augmentation of ground water based Mander W/S Scheme to accommodate FHTC within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000212/2022-2023 | 324/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 2.86 | 2.86 | 100
4230 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Mandar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000376/2021-2022 | 1813/TD | 11/02/2022 | 180 | BASANTA KUMAR MAITY | 199.91 | 122.57 | 70
4231 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000019/2021-2022 | 1261/TD | 13/12/2021 | 0 | Resource Division | 5.63 | 0 | 0
4232 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000052/2021-2022 | 1869/TD | 17/02/2022 | 0 | Resource Division | 5.31 | 0 | 0
4233 | Central Drilling | Digha Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TW BY DEPARTMENTAL RIG MACHINE IN RAMNAGAR-II BLOCK, UNDER CDD,PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000089/2022-2023 | 183/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 4.92 | 4.66 | 100
4234 | Central Drilling | Digha Sub-Division | PROVIDING TW MATERIALS CONFORMING TO 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000090/2022-2023 | 184/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 4.97 | 100
4235 | Central Drilling | Digha Sub-Division | PROVIDING PEA SIZE GRAVELS AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TW AT RAMNAGAR-II BLOCK, UNDER CMSD-I(D), CDD,PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000091/2022-2023 | 185/CMSD-I(D) | 10/06/2022 | 15 | PADMA ENGINEERING & CO. | 5 | 3.13 | 100
4236 | Central Drilling | Digha Sub-Division | ADDITIONAL CARRIAGE OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT MADAR PWSS (T/W-III), BLOCK - RAMNAGAR-II UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000134/2022-2023 | 352/CMSD-I (D) | 26/07/2022 | 10 | PADMA ENGINEERING & CO. | 0.16 | 0.16 | 100
4237 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000054/2023-2024 | 1220/W/MMD | 25/04/2023 | 360 | S.G.TECHNICAL SERVICE | 11.96 | 0 | 100
4238 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 58/TD | 05/04/2022 | 60 | BARH CONSTRUCTION | 130.82 | 130.17 | 100
4239 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (Part- B) | Assistant Engineer | Junior Engineer | ORD/000169/2022-2023 | 743/TD | 05/07/2022 | 60 | SATYABRATA BHAUMIK | 165 | 165.43 | 100
4240 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Paramanandapur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 330/TD | 25/04/2023 | 811 | SUDIP MANNA | 13.09 | 0 | 100
4241 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paramanandapur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2021-2022 | 1193/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.74 | 4.74 | 100
4242 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000727/2022-2023 | 2557/TD | 24/01/2023 | 60 | M/S. S. A. CONSTRUCTION | 41.95 | 41.3 | 100
4243 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Rejuvenation &Retrofitting of Laying Distribution System of proposed left out portion pipe line at Paramanandapur PWSS | Assistant Engineer | Junior Engineer | ORD/000830/2022-2023 | 3170/TD | 10/03/2023 | 20 | PURNA CHANDRA BARH | 7.63 | 7.46 | 100
4244 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01676/2023-2024 | BP-2023-24-737 | 29/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.07 | 0 | 0
4245 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 of Erashole PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01896/2023-2024 | BP-2023-24-853 | 08/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0
4246 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 33.7 | 100
4247 | Tamluk Division | Tamluk Sadar Sub-Division | MS structure for canel crossing, NH road boring with casing and concrete piller for Laying distribution system and rising main pipe line at Erasole Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000305/2024-2025 | 3105/TD | 23/09/2024 | 407 | TARUN KOLEY | 28.12 | 0 | 100
4248 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Erasole Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000369/2021-2022 | 1646/TD | 19/01/2022 | 20 | HORIZEN | 5.37 | 5.37 | 100
4249 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia,200 mm dia & 250 mm dia DI(K-9) rising main from 3rd & 4th. T/W to OHR at Erasole PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000452/2023-2024 | 1476/TD | 14/07/2023 | 843 | SAYAN MAITY | 10.15 | 0 | 100
4250 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of ground water based Erasol Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000479/2022-2023 | 1888/TD | 24/11/2022 | 1218 | TARUN KOLEY | 1110.82 | 768.23 | 100
4251 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2022-2023 | 409/TD | 25/05/2022 | 0 | Resource Division | 114.93 | 0 | 0
4252 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000086/2022-2023 | 1263/TD | 12/09/2022 | 0 | Resource Division | 44.05 | 0 | 0
4253 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Erashal Water Supply Scheme TW-IV (Ref. ID-203949710) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00109/2023-2024 | BP-2023-24-36 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
4254 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Erashal Water Supply Scheme TW-III (Ref. ID-203949718) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00110/2023-2024 | BP-2023-24-37 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
4255 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000061/2023-2024 | 1226/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 26.95 | 26.58 | 100
4256 | Tamluk Division | Tamluk Sadar Sub-Division | Jack Pushing of Railway Track Between NANDAKUMAR P.H. & LAVAN SATYAGARH SMARAK P.H. Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of ERASOLE Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia DI (K7) Carrier Pipe within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =48 Mtr) Nodal Point J393 to J338. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000720/2023-2024 | 2942/TD | 23/11/2023 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 68.57 | 53.19 | 100
4257 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & Renovation of Construction of switch Room cum Chlorine Room at OHR site and 2 nd.Tube Well site and Renovation of existing Boundary Wall at OHR site and 2 nd.Tube Well site and New construction of Boundary Wall at 3rd.& 4 th Tube Well site for Erasal Water Supply Scheme under Tamluk Sub Division,PHE Dte.. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000783/2022-2023 | 3019/TD | 27/02/2023 | 60 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.17 | 39.66 | 100
4258 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dhenkua Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000007/2022-2023 | 57/TD | 05/04/2022 | 180 | RAJ KUMAR SINGHA | 563.22 | 508.91 | 100
4259 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000069/2022-2023 | 346/TD | 13/05/2022 | 20 | TAPAS SANTRA | 4.49 | 4.49 | 100
4260 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000070/2022-2023 | 347/TD | 13/05/2022 | 20 | TAPAS SANTRA | 3.67 | 3.67 | 100
4261 | Tamluk Division | Haldia Sub-Division | Laying of Left-out portion Distribution pipe line and Household Tap Connection (FHTC) for Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000134/2024-2025 | 3466/TD | 06/11/2024 | 96 | RAJ KUMAR SINGHA | 54.66 | 0 | 70
4262 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenkua Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000160/2021-2022 | 1164/TD | 01/12/2021 | 7 | HORIZEN | 5.92 | 5.83 | 100
4263 | Tamluk Division | Haldia Sub-Division | G.I pipe column with M.S. Structure for laying of D.I pipe line & HDPE pipe line with Casing at Dhenkua Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= 65.00 mtr, {i) NP-116 to 46= 20mt + ii) NP-90 to 5= 2.5mt + iii) NP 10 to 11 = 2.5 Mtr. + iv) NP - 199 to 168 = 20.0mt + NP - 151 to 154 =20.0mtr.} | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000233/2022-2023 | 974/TD | 03/08/2022 | 20 | RAJ KUMAR SINGHA | 9.49 | 4.79 | 100
4264 | Tamluk Division | Haldia Sub-Division | Laying Rising main and supporting work with Drum Sheet walling and Earth filling in Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000234/2022-2023 | 975/TD | 03/08/2022 | 875 | RAJ KUMAR SINGHA | 87.92 | 79.54 | 100
4265 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Dhenkua Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000299/2022-2023 | 1133/TD | 30/08/2022 | 90 | DIPANKAR MALAKAR | 4.75 | 2.74 | 100
4266 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000013/2021-2022 | 1255/TD | 13/12/2021 | 0 | Resource Division | 12.45 | 0 | 0
4267 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000044/2021-2022 | 2345/TD | 31/03/2022 | 0 | Resource Division | 15.83 | 0 | 0
4268 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000125/2024-2025 | 802/TD | 18/03/2025 | 0 | Resource Division | 5.54 | 0 | 0
4269 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Dhenuka W/S Scheme (T/W-II), Sutahata Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000126/2023-2024 | 877/CDD | 11/07/2023 | 358 | MENAKA ENTERPRISE | 21.16 | 19.85 | 100
4270 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for Denkua Water Supply SchemeT/W-I (Ref. ID-224005066 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01617/2023-2024 | BP-2023-24-135 | 20/07/2023 | 0 | WBSEDCL | 0.11 | 0 | 0
4271 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Dhenkua Water supply scheme, Sutahata block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000389/2024-2025 | 2005/W/MMD | 30/08/2024 | 180 | P.K.ENGINEERING | 9.29 | 0 | 80
4272 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dhenkua water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001139/2022-2023 | 2120/W/MMD | 28/11/2022 | 120 | DIPALI CONSTRUCTION | 11.1 | 10.95 | 100
4273 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Terapara Jalpai to Jaganathpur (Basulia Hospital to Horikhali) road from Ch.0.42 KM to 2.00 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00238/2023-2024 | BP-2023-24-123 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.68 | 0 | 0
4274 | Tamluk Division | Haldia Sub-Division | Payment to WBSEDCL for Electric Quotation money of Begunberia Tube Well No. ¿ III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00378/2023-2024 | BP-2023-24-206 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
4275 | Tamluk Division | Haldia Sub-Division | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00703/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.59 | 0 | 0
4276 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Begunberia Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000033/2022-2023 | 132/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
4277 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000072/2022-2023 | 355/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100
4278 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000073/2022-2023 | 356/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.42 | 4.42 | 100
4279 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Begunberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000122/2021-2022 | 1000/TD | 01/11/2021 | 20 | SAYAN MAITY | 4.25 | 3.26 | 100
4280 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000174/2021-2022 | 1183/TD | 02/12/2021 | 20 | HORIZEN | 7 | 7 | 100
4281 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 3rd tubewell site of Begunberia Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-16mtr) & (length of Approach road-10mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000573/2023-2024 | 2162/TD | 31/08/2023 | 30 | M/S SOURAV MAHAPATRA | 22.85 | 16.96 | 20
4282 | Tamluk Division | Haldia Sub-Division | Laying Left Out Distribution System, FHTC work & Pilling work with Drum sheet Augmentation of ground water based Begunberia Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000578/2023-2024 | 2200/TD | 01/09/2023 | 520 | TAPAS SANTRA | 97.5 | 0 | 50
4283 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000015/2021-2022 | 1257/TD | 13/12/2021 | 0 | Resource Division | 71.92 | 0 | 0
4284 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000047/2021-2022 | 2347/TD | 31/03/2022 | 0 | Resource Division | 25.41 | 0 | 0
4285 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Begunberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000636/2021-2022 | 2335/TD | 29/03/2022 | 1282 | TAPAS SANTRA | 681.46 | 590.71 | 92
4286 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000126/2024-2025 | 803/TD | 18/03/2025 | 0 | Resource Division | 6.16 | 0 | 0
4287 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 12.76 | 60
4288 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
4289 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 108.99 | 94
4290 | Tamluk Division |  | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. |  |  | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 17.6 | 52
4291 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 614.75 | 70
4292 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 2894/TD | 21/11/2023 | 0 | Resource Division | 2.04 | 0 | 0
4293 | Tamluk Division | Haldia Sub-Division | Payment to WBSEDCL for Electric Quotation money of Tabakhali Tube Well No. ¿ III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00377/2023-2024 | BP-2023-24-205 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
4294 | Tamluk Division | Haldia Sub-Division | Way Leave permission from South Eastern Railway for Tabakhali PWSS for Application ID-SER-KGP-2023-WL-67 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01828/2023-2024 | BP-2023-24-822 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.17 | 0 | 0
4295 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000162/2021-2022 | 1166/TD | 01/12/2021 | 7 | HORIZEN | 7.85 | 7.74 | 100
4296 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.26 | 100
4297 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Tabakhali Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000341/2022-2023 | 1284/TD | 12/09/2022 | 60 | ELECTIVA ENTERPRISE | 4.77 | 3.37 | 100
4298 | Tamluk Division | Haldia Sub-Division | Laying left out pipe line,Canal crossing & Rising main of ground water based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000365/2023-2024 | 933/TD | 01/06/2023 | 561 | RAJ KUMAR SINGHA | 81.39 | 65.01 | 88
4299 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd tubewell site of Tabakhali W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000395/2023-2024 | 1084/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 3 | 100
4300 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000022/2022-2023 | 410/TD | 25/05/2022 | 0 | Resource Division | 205.42 | 0 | 0
4301 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000087/2022-2023 | 1264/TD | 12/09/2022 | 0 | Resource Division | 34 | 0 | 0
4302 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme Block - Sutahata under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002024/2022-2023 | 862/W/MMD | 27/03/2023 | 180 | M/S B ENTERPRISE | 13.41 | 0 | 70
4303 | Tamluk Division | Haldia Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000416/2022-2023 | 1578/TD | 14/10/2022 | 180 | RAJ KUMAR SINGHA | 709.93 | 448.02 | 55
4304 | Tamluk Division | Haldia Sub-Division | Jack Pushing of Railway Track Between BASULYA - BARADA Railway Station on Tamluk-Haldia Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Tabakhali Piped Water Supply Scheme of 150 mm Dia G.I. Casing Pipe and 125 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO H50/11 & H50/13, H50/12 & H50/14 within Haldia Sub-Division under Tamluk Division, P.H.E DTE. (Total Length = 80 Mtr) Nodal Point J38 - J40. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000722/2023-2024 | 2944/TD | 23/11/2023 | 20 | KRISHNENDU SEKHAR DAS | 72.62 | 59.1 | 100
4305 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2022-2023 | 599/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.61 | 100
4306 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur (Balighai) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000324/2021-2022 | 1617/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.71 | 5.71 | 100
4307 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied work for Madhabpur (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000380/2023-2024 | 1024/TD | 07/06/2023 | 60 | BASANTA KUMAR MAITY | 45.82 | 0 | 90
4308 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-II Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000418/2022-2023 | 1576/TD | 14/10/2022 | 991 | BASANTA KUMAR MAITY | 495.32 | 136.92 | 75
4309 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2022-2023 | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 16.02 | 100
4310 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000112/2022-2023 | 1666/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0
4311 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000284/2022-2023 | 2637/TD | 02/02/2023 | 0 | Resource Division | 15.45 | 0 | 0
4312 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of MADHABPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671978/QUOT/03/48 DT. 05-04-2024 Application NO- 2004671978 Application type-New connection Consumer Id- 204266733 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00537/2024-2025 | BP-2024-25-90 | 24/04/2024 | 0 | WBSEDCL | 1 | 0 | 0
4313 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for MADHABPUR Water Supply Scheme T/W-I, Zone-II (Ref. ID-204047955) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01869/2023-2024 | W/23-24/222 | 01/09/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
4314 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001927/2022-2023 | 846/W/MMD | 24/03/2023 | 180 | AHALYA ENGINEERING WORKS | 37.88 | 28.29 | 60
4315 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
4316 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) |  |  | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 907 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 206.03 | 94
4317 | Tamluk Division |  | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) |  |  | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 995 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 229.79 | 70
4318 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 2897/TD | 21/11/2023 | 0 | Resource Division | 4.61 | 0 | 0
4319 | Tamluk Division | Haldia Electrical Sub-Division | Quotation money payment to WBSEDCL for Khejuri Zone-II Water Supply Scheme of Tube Well No. - III | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00536/2023-2024 | BP-2023-24-284 | 17/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0
4320 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low land at Head Work site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2024-2025 | 1909/TD | 07/06/2024 | 7 | TECHNO ENTERPRISE. | 2.02 | 2.02 | 100
4321 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 55.24 | 100
4322 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000444/2022-2023 | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 0 | 40
4323 | Tamluk Division | Haldia Electrical Sub-Division | Construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000457/2023-2024 | 1502/TD | 17/07/2023 | 40 | RAI CONSTRUCTION | 9.19 | 7.99 | 100
4324 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000532/2023-2024 | 1858/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 100
4325 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000533/2023-2024 | 1859/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.95 | 0.94 | 100
4326 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Pump Houses and Laying Rising Main for water connection between 1st , 2nd and 3rd Tube Well at Khejuri Water Supply Scheme (Zone-II) within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000733/2023-2024 | 2984/TD | 29/11/2023 | 45 | M/S SOURAV MAHAPATRA | 22.43 | 10.21 | 70
4327 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-III) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000745/2023-2024 | 3147/TD | 07/12/2023 | 10 | TECHNO ENTERPRISE. | 0.91 | 0.9 | 100
4328 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000042/2022-2023 | 828/TD | 15/07/2022 | 0 | Resource Division | 60.29 | 0 | 0
4329 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Chargeable Head, KHEJURI, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049542) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01673/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0
4330 | Tamluk Division |  | Relaying of 125 mm dia GI Pipe & 150 mm dia GI pipe line for canal crossing with allied works due to damage of pipe line of N.P.-97-99 (part) for construction of culvert of Strengthening & Widening Contai Junput Road of Aladarput Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. |  |  | ORD/000264/2021-2022 | 569 / CSD | 08/12/2021 | 21 | MRINAL KANTI PRADHAN | 2.24 | 0 | 0
4331 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 427 nos] under JJM in Aladarput PWSS [Sarsa(532, part),Uttar Dauki(549,part),Dakshin Paikbar(574,part),Faridpur(575, part),Biswanathpur(576, part),Aladarput(578, part),Hosenaput(579, part),Kalaminaput(580, part),Dakshin Murabanya(581, part),Bichina(584, part),Purba Chechuraput(585,part )] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000266/2020-2021 | 2919/TD | 22/02/2021 | 20 | BARH CONSTRUCTION | 26.62 | 4.66 | 100
4332 | Tamluk Division |  | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000372/2021-2022 |  | 01/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0
4333 | Tamluk Division |  | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000420/2021-2022 | BP-2021-22-93 | 05/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0
4334 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (618 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Purba Puroshattampur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000353/2023-2024 | 880/TD | 01/06/2023 | 180 | BARH CONSTRUCTION | 281.85 | 169.52 | 66
4335 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000166/2023-2024 | 98/TD | 05/01/2024 | 0 | Resource Division | 3.81 | 0 | 0
4336 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000265/2022-2023 | 2692/TD | 06/02/2023 | 0 | Resource Division | 14.58 | 0 | 0
4337 | Midnapore Mechanical | Digha Sub-Division | Purushottampur W/S scheme PH-I Application no.-2004522734 ref.-204156888 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03197/2023-2024 | BP-2023-24-472 | 27/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
4338 | Midnapore Mechanical | Digha Sub-Division | Purushottampur W/S scheme PH-II Application no.-2004522748 ref.-204156889 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03198/2023-2024 | BP-2023-24-471 | 27/12/2023 | 0 | WBSEDCL | 2.78 | 0 | 0
4339 | Midnapore Mechanical | Digha Sub-Division | Additional Quotation Bill for New Service connection at T/W NO-I & II Of PURBA PURUSHOTTAMPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- PBN/SM/958 DT. 28-02-2024 Application NO- T/W NO-I: 2004522734 Con. Id- 204156888 ( T/W NO-I) Application NO- T/W NO-II: 2004522748 Con. Id- 204156889 ( T/W NO-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04267/2023-2024 | BP-2023-24-795 | 06/03/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
4340 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBO PURUSHOTTAMPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001647/2022-2023 | 541/W/MMD | 20/03/2023 | 530 | SOUMEN ELECTRIC | 21.56 | 19.72 | 80
4341 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 146.95 | 51
4342 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000096/2024-2025 | 2961/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0
4343 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000124/2022-2023 | 2402/TD | 16/01/2023 | 0 | Resource Division | 11.28 | 0 | 0
4344 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767101/QUOT/03 DT. 07-06-2024 Application NO- 2004767101 Application type-New connection Consumer Id- 204325527 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01221/2024-2025 | BP-2024-25-300 | 18/06/2024 | 0 | WBSEDCL | 16.47 | 0 | 0
4345 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2005003663/QUOT/03 DT. 11-12-2024 Application NO- 2005003663 Application type-New connection Consumer Id- 204470602 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03655/2024-2025 | C012524056101 | 09/01/2025 | 0 | WBSEDCL | 7.68 | 0 | 0
4346 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAJI BASAN and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001624/2022-2023 | 509/W/MMD | 20/03/2023 | 180 | SANJIB SAHA | 22.79 | 0 | 0
4347 | Tamluk Division | Haldia Electrical Sub-Division | Rising main and other allied works Augmentation of Amarshikasba Zone-II W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000198/2023-2024 | 399/TD | 27/04/2023 | 446 | AURGHA BHATTACHARYA | 7.68 | 2.41 | 100
4348 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Amarshikasba Zone-II PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000290/2023-2024 | 592/TD | 17/05/2023 | 45 | ANUSKA ENTERPRISE | 21.29 | 7.74 | 40
4349 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Amarshikasba Zone-II & its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000291/2023-2024 | 593/TD | 17/05/2023 | 60 | M/S SOURAV MAHAPATRA | 7.26 | 5.78 | 100
4350 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000322/2022-2023 | 617/TD | 21/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.32 | 100
4351 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (2238 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-II water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000750/2022-2023 | 2593/TD | 30/01/2023 | 878 | DAS ENTERPRISE | 372.65 | 254.87 | 100
4352 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design and Drawing) without sanitary and water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Amarshikasba Zone-II and its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (For Low land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000845/2023-2024 | 18/TD | 03/01/2024 | 240 | GOUTAM DEY | 3.75 | 0 | 100
4353 | Tamluk Division | Haldia Electrical Sub-Division | Drum Sheet walling 1.40m. (av.) high on sal-bullah / Eucalyptus bullah pilling with allied works of Amarshi Kasba Zone-II & its adjoining moujas PWSS within Patashpur-I Block under Contai-Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001257/2024-2025 | 130/CSD | 16/01/2025 | 7 | GHOSH CONSTRUCTION (GST : 19AXMPG8403A1ZO) | 0.97 | 0 | 100
4354 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000069/2023-2024 | 2645/TD | 13/10/2023 | 0 | Resource Division | 14.4 | 0 | 0
4355 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000118/2022-2023 | 1669/TD | 03/11/2022 | 0 | Resource Division | 57.23 | 0 | 0
4356 | Central Drilling | Haldia Electrical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300 mm X 200mm X 190mm Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme(Z-II,TW-I), Patashpur -I Block under Purba Medinipur District, CDD,P.H.E.Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000483/2022-2023 | 2122/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 15.74 | 12.47 | 100
4357 | Central Drilling | Haldia Electrical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 190 Mtrs. Depth) by utilising Departmental Machineries for Amarshi Kasba W/S Scheme (Zone-I,T/W-III) , Patashpur-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000515/2022-2023 | 2123/CDD | 02/03/2023 | 300 | MENAKA ENTERPRISE | 15.74 | 12.78 | 100
4358 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for AMARSIKASBA Water Supply Scheme T/W-I, Zone -II, (Ref. ID-204098661) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02897/2023-2024 | BP-2023-24-311 | 01/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
4359 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of AMARSI KASBA W/S Scheme under MMD, PHE, Dte. Block- Potashpur-I, AMARSI C.C.C. Ref. Memo No- 2004607907/QUOT/03 DT. 21-02-2024 Application NO- 2004607907 Application type-New connection Reference Id- 204223198 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04384/2023-2024 | BP-2023-24-822 | 13/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
4360 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001971/2022-2023 | 814/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 22.8 | 19.87 | 10
4361 | Tamluk Division |  | Rejuvenation to accommodate FHTC (450 nos.) under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) |  |  | ORD/000005/2021-2022 | 683/TD | 10/09/2021 | 20 | TAPAS SANTRA | 63.43 | 124.51 | 100
4362 | Tamluk Division | Tamluk Sadar Sub-Division | Electric Quotation Bill under Nandakumar CCC at Bargodagodar PWSS under Tamluk Division, PHE Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00135/2022-2023 | BP-2022-23-511 | 22/12/2022 | 0 | WBSEDCL | 2.57 | 0 | 0
4363 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with sand filling and jhama -metal consolidation of Thekuabazar- Pursaghat Road due to lcutting of hard shoulder for laying water pipelines by PHE Dte. within Tamluk Highway Sub-Division under Tamluk Highway Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00231/2023-2024 | BP-2023-24-116 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.12 | 0 | 0
4364 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with Bituminous Surfacing ,sand filling and jhama -metal consolidation of Tamluk -Moyna road from 10 KM to 11.30 KM due to cutting of Hard shoulder for laying water pipe lines by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00233/2023-2024 | BP-2023-24-118 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.09 | 0 | 0
4365 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money for Bargodagodar PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00612/2022-2023 | BP-2022-23-820 | 24/03/2023 | 0 | WBSEDCL | 8.99 | 0 | 0
4366 | Tamluk Division | Tamluk Sadar Sub-Division | Pending paymens from PHED for Restoration work of Different road under Tamluk Highway Division, P.W.(Roads) Directorate. Memo No. 340 Dated 21/02/2025 of Executive Engineer, Tamluk Highway Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00698/2025-2026 |  | 20/08/2025 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.08 | 0 | 0
4367 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr.and repairing & renovation of 450 cum OHR and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bargodagodar Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000187/2022-2023 | 812/TD | 12/07/2022 | 180 | CONCORD ENGINEERING | 774.2 | 589.81 | 76
4368 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bargodagodar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000190/2021-2022 | 1199/TD | 02/12/2021 | 20 | RADIANT | 8.93 | 8.93 | 100
4369 | Tamluk Division | Tamluk Sadar Sub-Division | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 0.55 | 100
4370 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000397/2022-2023 | 1445/TD | 27/09/2022 | 30 | TARUN KHATUA | 4.85 | 4.85 | 100
4371 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of 150/200 mm dia DI(K-9) for Rising main line from T/W-1 to Existing delivery main including CI/DI specials supply under Bargodagodar PWSS with in Nandakumar Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000429/2025-2026 | 2828/TSD | 08/09/2025 | 30 | BARH CONSTRUCTION | 0.89 | 0 | 100
4372 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000436/2022-2023 | 1208/TSD | 15/09/2022 | 30 | S.K. MONDAL | 2.66 | 2.3 | 0
4373 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of 80 mm dia sluice valve and construction of chamber for 80 mm dia sluice valve at Nodal point J-307 to J-308, J-270 to J-271 and J-307 to J-321 J-168 to J-196 under Bargodagodar PWSS under Tamluk Sub-Division of Tamluk division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000566/2024-2025 | 196/TSD | 22/01/2025 | 15 | TARUN KHATUA | 0.82 | 0 | 100
4374 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe lines with allied works to facilitate the FHTC connection for Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000586/2023-2024 | 2205/TD | 01/09/2023 | 900 | SK. NUR ISLAM | 27.66 | 24.78 | 60
4375 | Tamluk Division | Tamluk Sadar Sub-Division | Functional Household Tap Connection (FHTC-796 nos) of Bargodagodar water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000588/2023-2024 | 2206/TD | 01/09/2023 | 900 | SK. NUR ISLAM | 27.14 | 16.19 | 60
4376 | Tamluk Division | Tamluk Sadar Sub-Division | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at Head work site under Bargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000602/2023-2024 | 2214/TD | 01/09/2023 | 40 | BARH CONSTRUCTION | 6.22 | 0 | 0
4377 | Tamluk Division | Tamluk Sadar Sub-Division | Dismentling of existing damaged staff quarter and godown of Bargodagodar and its adjoining mouza Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000604/2024-2025 | 337/TSD | 17/02/2025 | 390 | SK. INJAMUL ALI | 2.81 | 0 | 100
4378 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling work at 3rd tube well site of Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000738/2022-2023 | 74/TSD | 11/01/2023 | 15 | TARUN KHATUA | 0.95 | 0.95 | 100
4379 | Tamluk Division | Tamluk Sadar Sub-Division | Jungle cutting at Head work site in connection repair & renovation of Boundary of Boargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000755/2023-2024 | 1659/TSD | 11/12/2023 | 7 | PURNA CHANDRA BARH | 0.24 | 0 | 0
4380 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bargodagodar PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000828/2022-2023 | 3167/TD | 10/03/2023 | 632 | BARH CONSTRUCTION | 33.83 | 28.07 | 80
4381 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300 mm x 200 mm dia x 240 mtr. deep tube well by direct rotary rig method for Replacement of head work site Tube well of Bargodagudar Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001240/2023-2024 | 1084/TD | 16/03/2024 | 20 | MANNA COMPUTER | 17.87 | 16.15 | 100
4382 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000007/2022-2023 | 97/TD | 11/04/2022 | 0 | Resource Division | 41.98 | 0 | 0
4383 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000067/2021-2022 | 645/TD | 27/06/2022 | 0 | Resource Division | 37.93 | 0 | 0
4384 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000203/2023-2024 | 1102/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
4385 | Central Drilling | Tamluk Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BATGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000016/2022-2023 | 434/CDD | 23/05/2022 | 30 | PADMA ENGINEERING & CO. | 13.86 | 13.01 | 100
4386 | Central Drilling | Tamluk Sadar Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCH, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000220/2022-2023 | 146/CMSD-I | 30/05/2022 | 3 | PADMA ENGINEERING & CO. | 0.35 | 0 | 0
4387 | Central Drilling | Tamluk Sadar Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 1.99 | 0
4388 | Central Drilling | Tamluk Sadar Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AND OTHERS AT SITE FOR CONSTRUCTION OF TUBE WELL IN BARGODAGODAR W/S SCHEME, NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000509/2022-2023 | 146/CMSD-I | 30/05/2022 | 3 | PADMA ENGINEERING & CO. | 0.31 | 0.3 | 100
4389 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001469/2022-2023 | 207/W/MMD | 10/02/2023 | 180 | SOUMEN ELECTRIC | 40.4 | 37.91 | 100
4390 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000004/2022-2023 | 60/TD | 05/04/2022 | 60 | TAPAS SANTRA | 154.84 | 129.6 | 100
4391 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part-D) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000008/2022-2023 | 55/TD | 05/04/2022 | 90 | MAA ANANDAMAYEE | 251.38 | 251.38 | 100
4392 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000009/2022-2023 | 54/TD | 05/04/2022 | 90 | HARIPADA PATTANAYAK | 273.36 | 272.86 | 100
4393 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000039/2022-2023 | 138/TD | 19/04/2022 | 1442 | BIDHAN MONDAL | 184.94 | 90.33 | 100
4394 | Tamluk Division | Haldia Electrical Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Kulbari Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000132/2023-2024 | 268/TD | 20/04/2023 | 855 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.15 | 0 | 100
4395 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kulbari Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000186/2021-2022 | 1195/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 10.5 | 10.5 | 100
4396 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 1 (One) no Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at OHR Site of Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000236/2022-2023 | 977/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 17.17 | 16.45 | 100
4397 | Tamluk Division | Haldia Electrical Sub-Division | Supply of DI Specials for Proposed Rejuvenation & Retrofitting of Laying Distribution System of KULBARI PWSS under tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000328/2022-2023 | 1229/TD | 07/09/2022 | 15 | BAGLAMUKHI SECURITY SERVICE | 4.81 | 4.81 | 100
4398 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Pump House at OHR site & 2nd Pump house and boundary wall at 2nd TW site and new construction of boundary wall at OHR site and renovation works of OHR for Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000357/2023-2024 | 925/TD | 01/06/2023 | 575 | HARIPADA PATTANAYAK | 44.56 | 0 | 100
4399 | Tamluk Division | Haldia Electrical Sub-Division | Sal-bullah /Eucalyptus bullah piling of pipe line and its allied works to accommodate FHTC at Kulbari water supply scheme in Chandipur Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur(PART-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000358/2023-2024 | 926/TD | 01/06/2023 | 20 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.86 | 12.86 | 100
4400 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 2(Two) nos M.S. Structure over irrigation canal to support 90 mm dia. UPVC distribution pipe under Kulbari Water Supply Scheme at NP 71-893 & NP 72-475 under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte.(Each length=15.00 Mtr ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000432/2024-2025 | 3553/TD | 19/11/2024 | 24 | MAA ANANDAMAYEE | 4.46 | 0 | 100
4401 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2022-2023 | 96/TD | 11/04/2022 | 0 | Resource Division | 43.14 | 0 | 0
4402 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000028/2022-2023 | 418/TD | 25/05/2022 | 0 | Resource Division | 4.92 | 0 | 0
4403 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000064/2021-2022 | 642/TD | 27/06/2022 | 0 | Resource Division | 27.12 | 0 | 0
4404 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000197/2023-2024 | 1097/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
4405 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0
4406 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0
4407 | Tamluk Division | Digha Sub-Division | Sinking of 250mm x 150mm dia Tube well of 210 mtr deep tubewell Drilling by Direct Rotary method with 150 dia.uPVC. Strainer of 30m.length all complete including cost of materials for Replacement of 2nd Tubewell at Bagmari & its adjoining mouzas Water Supply Scheme within Egra- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000116/2024-2025 | 1913/TD | 07/06/2024 | 20 | MAITY CONSTRUCTION | 12.06 | 10.45 | 100
4408 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 200 Cum Capacity OHR ( Intze type with pile foundatio ) & Accommodate FHTC ( 1230 Nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000180/2023-2024 | 294/TD | 20/04/2023 | 180 | BASANTA KUMAR MAITY | 401.59 | 256.63 | 63
4409 | Tamluk Division | Digha Sub-Division | Laying of balance distribution pipe line to provide Balance FHTC with allied works for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHE Dte, Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000596/2024-2025 | 568/TD | 17/02/2025 | 50 | MAITY CONSTRUCTION | 23.23 | 0 | 0
4410 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000115/2023-2024 | 79/TD | 05/01/2024 | 0 | Resource Division | 7.58 | 0 | 0
4411 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000267/2022-2023 | 2700/TD | 06/02/2023 | 0 | Resource Division | 46.45 | 0 | 0
4412 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-I, (Ref. ID-204134070) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03001/2023-2024 | BP-2023-24-358 | 24/11/2023 | 0 | WBSEDCL | 4.02 | 0 | 0
4413 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-II, (Ref. ID-204143154) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03055/2023-2024 | BP-2023-24-376 | 02/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
4414 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGMARI and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001687/2022-2023 | 560/W/MMD | 20/03/2023 | 438 | M/S B.M. ELECTRICAL | 22.81 | 21.13 | 10
4415 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Santipur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000475/2024-2025 | 3764/TD | 10/12/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
4416 | Tamluk Division | Tamluk Sadar Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 (from Mecheda bus stop to Hakola Bus stop) of Santipur Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001182/2023-2024 | 741/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.24 | 0 | 0
4417 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000168/2023-2024 | 117/TD | 05/01/2024 | 0 | Resource Division | 14.4 | 0 | 0
4418 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000208/2022-2023 | 2466/TD | 16/01/2023 | 0 | Resource Division | 21.59 | 0 | 0
4419 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Santipur W/S scheme H/W Site Application No.-2004562690 Ref.-204191008 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03464/2023-2024 | BP-2023-24-589 | 02/02/2024 | 0 | WBSEDCL | 10.61 | 0 | 0
4420 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
4421 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 15 | S.S.GHORAI | 2.13 | 0 | 70
4422 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 365 | S.S.GHORAI | 4.78 | 0 | 40
4423 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTIPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001340/2022-2023 | 2345/W/MMD | 29/12/2022 | 895 | GOENKA ENTERPRISE | 25.26 | 0 | 30
4424 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
4425 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Switch Room cum Chlorine Room at 2nd Tube Well site and Boundary Wall at Head Work site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000304/2024-2025 | 2904/TD | 10/09/2024 | 460 | TAPAS SANTRA | 27.24 | 0 | 100
4426 | Tamluk Division | Haldia Electrical Sub-Division | Additional Laying Distribution System of 200 mm dia upvc pipe line, Drumpsheet Pilling and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 300 mm dia(sec 19-23) and 180 mm dia(sec-22-57) of pipe line of Ananantapur Zone-II Water Supply Scheme of Tamluk Sub-Division under Tamluk Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000308/2024-2025 | 3138/TD | 26/09/2024 | 210 | TAPAS SANTRA | 53.77 | 0 | 100
4427 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000398/2023-2024 | 1082/TD | 08/06/2023 | 45 | TARUN KHATUA | 5.1 | 5.1 | 100
4428 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000463/2021-2022 | 1740/TD | 03/02/2022 | 20 | RADIANT | 3.89 | 3.86 | 100
4429 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (5686 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000481/2022-2023 | 1885/TD | 24/11/2022 | 859 | TAPAS SANTRA | 609.95 | 450.15 | 75
4430 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 200 /250/300mm dia DI(K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of approach road at 3rd tube well site under Anantapur Zone- II PWSS with in Tamluk Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000579/2023-2024 | 2201/TD | 01/09/2023 | 20 | TARUN KHATUA | 8.66 | 8.49 | 80
4431 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work Site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000600/2023-2024 | 2213/TD | 01/09/2023 | 40 | TARUN KHATUA | 5.14 | 5.12 | 100
4432 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000048/2022-2023 | 1018/TD | 08/08/2022 | 0 | Resource Division | 88.34 | 0 | 0
4433 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000057/2022-2023 | 1207/TD | 06/09/2022 | 0 | Resource Division | 2.44 | 0 | 0
4434 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000223/2023-2024 | 1122/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
4435 | Central Drilling | Haldia Electrical Sub-Division | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Anantapur W/S Scheme (Z-II, TW-III) Tamluk block under purba medinipur district, CDD, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000427/2022-2023 | 2116/CDD | 02/03/2023 | 30 | MENAKA ENTERPRISE | 17.75 | 16.11 | 0
4436 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for ANANTAPUR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048948) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01775/2023-2024 | BP-2023-24-188 | 11/08/2023 | 0 | WBSEDCL | 9.99 | 0 | 0
4437 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for ANANTAPUR, Water Supply Scheme ,Zone-I, T/W-III, (Ref. ID-204060666) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01816/2023-2024 | BP-2023-24-189 | 14/08/2023 | 0 | WBSEDCL | 6.18 | 0 | 0
4438 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001740/2022-2023 | 641/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.59 | 9.63 | 35
4439 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mustaphapur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2024-2025 | 2199/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4440 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 170.24 | 51
4441 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000052/2024-2025 | 1660/TD | 29/04/2024 | 0 | Resource Division | 11.12 | 0 | 0
4442 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000151/2022-2023 | 2457/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
4443 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MUSTAFAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649225/QUOT/03 DT. 20-03-2024 Application NO- 2004649225 Application type-New connection Consumer Id- 204250590 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00008/2024-2025 | BP-2024-25-2 | 04/04/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
4444 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MUSTAPHAPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886313/QUOT/03/583 DT. 06-09-2024 Application NO- 2004886313 Application type-New connection Consumer Id- 204391660 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02452/2024-2025 | C092443181607 | 27/09/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
4445 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUSTAPHAPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001620/2022-2023 | 507/W/MMD | 20/03/2023 | 742 | M/S DILIP MITRA | 22.77 | 0 | 85
4446 | Tamluk Division | Contai Sub-Division | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 0 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0
4447 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 1080 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 219.1 | 30
4448 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000083/2024-2025 | 2969/TD | 12/09/2024 | 0 | Resource Division | 12.36 | 0 | 0
4449 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000248/2022-2023 | 2718/TD | 06/02/2023 | 0 | Resource Division | 38.35 | 0 | 0
4450 | Midnapore Mechanical | Contai Sub-Division | Nayaput W/S scheme PH-I Application no.-2004522692 ref.-204156883 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03199/2023-2024 | BP-2023-24-473 | 27/12/2023 | 0 | WBSEDCL | 4.81 | 0 | 0
4451 | Midnapore Mechanical | Contai Sub-Division | Nayaput W/S scheme PH-II Application no.-2004522675 ref.-204156884 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03201/2023-2024 | BP-2023-24-474 | 27/12/2023 | 0 | WBSEDCL | 4.44 | 0 | 0
4452 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAYAPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001651/2022-2023 | 523/W/MMD | 20/03/2023 | 180 | S.G.TECHNICAL SERVICE | 23.69 | 16.85 | 55
4453 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Laying distribution system pipe line, accommodate FHTC(1309 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of 200 Cum. capacity RCC over Head Reservoir and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Kurpai PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000231/2023-2024 | 461/TD | 04/05/2023 | 1062 | MAA ANANDAMAYEE | 396.25 | 57.75 | 75
4454 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution System (missing nodal as per drawing) of 110 mm dia & 125 mm dia HDPE pipe line, Drumpsheet Pilling and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia (sec 203-206, 132-133, 437-443, 639-638, 705-713 and 183-155) of pipe line of Kurpai Water Supply Scheme of Tamluk Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000536/2024-2025 | 201/TD | 15/01/2025 | 441 | MAA ANANDAMAYEE | 36.38 | 0 | 100
4455 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000219/2022-2023 | 2679/TD | 06/02/2023 | 0 | Resource Division | 19.42 | 0 | 0
4456 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Kurpai W/S scheme H/W site. Application.-2004547144 Ref.-204177947 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03301/2023-2024 | BP-2023-24-547 | 15/01/2024 | 0 | WBSEDCL | 8.64 | 0 | 0
4457 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kurpai T/W-II Tamluk CCC Application No=2005004861 Reference ID=204470853 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03678/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
4458 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KURPAI AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000085/2023-2024 | 1271/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 35
4459 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 75.02 | 51
4460 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000031/2024-2025 | 1633/TD | 18/06/2025 | 0 | Resource Division | 8.76 | 0 | 0
4461 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000140/2022-2023 | 2440/TD | 16/01/2023 | 0 | Resource Division | 30.48 | 0 | 0
4462 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004707237/QUOT/03 DT. 29-04-2024 Application NO- 2004707237 MEMO NO: AMR/PHE/90 DT.29/04/2024 Application type-New connection Consumer Id- 204291521 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00855/2024-2025 | BP-2024-25-163 | 15/05/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
4463 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004944304/QUOT/03 DT. 25-10-2024 Application NO- 2004944304 Application type-New connection Consumer Id- 204428639 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03005/2024-2025 | C112423561463 | 19/11/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
4464 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAKRAMPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001404/2022-2023 | 2415/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.79 | 0 | 50
4465 | Tamluk Division | Digha Sub-Division | Additional Quotation for Additional Service connection Charges against APP NO: 2004521731 IRO DEPAL W/S Scheme T/W no-I AT DEPAL Under Jal Jeevan Mission under MMD, PHE, Dte. Block- RAMNAGAR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No-DGA/776 DT. 05-08-2024 Application NO- 100000115575 DT. 05-08-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860310305 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00761/2024-2025 | BP-2024-25-381 | 29/08/2024 | 0 | WBSEDCL | 11.8 | 0 | 0
4466 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 200.93 | 60
4467 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000129/2023-2024 | 108/TD | 05/01/2024 | 0 | Resource Division | 11.02 | 0 | 0
4468 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000309/2022-2023 | 2999/TD | 27/02/2023 | 0 | Resource Division | 22.33 | 0 | 0
4469 | Midnapore Mechanical | Digha Sub-Division | Depal W/S scheme TW no.-I Ref.-204156070 Application ID-2004521731 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03155/2023-2024 | BP-2023-24-439 | 19/12/2023 | 0 | WBSEDCL | 5.4 | 0 | 0
4470 | Midnapore Mechanical | Digha Sub-Division | DEPAL w/s SCHEME PH -II APPLICATION nO.-2004566534 REF.-204194525 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03535/2023-2024 | BP-2023-24-612 | 07/02/2024 | 0 | WBSEDCL | 24.63 | 0 | 0
4471 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEPAL and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001359/2022-2023 | 2370/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 85
4472 | Tamluk Division | Contai Sub-Division | Tube well, Pump House, 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2353 nos) under JJM with allied work for Chingur Dania- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000479/2023-2024 | 1552/TD | 19/07/2023 | 1046 | DAS ENTERPRISE | 764.26 | 293.31 | 70
4473 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000081/2024-2025 | 2953/TD | 12/09/2024 | 0 | Resource Division | 14.49 | 0 | 0
4474 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000336/2022-2023 | 2979/TD | 27/02/2023 | 0 | Resource Division | 17 | 0 | 0
4475 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 42.76 | 11
4476 | Midnapore Mechanical | Contai Sub-Division | Chingurdania W/S scheme PH No.-I Application No.-2004565714 Ref.-204193544 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03477/2023-2024 | BP-2023-24-594 | 02/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
4477 | Midnapore Mechanical | Contai Sub-Division | Quotation for New service connection at Chingurdaniya w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004620601 , Ref ID 204229471) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04330/2023-2024 | BP-2023-24-812 | 11/03/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
4478 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baispur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2024-2025 | 2195/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4479 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 189.99 | 51
4480 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000009/2025-2026 | 2071/TD | 12/08/2025 | 0 | Resource Division | 7.71 | 0 | 0
4481 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000126/2022-2023 | 2410/TD | 16/01/2023 | 0 | Resource Division | 21.35 | 0 | 0
4482 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAISPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004970204/QUOT/03/1383 DT. 19-11-2024 Application NO- 2004970204 Application type-New connection Consumer Id- 204449426 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03244/2024-2025 | C122405685539 | 05/12/2024 | 0 | WBSEDCL | 10.24 | 0 | 0
4483 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAISPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004962430/QUOT/03 DT. 12-10-2024 Application NO- 2004962430 Application type-New connection Consumer Id- 204443612 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03275/2024-2025 | C122405543180 | 05/12/2024 | 0 | WBSEDCL | 5.21 | 0 | 0
4484 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAISPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001346/2022-2023 | 2357/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0
4485 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Daidpur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000482/2023-2024 | 1568/TD | 19/07/2023 | 180 | M/S JOY MAA DURGA ENTERPRISE | 488.61 | 243.96 | 60
4486 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000031/2025-2026 | 2090/TD | 12/08/2025 | 0 | Resource Division | 10.15 | 0 | 0
4487 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000252/2022-2023 | 2714/TD | 06/02/2023 | 0 | Resource Division | 61 | 0 | 0
4488 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of UTTAR DAUDPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852092/QUOT/03/562 DT. 07-08-2024 Application NO- 2004852092 Application type-New connection Consumer Id- 204373375 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02123/2024-2025 | C092403062421 | 04/09/2024 | 0 | WBSEDCL | 6.07 | 0 | 0
4489 | Midnapore Mechanical | Digha Sub-Division | Uttar Daudpur W/S scheme PH-I Application no.-2004523051 ref.-204157004 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03189/2023-2024 | BP-2023-24-485 | 27/12/2023 | 0 | WBSEDCL | 3.69 | 0 | 0
4490 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR DAIDPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001358/2022-2023 | 2369/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 11.06 | 85
4491 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 235.32 | 40
4492 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000169/2023-2024 | 113/TD | 05/01/2024 | 0 | Resource Division | 9.76 | 0 | 0
4493 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000264/2022-2023 | 2701/TD | 06/02/2023 | 0 | Resource Division | 27.23 | 0 | 0
4494 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SANTRA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004746350/QUOT/03 DT. 22-05-2024 Application NO- 2004746350 Application type-New connection Consumer Id- 204313989 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01136/2024-2025 | BP-2024-25-256 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0
4495 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT TW-1 OF SANTRA WS SCHEME UNDER MMD PHE DTE , BLOCK-RAMNAGAR-1, DIGHA CCC APPLICATION NO-2004746369 CON ID-204313990 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01141/2024-2025 | BP-2024-25-255 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0
4496 | Midnapore Mechanical | Digha Sub-Division | Provisional quotation for Shifting of existing LT network iro PHE Dte to effect NSC at T/W-1 of Santra ws scheme under Digha CCC. Ref. ID-860323530 Application ID-100000127700 CON ID-204313990 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04010/2024-2025 | C022508499737 | 04/02/2025 | 0 | WBSEDCL | 0.66 | 0 | 0
4497 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTRA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001580/2022-2023 | 463/W/MMD | 20/03/2023 | 712 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 12.6 | 90
4498 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Uttar Khasda W/S Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000436/2023-2024 | 1419/TD | 12/07/2023 | 30 | PULAK KUMAR SAMANTA | 8.31 | 7.06 | 100
4499 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1 (One) no. Boosting Tube Well of Uttar Khasda & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000864/2023-2024 | 234/TD | 10/01/2024 | 390 | THE GODFATHER TRADING COMPANY | 3.44 | 0 | 100
4500 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Uttar Khasda Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000865/2023-2024 | 233/TD | 10/01/2024 | 60 | KAMAL KUMAR BERA | 4.02 | 3.82 | 100
4501 | Central Drilling | Contai Sub-Division | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260 mtrs. depth) by utilising Departmental machineries for uttar Khasda WS Scheme (TW-III) contai-I block under Purba midnapore District , CDD, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000344/2022-2023 | 1345/CDD | 24/11/2022 | 30 | MENAKA ENTERPRISE | 19.77 | 14.04 | 0
4502 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for UTTAR KHASDA Water Supply SchemeT/W-III (Ref. ID-204049279) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01636/2023-2024 | BP-2023-24-136 | 27/07/2023 | 0 | WBSEDCL | 2.59 | 0 | 0
4503 | Midnapore Mechanical | Contai Sub-Division | Uttar Khasda W/S scheme T/W-III Application-no.-2004381822 Ref.-204049279 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03165/2023-2024 | C072340248980 | 31/01/2025 | 0 | WBSEDCL | 0 | 0 | 0
4504 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001736/2022-2023 | 638/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 13.57 | 9.66 | 100
4505 | Tamluk Division | Haldia Sub-Division | Quotation bill for new service connection at TW-II of Mohanpur w/s scheme,Block-Sutahata under MMD, PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818907 Application type-new connection Reference ID-204355767 Quotation Date-12/07/2024 Quotation Due Date-14/07/2025 Contract Demand-6479 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00682/2024-2025 | BP-2024-25-311 | 02/08/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
4506 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000207/2023-2024 | 418/TD | 02/05/2023 | 1087 | NARAYAN CHANDRA DAS | 135.23 | 68.23 | 30
4507 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (300nos) and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000246/2023-2024 | 525/TD | 11/05/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 175.05 | 32.44 | 25
4508 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site ,Land Development work & Construction of Retaining wall of ground water based Mohanpur Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000730/2023-2024 | 2981/TD | 29/11/2023 | 540 | M/S SOURAV MAHAPATRA | 14.92 | 5.92 | 30
4509 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000793/2022-2023 | 3044/TD | 27/02/2023 | 60 | NARAYAN CHANDRA DAS | 135.23 | 0 | 0
4510 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000794/2022-2023 | 3045/TD | 27/02/2023 | 30 | FARID UDDIN AHMED | 89.21 | 23.55 | 30
4511 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (591 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000795/2022-2023 | 3046/TD | 27/02/2023 | 30 | ANUSKA ENTERPRISE | 71.82 | 0 | 0
4512 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000161/2022-2023 | 2474/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0
4513 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000191/2023-2024 | 640/W | 20/02/2024 | 0 | Resource Division | 12.26 | 0 | 0
4514 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Mohanpur W/S Scheme (T/W-I & II) , Sutahata Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000120/2023-2024 | 1387/CDD | 19/09/2023 | 318 | MENAKA ENTERPRISE | 31.41 | 29 | 100
4515 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Mohanpur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695195 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6800W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00647/2024-2025 | BP-2024-25-112 | 06/05/2024 | 0 | WBSEDCL | 16.83 | 0 | 0
4516 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MOHANPUR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001678/2022-2023 | 567/W/MMD | 20/03/2023 | 925 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 70
4517 | Tamluk Division | Tamluk Sadar Sub-Division | Land development at Head work site and 2nd Tube well site of Mamudpur Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000141/2024-2025 | 1921/TD | 07/06/2024 | 161 | SAYAN CONSTRUCTION | 7.12 | 0 | 95
4518 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1127 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Mamudpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000402/2023-2024 | 1094/TD | 08/06/2023 | 1118 | SUJATA CONSTRUCTION | 315 | 83.66 | 20
4519 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000297/2022-2023 | 3008/TD | 27/02/2023 | 0 | Resource Division | 20.18 | 0 | 0
4520 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at TW-I of Mamudpur W/S scheme under MMD PHE Dte. Block-Tamluk Tamluk CCC Application No.-2004916353 Consumer ID.-204409669 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02974/2024-2025 | C112402770847 | 05/11/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
4521 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Mamudpur at T/W NO-II W/S SCHEME under MMD,PHE,Dte. BLOCK- Tamluk WBSEDCL SUPPLY OFFICE: Tamluk C.C.C Ref. Memo No- 2004974247/Quot/03/1718 DT. 21-11-2024 APPLICATION NO: 2004974247 Consumer Id- 204451590 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03278/2024-2025 | C122406872784 | 06/12/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
4522 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001697/2022-2023 | 623/W/MMD | 20/03/2023 | 1198 | BHABANI PRASAD MANNA | 23.7 | 0 | 40
4523 | Tamluk Division | Contai Sub-Division | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1847 nos) under JJM with allied work for AJAYA- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000474/2023-2024 | 1515/TD | 17/07/2023 | 987 | TAPAS SANTRA | 664.53 | 432.68 | 70
4524 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000066/2024-2025 | 2946/TD | 12/09/2024 | 0 | Resource Division | 11.38 | 0 | 0
4525 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000339/2022-2023 | 2976/TD | 27/02/2023 | 0 | Resource Division | 32.62 | 0 | 0
4526 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.83 | 11
4527 | Midnapore Mechanical | Contai Sub-Division | Ajaya W/S scheme T/W -I Application No.-2004565721 Ref.-204193605 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03475/2023-2024 | BP-2023-24-593 | 02/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
4528 | Midnapore Mechanical | Contai Sub-Division | Ajaya W/S scheme T/W -II Application No.-2004565730 Ref.-204193622 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03476/2023-2024 | BP-2023-24-592 | 02/02/2024 | 0 | WBSEDCL | 8.24 | 0 | 0
4529 | Midnapore Mechanical | Contai Sub-Division | ADDITIONAL QUOTATION FOR AJAYA W/S PH-II UNDER JJM UNDER MIDNAPORE MECHANICAL DIVISION,PHE DTE. MEMO NO: KJR/QI/391 Dated:18.12.2025 Reference ID: 860358764 DT.18.12.2025 Application ID:100000155104 DT.18.12.2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04139/2025-2026 |  | 23/12/2025 | 0 | WBSEDCL | 4.43 | 0 | 0
4530 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJAYA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002290/2022-2023 | 2384/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 12.66 | 45
4531 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharat Katbar PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000188/2024-2025 | 2198/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4532 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 69.77 | 51
4533 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000049/2024-2025 | 1656/TD | 29/04/2024 | 0 | Resource Division | 11.67 | 0 | 0
4534 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000146/2022-2023 | 2450/TD | 16/01/2023 | 0 | Resource Division | 31.66 | 0 | 0
4535 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHARAT KOTBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760152/QUOT/03 DT. 04-06-2024 Application NO- 2004760152 Application type-New connection Consumer Id- 204322027 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01276/2024-2025 | BP-2024-25-319 | 24/06/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
4536 | Midnapore Mechanical | Contai Sub-Division | ADDITIONAL Quotation Bill for the errection work at T/W NO-I Of KHARAT KOTBAR W/S Scheme under JJM Under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No-PTP/QOT/855 DT. 05-08-2025 Application NO- 100000145028 DT. 05-08-2025 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860344668 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01903/2025-2026 |  | 18/08/2025 | 0 | WBSEDCL | 0.34 | 0 | 0
4537 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHARATKOTBAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811790/QUOT/03 DT. 11-07-2024 Application NO- 2004811790 Application type-New connection Consumer Id- 204351927 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01977/2024-2025 | BP-2024-25-565 | 14/08/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
4538 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF SEPTEMBER'2023 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04349/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
4539 | Midnapore Mechanical | Contai Sub-Division | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/W/MMD DATED-28.08.2024. FOR THE MONTH OF NOV'2024 UNDER HESD, PHE DTE | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04363/2025-2026 |  | 14/01/2026 | 0 | S.S.GHORAI | 0.2 | 0 | 0
4540 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
4541 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARAT KATBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001370/2022-2023 | 2381/W/MMD | 31/12/2022 | 1924 | ECO ENTERPRISE | 25.26 | 15.54 | 85
4542 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000485/2022-2023 | 1890/TD | 24/11/2022 | 60 | H. SAMANTA | 123.68 | 64.87 | 53
4543 | Tamluk Division | Digha Sub-Division | Construction of approach road at H/W site & 2nd T/W site of Sarrang Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2024-2025 | 209/TD | 15/01/2025 | 30 | ASEMA ENTERPRISE | 1.95 | 0 | 0
4544 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000289/2022-2023 | 2645/TD | 02/02/2023 | 0 | Resource Division | 16.37 | 0 | 0
4545 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Agar PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000163/2024-2025 | 2075/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4546 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall ,Rising main , O&M and accommodate FHTC (832 nos) under JJM with allied work for AGAR PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000346/2023-2024 | 850/TD | 31/05/2023 | 915 | JAGANNATH MAKAR | 196.83 | 75.94 | 60
4547 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & construction of R.C.C. Elevated Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied works under Agar & its adjoining moujas Water Supply Scheme in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000418/2023-2024 | 1087/TD | 08/06/2023 | 1077 | GOUTAM CONSTRUCTION | 75.53 | 0 | 60
4548 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000112/2023-2024 | 76/TD | 05/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
4549 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000315/2022-2023 | 3003/TD | 27/02/2023 | 0 | Resource Division | 20.51 | 0 | 0
4550 | Central Drilling | Tamluk Sadar Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 44.37 | 11
4551 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Agar Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004676891 Reference ID=204270379 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00668/2024-2025 | BP-2024-25-168 | 15/05/2024 | 0 | WBSEDCL | 0.29 | 0 | 0
4552 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Agar Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004699675 Reference ID=204286135 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00669/2024-2025 | BP-2024-25-169 | 15/05/2024 | 0 | WBSEDCL | 5.63 | 0 | 0
4553 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Quotation Bill for Agar T/W-II Matangini CCC Application No=100000125403 Reference ID=860320063 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03877/2024-2025 | C012539021905 | 21/01/2025 | 0 | WBSEDCL | 0.6 | 0 | 0
4554 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AGAR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000167/2023-2024 | 1409/W/MMD | 02/06/2023 | 180 | M/S B.M. ELECTRICAL | 21.62 | 0 | 0
4555 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Khar at Patashpur - II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000586/2024-2025 | 462/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
4556 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 22.13 | 51
4557 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000048/2024-2025 | 1655/TD | 29/04/2024 | 0 | Resource Division | 17.55 | 0 | 0
4558 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000153/2022-2023 | 2459/TD | 16/01/2023 | 0 | Resource Division | 53.73 | 0 | 0
4559 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004671992/QUOT/03/40 DT. 08-04-2024 Application NO- 2004671992 Application type-New connection Consumer Id- 204266827 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00501/2024-2025 | BP-2024-25-95 | 24/04/2024 | 0 | WBSEDCL | 5.83 | 0 | 0
4560 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886304/QUOT/03/581 DT. 06-09-2024 Application NO- 2004886304 Application type-New connection Consumer Id- 204391661 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02449/2024-2025 | C092443182184 | 27/09/2024 | 0 | WBSEDCL | 3.56 | 0 | 0
4561 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001674/2022-2023 | 569/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 27.17 | 0 | 52
4562 | Tamluk Division | Haldia Sub-Division | Quotation for new service connection at Bar Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No. 2004755767, Ref ID 204319519) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00605/2024-2025 | BP-2024-25-295 | 29/07/2024 | 0 | WBSEDCL | 24.37 | 0 | 0
4563 | Tamluk Division | Haldia Sub-Division | Ground water based Bar Amrit Bere Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (200 Cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2023-2024 | 1048/TD | 07/06/2023 | 629 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 412.67 | 268.46 | 45
4564 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000897/2022-2023 | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 0 | 50
4565 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Bar Amrit Bere PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001054/2023-2024 | 384/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4566 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000119/2023-2024 | 96/TD | 05/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
4567 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000341/2022-2023 | 2985/TD | 27/02/2023 | 0 | Resource Division | 18.82 | 0 | 0
4568 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for Baramritberia Water Supply scheme Tube well no.-I Mahishadal CCC Block-Mahishadal Application No.-2004603891 Ref ID.-204219157 Quatation Bill Date.-15/03/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04575/2023-2024 | BP-2023-24-890 | 22/03/2024 | 0 | WBSEDCL | 14.61 | 0 | 0
4569 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAMRIT BERE and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001632/2022-2023 | 514/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 20.88 | 100
4570 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Soil investigation & Accommodate FHTC (1527 nos) under JJM with allied work for BARMUNDA- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000498/2023-2024 | 1672/TD | 25/07/2023 | 887 | HALDIA DEVELOPMENT CONSTRUCTION | 584.47 | 0 | 48
4571 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barmunda PWSS at Patashpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001050/2023-2024 | 380/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4572 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2024-2025 | 1647/TD | 29/04/2024 | 0 | Resource Division | 9.41 | 0 | 0
4573 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000318/2022-2023 | 2995/TD | 27/02/2023 | 0 | Resource Division | 26.96 | 0 | 0
4574 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657865/QUOT/03 DT. 28-03-2024 Application NO- 2004657865 Application type-New connection Consumer Id- 204257681 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00258/2024-2025 | BP-2024-25-29 | 15/04/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
4575 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889786/QUOT/03 DT. 12-09-2024 Application NO- 2004889786 Application type-New connection Consumer Id- 204393533 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02501/2024-2025 | C092445097329 | 30/09/2024 | 0 | WBSEDCL | 4.5 | 0 | 0
4576 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARMUNDA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002030/2022-2023 | 938/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 22.77 | 17.51 | 65
4577 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at Head Work site Tube well of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000022/2023-2024 | 120/TD | 06/04/2023 | 40 | KALPANA BUILDERS | 57.98 | 52.05 | 100
4578 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000320/2022-2023 | 590/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.77 | 3.77 | 100
4579 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied works for Paniparul (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000599/2023-2024 | 2194/TD | 01/09/2023 | 60 | BASANTA KUMAR MAITY | 55.17 | 0 | 75
4580 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul Zone-II Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000723/2022-2023 | 2534/TD | 19/01/2023 | 894 | BASANTA KUMAR MAITY | 644.68 | 352.62 | 78
4581 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000232/2022-2023 | 2615/TD | 02/02/2023 | 0 | Resource Division | 122.45 | 0 | 0
4582 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000282/2022-2023 | 2635/TD | 02/02/2023 | 0 | Resource Division | 23.91 | 0 | 0
4583 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of PANIPARUL W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004773750/QUOT/03/483 DT. 18-06-2024 Application NO- 2004773750 Application type-New connection Consumer Id- 204332477 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01327/2024-2025 | BP-2024-25-360 | 01/07/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
4584 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for PANIPARUL Water Supply Scheme T/W-II, Zone -II, (Ref. ID-204087320) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02896/2023-2024 | BP-2023-24-312 | 01/11/2023 | 0 | WBSEDCL | 2.76 | 0 | 0
4585 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for PANIPARUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204128964) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03056/2023-2024 | BP-2023-24-389 | 02/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
4586 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001934/2022-2023 | 853/W/MMD | 24/03/2023 | 799 | M/S S.G. ENTERPRISE | 26.86 | 24.84 | 80
4587 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - II Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002702/2023-2024 | 1051/W/MMD | 13/03/2024 | 385 | GLACIER ENGINEERING CO. | 14 | 9.07 | 54
4588 | Tamluk Division | Contai Sub-Division | Bill for payment to WBSEDCL for Shifting of Electric Line for Mukundapur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02049/2023-2024 | BP-2023-24-961 | 14/03/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
4589 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 955 | MACKINTOSH BURN LIMITED | 10310.59 | 259.99 | 75
4590 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000085/2024-2025 | 2968/TD | 12/09/2024 | 0 | Resource Division | 8.17 | 0 | 0
4591 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000165/2022-2023 | 2393/TD | 16/01/2023 | 0 | Resource Division | 30.99 | 0 | 0
4592 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749319/QUOT/03 DT. 28-05-2024 Application NO- 2004749319 Application type-New connection Consumer Id- 204315788 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01145/2024-2025 | BP-2024-25-259 | 06/06/2024 | 0 | WBSEDCL | 2.83 | 0 | 0
4593 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001672/2022-2023 | 554/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 22.8 | 0 | 55
4594 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000460/2022-2023 | 1859/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.95 | 100
4595 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Repair of Pump House , Repair Boundary Wall , land development for approch road & Accommodate FHTC (70 nos) under JJM with allied work for Bathuari (Zone-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000648/2023-2024 | 2600/TD | 10/10/2023 | 813 | DILIP KUMAR GHOSH | 110.33 | 84.13 | 82
4596 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000052/2023-2024 | 2080/TD | 28/08/2023 | 0 | Resource Division | 14.36 | 0 | 0
4597 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000109/2023-2024 | 3012/TD | 29/11/2023 | 0 | Resource Division | 0.14 | 0 | 0
4598 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
4599 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (430 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000282/2023-2024 | 565/TD | 12/05/2023 | 1107 | JASODA ENTERPRISE | 125.59 | 86.85 | 75
4600 | Tamluk Division | Contai Sub-Division | 250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line,Pump House , Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur Block within Contai Sub-Division under Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000599/2024-2025 | 578/TD | 19/02/2025 | 180 | ARABINDA GHOSH | 217.97 | 0 | 0
4601 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (120 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000906/2022-2023 | 3461/TD | 27/03/2023 | 1168 | JASODA ENTERPRISE | 62.76 | 52.07 | 85
4602 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line & Accommodate FHTC (250 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000907/2022-2023 | 3462/TD | 27/03/2023 | 1074 | R CONSTRUCTION | 82.45 | 61.21 | 80
4603 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (320 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000908/2022-2023 | 3463/TD | 27/03/2023 | 849 | PARIA ENTERPRISE | 82.41 | 50.9 | 65
4604 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (74 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000909/2022-2023 | 3464/TD | 27/03/2023 | 1080 | LAKSHMI NARAYAN ENTERPRISE | 19.34 | 13.18 | 70
4605 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000182/2023-2024 | 631/W | 20/02/2024 | 0 | Resource Division | 12.74 | 0 | 0
4606 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000310/2022-2023 | 2966/TD | 27/02/2023 | 0 | Resource Division | 171.72 | 0 | 0
4607 | Central Drilling | Contai Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 49.1 | 11
4608 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ITABERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601903/QUOT/03 DT. 15-02-2024 Application NO- 2004601903 Application type-New connection Reference Id- 204217836 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00599/2024-2025 |  | 24/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
4609 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for Shifting of 33 KV FEEDER HT LINE AT SABITRAPUR( KANPUR W/S SCHEME ZONE-V, T/W NO-I) , RAMNAGRA -II BLOCK , DIGHA CCC, DIST.-PURBA MEDINIPUR. Ref. MEMO No- CD/1971 Dt. 22.02.2024 Application NO- 100000101137 Dt. 22/02/2024 Reference Id- 860292957 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04262/2023-2024 | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
4610 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for ITABERIA Water Supply Scheme, T/W-I, (Ref. ID-204217836) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04345/2023-2024 | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 0.49 | 0 | 0
4611 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
4612 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
4613 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 695 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000260/2023-2024 | 534/TD | 12/05/2023 | 1133 | M/S SREE DURGA ENTERPRISE | 199.79 | 154.02 | 75
4614 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 288 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000264/2023-2024 | 533/TD | 12/05/2023 | 1104 | M/S SREE DURGA ENTERPRISE | 111.4 | 91.22 | 82
4615 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, left out pipe line, road restoration, Accommodate FHTC (27 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000298/2024-2025 | 3067/TD | 19/09/2024 | 30 | DHANANJOY DAS | 34.51 | 0 | 2
4616 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 534 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000409/2023-2024 | 1095/TD | 08/06/2023 | 1107 | RELIABLE CONSTRUCTIONS | 253.87 | 107.87 | 25
4617 | Tamluk Division | Digha Sub-Division | Drum Sheet walling , pipe line(for FHTC), road restoration, Accommodate FHTC (60 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part ¿ A ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000534/2024-2025 | 210/TD | 15/01/2025 | 30 | RELIABLE CONSTRUCTIONS | 23.37 | 0 | 0
4618 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (275 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000920/2022-2023 | 3557/TD | 29/03/2023 | 30 | BUNBA CONSTRUCTION | 39.82 | 34.71 | 65
4619 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (116 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000921/2022-2023 | 3558/TD | 29/03/2023 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.49 | 8.15 | 60
4620 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Gopalpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001047/2023-2024 | 377/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
4621 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000173/2023-2024 | 109/TD | 05/01/2024 | 0 | Resource Division | 11.75 | 0 | 0
4622 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000217/2022-2023 | 2687/TD | 06/02/2023 | 0 | Resource Division | 21.28 | 0 | 0
4623 | Central Drilling | Digha Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.51 | 11
4624 | Central Drilling | Digha Sub-Division | Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000199/2023-2024 | 04/CMSD-II(D) | 11/01/2024 | 198 | MD NIZAMUDDIN | 0.94 | 2.36 | 45
4625 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Uttar Gopalpur ws scheme under MMD,PHE Dte. Ref Application no-2004579836, CON ID-204204432, PICABONI CCC,Block-Ramnagar II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03653/2023-2024 | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
4626 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of Uttar Gopalpur ws scheme under MMD, PHE Dte. Ref. Application no-2004579816, Ref Con ID-204204428. PICHABONI CCC, Block-Ramnagar-II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03656/2023-2024 | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 4.27 | 0 | 0
4627 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 1080 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
4628 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000086/2024-2025 | 2967/TD | 12/09/2024 | 0 | Resource Division | 2.47 | 0 | 0
4629 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000206/2022-2023 | 2399/TD | 16/01/2023 | 0 | Resource Division | 3.44 | 0 | 0
4630 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MASHAGON and ADJOINING MOUJAS, Block ¿ contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001684/2022-2023 | 559/W/MMD | 20/03/2023 | 180 | DIPALI CONSTRUCTION | 22.6 | 0 | 0
4631 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Ailan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000186/2024-2025 | 2196/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100
4632 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 892 | MACKINTOSH BURN LIMITED | 19507.71 | 257.69 | 51
4633 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000006/2025-2026 | 2069/TD | 12/08/2025 | 0 | Resource Division | 18.76 | 0 | 0
4634 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000131/2022-2023 | 2415/TD | 16/01/2023 | 0 | Resource Division | 25.14 | 0 | 0
4635 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of AILAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2005170629/QUOT/03/175 DT. 16-04-2025 Application NO- 2005170629 Application type-New connection Consumer Id- 204588611 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00705/2025-2026 |  | 08/05/2025 | 0 | WBSEDCL | 18.41 | 0 | 0
4636 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of AILAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2005047686/QUOT/03/131 DT. 27-01-2025 Application NO- 2005047686 Application type-New connection Consumer Id- 204498435 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04503/2024-2025 | C032587409521 | 27/03/2025 | 0 | WBSEDCL | 3.8 | 0 | 0
4637 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AILAN and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000088/2023-2024 | 1268/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0
4638 | Midnapore Mechanical | Digha Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
4639 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the New Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Tamluk Dev. Block (Av. depth 205 mtr.) = 03 Unit, Sahid Matangini Dev. Block (Av. depth 205mtr.) = 01 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 06 Unit. Name of Site : i) G.P.- Anantapur-I, Mouza- Maisali, J.L. No.-127, Plot No.- 16 under Tamluk Dev. Block, ii) G.P.- Municipality, Mouza- Daharpur, J.L. No.- 276, Plot No.- 442 under Tamluk Dev. Block, iii) G.P.- Pipulberia-I, Mouza - Gaurangapur, J.L. No.-150, Plot No.- 373 under Tamluk Dev. Block, iv) G.P.- Balluk-I, Mouza - Janubasan RH, J.L. No.- 44, Plot No.- 40 under Sahid Matangini Dev. Block, v) G.P.- Sarbodaya, Mouza- Naskarpur, J.L. No.-262, Plot No.- 120 under Egra-II Dev. Block & vi) G.P.- Basudevpur, Mouza- Shyamharibar, J.L. No.- 266, Plot No.- 3611 under Egra-II Dev. Block. |  |  | ORD/000045/2022-2023 | 175/TD | 25/04/2022 | 45 | CHANDA AGENCIES | 62.48 | 59.93 | 100
4640 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Khejuri-II Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 01Unit. Name of Site : i) G.P.- Nijkasba, Mouza- Thanaberia, J.L. No.- 98, Plot No.- 328 under Khejuri-II Dev. Block. |  |  | ORD/000051/2022-2023 | 296/TD | 06/05/2022 | 25 | SK. NUR ISLAM | 11.05 | 10.88 | 100
4641 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Ramnagar-I Dev. Block (Av. depth 230mtr.) = 01 Unit, Ramnagar-II Dev. Block (Av. depth 205mtr.) = 02 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 05 Unit. Name of Site : i) G.P.- Talgachari-I, Mouza- Talgachari, J.L. No.-108, Plot No.- 633 under Ramnagar-I Dev. Block, ii) G.P.- Balisai, Mouza- Bararankua, J.L. No.-200, Plot No.-307 under Ramnagar-II Dev. Block, iii) G.P.-Maithana, Mouza - Demuria Paikbar, J.L. No.-142, Plot No.-275 under Ramnagar-II Dev. Block, iv) G.P.- Paniparul, Mouza -Paniparul, J.L. No.-203, Plot No.-3329 under Egra-II Dev. Block & v) G.P.- Dubda, Mouza- Dubda, J.L. No.-191, Plot No.-38 under Egra-II Dev. Block. |  |  | ORD/000277/2021-2022 | 1526/TD | 11/01/2022 | 45 | BASANTA KUMAR MAITY | 53.79 | 53.72 | 100
4642 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Contai-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Contai-III Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 02 Unit. Name of Site : i) G.P.- Sabajpur, Mouza- Sabajpur, J.L. No.- 296, Plot No.- 503 under Contai-I Dev. Block, & ii) G.P.- Debendra, Mouza- Balageria, J.L. No.- 79, Plot No.- 250 under Contai-III Dev. Block, |  |  | ORD/000278/2021-2022 | 1527/TD | 11/01/2022 | 30 | SRIMANTA KUMAR MAITY | 22.46 | 10.79 | 100
4643 | Tamluk Division |  | Installation of display Board at 54 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000329/2024-2025 | 3288/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9 | 0 | 100
4644 | Tamluk Division |  | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. |  |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 0.37 | 100
4645 | Tamluk Division |  | Continuation Work Order for Hiring of Diesel Motor Cab/ Luxury Taxy (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2022 to 31.05.2023 i.e. 06 b(Six) months for the use of the office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. |  |  | ORD/000939/2022-2023 | 375/RWS/TSD | 30/11/2022 | 156 | SRIMANTA PANJA | 0.74 | 2.35 | 100
4646 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Deshpran Dev. Block (Av. depth 230 mtr.) = 01 Unit ] Total 01 Unit. Name of Site : i) G.P.- Basntia, Mouza- Purba Mukundapur, J.L. No.- 488, Plot No.- 120 under Deshpran Dev. Block |  |  | ORD/000279/2021-2022 | 1528/TD | 11/01/2022 | 20 | SUBRATA KUMAR BERA | 11.09 | 11.03 | 100
4647 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Nandakumar Dev. Block (Av. depth 260 mtr.) = 02 Unit, Mahishadal Dev. Block (Av. depth 260mtr.) = 01 Unit, Sutahata Dev. Block (Av. depth 260 mtr.) = 02 Unit & Kolaghat Dev. Block (Av. depth 205 mtr.) = 01 Unit ] Total 06 Unit. |  |  | ORD/000280/2021-2022 | 1529/TD | 11/01/2022 | 45 | ARABINDA GHOSH | 69.7 | 65.53 | 100
4648 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-II Dev. Block (Av. depth 230 mtr.) = 07 Unit ] Total 07 Unit. |  |  | ORD/000281/2021-2022 | 1530/TD | 11/01/2022 | 50 | MIDNAPUR PIPE CONCERN | 66.72 | 65.61 | 100
4649 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Chandipur Dev. Block (Av. depth 230 mtr.) = 02 Unit, Haldia Dev. Block (Av. depth 260mtr.) = 01 Unit, Panskura-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Patashpur-II Dev. Block (Av. depth 230 mtr.) = 02 Unit ] Total 06 Unit. |  |  | ORD/000282/2021-2022 | 1531/TD | 11/01/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 64.74 | 63.36 | 100
4650 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-I Dev. Block (Av. depth 230 mtr.) = 03 Unit & Khejuri-II Dev. Block (Av. depth 260 mtr.) = 02 Unit ] Total 05 Unit. |  |  | ORD/000283/2021-2022 | 1532/TD | 11/01/2022 | 45 | MIDNAPUR PIPE CONCERN | 50.45 | 48.67 | 100
4651 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 50 cum OHR & Accommodate FHTC (131 nos) under JJM with allied work for PANCHBERRYA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000513/2023-2024 | 1742/TD | 01/08/2023 | 719 | S.D. CONSTRUCTION | 141.9 | 0 | 0
4652 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000162/2023-2024 | 116/TD | 05/01/2024 | 0 | Resource Division | 0.81 | 0 | 0
4653 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000347/2022-2023 | 3017/TD | 27/02/2023 | 0 | Resource Division | 7.21 | 0 | 0
4654 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at PANCHBERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000045/2023-2024 | 1217/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.87 | 0 | 40
4655 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Dona Zone-I Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 249/TD | 19/04/2023 | 30 | GHOSH ENTERPRISE | 85.84 | 79.22 | 95
4656 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (610 nos.) under JJM in Dona Zone-I Water Supply Scheme within Moyan Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 250/TD | 19/04/2023 | 25 | GHOSH ENTERPRISE | 23.24 | 0 | 0
4657 | Tamluk Division | Contai Sub-Division | Providing 1321 Nos FHTC (Functional Household Tap Connection) with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Bhagawanpur-II Block under Contai Sub Division of Tamluk Division, PHE DTe.Purba Medinipur (Phase -II) | Assistant Engineer | Junior Engineer | ORD/000401/2023-2024 | 1069/TD | 08/06/2023 | 45 | TAPAS SANTRA | 91.09 | 0 | 0
4658 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 2096/TD | 29/08/2023 | 0 | Resource Division | 26.91 | 0 | 0
4659 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 2636/TD | 13/10/2023 | 0 | Resource Division | 8.14 | 0 | 0
4660 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in PAYA ( MAHAPRABHU) PWSS ( Phase-II) Block - Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 240/TD | 19/04/2023 | 30 | MAITY CONSTRUCTION | 67.92 | 57.26 | 100
4661 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000125/2023-2024 | 93//TD | 05/01/2024 | 0 | Resource Division | 1.66 | 0 | 0
4662 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000271/2022-2023 | 2672/TD | 06/02/2023 | 0 | Resource Division | 10.22 | 0 | 0
4663 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DAHADAYA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004991409/QUOT/03 DT. 05-12-2024 Application NO- 2004991409 Application type-New connection Consumer Id- 204463589 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03667/2024-2025 | C012524068154 | 09/01/2025 | 0 | WBSEDCL | 3.61 | 0 | 0
4664 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at DAHA DAYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000043/2023-2024 | 1214/W/MMD | 25/04/2023 | 889 | THE GODFATHER TRADING COMPANY | 12.14 | 5.32 | 65
4665 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for new service connection at TW-III of Barsundra w/s scheme,under MMD,PHE,Dte.,Purba Medinipur Block-Haldia, C.C.C.-Brajalalchak Application no.-2004651015 Application Type-New connection Quotation Date-22/03/2024 Quotation Due Date-24/03/2025 Contract Demand-10209 W | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00018/2024-2025 | BP-2024-25-17 | 08/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
4666 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at BARBASUDEBPUR and adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2024-2025 | 535/HESD | 10/06/2024 | 15 | KOLEY ENTERPRISE | 1.23 | 0.18 | 75
4667 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation, Rejuvenation, Other JJM works for the purpose of Geotagging at JALPAI and adjacent under MMD, P.H.E. Dte.in the Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000064/2024-2025 | 534/HESD | 10/06/2024 | 15 | MUKHERJEE ART CENTRE | 2.11 | 0.26 | 75
4668 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Thenkuachak, Zone-II PWSS in the District of Purba Medinipur under JJM programme | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000075/2023-2024 | 1244/W/MMD | 28/04/2023 | 703 | TAPAN KUMAR SARKAR | 11.15 | 0 | 80
4669 | Tamluk Division | Contai Sub-Division | Laying of different dia HDPE Pipe line to accommodate remaining FHTC under Augmentation of Amtalia PWSS within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte., in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000142/2023-2024 | 285/TD | 20/04/2023 | 40 | GHOSH ENTERPRISE | 56.31 | 55.82 | 100
4670 | Tamluk Division | Contai Sub-Division | Installation of display Board of Dariapur Retrofitting PWSS at 2 nos TW site , Amtalia Retrofitting PWSS at 2 nos TW site , Bakiput Retrofitting PWSS at 1 nos TW site inContai - II Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipur District. | Assistant Engineer | Junior Engineer | ORD/000298/2025-2026 | 1597/CSD | 19/06/2025 | 7 | AMIT PAYRA | 0.83 | 0 | 0
4671 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line With allied Works for Augmentation Of Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 665/TD | 19/05/2023 | 30 | M/S S. S. ENTERPRISE | 58.98 | 56.28 | 100
4672 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
4673 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001841/2022-2023 | 758/W/MMD | 23/03/2023 | 1269 | SOUMEN ELECTRIC | 11.85 | 5.47 | 40
4674 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000019/2023-2024 | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100
4675 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000009/2023-2024 | 346/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
4676 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for DAKSHIN MECHOGRAM Water Supply Scheme T/W- III, (Ref. ID-204066734) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01829/2023-2024 | BP-2023-24-205 | 24/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
4677 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 35
4678 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
4679 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 15 | S.S.GHORAI | 2.13 | 0 | 70
4680 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
4681 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 35.83 | 100
4682 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000007/2023-2024 | 348/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
4683 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional quotation for Kulbari w/s scheme PH III in the district of Purba Medinipur under MMD PHE Dte. (App ID 100000118086, Con ID 860311696) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02429/2024-2025 | C102415733205 | 05/10/2024 | 0 | WBSEDCL | 0.38 | 0 | 0
4684 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0
4685 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0
4686 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional quotation for Kulbari w/s scheme PH IV in the district of Purba MEdinipur under MMD PHE Dte. (Ref ID 860321422, App ID 100000126272) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03978/2024-2025 | C012552983326 | 31/01/2025 | 0 | WBSEDCL | 0.91 | 0 | 0
4687 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 0 | 55
4688 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya Zone II under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2023-2024 | 1080/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 5.27 | 100
4689 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000464/2022-2023 | 1876/TD | 22/11/2022 | 30 | PRASANTA MONDAL | 4.13 | 4 | 0
4690 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000493/2022-2023 | 1879/TD | 22/11/2022 | 60 | DIPANKAR MALAKAR | 5.11 | 5.09 | 100
4691 | Tamluk Division | Haldia Sub-Division | Canal crossing , laying Rising main, Construction of boundary wall of Head work site & 2nd TW site & Drum Sheet walling of Natshal Lakshya (Zone-II) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000590/2023-2024 | 2207/TD | 01/09/2023 | 502 | RAJ KUMAR SINGHA | 91.71 | 67.66 | 30
4692 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 183.73 | 65
4693 | Tamluk Division | Haldia Sub-Division | Supply and delivery of 3 nos office Table/Executive Desk (Godrej - 120cm X 60cm X 72.80cm, RH) 2 nos Chairs (without arms rest) and 2 nos stainless steel rack (72inch X 36inch X 15 inch) with 5nos selves) (all articles are should be of Godrej interio Brand) under office of the Assistant Engineer, Haldia Sub-Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001012/2023-2024 | 688/HSD, | 31/01/2024 | 343 | MALLIK TRADERS | 0.99 | 0 | 100
4694 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Tabakhali PWSS, Dakshinchak Zone-1 PWSS, Dakshinchak Zone-II PWSS, Natshal lakshya Zone-II PWSS) (Phase-V) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001170/2023-2024 | 766/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0.83 | 100
4695 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for NATSHALLAKHYA Water Supply Scheme Z-II, T/W-III (Ref. ID-204048971) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01635/2023-2024 | BP-2023-24-140 | 27/07/2023 | 0 | WBSEDCL | 4.26 | 0 | 0
4696 | Central Drilling | Haldia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-II, T/W-II), Mahisadal Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000123/2023-2024 | 876/CDD | 11/07/2023 | 386 | MENAKA ENTERPRISE | 21.16 | 19.11 | 100
4697 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001755/2022-2023 | 634/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 13.46 | 90
4698 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000141/2023-2024 | 122/TD | 05/01/2024 | 0 | Resource Division | 16.51 | 0 | 0
4699 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000259/2022-2023 | 2683/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0
4700 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HOGALBERYA and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001339/2022-2023 | 2344/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 25.26 | 0 | 40
4701 | Tamluk Division |  | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 75
4702 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur Districtunder JJM Program under MMD PHE Dte. |  |  | ORD/001437/2023-2024 | 3091/W/MMD | 29/11/2023 | 180 | M/S. S.R. ENTERPRISE | 11.83 | 0 | 0
4703 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004721008/QUOT/03 DT. 07-05-2024 Application NO- 2004721008 Application type-New connection Consumer Id- 204298882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00442/2024-2025 | BP-2024-25-170 | 10/06/2024 | 0 | WBSEDCL | 31.79 | 0 | 0
4704 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 155 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. (Part Work Order 1/2) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000195/2024-2025 | 315/TD | 22/01/2025 | 30 | PRANAB KUMAR DAS | 49.33 | 0 | 0
4705 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000497/2022-2023 | 1933/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.37 | 100
4706 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 355 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000520/2023-2024 | 1757/TD | 01/08/2023 | 909 | SUSIL KUMAR HAZRA | 193.96 | 49.81 | 55
4707 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-I PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001045/2023-2024 | 375/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0.95 | 100
4708 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2023-2024 | 2074/TD | 28/08/2023 | 0 | Resource Division | 13.25 | 0 | 0
4709 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000098/2023-2024 | 3001/TD | 29/11/2023 | 0 | Resource Division | 2.99 | 0 | 0
4710 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
4711 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-I in Purba Medinipur District,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000745/2023-2024 | 2289/W/MMD | 29/08/2023 | 701 | S.S.GHORAI | 23.52 | 11.31 | 90
Total | [10 empty] | 1982698.91 | 119548.89