## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | RCFA Division -I |  | Material Requisition To Resource Division |  |  | RTOR000012/2025-2026 | 2540/RCD-I | 01/09/2025 | 0 | Resource Division | 6.92 | 0 | 0
2 | Durgapur W/S Division |  | Formal order for the work of Laying of branch pipe line at Basudevpur ,Binodpur and Sashipur mouza with its adjoining area UPVC pipe of Kanchanpur W/s Scheme under DWSD, PHE Dte (SL-08) |  |  | ORD/000027/2021-2022 | 834/DWSD | 24/05/2021 | 15 | T.M.CONCRETE CREATION PVT LTD | 10.76 | 0 | 0
3 | Durgapur W/S Division |  | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Augmentation of Kanchanpur piped W/s Scheme (Part- A) |  |  | ORD/000165/2023-2024 | 1296/DWSD | 07/08/2023 | 15 | M/S MANDAL ENTERPRISE | 5.87 | 5.87 | 100
4 | Durgapur W/S Division |  | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Kanchanpur under Augmentation of Kanchanpur piped W/s Scheme (Part- B) |  |  | ORD/000166/2023-2024 | 1298/DWSD | 07/08/2023 | 15 | M/S BANERJEE CONSTRUCTION | 7.05 | 7.05 | 100
5 | Durgapur W/S Division |  | Continuation order for Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Retrofitting of ARRAH piped W/s Scheme (Part- A) |  |  | ORD/000173/2023-2024 | 1376/DWSD | 14/08/2023 | 7 | M/S MANDAL ENTERPRISE | 1.72 | 1.72 | 100
6 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) |  |  | ORD/000182/2021-2022 | 1403/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 3.03 | 0 | 0
7 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Dismantling of concre road and reconcreting the same at poral para,Khadrapara ,near Kanksa Police Station under pass to towards kanksa PS and Sher para under command areaof Kanksa zone-II W/s Scheme for providing of FHTC under DWSD,PHE Dte (SL-04) |  |  | ORD/000185/2021-2022 | 1406/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 4.56 | 0 | 0
8 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Madhammath Subashpally sher para of Kanksa mouza Zone-II Ph-II W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000186/2021-2022 | 1407/DWSD | 29/09/2021 | 15 | SWATI CORPORATION | 4.56 | 0 | 0
9 | Durgapur W/S Division |  | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000346/2021-2022 | 135/DWSD | 02/02/2022 | 15 | MD JAWED KHAN | 6.6 | 0 | 50
10 | Durgapur W/S Division |  | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000424/2021-2022 | 245/DWSD | 28/02/2022 | 15 | PRAVAT SARKAR | 4.97 | 0 | 50
11 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Ruidas para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000457/2022-2023 | 310/DWSD | 20/02/2023 | 15 | QUICK PAL SUPPLIERS | 6.96 | 6.96 | 100
12 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Akandara Bouri para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000458/2022-2023 | 311/DWSD | 20/02/2023 | 15 | M/S MONDAL ENTERPRISE | 6.94 | 6.87 | 0
13 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Hazra para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000460/2022-2023 | 312/DWSD | 20/02/2023 | 15 | GHOSH ENTERPRISE | 6.92 | 6.92 | 0
14 | Durgapur W/S Division |  | Acceptance cum formal order for the work of water supply arrangement at Muslim Para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000461/2022-2023 | 313/DWSD | 20/02/2023 | 15 | RUBY CONSTRUCTION | 6.96 | 6.96 | 0
15 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Akandara Adibasipara ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000462/2022-2023 | 314/DWSD | 20/02/2023 | 15 | JUBILEE CONSTRUCTION | 6.95 | 6.95 | 0
16 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement 1(One) No ICDS Centre at Shyambazar for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000463/2022-2023 | 315/DWSD | 20/02/2023 | 15 | KIRON ENTERPRISE | 12.15 | 11.92 | 0
17 | Durgapur W/S Division |  | Acceptance cum formal order for the work of water supply arrangement at Jatgoria Junior High School ICDS Centre having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000464/2022-2023 | 316/DWSD | 20/02/2023 | 15 | BASANTI TRADERS | 6.95 | 6.95 | 0
18 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Borobigha Adibasi para ICDS Centre of Domra Bagdipara ICDS, Domra Bagdipara,Satkahania billpara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000467/2022-2023 | 263/DWSD | 15/02/2023 | 25 | BISHAL ENTERPRISE | 21.24 | 21.24 | 0
19 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000025/2021-2022 | 962/RCD-I | 07/06/2021 | 30 | ASHA CONSTRUCTION | 45.95 | 83.29 | 0
20 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000026/2021-2022 | 963/RCD-I | 07/06/2021 | 30 | DAS & CHAKRABORTY | 45.92 | 10.12 | 0
21 | RCFA Division -I | RCFA Division I | Sinking of 4 (Four) nos river bed tube wells including collecting main at Runakuraghat for Flood damaged at river Ajoy under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl No. 14) | Assistant Engineer 1 | Junior Engineer | ORD/000034/2022-2023 | 1093/RCD I | 13/05/2022 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 4.99 | 4.73 | 100
22 | RCFA Division -I | RCFA Division I | Additional work of supplying, aligning and laying of 160 mm dia HDPE pipe line for distribution line at Bolkundi village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000551/2021-2022 | 250/RCD-I | 01/02/2022 | 15 | DAS & CHAKRABORTY | 2.05 | 2.05 | 0
23 | RCFA Division -I | RCFA Division I | Additional work for laying of different dia DI (K7) & HDPE pipe line with other allied work from Dabor OHR Zone-II (Lohat, Phulberiya, Patal, Sadhana, Madhaichak, Shyamdihi etc.) distribution Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 08) | Assistant Engineer 1 | Junior Engineer | ORD/000552/2021-2022 | 251/RCD-I | 01/02/2022 | 15 | ASHA CONSTRUCTION | 2.18 | 1.96 | 0
24 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE line (Parallel to main distribution) for Ghidoba village & Kushum Danali West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1 | Junior Engineer | ORD/000553/2021-2022 | 252/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.98 | 4.71 | 0
25 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 1 | Junior Engineer | ORD/000554/2021-2022 | 253/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.99 | 4.71 | 0
26 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba East side under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1 | Junior Engineer | ORD/000575/2021-2022 | 257/RCD-I | 01/02/2022 | 20 | B.T.M CONCERN | 4.98 | 4.75 | 0
27 | RCFA Division -I | RCFA Division I | Extension of UPVC Pipe line at Uttarrampur and Part of Kalisanko including connection to different ICDS & FP Schools for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl no 01) | Assistant Engineer 1 | Junior Engineer | ORD/000607/2021-2022 | 630/ RCD I | 09/03/2022 | 15 | KHEPI MAA TRADERS | 4.18 | 2.74 | 0
28 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE line (parallel to main distribution) at Ghidoba, Kushum Danali and extension of pipe line at Ghiadoba village for providing FHTC under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte.(Sl no 07) | Assistant Engineer 1 | Junior Engineer | ORD/000613/2021-2022 | 636/RCD 1 | 09/03/2022 | 15 | DAS & CHAKRABORTY | 3.01 | 2.45 | 0
29 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of UPVC line (parallel to main distribution) at Malladihi Hospital para towards Chayanpur for providing FHTC work under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl no 09) | Assistant Engineer 1 | Junior Engineer | ORD/000615/2021-2022 | 638/RCD 1 | 09/03/2022 | 15 | MD AAMIR KHAN | 2.82 | 0 | 0
30 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000018/2025-2026 | 2534/RCD-I | 01/09/2025 | 0 | Resource Division | 5.45 | 0 | 0
31 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000013/2021-2022 | 950/RCD-I | 07/06/2021 | 30 | UMA ENTERPRISE | 30.02 | 30.7 | 0
32 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000014/2021-2022 | 951/RCD-I | 07/06/2021 | 30 | TARAPRASAD SARKAR | 30.12 | 24.47 | 0
33 | RCFA Division -I | RCFA Division I | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission and its components at Barabani, Salanpur, Jamuria, Pandabeswar, Raniganj, Andal, Kansha & Durgapur Faridpur Block in the Districts of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000718/2023-2024 | Camp_02_8_Nos_Block_AE_II | 26/09/2023 | 30 | MUKHERJEE TRADERS | 3.79 | 3.79 | 100
34 | RCFA Division -I | RCFA Division I | Supply of it periphersls under sub district laboratory | Assistant Engineer 2 | Junior Engineer | BILL/00211/2024-2025 | 92/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.02 | 0 | 0
35 | RCFA Division -I | RCFA Division I | Fuel and vehicle bill for Feb 2023 to June 23 | Assistant Engineer 2 | Junior Engineer | BILL/00511/2023-2024 | 234/23-24 | 04/09/2023 | 0 | NIRMALA TRADERS | 1.19 | 0 | 0
36 | RCFA Division -I | RCFA Division I | Spiral Binding | Assistant Engineer 2 | Junior Engineer | BILL/00610/2023-2024 | 185/23-24 | 10/08/2023 | 0 | MUKHERJEE TRADERS | 0.68 | 0 | 0
37 | RCFA Division -I | RCFA Division I | Transporting loading and unloading of jackets Banners etc for pump operator and valve operation at sites under JJM | Assistant Engineer 2 | Junior Engineer | BILL/00611/2023-2024 | 179/23-24 | 08/08/2023 | 0 | SHARMA ENGINEERING WORKS | 0.18 | 0 | 0
38 | RCFA Division -I | RCFA Division I | hire charges & fuel bill of Ranajit Auto | Assistant Engineer 2 | Junior Engineer | BILL/00612/2023-2024 | 220/23-24 | 22/08/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
39 | RCFA Division -I | RCFA Division I | fuel bill shyamal maji jyly 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00613/2023-2024 | 220/23-24 | 24/08/2023 | 0 | RANAJIT AUTO | 0.16 | 0 | 0
40 | RCFA Division -I | RCFA Division I | Khepi Maa Traders | Assistant Engineer 2 | Junior Engineer | BILL/00614/2023-2024 | 215/23-24 | 22/08/2023 | 0 | KHEPI MAA TRADERS | 1.16 | 0 | 0
41 | RCFA Division -I | RCFA Division I | Hire charge and fuel bill for the month o June 2023 to August 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00759/2023-2024 | 323/23-24 | 17/10/2023 | 0 | KHEPI MAA TRADERS | 1.19 | 0 | 0
42 | RCFA Division -I | RCFA Division I | Submissin of quarterly revised return for non salary return Bill no 7236 to 7339 | Assistant Engineer 2 | Junior Engineer | BILL/00774/2023-2024 | 367/23-24 | 10/11/2023 | 0 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0
43 | RCFA Division -I | RCFA Division I | Vehicle bill for 37 D 0482 Oct 2023 and nov 2023 | Assistant Engineer 2 | Junior Engineer | BILL/01144/2023-2024 | 429/23-24 | 20/12/2023 | 0 | SHYAMAL MAJI | 0.3 | 0 | 0
44 | RCFA Division -I | RCFA Division I | Fuel bill for WB 37 D 0482 for Oct 23 and Nov 23 | Assistant Engineer 2 | Junior Engineer | BILL/01145/2023-2024 | 430/23-24 | 20/12/2023 | 0 | RANAJIT AUTO | 0.29 | 0 | 0
45 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 20.75 | 100
46 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000211/2023-2024 | 2242/RCD-I | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 12.81 | 11.11 | 100
47 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Subhas Para & Chunari Para (Sansad-III) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000258/2021-2022 | 1867/RCD-I | 28/10/2021 | 30 | DAS & CHAKRABORTY | 18.1 | 18.09 | 0
48 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 20.57 | 0
49 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 6.08 | 0
50 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Suri Para, Bisakhalakhi Tala (Sansad-VI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000261/2021-2022 | 1870/RCD-I | 28/10/2021 | 30 | JAYANTA DATTA | 18.06 | 18.06 | 0
51 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Puratan Mushlim Para & Dhibarpara (Sansad-VII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000262/2021-2022 | 1871/RCD-I | 28/10/2021 | 30 | RUBY CONSTRUCTION | 15.67 | 15.67 | 0
52 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kankardanga (Sansad-VIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000263/2021-2022 | 1872/RCD-I | 28/10/2021 | 30 | MS KALYAN ENTERPRISE | 10.6 | 10.6 | 0
53 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dangal Para (Sansad-XI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000264/2021-2022 | 1873/RCD-I | 28/10/2021 | 30 | SNEHA ELECTRIC | 13.31 | 13.3 | 0
54 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mulimpara & Ruidaspara (Sansad-XIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000265/2021-2022 | 1874/RCD-I | 28/10/2021 | 30 | MD. JAWED KHAN | 18.16 | 18.15 | 0
55 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Asthalpara (Sansad-XIV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000266/2021-2022 | 1875/RCD-I | 28/10/2021 | 30 | UNITED CONSTRUCTION | 13.32 | 13.32 | 0
56 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara (Sansad-XV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000267/2021-2022 | 1876/RCD-I | 28/10/2021 | 30 | B.T.M CONCERN | 15.25 | 15.25 | 0
57 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mukherjeepara & Khad Para (Sansad-XVII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000268/2021-2022 | 1877/RCD-I | 28/10/2021 | 30 | SIMA ENTERPRISE | 15.72 | 15.71 | 0
58 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 11.64 | 0
59 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Sukho Para (Sansad-XX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000270/2021-2022 | 1879/RCD-I | 28/10/2021 | 30 | SOMNATH SAMANTA | 15.63 | 15.63 | 0
60 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 2.26 | 100
61 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia HDPE pipe line and allied works at Kankardanga Part (Sansad-VIII) at Ukhra area under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 2 | Junior Engineer | ORD/000906/2022-2023 | 1162/RCD-I | 24/03/2023 | 15 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 1.42 | 1.29 | 100
62 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia distribution pipe line at Sukopara (Part), Bauripara (Part) etc adjacent area at Ukhra Gram Panchayet (Sansad-XX) Augmentation of RCFA Part-II (Zone-2A) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000939/2022-2023 | 1275/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.25 | 2.95 | 0
63 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000013/2025-2026 | 2539/RCD-I | 01/09/2025 | 0 | Resource Division | 7.13 | 0 | 0
64 | Durgapur W/S Division |  | Formal order for the work of Laying and aligning of DI K9 Rising main pipe line supplying of DI Specials and valves and other allied works under Command area of Bistupur piped W/s Scheme under DWSD PHE Dte (SL-12) |  |  | ORD/000109/2022-2023 | 749/DWSD | 10/05/2022 | 20 | MAK CONSTRUCTION CO. | 17.52 | 14.97 | 0
65 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connecting providing to Saraswatiganj (JL-49) ,Bistupur(JL-44) Mouzas under command area of Bistupur distribution system (Part-B) under Bistupur W/s Scheme (SL-01) |  |  | ORD/000126/2022-2023 | 813/DWSD | 21/05/2022 | 25 | SK. ABDUL HALIM | 76.67 | 72.69 | 0
66 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000127/2022-2023 | 814/DWSD | 21/05/2022 | 25 | MRITYUNJOY MUKHERJEE AND CO | 71.11 | 44.6 | 0
67 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying laying and aligning of UPVC distributing pipe line and allied works including FHTC and connection providing Kuldiha(JL-53),Pathardiha(JL-52) ,Keshbpur(JL-66) Mouzas under command area of Bistupur distribution system (Part-B) of Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-03) |  |  | ORD/000128/2022-2023 | 815/DWSD | 21/05/2022 | 25 | TARA CONSTRUCTION | 54.66 | 42.36 | 0
68 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for laying and aligning of DI K9 rising main pipe line and supplying DI specials ,valves & allied works under command area of Bistupur piped W/S Scheme under DWSD ,PHE Dte (Sl-06) |  |  | ORD/000133/2022-2023 | 820/DWSD | 23/05/2022 | 15 | MAK CONSTRUCTION CO. | 39.46 | 39.53 | 0
69 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of temporary approach road at Molandighi H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000141/2022-2023 | 962/DWSD | 17/06/2022 | 10 | MACHINO TECHNO | 4.11 | 4.09 | 0
70 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Land development at Molandighi H/W site & back filling of Bistupur H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-06) |  |  | ORD/000142/2022-2023 | 963/DWSD | 17/06/2022 | 10 | MRITYUNJOY MUKHERJEE AND CO | 4.15 | 4.17 | 0
71 | Durgapur W/S Division |  | Formal order for the work of 1 No road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack Pushing method at node point 540 of Bistupur piped W/S Scheme under DWSD,PHE Dte.(SL-01) |  |  | ORD/000170/2022-2023 | 1163/DWSD | 01/08/2022 | 25 | TARA CONSTRUCTION | 6.21 | 6.21 | 0
72 | Durgapur W/S Division |  | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-C) by modern trenchless technology through Jack pushing method at node point of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-09) |  |  | ORD/000176/2022-2023 | 1123/DWSD | 22/07/2022 | 25 | SK. ALIM | 12.44 | 12.44 | 0
73 | Durgapur W/S Division |  | Formal order for the work of 3 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-A) by modern trenchless technology through Jack pushing method at node point1 to 2 & 64 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-10) |  |  | ORD/000177/2022-2023 | 1110/DWSD | 19/07/2022 | 25 | MACHINO TECHNO | 18.64 | 18.64 | 0
74 | Durgapur W/S Division |  | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack pushing method at node point-414 to 402 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-11) |  |  | ORD/000178/2022-2023 | 1164/DWSD | 01/08/2022 | 25 | TARA CONSTRUCTION | 12.43 | 12.43 | 0
75 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Molandighi H/W site Pump house No-3 Tube well No-03 for Bistupur pipe W/S Scheme under DWSD,PHE Dte (SL-06) |  |  | ORD/000199/2022-2023 | 1061/DWSD | 08/07/2022 | 25 | DARPAN DAS & CO. | 4.82 | 3.02 | 0
76 | Durgapur W/S Division |  | Formal order for the work of Sinking of 1 No (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well no 3 site of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-02) |  |  | ORD/000257/2021-2022 | 1679/DWSD | 01/12/2021 | 25 | SK. ALIM | 9.32 | 6.7 | 0
77 | Durgapur W/S Division |  | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) |  |  | ORD/000258/2021-2022 | 1676/DWSD | 30/11/2021 | 35 | M/S. D. PALIT & CO. | 18.62 | 11.91 | 100
78 | Durgapur W/S Division |  | Acceptance cum formal order for the work of supplying and laying of 150 mm dia MS water carrying pipe with making necessary bend and others allied works at node point -414,323 and 540 near Kuldiha boys club ,Kuldiha More bus stand and Kuldiha bordoba More, Kanksa Block under Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-04) |  |  | ORD/000260/2022-2023 | 1577/DWSD | 02/11/2022 | 15 | TARA CONSTRUCTION | 37.4 | 33.92 | 0
79 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Bistupur Head work sites (Tube well no ¿I) under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-18) |  |  | ORD/000331/2021-2022 | 1805/DWSD | 28/12/2021 | 45 | BABA LOKENATH ENTERPRISE | 4.87 | 4.2 | 0
80 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿II) sites under Bistupur piped W/S scheme under DWSD,PHE Dte |  |  | ORD/000332/2021-2022 | 1808/DWSD | 29/12/2021 | 45 | CHATTERJEE CONSTRUCTION | 4.67 | 3.59 | 0
81 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿III) sites under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-21) |  |  | ORD/000334/2021-2022 | 1810/DWSD | 29/12/2021 | 45 | DARPAN DAS & CO. | 4.67 | 3.59 | 0
82 | Durgapur W/S Division |  | Fomal order for the work of Supplying laying and alinging of UPVC distribution pipe line (distribution system Part-B) and allied works including FHTC and connecrtion provided to Kuldiha,Pathardihi,Keshabpur moluzas under command area of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte |  |  | ORD/000353/2021-2022 | 148/DWSD | 07/02/2022 | 30 | TARA CONSTRUCTION | 147.47 | 139.68 | 0
83 | Durgapur W/S Division |  | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000354/2021-2022 | 149/DWSD | 07/02/2022 | 65 | MACHINO TECHNO | 377.24 | 232.69 | 100
84 | Durgapur W/S Division |  | Formal order for the work of Supplying, laying and aligning of UPVC distribution pipe line (Distribution system( Part-B) and allied works including functional house holds tap connection (FHTC) and connection providing to Saraswatiganj (JL No-49) ,Bistupur (JL No-44) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000355/2021-2022 | 150/DWSD | 07/02/2022 | 30 | SK. ALIM | 188.51 | 186.94 | 0
85 | Durgapur W/S Division |  | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000371/2021-2022 | 66/DWSD | 19/01/2022 | 15 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 8.89 | 80.89 | 0
86 | Durgapur W/S Division |  | Continuation order for the work of soil investigation for determining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated At Molandighi Reservoir site of Bistupur W/s Scheme under DWSD,PHE Dte |  |  | ORD/000467/2021-2022 | 303/DWSD | 10/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 0
87 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000521/2022-2023 | 336/DWSD | 20/02/2023 | 20 | GHOSH & ROY ENTERPRISE | 18.36 | 15.74 | 0
88 | Durgapur W/S Division |  | Acceptance cum formal order for the work-Construction of boundary wall at Saraswatiganj H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000522/2022-2023 | 337/DWSD | 20/02/2023 | 30 | CHATTERJEE CONSTRUCTION | 10.68 | 6.07 | 100
89 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of boundary wall at Ghatakdanga H/W site (PH No-3,TW No-3) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000523/2022-2023 | 286/A/DWSD | 16/02/2023 | 30 | DARPAN DAS & CO. | 12.08 | 0 | 0
90 | Durgapur W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 1752/DWSD | 16/12/2021 | 0 | Resource Division | 1.27 | 0 | 0
91 | Durgapur W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 1816/DWSD | 30/12/2021 | 0 | Resource Division | 20.35 | 0 | 0
92 | Durgapur W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 66/DWSD | 19/01/2022 | 0 | Resource Division | 80.94 | 0 | 0
93 | Durgapur W/S Division |  | Quatation for Bistupur Pump house no -02 |  |  | VCH/000223/2022-2023 | BP-2022-23-95 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.76 | 0 | 0
94 | Durgapur W/S Division |  | Quotation for Bistupur Pump house no -03 |  |  | VCH/000224/2022-2023 | BP-2022-23-96 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0
95 | Durgapur W/S Division |  | Quotation for Bistupur Pamp House No 1 |  |  | VCH/000761/2021-2022 | BP-2021-22-207 | 15/03/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.76 | 0 | 0
96 | Central Mechanical |  | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 2 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000003/2022-2023 | 734/CMD | 29/04/2022 | 30 | MAHADEV ENTERPRISE | 9.95 | 9.73 | 0
97 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorination Sistem and Internal House wiring for Tube well No. 3 at Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000018/2022-2023 | 913/CMD | 31/05/2022 | 30 | ASHUTOSH DAS & CO. | 9.96 | 9.69 | 0
98 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery , Voltage stabilizer , Chlorinator and Internal House wiring for Tube well No. 1 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. |  |  | ORD/000724/2021-2022 | 478/CMD | 28/03/2022 | 30 | C.M. ENTERPRISE | 9.74 | 9.56 | 0
99 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Special repair and renovation of existing high lift Pump house, boundary Walls, Guard rooms, CWR, Switch Room etc, and allied works at H/W site of Ondal Phase-I Piped water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 03) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000008/2023-2024 | 1404 RCD I | 12/04/2023 | 60 | NATIONAL CONSTRUCTION | 13.75 | 12.12 | 100
100 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 5 (five) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Ondal (Phase-I & Phase-II) piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL NO 6) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000112/2022-2023 | 1287/RCD I | 03/06/2022 | 30 | DAS & CHAKRABORTY | 75.11 | 36.68 | 100
101 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000122/2022-2023 | 1608/RCD-I | 06/07/2022 | 1057 | AMAR CONSTRUCTION | 53.68 | 31.3 | 100
102 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000123/2022-2023 | 1609/RCD-I | 06/07/2022 | 90 | UMA ENTERPRISE | 67.49 | 65.53 | 100
103 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction additional length of Boundary wall including land development and Pathway at Khas Kajora OHR site at Andal Block for Augmentation of Ondal (Phase-I) Water Supply Scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000201/2024-2025 | 2467/RCD-I | 01/10/2024 | 45 | M/S UNIT CONSTRUCTION | 21.86 | 17.76 | 100
104 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-A) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000214/2023-2024 | 2222/RCD-I | 17/07/2023 | 30 | M/S SUBHRADEEP | 16.33 | 15.89 | 100
105 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work for collecting main of River bed tube well in Damodar River for Augmentation of Ondal (Phase-I) Water Supply Scheme under JJM at Andal H/W Site under Andal Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000222/2024-2025 | 2543/RCD-I | 29/10/2024 | 30 | MAA ENTERPRISE | 10.75 | 9.73 | 100
106 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-C) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000233/2023-2024 | 2215/RCD-I | 17/07/2023 | 30 | M/S UNIT CONSTRUCTION | 30.8 | 30.73 | 100
107 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of dedicated distribution line for Dignala village along the main road for Augmentation of Ondal (Phase-I) PWSS Andal Block, Dist-PaschimBardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000281/2025-2026 | 1385/RCD-I | 15/05/2025 | 25 | UNITED CONSTRUCTION | 33.95 | 0 | 100
108 | RCFA Division -I | Asansol Mechanical Division | Distribution Network for Augmentation of Ondal Phase-1 Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000297/2022-2023 | 2452/RCD-I | 13/10/2022 | 180 | M/S PIONEER CONSTRUCTION | 307.62 | 304.88 | 100
109 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work cutting hard rock,boulder concrete and others work including filling earth, removal rubbish of Augmentation of Ondal Phase-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000307/2023-2024 | 2382/RCD-I | 07/08/2023 | 30 | M/S UNIT CONSTRUCTION | 89.75 | 81.28 | 100
110 | RCFA Division -I | Asansol Mechanical Division | Supply fitting fixing different dia valve and allied works in connection with laying distribution system including FHTC of Ondal Phase-I Water Supply Scheme (Part-B) under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000338/2023-2024 | 2465/RCD-I | 18/08/2023 | 30 | AMAR CONSTRUCTION | 0.62 | 0.62 | 100
111 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency Repairing of 50 sqmm x 4 core Al Armoured damaged cable line provided of FHTC Pipe line near Dignala OHR Site under Andal W/S Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000480/2023-2024 | 2887/RCD-I | 06/10/2023 | 15 | T R ENTERPRISE | 3.72 | 3.72 | 100
112 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of rising main for Augmentation of Andal Phase-I (Dignala OHR) from Andal H/W Site under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000505/2024-2025 | 131/RCD-I | 08/01/2025 | 45 | UNITED CONSTRUCTION | 16.84 | 0 | 100
113 | RCFA Division -I | Asansol Mechanical Division | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000535/2021-2022 | 501/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.91 | 3.91 | 0
114 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional for supplying, aligning and laying HDPE pipe, dismantling & concerting, supplying sluice valve and other allied works for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000647/2023-2024 | 3424/RCD-1 | 24/11/2023 | 30 | M/S SUBHRADEEP | 34.89 | 34.51 | 100
115 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency repairing and maintenance work of damaged RCC Elevated Reservoir including of capacity 700cum at Ramprasadpur of Augmentation of Ondal Phase-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000763/2022-2023 | 390/RCD I | 30/01/2023 | 60 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 12.78 | 12.62 | 100
116 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000006/2022-2023 | 2346/RCD-I | 28/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
117 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000017/2022-2023 | 3132 | 09/12/2022 | 0 | Resource Division | 40.44 | 0 | 0
118 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-16, 17 & 18 and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000279/2024-2025 | 1674/AMD | 04/10/2024 | 213 | EASTERN INDIA SALES AND SERVICE | 31.75 | 0 | 100
119 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Ramprasadpur Head Works Site under Andal Water Supply Scheme, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000450/2024-2025 | 2117/AMD | 16/12/2024 | 30 | M/S JIT ENTERPRISE | 4.16 | 0 | 100
120 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping machineries in the Newly sunk River Bed Tube Well No-11,12,13,14 & 15 and other allied works at Ramprasadpur HeadWorks Site under Andal Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000650/2023-2024 | 554/AMD | 14/03/2024 | 30 | EASTERN INDIA SALES AND SERVICE | 6.62 | 6.58 | 100
121 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Kanyapur (near Durgamandir) under Nuni Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000398/2021-2022 | 145/AMD | 11/02/2022 | 7 | M/S SWAPAN BANERJEE | 2.46 | 2.45 | 0
122 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Kapatiya Village & Saroda Pally within Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000399/2021-2022 | 146/AMD | 11/02/2022 | 7 | UNIQUE ENTERPRISE | 3.25 | 3.22 | 0
123 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Choto Nuni (Majhi Para) and Upadhya Para withih Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000400/2021-2022 | 147/AMD | 11/02/2022 | 7 | ANANYA CONSTRUCTION | 3.72 | 3.7 | 0
124 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Sen-Raliegh B. Block within Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000401/2021-2022 | 148/AMD | 11/02/2022 | 7 | VIKING TRADERS | 1.3 | 1.29 | 0
125 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Nuni village within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000402/2021-2022 | 149/AMD | 11/02/2022 | 7 | HINDUSTHAN CONSULTANT FIRM | 1.29 | 0 | 0
126 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Nuni Namo Para within Nuni and Adjoining Mouzas and Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000403/2021-2022 | 150/AMD | 11/02/2022 | 7 | PESTCO INDIA | 3.74 | 3.72 | 0
127 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Nadiha Market (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000404/2021-2022 | 151/AMD | 11/02/2022 | 7 | M/S SWAPAN BANERJEE | 3.22 | 3.2 | 0
128 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Nayabasti (Gandhinagar) under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000405/2021-2022 | 152/AMD | 11/02/2022 | 7 | M/S JIT ENTERPRISE | 4.56 | 4.54 | 0
129 | Asansol Mechanical | Asansol Mechanical Division | Additional work related to Providing House to House Connection from existing distribution system at Monoharbohal Village under Panchgachia Zone Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000406/2021-2022 | 153/AMD | 11/02/2022 | 7 | PESTCO INDIA | 2.93 | 2.91 | 0
130 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Carriage DI pipe & specials from Searsole to Andal for rising main pipeline work at Andal block of Augmentation of sub surface water supply scheme for Andal Phase-II/B RCFA Division-I ,PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000180/2024-2025 | 2428/RCD-I | 26/09/2024 | 15 | MRITYUNJOY MUKHERJEE & CO. | 5.04 | 0 | 10
131 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of the pushing 300 mm Dia MS rising main through 600 mm Dia pipe under Hinglow River for the work Of OCP based Kajora site of Augmentation of sub surface water supply scheme for Ondal Phase-II/B Under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000182/2024-2025 | 2430/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 48.99 | 16.1 | 100
132 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of 600 mm Dia RCC pipe road crossing trenchless method jack pushing under NH-19 at Railway Kajora more to Andal Police station under OCP based KAJORA of Augmentation sub surface water supply scheme Ondal Phase-II/B under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000183/2024-2025 | 2431/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 73.64 | 73.64 | 100
133 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for cutting hard rock at Kajora OHR Site for Ghanashyampur abandoned Kajora of Augmentation of sub surface water based PWSS for Andal Phase-II/B under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000190/2024-2025 | 2426/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 14.71 | 0 | 100
134 | RCFA Division -I | RCFA Division I | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-1) | Assistant Engineer 2 | Junior Engineer | ORD/000331/2022-2023 | 2836/RCDI | 28/10/2022 | 885 | M/S KALYANI ENTERPRISE | 88.58 | 24.33 | 60
135 | RCFA Division -I | RCFA Division I | Supply & erection of Swajal Village Boards (102 nos) having M.S. Channel/Angle Posts & 1.5 mm thick M.S. synthetic enamel paint over a coat of red oxied primer including lettering complete at different places under Augmentation of sub surface water based for PWSS Ondal Phase-II/B under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000349/2024-2025 | Camp-02_Swajal/AE/24-25 | 03/10/2024 | 120 | SHARMA ENGINEERING WORKS | 20.55 | 0 | 50
136 | RCFA Division -I | RCFA Division I | Formal work order for construction of 450 cum capacity 20 mtr staging height RCC over head reservoir pipe connection and cost of pipes, specials at Andal village for Augmentation of Ondal Phase-II/B piped water supply scheme under RCFA Div-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2022-2023 | 18 /RCD I | 05/01/2023 | 9 | AMAR CONSTRUCTION | 129.3 | 129.3 | 100
137 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for augmentation of Ondal (Phase-II/B) piped Water Supply Scheme including FHTC & allied works within Ondal Block under RCFA Div-I, PHE Dte.(Part-3) | Assistant Engineer 2 | Junior Engineer | ORD/000600/2022-2023 | 15/RCDI | 05/01/2023 | 30 | DAS & CHAKRABORTY | 178.26 | 60.64 | 85
138 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of 200 mm dia rising main from Dignala OHR ste to proposed OHR site at Andal BL & LRO office for the proposed Augmentation work of Andal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2022-2023 | 343/RCDI | 30/01/2023 | 822 | D.S.C. CONCERN | 7.65 | 4.3 | 65
139 | RCFA Division -I | RCFA Division I | Formal order for distribution network for augmentation of Ondal (Phase -II/B) piped Water Supply scheme including FHTC & allied work within ondal block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000780/2022-2023 | 819/RCDI | 10/03/2023 | 30 | M/S MONI TRADERS | 108.27 | 34.49 | 60
140 | RCFA Division -I | RCFA Division I | Acceptance cum work order forConstruction of Boundary Wall with Gate at OHR Site (Length-160 mtrs) at Ondal Block for Augmentation of Ondal Phase- II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000879/2022-2023 | 1126/ RCD I | 24/03/2023 | 30 | AMAR CONSTRUCTION | 13.43 | 13.27 | 100
141 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Ondal Phase II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 04) | Assistant Engineer 2 | Junior Engineer | ORD/000888/2022-2023 | 1148/RCD-1 | 24/03/2023 | 30 | AMAR CONSTRUCTION | 6.5 | 6.09 | 100
142 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Guard room with toilet under Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000896/2022-2023 | 1150/RCD-1 | 24/03/2023 | 60 | SUBHADEEP DAS | 5.64 | 5.53 | 100
143 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at OHR Site for Augmentation of Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No. 34) | Assistant Engineer 2 | Junior Engineer | ORD/000915/2022-2023 | 1177/RCD-1 | 24/03/2023 | 90 | SUBHADEEP DAS | 4.61 | 3.91 | 100
144 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000012/2023-2024 | 2206/RCD-I | 17/07/2023 | 0 | Resource Division | 24.19 | 0 | 0
145 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000016/2022-2023 | 2927/RCD-I | 17/11/2022 | 0 | Resource Division | 85.11 | 0 | 0
146 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000019/2022-2023 | 3125 | 09/12/2022 | 0 | Resource Division | 220.25 | 0 | 0
147 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-95 at Sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00117/2024-2025 | 50/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0
148 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-93 at sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00118/2024-2025 | 51/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.9 | 0 | 0
149 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-13) | Assistant Engineer 2 |  | ORD/000068/2023-2024 | 1762/RCD I | 16/05/2023 | 1051 | MD AAMIR KHAN | 308.67 | 170.31 | 80
150 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (zone-13) with Construction of 400 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain ad internal pathway at OHR site under Jamuria Block, District- Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000100/2023-2024 | 1844/RCD-I | 31/05/2023 | 365 | JAYANTA DATTA | 129.69 | 99.19 | 65
151 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Charanpur Bus Stand and Faridpur of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000238/2023-2024 | 2231/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 14.44 | 14.39 | 100
152 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary Wall with gate (length 200 mtr.) land development with approach road including internal drain at H/W site & construction of guard room with toilet at Baliapur under Barabani Block in Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000273/2023-2024 | 2330/RCD-I | 01/08/2023 | 90 | AMAR CONSTRUCTION | 31.48 | 30.67 | 100
153 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 6 (Six) nos 200 mm dia river bed tube wells including collecting main for river Damodar at Kalajharia of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000348/2023-2024 | 2482/RCD-I | 23/08/2023 | 30 | A. CONSTRUCTION CO. | 13.15 | 11.12 | 100
154 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 5 (Five) nos 200 mm dia river bed tube well in the river of Damodar at Kalajharia H/W site for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000489/2023-2024 | 2884/RCD-1 | 06/10/2023 | 45 | A CONSTRUCTION CO | 9.8 | 9.62 | 100
155 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Churulia (200 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000541/2023-2024 | 3019/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100
156 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Kendra (750Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000545/2023-2024 | 3027/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.92 | 4.92 | 100
157 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 400 cum capacity RCC Over Head Reservoir at (Zone-13) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000553/2022-2023 | 3347/RCDI | 23/12/2022 | 782 | MOYTEC | 0.46 | 0 | 100
158 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and delivery of Centrifugal Pump Motor Set for Nimsha Village (High Lift) at Shemalya under AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) Block - Jamuria, Dist - Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000699/2023-2024 | 3502/RCD-1 | 30/11/2023 | 10 | M/S SWAPAN BANERJEE | 21.05 | 21.05 | 100
159 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied works at Churulia under Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000705/2023-2024 | 3501/RCD-1 | 30/11/2023 | 90 | SIMA ENTERPRISE | 23.68 | 22.16 | 100
160 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Churulia OHR site of AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000706/2023-2024 | 3500/RCD-1 | 30/11/2023 | 30 | ASHA CONSTRUCTION | 28.18 | 5.99 | 100
161 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room with toilet under Mangalpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000922/2023-2024 | 300/RCD-I | 07/02/2024 | 15 | M/S SUBHRADEEP | 5.63 | 0 | 0
162 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of Boundary Wall at Khandra Bisswari OHR Site under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000923/2023-2024 | 299/RCD-I | 07/02/2024 | 45 | NATIONAL CONSTRUCTION | 11.15 | 6.65 | 100
163 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for distribution network & allied work at Ondal Block of RCFA Part-II (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000968/2023-2024 | 717/RCD-I | 01/03/2024 | 30 | M/S UNIT CONSTRUCTION | 92.71 | 92.67 | 100
164 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000030/2023-2024 | 2944/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
165 | RCFA Division -I | RCFA Division I | Restoration and repairing work form Ch. 6.889 km to Ch 12.7 mm km of Chinchuria-Bhuri road under Asansol Division, PWD for laying pipe line under JJM | Assistant Engineer 2 |  | BILL/00464/2023-2024 | 236/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 68.17 | 0 | 0
166 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14A) | Assistant Engineer 2 |  | ORD/000027/2023-2024 | 1617/RCD I | 25/04/2023 | 180 | KONAR CONSTRUCTION | 365.88 | 115.24 | 35
167 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-14A) with Construction of 1250 cum capacity RCC OHR with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000102/2023-2024 | 1842/RCD-I | 31/05/2023 | 365 | A. CONSTRUCTION CO. | 277.09 | 214.82 | 40
168 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Majiara (250 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000542/2023-2024 | 3020/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100
169 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 1250 cum capacity RCC Over Head Reservoir at (Zone-14A) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000554/2022-2023 | 3348/RCDI | 23/12/2022 | 782 | G. MITRA & ASSOCIATES | 0.5 | 0 | 100
170 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 2 |  | ORD/000655/2023-2024 | 3427/RCD-1 | 24/11/2023 | 160 | MACHINO TECHNO | 58.12 | 47.13 | 100
171 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala irrigation Damp within command area of Zone-IX Part-I distribution system under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000672/2023-2024 | 3439/RCD-1 | 24/11/2023 | 15 | KHEPI MAA TRADERS | 22.98 | 22.91 | 100
172 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia MS & HDPE Pipe line and mending works at Chanchani (Sansad-XII) of Ukhra area under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 |  | ORD/000771/2022-2023 | 397/RCDI | 30/01/2023 | 30 | M/S B.K. CONSTRUCTION | 11.94 | 10.71 | 100
173 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000031/2023-2024 | 2943/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
174 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work along with Construction of Guard room with Toilet for Construction of 150 cum capacity RCC OHR with 20 Mtr staging height RCC Over Head Reservoir Piped connection and cost of pipes, specials at Augmentation of PWSS of RCFA Part-II (Zone-14C) Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000054/2024-2025 | 1744/RCD-I | 18/07/2024 | 256 | NATIONAL CONSTRUCTION | 12.73 | 2.98 | 85
175 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Additional works of Pump House and other allied works at Damalia H/W Site for Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA, Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000094/2024-2025 | 2128/RCD-I | 27/08/2024 | 45 | B.T.M. CONCERN | 15.28 | 15.12 | 100
176 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance Work of Road Restoration In Connection With Improvement of RCFA _Part-I Water Supply Scheme for Amritnagar Zone-II of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000108/2024-2025 | 2130/RCD-I | 27/08/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 48.27 | 47.82 | 100
177 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for crossing of NH-60 by Jack Pushing Method and allied works at Haripur near CB Cure Hospital within Pandabeswar Block of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000252/2025-2026 | 1474/RCD-I | 15/05/2025 | 20 | MD AAMIR KHAN | 13.99 | 0 | 100
178 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Supplying aligning & laying 90 mm dia HDPE pipe line bye pass at Kallya, Dharashpur & Pahargara under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000401/2023-2024 | 2583/RCD-I | 07/09/2023 | 15 | ASHA CONSTRUCTION | 8.67 | 8.54 | 100
179 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc.) 03 nos. location at Haripur (Zone-14C) within Pandabeswar Block of Augmentation of PWSS RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2024-2025 | 140/RCD-I | 08/01/2025 | 90 | MD AAMIR KHAN | 85.12 | 0 | 60
180 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000589/2023-2024 | 2263/RCD-I | 19/07/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 10.12 | 60
181 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14C) | Assistant Engineer 2 | Junior Engineer | ORD/000604/2022-2023 | 38/RCD-I | 11/01/2023 | 90 | PRADIP KUMAR DEB | 378.29 | 291.68 | 100
182 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work supplying, laying and pushing of 600 mm dia MS cashing pipe for Railway crossing by Jack Pushing method with 150 mm dia MS water carrier pipe in Rupnarayanpur in between 232/16-18 (SLS-RNPR) in Asansol Division under distribution network Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000659/2023-2024 | 3430/RCD-1 | 24/11/2023 | 45 | TARA CONSTRUCTION | 55.01 | 50.99 | 100
183 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001080/2023-2024 | 2382_A_RCD_I | 07/08/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 17.08 | 100
184 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000033/2023-2024 | 2941/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
185 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service connection for Amlajora H/W site under Amlajora piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00156/2023-2024 | BP-2023-24-97 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
186 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service connection charges for Amlajora H/W Site TW-II under Amlajora Piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00157/2023-2024 | BP-2023-24-98 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.52 | 0 | 0
187 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000174/2023-2024 | 1397/DWSD | 17/08/2023 | 184 | BIPLAB BANERJEE | 0.82 | 1.58 | 30
188 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying distribution system rising main construction of 250 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with FHTC for Amlajora piped W/s Scheme under DWSD,PHE Dte ,Dist-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000220/2022-2023 | 1175/DWSD | 02/08/2022 | 12 | RANADHIR SINHA | 426.89 | 287.14 | 100
189 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Amlajora piped W/s Scheme under DWSD ,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000223/2022-2023 | 1234/DWSD | 17/08/2022 | 15 | JOY GURU ENTERPRISE | 14.68 | 14.14 | 0
190 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Amlajora, Birudiha piped W/s Scheme and Kataberia PWSS under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000565/2022-2023 | 528/DWSD | 29/03/2023 | 15 | MEASURE LAND | 7.53 | 7.53 | 0
191 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000004/2023-2024 | 787/DWSD | 25/05/2023 | 0 | Resource Division | 25.85 | 0 | 0
192 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000009/2022-2023 | 255/F/DWSD | 15/02/2023 | 0 | Resource Division | 10.47 | 0 | 0
193 | Asansol Mechanical | Asansol Mechanical Division | Quotation As per WBSEDCL procedure- A (2010) on turnkey/ full deposit basis for the of Amlajora Tube Well no. -III, under Kanksa Block, Dist. Paschim Barddhaman | Assistant Engineer-II | Junior Engineer-3 | BILL/00169/2025-2026 |  | 02/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.23 | 0 | 0
194 | Asansol Mechanical | Asansol Mechanical Division | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000631/2023-2024 | 530/AMD | 12/03/2024 | 90 | P.K.ENGINEERING | 11.43 | 11.15 | 100
195 | Asansol Mechanical | Asansol Mechanical Division | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-II at Amlajora Water Supply Scheme, under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000632/2023-2024 | 531/AMD | 12/03/2024 | 90 | M/S SAJAHAN CHOWDHURY | 11.46 | 11.46 | 100
196 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 37.25 | 100
197 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying & pushing of 600 mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g. Jack Pushing Method) MS water carrier pipe and other allied works under command area of Tetikhola (Part-E) under Tetikhola Piped Water Supply Scheme, Block Durgapur-Faridpur, Dist-Paschim Bardhaman | Assistant Engineer-II | Junior Engineer-5 | ORD/001141/2023-2024 | 940/RCD-I | 15/03/2024 | 15 | TARA CONSTRUCTION | 9.51 | 4.74 | 100
198 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE/CI/DI distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-B) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-13) | Assistant Engineer-II | Junior Engineer-5 | ORD/000027/2023-2024 | 762/DWSD | 22/05/2023 | 35 | JOY GURU ENTERPRISE | 94.09 | 65.76 | 85
199 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-C) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | Assistant Engineer-II | Junior Engineer-5 | ORD/000028/2023-2024 | 759/DWSD | 19/05/2023 | 35 | ANWESHA CONSTRUCTION | 98.7 | 49.22 | 65
200 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-E) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | Assistant Engineer-II | Junior Engineer-5 | ORD/000029/2023-2024 | 761/DWSD | 22/05/2023 | 35 | SWATI CORPORATION | 95.42 | 81.27 | 45
201 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-D) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | Assistant Engineer-II | Junior Engineer-5 | ORD/000030/2023-2024 | 763/DWSD | 22/05/2023 | 35 | PRAVAT SARKAR | 98.69 | 33.51 | 40
202 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-F) under Tetikhala piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman | Assistant Engineer-II | Junior Engineer-5 | ORD/000031/2023-2024 | 811/DWSD | 29/05/2023 | 35 | CHATTERJEE CONSTRUCTION | 87.79 | 60.58 | 75
203 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area of TETIKHOLA (Part-A) under Tetikhola piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-18) | Assistant Engineer-II | Junior Engineer-5 | ORD/000032/2023-2024 | 810/DWSD | 29/05/2023 | 35 | BASANTI TRADERS | 99.25 | 78.14 | 70
204 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Drawing design and surveying work for proposed piped W/S Scheme of Tetikhola Piped W/s Scheme under DWSD ,PHE Dte (SL-14) | Assistant Engineer-II | Junior Engineer-5 | ORD/000169/2022-2023 | 1035/DWSD | 04/07/2022 | 15 | APEX ENGINEERING | 3.9 | 3.9 | 0
205 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 03 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at TETIKHOLA H/W site & TW-II site of Durgapur-Faridpur Block under TETIKHOLA piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000456/2022-2023 | 309/DWSD | 20/02/2023 | 681 | M/S. D. PALIT & CO. | 47.15 | 0 | 100
206 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of construction of boundary wall at TETIKHOLA pump house site No-2 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000505/2022-2023 | 321/DWSD | 20/02/2023 | 30 | CHATTERJEE CONSTRUCTION | 15.35 | 0 | 0
207 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangement at TW No-2 site at Tetikhola H/W site under Tetikhola piped W/S Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000507/2022-2023 | 324/DWSD | 20/02/2023 | 35 | MUKHERJEE ENTERPRISE | 13.83 | 0 | 0
208 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Tetikhola H/W site (OHR ) site ,land development ,approach road and others allied works of Augmentation of Tetikhola piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000513/2022-2023 | 330/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 34.05 | 0 | 0
209 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at TW No-3 site at Tetikhola under Tetikhola piped W/S Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000518/2022-2023 | 335/DWSD | 20/02/2023 | 25 | M/S BANERJEE CONSTRUCTION | 6.88 | 6.88 | 100
210 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at TETIKHOLA pump house site No-3 under Tetikhola piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000520/2022-2023 | 322/DWSD | 20/02/2023 | 30 | BABA LOKENATH ENTERPRISE | 15.35 | 0 | 0
211 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying ,aligning of DI K9 R/M pipe and interconnection between 3 Nos Tube well with OHR and other allied works of Tetikhola piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000605/2022-2023 | 504/DWSD | 28/03/2023 | 25 | BISHAL ENTERPRISE | 48.29 | 0 | 50
212 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-5 | RTOR000006/2023-2024 | 788/DWSD | 25/05/2023 | 0 | Resource Division | 26.4 | 0 | 0
213 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Tube Well No-I,II and III under Tetikhola Piped Water Supply Scheme, Block- Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000039/2023-2024 | 1022/AMD | 19/04/2023 | 90 | M/S SWAPAN BANERJEE | 34.29 | 0 | 0
214 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-4 &5 AT TETIKHOLA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE., BOLCK- DURGAPUR-FARIDPUR, DIST- PASCHIM BARDHAMAN. | Assistant Engineer-II | Junior Engineer-5 | ORD/000360/2024-2025 | 1925/AMD | 19/11/2024 | 165 | PESTCO INDIA | 22.69 | 0 | 0
215 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional works for distribution main pipe line including Road Restoration under Augmentation of Jatgoria Water Supply Scheme Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000235/2024-2025 | 2607/RCD-I | 12/11/2024 | 90 | SUPERSKILL | 84.46 | 0 | 0
216 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Guard Room at Jatgoria Head Works Site under Augmentation of Jatgoria Water Supply Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000314/2024-2025 | 2730/RCD-I | 26/11/2024 | 90 | IMPULSE INTERNATIONAL | 5.53 | 0 | 40
217 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for balance work for Construction of site office at Panagarh of RCFA Division-I PHE Dte. under Augmentation of Jatgoria W/S Scheme JJm Fund. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000911/2023-2024 | 211/RCD-I | 29/01/2024 | 60 | BASANTI TRADERS | 32.98 | 32.76 | 100
218 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of JATGARIA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -09) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000190/2023-2024 | 1192/DWSD | 25/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
219 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Jatgoria piped W/s Scheme udner DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000232/2023-2024 | 1579/DWSD | 21/09/2023 | 558 | SUPER SKILL | 145.14 | 32.51 | 100
220 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF JATGORIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000473/2024-2025 | 2181/AMD | 26/12/2024 | 30 | SAIKET SINHA | 11.61 | 0 | 0
221 | Durgapur W/S Division | Asansol Mechanical Division | New service connection charges for Dandeswar piped Water supply scheme TW-I | Assistant Engineer-II | Junior Engineer-3 | BILL/00062/2023-2024 | BP-2023-24-37 | 01/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.62 | 0 | 0
222 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service charges for Kanchanpur TW-III under Kanksa block of Dandeswar piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00158/2023-2024 | BP-2023-24-99 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.67 | 0 | 0
223 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service charges for Dandeswar TW-II under Dandeswar piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00159/2023-2024 | BP-2023-24-100 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.83 | 0 | 0
224 | Durgapur W/S Division | Asansol Mechanical Division | 1 (One) No Trial bore by DR method using rig machine at Dwandeswar ,Block-Kanksa under Augmentation of Dandeswar PWSS under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000214/2023-2024 | 1446/DWSD | 25/08/2023 | 15 | M/S BADAL GHOSH | 1 | 1 | 100
225 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Dandeswar piped W/s Scheme under DWSD ,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000224/2022-2023 | 1240/DWSD | 18/08/2022 | 15 | M/S BADAL GHOSH | 14.75 | 13.3 | 0
226 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying distribution system rising main construction of 150 M3 reservoir with 20 mtrs staging height including soil investigation construction of Pump house (5.4 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house(3.60 X 3.00 m) with FHTC for Dandeswar water Supply schme under DWSD ,PHE Dte (NS) | Assistant Engineer-II | Junior Engineer-3 | ORD/000264/2022-2023 | 1614/DWSD | 21/11/2022 | 365 | POWER TOOLS AND ENGINEERING | 164.79 | 139.27 | 80
227 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000006/2022-2023 | 255/B/DWSD | 15/02/2023 | 0 | Resource Division | 4.24 | 0 | 0
228 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Dandeshwar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000008/2023-2024 | 1654/CMD | 06/04/2023 | 30 | P.K. ENGINEERING | 21.21 | 20.57 | 80
229 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work Order for Repairing, Renovation, renewing & oversauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Work Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75 cum/hr-2nos) at Madantore Head Works site for Madantore W/S Scheme under RCFA Division-I PHE Dte (Part-B) iii) for 4 nos. iron removal Plant (Pressure type) each capacity 20 cum /hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Work Site under RCFA Division-I PHE Dte. (Part-D). | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000009/2023-2024 | 1391/RCD I | 11/04/2023 | 356 | TARAPRASAD SARKAR | 97.93 | 45.74 | 100
230 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network including providing FHTC Work under Augmentation of Churulia and its adjoining mouzas (Zone-II) PWSS Block- Jamuira, Dist- Paschim Bardhaman under RCFA Div-I Phe,Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000103/2022-2023 | 1276/RCD-I | 02/06/2022 | 90 | MD AAMIR KHAN | 70.29 | 48.29 | 100
231 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Churulia and its Adjoining Mouzas PWSS under RCFA Division-I PHE Dte.(SL NO 09) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000114/2022-2023 | 1283/RCD I | 02/06/2022 | 30 | R B ENTERPRISE | 13 | 8.2 | 80
232 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Augmentation of Churulia and its adjoining mouzas (Zone-I) PWSS by construction of OHR of capacity 100 cum with 20 mtr staging height LDS with necessary interconnection & FHTC work Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000118/2022-2023 | 1372/RCD-I | 16/06/2022 | 1172 | ASHA CONSTRUCTION | 306.57 | 156.81 | 100
233 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for construction of 200 cum capacity 20 mtr staging height RCC over Head Reservoir, pipe connection and cost of pipes specials of Churulia piped Water Supply Scheme under RCFA Div-I PHE Dte in the District of Paschim Bardhaman. Ref PC-I/OHR/09/2021 | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000543/2022-2023 | 3245/RCD I | 20/12/2022 | 274 | ASHA CONSTRUCTION | 71.55 | 71.55 | 100
234 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for laying of 150 mm and 200 mm dia rising main for the proposed augmentation work of Churulia and its adjoining mouzas piped water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000613/2022-2023 | 3273/RCD I | 20/12/2022 | 621 | T.R. ENTERPRISE | 21.17 | 10.65 | 70
235 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in river Ajoy of Augmentation of Churulia PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000761/2022-2023 | 388/RCDI | 30/01/2023 | 45 | ASHA CONSTRUCTION | 41.46 | 40.95 | 100
236 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of Concrete retaining wall with land development Churulia Ajoy River Bed Site under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000852/2022-2023 | 1088/RCD-I | 23/03/2023 | 90 | S. CHAKRABORTY & CO. | 44.66 | 40.55 | 100
237 | RCFA Division -I | Asansol Mechanical Division | Acceptance come work order for Balance work for distribution network of Churulia Madhudanga and its adjoining mouzas (Zone-II) under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000854/2022-2023 | 1087/RCD-I | 23/03/2023 | 90 | MD AAMIR KHAN | 16.38 | 16.32 | 100
238 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000004/2023-2024 | 1639/RCD-I | 27/04/2023 | 0 | Resource Division | 45.72 | 0 | 0
239 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000024/2022-2023 | 3127 | 09/12/2022 | 0 | Resource Division | 178.46 | 0 | 0
240 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000031/2022-2023 | 106/RCD-I | 20/01/2023 | 0 | Resource Division | 159.09 | 0 | 0
241 | Asansol Mechanical | Asansol Mechanical Division | Quotation for New Connection at Churulia. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | BILL/00022/2023-2024 | BP-2023-24-6 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.94 | 0 | 0
242 | Asansol Mechanical | Asansol Mechanical Division | Installation of yard lighting arrangement, electrical wiring of pump house and other allied works at Churulia Pump House under Augmentation of Churulia Piped Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000036/2025-2026 | 955/AMD | 16/05/2025 | 232 | CIEMENICS | 3.67 | 0 | 100
243 | Asansol Mechanical | Asansol Mechanical Division | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at Ajoyghat Head Works Site in the basis of "Augmentation of Churulia & Its Adjoining Mouzas"Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000538/2022-2023 | 747/AMD | 16/03/2023 | 1346 | BENGAL CONSTRUCTION | 116.52 | 60.15 | 100
244 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at BONAGRAM Mouza of Bonagaram piped W/s Scheme under DWSD, PHE Dte(Part-A ,B & C)(SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000210/2022-2023 | 789/DWSD | 18/05/2022 | 45 | BISHAL ENTERPRISE | 22.78 | 22.89 | 100
245 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 450 cum capacity 20 mtr. staging height RCC Over Head Reservoir (Pipe connection and cost of pipes. specials at Raniganj Block (Zone-18) for Augmentation of RCFA Part-II piped Water Supply Scheme under RCFA Division-I PHe Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/04/2022 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000154/2023-2024 | 1901/RCD-I | 09/06/2023 | 366 | SRI KRISHNA ENTERPRISE | 130.86 | 39.26 | 20
246 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000380/2023-2024 | 2553/RCD-I | 31/08/2023 | 7 | SINGHA ROY & CO. | 0.98 | 0.98 | 100
247 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000466/2023-2024 | 2872/RCD-1 | 06/10/2023 | 90 | SWATI CORPORATION | 21.83 | 21.48 | 100
248 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000473/2023-2024 | 2862/RCD-I | 06/10/2023 | 544 | SWATI CORPORATION | 44.91 | 39.27 | 100
249 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of concrete dismantling & re concreting with other allied works at distribution networks including additional laying of pipe line for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000493/2023-2024 | 2885/RCD-1 | 06/10/2023 | 30 | SWATI CORPORATION | 73.24 | 60.8 | 100
250 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000557/2022-2023 | 3351/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100
251 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000816/2022-2023 | 998/RCDI | 22/03/2023 | 1016 | SWATI CORPORATION | 454.37 | 284.71 | 100
252 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000914/2022-2023 | 1176/RCD-1 | 24/03/2023 | 90 | GOPAL CONSTRUCTION | 4.61 | 0 | 0
253 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000944/2023-2024 | 489/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.36 | 9.32 | 100
254 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Carring, stacking of different dia (80 mm to 700 mm dia) C.I./D.I. specials, valves grannual chlorine etc including surface dressing, road base at Searsole Stack yard under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000976/2023-2024 | 463/RCD-1 | 12/02/2024 | 20 | M/S MONDAL ENTERPRISE | 10.95 | 10.91 | 100
255 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work related to Rising Main Part-A for concrete cutting and road restoration at Ethora village including interconnection and Barabani OHR including Bituminous road cutting etc allied works under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000978/2023-2024 | 465/RCD-1 | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 25.64 | 24.96 | 100
256 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Godown for stacking of Cholorine at Searsole Head Work site of Augmentation PWSS Of RCFA Part-II (Zone-18) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000980/2023-2024 | 466/RCD-1 | 12/02/2024 | 90 | M/S MONDAL ENTERPRISE | 9.5 | 9.27 | 100
257 | RCFA Division -I | RCFA Division I | Formal work order for Acceptance order for Construction of 700 cum capacity 20 mtr staging height RCC Over Head Reservior (pipe connection and cost of pipes, specials and land devlopment with approached road including internal drain at Mohishila OHR within Asansol Municipal Corporation area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001078/2023-2024 | 805/RCD-I | 13/03/2024 | 180 | GITA CONSTRUCTION | 180.36 | 95.61 | 82
258 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000037/2023-2024 | 2937/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
259 | RCFA Division -I | RCFA Division I | Suuply of UPS laboratory antivirus toner 12 for Asansol Laboratory | Assistant Engineer 2 | Junior Engineer | BILL/00210/2024-2025 | 91/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.08 | 0 | 0
260 | RCFA Division -I | RCFA Division I | Supply of chair for SE/RCFA Circle | Assistant Engineer 2 | Junior Engineer | BILL/00330/2023-2024 | 151/23-24 | 25/07/2023 | 0 | GLOBAL LOGISTIC CO | 0.23 | 0 | 0
261 | RCFA Division -I | RCFA Division I | hirting of maxi cab for date 27.7.2023 to 28.07.2023 us of AE RCFA Div WB37D 9526 | Assistant Engineer 2 | Junior Engineer | BILL/00532/2023-2024 | 256/23-24 | 11/09/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
262 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia HDPE Pipe line including concrete cutting mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Improvement of Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/01008/2023-2024 | 372/23-24 | 21/11/2023 | 0 | B.T.M. CONCERN | 2.14 | 0 | 0
263 | RCFA Division -I | RCFA Division I | Supply of 10 mm into female 15 mm outer male reducer Brass Bush at Searsole Store to provide interconnection work in between maniflod and ferrule under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000208/2022-2023 | 1909/RCD-I | 12/08/2022 | 7 | SNEHA ELECTRIC | 4.69 | 4.69 | 0
264 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000215/2023-2024 | 2243/RCD-1 | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 13.23 | 11.39 | 100
265 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 5.97 | 0
266 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 15.22 | 0
267 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 5.48 | 0
268 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Guzarbagh (Sansad-XXI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000271/2021-2022 | 1880/RCD-I | 28/10/2021 | 30 | R B ENTERPRISE | 13.3 | 13.3 | 0
269 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Safique Nagar (Sansad-XXII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000272/2021-2022 | 1881/RCD-I | 28/10/2021 | 30 | A. CONSTRUCTION CO. | 18.11 | 18.11 | 0
270 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Bibirbandh Para and Santipara (Sansad-I) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000365/2021-2022 | 2323/RCD-I | 16/12/2021 | 30 | GITASHREE FABRICATION | 18.16 | 18.16 | 0
271 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Huchukpara (Sansad-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000366/2021-2022 | 2324/RCD-I | 16/12/2021 | 30 | A. CONSTRUCTION CO. | 15.53 | 15.53 | 0
272 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Das Para (Sansad-XIX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000367/2021-2022 | 2325/RCD-I | 16/12/2021 | 30 | JYOGOMAYA ENTERPRISE | 12.46 | 10.43 | 0
273 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-XII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000368/2021-2022 | 2326/RCD-I | 16/12/2021 | 30 | M/S B.K. CONSTRUCTION | 25.7 | 17.19 | 100
274 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-X) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000369/2021-2022 | 2327/RCD-I | 16/12/2021 | 30 | ASHA CONSTRUCTION | 27.72 | 18.23 | 0
275 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000370/2021-2022 | 2328/RCD-I | 16/12/2021 | 30 | MD AAMIR KHAN | 14.42 | 14.42 | 0
276 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000371/2021-2022 | 2329/RCD-I | 16/12/2021 | 30 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 14.4 | 10.71 | 0
277 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000372/2021-2022 | 2332/RCD-I | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 7.14 | 0
278 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 10.48 | 100
279 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000491/2021-2022 | 120/RCD-I | 20/01/2022 | 30 | GLOBAL CONSTRUCTION | 14.23 | 13.36 | 0
280 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Sanyasi Kalitala (Sansad-XVI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000496/2021-2022 | 2491/RCD-I | 31/12/2021 | 30 | TARA CONSTRUCTION | 11.24 | 10.92 | 0
281 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Asthana (Sansad-IX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000498/2021-2022 | 198/RCD-I | 28/01/2022 | 30 | B M SARKAR | 13.04 | 10.18 | 0
282 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000851/2021-2022 | 2332/RCD-1 | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 4.03 | 0
283 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000014/2025-2026 | 2538/RCD-I | 01/09/2025 | 0 | Resource Division | 6.58 | 0 | 0
284 | RCFA Division -I | Asansol Mechanical Division | Road restoration of work 03 nes location (Reghunathpur Kantaberia via Molandihi, Muchipara Shibpur, Reghunathpur Kantaberna via Molandihi) | Assistant Engineer-II | Junior Engineer-5 | BILL/00544/2024-2025 | 275/24-25 | 06/09/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 26.8 | 0 | 0
285 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Jemua Water Supply Scheme at Gopalpur within Durgapur Faridpur Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000019/2024-2025 | 1522/RCD-I | 14/06/2024 | 292 | ASHA CONSTRUCTION | 22.23 | 0 | 100
286 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work for crossing of culvert and allied works at Ramnagar under Augementation of (RCFA Part-III, Zone-II) PWSS within Pandabeswar Block of RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000298/2025-2026 | 1402/RCD-I | 15/05/2025 | 30 | MAK CONSTRUCTION CO | 14.79 | 0 | 100
287 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPurbapara at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000323/2025-2026 | 1509/RCD-I | 20/05/2025 | 73 | DAWN CONSTRUCTION | 23.41 | 0 | 40
288 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying and pushing by adopting trenchless technology (jack pushing method) additional for distribution network for Augmentation of RCFA part-III (Zone-II) PWSS including FHTC and allied works under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000339/2024-2025 | 2779/RCD-I | 28/11/2024 | 180 | MAK CONSTRUCTION CO | 35.16 | 0 | 68
289 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g Jack Pushing Method etc.) 03 nos. location at Bahula(Zone-9) within Pandabeswar Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000536/2024-2025 | 139/RCD-I | 08/01/2025 | 45 | MD AAMIR KHAN | 40.95 | 0 | 100
290 | RCFA Division -I | Asansol Mechanical Division | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer-II | Junior Engineer-5 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 1.6 | 35
291 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Detailed study of Households/Habitations of Barabani, Faridpur-Durgapur, Jamuria, Kanksa, Ondal, Pandabeswar, Raniganj and Salanpur blocks under Paschim Barddhaman District under the jurisdiction of RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/001073/2023-2024 | 803/RCD-I | 13/03/2024 | 2224 | HORIZEN | 67.79 | 48.15 | 80
292 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 750 M3 capacity 20 mtr Staging height RCC OHR with soil test 105 M3 CWR 35M3/Hr EIP and 250/200 DI K9 Rising main with necessary allied works at Ramnagar under Augmentation of RCFA Part-III(Zone-II) W/S Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-5 | ORD/000008/2023-2024 | 587/A/DWSD | 12/04/2023 | 1005 | AMAR CONSTRUCTION | 305.39 | 152.9 | 90
293 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work at RCC Over Head Reservoir (OHR) Site at Ramnagar H/W Site under Augmentation 0f RCFA, Pt- III , Zone- II Water Supply Scheme (JJM) under Durgapur Water Supply Division, P.H.E. Dte. (Sl- 01) | Assistant Engineer-II | Junior Engineer-5 | ORD/000053/2023-2024 | 839/DWSD | 05/06/2023 | 15 | RANJIB GHATAK | 0.95 | 0 | 0
294 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 4,5 ,6 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) | Assistant Engineer-II | Junior Engineer-5 | ORD/000111/2023-2024 | 05/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100
295 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 12,14,15 Ext ) to combat drought like situation at Ramnagari head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) | Assistant Engineer-II | Junior Engineer-5 | ORD/000118/2023-2024 | 07/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100
296 | Durgapur W/S Division | Asansol Mechanical Division | Emergent Road restoration dismanttled road of Paranganj mouza of Jemua Piped Water supply scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000123/2023-2024 | 1197/DWSD | 27/07/2023 | 35 | MAK CONSTRUCTION CO. | 14.52 | 14.4 | 100
297 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,2,3 Ext) to combat drought like situation at Ramnagar head work site under Augmentation of RCFA,Part-III (Zone-II) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | Assistant Engineer-II | Junior Engineer-5 | ORD/000126/2023-2024 | 10/SPOT/DWSD | 16/06/2023 | 4 | RANJIB GHATAK | 0.99 | 0.99 | 100
298 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of demarcation of new land for mahal OHR site and repairing of UPVC pipe line and allied works at Konda ,Gobindapur village under Modified RCFA Part-III W/s Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-5 | ORD/000136/2022-2023 | 952/DWSD | 16/06/2022 | 10 | RANJIB GHATAK | 3.19 | 3.19 | 0
299 | Durgapur W/S Division | Asansol Mechanical Division | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000156/2023-2024 | 1287/DWSD | 07/08/2023 | 45 | MOTIONMASS TECHNO (OPC) PVT LTD | 6.75 | 6.58 | 100
300 | Durgapur W/S Division | Asansol Mechanical Division | Repairing of existing concrete road restoration and other allied works at Dalubandh mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-D) | Assistant Engineer-II | Junior Engineer-5 | ORD/000158/2023-2024 | 1289/DWSD | 07/08/2023 | 25 | PRAKRITI CONSTRUCTION | 7.82 | 7.81 | 80
301 | Durgapur W/S Division | Asansol Mechanical Division | Repairing of existing concrete road restoration and other allied works at Konda ,Gobindapur mouza under Augmentation of RCFA Part-III (Zone-I) piped W/s Scheme under DWSD,PHE Dte (Part-A) | Assistant Engineer-II | Junior Engineer-5 | ORD/000167/2023-2024 | 1299/DWSD | 07/08/2023 | 15 | SAIKAT RAY | 9.62 | 9.62 | 100
302 | Durgapur W/S Division | Asansol Mechanical Division | Repairing of existing concrete road restoration and other allied works at Baidhayanathpur mouza under Augmentation of RCFA Part-III (Zone-II) piped W/s Scheme under DWSD,PHE Dte (Part-B) | Assistant Engineer-II | Junior Engineer-5 | ORD/000168/2023-2024 | 1300/DWSD | 07/08/2023 | 25 | BASANTI TRADERS | 8.92 | 6.9 | 70
303 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of ''Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12)'' | Assistant Engineer-II | Junior Engineer-5 | ORD/000175/2023-2024 | 748/DWSD | 18/05/2023 | 15 | RANJIB GHATAK | 1.51 | 1.5 | 100
304 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - II (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-04) | Assistant Engineer-II | Junior Engineer-5 | ORD/000185/2023-2024 | 1235/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
305 | Durgapur W/S Division | Asansol Mechanical Division | Additional work for connection of OHR to distribution main and supplying and laying of UPVC pipe line and laying of 600 mm dia RCC NP3 hume pipe modern hydraulic Jack pushing method including laying of 250 mm dia MS pipe with necessary allied works at Mohal OHR to Gobindapur under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000213/2023-2024 | 1448/DWSD | 25/08/2023 | 30 | SAIKAT RAY | 11.66 | 0 | 0
306 | Durgapur W/S Division | Asansol Mechanical Division | Additional work supplying and laying of alternative rute for extra rising main of 250 mm dia DI (K9) and 200 mm dia HDPE pipe line with necessary allied works from Ramnagar H/W site to Mohal OHR under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000215/2023-2024 | 1449/DWSD | 25/08/2023 | 305 | RANJIB GHATAK | 67.61 | 0 | 100
307 | Durgapur W/S Division | Asansol Mechanical Division | Additional work supplying and laying of UPVC pipe le and laying with necessary allied works at Mohal ,Gobindapur under Augmentation of RCFA Part-III (Zone-II) (Part-B) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000216/2023-2024 | 1452/DWSD | 25/08/2023 | 25 | M/S BADAL GHOSH | 9.78 | 9.72 | 100
308 | Durgapur W/S Division | Asansol Mechanical Division | Additional work for UPVC pipe line and laying with necessary allied works at Ramnagar (existing OHR Part-2A) under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000219/2023-2024 | 1447/DWSD | 25/08/2023 | 25 | RANJIB GHATAK | 9.61 | 9.6 | 100
309 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for collecting main with manifold for IEP at Ramnagar H/W site and DI distribution line at ROB new culvert portion under Augmentation of RCFA Part-III (Zone-II) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000222/2023-2024 | 1499/DWSD | 04/09/2023 | 15 | RANJIB GHATAK | 19.4 | 17.6 | 100
310 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) | Assistant Engineer-II | Junior Engineer-5 | ORD/000261/2022-2023 | 872/DWSD | 26/05/2022 | 15 | RANJIB GHATAK | 13.63 | 13.49 | 100
311 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar) (Part - 1A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000270/2022-2023 | 1684/DWSD | 09/12/2022 | 45 | M/S KALYANI ENTERPRISE | 43.17 | 41.37 | 100
312 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar ) (Part - 1B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.(DL-02) | Assistant Engineer-II | Junior Engineer-5 | ORD/000271/2022-2023 | 272/DWSD | 16/02/2023 | 45 | GHOSH ENTERPRISE | 31.84 | 15.06 | 100
313 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 A) Under Augmentation of RCFA Pt - III Zone - II W/S (JJM) Scheme under Durgapur Water Supply Division, PHE Dte.(S-3) | Assistant Engineer-II | Junior Engineer-5 | ORD/000272/2022-2023 | 1686/DWSD | 09/12/2022 | 45 | AMAR CONSTRUCTION | 45.34 | 42.47 | 80
314 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From Ext. OHR Ramnagar )(Part - 2 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme(JJM) under Durgapur Water Supply Division, PHE Dte.(Sl-4) | Assistant Engineer-II | Junior Engineer-5 | ORD/000273/2022-2023 | 427/DWSD | 13/03/2023 | 45 | TARA PRASAD SARKAR | 34.36 | 22.91 | 100
315 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 3 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000275/2022-2023 | 1688/DWSD | 09/12/2022 | 966 | MAK CONSTRUCTION CO. | 75.68 | 62.05 | 100
316 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work at Danya under Augmentation of RCFA Part-III (Zone-II) W/S Scheme (JJM) under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000275/2023-2024 | 1562/DWSD | 20/09/2023 | 15 | MAITO MAA ENTERPRISE | 2.99 | 2.99 | 100
317 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 3 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte.. | Assistant Engineer-II | Junior Engineer-5 | ORD/000276/2022-2023 | 26/DWSD | 09/01/2023 | 45 | KIRON ENTERPRISE | 39.5 | 26.2 | 100
318 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 4 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000277/2022-2023 | 1690/DWSD | 09/12/2022 | 45 | RANJIB GHATAK | 52.17 | 47.46 | 70
319 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 4 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000278/2022-2023 | 46/DWSD | 11/01/2023 | 45 | RANJIB GHATAK | 36.4 | 29.81 | 0
320 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Repairing and road restoration side drainage system and other allied FHTC related works at Patseura village under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD. | Assistant Engineer-II | Junior Engineer-5 | ORD/000278/2023-2024 | 1564/DWSD | 20/09/2023 | 15 | SHWET BARANI | 3.66 | 0 | 0
321 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From Ext. OHR Ramnagar )(Part - 5 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000279/2022-2023 | 1692/DWSD | 09/12/2022 | 45 | BASANTI TRADERS | 32.47 | 23.73 | 1
322 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works for shifting of existing line due to ROB at Pandabeswar under RCFA Pt-III (Zone-II) W/s Scheme under DWSD,PHE Dte. (SL-6) | Assistant Engineer-II | Junior Engineer-5 | ORD/000280/2021-2022 | 1571/DWSD | 27/10/2021 | 20 | RANJIB GHATAK | 3.59 | 3.59 | 0
323 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From Ext. OHR Ramnagar )(Part - 5 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000281/2022-2023 | 270/DWSD | 16/02/2023 | 45 | D. S. ENTERPRISE | 27.65 | 12.83 | 100
324 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 6 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000282/2022-2023 | 45/DWSD | 11/01/2023 | 45 | RANJIB GHATAK | 21.38 | 16.28 | 85
325 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 6 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000289/2022-2023 | 1696/DWSD | 09/12/2022 | 45 | HIRANMAY GHOSH | 30.39 | 29.96 | 68
326 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 7 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000290/2022-2023 | 1697/DWSD | 09/12/2022 | 45 | JAYANTA DATTA | 51.74 | 38.7 | 65
327 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 8A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000292/2022-2023 | 1695/DWSD | 09/12/2022 | 1056 | RUBY CONSTRUCTION | 51.35 | 33.7 | 70
328 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 8 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000293/2022-2023 | 1698/DWSD | 09/12/2022 | 45 | ASHA CONSTRUCTION | 35.77 | 23.48 | 85
329 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A (From New OHR Ramnagar) (Part - 9 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000294/2022-2023 | 1699/DWSD | 09/12/2022 | 45 | JOY GURU ENTERPRISE | 49.65 | 43.58 | 90
330 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 9 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000295/2022-2023 | 387/DWSD | 01/03/2023 | 45 | JOY GURU ENTERPRISE | 26.58 | 17.48 | 100
331 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A (From New OHR Ramnagar) (Part - 10 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000298/2022-2023 | 1701/DWSD | 09/12/2022 | 45 | BABA LOKENATH ENTERPRISE | 58.48 | 50.06 | 75
332 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II A(From New. OHR Ramnagar )(Part - 10 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000300/2022-2023 | 391/DWSD | 01/03/2023 | 45 | BISHAL ENTERPRISE | 38.7 | 0 | 0
333 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II A(From New. OHR Ramnagar )(Part - 7 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000302/2022-2023 | 426/DWSD | 13/03/2023 | 45 | DIP CONSTRUCTION | 34.53 | 14.98 | 65
334 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000303/2022-2023 | 1704/DWSD | 09/12/2022 | 45 | AMARANJALI CONSTRUCTION | 37.9 | 31.57 | 65
335 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 11 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000304/2022-2023 | 428/DWSD | 13/03/2023 | 45 | AMARANJALI CONSTRUCTION | 31.13 | 12.76 | 80
336 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000313/2022-2023 | 1706/DWSD | 09/12/2022 | 45 | SUJAY KUMAR RAY | 50.44 | 45.54 | 85
337 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 12 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000314/2022-2023 | 271/DWSD | 16/02/2023 | 45 | SHWET BARANI | 32.57 | 14.8 | 100
338 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000315/2022-2023 | 1708/DWSD | 09/12/2022 | 45 | B.M. SARKAR | 40.19 | 27.41 | 0
339 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 13 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000321/2022-2023 | 29/DWSD | 09/01/2023 | 45 | PRAVAT SARKAR | 28.7 | 16.11 | 0
340 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 14 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000322/2022-2023 | 1710/DWSD | 09/12/2022 | 45 | CHATTERJEE CONSTRUCTION | 20.6 | 19.56 | 85
341 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 14 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000323/2022-2023 | 1711/DWSD | 09/12/2022 | 45 | SAIKAT RAY | 21.33 | 14.24 | 85
342 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000324/2022-2023 | 1712/DWSD | 09/12/2022 | 45 | MAITO MAA ENTERPRISE | 33.13 | 28.92 | 100
343 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 15 B) Under Augmentation of RCFA Pt - III, Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000325/2022-2023 | 73/DWSD | 18/01/2023 | 45 | SARKAR AGENCY | 24.19 | 0 | 0
344 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III,Zone II B (From Mahal OHR) (Part - 17 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000326/2022-2023 | 1714/DWSD | 09/12/2022 | 45 | M/S BADAL GHOSH | 58.47 | 54.83 | 85
345 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and Laying of Different dia UPVC pipe line With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 A) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000327/2022-2023 | 1715/DWSD | 09/12/2022 | 45 | M/S MONDAL ENTERPRISE | 29.3 | 28.85 | 100
346 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 16 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000332/2022-2023 | 28/DWSD | 09/01/2023 | 45 | M/S MONDAL ENTERPRISE | 23.8 | 21.49 | 90
347 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Providing FHTC With necessary allied works at Pandabeswar Block of RCFA Pt-III, Zone II B (From Mahal OHR) (Part - 17 B) Under Augmentation of RCFA Pt - III Zone - II W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000333/2022-2023 | 27/DWSD | 09/01/2023 | 45 | M/S BADAL GHOSH | 38.49 | 18.77 | 0
348 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 5 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-A) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000446/2022-2023 | 389/DWSD | 01/03/2023 | 15 | RANJIB GHATAK | 35.85 | 35.6 | 100
349 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 6 Nos 200 mm dia river bed tube wells with collecting main with manifold in river Ajoy at Ramnagar H/W site (Part-B) under Augmentation of RCFA Part-III (Zone-II/JJM) piped W/S Scheme under DWSD,PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000447/2022-2023 | 390/DWSD | 01/03/2023 | 20 | RANJIB GHATAK | 42.39 | 42.33 | 100
350 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Supply ,Installation and fabrication of 5 Nos 50 cum./Hr capacity pressure type Iron Elimination Plant which consist of one filter chamber ( dia- 3 m,height -1.5 mtr ) and one oxidation chamber ( dia -1.00 m height -1.2 m) each and Construction of Blower Room (6.50m X 4.00m) With I.E.P. Platform, Plinth, Roof Top Treatment, Plinth Protection and Side Drain at Ramnagar H/W site under Augmentation 0f RCFA, Pt- III (Zone- II) W/S Scheme (JJM) under D.W.S.D., P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000334/2022-2023 | 1718/DWSD | 09/12/2022 | 45 | ALOK ENTERPRISE | 86.64 | 85.97 | 100
351 | Durgapur W/S Division | Asansol Mechanical Division | formal order for the work of Repairing ,shifting and replacing of UPVC pipe line and allied works at Fulbagan More to WBSEDCL office under Augmentation of RCFA Part-III (Zone-II) piped W/S Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000449/2022-2023 | 388/DWSD | 01/03/2023 | 20 | RANJIB GHATAK | 6.59 | 6.58 | 0
352 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-5 | RTOR000003/2023-2024 | 786/DWSD | 25/05/2023 | 0 | Resource Division | 172.1 | 0 | 0
353 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-5 | RTOR000014/2022-2023 | 402/DWSD | 03/03/2023 | 0 | Resource Division | 271.47 | 0 | 0
354 | Asansol Mechanical | Asansol Mechanical Division | Quotation for new connection at Natundanga OHR under RCFA Part-III(Zone-II) water supply scheme. | Assistant Engineer-II | Junior Engineer-5 | BILL/00131/2024-2025 | BP-2024-25-20 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0
355 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery and installation of Electro-Mechanical equipments in existing Ramnagar Pump House in the basis of "Augmentation of Ramnagar Head works Site under R.C.F.A.-III(Zone-II)" Water Supply Scheme under Asansol Mechnical Division,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000412/2022-2023 | 361/AMD | 09/02/2023 | 811 | SUNRISE ENGINEERING CORPORATION | 65.77 | 51.13 | 100
356 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery and installation of Electro-Mechanical equipment at Mahal & ECL Head Works site in the basis for ''Augmentation of Ramnagar Head Works site under R.C.F.A.-III(Zone-II) water supply scheme" under Asansol Mechanical Division, P.H.E. Dte., Block-Pandabeswar, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000413/2022-2023 | 362/AMD | 09/02/2023 | 90 | R.N.S TRADING | 83.82 | 52.68 | 62
357 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Boundary Wall at OCP Based Treatment Plant at Kajora under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000036/2024-2025 | 1591/RCD-I | 27/06/2024 | 414 | MACHINO TECHNO | 25.99 | 0 | 100
358 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work for retaining wall construction and with allied work for Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of steel Truss Bridge, Guard room, CWR, Boundary wall, Laying of raising main, Land development Etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000097/2024-2025 | 2116/RCD-I | 27/08/2024 | 353 | MRITYUNJOY MUKHERJEE & CO. | 46.19 | 0 | 100
359 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional Work For Concrete , MS Girder In connection With source Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP ) including intake arrangement construction of steel Truss Bridge , Guard room ,CWR, Boundary wall, Laying of raising main, Land development etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000098/2024-2025 | 2118/RCD-I | 27/08/2024 | 445 | MACHINO TECHNO | 82.14 | 0 | 100
360 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Laying 300 mm dia Raising Main through 600 mm dia MS pipe by trenchless technique under railway / NH / SH for the OCP base PWSS of Kajora (Ghanashampur OCP) of OCP Kajora PWSS under RCFA Division -1 PHE Dte. . | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000101/2024-2025 | 2121/RCD-I | 27/08/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 57.67 | 45.88 | 100
361 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying 300 mm Dia rising main through 600 mm Dia Ms pipe by trenchless technique under railway /NH/SH FOR THE OCP base PWSS OF Kajora (Ghanashyampur OCP) of OCP Kajora PWSS under RCFA Division-I PHE, Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000181/2024-2025 | 2429/RCD-I | 26/09/2024 | 60 | MRITYUNJOY MUKHERJEE & CO. | 54.06 | 0 | 100
362 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including, Intake Arrangement, Construction of Steel Truss Bridge, Guardroom, CWR, Boundary Wall, Laying of Rising Main, Land Development etc. & other allied works of OCP Kajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000192/2023-2024 | 2148/RCD-I | 12/07/2023 | 275 | MRITYUNJOY MUKHERJEE & CO. | 120.71 | 119.78 | 16
363 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Crossing 250 mm Dia MS pipe under the canal in connection with source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of Steel Truss Bridge, Guard Room, CWR Boundary wall, Laying of rising main, land Development etc. and other allied works of OCP Kajora PWSS under RCFA Division-I PHE, Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000318/2024-2025 | 2760/RCD-I | 28/11/2024 | 260 | MRITYUNJOY MUKHERJEE & CO. | 14.7 | 0 | 100
364 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Route Survey & Preparation of DPR for Augmentation of Kajora Piped Water Supply Scheme. Augmentation of Kajora Piped Water Supply Scheme including Providing FHTC Block : Andal District- Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000617/2023-2024 | 3381/RCD-I | 21/11/2023 | 15 | APEX ENGINEERING | 2.54 | 2.54 | 100
365 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Pump House under at Kajora under Kajora OCP based PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001122/2023-2024 | 928/RCD-I | 15/03/2024 | 90 | MACHINO TECHNO | 35.86 | 35.85 | 100
366 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for New Connection at Kajora | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | BILL/00079/2023-2024 | BP-2023-24-16 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.31 | 0 | 0
367 | Asansol Mechanical | Asansol Mechanical Division | Additional works Corresponding to ''Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Kajora Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Andal, District-Paschim Bardhaman'' | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000072/2025-2026 | 1111/AMD | 16/06/2025 | 30 | ORIENTAL ENGINEERING CO. | 17.15 | 0 | 100
368 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard & Bridge lighting arrangement and other allied works at Kajora Pump House under Kajora Piped Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000277/2024-2025 | 1679/AMD | 04/10/2024 | 227 | PESTCO INDIA | 23.43 | 0 | 100
369 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Kajora Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Andal, District-Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000431/2022-2023 | 483/AMD | 22/02/2023 | 867 | ORIENTAL ENGINEERING CO. | 393.09 | 286.06 | 100
370 | Asansol Mechanical | Asansol Mechanical Division | New Power Connection at Damalia Pumping Station. | Assistant Engineer-II | Junior Engineer-5 | BILL/00021/2023-2024 | BP-2023-24-12 | 19/05/2023 | 0 | INDIA POWER CORPN. LTD. | 24.34 | 0 | 0
371 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000001/2023-2024 | 872/AMD | 04/04/2023 | 366 | EASTERN INDIA SALES AND SERVICE | 166.24 | 121.25 | 100
372 | Asansol Mechanical | Asansol Mechanical Division | Allied Works Corresponding to "Providing and Installation of Sub-Station Equipments and other accessories at Amritnagar Zone-II Water Supply Scheme within RCFA Part-II area, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000074/2024-2025 | 1205/AMD | 07/08/2024 | 45 | EASTERN INDIA SALES AND SERVICE | 12.75 | 0 | 100
373 | RCFA Division -I | RCFA Division I | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 22.11.2023 in Indian railway from Andal to Bhaktarnagar under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00821/2023-2024 | 390/23-24 | 29/11/2023 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0
374 | RCFA Division -I | RCFA Division I | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 22.11.2023 in Indian railway from Andal to Andal Junction Cabin under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00822/2023-2024 | test | 30/11/2023 | 0 | EASTERN RAILWAY | 0.24 | 0 | 0
375 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work laying of different dia HDPE & MS pipe including installation of sluice valve and chamber in different location of Dakshin Khanda & Khandra GP under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000468/2023-2024 | 2860/RCD-I | 06/10/2023 | 30 | UNITED CONSTRUCTION | 25.34 | 22.45 | 90
376 | RCFA Division -I | RCFA Division I | Laying of different dia distribution pipe line at Ghosalpara, Dharmarajtala, Sabarpara, Dagalpara, Ghosalpara, Kamarpara, MajhiPara etc area of Dakshin Khanda area under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000586/2022-2023 | 3294/RCD I | 20/12/2022 | 45 | UNITED CONSTRUCTION | 52.8 | 52.4 | 0
377 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work 300 mm dia MS pipe line for Singharani Bridge crossing and Kajora at Madanpur under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000636/2023-2024 | 3418/RCD-1 | 24/11/2023 | 30 | MD. JAWED KHAN | 11.59 | 11.05 | 100
378 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of FHTC Platform in different household at Dakshin Khanda (Jl No. 36) Block ¿ Andal under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000759/2022-2023 | 385/RCD I | 30/01/2023 | 45 | UNITED CONSTRUCTION | 34.42 | 28.04 | 100
379 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II piped water supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte (Zone-1A) (Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000781/2022-2023 | 818/RCDI | 10/03/2023 | 905 | ASHA CONSTRUCTION | 249.09 | 53.6 | 70
380 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work line concrete cutting and allied works for Augmentation of Nutondanga RCFA Part-II (Zone-1A) piped W/S Scheme of durgapur sub-Division under RCFA division-I PHE dte. | Assistant Engineer 2 | Junior Engineer | ORD/000909/2023-2024 | 214/RCD-I | 29/01/2024 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 35.52 | 35.52 | 70
381 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying 160 mm dia HDPE pipe line along Domahani Jamuria Road under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000921/2022-2023 | 1254/RCD-I | 27/03/2023 | 15 | NATIONAL CONSTRUCTION | 3.85 | 3.84 | 100
382 | RCFA Division -I | RCFA Division I | Allied work of laying distribution system of Balance Work of laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000934/2023-2024 | 497/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 73.78 | 72.39 | 100
383 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Electrical wiring of C and D type quarter building, PHE Housing Complex and Installation of street including arrangement and fedar box and other allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000961/2023-2024 | 484/RCD-I | 12/02/2024 | 15 | T R ENTERPRISE | 13.35 | 13.32 | 100
384 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Augmentation of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000971/2023-2024 | 486/RCD-I | 12/02/2024 | 25 | M/S KALYAN ENTERPRISE | 10.68 | 10.57 | 100
385 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for distribution network for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme including FHTC and allied works within Ondal Block under RCFA Division-I PHE Dte. (Part-I) | Assistant Engineer 2 | Junior Engineer | ORD/000988/2023-2024 | 470/RCD-1 | 12/02/2024 | 30 | SIMA ENTERPRISE | 5.59 | 4.39 | 100
386 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 90 mm HDPE pipe line inter connection stand post and other allied works at Dakshin Khanda, Moira and adjacent area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000990/2023-2024 | 471/RCD-1 | 12/02/2024 | 30 | UNITED CONSTRUCTION | 9.57 | 9.43 | 100
387 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000016/2023-2024 | 2936/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
388 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of distribution pipe line of Kanska Zone-II (Part-B)from OHR to Pathanpara under Augmentation of Birudiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/001178/2023-2024 | 1019/RCD-I | 16/03/2024 | 45 | MD AAMIR KHAN | 35.4 | 35.37 | 100
389 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000043/2023-2024 | 134/RCD-I | 18/01/2024 | 0 | Resource Division | 130.63 | 0 | 0
390 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of creating a separate zone for BIRUDIHA of Birudiha piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Birudiha, Manikara Mouza under Augmentation of BIRUDIHA piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000109/2023-2024 | 1136/DWSD | 20/07/2023 | 712 | M/S K.B.CONSTRUCTION | 98.43 | 70.96 | 100
391 | Durgapur W/S Division | Asansol Mechanical Division | Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Birudiha piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000230/2023-2024 | 1551/DWSD | 19/09/2023 | 398 | KHAN ENTERPRISE | 291.36 | 0 | 90
392 | Asansol Mechanical | Asansol Mechanical Division | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 3, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00835/2024-2025 | BP-2024-25-72 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0
393 | Asansol Mechanical | Asansol Mechanical Division | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 5, under Augmentation of Birudiha Water Supply Scheme, Block- Kanksa, Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00836/2024-2025 | BP-2024-25-73 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0
394 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY FOR TUBE WELL NO-5 (BEHIND GOURI DEVI HOSPITAL) AT AUGMENTATION OF BIRUDIHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE., BLOCK- KANKSA, DIST- PASCHIM BARDHAMAN. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000033/2025-2026 | 953/AMD | 16/05/2025 | 30 | PESTCO INDIA | 2.56 | 0 | 100
395 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Hat tola) & TUBE WELL NO-4 (H/W Site) AT AUGMENTATION OF BIRUDIHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000326/2024-2025 | 1819/AMD | 29/10/2024 | 560 | SUNRISE ENGINEERING CORPORATION | 22.13 | 0 | 11
396 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000015/2021-2022 | 952/RCD-I | 07/06/2021 | 30 | DIP CONSTRUCTION | 23.01 | 4.1 | 0
397 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000016/2021-2022 | 953/RCD-I | 07/06/2021 | 30 | TARA MA ENTERPRISE | 23.02 | 45.17 | 0
398 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] | Assistant Engineer 1 | Junior Engineer | ORD/000017/2021-2022 | 954/RCD-I | 07/06/2021 | 30 | PINKI ENTERPRISE | 23.02 | 39.98 | 0
399 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000018/2021-2022 | 955/RCD-I | 07/06/2021 | 30 | MD AAMIR KHAN | 22.98 | 45.44 | 0
400 | RCFA Division -I | RCFA Division I | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC to Manahora, Kanskuli (Part) and Kalisanko villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1 | Junior Engineer | ORD/000139/2022-2023 | 1433/RCD I | 27/06/2022 | 45 | GITASREE FABRICATION | 1.97 | 1.76 | 0
401 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kalya (part) and Siakulberia and Chotkara (Part) village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 12) | Assistant Engineer 1 | Junior Engineer | ORD/000573/2021-2022 | 255/RCD-I | 01/02/2022 | 20 | JAYANTA DATTA | 4.99 | 4.64 | 0
402 | RCFA Division -I | RCFA Division I | Extension of HDPE pipe line (Parallel to main distribution) at village Kirtansala and Dharaspur village (Part) for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 1 | Junior Engineer | ORD/000578/2021-2022 | 260/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.98 | 4.64 | 0
403 | RCFA Division -I | RCFA Division I | Extension of UPVC pipe line (Parallel to main distribution) at village Ghiadoba and Kusumdanali West side for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 1 | Junior Engineer | ORD/000580/2021-2022 | 262/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 3.58 | 2.79 | 0
404 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000015/2025-2026 | 2537/RCD-I | 01/09/2025 | 0 | Resource Division | 3.7 | 0 | 0
405 | RCFA Division -I | RCFA Division I | Color Xerox repairing and supply of color xerox toner | Assistant Engineer 2 | Junior Engineer | BILL/00292/2024-2025 | 131/24-25 | 11/07/2024 | 0 | MUKHERJEE TRADERS | 0.17 | 0 | 0
406 | RCFA Division -I | RCFA Division I | Bill for GST Return Oct 2023 to Feb 2024 24 Q 1 & Q 2 2023-2024 and 16 A 26 Q 23-24 | Assistant Engineer 2 | Junior Engineer | BILL/00348/2024-2025 | 172/24-25 | 25/07/2024 | 0 | SHRESTHA & ASSOCIATES | 0.44 | 0 | 0
407 | RCFA Division -I | RCFA Division I | Arrangement of Stationary items , Flex and Tea snacks for Krmashree meeting held on 12.07.2024 at RTC Hall Asansol | Assistant Engineer 2 | Junior Engineer | BILL/00358/2024-2025 | 171/24-25 | 26/07/2024 | 0 | BLESSING ENTERPRISE | 0.14 | 0 | 0
408 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill 16.05.2023 to 15.08.2023 | Assistant Engineer 2 | Junior Engineer | BILL/00635/2023-2024 | 264/23-24 | 27/09/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0
409 | RCFA Division -I | RCFA Division I | Hire charges for the month of August 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00636/2023-2024 | 262/23-24 | 27/09/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
410 | RCFA Division -I | RCFA Division I | Fuel bill of WB 37D 0482 | Assistant Engineer 2 | Junior Engineer | BILL/00637/2023-2024 | 263/23-24 | 27/09/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
411 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Maira area Dakshin Khnada (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000246/2022-2023 | 2212/RCD-I | 14/09/2022 | 30 | UNITED CONSTRUCTION | 44.65 | 9.74 | 0
412 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B1) | Assistant Engineer 2 | Junior Engineer | ORD/000305/2021-2022 | 2130/RCD-I | 29/11/2021 | 30 | D.S. ENTERPRISE | 18.12 | 12.86 | 0
413 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B2) | Assistant Engineer 2 | Junior Engineer | ORD/000306/2021-2022 | 2131/RCD-I | 29/11/2021 | 30 | M/S B.K. CONSTRUCTION | 18.13 | 18.13 | 0
414 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C1) | Assistant Engineer 2 | Junior Engineer | ORD/000307/2021-2022 | 2132/RCD-I | 29/11/2021 | 30 | KHEPI MAA TRADERS | 17.52 | 17.52 | 0
415 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Pandabeswar of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C2) | Assistant Engineer 2 | Junior Engineer | ORD/000308/2021-2022 | 2133/RCD-I | 29/11/2021 | 30 | MRITYUNJOY MUKHERJEE & CO. | 18.7 | 12.53 | 0
416 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Khandra (CT) (JL no. 32, Block - Andal) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000318/2021-2022 | 2145/RCD-I | 29/11/2021 | 488 | DAS & CHAKRABORTY | 78.91 | 68.92 | 100
417 | RCFA Division -I | RCFA Division I | Laying of different dia HDPE pipe line including repairing work of UPVC pipe line and etc. allied works under Khandra Zone distribution pipe line under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 2 | Junior Engineer | ORD/000508/2021-2022 | 222/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.79 | 4.79 | 0
418 | RCFA Division -I | RCFA Division I | Supply, fitting fixing of street stand posts and crossing of distribution water branch main through Khandra main road and etc. including interconnection work under Khandra Zone under RCFA Part-II W/S Scheme. (Sl No. 11) | Assistant Engineer 2 | Junior Engineer | ORD/000509/2021-2022 | 223/RCD I | 01/02/2022 | 12 | UNITED CONSTRUCTION | 2.61 | 2.61 | 0
419 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of different dia distribution pipe line and allied works etc at Bisseswari Muslimpara and adjacent area of Khandra area under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000636/2022-2023 | 334/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 7.68 | 0.73 | 100
420 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line towards Bisserari, Anandapally and etc. adjacent area under Khandra area Block Andal & Pandabeswar of Improvement of RCFA Part-II Water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000684/2022-2023 | 372/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 6.87 | 1.11 | 100
421 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different 140 mm dia HDPE pipe line including interconnection and fitting, fixing sluice valves and etc allied works at Maira Dipu area under Khandra Zone under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000923/2022-2023 | 1259/ RCD I | 27/03/2023 | 15 | TARA CONSTRUCTION | 2.32 | 2.16 | 0
422 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia HDPE pipe line towards Ruidas Para and Baouripara under Dakshin Khanda (Jl No. 36) area Block - Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000938/2022-2023 | 1272/ RCD I | 27/03/2023 | 15 | DURGADAS MONDAL | 3.71 | 3.68 | 0
423 | RCFA Division -I | RCFA Division I | Acceptance cum work order Interconnection work of 200 distribution main at Ukhra Zone and emergency repairing of 400 mm dia rising main at Khandra Zone under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000947/2022-2023 | 1285/ RCD I | 27/03/2023 | 15 | RANJIB GHATAK | 4.28 | 4.26 | 100
424 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000003/2021-2022 | 2283 | 12/12/2021 | 0 | Resource Division | 18.59 | 0 | 0
425 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000007/2025-2026 | 2544/RCD-I | 01/09/2025 | 0 | Resource Division | 3.35 | 0 | 0
426 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional supplying laying and aligning of distribution system including FHTC for Shyamla in Chatrisganda Mouza, Block Jamuria Paschim Bardhaman under Augmentation of Madantore PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000114/2024-2025 | 2137/RCD-I | 27/08/2024 | 45 | DAWN CONSTRUCTION | 38 | 33.69 | 100
427 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-4 Segment) for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000157/2022-2023 | 1708/RCD-I | 15/07/2022 | 881 | DAWN CONSTRUCTION | 48.67 | 32.88 | 100
428 | RCFA Division -I | Asansol Mechanical Division | Laying of distribution system including FHTC work for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000293/2022-2023 | 2450/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 246.41 | 70.1 | 100
429 | RCFA Division -I | Asansol Mechanical Division | Detailed Route Survey, Design Drawing & DPR Preparation for Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 4) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000539/2021-2022 | 503/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 0
430 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of Capacity 250 cum at Madantore under Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000557/2023-2024 | 3186/RCD-I | 01/11/2023 | 270 | A.K.CONSTRUCTION | 10.95 | 8.9 | 100
431 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repair and renovation works of Clear Water Reservoir of Capacity 150 cum for Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000558/2023-2024 | 3187/RCD-I | 01/11/2023 | 180 | A.K.CONSTRUCTION | 10.86 | 0 | 0
432 | RCFA Division -I | Asansol Mechanical Division | Construction of Pump House at Churulia under Madantore Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000572/2022-2023 | 3281/RCDI | 20/12/2022 | 90 | M/S MONDAL ENTERPRISE | 30.24 | 30.24 | 100
433 | RCFA Division -I | Asansol Mechanical Division | Acceptance work order for Construction of Chlorine Room of Size (4.50 x 3.50 m) at Churulia for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000644/2022-2023 | 342/RCDI | 30/01/2023 | 15 | ANAMIKA CONSTRUCTION | 4.6 | 4.42 | 100
434 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 1 (One) no. 200 mm dia river bed tube well in the river Ajoy including 01 (One) no collecting main of Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 22) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000886/2022-2023 | 1165/RCD I | 24/03/2023 | 60 | R B ENTERPRISE | 5.77 | 5.68 | 0
435 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for repair and renovation works of GLR of capacity 90 cum for Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 23) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000889/2022-2023 | 1166/RCD I | 24/03/2023 | 180 | A.K.CONSTRUCTION | 6.48 | 0 | 5
436 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Repairing & shifting work of DI pipes and allied repairing at Madanpur under Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000928/2022-2023 | 1261/ RCD I | 27/03/2023 | 15 | MAK CONSTRUCTION CO. | 3.22 | 3.21 | 100
437 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional works of Dismantling and concrete works supplying aligning and laying HDPE pipe and other allied works at distribution system network for Bagdiha (Part-D) Augmentation of Madantor Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000973/2023-2024 | 491/RCD-I | 12/02/2024 | 45 | TARA MA ENTERPRISE | 18.79 | 11.87 | 75
438 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply & Delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/001034/2023-2024 | 713/RCD-I | 29/02/2024 | 20 | NEZONE TUBES LIMITED | 95.53 | 95.49 | 100
439 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000011/2022-2023 | 2351/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
440 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000023/2022-2023 | 3130 | 09/12/2022 | 0 | Resource Division | 12.9 | 0 | 0
441 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous chlorination system at Churulia High lift pump house under Madantore W/S scheme. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000137/2024-2025 | 1322/AMD | 21/08/2024 | 197 | M/S. SOMA ENTERPRISE | 28.71 | 0 | 100
442 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Pump Motor Set in the basis of "Augmentation of Madantor & Its Adjoining Mouzas "Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000505/2022-2023 | 607/AMD | 03/03/2023 | 580 | M/S. SOMA ENTERPRISE | 14.44 | 11.82 | 100
443 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Telipara W/S Scheme , Pump House No- 01 , Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00205/2022-2023 | BP-2022-23-337 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.45 | 0 | 0
444 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Telipara W/S Scheme , Pump House No- 02 , Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00206/2022-2023 | BP-2022-23-338 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0
445 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000008/2022-2023 | 554/DWSD | 11/04/2022 | 25 | M/S SANTANU PALIT & CO. | 127.01 | 0 | 0
446 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connecting (FHTC ) and connection providing to Raghunathpur Mouza-39 and Paschim Gangarampur Mouza- JL-92 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (Part-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000009/2022-2023 | 642/DWSD | 21/04/2022 | 25 | M/S PROCHESTA ENTERPRISE | 98.21 | 98.21 | 85
447 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-1 or H/W Site of Telipara piped W/S Scheme under DWSD, PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000010/2022-2023 | 576/DWSD | 13/04/2022 | 45 | M/S KALYANI ENTERPRISE | 6.21 | 6.21 | 100
448 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of Pump house cum Chlorine Room with Sanitary Plumbing arrangement at Jamdoba tube well No-2 or H/W Site of Telepara piped W/S Scheme under DWSD, PHE Dte (SL-06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000011/2022-2023 | 641/DWSD | 21/04/2022 | 45 | MUKHERJEE ENTERPRISE | 6.15 | 6.06 | 0
449 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 200 M3 capacity , 20 mtr staging height RCC Over head Reservoir (OHR) at Jamdoba of Telipara piped W/s Scheme under Durgapur W/S Division, PHE Dte (SL-07) | Assistant Engineer-II | Junior Engineer-3 | ORD/000012/2022-2023 | 575/DWSD | 13/04/2022 | 1506 | M/S KALYANI ENTERPRISE | 62.35 | 19.72 | 100
450 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and other allied works under Telipara piped W/s Scheme of DWSD,PHE Dte (SL-06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000103/2022-2023 | 786/DWSD | 18/05/2022 | 10 | M/S MONDAL ENTERPRISE | 14.09 | 12.59 | 0
451 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 No Tube well 250 mm X 150 mm big dia Tube well 210 mtr depth direct rotary rig method using PVC pipe & Pre packed resin bonded gravels filter for Telipara piped W/s Scheme under DWSD, PHE Dte (SL-10) | Assistant Engineer-II | Junior Engineer-3 | ORD/000107/2022-2023 | 739/DWSD | 06/04/2022 | 10 | M/S. D. PALIT & CO. | 22.86 | 18.07 | 0
452 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.08.2023 to 17.02.2024). (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000191/2023-2024 | 1364/DWSD | 11/08/2023 | 184 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 100
453 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.02.2023 to 17.08.2023). (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000501/2022-2023 | 133/DWSD | 31/01/2023 | 181 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 80
454 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Jamdoba of Telipara W/s Scheme pump house No-II under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000567/2022-2023 | 481/DWSD | 22/03/2023 | 45 | MUKHERJEE ENTERPRISE | 14.92 | 12.84 | 100
455 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work Balance work for construction of pump house with approach road and others allied works at Jamdoba pump house No-II Telipara piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000595/2022-2023 | 579/DWSD | 10/03/2023 | 20 | MUKHERJEE ENTERPRISE | 5.68 | 5.68 | 100
456 | Durgapur W/S Division | Asansol Mechanical Division | Water supply arrangement to 6(Six) Nos AWC without electricity at Jamdoba,Telipara, Nabagram Majhiara & other allied works under Telipara Piped Water Supply Scheme.(TSM/004035) under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000665/2022-2023 | 625/A/DWSD | 21/04/2022 | 20 | B. T. M. CONCERN | 34.06 | 32.79 | 100
457 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000014/2021-2022 | 330/DWSD | 15/03/2022 | 0 | Resource Division | 37.85 | 0 | 0
458 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Garkilla Kherobari W/S Scheme, P.H. No - 01, Gopalpur CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00181/2022-2023 | BP-2022-23-332 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.8 | 0 | 0
459 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) | Assistant Engineer-II | Junior Engineer-3 | ORD/000167/2022-2023 | 764/DWSD | 13/05/2022 | 45 | BABA LOKENATH ENTERPRISE | 28.84 | 24.12 | 100
460 | RCFA Division -I | Asansol Mechanical Division | Fuel bill in faver of Ranajit auto for the month of October 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt. of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | BILL/01095/2024-2025 |  | 14/01/2025 | 0 | RANAJIT AUTO | 0.18 | 0 | 0
461 | RCFA Division -I | Asansol Mechanical Division | Repairing and renovation of staff quarter (Group A Type) and other allied works at Kalyaneswari Township under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000019/2022-2023 | 1078/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.86 | 4.72 | 100
462 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying Rising Main of Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000055/2024-2025 | 1745/RCD-I | 18/07/2024 | 260 | M/S MONDAL ENTERPRISE | 28.19 | 4.69 | 60
463 | RCFA Division -I | Asansol Mechanical Division | Balance work of Supplying,laying and aligning of Distribution system includind FHTC for Shyamla W/S Scheme in Shyamla and Bhuri Mouza, Block jamuria, Dist-Paschim Bardhaman under Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000082/2024-2025 | Camp-02_Shyamla_AE-II/24- | 06/08/2024 | 30 | TARA CONSTRUCTION | 12.5 | 12.41 | 100
464 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000108/2022-2023 | 1277/RCD-I | 02/06/2022 | 579 | JAYANTA DATTA | 32.82 | 24.1 | 85
465 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000109/2022-2023 | 1278/RCD-I | 02/06/2022 | 90 | MD. JAWED KHAN | 38.01 | 29.87 | 0
466 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte.(Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000111/2022-2023 | 1279/RCD I | 02/06/2022 | 90 | M/S B.K. CONSTRUCTION | 59.35 | 38.85 | 80
467 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000113/2022-2023 | 1281/RCD I | 02/06/2022 | 30 | MAA ENTERPRISE. | 11.06 | 10.81 | 0
468 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Sarisathali OHR site of Augmentation of Sarsathali Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000206/2023-2024 | 2219/RCD-I | 17/07/2023 | 30 | M/S CHANDI CHARAN ROY | 29.79 | 18.72 | 65
469 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for laying of distribution system including adopting trench less technology for one location near Khosnagar Health Centre and allied works under Augmentation of Sarishatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000285/2023-2024 | 2334/RCD-I | 01/08/2023 | 15 | M/S B.K. CONSTRUCTION | 11.2 | 9.4 | 100
470 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying rising main including Guard room with Toilet including 12 (Twelve) nos Tube Well and Collecting main at River Ajoy under due to open cast mining activity of ECL Salanpur area for Sarisatali and Majiara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000290/2023-2024 | 2339/RCD-I | 01/08/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.93 | 13.26 | 20
471 | RCFA Division -I | Asansol Mechanical Division | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at District Magistrate bungalow, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000417/2023-2024 | Camp_2_DM_Office_AE_II_20 | 01/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.87 | 7.74 | 100
472 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of OHR (Capacity 300 cum, staging Height 20 mtrs) for Augmentation of Sarisathali Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block-Barabani, Dist - Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000458/2022-2023 | 2933/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 85.83 | 85.83 | 100
473 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 (Two) nos 200 mm dia river bed tube well including collecting main in the river of Ajoy for Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000467/2023-2024 | 2859/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 7.67 | 7.16 | 100
474 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR for Augumentation of Sarshatali Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(Sl No 04) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000480/2021-2022 | 2348/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 0
475 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution network for augmentation of Sarisathali piped Water Supply scheme including FHTC work, Block-Baraboni, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000534/2022-2023 | 3231//RCDI | 19/12/2022 | 987 | SRI KRISHNA ENTERPRISE | 133.36 | 14.98 | 100
476 | RCFA Division -I | Asansol Mechanical Division | Interconnection at Nimcha OHR site and allied works at Nimcha village for Amritnagar -II under Augmentation of Sarshathali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000637/2024-2025 | Camp-02_Nimcha/AE-II/24-2 | 18/02/2025 | 20 | MD. JAWED KHAN | 8.06 | 0 | 100
477 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying aligning & laying 225 mm dia HDPE pipe line in related to distribution Network for Augmentation of Sarisatali Piped W/S Scheme under RCFA Division-I PHE Dte. ( Sl No. 18) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000848/2022-2023 | 1085/RCD I | 23/03/2023 | 90 | JAYANTA DATTA | 19.21 | 18.02 | 100
478 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Chlorine room of size 4 mtr x 4 mtr x3.5 mtr (Ht) at Sarsatali under Augmentation of Sarsatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/001085/2023-2024 | 875/RCD-I | 15/03/2024 | 60 | JAI MAHARAJ ENTERPRISE | 3.99 | 3.99 | 100
479 | Asansol Mechanical | Asansol Mechanical Division | Providing & Installation of Low Lift Pumping Machineries at newly sunk Tube Wells at Kharabar river bed under Sarshatali Piped Water Supply scheme, Block : Baraboni, Dist : Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000041/2023-2024 | 1024/AMD | 19/04/2023 | 90 | M/S. SOMA ENTERPRISE | 13.7 | 13.68 | 100
480 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of vertical Pumping Machineries under Sarisathali Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000073/2025-2026 | 1112/AMD | 16/06/2025 | 30 | M/S. SOMA ENTERPRISE | 11.05 | 0 | 0
481 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of road at Runakuraghat H/W site including earth filling,treeguard making including repairing and restoration of rising main including collecting main under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000006/2024-2025 | 1432/RCD-I | 06/06/2024 | 45 | SRI KRISHNA ENTERPRISE | 58.57 | 57.74 | 100
482 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 26.38 | 100
483 | RCFA Division -I | Asansol Mechanical Division | Plumbing works, sanitary fitting, flooring and other allied works of staff Quarter (Group A Type) and other allied works at Kalyaneswari township under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000018/2022-2023 | 1077/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 3.89 | 3.82 | 100
484 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 10.08 | 75
485 | RCFA Division -I | Asansol Mechanical Division | acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Tematha Panuria Bazar, Gourandi Bazar, Aliganj Road including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000222/2023-2024 | 2226/RCD-I | 17/07/2023 | 30 | A. CONSTRUCTION CO. | 30.14 | 29.86 | 100
486 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Bhtas more, ardanga more on Asansol Runakuraghat Road, including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000224/2023-2024 | 2227/RCD-I | 17/07/2023 | 30 | GITA CONSTRUCTION | 43.42 | 39.5 | 91
487 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work at Baradanga, Alipur and Kanta Pahari Villages under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000240/2022-2023 | 2015/RCD-I | 26/08/2022 | 45 | GITA CONSTRUCTION | 44.01 | 24.63 | 40
488 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution System surrounding OHR near Panuria under Agumentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000242/2022-2023 | 2151/RCD-I | 02/09/2022 | 30 | A. CONSTRUCTION CO. | 28.88 | 26.24 | 100
489 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Providing FHTC work at Panuria (Part) and adjacent Habitation under Augmentation of Panuria Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000295/2022-2023 | 2468/RCDI | 14/10/2022 | 45 | A. CONSTRUCTION CO. | 69.99 | 65.36 | 100
490 | RCFA Division -I | Asansol Mechanical Division | Acceptence cum work order for Laying of different dia distribution pipe line and etc. work at Tanti para, Camp para, Sasan para etc. under Khandra area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000405/2023-2024 | 2587/RCD-I | 07/09/2023 | 15 | D.S.ENTERPRISE | 7.48 | 7.42 | 100
491 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR for Augmentation of Panuria Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000449/2021-2022 | 2345/RCD-I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.02 | 3.02 | 0
492 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for new pipe line of 200 mm, 90 mm and 75 mm dia at Panuria Bazar under Panuria GP under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000576/2022-2023 | 3285/RCD I | 20/12/2022 | 60 | SRI KRISHNA ENTERPRISE | 12.15 | 12.08 | 0
493 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution System at Katapahari, Alipur, Baradanga village and surrounding area (Part-B) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000585/2021-2022 | 598/RCD-I | 07/03/2022 | 60 | GITA CONSTRUCTION | 78.27 | 70.11 | 91
494 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution System at Panuria village at surrounding area (Part-C) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000586/2021-2022 | 599/RCD-I | 07/03/2022 | 60 | A. CONSTRUCTION CO. | 76.15 | 76.13 | 100
495 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for construction of C.W.R. (Clear water Reservoir) of capacity 200 Cu.m & allied Work at Panuria under Augmentation of Panuria Piped Water Supply Scheme under RCFA Divn.-I. P.H.E. Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000594/2022-2023 | 3276/RCDI | 20/12/2022 | 90 | SAMIR KUMAR ROY CHOWDHURY | 22.05 | 20.65 | 70
496 | RCFA Division -I | Asansol Mechanical Division | Formal work order for construction of 350 cum capacity 20 mtr staging height RCC over Head Reservoir (Piped connection and cost of pipes, specials at Gourandi H/W site for Augmentation of Panuria Piped Water Supply Scheme under RCFA Div-I, PHE dte in the District of Pachim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000618/2022-2023 | 102/RCD I | 20/01/2023 | 212 | A. CONSTRUCTION CO. | 115.99 | 115.99 | 100
497 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Proposed Pump House including Toilet of Augmentation Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000836/2022-2023 | 1064/RCD-I | 23/03/2023 | 180 | RUBY CONSTRUCTION | 31.13 | 31.12 | 100
498 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of existing culvert, Pump House, Staff Quarter under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000891/2022-2023 | 1167/RCD I | 24/03/2023 | 90 | R B ENTERPRISE | 5.94 | 5.88 | 0
499 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000002/2024-2025 | 1179/RCD-I | 03/04/2024 | 0 | Resource Division | 37.47 | 0 | 0
500 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000007/2022-2023 | 2347/RCD-I | 28/09/2022 | 0 | Resource Division | 21.56 | 0 | 0
501 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000013/2021-2022 | 696/RCD-I | 23/03/2022 | 0 | Resource Division | 92.44 | 0 | 0
502 | Asansol Mechanical | Asansol Mechanical Division | QUOTATION MONEY FOR NEW CONNECTION AT PANURIA | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00026/2023-2024 | BP-2023-24-7 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0
503 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000433/2022-2023 | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 60.38 | 68
504 | RCFA Division -I | RCFA Division I | Arrangement of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conference hall | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01309/2023-2024 | 494/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.1 | 0 | 0
505 | RCFA Division -I | RCFA Division I | Arrangemen of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conferenc hall | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01310/2023-2024 | 495/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.09 | 0 | 0
506 | RCFA Division -I | RCFA Division I | Supply of it peripherals | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01741/2023-2024 | 497/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.43 | 0 | 0
507 | RCFA Division -I | RCFA Division I | Supply of computer desktop | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01742/2023-2024 | 498/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0
508 | RCFA Division -I | RCFA Division I | AMC for xerox machine | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01743/2023-2024 | 455/23-24 | 04/01/2024 | 0 | WORK CHARGE BILL | 0.21 | 0 | 0
509 | RCFA Division -I | RCFA Division I | Repair & maintenance on contract basis of computers and local area network under SERCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01745/2023-2024 | 499/23-24 | 01/02/2024 | 0 | KALPANA ENTERPRISE | 0.46 | 0 | 0
510 | RCFA Division -I | RCFA Division I | Hiring charge of Maxi cab (non conditioned) stage II / BS III for ofice use Veh WB 37 D 9526 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01746/2023-2024 | 553/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
511 | RCFA Division -I | RCFA Division I | Hirig of maxi cab state II/BS III for the office use of the Assistant Engineer | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01747/2023-2024 | 554/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
512 | RCFA Division -I | RCFA Division I | Hire charges bill for vehicle no WB 37 D0482 for the month of January | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01748/2023-2024 | 570/23-24 | 27/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
513 | RCFA Division -I | RCFA Division I | Fuel bill of Ranajit Auto vehicle no WB 37 D 0482 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01749/2023-2024 | 571/23-24 | 27/02/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0
514 | RCFA Division -I | RCFA Division I | Vehicle bill for the month of Dec 2023 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01750/2023-2024 | 529/23-24 | 06/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
515 | RCFA Division -I | RCFA Division I | Fuel bill for shyamal Maji for the month of Dec 23 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01751/2023-2024 | 530/23-24 | 08/02/2024 | 0 | RANAJIT AUTO | 0.17 | 0 | 0
516 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for sinking 3 nos 200 mm dia river bed tube wells and allied repairing work in river Damodar including surging of tube wells at Damalia H/W site under Tirat Mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 11) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000002/2023-2024 | 1387/RCD-I | 11/04/2023 | 12 | D.S.C. CONCERN | 6.88 | 6.87 | 0
517 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency supplying aligning and laying of different dia HDPE pipe line for by pass water supply arrangement to Roypara, Singhapara and adjacent areas under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000007/2022-2023 | 937/RCD-I | 26/04/2022 | 30 | M/S MONDAL ENTERPRISE | 24.23 | 24.17 | 0
518 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through retrofitting at Saheb Bangla & allied areas at Khottamdihi Block Pandabeswar of Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000039/2021-2022 | 978/RCD-I | 17/06/2021 | 1550 | A.K. SIKDAR | 19.13 | 26.36 | 100
519 | RCFA Division -I | RCFA Division I | Acceptance cum work order Providing FHTC of retrofitting at Kumardihi village (Left out portion) of kumardiha Mouza, GP-Ratibati, Block Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000057/2023-2024 | 1742/RCD I | 11/05/2023 | 15 | D.S.C. CONCERN | 7.9 | 7.51 | 0
520 | RCFA Division -I | RCFA Division I | Continuation work order for Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000098/2021-2022 | 816/RCD-I | 19/04/2021 | 45 | GITA CONSTRUCTION | 11.84 | 9.17 | 0
521 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000102/2020-2021 | 1156 /RCD I | 23/12/2020 | 20 | A.K.CONSTRUCTION | 4.43 | 6.18 | 0
522 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000103/2020-2021 | 1157/RCD I | 23/12/2020 | 20 | DHRUBA ENTERPRISE | 4.45 | 6.13 | 0
523 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000104/2020-2021 | 1158/RCD I | 23/12/2020 | 20 | M/S MONDAL CONSTRUCTION | 4.44 | 6.17 | 0
524 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000105/2020-2021 | 1159/RCD I | 23/12/2020 | 20 | VISUVIOUS | 4.47 | 6.17 | 0
525 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000106/2020-2021 | 1160/RCD I | 23/12/2020 | 20 | MS KALYAN ENTERPRISE | 4.45 | 6.37 | 0
526 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Providing FHTC through Retrofitting at Chelod Mouza, G.P.-Tirat, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000108/2020-2021 | 1167/RCD-I | 23/12/2020 | 30 | MRITYUNJOY MUKHERJEE & CO. | 37.97 | 31.34 | 0
527 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000110/2020-2021 | 1185/RCD-I | 24/12/2020 | 30 | SWATI CORPORATION | 39.19 | 58.25 | 0
528 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Providing FHTC through Retrofitting at Kumardiha Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000111/2020-2021 | 1186/RCD-I | 24/12/2020 | 30 | M/S B.K. CONSTRUCTION | 19.63 | 35.64 | 0
529 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Seora Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000112/2020-2021 | 1187/RCD-I | 24/12/2020 | 30 | A. CONSTRUCTION CO. | 20.48 | 39.53 | 0
530 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ratibati (Part-II), G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 06) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000113/2020-2021 | 1188/RCD-I | 24/12/2020 | 30 | SOMNATH SAMANTA | 22.88 | 40 | 0
531 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 2 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000114/2020-2021 | 1189/RCD-I | 24/12/2020 | 30 | GITASHREE FABRICATION | 12.68 | 19.38 | 0
532 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mines Quarter Booth No. 3, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000115/2020-2021 | 1190/RCD-I | 24/12/2020 | 30 | SIMA ENTERPRISE | 9.93 | 12.38 | 0
533 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dom Para Both No. 4, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000116/2020-2021 | 1191/RCD-I | 24/12/2020 | 30 | DAWN CONSTRUCTION | 18.7 | 7.57 | 0
534 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khottamdih Village, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 04) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000117/2020-2021 | 1192/RCD-I | 24/12/2020 | 30 | M/S MONI TRADERS | 14.1 | 19.45 | 0
535 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 3 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000118/2020-2021 | 1193/RCD-I | 24/12/2020 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 16.09 | 22.19 | 0
536 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) (Sl No. 06) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000119/2020-2021 | 1194/RCD-I | 24/12/2020 | 30 | DURGADAS MONDAL | 9.08 | 10.62 | 0
537 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000120/2020-2021 | 1195/RCD-I | 24/12/2020 | 30 | UNITED CONSTRUCTION | 9.15 | 13.54 | 0
538 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000122/2020-2021 | 1155/RCD I | 23/12/2020 | 20 | ZEROTH CONTROL SYSTEM | 4.4 | 5.68 | 0
539 | RCFA Division -I | RCFA Division I | Laying of HDPE pipe line and other repairing work of distribution at Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000152/2022-2023 | 1446/RCD I | 27/06/2022 | 45 | M/S MONDAL ENTERPRISE | 2.54 | 2.49 | 0
540 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, aligning and laying of DI & HDPE pipe line for water supply arrangement to Kumardiha village under Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000156/2021-2022 | 1584/RCD-I | 07/09/2021 | 30 | M/S MONDAL ENTERPRISE | 20.03 | 19.9 | 0
541 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia UPVC/HDPE pipe line for extension of distribution system regarding FHTC work at Kumardiha mouza of Ratibati water supply scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000160/2021-2022 | 1585/RCD-I | 07/09/2021 | 30 | M/S B.K. CONSTRUCTION | 14.42 | 13.73 | 0
542 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, Aligning and laying of HDPE pipe line for FHTC work at Chapui mouzas of Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000162/2021-2022 | 1587/RCD-I | 07/09/2021 | 30 | SWATI CORPORATION | 25.46 | 17.1 | 0
543 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000215/2020-2021 | 432 /RCD-I | 04/03/2021 | 45 | GITA CONSTRUCTION | 46.13 | 75.61 | 0
544 | RCFA Division -I | RCFA Division I | Sinking of 3 (Three) nos 200 mm dia River Bed Tube Wells including repairing work of 100 mm dia Collecting Mains which were damaged due to flood in the month of July - August & etc. allied works at River Damodar under Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. (sl no 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000278/2021-2022 | 1937/RCD I | 09/11/2021 | 20 | M/S PIONEER CONSTRUCTION | 3.17 | 2.92 | 0
545 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari Bauri Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000294/2021-2022 | 2026/RCD-I | 24/11/2021 | 30 | RANJIB GHATAK | 26.95 | 22.7 | 0
546 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari General Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000295/2021-2022 | 2027/RCD-I | 24/11/2021 | 30 | SWATI CORPORATION | 39.08 | 31.16 | 0
547 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and laying of 16 sqmm x 4 core Al armored PVC power cable and 10 HP Submersible Pump at Ratibati river bed pump house site damaged due to spreading of fire of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000298/2021-2022 | 2030/RCD-I | 24/11/2021 | 10 | M/S PIONEER CONSTRUCTION | 11.72 | 11.72 | 0
548 | RCFA Division -I | RCFA Division I | Annual Maintenance Contract (AMC) for Computers, Prnters, UPS & other related peripherals installed at office chamber of the Assistant Engineer, Junior Engineers, DPMU, IEC under of the Executive Engineer, RCFA Division-I PHE Dte. (Period from 01.07.2023 to 31.12.2023) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000308/2023-2024 | 2039/RCD-I | 30/06/2023 | 184 | SHARMA ENGINEERING WORKS | 0.9 | 0.9 | 100
549 | RCFA Division -I | RCFA Division I | Laying of 50 mm dia PVC pipe line and construction of different dia valve chamber, FHTC work and etc. allied works at Kendra area under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000326/2021-2022 | 2175/RCD I | 06/12/2021 | 10 | MS KALYAN ENTERPRISE | 4.57 | 4.47 | 0
550 | RCFA Division -I | RCFA Division I | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No 17) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000339/2020-2021 | 363/RCD I | 26/02/2021 | 7 | SWATI CORPORATION | 4.68 | 9.36 | 0
551 | RCFA Division -I | RCFA Division I | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chelod Mouza, G.P.- Tirat, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte.(SL NO 18) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000341/2020-2021 | 364/RCD I | 26/02/2021 | 7 | MRITYUNJOY MUKHERJEE & CO. | 4.66 | 9.33 | 0
552 | RCFA Division -I | RCFA Division I | Hiring of Maxi Cab (Non Air- conditioned ) bharatstage - III/BS-III purchased on after 01.05.2008 with Diesel / LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal ( w.e.f 16.08.2023 to 15.02.2024) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000354/2023-2024 | 2420/RCD-I | 11/08/2023 | 184 | PRAMIT CHATTERJEE | 0.9 | 2.37 | 100
553 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dhandardihi Mouza, Vill-Madanpur, Block-Andal of Dhandardihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000357/2020-2021 | 1032/RCD-I | 05/11/2020 | 30 | MACHINO TECHNO | 43.84 | 13.66 | 0
554 | RCFA Division -I | RCFA Division I | Supply, fitting fixing railling, grill, painting of pump house, CWR, chlorine room etc and allied works at Ratibati H/W and Tirat Colliery H/W site under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000359/2021-2022 | 2203/RCD I | 06/12/2021 | 21 | SOMNATH SAMANTA | 3.53 | 2.97 | 0
555 | RCFA Division -I | RCFA Division I | Laying UPVC pipeline for FHTC work for Dhandadihi W/S Scheme under RCFA Div-I, PHE Dte.(Sl no 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000456/2021-2022 | 2458/RCD I | 31/12/2021 | 10 | MACHINO TECHNO | 3.83 | 3.82 | 0
556 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Kumardiha village area of Chold mouza, GP -Ratibati Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 08) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000462/2021-2022 | 2465/RCD I | 31/12/2021 | 7 | D.S.C. CONCERN | 4.81 | 4.81 | 0
557 | RCFA Division -I | RCFA Division I | Additional laying of different dia UPVC pipeline for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 09) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000463/2021-2022 | 2466/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 4.78 | 4.55 | 0
558 | RCFA Division -I | RCFA Division I | Hard rock cutting, laying of different dia UPVC pipe line for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 10) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000464/2021-2022 | 2467/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 3.06 | 2.82 | 0
559 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Damra rural and adjacent area of Chelod mouza, G.P, Tirat , GP Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 11) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000465/2021-2022 | 2468/RCD I | 31/12/2021 | 10 | GOPAL CONSTRUCTION | 4.68 | 4.68 | 0
560 | RCFA Division -I | RCFA Division I | Laying of different dia UPVC pipeline for extension system regarding FHTC work at Chelod village of Ratibati W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000488/2021-2022 | 2464/RCD-I | 31/12/2021 | 15 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.81 | 2.35 | 0
561 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia PVC/HDPE pipe line for extension of distribution system regarding FHTC work at Ratibati Mouza of Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000558/2021-2022 | 581/RCD-I | 02/03/2022 | 15 | SOMNATH SAMANTA | 9.58 | 9.55 | 0
562 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Chelod village area (Part-A) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000601/2021-2022 | 278/RCD-I | 01/02/2022 | 30 | M/S MONDAL CONSTRUCTION | 4.84 | 4.55 | 0
563 | RCFA Division -I | RCFA Division I | Laying of Different dia UPVC /PVC pipeline for extention of distribution system regarding FHTC work at Saora Mouza of Ratibati Water supply Scheme under RCFA Div-I PHE Dte. (Sl No 17) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000602/2021-2022 | 280/RCD-I | 01/02/2022 | 30 | A. CONSTRUCTION CO. | 4.81 | 4.81 | 0
564 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Chelod village area (Part-B) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000606/2021-2022 | 279/RCD-I | 01/02/2022 | 30 | M/S U.G. ENTERPRISE | 4.84 | 4.84 | 100
565 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE pipe line for byepass water supply arrangement to Chapui village under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A)(Sl no 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000608/2021-2022 | 631/RCD-1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.75 | 4.75 | 0
566 | RCFA Division -I | RCFA Division I | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-B)(Sl no 3) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000609/2021-2022 | 632/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.76 | 4.72 | 0
567 | RCFA Division -I | RCFA Division I | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-C)(Sl no 04) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000610/2021-2022 | 633/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.84 | 4.82 | 0
568 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Interconnection work including Augurboring, supply of value, construction of valve, construction of valve chamber within command under Dabor OHR under Retrofitting of 4 Nos. PWSS for providing FHTC under RCFA Division-I PHE Dte (sl. no-6). | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000772/2022-2023 | 804/RCD-I | 06/03/2023 | 10 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 12.51 | 12.28 | 0
569 | RCFA Division -I | RCFA Division I | Acceptance cum work order Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000924/2022-2023 | 1257/RCD-I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.31 | 4.15 | 0
570 | RCFA Division -I | RCFA Division I | Acceptance cum work order Supplying Laying 90 mm dia HDPE pipe line, sluice valve chamber, Street Stand Post and other allied works within Amritnagar Rising Main & Distribution of Tirat Colliery W/S Scheme Zone under Improvement Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000943/2022-2023 | 1279/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.81 | 4.8 | 0
571 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Street Stand Post, Sluice Valve Chamber and Aligning Laying HDPE pipe in different places (Nimcha, Damra, Chelod Bouripara, Tirat Hospital Etc.) under Tirat Colliery W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000944/2022-2023 | 1281/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.57 | 4.57 | 80
572 | RCFA Division -I | RCFA Division I | Acceptance cum work order 300 mm dia MS Bye pass line and interconnection work at Khandra OHR site and allied works of Dakhin Khandra and Mahira adjacent area under Retrofitting of 4 Nos. Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000957/2022-2023 | 1056/RCD-I | 23/03/2023 | 15 | UNITED CONSTRUCTION | 15.47 | 15.47 | 0
573 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | RTOR000009/2021-2022 | 439/RCD-I | 21/02/2022 | 0 | Resource Division | 11 | 0 | 0
574 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | RTOR000011/2025-2026 | 2533/RCD-I | 01/09/2025 | 0 | Resource Division | 17.96 | 0 | 0
575 | RCFA Division -I | RCFA Division I | Repairing of 6 (Six) nos panel board, panel board wiring, Supply and installation of 10 HP submersible pump & motor & cable laying & other allied works at Ratibati river bed pump house site of Ratibati W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | VCH/000069/2022-2023 | 172/22-23 | 13/06/2022 | 0 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0
576 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Dhandardihi Mouza, vill-Madanpur, Block -Andal of Dhandadihi Water supply scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | VCH/000832/2020-2021 | 45/21-22 | 15/07/2021 | 0 | MACHINO TECHNO | 25.79 | 0 | 0
577 | RCFA Division -I | Asansol Mechanical Division | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and barabani (BBI) station of Asansol Division, Eastern Railway | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00011/2023-2024 | 30/23-24 | 03/05/2023 | 0 | EASTERN RAILWAY | 0.53 | 0 | 0
578 | RCFA Division -I | Asansol Mechanical Division | DEPOSITION OF WAY LEAVE FEE (ER-ASN-2023-WL-17) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00017/2023-2024 | 41/23-24 | 10/05/2023 | 0 | EASTERN RAILWAY | 5.37 | 0 | 0
579 | RCFA Division -I | Asansol Mechanical Division | June 2022 to Novemeber & December 2022 to Feburary 2023 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00030/2023-2024 | 19/23-24 | 18/04/2023 | 0 | PRASENJIT DEY | 3.6 | 0 | 0
580 | RCFA Division -I | Asansol Mechanical Division | Restoration amount for unauthorised execavation and damaged at Ethora Nuni Road [Road connecting FR 10 and FR 19 (FR 13) under Asansol highwa | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00039/2022-2023 | Asn-Highway-PWD | 11/01/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 10.45 | 0 | 0
581 | RCFA Division -I | Asansol Mechanical Division | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and Barabani stan (BBI) km post 25/02-25/03 of Asansol Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00058/2023-2024 | 65/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 4.63 | 0 | 0
582 | RCFA Division -I | Asansol Mechanical Division | Deposition of way leave fee for pipeline crossing of Railway track in between Salanpur (SLS) and Rupnarayanpur (RNPR) km post 23/15-17 to 231/16-18 of Asansol Division, Eastern Railway | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00059/2023-2024 | 64/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 5.12 | 0 | 0
583 | RCFA Division -I | Asansol Mechanical Division | Desposition of way leave Fees for Railway crossing for pipeline. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00147/2022-2023 | 947/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 5.04 | 0 | 0
584 | RCFA Division -I | Asansol Mechanical Division | Deposition of way leave Fees for Railway crossing for pipeline. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00150/2022-2023 | 946/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 6.08 | 0 | 0
585 | RCFA Division -I | Asansol Mechanical Division | ER-ASN-2023-WL-28 (Salanpur SLS to Rupnarayanpur RNPR) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00278/2023-2024 | 130/23-24 | 10/07/2023 | 0 | EASTERN RAILWAY | 5.7 | 0 | 0
586 | RCFA Division -I | Asansol Mechanical Division | fuel bill For WB 37D 0482 Nov 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00432/2022-2023 | 821/22-23 | 20/01/2023 | 0 | RANAJIT AUTO | 0.27 | 0 | 0
587 | RCFA Division -I | Asansol Mechanical Division | Hiring of Maxi Cab (Non Air-conditioned) Bharat Stage-II/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. for the Office use of the Assistant Engineer, RCFA Division-I, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.07.2022 to 30.06.2023)(sl no 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00703/2022-2023 | 1210/22-23 | 31/03/2023 | 0 | NIRMALA TRADERS | 2.8 | 0 | 0
588 | RCFA Division -I | Asansol Mechanical Division | Vehicle bill | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00704/2022-2023 | 1166/22-23 | 31/03/2023 | 0 | KHEPI MAA TRADERS | 2.21 | 0 | 0
589 | RCFA Division -I | Asansol Mechanical Division | VEHICLE BILL | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00705/2022-2023 | 1165/22-23 | 30/03/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0
590 | RCFA Division -I | Asansol Mechanical Division | IT GST FILLING | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00706/2022-2023 | 1206/22-23 | 30/03/2023 | 0 | SHRESTHA & ASSOCIATES | 0.5 | 0 | 0
591 | RCFA Division -I | Asansol Mechanical Division | VEHICLE BILL | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00707/2022-2023 | 1113/22-23 | 30/03/2023 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0
592 | RCFA Division -I | Asansol Mechanical Division | Supply of computer for Assistant Enginner-II | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00708/2022-2023 | 944/22-23 | 30/03/2023 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0
593 | RCFA Division -I | Asansol Mechanical Division | Engagement of 01 (One) no person under control of 2 (Two) nos AE/RCFA Div-I day to day report and return of FHTC as per scheme wise panchayet wise and updation of JJm | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00761/2023-2024 | 320/23-24 | 16/10/2023 | 0 | MUKHERJEE TRADERS | 0.49 | 0 | 0
594 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Div-I PHE Dte. (Part B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000001/2022-2023 | 931/RCD-I | 26/04/2022 | 736 | M/S MONDAL ENTERPRISE | 82.94 | 61.98 | 100
595 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000002/2022-2023 | 932/RCD-I | 26/04/2022 | 615 | DIP CONSTRUCTION | 61.83 | 51.53 | 100
596 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000003/2022-2023 | 933/RCD-I | 26/04/2022 | 90 | M/S K & KONAR CONSTRUCTION | 75.35 | 69.5 | 90
597 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000004/2022-2023 | 934/RCD-I | 26/04/2022 | 90 | SRI KRISHNA ENTERPRISE | 86.98 | 30.45 | 65
598 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000005/2022-2023 | 935/RCD-I | 26/04/2022 | 90 | KHEPI MAA TRADERS | 71.89 | 67.45 | 75
599 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000006/2022-2023 | 936/RCD-I | 26/04/2022 | 90 | M/S MONI TRADERS | 75.17 | 40.2 | 70
600 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing of 600mm dia ms water Carrer pipe and road Crossing by adopting trenchless technology at Dendua more to Kalyaneswri road of improvement of RCFA Part-I in connection of rasing main (part-A) under RCFA Division-I PHE Dte.(Sl No. 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000007/2023-2024 | 1405/RCD-1 | 12/04/2023 | 357 | MD AAMIR KHAN | 90.31 | 68.18 | 100
601 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-B) (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000010/2022-2023 | 1006/RCD-I | 05/05/2022 | 60 | M/S SANTANU PALIT & CO. | 93.2 | 0 | 70
602 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-D) (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000011/2022-2023 | 1007/RCD-I | 05/05/2022 | 90 | GITASREE FABRICATION | 77.41 | 66.72 | 85
603 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000012/2022-2023 | 1020/RCD-I | 06/05/2022 | 180 | SWATI CORPORATION | 149.9 | 63.87 | 85
604 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 58.28 | 100
605 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000014/2022-2023 | 1039/RCD-I | 10/05/2022 | 1179 | DAS & CHAKRABORTY | 130.86 | 56.55 | 100
606 | RCFA Division -I | Asansol Mechanical Division | Formal Work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000016/2022-2023 | 1073/RCD-I | 13/05/2022 | 719 | MD AAMIR KHAN | 115.25 | 75.01 | 90
607 | RCFA Division -I | Asansol Mechanical Division | Formal work order for 200 mm, 160 mm & 90 mm dia HDPE PE-80 distribution network of RCFA Part-I Water Supply Scheme command area of Zone-IX under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000034/2023-2024 | 1612/RCD I | 25/04/2023 | 90 | KHEPI MAA TRADERS | 149.55 | 53.69 | 90
608 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line within distribution network within command are of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000036/2023-2024 | 1610/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 114.21 | 98.16 | 86
609 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-IX under RCFA Division-I PHE Dte. (Part C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000095/2022-2023 | 1213/RCD-I | 30/05/2022 | 1281 | T M CONCRETE CREATION PRIVATE LIMITED | 131.44 | 108.9 | 65
610 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000096/2022-2023 | 1214/RCD-I | 30/05/2022 | 90 | RANJIB GHATAK | 100.72 | 90.61 | 90
611 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII with LDS & FHTC Work | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000105/2022-2023 | 1329/RCD-I | 09/06/2022 | 180 | SWATI CORPORATION | 399.2 | 327.2 | 100
612 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of drain at Dabor mouzas under RCFA Part-I W/S Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000106/2023-2024 | 1865/RCD-1 | 01/06/2023 | 60 | TARA CONSTRUCTION | 10.11 | 10 | 85
613 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of 1 (One) no. Chlorine Room including Plinth protection, drain for 900 cum and 250 cum OHR at Baliapur under Improvement of RCFA (Part-I) Piped Water Supply Scheme. under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000115/2024-2025 | 2138/RCD-I | 27/08/2024 | 60 | AMAR CONSTRUCTION | 9.01 | 0 | 100
614 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000117/2022-2023 | 1379/RCD-I | 17/06/2022 | 180 | MRITYUNJOY MUKHERJEE & CO. | 466.46 | 346.89 | 80
615 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000119/2022-2023 | 1605/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 78.73 | 37.76 | 80
616 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000124/2022-2023 | 1610/RCD-I | 06/07/2022 | 990 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 64.62 | 18.73 | 100
617 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 16.36 | 75
618 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000126/2022-2023 | 1612/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 60.85 | 21.88 | 65
619 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000127/2022-2023 | 1613/RCD-I | 06/07/2022 | 90 | KONAR CONSTRUCTION | 64.73 | 23.94 | 75
620 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000128/2022-2023 | 1614/RCD-I | 06/07/2022 | 90 | TARA CONSTRUCTION | 88.3 | 43.84 | 70
621 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-7 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000130/2022-2023 | 1702/RCD-I | 14/07/2022 | 45 | UNITED CONSTRUCTION | 20.25 | 19.99 | 5
622 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-9 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000131/2022-2023 | 1703/RCD-I | 14/07/2022 | 45 | SOMNATH SAMANTA | 28.67 | 0 | 5
623 | RCFA Division -I | Asansol Mechanical Division | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 2.35 | 0
624 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-5 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000158/2022-2023 | 1707/RCD-I | 14/07/2022 | 45 | M/S B.K. CONSTRUCTION | 32.05 | 20.27 | 100
625 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Laying & Pushing of 600 mm dia MS Water Carrier pipe and road Crossing by adopting trench less technology at Dendua more to Kalyaneswari road of Improvement of RCFA Part-I in connection of rising main (Part-A) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000158/2023-2024 | 1883/1/RCD-I | 07/06/2023 | 15 | MD AAMIR KHAN | 66.19 | 66.19 | 0
626 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Rupnarayanpur OHR of Capacity 1135 cum staging height 20 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000163/2021-2022 | 1588/RCD-I | 07/09/2021 | 30 | BKB INFRA PROJECTS PVT LTD | 37.48 | 37.45 | 0
627 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-8 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000163/2022-2023 | 1712/RCD-I | 15/07/2022 | 45 | SIMA ENTERPRISE | 24.13 | 0 | 5
628 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 Nos. location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000164/2023-2024 | 1911/RCD-I | 14/06/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 19.62 | 15.26 | 80
629 | RCFA Division -I | Asansol Mechanical Division | Hiring of maxi cab (Non-airconditioned)Bharat stage-II/BS-II purchased on or after 01.05.2008 with diesel/LPG/CNG engine for the office use of the Assistant Engineer, RCFA Div-I, PHE dte, Govt of West Bengal (w.e.f 01.09.2021 to 31.08.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000194/2021-2022 | 1541/RCD I | 31/08/2021 | 365 | KHEPI MAA TRADERS | 1.73 | 1.14 | 0
630 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-VI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000205/2022-2023 | 1874/RCD-I | 04/08/2022 | 12 | KAMIRUL SK & CO | 76.6 | 68.94 | 100
631 | RCFA Division -I | Asansol Mechanical Division | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman (Sl No. 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000207/2022-2023 | 1908/RCD-I | 12/08/2022 | 7 | SHARMA ENGINEERING WORKS | 1.3 | 1.3 | 0
632 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for the laying of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000207/2023-2024 | 2208/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 12.78 | 11.55 | 100
633 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000217/2023-2024 | 2211/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 19.71 | 11.22 | 60
634 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines and Supplying Aligning Laying MS pipe (including carring loading & unloading at work site) Head Works Site (node point R1-1) and Lalganj Hat of Improvement RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000223/2023-2024 | 2246/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 17.17 | 15.58 | 100
635 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000225/2023-2024 | 2247/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 10.06 | 9.8 | 100
636 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work laying of 180 mm dia HDPE pipe line at Alladi More to Jemnari Bus Stand and Railway crossing at Rupnarayanpur village in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of (Zone-V) with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000227/2023-2024 | 2212/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 54.74 | 10.58 | 100
637 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000229/2023-2024 | 2248/RCD-1 | 17/07/2023 | 30 | SWATI CORPORATION | 12.73 | 9.93 | 80
638 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 3 (Three) nos. location at Lalganj Domohani Road under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000234/2023-2024 | 2230/RCD-I | 17/07/2023 | 30 | R B ENTERPRISE | 42.66 | 26.2 | 65
639 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000236/2023-2024 | 2216/RCD-I | 17/07/2023 | 30 | SIMA ENTERPRISE | 16.68 | 15.96 | 100
640 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Gowalabathan More towards Jamuria Road, Gowala para more towards Domohani Village, Goshala More towards Domohani village under Improvement of RCFA Part-I (Zone-11, Part-5) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000239/2023-2024 | 2232/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 19.77 | 19.76 | 100
641 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Kelejhora Health Centre More under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000242/2023-2024 | 2233/RCD-I | 17/07/2023 | 30 | SNEHA ELECTRIC | 29.11 | 16.38 | 55
642 | RCFA Division -I | Asansol Mechanical Division | Acceptation cum work order for Additional work for allied work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000246/2023-2024 | 2254/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 99.31 | 71.44 | 100
643 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for laying of 200 mm dia Rising Main under Lalganj Bridge by concrete conduit and allied MS work including adopting trench less technology (e.g. Jack Pushing Method etc) of 04 (Four) nos. location at Barabani & near Kelejora Health Centre in connection to rising main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000248/2023-2024 | 2235/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 50.86 | 50.09 | 100
644 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000250/2023-2024 | 2239/RCD-I | 17/07/2023 | 259 | MRITYUNJOY MUKHERJEE & CO. | 88.68 | 0 | 100
645 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dabor More (250 mm dia Water Carrier 02 nos) and Dendua road to Chittaranjan road 01 no 450 mm dia Water Carrier and 02 nos 450 mm dia Water Carrier Pipe on Bonjemary Road of Salanpur Block under Improvement of RCFA Part-I (Part-A Rising Main) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000249/2023-2024 | 2236/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 51.47 | 51.44 | 100
646 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000252/2023-2024 | 2238/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 39.57 | 24.47 | 100
647 | RCFA Division -I | Asansol Mechanical Division | Construction of 450 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at Barabani (Zone-XIII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman [Rf Drwaing no. PC-I/OHR/04/2012(Sheet 1& 2) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000291/2022-2023 | 2448/RCD-I | 13/10/2022 | 365 | JOY HIND TUBEWELLS | 122.44 | 122.44 | 0
648 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Urgent basis repairing work of Churulia OHR of capacity 100000 gallons and 20 mtr staging height under Churulia Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000293/2021-2022 | 2025/RCD-I | 24/11/2021 | 30 | ASHA CONSTRUCTION | 15.47 | 15.33 | 0
649 | RCFA Division -I | Asansol Mechanical Division | Distribution Network for Improvement of RCFA Part-II Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000294/2022-2023 | 2451/RCD-I | 13/10/2022 | 180 | SINGHA ROY & CO. | 270.57 | 65.85 | 0
650 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for the laying of DI pipe, MS work, making valve chamber and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000295/2023-2024 | 2366/RCD-I | 04/08/2023 | 30 | SNEHA ELECTRIC | 51.75 | 50.2 | 98
651 | RCFA Division -I | Asansol Mechanical Division | Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone VII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000298/2022-2023 | 2453/RCD-I | 13/10/2022 | 365 | SINGHA ROY & CO. | 181.16 | 181.16 | 100
652 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order of Construction of CWR (Clear Water Reservoir) of Capacity 500 cum and allied work at Dendua under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000302/2022-2023 | 2484/RCD I | 18/10/2022 | 120 | D.S. ENTERPRISE | 61.78 | 43.72 | 96
653 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Construction of 350 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-IX) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000324/2022-2023 | 2403/RCD-I | 30/09/2022 | 365 | MALLICK ENTERPRISE | 107.64 | 107.64 | 95
654 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-F) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000327/2022-2023 | 2404/RCD-I | 30/09/2022 | 180 | GITA CONSTRUCTION | 201.57 | 131.66 | 67
655 | RCFA Division -I | Asansol Mechanical Division | Formal Work Oder for Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-XI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000380/2022-2023 | 2005/RCD-I | 25/08/2022 | 365 | AMAR CONSTRUCTION | 181 | 162.9 | 100
656 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Malbahal OHR site of Improvement of RCFA Part-I Piped Water Supply Scheme under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000431/2023-2024 | 2662/RCD-I | 26/09/2023 | 583 | AMAR CONSTRUCTION | 35.5 | 0 | 100
657 | RCFA Division -I | Asansol Mechanical Division | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022) (Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000453/2021-2022 | 2456/RCD I | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 0
658 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000490/2021-2022 | 376/RCD-I | 15/02/2022 | 30 | MD AAMIR KHAN | 22.72 | 10.42 | 100
659 | RCFA Division -I | Asansol Mechanical Division | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000530/2022-2023 | 3143/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 100
660 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000531/2021-2022 | 491/RCD-I | 24/02/2022 | 90 | R B ENTERPRISE | 27.59 | 26.92 | 85
661 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000532/2021-2022 | 492/RCD-I | 24/02/2022 | 90 | SNEHA ELECTRIC | 25.78 | 25.39 | 75
662 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-3 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000533/2021-2022 | 493/RCD-I | 24/02/2022 | 401 | VISUVIOUS | 25.41 | 23.7 | 100
663 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000536/2021-2022 | 494/RCD-I | 24/02/2022 | 1042 | DAWN CONSTRUCTION | 68.87 | 65.56 | 100
664 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000538/2021-2022 | 495/RCD-I | 24/02/2022 | 1101 | M/S B.K. CONSTRUCTION | 44.11 | 37.17 | 100
665 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-6 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000541/2021-2022 | 496/RCD-I | 24/02/2022 | 1087 | UMA ENTERPRISE | 63.83 | 50.69 | 70
666 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000542/2021-2022 | 497/RCD-I | 24/02/2022 | 90 | UNITED CONSTRUCTION | 23.75 | 23.72 | 80
667 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000543/2021-2022 | 498/RCD-I | 24/02/2022 | 90 | SIMA ENTERPRISE | 30.98 | 29.26 | 81
668 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-9 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000544/2021-2022 | 499/RCD-I | 24/02/2022 | 90 | SOMNATH SAMANTA | 39.28 | 38.73 | 98
669 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) of Water Pipe Lines including supplying and laying of 400 mm dia MS Pipe line at Alladi More on Sitarampur Chittaranjan Road in connection to rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000580/2022-2023 | 3288/RCD I | 20/12/2022 | 15 | MAK CONSTRUCTION CO. | 16.45 | 16.38 | 0
670 | RCFA Division -I | Asansol Mechanical Division | Laying of Rising Main (Part-B) at Mohismura Culvat crossing by constructing concrete piller, MS work and allied works under Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000581/2022-2023 | 3289/RCD I | 20/12/2022 | 17 | M/S MONDAL ENTERPRISE | 10.26 | 8.52 | 100
671 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for dedicated bypass line from Prantapally Durga Mandir to Kalyan Gram under Jitpur Uttarrampur GP under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000584/2022-2023 | 3292/RCD I | 20/12/2022 | 15 | ASHA CONSTRUCTION | 11.77 | 11.48 | 0
672 | RCFA Division -I | Asansol Mechanical Division | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000595/2022-2023 | SpotNIQ.Camp-02/Office/AE | 31/05/2022 | 183 | PRASENJIT DEY | 0.9 | 0 | 0
673 | RCFA Division -I | Asansol Mechanical Division | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000596/2022-2023 | Spot/NIQ/Camp-02/Office/A | 31/05/2022 | 6 | PRASENJIT DEY | 0.9 | 0 | 0
674 | RCFA Division -I | Asansol Mechanical Division | Repalcing of old and damaged C.I. spiral stairs and other allied minor repairing works at Panchgachia OHR (Capacity 55000 gallon staging height 10 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte.(Sl no 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000612/2021-2022 | 635/RCD 1 | 09/03/2022 | 15 | RUBY CONSTRUCTION | 3.87 | 3.83 | 0
675 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Urgent basis repairing work of D P Colony (OHR) at D P Colony W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000618/2021-2022 | 712/RCD-I | 24/03/2022 | 30 | RUBY CONSTRUCTION | 15.72 | 15.13 | 0
676 | RCFA Division -I | Asansol Mechanical Division | Acceptance work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 450 mm dia MS pipe line at Mohismura More on NH Madhaichak Road in connection to rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000643/2022-2023 | 341/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 8.69 | 8.51 | 0
677 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Samdi and surrounding villages within Samdi Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000653/2023-2024 | 3450/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.39 | 3.35 | 100
678 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VI) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000658/2022-2023 | 357/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 3.75 | 100
679 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 450 mm dia MS Pipe Line at Hunuman Mandir on Mohismura Ethora Road near Ethora OHR inconnection to rising main (Part-B) under Augmentation of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000676/2022-2023 | 360/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 11.17 | 11.09 | 0
680 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Different dia HDPE pipe line including extra cutting Laterate /sandstone and concrete cutting of distribution of pipe line Zone-I (Part-B) at Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000682/2022-2023 | 370/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 25.76 | 11.14 | 95
681 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000686/2022-2023 | 374/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.75 | 3.69 | 0
682 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000687/2022-2023 | 375/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.12 | 3.07 | 0
683 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply and delivery of CI sluice valve and C.I/D.I specials under improvement of RCFA part-I piped water supply scheme under RCFA div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000701/2022-2023 | 613/RCD I | 23/02/2023 | 10 | MAKALI ENGINEERING CORPORATION | 28.49 | 28.49 | 0
684 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Blower Room, Concrete Platform Drain, Approach Road and Boundary Wall and other allied works at Dhobaru Head Works Site under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000707/2024-2025 | 453/RCD-I | 12/03/2025 | 90 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 91.8 | 0 | 58
685 | RCFA Division -I | Asansol Mechanical Division | Accepatance cum work order for construction of chlorine room of size (4.50 X 3.50m) at (Zone-IX) of Baraboni Block for Improvement of RCFA Part-I piped water supply scheme under RCFA Div-I, PHE Dte., in the District Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000737/2022-2023 | 676/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 2.91 | 100
686 | RCFA Division -I | Asansol Mechanical Division | Additional extra cutting laterate/sandstone of distribution network for improvement of Part-I W/S Scheme within command area of Zone VII under RCFA Div-I, PHE Dte(Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000747/2022-2023 | 695/RCD I | 02/03/2023 | 7 | TARA CONSTRUCTION | 0.83 | 0.79 | 0
687 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying aligning and laying of HDPE Pipe line for restoration of pipe line towards MSPL at Kalyaneswari Dendua Road and supplying CI/DI specials in connection to aligning of rising main Part-A for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000762/2022-2023 | 389/RCD I | 30/01/2023 | 10 | MD AAMIR KHAN | 21.01 | 20.7 | 0
688 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Panchagachia OHR of Capacity 1000 cum staging height 15 mtr under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000777/2022-2023 | 399/RCD I | 30/01/2023 | 90 | RUBY CONSTRUCTION | 20.33 | 11.62 | 100
689 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work for laying of distribution network for Improvement RCFA Part-I Piped Water Supply Scheme within command area of Zone-XI (Part-9 Distribution Segment) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000831/2022-2023 | 1035/RCDI | 23/03/2023 | 376 | SOMNATH SAMANTA | 42.19 | 20.02 | 100
690 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for the additional work for the laying of different dia (315 mm , 280 mm, 225 mm ) dia HDPE pipe instead of different dia (300 mm , 250 mm, 200 mm) dia DJ pipe of distribution network for improvement RCA Part-I Water Supply Scheme within command area of Zone VI under RCFA Div-I, PHE Dte (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000832/2022-2023 | 1051/RCD I | 23/03/2023 | 30 | DIP CONSTRUCTION | 98.08 | 89.82 | 100
691 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional dedicated line to Sen Raleigh (Block-B) under Panchgachiya Distribution zone including laying of UPVC pipe line and allied works under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000833/2022-2023 | 1054/RCD I | 23/03/2023 | 15 | RUBY CONSTRUCTION | 11.13 | 11.11 | 0
692 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 nos location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000837/2022-2023 | 1065/RCD-I | 23/03/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 45.79 | 45.79 | 50
693 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Dismanting of existing Drain and reconstruction the same, Construction of RCC pipe carring structur and other allied work at Alladih more and Rupnarayanpur Railway Station Site of improvement of RCFA Part -I in Connection of Rising main Part-A under RCFA Division-I PHE Dte.(Sl No. 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000838/2022-2023 | 1066/RCD I | 23/03/2023 | 30 | MAK CONSTRUCTION CO. | 31.64 | 29.75 | 100
694 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 500 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 200 mm dia 250 mm dia MS pipe line at different location on Asansol Chittanrajan Road, Kalyaneswari Dendua road within command area of rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000834/2022-2023 | 1060/RCD-I | 23/03/2023 | 15 | MAK CONSTRUCTION CO. | 40.5 | 39.62 | 100
695 | RCFA Division -I | Asansol Mechanical Division | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022)(Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000838/2021-2022 | 2456/RCD- 1 | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 0
696 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of drain at Ethora and its adjoining mouzas under Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000849/2022-2023 | 1086/RCD-I | 23/03/2023 | 60 | SWATI CORPORATION | 23.95 | 23.94 | 0
697 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines at Sandi More (Node point 137) Sandi Masimura More (Node point 85) and Lalganj Domhani Road (Node point 5-26) under Augmentation of RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000857/2022-2023 | 1093/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 19.65 | 19.65 | 0
698 | RCFA Division -I | Asansol Mechanical Division | Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 500 mm dia and 150 mm dia MS pipe line at different location on Asansol Chittaranjan Road within command area of Zone-I (Dendua OHR) Distribution system (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000861/2022-2023 | 1095/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 25.75 | 25.59 | 0
699 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. jack Pushing Method etc) of Water Pipe Lines at Dabor More (Node point 334) Youth club (Node point 398) and Jaya hotel (Node point 228) Augmentation of RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) (Sl No. 28) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000862/2022-2023 | 1094 / RCD-I | 23/03/2023 | 30 | TARA CONSTRUCTION | 23.59 | 23.59 | 0
700 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000874/2022-2023 | 1134/RCD-I | 24/03/2023 | 30 | M/S K & KONAR CONSTRUCTION | 30.49 | 19 | 100
701 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000875/2022-2023 | 1136/RCD-I | 24/03/2023 | 30 | DAWN CONSTRUCTION | 56.15 | 31.27 | 90
702 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000878/2022-2023 | 1138/RCD-I | 24/03/2023 | 30 | UNITED CONSTRUCTION | 24.64 | 17.12 | 90
703 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Lalganj more and Nuni more in related to laying of rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000883/2022-2023 | 1127/ RCD I | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 23.75 | 23.62 | 0
704 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCAF Division-I PHE Dte. (Part-C) (Sl. No. 17) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000893/2022-2023 | 1143/ RCD I | 24/03/2023 | 30 | RANJIB GHATAK | 26.19 | 12.65 | 90
705 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) under RCAF Division-I PHE Dte. (SL No. 16) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000895/2022-2023 | 1142/ RCD I | 24/03/2023 | 283 | UMA ENTERPRISE | 76.17 | 32.7 | 100
706 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Road crossing by open cut near to Nuni more including construction of drain, laterite cutting, concrete and bitumen road cutting and allied works at Ethora and adjacent area for laying of Rising Main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000898/2022-2023 | 1152/RCD-1 | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 5.09 | 4.7 | 100
707 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Dismantling of existing guard room and store room for construction of 500 cum CWR at Dendua Boosting station of Improvement of RCFA Part-I under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000901/2022-2023 | 1153/RCD-1 | 24/03/2023 | 10 | D.S. ENTERPRISE | 1.02 | 1.02 | 0
708 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000939/2021-2022 | 376_RCD_I | 15/02/2022 | 30 | MD AAMIR KHAN | 0 | 0 | 0
709 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine, for the office Use of the Executive Engineer, RCFA Division-I PHE Dte. (w.e.f. 01.12.2022 to 31.05.2023) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000955/2022-2023 | 3057/RCD-I | 30/11/2022 | 182 | PRASENJIT DEY | 0.9 | 0 | 0
710 | RCFA Division -I | Asansol Mechanical Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/001164/2023-2024 | Camp-02-Wall-Writing-AE-I | 18/01/2024 | 30 | MUKHERJEE TRADERS | 6.61 | 6.59 | 100
711 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of RCC column and M.S Structural Bridge for laying of 200 m dia MS pipe and other allied work for distribution network for Improvement of RCFA Part-I water supply scheme within command area of Zone-VII under RCFA Division ¿I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/001172/2023-2024 | 1012/RCD-I | 16/03/2024 | 30 | UNITED CONSTRUCTION | 6.54 | 6.47 | 100
712 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000002/2023-2024 | 1637/RCD-I | 27/04/2023 | 0 | Resource Division | 127.23 | 0 | 0
713 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000005/2021-2022 | 301/RCD-I | 02/02/2022 | 0 | Resource Division | 676.57 | 0 | 0
714 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000006/2021-2022 | 392/RCD-I | 16/02/2022 | 0 | Resource Division | 2340.25 | 0 | 0
715 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000008/2022-2023 | 2352/RCD-I | 28/09/2022 | 0 | Resource Division | 92.4 | 0 | 0
716 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000011/2021-2022 | 677/RCD-I | 21/03/2022 | 0 | Resource Division | 57.29 | 0 | 0
717 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000013/2022-2023 | 2644/RCD-I | 28/10/2022 | 0 | Resource Division | 64.5 | 0 | 0
718 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000015/2022-2023 | 2626/RCD-I | 17/11/2022 | 0 | Resource Division | 27.66 | 0 | 0
719 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000028/2022-2023 | 19/RCD-I | 05/01/2023 | 0 | Resource Division | 121.92 | 0 | 0
720 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000030/2022-2023 | 54/RCD-I | 11/01/2023 | 0 | Resource Division | 180.92 | 0 | 0
721 | RCFA Division -I | Asansol Mechanical Division | Payment for sample PT test bill no 376/21-22 dt. 25.06.2021 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000011/2022-2023 | 545/22-23 | 01/11/2022 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0
722 | RCFA Division -I | Asansol Mechanical Division | Hire charges bill for vehicle no WB 37 D 0482 for the month of March 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000121/2022-2023 | 518/22-23 | 29/09/2022 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0
723 | RCFA Division -I | Asansol Mechanical Division | Submission of Quarterly regular return for non-salary 26Q3 & 26Q4 Regular Return for Salary 24Q3 & 24Q4 for the F.Y 2021-2022 and creation of Form 16 Part A & B 26Q2 for the F.Y 202021-22 Revised return for non salary return for the quarter 26Q3 & 26Q4 for the financial 2021-22 includes GST return for the month of April 2021 to March 2022 and April 2022 to May 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000366/2022-2023 | 383/22-23 | 17/08/2022 | 0 | SHRESTHA & ASSOCIATES | 0.58 | 0 | 0
724 | RCFA Division -I | Asansol Mechanical Division | Payment for furniture | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000668/2022-2023 | 433/22-23 | 21/09/2022 | 0 | VYAS & CO. | 2.35 | 0 | 0
725 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for Enhanacement of Load at Dendua. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00027/2023-2024 | BP-2023-24-9 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.88 | 0 | 0
726 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for New Connection of Load at Tabadi (Adibasi Para) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00028/2023-2024 | BP-2023-24-9 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0
727 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for New Connection of Load at Dhonudi. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00029/2023-2024 | BP-2023-24-10 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.34 | 0 | 0
728 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for New Connection of Load at Lalganj | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00030/2023-2024 | BP-2023-24-11 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0
729 | Asansol Mechanical | Asansol Mechanical Division | Quotation for Earnest money deposit for Bulk Power Supply at Ethora boosting Station Under Improvement of RCFA Part I WS Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00452/2023-2024 | BP-2023-24-31 | 13/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
730 | Asansol Mechanical | Asansol Mechanical Division | Meter Shifting Charge of Ethora Water tank under Improvement of RCFA (Part-I) Piped Water Supply Scheme | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00564/2023-2024 | BP-2023-24-53 | 29/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0
731 | Asansol Mechanical | Asansol Mechanical Division | Shifting of High Tension Line and Street Light from the Proposed WTP plant area in Kalyaneswari Campus under Improvement of RCFA I Water Supply Scheme | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00682/2023-2024 | BP-2023-24-59 | 26/12/2023 | 0 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 0.24 | 0 | 0
732 | Asansol Mechanical | Asansol Mechanical Division | Service connection and Security Deposit charge at Ethora Boosting Station under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00778/2023-2024 | BP-2023-24-67 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 25.69 | 0 | 0
733 | Asansol Mechanical | Asansol Mechanical Division | Additional quotation for drawl of HT line to avoid ROW issue for Ethora Boosting Station under Improvement of RCFA Part-I Water supply scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/01137/2024-2025 | BP-2024-25-96 | 28/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.74 | 0 | 0
734 | Asansol Mechanical | Asansol Mechanical Division | Additional Electrical and illumination works and installation of 1 Ton Capacity mono rail at Dendua Boosting Station Pump House, under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000028/2025-2026 | 948/AMD | 16/05/2025 | 30 | EASTERN INDIA SALES AND SERVICE | 7.91 | 0 | 100
735 | Asansol Mechanical | Asansol Mechanical Division | Installation of yard lighting arrangement, electrical wiring of chlorine room with lighting luminaries of Tabadi O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000034/2025-2026 | 954/AMD | 16/05/2025 | 202 | P.K.ENGINEERING | 4.23 | 0 | 100
736 | Asansol Mechanical | Asansol Mechanical Division | Installation of yard lighting arrangement, electrical wiring of chlorine room of Lalganj O.H.R.(Zone-IX & XI) premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000037/2025-2026 | 956/AMD | 16/05/2025 | 202 | P.K.ENGINEERING | 7.92 | 0 | 100
737 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous chlorination system at Malladi OHR Site under Augmentation of RCFA Part-I Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000056/2025-2026 | 992/AMD | 23/05/2025 | 30 | P.K.ENGINEERING | 28.7 | 0 | 0
738 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Dendua Pump House under Improvement R.C.F.A. PART-I Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000067/2024-2025 | 1198/AMD | 07/08/2024 | 45 | EASTERN INDIA SALES AND SERVICE | 5.46 | 0 | 100
739 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at Dendua Boosting Station under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000414/2022-2023 | 363/AMD | 09/02/2023 | 729 | EASTERN INDIA SALES AND SERVICE | 20.86 | 18.44 | 100
740 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at OHR Site at under Zone-VI under Augmentation of RCFA Part-I Water Supply Scheme, Dist.- Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000415/2022-2023 | 364/AMD | 09/02/2023 | 930 | MAHADEV ENTERPRISE | 20.86 | 18.56 | 100
741 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-VII under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000416/2022-2023 | 365/AMD | 09/02/2023 | 1676 | ORIENTAL ENGINEERING CO. | 20.75 | 18.34 | 80
742 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-IX under Augmentation of RCFA Part-I water Supply Scheme, Block-Salanpur, Dist.- Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000417/2022-2023 | 366/AMD | 09/02/2023 | 919 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.85 | 18.55 | 100
743 | Asansol Mechanical | Asansol Mechanical Division | Providing And Installation of Electro-Mechanical Equipments and Allied Works at Dendua Boosting Station under Augmentation of RCFA Part-I Water Supply Scheme, Block-Salanpur, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000418/2022-2023 | 1951/AMD | 22/12/2022 | 771 | EASTERN INDIA SALES AND SERVICE | 129.01 | 72.34 | 100
744 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XI under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000421/2022-2023 | 418/AMD | 16/02/2023 | 919 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 20.56 | 18.28 | 100
745 | Asansol Mechanical | Asansol Mechanical Division | Providing And Installation of Electro-Mechanical Equipments and Sub-Stations Equipments at Ethora Boosting Station under Improvement of RCFA Part-I Water Supply Scheme, Block-Salanpur, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000437/2023-2024 | 2012/AMD | 06/11/2023 | 1188 | NEW ALIGNMENT | 267.24 | 181.05 | 93
746 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Ethora Boosting Station under " improvement of RCFA Part-I" Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000437/2024-2025 | 2095/AMD | 12/12/2024 | 387 | PREMNATH MITRA | 23.48 | 0 | 100
747 | Asansol Mechanical | Asansol Mechanical Division | Allied Works Corresponding to "Providing And Installation of Electro-Mechanical Equipments and Sub-Stations Equipments at Ethora Boosting Station under Improvement of RCFA Part-I Block:- Salanpur, Dist -Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000452/2024-2025 | 2121/AMD | 16/12/2024 | 142 | NEW ALIGNMENT | 8.12 | 0 | 70
748 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of Gaseous Chlorination system at OHR Site under Zone-XIII under Augmentation of RCFA Part-I water Supply Scheme, Dist.- Paschim Bardhaman. (2nd Call). | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000506/2022-2023 | 608/AMD | 03/03/2023 | 1036 | M/S SAJAHAN CHOWDHURY | 20.86 | 18.56 | 100
749 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of LT PDB Panel at Kalyaneswari Head works site under improvement of RCFA Part-I Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000751/2024-2025 | 601/AMD | 12/03/2025 | 426 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 91.78 | 0 | 75
750 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-91 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00114/2024-2025 | 47/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0
751 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-90 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00116/2024-2025 | 49/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0
752 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-18 under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00156/2024-2025 | 69/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 14.3 | 0 | 0
753 | RCFA Division -I | RCFA Division I | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-56 Payment of wayleave facility charges. | Assistant Engineer 2 | Junior Engineer | BILL/00545/2024-2025 | 272/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 6.27 | 0 | 0
754 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped Water Supply including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000003/2023-2024 | 1390/RCD I | 11/04/2023 | 90 | M/S SRI MAHADEO ENTERPRISES | 294.95 | 247.45 | 85
755 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000092/2023-2024 | 1755/RCD-I | 12/05/2023 | 90 | MAA DURGA ENTERPRISE | 4.6 | 0 | 0
756 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Raniganj Block (Zone-11) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000097/2023-2024 | 1841/RCD-I | 31/05/2023 | 366 | DAS & CHAKRABORTY | 115.95 | 104.36 | 90
757 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala more to towards Amnala village surrounding area (Zone-IX) under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000226/2023-2024 | 2228/RCD-I | 17/07/2023 | 30 | KHEPI MAA TRADERS | 13.09 | 13.09 | 100
758 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional work repairing old plaster surface, color washing, painting and R.B.T. (Reinforced Barbed Tape) Concertina fencing on wall and allied works at Kalyaneswari Inspection Bungalow under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000399/2023-2024 | 2581/RCD-I | 07/09/2023 | 15 | JYOGOMAYA ENTERPRISE | 5.71 | 5.14 | 100
759 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Ethora (779 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000535/2023-2024 | 3016/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100
760 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Pariharpur (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000536/2023-2024 | 3023/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100
761 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Amritnagar (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000543/2023-2024 | 3026/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100
762 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000556/2022-2023 | 3350/RCDI | 23/12/2022 | 770 | MOYTEC | 0.49 | 0.49 | 100
763 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 3 (Three) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at D.P Colony H/W Site for D P Colony Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2023-2024 | 3423/RCD-1 | 24/11/2023 | 15 | DURGA DAS MONDAL | 9.53 | 9.49 | 100
764 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional supplying, aligning, laying HDPE & PVC pipe line, construction of sluice valve chamber and other allied works under Tirat Mouza (Taldanga, Pathan Dhaora & Shyamdanga) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000648/2023-2024 | 3425/RCD-1 | 24/11/2023 | 30 | RUBY CONSTRUCTION | 6.78 | 6.65 | 100
765 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Trial Run for Barabani Kashidanga under Improvement of RCFA Part-I (Zone-XI) Piped W/S Scheme under RCFA Division-I PHE Dte. (180 days) | Assistant Engineer 2 | Junior Engineer | ORD/000665/2023-2024 | 3455/RCD-I | 24/11/2023 | 180 | UNITED CONSTRUCTION | 1.08 | 0 | 0
766 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying distribution main over concrete pillar including supply of rubber gusket within Zone-XI Part-I under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000676/2023-2024 | 3475/RCD-I | 28/11/2023 | 15 | R B ENTERPRISE | 4.89 | 1.86 | 100
767 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Dismantling & concrete works, Supplying, Aligning & Laying HDPE Pipe and other allied works at distribution system Network for Shyamlya in Chatrisganda Mouza under Shyamlya Gram Panchayat under Jamuria Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000701/2023-2024 | 3499/RCD-1 | 30/11/2023 | 30 | DAWN CONSTRUCTION | 45.48 | 45.02 | 100
768 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying collecting and other allied works at DP Colony PWSS under RCFA Division-I PHE Dte. Augmentation PWSS of RCFA Part-II (Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000947/2023-2024 | 505/RCD-I | 12/02/2024 | 30 | DURGA DAS MONDAL | 7.01 | 6.9 | 100
769 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for Enamel paint, painting, weather coat at treatment plant, bridge, CWR and other places for Amritnagar Zone-I under Augmentation of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000964/2023-2024 | 507/RCD-I | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 16.92 | 16.1 | 100
770 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work concrete cutting, restoration of road and allied works within command area of Zone-11 (Part-6 Distribution Segment) of under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000983/2023-2024 | 467/RCD-1 | 12/02/2024 | 20 | M/S SUBHRADEEP | 17.08 | 16.96 | 100
771 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Extension of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001120/2023-2024 | 926/RCD-I | 15/03/2024 | 20 | SIMA ENTERPRISE | 7.02 | 6.79 | 100
772 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area Zone-VII of Augmentation of RCFA Part-II (Zone-11) PWSS under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/001215/2023-2024 | 935_RCD_I | 15/03/2024 | 15 | KONAR CONSTRUCTION | 23.57 | 23.52 | 100
773 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000027/2023-2024 | 2947/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
774 | Durgapur W/S Division | Asansol Mechanical Division | Quotation money for new electric service connection at Birudiha under Birudiha piped W/s Scheme. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00063/2023-2024 | BP-2023-24-38 | 01/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0
775 | Durgapur W/S Division | Asansol Mechanical Division | New service connection charges for birudiha Water Supply scheme (TW-2) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00148/2023-2024 | BP-2023-24-89 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0
776 | Durgapur W/S Division | Asansol Mechanical Division | Dismantling of concrete road and bituminiou road and land development for constrution of 250 M3 OHR of 20 mtr staging height as per Deptt drawing ,laying alingining of rising main and provding FHTC connection of all mouzas under command area of Birudiha piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000087/2023-2024 | 722/DWSD | 11/05/2023 | 25 | M/S K.B.CONSTRUCTION | 30.05 | 29.88 | 100
777 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Birudiha piped W/s Scheme under DWSD ,PHE Dte (SL-04) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000225/2022-2023 | 1241/DWSD | 18/08/2022 | 15 | MD AAMIR KHAN | 14.75 | 14.3 | 0
778 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying distribution system ,Rising main ,constrcution of 250 M3 Reservoir with 20 mtr staing height including soil inverstigation ,construction of Pump house (5.4X3.60) with sanitary and Water supply arrangement and construction of Pump house (3.60 X 3.00 m) wiht FHTC for Birudiha piped W/s Scheme under DWSD ,PHE Dte (New Scheme). | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000250/2022-2023 | 1437/DWSD | 13/10/2022 | 365 | KHAN ENTERPRISE | 524.96 | 477.66 | 100
779 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Birudiha water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000011/2023-2024 | 1657/CMD | 06/04/2023 | 30 | MAA TARA ENTERPRISE | 21.19 | 20.56 | 100
780 | RCFA Division -I | RCFA Division I | PAYMENT OF WALEAVE PLAN & SURVEY CHARGES ER-ASN-2024-WL-10 | Assistant Engineer 2 |  | BILL/00002/2024-2025 | 03/24-25 | 18/04/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
781 | RCFA Division -I | RCFA Division I | Payment of Way leave Plan & Survey charges for track crossing proposal with Application ID ER-ASN2024-WL-18 dt 15.04.2024 | Assistant Engineer 2 |  | BILL/00012/2024-2025 | 11/24-25 | 24/04/2024 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0
782 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network & allied work at Ondal Block of RCFA Part-II (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000028/2023-2024 | 1618/RCD I | 25/04/2023 | 372 | M/S UNIT CONSTRUCTION | 231.44 | 209.84 | 100
783 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for supplying & laying M.S pipe, Supplying specials for Interconnection work for Improvement of RCFA Part-I for Augmentation of RCFA Part-II (Zone-2) PWSS within command area of Zone-VIII under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000085/2024-2025 | 2110/RCD-I | 27/08/2024 | 25 | TARA CONSTRUCTION | 13.73 | 13.21 | 100
784 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works for Laying & pushing of 600mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) , MS water carrier pipe and other allied works at different location (Node point:- 226-232, 289-292, 441-442, 69-76, 63-64, 256-272 ) of distribution network for Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000089/2024-2025 | 2114/RCD-I | 27/08/2024 | 60 | SWATI CORPORATION | 35.82 | 0 | 100
785 | RCFA Division -I | RCFA Division I | Formal Work order for construction of 900 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-2) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000098/2023-2024 | 1846/RCD-I | 31/05/2023 | 366 | M/S CHANDI CHARAN ROY | 199.25 | 199.25 | 90
786 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of important roads (2 nos location at zone-4A) of Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 2 |  | ORD/000110/2024-2025 | 2132/RCD-I | 27/08/2024 | 30 | UNITED CONSTRUCTION | 39.74 | 32.91 | 100
787 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 54.81 | 70
788 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying 100 mm dia MS water pipe with 600 mm dia MS casing pipe line for Railway Crossing in Parasia sliding at KM CB-2/15 to CB-2/16 in Asansol Division of Eastern Railway under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000196/2025-2026 | 1374/RCD-I | 15/05/2025 | 30 | SWATI CORPORATION. | 24.14 | 0 | 100
789 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 01 (One) location on Salanpur ¿ Khuidica road and supplying and laying MS pipe near culvert and gas line including ancillary work within command area of Zone-I (Dendua OHR Site) Part-C under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000220/2023-2024 | 2225/RCD-I | 17/07/2023 | 259 | DAS & CHAKRABORTY | 15.47 | 12.05 | 100
790 | RCFA Division -I | RCFA Division I | Formal Work Order for Additional supplying laying 280 mm & 225 mm dia HDPE pipe line for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000311/2023-2024 | 2384/RCD-I | 07/08/2023 | 60 | SWATI CORPORATION | 124.64 | 97.3 | 80
791 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution of pipe line from Alinagar OHR to Khattardihi Village via Minsa Das Para including Laying & Pushing by adopting trench less technology (e.g, Jack Pushing Method etc) & other allied work under Shyamla GP under Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000515/2024-2025 | 115/RCD-I | 08/01/2025 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 47.67 | 9.81 | 80
792 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line towards Teli Para (Sansad -XIV) under Ukhra area Block- Andal & Pandabswar of Augmentation of RCFA Part-II (Zone-2) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000559/2023-2024 | 3188/RCD-I | 01/11/2023 | 15 | NILIMA CONSTRUCTION | 2.49 | 2.3 | 100
793 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-2) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000564/2022-2023 | 3358/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.48 | 100
794 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, aligning & Laying of different dia HDPE pipe line and allied works for dedicated line to Chotkara village and Satta under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000579/2023-2024 | 2989-RCD-I | 12/10/2023 | 15 | SHREE DURGA ENTERPRISE | 5.85 | 5.83 | 100
795 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of damaged collecting main in river Damodar rising main to D.P Colony OHR and allied works of DP colony W/S scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 |  | ORD/000611/2023-2024 | 3370/RCD-1 | 21/11/2023 | 15 | DURGA DAS MONDAL | 4.98 | 4.42 | 100
796 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara Block Anda & Pandabeswar of Ukhra under Augmentation of RCFA Part-II (Zone-2) PWSS under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 |  | ORD/000680/2022-2023 | 367/RCDI | 30/01/2023 | 30 | JAI MAHARAJ ENTERPRISE | 5.62 | 5.2 | 100
797 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE Pipe Line including concrete cutting, mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Ukhra under Additional works under Ukhra & its adjoining mouzas water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000693/2022-2023 | 382/RCD I | 30/01/2023 | 15 | B.T.M CONCERN | 20.71 | 20.34 | 100
798 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000017/2023-2024 | 2958/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
799 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-I) Pipe Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000037/2023-2024 | 1609/RCD I | 25/04/2023 | 90 | GITA CONSTRUCTION | 245.36 | 156.7 | 65
800 | RCFA Division -I | RCFA Division I | Formal Work Order for Construction of Sub-station, CWR and Pump House including toilet at Ethora under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000173/2023-2024 | 2009/RCD-I | 26/06/2023 | 120 | D.S. ENTERPRISE | 122.25 | 43.74 | 40
801 | RCFA Division -I | RCFA Division I | Urgent Basis rapairing of 50 sqmm x 4 core Al Armoured Damaged cable line street Light Providing of FHTC Pipe line near Andal More to Culvert (Bridge) under Dignala OHR dite under Andal W/s scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000560/2023-2024 | SpotNit_Camp_02/AndalMore | 09/10/2023 | 10 | T R ENTERPRISE | 6.17 | 6.16 | 100
802 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Jagrdih, Gopal area ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000601/2023-2024 | 3283/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.12 | 6.11 | 100
803 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) 02 (Two) Nos. Near Dakshin Khanda Dharmaraj Tala and Khandra BPHC under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000656/2023-2024 | 3428/RCD-1 | 24/11/2023 | 15 | UNITED CONSTRUCTION | 18.39 | 17.65 | 100
804 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Shifting of 450 mm dia Rising main for ECL Railway siding near Dalmia OCP for extension of Bonjemari Colliery under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001108/2023-2024 | 913/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 43.51 | 42.65 | 100
805 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Laying of Rising main including allied works of for extension of Bonjemary Colliery and ECL Railway siding under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001109/2023-2024 | 914/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 38.46 | 38.42 | 100
806 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for concrete cutting, restoration of road and allied works Dakshin Khanda area under RCFA Part-II W/S Scheme PHE Dte. [Zone-1A] | Assistant Engineer 2 | Junior Engineer | ORD/001111/2023-2024 | 917/RCD-I | 15/03/2024 | 30 | UNITED CONSTRUCTION | 17.04 | 16.94 | 100
807 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Construction of pillar, MS pipe, specials, GI Pipe and allied works within Zone-I near Dendua under Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001118/2023-2024 | 924/RCD-I | 15/03/2024 | 45 | SWATI CORPORATION | 25.03 | 24.35 | 100
808 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work Distribution Network for Augmentation of RCFA Part-II (Zone-1) Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/001123/2023-2024 | 929/RCD-I | 15/03/2024 | 45 | UNITED CONSTRUCTION | 32.03 | 24.47 | 100
809 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Dedicated pipe line beyond Patal Lakhi Mandir including FHTC connections and allied works for Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division - I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001131/2023-2024 | 916/RCD-I | 15/03/2024 | 30 | RAJAT BARAN CHAND | 17.3 | 17.12 | 100
810 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional supplying laying 90 mm dia, HDPE pipe line at Tentul Tala and Damalia Village including repairing different dia pipe line in different places in Tirat Mouza within Amritnagar Distribution Zone under Augmentation Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001139/2023-2024 | 937/RCD-I | 15/03/2024 | 15 | RUBY CONSTRUCTION | 6.88 | 6.85 | 100
811 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for concrete cutting and concreting and distribution network for RCFA Part-II PWSS including FHTC and allied work under RCFA Division-I PHE Dte. Zone-12B (Segement 2) | Assistant Engineer 2 | Junior Engineer | ORD/001170/2023-2024 | 1009/RCD-I | 16/03/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 31.75 | 0 | 0
812 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying pipeline and allied works from Kelejora Health Centre Crossing towards Barabani Village (ICML Road) withthin Zone XIII of Augmentation RCFA Part-II (Zone-I) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001171/2023-2024 | 1011/RCD-I | 16/03/2024 | 168 | PINKI ENTERPRISE | 31.63 | 0 | 100
813 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of laying of rising main at Surjanagar Head Work Site to High lift site and interconnection of collecting main to CWR in the river of Damodar under Augmentation of RCFA Part-II (Zone-I) PWSS under RCFA Division-I. PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001175/2023-2024 | 1014/RCD-I | 16/03/2024 | 45 | MAK CONSTRUCTION CO | 40.81 | 10.39 | 100
814 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000015/2023-2024 | 2935/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
815 | RCFA Division -I | RCFA Division I | Way leave permission of 250 mm dia waer pipeline (Jal Jeevan Mision) near LC Gate No. 9/Spl/T near Pandabeswar Station in Asansol Divison of Eastern Railway by RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00987/2024-2025 | 415/24-25 | 05/12/2024 | 0 | EASTERN RAILWAY | 68.95 | 0 | 0
816 | RCFA Division -I | RCFA Division I | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line and extension of HDPE pipe to adjacent village of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000030/2023-2024 | 1615/RCD I | 25/04/2023 | 90 | DAS & CHAKRABORTY | 115.96 | 107.47 | 100
817 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA part-II Piped Water Supply Scheme (Zone-7) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000155/2023-2024 | 1900/RCD-I | 09/06/2023 | 365 | TARAPRASAD SARKAR | 150.41 | 21.85 | 25
818 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-7) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000560/2022-2023 | 3354/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
819 | RCFA Division -I | RCFA Division I | Additional extra cutting Laterrate / sandstone of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Div-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000573/2023-2024 | 2694/RCD-I | 27/09/2023 | 15 | TARA CONSTRUCTION | 0.94 | 0.84 | 100
820 | RCFA Division -I | RCFA Division I | Acceptance Cum work order for Additional work for distribution network for Improvement of RCFA Part-II Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000675/2022-2023 | 358/RCD I | 30/01/2023 | 336 | UNITED CONSTRUCTION | 62.01 | 5.82 | 100
821 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-1 | Assistant Engineer 2 | Junior Engineer | ORD/000850/2022-2023 | 1098/ RCD-I | 23/03/2023 | 90 | MAK CONSTRUCTION CO. | 97.63 | 13.69 | 15
822 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-2 | Assistant Engineer 2 | Junior Engineer | ORD/000853/2022-2023 | 1100/RCD I | 23/03/2023 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 89.86 | 37.08 | 50
823 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-3 (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000856/2022-2023 | 1102/RCD I | 23/03/2023 | 90 | RUBY CONSTRUCTION | 94.47 | 48.98 | 70
824 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-4 | Assistant Engineer 2 | Junior Engineer | ORD/000858/2022-2023 | 1104/RCD I | 23/03/2023 | 90 | M/S MONI TRADERS | 93.11 | 39.26 | 45
825 | RCFA Division -I | RCFA Division I | Acceptance cum work order for distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/000863/2022-2023 | 1106/RCD I | 23/03/2023 | 90 | B.T.M CONCERN | 94.6 | 60.02 | 65
826 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional supplying, Laying & Aligning of HDPE pipe, including providing FHTC retrofitting (left out portion) at Ratibati village under Augmentation PWSS of RCFA Part-II (Zone-7) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001023/2023-2024 | 622/RCD-I | 27/02/2024 | 15 | M/S KALYAN ENTERPRISE | 4.09 | 4.09 | 100
827 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000021/2023-2024 | 2950/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
828 | RCFA Division -I | RCFA Division I | Formal work order for Supplying laying different HDPE Pipe line for Improvement of RCFA Part-I Water Supply Scheme within Command area of Zone-VIII with LDS work under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000031/2023-2024 | 1614/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 128.33 | 22.19 | 80
829 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 450 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-5) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000042/2023-2024 | 1608/RCD I | 25/04/2023 | 366 | HIRANMAY GHOSH | 137.5 | 137.5 | 50
830 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000422/2023-2024 | 2620/RCD-I | 13/09/2023 | 15 | MD AAMIR KHAN | 38.07 | 32.09 | 100
831 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work for bridge with foundation at Chalbalpur under Amritnagar Zone-II for Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000513/2023-2024 | 2864/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.54 | 87.26 | 100
832 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of new boundary wall, Land developing and Pathway and other allied works at Nimsa mouza RCC over Head Site at Shyamla under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Length 188 Mtr) | Assistant Engineer 2 | Junior Engineer | ORD/000519/2023-2024 | 2873/RCD-I | 06/10/2023 | 90 | M/S CHANDI CHARAN ROY | 21.97 | 13.21 | 100
833 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and pushing MS pipe through RCC pipe in different dia and different including cutting welding for barricading jointing for Augmentation of RCFA Part-II (Zone-5) PWSS under Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000523/2023-2024 | 2881/RCD-I | 06/10/2023 | 178 | MRITYUNJOY MUKHERJEE & CO. | 16.98 | 0 | 100
834 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying. Aligning and laying MS pipe (Node no. 45-47, 61-62, 5-16, 44-45) construction of Guard wall, concrete dismantling with re concreting and other allied works for Shyamla & Bhuri Mouzas, Block-Jamuria, Dist-Paschim Bardhaman under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000524/2023-2024 | 2882/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 13.8 | 10.84 | 100
835 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-5) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000565/2022-2023 | 3359/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100
836 | RCFA Division -I | RCFA Division I | Formal work order for distribution network including FHTC & allied work at Ondal Block of RCFA Part-II(zone -5) pipe water supply under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000811/2022-2023 | 954/RCDI | 20/03/2023 | 926 | M/S PIONEER CONSTRUCTION | 475.88 | 209.15 | 80
837 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000019/2023-2024 | 2954/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
838 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-72 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00788/2023-2024 | 382/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
839 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-71 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00790/2023-2024 | 378/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0
840 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-70 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00791/2023-2024 | 379/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0
841 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-69 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00792/2023-2024 | 380/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
842 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-68 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00793/2023-2024 | 381/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
843 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-67 for Nimcha - Kalipahari under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00794/2023-2024 | 383/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0
844 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) in Asansol Division under JJM under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000423/2023-2024 | 2621/RCD-I | 13/09/2023 | 15 | MAK CONSTRUCTION CO. | 62.81 | 62.23 | 100
845 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, Aligning, laying HDPE pipe & Supply Sluice Valve & construction of sluice valve chamber including providing FHTC and other allied works at Ratibati village Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000469/2023-2024 | 2874/RCD-1 | 06/10/2023 | 30 | NIYATI CONSTRUCTION | 7.87 | 7.86 | 100
846 | RCFA Division -I | RCFA Division I | Acceptance cum work order for 2nos of Emergency repairing work of 450 mm dia rising main at Upper Jamdoba and Nichu Para under RCFA Part-II W7S scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000483/2023-2024 | 2890/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.29 | 2.29 | 100
847 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 90mm dia HDPE pipe and allied works at Bauri para of Khandra area of Block-Ondal under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000487/2023-2024 | 2893/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.33 | 2.33 | 100
848 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Parasia Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000507/2023-2024 | 2969/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
849 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHADURPUR Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000508/2023-2024 | 2970/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
850 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for HARIPUR Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000509/2023-2024 | 2971/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100
851 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for RATIBATI Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000510/2023-2024 | 2972/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
852 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHULA Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000511/2023-2024 | 2973/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100
853 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Panchgachia & Majiara Water Supply Scheme for Implementation of JJM at Barabani Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000512/2023-2024 | 2974/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
854 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur in between KM 227/31-33 and Salanpur (SLS) ¿ Rupnarayanpur (RNPR) Station in Asansol Division of JJM under Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000518/2023-2024 | 2870/RCD-I | 06/10/2023 | 30 | SWATI CORPORATION | 67.3 | 60.1 | 100
855 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of HDPE pipeline and MS work and interconnection of Raniganj Chati,Baliapur and adjacent area of Zone-IX for Augmentation of PWSS of RCFA Part-II (Zone-3) under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000525/2024-2025 | 126/RCD-I | 08/01/2025 | 30 | DAWN CONSTRUCTION | 16.98 | 0 | 100
856 | RCFA Division -I | RCFA Division I | Balance work of Laying of 200 mm dia HDPE pipe line and road restoration at Raghunathchak, Raniganj Chati, Baliapur and adjacent area within Zone-IX of Augmentation PWSS of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000589/2024-2025 | Camp_02_Raghunathchak_AE- | 09/12/2024 | 15 | DAWN CONSTRUCTION | 13.12 | 0 | 100
857 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency work for Withdrawing and Relaying of collecting main and other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar water supply scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000608/2023-2024 | 3368/RCD-1 | 21/11/2023 | 15 | M/S KALYAN ENTERPRISE | 2.78 | 2.78 | 100
858 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000620/2023-2024 | 3383/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 4.27 | 4.27 | 100
859 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying aligning, Laying of PVC pipe, HDPE pipe sluice valve, Sluice valve chamber and other allied works at Oriapara, Chapui Vaskadaora 7 nos pit to Rangadanga Talbagan under Ratibati Gram Panchayet under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000637/2023-2024 | 3419/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 7.78 | 7.78 | 100
860 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Withdrawing, supplying, aligning Relaying of 80 mm dia PVC pipe line, repairing of street stand post and other allied works at Goylapara under Tirat Gram Panchyat under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000639/2023-2024 | 3420/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 6.24 | 0 | 100
861 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-3)(Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000821/2022-2023 | 1002/RCDI | 22/03/2023 | 120 | SINGHA ROY & CO. | 392.43 | 361.61 | 86
862 | RCFA Division -I | RCFA Division I | Emergent Sinking of one no.200 x 165 mm Rig box tubewell at ADM Bunglow, Asansol, Paschim Bardhaman, Under R.C.F.A Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000888/2023-2024 | SpotNITCamp-02/ADMBunglow | 09/01/2024 | 7 | M/S CHANDI CHARAN ROY | 7.5 | 7.44 | 100
863 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying Aligning & laying HDPE pipe supplying sluice valve and others allied works of different places under Nutun Egara under Narayankuri W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000933/2023-2024 | 496/RCD-1 | 12/02/2024 | 45 | DIP CONSTRUCTION | 8.67 | 8.67 | 100
864 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Road Crossing by adopting trenchless technology at 3 (Three) nos locations near ECL stack yard including restoration of road from Dabor more to Amdanga more in connection to rising main Part-A under Improvement of RCFA Part-I in Connection of Rising Main (Part-A) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000957/2023-2024 | 482/RCD-I | 12/02/2024 | 45 | MD AAMIR KHAN | 44.01 | 43.95 | 100
865 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Laying MS pipe over bridge / culvert including adopting trench less technology (e.g. Jack Pushing Method etc) at 4 (Four) nos location within laying distribution system of Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000959/2023-2024 | 483/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 25.18 | 24.97 | 100
866 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of dismantling & concrete works, laterite and sand filling at distribution system network for RCFA Part-II (Zone-3) PWSS including FHTC & allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000977/2023-2024 | 493/RCD-I | 12/02/2024 | 35 | SINGHA ROY & CO. | 77.52 | 74.45 | 100
867 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Replacing existing UPVC pipe line with HDPE at Marickkota and different village under Salanpur Block under RCFA Part-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000981/2023-2024 | 509/RCD-I | 12/02/2024 | 45 | SUKHENDU MAJUMDAR | 6.37 | 0 | 0
868 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of sinking of 3 (Three) nos. 200 mm dia river bed tube well including collecting main in the river Damodar at Gourbazar H/W Site for Hourbazar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000982/2023-2024 | 510/RCD-I | 12/02/2024 | 25 | R B ENTERPRISE | 12.96 | 12.52 | 100
869 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work of 50 cum/hr capacity I.E. Plant at Churulia and Madanpur Head Works Site Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000989/2023-2024 | 475/RCD-I | 12/02/2024 | 120 | TARAPRASAD SARKAR | 31.29 | 23.47 | 100
870 | RCFA Division -I | RCFA Division I | Continuation of work order for Conducting route survey, design rising main network and preparation & submission of source Augmentation DPR for Ukhra OHR of RCFA (Part-I) PWSS. | Assistant Engineer 2 | Junior Engineer | ORD/001008/2023-2024 | 3523-A/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
871 | RCFA Division -I | RCFA Division I | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Improvement of Collector well by infiltration gallery at Kalajharia Part-II W/S Scheme | Assistant Engineer 2 | Junior Engineer | ORD/001011/2023-2024 | 3523-B/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
872 | RCFA Division -I | RCFA Division I | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Madanpur OHR of RCFA (Part-I) PWSS under RCFA DIVISION-I , P.H.E Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001012/2023-2024 | 3523-C/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 4.97 | 100
873 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional repairing and maintenance work of RCC Elevated reservoir, Boundary Wall and other allied works at Mangalpur of 25000 gallon capacity under Augmentation of RCFA Part-II (Zone-3) Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001186/2023-2024 | 938/RCD-I | 15/03/2024 | 15 | M/S SUBHRADEEP | 16.89 | 16.53 | 100
874 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional providing FHTC of retrofitting at kumardiha Village (left out portion) of Kumardiha Mouza, GP-Ratibati Block Raniganj of Ratibati Water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001206/2023-2024 | 1023/RCD-I | 16/03/2024 | 30 | SAYAN CONSTRUCTION | 5.65 | 0 | 0
875 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000013/2023-2024 | 2933/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
876 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 27.86 | 100
877 | Durgapur W/S Division | Asansol Mechanical Division | Quotation money for new electric connection for Augmentation of ground water based water supply scheme for Banagarm part under Durgapur W/s Division, PHE Dte,Block -Kanksa,Dist-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | BILL/00038/2023-2024 | BP-2023-24-25 | 18/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0
878 | Durgapur W/S Division | Asansol Mechanical Division | Balance work for construction of Pump house /Chlorine room sinking of 150 X80X120 mtr depth TW ,supplying laying of HDPE distribution pipe line and providing FHTC at Banagram mouza of Augmentation of Banagram piped W/s Scheme under DWSD,PHE Dte.(SM/16903) | Assistant Engineer-II | Junior Engineer-3 | ORD/000192/2023-2024 | 1606/DWSD | 21/08/2023 | 865 | BISHAL ENTERPRISE | 47.01 | 0 | 100
879 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Banagram Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000932/2022-2023 | 1309/CMD | 22/03/2023 | 30 | K.S.P. ENTERPRISE | 9.99 | 8.45 | 70
880 | Central Mechanical | Asansol Mechanical Division | Supply & Delivery of Pump Motor Set at TW No: 01 of Banagram water supply scheme under CMD, PHE, Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001165/2023-2024 | 111/DIC/BMSD(D) | 04/10/2023 | 15 | K.S.P. ENTERPRISE | 0.52 | 0 | 100
881 | RCFA Division -I | RCFA Division I | Fuel bill in faver of Ranajit auto for the month of September 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt of west bengal | Assistant Engineer 2 | Junior Engineer | BILL/00990/2024-2025 |  | 04/12/2024 | 0 | RANAJIT AUTO | 0.21 | 0 | 0
882 | RCFA Division -I | RCFA Division I | Fuel bill in faver of Ranajit auto for the month of October 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt of west bengal | Assistant Engineer 2 | Junior Engineer | BILL/00992/2024-2025 |  | 04/12/2024 | 0 | RANAJIT AUTO | 0.11 | 0 | 0
883 | RCFA Division -I | RCFA Division I | Fuel bill in faver of Ranajit auto for the month of December 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt. of west bengal | Assistant Engineer 2 | Junior Engineer | BILL/01142/2024-2025 |  | 20/01/2025 | 0 | RANAJIT AUTO | 0.19 | 0 | 0
884 | RCFA Division -I | RCFA Division I | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000160/2024-2025 | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0.33 | 33
885 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Supply and laying MS water carrier pipe and allied works of Improvement of RCFA Part-I in connection of Rising Main (Part-A) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000209/2023-2024 | 2209/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 37.26 | 36.13 | 100
886 | RCFA Division -I | RCFA Division I | Acceptance cum Providing FHTC of retrofitting at Kumardihi village (left out portion) of kumardihi Mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Sceme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000775/2022-2023 | 806/RCD-I | 06/03/2023 | 20 | M/S MONDAL CONSTRUCTION | 13.78 | 12.41 | 100
887 | RCFA Division -I | RCFA Division I | acceptance cum work order Repairing of 450 mm dia DI pipe line at Baidyanathpur, Barachak, Jagaridih area of ASTA rising main of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2022-2023 | 1282/RCD-I | 27/03/2023 | 15 | SIMA ENTERPRISE | 2.66 | 2.66 | 0
888 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for railway crossing in between Jamuria (JMA) and Barabani (BBI) at KM 25/2-3 in Asansol Division under JJM of Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001124/2023-2024 | 931/RCD-I | 15/03/2024 | 30 | SOMNATH SAMANTA | 23.15 | 22.61 | 100
889 | RCFA Division -I | Asansol Mechanical Division | Separate connection for Hazrabera under Prayagpur OHR Kanksa Zone-II (Part-B) under Augmentation of Tilakchandrapur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001061/2023-2024 | 707/RCD-I | 29/02/2024 | 15 | MALLICK CONSTRUCTION | 0.91 | 0.89 | 100
890 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Emergency repairing and etc allied works at different places within Basudha area,Domra area ,Tilakchandrapur area ,Krikrishnapur and Roopganj area under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000276/2023-2024 | 1562/A/DWSD | 20/09/2023 | 15 | GHOSH ENTERPRISE | 3.29 | 3.28 | 100
891 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 2(Two) Nos TW,FHTC,laying Rising main and laying distribution system (LDS) ,construction of boundary wall ,Pump House and restoration of road another allied works for Augmentation of ground water based W/s Scheme for Trilakchandrapur under DWSD,Block-Kanksa,Dist-Paschim Bardhhaman | Assistant Engineer-II | Junior Engineer-3 | ORD/000281/2023-2024 | 1826/DWSD | 05/12/2023 | 728 | SHWET BARANI | 243.78 | 111.4 | 100
892 | Asansol Mechanical | Asansol Mechanical Division | Quotation Payment for Trilockchandrapur T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. | Assistant Engineer-II | Junior Engineer-3 | BILL/00038/2024-2025 | BP-2024-25-11 | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0
893 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL Procedure-A (2010) ON Turn key/ Full deposit basis for the site of Trilockchandrapur Pump House no-4, Trilockchandrapur under Kanksa Block under Panagarh CCC supply office. | Assistant Engineer-II | Junior Engineer-3 | BILL/00076/2024-2025 | BP-2024-25-12 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.48 | 0 | 0
894 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND YARD LIGHTING INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 & TUBE WELL NO-4 AT AUGMENTATION OF TILAKCHANDRAPUR PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000322/2024-2025 | 1820/AMD | 29/10/2024 | 715 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 26.65 | 0 | 100
895 | RCFA Division -I | Asansol Mechanical Division | Restoration of damaged road surface due to the cause of earthwork in connection with placement of under ground water pipe line in stretches at Pandabeswar-Natundanga Road from Chainage 0.000 km to 2.00 Km 2.500 to 3.000 Km 5.500 to 5.800 km, 7.900 km to 8.141 km in the district of Paschim Bardhaman under Asansol Division PWD | Assistant Engineer-II | Junior Engineer-5 | BILL/01547/2023-2024 | 629/23-24 | 15/03/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 33.26 | 0 | 0
896 | Durgapur W/S Division | Asansol Mechanical Division | Construction of 100 M3 capacity Clear Water Reservoir (CWR) at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000090/2023-2024 | 1094/DWSD | 14/07/2023 | 60 | KALPANA BUILDERS | 32.52 | 32.1 | 100
897 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) | Assistant Engineer-II | Junior Engineer-5 | ORD/000091/2023-2024 | 1095/DWSD | 14/07/2023 | 30 | CHANDAN HAZRA | 18.32 | 14.9 | 82
898 | Durgapur W/S Division | Asansol Mechanical Division | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-C). | Assistant Engineer-II | Junior Engineer-5 | ORD/000092/2023-2024 | 1096/DWSD | 14/07/2023 | 749 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 93.43 | 23.12 | 70
899 | Durgapur W/S Division | Asansol Mechanical Division | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-B). | Assistant Engineer-II | Junior Engineer-5 | ORD/000093/2023-2024 | 1098/DWSD | 14/07/2023 | 993 | UNITED CONSTRUCTION | 93.32 | 66.94 | 100
900 | Durgapur W/S Division | Asansol Mechanical Division | Supplying,laying and alingining of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist-Paschim Bardhaman.(Part-F). | Assistant Engineer-II | Junior Engineer-5 | ORD/000094/2023-2024 | 1099/DWSD | 14/07/2023 | 30 | M/S BADAL GHOSH | 99.72 | 65.25 | 100
901 | Durgapur W/S Division | Asansol Mechanical Division | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) | Assistant Engineer-II | Junior Engineer-5 | ORD/000095/2023-2024 | 1100/DWSD | 14/07/2023 | 992 | A CONSTRUCTION CO. | 98.78 | 41.19 | 50
902 | Durgapur W/S Division | Asansol Mechanical Division | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-E). | Assistant Engineer-II | Junior Engineer-5 | ORD/000096/2023-2024 | 1101/DWSD | 14/07/2023 | 658 | KALPANA BUILDERS | 99.89 | 0 | 65
903 | Durgapur W/S Division | Asansol Mechanical Division | Supplying, laying and aligning of HDPE distribution pipe line and other allied works under command area of SARPI piped W/S system under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-G). | Assistant Engineer-II | Junior Engineer-5 | ORD/000097/2023-2024 | 1102/DWSD | 14/07/2023 | 840 | HIRANMAY GHOSH | 97.54 | 43.97 | 80
904 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-B) | Assistant Engineer-II | Junior Engineer-5 | ORD/000098/2023-2024 | 1103/DWSD | 14/07/2023 | 35 | MAK CONSTRUCTION CO. | 27.48 | 27.44 | 100
905 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 2Nos 200 mm dia River bed tube well with collecting main with manifold in river AJOY at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-C) | Assistant Engineer-II | Junior Engineer-5 | ORD/000099/2023-2024 | 1104/DWSD | 14/07/2023 | 30 | MAITO MAA ENTERPRISE | 18.32 | 10.96 | 100
906 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 3 Nos 200 mm dia River bed tube well with collecting main with manifold in river "AJOY" at Bhaburia H/W Site under RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC in Durgapur-Faridpur block ,Dist.-Paschim Bardhhaman.(Part-A) | Assistant Engineer-II | Junior Engineer-5 | ORD/000100/2023-2024 | 1105/DWSD | 14/07/2023 | 35 | BISHAL ENTERPRISE | 27.47 | 23.76 | 90
907 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SARPI PWSS under DURGAPUR-FARIDPUR Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) | Assistant Engineer-II | Junior Engineer-5 | ORD/000181/2023-2024 | 924/DWSD | 23/06/2023 | 7 | CARTO | 0.78 | 0 | 0
908 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission for Pratabpur Mouza (JL-48) under retrofitting of Jemua Piped Water Supply Scheme under Durgapur Faridpur Block under DWSD PHE Dte.(Sl-04) | Assistant Engineer-II | Junior Engineer-5 | ORD/000229/2023-2024 | 1394/DWSD | 16/08/2023 | 10 | GHOSH & ROY ENTERPRISE | 0.96 | 0.96 | 100
909 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000474/2021-2022 | 180/DWSD | 11/02/2022 | 15 | SHWET BARANI | 4.12 | 0 | 100
910 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-5 | RTOR000008/2023-2024 | 1665/DWSD | 12/10/2023 | 0 | Resource Division | 922.9 | 0 | 0
911 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-5 | RTOR000009/2023-2024 | 1833/DWSD | 06/12/2023 | 0 | Resource Division | 236.81 | 0 | 0
912 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for new connection under Sharpi Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | BILL/00534/2023-2024 | BP-2023-24-45 | 03/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0
913 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for New Connection under Sharpi Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | BILL/00535/2023-2024 | BP-2023-24-44 | 03/11/2023 | 0 | WEST BENGAL ENGINEERING CO. | 3.65 | 0 | 0
914 | Asansol Mechanical | Asansol Mechanical Division | Load Enhancement for Natundanga Zone under Sharpi PWSS | Assistant Engineer-II | Junior Engineer-5 | BILL/00574/2024-2025 | BP-2024-25-59 | 26/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 21.33 | 0 | 0
915 | Asansol Mechanical | Asansol Mechanical Division | Security deposit and Earnest money for the sharpi O.H.R. under Augmentation of Sharpi Water supply scheme. | Assistant Engineer-II | Junior Engineer-5 | BILL/01135/2024-2025 | BP-2025-26-1 | 18/07/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.93 | 0 | 0
916 | Asansol Mechanical | Asansol Mechanical Division | Quotation for new connection at Jagannathpur O.H.R. under Sharpi Water supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | BILL/01136/2024-2025 | BP-2024-25-88 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.51 | 0 | 0
917 | Asansol Mechanical | Asansol Mechanical Division | Supply delivery and installation of submersible pumping machinery in the newly sunk ground bored tubewell, lighting arrangement at new Bhaburia headworks site and corresponding sharpi O.H.R under RBTW water based water supply scheme for sharpi and adjoining areas under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000023/2025-2026 | 943/AMD | 16/05/2025 | 30 | M/S JIT ENTERPRISE | 14.96 | 0 | 0
918 | Asansol Mechanical | Asansol Mechanical Division | Providing & Installation of Centrifugal Pumping Machineries(No-04) at Amdahi Boosting Station under Augmentation of Sharpi Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000071/2025-2026 | 1110/AMD | 16/06/2025 | 30 | WEST BENGAL ENGINEERING CO. | 32.17 | 0 | 0
919 | Asansol Mechanical | Asansol Mechanical Division | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at New Bhaburia Head Works Site and Madhaiganj Boosting Station under Sharpi Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Durgapur-Faridpur, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000178/2023-2024 | 1402/AMD | 19/07/2023 | 366 | MACHINE SUPPLIERS SYNDICATE(P) LTD. | 338.11 | 202.91 | 60
920 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Madhaiganj Boosting Station under Sharpi & adjoining mouzs Piped Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000441/2024-2025 | 2099/AMD | 12/12/2024 | 30 | M/S SWAPAN BANERJEE | 19.61 | 0 | 0
921 | RCFA Division -I | Asansol Mechanical Division | Permission for laying of water pipeline along NH-02 from Duburdih (km. 441+780) to Kalla More (Km. 462+080) and 1 no. crossing acros NH-2 in the state of West Bengal unde RCFA Divn-I PHE Dte - Submission of Bank Guarantee reg. | Assistant Engineer-I | Junior Engineer-4 | BILL/00053/2024-2025 | 268/24-25 | 05/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 104.25 | 0 | 0
922 | RCFA Division -I | Asansol Mechanical Division | Restoreation and repairing work from Ch. 13415 to 14300 of Neamatpur - Rupnarayanpur Road (FR-10) under Asansol Division, PWD for laying of distribution system of Zone - VII under JJM work in the district of Paschim Bardhaman during the year 2024-2025 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | BILL/00307/2024-2025 | 168/24-25 | 23/07/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 14.85 | 0 | 0
923 | RCFA Division -I | Asansol Mechanical Division | Execution of agreement with Damodar Valley Corporation for drawl of 15.757 (Fifteen point seven five seven) MGD raw water for RCFA Part-II piped water supply scheme under RCFA Public Health Engineering Directorate, Asansol from Maithon Reservoir | Assistant Engineer-I | Junior Engineer-4 | BILL/00769/2023-2024 | 371/23-24 | 21/11/2023 | 0 | DAMODAR VALLEY CORPORATION | 13.08 | 0 | 0
924 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-55 for Asansol East Cabin - Asansol East Hump under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00834/2023-2024 | 404/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 149.35 | 0 | 0
925 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-57 for Kalipahari - Nimcha under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00837/2023-2024 | 410/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 5.28 | 0 | 0
926 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-56 for Damodar under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00839/2023-2024 | 405/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 19.69 | 0 | 0
927 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-61 for Baktarnagar - Raniganj under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00842/2023-2024 | 409/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 9.91 | 0 | 0
928 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-53 for Salanpur - Sitarampur link Cabin under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00848/2023-2024 | 403/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.82 | 0 | 0
929 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-52 for Damagoria under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00850/2023-2024 | 407/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.2 | 0 | 0
930 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-58 for Sonachara - Topsi under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00855/2023-2024 | 412/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 10.27 | 0 | 0
931 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-59 for Pandabeswar - Ukhra under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00859/2023-2024 | 408/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 8.26 | 0 | 0
932 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-60 for Topsi - Sripur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00861/2023-2024 | 411/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.67 | 0 | 0
933 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-54 for Chinchuria - Sitarampur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00865/2023-2024 | 406/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.78 | 0 | 0
934 | RCFA Division -I | Asansol Mechanical Division | Permission for laying of water pipeline along NH-02 from Duburdih (km 441.780) to Kalla More (k. 462.080) and 1 no crossing across NH-2 in th state of West Bengal under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. RCFA Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/01344/2023-2024 | 545/23-24 | 08/02/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 169.62 | 0 | 0
935 | RCFA Division -I | Asansol Mechanical Division | Restoration work of damaged road flank caused by PHE for laying water pipe line at kajora Haripur from 0.00 km to 10.74 km at Ukhra Madhaigand road rom 0.00 to 12.13 km at Galigram - Kutruki - Chandipur road between 9 km to 12 km , Raghunathpur - Kantaberia road at 19th km near kantabaria Raghunathpur Kantaberia road from 0.00 kmp to 3.50 near Jamdoba village under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/01345/2023-2024 | 544/23-24 | 08/02/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 32.25 | 0 | 0
936 | RCFA Division -I | Asansol Mechanical Division | Damage of "PMGSY" and "Pathashree" Roads due to laying of PHED pipeline and tentative estimates for restoration | Assistant Engineer-I | Junior Engineer-4 | BILL/01354/2023-2024 | 549/23-24 | 12/02/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 46.78 | 0 | 0
937 | RCFA Division -I | Asansol Mechanical Division | crossing 300 mm dia DI water pipe line Harishpur (chainage: 257.700 KM (Ex -Barauni) in Asansol - Jasidhi section of 12.75" diameter Haldia-Barauni pipeline (12.75"HBPL) ) | Assistant Engineer-I | Junior Engineer-4 | BILL/01693/2025-2026 |  | 30/12/2025 | 0 | INDIAL OIL CORPORATION LIMITED (IOCL). | 0.3 | 0 | 0
938 | RCFA Division -I | Asansol Mechanical Division | crossing 750 mm dia DI water pipe line khunustoria (chainage: 251.69 KM (Ex -Barauni) in Haldia - Asansol section of 12.75" diameter Haldia-Barauni pipeline (12.75"HBPL) ) | Assistant Engineer-I | Junior Engineer-4 | BILL/01694/2025-2026 |  | 30/12/2025 | 0 | INDIAL OIL CORPORATION LIMITED (IOCL). | 0.3 | 0 | 0
939 | RCFA Division -I | Asansol Mechanical Division | crossing 500 mm dia DI water pipe line Shivdanga (chainage: 243.250 KM (Ex -Barauni) in Haldia- Asansol section of 12.75" diameter Haldia-Barauni pipeline (12.75"HBPL) ) | Assistant Engineer-I | Junior Engineer-4 | BILL/01695/2025-2026 |  | 30/12/2025 | 0 | INDIAL OIL CORPORATION LIMITED (IOCL). | 0.3 | 0 | 0
940 | RCFA Division -I | Asansol Mechanical Division | crossing 1100 mm dia DI water pipe line Dhadka (chainage: 236.39 KM (Ex -Barauni) in Asansol - Jasidih section of 12.75" diameter Haldia-Barauni pipeline (12.75"HBPL) ) | Assistant Engineer-I | Junior Engineer-4 | BILL/01696/2025-2026 |  | 30/12/2025 | 0 | INDIAL OIL CORPORATION LIMITED (IOCL). | 0.3 | 0 | 0
941 | RCFA Division -I | Asansol Mechanical Division | crossing 1100 mm dia DI water pipe line Melakola (chainage: 225.45 KM (Ex -Barauni) in Asansol - Jasidih section of 12.75" diameter Haldia-Barauni pipeline (12.75"HBPL) ) | Assistant Engineer-I | Junior Engineer-4 | BILL/01697/2025-2026 |  | 30/12/2025 | 0 | INDIAL OIL CORPORATION LIMITED (IOCL). | 0.3 | 0 | 0
942 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work for laying of HDPE and MS pipeline restoration of drain,road and culvert and allied works at Zone-XI(Segment-5) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I.PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000007/2024-2025 | 1431/RCD-I | 06/06/2024 | 15 | M/S B.K. CONSTRUCTION | 11.57 | 9.26 | 100
943 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying pipe line for Chapui, Kumardihi village under Ratibati Gram Panchayet, Raniganj Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000017/2024-2025 | 1520/RCD-I | 14/06/2024 | 45 | M/S U.G. ENTERPRISE | 11.77 | 11.05 | 100
944 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional laying of different dia HDPE pipe line at Madhudanga village and adjacent area within Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000021/2024-2025 | 1524/RCD-I | 14/06/2024 | 45 | MD AAMIR KHAN | 20.3 | 17.53 | 100
945 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000024/2024-2025 | 1517/RCD-I | 14/06/2024 | 15 | INDIA PIPE FITTING CO | 96.97 | 96.86 | 100
946 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying & Pushing by adopting trench less technology (e.g. jack Pushing Method etc) additional for Distribution Network of Augmentation of RCFA Part-II PWSS within command area of Vol-I (Segment-V) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000028/2024-2025 | 1581/RCD-I | 27/06/2024 | 30 | DIP CONSTRUCTION | 37.13 | 0 | 0
947 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Stack Yard (including filling of low land), Jungle cutting, Surface dressing, Dismantling related to RCFA Part-II WTP Site at Kalyaneswari Town ship under RCFA Division-I PHE Dte. Improvement of RCFA Part-II Vol-I | Assistant Engineer-I | Junior Engineer-4 | ORD/000029/2024-2025 | 1582/RCD-I | 27/06/2024 | 45 | UNITED CONSTRUCTION | 18.67 | 18.18 | 100
948 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of CWR 150 cum at Shyamla for Kendra Khottamdihi of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000033/2024-2025 | 1587/RCD-I | 27/06/2024 | 90 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 28.76 | 21.95 | 90
949 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I | Junior Engineer-4 | ORD/000034/2024-2025 | 1588/RCD-I | 27/06/2024 | 45 | SIMA ENTERPRISE | 27.22 | 26.18 | 100
950 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying pipe line and allied works from Kelejora Health Center towards Domohani Bazar within Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000035/2024-2025 | 1589/RCD-I | 27/06/2024 | 45 | R B ENTERPRISE | 34.16 | 32.87 | 100
951 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Extension and renovation work of Annex Building including other allied works inside the premises of RCFA Division-I Office Campus under Augmentation of RCFA Part-II, Volume-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000048/2024-2025 | 1698/RCD-I | 11/07/2024 | 180 | M/S KALYANI ENTERPRISE | 28.95 | 13.56 | 100
952 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for providing FHTC within command area of Zone-I (Dendua OHR Site) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte.(Part-B) | Assistant Engineer-I | Junior Engineer-4 | ORD/000052/2024-2025 | 1742/RCD-I | 18/07/2024 | 355 | TARA CONSTRUCTION | 66.88 | 26.1 | 100
953 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000072/2024-2025 | 1938/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 96.16 | 96.16 | 100
954 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000073/2024-2025 | 1937/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 92.83 | 92.83 | 100
955 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting and regulating apparatus for distribution system and rising main under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000138/2024-2025 | 2232/RCD-i | 10/09/2024 | 30 | MAKALI ENGINEERING CORPORATION | 94.06 | 93.98 | 100
956 | RCFA Division -I | Asansol Mechanical Division | Supply & erection of Govt. Land Boards (51 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Raniganj, Andal, Pandabeswar, Kanksa & Durgapur-Faridpur Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000134/2024-2025 | Camp-02-Raniganj/AE/2024- | 20/08/2024 | 15 | MUKHERJEE TRADERS | 9.91 | 0 | 100
957 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply & erection on Information Boards (51 nos) having M.S. Channel/Angle posts & 1.5 mm thick M.S Synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur, Barabani & Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000136/2024-2025 | 2231/RCD-¦ | 10/09/2024 | 15 | SHARMA ENGINEERING WORKS | 9.9 | 9.86 | 100
958 | RCFA Division -I | Asansol Mechanical Division | Supply & erection of Govt. Land Boards ( 102 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000139/2024-2025 | Camp-02-Jamuria-AE/2024-2 | 20/08/2024 | 15 | UNITED CONSTRUCTION | 20.45 | 19.85 | 100
959 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Surveying, Design, Detail Engineering, Supplying and Construction, Erection, Installation, Testing, Commissioning of Fixed type Intake Jetty with raw water pump house capable of transmitting 100 MLD capacity, Raw Water Rising Main, Bank Protection, Construction of Sub Station buildings, 98 MLD (Minimum)capacity Water Treatment Plant (WTP) (out put) based on conventional technologies considering extra 20% overloading (wherever applicable) Clear Water Pumping Mains, four Booster Stations at Searsole, Shankarpur, Bansra & Benali and Head Works Site at Mohisila including pumping machineries, SCADA for the total system on EPC/Turnkey basis in a single package including 3 (Three) months Trial Run and Operation & Maintenance for 5 years for Surface Based W/S Scheme for RCFA Part-II Augmentation Water Supply Scheme as per scope of contract. | Assistant Engineer-I | Junior Engineer-4 | ORD/000377/2023-2024 | 2514/RCD-I | 25/08/2023 | 731 | GAJA ENGINEERING PRIVATE LIMITED | 35005.02 | 10971.46 | 25
960 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing between Chinchuria (CCR) and Sitarampur (STN) at KM 34/8-9 (Sitarampur end of LC No. 12/A/E) in Asansol Division under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000424/2023-2024 | 2622/RCD-I | 13/09/2023 | 15 | M/S MONDAL ENTERPRISE | 31.21 | 29.86 | 100
961 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-70 mtr) and drain (Length-160 mtr) at Bansketia OHR site of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000432/2023-2024 | 2663/RCD-I | 26/09/2023 | 30 | AMAR CONSTRUCTION | 39.04 | 23.76 | 100
962 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for 450 mm dia pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc) Ch. 222.05 near Damlia OCP for IOCL crossing of rising main (Part-A) under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000517/2024-2025 | 117/RCD-I | 08/01/2025 | 236 | MD AAMIR KHAN | 29.48 | 0 | 100
963 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Interconnection at Kalyaneswari WTP Site, Banskatia OHR and bypass line, Kadvita More branch line, Dendua OHR, Rupnarayanpur OHR and construction of valve chamber etc under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000518/2024-2025 | 118/RCD-I | 08/01/2025 | 45 | MAK CONSTRUCTION CO | 46.44 | 0 | 100
964 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting aparatus of collecting maun including other allied work under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte.(Part A and Part B) | Assistant Engineer-I | Junior Engineer-4 | ORD/000519/2025-2026 | 2128/RCD-I | 22/07/2025 | 15 | MAKALI ENGINEERING CORPORATION | 83.86 | 0 | 100
965 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Flow control of rising main and different dia distribution system by regulating apparatus under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000520/2025-2026 | 2129/RCD-I | 22/07/2025 | 15 | MAKALI ENGINEERING CORPORATION | 44.5 | 0 | 100
966 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply and delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000550/2023-2024 | 3044/RCD-I | 17/10/2023 | 20 | INDIA PIPE FITTING CO | 94.09 | 93.19 | 100
967 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Zone VII (Part E) water Supply scheme within command area of Zone VII under RCFA Div-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000633/2023-2024 | 3444/RCD-I | 24/11/2023 | 557 | TARA CONSTRUCTION | 2.64 | 0 | 100
968 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Supply and laying of MS water Carrier pipe of dia 600 mm, 450 mm, 350 mm, 250 mm and allied works in connection of Rising Main (Part-A) to Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000635/2023-2024 | 3417/RCD-1 | 24/11/2023 | 30 | MD AAMIR KHAN | 70.38 | 68.02 | 100
969 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying E.R.M.S. Black pipe of approved quality including carring, stacking at works for crossing of 12 nos culvert/cannel of by the side of PWD road under Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000651/2023-2024 | 3426/RCD-1 | 24/11/2023 | 20 | SWATI CORPORATION | 7.09 | 4.21 | 100
970 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Bolkunda and surrounding villages within Filberia-Bolkunda Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000652/2023-2024 | 3449/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.52 | 3.5 | 100
971 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balanced work at Shyamsundarpur Zone-13 of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000926/2024-2025 | 2802_RCD-1 | 29/11/2024 | 244 | MD AAMIR KHAN | 95.62 | 0 | 100
972 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for concrete dismantling restoration of concrete for 350 mm D.I. and 315 mm HDPE pipe line repair damaged PVC and GI pipe line and other allied works for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I within command area of Zone-VIII under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000945/2023-2024 | 490/RCD-I | 12/02/2024 | 30 | TARA CONSTRUCTION | 11.01 | 9.48 | 100
973 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for for 450 mm dia pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc) Ch. 222.05 near Damlia OCP for IOCL crossing of rising main (Part-A) under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001004/2024-2025 | 358-A/RCD-I | 21/02/2025 | 213 | MD AAMIR KHAN | 27.3 | 0 | 100
974 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution Network for Laying distribution system including FHTC for 5 (Two) nos uncoverd village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001134/2023-2024 | 807/RCD-I | 14/03/2024 | 505 | UMA ENTERPRISE | 107.86 | 59.72 | 30
975 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for Shifting of Rising main for extension of Bonjemary Colliery and ECL Railway siding near Dalmia OCP under ECL Deposite Scheme under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001173/2023-2024 | 1013/RCD-I | 16/03/2024 | 15 | R B ENTERPRISE | 30.24 | 30.2 | 100
976 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc), additional for Rising main and culvert crossing near Semlya Head Work Site under Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001207/2023-2024 | 1010/RCD-I | 16/03/2024 | 15 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.72 | 12.23 | 100
977 | RCFA Division -I | Asansol Mechanical Division | Additional works for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) and MS water carrier pipe under I.O.C.L pipe line at Basudevpur village of distribution network for RCFA Part-I within command area of Zone-I (Part B) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Div-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001246/2023-2024 | Camp-02_Basudebpur/AE/23- | 15/03/2024 | 30 | SWATI CORPORATION | 10.13 | 10.11 | 100
978 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000002/2025-2026 | 960/RCD-I | 23/04/2025 | 0 | Resource Division | 1617.14 | 0 | 0
979 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000003/2025-2026 | 961/RCD-I | 23/04/2025 | 0 | Resource Division | 191.48 | 0 | 0
980 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000039/2023-2024 | 2980/RCD-I | 12/10/2023 | 0 | Resource Division | 5756.61 | 0 | 0
981 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000041/2023-2024 | 3662/RCD-I | 28/12/2023 | 0 | Resource Division | 35.15 | 0 | 0
982 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000042/2023-2024 | 106/RCD-I | 10/01/2024 | 0 | Resource Division | 308 | 0 | 0
983 | Asansol Mechanical | Asansol Mechanical Division | Bulk power supply at 33kv to premises PHE DTE ,kalyaneswari WTP ,JL-01,plot-313,KALYANESWARI wtp area,paschim burdwan-713369 for an ultimate contract demand 2246kva | Assistant Engineer-I | Junior Engineer-4 | BILL/00130/2024-2025 | BP-2024-25-19 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 103.61 | 0 | 0
984 | Asansol Mechanical | Asansol Mechanical Division | Supply & Erection of 33 KV, S/C, Electrical Equipments & accessories related to the diversion of 33KV transmission line at Kalyaneswari W.T.P under Asansol Mechanical Division. P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000043/2024-2025 | 1087/AMD | 25/07/2024 | 160 | OHMS ELECTRICAL AND CO | 23.95 | 16.82 | 80
985 | Asansol Mechanical | Asansol Mechanical Division | Providing of lighting luminaries, electrical wiring of chlorine room with yard lighting arrangement of Dhanudi O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000044/2024-2025 | 1130/AMD | 30/07/2024 | 156 | CIEMENICS | 5.7 | 0 | 100
986 | Asansol Mechanical | Asansol Mechanical Division | Providing & Installation of Electrical Equipments For Sub-Station at Intake and Water Treatment Plant under Augmentation of RCFA Part-II Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000312/2023-2024 | 1687/AMD | 07/09/2023 | 366 | WEST BENGAL ENGINEERING CO. | 1704.7 | 1206.59 | 70
987 | Asansol Mechanical | Asansol Mechanical Division | Providing 33KV, 25KA, 1250A, 2 Panel VCB & 33KV Metering Arrangement & Relay Panel for Substation at Water Treatment Plant under Augmentation of RCFA Par-Il Piped W/S Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000527/2024-2025 | 148/AMD | 05/02/2025 | 30 | WEST BENGAL ENGINEERING CO. | 44.4 | 0 | 0
988 | Asansol Mechanical | Asansol Mechanical Division | Different Electro-mechanical works in connection with the execution of Electrical Sub-station and other works at Intake under Augmentation of RCFA Part-II Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-4 | ORD/000806/2024-2025 | 617/AMD | 13/03/2025 | 90 | WEST BENGAL ENGINEERING CO. | 119.63 | 0 | 0
989 | RCFA Division -I | Asansol Mechanical Division | Construction of Pumping Station at Itapara new H/W Site of Itapara Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000127/2020-2021 | 14 / RCD I | 08/01/2021 | 45 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 2.75 | 0 | 0
990 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-6 Segment) for augmentation of Itapara piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000161/2022-2023 | 1699/RCD-I | 13/07/2022 | 923 | UMA ENTERPRISE | 44.47 | 16.76 | 45
991 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000482/2021-2022 | 2346/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.82 | 2.82 | 0
992 | RCFA Division -I | Asansol Mechanical Division | Rising Main for Augmentation of Itapara Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000566/2022-2023 | 3277/RCD I | 20/12/2022 | 529 | DURGADAS MONDAL | 34.74 | 19.21 | 80
993 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of approach road, land development, CWR painting, Cable trench slab, drainage system at Runakuraghat H/W campus under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000859/2022-2023 | 1090/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 37.83 | 35.84 | 100
994 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Guard Room with toilet at Malladihi OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000967/2023-2024 | 717-A/RCD-I | 01/03/2024 | 90 | PINKI ENTERPRISE | 5.97 | 0 | 0
995 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Guard Room with toilet at Dabor OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000970/2023-2024 | 460/RCD-1 | 12/02/2024 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 5.97 | 0 | 0
996 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of valves, construction of valve chamber, supplying laying HDPE/UPVC/GI pipe line and allied works at Putulia, Hosenpur and adjacent area under Augmentation of Itapara W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000972/2023-2024 | 461/RCD-1 | 12/02/2024 | 30 | R B ENTERPRISE | 7.72 | 7.67 | 100
997 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of spout, repairing and restoration of pipe line, FHTC connection and allied land development works within distribution system under Malladihi OHR under Augmentation of Itapara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000986/2023-2024 | 469/RCD-1 | 12/02/2024 | 15 | ASHA CONSTRUCTION | 7.18 | 6.99 | 100
998 | RCFA Division -I | Asansol Mechanical Division | Continuation of work order for Conducting route survey , design rising main network and preparation & submission of source augmentation DPR for Itapara PWSS for Impementation of JJM at Barabani block under RCFA DIVISION-I P.H.E. Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001009/2023-2024 | 74/A/RCD-I | 02/01/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100
999 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Renovation of filter bed, changing of Media and allied works at Salanpur Dalmia OCP Project under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001070/2023-2024 | 101_A_RCD-I | 09/01/2024 | 15 | R B ENTERPRISE | 7.46 | 0 | 0
1000 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for raising height of tube well to encounter flood including surging of tube well, repairing work of collecting main at river Ajoy at Churulia under Augmentation of Itapara Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001087/2023-2024 | 876/RCD-I | 15/03/2024 | 15 | MD AAMIR KHAN | 4.09 | 0 | 100
1001 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000011/2023-2024 | 2207/RCD-I | 17/07/2023 | 0 | Resource Division | 160.38 | 0 | 0
1002 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000029/2022-2023 | 28/RCD-I | 10/01/2023 | 0 | Resource Division | 92.01 | 0 | 0
1003 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000032/2022-2023 | 121/RCD-I | 24/01/2023 | 0 | Resource Division | 222.41 | 0 | 0
1004 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000433/2022-2023 | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 62.07 | 68
1005 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying DI pipe at Shilampur under Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC of Gopalpur PWSS under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000064/2024-2025 | 1794/RCD-I | 24/07/2024 | 161 | MD AAMIR KHAN | 8.7 | 6.99 | 100
1006 | RCFA Division -I | Asansol Mechanical Division | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer-II | Junior Engineer-3 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 0.8 | 35
1007 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service connection charges for Kanksa Zone-II Part-A TW-1 | Assistant Engineer-II | Junior Engineer-3 | BILL/00164/2023-2024 | BP-2023-24-104 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.04 | 0 | 0
1008 | Durgapur W/S Division | Asansol Mechanical Division | Electricity charges for installation of service connection for Kanksa Zone-II Part-A TW-II | Assistant Engineer-II | Junior Engineer-3 | BILL/00165/2023-2024 | BP-2023-24-105 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0
1009 | Durgapur W/S Division | Asansol Mechanical Division | Quotation money for service connection Kanksa Zone-II Part-A TW-III | Assistant Engineer-II | Junior Engineer-3 | BILL/00166/2023-2024 | BP-2023-24-106 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0
1010 | Durgapur W/S Division | Asansol Mechanical Division | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | Assistant Engineer-II | Junior Engineer-3 | BILL/00441/2023-2024 | BP-2023-24-221 | 21/09/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 17.96 | 0 | 0
1011 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and other allied works at Madhabmat under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000001/2022-2023 | 659/DWSD | 22/04/2022 | 10 | BASANTI TRADERS | 10.58 | 8.45 | 100
1012 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-1 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000002/2022-2023 | 660/DWSD | 22/04/2022 | 10 | RANJIB GHATAK | 14.01 | 12.95 | 0
1013 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000003/2022-2023 | 653/DWSD | 22/04/2022 | 10 | JOY GURU ENTERPRISE | 14 | 11.75 | 0
1014 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000004/2022-2023 | 548/DWSD | 08/04/2022 | 10 | AHS R INFRA PRIVATE LIMITED | 14.04 | 13.02 | 0
1015 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 500 M3 capacity, 20 mtr staging height Over Head Reservoir at Madhabmat Tube well No-1 Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD , PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000005/2022-2023 | 571/DWSD | 12/04/2022 | 184 | SAIKAT RAY | 99.22 | 95.07 | 100
1016 | Durgapur W/S Division | Asansol Mechanical Division | Approach road & others necessary allied works at Madhabmat 2nd Pump house to 3rd Pump House ,Kanksa for Kanksa Zone-II/A W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000115/2023-2024 | 1057/DWSD | 20/07/2023 | 30 | A.K.D. ENTERPRISE | 25.4 | 25.36 | 100
1017 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0
1018 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at Railpar Sarada Pally near DVC Canal under command area of Kanksa Zone-II/Pt-A distribution main by modern trenches less technology through JACK Pushing method under Augmentation of RCFA part III Zone I piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000142/2023-2024 | 1272/DWSD | 07/08/2023 | 620 | SAIKAT RAY | 8.56 | 0 | 100
1019 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJN at Debipur mouza -87 and its adjoining area under command area of Augmentation of Kanksa (Zone-II/A ) piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-12) | Assistant Engineer-II | Junior Engineer-3 | ORD/000162/2022-2023 | 1032/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.99 | 4.99 | 0
1020 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-1 Tube well No-01(OHR Site) for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000195/2022-2023 | 1055/DWSD | 07/07/2022 | 25 | MUKHERJEE ENTERPRISE | 4.82 | 4.44 | 100
1021 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-2 Tube well No-02 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000196/2022-2023 | 1056/DWSD | 07/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 4.44 | 100
1022 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Madhabmat Pump house No-3 Tube well No-03 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000201/2022-2023 | 1063/DWSD | 08/07/2022 | 25 | A.K.D. ENTERPRISE | 4.82 | 4.42 | 100
1023 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of supplying ,laying of distribution system and providing functional house hold tap connection (FHTC) including reconnection of existing FHTC from AC pipe line to newly laid different dia HDPE pie line for Kanksa (zone-II/A) piped W/s Scheme under DWSD,PHE Dte (Augmentation Scheme) Dist.-Paschim Bardhhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000251/2022-2023 | 1361/DWSD | 20/09/2022 | 122 | SAIKAT RAY | 236.37 | 239.55 | 0
1024 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying and laying of 90/75 mm dia HDPE pipe and 63/50 mm dia UPVC pipe line with necessary allied work at Sundiara and Tilakchnadrapur mouza JL-63/67) under Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000408/2021-2022 | 312/DWSD | 11/03/2022 | 15 | SK. ABDUL HALIM | 9.12 | 9.11 | 0
1025 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Additional work for providing FHTC tap connection with jjm at Ijjatganj mouza(JL-71) and laying 125 mm dia HDPE and 63/50 mm dia UPVC pipe under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000409/2021-2022 | 333/DWSD | 15/03/2022 | 15 | RANJIB GHATAK | 29.48 | 29.65 | 0
1026 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Laying and aligning of distribution pipe line from zero point and allied works under Augmentation of Kanksa Zone-II/Part-A) piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000441/2022-2023 | 104/DWSD | 24/01/2023 | 20 | PAYAL CONSTRUCTION | 8.6 | 8.59 | 0
1027 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of balance work of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme with construction of boundary wall ,approach road,canal crossing ,leftout LDS,FHTC reconnection of FHTC at Kansa(Part),Debipur(Part),Panagarh(Part),Ijjatganj(Part), mouzas of JL-86,88,87,85 of Kanksa block under DWSD ,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000451/2022-2023 | 225/DWSD | 06/02/2023 | 90 | SAIKAT RAY | 197.71 | 163.93 | 100
1028 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-I tube well no-1 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000458/2021-2022 | 379/DWSD | 24/03/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 4.7 | 0
1029 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-II tube well no-2 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte(SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000459/2021-2022 | 583/DWSD | 25/03/2022 | 45 | GHOSH & ROY ENTERPRISE | 4.89 | 4.69 | 0
1030 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-III tube well no-3 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000461/2021-2022 | 385/DWSD | 25/03/2022 | 45 | A.K.D. ENTERPRISE | 4.89 | 4.7 | 0
1031 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of soil investigation for determing the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC elevated at Madhabmath Reservoir site of Augmentation of Kanksa (Zone-II/A) piped W.S Scheme under DWSD ,PHE DTe. | Assistant Engineer-II | Junior Engineer-3 | ORD/000470/2021-2022 | 354/DWSD | 21/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 0
1032 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-3,TW No-3) site under Augmentation of Kanksa Zone-II/Part-A piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000524/2022-2023 | 297/A/DWSD | 17/02/2023 | 30 | A.K.D. ENTERPRISE | 11.08 | 9.88 | 0
1033 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000009/2021-2022 | 307/DWSD | 15/03/2022 | 0 | Resource Division | 45.42 | 0 | 0
1034 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of Kanksa Zone - II/A Water Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000072/2023-2024 | 2571/CMD | 06/06/2023 | 580 | M/S. SWAPAN BANERJEE | 29.92 | 9.58 | 31
1035 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work of Augmentation of Kanksa Zone-ii/C piped W/s Scheme with construction of boundary wall renovation of all existing structure repairing of all water retaining structure left out LDS FHTC reconnection of FHTC at Kanksa (Part) ,Debipur (Part), Paragraph (Part), Prayagpur(Part) mouzas of JL-86,88,87 of Kanksa block under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000572/2022-2023 | 490/DWSD | 23/03/2023 | 45 | BRINDABAN KONAR | 94.94 | 3.85 | 100
1036 | Durgapur W/S Division | Asansol Mechanical Division | Quotation money for electrification service charges for Kanksa Zone-II/Part-B TW-I | Assistant Engineer-II | Junior Engineer-3 | BILL/00161/2023-2024 | BP-2023-24-101 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.56 | 0 | 0
1037 | Durgapur W/S Division | Asansol Mechanical Division | Electricity connection quotation fees for Kanksa Zone-II Part-B TW-2 | Assistant Engineer-II | Junior Engineer-3 | BILL/00162/2023-2024 | BP-2023-24-102 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0
1038 | Durgapur W/S Division | Asansol Mechanical Division | Service connection quotation money for Kanksa Zone- Part-B TW-3 | Assistant Engineer-II | Junior Engineer-3 | BILL/00163/2023-2024 | BP-2023-24-103 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.13 | 0 | 0
1039 | Durgapur W/S Division | Asansol Mechanical Division | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | Assistant Engineer-II | Junior Engineer-3 | BILL/00441/2023-2024 | BP-2023-24-221 | 21/09/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 17.96 | 0 | 0
1040 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Trail bore for sinking of 3(Three) Nos (300X200 mm dia ) big tube well of 210 mtr depth by DR method using UPVC pipe and UPVC deep well screen RDS at Kanksa (Zone-II) tube well site of Augmentation of Kanksa Zone-II/Part-B &C) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000037/2023-2024 | 771/DWSD | 22/05/2023 | 15 | JOY GURU ENTERPRISE | 4.81 | 4.81 | 0
1041 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Electrical wiring and other allied works for modernization of Gopalpur for Laboratory NABL accreditation of sub-District Water Testing Lab at Kanksa of Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000039/2023-2024 | 764/DWSD | 22/05/2023 | 15 | BASANTI TRADERS | 1.72 | 1.72 | 100
1042 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied works at Akandara covering Jemua and Paranganj area under Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme under DWSD, PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000100/2022-2023 | 765/DWSD | 13/05/2022 | 15 | AMAR CONSTRUCTION | 70.22 | 66.5 | 0
1043 | Durgapur W/S Division | Asansol Mechanical Division | Special repair and renovation of 1(One) No 450 M3 capacity RCC Elevated Reservoir (OHR) at OHR site boundary wall and 2 (Two) Nos Pump house at Kanksa (Zone-II/Part-B) under Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000114/2023-2024 | 1138/DWSD | 20/07/2023 | 30 | MAK CONSTRUCTION CO. | 35.76 | 9.09 | 80
1044 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0
1045 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of additional work for providing FHTC tap connecting with JJM at Prayagpur mouza -88 and its adjoining area under command area of Augmentation of Kanksa (Zoe-II/B_) piped W/S Scheme block Kanksa under DWSD,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000157/2022-2023 | 1025/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 5.03 | 0
1046 | Durgapur W/S Division | Asansol Mechanical Division | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa zone-II/Part-B) under Augmentation of Kanksa (Zone-II) (Part-B) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000159/2023-2024 | 1291/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 5.74 | 0 | 10
1047 | Durgapur W/S Division | Asansol Mechanical Division | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanksa zone-II/Part-B) under Augmentation of Kanksa (Zone-II) (Part-B) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000160/2023-2024 | 1292/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 6.02 | 0 | 100
1048 | Durgapur W/S Division | Asansol Mechanical Division | Laying & aligning of DI K9 rising main pipe line and interconnection of TW No-3 with OHR and other allied works of Augmentation of Kanksa Zone-II/Part-B piped W/s Scheme under DWSD ,PHE Dte (Pat-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000164/2023-2024 | 1295/DWSD | 07/08/2023 | 657 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 16.23 | 0 | 70
1049 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying distribution system and providing functional house hold tap connection (FHTC) including reconnection of exiting FHTC form AC pipe line to newly laid different dia pipe line for Kanksa (Zone-II/Part-B) under DWSD ,PHE Dte (Augmentation Scheme) | Assistant Engineer-II | Junior Engineer-3 | ORD/000252/2022-2023 | 1449/DWSD | 17/10/2022 | 123 | MD AAMIR KHAN | 217.39 | 222.62 | 0
1050 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of extensioin of pipe line from existing pipe line of Kanksa Zone-II PH-II W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Debipur mouza JL-87 ,Sharmapara ,Singh para under DWSD,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000285/2021-2022 | 1606/DWSD | 12/11/2021 | 20 | M/S. D. PALIT & CO. | 18.1 | 18.1 | 0
1051 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Z-II)(Ph-II) W/s Scheme to laying branch pipe line in kanksa block for providing FHTC at PanagarhJL_85) at Palpara ,Hazra Para ,Kumanrpara near TC pur Panchayat ,Panagarh bypass under DWSD PHE Dte (Sl-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000359/2021-2022 | 78/DWSD | 24/01/2022 | 15 | GITA CONSTRUCTION | 3.46 | 0 | 0
1052 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Guard wall at Madhabmat pukur par of Kanksa (Zone-II) piped W/s Scheme under DWSD, PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000428/2021-2022 | 405/DWSD | 30/03/2022 | 10 | TARA CONSTRUCTION | 4.38 | 2.71 | 100
1053 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Replacement of pipe line from existing pipe line of Kanksa (Zone-II) W/s Scheme at Madhabmat and near under bypass in Kanksa Block under DWSD, PHE Dte (Sl-4) | Assistant Engineer-II | Junior Engineer-3 | ORD/000431/2021-2022 | 411/DWSD | 30/03/2022 | 7 | SWATI CORPORATION | 3.13 | 3.14 | 0
1054 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Emergent supply fitting fixing of Sluice Valve for repairing and maintenance of pipe line under Kanksa (Zone-II) W/S Scheme under DWSD ,PHE Dte.(SL-06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000433/2021-2022 | 413/DWSD | 30/03/2022 | 10 | SWATI CORPORATION | 2 | 1.94 | 0
1055 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying and aligning of distribution pipe line from zero point to Jhanjra more and allied works under Augmentation of Kanksa Zone-II/Part-B) piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000443/2022-2023 | 302/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 13.91 | 13.91 | 0
1056 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 06 Nos 300X200 mm dia Tube well with 210 mtr Depth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Kanksa (Zone-II) Part-B,C tube well site of Augmentation of Kanksa Zone-II(Part-B & C) piped W/s Scheme under DWSD ,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000454/2022-2023 | 254/DWSD | 15/02/2023 | 60 | JOY GURU ENTERPRISE | 94.05 | 46.1 | 0
1057 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000010/2021-2022 | 327/DWSD | 15/03/2022 | 0 | Resource Division | 6.6 | 0 | 0
1058 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of Augmentation of Kanksa (Zone-II/Part-B) piped W/s Scheme with construction of boundary wall renovation of all existing structure ,repairing of all water retaining structure ,let-out LDS,FHTC,Re connection of FHTC at Kanksa (Part) ,Debipur(Part),Paragraph (Part), Prayagpur(Part) mouzas of JL No-86,88,87,88 of Kanksa block under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000475/2022-2023 | 238/DWSD | 08/02/2023 | 90 | MD AAMIR KHAN | 181.79 | 180.81 | 100
1059 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of Kanksa Zone - II/B Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000076/2023-2024 | 2572/CMD | 06/06/2023 | 30 | JAL PRAVAHIKA PVT LTD | 29.1 | 18.56 | 98
1060 | Central Mechanical | Asansol Mechanical Division | Supply & laying of cable for actuator of Tube well No ¿ 2 at Augmentation of Kanksa Zone -II/B water supply scheme under Central Mechanical Division PHE, Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001756/2023-2024 | 130/DIC/BMSD(D) | 29/02/2024 | 7 | JAL PRAVAHIKA PVT LTD | 0.86 | 0.86 | 100
1061 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Kiosk box and other allied work for Tube well No: 2 & 3 at Augmentation of Kanksa Zone -II/B water supply scheme under Central Mechanical Division PHE, Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001757/2023-2024 | 131/DIC/BMSD(D) | 29/02/2024 | 15 | JAL PRAVAHIKA PVT LTD | 0.58 | 0.58 | 100
1062 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000165/2022-2023 | 773/DWSD | 17/05/2022 | 45 | JOY GURU ENTERPRISE | 41.01 | 35.36 | 0
1063 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000253/2022-2023 | 1426/DWSD | 08/10/2022 | 10 | JOY GURU ENTERPRISE | 12.21 | 8.7 | 0
1064 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I Phe Dte. (Zone-9A) | Assistant Engineer 2 |  | ORD/000073/2023-2024 | 1760/RCD I | 16/05/2023 | 839 | ASHA CONSTRUCTION | 345.86 | 145.44 | 80
1065 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work and crossing road by trenchless technology in different site connection with distribution network including FHTC & allied work at Andal Block of Augmentation PWSS RCFA Part-II (Zone-9A) under RCFA Division-I PHE, Dte | Assistant Engineer 2 |  | ORD/000193/2024-2025 | 2420/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 69.72 | 18.46 | 100
1066 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Repairing of Boundary Wall for 45 mtr at Chora OHR Site of RCFA Part-II (Zone- 9, 9A and 9B) PWSS Block-Pandabeswar under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 2 |  | ORD/000916/2022-2023 | 1144/RCD-1 | 24/03/2023 | 15 | N.R. CONSTRUCTION | 4.61 | 1.86 | 100
1067 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-9A(Segment-III) under RCFA Division-I. PHE Dte. | Assistant Engineer 2 |  | ORD/001176/2023-2024 | 1016/RCD-I | 16/03/2024 | 45 | UNITED CONSTRUCTION | 35.76 | 19.29 | 70
1068 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000024/2023-2024 | 2951/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1069 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-08 at Andal under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00112/2024-2025 | 46/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.81 | 0 | 0
1070 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-10 under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00155/2024-2025 | 68/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 4.73 | 0 | 0
1071 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under RCFA Part-II PWSS (Zone-9) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000014/2024-2025 | 1516/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 99.5 | 99.5 | 100
1072 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply of different dia Sluice valve, including C.I. / D.I. Specials to the Searsole Store of RCFA Part-II (Zone-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000015/2024-2025 | 1518/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 77.57 | 77.57 | 100
1073 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Prt-II Pipe Water Supply scheme including FHTC & allied ork under RCFA Division-I PHE Dte. (Zone-9) Parshkol (Part-A) | Assistant Engineer 2 |  | ORD/000038/2023-2024 | 1607/RCD I | 25/04/2023 | 90 | MD AAMIR KHAN | 107.46 | 50.4 | 70
1074 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work related to shifting Rising main, laying of distribution network, Road restoration and other allied work for Ondal Block of Augmentation PWSS of RCFA Part-II (Zone - 9) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000199/2024-2025 | 2457/RCD-I | 01/10/2024 | 30 | M/S UNIT CONSTRUCTION | 45.22 | 0 | 100
1075 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Dedicated line towards Paharpur village, Kallya village and necessary repairing including supply of valve construction of valve chamber etc. within Distribution Network of Dabor OHR under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000395/2023-2024 | 2577/RCD-I | 07/09/2023 | 15 | DHRUBA ENTERPRISE | 9.05 | 7.3 | 100
1076 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of laying dia HDPE Pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-9 for Augmentation of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000517/2023-2024 | 2868/RCD-I | 06/10/2023 | 453 | MACHINO TECHNO | 89.05 | 23.11 | 50
1077 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line at Pure Jambad Hattala Zone, Real Jambad under Bahula (CT) (Jl No. 30, Block-Pandabeswar under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000593/2022-2023 | 3299/RCD I | 20/12/2022 | 60 | GITA CONSTRUCTION | 78.64 | 21.9 | 90
1078 | RCFA Division -I | RCFA Division I | Acceptance cum work order for 2 nos Emergency repairing work of 450mm dia rising main at Basu Vata and Jamdoba under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2 |  | ORD/000610/2023-2024 | 3376/RCD-I | 21/11/2023 | 15 | KHEPI MAA TRADERS | 2.16 | 2.16 | 100
1079 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 |  | ORD/000663/2023-2024 | 3432/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.86 | 6.86 | 100
1080 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Pump House at Dendua for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000696/2022-2023 | 487/RCDI | 03/02/2023 | 90 | D.S. ENTERPRISE | 30.3 | 23.52 | 77
1081 | RCFA Division -I | RCFA Division I | Emergency repairing work 750 mm dia Rising main at Kalyaneswari Dendua road under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000736/2023-2024 | Camp_02_Kalyaneswari_AE_I | 06/10/2023 | 15 | MD AAMIR KHAN | 2.75 | 2.67 | 100
1082 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repair and renovation works of one no RCC Elevated Reservoir of capacity 1362 cum at Chora for RCFA Part-II (Zone-9, 9A & 9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 |  | ORD/000844/2022-2023 | 1078/RCD I | 23/03/2023 | 270 | ASHA CONSTRUCTION | 17.06 | 14.88 | 100
1083 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied works under RCFA Division-I PHE Dte.(Zone-9) Parshkol (Part-B)(Sl No. 16) | Assistant Engineer 2 |  | ORD/000846/2022-2023 | 1081/RCD I | 23/03/2023 | 90 | ALOKESH BANERJEE | 40.44 | 13.78 | 35
1084 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Store Room at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 25) | Assistant Engineer 2 |  | ORD/000894/2022-2023 | 1168/RCD I | 24/03/2023 | 90 | M/S S.K. ENTERPRISE | 4.61 | 0 | 0
1085 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 2 |  | ORD/000915/2023-2024 | 212/RCD-I | 29/01/2024 | 90 | KALYAN DAWN | 4.57 | 0 | 100
1086 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000973/2022-2023 | 3148/RCD-I | 12/12/2022 | 7 | AMAR CONSTRUCTION | 0.98 | 0.98 | 100
1087 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000023/2023-2024 | 2949/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1088 | RCFA Division -I | RCFA Division I | Way leave permission for water supply poipe line for JJM carrier pipe dia 250 mm at Pandabeswar under Augmentation of RCFA PART-II (ZONE-8) under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00864/2024-2025 | 398/24-25 | 29/10/2024 | 0 | EASTERN RAILWAY | 1.19 | 0 | 0
1089 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-8) with Construction of 250 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman, (Sl No. 07). | Assistant Engineer 2 | Junior Engineer | ORD/000005/2023-2024 | 1402 RCD I | 12/04/2023 | 365 | PINKI ENTERPRISE | 95.85 | 86.37 | 65
1090 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 04 nos location (Bus stand/Taxi stand Domohani Bazar, Rural more, Near Domohani Electric Supply Office, BDO Office More) of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-6) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000231/2023-2024 | 2229/RCD-I | 17/07/2023 | 30 | UMA ENTERPRISE | 30.82 | 0 | 0
1091 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000296/2023-2024 | 2367/RCD-I | 04/08/2023 | 30 | R B ENTERPRISE | 47.39 | 40.66 | 86
1092 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of MS pipe carrier bridge, additional (Extra line) supplying, aligning & laying HDPE pipe line and other works of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000297/2023-2024 | 2368/RCD-I | 04/08/2023 | 60 | SWATI CORPORATION | 28.11 | 26.64 | 100
1093 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional (Extra line Node no. 550-550A, 555-548, 554-547, 527-321, 378-296, 397-423, 423-441) supplying, aligning & laying HDPE pipe line of RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000406/2023-2024 | 2588/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 7.55 | 7.46 | 100
1094 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Augmentation of RCFA Part-II (Zione-8) within command area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000522/2023-2024 | 2880/RCD-I | 06/10/2023 | 90 | SWATI CORPORATION | 10.6 | 10.6 | 100
1095 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 250 cum capacity RCC Over Head Reservoir at (Zone-8) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000561/2022-2023 | 3355/RCDI | 23/12/2022 | 777 | MOYTEC | 0.49 | 0.49 | 100
1096 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for crossing of 07 nos (Node Point :139-140,153-3,42-43,86-87,60-61, and 38-40 culvert/canal of by the side of PWD road under Improvement RCFA Part-I water Supply scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000720/2023-2024 | 3614/RCD-I | 20/12/2023 | 15 | TARA CONSTRUCTION | 3.32 | 0 | 0
1097 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000723/2023-2024 | 3612/RCD-1 | 20/12/2023 | 15 | SWATI CORPORATION | 2.78 | 0 | 0
1098 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Pump Houses (Size 14 mtr x 10 mtr x 8 mtr) under at Madanpur H/W Site under AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000724/2023-2024 | 3611/RCD-1 | 20/12/2023 | 567 | D.S.C. CONCERN | 35.91 | 16.6 | 50
1099 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000955/2023-2024 | 2455/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 0
1100 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Emergent dismantling of RCC Elevated Reservoir capacity 682 cum staging height 20 meter at Mohishila OHR within Asansol Municipal Corporation area of Augmentation PWSS of RCFA Part-II (Zone-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001018/2023-2024 | 519/RCD-I | 16/02/2024 | 45 | GITA CONSTRUCTION | 17.37 | 17.35 | 100
1101 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply & Delivery of GI pipe including loading , unloading and carriage to Searsole store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001022/2023-2024 | 626/RCD-I | 27/02/2024 | 20 | MAKALI ENGINEERING CORPORATION | 93.69 | 93.69 | 100
1102 | RCFA Division -I | RCFA Division I | Formal work order for Laying distribution system including FHTC for 5 (Two) nos uncovered village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part-II (zone-10) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001074/2023-2024 | 806/RCD-I | 13/03/2024 | 90 | UMA ENTERPRISE | 107.86 | 0 | 0
1103 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000022/2023-2024 | 2948/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1104 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-IV) under RCFA Division-I PHE Division-I PHE Dte. (Sl No. 08). | Assistant Engineer 2 | Junior Engineer | ORD/000053/2023-2024 | 1706/ RCD I | 03/05/2023 | 90 | DURGADAS MONDAL | 85.16 | 45.25 | 55
1105 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-10) with Construction of 350 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000099/2023-2024 | 1845/RCD-I | 31/05/2023 | 365 | RUBY CONSTRUCTION | 126.43 | 42.18 | 20
1106 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of DP Colony (450 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000533/2023-2024 | 3022/RCD-1 | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100
1107 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Rupnarayanpur (1182 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000534/2023-2024 | 3015/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100
1108 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Chora (1135Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000540/2023-2024 | 3025/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100
1109 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-10) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000562/2022-2023 | 3356/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
1110 | RCFA Division -I | RCFA Division I | Sub Soil investigation for 350 cum capacity RCC Over Head Reservoir at (zone-IX) of Barabani Block for Improvement of RCFA Part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. In the District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000580/2023-2024 | 2695/RCD-I | 27/09/2023 | 7 | MALLICK ENTERPRISE | 0.98 | 0 | 0
1111 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-XIII) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. In the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000582/2023-2024 | 2696/RCD-I | 27/09/2023 | 7 | JOY HIND TUBEWELLS | 0.98 | 0 | 0
1112 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Bidyanandapur of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000612/2023-2024 | 3377/RCD-I | 21/11/2023 | 15 | SIMA ENTERPRISE | 4.03 | 2.23 | 100
1113 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Jitpur Uttarrampur and surrounding villages within Jitpur Uttarrampur Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000654/2023-2024 | 3451/RCD-I | 24/11/2023 | 15 | DIP ENTERPRISE | 4.49 | 4.38 | 100
1114 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying and distribution system for Improvement of RCFA Part-I Water Supply Scheme under Command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000683/2023-2024 | 3472/RCD-I | 28/11/2023 | 30 | GITA CONSTRUCTION | 95.09 | 70.58 | 100
1115 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line (left out portion) including adopting trench less technologies and other allied works at Moul Danga village under Barabani Block of Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000685/2023-2024 | 3284/RCD-1 | 08/11/2023 | 30 | SRI KRISHNA ENTERPRISE | 19.21 | 16.46 | 100
1116 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-III) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000851/2022-2023 | 1112/ RCD I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 86.38 | 65.24 | 75
1117 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-II) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000855/2022-2023 | 1113/ RCD I | 23/03/2023 | 1174 | M/S KONAR CONSTRUCTION | 84.65 | 11.07 | 50
1118 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-I) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000860/2022-2023 | 1115/ RCD I | 23/03/2023 | 90 | M/S B.K. CONSTRUCTION | 86.29 | 32 | 38
1119 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-VI) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000866/2022-2023 | 1108/RCD-I | 23/03/2023 | 90 | VISUVIOUS | 54.47 | 47.84 | 90
1120 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-V) under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 2 | Junior Engineer | ORD/000867/2022-2023 | 1110/RCD-I | 23/03/2023 | 90 | DIP CONSTRUCTION | 90.17 | 31.53 | 35
1121 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance Work of different work to Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000962/2023-2024 | 506/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 82.78 | 82.05 | 100
1122 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000026/2023-2024 | 2955/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1123 | RCFA Division -I | RCFA Division I | Restoration work for laying of under ground water supply line (400 mm dia) Ch. 0.100 kmp to ch 1.350 on Ukhra Haripur (0-5) road in the district of Pachim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00463/2023-2024 | 235/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 32.64 | 0 | 0
1124 | RCFA Division -I | RCFA Division I | Formal work order Distribution Network including FHTC & alied work at Ondal Block of RCFA Part-II (Zone-12A) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000065/2023-2024 | 1764/RCD I | 16/05/2023 | 962 | MRITYUNJOY MUKHERJEE & CO. | 610.49 | 195.98 | 70
1125 | RCFA Division -I | RCFA Division I | Formal work for Construction of 1000 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connetion and cost of pipes,specials at Ondal Block (Zone-12A) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil investigation and chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. in District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000096/2023-2024 | 1847/RCD-I | 31/05/2023 | 366 | M/S PIONEER CONSTRUCTION | 203.2 | 203.2 | 100
1126 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Pancgachia (240 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2023-2024 | 3017/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 4.92 | 100
1127 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 1000 cum capacity RCC Over Head Reservoir at (Zone-12A) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000578/2022-2023 | 3366/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
1128 | RCFA Division -I | RCFA Division I | Formal work order for distributionn network for RCFA Part-II piped Water Supply Including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-12B)(Segment-1) | Assistant Engineer 2 | Junior Engineer | ORD/000805/2022-2023 | 931/RCDI | 14/03/2023 | 60 | ARISTOCON ENGINEER'S CO-OP. SOCIETY LTD. | 157.79 | 128.25 | 82
1129 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000028/2023-2024 | 2946/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1130 | RCFA Division -I | RCFA Division I | 100 mm dia water pipe line with 600 mm dia MS Casing pipe line (Jal Jeevan Mission) by R.C.F.A Division-1, PHE DTE, Asansol in between Parasia Siding ¿ New Jambad Siding at Km. CB-2/15-16 in Asansol Division of Eastern Railway under AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | Assistant Engineer 2 | Junior Engineer | BILL/00863/2024-2025 | 396/24-25 | 28/10/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0
1131 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work of allied items at Andal OHR Site under Phase-II/B under RCFA Division-I PHE Dte. AUGMENTATION PWSS OF RCFA PART-II (Zone-12B) | Assistant Engineer 2 | Junior Engineer | ORD/000063/2024-2025 | 1647/RCD-I | 04/07/2024 | 15 | AMAR CONSTRUCTION | 5.25 | 5.25 | 100
1132 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Barabani (910 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000539/2023-2024 | 3018/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.95 | 4.95 | 100
1133 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Shankarpur under Pandabeswar H/W Site within Pandabeswar Block for Augmentation of PWSS of RCFA Part-II (Zone-12B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000558/2024-2025 | 162/RCD-I | 08/01/2025 | 90 | DIP CONSTRUCTION | 34.75 | 0 | 0
1134 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-12B)(Segment-2). | Assistant Engineer 2 | Junior Engineer | ORD/000631/2022-2023 | 485/RCDI | 03/02/2023 | 60 | M/S SINGH & KONAR CONSTRUCTION | 155.21 | 92 | 80
1135 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-12 A) Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000669/2023-2024 | 3436/RCD-1 | 24/11/2023 | 60 | MRITYUNJOY MUKHERJEE & CO. | 81.28 | 48.77 | 65
1136 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work Balance work of Road restoration in connection with laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 mm NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000941/2023-2024 | 500/RCD-I | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 54.54 | 54.54 | 100
1137 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied works of laying distribution system of balance work of supply & laying of HDPE pipe under Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000942/2023-2024 | 498/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 78.67 | 76.89 | 100
1138 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of restoration approach road in Amritnagar Zone-I for Augmentation of RCFA Part-II under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000948/2023-2024 | 499/RCDI | 12/02/2024 | 30 | MACHINO TECHNO | 24.72 | 24.7 | 100
1139 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000029/2023-2024 | 2945/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1140 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-92 at Ukhra under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00115/2024-2025 | 48/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 16.46 | 0 | 0
1141 | RCFA Division -I | RCFA Division I | 6 lanning of Barwa-Adda Panagarh Section of NH-2 from Km. 398.240 to km 521.120 including Panagarh Bypass in the states of Jharkhand and West Bengal under NHDP Phase V on Toll on DBFOT pattern : Proposal for laying of under ground water pipeline of RCFA Division-I PHE Dte along & across NH-19 (Old NH-2) in the stretches along from Km 485+400 to Km 489+050 (LHS) , Km 486+427 to Km 488+599 (RHS) & km 488+651 to Km 489+100 (RHS) & across at Km 486+910 & km 488+854, District Pachim Bardhaman : Deposition of fees - reg. | Assistant Engineer 2 | Junior Engineer | BILL/00173/2025-2026 | 218/25-26 | 30/07/2025 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 33.2 | 0 | 0
1142 | RCFA Division -I | RCFA Division I | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-57 Payment of wayleave facility charges. | Assistant Engineer 2 | Junior Engineer | BILL/00546/2024-2025 | 273/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 9.09 | 0 | 0
1143 | RCFA Division -I | RCFA Division I | Restoration work for laying of 450 mm D.I. K9 pipeline under JJM work within the paved carriageway from Ch. 0.000 km to Ch. kmp at Right Side, Ch 03.006 km to Ch. 3.206 kmp at left side & ch. 4.570 km to Ch. 5.000 kmp at left side of Ukhra-Haripur Road under Asansol Division, PWD in the district of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00880/2024-2025 | 401/24-25 | 11/11/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 24.61 | 0 | 0
1144 | RCFA Division -I | RCFA Division I | Proposal for laying of underground water pipeline of R.C.F.A Division-I, P.H.E Dte. along & across NH-19 (Old NH-2) in the stretches - along from Km 485+400 to Km 489+050 (LHS), Km 486+427 to Km 488+599 (RHS) & Km 488+651 to Km 489+100 (RHS) & across at Km 486+910 & Km 488+854, Dist-Paschim Bardhaman, West Bengal. for Bank Guarantee | Assistant Engineer 2 | Junior Engineer | BILL/01330/2025-2026 |  | 29/10/2025 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 19.89 | 0 | 0
1145 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Pipe Water Supply Scheme (Zone-15) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000101/2023-2024 | 1843/RCD-I | 31/05/2023 | 365 | GITA CONSTRUCTION | 150.65 | 0 | 0
1146 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-15) | Assistant Engineer 2 | Junior Engineer | ORD/000254/2023-2024 | 2299/RCD-I | 24/07/2023 | 892 | SWATI CORPORATION | 516.27 | 197.04 | 100
1147 | RCFA Division -I | RCFA Division I | Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000321/2023-2024 | Camp-02-Sign-Board-AE-II | 30/06/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 15.83 | 70
1148 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work for bridge at Chalbalpur in connection with the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000514/2023-2024 | 2865/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 70.4 | 52.84 | 100
1149 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 100 cum & allied work at Bagdiha under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000520/2023-2024 | 2877/RCD-I | 06/10/2023 | 90 | M/S KALYANI ENTERPRISE | 18.69 | 0 | 0
1150 | RCFA Division -I | RCFA Division I | Acceptance Order for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC within command area of Zone-15 under JAMURIA Block in the district of Paschim Bardhhaman under RCFA Division - I PHE Dte. [PART-C] | Assistant Engineer 2 | Junior Engineer | ORD/000526/2025-2026 | 2148/RCD-I | 28/07/2025 | 216 | UNITED CONSTRUCTION | 129.89 | 0 | 55
1151 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-15) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000563/2022-2023 | 3357/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 0
1152 | RCFA Division -I | RCFA Division I | Formal work order for construction of CWR 150 cum, sub station building of H/W site, pump house, chlorine room and other allied work (Bank of Ajoy river) under Semalya water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000917/2022-2023 | 1216/RCDI | 24/03/2023 | 1320 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 120.09 | 75.06 | 100
1153 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000034/2023-2024 | 2940/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1154 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 73.08 | 70
1155 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 (Four) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Amritnagar Water Supply Scheme (Phase-I & II) under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000367/2022-2023 | 2875/RCD-I | 07/11/2022 | 30 | NIYATI CONSTRUCTION | 24.5 | 17.68 | 0
1156 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency Sinking of 04 (Four) nos. 200 mm dia river bed tube well including collecting main for in the river Damodar of Amritnagar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000389/2023-2024 | 2575/RCD-I | 07/09/2023 | 323 | M/S UNITED CONSTRUCTION | 6.75 | 6.13 | 100
1157 | RCFA Division -I | Asansol Mechanical Division | Acceptence cum work order for Dismantling & reconstruction of flooring of pump house, CWR and other allied works at H/W site of Tirat Colliery under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000402/2023-2024 | 2584/RCD-I | 07/09/2023 | 15 | MS KALYAN ENTERPRISE | 5.16 | 5.1 | 100
1158 | RCFA Division -I | Asansol Mechanical Division | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (sL no. 01) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000534/2021-2022 | 500/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 0
1159 | RCFA Division -I | Asansol Mechanical Division | Formal work order for laying of distribution system to accommodate FHTC and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe with all necessary specials, saddle piece etc. all complete at Egara, Amkula and part of Nimcha Mouza Part-B) for Augmnentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Division I, PHE Dte.under RCFA Division I,PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000603/2022-2023 | 37/RCD I | 11/01/2023 | 760 | TARAPRASAD SARKAR | 164.7 | 43.33 | 50
1160 | RCFA Division -I | Asansol Mechanical Division | Formal work order for laying of distribution system to accommodate FHTC and proving FHTC including supplying, laying,fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe wth all necessary specials, saddle piece etc all complete at Murgasole mouza for augmentation of Sub surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000605/2022-2023 | 35/RCD I | 11/01/2023 | 90 | DAS & CHAKRABORTY | 113.18 | 45.55 | 0
1161 | RCFA Division -I | Asansol Mechanical Division | Acceptance work order for sinking of 6 nos river bed 200 dia tube well including laying of collecting main for augmentation of sub surface water based piped water supply scheme for Amritnagar Zone-I within RCFA Part-II area under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000614/2022-2023 | 3272/RCDI | 20/12/2022 | 30 | M/S MONDAL CONSTRUCTION | 13.37 | 13.37 | 100
1162 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work for Laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000951/2023-2024 | 478/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 44.86 | 31.52 | 80
1163 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for supply and laying HDPE pipe instead of DI pipe for the work of laying distribution system under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000952/2023-2024 | 501/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 30.11 | 15.98 | 50
1164 | RCFA Division -I | Asansol Mechanical Division | Laying of distribution system to accommodation FHTC and providing FHTC including supplying, laying, fitting fixing of 15mm NB PVC (schedule 80) /20 mm OD HDPE (PE ,PN6) pipe with all necessary specials.saddle piece etc all complete at Egara, Amkula and part of Nimcha mouza for Improvement of RCFA Part-II Water Supply Scheme under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000607/2022-2023 | 36/RCD I | 11/01/2023 | 45 | M/S SINGH & KONAR CONSTRUCTION | 167.84 | 31.26 | 55
1165 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for adopting trench less technology (e.g. Jack Pushing Method etc) at i) Opposite Amritnagar OHR, ii) near Nimcha Kata More, iii) near Mincha Rail gate and allied MS work, supply of valves, specials etc at Murgathole Mouza under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000641/2023-2024 | 3421/RCD-1 | 24/11/2023 | 147 | DAS & CHAKRABORTY | 33.99 | 0 | 100
1166 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Pipe line crossing adopting trench less Technology (e.g. Jack Pushing method etc.) near Deshbandhu Park, Chittaranjan Road, Joadbari Rupnarayanpur from node no 921 to 924 RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000979/2023-2024 | 494/RCD-I | 12/02/2024 | 15 | KONAR CONSTRUCTION | 6.55 | 6.55 | 100
1167 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying of DI pipe under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000985/2023-2024 | 473/RCD-I | 12/02/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 8.65 | 2.84 | 80
1168 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000991/2023-2024 | 481/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 32.24 | 80
1169 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Laying of Distribution System to Accommodate FHTC and Providing FHTC including Supplying laying, fitting, fixing of 15 mm NB PVC (Schedule 80) 20 mm OD HDPE (PE 100, PN 6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001036/2022-2023 | 2455./RCD-I | 02/11/2022 | 180 | MACHINO TECHNO | 130.76 | 104.24 | 90
1170 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000021/2022-2023 | 3126 | 09/12/2022 | 0 | Resource Division | 86.94 | 0 | 0
1171 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at New Damalia Pump House under Amritnagar Zone-I, within RCFA Part-II Area Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000073/2024-2025 | 1204/AMD | 07/08/2024 | 45 | M/S JIT ENTERPRISE | 4.09 | 3.95 | 100
1172 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and allied Works at Damalia under Augmentation of Amritnagar Zone-I Water Supply Scheme, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000432/2022-2023 | 484/AMD | 22/02/2023 | 365 | ORIENTAL ENGINEERING CO. | 114.65 | 72.08 | 100
1173 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 33.78 | 100
1174 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work of supplying ,laying and aligning of HDPE Distribution pipeline & allied works including functional household tap connection (FHTC) at Pathanpara command area for Augmentation of Ground Water Based Water Supply Scheme for Telipara under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000385/2025-2026 | 1759/RCDI | 18/06/2025 | 166 | MAK CONSTRUCTION CO | 76.14 | 0 | 50
1175 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work of laying distribution system, New FHTC and re connection of FHTC at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000455/2025-2026 | 2010/RCD-I | 11/07/2025 | 30 | M/S KALYANI ENTERPRISE | 18.97 | 0 | 0
1176 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Switch Room (5.4 m x 3.6 m) at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000615/2025-2026 | 2011/RCD-I | 11/07/2025 | 90 | MOUMITA ENTERPRISE | 6.73 | 0 | 0
1177 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work for supplying laying and aligning of HDPe distribution pipe line and allied works including FHTC and connection providing to Raghunathpur mouzas JL-39 and Paschim Gangarampur mouzas JL-92 of Augmentation of Telipara W/s Scheme under DWSD under DWSD ,PHE Dte (SL-15) | Assistant Engineer-II | Junior Engineer-3 | ORD/000019/2023-2024 | 713/DWSD | 11/05/2023 | 60 | M/S PROCHESTA ENTERPRISE | 171.21 | 145.6 | 100
1178 | Durgapur W/S Division | Asansol Mechanical Division | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/000072/2023-2024 | 1059/DWSD | 12/07/2023 | 30 | JOY GURU ENTERPRISE | 19.4 | 0 | 0
1179 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying & aligning of HDPE distribution pipe line and allied works including Functional House Holds Tap connectin (FHTC ) and connection providing to Jamdoba Mouza-40 and Telipara Mouza- JL-41 of Telipara block -Kanksa under TELIPARA piped W/s Scheme under DWSD, PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000097/2022-2023 | 648/DWSD | 21/04/2022 | 25 | M/S SANTANU PALIT & CO. | 127.01 | 20.48 | 75
1180 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of 1(One) No PWD road crossing at JAMDOBA under command area of Telipara distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte (Part-C) | Assistant Engineer-II | Junior Engineer-3 | ORD/000144/2023-2024 | 1273/DWSD | 07/08/2023 | 15 | SK. ALIM | 8.74 | 8.74 | 100
1181 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000166/2022-2023 | 774/DWSD | 17/05/2022 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 2.01 | 100
1182 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipeline and allied works including FHT C and connection providing to Jamdoba mouzaJLNo-40 andTelipara MouzaJL-41of Telipara W/s Scheme udner DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000210/2023-2024 | 1089/DWSD. | 13/07/2023 | 45 | MAK CONSTRUCTION CO. | 93.52 | 90.71 | 100
1183 | Durgapur W/S Division | Asansol Mechanical Division | Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000231/2023-2024 | 1559/DWSD | 20/09/2023 | 10 | M/S MONDAL ENTERPRISE | 3.55 | 1.01 | 100
1184 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying aligning and laying of 150/250 mm dia MS pipe at Telipara under Augmentation of Telipara piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000273/2023-2024 | 1560/DWSD | 20/09/2023 | 10 | M/S MONDAL ENTERPRISE | 3.55 | 0 | 0
1185 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of modernization of the existing Gopalpur Lab for NABL accreditation of Sub-district water testing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000363/2021-2022 | 87/DWSD | 27/01/2022 | 15 | BASANTI TRADERS | 4.39 | 4.12 | 100
1186 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000472/2021-2022 | 1631/DWSD | 18/11/2021 | 15 | SHWET BARANI | 3.99 | 0 | 100
1187 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work for supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to JAMDOBA mouzas JL-40 and Paschim Telipara mouzas JL-41 of Augmentation of Telipara W/s Scheme under DWSD under | Assistant Engineer-II | Junior Engineer-3 | ORD/000604/2022-2023 | 501/DWSD | 27/03/2023 | 60 | M/S SANTANU PALIT & CO. | 93.42 | 16.88 | 80
1188 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000002/2023-2024 | 1576/CMD | 04/04/2023 | 30 | C.M. ENTERPRISE | 9.49 | 9.26 | 100
1189 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Telipara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000155/2022-2023 | 3143/CMD | 29/11/2022 | 30 | M/S. SWAPAN BANERJEE | 9.56 | 9.22 | 100
1190 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying of pipe line (Left Out) with HDPE pipe with FHTC at Seterbundhu, Kanksa Colony & Subhaspally within command area of Kanksa Zone-II/C PWSS with reconnection of existing FHTC and other allied works of Augmentation of Napara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000219/2025-2026 | 1441/RCD-I | 15/05/2025 | 45 | MAK CONSTRUCTION CO | 27.33 | 0 | 100
1191 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of RCC Conduit for crossing of HDPE Rising Main across the Kunur river at Jemua Augmentation of Ground Water Based Water Supply Scheme for Napara under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000223/2024-2025 | 2542/RCD-I | 29/10/2024 | 90 | ASHA CONSTRUCTION | 64.49 | 0 | 50
1192 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Sukna with Boundary wall, Pump House & other allied works of Augmentation of ground water based water supply scheme for Napara under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000295/2024-2025 | 2625/RCD-I | 14/11/2024 | 137 | UNITED CONSTRUCTION | 27.73 | 9.41 | 60
1193 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Dhobaghata with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Napara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000357/2024-2025 | 2848/RCD-I | 04/12/2024 | 309 | UNITED CONSTRUCTION | 54.09 | 0 | 60
1194 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 500 cum & allied work at Pansuili Head Works Site under Augmentation of Ground Water Based Water Supply Scheme for Napara W/S Scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-3 | ORD/000359/2024-2025 | 2851/RCD-I | 04/12/2024 | 362 | BABA LOKNATH ENTERPRISE | 63.91 | 5.82 | 40
1195 | RCFA Division -I | Asansol Mechanical Division | Formal work order for creating separate zone for Adibasipara near WTP Panagarh, supplying, laying of 160 mm dia HDPE distribution pipe line and other allied works at Anandapur, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), at Bistupur and Dannay. Mohal & Sinking of 2 Nos 300 X 200 MM dia RBT tube well at Silampur under Augmentation of Kanksha (Zone-I & II), Augmentation of RCFA Part-III (Zone-II), Augmentation of ground water based water supply scheme Napara under RCFA Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/001024/2023-2024 | 662/RCD-I | 29/02/2024 | 90 | SARASWATI ENTERPRISE | 119.89 | 105.01 | 100
1196 | RCFA Division -I | Asansol Mechanical Division | Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Telipara PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer-I | Junior Engineer-3 | ORD/001028/2023-2024 | 684_RCD-1 | 29/02/2024 | 184 | MALLICK ENTERPRISE | 1.64 | 0 | 0
1197 | RCFA Division -I | Asansol Mechanical Division | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of Augumentation of Napara piped W/S Scheme,under D.W.S.D., P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/001039/2022-2023 | 327/DWSD | 20/02/2023 | 35 | DARPAN DAS & CO | 70.42 | 66.42 | 75
1198 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL90) under Augmentation of Napara Piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) | Assistant Engineer-I | Junior Engineer-3 | ORD/001189/2023-2024 | 1014/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 96.46 | 0 | 0
1199 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of construction of pump house cum chlorine room at Silampur pump house No-I H/W site for of Kanksa (Zone-I) Under Augmentation of Napara P piped W/s Scheme under DWSD,PHE Dt | Assistant Engineer-I | Junior Engineer-3 | ORD/001236/2023-2024 | 1279_DWSD | 07/08/2023 | 45 | MUKHERJEE ENTERPRISE | 6.41 | 6.41 | 100
1200 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 350 M3 OHR of 20 mtr staging height as per Deptt drawing laying aligning of Rising main and providing of FHTC connection of all mouzas under command area of Augmentation of Napara piped W/s Scheme under DWSD ,PHE Dte . | Assistant Engineer-I | Junior Engineer-3 | ORD/000018/2023-2024 | 712/DWSD | 11/05/2023 | 60 | SK. ALIM | 307.16 | 264.06 | 100
1201 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 2 Nos tube well 300 mm X 200 mm tube well of 210 mtrs depth by Direct rotary rig method using UPVC Piped CD and UPVC Deep well screen RDS filter at Napara site under Block-Kanksa under Augmentation of Napara piped W/s Scheme under DWD ,PHE Dte | Assistant Engineer-I | Junior Engineer-3 | ORD/000170/2023-2024 | 1301/DWSD | 07/08/2023 | 30 | SK. ALIM | 31.47 | 19.19 | 100
1202 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Napara Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000057/2023-2024 | 2517/CMD | 02/06/2023 | 30 | SOUNAK ENTERPRISE | 23.32 | 22.49 | 100
1203 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL Procedure-A (2010) ON Turn key/ Full deposit basis for the site of Napara Sukhna Pump House no-4, under Kanksa Block under Panagarh CCC supply office | Assistant Engineer-I | Junior Engineer-3 | BILL/00077/2024-2025 | BP-2024-25-13 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0
1204 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL Procedure-A (2010) for the site of Napara TW No-03, Dhobaghata. | Assistant Engineer-I | Junior Engineer-3 | BILL/00585/2024-2025 | BP-2024-25-67 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.48 | 0 | 0
1205 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Dhobi Ghat) & TUBE WELL NO-4 (Sukna) AT NAPARA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-I | Junior Engineer-3 | ORD/000323/2024-2025 | 1816/AMD | 29/10/2024 | 214 | SINHA ELECTRICALS | 25.96 | 0 | 100
1206 | RCFA Division -I | RCFA Division I | Installation of Jio Fiber connection for Six months under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | BILL/00329/2024-2025 | 153/24-25 | 19/07/2024 | 0 | MUKHERJEE TRADERS | 0.07 | 0 | 0
1207 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Gourbazar, Bindudihi, Hosenpara villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl NO. 05) | Assistant Engineer 1 | Junior Engineer | ORD/000142/2022-2023 | 1436/RCD I | 27/06/2022 | 45 | M/S S.K. ENTERPRISE | 4.97 | 4.48 | 0
1208 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 0 | 0
1209 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Gourbazar Village, Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000191/2021-2022 | 1865/RCD-I | 28/10/2021 | 30 | M/S S.K. ENTERPRISE | 13.17 | 12.21 | 0
1210 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Putulia (Part), Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000192/2021-2022 | 1866/RCD-I | 28/10/2021 | 30 | VISUVIOUS | 12.85 | 10.95 | 0
1211 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000006/2025-2026 | 2545/RCD-I | 01/09/2025 | 0 | Resource Division | 1.09 | 0 | 0
1212 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000008/2021-2022 | 437/RCD-I | 21/02/2022 | 0 | Resource Division | 2.75 | 0 | 0
1213 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and delivery of C.I. Sluice valve and D.I Specials under Improvement of RCFA part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000055/2023-2024 | 1729/RCD-1 | 08/05/2023 | 10 | SSPR VALVE MANUFACTURING PVT LTD | 45.31 | 45.31 | 100
1214 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Requirement of different type water regulating apparatus including water leakage protection apparatus etc. for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000056/2023-2024 | 1730/RCD-1 | 08/05/2023 | 10 | MAKALI ENGINEERING CORPORATION | 45.99 | 45.99 | 0
1215 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for laying & pushing of 600 to 1000 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) and MS pipe including supply of collar and allied work at Ethora Nuni more Panchgachiya and Lalganj more in connection to rising main Part-B under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000218/2023-2024 | 2224/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 30.17 | 25.6 | 100
1216 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying of 450 mm dia distribution main under Lalganj Bridge by concrete conduit and allied MS work in connection to distribution network of Zone-XI (Part-1) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000251/2023-2024 | 2237/RCD-1 | 17/07/2023 | 30 | R B ENTERPRISE | 16.06 | 13.45 | 100
1217 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Route Survey and Preparation of DPR for Augmentation of Churulia Piped Water Supply Scheme, Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block., District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000716/2023-2024 | 3373/RCD-1 | 21/11/2023 | 15 | APEX ENGINEERING | 3.61 | 3.61 | 100
1218 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of stand post on emergency basis at Rupnarayanpur, Rangamati area of Rupnarayanpur Zone under 4 Nos. retrofitting PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000987/2022-2023 | 1266/RCD-1 | 27/03/2023 | 15 | B.B. CONSTRUCTION | 2.8 | 2.78 | 0
1219 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Separate connection for Ijjatgunj OHR Kanksa Zone-II (Part-C) under RCFA Division - I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000141/2024-2025 | 2245/RCD-I | 11/09/2024 | 30 | COMPUTER MEDIA | 6.62 | 0 | 70
1220 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-D) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer-II | Junior Engineer-3 | ORD/001033/2023-2024 | 688/RCD-1 | 29/02/2024 | 184 | AMARANJALI CONSTRUCTION | 1.79 | 0 | 0
1221 | Durgapur W/S Division | Asansol Mechanical Division | Replacement of damaged PCC pole with allied work. | Assistant Engineer-II | Junior Engineer-3 | BILL/00032/2023-2024 | BP-2023-24-24 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.69 | 0 | 0
1222 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied work at Kanchanpur and Kanksa under command area of Augmentation of Kanksa Zone-II/C piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000013/2023-2024 | 677/DWSD | 03/05/2023 | 673 | JOY GURU ENTERPRISE | 29.76 | 28.62 | 100
1223 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0
1224 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Guard room cum rest shed at Kanksa Ijjatganj 2nd Pump house site of Augmentation of Kaksa (Zone-II) /Part-C) piped W/S Scheme under DWSD,PHE Dte (SL-09) | Assistant Engineer-II | Junior Engineer-3 | ORD/000123/2022-2023 | 785/DWSD | 18/05/2022 | 15 | BASANTI TRADERS | 4.99 | 4.05 | 0
1225 | Durgapur W/S Division | Asansol Mechanical Division | Repairing and renovation of pump house with sanitary arrangement as well as boundary wall at H/W site (Ijjatganj OHR) of Augmentation of Kaksa (Zone-II/Pt-C) piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | ORD/000124/2023-2024 | 1198/DWSD | 27/07/2023 | 30 | MAITO MAA ENTERPRISE | 14.93 | 0 | 0
1226 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at kanksa underpass under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000143/2023-2024 | 1274/DWSD | 07/08/2023 | 633 | MRITYUNJOY MUKHERJEE AND CO | 12.05 | 0 | 100
1227 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangemnt at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000147/2023-2024 | 1277/DWSD | 07/08/2023 | 45 | PRADIP CHOUDHARY | 5.83 | 0 | 100
1228 | Durgapur W/S Division | Asansol Mechanical Division | 1(One) No PWD road crossing SH-34 at Mini bazar more under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000155/2023-2024 | 1286/DWSD | 07/08/2023 | 633 | MACHINO TECHNO | 10.92 | 0 | 100
1229 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order Additional work for providing FHTC tap connection with JJM at Kanksa mouza-89 and its adjoing are a under command area of Augmentation of Kanksa Zone-II/C W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000156/2022-2023 | 1024/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 0
1230 | Durgapur W/S Division | Asansol Mechanical Division | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanchanpur of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000161/2023-2024 | 1293/DWSD | 07/08/2023 | 45 | MAJI DEVELOPERS | 6.09 | 0 | 100
1231 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Kanksa (Zone-II) piped W/S Scheme DWSD,PHE Dte.(SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000181/2021-2022 | 1601/DWSD | 12/11/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 19.55 | 19.55 | 0
1232 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Repairing of MS structural and supplying hoisting 2000 Liters PVC water storage tank and others allied works at Kanksa of Augmentation of Kanksa (Zone-II/C) W/s Scheme under DWSD,PHE Dte (SL-07) | Assistant Engineer-II | Junior Engineer-3 | ORD/000200/2022-2023 | 1062/DWSD | 08/07/2022 | 25 | SWATI CORPORATION | 3.53 | 3.24 | 100
1233 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying of distribution system and providing FHTC including reconnection of exiting FHTC from AC pipe line to newly laid different dia HDPE pipe line for Augmentation of Kanksa (Zone-II/Part-C) piped W/S Scheme under DWSD ,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000211/2022-2023 | 1161/DWSD | 01/08/2022 | 4 | BRINDABAN KONAR | 216.66 | 187.07 | 80
1234 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Additional FHTC in connection with JJM for Prayagpur (CT) mouza (JL-88) under command area of Kanksa (Zone-II)(Ph-II) W/S Scheme at Kanksa block under DWSD PHE Dte . | Assistant Engineer-II | Junior Engineer-3 | ORD/000312/2021-2022 | 1766/DWSD | 16/12/2021 | 30 | B. T. M. CONCERN | 19.37 | 19.61 | 0
1235 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000348/2021-2022 | 199/DWSD | 16/02/2022 | 15 | GITA CONSTRUCTION | 9.72 | 9.01 | 0
1236 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Providing water supply to Birudiha High school under Kanksa block covered by Kanksa (Zone-II) having electricity but uncovered by PWSS under DWSD, PHE Dte (SL-26) | Assistant Engineer-II | Junior Engineer-3 | ORD/000382/2021-2022 | 120/DWSD | 01/02/2022 | 20 | BASANTI TRADERS | 2.11 | 0 | 0
1237 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000392/2020-2021 | 186/DWSD | 04/02/2021 | 45 | M/S BADAL GHOSH | 4.92 | 4.68 | 0
1238 | Durgapur W/S Division | Asansol Mechanical Division | Formal-Order for the work of Laying and aligning of distribution network of command area of Kanksa (Zone-II/C) and other allied works under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | ORD/000444/2022-2023 | 301/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 16.09 | 16.09 | 0
1239 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Laying and aligning rising main pipe line supplying of DI specials ,valves and allied works at Akandara under command area of Augmentation of Kanksa (Zone-II/C)(Part-B) piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000450/2022-2023 | 298/DWSD | 20/02/2023 | 30 | MAK CONSTRUCTION CO. | 92.36 | 91.71 | 0
1240 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 06 Nos 300X200 mm dia Tube well with 210 mtr Depth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Kanksa (Zone-II) Part-B,C tube well site of Augmentation of Kanksa Zone-II(Part-B & C) piped W/s Scheme under DWSD ,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000454/2022-2023 | 254/DWSD | 15/02/2023 | 60 | JOY GURU ENTERPRISE | 94.05 | 46.1 | 0
1241 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000011/2021-2022 | 328/DWSD | 15/03/2022 | 0 | Resource Division | 6.86 | 0 | 0
1242 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Kanksa Zone-II/Part-C Pump house no -01 | Assistant Engineer-II | Junior Engineer-3 | VCH/000225/2022-2023 | BP-2022-23-97 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.43 | 0 | 0
1243 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Kanksa Zone-II/Part-C Pump house no -02 | Assistant Engineer-II | Junior Engineer-3 | VCH/000226/2022-2023 | BP-2022-23-98 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0
1244 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Kanksa Zone-II/Part-C Pump house no -03 | Assistant Engineer-II | Junior Engineer-3 | VCH/000227/2022-2023 | BP-2022-23-99 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0
1245 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | Assistant Engineer-II | Junior Engineer-3 | ORD/000004/2022-2023 | 735/CMD | 29/04/2022 | 30 | STANDARD ELECTRICALS | 9.22 | 8.99 | 0
1246 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | Assistant Engineer-II | Junior Engineer-3 | ORD/000014/2022-2023 | 979/CMD | 14/06/2022 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.67 | 0
1247 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman | Assistant Engineer-II | Junior Engineer-3 | ORD/000015/2022-2023 | 978/CMD | 14/06/2022 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.61 | 0
1248 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Pump House No-01 under Kanksa Zone-II/C (Madhabmath) Water Supply Scheme, Block- Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000313/2024-2025 | 1808/AMD | 29/10/2024 | 30 | SUDIKSHA CONSTRUCTION | 2.96 | 0 | 0
1249 | Durgapur W/S Division |  | Formal order for the work of Construction of 400 M3 capacity ,20 mtr staging height of RCC OHR for Kanksa Zone-II/Part-D piped W/s Scheme under DWSD,PHE Dte(SL-03) |  |  | ORD/000098/2022-2023 | 788/DWSD | 18/05/2022 | 184 | RANJIB GHATAK | 88.59 | 0 | 0
1250 | Durgapur W/S Division |  | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied work under command area of Kanksa under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-04) |  |  | ORD/000101/2022-2023 | 751/DWSD | 11/05/2022 | 7 | CHATTERJEE CONSTRUCTION | 9.77 | 1.88 | 0
1251 | Durgapur W/S Division |  | Formal order for the work of Supplying, laying and aligning of 160 mm dia HDPE distribution pipe line and allied works at Railpar Saradapally of Prayagpur mouza under command areas under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-05) |  |  | ORD/000102/2022-2023 | 752/DWSD | 11/05/2022 | 15 | SAIKAT RAY | 16.19 | 16.06 | 0
1252 | Durgapur W/S Division |  | Formal order for the work of Providing functional house hold tap connection (FHTC) in connection with JJM at Railpar Nepali Para of Prayagpur Mouza(JL-89) under command area of Augmentation of Kanksa (Zone-II /P-D) piped W/s Scheme (SL-01) |  |  | ORD/000108/2022-2023 | 747/DWSD | 10/05/2022 | 10 | MAK CONSTRUCTION CO. | 37.33 | 25.1 | 0
1253 | Durgapur W/S Division |  | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte |  |  | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 15 | TARA CONSTRUCTION | 4.94 | 0 | 0
1254 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional FHTC work at Kanksa block and supplying laying and aligning of HDPE distribution pipe line and allied works at Railpar Sarada Pally and Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/Part-D) Piped W/s Scheme under DWSD ,PHE Dte. (SL-04) |  |  | ORD/000129/2022-2023 | 816/DWSD | 21/05/2022 | 30 | SAIKAT RAY | 80.17 | 76.74 | 0
1255 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of HDPE distribution pipe line and allied works at Railpar Sarada Pally of Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/D) piped W/S Scheme under DWSD,PHE Dte (Part-C) (SL-05) |  |  | ORD/000132/2022-2023 | 819/DWSD | 23/05/2022 | 30 | MD AAMIR KHAN | 76.63 | 76.81 | 0
1256 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJM at Panagarh mouza-88 and its adjoing area under command area of Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000168/2022-2023 | 1026/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.89 | 4.89 | 0
1257 | Durgapur W/S Division |  | Formal order for the work of Making of concrete RCC pier and supplying laying of MS water carrier pipe and 600 mm dia NP 3 Hume pipe with crossing of road and culvert of distribution system Kanksa (Zone--II/D) at Railpar Sarada Pally of Prayagpur mouza under command area of Augmentation of Kanksa (Zone-II/D W/s Scheme under DWSD ,PHE Dte (Part-C) |  |  | ORD/000179/2022-2023 | 1159/DWSD | 01/08/2022 | 30 | MD AAMIR KHAN | 44.11 | 44.28 | 0
1258 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Sarada Pally H/W Site Pump house No-3 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-04) |  |  | ORD/000197/2022-2023 | 1054/DWSD | 07/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 3.08 | 100
1259 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works plinth protection ,roof treatment ,drain and other allied works at Sarada Pally H/W Site Pump house No-1 &T.W-01(OHR site) for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-05) |  |  | ORD/000198/2022-2023 | 1060/DWSD | 08/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 3.08 | 100
1260 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Sinking of 1 Nos tube well 300 mm X 200 mm tube well 150 mtr depth by Direct rotary Rig method using PVC pipe and fiber galss reinforced epoxy resin slotted at existing tube well no-02 at near Railine under Augmentation of Kanksa (Z-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte (SL-13) |  |  | ORD/000232/2022-2023 | 1262/DWSD | 25/08/2022 | 15 | JOY GURU ENTERPRISE | 10.99 | 10.48 | 0
1261 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-03) |  |  | ORD/000307/2020-2021 | 1433/DWSD | 28/12/2020 | 60 | SUJAY KUMAR RAY | 42.78 | 39.52 | 0
1262 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-C) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000309/2020-2021 | 1435/DWSD | 28/12/2020 | 60 | ASHOK KUMAR GHOSH | 42.78 | 38.48 | 0
1263 | Durgapur W/S Division |  | Formal for the work of Extension of pipe line from exisitng pipe line of Kanksa (Zone-II) (Ph-II) W/S scheme at Panagarh Bazar and east canal par in Kanksa block to providing FHTC at Kanksa mouza(JL-89) under DWSD PHE Dte |  |  | ORD/000310/2021-2022 | 1773/DWSD | 20/12/2021 | 30 | M/S PIONEER CONSTRUCTION | 13.23 | 13.02 | 0
1264 | Durgapur W/S Division |  | Formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and allied works at Rail par Sarada Pally of Prayagpur Mouza under command area of Augmentation of Kanksa (Zone-II/D) W/S Scheme under DWSD ,PHE Dte (Part-C)(SL-01) |  |  | ORD/000388/2021-2022 | 185/DWSD | 11/02/2022 | 30 | MD AAMIR KHAN | 80.93 | 80.83 | 0
1265 | Durgapur W/S Division |  | Formal order for the work of Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-D) (SL-02) |  |  | ORD/000389/2021-2022 | 187/DWSD | 15/02/2022 | 30 | SAIKAT RAY | 85.77 | 87.48 | 0
1266 | Durgapur W/S Division |  | Formal order for the work of Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-B) |  |  | ORD/000393/2021-2022 | 201/DWSD | 17/02/2022 | 30 | AMARANJALI CONSTRUCTION | 94.15 | 75.19 | 0
1267 | Durgapur W/S Division |  | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-02 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000398/2021-2022 | 198/DWSD | 16/02/2022 | 30 | RANJIB GHATAK | 10.3 | 10.26 | 0
1268 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-1 tube well No-01(OHR) for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-01) |  |  | ORD/000400/2021-2022 | 240/DWSD | 25/02/2022 | 45 | GHOSH & ROY ENTERPRISE | 4.89 | 4.76 | 100
1269 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-2 tube well No-02 for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000401/2021-2022 | 241/DWSD | 25/02/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 3.76 | 100
1270 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-3 tube well No-03(for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-03) |  |  | ORD/000402/2021-2022 | 242/DWSD | 25/02/2022 | 45 | CHATTERJEE CONSTRUCTION | 4.89 | 3.76 | 0
1271 | Durgapur W/S Division |  | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-01 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000397/2021-2022 | 202/DWSD | 17/02/2022 | 30 | JOY GURU ENTERPRISE | 10.3 | 10.26 | 0
1272 | Durgapur W/S Division |  | Formal order for the work Sinking of 1No(300X200 mm) dia tube well 210 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-03 site at Railpar Saradapally near DVC branch canal for Augmentation of ground water base Kanksa (Zone-II/D) piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000399/2021-2022 | 188/DWSD | 15/02/2022 | 30 | AHS R INFRA PRIVATE LIMITED | 10.3 | 10.26 | 0
1273 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-I at Railpar Sarod Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte.(SL-01) |  |  | ORD/000455/2021-2022 | 376/DWSD | 24/03/2022 | 7 | JOY GURU ENTERPRISE | 4.4 | 2.92 | 0
1274 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-II at Railpar Sarada Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte. (SL-02) |  |  | ORD/000456/2021-2022 | 377/DWSD | 24/03/2022 | 7 | RANJIB GHATAK | 4.39 | 3.78 | 0
1275 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional bore for sinking of 01 Nos (300X200 mm dia) tube well of 210 mtr deep by DR drilling method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well No-III at Railpar Sarada Pally near DVC branch canal under Augmentation of Kanksa (Zone-II/Part-D) piped W/s Scheme under DWSD ,PHE Dte.(SL-03) |  |  | ORD/000457/2021-2022 | 378/DWSD | 24/03/2022 | 7 | AHS R INFRA PRIVATE LIMITED | 4.4 | 3.29 | 0
1276 | Durgapur W/S Division |  | Continuation order for the work of soil investigation for demining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated at Sarada Pally reservoir site of Augmentation of Kaksa Zone-II/D piped W/s Scheme under DWSD ,.PHE Dte |  |  | ORD/000469/2021-2022 | 287/DWSD | 08/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 0
1277 | Durgapur W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 329/DWSD | 15/03/2022 | 0 | Resource Division | 45.86 | 0 | 0
1278 | Durgapur W/S Division |  | Quotation for Kanksa Zone-II/Part-D Pump house no -01 |  |  | VCH/000229/2022-2023 | BP-2022-23-100 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.77 | 0 | 0
1279 | Durgapur W/S Division |  | Quotation for Kanksa Zone-II/Part-D Pump house no -02 |  |  | VCH/000230/2022-2023 | BP-2022-23-101 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0
1280 | Durgapur W/S Division |  | Quotation for Kanksa Zone-II/Part-D Pump house no -03 |  |  | VCH/000231/2022-2023 | BP-2022-23-102 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0
1281 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim -Bardhaman. |  |  | ORD/000001/2022-2023 | 732/CMD | 29/04/2022 | 30 | JAGANNATH ENTERPRISE | 9.67 | 9.44 | 0
1282 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman |  |  | ORD/000017/2022-2023 | 912/CMD | 31/05/2022 | 30 | DELTA ENGINEERING ENTERPRISE | 9.88 | 9.72 | 0
1283 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Kanksa [Zone-II / D ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim -Bardhaman. |  |  | ORD/000668/2022-2023 | 733/CMD | 29/04/2022 | 30 | CHATTERJEE ENTERPRISE | 9.65 | 9.4 | 0
1284 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of Concrete dismantling, Concrete restoration, Bolder cutting and other allied works at distribution network of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Div-I,PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000053/2024-2025 | 1743/RCD-I | 18/07/2024 | 255 | SWATI CORPORATION | 67.64 | 21.06 | 30
1285 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Left out part at Banbahal village distribution pipe line Zone-4A under Pandabeswar Block for smooth running of water supply near Shankarpur area of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000238/2025-2026 | 1460/RCD-I | 15/05/2025 | 30 | BABA LOKNATH ENTERPRISE | 18.07 | 0 | 80
1286 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc0 at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000600/2023-2024 | 3282/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.34 | 6.02 | 100
1287 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000670/2023-2024 | 3437/RCD-1 | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 9.31 | 100
1288 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of chlorine room of size (4.50 X 3.50 m) at (Zone-XIII) of Baraboni block for Improvement of RCFA Pt-I piped Water Supply under RCFA Div-I, PHE Dte. in the district of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000738/2022-2023 | 677/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 3.89 | 100
1289 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network and allied work for Ukhra area of RCFA Part-II Piped Water Supply Scheme allied work under RCFA Division-I PHE Dte. (Zone-2A)(Sl. No. 13) | Assistant Engineer 2 | Junior Engineer | ORD/000845/2022-2023 | 1080/RCD-I | 23/03/2023 | 90 | GITASREE FABRICATION | 97.2 | 0 | 80
1290 | RCFA Division -I | RCFA Division I | Acceptance cum work order Concrete road cutting and mending work for laying distribution pipe line at Das Para (Sansad-XIX) at Ukhra area Block ¿ Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 17) | Assistant Engineer 2 | Junior Engineer | ORD/000903/2022-2023 | 1161/RCD-I | 24/03/2023 | 15 | JYOGOMAYA ENTERPRISE | 2.01 | 1.94 | 100
1291 | RCFA Division -I | RCFA Division I | Formal work order for Additional work for allied work in connection with in connection supply, laying fitting, fixing of 15 mm NB PVC (Schedule 80) / 2020 mm OD HDPE (PE 80, PN 6) pipe with all necessary specials piece etc. all complete for Augmentation of Sub-Station Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000904/2023-2024 | 158/RCD-I | 22/01/2024 | 435 | MRITYUNJOY MUKHERJEE & CO. | 213.03 | 182.47 | 85
1292 | RCFA Division -I | RCFA Division I | Acceptance cum work order Concrete road cutting mending works for laying of distribution pipe line at Kankardanga Part (Sansad-VIII) at Ukhra area Block-Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 19) | Assistant Engineer 2 | Junior Engineer | ORD/000909/2022-2023 | 1163/RCD-I | 24/03/2023 | 15 | MS KALYAN ENTERPRISE | 2.77 | 2.71 | 100
1293 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000018/2023-2024 | 2956/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1294 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme Including FHTC & allied work under RCFA Division-I PHE Dte. (Zone 9B) (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000001/2023-2024 | 1348/RCD-I | 04/04/2023 | 30 | M/S SANTANU PALIT & CO. | 156.13 | 33.23 | 30
1295 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of making spout and Platform with other allied work at Amritnagar Zone -1 under Augmentation PWSS of RCFA Part-II (Zone - 9 B) under RCFA Division 1 PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000194/2024-2025 | 2421/RCD-I | 26/09/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 41.77 | 0 | 100
1296 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 06 (Six) nos. river bed tube wells including collecting main, sluice valve chamber & other allied works at Shyamlya H/W site at Ajoy river under Shyamla Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000208/2023-2024 | 2241/RCD-1 | 17/07/2023 | 30 | MAA ENTERPRISE. | 33.68 | 32.87 | 100
1297 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repair and renovation works of One no RCC Elevated Reservoir of Capacity 1362 cum at Khandra for Augmentation RCFA Part-II (Zone-9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000247/2023-2024 | 2234/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 16.43 | 16.29 | 100
1298 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte. (Zone-9B)(Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000630/2022-2023 | 486/RCDI | 03/02/2023 | 30 | M/S MONDAL ENTERPRISE | 156.13 | 71.14 | 70
1299 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000025/2023-2024 | 2953/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1300 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Road crossing of 250 mm dia Rising Main for under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under Raniganj Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000102/2024-2025 | 2122/RCD-I | 27/08/2024 | 30 | MD. JAWED KHAN | 8.41 | 8.59 | 100
1301 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dhunabaid of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) under Augmentation of sub surface water supply scheme for Amritnagar Zone-II under RCFA, Division-1,P.H.E.Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000104/2024-2025 | 2124/RCD-I | 27/08/2024 | 30 | DAS & CHAKRABORTY | 12.7 | 0 | 100
1302 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Pathan Dahwra of Murgasole Mouza under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA, Division-1, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000106/2024-2025 | 2126/RCD-I | 27/08/2024 | 25 | DAS & CHAKRABORTY | 7.38 | 5.26 | 100
1303 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Sinking of 6 (Six) nos. river bed tube wells including collecting main & other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar Zone II water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000116/2024-2025 | 2136/RCD-I | 27/08/2024 | 216 | M/S MONDAL CONSTRUCTION | 12.6 | 0 | 30
1304 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of OHR and Construction of new boundary wall, Land developing and Path way and other allied works at Saora mouza, Plot No:2787 at R.C.C over Head Site of Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under Raniganj Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000215/2024-2025 | 2550/RCD-I | 29/10/2024 | 154 | DAS & CHAKRABORTY | 26.19 | 13.58 | 80
1305 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of laying distribution system for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000244/2023-2024 | 2253/RCD-1 | 17/07/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 62.23 | 62.13 | 100
1306 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of laying distribution system to Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000245/2023-2024 | 2255/RCD-1 | 17/07/2023 | 30 | MACHINO TECHNO | 28.24 | 28.13 | 100
1307 | RCFA Division -I | RCFA Division I | Acceptance cum work order of rising main for Amritnagar Zone-II Water Supply Scheme for Ranoganj Block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000303/2022-2023 | 2513/RCD I | 20/10/2022 | 30 | MD. JAWED KHAN | 38.5 | 38.44 | 100
1308 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional Work for crossing Nunia River through the riverbed and allied works of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000398/2023-2024 | 2580/RCD-I | 07/09/2023 | 15 | MD. JAWED KHAN | 7.58 | 7.43 | 100
1309 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 2 | Junior Engineer | ORD/000540/2021-2022 | 504/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.23 | 4.23 | 0
1310 | RCFA Division -I | RCFA Division I | Laying of Distribution System to Accommodate FHTC and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division I, PHE Dte.under RCFA Division I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000301/2022-2023 | 2455/RCD-I | 13/10/2022 | 536 | MACHINO TECHNO | 366.55 | 235.84 | 100
1311 | RCFA Division -I | RCFA Division I | Acceptance cum wor order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Amritnagar under Augmentation of Sub Surface Water Supply Scheme of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000574/2022-2023 | 3283/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.04 | 14 | 100
1312 | RCFA Division -I | RCFA Division I | Acceptance cum work order for supplying 90 mm dia HDPE pipe line at Murgathol Adibasipara and Old Egera Including repairing different dia pipe line in different places within Amritnagar Distribution Zone under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division- IPHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000792/2022-2023 | 410/RCD-I | 30/01/2023 | 20 | DAS & CHAKRABORTY | 9.23 | 9.18 | 0
1313 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary Wall with Gate at OHR Site (Length- 120 mtrs) at Nimcha village of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000876/2022-2023 | 1125/ RCD I | 24/03/2023 | 1014 | ZEROTH CONTROL SYSTEM | 10.18 | 0 | 100
1314 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Special Repair & Renovation of existing High Lift Pump House, Boundary Wall, Guard Room, CWR, Switch Room etc. and allied works at H/W Site of Amritnagar Piped Water Supply Scheme. | Assistant Engineer 2 | Junior Engineer | ORD/000880/2022-2023 | 1145/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 9.83 | 9.59 | 0
1315 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Boundary Wall with Gate at OHR Site (Length-80 mtrs) at Amritnagar H/W Site (Damalia village) of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000884/2022-2023 | 1147/RCD-1 | 24/03/2023 | 892 | M/S MONDAL CONSTRUCTION | 7.04 | 6.94 | 100
1316 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No.- 05) | Assistant Engineer 2 | Junior Engineer | ORD/000892/2022-2023 | 1149/RCD-1 | 24/03/2023 | 948 | ZEROTH CONTROL SYSTEM | 6.5 | 0 | 40
1317 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000014/2022-2023 | 2925/RCD-I | 17/11/2022 | 0 | Resource Division | 356.25 | 0 | 0
1318 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000022/2022-2023 | 3129 | 09/12/2022 | 0 | Resource Division | 60.34 | 0 | 0
1319 | RCFA Division -I | RCFA Division I | Formal work word for Distribution Network for RCFA Part-II Pipe Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-16). | Assistant Engineer 2 | Junior Engineer | ORD/000039/2023-2024 | 1606/RCD I | 25/04/2023 | 251 | JOY HIND TUBEWELLS | 488.35 | 417.76 | 100
1320 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 600 cum capacity 20 mtr. Staging height RCC Over head Reservoir (pipe connection and cost of pipes, special at Raniganj Block (Zone-16) for Augmentation of RCFA Division-II piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000156/2023-2024 | 1899/RCD-I | 09/06/2023 | 366 | ASHA CONSTRUCTION | 154.85 | 93.83 | 45
1321 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS pipes under the Railway track by jack pushing technology at different spots and pushing diff. dia M.S pipes throgh 600 mm dia MS pipes in connection with the work for the laying distribution system for Augmentation of Sub - Surface water based piped water supply scheme for Amritnagar Zone -II for Augmentation of PWSS RCFA Part-II (Zone-16) Under RCFA Division -I PHE. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000192/2024-2025 | 2419/RCD-I | 26/09/2024 | 187 | MRITYUNJOY MUKHERJEE & CO. | 40.11 | 34.45 | 70
1322 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-II Water Supply Scheme within command area of Zone-16 including FHTC work (Part-A) under RCFA Div-I PHE Dte. (Mouza-Sahebganj) | Assistant Engineer 2 | Junior Engineer | ORD/000532/2022-2023 | 3160/RCD-I | 13/12/2022 | 30 | KRISHNA KUMAR TODI HUF | 88.68 | 79.11 | 100
1323 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000559/2022-2023 | 3353/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100
1324 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for laying of HDPE pipeline and PVC pipeline and allied works at Nabagram, Ukhra (Sansad-VI) Chatterjee para and Bahula Colony under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000660/2023-2024 | 3453/RCD-I | 24/11/2023 | 15 | MD AAMIR KHAN | 4.36 | 4.24 | 100
1325 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 31) | Assistant Engineer 2 | Junior Engineer | ORD/000911/2022-2023 | 1175/RCD I | 24/03/2023 | 90 | N.R. CONSTRUCTION | 4.61 | 0 | 0
1326 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying aligning laying HDPE pipe Mechanical fitting supplying sluice valve and other allied works at (Mouza-Sahenganj) under Zone-16 Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001019/2023-2024 | 572/RCD-I | 23/02/2024 | 30 | KRISHNA KUMAR TODI HUF | 36.45 | 36.45 | 100
1327 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000035/2023-2024 | 2939/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1328 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Napara W/S Scheme, P.H. No - 1, Gopalpur CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00177/2022-2023 | BP-2022-23-329 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0
1329 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Napara W/S Scheme, P.H. No - 02, Gopalpur CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00178/2022-2023 | BP-2022-23-330 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.8 | 0 | 0
1330 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2023 to 29.02.2024). (Sl-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000174/2023-2024 | 1397/DWSD | 17/08/2023 | 184 | BIPLAB BANERJEE | 0.82 | 0.8 | 30
1331 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying distribution system, Rising main construction of 350 M3 Over Head Reservoir with 20 Mtr staging height including soil investigation ,construction of Pump House (5.4X3.6mtr) with Sanitary and water supply arrangement & construction of Pump house (3.6X3.00 m) with FHTC for NAPARA piped W/s Scheme under DWSD,PHE Dte ,Dist.-Paschim Bardhhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000221/2022-2023 | 1174/DWSD | 02/08/2022 | 12 | SK. ALIM | 522.15 | 514.4 | 100
1332 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Napara piped W/s Scheme under DWSD ,PHE Dte (SL-08) | Assistant Engineer-II | Junior Engineer-3 | ORD/000230/2022-2023 | 1255/DWSD | 23/08/2022 | 15 | SK. ALIM | 14.76 | 14.73 | 0
1333 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.03.2023 to 31.08.2023). (Sl-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000502/2022-2023 | 134/DWSD | 31/01/2023 | 181 | BIPLAB BANERJEE | 0.82 | 2.4 | 80
1334 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Dismantling of concrete road for laying distribution system rising main construction of 350 M3 reservoir with 20 mtr staging height including soil investigation construction of pump house (5.40 X 3.60 m) with sanitary and construction of pump house 3.60 X 3.00 m) for Napara piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000570/2022-2023 | 489/DWSD | 23/03/2023 | 20 | SK. ABDUL HALIM | 4.39 | 4.39 | 0
1335 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000005/2023-2024 | 789/DWSD | 25/05/2023 | 0 | Resource Division | 7.07 | 0 | 0
1336 | RCFA Division -I | RCFA Division I | Car bill may 23 and june 23 | Assistant Engineer 1 | Junior Engineer | BILL/00518/2023-2024 | 234/2/23-24 | 05/09/2023 | 0 | NIRMALA TRADERS | 0.78 | 0 | 0
1337 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-B) under Roshna W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000138/2022-2023 | 1432/RCD I | 27/06/2022 | 45 | MD SARFARAZ ALAM | 4.98 | 4.65 | 0
1338 | RCFA Division -I | RCFA Division I | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-A) under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1 | Junior Engineer | ORD/000140/2022-2023 | 1434/RCD I | 27/06/2022 | 45 | MD AAMIR KHAN | 5 | 4 | 0
1339 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Roshna & Baspahari villages under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000144/2022-2023 | 1438/RCD I | 27/06/2022 | 45 | SHREE DURGA ENTERPRISE | 3.22 | 3.1 | 0
1340 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Daskeary Village Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000188/2021-2022 | 1862/RCD-I | 28/10/2021 | 30 | M/S MONI TRADERS | 39.47 | 35.31 | 0
1341 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Roshna (Part) Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000189/2021-2022 | 1863/RCD-I | 28/10/2021 | 30 | SRI KRISHNA ENTERPRISE | 12.81 | 9.39 | 0
1342 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Parulberia Mouza Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000190/2021-2022 | 1864/RCD-I | 28/10/2021 | 30 | MAK CONSTRUCTION CO. | 20.28 | 17.74 | 0
1343 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Distribution Network including supply of Hume pipe, G.I. pipe Sluice Valve and allied works for Augmentation of Roshna PWS (Part-D) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000237/2023-2024 | 2251/RCD-1 | 17/07/2023 | 30 | JYOGOMAYA ENTERPRISE | 10.86 | 5.29 | 100
1344 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000007/2021-2022 | 438/RCD-I | 21/02/2022 | 0 | Resource Division | 8.25 | 0 | 0
1345 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000010/2025-2026 | 2541/RCD-I | 01/09/2025 | 0 | Resource Division | 2.52 | 0 | 0
1346 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construciton of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanityary and water supply arrangment at Jemua tube well no -III site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000014/2023-2024 | 678/DWSD | 03/05/2023 | 30 | SIL ENTERPRISE | 6.92 | 6.92 | 100
1347 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig mehtod using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000016/2023-2024 | 680/DWSD | 03/05/2023 | 474 | RANJIB GHATAK | 31.43 | 30.86 | 100
1348 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of 5.4 m X 3.60 m swtich room with plinth height (600 mm to 20000 mm ) with sanitary and water supply arrangement at Jemua tube well no -II site of retrofitting of Jemua Piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000017/2023-2024 | 681/DWSD | 03/05/2023 | 811 | RANA ENTERPRISE | 6.84 | 0 | 51
1349 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Sinking of 2 Nos 300X200 mm dia TW 210 mtr deep by DR rig method using UPVC pipe CD and UPVC deep well screen (RDS) at Jemua H/W site and 1 No TW site of Faridpur block of retrofitting of Jemua piped W/s Scheme under DWSD ,PHE Dte (SL-19) |  |  | ORD/000025/2023-2024 | 757/DWSD | 19/05/2023 | 20 | M/S BADAL GHOSH | 31.47 | 22.07 | 100
1350 | Durgapur W/S Division |  | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-A) |  |  | ORD/000068/2023-2024 | 1065/DWSD | 12/07/2023 | 25 | B.M. SARKAR | 9.67 | 0 | 0
1351 | Durgapur W/S Division |  | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274)(Part-C) |  |  | ORD/000071/2023-2024 | 1058/DWSD | 12/07/2023 | 25 | B.M. SARKAR | 9.82 | 0 | 0
1352 | Durgapur W/S Division |  | Acceptance cum formal order for the work of providing FHTC connection and connection providing to Jemua Mouza (JL-80) under Jemua piped W/S Scheme under DWSD,PHE Dte (SM/06274) (Part-B) |  |  | ORD/000074/2023-2024 | 1068/DWSD | 12/07/2023 | 20 | ASHA CONSTRUCTION | 10.5 | 0 | 100
1353 | Durgapur W/S Division |  | Acceptance cum formal order for the work of providing FHTC in connection with JJM for Jemua mouza (JL-80) under Retrofitting of Jemua piped W/s Scheme of Durgapur-Faridpur Block (SM/16249) (Part-D) |  |  | ORD/000076/2023-2024 | 1071/DWSD | 12/07/2023 | 963 | KIRON ENTERPRISE | 9.93 | 7.63 | 70
1354 | Durgapur W/S Division |  | Acceptance cum formal order for the work of additional work for providing FHTC in connection with JJM for Nachan Mouza(JL-47) under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte (SM/13685) |  |  | ORD/000077/2023-2024 | 1064/DWSD | 12/07/2023 | 25 | M/S MONDAL ENTERPRISE | 14.55 | 13.65 | 100
1355 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of Jemua PWSS under Durgapur-Faridpur Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-01) |  |  | ORD/000176/2023-2024 | 914/DWSD | 22/06/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
1356 | Durgapur W/S Division |  | Additional repairing and replacement and restoration due to pipe line laying and pavers block and making platform including extra deapth of TW at Jamuna village and other allied works under providing water supply under Retrofitting of Jemua piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000218/2023-2024 | 1445/DWSD | 25/08/2023 | 15 | SATYAM POWER | 3.43 | 3.43 | 100
1357 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of boundary wall at Akandara Pump house site TW No-2 site under Jemua piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000515/2022-2023 | 332/DWSD | 20/02/2023 | 30 | DARPAN DAS & CO. | 15.05 | 8.45 | 100
1358 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional Work for distribution main pipe line Panagarh Gram Shibtola of Kanksa Zone-II Part-B of Augmentation of Kanchanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000378/2024-2025 | 3106/RCD-I | 13/12/2024 | 60 | MD AAMIR KHAN | 37.68 | 20.56 | 100
1359 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work of construction of IEP, drain and platform and other allied works at Kanchanpur under Augmentation of Kanchanpur Piped water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000395/2025-2026 | 1761/RCDI | 18/06/2025 | 30 | RUPALI ELECTRONICS | 15.48 | 0 | 0
1360 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000108/2023-2024 | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0
1361 | Durgapur W/S Division | Asansol Mechanical Division | Repairing and replacement and installation of Water supply arrangement at Kanchanpur FP School to provide water supply to school ,Block-Kanksa,Dist-Paschim Bardhhaman under Augmentation of Kanchanpur piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000243/2023-2024 | 1619/DWSD | 03/10/2023 | 30 | BISHAL ENTERPRISE | 2.23 | 2.23 | 100
1362 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for tube well No. - 3 at Kanchanpur Water Supply Scheme of (Kanksa Block, Paschim-Bardhaman) | Assistant Engineer-II | Junior Engineer-3 | ORD/001269/2023-2024 | 17/CMD | 03/01/2024 | 30 | S.P. CONSTRUCTION | 12.36 | 0 | 100
1363 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING AT KANCHANPUR PIPED WATER SUPPLY SCHEME FOR TUBE WELL NO-4 UNDER ASSANSOL MECHANICAL DIVISION, PHE DTE., BLOCK-KANKSHA, DIST.- PASCHIM-BARDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/000281/2024-2025 | 1675/AMD | 04/10/2024 | 119 | M/S. S. S. ENTERPRISE | 13.33 | 0 | 100
1364 | Asansol Mechanical | Asansol Mechanical Division | Deposition of earnest money for the proposed enhancement of the load at your premises at Dalurbandh, Pandabeswar | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | BILL/00024/2024-2025 | BP-2024-25-7 | 24/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1365 | Asansol Mechanical | Asansol Mechanical Division | Electric quotation for load enhancement of Bhaburia Head works under providing & installation of sub-station equipment and other accessories of ramnagar head works under RCFA Part-III(Zone-II) water supply scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | BILL/00343/2025-2026 |  | 19/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 31.71 | 0 | 0
1366 | Asansol Mechanical | Asansol Mechanical Division | Quotation for ramnagar sub-station under RCFA Part-III(Zone-II) Water supply scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | BILL/00921/2024-2025 | BP-2024-25-75 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 29.25 | 0 | 0
1367 | Asansol Mechanical | Asansol Mechanical Division | Providing & Installation of Sub-Mersible Pumping Machineries at RBTW No-20,21,22 & 23 other allied works at Ramnagar Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | ORD/000440/2024-2025 | 2098/AMD | 12/12/2024 | 253 | SUNRISE ENGINEERING CORPORATION | 12.41 | 0 | 100
1368 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house & Substation Buliding with Yard lighting arrangement and other allied works at Mahal & ECL Pump House under RCFA Part-III(Zone-II) Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | ORD/000449/2024-2025 | 2116/AMD | 16/12/2024 | 30 | SUNRISE ENGINEERING CORPORATION | 20.39 | 0 | 0
1369 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | ORD/000520/2023-2024 | 8/AMD | 02/01/2024 | 366 | R.N.S TRADING | 145.04 | 0 | 0
1370 | Asansol Mechanical | Asansol Mechanical Division | Allied Works Corresponding to "Providing and Installation of Substation Equipments and other Accessories at Ramnagar Head Works Site Under RCFA Part-III (Zone-II) Water Supply Scheme, Block: Pandabeswar, Dist. Paschim Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-5 | ORD/000524/2024-2025 | 145/AMD | 05/02/2025 | 30 | BENGAL CONSTRUCTION | 8.18 | 0 | 0
1371 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 24.49 | 100
1372 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000019/2021-2022 | 956/RCD-I | 07/06/2021 | 30 | SUMIT BANERJEE | 23.02 | 38.36 | 0
1373 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000020/2021-2022 | 957/RCD-I | 07/06/2021 | 30 | BABA LOKNATH ENTERPRISE | 23.01 | 43.71 | 0
1374 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000021/2021-2022 | 958/RCD-I | 07/06/2021 | 30 | KHEPI MAA TRADERS | 22.98 | 5.31 | 0
1375 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000061/2021-2022 | 1147/RCD-I | 22/07/2021 | 30 | GITASHREE FABRICATION | 21.97 | 21.9 | 0
1376 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of Morum cutting, concrete cutting, Hard rock cutting, Bituminus Road cutting different dia DI (K-7) & HDPE pipe line with other allied works from Dabor OHR Zone-II (Pahargara, Mohanpur, Partabpur, Bolkundi etc) distribution under Retrofitting Chotkara-Kanskuli W/S Scheme Zone II under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000161/2021-2022 | 1586/RCD-I | 07/09/2021 | 30 | DAS & CHAKRABORTY | 11.29 | 10.88 | 0
1377 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Chotkara (Part) for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1 | Junior Engineer | ORD/000576/2021-2022 | 258/RCD-I | 01/02/2022 | 15 | JAYANTA DATTA | 2.59 | 2.48 | 0
1378 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000016/2025-2026 | 2536/RCD-I | 01/09/2025 | 0 | Resource Division | 5.15 | 0 | 0
1379 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of 200 cum capacity 20 mtr. Staging height RCC Over Head Reservoir (pipe connection and cost of pipes, speciials at jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000006/2023-2024 | 1403 RCD I | 12/04/2023 | 366 | SRI KRISHNA ENTERPRISE | 72.48 | 72.48 | 99
1380 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000097/2022-2023 | 1270/RCD-I | 02/06/2022 | 90 | M/S S.K. ENTERPRISE | 24.81 | 23.46 | 100
1381 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000098/2022-2023 | 1271/RCD-I | 02/06/2022 | 90 | ALOKESH BANERJEE | 23.92 | 23.08 | 80
1382 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000099/2022-2023 | 1272/RCD-I | 02/06/2022 | 90 | B.T.M CONCERN | 55.19 | 55.16 | 100
1383 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for Distribution Network including adopting trench less technology at two places under Augmentation of Jamgram Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000216/2023-2024 | 2223/RCD-I | 17/07/2023 | 30 | B.T.M CONCERN | 39.15 | 35.84 | 92
1384 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Jamgram OHR site of Augmentation of Jamgram Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000346/2023-2024 | 2479/RCD-I | 23/08/2023 | 30 | SRI KRISHNA ENTERPRISE | 36.83 | 0 | 5
1385 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Sinking of 4 (Four) nos river bed tube wells including collecting main & other allied works at Unionpara H/W under RCFA Part-II at Damodar river under Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000349/2023-2024 | 2483/RCD-I | 23/08/2023 | 30 | T.R. ENTERPRISE | 11.42 | 11.08 | 100
1386 | RCFA Division -I | Asansol Mechanical Division | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000404/2022-2023 | 2519/RCDI | 20/10/2022 | 712 | MAA ENTERPRISE | 22.6 | 14.53 | 60
1387 | RCFA Division -I | Asansol Mechanical Division | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000405/2022-2023 | 2520/RCDI | 20/10/2022 | 30 | B.T.M CONCERN | 50.77 | 26.46 | 65
1388 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency Repairing of 750 mm dia Rising main with supply of leak repairing clamp and allied works related to supply of CI/DI specials etc, under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000412/2023-2024 | 2612/RCD-I | 12/09/2023 | 20 | MAKALI ENGINEERING CORPORATION | 98.81 | 98.81 | 100
1389 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR for Augumentation of Jamgram Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(sl no 03) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000481/2021-2022 | 2347/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 0
1390 | RCFA Division -I | Asansol Mechanical Division | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000525/2022-2023 | 3138/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
1391 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for rising Main for Augmentation of Jamgram Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000569/2022-2023 | 3278/RCD I | 20/12/2022 | 21 | DEBI PRASAD MAJI | 15.63 | 11.07 | 100
1392 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Pump House at Jamgram for Augmentation of Jamgarm Piped Water Supply Scheme under RCFA, Division-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000570/2022-2023 | 3279/RCDI | 20/12/2022 | 468 | R B ENTERPRISE | 20.73 | 18.51 | 100
1393 | RCFA Division -I | Asansol Mechanical Division | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-III) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000606/2022-2023 | 3274/RCDI | 20/12/2022 | 623 | M/S S.K. ENTERPRISE | 22.96 | 20.69 | 50
1394 | RCFA Division -I | Asansol Mechanical Division | Additional work like Horizonal Augar boring, dismantaling concrete and allied works in releted to part-B of Augmentation of jamgram PWSS under RCFA division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000642/2023-2024 | 3394/RCD-I | 23/11/2023 | 7 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100
1395 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for laying of HDPE Pipe line from Panuria Bazar to Shirikhad Para under Jamgram Panuria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000646/2022-2023 | 344/RCD I | 30/01/2023 | 15 | SHREE DURGA ENTERPRISE | 1.35 | 1.34 | 0
1396 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying 110 mm dia HDPE pipe with construction of piller for crossing a water body within Jamgram PWSS Part-C under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000674/2023-2024 | 3458/RCD-1 | 24/11/2023 | 15 | ALOKESH BANERJEE | 3.39 | 2.53 | 100
1397 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Ground Level Reservoir of capacity 105 cum for Augmentation Jamgram & its Adjoining Mouza Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000835/2022-2023 | 1062/RCD-I | 23/03/2023 | 375 | SUBHADEEP DAS | 12.25 | 11.43 | 100
1398 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme including FHTC work Block Barabani, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000960/2022-2023 | 1053/RCD-I | 23/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 90.22 | 34.13 | 55
1399 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional by constructing pillar for water body crossing including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work and allied works related to rising main of Itapara and adjoining mouzas under Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001062/2023-2024 | 502/RCD-I | 12/02/2024 | 232 | DURGA DAS MONDAL | 38.11 | 36.63 | 100
1400 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Switch room and balance work of approach road towards Gourbazar Head Works Site under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001115/2023-2024 | 921/RCD-I | 15/03/2024 | 60 | R B ENTERPRISE | 8.42 | 8.25 | 100
1401 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of Laying distribution system within distribution network for Augmentation of Jamgram PWSS under RCFA Div- I, PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001121/2023-2024 | 927/RCD-I | 15/03/2024 | 45 | B.T.M. CONCERN | 35.23 | 34.38 | 89
1402 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000010/2022-2023 | 2350/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
1403 | Asansol Mechanical | Asansol Mechanical Division | New Connection at Jamgram Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | BILL/00170/2022-2023 | BP-2022-23-28 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0
1404 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Gourbazar Pump House under Augmentation of Jamgram Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000134/2024-2025 | 1319/AMD | 21/08/2024 | 45 | INDUSTRIAL ELECTRICAL CORPORATION | 2.79 | 0 | 100
1405 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Pumping Machineries and other Electro-Mechanical equipment at Jamgram Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block- Barabani, District-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000411/2022-2023 | 360/AMD | 09/02/2023 | 90 | INDUSTRIAL ELECTRICAL CORPORATION | 46.39 | 45.36 | 100
1406 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. jack Pushing Method etc) for crossing of NH-60 near Pandabeswar H/W Site to carry 350 mm dia distribution & 250 mm dia rising main pipe line under RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000018/2024-2025 | 1521/RCD-I | 14/06/2024 | 45 | HIRANMAY GHOSH | 14.09 | 0 | 0
1407 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia Horizontal River Bed Tube Well with fitting of 200 mm dia Strainer (12.2 mtr) in river Ajay & Collecting line under RCFA Part-III Zone-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000020/2024-2025 | 1523/RCD-I | 14/06/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 14.42 | 0 | 100
1408 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work of Replacement of A.C pipe of Main Distribution pipeline from Madhaiganj OHR to RANGAMATI Village including ROAD Restoration of Rangamati Village Of Augmentation of RCFA part III Zone I under RCFA Div- I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000217/2024-2025 | 2547/RCD-I | 29/10/2024 | 154 | BASANTI TRADERS | 32.79 | 4.65 | 40
1409 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of Rising main and other allied works from Panshuili H/W Site to Natundanga OHR of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000224/2024-2025 | 2556/RCD-I | 29/10/2024 | 180 | UNITED CONSTRUCTION | 36.87 | 2.57 | 70
1410 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Improvement & Overhauling of 5 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Bhaburia H/W Site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA W/S Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000241/2024-2025 | 2615/RCD-I | 13/11/2024 | 30 | SREE ENTREPRENEUR | 24.71 | 6.31 | 100
1411 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for HDPE distribution pipe line laying for Gourbazar and Bhabanandapur village and other allied works under Augmentation of RCFA Part-III (Zone-I) PWSS under RCFA Davison-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000263/2025-2026 | 1485/RCD-I | 15/05/2025 | 120 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 34.41 | 0 | 80
1412 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional pipe line with of HDPE pipe with at Pratappur and Kalikapur with re-connection of existing FHTC and other allied works of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000291/2024-2025 | 2628/RCD-I | 14/11/2024 | 182 | SIMA ENTERPRISE | 57.5 | 9.31 | 80
1413 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of Railway Track near Fulbagan more DVC para to carry 250 mm dia distribution line of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000298/2024-2025 | 2635/RCD-I | 14/11/2024 | 60 | RUBY CONSTRUCTION | 19.07 | 0 | 100
1414 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells with collecting main and allied work in the river Ajoy at Pansuili Head Works Site under Augmentation of RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000301/2025-2026 | 1405/RCD-I | 15/05/2025 | 25 | AMARANJALI CONSTRUCTION | 11.04 | 0 | 100
1415 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPaschim Para at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000325/2025-2026 | 1511/RCD-I | 20/05/2025 | 87 | UNITED CONSTRUCTION | 22.25 | 0 | 60
1416 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Sub-Station Building at Ramnagar H/W Site within Pandabeswar Block under RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000373/2024-2025 | 3101/RCD-I | 13/12/2024 | 292 | RANJIB GHATAK | 36.86 | 0 | 90
1417 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of distribution pipe line including allied works at Sarpi village under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000380/2024-2025 | 3108/RCD-I | 13/12/2024 | 45 | UNITED CONSTRUCTION | 30.42 | 11.6 | 100
1418 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology(e.g. Jack Pushing Method etc)of 03(Three) nos. location at Sarpi Maji para, Shyamsundarpur More and Kumardihi gram near stadium under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000534/2024-2025 | 137/RCD-I | 08/01/2025 | 30 | MAK CONSTRUCTION CO | 22.97 | 0 | 100
1419 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Laudoha OHR site at Laudoha under RCFA Part-III Water Supply Scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/001209/2023-2024 | 1021/RCD-I | 16/03/2024 | 45 | M/S A G CONSTRUCTION | 8.87 | 8.84 | 100
1420 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Pansiuli OHR site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/001222/2023-2024 | 1022/RCD-I | 16/03/2024 | 564 | SHWET BARANI | 13.3 | 0 | 100
1421 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for rest portion UPVC pipe line and FHTC at Benabandhi (JL-11) and Maheshpur(JL-12) mouza under Augmentaiton of RAFA Part-III Zone-I piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-2 | ORD/000033/2023-2024 | 739/DWSD | 22/05/2023 | 60 | KIRON ENTERPRISE | 51.72 | 48.44 | 100
1422 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work at RCC OHR site at NUTANDANGA under Augmentation of RCFA Part-III (Zone-I) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-2 | ORD/000041/2023-2024 | 766/DWSD | 22/05/2023 | 15 | M/S PROCHESTA ENTERPRISE | 4.49 | 4.48 | 100
1423 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Urgent Repairing of 250 dia pipe line with necessary alid works at Nabaghanapur to Jhanjra Project Portion under Augmentation 0f RCFA ,Pt-III, Zone -I W/S Scheme (JJM) Under Durgapur Water Supply Division, P.H.E. Dte. (Sl-02) | Assistant Engineer-II | Junior Engineer-2 | ORD/000054/2023-2024 | 838/DWSD | 05/06/2023 | 15 | RUBY CONSTRUCTION | 0.75 | 0 | 100
1424 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Providing FHTC work at Rangamati Mouza(JL-10) under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) | Assistant Engineer-II | Junior Engineer-2 | ORD/000069/2023-2024 | 1066/DWSD | 12/07/2023 | 30 | BASANTI TRADERS | 18.67 | 11.68 | 50
1425 | Durgapur W/S Division | Asansol Mechanical Division | Additioinal work for rest portion UPVC pipe line at Rangamati mouza under Augmentation of RCFA Part-III(Zone-I) piped W/S Scheme under DWSD,PHE Dte (SM/11454) | Assistant Engineer-II | Junior Engineer-2 | ORD/000084/2023-2024 | 1073/DWSD | 12/07/2023 | 25 | BASANTI TRADERS | 9.56 | 6.54 | 100
1426 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 3,4,5 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | Assistant Engineer-II | Junior Engineer-2 | ORD/000105/2023-2024 | 04/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1427 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 7,9,10 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) | Assistant Engineer-II | Junior Engineer-2 | ORD/000117/2023-2024 | 06/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1428 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 16,17,18 Ext ) to combat drought like situation at Pansiuli head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-02) | Assistant Engineer-II | Junior Engineer-2 | ORD/000127/2023-2024 | 11/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1429 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.07.2023 to 31.12.2023).(Sl-01) | Assistant Engineer-II | Junior Engineer-2 | ORD/000102/2023-2024 | 944/DWSD | 28/06/2023 | 183 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 100
1430 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -11,12 Ext & 4 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-03) | Assistant Engineer-II | Junior Engineer-2 | ORD/000128/2023-2024 | 12/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1431 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No -10,13 Ext & 14 New ) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-04) | Assistant Engineer-II | Junior Engineer-2 | ORD/000129/2023-2024 | 13/SPOT/DWSD | 16/06/2023 | 4 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1432 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional Wash out work for 200 mm dia River Bed Tube Wells in River Ajoy at PANSULI Head Works Site under Augmentation of RCFA, Pt-III, Zone - I Part -A Water Supply Scheme under DWSE, PHE Dte. (Sl-05) | Assistant Engineer-II | Junior Engineer-2 | ORD/000130/2023-2024 | 14/SPOT/DWSD | 16/06/2023 | 631 | AMARANJALI CONSTRUCTION | 0.61 | 0.6 | 100
1433 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Instalation of Water Level Indicater at Loudoha head work site under RCFA,Part-III ,Zone -I W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-07) | Assistant Engineer-II | Junior Engineer-2 | ORD/000132/2023-2024 | 16/SPOT/DWSD | 16/06/2023 | 7 | KARMAKAR CONSTRUCTION | 0.77 | 0.77 | 100
1434 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Surging of 03 Nos river bed tube wells (No - 1,3,4 Ext) to combat drought like situation at Pansuili head work site under Augmentation of RCFA,Part-III (Zone-I) W/S Scheme (JJM) under Durgapur Water Supply Division , PHE Dte. (Sl-01) | Assistant Engineer-II | Junior Engineer-2 | ORD/000137/2023-2024 | 1254/DWSD | 02/08/2023 | 10 | KARMAKAR CONSTRUCTION | 1 | 1 | 100
1435 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Drawing ,design and surveying work for proposed piped W/s Scheme of Sarpi W/S Scheme under DWSD, PHE Dte(SL-02) | Assistant Engineer-II | Junior Engineer-2 | ORD/000154/2022-2023 | 1022/DWSD | 04/07/2022 | 10 | APEX ENGINEERING | 4.09 | 4.09 | 100
1436 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) Maheshpur(JL-12) Mouza of Augmentation of RCFA Part-III Piped W/s Scheme (Zone-I) (Part-B) W/s Scheme under DWSD,PHE Dte (SL-07) | Assistant Engineer-II | Junior Engineer-2 | ORD/000180/2022-2023 | 874/DWSD | 26/05/2022 | 25 | BASANTI TRADERS | 22.24 | 18.46 | 0
1437 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 150 M3 capacity 20 mtr staging height RCC over Head Reservoir (OHR) at Nutandanga under Augmentation of RCFA Part-III W/s Scheme (Zone-I/Part-B) under DWSD, PHE Dte (SL-13) | Assistant Engineer-II | Junior Engineer-2 | ORD/000181/2022-2023 | 875/DWSD | 26/05/2022 | 184 | M/S PROCHESTA ENTERPRISE | 64.33 | 56.33 | 0
1438 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of RCFA Part - III Zone - I (PART - B) under Durgapur Faridpur Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 03) | Assistant Engineer-II | Junior Engineer-2 | ORD/000184/2023-2024 | 1201/DWSD | 27/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
1439 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 500 M3 capacity 20 mtr staging height RCC Over Head Reservoir (OHR) at Mohal under Augmentation of RCFA Part-III (Zone-I/Part-B) W/s Scheme under DWSD, PHE Dte (SL_14) | Assistant Engineer-II | Junior Engineer-2 | ORD/000207/2022-2023 | 278/DWSD | 16/05/2022 | 184 | RANJIB GHATAK | 96.93 | 82.66 | 85
1440 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-B) W/S Scheme under DWSD,PHE Dte. (SL_09) | Assistant Engineer-II | Junior Engineer-2 | ORD/000208/2022-2023 | 856/DWSD | 24/05/2022 | 10 | RANAJOY ENTERPRISE | 19.57 | 14.03 | 100
1441 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of of Sinking of 4 Nos 200 mm dia river bed tube wells with collecting main in river Ajoy at Pansuili H/W under Augmentation of RCFA Part-III(Zone-I)(Part-A) W/S Scheme under DWSD,PHE Dte. (SL_15) | Assistant Engineer-II | Junior Engineer-2 | ORD/000209/2022-2023 | 857/DWSD | 24/05/2022 | 15 | RANAJOY ENTERPRISE | 18.48 | 14.81 | 100
1442 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying and laying of different dia UPVC pipe line with necessary allied works at Rangamatia (JL-10),Benebandhi(JL-11) ,Maheshpur(JL-12) mouza of Augmentation of RCFA Part-III W/s Scheme (Zone-I)/Part-A) W/S Scheme under DWSD,PHE Dte.(SL-02) | Assistant Engineer-II | Junior Engineer-2 | ORD/000266/2022-2023 | 1005/DWSD | 28/06/2022 | 15 | KIRON ENTERPRISE | 19.46 | 16.77 | 85
1443 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal work order for the work of Withdrawing existing damaged 150 mm dia AC pipe line and laying 160 mm dia (OD) HDPE pipe in the same trench from Madhaiganj OHR site towards Rangamati village under RCFA Pt-III W/S Scheme under DWSD, PHE Dte (SL-24) | Assistant Engineer-II | Junior Engineer-2 | ORD/000350/2020-2021 | 69/DWSD | 13/01/2021 | 15 | KARMAKAR CONSTRUCTION | 2.31 | 2.31 | 0
1444 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying of CI Pipe line ,sluice valves ,UPVC pipe line and allied works at Madhaiganj H/W Site under Modified RCFA Part-III W/s Scheme under DWSD, PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-2 | ORD/000358/2021-2022 | 75/DWSD | 21/01/2022 | 15 | KARMAKAR CONSTRUCTION | 2.57 | 2.5 | 0
1445 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Augmentation at Natundanga of RCFA Part-III (Zone--I/A) piped W/s Scheme including laying distribution network (LDS) and functinal household tap connection (FHTC) under Durgapur W/s Division, PHE Dte ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman (SL-02) | Assistant Engineer-II | Junior Engineer-2 | ORD/000372/2022-2023 | 1778/DWSD | 23/12/2022 | 739 | ALOK ENTERPRISE | 634.56 | 448.32 | 75
1446 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Augmentation of RCFA Part-III )Zone-I/Part-B) piped W/s Scheme by construction of 250 M3 RCC OHR of 20 mtr staging height with necessary interconnection soil investigation including laying distribution network and Functional House Tap Connection (FHTC) under DWSD,PHE Dte ,Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (Sl-01 | Assistant Engineer-II | Junior Engineer-2 | ORD/000373/2022-2023 | 1779/DWSD | 23/12/2022 | 12 | UMWELT ENGINEER PVT LTD | 919.36 | 917.39 | 90
1447 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of augmentation at Madhaiganj of RCFA Part-III (Zone-I/C) piped W/s Scheme including laying distribution network and functional household tap connection (FHTC) under Durgapur W/S Division, PHE Dte Block-Durgapur-Faridpur ,Dist.-Paschim Bardhhaman. | Assistant Engineer-II | Junior Engineer-2 | ORD/000380/2022-2023 | 05/DWSD | 02/01/2023 | 120 | IJABUL SEKH | 279.99 | 236.03 | 100
1448 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) | Assistant Engineer-II | Junior Engineer-2 | ORD/000438/2022-2023 | 1801/DWSD | 30/12/2022 | 182 | PRAMIT CHATTERJEE | 0.82 | 0.8 | 0
1449 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area fro providing of FHTC at Ichhapur mouza(JL-50) under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-2 | ORD/000476/2021-2022 | 192/DWSD | 15/02/2022 | 15 | SHWET BARANI | 4.45 | 4.45 | 100
1450 | Durgapur W/S Division | Asansol Mechanical Division | Laying additional distribution pipeline with necessary allied works for providing FHTC work under Durgapur-Faridpur Block of Augmentation of RCFA Part-III W/s Scheme (Zone-I) under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-2 | ORD/000666/2022-2023 | 1146/DWSD. | 04/07/2022 | 20 | SHWET BARANI | 5.69 | 5.64 | 100
1451 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000001/2022-2023 | 1228/DWSD | 17/08/2022 | 0 | Resource Division | 9.52 | 0 | 0
1452 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000005/2022-2023 | 1377/DWSD | 22/09/2022 | 0 | Resource Division | 61.6 | 0 | 0
1453 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000011/2022-2023 | 255/A/DWSD | 15/02/2023 | 0 | Resource Division | 30.8 | 0 | 0
1454 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000012/2022-2023 | 256/DWSD | 15/02/2023 | 0 | Resource Division | 61.6 | 0 | 0
1455 | Asansol Mechanical | Asansol Mechanical Division | Quotation for natundanga O.H.R. under RCFA-III(Zone-I) Water supply scheme. | Assistant Engineer-II | Junior Engineer-2 | BILL/00481/2024-2025 | BP-2024-25-43 | 05/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.09 | 0 | 0
1456 | Asansol Mechanical | Asansol Mechanical Division | Providing And Installation of Submersible pumping Machineries, PDB-Cum-MCC Panel and other Electro-Mechanical accessories at Head Works site at Pansuli under Augmentation of RCFA Part-III (Zone-I) Water Supply Scheme, Block-Faridpur-Durgapur, Dist.-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-2 | ORD/000392/2022-2023 | 252/AMD | 02/02/2023 | 30 | INDUSTRIAL ELECTRICAL CORPORATION | 33.68 | 30.8 | 0
1457 | RCFA Division -I |  | Acceptance cum work order for Re-connection of FHTC & additional Functional Household Tap Connection (FHTC) for Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC for new pipe line laying under RCFA Division-I PHE Dte. |  |  | ORD/000289/2024-2025 | 2630/RCD-I | 14/11/2024 | 135 | SHWET BARANI | 23.56 | 0 | 100
1458 | Durgapur W/S Division |  | Formal order for the work of Laying of 110/90/75 mm dia HDPE pipe line with necessary allied works at Annandapur mouza ICDS to Dompara under Kanksa (Zone-I ) W/s Scheme for upcoming combat draught like situation in Kanksa block under DWSD,PHE Dte (SL-04) |  |  | ORD/000022/2021-2022 | 832/DWSD | 24/05/2021 | 15 | M/S KALYANI ENTERPRISE | 5.12 | 0.74 | 0
1459 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJM at Radhamohanpur mouza-36 and its adjoining area under command area of Basudha piped W/s Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000046/2022-2023 | 581/DWSD | 21/04/2022 | 7 | JOY GURU ENTERPRISE | 4.77 | 4.83 | 0
1460 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing water supply of office of the deputy inspector General of Police group center at Radhamohanpur under Kanksa and Bonkati GP having with electricity but uncovered by PWSS under DWSD,PHE Dte (SL-03) |  |  | ORD/000047/2022-2023 | 582/DWSD | 21/04/2022 | 7 | JOY GURU ENTERPRISE | 2.12 | 2.12 | 0
1461 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000091/2022-2023 | 723/DWSD | 06/05/2022 | 15 | BABA LOKENATH ENTERPRISE | 30.27 | 5.38 | 0
1462 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Panagarh mouza(JL-85) of Pal para,Hazra bera,Kumar para ,near Tilakchandrpaur Panchayat near Panagarh bypass under DWSD,PHE Dte (SL-12) |  |  | ORD/000092/2021-2022 | 1104/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.98 | 4.98 | 0
1463 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Jhinuk Garia and Kanksa Hotal para under DWSD,PHE Dte (SL-13) |  |  | ORD/000093/2021-2022 | 1105/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.82 | 4.82 | 0
1464 | Durgapur W/S Division |  | Acceptance cum form order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Duck Bunglow and Kanksa colony para under DWSD,PHE Dte (SL-14) |  |  | ORD/000094/2021-2022 | 1106/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.98 | 4.98 | 0
1465 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Kanksa mouza(JL-89) at Kanksa Adibashipara and Kanksa 3 No colony under DWSD,PHE Dte (SL-15) |  |  | ORD/000095/2021-2022 | 1107/DWSD | 30/07/2021 | 15 | GITA CONSTRUCTION | 4.89 | 4.89 | 0
1466 | Durgapur W/S Division |  | Formal order for the work of Restoration of exiting house hold tap connection (Damaged) and re connection of the same in connection of JJM and changes of defective pipe line of 90/110/125/140/200 mm dia UPVC pipe line at different places of distribution main command area of Basudha Piped W/s Scheme under DWSD,PHE Dte (SL-08) |  |  | ORD/000175/2022-2023 | 1160/DWSD | 01/08/2022 | 10 | MD AAMIR KHAN | 5.04 | 4.99 | 0
1467 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Replace damaged 250 mtr 150 mm dai AC pipe with the UPVC 160 mm dia pipe line at Panagarh Baruipara ,Ijjatganj OHR cleaning leakage bursting at Ijjatganj and others allied works of Kanksa Zone-II ph-II W/s Scheme under DWSD,PHE Dte (SL_06) |  |  | ORD/000187/2021-2022 | 1408/DWSD | 29/09/2021 | 15 | RANJIB GHATAK | 4.2 | 4.2 | 0
1468 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Withdrawing of damaged 160 mm dia UPVC pipe and laying of additional length of pipe at Basudha and Ajodhya and repairing of damaged pipe due to newly constructed WBSRDA road and others allied works of Basudha W/s Scheme under DWSD,PHE Dte (SL-08) |  |  | ORD/000202/2022-2023 | 1074/DWSD | 12/07/2022 | 15 | MAK CONSTRUCTION CO. | 4.26 | 4.24 | 0
1469 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000258/2020-2021 | 1317/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 25.99 | 3.37 | 0
1470 | Durgapur W/S Division |  | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) |  |  | ORD/000258/2021-2022 | 1676/DWSD | 30/11/2021 | 35 | M/S. D. PALIT & CO. | 18.62 | 1.29 | 100
1471 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Z-II)(Ph-II) W/s Scheme to laying branch pipe line in kanksa block for providing FHTC at PanagarhJL_85) at Palpara ,Hazra Para ,Kumanrpara near TC pur Panchayat ,Panagarh bypass under DWSD PHE Dte (Sl-04) |  |  | ORD/000359/2021-2022 | 78/DWSD | 24/01/2022 | 15 | GITA CONSTRUCTION | 3.46 | 3.39 | 0
1472 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) |  |  | ORD/000392/2020-2021 | 186/DWSD | 04/02/2021 | 45 | M/S BADAL GHOSH | 4.92 | 0 | 0
1473 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-I W/s Scheme to combat draught like situation at in Kaksa Block to providing FHTC at Ijjatganj Mouza (JL-79) under DWSD,PHE Dte..(SL-04) |  |  | ORD/000417/2020-2021 | 273/DWSD | 26/02/2021 | 25 | RANJIB GHATAK | 4.97 | 0 | 0
1474 | Durgapur W/S Division |  | Continuation order for the work of providing functional household tap connection (FHTC) in connection with JJM at Kajladihi mouza(JL-26) under command area of Krishnapur Piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte. |  |  | ORD/000427/2021-2022 | 346/DWSD | 17/03/2022 | 15 | THE STAR & CO | 2.72 | 0 | 0
1475 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing restoration of distribution system of Nachan OHR (Part-B) from Nachan More to Dhaboni Lobnapara under Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte.(SL-05) |  |  | ORD/000432/2021-2022 | 412/DWSD | 30/03/2022 | 15 | PAYAL CONSTRUCTION | 4.63 | 1.64 | 0
1476 | Durgapur W/S Division |  | Acceptance cum formal order for the work of laying of distribution pipe line with necessary allied work at Domra and Piariganj mouza under Tilakchandrapur W/s Scheme for FHTC under DWSD, PHE Dte. |  |  | ORD/000443/2021-2022 | 422/DWSD | 30/03/2022 | 10 | AMARANJALI CONSTRUCTION | 4.74 | 4.73 | 0
1477 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road for extension of pipe line from existing pipe line of Kanksa (Zone-II) (Phase-II) W/s Scheme to laying branch pipe line in Kanksa block to providing FHTC at Kanksa Mouza (JL-89) at Jhinuk Raia Hotel para ,Duck bungalow colony para under DWSD, PHE Dte.(SL-16) |  |  | ORD/000452/2021-2022 | 431/DWSD | 30/03/2022 | 15 | GITA CONSTRUCTION | 4.95 | 4.95 | 0
1478 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 44.64 | 100
1479 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Kotalpukur W/S Scheme , Pump House No- 01 , Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00207/2022-2023 | BP-2022-23-339 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.47 | 0 | 0
1480 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Kotalpukur(JL-30) ,Nimtakuri(JL-30),Masna(JL-31) mouzas of Kotalpukur piped W/S scheme under DWSD,PHE Dte (SL-22) | Assistant Engineer-II | Junior Engineer-3 | ORD/000021/2023-2024 | 733/DWSD | 15/05/2023 | 535 | JOY GURU ENTERPRISE | 146.29 | 94.38 | 100
1481 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Kotalpukur,Masna,Nimtikuri mouzas of Kotalpukur piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000165/2022-2023 | 773/DWSD | 17/05/2022 | 45 | JOY GURU ENTERPRISE | 41.01 | 0 | 0
1482 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Additional work of laying of HDPE distribution pipe line 75/90 mm dia and providing FHTC at Kotalpukur (JL-30),Nimtakuri(JL-32) & Masna(JL-31) mouzas of Kotalpukur piped W/s Scheme under DWSD,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000253/2022-2023 | 1426/DWSD | 08/10/2022 | 10 | JOY GURU ENTERPRISE | 12.21 | 3.51 | 0
1483 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Route survey and preparation of DPr for Augmentation of Garkilla-Kherobari,Banagram, Kotalpur, Dhobaru piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000562/2022-2023 | 525/DWSD | 29/03/2023 | 15 | MEASURE LAND | 9.24 | 9.24 | 0
1484 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and internal House Wiring for Tube Well No. -01 at Kotalpukur (Nimtikuri) Water Supply Scheme under CMD, PHE Dte., Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000001/2023-2024 | 1575/CMD | 04/04/2023 | 30 | SAIKAT ENTERPRISE | 8.99 | 8.48 | 100
1485 | Asansol Mechanical | Asansol Mechanical Division | QUOTATION AS PER WBSEDCL PROCEDURE-A (2010) FOR THE SITE OF KOTALPUKUR, TW NO-II, BANKATI. | Assistant Engineer-II | Junior Engineer-3 | BILL/00587/2024-2025 | BP-2024-25-65 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.65 | 0 | 0
1486 | Asansol Mechanical | Asansol Mechanical Division | Supply delivery and installation of submersible pumping machinery, chlorination system and internal house wiring for tube well no-2 at augmentation of ground water based water supply scheme for Kotalpukur under Asansol Mechanical Division. PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000500/2024-2025 | 2202/AMD | 27/12/2024 | 102 | SAIKET SINHA | 5.93 | 0 | 100
1487 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Pumping Machineries, PDB CUM MCC Panel, Substation Equipments and other Accessories at Head Works Site at Pansuli under RCFA-III(Zone-I) Water Supply Scheme, Block: Faridpur-Durgapur, Dist. Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-2 | ORD/000002/2023-2024 | 873/AMD | 04/04/2023 | 366 | INDUSTRIAL ELECTRICAL CORPORATION | 137.21 | 136.29 | 73
1488 | Asansol Mechanical | Asansol Mechanical Division | Withdrawing and lowering of Submersible pumping machineries at RBTW No-9 & 14 with Other allied works at Pansuli Head Works Site under RCFA Part-III(Zone-I) Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-2 | ORD/000034/2024-2025 | 1036/AMD | 16/07/2024 | 30 | CIEMENICS | 4.05 | 4 | 100
1489 | Asansol Mechanical | Asansol Mechanical Division | Providing of lighting luminaries, with yard lighting arrangement of Laudoha O.H.R. premises under Improvement of RCFA Part-I W/S Scheme. | Assistant Engineer-II | Junior Engineer-2 | ORD/000045/2024-2025 | 1131/AMD | 30/07/2024 | 167 | V. P. CONCERN | 3.84 | 0 | 100
1490 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Pansuli Head Works Site under improvement of RCFA Part-III(Zone-I) Water Supply Scheme, Asansol Mechanical Division, P.H.E Dte. Block-Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-2 | ORD/000320/2024-2025 | 1814/AMD | 29/10/2024 | 277 | SUNRISE ENGINEERING CORPORATION | 48.22 | 0 | 100
1491 | Durgapur W/S Division | Asansol Mechanical Division | Additional quotation for effecting NSC under revised estimate for Dhobaru W/S Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00746/2023-2024 | BP-2023-24-366 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0
1492 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Dhobaru mouzas of Dhobaru piped W/S scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000104/2023-2024 | 1133/DWSD | 20/07/2023 | 30 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 109.55 | 70.62 | 80
1493 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of DHOBARU (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000183/2023-2024 | 1194/DWSD | 25/07/2023 | 7 | CARTO | 0.78 | 0.78 | 100
1494 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Dhobaru Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000004/2023-2024 | 1578/CMD | 04/04/2023 | 30 | DUTTA ENTERPRISE | 8.97 | 8.5 | 100
1495 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution Network for Augmentation of Jamuri (Rural) (Zone-I) RCFA Part-II Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000032/2023-2024 | 1613/RCD I | 25/04/2023 | 30 | M/S B.K. CONSTRUCTION | 132.16 | 76.95 | 65
1496 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Construction of Water sample collection cum Laboratory cum ISA & DPMU activity center as well as training hall etc. in the premises of RCFA office building under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000172/2023-2024 | 2008/RCD-I | 26/06/2023 | 564 | M/S CHANDI CHARAN ROY | 241.14 | 151.22 | 67
1497 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 03 (Three) nos. location at Lalganj Domohani Road, Kelejhora Health Centre More to Puchra Road, Puchra to Natudihi Road under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000240/2023-2024 | 2217/RCD-I | 17/07/2023 | 30 | VISUVIOUS | 30.35 | 30.36 | 100
1498 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR & Route Survey for augumentation of Jamuria (Rural) (Zone-I) piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. (Sl No. 32) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000251/2022-2023 | 2247/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 0
1499 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing in between KM 27/21-23 and between Barabani (BBI) and Jamuria (JMA) Station in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000286/2023-2024 | 2335/RCD-I | 01/08/2023 | 15 | M/S MONDAL ENTERPRISE | 36.29 | 34.64 | 100
1500 | RCFA Division -I | Asansol Mechanical Division | Acceptence cum work order for Additional Supplying, Laying and Aligning HDPE pipe line, construction of street stand post and allied works under Ballavpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000403/2023-2024 | 2585/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 6.32 | 6.15 | 100
1501 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of 200 mm dia rising main for the proposed of Shyamla for Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000686/2023-2024 | 3285/RCD-1 | 08/11/2023 | 30 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.63 | 11.21 | 85
1502 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Jamuria under Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000732/2023-2024 | 3656/RCD-1 | 28/12/2023 | 330 | MD SARFARAZ ALAM | 23.33 | 20.38 | 70
1503 | RCFA Division -I | Asansol Mechanical Division | Formal work order for distribution network for augmentation of Jamuria (Rural)(Zone-I) pipe water Supply Scheme including FHTC allied work wthin Jamuria Block under RCFA Div-I PHE Dte.(Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000782/2022-2023 | 813/RCD I | 10/03/2023 | 30 | DIP CONSTRUCTION | 151.47 | 43.68 | 20
1504 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Constriction of OHR (Capacity 350 cum, staging Height 20 mtrs) for Augmentation of Jamuria Rural (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block Barabani, Dist- Paschim Bardhaman. (2nd Call) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000814/2023-2024 | 95/RCD-1 | 08/01/2024 | 366 | M/S SINGH & KONAR CONSTRUCTION | 108 | 0 | 50
1505 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Sinking of 03 (Three) Nos river bed tube wells including collecting main, Sluice Valve chamber & other allied work at Darbardanga H/W at Ajoy River under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000843/2022-2023 | 1076/RCD-I | 23/03/2023 | 90 | MAA ENTERPRISE. | 19.58 | 8.87 | 100
1506 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional estimate for concrete conduit for water body crossing at 4 (Four) nos location including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work, Supply of valve, hard rock cutting, valve chamber and allied works related to distribution network at Churulia, Rakhakura, Joynagar, Chinchurbil etc villages under Augmentation of Jamuria Rural (Zone-1) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000984/2023-2024 | 468/RCD-1 | 12/02/2024 | 45 | ASHA CONSTRUCTION | 39.4 | 38.15 | 100
1507 | Asansol Mechanical | Asansol Mechanical Division | Quotation money for New Connection at Darbardanga | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | BILL/00080/2023-2024 | BP-2023-24-17 | 05/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.48 | 0 | 0
1508 | Asansol Mechanical | Asansol Mechanical Division | Additional works for making Suction Common Header and supply delivery of cubical kisok box under Augmentation of Jamuria (Rural) Zone - I and II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000029/2025-2026 | 949/AMD | 16/05/2025 | 30 | SUNRISE ENGINEERING CORPORATION | 1.1 | 0 | 100
1509 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Jamuria Pump House under Augmentation of Jamuria Rural Zone-I Piped Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000068/2024-2025 | 1199/AMD | 07/08/2024 | 45 | SUNRISE ENGINEERING CORPORATION | 6.08 | 0 | 100
1510 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000436/2022-2023 | 491/AMD | 22/02/2023 | 731 | SUNRISE ENGINEERING CORPORATION | 145.5 | 94.72 | 100
1511 | Asansol Mechanical | Asansol Mechanical Division | Supply & Installation of submersible pumping machineries and other allied Works at Low Lift RBTW for Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000443/2024-2025 | 2101/AMD | 12/12/2024 | 30 | SUNRISE ENGINEERING CORPORATION | 13.89 | 0 | 100
1512 | Asansol Mechanical | Asansol Mechanical Division | Providing of lighting luminaries inconnection with yard lighting arrangement of newly constructed Pump House premises under Augmentation of Jamuria Rural (Zone-I) Water Supply Scheme. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000472/2024-2025 | 2179/AMD | 26/12/2024 | 166 | SASTIK ENTERPRISE | 12.05 | 0 | 100
1513 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garkilla -Kherobari (JL-27),Gourangapur(JL-28) mouzas of Garkilla-Kherobari piped W/S scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000022/2023-2024 | 735/DWSD | 15/05/2023 | 60 | BABA LOKENATH ENTERPRISE | 104.15 | 103.23 | 85
1514 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at Garkilla-Kherobari,Gourangapur(28) mouzas of Garkilla-Kherobari piped W/s Scheme under DWSD, PHE Dte under DWSD, PHE Dte (Part-A ,B & C) (SL-5) | Assistant Engineer-II | Junior Engineer-3 | ORD/000167/2022-2023 | 764/DWSD | 13/05/2022 | 45 | BABA LOKENATH ENTERPRISE | 28.84 | 4.29 | 100
1515 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garkilla Khorobari Water Supply Scheme of Paschim Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000922/2022-2023 | 1222/CMD | 16/03/2023 | 30 | SOUVIK HALDER | 10.21 | 8.74 | 70
1516 | Central Mechanical | Asansol Mechanical Division | Supply & Delivery of Pump Motor Set at TW No: 01 of Garkilla Khorobari water supply scheme under CMD, PHE, | Assistant Engineer-II | Junior Engineer-3 | ORD/001166/2023-2024 | 110/DIC/BMSD(D) | 04/10/2023 | 15 | SOUVIK HALDER | 0.52 | 0.52 | 100
1517 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution and allied works including FHTC and connection providing to Paranganj mouzas JL-79 part-B under command area of Jemua Piped W/s Scheme under DWSD, PHE Dte. |  |  | ORD/000004/2023-2024 | 584/DWSD | 11/04/2023 | 1116 | M/S UNIQUE | 31.1 | 22.9 | 100
1518 | RCFA Division -I | Asansol Mechanical Division | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 7 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 100
1519 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balanced work Sinking of 03 (Three) nos. 200 mm dia river bed tube well in the river of Ajoy (Pandabeswar H/W Site) for Source Augmentation of RCFA Part-II W/S Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000083/2024-2025 | 2108/RCD-I | 27/08/2024 | 278 | B.T.M. CONCERN | 23.41 | 11.92 | 70
1520 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 6 (Six) nos. 200 mm dia river bed tube well including 3 nos. collecting main in the river Ajoy at Runakuraghat H/W site for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000103/2024-2025 | 2123/RCD-I | 27/08/2024 | 25 | MAA ENTERPRISE | 13.24 | 12.75 | 100
1521 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Hydro-Geological study of Sub-Surface Water Flow with Sinking of Tube Well in Damodar & Ajay River bed and Bank Position of Source Augmentation of RCFA Part-II Water Supply Scheme by installing River bed tube well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000178/2024-2025 | 2435/RCD-I | 26/09/2024 | 15 | ENVIROTECH SOLUTIONS | 95 | 25.16 | 100
1522 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply and laying 240 sqmm 3.5 core cable at Kalajharia complex for searching of infiltration gallery of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000284/2025-2026 | 1388/RCD-I | 15/05/2025 | 10 | MRITYUNJOY MUKHERJEE & CO. | 27.6 | 0 | 100
1523 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000287/2023-2024 | 2336/RCD-I | 01/08/2023 | 530 | MD AAMIR KHAN | 43.86 | 21.67 | 50
1524 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000288/2023-2024 | 2337/RCD-I | 01/08/2023 | 30 | M/S MONI TRADERS | 42.45 | 41.38 | 55
1525 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting and regulating apparatus for distribution system and rising main of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000333/2025-2026 | 1616/RCD-I | 29/05/2025 | 20 | MAKALI ENGINEERING CORPORATION | 50.69 | 0 | 100
1526 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus Source of Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000601/2024-2025 | 266/RCD-I | 04/02/2025 | 30 | MAKALI ENGINEERING CORPORATION | 78.96 | 39.09 | 100
1527 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000602/2024-2025 | 267/RCD-I | 04/02/2025 | 30 | MAKALI ENGINEERING CORPORATION | 87.75 | 0 | 100
1528 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000937/2023-2024 | 477/RCD-I | 12/02/2024 | 30 | NIYATI CONSTRUCTION | 29.98 | 23.43 | 100
1529 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work of Emergent laying of Collecting Main for sinking of 4 nos river bed tube well and making of manifold with in addition of connecting of 10 nos tube well in River Ajoy at Bhaburia Head Works Site under RBT Type Sarpi, Jamgora Jagannathpur and Gourbazar-Ichapur Water Supply Scheme for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000371/2024-2025 | 3099/RCD-I | 13/12/2024 | 45 | MD AAMIR KHAN | 46.32 | 0 | 100
1530 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work of collecting main of river bed tube well in Ajay river for Gourbazar-Ichapur Piped Water Supply Scheme from river bed manifold to Bhaburia Old CWR under JJM at Durgapur-Faridpur Block of Augmentation of Gourbazar-Ichapur W/S Scheme of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000704/2024-2025 | 451/RCD-I | 12/03/2025 | 45 | MAK CONSTRUCTION CO | 24 | 0 | 100
1531 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000953/2023-2024 | 479/RCD-I | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 15.54 | 8.02 | 100
1532 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000954/2023-2024 | 480/RCD-I | 12/02/2024 | 30 | MD. JAWED KHAN | 15.82 | 8.15 | 100
1533 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000969/2023-2024 | 485/RCD-I | 12/02/2024 | 25 | SOMNATH SAMANTA | 19.46 | 19.45 | 100
1534 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 30 | TARA MA ENTERPRISE | 13.02 | 2.87 | 100
1535 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 30 | MAK CONSTRUCTION CO | 22.57 | 17.67 | 100
1536 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/001105/2023-2024 | 894/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 3.05 | 2.99 | 100
1537 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/001106/2023-2024 | 895/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 4.51 | 4.42 | 100
1538 | Asansol Mechanical | Asansol Mechanical Division | Electric quotation for Narayankuri PWSS under Source augmentation of RCFA Part-II by installing RBTW under RCFA Division-I PHe Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | BILL/00342/2025-2026 |  | 19/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0
1539 | Asansol Mechanical | Asansol Mechanical Division | Supply & Installation of submersible pumping machineries at Newly sunk 8 Nos Low Lift RBTWs at Madanpur Lowlift under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000024/2025-2026 | 944/AMD | 16/05/2025 | 30 | BENGAL CONSTRUCTION | 24.61 | 0 | 0
1540 | Asansol Mechanical | Asansol Mechanical Division | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000035/2024-2025 | 1037/AMD | 16/07/2024 | 45 | PESTCO INDIA | 8.93 | 8.87 | 100
1541 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Amkula-5 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000036/2024-2025 | 1038/AMD | 16/07/2024 | 180 | SUNRISE ENGINEERING CORPORATION | 8.47 | 0 | 100
1542 | Asansol Mechanical | Asansol Mechanical Division | Lowering of submersible pumping machineries in Newly sunk RBTW No-14 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000037/2024-2025 | 1039/AMD | 16/07/2024 | 291 | EASTERN INDIA SALES AND SERVICE | 8.15 | 0 | 100
1543 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000038/2024-2025 | 1040/AMD | 16/07/2024 | 511 | PREMNATH MITRA | 10.27 | 0 | 100
1544 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 01-06 at Surjanagar Lowlift Pump House under ASTA W/S Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000039/2024-2025 | 1041/AMD | 16/07/2024 | 45 | BENGAL CONSTRUCTION | 10.6 | 0 | 100
1545 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-8 at Union Para Low Lift under Ballavpur Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000046/2024-2025 | 1132/AMD | 30/07/2024 | 369 | HINDUSTHAN CONSULTANT FIRM | 4.84 | 0 | 100
1546 | Asansol Mechanical | Asansol Mechanical Division | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000047/2024-2025 | 1133/AMD | 30/07/2024 | 60 | PESTCO INDIA | 8.93 | 8.87 | 100
1547 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000048/2024-2025 | 1134/AMD | 30/07/2024 | 60 | M/S. SOMA ENTERPRISE | 8.55 | 6.95 | 100
1548 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs no-13 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000049/2024-2025 | 1135/AMD | 30/07/2024 | 60 | M/S S.G.ENTERPRISE | 9.75 | 0 | 0
1549 | Asansol Mechanical | Asansol Mechanical Division | Installation of transformer(315 KVA), Supply, delivery and installation S/M, Pump-Motor set, and other allied works at Madanpur Head Works Site under RCFA Part-II Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000069/2025-2026 | 1108/AMD | 16/06/2025 | 30 | M/S SAJAHAN CHOWDHURY | 37.68 | 0 | 0
1550 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000070/2024-2025 | 1201/AMD | 07/08/2024 | 45 | M/S JIT ENTERPRISE | 8.85 | 8.83 | 100
1551 | Asansol Mechanical | Asansol Mechanical Division | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000071/2024-2025 | 1202/AMD | 07/08/2024 | 45 | PESTCO INDIA | 4.97 | 4.92 | 100
1552 | Asansol Mechanical | Asansol Mechanical Division | Lowering of submersible pumping machineries in Newly sunk RBTW No-15 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000075/2024-2025 | 1206/AMD | 07/08/2024 | 288 | INDUSTRIAL ELECTRICAL CORPORATION | 8.18 | 0 | 100
1553 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no- 7 & 8 at Narayankuri Pump House under Narayankuri Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000318/2024-2025 | 1812/AMD | 29/10/2024 | 216 | HINDUSTHAN CONSULTANT FIRM | 11.21 | 0 | 100
1554 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-7 at Union Para Low Lift under Ballavpur Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000319/2024-2025 | 1813/AMD | 29/10/2024 | 306 | M/S S.G.ENTERPRISE | 5.28 | 0 | 100
1555 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no-9 and 10 at Narayankuri Pump House under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000438/2024-2025 | 2096/AMD | 12/12/2024 | 30 | PREMNATH MITRA | 9.89 | 0 | 0
1556 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries in Newly sunk RBTW No- 8 for CWR at Ajoyghat Pumping Station under source Augmentation of RCFA part-II Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000439/2024-2025 | 2097/AMD | 12/12/2024 | 30 | M/S. SOMA ENTERPRISE | 5.6 | 0 | 100
1557 | Asansol Mechanical | Asansol Mechanical Division | Providing and installation of submersible pumping machineries at newly sunk river bed tube well No-31 & 32 and other allied works at Kalajharia Water Works under source Augmentation of RCFA-II Water Supply Scheme. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000442/2024-2025 | 2100/AMD | 12/12/2024 | 30 | EASTERN INDIA SALES AND SERVICE | 28.6 | 0 | 100
1558 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied works of Gopalpur site office including construction of pump house, premises development under Augmentation of Shyambazar water supply scheme of RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000086/2024-2025 | 2111/RCD-I | 27/08/2024 | 181 | BASANTI TRADERS | 33.72 | 4.06 | 65
1559 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area Shyambazar under Augmentation Shyambazar piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | Assistant Engineer-II | Junior Engineer-3 | ORD/001210/2023-2024 | 795/DWSD | 12/09/2023 | 30 | MAJI DEVELOPERS | 98.7 | 95.14 | 100
1560 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of SHYAMBAZAR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000187/2023-2024 | 1238/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
1561 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Shyambazar piped W/s Scheme under DWSD, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000241/2023-2024 | 1527/DWSD | 13/09/2023 | 1463 | DUTTA ENTERPRISE | 208.13 | 174.64 | 100
1562 | Durgapur W/S Division | Asansol Mechanical Division | Supplying laying and testing of HDPE pipeline and other allied works from Ajodhya village to Satkahania under Augmentation of Shyambazar piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000242/2023-2024 | 1617/DWSD | 03/10/2023 | 607 | BASANTI TRADERS | 9.94 | 0 | 100
1563 | Asansol Mechanical | Asansol Mechanical Division | Payment for Quotation as per WBSEDCL Procedure - A (2010) on turn-key / full deposite basis for the site of Shyambazar T/W No - 03 (bramhanpara) under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | BILL/00149/2025-2026 |  | 20/05/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.17 | 0 | 0
1564 | Asansol Mechanical | Asansol Mechanical Division | Supply & Installation Of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System And Internal House Wiring For Tube Well No-3 At Augmentation Of Ground water based water supply scheme for Shyambazar Under Asansol Mechanical Division, Phe Dte., Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000032/2025-2026 | 952/AMD | 16/05/2025 | 30 | PESTCO INDIA | 11.61 | 0 | 0
1565 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied work at Pump House No- 01 under Shymbazar Water Supply Scheme, Block-Kanksa, Dist- Paschim Bardhaman under Asansol Mechanical Division,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000282/2024-2025 | 1676/AMD | 04/10/2024 | 30 | M/S JIT ENTERPRISE | 4.11 | 0 | 100
1566 | RCFA Division -I | Asansol Mechanical Division | License Fees for five (05) years for 6-lanning of Barwa Adda - Panagarh section of NH-2 from km 398.240 to km 521.120 including Panagarh Bypass in the state of Jharkhand & West Bengal under NHDP Phase -V on BOT (Toll) on DBFOT pattern - Permission for laying of water pipeline along NH-2 from Kalla more (km 462+080) to Harishpur (km+918) and 7 nos crossing across NH-2 in the state of West Bengal under Augmentatin of RCFA Pt II Volume -II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/00522/2024-2025 | 282/24-25 | 09/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 164.48 | 0 | 0
1567 | RCFA Division -I | Asansol Mechanical Division | Permission for laying of water pipeline along NH-2 from Kalla more (Km 462+080) to Harishpur (km 481+918) and 7 no. of crossing across NH-2 in the state of west bengal under RCFA divn-I,PHE dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01108/2024-2025 | 420/24-25 | 22/01/2025 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 64.87 | 0 | 0
1568 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01359/2023-2024 | 559/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 16.52 | 0 | 0
1569 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-67 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01361/2023-2024 | 560/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 10.41 | 0 | 0
1570 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-69 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01362/2023-2024 | 561/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
1571 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-71 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01363/2023-2024 | 562/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0
1572 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01364/2023-2024 | 563/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 17.21 | 0 | 0
1573 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-70 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01365/2023-2024 | 564/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0
1574 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-68 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01366/2023-2024 | 565/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
1575 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-72 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01367/2023-2024 | 566/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
1576 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-93 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01538/2023-2024 | 623/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
1577 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-91 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01539/2023-2024 | 624/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
1578 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-08 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01540/2023-2024 | 625/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
1579 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-90 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01541/2023-2024 | 626/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
1580 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-92 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01542/2023-2024 | 627/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.28 | 0 | 0
1581 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-95 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01543/2023-2024 | 628/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
1582 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for approach concrete road, room and toilet repairing, materials shifting and stacking and etc allied works at Searsole Stack yard under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000022/2024-2025 | 1525/RCD-I | 14/06/2024 | 45 | M/S MONDAL ENTERPRISE | 16.4 | 14.01 | 100
1583 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of laying 250 mm dia HDPE pipe line and PWD road crossing from Semalya to Kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II | Assistant Engineer-I | Junior Engineer-3 | ORD/000041/2024-2025 | 1642/RCD-I | 04/07/2024 | 497 | UMA ENTERPRISE | 71.29 | 0 | 100
1584 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000050/2024-2025 | 1750/RCD-I | 18/07/2024 | 20 | MAKALI ENGINEERING CORPORATION | 94.91 | 94.91 | 100
1585 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional for Distribution Network for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Part-4) Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000051/2024-2025 | 1741/RCD-I | 18/07/2024 | 45 | UNITED CONSTRUCTION | 30.14 | 29.22 | 85
1586 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000059/2024-2025 | 1751/RCD-I | 18/07/2024 | 20 | INDIA PIPE FITTING CO | 93.63 | 93.56 | 100
1587 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Realtime Water Quality Monitoring including 1 year maintenance for the OHR as hereunder RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000079/2024-2025 | 2033/RCD-I | 21/08/2024 | 455 | MAXBRIDGE SOLUTIONS LLP | 33.46 | 0 | 55
1588 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Visiter room and driver rest room at office premises Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000120/2024-2025 | 2155/RCD-I | 29/08/2024 | 90 | G. CONSTRUCTION | 18.48 | 15.51 | 100
1589 | RCFA Division -I | Asansol Mechanical Division | Emergency repairing work of 110 mm dia HDPE distribution main and G.I. line of Health World Hospital of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000165/2024-2025 | Camp-02_Health-World/AE/2 | 22/08/2024 | 10 | M/S CHANDI CHARAN ROY | 4.2 | 4.18 | 100
1590 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards (31 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur ,Barabani, Andal ,Pandabeswar ,Raniganj and Durgapur Faridpur Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000056/2024-2025 | 1746/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 6.1 | 5.12 | 100
1591 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards (49 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Kanksa Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000057/2024-2025 | 1747/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 9.69 | 8.45 | 100
1592 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards(43 nos)having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000058/2024-2025 | 1748/RCD-I | 18/07/2024 | 15 | UNITED CONSTRUCTION | 8.48 | 7.78 | 100
1593 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-A) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000196/2024-2025 | 2451/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 78.04 | 78.04 | 100
1594 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-B) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-3 | ORD/000197/2024-2025 | 2452/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 81.71 | 21.64 | 100
1595 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for construction work and Interior Decoration of Office Building in Asansol under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000209/2024-2025 | 2513/RCD-I | 04/10/2024 | 45 | M/S KALYANI ENTERPRISE | 41.78 | 5.37 | 100
1596 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Laying of different dia HDPE pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-IX for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000305/2023-2024 | 2383/RCD-I | 07/08/2023 | 90 | DAWN CONSTRUCTION | 105.48 | 90.97 | 100
1597 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000604/2023-2024 | 3297/RCD-I | 10/11/2023 | 15 | MD AAMIR KHAN | 24.44 | 23.98 | 100
1598 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) inAsansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000606/2023-2024 | 3298/RCD-1 | 10/11/2023 | 15 | MAK CONSTRUCTION CO | 45.92 | 45.77 | 100
1599 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Renovation work at Kalyaneswari Inspection Bungalow & WTP under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000721/2023-2024 | 3610/RCD-1 | 20/12/2023 | 540 | M/S KALYANI ENTERPRISE | 81.82 | 7.51 | 100
1600 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency repairing of 50 sqmm x 4 core Al Armoured damaged cable line and other allied Electrical works at Executive Engineer office building, SE office building, rest room & B type quarter under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000722/2023-2024 | 3573_RCD/1 | 12/12/2023 | 15 | T R ENTERPRISE | 6.82 | 6.8 | 100
1601 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Operation and regulatiing of different dia S/V of Distribution system and rising main for FHTC work for Mdira, Dighalpahari, Chotkara and Kanskuli villages under administrative contingency of JJM under RCFA Division -I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000820/2023-2024 | 101/RCD-1 | 09/01/2024 | 239 | SRI KRISHNA ENTERPRISE | 2.91 | 0 | 100
1602 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of different dia Sluice Valve, Air Valve, NRV including C.I./D.I Specials to the Searsole Store of Augmentation of RCFA Part-II (Zone-18) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000910/2023-2024 | 215/RCD-I | 29/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 49.92 | 49.92 | 100
1603 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-15) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000912/2023-2024 | 216/RCD-I | 29/01/2024 | 20 | INDIA PIPE FITTING CO | 89.25 | 89.23 | 100
1604 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-17) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000914/2023-2024 | 217/RCD-I | 29/01/2024 | 20 | MAKALI ENGINEERING CORPORATION | 90.4 | 90.4 | 100
1605 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying of rising main at Surjanagar Head Works Site to High lift site under ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000935/2023-2024 | 476/RCD-I | 12/02/2024 | 45 | MAK CONSTRUCTION CO | 58.51 | 58.43 | 100
1606 | RCFA Division -I | Asansol Mechanical Division | Allied work of laying distribution system of Improvement of RCFA Part-I Commanded area of Zone-V with LDS FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000936/2023-2024 | 451/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 25.84 | 25.44 | 100
1607 | RCFA Division -I | Asansol Mechanical Division | Allied work Balance Work of Road restoration in connection with formal work order Distribution network including FHTC and allied work at Ondal Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000938/2023-2024 | 452/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 43.94 | 38.19 | 100
1608 | RCFA Division -I | Asansol Mechanical Division | Construction of restoration approach road in Chalbalpur at Amritnagar Zone-I under RCFA Part-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000943/2023-2024 | 453/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 20.62 | 20.5 | 100
1609 | RCFA Division -I | Asansol Mechanical Division | Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000950/2023-2024 | 455/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 21.29 | 19.26 | 100
1610 | RCFA Division -I | Asansol Mechanical Division | Laying 300 mm dia MS water pipe line with 600 mm dia MS cashing pipe for Railway crossing in Salanpur in between KM 231/16-18 and Salanpur (SLS) Rupnarayanpur (RNPR) Station in Asansol Diviion under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000956/2023-2024 | 456/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 37.06 | 36.88 | 100
1611 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work of Laying and pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) with 400 mm dia and 300 mm dia MS water carrier pipe line at Node point (82-83) and (74-75) for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000939/2023-2024 | 487/RCD-I | 12/02/2024 | 25 | SWATI CORPORATION | 17.43 | 16.96 | 100
1612 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency repairing work of CI rising main (500 mm dia, 200 mm dia & 150 mm dia ) at Chotdola more, Dhasal more and new Kenda and Searsole H/W site near Pump House under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000958/2023-2024 | 504/RCD-I | 12/02/2024 | 30 | DAWN CONSTRUCTION | 8.84 | 0 | 0
1613 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Adopting trench less technology (e.g. Jack Pushing Method etc.) at 3 (Three) nos location within laying distribution system of Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000963/2023-2024 | 457/RCD-1 | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 23.02 | 23.02 | 100
1614 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of pipe line from Domhani Asansol main Road near BDO Office to Domohani PHC and construction of stand post at different places at Domohani Bazar under Barabani Development Block under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000966/2023-2024 | 458/RCD-1 | 12/02/2024 | 20 | UNITED CONSTRUCTION | 6.71 | 4.03 | 62
1615 | RCFA Division -I | Asansol Mechanical Division | Laying of 110 mm dia HDPE pipeline including pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology at Health World Hospital, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. Extension work. | Assistant Engineer-I | Junior Engineer-3 | ORD/001020/2023-2024 | Camp-02_Health_World_AE-I | 21/02/2024 | 20 | M/S CHANDI CHARAN ROY | 18.54 | 18.06 | 100
1616 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supplying of different pipe specials for Ondal (Phase-I) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II for providing FHTC under Andal Block | Assistant Engineer-I | Junior Engineer-3 | ORD/001168/2023-2024 | 1006/RCD-I | 16/03/2024 | 15 | M/S UNIT CONSTRUCTION | 12.5 | 10.91 | 100
1617 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Modification, Improvement of storage, documents with seating arrangement of entire Central Circle, PHE Dte. at Purta Bhawan in the District of Purba Bardhhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/001183/2023-2024 | 932/RCD-I | 15/03/2024 | 196 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.53 | 0 | 100
1618 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3 | RTOR000001/2024-2025 | 1178/RCD-I | 03/04/2024 | 0 | Resource Division | 337.92 | 0 | 0
1619 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3 | RTOR000004/2025-2026 | 962/RCD-I | 23/04/2025 | 0 | Resource Division | 313.98 | 0 | 0
1620 | Asansol Mechanical | Asansol Mechanical Division | Installation Charge and Security Deposit for Bulk Power Supply at Intake Sub-Station Sarkuri Salanpur Under Augmentation of RCFA Part-II | Assistant Engineer-I | Junior Engineer-3 | BILL/00003/2024-2025 | BP-2024-25-2 | 15/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 54.89 | 0 | 0
1621 | Asansol Mechanical | Asansol Mechanical Division | DIVERSION OF 33KV S/C PHE FEEDER INSIDE THE PREMISES OF THE PHE DUE TO PROPOSED WTP,KALYNESWARI FOR M/S PHE DIRECTORATE,ASANSOL | Assistant Engineer-I | Junior Engineer-3 | BILL/00022/2024-2025 | BP-2024-25-4 | 23/04/2024 | 0 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 2.8 | 0 | 0
1622 | Asansol Mechanical | Asansol Mechanical Division | Shifting of overhead line inside the premises of benali boosting station | Assistant Engineer-I | Junior Engineer-3 | BILL/00075/2024-2025 | BP-2024-25-14 | 17/05/2024 | 0 | INDIA POWER CORPN. LTD. | 2.84 | 0 | 0
1623 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of NOV, 2023. | Assistant Engineer-I | Junior Engineer-3 | BILL/00303/2024-2025 | BP-2024-25-27/4 | 30/07/2024 | 0 | RANAJIT AUTO | 0.09 | 0 | 0
1624 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of DECEMBER, 2023. | Assistant Engineer-I | Junior Engineer-3 | BILL/00305/2024-2025 | BP-2024-25-27/5 | 30/07/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1625 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of NOVEMBER, 2023 | Assistant Engineer-I | Junior Engineer-3 | BILL/00307/2024-2025 | BP-2024-25-27/2 | 30/07/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1626 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of JANUARY, 2024 | Assistant Engineer-I | Junior Engineer-3 | BILL/00310/2024-2025 | BP-2024-25-30 | 06/08/2024 | 0 | RANAJIT AUTO | 0.26 | 0 | 0
1627 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of FEBRUARY, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00312/2024-2025 | BP-2024-25-30/1 | 06/08/2024 | 0 | RANAJIT AUTO | 0.27 | 0 | 0
1628 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of NOVEMBER, 2023. | Assistant Engineer-I | Junior Engineer-3 | BILL/00313/2024-2025 | BP-2024-25-27 | 30/07/2024 | 0 | RANAJIT AUTO | 0.2 | 0 | 0
1629 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of DECEMBER, 2023 | Assistant Engineer-I | Junior Engineer-3 | BILL/00315/2024-2025 | BP-2024-25-27/1 | 30/07/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0
1630 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of JANUARY, 2024 | Assistant Engineer-I | Junior Engineer-3 | BILL/00317/2024-2025 | BP-2024-25-30/2 | 06/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
1631 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of FEBRUARY, 2024 | Assistant Engineer-I | Junior Engineer-3 | BILL/00319/2024-2025 | BP-2024-25-30/3 | 06/08/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1632 | Asansol Mechanical | Asansol Mechanical Division | Fuel Charges for the Cab of AE - I under AMD, PHE Dte. for the month of DECEMBER, 2023 | Assistant Engineer-I | Junior Engineer-3 | BILL/00320/2024-2025 | BP-2024-25-27/3 | 30/07/2024 | 0 | RANAJIT AUTO | 0.26 | 0 | 0
1633 | Asansol Mechanical | Asansol Mechanical Division | Payment of Security Deposite & Remaining Earnest Money for Bansra Boosting Station (Consumer ID- 950085633) under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/00398/2024-2025 | BP-2024-25-24 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 24.84 | 0 | 0
1634 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of March, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00459/2024-2025 | BP-2024-25-33/1 | 23/08/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1635 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of April, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00461/2024-2025 | BP-2024-25-33/3 | 23/08/2024 | 0 | RANAJIT AUTO | 0.15 | 0 | 0
1636 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of March, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00463/2024-2025 | BP-2024-25-33/5 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
1637 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of April, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00465/2024-2025 | BP-2024-25-33/7 | 23/08/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1638 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Jan, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00467/2024-2025 | BP-2024-25-34/1 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
1639 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Feb, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00469/2024-2025 | BP-2024-25-34/3 | 23/08/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1640 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of March,2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00471/2024-2025 | BP-2024-25-34/5 | 23/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
1641 | Asansol Mechanical | Asansol Mechanical Division | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of April, 2024. | Assistant Engineer-I | Junior Engineer-3 | BILL/00473/2024-2025 | BP-2024-25-62 | 28/10/2024 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1642 | Asansol Mechanical | Asansol Mechanical Division | PAYMENT OF SECURITY DEPOSIT & EARNEST MONEY FOR BULK POWER SUPPLY AT SHANKARPUR BOOSTING STATION. | Assistant Engineer-I | Junior Engineer-3 | BILL/00589/2024-2025 | BP-2024-25-63 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.9 | 0 | 0
1643 | Asansol Mechanical | Asansol Mechanical Division | Quotation for Earnest Money Deposit at Bansra Boosting Station, Kunustoria under Augmentation of RCFA II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00692/2023-2024 | BP-2023-24-61 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1644 | Asansol Mechanical | Asansol Mechanical Division | Quotation for Earnest Money Deposit at Searsole Boosting Station, Ranisayer under Augmentation of RCFA II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00693/2023-2024 | BP-2023-24-62 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1645 | Asansol Mechanical | Asansol Mechanical Division | PAYMENT OF QUOTATION AS PER WBSEDCL PROCEDURE - A (2010) ON TURN-KEY/ FULL DEPOSIT BASIS FOR THE SITE OF SAORA OHR SITE, UNDER AUGMENTATION OF RCFA PART -II PIPED WATER SUPPLY SCHEME VOLUME-II (BOOSTER STATIONS & ALLIED WORKS) UNDER RCFA DIV.-I, PHE DTE | Assistant Engineer-I | Junior Engineer-3 | BILL/00693/2025-2026 |  | 15/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.57 | 0 | 0
1646 | Asansol Mechanical | Asansol Mechanical Division | Quotation for Earnest Money Deposit at Sankarpur Boosting Station, Chhora under Augmentation of RCFA II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00694/2023-2024 | BP-2023-24-63 | 28/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1647 | Asansol Mechanical | Asansol Mechanical Division | PAYMENT OF QUOTATION AS PER WBSEDCL PROCEDURE - A (2010) ON TURN-KEY/ FULL DEPOSIT BASIS FOR THE SITE OF EGARA OHR SITE, UNDER AUGMENTATION OF RCFA PART -II PIPED WATER SUPPLY SCHEME VOLUME-II (BOOSTER STATIONS & ALLIED WORKS) UNDER RCFA DIV.-I, PHE DTE | Assistant Engineer-I | Junior Engineer-3 | BILL/00694/2025-2026 |  | 15/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0
1648 | Asansol Mechanical | Asansol Mechanical Division | PAYMENT OF QUOTATION AS PER WBSEDCL PROCEDURE - A (2010) ON TURN-KEY/ FULL DEPOSIT BASIS FOR THE SITE OF SAHEBGANJ OHR SITE, UNDER AUGMENTATION OF RCFA PART -II PIPED WATER SUPPLY SCHEME VOLUME-II (BOOSTER STATIONS & ALLIED WORKS) UNDER RCFA DIV.-I, PHE DTE. | Assistant Engineer-I | Junior Engineer-3 | BILL/00695/2025-2026 |  | 15/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.7 | 0 | 0
1649 | Asansol Mechanical | Asansol Mechanical Division | Earnest Money Deposit for Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00696/2023-2024 | BP-2023-24-65 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1650 | Asansol Mechanical | Asansol Mechanical Division | Earnest Money Deposit for Bulk Power Supply at Intake sub-station Sarkuri Salanpur under Augmentation of RCFA Part II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00697/2023-2024 | BP-2023-24-66 | 02/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1651 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for Earnest Money Deposition for Bulk Power supply at Kalyaneswari under Augmentation of RCFA Part II WS Scheme. | Assistant Engineer-I | Junior Engineer-3 | BILL/00777/2023-2024 | BP-2023-24-69 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.2 | 0 | 0
1652 | Asansol Mechanical | Asansol Mechanical Division | Bulk Power Supply at Searsole Boosting Station under Augmentation of RCFA Part II. | Assistant Engineer-I | Junior Engineer-3 | BILL/00911/2023-2024 | BP-2023-24-76 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 93.38 | 0 | 0
1653 | Asansol Mechanical | Asansol Mechanical Division | Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II. | Assistant Engineer-I | Junior Engineer-3 | BILL/00912/2023-2024 | BP-2023-24-77 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.75 | 0 | 0
1654 | Asansol Mechanical | Asansol Mechanical Division | PAYMENT OF QUOTATION AS PER WBSEDCL PROCEDURE - A (2010) ON TURN-KEY/ FULL DEPOSIT BASIS FOR THE SITE OF CHELAD OHR SITE, UNDER AUGMENTATION OF RCFA PART -II PIPED WATER SUPPLY SCHEME VOLUME-II (BOOSTER STATIONS & ALLIED WORKS) UNDER RCFA DIV.-I, PHE DTE | Assistant Engineer-I | Junior Engineer-3 | BILL/01096/2025-2026 |  | 09/01/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.66 | 0 | 0
1655 | Asansol Mechanical | Asansol Mechanical Division | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-I under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000087/2023-2024 | 1091/AMD | 25/04/2023 | 365 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0.84 | 83
1656 | Asansol Mechanical | Asansol Mechanical Division | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-II under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000088/2023-2024 | 1092/AMD | 25/04/2023 | 365 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0.88 | 83
1657 | Asansol Mechanical | Asansol Mechanical Division | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Executive Engineer under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000089/2023-2024 | 1099/AMD | 26/04/2023 | 365 | SUNRISE ENGINEERING CORPORATION | 1.79 | 0.87 | 67
1658 | Asansol Mechanical | Asansol Mechanical Division | Providing & Installation of Electrical Equipments For Sub-Station at Mohishila Boosting Station (GLR-I & II), Searsole Boosting Station (GLR-I & II), Sankarpur Clear Water Boosting Station and Banshra Clear Water Boosting Station and Gaseous Chlorination system at different OHR sites with illumination under Augmentation of RCFA Part-II Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000203/2023-2024 | 1492/AMD | 04/08/2023 | 366 | ORIENTAL ENGINEERING CO. | 1965.22 | 1393.7 | 71
1659 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Providing FHTC of retrofitting at Kumardiha village (left out portion) of Kumardiha Mouza, Retrofitting of Madantore PWSS for providing FHTC under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000281/2024-2025 | 2619/RCD-I | 14/11/2024 | 20 | D.S.C. CONCERN | 6.57 | 0 | 0
1660 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of pipe line including supply of valve, construction of valve chamber, restoration of FHTC etc. at Bathan Bari, Sidhabari, Kalyaneswari and adjoining area Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000516/2024-2025 | 116/RCD-I | 08/01/2025 | 45 | DIP CONSTRUCTION | 13.76 | 0 | 100
1661 | RCFA Division -I | RCFA Division I | Acceptance cum work order for supplying, aligning, laying of PVC & HDPE Pipeline, Construction of Sluice valve chamber and supplying, aligning, laying of G.I Pipe under Retrofitting of Madantore PWSS scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000784/2022-2023 | 405/RCD-I | 30/01/2023 | 15 | M/S S.K. ENTERPRISE | 5.17 | 5.17 | 0
1662 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 5 (Five nos. 200mm dia river bed tube wells including collecting main instead of defunct tube well at river Damodar (intake well Site ) Kalajharia Under Omprovement of RCFS part-II W/S Scheme under RCFA Division-I PHE Dte. (Part-G). | Assistant Engineer 2 | Junior Engineer | ORD/000789/2022-2023 | 402/RCDI | 30/01/2023 | 15 | DURGADAS MONDAL | 8.43 | 7.68 | 0
1663 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repairing & shifting work of DI pipes, repairing of 350 mm dia MS pipe and allied repairing at Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000940/2022-2023 | 1278/ RCD I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.78 | 4.69 | 100
1664 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000006/2023-2024 | 1857/RCD-I | 31/05/2023 | 0 | Resource Division | 1.76 | 0 | 0
1665 | RCFA Division -I | RCFA Division I | Arrangement of breakfast (Tea with snacks) for DWSM meeting held on 27.07.2024 at ADDA Conference hall, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00935/2024-2025 | 240/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.08 | 0 | 0
1666 | RCFA Division -I | RCFA Division I | Arrangeme of tiffin packets for DWSM meeting held on 27.07.2024 at ADDA Conferene hall, Asansol, Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00936/2024-2025 | 241/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.09 | 0 | 0
1667 | RCFA Division -I | RCFA Division I | Installation of quick Heal Anti Viru for 3 years under RCFA Diivison-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00937/2024-2025 | 245/24-25 | 27/08/2024 | 0 | MUKHERJEE TRADERS | 0.09 | 0 | 0
1668 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 2 | Junior Engineer | ORD/000299/2021-2022 | 2124/RCD-I | 29/11/2021 | 30 | A.K.CONSTRUCTION | 14.4 | 14.4 | 0
1669 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B) | Assistant Engineer 2 | Junior Engineer | ORD/000300/2021-2022 | 2125/RCD-I | 29/11/2021 | 30 | UNITED CONSTRUCTION | 14.36 | 14.36 | 0
1670 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000301/2021-2022 | 2126/RCD-I | 29/11/2021 | 30 | DURGADAS MONDAL | 14.37 | 14.26 | 0
1671 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ D) | Assistant Engineer 2 | Junior Engineer | ORD/000302/2021-2022 | 2127/RCD-I | 29/11/2021 | 30 | SIMA ENTERPRISE | 14.42 | 14.42 | 0
1672 | RCFA Division -I | RCFA Division I | Acceptance cum work for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ E) | Assistant Engineer 2 | Junior Engineer | ORD/000303/2021-2022 | 2128/RCD-I | 29/11/2021 | 30 | M/S KALYANI ENTERPRISE | 14.45 | 14.44 | 0
1673 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ F) | Assistant Engineer 2 | Junior Engineer | ORD/000304/2021-2022 | 2129/RCD-I | 29/11/2021 | 30 | M/S SUBHRADEEP | 16.51 | 16.51 | 0
1674 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and interconnection work of different dia HDPE pipe line unde Dakshin Khanda area Khandra Zone under RCFA Pt-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000489/2021-2022 | 118/RCD-I | 20/01/2022 | 30 | UNITED CONSTRUCTION | 13.96 | 10.91 | 0
1675 | RCFA Division -I | RCFA Division I | Laying of 25 mm dia PVC pipe line at Ukhra Adarsha Hindi High School and installation of Street stand post and etc. allied works at Dakshin Khanda area under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000510/2021-2022 | 224/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.63 | 4.63 | 0
1676 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000526/2022-2023 | 3139/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
1677 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000528/2022-2023 | 3141/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
1678 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000529/2022-2023 | 3142/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
1679 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000531/2022-2023 | 3144/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
1680 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000002/2021-2022 | 2281/RCD-I | 12/12/2021 | 0 | Resource Division | 10.17 | 0 | 0
1681 | Durgapur W/S Division | Asansol Mechanical Division | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur | Assistant Engineer-II | Junior Engineer-3 | BILL/00176/2022-2023 | BP-2022-23-333 | 15/03/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 18 | 0 | 0
1682 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying & laying of different dia HDPE pipe line with necessary allied works at Silampur mouza(JL-90) block -Kanksa under Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000006/2022-2023 | 651/DWSD | 22/04/2022 | 25 | MD AAMIR KHAN | 91.75 | 82.05 | 60
1683 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying & laying of different dia HDPE pipe line with necessary allied works at Ayma Biswanathpur and Gangbil Mouza (JL-82/83) block -Kanksa under Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000007/2022-2023 | 658/DWSD | 22/04/2022 | 25 | TARA PRASAD SARKAR | 77.97 | 77.17 | 100
1684 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 350 M3 capacity , 20 mtr staging height RCC Over head Reservoir (OHR) at Silampur Pump House No-1 of Augmentation of Kaksa piped W/s Scheme under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000013/2022-2023 | 652/DWSD | 22/04/2022 | 184 | MD AAMIR KHAN | 83.27 | 74.24 | 85
1685 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work at RCC O HR site at Silampur under Augmentation of Kanksa (Zone-I) Piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000038/2023-2024 | 763/DWSD. | 22/05/2023 | 20 | MD AAMIR KHAN | 6.88 | 2.84 | 80
1686 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of latrine and boundary wall of pump house cum chlorine room and necessary allied works at Anandpur H/W site for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000043/2023-2024 | 767/DWSD | 22/05/2023 | 15 | CHANDAN HAZRA | 6.76 | 6.56 | 100
1687 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Trail bore for 2 Nos (300x200 mm dia) tube well by direct rotary method at Annandapur and Shilampur pump house at Kanksa (Zone-I) for Augmentation of ground water of Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000048/2022-2023 | 583/DWSD | 21/04/2022 | 7 | RANJIB GHATAK | 3.91 | 3.91 | 0
1688 | Durgapur W/S Division | Asansol Mechanical Division | Additional work of supplying and laying of different dia HDPE pipe line with necessary allied works at Aymabiswanath ,Gangbill mouza(JL-82,83) block-Kanksa under Augmentation of Kanksa Zone-I piped W/S scheme under DWSD,PHE Dte (SM/10208) | Assistant Engineer-II | Junior Engineer-3 | ORD/000070/2023-2024 | 1067/DWSD | 12/07/2023 | 30 | TARA PRASAD SARKAR | 96.72 | 74.03 | 100
1689 | Durgapur W/S Division | Asansol Mechanical Division | Construction of boundary wall at railpar Saroda Pally head works site pump house No-III WT_3 for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000088/2023-2024 | 721/DWSD | 11/05/2023 | 25 | CHATTERJEE CONSTRUCTION | 14.8 | 9.48 | 100
1690 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 1 No Tube well 250 mm X 150 mm big dia Tube well 150 mtr deapth direct rotary rig method using PVC pipe & fiber glass rein forced epoxy resin slotted TW No-1 Part-A site at Shilampur Pump house under Kanksa block (Zone-I) for Kanksa piped W/s Scheme (Zone-I) under DWSD, PHE Dte (SL-11) | Assistant Engineer-II | Junior Engineer-3 | ORD/000099/2022-2023 | 748/DWSD | 10/05/2022 | 10 | RANJIB GHATAK | 10.68 | 10.67 | 0
1691 | Durgapur W/S Division | Asansol Mechanical Division | Construction of boundary wall at Railpar Saroda Pally H/W site pump house no-2/TW-II for Augmentation of Kanksa Zone-I) piped W/s Scheme under DWSD ,PHE Dte . | Assistant Engineer-II | Junior Engineer-3 | ORD/000101/2023-2024 | 1106/DWSD | 14/07/2023 | 40 | MUKHERJEE ENTERPRISE | 14.79 | 9.46 | 100
1692 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction boundary wall at Shilampur pump house No-1 under Augmentation of ground water base Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte (SL-16) | Assistant Engineer-II | Junior Engineer-3 | ORD/000131/2022-2023 | 818/DWSD | 23/05/2022 | 20 | BASANTI TRADERS | 10.89 | 9.18 | 100
1693 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying , fitting , fixing and fabrication of sign board With Necessary allied Work at different Placeses of ongoing New PWSS &Augamentation Scheme (As per Departmental Approved drawing & Direction) in connection with Augmentation of Kanksa Zone - I Pipe W/S Scheme ( JJM) Work under Durgapur Water Supply Division ,PHE Dte. (Sl - 06) | Assistant Engineer-II | Junior Engineer-3 | ORD/000131/2023-2024 | 15/SPOT/DWSD | 16/06/2023 | 7 | AMARANJALI CONSTRUCTION | 0.96 | 0 | 0
1694 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supply, delivery & installation of Poly vinayle laminated board including framework for different Head Work site of New PWSs (JJM) under Kanksa Zone- I W/S Scheme under EE/DWSD/ PHE Dte. (Sl- 04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000136/2023-2024 | 1189/DWSD | 25/07/2023 | 15 | JOY GURU ENTERPRISE | 0.82 | 0.82 | 100
1695 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of repairing of office room and necessary allied works under Augmentation of Kanksa Zone-I piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000141/2023-2024 | 1271/DWSD | 07/08/2023 | 15 | A.K.D. ENTERPRISE | 4.9 | 1.74 | 100
1696 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of construction of pump house cum chlorine room at Silampur pump house No-I H/W site for Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000148/2023-2024 | 1279/DWSD | 07/08/2023 | 45 | MUKHERJEE ENTERPRISE | 6.41 | 0 | 100
1697 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional trail bore by direct Rotary method drilling using Rig machin at Kanchanpur/Basdebpur H/W Site for newly sinking of Well No-I and II under Augmentation of Kanksa (Zone-I) piped W/s scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000149/2023-2024 | 1280/DWSD | 07/08/2023 | 10 | JOY GURU ENTERPRISE | 2.27 | 2.27 | 100
1698 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KANCHANPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000178/2023-2024 | 916/DWSD | 22/06/2023 | 7 | CARTO | 0.78 | 0 | 0
1699 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of TILAKCHANDRAPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000179/2023-2024 | 917/DWSD | 22/06/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0
1700 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Details route survey ,drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Kanksa (Zone-I) piped W/S Scheme DWSD,PHE Dte (Sl-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000180/2021-2022 | 1420/DWSD | 27/09/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.52 | 5.52 | 0
1701 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KRISHNAPUR PWSS under KANKSA Development Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000180/2023-2024 | 918/DWSD | 22/06/2023 | 7 | CARTO | 0.78 | 0 | 0
1702 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of Kanksa Zone - I (PART - B) under Kanksa Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No - 05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000186/2023-2024 | 1239/DWSD | 31/07/2023 | 7 | CARTO | 0.78 | 0.78 | 100
1703 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KRISHNAPUR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -07) | Assistant Engineer-II | Junior Engineer-3 | ORD/000188/2023-2024 | 1237/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0
1704 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of KANCHANPUR (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No -08) | Assistant Engineer-II | Junior Engineer-3 | ORD/000189/2023-2024 | 1236/DWSD | 31/07/2023 | 7 | MEASURE LAND | 0.78 | 0 | 0
1705 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Sarada Pally H/W Site Pump house No-3 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000197/2022-2023 | 1054/DWSD | 07/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 1.36 | 100
1706 | Durgapur W/S Division | Asansol Mechanical Division | Dismantling of concrete road and bituminous road of Augmentation of Kanksa zone I/B piped W/s Scheme with construction of boundary wall renovation of all existing structure repairing of all retaining structure left out LDS FHTC Reconnection of FHTC at Kanksa (Part),Debipur(Part),Panagarh(Part) ,Prayagpur(Part) mouza of JL-86,87,88 of Kanksa Block under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000200/2023-2024 | 1090/DWSD | 13/07/2023 | 30 | MAK CONSTRUCTION CO. | 23.98 | 23.91 | 100
1707 | Durgapur W/S Division | Asansol Mechanical Division | Replacement of existing pipeline for Physical certificate of HarGhar Jal IN connection of JJM of Augmentation of Kanksa (Zone-I ) piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000201/2023-2024 | 1092/DWSD | 13/07/2023 | 30 | MD AAMIR KHAN | 36.07 | 34.74 | 100
1708 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works and other allied works at Sarada Pally H/W Site Pump house No-2 &T.W-02 for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-09) | Assistant Engineer-II | Junior Engineer-3 | ORD/000203/2022-2023 | 1075/DWSD | 12/07/2022 | 25 | MUKHERJEE ENTERPRISE | 4.82 | 1.37 | 100
1709 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Molandighi H/W site Pump house No-1 Tube well No-01 for Bistupur pipe W/S Scheme under DWSD,PHE Dte (SL-10) | Assistant Engineer-II | Junior Engineer-3 | ORD/000204/2022-2023 | 1076/DWSD | 12/07/2022 | 25 | CHATTERJEE CONSTRUCTION | 4.82 | 1.16 | 100
1710 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional FHTC and necessary allied works at Silampur(JL-90) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000257/2022-2023 | 1574/DWSD | 02/11/2022 | 15 | MD AAMIR KHAN | 7.26 | 7.12 | 100
1711 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional FHTC and necessary allied works at Ayma Biswanathpur(JL-82),Ganbil(JL-83) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000258/2022-2023 | 1575/DWSD | 02/11/2022 | 15 | TARA PRASAD SARKAR | 23.21 | 23.2 | 100
1712 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for supplying and laying of different dia HDPE pipe line with FHTC and necessary allied Works at Anandapur (JL-89) mouza of Augmentation of Kanksa (Zone-I) piped W/s Scheme under DWSD,PHE Dte. (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000259/2022-2023 | 1576/DWSD | 02/11/2022 | 847 | RANJIB GHATAK | 12.79 | 0 | 100
1713 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Replaying of 160 mm /110 mm dia HDPE main pipe line at Panagarh to Shilampur road of Kanksa (Zone-I) W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000261/2021-2022 | 1708/DWSD | 08/12/2021 | 30 | MAK CONSTRUCTION CO. | 9.64 | 9.83 | 0
1714 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Annandapur mouza (JL-89) under command area of Kanksa Zone-I piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-24) | Assistant Engineer-II | Junior Engineer-3 | ORD/000269/2020-2021 | 1324/DWSD | 09/12/2020 | 45 | M/S KALYANI ENTERPRISE | 18.17 | 18.25 | 0
1715 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying of 90 mm dia HDPE pipe line and withdrawing of 90 mm dia UPVC and laying the same in opposite flank of road with necessary allied works at Anandapur mouza,ICDS to Dompara under Kanksa (Z-I) W/s Scheme ,Block -Kanksa for cambat of upcoming drought unde DWSD , PHE Dte . (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000356/2021-2022 | 73/DWSD | 21/01/2022 | 10 | RANJIB GHATAK | 1.78 | 1.79 | 0
1716 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work Supplying ,laying and aligning of HDPE distribution pipe line and allied works at Railpar Saradapally Mouza under command area of Augmentation of Kanksa (Zone-II/D) under DWSD ,PHE Dte (Part-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000394/2021-2022 | 184/DWSD | 11/02/2022 | 30 | M/S S. CHOUDHURY | 96.45 | 37.88 | 100
1717 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying& laying of different dia HDPE pipe line with necessary allied works at Anandapur Mouza(JL-89),Block -Kanksa under Augmentation of Kanksa (Zone-I W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000395/2021-2022 | 197/DWSD | 16/02/2022 | 30 | AMAR CONSTRUCTION | 27.51 | 15.36 | 0
1718 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Sinking of 1No(300X200 mm) dia tube well 150 mtr deep by direct rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at Tube well No-03 site at Anandapur under Kanksa block (Zone-I) for Augmentation of ground water base Kanksa (Zone-I) piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000396/2021-2022 | 196/DWSD | 16/02/2022 | 30 | RANJIB GHATAK | 10.43 | 10.22 | 0
1719 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at AnandaPur H/W site of ground water base Kanksa(Zone-I) pipe W/s Scheme under DWSD ,PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000403/2021-2022 | 241/A/DWSD | 25/02/2022 | 45 | CHANDAN HAZRA | 4.99 | 4.89 | 0
1720 | Durgapur W/S Division | Asansol Mechanical Division | Continuation for the work of Providing functional house hold tap connection (FHTC) in connection with JJM for Domra mouza-68 under command area of Trilakchandrapur piped W/s Scheme at Kanksa Block under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000426/2021-2022 | 347/DWSD | 17/03/2022 | 1110 | AMARANJALI CONSTRUCTION | 3.03 | 0 | 100
1721 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Supplying and laying of 150 mm dia DIC (K9) & 150 mm dia HDPE pipe line with necessary allied works at Kanksa block of Anandpur to Silampur under Augmentation of Kanksa (Zone-I) piped W/s Scheme (JJM) under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000445/2022-2023 | 108/DWSD | 24/01/2023 | 20 | A.K.D. ENTERPRISE | 4.96 | 4.78 | 100
1722 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Urgent repairing of 250 mm dia pipe line and UPVC pipe line with necessary allied works at Silampur ,Gungbill an Aymma Biswanathpur distribution area under Kanksa (Zone-I) Pipe W/s Scheme under DWSD, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000447/2021-2022 | 426/DWSD | 30/03/2022 | 10 | MD AAMIR KHAN | 4.82 | 4.76 | 0
1723 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Rearing of pump house -I boundary wall and plinth protection at Silampur under Kanksa (Zone-I) for Augmentation of ground water based Kanksa (Zone-I) piped W/s Scheme under DWSD, PHE Dte.(SL-13) | Assistant Engineer-II | Junior Engineer-3 | ORD/000449/2021-2022 | 428/DWSD | 30/03/2022 | 15 | BASANTI TRADERS | 4.84 | 1.46 | 0
1724 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000013/2022-2023 | 399/DWSD | 03/03/2023 | 0 | Resource Division | 7.39 | 0 | 0
1725 | Durgapur W/S Division | Asansol Mechanical Division | Quatation for Kanksa Zone -I Pump house no -03 | Assistant Engineer-II | Junior Engineer-3 | VCH/000232/2022-2023 | BP-2022-23-103 | 02/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.97 | 0 | 0
1726 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of Kanksa Zone - I Water Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000070/2023-2024 | 2570/CMD | 06/06/2023 | 30 | MS DAS ELECTRIC CO | 19.35 | 9.41 | 46
1727 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Pump House No-01 under Augmentation of Kanksa Zone-I Water Supply Scheme, Block- Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000315/2024-2025 | 1809/AMD | 29/10/2024 | 30 | M/S A.D.ENTERPRISE | 2.97 | 0 | 0
1728 | RCFA Division -I | Asansol Mechanical Division | Fuel bill in favor of Ranjit Auto for the month of March 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00221/2024-2025 | 109/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.2 | 0 | 0
1729 | RCFA Division -I | Asansol Mechanical Division | Fuel bill in favor of Ranjit Auto for the month of April 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00222/2024-2025 | 110/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0
1730 | RCFA Division -I | Asansol Mechanical Division | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00487/2024-2025 | 255/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0
1731 | RCFA Division -I | Asansol Mechanical Division | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00489/2024-2025 | 257/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
1732 | RCFA Division -I | Asansol Mechanical Division | Fuel bill in faver of Ranajit auto for the month of august 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00968/2024-2025 |  | 29/11/2024 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1733 | RCFA Division -I | Asansol Mechanical Division | Fuel bill in faver of Ranajit auto for the month of july 2024 for one no vechile for office of the deputy superitending enginer RCFA W/S Circle PHE dte govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00989/2024-2025 |  | 03/12/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0
1734 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of construction of CWR at Runakuraghat for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000062/2024-2025 | 1590/RCD-I | 27/06/2024 | 45 | SAMIR KUMAR ROY CHOWDHURY | 9.92 | 9.07 | 100
1735 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000100/2022-2023 | 1273/RCD-I | 02/06/2022 | 90 | SRI KRISHNA ENTERPRISE | 75.81 | 74.68 | 100
1736 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000101/2022-2023 | 1274/RCD-I | 02/06/2022 | 670 | RUBY CONSTRUCTION | 41.7 | 37.77 | 80
1737 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000102/2022-2023 | 1275/RCD-I | 02/06/2022 | 90 | JYOGOMAYA ENTERPRISE | 28.02 | 28.01 | 100
1738 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL No 08) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000115/2022-2023 | 1282/RCDI | 02/06/2022 | 30 | SRI KRISHNA ENTERPRISE | 21.96 | 10.24 | 100
1739 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme including FHTC Work and Construction of 300 cum capacity 20 Mtr staging height RCC Over Head Reservoir Block Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000121/2022-2023 | 1607/RCD-I | 06/07/2022 | 180 | SRI KRISHNA ENTERPRISE | 163.56 | 163.51 | 100
1740 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing of Boundary wall, dismantling & reconstruction of flooring of Pump House, CWR and other allied work at H/W site of Ballavpur Hospital under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000267/2023-2024 | 2324/RCD-I | 01/08/2023 | 21 | SUBHADEEP DAS | 7.46 | 7.4 | 100
1741 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Extension of pipe line for providing 60 nos FHTC at different area of Kendra for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000470/2023-2024 | 2861/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 26.79 | 23.92 | 100
1742 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR for Augumentation of Roshna Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000479/2021-2022 | 2349/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.03 | 3.03 | 0
1743 | RCFA Division -I | Asansol Mechanical Division | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000527/2022-2023 | 3140/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 50
1744 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for laying of 200 mm dia rising main for Roshna OHR from Gourandi CWR under Augmentation of Roshna Piped water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000830/2022-2023 | 1034/RCDI | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 11.44 | 8.64 | 60
1745 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order forLaying of different dia HDPE pipe line including concrete cutting and mending work at Khyerbaid, Amdiha area Zone-IX under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 26) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000864/2022-2023 | 1092/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 24.69 | 13.18 | 80
1746 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing, Renovation, renewing & overhauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Works Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 Nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75cum/hr ¿ 2nos) at Madantore Head works site for Madantore W/S Scheme under RCFA Division-I PHE Dte. (Part-B) iii) for 4 nos. Iron removal Plant (Pressure type) each capacity 20 cum/hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. Iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Works Site under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000879/2023-2024 | 1391_I_RCD_I | 11/04/2023 | 60 | TARAPRASAD SARKAR | 52.19 | 46.97 | 70
1747 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Additional work for the laying of 315 mm dia HDPE pipe instead of 300 mm dia D.I. pipe of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000882/2022-2023 | 1140/RCD-I | 24/03/2023 | 30 | UMA ENTERPRISE | 71.96 | 70.46 | 30
1748 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of 1.5 mtrs Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 3 layer Barbed Wire around Roshna Head Works Site under Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 09) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000887/2022-2023 | 1131/ RCD I | 24/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 27.16 | 25.57 | 95
1749 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional laying of 90 mm dia HDPE pipe of distribution network at Aliganj and surrounding area for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000897/2022-2023 | 1151/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 5.99 | 4.63 | 50
1750 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional Laying of 200 mm dia rising main for the Augmentation of Roshna Piped Water Supply Scheme . under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000975/2023-2024 | 462/RCD-1 | 12/02/2024 | 30 | T R ENTERPRISE | 12.98 | 12.18 | 100
1751 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying and pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Aliganj within distribution system Part-C of Roshna under Augmentation of Roshna PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000992/2023-2024 | 472/RCD-1 | 12/02/2024 | 25 | RUBY CONSTRUCTION | 11.75 | 0 | 100
1752 | RCFA Division -I | Asansol Mechanical Division | Formal work order for construction of CWR 150 cum, sub station building of H/W site, pump house, chlorine room and other allied work (Bank of Ajoy river) under Semalya Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001037/2022-2023 | 1216_1_RCD-I | 24/03/2023 | 120 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 72.59 | 0 | 0
1753 | RCFA Division -I | Asansol Mechanical Division | Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.03.2024 to 31.08.2024) (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001128/2023-2024 | 718C/RCD-I | 01/03/2024 | 184 | SHYAMAL MAJI | 0.9 | 0.6 | 10
1754 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for Additional work including Adopting Trench less technology (e.g. Jack Pushing Method etc) at 04(Four) nos. location at (i)Churulia Main Road, (ii)Nazrul Academy Road Crossing (iii)Likapur Road Crossing (iv)Madhudanga OHR and allied MS work including open cut at pump house and existing OHR site including supply of Hume pipe in related to rising main of Churulia and Madantore under Augmentation of Roshna PWSS under RCFA Division ¿I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001179/2023-2024 | 1020/RCD-I | 16/03/2024 | 30 | T R ENTERPRISE | 40.55 | 39.86 | 100
1755 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000003/2023-2024 | 1638/RCD-I | 27/04/2023 | 0 | Resource Division | 30.48 | 0 | 0
1756 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000009/2022-2023 | 2349/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
1757 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries in Newly sunk RBTW No-6 & 7 for CWR at Roshna Pump House under Roshna Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000317/2024-2025 | 1811/AMD | 29/10/2024 | 30 | M/S SAJAHAN CHOWDHURY | 12.12 | 0 | 0
1758 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and Allied Works at Panuria under Augmentation of Panuria Itapara Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000433/2022-2023 | 488/AMD | 22/02/2023 | 365 | BENGAL CONSTRUCTION | 180 | 0 | 68
1759 | Asansol Mechanical | Asansol Mechanical Division | Providing And Installation of Electro-Mechanical Equipments and Allied Works at Gourandi under Augmentation of Roshna Piped Water Supply Scheme, Block-Baraboni, Dist.-Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000504/2022-2023 | 606/AMD | 03/03/2023 | 90 | M/S SWAPAN BANERJEE | 32.53 | 21.61 | 70
1760 | Asansol Mechanical | Asansol Mechanical Division | Lowering of Submersible Pumping Machineries for Newly Sunk RBTWs under Panuria Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000652/2023-2024 | 552/AMD | 14/03/2024 | 30 | BENGAL CONSTRUCTION | 6.28 | 6.28 | 100
1761 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Dhobaru W/S Scheme , Pump House No- 01 , Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00204/2022-2023 | BP-2022-23-335 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.47 | 0 | 0
1762 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distribution pipe line and providing FHTC at DHOBARU mouza of Dhobaru piped W/s Scheme under DWSD, PHE Dte (Part-A ,B and C) (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000166/2022-2023 | 774/DWSD | 17/05/2022 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 44.99 | 41.09 | 100
1763 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 48.41 | 100
1764 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- I) under Jamuria Block in the district of Paschim Bardhaman Under RCFA Division - I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000100/2024-2025 | 2120/RCD-I | 27/08/2024 | 60 | SIMA ENTERPRISE | 46.06 | 0 | 40
1765 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of Distribution Network for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part- A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000111/2024-2025 | 2133/RCD-I | 27/08/2024 | 146 | M/S B.K. CONSTRUCTION | 20.94 | 10.82 | 65
1766 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural-II Piped Water Supply Scheme including FHTC work (Segment-III) under Jamuria Block in the the District of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000112/2024-2025 | 2134/RCD-I | 27/08/2024 | 582 | DAWN CONSTRUCTION | 95.92 | 20.33 | 40
1767 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- II) under Jamuria Block in the district of Paschim Bardhaman under RCFA Division - I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000118/2024-2025 | 2117/RCD-I | 27/08/2024 | 804 | MS SAMANTA CONSTRUCTION | 48.54 | 0 | 100
1768 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR & Route Survey for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000250/2022-2023 | 2230/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.58 | 3.58 | 0
1769 | RCFA Division -I | Asansol Mechanical Division | Distribution network for Augmentation of Jamuria Rural-II Piped Water Scheme including FHTC work Block Jamuria, Dist Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000292/2022-2023 | 2449/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 236.71 | 59.28 | 100
1770 | RCFA Division -I | Asansol Mechanical Division | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000524/2022-2023 | 3137/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0
1771 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of High Lift Pump House at Riverside H/W site under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000573/2022-2023 | 3282/RCDI | 20/12/2022 | 90 | GLOBAL CONSTRUCTION | 31.24 | 27.01 | 90
1772 | RCFA Division -I | Asansol Mechanical Division | Formal work order for augmentation of Jamuria (Rural)(zone-I) piped water supply scheme including FHTC & allied work within Jamuria Block under RCFA Div-I, PHE Dte.(Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000599/2022-2023 | 16/RCD I | 05/01/2023 | 30 | DIP CONSTRUCTION | 0 | 0 | 0
1773 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Rising Main of Augmentation of Jamuria Rural (Zone-I & II) under RCFA Division-I PHE Dte (sl.no-14) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000773/2022-2023 | 805/RCD-I | 06/03/2023 | 60 | M/S MONDAL ENTERPRISE | 22.77 | 8.18 | 40
1774 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000005/2022-2023 | 2345/RCD-I | 28/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
1775 | RCFA Division -I | RCFA Division I | Acceptance cum formal order for the work of Construction of boundary wall at OHR site approach road ,drain blower room and plantation and other allied works of Jemua W/S Scheme under Augmentation of Gopalpur W/s Scheme of Durgapur-Faridpur Block under DWSD, PHE Dte | Assistant Engineer 2 |  | ORD/001235/2023-2024 | 587/DWSD | 11/04/2023 | 45 | GITA CONSTRUCTION | 61.45 | 58.7 | 100
1776 | Durgapur W/S Division | RCFA Division I |  | Assistant Engineer 2 |  | BILL/00242/2023-2024 | BP-2023-24-121 | 07/08/2023 | 0 | P C FORMS & STATIONERY | 0.19 | 0 | 0
1777 | Durgapur W/S Division | RCFA Division I | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2023 to 31.10.2023) (Vehicle No-WB37D6848) | Assistant Engineer 2 |  | ORD/000020/2023-2024 | 654/DWSD | 27/04/2023 | 183 | PRAMIT CHATTERJEE | 0.82 | 2.36 | 100
1778 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Replacement of existing pipe line at Nachan OHR to Protapur gram for Physical certification of HarGhar Jal in connection with JJM of Augmentation Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-03) | Assistant Engineer 2 |  | ORD/000026/2023-2024 | 758/DWSD | 19/05/2023 | 20 | GHOSH & ROY ENTERPRISE | 9.66 | 9.64 | 100
1779 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-A) | Assistant Engineer 2 |  | ORD/000045/2023-2024 | 768/DWSD | 22/05/2023 | 10 | SAIKAT RAY | 4.96 | 4.96 | 100
1780 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-B) | Assistant Engineer 2 |  | ORD/000047/2023-2024 | 771/DWSD. | 22/05/2023 | 10 | GHOSH & ROY ENTERPRISE | 4.83 | 4.83 | 100
1781 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Gopalpur distribution system & Its all command areas of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-07) | Assistant Engineer 2 |  | ORD/000051/2022-2023 | 586/DWSD | 21/04/2022 | 7 | QUICK PAL SUPPLIERS | 4.82 | 4.39 | 0
1782 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Distribution of abandoned existing structure at Gopalpur H/W site and others Pump House site under Augmentation of Gopalpur W/s Scheme of DWSD,PHE Dte (SL-08) | Assistant Engineer 2 |  | ORD/000052/2022-2023 | 587/DWSD | 21/04/2022 | 7 | CHATTERJEE CONSTRUCTION | 2.16 | 2.07 | 0
1783 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Dismantling of existing boundary wall and reconstruction of balance portion boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-09) | Assistant Engineer 2 |  | ORD/000104/2022-2023 | 750/DWSD | 10/05/2022 | 10 | D. S. ENTERPRISE | 29.41 | 29.22 | 0
1784 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Replacement of existing pipe line and extended the same of total command area of distribution network for physical certification of Har Ghat Jal in connection with JJM of Augmentation of Gopalpur piped W/S Scheme under DWSD ,PHE Dte. | Assistant Engineer 2 |  | ORD/000107/2023-2024 | 1135/DWSD | 20/07/2023 | 30 | MD AAMIR KHAN | 25.46 | 23.4 | 100
1785 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE/DI distribution pipe line and allied works including FHTC and connection providing to ICDS ,Health Centre, Govt Building ,School under command area of Gopalpur Mouza of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte . (SL-17) | Assistant Engineer 2 |  | ORD/000130/2022-2023 | 817/DWSD | 21/05/2022 | 184 | MACHINO TECHNO | 77.49 | 51.75 | 0
1786 | Durgapur W/S Division | RCFA Division I | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) under Retrofitting of Jemua piped W/s Scheme, Augmentation of Bistupur water supply scheme, Augmentation of Gopalpur, water supply scheme, Augmentation of Roopganj Water supply scheme of Durgapur-Faridpur Block (SM/16249) | Assistant Engineer 2 |  | ORD/000085/2023-2024 | 1074/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 18.4 | 18.19 | 100
1787 | Durgapur W/S Division | RCFA Division I | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2022 to 30.04.2023) (Vehicle No-WB37D6848) | Assistant Engineer 2 |  | ORD/000095/2022-2023 | 687/DWSD | 28/04/2022 | 365 | PRAMIT CHATTERJEE | 1.65 | 4.36 | 0
1788 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Construction of temporary approach road at Gopalpur H/W site of Gopalpur piped W/s Scheme under DWSD ,PHE Dte(SL-07) | Assistant Engineer 2 |  | ORD/000143/2022-2023 | 975/DWSD | 22/06/2022 | 15 | AMAR CONSTRUCTION | 4.11 | 3.97 | 0
1789 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme (Part-A, B) | Assistant Engineer 2 |  | ORD/000145/2023-2024 | 1275/DWSD | 07/08/2023 | 15 | JOY GURU ENTERPRISE | 8.95 | 8.94 | 100
1790 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Roopganj piped W/s Scheme (Part-A, B) | Assistant Engineer 2 |  | ORD/000146/2023-2024 | 1276/DWSD | 07/08/2023 | 15 | JOY GURU ENTERPRISE | 8.95 | 8.95 | 100
1791 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Land development at Gopalpur H/W site and back filling along the boundary wall of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-12) | Assistant Engineer 2 |  | ORD/000147/2022-2023 | 979/DWSD | 22/06/2022 | 15 | AMAR CONSTRUCTION | 4.63 | 4.39 | 0
1792 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Extension of existing Gopalpur sub district laboratory at Kanksa of Augmentation of Gopalpur piped W/s Scheme under DWD ,PHE Dte (SL-13) | Assistant Engineer 2 |  | ORD/000148/2022-2023 | 980/DWSD | 22/06/2022 | 15 | BASANTI TRADERS | 4.94 | 3.9 | 100
1793 | Durgapur W/S Division | RCFA Division I | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme. | Assistant Engineer 2 |  | ORD/000171/2023-2024 | 1302/DWSD | 07/08/2023 | 15 | V.C.CONSTRUCTION | 4.75 | 4.71 | 100
1794 | Durgapur W/S Division | RCFA Division I | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2022 to 28.02.2023). (Sl-01) | Assistant Engineer 2 |  | ORD/000218/2022-2023 | 1236/DWSD | 17/08/2022 | 184 | BIPLAB BANERJEE | 0.82 | 2.4 | 0
1795 | Durgapur W/S Division | RCFA Division I | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.08.2022 to 17.02.2023). (SL-02) | Assistant Engineer 2 |  | ORD/000219/2022-2023 | 1237/DWSD | 17/08/2022 | 184 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 0
1796 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) | Assistant Engineer 2 |  | ORD/000261/2022-2023 | 872/DWSD | 26/05/2022 | 15 | RANJIB GHATAK | 13.63 | 0 | 100
1797 | Durgapur W/S Division | RCFA Division I | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.11.2023 to 30.04.2024) (Vehicle No-WB37D6848) | Assistant Engineer 2 |  | ORD/000272/2023-2024 | 1702/DWSD | 31/10/2023 | 182 | PRAMIT CHATTERJEE | 0.82 | 1.57 | 60
1798 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Additional work for restoration and repairing of pipe line and construction of Sluice Valve chamber and cement concrete and other allied works for Augmentation of Gopalpur W/S Scheme under DWSD ,PHE Dte . | Assistant Engineer 2 |  | ORD/000274/2023-2024 | 1561/DWSD | 20/09/2023 | 685 | AMAR CONSTRUCTION | 5.15 | 0 | 100
1799 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Sinking 3(Three) Nos 300X200 mm dia Tube well 210 mtr deep by DR ring method using PVC pipe and fibber glass reinforced epoxy resin slotted at Gopalpur H/W site under Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer 2 |  | ORD/000286/2021-2022 | 1749/DWSD | 15/12/2021 | 30 | M/S. D. PALIT & CO. | 42.11 | 27.75 | 100
1800 | Durgapur W/S Division | RCFA Division I | Formal for the work of Construction of 500 M3 capacity ,20 Mtr staging height RCC Elevated Over Head Reservoir at Gopalpur under Augmentation of Gopalpur piped W/s Scheme under DWSD, PHE Dte.(SL-02) | Assistant Engineer 2 |  | ORD/000287/2021-2022 | 1745/DWSD | 15/12/2021 | 184 | AMAR CONSTRUCTION | 92 | 78.97 | 0
1801 | Durgapur W/S Division | RCFA Division I | Acceptance for the work fabrication and erection of MS structural bridge used to cross 600 mm dia rising main pipe line near Bankura more under surface based W/s Scheme for Panagarh Industrial Park under DWSD,PHE Dte (SL-03) | Assistant Engineer 2 |  | ORD/000288/2021-2022 | 1715/DWSD | 09/12/2021 | 40 | MACHINO TECHNO | 68.77 | 0 | 0
1802 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of dismantling of abandoned existing structure at Gopalpur H/W site of Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-02) | Assistant Engineer 2 |  | ORD/000289/2021-2022 | 1660/DWSD | 25/11/2021 | 20 | QUICK PAL SUPPLIERS | 3.94 | 3.87 | 0
1803 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Gopalpur mouza for Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-01) | Assistant Engineer 2 |  | ORD/000290/2021-2022 | 1661/DWSD | 25/11/2021 | 25 | M/S UNIQUE | 4 | 3.68 | 0
1804 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Repairing as well as extension of boundary wall with supply fitting fixing of ornamental Gate at Gopalpur H/W site of Gopalpur Mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer 2 |  | ORD/000301/2021-2022 | 1767/DWSD | 17/12/2021 | 30 | D. S. ENTERPRISE | 8.1 | 7.18 | 0
1805 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and allied works under command area of Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer 2 |  | ORD/000303/2021-2022 | 1758/DWSD | 16/12/2021 | 30 | RANJIB GHATAK | 15.53 | 0 | 0
1806 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Hire & labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling of RCC elevated 350 M3 OHR of 20 mtr staging height at Gopalpur H/W Site under DWSD ,PHE Dte | Assistant Engineer 2 |  | ORD/000304/2021-2022 | 1765/DWSD | 17/12/2021 | 30 | TARA CONSTRUCTION | 12.55 | 0 | 0
1807 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Repairing and renovation of PH with sanitary arrangement as well as boundary wall at PH site (T.No-II & III) of crackly nature of soil according to Deptt drawing no GWSS/EC/PHE Dte /DRG-3/7-8 ,Size-5.9X4.10 m out to out) at Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer 2 |  | ORD/000302/2021-2022 | 1737/DWSD | 13/12/2021 | 45 | CHANDAN HAZRA | 25.78 | 24.35 | 100
1808 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Gopalpur piped W/S Scheme DWSD, PHE Dte.(SL-02) | Assistant Engineer 2 |  | ORD/000336/2021-2022 | 1685/DWSD | 02/12/2021 | 30 | M/S R.DUTTA AND CO. | 8.48 | 8.48 | 0
1809 | Durgapur W/S Division | RCFA Division I | Formal order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer 2 |  | ORD/000341/2021-2022 | 68/DWSD | 19/01/2022 | 180 | MRITYUNJOY MUKHERJEE AND CO | 494.51 | 304.99 | 100
1810 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Supplying fitting fixing of PCC precast pillar and fencing with barbed wire errection of Govt sign board 03 nos place for protection of vest land at Molandighi of Bistupur W/s Scheme of 03 Nos at Gopalpur of Augmentation of Gopal pur piped W/s Scheme | Assistant Engineer 2 |  | ORD/000362/2021-2022 | 84/DWSD | 25/01/2022 | 15 | MD JAWED KHAN | 2.33 | 2.33 | 0
1811 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Electric wiring and other allied works for modernization of the existing Gopalpur lab for NABL accreditation of Sub-District Water test ing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer 2 |  | ORD/000368/2021-2022 | 100/DWSD | 31/01/2022 | 15 | BASANTI TRADERS | 1.65 | 1.57 | 0
1812 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer 2 |  | ORD/000370/2021-2022 | 65/DWSD | 19/01/2022 | 30 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 34.25 | 34.28 | 0
1813 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-2 tube well No-02 for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-02) | Assistant Engineer 2 |  | ORD/000401/2021-2022 | 241/DWSD | 25/02/2022 | 45 | MUKHERJEE ENTERPRISE | 4.89 | 1.01 | 100
1814 | Durgapur W/S Division | RCFA Division I | Formal order for the work Laying and aligning of distribution pipe line from Bonsol to towards Jhajra Majipara and allied works under Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer 2 |  | ORD/000440/2022-2023 | 300/DWSD | 20/02/2023 | 15 | BABA LOKENATH ENTERPRISE | 6.27 | 6.27 | 0
1815 | Durgapur W/S Division | RCFA Division I | Acceptance order for the work of Balance work for construction of boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer 2 |  | ORD/000448/2022-2023 | 111/DWSD | 24/01/2023 | 15 | D. S. ENTERPRISE | 4.36 | 4.34 | 0
1816 | Durgapur W/S Division | RCFA Division I | Continuation for the work of soil investigation for demining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated at Gopalpur Reservoir site of Augmentation of Gopalpur W/s Scheme under DWSD ,PHEDte | Assistant Engineer 2 |  | ORD/000468/2021-2022 | 353/DWSD | 21/03/2022 | 25 | MABCO CONSULTANT | 1.2 | 1.2 | 0
1817 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Water supply arrangement at Kajladighi ICDS Centre of Bibihar GP having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Aug: of Gopalpur piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer 2 |  | ORD/000471/2022-2023 | 294/DWSD | 17/02/2023 | 15 | RANJIB GHATAK | 6.95 | 6.95 | 100
1818 | Durgapur W/S Division | RCFA Division I | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) | Assistant Engineer 2 |  | ORD/000438/2022-2023 | 1801/DWSD | 30/12/2022 | 182 | PRAMIT CHATTERJEE | 0.82 | 1.6 | 0
1819 | Durgapur W/S Division | RCFA Division I | Continuation order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer 2 |  | ORD/000689/2022-2023 | 700/DWSD | 29/04/2022 | 90 | MRITYUNJOY MUKHERJEE AND CO | 66.45 | 65.8 | 100
1820 | Durgapur W/S Division | RCFA Division I | Continuation order for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer 2 |  | ORD/000691/2022-2023 | 702/DWSD | 29/04/2022 | 25 | MACHINO TECHNO | 67.7 | 67.42 | 100
1821 | Durgapur W/S Division | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000002/2021-2022 | 1751/DWSD | 16/12/2021 | 0 | Resource Division | 1.27 | 0 | 0
1822 | Durgapur W/S Division | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000005/2021-2022 | 1815/DWSD | 30/12/2021 | 0 | Resource Division | 19.8 | 0 | 0
1823 | Durgapur W/S Division | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000007/2021-2022 | 65/DWSD | 19/01/2022 | 0 | Resource Division | 34.32 | 0 | 0
1824 | Durgapur W/S Division | RCFA Division I | Quotation for Gopalpur Pump house no -02 | Assistant Engineer 2 |  | VCH/000221/2022-2023 | BP-2022-23-93 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0
1825 | Durgapur W/S Division | RCFA Division I | Quotation for Gopalpur Pump house no -03 | Assistant Engineer 2 |  | VCH/000222/2022-2023 | BP-2022-23-94 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.81 | 0 | 0
1826 | Durgapur W/S Division | RCFA Division I | Quotation for Gopalpur Pamp House No 1 | Assistant Engineer 2 |  | VCH/000762/2021-2022 | BP-2021-22-208 | 15/03/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0
1827 | Central Mechanical | RCFA Division I | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Augmentation of Gopalpur Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer 2 |  | ORD/000016/2022-2023 | 911/CMD | 31/05/2022 | 30 | INDIA ENTERPRISE | 9.16 | 8.95 | 0
1828 | Central Mechanical | RCFA Division I | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Augmentation of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer 2 |  | ORD/000158/2022-2023 | 1243/CMD | 12/07/2022 | 30 | GOENKA ENTERPRISE | 10.21 | 10.09 | 0
1829 | Central Mechanical | RCFA Division I | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 1 of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000725/2021-2022 | 477/CMD | 28/03/2022 | 30 | RNS TRADING | 9.64 | 9.48 | 0
1830 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Shyambazar W/S Scheme, P.H. No - 02, Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00179/2022-2023 | BP-2022-23-331 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.36 | 0 | 0
1831 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Shyambazar W/S Scheme , Pump House No- 01 , Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00208/2022-2023 | BP-2022-23-340 | 17/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0
1832 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Shyambazar piped W/s Scheme under DWSD ,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000222/2022-2023 | 1233/DWSD | 17/08/2022 | 15 | M/S. D. PALIT & CO. | 14.76 | 13.63 | 0
1833 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying distribution system ,rising main construction of 150 M3 with 20 mtr staging height including soil investigation construction of Pump house (5.4X3.6 m) with sanitary and Water supply arrangement and construction of pump house (3.6X3.00 mtr) for Shyambazar W/s Scheme under DWSD ,PHE Dte (New Scheme) | Assistant Engineer-II | Junior Engineer-3 | ORD/000267/2022-2023 | 1648/DWSD | 02/12/2022 | 2190 | DUTTA ENTERPRISE | 213.72 | 194.67 | 100
1834 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Shyambazar ,Telipara piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000564/2022-2023 | 527/DWSD | 29/03/2023 | 15 | MEASURE LAND | 5 | 5 | 0
1835 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000004/2022-2023 | 1231/DWSD | 17/08/2022 | 0 | Resource Division | 18.93 | 0 | 0
1836 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000007/2022-2023 | 255/C/DWSD | 15/02/2023 | 0 | Resource Division | 5.32 | 0 | 0
1837 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000005/2023-2024 | 1579/CMD | 04/04/2023 | 30 | MS DAS ELECTRIC CO | 9.3 | 8.87 | 100
1838 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Shambazar Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000006/2023-2024 | 1580/CMD | 04/04/2023 | 30 | A.S. ENTERPRISE | 9.3 | 8.81 | 100
1839 | Asansol Mechanical | Asansol Mechanical Division | Lowering of column pipe including withdrawing, lowring and other allied works at Shyambazar, TW No.-01, under Block - Kanksa, Dist - Paschim Bardhaman under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000390/2025-2026 | 1959/AE-II/AMD | 10/12/2025 | 10 | MITRA ENTERPRISE | 0.34 | 0 | 100
1840 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work for pushing 300 mm dia MS Rising main through 600 mm Dia RCC pipe road crossing trenchless method under NH-19 at front topline more under OCP based Kajora site Augmentation of sub surface water supply scheme ondal phase-II/A under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000179/2024-2025 | 2427/RCD-I | 26/09/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 12.98 | 0 | 100
1841 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-2) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000228/2023-2024 | 2213/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 11.57 | 6.78 | 100
1842 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-3) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000230/2023-2024 | 2214/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 56.6 | 24.99 | 50
1843 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Augmentation of Ondal (Phase ¿ II/A) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part - 3) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000245/2022-2023 | 2211/RCD-I | 14/09/2022 | 45 | UNITED CONSTRUCTION | 88.03 | 74.93 | 90
1844 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order of distribution network for augmentation of Ondal (Phase II/A) piped water supply scheme including FHTC & allied work within Ondal Block under RCFA Div-I, PHE Dte. (Part-I) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000296/2022-2023 | 2482/RCD I | 17/10/2022 | 45 | SIMA ENTERPRISE | 89.81 | 71.28 | 90
1845 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order of distribution network for augmentation Of Ondal (Phase-II/A) piped Water Supply scheme including FHTC & allied works Ondal Block under RCFA Div-I PHE Dte.(Part-2) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000299/2022-2023 | 2483/RCD I | 17/10/2022 | 45 | SOMNATH SAMANTA | 89.8 | 65.01 | 90
1846 | RCFA Division -I | Asansol Mechanical Division | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000537/2021-2022 | 502/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.54 | 4.54 | 0
1847 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Ramprasadpur H/W Site under Augmentation of Sub Surface Water Supply Scheme of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000575/2022-2023 | 3284/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.05 | 22.01 | 70
1848 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of capacity 550 cum at Dignala for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000873/2022-2023 | 1124/ RCD I | 24/03/2023 | 90 | M/S SUBHRADEEP | 11 | 9.25 | 100
1849 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-1) Block- Andal Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000885/2022-2023 | 1129/ RCD I | 24/03/2023 | 30 | SIMA ENTERPRISE | 13.76 | 9.36 | 80
1850 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000018/2022-2023 | 3131 | 09/12/2022 | 0 | Resource Division | 106.94 | 0 | 0
1851 | Asansol Mechanical | Asansol Mechanical Division | Quotation Money for Load Enhancement at Andal | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | BILL/00023/2023-2024 | BP-2023-24-5 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.28 | 0 | 0
1852 | Asansol Mechanical | Asansol Mechanical Division | Deposition of the Earnest Money for the proposed enhancement of the load at Ramprasadpur Andal BDN | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | BILL/00169/2022-2023 | BP-2022-23-27 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1853 | Asansol Mechanical | Asansol Mechanical Division | Quotation for enhancement of load at 11 KV from 200 KVA to 305 KVA to your premises at Ramprasadpur,Andal, Paschim Burdwan. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | BILL/00223/2022-2023 |  | 23/02/2023 | 0 | W.B.S.E.D.C.L | 11.28 | 0 | 0
1854 | Asansol Mechanical | Asansol Mechanical Division | Deposit for Earnest Money Application | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | BILL/00307/2023-2024 | BP-2023-24-22 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0
1855 | Asansol Mechanical | Asansol Mechanical Division | Quotation for enhancement of load at Basudebpur under Augmentation of Andal. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | BILL/00453/2023-2024 | BP-2023-24-33 | 14/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0
1856 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Andal (Phase-II/A) Water Supply Scheme, Block : Andal, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000435/2022-2023 | 490/AMD | 22/02/2023 | 1244 | EASTERN INDIA SALES AND SERVICE | 151.5 | 105.83 | 100
1857 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14B) | Assistant Engineer 2 |  | ORD/000071/2023-2024 | 1761/RCD I | 16/05/2023 | 961 | MD AAMIR KHAN | 409.77 | 65.24 | 15
1858 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for distribution network including supply of Hume pipe, G.I. pipe and adopting trench less technologies at 02 (Two) locations in connection to Zone-I Part-A Dendua OHR for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000294/2023-2024 | 2365/RCD-I | 04/08/2023 | 30 | ASHA CONSTRUCTION | 15.08 | 14.43 | 100
1859 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance and other allied works for construction of store room at work site for(Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II (Zone-14B) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000542/2024-2025 | 145/RCD-I | 08/01/2025 | 90 | RANJIB GHATAK | 20.29 | 0 | 70
1860 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Shifting of existing rising main for construction of new Pump House at Dendua OHR Campus under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000599/2023-2024 | 3281/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 12.45 | 12.26 | 100
1861 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Kallya and surrounding villages within Kallya Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000658/2023-2024 | 3452/RCD-I | 24/11/2023 | 15 | JAI MAHARAJ ENTERPRISE | 3.71 | 3.69 | 100
1862 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines at Railway Gate (Node No 116 to 128) under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/000661/2023-2024 | 3431/RCD-1 | 24/11/2023 | 90 | SINGHA ROY & CO. | 44.79 | 37.7 | 100
1863 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Baidyanathpur under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000681/2023-2024 | 3473/RCD-I | 28/11/2023 | 551 | MAA ENTERPRISE | 23.33 | 20.84 | 25
1864 | RCFA Division -I | RCFA Division I | Acceptance cum work order of additional works of Dismantling & concrete works, Jack Pushing Supplying, Aligning and laying and other allied works at distribution system Networks for Shyamlya in Nimsa mouza under Shyamlya Gram Panchayat under Jamuria Block of Augmentation of PWSS RCFA Part-II (Zone-14B) under R.C.F.A Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000713/2023-2024 | 2883/RCD-I | 06/10/2023 | 543 | A CONSTRUCTION CO | 37.4 | 14.4 | 100
1865 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 03 (Three) nos. 200 mm dia river bed tube well including laying of 250 mm dia HDPE pipe line in the river of Ajoy for Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000717/2023-2024 | 3546/RCD-1 | 07/12/2023 | 30 | B.T.M. CONCERN | 21.19 | 1.96 | 10
1866 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000001/2025-2026 | 810/RCD-I | 16/04/2025 | 0 | Resource Division | 61.6 | 0 | 0
1867 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000004/2024-2025 | 381/RCD-I | 28/02/2025 | 0 | Resource Division | 30.8 | 0 | 0
1868 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000032/2023-2024 | 2942/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1869 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Garadaha W/S Scheme, P.H. No - 01, Panagarh CCC | Assistant Engineer-II | Junior Engineer-3 | BILL/00180/2022-2023 | BP-2022-23-328 | 15/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0
1870 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of pump house/Chlorine room,sinking tube well of 150 X 80 X 120 mtr depth and supplying laying of HDPE distributing pipe line and providing FHTC at Garadaha Mouza of Garadaha piped W/s Scheme under DWSD, PHE Dte (Part-A ,B & C) (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000237/2022-2023 | 775/DWSD | 17/05/2022 | 45 | SHWET BARANI | 38.51 | 34 | 0
1871 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 250 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Samlya for Samlya Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Ref Drawing No. PC-I/OHR/10/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000459/2022-2023 | 2934/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 80.02 | 24.01 | 100
1872 | RCFA Division -I | RCFA Division I | Formal Work Order for Supplying, laying and aligning of distribution system including FHTC for Shyamla W/S Scheme in Syamla and Bhuri Mouza, Block ¿ Jamuria, Dist ¿ Bardhaman under Shyamla W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000479/2022-2023 | 2029/RCD-I | 30/08/2022 | 1030 | SWATI CORPORATION | 337.77 | 234.46 | 85
1873 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, laying and aligning of distribution system for Part of Kendra Khottamdihi Mouza (JL No. 001), Bajari (Jl No. 023) & Sonpur (Jl No. 022) for Kendra Khottamdihi W/S Scheme (Zone-I) , Block:-Pandabeswar under RCFA Division-I PHE Dte. (Part-A) under JJM (RCFA Part-II) | Assistant Engineer 2 | Junior Engineer | ORD/000824/2022-2023 | 800/RCD-I | 06/03/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 95.19 | 83.15 | 100
1874 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000005/2023-2024 | 1854/RCD-I | 31/05/2023 | 0 | Resource Division | 7.25 | 0 | 0
1875 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000009/2025-2026 | 2542/RCD-I | 01/09/2025 | 0 | Resource Division | 16.69 | 0 | 0
1876 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & Aallied work under RCFA Division-I PHE Dte. (Zone-19) (Part-B). | Assistant Engineer 2 |  | ORD/000035/2023-2024 | 1611/RCD I | 25/04/2023 | 180 | UMA ENTERPRISE | 195.63 | 64.28 | 65
1877 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied Work under RCFA Division-I PHE Dte. (Zone-19)(Part-A) | Assistant Engineer 2 |  | ORD/000040/2023-2024 | 1605/RCD I | 25/04/2023 | 180 | A. CONSTRUCTION CO. | 233.19 | 92.45 | 70
1878 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Distribution Network for Augmentation of RCFA Part-II (Zone-19) (Part-A) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000043/2024-2025 | 1644/RCD-I | 04/07/2024 | 20 | A CONSTRUCTION CO | 9.41 | 9.41 | 100
1879 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-19) with Construction of 600 cumcapacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District -Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000094/2023-2024 | 1830/RCD-I | 29/05/2023 | 365 | SWATI CORPORATION | 181.97 | 169.89 | 40
1880 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of Construction of Rigid Pavement for the approach road from the main road towards Head Work Site and Laying of Pipe line for Pandebeswar Block of Augmentation PWSS of RCFA Part-II (Zone-19) under RCFA Division-I P.H.E Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000096/2024-2025 | 2127/RCD-I | 27/08/2024 | 30 | SWATI CORPORATION | 10.61 | 0 | 100
1881 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-19) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000555/2022-2023 | 3349/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
1882 | RCFA Division -I | RCFA Division I | Formal work order of laying of 200 mm dia HDPE pipe line from Semalya to kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000601/2022-2023 | 14/RCDI | 05/01/2023 | 452 | UMA ENTERPRISE | 157.45 | 156.69 | 100
1883 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) of 03 ( Three) Nos. location at Bankola Rail gate, Bankola Siding ECL & Bankola Water Supply Gate under Augmentation of RCFA Part-II Zone 19 PWSS under RCFA,Division-I,P.H.E.Dte. | Assistant Engineer 2 |  | ORD/001113/2023-2024 | 919/RCD-I | 15/03/2024 | 30 | A CONSTRUCTION CO | 42.4 | 42.34 | 100
1884 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Interconnection at Baliapur OHR Site (02 nos. OHR), Barabani OHR and Barabani Railway crossing of RCFA Part-II Zone-19 PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/001119/2023-2024 | 925/RCD-I | 15/03/2024 | 30 | M/S MONDAL ENTERPRISE | 22.75 | 22.33 | 100
1885 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000038/2023-2024 | 2957/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1886 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000029/2023-2024 | 1616/RCD I | 25/04/2023 | 180 | SIMA ENTERPRISE | 115.57 | 81.84 | 75
1887 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Construction of Pump House at River side H/W for Augmentation Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000110/2023-2024 | 1867/RCD-1 | 01/06/2023 | 180 | M/S KALYANI ENTERPRISE | 19.55 | 0 | 0
1888 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000160/2024-2025 | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0 | 33
1889 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Bagdiha for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/12/2012 (Sheet No. 1 & 2) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000184/2023-2024 | 2042/RCD-I | 04/07/2023 | 366 | DHANANJOY DUTTA | 108 | 59.72 | 50
1890 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 03 (Three) nos. river bed tube wells including collecting main, sluice valve chamber, reinforcement & other allied works at Bagdiha H/W site at Ajoy river under Augmentation of Bagdiha Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000205/2023-2024 | 2240/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 24.44 | 0 | 0
1891 | RCFA Division -I | Asansol Mechanical Division | Acceptance Cum work order Laying of different dia distribution pipe line and concrete road cutting and mending works at Bagdi para, Dangal Para, Telipara etc adjacent area Dakshin Khanda area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000212/2023-2024 | 2221/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 10.09 | 8.45 | 100
1892 | RCFA Division -I | Asansol Mechanical Division | Preparation of DPR & Route Survey for augumentation of Bagdiha piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000279/2022-2023 | 2246/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 0
1893 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc) and allied works at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000284/2023-2024 | 2333/RCD-I | 01/08/2023 | 15 | SIMA ENTERPRISE | 46.6 | 36.04 | 77
1894 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Sinking of 3 (Three) nos 200 mm dia river bed tube wells including collecting main in the river Ajoy at Bagdiha under Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000350/2023-2024 | 2484/RCD-I | 23/08/2023 | 30 | M/S KALYANI ENTERPRISE | 24.12 | 0 | 0
1895 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Bye pass connection including supplying, aligning, laying of HDPE pipe and other allied works at Bagdiha Head Works Site to Bagdiha Siddapur High School under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000767/2022-2023 | 393/RCDI | 30/01/2023 | 30 | BABA LOKNATH ENTERPRISE | 30.27 | 17.57 | 100
1896 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000839/2022-2023 | 1069/RCD-I | 23/03/2023 | 90 | M/S S.K. ENTERPRISE | 61.35 | 21.2 | 35
1897 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Rising Main for Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000840/2022-2023 | 1067/RCD I | 23/03/2023 | 1105 | D.S.C. CONCERN | 12.64 | 0 | 100
1898 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000841/2022-2023 | 1071/RCD-I | 23/03/2023 | 90 | TARA MA ENTERPRISE | 54.95 | 15.27 | 0
1899 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-E)( Sl No. 10) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000865/2022-2023 | 1072/RCD-I | 23/03/2023 | 90 | R B ENTERPRISE | 68.85 | 31.93 | 50
1900 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of boundary wall Gate at OHR Site (Length-60 mtrs) at Bagdiha of Jamuria Block for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in District Paschim Bardhaman (Sl No. 20) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000913/2022-2023 | 1164/ RCD I | 24/03/2023 | 60 | M/S KALYANI ENTERPRISE | 5.31 | 0 | 0
1901 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Plastering, painting works of Boundary Wall, Pump House, Chlorine Room CWR and other allied works and other allied works under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000950/2022-2023 | 1280/RCD-I | 27/03/2023 | 15 | M/S KALYANI ENTERPRISE | 5.04 | 5.04 | 0
1902 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | RTOR000009/2023-2024 | 2029/RCD-I | 30/06/2023 | 0 | Resource Division | 127.95 | 0 | 0
1903 | Asansol Mechanical | Asansol Mechanical Division | New Connection Charge at Bagdiha Water Supply Scheme | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | BILL/00171/2022-2023 | BP-2022-23-29 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.15 | 0 | 0
1904 | Asansol Mechanical | Asansol Mechanical Division | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Bagdiha Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000437/2022-2023 | 492/AMD | 22/02/2023 | 365 | PREMNATH MITRA | 126.31 | 31.11 | 25
1905 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 39.27 | 100
1906 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency provision of AC Photovoltaic Submersible Solar within the bore well / tube well along with 2400 watt peak capacity Solar Photovoltaic array on MS structure with the sinking of 150 mm dia tube well 150 meter deep by DR Rig method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Jhinukguri Adibasipara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000253/2025-2026 | 1475/RCD-I | 15/05/2025 | 30 | MAK CONSTRUCTION CO | 16.37 | 0 | 100
1907 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Creating separate zone with pipe line & additional FHTC including Water sources at Sibpur Ruidaspara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000366/2024-2025 | 3066/RCD-I | 10/12/2024 | 90 | HIRANMAY GHOSH | 26.47 | 17.27 | 100
1908 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Boundary wall and allied works at Krishnapur tube well No-02 under Augmentation of Krishnapur Piped water Supply scheme under Kanksa Block under RCFA Division-I,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/001188/2023-2024 | 1007/RCD-I | 16/03/2024 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.12 | 5.54 | 80
1909 | Asansol Mechanical | Asansol Mechanical Division | Payment for Quotation as per WBSEDCL Procedure-A (2010) on turn - key/full deposit basis for the site of Krishnapur Pump Houde No-3, Block- Kanksa, under AMD, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | BILL/00415/2025-2026 |  | 09/07/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.53 | 0 | 0
1910 | Asansol Mechanical | Asansol Mechanical Division | Load Extension at Pump house No-1 and 2 under Sub Surface Water Based Water Supply Scheme, Block-kanksa, Paschim bardhaman. | Assistant Engineer-II | Junior Engineer-3 | BILL/00703/2025-2026 |  | 25/09/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.35 | 0 | 0
1911 | Asansol Mechanical | Asansol Mechanical Division | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube Well No-03 At augmentation of Krishnapur Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000411/2024-2025 | 1982/AMD | 27/11/2024 | 30 | M/S JIT ENTERPRISE | 11.63 | 0 | 0
1912 | Asansol Mechanical | Asansol Mechanical Division | Supply Delivery and Installation Of Voltage Stabilizer, PDB Cum MCC Panel and other Allied Electrical Works For Tube Well No- I & II At Augmentation Of Krishnapur Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000454/2024-2025 | 2120/AMD | 16/12/2024 | 30 | SINHA ELECTRICALS | 14.52 | 0 | 100
1913 | Durgapur W/S Division |  | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) |  |  | ORD/000006/2021-2022 | 719/DWSD | 29/04/2021 | 25 | BABA LOKENATH ENTERPRISE | 4.99 | 0 | 0
1914 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line of different dia UPVC pipe at Kalikapur mouza to combat draught like situation in Durgapur-Faridpur block to providing FHTC at Kalikapur mouza(JL-30) under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte (SL-08) |  |  | ORD/000009/2021-2022 | 722/DWSD | 29/04/2021 | 30 | M/S MONDAL ENTERPRISE | 4.99 | 0 | 0
1915 | Durgapur W/S Division |  | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) |  |  | ORD/000023/2021-2022 | 796/DWSD | 12/05/2021 | 15 | BABA LOKENATH ENTERPRISE | 12.9 | 0 | 0
1916 | Durgapur W/S Division |  | Formal order for the work of Repairing ,extension as well as replace of damage AC pipe line and allied works at Colony Bouri para ,Upper Bagdi para ,Adibasi para under Jamgora(Mouza-23) under command area of Jamgora-Jagannathpur W/s Scheme for combat upcoming drought like situation under DWSD, PHE Dte (SL-07) |  |  | ORD/000025/2021-2022 | 829/DWSD | 24/05/2021 | 10 | RANJIB GHATAK | 7.26 | 0 | 0
1917 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000091/2022-2023 | 723/DWSD | 06/05/2022 | 15 | BABA LOKENATH ENTERPRISE | 30.27 | 24.89 | 0
1918 | Durgapur W/S Division |  | Formal order for the work of Emegency repairng and restoration of distribution system from command area of Gourbazar OHR {(Srikrishnapur, Kailashpur (Part)} under Gourbazar-Ichhapur piped W/s Scheme under DWSD, PHE Dte (SL-11) |  |  | ORD/000115/2021-2022 | 1780/DWSD | 20/12/2021 | 10 | JOY GURU ENTERPRISE | 5.6 | 4.97 | 0
1919 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing and restoration of distributing system from Nachan OHR to Jamgora ,Nachan more to jamgora samshan distribution main road crossing at Nachan with Hume pipe ,Bansia pratabpur and extension of pipe at different places of Pratabpur gram of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000120/2022-2023 | 781/DWSD | 18/05/2022 | 15 | M/S MONDAL ENTERPRISE | 4.56 | 0 | 0
1920 | Durgapur W/S Division |  | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Patsaora mouza under Gourbazar-Ichhapur piped W/S Scheme for FHT C work under DWSD, PHE Dte.(SL-03) |  |  | ORD/000172/2022-2023 | 1146/DWSD | 28/07/2022 | 20 | SHWET BARANI | 5.69 | 0 | 0
1921 | Durgapur W/S Division |  | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000277/2021-2022 | 1643/DWSD | 23/11/2021 | 10 | PRAVAT SARKAR | 4.96 | 3.64 | 0
1922 | Durgapur W/S Division |  | Formal order for the work of Supplying and laying of 110 mm and 90 mm dia UPVC pipe at Bansgora (Main road to Akhrapara) for providing FHTC of Bansgora Mouza JL-38 of Jamgora-Jagannathpur W/s Scheme under DWSD PHE Dte |  |  | ORD/000298/2021-2022 | 1775/DWSD | 20/12/2021 | 25 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 7.57 | 7.63 | 0
1923 | Durgapur W/S Division |  | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). |  |  | ORD/000305/2021-2022 | 1735/DWSD | 13/12/2021 | 10 | PRAVAT SARKAR | 4.97 | 4.97 | 0
1924 | Durgapur W/S Division |  | Continuation order for the work of the work of Providing functional house hold tap connection (FHTC ) in connection with JJM for Huchuk Danga Jamgora-Jagannathpur piped W/S Scheme Mouza-Dannaya /Jamgora(JL-23) block-Durgapur-Faridpur ,Paschim Bardhaman under DWSD,PHE Dte |  |  | ORD/000337/2021-2022 | 25/DWSD | 06/01/2022 | 15 | RANJIB GHATAK | 3.49 | 3.51 | 0
1925 | Durgapur W/S Division |  | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) |  |  | ORD/000347/2021-2022 | 140/DWSD | 03/02/2022 | 7 | SHWET BARANI | 13.62 | 13.6 | 0
1926 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of collection main necessary repairing works in river Ajoy at Bhaburia H/W site under Jamgora -Jagannathpur piped W/s Scheme and Gourbazar-Ichhapur piped W/s Scheme.(Part-A) |  |  | ORD/000360/2021-2022 | 79/DWSD | 24/01/2022 | 15 | RANAJOY ENTERPRISE | 3.85 | 0 | 0
1927 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of distribution pipe line with necessary allied works for FHTC purpose at Maheshpur village Muchipara,Chasa para Moheshpur Mouza(JL-12),Durgapur-Faridpur block under DWSD PHE Dte |  |  | ORD/000364/2021-2022 | 88/DWSD | 27/01/2022 | 15 | M/S BADAL GHOSH | 4.87 | 4.92 | 0
1928 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of collecting main necessary repairing works in river Ajoy at Bhaburia H/w Site under Jamgora-Jagannathpur and Gourbazar-Ichhapur W/s Scheme for combat flood damaged under DWSD, PHE Dte |  |  | ORD/000366/2021-2022 | 97/DWSD | 28/01/2022 | 15 | RANAJOY ENTERPRISE | 3.29 | 0 | 50
1929 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Surging of 5 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-B) |  |  | ORD/000369/2021-2022 | 101/DWSD | 31/01/2022 | 20 | RANAJOY ENTERPRISE | 1.8 | 0 | 50
1930 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing restoration and chokage cleaning of distribution system of Hetedoba OHR from Hetedoba OHR to Sarpi more of Gourbazar-Ichhapur piped W.S Scheme under DWSD,PHE Dte |  |  | ORD/000374/2021-2022 | 112/DWSD | 01/02/2022 | 20 | PAYAL CONSTRUCTION | 3.24 | 0 | 0
1931 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Surging of 12 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-A) |  |  | ORD/000375/2021-2022 | 113/DWSD | 01/02/2022 | 20 | RANAJOY ENTERPRISE | 4.31 | 0 | 0
1932 | Durgapur W/S Division |  | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) |  |  | ORD/000390/2021-2022 | 10/DWSD | 04/01/2022 | 15 | PRAVAT SARKAR | 4.84 | 4.84 | 0
1933 | Durgapur W/S Division |  | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte |  |  | ORD/000412/2021-2022 | 244/DWSD | 22/02/2022 | 25 | M/S BADAL GHOSH | 2.09 | 1.99 | 0
1934 | Durgapur W/S Division |  | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000424/2021-2022 | 245/DWSD | 28/02/2022 | 15 | PRAVAT SARKAR | 4.97 | 0 | 50
1935 | Durgapur W/S Division |  | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000425/2021-2022 | 239/DWSD | 25/02/2022 | 15 | PRAVAT SARKAR | 4.92 | 4.39 | 0
1936 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Making interconnection of Over flow line and laying of additonal distribution pipe line with necessary allied works for FHTC purpose at Jagnnathpur gram under Jamgora-Jagannathpur W/S Scheme under DWSD PHE Dte (SL-06) |  |  | ORD/000442/2021-2022 | 421/DWSD | 30/03/2022 | 10 | M/S BADAL GHOSH | 3.69 | 3.68 | 0
1937 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of distribution pipe line for (FHTC) in connection with JJM and additional work of Solar Tube well site and necessary allied work at Huchukdanga village ,Paschim Bardhaman under DWSD, PHE Dte (SL-10) |  |  | ORD/000446/2021-2022 | 425/DWSD | 30/03/2022 | 10 | RANJIB GHATAK | 3.81 | 3.8 | 0
1938 | RCFA Division -I | RCFA Division I | Arrangement of brakfast and lunch box, etc. for DWSM meeting held on 22.06.2024 at ADDA conference hall | Assistant Engineer 2 |  | BILL/00256/2024-2025 | 121/24-25 | 03/07/2024 | 0 | MUKHERJEE TRADERS | 0.28 | 0 | 0
1939 | RCFA Division -I | RCFA Division I | Fuel bill of Ranajit auto against vehicle no WB 37D 0482 for the month of May | Assistant Engineer 2 |  | BILL/00265/2023-2024 | 116/1/23-24 | 03/07/2023 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1940 | RCFA Division -I | RCFA Division I |  | Assistant Engineer 2 |  | BILL/00327/2023-2024 | 149/1/23-24 | 21/07/2023 | 0 | RANAJIT AUTO | 0.17 | 0 | 0
1941 | RCFA Division -I | RCFA Division I | April 2023 | Assistant Engineer 2 |  | BILL/00559/2023-2024 | 77/23-24 | 06/06/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
1942 | RCFA Division -I | RCFA Division I | fuel bill april 2023 shyamal maji | Assistant Engineer 2 |  | BILL/00560/2023-2024 | 77/1/23-24 | 06/06/2023 | 0 | RANAJIT AUTO | 0.2 | 0 | 0
1943 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | BILL/00619/2023-2024 | 204/23-24 | 18/08/2023 | 0 | MACHINO TECHNO | 19.87 | 0 | 0
1944 | RCFA Division -I | RCFA Division I | Hire charge and fuel bill for the month of July 2023 to September 2023 | Assistant Engineer 2 |  | BILL/00754/2023-2024 | 339/23-24 | 17/10/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
1945 | RCFA Division -I | RCFA Division I | Fuel bill for WB37D0482 for the month of Sept 2023 | Assistant Engineer 2 |  | BILL/00755/2023-2024 | 339/1/23-24 | 17/10/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1946 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill for the month of July 2023 to Sept 2023 | Assistant Engineer 2 |  | BILL/00756/2023-2024 | 338/23-24 | 17/10/2023 | 0 | NIRMALA TRADERS | 1.2 | 0 | 0
1947 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill for Executive Engineer RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00823/2023-2024 | 291/23-24 | 10/10/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
1948 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repairing laying PVC pipe line and allied work at Asansol District Hospital under RCFA Division-I PHE Dte. (Sl. No. 34) | Assistant Engineer 2 |  | ORD/000060/2023-2024 | 1751/RCD I | 12/05/2023 | 15 | UNITED CONSTRUCTION | 3.23 | 3.23 | 0
1949 | RCFA Division -I | RCFA Division I | Construction of guard wall on emergency basis near Kalyaneswari I.B. gate under Retrofitting Bahula mouza RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 |  | ORD/000064/2022-2023 | 1111/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.7 | 4.47 | 100
1950 | RCFA Division -I | RCFA Division I | Emergency basis construction of culvert near Kalyaneswari I.B. gate under Retrofitting Bahula mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 17) | Assistant Engineer 2 |  | ORD/000069/2022-2023 | 1116/RCDI | 13/05/2022 | 45 | R B ENTERPRISE | 4.93 | 4.92 | 100
1951 | RCFA Division -I | RCFA Division I | Hiring of Maxi Cab (Non Air-conditioned)(Bharat stage-III/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal (w.e.f 16.08.2022 to 15.08.2023) | Assistant Engineer 2 |  | ORD/000204/2022-2023 | 1907/RCDI | 12/08/2022 | 12 | PRAMIT CHATTERJEE | 1.8 | 0.79 | 0
1952 | RCFA Division -I | RCFA Division I | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000309/2023-2024 | 2040/RCD-I | 30/06/2023 | 7 | MUKHERJEE TRADERS | 0.86 | 0.86 | 100
1953 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 |  | ORD/000316/2021-2022 | 2143/RCD-I | 29/11/2021 | 120 | GITA CONSTRUCTION | 81.14 | 61.82 | 0
1954 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-B) | Assistant Engineer 2 |  | ORD/000317/2021-2022 | 2144/RCD-I | 29/11/2021 | 120 | MD AAMIR KHAN | 81 | 59.89 | 0
1955 | RCFA Division -I | RCFA Division I | Acceptance cum work order Cleaning compound premises of Ballavpur Hospital & Unionpara Head Works Site under RCFA Part-II W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 |  | ORD/000330/2023-2024 | 2452/RCD-I | 18/08/2023 | 15 | SWATI CORPORATION | 0.97 | 0.96 | 100
1956 | RCFA Division -I | RCFA Division I | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at Health World Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000440/2023-2024 | Camp-02-Health-World-Hosp | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.77 | 7.65 | 100
1957 | RCFA Division -I | RCFA Division I | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at ESI Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000441/2023-2024 | Camp-2-ESI-Hospital-AE-II | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.84 | 7.68 | 100
1958 | RCFA Division -I | RCFA Division I | Cleaning compound premises, painting works and preparing approched road with sand and stone dust and other allied works at Kalyaneswari Inspection bunglow under Bahual Retrofitting under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2 |  | ORD/000511/2021-2022 | 225/RCDI | 01/02/2022 | 7 | JYOGOMAYA ENTERPRISE | 1.81 | 1.81 | 100
1959 | RCFA Division -I | RCFA Division I | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Deputy Superintending Engineer Engineer, RCFA W/S Circle, PHE Dte Govt. of West Bengal (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 |  | ORD/000872/2022-2023 | 455/RCDI | 31/01/2023 | 181 | SHYAMAL MAJI | 0.9 | 0.3 | 80
1960 | RCFA Division -I | RCFA Division I | Acceptance cum work order Supply and installation of sluice valve, shifting of household connection instead of old AC pipe line to distribution branch and etc allied works at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000926/2022-2023 | 1258/ RCD I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.5 | 2.49 | 0
1961 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of 90 mm dia HDPE pipe line and etc allied works at Baidyanathpur Namopara, Bouripara under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000929/2022-2023 | 1264/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.72 | 2.59 | 0
1962 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia distribution pipe line at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000942/2022-2023 | 1276/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.61 | 3.48 | 0
1963 | RCFA Division -I | RCFA Division I | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA Div-I PHE Dte (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 |  | ORD/000969/2022-2023 | 3439/RCD-I | 30/12/2022 | 182 | M/S KALYANI ENTERPRISE | 4.51 | 4.51 | 100
1964 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000001/2021-2022 | 2280/RCD-I | 12/12/2021 | 0 | Resource Division | 20.23 | 0 | 0
1965 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000008/2025-2026 | 2543/RCD-I | 01/09/2025 | 0 | Resource Division | 8.23 | 0 | 0
1966 | RCFA Division -I | Asansol Mechanical Division | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. | Assistant Engineer-II | Junior Engineer-3 | BILL/00105/2024-2025 | 53/24-25 | 20/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.8 | 0 | 0
1967 | RCFA Division -I | Asansol Mechanical Division | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. :- Cost of Boundary demarcation with pillar | Assistant Engineer-II | Junior Engineer-3 | BILL/00146/2024-2025 | 66/24-25 | 28/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.3 | 0 | 0
1968 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of Rising Main from Tube Well to OHR at Roopganj Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000045/2024-2025 | 1646/RCD-I | 04/07/2024 | 242 | M/S KALYANI ENTERPRISE | 12.36 | 7.58 | 100
1969 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 nos of 300 x 200 mm dia tube well 210 mtr deep by D.R. Rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) at Bandra village and Roopganj of Augmentation of Roopganj PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000456/2025-2026 | 2009/RCD-I | 11/07/2025 | 20 | M/S KALYANI ENTERPRISE | 27.78 | 0 | 100
1970 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at kanchanpur of kanksa block under Augmentation of Roopganj Piped W/S Scheme under DWSD PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001227/2023-2024 | 1293/DWSD | 07/08/2023 | 45 | MAJI DEVELOPERS | 6.09 | 6.09 | 100
1971 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part C under Augmentation of Roopganj Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/001234/2023-2024 | 1277_DWSD | 07/08/2023 | 45 | PRADIP CHOUDHARY | 5.83 | 5.83 | 100
1972 | Durgapur W/S Division | Asansol Mechanical Division | Electricity service connection rupganj piped W/s Scheme | Assistant Engineer-II | Junior Engineer-3 | BILL/00153/2023-2024 | BP-2023-24-94 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.95 | 0 | 0
1973 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Emergency work of concreting of exiting dismantled road at ARRAH mouza of Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000036/2023-2024 | 742/DWSD | 16/05/2023 | 15 | M/S BADAL GHOSH | 4.78 | 4.75 | 100
1974 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Emergent work of Concreting of exiting dismantled road of Augmentation of Roopganj piped W/S Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000046/2023-2024 | 769/DWSD | 18/04/2023 | 10 | M/S BADAL GHOSH | 4.78 | 4.76 | 100
1975 | Durgapur W/S Division | Asansol Mechanical Division | Emergent work of concreting of exiting dismantalled road at Roopganj under Augmentation of Roopganj piped W/s Scheme (SM/10203) | Assistant Engineer-II | Junior Engineer-3 | ORD/000083/2023-2024 | 1076/DWSD | 12/07/2023 | 25 | CHATTERJEE CONSTRUCTION | 4.69 | 0 | 0
1976 | Durgapur W/S Division | Asansol Mechanical Division | Replacement of existing pipe line at Nachan OHR to Bansia gram for Physical certification of Har Ghar Jal in connection with JJM of Augmentation Roopganj piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000086/2023-2024 | 719/DWSD | 11/05/2023 | 25 | CHANDAN HAZRA | 23.76 | 23.59 | 100
1977 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 1 No(300X200 mm dia)-Sinking of 1 No (300 mm X 200 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH SIBTALA (T.No-01) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte (SL-10) | Assistant Engineer-II | Junior Engineer-3 | ORD/000124/2022-2023 | 811/DWSD | 21/05/2022 | 10 | JOY GURU ENTERPRISE | 13.78 | 12.81 | 0
1978 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 1 No (250 mm X 150 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH BAZAR (T.No-03) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte.(SL-11) | Assistant Engineer-II | Junior Engineer-3 | ORD/000125/2022-2023 | 812/DWSD | 21/05/2022 | 10 | JOY GURU ENTERPRISE | 11.86 | 11 | 0
1979 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at ARRAH bazar T.No-III Pump house & tube well no-3 for Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000138/2022-2023 | 954/DWSD | 16/06/2022 | 45 | KIRON ENTERPRISE | 4.87 | 2.44 | 0
1980 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sanitary arrangement and plumbing work at Molandighi H/W site pump house no-II tube wno II for Bistupur piped W/S Scheme under DWSD, PHE Dte(SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000140/2022-2023 | 961/DWSD | 17/06/2022 | 10 | BABA LOKENATH ENTERPRISE | 4.8 | 3.91 | 100
1981 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional FHT work of Arrah mouza and Roopganj mouza part under command area of Augmentation of Roopganj Piped W/S Scheme under DWSD ,PHE Dte(SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000155/2022-2023 | 1023/DWSD | 04/07/2022 | 10 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 0
1982 | Durgapur W/S Division | Asansol Mechanical Division | Repairing of existing concrete road restoration and other allied works under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (Part-D) | Assistant Engineer-II | Junior Engineer-3 | ORD/000157/2023-2024 | 1288/DWSD | 07/08/2023 | 20 | CHANDAN HAZRA | 8.69 | 8.66 | 100
1983 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Roopganj near tube well under Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-08) | Assistant Engineer-II | Junior Engineer-3 | ORD/000158/2022-2023 | 1028/DWSD | 04/07/2022 | 7 | R.C.ENTERPRISE | 4.01 | 0 | 0
1984 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of pump house cum Chlorine room at Roopganj H/W site near TW-1/2/3 pf Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte (SL-09) | Assistant Engineer-II | Junior Engineer-3 | ORD/000159/2022-2023 | 1029/DWSD | 04/07/2022 | 15 | R.C.ENTERPRISE | 4.45 | 3.23 | 0
1985 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works under command area o Roopganj mouza of Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-07) | Assistant Engineer-II | Junior Engineer-3 | ORD/000173/2022-2023 | 1165/DWSD | 01/08/2022 | 30 | M/S BADAL GHOSH | 60.68 | 59.5 | 0
1986 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Restoration of drain PCC road at Roopganj and Arrah repairing of valve chamber ,construction of masonry community tank with supply of 2000 Ltrs PVC tank at Arrah Samshan supply fitting fixing and installation of sluice valve under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000200/2021-2022 | 1640/DWSD | 23/11/2021 | 45 | M/S KALYANI ENTERPRISE | 12.12 | 10.04 | 0
1987 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of water supply arrangement at different places to combat water crisis at Kanksa block of Arrah ,Roopganj and Araichand under Roopganj piped W/s Scheme under DWSD ,PHE Dte (SL-11) | Assistant Engineer-II | Junior Engineer-3 | ORD/000324/2021-2022 | 1797/DWSD | 24/12/2021 | 7 | M/S KALYANI ENTERPRISE | 4.99 | 4.99 | 0
1988 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) | Assistant Engineer-II | Junior Engineer-3 | ORD/000329/2021-2022 | 1803/DWSD | 28/12/2021 | 10 | M/S KALYANI ENTERPRISE | 2.32 | 1.16 | 0
1989 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Roopganj Piped W/s Scheme under, DWSD, PHE Dte.(SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000335/2021-2022 | 1684/DWSD | 02/12/2021 | 30 | M/S R.DUTTA AND CO. | 6.39 | 6.39 | 0
1990 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-A) under command area of Rupganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000372/2020-2021 | 144/DWSD | 28/01/2021 | 45 | M/S KALYANI ENTERPRISE | 28.83 | 28.84 | 0
1991 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Replacement of damaged AC pipe with 90 mm dia HDPE from Roopganj more to Araichand gram of Augmentation of Roopganj Piped W/s Scheme under DWSD ,PHE Dte(SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000407/2021-2022 | 334/DWSD | 15/03/2022 | 15 | M/S KALYANI ENTERPRISE | 10.23 | 10.25 | 0
1992 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-C) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) | Assistant Engineer-II | Junior Engineer-3 | ORD/000418/2021-2022 | 402/DWSD | 29/03/2022 | 25 | M/S KALYANI ENTERPRISE | 26.32 | 27.01 | 0
1993 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Construction of 350 M3 capacity Over Head Reservoir having 20 Mtr staging height of RCC OHR at Roopganj H/W site under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000419/2021-2022 | 416/A/DWSD | 30/03/2022 | 180 | AMARANJALI CONSTRUCTION | 83.6 | 47.35 | 75
1994 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-A) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000420/2021-2022 | 404/DWSD | 29/03/2022 | 25 | DARPAN DAS & CO. | 63.18 | 49.67 | 0
1995 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-D) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-04) | Assistant Engineer-II | Junior Engineer-3 | ORD/000421/2021-2022 | 397/DWSD | 28/03/2022 | 30 | M/S BADAL GHOSH | 74.2 | 71 | 0
1996 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-B) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-02) | Assistant Engineer-II | Junior Engineer-3 | ORD/000422/2021-2022 | 401/DWSD | 29/03/2022 | 30 | M/S KALYANI ENTERPRISE | 92.48 | 87.5 | 0
1997 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Laying and aligning of distribution pipe line from Hetedoba OHR,DI Specials ,Valves and allied works under Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000439/2022-2023 | 299/DWSD | 20/02/2023 | 20 | BABA LOKENATH ENTERPRISE | 16.32 | 16.06 | 0
1998 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Arrah Distribution main and other allied work for Roopganj piped W/s Scheme all command area of Roopganj W/s Scheme under DWSD, PHE Dte.(SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000441/2021-2022 | 420/DWSD | 30/03/2022 | 15 | M/S KALYANI ENTERPRISE | 4.1 | 4.09 | 100
1999 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 01 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Roogganj H/W site of Kanksa Block of Augmentation of Roopganj piped W/s Scheme udner DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000455/2022-2023 | 308/DWSD | 20/02/2023 | 15 | M/S BADAL GHOSH | 15.73 | 13.44 | 0
2000 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Re-connection of exiting FHTC from AC pipe line to newly laid different dia pipe line FHTC and also few new connection with JJM for Roopganj mouza (JL-54) under command area of Augmentation of Roopganj W/s Scheme,Block-Kanksa under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000478/2022-2023 | 317/DWSD | 20/02/2023 | 25 | M/S BADAL GHOSH | 57.68 | 50.62 | 0
2001 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Laying ,aligning of DI K9 rising main pipe and interconnection between 3 TW with OHR and other allied works of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000508/2022-2023 | 325/DWSD | 20/02/2023 | 25 | M/S KALYANI ENTERPRISE | 24.33 | 13.25 | 100
2002 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at PH No-3 TW No-3 site of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000512/2022-2023 | 329/DWSD | 20/02/2023 | 30 | MAA KHEPIMAYER CHARANE | 6.9 | 0 | 0
2003 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work for laying of HDPE pipe line for providing FHTC in connection with JJM at Arrah mouza (JL-89) part-C under command area of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000519/2022-2023 | 319/DWSD | 20/02/2023 | 20 | M/S BADAL GHOSH | 97.2 | 73.7 | 100
2004 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-3 | RTOR000013/2021-2022 | 331/DWSD | 15/03/2022 | 0 | Resource Division | 41.84 | 0 | 0
2005 | Durgapur W/S Division | Asansol Mechanical Division | Quatation for Roopganj Pump house no -03 | Assistant Engineer-II | Junior Engineer-3 | VCH/000220/2022-2023 | BP-2022-23-92 | 14/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0
2006 | Durgapur W/S Division | Asansol Mechanical Division | Quotation for Roopganj Pump house no -04 | Assistant Engineer-II | Junior Engineer-3 | VCH/000233/2022-2023 | BP-2022-23-104 | 02/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.68 | 0 | 0
2007 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000154/2022-2023 | 1242/CMD | 12/07/2022 | 30 | AHALYA ENGINEERING WORKS | 10.2 | 9.8 | 100
2008 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000159/2022-2023 | 1244/CMD | 12/07/2022 | 30 | DEY ENTERPRISE | 9.86 | 9.52 | 80
2009 | Asansol Mechanical | Asansol Mechanical Division | Additional works for Chlorination other electrical works at Augmentation of Rupganj Piped Water Supply Scheme, Tube Well No- 5, Block- Kanksa, Paschim Bardhaman, under Asansol Mechanical Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000027/2025-2026 | 947/AMD | 16/05/2025 | 30 | M/S S.G.ENTERPRISE | 3.5 | 0 | 100
2010 | Asansol Mechanical | Asansol Mechanical Division | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Rupganj Water Supply Scheme, P/H No-05 under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000633/2023-2024 | 532/AMD | 12/03/2024 | 90 | M/S S.G.ENTERPRISE | 11.47 | 10.79 | 100
2011 | Durgapur W/S Division | Asansol Mechanical Division | Service charges for new electricity connection at BamunnaraH/W site under Bamunara piped W/S Scheme | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00154/2023-2024 | BP-2023-24-95 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.76 | 0 | 0
2012 | Durgapur W/S Division | Asansol Mechanical Division | Electricity Service connection for Bamunnara TW-II H/W site under Bamunnara piped W/s Scheme | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00155/2023-2024 | BP-2023-24-96 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.35 | 0 | 0
2013 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Bamunara piped W/s Scheme under DWSD ,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000226/2022-2023 | 1242/DWSD | 18/08/2022 | 15 | AHS R INFRA PRIVATE LIMITED | 14.76 | 13.36 | 0
2014 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and allied works construction 400 M3 OHR with 20 mtr staging height including soil investigation and construction of pump house (5.40 m X 3.60 m) with sanitary and water supply arrangement and construction of pump house (3.60X3.00 m) with FHTC for Bamunara piped water Supply scheme under DWSD ,PHE Dte (NS) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000265/2022-2023 | 1438/DWSD | 13/10/2022 | 1024 | HANNAN BUILDERS PVT. LTD. | 658.55 | 515.69 | 100
2015 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Bistupur ,Bamunara piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000563/2022-2023 | 526/DWSD | 29/03/2023 | 15 | MEASURE LAND | 8.11 | 7.62 | 0
2016 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000002/2022-2023 | 1230/DWSD | 17/08/2022 | 0 | Resource Division | 46.44 | 0 | 0
2017 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000008/2022-2023 | 255/D/DWSD | 15/02/2023 | 0 | Resource Division | 17.04 | 0 | 0
2018 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery, Voltages Stabilizer , Chlorination system and internal House wiring for Tube well for Tube well no:- 1 & 2 at Bamunara water supply scheme under CMD PHE Dte, Dist: Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000009/2023-2024 | 1656/CMD | 06/04/2023 | 30 | D.K. ELECTRIC | 22.77 | 22.04 | 100
2019 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-A). | Assistant Engineer 2 |  | ORD/000041/2023-2024 | 1604/RCD I | 25/04/2023 | 180 | PINKI ENTERPRISE | 115.02 | 87.84 | 85
2020 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-D) (Sl No. 14) | Assistant Engineer 2 |  | ORD/000054/2023-2024 | 1707/ RCD I | 03/05/2023 | 90 | MD. JAWED KHAN | 69.87 | 49.08 | 80
2021 | RCFA Division -I | RCFA Division I | Laying of distribution system at Khottamdihi village including FHTC works under Kendra Khottamdihi W/S Scheme under RCFA Div-I, PHE dte. | Assistant Engineer 2 |  | ORD/000399/2022-2023 | 2643/RCDI | 28/10/2022 | 225 | JAYANTA DATTA | 100 | 0 | 100
2022 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of ASTA (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000531/2023-2024 | 3021/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100
2023 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Dendua(1135Cum) and ancillary structure sconducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000532/2023-2024 | 3014/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100
2024 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Searsole (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000538/2023-2024 | 3024/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100
2025 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction for Additional works of MS manifold including interconnection in beetween CWR and pump house and etc allied works at Samlya H/W under Samlya W/S Scheme under RCFA Division-I PHe Dte. | Assistant Engineer 2 |  | ORD/000571/2023-2024 | 2869/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 6.41 | 6.16 | 100
2026 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000657/2022-2023 | 356/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 3.78 | 100
2027 | RCFA Division -I | RCFA Division I | Continuation work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. under JJM (RCFA Part-II) | Assistant Engineer 2 |  | ORD/000825/2022-2023 | 801/RCD-I | 06/03/2023 | 30 | MACHINO TECHNO | 67.77 | 65.09 | 100
2028 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-C) | Assistant Engineer 2 |  | ORD/000868/2022-2023 | 1118/RCD-I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 81.57 | 75.71 | 90
2029 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-E) | Assistant Engineer 2 |  | ORD/000869/2022-2023 | 1120/RCD-I | 23/03/2023 | 800 | JAYANTA DATTA | 91.65 | 20.35 | 70
2030 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-B)(Sl No. 12) | Assistant Engineer 2 |  | ORD/000870/2022-2023 | 1116/RCD-I | 23/03/2023 | 90 | BABA LOKNATH ENTERPRISE | 71.02 | 48.63 | 80
2031 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Store Room at Head Works Site for (Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 29) | Assistant Engineer 2 |  | ORD/000902/2022-2023 | 1173/RCD I | 24/03/2023 | 90 | RANJIB GHATAK | 4.61 | 0 | 0
2032 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at Shankarpur OHR Site for Augmentation of RCFA part-II (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 27) | Assistant Engineer 2 |  | ORD/000904/2022-2023 | 1171/RCD I | 24/03/2023 | 277 | RANJIB GHATAK | 4.61 | 0 | 100
2033 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Approach road and others necessary allied works at Front Gate to village road for Shankarpur OHR Site (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 28) | Assistant Engineer 2 |  | ORD/000908/2022-2023 | 1172/RCD I | 24/03/2023 | 60 | RANJIB GHATAK | 3.78 | 3.7 | 100
2034 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including adopting trench less technology b(e.g. Jack Pushing Method etc) of 02 (Two) nos location at Sankarpur (near Footbal ground ) and Shankarpur GP office under Augmentation of RCFA Part-II (Zone-4A) PWSS (Part-C ) under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 |  | ORD/000913/2023-2024 | 213/RCD-I | 29/01/2024 | 15 | UNITED CONSTRUCTION | 13.08 | 11.74 | 100
2035 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Allied work for bridge, road and other allied work at Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000965/2023-2024 | 508/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 81.93 | 81.91 | 100
2036 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000014/2023-2024 | 2934/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
2037 | Durgapur W/S Division | Asansol Mechanical Division | New service connection charges for jatgoria piped W/s Scheme | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00082/2023-2024 | BP-2023-24-54 | 08/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.22 | 0 | 0
2038 | Durgapur W/S Division | Asansol Mechanical Division | New service connection charges for jatgoria water supply scheme TW-2 | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00083/2023-2024 | BP-2023-24-55 | 08/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.17 | 0 | 0
2039 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 2 Nos tube well 250 mm X 150 mm tube well 120 mtr depth by Direct rotary Rig method using PVC pipe and prepacked resin bonded gravel filter for Jatgoria piped W/s Scheme under DWSD ,PHE Dte(SL-07) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000229/2022-2023 | 1254/DWSD | 23/08/2022 | 15 | RANJIB GHATAK | 14.75 | 14.03 | 100
2040 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work laying distribution system rising main ,construction of 100M3 reservoir with 20mtr staging height including soil investigation construction of pump house (5.40X3.60 m) with sanitary and water supply arrangement and construction of pump house (3.6 X 3.00 m) for Jatgoria W/s Scheme ,Kanksa block under DWSD,PHE Dte (NS) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000269/2022-2023 | 1656/DWSD | 05/12/2022 | 365 | SUPER SKILL | 170.87 | 109.73 | 45
2041 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000002/2023-2024 | 694/DWSd | 08/05/2023 | 0 | Resource Division | 21.35 | 0 | 0
2042 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000010/2022-2023 | 255/E/DWSD | 15/02/2023 | 0 | Resource Division | 3.88 | 0 | 0
2043 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Jatgaria Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000010/2023-2024 | 1655/CMD | 06/04/2023 | 30 | CHOUDHURY ENTERPRISE | 21.07 | 20.29 | 40
2044 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network Including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000066/2023-2024 | 1763/RCD I | 16/05/2023 | 962 | MACHINO TECHNO | 541.2 | 167.23 | 30
2045 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology at 4 nos location (Dabor more, Achhra Road, Rupnarayanpur Phari, Rupnarayanpur Chittaranjan Road) of Salanpur Block under Improvement of RCFA Part-I (Zone-7, Part-F) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000289/2023-2024 | 2338/RCD-I | 01/08/2023 | 15 | GITA CONSTRUCTION | 67.97 | 63.53 | 100
2046 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone- under RCFA Division-I PHE Dte. (Part-B). | Assistant Engineer 2 | Junior Engineer | ORD/000516/2023-2024 | 2867/RCD-I | 06/10/2023 | 15 | MACHINO TECHNO | 41.98 | 38.27 | 100
2047 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard room with toilet at Dendua under Salanpur Block for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2023-2024 | 3280/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 7.61 | 7.29 | 100
2048 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional emergency work road restoration, laying of PVC pipe and other allied work for balance part at different location of Ramnagar and adjoining area within Pandabeswar Block for Augmentation PWSS of RCFA Part-II (Zone-6) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000705/2025-2026 | 2632/RCD-I | 08/09/2025 | 25 | M/S MONDAL ENTERPRISE | 10.1 | 0 | 90
2049 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000791/2023-2024 | 3437_RCD_I | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 0 | 0
2050 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply fitting and allining of 250 mm dia non return valve and 80 mm dia air valve and etc allied works at Bilpahari OCP area on distribution main under Kendra Khottamdihi water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000797/2023-2024 | 2896_RCD-I | 06/10/2023 | 30 | M/S UNIT CONSTRUCTION | 2.42 | 0 | 0
2051 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work Balance Work of Road restoration in connection with Distribution Network including FHTC and allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2023-2024 | 454/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 45.34 | 43.8 | 50
2052 | RCFA Division -I | RCFA Division I | Formal work order for construction of 600 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-6) for Augmentation of RCFA Part_II Piped Water Supply Scheme including Soil investigation and Chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman.(2nd Call). | Assistant Engineer 2 | Junior Engineer | ORD/001016/2023-2024 | 558/RCD-I | 21/02/2024 | 366 | MRITYUNJOY MUKHERJEE & CO. | 151 | 75.5 | 42
2053 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc) at Kunustoria for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I.PHE Dte.(Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/001165/2023-2024 | 1017/RCD-I | 16/03/2024 | 15 | B.T.M. CONCERN | 22.8 | 21.52 | 100
2054 | RCFA Division -I | RCFA Division I | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA div-I PHE Dte (w.e.f 01.08.2023 to 31.01.2024) | Assistant Engineer 2 | Junior Engineer | ORD/001166/2023-2024 | 2319_RCD-I | 31/07/2023 | 184 | M/S KALYANI ENTERPRISE | 4.49 | 0 | 0
2055 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying distribution pipe line of providing FHTC at Harispur Taldanga under Madanpur Gram Panchayat of Andal Block of JJM work AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) under RCFA Division-I.PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001169/2023-2024 | 1008/RCD-I | 16/03/2024 | 15 | M/S MONDAL ENTERPRISE | 5.56 | 5.55 | 100
2056 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000020/2023-2024 | 2952/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
2057 | RCFA Division -I | RCFA Division I | Restoration work for laying D.I pipeline along the Hard Shoulder from Ch. 3.67 Km to Ch. 8.50 kmp at left side and from ch. 3.00 to Ch. 4.50 kmp (ICDS more to Maira colliary ) at right side of Andal - Ukhra Road under Asansol Division, PWD in the district of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00217/2024-2025 | 112/24-25 | 21/06/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 20.4 | 0 | 0
2058 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of construction of 500 cum capacity 20 mtr. staging height RCC Over Head Reservoir (piped connection and cost of pipes, specials at Raniganj Block (Zone-17) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000095/2023-2024 | 1829/RDC-i | 29/05/2023 | 366 | SWATI CORPORATION | 131.06 | 131.06 | 100
2059 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Amdiha more towards Itapara village Surrounding area (Zone-IX) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000283/2023-2024 | 2332/RCD-I | 01/08/2023 | 15 | SRI KRISHNA ENTERPRISE | 19.97 | 18.86 | 100
2060 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000465/2023-2024 | 2871/RCD-1 | 06/10/2023 | 90 | TARA CONSTRUCTION | 24.96 | 24.82 | 100
2061 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of concrete dismantling & re-concreting with other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000472/2023-2024 | 2876/RCD-1 | 06/10/2023 | 30 | TARA CONSTRUCTION | 76.37 | 40.54 | 100
2062 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000474/2023-2024 | 2863/RCD-I | 06/10/2023 | 573 | TARA CONSTRUCTION | 38.14 | 32.73 | 90
2063 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2 | Junior Engineer | ORD/000515/2023-2024 | 2866/RCD-I | 06/10/2023 | 30 | MACHINO TECHNO | 88.08 | 88.08 | 100
2064 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard room with toilet at Shyamla Over Head site under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000521/2023-2024 | 2879/RCD-I | 06/10/2023 | 90 | G. CONSTRUCTION | 5.48 | 5.35 | 100
2065 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 500 cum capacity RCC Over Head Reservoir at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000558/2022-2023 | 3352/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0.49 | 100
2066 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Pump House at Damalia H/W site for Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000571/2022-2023 | 3280/RCDI | 20/12/2022 | 45 | B.T.M CONCERN | 30.19 | 30.03 | 70
2067 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and providing FHTC painting of H/W site for Dhandardihi Piped water supply Scheme Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000609/2023-2024 | 3369/RCD-1 | 21/11/2023 | 15 | MD. JAWED KHAN | 3.12 | 2.97 | 100
2068 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of UPVC pipe line supply fitting and fixing of valves and allied works under Dhandardihi water supply scheme under RCFA Division -I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000622/2023-2024 | 3375/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 3.61 | 3.55 | 100
2069 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room, extension of Boundary Wall, Land Development, approached road and allied works under Augmentation of RCFA Part-II (Zone-17) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000626/2023-2024 | 3416/RCD-1 | 24/11/2023 | 60 | DIP CONSTRUCTION | 25.93 | 25.88 | 100
2070 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000664/2023-2024 | 3433/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.6 | 6.6 | 100
2071 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction work of Damaged RCC Elevated Reservoir including dismantling and reconstruction of Top dome of capacity 1135 cum of Sankarpur OHR under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000764/2022-2023 | 391/RCDI | 30/01/2023 | 1296 | RANJIB GHATAK | 33.55 | 26.45 | 100
2072 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000815/2022-2023 | 997/RCDI | 22/03/2023 | 855 | TARA CONSTRUCTION | 342.78 | 139.59 | 75
2073 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 30) | Assistant Engineer 2 | Junior Engineer | ORD/000910/2022-2023 | 1174/RCD I | 24/03/2023 | 739 | N.R. CONSTRUCTION | 4.61 | 0 | 100
2074 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000940/2023-2024 | 488/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.16 | 8.81 | 100
2075 | RCFA Division -I | RCFA Division I | Additional work for supply and delivery of CI/DI specials including hard rock cutting, restoration of drain and supply of MS pipe (500 mm dia) and allied works within Zone-I Part-B under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000960/2023-2024 | 464/RCD-1 | 12/02/2024 | 20 | SWATI CORPORATION | 18.11 | 17.86 | 100
2076 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works for construction of boundary wall with gate at OHR site (length 150 mtr) and land development with approach road including internal drain at Head Work Site for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/001136/2023-2024 | 934/RCD-I | 15/03/2024 | 15 | SWATI CORPORATION | 20.16 | 17.76 | 100
2077 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000036/2023-2024 | 2938/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
2078 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-B) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte (SL-06) |  |  | ORD/000001/2021-2022 | 715/DWSD | 29/04/2021 | 20 | S.S.CONSTRUCTION | 4.98 | 9.97 | 0
2079 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Roopganj W/S Scheme to combat draught like situation in Kanksa block to providing FHTC at Roopganj mouza (JL-54) under DWSD, PHE Dte (SL-07) |  |  | ORD/000002/2021-2022 | 716/DWSD | 29/04/2021 | 25 | M/S KALYANI ENTERPRISE | 4.96 | 9.91 | 0
2080 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-A) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte(Sl-05) |  |  | ORD/000005/2021-2022 | 718/DWSD | 29/04/2021 | 25 | M/S S. CHOUDHURY | 4.85 | 9.72 | 0
2081 | Durgapur W/S Division |  | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) |  |  | ORD/000006/2021-2022 | 719/DWSD | 29/04/2021 | 25 | BABA LOKENATH ENTERPRISE | 4.99 | 9.94 | 0
2082 | Durgapur W/S Division |  | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) |  |  | ORD/000023/2021-2022 | 796/DWSD | 12/05/2021 | 15 | BABA LOKENATH ENTERPRISE | 12.9 | 25.24 | 0
2083 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing functional house hold Tap connection (FHTC) in connection with JJM for Kalikapur mouza(JL-30) under command area of Jamgora-Jagannathpur W/S Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000024/2021-2022 | 794/DWSD | 12/05/2021 | 15 | M/S MONDAL ENTERPRISE | 11.05 | 22.53 | 0
2084 | Durgapur W/S Division |  | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Sarpi Adibasipara,Dhibarpara ,Bouripara,Ruidaspara, Mondalpara,Karmakarpara under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000059/2021-2022 | 1055/DWSD | 22/07/2021 | 15 | RANJIB GHATAK | 8.27 | 16.49 | 0
2085 | Durgapur W/S Division |  | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Domra and Piariganj mouza distribution zone under Tilakchandrapur W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000062/2021-2022 | 990/DWSD | 05/07/2021 | 20 | AMARANJALI CONSTRUCTION | 11.94 | 23.82 | 0
2086 | Durgapur W/S Division |  | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kajladihi mouza (JL-26) under command area of Krishnapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000073/2020-2021 | 902/DWSD | 22/09/2020 | 45 | THE STAR & CO | 16.5 | 32.83 | 0
2087 | Durgapur W/S Division |  | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for RUPGANGANJ mouza (JL-54)under command area of Rupganj W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-02) |  |  | ORD/000074/2020-2021 | 1355/DWSD | 09/12/2020 | 45 | M/S KALYANI ENTERPRISE | 13.97 | 28.47 | 0
2088 | Durgapur W/S Division |  | Formal work- order for the work of ----Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudebpur mouza (JL-5)under command area of Kanchanpur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-03) |  |  | ORD/000075/2020-2021 | 930/DWSD | 22/09/2020 | 45 | MACHINO TECHNO | 15.79 | 26.46 | 0
2089 | Durgapur W/S Division |  | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shilampur mouza (JL-90)under command area of Kanksa Zone-I W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000076/2020-2021 | 932/DWSD | 25/09/2020 | 45 | MD AAMIR KHAN | 43.86 | 90.26 | 0
2090 | Durgapur W/S Division |  | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Piariganj mouza (JL-93) under command area of Tilakchandrapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-11) |  |  | ORD/000077/2020-2021 | 1356/DWSD | 09/12/2020 | 45 | AMARANJALI CONSTRUCTION | 13.52 | 26.96 | 0
2091 | Durgapur W/S Division |  | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Srikrishnapur mouza (JL No-09) under command area of Gourbazar-Ichhapur W/s Scheme Durgapur-Faridpur Block, Paschim Bardhaman under Durgapur W/S Division, PHE Dte. |  |  | ORD/000080/2020-2021 | 897/DWSD | 22/09/2020 | 45 | JOY GURU ENTERPRISE | 19.09 | 37.94 | 0
2092 | Durgapur W/S Division |  | FORMAL WORK ORDER FOR the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rajkusum mouza (JL-72) under command area of Rajkusum W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000081/2020-2021 | 875/DWSD | 15/09/2020 | 45 | RANJIB GHATAK | 31.99 | 15.07 | 0
2093 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Dhabani(JL-43) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000081/2021-2022 | 1093/DWSD | 30/07/2021 | 15 | RANJIB GHATAK | 4.44 | 8.87 | 0
2094 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Additional work for providing FHTC in connection with JJM at Pratappur(JL-40) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000083/2021-2022 | 1095/DWSD | 30/07/2021 | 15 | JAYANTA DATTA | 4.2 | 8.07 | 0
2095 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Jabuna (JL-55) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte (SL-06) |  |  | ORD/000086/2021-2022 | 1098/DWSD | 30/07/2021 | 10 | D. S. ENTERPRISE | 0.63 | 1.26 | 0
2096 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme with concrete cutting and re-concreting to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-D) under DWSD,PHE Dte(SL-10) |  |  | ORD/000090/2021-2022 | 1102/DWSD | 30/07/2021 | 15 | MANAS KUMAR SAHA | 3.97 | 7.83 | 0
2097 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-F) under DWSD,PHE Dte (SL-11). |  |  | ORD/000091/2021-2022 | 1103/DWSD | 30/07/2021 | 15 | MANAS KUMAR SAHA | 4.85 | 9.7 | 0
2098 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of replacement of AC pipe line with UPVC pipe line at Mollapara More to Kansa Gangulipara under Kanksa W/S Scheme under DWSD, PHE Dte (SL-07) |  |  | ORD/000093/2020-2021 | 918/DWSD | 22/09/2020 | 20 | RANJIB GHATAK | 4.85 | 9.86 | 0
2099 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from exisitn pipe line Kanksa (Zone-II (Ph-II) W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Kanksa mouza (JL_89) under DWSD ,PHE Dte at Poral para,Khadra para under DWSD,PHE Dte (SL-19) |  |  | ORD/000099/2021-2022 | 1111/DWSD | 30/07/2021 | 15 | SWATI CORPARATION | 4.95 | 10.06 | 0
2100 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing functional houehold tap connection (FHTC) in connection with JJM at Bonsol Mouza(JL_49) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-01) |  |  | ORD/000101/2021-2022 | 1272/DWSD | 02/09/2021 | 60 | JOY GURU ENTERPRISE | 22.47 | 22.45 | 0
2101 | Durgapur W/S Division |  | Formal for the work of Providing functional household tap connection (FHTC) in connection with JJM at Shyamsundarpur Mouza(JL_07) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(Part-C) (SL-03) |  |  | ORD/000102/2021-2022 | 1254/DWSD | 27/08/2021 | 60 | PRAVAT SARKAR | 27.33 | 27.3 | 0
2102 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing functional house hold tap connection (FHTC) in connection with JJM at Tilakchandrapur Mouza(JL_63) & Sundiara(JL-67),Block-Kanksa ,Dist.-Paschim Bardhaman under Tilakchandrapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-05) |  |  | ORD/000103/2021-2022 | 1229/DWSD | 23/08/2021 | 45 | S K ALIM | 15.03 | 15.01 | 0
2103 | Durgapur W/S Division |  | Formal order for the work of Replace of damaged AC pipe line with HDPE pipe from Kanksa under pass towards Kanksa PS of Kanksa (Zone-II & Ph-II) W/S Scheme under DWSD,PHE Dte (SL-06) |  |  | ORD/000104/2021-2022 | 1374/DWSD | 17/09/2021 | 20 | SWATI CORPARATION | 9.71 | 19.78 | 0
2104 | Durgapur W/S Division |  | Acceptance order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Ichhapur Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-08) |  |  | ORD/000106/2021-2022 | 1195/DWSD | 11/08/2021 | 60 | SHWET BARANI | 22.71 | 22.74 | 0
2105 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Bhadrapur Mouza & Basgora Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte. |  |  | ORD/000107/2021-2022 | 1253/DWSD | 27/08/2021 | 60 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 6.7 | 6.66 | 0
2106 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Nachan mouza for provding FHTC in connection with JJM for Nachan mouza(JL-39) (Part-A) under command are aof Jamgora-Jagannathpur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte (SL-24) |  |  | ORD/000111/2021-2022 | 1116/DWSD | 30/07/2021 | 15 | BABA LOKENATH ENTERPRISE | 4.59 | 9.39 | 0
2107 | Durgapur W/S Division |  | Formal order for the work of Repairing ,extension as well as replace of damaged pipe line and allied works at Sarpi mouza (JL-35) under command area of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-09) |  |  | ORD/000113/2021-2022 | 1300/DWSD | 09/09/2021 | 20 | KIRON ENTERPRISE | 6.59 | 13.15 | 0
2108 | Durgapur W/S Division |  | Formal order for the work of Additional work for provding FHTC in connection with JJM and Jal Swapna at Ijjatganj mouza (JL_71) under command area of kanksa (Zone-II) W/s Scheme of block-Durgapur-Fardipur under DWSD ,PHE Dte (SL-08) |  |  | ORD/000114/2021-2022 | 1375/DWSD | 17/09/2021 | 45 | RANJIB GHATAK | 33.78 | 34.4 | 0
2109 | Durgapur W/S Division |  | Formal order for the work of Extension of existing pipe line of Kanchanpur to combat drought like situation in Kanksa block to providng FHTC at Kanchanpur,Sashipu,Benodpur,Dubrajpur,Basudebpur,Talbahari mouzas repiring of leakage bursting 160 to 90 mm dia at different places ,restoration of drain village road supply of hume pipe at pump house No-II and others allied works of cmmand area under Kanchanpur piped W/s Scheme (SL-02) |  |  | ORD/000116/2021-2022 | 1291/DWSD | 07/09/2021 | 20 | MRITYUNJOY MUKHERJEE AND CO | 12.82 | 12.7 | 0
2110 | Durgapur W/S Division |  | Formal order for the work of Providing additional number of FHTC and laying of branch pipe line from existing pipe line in connection with JJM for Basuhda Mouza (JL_35) under command area of Basudha W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-06) |  |  | ORD/000117/2021-2022 | 1376/DWSD | 17/09/2021 | 60 | M/S S. CHOUDHURY | 38.92 | 40.02 | 0
2111 | Durgapur W/S Division |  | Formal order for the work of Supplying and laying of 140 mm dia UPVC pipe line from Hetedoba OHR to Jhajra more for water supply of Sarpi more ,Jhanjra gram and Adibasipara of Jamgora under Jamgora-Jagannathpur piped W/s Scheme.(SL-07) |  |  | ORD/000118/2021-2022 | 1371/DWSD | 17/09/2021 | 20 | MD AAMIR KHAN | 23.48 | 0 | 0
2112 | Durgapur W/S Division |  | Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) |  |  | ORD/000122/2021-2022 | 1225/DWSD | 19/08/2021 | 10 | KIRON ENTERPRISE | 1.22 | 2.27 | 0
2113 | Durgapur W/S Division |  | Continuation order for the work of Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) |  |  | ORD/000123/2021-2022 | 1214/DWSD | 17/08/2021 | 15 | KIRON ENTERPRISE | 4.84 | 9.72 | 0
2114 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Nachan ,Bansia, Dhabani Labnapara for providing sufficient water to every house hold of Gourbazar -Ichhapur piped W/s Scheme under DWSD ,PHE Dte(SL-01) |  |  | ORD/000131/2021-2022 | 1162/DWSD | 02/08/2021 | 15 | M/S MONDAL ENTERPRISE | 4.75 | 0 | 0
2115 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Protapur ,Kalikapur and Jamgora village under command area of Nachan OHR of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-02) |  |  | ORD/000132/2021-2022 | 1163/DWSD | 02/08/2021 | 20 | RANJIB GHATAK | 4.85 | 0 | 100
2116 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system from command area of Gourbazar OHR (Gourbazar-Srikrishanapur,Kailashpur(Part) for providing sufficient Water to every house holds under Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (Part-B) (SL-03) |  |  | ORD/000133/2021-2022 | 1164/DWSD | 02/08/2021 | 15 | JOY GURU ENTERPRISE | 3.49 | 0 | 0
2117 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line and replace old damaged AC pipe line with HDPE pipe of Kanksa Zone-I W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Shilampur Gosh Para Mouza JL-89 under DWSD ,PHE Dte (SL-10) |  |  | ORD/000137/2021-2022 | 1320/DWSD | 14/09/2021 | 15 | MAK CONSTRUCTION CO. | 4.91 | 9.83 | 0
2118 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying ,fitting and fixing of CI special ,valve construction of Sluice valve chamber & others allied work for distribution system of entire command area of Gourbazar OHR site under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-16) |  |  | ORD/000138/2021-2022 | 1177/DWSD | 02/08/2021 | 15 | JOY GURU ENTERPRISE | 4.36 | 0 | 0
2119 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supply fitting fixing and installation of sluice valve for O & Mtc of Kanksa (Zone-II (Ph-II) W/s Scheme command area of Panagarh ,Prayagpur Mouza under DWSD ,PHE Dte. (SL-13) |  |  | ORD/000141/2021-2022 | 1322/DWSD | 14/09/2021 | 15 | TARA CONSTRUCTION | 4.93 | 0 | 0
2120 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at different places to combat water crisis at Bonsal,Hetedoba,Jabber Pally & Hetedoba, block - Durgapur-Faridpur of Ichhapur GP under DWSD, PHE Dte . (SL-28) |  |  | ORD/000145/2021-2022 | 1183/DWSD | 06/08/2021 | 15 | JOY GURU ENTERPRISE | 3.21 | 0 | 0
2121 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergent supply fitting ,fixing of sluice valve for repairing and maintenance of pipe line under command area of Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-30). |  |  | ORD/000146/2021-2022 | 1184/DWSD | 06/08/2021 | 20 | TARA CONSTRUCTION | 3.86 | 0 | 0
2122 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Jamgora-Jagannathpur W/s Scheme to combat draught like situation in Durgapur-Faridpur block to provide FHTC at Banerjeepara,Mukherjee para ,Bouri Para ,Harimandir ,Durgamandir of Nachan Gram from Nachan bypass of Nachan Mouza (JL-39) (Part-B) under DWSD, PHE Dte(SL-18) |  |  | ORD/000157/2021-2022 | 1326/DWSD | 14/09/2021 | 15 | BABA LOKENATH ENTERPRISE | 4.5 | 0 | 0
2123 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying and laying of additional 90 mm /75 mm dia HDPE pipe line with concrete works and necessary works at Gangbill and Ayma Biswanathpur near Itvata More of Ayma Biswanathpur Mouza(JL-82 & 83) under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte (Part-A)(SL-25) |  |  | ORD/000161/2021-2022 | 1330/DWSD | 14/09/2021 | 20 | MAK CONSTRUCTION CO. | 4.91 | 9.76 | 0
2124 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional 90 mm dia HDPE pipe line with necessary allied works at Ayma Biswanathpur Mouza (JL-82) Balighat towards Ketan of Ayama Biswanthpur under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte.(SL-26) |  |  | ORD/000162/2021-2022 | 1331/DWSD | 14/09/2021 | 20 | MAK CONSTRUCTION CO. | 4.85 | 9.65 | 0
2125 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Bypass connection from existing R/M at Gopalpur OHR site and jungle cutting at head work site Pump house Site -II and III of Gopalpur W/s Scheme under DWSD,PHE Dte .(SL-29) |  |  | ORD/000163/2021-2022 | 1333/DWSD | 14/09/2021 | 15 | QUICK PAL SUPPLIERS | 4.94 | 0 | 0
2126 | Durgapur W/S Division |  | Laying of UPVC pipe line and other allied works at Kanksa under Pass to Molla para under Kanksa W/s Scheme under DWSD,PHE Dte.(SL-26) |  |  | ORD/000165/2020-2021 | 1044/DWSD | 09/10/2020 | 15 | M/S KALYANI ENTERPRISE | 4.94 | 9.84 | 0
2127 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Cleaning the chokage of AC Pipe line of 80 /100/150 mm dia for providing water supply to Arrah Mouza & other allied works for providing FHTC of Roopgnaj W/s Scheme under DWSD ,PHE Dte (SL-34) |  |  | ORD/000165/2021-2022 | 1336/DWSD | 14/09/2021 | 10 | M/S KALYANI ENTERPRISE | 4.14 | 0 | 0
2128 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emegent supply ,fitting -fixing of Sluice valve for repairing and maintenance of pipe line under command area from Sarpi village,Amlouka,Patseura,Arati,Jabuna areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-01) |  |  | ORD/000167/2021-2022 | 1338/DWSD | 14/09/2021 | 15 | MD AAMIR KHAN | 4.56 | 0 | 0
2129 | Durgapur W/S Division |  | Acceptance cum formal order for the Work of Emergent supplying, fitting fixing of Sluice valve for repairing and maintenance of ppe line under command are a of Ichhapur areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000168/2021-2022 | 1339/DWSD | 14/09/2021 | 20 | MD AAMIR KHAN | 4.42 | 0 | 0
2130 | Durgapur W/S Division |  | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (part-B) |  |  | ORD/000177/2021-2022 | 1283/DWSD | 06/09/2021 | 15 | RANJIB GHATAK | 4.12 | 3.86 | 0
2131 | Durgapur W/S Division |  | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-A) |  |  | ORD/000178/2021-2022 | 1273/DWSD | 02/09/2021 | 15 | RANJIB GHATAK | 4.21 | 0 | 0
2132 | Durgapur W/S Division |  | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-C) |  |  | ORD/000179/2021-2022 | 1290/DWSD | 07/09/2021 | 15 | RANJIB GHATAK | 3.75 | 3.75 | 0
2133 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) |  |  | ORD/000182/2021-2022 | 1403/DWSD | 23/09/2021 | 15 | SWATI CORPORATION | 3.03 | 0 | 0
2134 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Emergency repairing kanksa Zone-I(Ijjatganj) Phase-I W/s Scheme pipe line of entire command area for providing sufficient water to every house hold to Kanksa mouza, Ijjatganj and Prayagpur mouza under DWSD,PHE Dte(SL-02) |  |  | ORD/000183/2021-2022 | 1404/DWSD | 23/09/2021 | 20 | DAS & CHAKRABORTY | 4.91 | 4.59 | 0
2135 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Prayagpur mouza for laying of branch line under command area of Kanksa Zone-II W/s Scheme for providing of FHTC under DWSD ,PHE Dte (SL-03) |  |  | ORD/000184/2021-2022 | 1405/DWSD | 23/09/2021 | 15 | B. T. M. CONCERN | 4.55 | 1.63 | 0
2136 | Durgapur W/S Division |  | Formal order for the work of Additional functional house hod tap connection FHTC in connection with JJM at Nachan mouza (JL-39) under command area of Jamgora-Jagannathpur piped W/s Scheme block -Durgapur-Faridpur under DWSD, PHE Dte (SL-03) |  |  | ORD/000202/2021-2022 | 1634/DWSD | 22/11/2021 | 30 | BABA LOKENATH ENTERPRISE | 11.05 | 11.1 | 0
2137 | Durgapur W/S Division |  | Formal order for the work of Emergency provision of AC photovoltaic submersible solar pum set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at near DVC School Para under Pandebaswar Block under DWSD ,PHE Dte (SL-12) |  |  | ORD/000207/2021-2022 | 1596/DWSD | 08/11/2021 | 30 | RANJIB GHATAK | 13.56 | 0 | 0
2138 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000219/2020-2021 | 1156/DWSD | 28/10/2020 | 45 | M/S BADAL GHOSH | 10.15 | 18.01 | 0
2139 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Tilakchandrapur mouza (JL-63)under command area of Tilakchandrapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000220/2020-2021 | 1157/DWSD | 28/10/2020 | 45 | S K ALIM | 22.47 | 44.88 | 0
2140 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rautdihi mouza (JL-25) under command area of Bidbahar GP Krishnapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(sl-17) |  |  | ORD/000221/2020-2021 | 1158/DWSD | 28/10/2020 | 45 | THE STAR & CO | 5.59 | 11.08 | 0
2141 | Durgapur W/S Division |  | Acceptance cum formal work order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Bankati mouza (JL-33)under command area of Basudha W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte(SL-18) |  |  | ORD/000222/2020-2021 | 1159/DWSD | 28/10/2020 | 45 | BISHAL ENTERPRISE | 14.6 | 26.56 | 0
2142 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jamgora mouza (JL-23) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000246/2020-2021 | 1332/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 24.63 | 49.21 | 0
2143 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kalikapur mouza (JL-30) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-02) |  |  | ORD/000247/2020-2021 | 1304/DWSD | 09/12/2020 | 45 | M/S MONDAL ENTERPRISE | 11.59 | 23.85 | 0
2144 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banshia mouza (JL-31) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-03) |  |  | ORD/000248/2020-2021 | 1305/DWSD | 09/12/2020 | 45 | BABA LOKNATH ENTERPRISE | 17.74 | 36.51 | 0
2145 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000250/2020-2021 | 1307/DWSD | 09/12/2020 | 45 | M/S BADAL GHOSH | 6.63 | 11.82 | 0
2146 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Hetedoba mouza (JL-48) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000251/2020-2021 | 1308/DWSD | 09/12/2020 | 45 | AMARANJALI CONSTRUCTION | 12.32 | 24.45 | 0
2147 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Arati mouza (JL-54) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-09) |  |  | ORD/000253/2020-2021 | 1310/DWSD | 09/12/2020 | 45 | BISHAL ENTERPRISE | 26.15 | 52.59 | 0
2148 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sibpur mouza (JL-20) under command area of within Bidbhar GP, Kanksa Block of Krishnapur piped W/s Scheme under Durgapur W/S Division, PHE Dte.(SL-10) |  |  | ORD/000254/2020-2021 | 1311/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 21.43 | 41.64 | 0
2149 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jabuna mouza (JL-55) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-11) |  |  | ORD/000255/2020-2021 | 1312/DWSD | 09/12/2020 | 45 | D. S. ENTERPRISE | 11.37 | 22.72 | 0
2150 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Ichhapur mouza (JL-50) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-12) |  |  | ORD/000256/2020-2021 | 1315/DWSD | 09/12/2020 | 45 | SHWET BARANI | 25.79 | 45.26 | 0
2151 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Patsaora mouza (JL-53) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-13) |  |  | ORD/000257/2020-2021 | 1316/DWSD | 09/12/2020 | 45 | SHWET BARANI | 19.08 | 30.69 | 50
2152 | Durgapur W/S Division |  | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000258/2020-2021 | 1317/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 25.99 | 44.23 | 0
2153 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kanchanpur mouza (JL-02) under command area of Kanchanpur piped W/s Scheme of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000259/2020-2021 | 1318/DWSD | 09/12/2020 | 45 | MRITYUNJOY MUKHERJEE AND CO | 17.56 | 29.42 | 0
2154 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing FHTC in connection with JJM for Radhamohanpur Mouza(JL-36) under command area of Basudha piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte (SL-04) |  |  | ORD/000259/2021-2022 | 1706/DWSD | 08/12/2021 | 30 | MD AAMIR KHAN | 24.05 | 24.6 | 0
2155 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing FHTC in connection with JJM for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte |  |  | ORD/000260/2021-2022 | 1707/DWSD | 08/12/2021 | 30 | MD AAMIR KHAN | 42.05 | 43.15 | 0
2156 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Sundiara mouza (JL-67) under command area of Trilockchandrapur piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000261/2020-2021 | 1319/DWSD | 09/12/2020 | 45 | S K ALIM | 14.52 | 28.98 | 0
2157 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ijjatganj mouza (JL-71) under command area of Kanksa Zone-II(Ph-I) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-17) |  |  | ORD/000262/2020-2021 | 1320/DWSD | 09/12/2020 | 45 | RANJIB GHATAK | 42.68 | 85.03 | 0
2158 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Basudha mouza (JL-35) under command area of Basudha piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) |  |  | ORD/000263/2020-2021 | 1321/DWSD | 09/12/2020 | 45 | M/S S. CHOUDHURY | 42.77 | 82.12 | 0
2159 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Pryagpur mouza (JL-88) under command area of Kanksa Zone-II(Ph-II) (Pt-A) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-19) |  |  | ORD/000264/2020-2021 | 1322/DWSD | 09/12/2020 | 45 | DAS & CHAKRABORTY | 43.55 | 87.22 | 0
2160 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Debipur mouza (JL-87) under command areaof Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-21) |  |  | ORD/000265/2020-2021 | 1313/DWSD | 09/12/2020 | 45 | M/S. D. PALIT & CO. | 43.64 | 82.83 | 0
2161 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-20) |  |  | ORD/000266/2020-2021 | 1314/DWSD | 09/12/2020 | 45 | UMWELT ENGINEER PVT LTD | 43.6 | 89.47 | 0
2162 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ayma Biswanathpur & Gangbil mouza (JL-82 & 83) under command area of Kanksa Zone-I piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-22) |  |  | ORD/000267/2020-2021 | 1363/DWSD | 10/12/2020 | 45 | MD AAMIR KHAN | 41.61 | 83.23 | 0
2163 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kalinagar mouza (JL-27) under command area Durgapur-Faridpur Block of Jamgora-Jagnnathpur piped W/s Scheme of under Durgapur W/S Division, PHE Dte (SL-23) |  |  | ORD/000268/2020-2021 | 1323/DWSD | 09/12/2020 | 45 | M/S BADAL GHOSH | 5.52 | 10.49 | 0
2164 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Pratappur mouza (JL-40) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-25) |  |  | ORD/000270/2020-2021 | 1325/DWSD | 09/12/2020 | 45 | JAYANTA DATTA | 18.89 | 37.73 | 0
2165 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bhadrapur(JL-34) & Banshgara mouza (JL-38) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-26) |  |  | ORD/000271/2020-2021 | 1326/DWSD | 09/12/2020 | 45 | GHOSH ENTERPRISE | 12.83 | 25.55 | 0
2166 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kendua mouza (JL-36) & Chapabandhi (JL-37) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-27) |  |  | ORD/000272/2020-2021 | 1328/DWSD | 09/12/2020 | 45 | CHANDAN HAZRA | 11.53 | 19.43 | 0
2167 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bansol mouza (JL-49) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-28) |  |  | ORD/000273/2020-2021 | 1329/DWSD | 09/12/2020 | 45 | JOY GURU ENTERPRISE | 29.98 | 59.92 | 0
2168 | Durgapur W/S Division |  | Acceptance cum formal order for the work of additional laying of pipe line and repairing of damage road with concrete work at Sarpi (Mouza-35) under command area of retrofitting of improvement of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000273/2021-2022 | 1553/DWSD | 27/10/2021 | 20 | K.M. ENTERPRISE | 2.3 | 0 | 0
2169 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. (SL-29) |  |  | ORD/000274/2020-2021 | 1330/DWSD | 09/12/2020 | 45 | KIRON ENTERPRISE | 29.51 | 58.92 | 0
2170 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-A) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-30) |  |  | ORD/000275/2020-2021 | 1331/DWSD | 09/12/2020 | 45 | PRAVAT SARKAR | 33.89 | 67.46 | 0
2171 | Durgapur W/S Division |  | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000277/2021-2022 | 1643/DWSD | 23/11/2021 | 10 | PRAVAT SARKAR | 4.96 | 1.32 | 0
2172 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Water supply arrangement at Maheshpur village within Durgapur-Faridpur Block to combat waters crisis and protection of RCC Columns within Tumuni river near Jagannathpur village under DWSD, PHE Dte(SL-5) |  |  | ORD/000281/2021-2022 | 1572/DWSD | 27/10/2021 | 15 | M/S BADAL GHOSH | 1.98 | 0 | 0
2173 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Replacement of damage existing distribution pipe line with 75 mm UPVC line and necessary allied works at Loudoha village Palpara,Ghosh Para & Banerjee para under RCFA Pt-III W/s Scheme under DWSD ,PHE Dte (SL-3) |  |  | ORD/000283/2021-2022 | 1575/DWSD | 27/10/2021 | 15 | D. S. ENTERPRISE | 4.67 | 0 | 0
2174 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of cutting of concrete road with supplying ,laying of 160 mm dia OD HDPE pipe from Pump house to pond providing water to Roopganj and Arrah mouza and others allied works for providing FHTC of roopganj W/s Scheme under DWSD ,PHE Dte (SL-18) |  |  | ORD/000285/2020-2021 | 1350/DWSD | 09/12/2020 | 15 | M/S KALYANI ENTERPRISE | 3.09 | 6.16 | 0
2175 | Durgapur W/S Division |  | Formal order for the work of Providing additional number of FHTC in connection with JJM for Roopganj mouza(JL-91) with extension of branch pipe line at Roopganj and Arrah under command are a of Roopganj W/S Scheme at Kanksa block under DWSD ,PHE Dte |  |  | ORD/000295/2021-2022 | 1783/DWSD | 21/12/2021 | 30 | M/S KALYANI ENTERPRISE | 17.08 | 17.39 | 0
2176 | Durgapur W/S Division |  | Formal order for the work of Emergency repairing and restoration of distribution system from command are a of Jagannathpur OHR (Gopendanga ,Kalinagar,Jagannathpur,Kailashpur part) Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte. |  |  | ORD/000296/2021-2022 | 1778/DWSD | 20/12/2021 | 20 | M/S BADAL GHOSH | 5.54 | 0 | 0
2177 | Durgapur W/S Division |  | Formal for the work of Additional FHTC in connection with JJM at Hetedoba Mouza under command area of Gourbazar-Ichhapur piped W/S Scheme of Durgapur-Faridpur block under DWSD PHE Dte . |  |  | ORD/000297/2021-2022 | 1779/DWSD | 21/12/2021 | 25 | RANAJOY ENTERPRISE | 9.62 | 8.76 | 0
2178 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-E) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-01) |  |  | ORD/000305/2020-2021 | 1431/DWSD | 28/12/2020 | 60 | SWATI CORPARATION | 42.78 | 87.48 | 0
2179 | Durgapur W/S Division |  | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). |  |  | ORD/000305/2021-2022 | 1735/DWSD | 13/12/2021 | 10 | PRAVAT SARKAR | 4.97 | 0 | 0
2180 | Durgapur W/S Division |  | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Tilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000306/2021-2022 | 1663/DWSD | 25/11/2021 | 10 | AMARANJALI CONSTRUCTION | 4.97 | 0 | 0
2181 | Durgapur W/S Division |  | Continuation order for the work of Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000307/2021-2022 | 1662/DWSD | 25/11/2021 | 10 | BADAL GHOSH | 1.91 | 1.91 | 0
2182 | Durgapur W/S Division |  | Acceptance cum formal workorder for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-F) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-05) |  |  | ORD/000308/2020-2021 | 1434/DWSD | 28/12/2020 | 45 | TARA CONSTRUCTION | 27.72 | 56.89 | 0
2183 | Durgapur W/S Division |  | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Mahespur mouza (JL-12) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000308/2021-2022 | 1746/DWSD | 15/12/2021 | 10 | BADAL GHOSH | 3.96 | 3.96 | 0
2184 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Ijjatganj mouza (JL-71) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) |  |  | ORD/000310/2020-2021 | 1436/DWSD | 28/12/2020 | 25 | QUICK PAL SUPPLIERS | 5.93 | 11.78 | 0
2185 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Debipur mouza (JL-87) (Pt-B) under command area of Kanksa Zone-II (Ph-II) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-08) |  |  | ORD/000311/2020-2021 | 1437/DWSD | 28/12/2020 | 60 | M/S. D. PALIT & CO. | 42.74 | 57.64 | 0
2186 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhanagar mouza (JL-24) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-09) |  |  | ORD/000312/2020-2021 | 1338/DWSD | 28/12/2020 | 20 | THE STAR & CO | 5.48 | 10.92 | 0
2187 | Durgapur W/S Division |  | Formal for the work of Emergency provision of AC phtovoltaic submersible solar pump set within bore well tube well along with 2400 peak watt capacity soalr photovoltaic array on Ms structure with sinking of 150 mm dia tube well 90 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Kalinagar under GP-Pratabpur Block-Durgapur-Faridpur under DWSD, PHE Dte |  |  | ORD/000313/2021-2022 | 1776/DWSD | 20/12/2021 | 30 | M/S BADAL GHOSH | 11.69 | 0 | 0
2188 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Prayagpur mouza (JL-88) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000314/2020-2021 | 1439/DWSD | 28/12/2020 | 25 | DAS & CHAKRABORTY | 7.24 | 7.33 | 0
2189 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Satkahania mouza (JL-34) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-12) |  |  | ORD/000315/2020-2021 | 1440/DWSD | 28/12/2020 | 25 | SUBHADEEP DAS | 8.66 | 15.2 | 0
2190 | Durgapur W/S Division |  | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhamohanpur mouza (JL-36) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000316/2020-2021 | 1441/DWSD | 28/12/2020 | 25 | MD AAMIR KHAN | 13.53 | 27.39 | 0
2191 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudha mouza (JL-35) (Pt-B)under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000317/2020-2021 | 1442/DWSD | 28/12/2020 | 25 | SAIKAT RAY | 17.42 | 33.88 | 0
2192 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Jabber Pally ,Bansal Vadupara under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-A)(SL-04) |  |  | ORD/000317/2021-2022 | 1790/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 5 | 5 | 0
2193 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Dubrajpur,Sashipur,Benodpur,Sundipur,Talbahari,Srirampur Mouzas (JL-9,8,6,4,3,1)under command area of Kanchanpur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000318/2020-2021 | 1443/DWSD | 28/12/2020 | 30 | MACHINO TECHNO | 27.32 | 45.74 | 0
2194 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park ,Majhipara and Bouri Para under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-B)(SL-05) |  |  | ORD/000318/2021-2022 | 1791/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 4.93 | 4.92 | 0
2195 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) (Part-B) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000319/2020-2021 | 1445/DWSD | 28/12/2020 | 25 | GITA CONSTRUCTION | 17.07 | 27.86 | 0
2196 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park, DMC area of Vivekananda Nagar under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-C) (SL No-06) |  |  | ORD/000319/2021-2022 | 1792/DWSD | 23/12/2021 | 15 | JOY GURU ENTERPRISE | 4.96 | 4.93 | 0
2197 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Krishnapur mouza (JL-23) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000320/2020-2021 | 1447/DWSD | 28/12/2020 | 20 | THE STAR & CO | 5.63 | 11.17 | 0
2198 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Protapur mouza (JL-40) under Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte (SL-07) |  |  | ORD/000320/2021-2022 | 1793/DWSD | 23/12/2021 | 15 | JAYANTA DATTA | 4.56 | 4.54 | 0
2199 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-A) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) |  |  | ORD/000321/2020-2021 | 1448/DWSD | 28/12/2020 | 60 | GITA CONSTRUCTION | 42.61 | 76.74 | 0
2200 | Durgapur W/S Division |  | Acceptance cum Formal work-Order for the work of ---Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000322/2020-2021 | 1449/DWSD | 28/12/2020 | 25 | M/S BADAL GHOSH | 14.76 | 26.44 | 0
2201 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of laying 75 mm dia HDPE pipe line at Prayagpur canal Par in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-B) under DWSD ,PHE Dte (SL-09) |  |  | ORD/000322/2021-2022 | 1795/DWSD | 24/12/2021 | 15 | CHATTERJEE CONSTRUCTION | 3.26 | 3.33 | 0
2202 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying and laying of laying 75 mm dia HDPE pipe line at Prayagpur canal per in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-A) under DWSD ,PHE Dte (SL-10) |  |  | ORD/000323/2021-2022 | 1796/DWSD | 24/12/2021 | 15 | CHATTERJEE CONSTRUCTION | 4.98 | 5.01 | 0
2203 | Durgapur W/S Division |  | Formal order for the work of sinking 1 No. 250 mm X 150 mm dia tube well 90 mtr deep by DR method using PVC pipe and fiber glass reinforced epoxy resin slotted at Krishnapur H/W site (OHR) under Krishnapur W/s Scheme under Durgapur W/s Division, PHE Dte |  |  | ORD/000327/2020-2021 | 41/DWSD | 13/01/2021 | 10 | AMARANJALI CONSTRUCTION | 7.02 | 0 | 0
2204 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional distribution pipe line with necessary allied works for FHTC purpose at Jagannathpur gram,Jagganathpur Dangal para to Kailashpur upper para ,Kalinagar main road to upper para ,Gopendanga main road to Bagdi para under Improvement of Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000328/2021-2022 | 1802/DWSD | 27/12/2021 | 20 | M/S BADAL GHOSH | 3.99 | 3.99 | 0
2205 | Durgapur W/S Division |  | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) |  |  | ORD/000329/2021-2022 | 1803/DWSD | 28/12/2021 | 10 | M/S KALYANI ENTERPRISE | 2.32 | 0 | 0
2206 | Durgapur W/S Division |  | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000346/2021-2022 | 135/DWSD | 02/02/2022 | 15 | MD JAWED KHAN | 6.6 | 0 | 50
2207 | Durgapur W/S Division |  | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) |  |  | ORD/000347/2021-2022 | 140/DWSD | 03/02/2022 | 7 | SHWET BARANI | 13.62 | 0 | 0
2208 | Durgapur W/S Division |  | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) |  |  | ORD/000348/2021-2022 | 199/DWSD | 16/02/2022 | 15 | GITA CONSTRUCTION | 9.72 | 0 | 0
2209 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) |  |  | ORD/000354/2020-2021 | 72/DWSD | 13/01/2021 | 25 | MAK CONSTRUCTION CO. | 4.98 | 10.04 | 0
2210 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Matwangini more to Bhabandapur village road of Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000357/2021-2022 | 74/DWSD | 21/01/2022 | 20 | R.K.ENTERPRISE | 4.99 | 0 | 0
2211 | Durgapur W/S Division |  | Acceptance cum formal order for the work of repairing of existing distribution pipe line with 110 mm UPVC line and necessary allied works at Nakrakonda village under RCFA Pt-III W/s Scheme under DWSD, PHE Dte (SL-12) |  |  | ORD/000367/2021-2022 | 98/DWSD | 28/01/2022 | 15 | RANAJOY ENTERPRISE | 1.25 | 0 | 0
2212 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banguri mouza (JL-52) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000370/2020-2021 | 142/DWSD | 28/01/2021 | 30 | SUBHADEEP DAS | 7.7 | 6.82 | 0
2213 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Nabagram mouza (JL-22) having habitations Nabagram and Jambon within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000371/2020-2021 | 143/DWSD | 28/01/2021 | 30 | RANJIB GHATAK | 13.2 | 12.03 | 0
2214 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-B) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000373/2020-2021 | 145/DWSD | 28/01/2021 | 50 | M/S KALYANI ENTERPRISE | 36.43 | 32.48 | 0
2215 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-C) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000374/2020-2021 | 146/DWSD | 28/01/2021 | 45 | DARPAN DAS & CO. | 24.19 | 48.27 | 0
2216 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Trilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) |  |  | ORD/000375/2020-2021 | 155/DWSD | 28/01/2021 | 45 | AMARANJALI CONSTRUCTION | 21.66 | 43.26 | 0
2217 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-B) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000378/2020-2021 | 170/DWSD | 03/02/2021 | 45 | RANJIB GHATAK | 26.91 | 48.03 | 0
2218 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-B) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte .(SL-02) |  |  | ORD/000379/2020-2021 | 171/DWSD | 03/02/2021 | 25 | PRAVAT SARKAR | 37.43 | 63.5 | 0
2219 | Durgapur W/S Division |  | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) |  |  | ORD/000390/2021-2022 | 10/DWSD | 04/01/2022 | 15 | PRAVAT SARKAR | 4.84 | 0 | 0
2220 | Durgapur W/S Division |  | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte |  |  | ORD/000412/2021-2022 | 244/DWSD | 22/02/2022 | 25 | M/S BADAL GHOSH | 2.09 | 0 | 0
2221 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Laying of PVC pipe line at Shibpur Mouza (JL-20) and Nabagram Mouza (JL 22) in connection with FHTC under Krishnapur W/s Scheme under DWSD, PHE Dte.(SL-02) |  |  | ORD/000415/2020-2021 | 271/DWSD | 26/02/2021 | 10 | RANJIB GHATAK | 2.23 | 4.47 | 0
2222 | Durgapur W/S Division |  | Continuation for the work of providing functional household tap connection (FHTC) in connection with JJM at Srikrishnapur mouza (JL No-09),Baidayanathpur and Kailashpur(JL No-09/20/22) under Retrofitting of Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000415/2021-2022 | 266/DWSD | 04/03/2022 | 15 | JOY GURU ENTERPRISE | 3.6 | 3.58 | 0
2223 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Supplying of extra UPVC pipe line at different places of Kendua Hazra para ,Bouri para and Chapabandhi in connection of FHTC under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte.(SL-06) |  |  | ORD/000419/2020-2021 | 275/DWSD | 26/02/2021 | 20 | CHANDAN HAZRA | 2.89 | 5.08 | 0
2224 | Durgapur W/S Division |  | Acceptance cum formal order for the work of laying of PVC pipe line at Kailashpur village within Jagannathpur Mouza in connection with FHTC under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-07) |  |  | ORD/000420/2020-2021 | 276/DWSD | 26/02/2021 | 10 | M/S BADAL GHOSH | 2.07 | 4.13 | 0
2225 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-D) under DWSD,PHE Dte (SL-56) |  |  | ORD/000447/2020-2021 | 301/DWSD | 26/02/2021 | 30 | MANAS KUMAR SAHA | 4.31 | 8.62 | 0
2226 | Durgapur W/S Division |  | Acceptance cum formal order for the work Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-E) under DWSD,PHE Dte(SL-57) |  |  | ORD/000448/2020-2021 | 302/DWSD | 26/02/2021 | 30 | MANAS KUMAR SAHA | 4.98 | 9.96 | 0
2227 | Durgapur W/S Division |  | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa (Zone-II) Ph-II W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Prayagpur Mouza(JL-88)(Part-C) under DWSD,PHE Dte |  |  | ORD/000462/2020-2021 | 317/DWSD | 26/02/2021 | 30 | B. T. M. CONCERN | 4.98 | 4.98 | 0
2228 | Durgapur W/S Division |  | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna |  |  | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 29.28 | 100
2229 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000022/2021-2022 | 959/RCD-I | 07/06/2021 | 30 | JAYANTA DATTA | 23.01 | 4.02 | 0
2230 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000023/2021-2022 | 960/RCD-I | 07/06/2021 | 30 | M/S MONDAL ENTERPRISE | 23 | 40.38 | 0
2231 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000024/2021-2022 | 961/RCD-I | 07/06/2021 | 30 | S. CHAKRABORTY & CO. | 22.97 | 45.64 | 0
2232 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000062/2021-2022 | 1148/RCD-I | 22/07/2021 | 30 | GITA CONSTRUCTION | 22.58 | 45.26 | 0
2233 | RCFA Division -I | RCFA Division I | Formal Work Order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) near Kanskuli DAM for dedicated pipe line towards Kanskuli village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000078/2023-2024 | 1772/RCD-I | 18/05/2023 | 15 | SRI KRISHNA ENTERPRISE | 4.37 | 4.37 | 0
2234 | RCFA Division -I | RCFA Division I | Emergency for providing balance FHTC through retrofitting at Shamdi G.P. area and Chayanpur and adjacent villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 1 | Junior Engineer | ORD/000211/2022-2023 | 1980/RCD I | 24/08/2022 | 15 | KHEPI MAA TRADERS | 4.54 | 4.04 | 0
2235 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kirtansala (part) and Dharaspur village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 11) | Assistant Engineer 1 | Junior Engineer | ORD/000572/2021-2022 | 254/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.95 | 4.76 | 0
2236 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000017/2025-2026 | 2535/RCD-I | 01/09/2025 | 0 | Resource Division | 4.99 | 0 | 0
2237 | RCFA Division -I | Asansol Mechanical Division | Shifting of office of the Executive Engineer, Durgapur W/s Division, PHE Dte, ADDA Administrative Building, EPIP Complex, Banskopa, Durgapur-12 to Nababhat, PHE Complex, Purba Bandhaman under Augmentation of Kataberia PWSS, Augmentation of Telipara under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/001150/2023-2024 | 3516/RCD-I | 01/12/2023 | 15 | AMARANJALI CONSTRUCTION | 3.83 | 3.83 | 100
2238 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte (SL-11) | Assistant Engineer-II | Junior Engineer-5 | ORD/000001/2023-2024 | 578/DWSD | 10/04/2023 | 45 | M/S MANDAL ENTERPRISE | 6.84 | 6.84 | 100
2239 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Khatgoria mouzas JL-29 (Part-B) under command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000002/2023-2024 | 580/DWSD | 10/04/2023 | 40 | SAIKAT RAY | 96.67 | 76.26 | 100
2240 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m witch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -I of Kataberia piped W/s Scheme under DWSD PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000003/2023-2024 | 581/DWSD | 10/04/2023 | 45 | MAJI DEVELOPERS | 6.92 | 0 | 100
2241 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria of Kataberia piped W/s Scheme pump house -II under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000005/2023-2024 | 585/DWSD | 11/04/2023 | 45 | SIL ENTERPRISE | 14.8 | 14.74 | 100
2242 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying ,laying and aligning of Hoped distribution pipe line and allied works including FHTC tap connection and connection & providing to Khatgoria Mouzas JL-29 (Part-C) under Command area of Kataberia pipe W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000006/2023-2024 | 586/DWSD | 11/04/2023 | 45 | TARA PRASAD SARKAR | 94.91 | 80.73 | 80
2243 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work for water supply arrangement for 1(One) No SLWM center at Bargoria and burning ghat at Bargoria ,Block-Durgapur-Faridpur for having no electricity with solar power connection including pipe line works and other allied works under proposed piped W/S Scheme for Kataberia under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000044/2023-2024 | 770/DWSD | 22/05/2023 | 30 | BHUMIKA ENTERPRISE | 7.46 | 7.46 | 0
2244 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Labnapara under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 01) | Assistant Engineer-II | Junior Engineer-5 | ORD/000133/2023-2024 | 1179/DWSD | 24/07/2023 | 15 | GHOSH & ROY ENTERPRISE | 1 | 1 | 100
2245 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Kataberia under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 02) | Assistant Engineer-II | Junior Engineer-5 | ORD/000134/2023-2024 | 1191/DWSD | 25/07/2023 | 15 | GHOSH & ROY ENTERPRISE | 1 | 1 | 100
2246 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying installation of 4(Four) Nos Centrifugal pumping machinery of 1 Hp for providing port water for existing Stand alon at Jamgora under Kataberia piped W/s Scheme under DWSD,PHE Dte. (Sl- 03) | Assistant Engineer-II | Junior Engineer-5 | ORD/000135/2023-2024 | 1178/DWSD | 24/07/2023 | 15 | GOUTAM GHOSH | 1 | 1 | 100
2247 | Durgapur W/S Division | Asansol Mechanical Division | Sinking of 2 (Two) Nos 300X200X210 m depth by Direct reverse rotary method using UPVC pipe (CD) deep well screen (RDS) at Kataberia H/W site TW No-I site of Durgapur-Faridpur Block under PROPOSED GROUND WATER BASED WATER SUPPLY SCHEME FOR KATABERA, UNDER DURGAPUR W/S DIVISION , BLOCK : FARIDPUR-DURGAPUR, DISTRICT : PASCHIM BARDDHAMAM(SM/16249) | Assistant Engineer-II | Junior Engineer-5 | ORD/000073/2023-2024 | 1072/DWSD | 12/07/2023 | 30 | KIRON ENTERPRISE | 29.66 | 28.23 | 60
2248 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 1 no Tubewell for Triat Bore 150 mm. big dia. Tube wel 90 mtr deep by Direct Rotary Rig methed at Akandara for Jem Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte.(Sl-02) | Assistant Engineer-II | Junior Engineer-5 | ORD/000226/2023-2024 | 48-SPOT/DWSD | 03/07/2023 | 15 | M/S BADAL GHOSH | 1 | 1 | 100
2249 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Cleaning the chokage of different dia pipeline at Gourbazar area under Durgapur W/S Divn,PHE Dte (Sl- 02) | Assistant Engineer-II | Junior Engineer-5 | ORD/000227/2023-2024 | 1392/DWSD | 16/08/2023 | 10 | GHOSH & ROY ENTERPRISE | 0.99 | 0.99 | 100
2250 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Khatgoria H/W (OHR) site of land development approach road and others allied works of Kantaberia Piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000580/2022-2023 | 491/DWSD | 24/03/2023 | 45 | GHOSH & ROY ENTERPRISE | 33.88 | 33.34 | 100
2251 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Constructions of 5.40 X 3.6 m switch room with plinth height (600 X 2000 mm ) with sanitary and water supply arrangement at Kataberia TW no -II of Kataberia piped W/s Scheme under DWSD PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000581/2022-2023 | 495/DWSD | 24/03/2023 | 45 | M/S MONDAL ENTERPRISE | 6.84 | 0 | 0
2252 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution system with construction of 150 M3 capacity 20 mtr staging height RCC OHR including pipe connection and soil investigation at Kataberia piped W/s Scheme under DWSD PHE Dte (SL-9) | Assistant Engineer-II | Junior Engineer-5 | ORD/000594/2022-2023 | 499/DWSD | 27/03/2023 | 827 | M/S K.B.CONSTRUCTION | 99.75 | 50.33 | 55
2253 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of laying and aligning of DI K9 R/M pipe line supplying DI specials valves and allied works under Command area of Kataberia piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000603/2022-2023 | 500/DWSD | 27/03/2023 | 30 | KANJILAL & CO. | 18.3 | 4.08 | 60
2254 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works including FHTC and connection providing to Kataberia mouzas JL-50 part-A under command area of augmentation of Kantaberia & Bistupur piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-5 | ORD/000606/2022-2023 | 504/A/DWSD | 28/03/2023 | 40 | BISHAL ENTERPRISE | 78.86 | 74.88 | 100
2255 | Asansol Mechanical | Asansol Mechanical Division | QUOTATION MONEY FOR NEW CONNECTION AT KANTABERIA. | Assistant Engineer-II | Junior Engineer-5 | BILL/00024/2023-2024 | BP-2023-24-3 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.3 | 0 | 0
2256 | Asansol Mechanical | Asansol Mechanical Division | QUOTATION MONEY FOR NEW CONNECTION AT KHATGORIA | Assistant Engineer-II | Junior Engineer-5 | BILL/00025/2023-2024 | BP-2023-24-4 | 19/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0
2257 | Asansol Mechanical | Asansol Mechanical Division | New Connection at Kantabeira RBTW | Assistant Engineer-II | Junior Engineer-5 | BILL/00840/2024-2025 | BP-2024-25-74 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.37 | 0 | 0
2258 | Asansol Mechanical | Asansol Mechanical Division | Service Connection Charge at Kantaberia. | Assistant Engineer-II | Junior Engineer-5 | BILL/00939/2023-2024 | BP-2023-24-84 | 14/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.28 | 0 | 0
2259 | Asansol Mechanical | Asansol Mechanical Division | Service Connection Charge at Khatagoria under Katabera. | Assistant Engineer-II | Junior Engineer-5 | BILL/00940/2023-2024 | BP-2023-24-85 | 14/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0
2260 | Asansol Mechanical | Asansol Mechanical Division | Supply, delivery & installation of Submersible Pumping Machineries, Chlorinator and other allied materials for TubeWell No-I, II under Kantaberia Piped Water Supply Scheme, Block-Faridpur-Durgapur, District-Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-5 | ORD/000040/2023-2024 | 1023/AMD | 19/04/2023 | 714 | M/S SWAPAN BANERJEE | 22.85 | 5.66 | 100
2261 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY & INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-05 AND OTHER ALLIED WORKS FOR T/W-01 AT KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASSANSOL MECHANICAL DIVISION, PHE DTE.,BLOCK-DURGAPUR-FARIDPUR, DIST.- PASCHIM-BARDHAMAN | Assistant Engineer-II | Junior Engineer-5 | ORD/000278/2024-2025 | 1680/AMD | 04/10/2024 | 157 | M/S SWAPAN BANERJEE | 18.46 | 0 | 90
2262 | Asansol Mechanical | Asansol Mechanical Division | Providing of lighting luminaries, electrical wiring of chlorine room with yard lighting arrangement of Kantaberia O.H.R. premises under Katabera W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000280/2024-2025 | 1673/AMD | 04/10/2024 | 30 | SARVATAH PROJECTS PRIVATE LIMITED | 6.28 | 0 | 0
2263 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATIONF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-6 AT AUGMENTATION KANTABERIA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-5 | ORD/000359/2024-2025 | 1924/AMD | 19/11/2024 | 293 | R.M.D. TRADING | 11.76 | 0 | 100
2264 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional works for distribution network for RBTW water based water supply scheme for Sarpi and its joining mouza (Part-C) at Arati village including FHTC & allied works AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II Durgapur-Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000065/2024-2025 | 1795/RCD-I | 24/07/2024 | 45 | M/S BADAL GHOSH | 44.53 | 37.53 | 100
2265 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional pipe line from Madhaiganj to Jamdoba Adibasi Para including re-connection of FHTC under Augmentation of Amlajora Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000290/2024-2025 | 2629/RCD-I | 14/11/2024 | 90 | M/S BADAL GHOSH | 37.59 | 9.44 | 100
2266 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of laying distribution system, rising main, construction of 250 cum reservoir with 20 mtr staging height including soil investigation, construction of pump house (5.40 m x 3.60 m) with sanitary & W/S arrangement & construction of pump house (3.60 m x 3.00 m) for Amlajora W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000320/2025-2026 | 1424/RCD-I | 15/05/2025 | 90 | RANADHIR SINHA | 59.19 | 0 | 70
2267 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Additional work for covering isolated area beyond the NH2 by creating a 2 (Two) nos separate zone under command area of Amlajora PWSS at the embankment of Durgapur Panagarh DVC branch canal situated in between DVC branch canal to Kol-Del Railway track and Biharpur Gram with sinking of 2 nos tube well 300 x 200 mm dia, Construction of Pump House cum/Switch room 5.4 m x 3.6 and laying of LDS with necessary inter connection including all others works of Amlajora PWSS under Augmentation of Amlajora Piped W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000390/2024-2025 | 3191/RCD-I | 23/12/2024 | 90 | RANADHIR SINHA | 156.64 | 0 | 40
2268 | RCFA Division -I | Asansol Mechanical Division | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/001040/2022-2023 | 326/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 81.29 | 81.06 | 100
2269 | RCFA Division -I | Asansol Mechanical Division | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) underAUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/001237/2023-2024 | 1074/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 18.4 | 0 | 0
2270 | Durgapur W/S Division | Asansol Mechanical Division | Quotation from WBSEDCL for new service connection for Shilampur under Augmentation of Amlajora PWSS ,Kaksa | Assistant Engineer-II | Junior Engineer-3 | BILL/00757/2023-2024 | BP-2023-24-367 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.27 | 0 | 0
2271 | Durgapur W/S Division | Asansol Mechanical Division | Dismantling of concrete road and bitumunious road for balance work of laying distribution system ,RM construction of 250 M3 OHR including soil investigation ,construction of Pump house (5.40X3.60 with sanitary and water supply arrangment etc of pump house (3.6X3m) for Amlajora W/s scheme of DWSD,PHE Dte(SM/11937) | Assistant Engineer-II | Junior Engineer-3 | ORD/000075/2023-2024 | 1070/DWSD | 12/07/2023 | 20 | RANADHIR SINHA | 28.91 | 28.9 | 100
2272 | Durgapur W/S Division | Asansol Mechanical Division | Laying and aligining rising main pipe line supplying DI Specials valves and other allied works at Amlajora of Augmentation of Amlajora piped W/s Scheme (SM/11937) | Assistant Engineer-II | Junior Engineer-3 | ORD/000082/2023-2024 | 1075/DWSD | 12/07/2023 | 30 | RANADHIR SINHA | 35.91 | 34.69 | 100
2273 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Near Canalpar) , TUBE WELL NO-4 (Biharpur) and TUBE WELL NO-5 AT AMLAJORA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000474/2024-2025 | 1889/AMD | 12/11/2024 | 30 | DEY ENTERPRISE | 37.85 | 0 | 0
2274 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 450 M3 OHR of 20 mtr staging height including soil testing construction of pump house (5.40X 3.60 m) with Sanitary arrangement and construction of pump house )3.60 X 3.00 m) of Augmentation of Amlajora piped W/s Scheme under DWSD ,PHE Dte . | Assistant Engineer-II | Junior Engineer-3 | ORD/000024/2023-2024 | 785/DWSD | 23/05/2023 | 678 | RANADHIR SINHA | 387.89 | 375.86 | 100
2275 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Dismantling of concrete road for laying distribution system rising main construction of 350 M3 reservoir with 20 mtr staging height including soil investigation construction of pump house (5.40 X 3.60 m) with sanitary and construction of pump house 3.60 X 3.00 m) for Amlajora piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000569/2022-2023 | 488/DWSD | 23/03/2023 | 15 | RANADHIR SINHA | 5.99 | 5.99 | 0
2276 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of construction of Pump house /Chlorine room sinking of 150X80 X120 mm depth tube well supplying laying of HDPE distribution pipe in and providing FHTC at Garadaha mouzas of Garadaha piped W/S scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000023/2023-2024 | 734/DWSD | 15/05/2023 | 687 | SHWET BARANI | 102.39 | 44.95 | 45
2277 | Central Mechanical | Asansol Mechanical Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Garadaha Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000003/2023-2024 | 1577/CMD | 04/04/2023 | 30 | RAJIB COMPANY | 8.97 | 8.17 | 100
2278 | Central Mechanical | Asansol Mechanical Division | Supply & Delivery of Pump Motor Set at TW No: 01 of Garadaha water supply scheme under CMD, PHE, Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001164/2023-2024 | 112/DIC/BMSD(D) | 04/10/2023 | 15 | RAJIB COMPANY | 0.52 | 0.52 | 100
2279 | Asansol Mechanical | Asansol Mechanical Division | Supply and Installation of Submersible Pumping Machinery and Internal House Wiring for Tube Well No-02 At augmentation of Garadaha Piped Water Supply Scheme under Asansol Mechanical Division, PHE Dte, Block- Kanksa, Dist- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000448/2024-2025 | 2115/AMD | 16/12/2024 | 30 | V. P. CONCERN | 4.93 | 0 | 0
2280 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction 02 Nos pump house construction of 150 M3 OHR of 20 Mtr staging height as per Deptt drawing laying aligning of rising main and providing FHTC connection of all mouzas under Command area of Augmentation Dandeswar piped W/s Scheme under DWSD, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000221/2023-2024 | 796/DWSD | 24/05/2023 | 678 | POWER TOOLS AND ENGINEERING | 122.46 | 94.34 | 80
2281 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of balance work for supplying and laying of HDPE distribution pipe line construction of pipe carrying structure and allied works at Railpar of Prayagpur mouza under AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR DANDESHWAR, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/000504/2022-2023 | 320/DWSD | 20/02/2023 | 20 | SAIKAT RAY | 87.4 | 72.2 | 100
2282 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for laying of HDPE pipe line and providing FHTC in connection with JJM at Arrah mouza (JL-89) under command area of Augmentation of Dandeswar piped W/s Scheme under DWSD ,PHE Dte (Part-B) | Assistant Engineer-II | Junior Engineer-3 | ORD/000509/2022-2023 | 326/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 81.29 | 0 | 50
2283 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Route survey and preparation of DPR for Augmentation of Jatgoria ,Napara and Dandeswar piped W/s Scheme and Kataberia PWSS under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000566/2022-2023 | 529/DWSD | 29/03/2023 | 15 | MEASURE LAND | 6.74 | 6.74 | 0
2284 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells in the river Ajoy at Bhaburia Head Work Site under Augmentation of ground water based water supply scheme for Basudha Piped Water Supply Scheme (JJM) under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000191/2024-2025 | 2443/RCD-I | 30/09/2024 | 166 | MACHINO TECHNO | 12.11 | 3.04 | 100
2285 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 nos 200 mm dia River Bed Tube Wells in the River Ajoy at Bhaburia Head Works Site under Basudha PWSS W/S Scheme (JJM) under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-3 | ORD/000215/2025-2026 | 1437/RCD-I | 15/05/2025 | 28 | MD AAMIR KHAN | 11.99 | 0 | 100
2286 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Improvement & Overhauling of 2 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Basusha H/W site & at Krishnapur of Augmentation of Ground Water Based Water Supply Scheme for Basudha under RCFA W/S Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000251/2024-2025 | 2614/RCD-I | 13/11/2024 | 30 | RUPALI ELECTRONICS | 12.85 | 12.78 | 100
2287 | RCFA Division -I | Asansol Mechanical Division | Formal work order for sinking of 02(two) nos TW. FHTC,laying Rising main & laying distribution system(LDS) construction of boundary wall, pump house and restoration of road & and other allied works for Augmentation of ground water based W/S scheme for Basudha under RCFA Division-I, PHE Dte. Block-Kanksa, Dist- Paschim Bardhaman, | Assistant Engineer-II | Junior Engineer-3 | ORD/001015/2023-2024 | 559/RCD-I | 21/02/2024 | 130 | MRITYUNJOY MUKHERJEE & CO. | 209.86 | 164.5 | 90
2288 | Asansol Mechanical | Asansol Mechanical Division | Quotation Payment for Basudha T/W No-3, under Kanksa Block, Paschim Bardhaman as per WBSEDCL Procedure-A(2010) on Turn-Key/Full Deposit Basis. | Assistant Engineer-II | Junior Engineer-3 | BILL/00025/2024-2025 | BP-2024-25-6 | 24/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.7 | 0 | 0
2289 | Asansol Mechanical | Asansol Mechanical Division | Providing & fitting, fixing of lighting luminaries of pump house with yard lighting arrangement and other allied works at Basudha Pump House No-03 (OHR Site) under Augmentation of Basudha Water Supply Scheme, Block-Kanksa, Dist.- Paschim Bardhaman under Asansol Mechanical Division, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000026/2025-2026 | 946/AMD | 16/05/2025 | 30 | CIEMENICS | 4.4 | 0 | 0
2290 | Asansol Mechanical | Asansol Mechanical Division | Supply and installation of submersible pumping machinery, voltage stabilizer, chlorination system and internal house wiring of augmentation of basudha water supply scheme p/h no-03 under Asansol Mechanical Division, PHE Dte., Dist.- Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer-3 | ORD/000136/2024-2025 | 1321/AMD | 21/08/2024 | 133 | PESTCO INDIA | 12.03 | 0 | 100
2291 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATIONOF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 AT AUGMENTATION OF BASUDHA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer-3 | ORD/000325/2024-2025 | 1818/AMD | 29/10/2024 | 30 | M/S A.D.ENTERPRISE | 11.61 | 0 | 0
2292 | RCFA Division -I | Asansol Mechanical Division | Restoration of Concrete road of Gopalpur & surrounding area under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000144/2024-2025 | Camp-02-Gopalpur-AE-2024- | 02/09/2024 | 10 | M/S CHANDI CHARAN ROY | 9.5 | 9.49 | 100
2293 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying of pipe line (Left Out) with HDPE pipe with FHTC at Prayagpur & Palpara within command area of Kanksa Zone-II/B PWSS with re connection of existing FHTC and other allied works of Augmentation of Ground Water Based Water Supply Scheme for Bamunara under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000218/2025-2026 | 1440/RCD-I | 15/05/2025 | 30 | MD AAMIR KHAN | 33.95 | 0 | 100
2294 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Creating at 3 (Three) nos Separate Zone of Bamunara PWSS at Banskopa Toll Plaza to Rajbundh Railway Station, Rajbundh Choti, EPIP area of Banskopa mouza and Gopalpur mouza part (40%) situated between NH2 to Kolkata ¿ Delhi Railway track with sinking of 2 nos 300 x 200 mm dia, 01 no 150 x 150 mm dia Tubewell, Construction of Pump House cum Switch Room 5.40 x 3.60 mtr and LDS with necessary interconnection including all others works of Bamunara PWSS under Augmentation of Bamunara Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000391/2024-2025 | 3190/RCD-I | 23/12/2024 | 180 | HANNAN BUILDERS PVT. LTD. | 216.57 | 0 | 45
2295 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Flow control of rising main and different dia distribution system by regulating apparatus for Augmentation of Ground Water Based Water Supply Scheme for Bamunara under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000401/2025-2026 | 1778/RCD-I | 19/06/2025 | 20 | MAKALI ENGINEERING CORPORATION | 60.83 | 0 | 100
2296 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Construction of 350 cum OHR at Arrah Sibtala, Block-Kanksa Dist - Paschim Bardhaman under Augmentation of Bamunara W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000916/2023-2024 | 210/RCD-I | 29/01/2024 | 60 | AMARANJALI CONSTRUCTION | 39.01 | 7.74 | 65
2297 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Acceptance order for Sinking of 02 (Two) no.s TW, FHTC, Laying Rising main & laying distribution system(LDS) construction of boundary wall, Pump House and restoration of road & other allied works for Augmentation of ground water based Bamunara PWSS under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/001079/2023-2024 | 809/RCD-I | 14/03/2024 | 413 | RANJIB GHATAK | 91.37 | 0 | 90
2298 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Approach road & others necessary allied works at Madhabmat front gate to village road for Kanksa Zone-II/A W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000015/2023-2024 | 679/DWSD | 03/05/2023 | 45 | SAIKAT RAY | 28.31 | 27.4 | 100
2299 | Durgapur W/S Division | Asansol Mechanical Division | Additional work of supplying and laying of different dia HDPE pipe line with necessary allied works at Silampur(JL-90) block-Kanksa under Augmentation of Kanksa Zone-I piped W/S scheme under DWSD,PHE Dte (SM/10208) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000081/2023-2024 | 1077/DWSD | 12/07/2023 | 35 | MAK CONSTRUCTION CO. | 96.46 | 5.3 | 45
2300 | Durgapur W/S Division | Asansol Mechanical Division | Special renovation work for modifying of existing structure under JJM at Ijjatganj 2 No pump house site including go down and guard room as well as boundary wall of Augmentation of Kanksa Zone-II/C piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000122/2023-2024 | 1196/DWSD | 27/07/2023 | 30 | MUKHERJEE ENTERPRISE | 15.31 | 12.32 | 100
2301 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Repairing of existing concrete road restoration and other allied works under Augmentation of Bamunnara piped W/s Scheme under DWSD,PHE Dte (Part-E) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000152/2023-2024 | 1283/DWSD | 07/08/2023 | 15 | AHS R INFRA PRIVATE LIMITED | 9.13 | 9.13 | 100
2302 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Balance work of supplying and laying of HDPE distribution system with construction of 02 Nos Pump house ,Construction of 450 M3 OHR of 20 mtr staging height including soil testing construction of pump house (5.40X 3.60 m) with Sanitary arrangement and construction of pump house )3.60 X 3.00 m) of Augmentation of Bamunara piped W/s Scheme under DWSD ,PHE Dte . | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000103/2023-2024 | 1148/DWSD | 20/07/2023 | 573 | HANNAN BUILDERS PVT. LTD. | 498.67 | 426 | 100
2303 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of creating a separate zone for BAMUNNARA of Bamunara piped W/S Scheme with construction of Pump house /Chlorine room Sin king of 1500 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Amlajora (64), Gopalpur(CT)(65) Mouza under Augmentation of BAMUNNARA piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000106/2023-2024 | 1141/DWSD | 20/07/2023 | 866 | AHS R INFRA PRIVATE LIMITED | 96.38 | 91.18 | 100
2304 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000108/2023-2024 | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0
2305 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Preparation and Submission of DPR for Augmentation of BAMUNARA (PART - B) under DURGAPUR-FARIDPUR Block under Durgapur Water Supply Division, P.H.E Dte. (Sl No-01) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000182/2023-2024 | 1193/DWSD | 25/07/2023 | 7 | MEASURE LAND | 0.78 | 0.78 | 100
2306 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works plinth protection ,roof treatment ,drain and other allied works at Sarada Pally H/W Site Pump house No-1 &T.W-01(OHR site) for Augmentation of Kanksa (Zone-II/D) pipe W/S Scheme under DWSD,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000198/2022-2023 | 1060/DWSD | 08/07/2022 | 25 | GHOSH & ROY ENTERPRISE | 4.82 | 1.5 | 100
2307 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional work for supplying ,laying and alinging of HDPE distribution pipe line and allied works at Railpar Saroda Pally of Kanksa mouza under command area of Augmentation of Kanksa piped W/s Scheme under DWSD ,PHE Dte (Part-B) | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000479/2022-2023 | 318/DWSD | 20/02/2023 | 800 | AMARANJALI CONSTRUCTION | 60.53 | 24.4 | 80
2308 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangement at OHR site Arrah Shibtala of Augmentation of Bamunara piped W/S Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000506/2022-2023 | 323/DWSD | 20/02/2023 | 30 | NANDADULAL KONAR | 6.92 | 6.92 | 100
2309 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Arrah H/W site OHR site ,Land development ,approach road and other allied works of Bamunara piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000511/2022-2023 | 328/DWSD | 20/02/2023 | 35 | AMARANJALI CONSTRUCTION | 30.43 | 0 | 0
2310 | Durgapur W/S Division | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000007/2023-2024 | 1557/DWSD | 20/09/2023 | 0 | Resource Division | 20.93 | 0 | 0
2311 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL Procedure-A (2010) for the site of Bamunara TW No.-03, Rajbandh Uttarpara. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00586/2024-2025 | BP-2024-25-66 | 28/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.91 | 0 | 0
2312 | Asansol Mechanical | Asansol Mechanical Division | Quotation payment as per WBSEDCL Procedure-A (2010) for Pump House No 5, under Augmentation of Bamunara Water Supply Scheme, near Rajbadh Choti, Block- Kanksa, Paschim Bardhaman. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00834/2024-2025 | BP-2024-25-71 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0
2313 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL procedure-A (2010) on Turn-key/full deposit basis for the site of Bamunara T.W -04, Baskopa. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | BILL/00907/2024-2025 | BP-2024-25-78 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.03 | 0 | 0
2314 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY, DELIVERY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-3 (Rajmath Uttarpara), TUBE WELL NO-4 (Banskopa) , and TUBE WELL NO-5 (Rajbandh) AT BAMUNARA PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000324/2024-2025 | 1817/AMD | 29/10/2024 | 30 | M/S SAJAHAN CHOWDHURY | 34.88 | 0 | 0
2315 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of CWR (200 cum capacity) and allied work at Madhaiganj OHR site under Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000023/2024-2025 | 1538/RCD-I | 19/06/2024 | 286 | B.T.M. CONCERN | 37.18 | 0 | 100
2316 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of Laying distribution system within distribution network for Rangamati of Augmentation of Ground Water Based Water Supply Scheme for Bistupur under Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000044/2024-2025 | 1645/RCD-I | 04/07/2024 | 45 | BASANTI TRADERS | 18.35 | 4.71 | 50
2317 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur Bazar (Left Side) of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000188/2025-2026 | 1363-RCD-I | 15/05/2025 | 78 | DAWN CONSTRUCTION | 40.06 | 0 | 100
2318 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Right including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000189/2025-2026 | 1362-RCD-I | 15/05/2025 | 60 | UNITED CONSTRUCTION | 61.57 | 0 | 100
2319 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Kuldiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000218/2024-2025 | 2551/RCD-I | 28/10/2024 | 240 | TARA CONSTRUCTION | 50.54 | 0 | 25
2320 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of Supplying, laying and aligning of HDPE distribution pipe line / rising main & allied works at Bistupur Head Works Site and Saraswatingunj command area of Bistupr PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000246/2025-2026 | 1468/RCD-I | 15/05/2025 | 170 | MRITYUNJOY MUKHERJEE & CO. | 79.35 | 0 | 70
2321 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional 1 no sinking of 300 x 200 mm dia& distribution pipe line with interconnection for GopalpurNamoparaAdibasipara at ChatallidangaGosaidanga, Dangapara, Dhoadanga for Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000256/2025-2026 | 1478/RCD-I | 15/05/2025 | 60 | RANJIB GHATAK | 73.79 | 0 | 0
2322 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Crossing 200 mm dia MS pipes under Highway by Jack Pushing Technology at different spots pushing different dia MS pipe at Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000265/2025-2026 | 1487/RCD-I | 15/05/2025 | 60 | MRITYUNJOY MUKHERJEE & CO. | 67.58 | 0 | 100
2323 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of supplying laying and aligning of HDPE distribution pipe line & allied works including Function House Hold Tap Connection (FHTC) and re concoction at Ghatakdanga, Akandara and Saraswatigunj under command area of Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000266/2025-2026 | 1488/RCD-I | 15/05/2025 | 170 | MACHINO TECHNO | 44.86 | 0 | 50
2324 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Rakshitpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000293/2024-2025 | 2627/RCD-I | 14/11/2024 | 352 | MACHINO TECHNO | 70.46 | 0 | 20
2325 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Creating separate zone with pipe & additional FHTC including Water sources at Chua Adhibasipara under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000296/2024-2025 | 2639/RCD-I | 14/11/2024 | 352 | MRITYUNJOY MUKHERJEE & CO. | 20.41 | 2.35 | 50
2326 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur (Right Side) including Paschimpara, Bauripara, Generalparaof Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000329/2025-2026 | 1515/RCD-I | 20/05/2025 | 227 | UNITED CONSTRUCTION | 38.56 | 0 | 80
2327 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Left including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000330/2025-2026 | 1516/RCD-I | 20/05/2025 | 60 | UNITED CONSTRUCTION | 70.8 | 0 | 100
2328 | RCFA Division -I | Asansol Mechanical Division | Construction of Separate Zone at Pathardiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000369/2024-2025 | 3097/RCD-I | 13/12/2024 | 313 | T M CONCRETE CREATION PVT.LTD | 45.89 | 0 | 40
2329 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction Boundary Wall at Bistupur H/W Site Pump House no 1 Tube well No. 1 under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000376/2024-2025 | 3104/RCD-I | 13/12/2024 | 60 | RANA ENTERPRISE | 15.43 | 0 | 0
2330 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Keshabpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000632/2024-2025 | 318/RCD-I | 12/02/2025 | 262 | MRITYUNJOY MUKHERJEE & CO. | 22.9 | 0 | 80
2331 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying of pipe line (Left out) with HDPE pipe including FHTC within command area of Kanksa Zone-I PWSS with reconnection of existing FHTC and other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000705/2024-2025 | 445/RCD-I | 12/03/2025 | 60 | MAK CONSTRUCTION CO | 78.15 | 0 | 72
2332 | RCFA Division -I | Asansol Mechanical Division | Formal work order for creating separate zone for Amlajora, supplying, laying of HDPE distribution pipeline and other allied works at Sarpi, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), construction of 5.40 X 3.6 meter switch room including additional concreting of exition dismantled road after extension of pipeline and retrofitting of existing distribution system under RBT Sarpi PWSS, Augmentation of Gopalpur & Bistupur PWSS and Amlajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001013/2023-2024 | 548/RCD-I | 20/02/2024 | 599 | HIRANMAY GHOSH | 200.38 | 59.65 | 40
2333 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part B under Augmentation of Bistupur Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/001233/2023-2024 | 1292/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 6.02 | 6.02 | 100
2334 | Durgapur W/S Division | Asansol Mechanical Division | Road restoration with demand of fund for different road stretches within Bistupur under Augmentation of Bistupur piped W/s Scheme under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | BILL/00205/2023-2024 | BP-2023-24-114 | 28/07/2023 | 0 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 28.83 | 0 | 0
2335 | Durgapur W/S Division | Asansol Mechanical Division | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) | Assistant Engineer-II | Junior Engineer-3 | ORD/000079/2023-2024 | 1079/DWSD | 12/07/2023 | 30 | MRITYUNJOY MUKHERJEE AND CO | 9.9 | 9.75 | 99
2336 | Durgapur W/S Division | Asansol Mechanical Division | Additional work of supplying and laying of different dia HDPE distribution pipe line and allied works under command area of Augmentation of Bistupur piped W/S scheme under DWSD,PHE Dte (SM/08877) (Part-B) | Assistant Engineer-II | Junior Engineer-3 | ORD/000080/2023-2024 | 1078/DWSD | 12/07/2023 | 20 | MRITYUNJOY MUKHERJEE AND CO | 9.91 | 9.86 | 99
2337 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Construction of 450 cum OHR, Laying, Aligning of DI (K9) Rising main (22 km) Pipe line and interconnection between rising main with OHR 2 nos House at Madhaiganj and Bhaburia H/W site and other allied works of RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC under Augmentation of Bistupur PWSS in Durgapur-Faridpur Block, Dist-Paschim Bardhaman under Durgapur W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001232/2023-2024 | 126_RCD_I | 16/01/2024 | 834 | GITA CONSTRUCTION | 305.57 | 124.71 | 100
2338 | Durgapur W/S Division | Asansol Mechanical Division | Balance work for installation of solar pumping machineries including solar pannel and other allied works for 6 Nos ICDS/AWC/School at Labnapara Bouripara,Pratabpur ICDS ,Jamgora Nichupara Bagdipara,Pratabpur Bus stands and pangar FP school ICDS and Kailashpur 52 ICDS under providng running water supply to ICDS/School ,HCF and other Public Ins of Kanksa and Durgapur-Faridpur Block under Retrofitting of Jemua Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/000072/2023-2024 | 1059/DWSD | 12/07/2023 | 30 | JOY GURU ENTERPRISE | 19.4 | 0 | 0
2339 | Durgapur W/S Division | Asansol Mechanical Division | Balance work for laying and alinging of DI K9 rising main pipe line supplying DI specials valves andallied works under command area of Bistupur piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000089/2023-2024 | 720/DWSD | 11/05/2023 | 30 | MAK CONSTRUCTION CO. | 21.57 | 19.05 | 100
2340 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Creating a separate zone for PATHANPARA and Bagdipara of Kanksa (Zone-II/Part-C) with construction of Pump house /Chlorine room Sinking of 150 mm X 80 mm X 150 mtr deep Tube well & supplying laying of HDPE distribution pipe line and providing FHTC at Paragraph Mouza under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000108/2023-2024 | 1139/DWSD | 20/07/2023 | 45 | JOY GURU ENTERPRISE | 95.5 | 0 | 0
2341 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method Note- 46 and node point 64,65 under Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-C) | Assistant Engineer-II | Junior Engineer-3 | ORD/000151/2023-2024 | 1282/DWSD | 07/08/2023 | 15 | MRITYUNJOY MUKHERJEE AND CO | 10.92 | 10.92 | 100
2342 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Bistupur piped W/s Scheme (Part-A & B) | Assistant Engineer-II | Junior Engineer-3 | ORD/000153/2023-2024 | 1284/DWSD | 07/08/2023 | 15 | AHS R INFRA PRIVATE LIMITED | 9.08 | 9.04 | 100
2343 | Durgapur W/S Division | Asansol Mechanical Division | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-B) | Assistant Engineer-II | Junior Engineer-3 | ORD/000154/2023-2024 | 1285/DWSD | 07/08/2023 | 15 | MACHINO TECHNO | 10.92 | 10.92 | 100
2344 | Durgapur W/S Division | Asansol Mechanical Division | Water supply arrangement for guard shed with solar power connection to provide water supply block -Kanksa under Augmentation of Bistupur Piped W/s scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000162/2023-2024 | 1290/DWSD | 07/08/2023 | 20 | SUNDAR CONSTRUCTION | 5.95 | 5.95 | 100
2345 | Durgapur W/S Division | Asansol Mechanical Division | 1(One) No PWD road crossing at Bistupur under command area of Bistupur distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Augmentation of Bistupur piped W/s Scheme under DWSD ,PHE Dte (Part-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000163/2023-2024 | 1294/DWSD | 07/08/2023 | 15 | MRITYUNJOY MUKHERJEE AND CO | 10.91 | 10.91 | 100
2346 | Durgapur W/S Division | Asansol Mechanical Division | Balance work of providing water supply to Molandighi Junior Grills H.S. Molandighi Adivasi para SSK Arraha library and Bistupur brahmin para ICDS for providing Water supply to school under Durgapur-Faridpur/Kanksa Block under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000169/2023-2024 | 1297/DWSD | 07/08/2023 | 15 | MUKHERJEE ENTERPRISE | 3.94 | 3.94 | 100
2347 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Sinking of 1 No tube well 250 mm X 150 mm tube well of 210 mtrs depth by Direct rotary rig method using PVC pipe and prepacked resin bonded gravel filter at Tilackchandrapur barobandh Adibasipara,Block-Kanksa under Augmentation of Bistupur piped W/s Scheme under DWD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000172/2023-2024 | 1303/DWSD | 07/08/2023 | 30 | MONDAL PRECISION PVT LTD | 10.8 | 10.71 | 100
2348 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of laying of distribution system and providing FHTC including reconnection of exiting FHTC from AC pipe line to newly laid different dia HDPE pipe line for Augmentation of Kanksa (Zone-II/Part-C) piped W/S Scheme under DWSD ,PHE Dte (SL-05) | Assistant Engineer-II | Junior Engineer-3 | ORD/000211/2022-2023 | 1161/DWSD | 01/08/2022 | 4 | BRINDABAN KONAR | 216.66 | 15.54 | 80
2349 | Durgapur W/S Division | Asansol Mechanical Division | Additional works for supplying laying of HDPE pipe line including MS pipe lying and fabricating and other allied works at Bistupur under Augmentation of Bistupur piped W/s Scheme under DWSD,PHEDte . | Assistant Engineer-II | Junior Engineer-3 | ORD/000217/2023-2024 | 1453/DWSD | 25/08/2023 | 25 | MRITYUNJOY MUKHERJEE AND CO | 18.95 | 18.93 | 100
2350 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work for installation and fabrication of MS structural work and solar panel at Biharpur and Babnabera FP school under Augmentation of Bistupur piped W/s Scheme under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000220/2023-2024 | 1454/DWSD | 25/08/2023 | 15 | M/S MONDAL ENTERPRISE | 5.35 | 5.35 | 100
2351 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of renovation and modification of administrative office at PHE complex Nababhat (2nd Floor) in connection with Augmentation of Bistupur PWSS under DWSD,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000223/2023-2024 | 1510/DWSD | 07/09/2023 | 25 | SANDIPAN SENGUPTA | 14.99 | 13.91 | 80
2352 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance order for the work of Construction of of 500 M3 capacity ,20 Mtr staging height RCC Over Head Reservoir at Molandighi of Bistupur piped W/S Scheme under Durgapur W/S Division, PHE Dte .(SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000256/2021-2022 | 1650/DWSD | 25/11/2021 | 120 | MRITYUNJOY MUKHERJEE AND CO | 92.97 | 18.1 | 100
2353 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of implementation of ground water based mini piped water supply scheme in 7(Seven) nos villages under Durgapur-Faridpur and Kanksa blocks max 100 HH under DWSD,PHE Dte in connection with Jal Swapna | Assistant Engineer-II | Junior Engineer-3 | ORD/000268/2022-2023 | 1162/DWSD | 01/08/2022 | 792 | MONDAL PRECISION PVT LTD | 275.32 | 0 | 100
2354 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Balance work of providing FHTC in connection with JJM for Kanksa (Zone-II) Part-B for Augmentation of BISTUPUR W/S Scheme (JJM) under DWSD,PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000277/2023-2024 | 1563/DWSD | 20/09/2023 | 681 | MD AAMIR KHAN | 30.61 | 0 | 100
2355 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of Providing FHTC in connection with JJM for Gourbazar-Ichhapur W/s Scheme mouza-Patsaora(JL-53) Part-A block-Durgapur-Faridpur block, Dist.- Paschim Bardhaman under DWSD, PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000278/2021-2022 | 1596/DWSD | 08/11/2021 | 10 | SHWET BARANI | 4.52 | 4.46 | 100
2356 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000473/2021-2022 | 1632/DWSD | 18/11/2021 | 15 | SHWET BARANI | 3.99 | 3.99 | 100
2357 | Durgapur W/S Division | Asansol Mechanical Division | Continuation order for the work of additional number of FHTC in connection with JJM Ichhapur(Mouza-91) with extension of branch pipe line of command area of Gourbazar-Ichhapur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000475/2021-2022 | 179/DWSD | 11/02/2022 | 15 | SHWET BARANI | 3.99 | 3.99 | 100
2358 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Aug of Bistupur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000342/2021-2022 | 81/DWSD | 25/01/2022 | 65 | MACHINO TECHNO | 377.99 | 0 | 0
2359 | Durgapur W/S Division | Asansol Mechanical Division | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) | Assistant Engineer-II | Junior Engineer-3 | ORD/000354/2021-2022 | 149/DWSD | 07/02/2022 | 65 | MACHINO TECHNO | 377.24 | 133.19 | 100
2360 | Durgapur W/S Division | Asansol Mechanical Division | Acceptance cum formal order for the work of Construction of boundary wall at Bistupur H/W Site PH No-1 ,TW No-1 site under Augmentation Bistupur piped W/s Scheme under DWSD ,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000517/2022-2023 | 334/DWSD | 20/02/2023 | 20 | M/S SHYAM KANTA GHOSH | 27.51 | 0 | 0
2361 | Asansol Mechanical | Asansol Mechanical Division | Payment for the Quotation as per WBSEDCL procedure-A (2010) on turn-key / full deposit basis, for the site of Bistupur, T.W. No.-08, Rakhitpur. | Assistant Engineer-II | Junior Engineer-3 | BILL/00151/2025-2026 |  | 22/05/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.28 | 0 | 0
2362 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per wbsedcl procedure-A (2010) on turn-key/full deposit basis for the site of Bistupur, Pump house no-06, Pathardiha, near Essar oil plant. | Assistant Engineer-II | Junior Engineer-3 | BILL/00905/2024-2025 | BP-2024-25-76 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0
2363 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL procedure-A (2010) on Turn-key / Full deposit basis for the site of Bistupur, Pump House No.-05, Kuldiha, Near Dangapara ICDS. | Assistant Engineer-II | Junior Engineer-3 | BILL/00906/2024-2025 | BP-2024-25-77 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0
2364 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL procedure-A(2010) on turn-key/ full deposit basis for the site of Bistupur, TW No.-07, near Malandighi. | Assistant Engineer-II | Junior Engineer-3 | BILL/00978/2024-2025 | BP-2024-25-81 | 12/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.61 | 0 | 0
2365 | Asansol Mechanical | Asansol Mechanical Division | Quotation as per WBSEDCL Procedure-A (2010) on Turn-Key/ Full deposit basis for the site of Bistupur, TW No.-04, Chua, Rakhitpur, near Primary School. | Assistant Engineer-II | Junior Engineer-3 | BILL/00979/2024-2025 | BP-2024-25-80 | 12/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.38 | 0 | 0
2366 | Asansol Mechanical | Asansol Mechanical Division | Supply And Installation Of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System And Internal House Wiring For Tube Well No-4, Tube Well No-5 and Tube Well No-6 At Augmentation Of Bistupur Piped Water Supply Scheme Under Asansol Mechanical Division, PHE. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000453/2024-2025 | 2119/AMD | 16/12/2024 | 1413 | M/S SAJAHAN CHOWDHURY | 34.81 | 0 | 47
2367 | Asansol Mechanical | Asansol Mechanical Division | SUPPLY AND INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY, VOLTAGE STABILIZER, CHLORINATION SYSTEM AND INTERNAL HOUSE WIRING FOR TUBE WELL NO-7 (MALANDIGHI) & TUBE WELL NO-8 (RAKSHITPUR) AT AUGMENTATION OF BISTUPUR PIPED WATER SUPPLY SCHEME UNDER ASANSOL MECHANICAL DIVISION, PHE DTE., BLOCK- KANKSA, DIST- PASCHIM BARDHAMAN. | Assistant Engineer-II | Junior Engineer-3 | ORD/000031/2025-2026 | 951/AMD | 16/05/2025 | 395 | M/S SAJAHAN CHOWDHURY | 23.47 | 0 | 16
Total | [10 empty] | 136887.67 | 62958.88