## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 |  | 6 | 0 | 22
2 | Office of the CE,Head Quarter | 4 | 0 | 12
3 | Alipore Division | 460 | 3 | 14
4 | Barasat Division | 181 | 2 | 15
5 | Nadia Division | 249 | 0 | 2
6 | Murshidabad Division | 197 | 2 | 13
7 | North 24 Pgs W/S Division I | 13 | 0 | 9
8 | Midnapore Division | 442 | 4 | 18
9 | Tamluk Division | 383 | 1 | 6
10 | Bankura Division | 892 | 7 | 10
11 | RCFA Division I | 29 | 0 | 8
12 | Nadia Arsenic Division I | 101 | 0 | 5
13 | Durgapur W/S Division | 108 | 0 | 1
14 | Purulia Division | 76 | 1 | 10
15 | Howrah Division | 160 | 2 | 5
16 | Hooghly Division | 351 | 1 | 8
17 | Burdwan Division | 274 | 0 | 13
18 | Birbhum Division | 331 | 0 | 12
19 | Raiganj Division | 243 | 5 | 18
20 | Jalpaiguri Division | 211 | 1 | 9
21 | Coochbehar Division | 292 | 1 | 12
22 | Siliguri W/S Division | 119 | 2 | 5
23 | Neorakhola W/S Mnt. Division | 334 | 9 | 21
24 | Darjeeling Division | 7 | 0 | 0
25 | Kalimpong Division | 35 | 0 | 0
26 | Malda Division | 196 | 0 | 10
27 | Malda Arsenic Area W/S Division | 70 | 0 | 4
28 | Balurghat Division | 228 | 3 | 7
29 | Electrical Division | 2 | 0 | 0
30 | South 24 Pgs Mechanical Division | 0 | 0 | 5
31 | Central Mechanical Division | 0 | 0 | 1
32 | Asansol Mechanical Division | 0 | 0 | 4
33 | Purulia Mechanical Division | 3 | 1 | 1
34 | Bolpur Mechanical Division | 1 | 0 | 3
35 | Midnapore Mechanical Division | 72 | 1 | 5
36 | Bankura Mechanical Division | 4 | 0 | 2
37 | Resources Division | 9 | 0 | 95
38 | Eastern Mechanical Division | 4 | 3 | 4
39 | Malda Mechanical Division | 2 | 0 | 1
40 | Northern Mechanical Division | 0 | 0 | 1
41 | Special Investigation Division | 0 | 0 | 0
42 | Survey Division | 0 | 0 | 0
43 | Investigation Unit | 0 | 0 | 6
44 | Planning and Design Division IV | 0 | 0 | 7
45 | South 24 Pgs. W/S Division - I | 349 | 0 | 14
46 | Barasat Arsenic Division | 21 | 0 | 5
47 | Nadia Arsenic Civil Division II | 43 | 0 | 0
48 | Berhampur Division I | 60 | 2 | 0
49 | Berhampur M/E Division | 0 | 0 | 1
50 | WSSO | 0 | 0 | 0
51 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
52 | Alipurduar Division | 217 | 2 | 3
53 | Kurseong Division | 27 | 0 | 1
54 | Northern Mechanical Division II | 1 | 0 | 1
55 | Project Implementation Unit,Purba Midnapur(ADB) | 0 | 0 | 0
56 | Jhargram Division | 135 | 7 | 7
57 | Jhargram Mechanical Division | 0 | 0 | 1
Total |  | 6942 | 60 | 438