## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 |  | 6 | 0 | 22
2 | Office of the CE,Head Quarter | 4 | 0 | 12
3 | Alipore Division | 466 | 3 | 14
4 | Barasat Division | 261 | 2 | 15
5 | Nadia Division | 258 | 0 | 2
6 | Murshidabad Division | 366 | 2 | 13
7 | North 24 Pgs W/S Division I | 61 | 0 | 9
8 | Midnapore Division | 483 | 3 | 17
9 | Tamluk Division | 441 | 1 | 6
10 | Bankura Division | 759 | 7 | 10
11 | RCFA Division I | 38 | 0 | 8
12 | Nadia Arsenic Division I | 107 | 0 | 5
13 | Durgapur W/S Division | 117 | 0 | 1
14 | Purulia Division | 83 | 1 | 10
15 | Howrah Division | 162 | 1 | 5
16 | Hooghly Division | 420 | 1 | 8
17 | Burdwan Division | 312 | 0 | 13
18 | Birbhum Division | 374 | 0 | 12
19 | Raiganj Division | 272 | 5 | 18
20 | Jalpaiguri Division | 231 | 1 | 9
21 | Coochbehar Division | 301 | 0 | 12
22 | Siliguri W/S Division | 125 | 2 | 5
23 | Neorakhola W/S Mnt. Division | 259 | 8 | 21
24 | Darjeeling Division | 7 | 0 | 0
25 | Kalimpong Division | 17 | 0 | 0
26 | Malda Division | 197 | 0 | 10
27 | Malda Arsenic Area W/S Division | 70 | 0 | 4
28 | Balurghat Division | 231 | 2 | 7
29 | Electrical Division | 2 | 0 | 0
30 | South 24 Pgs Mechanical Division | 0 | 0 | 5
31 | Central Mechanical Division | 0 | 0 | 1
32 | Asansol Mechanical Division | 0 | 0 | 4
33 | Purulia Mechanical Division | 3 | 1 | 1
34 | Bolpur Mechanical Division | 1 | 0 | 3
35 | Midnapore Mechanical Division | 72 | 1 | 5
36 | Bankura Mechanical Division | 4 | 0 | 2
37 | Resources Division | 9 | 0 | 95
38 | Eastern Mechanical Division | 5 | 2 | 4
39 | Malda Mechanical Division | 2 | 0 | 1
40 | Northern Mechanical Division | 0 | 0 | 1
41 | Special Investigation Division | 0 | 0 | 0
42 | Survey Division | 0 | 0 | 0
43 | Investigation Unit | 0 | 0 | 6
44 | Planning and Design Division IV | 0 | 0 | 7
45 | South 24 Pgs. W/S Division - I | 366 | 0 | 14
46 | Barasat Arsenic Division | 19 | 0 | 5
47 | Nadia Arsenic Civil Division II | 104 | 0 | 0
48 | Berhampur Division I | 110 | 2 | 0
49 | Berhampur M/E Division | 0 | 0 | 1
50 | WSSO | 0 | 0 | 0
51 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
52 | Alipurduar Division | 226 | 2 | 3
53 | Kurseong Division | 19 | 0 | 1
54 | Northern Mechanical Division II | 1 | 0 | 1
55 | Project Implementation Unit,Purba Midnapur(ADB) | 1 | 0 | 0
56 | Jhargram Division | 134 | 6 | 7
57 | Jhargram Mechanical Division | 0 | 0 | 1
Total |  | 7506 | 53 | 437