## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 | Office of the CE,Head Quarter | 4 | 0 | 12
2 | Alipore Division | 447 | 1 | 14
3 | Barasat Division | 236 | 2 | 15
4 | Nadia Division | 258 | 0 | 2
5 | Murshidabad Division | 305 | 11 | 13
6 | North 24 Pgs W/S Division I | 61 | 0 | 9
7 | Midnapore Division | 469 | 7 | 17
8 | Tamluk Division | 411 | 1 | 6
9 | Bankura Division | 634 | 4 | 10
10 | RCFA Division I | 48 | 0 | 8
11 | Nadia Arsenic Division I | 35 | 5 | 5
12 | Durgapur W/S Division | 108 | 0 | 1
13 | Purulia Division | 83 | 1 | 10
14 | Howrah Division | 13 | 1 | 5
15 | Hooghly Division | 386 | 4 | 8
16 | Burdwan Division | 301 | 0 | 13
17 | Birbhum Division | 164 | 2 | 12
18 | Raiganj Division | 271 | 6 | 18
19 | Jalpaiguri Division | 225 | 1 | 9
20 | Coochbehar Division | 298 | 0 | 12
21 | Siliguri W/S Division | 104 | 0 | 5
22 | Neorakhola W/S Mnt. Division | 255 | 7 | 21
23 | Darjeeling Division | 2 | 0 | 0
24 | Kalimpong Division | 11 | 0 | 0
25 | Malda Division | 194 | 0 | 10
26 | Malda Arsenic Area W/S Division | 68 | 0 | 4
27 | Balurghat Division | 283 | 3 | 7
28 | Electrical Division | 4 | 0 | 0
29 | South 24 Pgs Mechanical Division | 0 | 4 | 5
30 | Central Mechanical Division | 2 | 0 | 1
31 | Asansol Mechanical Division | 3 | 0 | 4
32 | Purulia Mechanical Division | 3 | 1 | 1
33 | Bolpur Mechanical Division | 1 | 0 | 3
34 | Midnapore Mechanical Division | 125 | 27 | 5
35 | Bankura Mechanical Division | 14 | 0 | 2
36 | Resources Division | 9 | 0 | 95
37 | Eastern Mechanical Division | 5 | 12 | 4
38 | Malda Mechanical Division | 2 | 5 | 1
39 | Northern Mechanical Division | 24 | 8 | 1
40 | Special Investigation Division | 0 | 0 | 0
41 | Survey Division | 0 | 0 | 0
42 | Investigation Unit | 0 | 0 | 6
43 | Planning and Design Division IV | 0 | 0 | 7
44 | South 24 Pgs. W/S Division - I | 360 | 0 | 14
45 | Barasat Arsenic Division | 29 | 0 | 5
46 | Nadia Arsenic Civil Division II | 66 | 1 | 0
47 | Berhampur Division I | 175 | 6 | 0
48 | Berhampur M/E Division | 0 | 6 | 1
49 | WSSO | 0 | 0 | 0
50 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
51 | Alipurduar Division | 227 | 2 | 3
52 | Kurseong Division | 24 | 0 | 1
53 | Northern Mechanical Division II | 15 | 0 | 1
54 | Project Implementation Unit,Purba Midnapur(ADB) | 1 | 0 | 0
55 | Jhargram Division | 159 | 6 | 7
56 | Jhargram Mechanical Division | 6 | 25 | 1
Total |  | 6928 | 159 | 415