## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 | Office of the CE,Head Quarter | 4 | 2 | 12
2 | Alipore Division | 466 | 167 | 14
3 | Barasat Division | 261 | 153 | 15
4 | Nadia Division | 258 | 150 | 2
5 | Murshidabad Division | 366 | 49 | 13
6 | North 24 Pgs W/S Division I | 62 | 36 | 9
7 | Midnapore Division | 483 | 148 | 17
8 | Tamluk Division | 441 | 173 | 6
9 | Bankura Division | 738 | 324 | 10
10 | RCFA Division I | 38 | 17 | 8
11 | Nadia Arsenic Division I | 107 | 114 | 5
12 | Durgapur W/S Division | 117 | 56 | 1
13 | Purulia Division | 83 | 80 | 10
14 | Howrah Division | 162 | 96 | 5
15 | Hooghly Division | 420 | 125 | 8
16 | Burdwan Division | 312 | 150 | 13
17 | Birbhum Division | 374 | 70 | 12
18 | Raiganj Division | 272 | 170 | 18
19 | Jalpaiguri Division | 231 | 85 | 9
20 | Coochbehar Division | 301 | 176 | 12
21 | Siliguri W/S Division | 125 | 17 | 5
22 | Neorakhola W/S Mnt. Division | 259 | 129 | 21
23 | Darjeeling Division | 7 | 5 | 0
24 | Kalimpong Division | 17 | 12 | 0
25 | Malda Division | 197 | 73 | 10
26 | Malda Arsenic Area W/S Division | 70 | 19 | 4
27 | Balurghat Division | 231 | 59 | 7
28 | Electrical Division | 2 | 1 | 0
29 | South 24 Pgs Mechanical Division | 0 | 0 | 5
30 | Central Mechanical Division | 0 | 0 | 1
31 | Asansol Mechanical Division | 0 | 1 | 4
32 | Purulia Mechanical Division | 3 | 3 | 1
33 | Bolpur Mechanical Division | 1 | 1 | 3
34 | Midnapore Mechanical Division | 72 | 7 | 5
35 | Bankura Mechanical Division | 4 | 1 | 2
36 | Resources Division | 9 | 1 | 95
37 | Eastern Mechanical Division | 5 | 2 | 4
38 | Malda Mechanical Division | 2 | 2 | 1
39 | Northern Mechanical Division | 0 | 0 | 1
40 | Special Investigation Division | 0 | 0 | 0
41 | Survey Division | 0 | 0 | 0
42 | Investigation Unit | 0 | 2 | 6
43 | Planning and Design Division IV | 0 | 0 | 7
44 | South 24 Pgs. W/S Division - I | 366 | 65 | 14
45 | Barasat Arsenic Division | 19 | 33 | 5
46 | Nadia Arsenic Civil Division II | 106 | 44 | 0
47 | Berhampur Division I | 110 | 39 | 0
48 | Berhampur M/E Division | 0 | 0 | 1
49 | WSSO | 0 | 0 | 0
50 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
51 | Alipurduar Division | 227 | 129 | 3
52 | Kurseong Division | 19 | 3 | 1
53 | Northern Mechanical Division II | 1 | 0 | 1
54 | Project Implementation Unit,Purba Midnapur(ADB) | 1 | 0 | 0
55 | Jhargram Division | 134 | 76 | 7
56 | Jhargram Mechanical Division | 0 | 0 | 1
Total |  | 7483 | 3065 | 415