## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl No. | Division | Physical progress is but Target Date Exceeded | Physical Progress % > 80% but Finacial Progress % | Target date is Blank
1 |  | 6 | 3 | 22
2 | Office of the CE,Head Quarter | 4 | 2 | 12
3 | Alipore Division | 460 | 128 | 14
4 | Barasat Division | 258 | 126 | 15
5 | Nadia Division | 258 | 123 | 2
6 | Murshidabad Division | 336 | 42 | 13
7 | North 24 Pgs W/S Division I | 36 | 30 | 9
8 | Midnapore Division | 485 | 110 | 17
9 | Tamluk Division | 423 | 104 | 6
10 | Bankura Division | 894 | 228 | 10
11 | RCFA Division I | 38 | 12 | 8
12 | Nadia Arsenic Division I | 107 | 76 | 5
13 | Durgapur W/S Division | 117 | 54 | 1
14 | Purulia Division | 83 | 64 | 10
15 | Howrah Division | 162 | 67 | 5
16 | Hooghly Division | 420 | 103 | 8
17 | Burdwan Division | 311 | 129 | 13
18 | Birbhum Division | 371 | 55 | 12
19 | Raiganj Division | 272 | 149 | 18
20 | Jalpaiguri Division | 217 | 63 | 9
21 | Coochbehar Division | 295 | 178 | 12
22 | Siliguri W/S Division | 120 | 16 | 5
23 | Neorakhola W/S Mnt. Division | 338 | 190 | 21
24 | Darjeeling Division | 7 | 5 | 0
25 | Kalimpong Division | 35 | 29 | 0
26 | Malda Division | 196 | 61 | 10
27 | Malda Arsenic Area W/S Division | 70 | 16 | 4
28 | Balurghat Division | 231 | 50 | 7
29 | Electrical Division | 2 | 1 | 0
30 | South 24 Pgs Mechanical Division | 0 | 0 | 5
31 | Central Mechanical Division | 0 | 0 | 1
32 | Asansol Mechanical Division | 0 | 1 | 4
33 | Purulia Mechanical Division | 3 | 2 | 1
34 | Bolpur Mechanical Division | 1 | 1 | 3
35 | Midnapore Mechanical Division | 72 | 7 | 5
36 | Bankura Mechanical Division | 4 | 1 | 2
37 | Resources Division | 9 | 1 | 95
38 | Eastern Mechanical Division | 5 | 3 | 4
39 | Malda Mechanical Division | 2 | 2 | 1
40 | Northern Mechanical Division | 0 | 0 | 1
41 | Special Investigation Division | 0 | 0 | 0
42 | Survey Division | 0 | 0 | 0
43 | Investigation Unit | 0 | 2 | 6
44 | Planning and Design Division IV | 0 | 0 | 7
45 | South 24 Pgs. W/S Division - I | 354 | 53 | 14
46 | Barasat Arsenic Division | 21 | 13 | 5
47 | Nadia Arsenic Civil Division II | 63 | 8 | 0
48 | Berhampur Division I | 100 | 30 | 0
49 | Berhampur M/E Division | 0 | 0 | 1
50 | WSSO | 0 | 0 | 0
51 | Project Management Unit,WBPWSP,Purulia | 0 | 0 | 1
52 | Alipurduar Division | 217 | 108 | 3
53 | Kurseong Division | 27 | 5 | 1
54 | Northern Mechanical Division II | 1 | 0 | 1
55 | Project Implementation Unit,Purba Midnapur(ADB) | 1 | 0 | 0
56 | Jhargram Division | 135 | 62 | 7
57 | Jhargram Mechanical Division | 0 | 0 | 1
Total |  | 7567 | 2513 | 437