## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR DAMODARKHALI WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09244 | TSM/008763 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 14 | 1593 | inf | nan | 95 | 0
2 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR CHANDPUR WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09245 | TSM/008762 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 8 | 430 | inf | nan | 70 | 0
3 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR TALDAHA WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09246 | TSM/008761 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 16 | 660 | inf | nan | 36 | 0
4 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-III WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09247 | TSM/008760 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 9 | 739 | inf | nan | 37 | 0
5 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR HELENCHI ZONE-II WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09248 | TSM/008758 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 13 | 2269 | inf | nan | 52 | 0
6 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA KHANJEPUR WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09249 | TSM/008759 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 13 | 234 | inf | nan | 70 | 0
7 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BAHIRGACHI ZONE-II WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09250 | TSM/008757 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 14 | 671 | inf | nan | 77 | 0
8 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION) BY RETROFITTING UNDER JAL SWAPNA FOR BANSBARIA WATER SUPPLY SCHEME IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09251 | TSM/008756 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 7 | 962 | inf | nan | 90 | 0
9 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED BALIBANGA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09253 | TSM/008731 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 13 | 1322 | inf | nan | 70 | 0
10 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED SAKDAHA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09254 | TSM/008730 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 17 | 226 | inf | nan | 58 | 0
11 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED CHANDERGHAT PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09255 | TSM/008736 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 10 | 1308 | inf | nan | 65 | 0
12 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED LAKSHMIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09256 | TSM/008734 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 12 | 1556 | inf | nan | 49 | 0
13 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED BAGBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09257 | TSM/008732 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 20 | 266 | inf | nan | 51 | 0
14 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED NISCHINTAPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09258 | TSM/008728 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 13 | 1595 | inf | nan | 59 | 0
15 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED MOBARAKPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09259 | TSM/008725 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 12 | 2353 | inf | nan | 78 | 0
16 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED GONGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09260 | TSM/008729 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 11 | 1106 | inf | inf | 80 | 73
17 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED TENGRA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09261 | TSM/008727 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 20 | 138 | inf | inf | 92 | 86
18 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED KADIPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09262 | TSM/008726 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 14 | 833 | inf | nan | 51 | 0
19 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED FATEPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09263 | TSM/008724 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 8 | 89 | inf | nan | 8 | 0
20 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | AUGMENTATION OF GROUND BASED WATER BASED KRISHNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-II BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09264 | TSM/008723 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 18 | 9 | inf | nan | 43 | 0
21 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED BETBERIA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09266 | TSM/008721 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 12 | 372 | inf | nan | 55 | 0
22 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED PATHARGHATA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09267 | TSM/008720 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 16 | 3580 | inf | nan | 43 | 0
23 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | AUGMENTATION OF GROUND BASED WATER BASED SHYAMNAGAR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KRISHNAGANJ BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09268 | TSM/008719 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 19 | 1411 | inf | nan | 60 | 0
24 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED BAHADURPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09269 | TSM/008718 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 16 | 570 | inf | nan | 58 | 0
25 | Nadia Arsenic Civil Division II | NADIA | Chapra | AUGMENTATION OF GROUND BASED WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER CHAPRA BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09270 | TSM/008717 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | 03/11/2021 | 30/11/2021 | 31/12/2025 | 27/01/2026 | 15 | 2595 | inf | nan | 60 | 0
26 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | AUGMENTATION OF GROUND BASED WATER BASED PUTHIMARI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER TEHATTA-I BLOCK IN NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09271 | TSM/008671 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 03/11/2021 | 03/11/2021 | 31/12/2025 | 27/01/2026 | 14 | 1269 | inf | nan | 24 | 0
27 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | Retrofitting of Barnia water supply scheme (Phase-II) under Tehatta-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09685 | TSM/008241 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 25/11/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 10 | 2718 | inf | nan | 90 | 0
28 | Nadia Arsenic Civil Division II | NADIA | Chapra | Retrofitting of Brittihuda water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09686 | TSM/008242 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | 25/11/2021 | 15/09/2021 | 31/12/2025 | 27/01/2026 | 14 | 2799 | inf | nan | 90 | 0
29 | Nadia Arsenic Civil Division II | NADIA | Chapra | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | TSM/008243 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | 25/11/2021 | 15/09/2021 | 31/12/2025 | 27/01/2026 | 12 | 2543 | inf | nan | 90 | 0
30 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | Retrofitting of Patharghata water supply scheme (Phase-II) under Tehatta-I Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09696 | TSM/008240 | Retrofitting |  |  |  | 25/11/2021 | 15/09/2021 | 31/12/2025 | 27/01/2026 | 4 | 2532 | inf | nan | 62 | 0
31 | Nadia Arsenic Civil Division II | NADIA | Karimpur - II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | TSM/008244 | Retrofitting | Nadia Arsenic Civil Division II | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | 25/11/2021 | 15/09/2021 | 31/12/2025 | 27/01/2026 | 16 | 3249 | inf | nan | 82 | 0
32 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-II WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09866 | TSM/009127 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 18 | 550 | inf | nan | 32 | 0
33 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | TSM/009118 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 06/12/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 13 | 1059 | inf | nan | 35 | 0
34 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | TSM/009107 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 18 | 2255 | inf | nan | 30 | 0
35 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DIGRI TO ACCOMMODATE FHTC IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II, PHE DTE. | SM/09870 | TSM/009095 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 06/12/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 13 | 2623 | inf | nan | 62 | 0
36 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | TSM/009098 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | 06/12/2021 | 07/12/2021 | 31/12/2025 | 27/01/2026 | 17 | 2653 | inf | nan | 51 | 0
37 | Nadia Arsenic Civil Division II | NADIA | Krishnaganj | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MATIARY WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09872 | TSM/009113 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 06/12/2021 | 10/01/2022 | 31/12/2025 | 27/01/2026 | 17 | 2266 | inf | nan | 71 | 0
38 | Nadia Arsenic Civil Division II | NADIA |  | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | TSM/008045 | Anganwadi | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | 08/12/2021 | 15/12/2021 | 31/12/2025 | 27/01/2026 | 55 | 19352 | inf | nan | 89 | 0
39 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | Dhopahat Piped Water Supply Scheme | SM/09942 | TSM/008625 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 13/12/2021 | 15/04/2022 | 31/03/2026 | 27/01/2026 | 25 | 1823 | inf | nan | 43 | 0
40 | Nadia Arsenic Civil Division II | NADIA |  | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | TSM/008755 | Anganwadi | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | 19/01/2022 | 31/01/2022 | 31/12/2025 | 27/01/2026 | 51 | 33147 | inf | nan | 85 | 0
41 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARNIA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10093 | TSM/009109 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 01/02/2022 | 03/03/2022 | 31/12/2025 | 27/01/2026 | 40 | 3734 | inf | nan | 7 | 0
42 | Nadia Arsenic Civil Division II | NADIA | Chapra | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | TSM/009068 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 15/02/2022 | 31/03/2026 | 27/01/2026 | 31 | 1582 | inf | nan | 48 | 0
43 | Nadia Arsenic Civil Division II | NADIA | Chapra | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | TSM/009069 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 15/02/2022 | 31/03/2026 | 27/01/2026 | 23 | 1261 | inf | nan | 38 | 0
44 | Nadia Arsenic Civil Division II | NADIA | Chapra | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | TSM/009022 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 02/02/2022 | 15/02/2022 | 31/03/2026 | 27/01/2026 | 28 | 1374 | inf | nan | 36 | 0
45 | Nadia Arsenic Civil Division II | NADIA | Chapra | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | TSM/009105 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 22/02/2022 | 03/03/2022 | 31/12/2025 | 27/01/2026 | 41 | 3798 | inf | nan | 47 | 0
46 | Nadia Arsenic Civil Division II | NADIA | Karimpur - II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | TSM/009115 | Augmentation | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 22/02/2022 | 03/03/2022 | 31/12/2025 | 27/01/2026 | 58 | 4561 | inf | nan | 46 | 0
47 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | TSM/009215 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 01/05/2022 | 31/03/2026 | 27/01/2026 | 29 | 1235 | inf | nan | 47 | 0
48 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | TSM/008886 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 08/04/2022 | 10/05/2022 | 31/03/2026 | 27/01/2026 | 24 | 1124 | inf | nan | 44 | 0
49 | Nadia Arsenic Civil Division II | NADIA | Chapra | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | TSM/008804 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 08/04/2022 | 01/05/2022 | 31/03/2026 | 27/01/2026 | 24 | 1665 | inf | nan | 48 | 0
50 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | TSM/008994 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 10/05/2022 | 31/03/2026 | 27/01/2026 | 28 | 1218 | inf | nan | 53 | 0
51 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | TSM/008951 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 10/05/2022 | 25/04/2025 | 27/01/2026 | 24 | 1975 | inf | nan | 52 | 0
52 | Nadia Arsenic Civil Division II | NADIA | Santipur | Manik Nagar Piped W/S Scheme | SM/10407 | TSM/008673 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 08/04/2022 | 10/05/2022 | 31/03/2026 | 27/01/2026 | 24 | 1182 | inf | nan | 46 | 0
53 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | TSM/008996 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 08/04/2022 | 01/05/2022 | 31/03/2026 | 27/01/2026 | 31 | 1387 | inf | nan | 38 | 0
54 | Nadia Arsenic Civil Division II | NADIA | Hanskhali | SANATANPUR PIPED WATER SUPPLY SCHEME | SM/10409 | TSM/008959 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 08/04/2022 | 01/05/2022 | 31/03/2026 | 27/01/2026 | 24 | 1283 | inf | nan | 40 | 0
55 | Nadia Arsenic Civil Division II | NADIA | Chapra | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | TSM/008800 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 08/04/2022 | 10/05/2022 | 31/03/2026 | 27/01/2026 | 25 | 1651 | inf | nan | 40 | 0
56 | Nadia Arsenic Civil Division II | NADIA | Tehatta - II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | TSM/008657 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | 20/04/2022 | 10/05/2022 | 31/03/2026 | 27/01/2026 | 30 | 4138 | inf | nan | 42 | 0
57 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | TSM/011905 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 25/08/2022 | 21/11/2022 | 31/03/2026 | 27/01/2026 | 22 | 1847 | inf | nan | 16 | 0
58 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | TSM/011888 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 25/08/2022 | 20/11/2022 | 31/03/2026 | 27/01/2026 | 19 | 1800 | inf | nan | 10 | 0
59 | Nadia Arsenic Civil Division II | NADIA | Tehatta - I | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | TSM/011903 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 25/08/2022 | 21/11/2022 | 31/03/2026 | 27/01/2026 | 20 | 2060 | inf | nan | 10 | 0
60 | Nadia Arsenic Civil Division II | NADIA | Karimpur - II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | TSM/014311 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 13/09/2022 | 05/12/2022 | 31/03/2026 | 27/01/2026 | 19 | 509 | inf | nan | 23 | 0
61 | Nadia Arsenic Civil Division II | NADIA | Karimpur - I | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | TSM/014577 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 13/09/2022 | 20/11/2022 | 31/03/2026 | 27/01/2026 | 17 | 905 | inf | nan | 11 | 0
62 | Nadia Arsenic Civil Division II | NADIA | Chapra | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | TSM/012015 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | 14/09/2022 | 20/11/2022 | 31/03/2026 | 27/01/2026 | 17 | 2816 | inf | nan | 9 | 0
63 | Nadia Arsenic Civil Division II | NADIA | Krishnagar - I | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | TSM/015027 | New | Nadia Arsenic Civil Division II | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | 20/01/2023 | 24/01/2023 | 31/03/2026 | 27/01/2026 | 23 | 3397 | inf | nan | 8 | 0
Total | [14 empty] | 1258 | 154227 | 0 | 0 |  | NAN