## H2- Exception Report on Scheme
H2- Exception Report on Scheme
Sl. No. | Division | District | Block | Scheme Name | Scheme SM Code | Scheme TSM Code | Scheme Category | Sub Division | Name of AE entrusted | Name of JE entrusted | Date of Sanction | Date of Commencement | Target Date of Completion | Date Of Updation | Work Order Issued | FHTCs | Sanctioned Cost | Payment | Physical Progress (in %) | Financial Progress (in %)
1 | Berhampur Division I | MURSHIDABAD | Beldanga - II | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part | SM/07889 | TSM/006515 | Retrofitting | Berhampur Division I | Assistant Engineer-II | Junior Engineer-II | 19/01/2021 | 14/11/2021 | 31/12/2024 | 21/05/2024 | 1 | 629 | 0 | 0 | 82 | 0
2 | Berhampur Division I | MURSHIDABAD | Beldanga - I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I | SM/07890 | TSM/006900 | Retrofitting | Berhampur Division I | Assistant Engineer-II | Junior Engineer-I | 19/01/2021 | 21/02/2022 | 31/12/2024 | 21/05/2024 | 2 | 4583 | 0 | 0 | 82 | 0
3 | Berhampur Division I | MURSHIDABAD | Nawda | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | TSM/010430 | New | Berhampur Division I | Assistant Engineer-II,ASSISTANT ENGINEER-I | JE,Junior engineer-II | 26/07/2022 | 10/05/2023 |  | 12/06/2023 | 2 | 436 | 0 | 0 | 100 | 0
Total | [14 empty] | 5 | 5648 | 0 | 0 |  | 0