## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block , SM/07422 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Huchaimallick mouza and remaining part of Fakna mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 12 | 1222/SWSD | 01/11/2021 | 20 | PRADIP GUHA | 16.83 | 0 | 0 | 68
2 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Birsing Piped water Supply Scheme at Naxalbari Block , SM/07422 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Birsing mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 11. | 1221/SWSD | 01/11/2021 | 35 | M/S MATRI CONSTRUCTION | 31.13 | 0 | 0 | 100
3 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Mangalsing Piped water Supply Scheme , SM/07029 | Retrofitting | Extension of distribution pipeline within the command area for providing 100% Functional House Hold Tap Connections under Jal Jeevan Mission & Jal Swapno Programme of Mangalsing PWWS at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 06 | 987/SWSD | 06/09/2021 | 25 | NARAYAN CH GHOSH | 4.3 | 0 | 0 | 100
4 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Paschim Madati Mouza part of Purba Madati Piped water Supply Scheme (Part-A) , SM/07070 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Paschim Madati twenty six point sixty three percent Habitation Alim Ganj Chowdhry Gach and Gava Ganga of Purba Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | 1079/SWSD | 18/12/2020 | 40 | SHRI ANUP BASU | 35.92 | 0 | 0 | 65
5 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) , SM/07049 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | 1011/SWSD | 11/12/2020 | 40 | M/S DEBRAJ ENTERPRISE | 37.92 | 0 | 0 | 100
6 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) , SM/07049 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area village Madan habitation Madan and village Uttar Ramdhan habitation Goursing and Wairish of Uttar Ramdhan and adjoining Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | 1010/SWSD | 11/12/2020 | 35 | M/S DEBRAJ ENTERPRISE | 37.87 | 21.13 | 50 | 100
7 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) , SM/07049 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
8 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) , SM/07049 | Retrofitting | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2022 TO 31.08.2022. (FOR EXECUIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) (i.e. SIX MONTHS) | 2301/SWSD | 28/02/2022 | 184 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 0 | 100
9 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jiban Sing, Madan and Uttar Ramdhan Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-B) , SM/07049 | Retrofitting | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR RAMDHAN PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 246/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 0 | 100
10 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Rajajhar & Rangapani village of Ranidanga-Rangapani Piped water Supply Scheme , SM/07037 | Retrofitting | HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 28.02.2023 (FOR EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. SIX MONTHS. | 1227/SWSD | 31/08/2022 | 6 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 0 | 100
11 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Rajajhar & Rangapani village of Ranidanga-Rangapani Piped water Supply Scheme , SM/07037 | Retrofitting | Continuation order for Hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of The Chief Engineer (Civil), Northern Zone, P.H.E. Dte. Vivekananda Bhawan (2nd floor), Hill Cart Road, Siliguri for the period from 01.08.2023 to 31.12.2023 (for Chief Engineer (Civil), Northern Zone, P.H.E. Dte.) i.e. 05 (Five) months. | 1051/SWSD | 28/07/2023 | 153 | PINKI DAM | 0.74 | 0 | 0 | 100
12 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme , SM/07045 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Churaman Habitation Churaman, village Thuna Habitation Thuna village Thuna Chhat Habitation Thunar Chhat and village Baramala Habitation Baramala of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte | 1090/SWSD | 18/12/2020 | 45 | SHRI ANUP BASU | 37.37 | 0 | 0 | 100
13 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme , SM/07045 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Fulbar Habitation Fulbar and village Bhalamanshi Habitation Charge more of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte (3rd CALL) | 695/SWSD | 02/08/2021 | 45 | SHRI ANUP BASU | 36.74 | 0 | 0 | 30
14 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bhalamanshi Piped water Supply Scheme , SM/07045 | Retrofitting | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | 3155/SWSD | 25/11/2024 | 30 | PALLAB BHOWAL | 26.07 | 0 | 0 | 0
15 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. , SM/10774 | Retrofitting | Material Requisition To Resource Division | 1900/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.36 | 0 | 0 | 0
16 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. , SM/10774 | Retrofitting | Material Requisition To Resource Division | 2579/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.36 | 0 | 0 | 0
17 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWSS at Soom 1st Division. , SM/10774 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Danra Goan, Soom 1st Division, Gram Panchyat -Soom Singtam, Block Bijanbari -PullBazar. TSM No. 009476 SM Code-SM/08937 | 556/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.53 | 0 | 0 | 100
18 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-110 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 28.3 | 0 | 0 | 0
19 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.73 | 0 | 0 | 0
20 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-B) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 08. | 2434//SWSD | 21/03/2022 | 60 | S.K. BANIK | 68.28 | 0 | 0 | 65
21 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-C) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 09. | 2435/SWSD | 21/03/2022 | 50 | S.K. BANIK | 53.92 | 0 | 0 | 25
22 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Soil Investigation of Pauchkelguri PWSS for Construction of 200 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | 388/SSD | 20/07/2022 | 20 | R.B.TESTING | 1.02 | 0 | 0 | 100
23 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Construction of Pump House (5.4 X 3.60) size with (1.35 X 2.10 M) size toilet, plinth protection etc. and boundary wall at Khopalasi of PAUCHAKELGURI Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 642/SWSD | 15/06/2023 | 45 | U.K CONSTRUCTIONS | 12.89 | 0 | 0 | 50
24 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Material Requisition To Resource Division | 2172/SWSD | 11/02/2022 | 0 | Resource Division | 39.61 | 0 | 0 | 0
25 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Material Requisition To Resource Division | 1448/SWSD | 29/09/2022 | 0 | Resource Division | 9.74 | 0 | 0 | 0
26 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. I under MATIGARA CCC [APPLICATION NO. 4003058425 ; Reference ID : 402932707] | BP/23-24/05 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
27 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. II under MATIGARA CCC [APPLICATION NO. 4003058421 ; Reference ID : 402932706] | BP/23-24/05 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
28 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | New Service Connection Charge for PACHKELGURI, T/W I, under MATIGARA CCC, [APPLICATION NO. 4003199222, Reference ID : 403050473] | BP/23-24/67 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0 | 0
29 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
30 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Construction of 200 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Pauchakelguri and adjoining mouzas water supply scheme within Matigara block under Siliguri Sub Division, PHE Dte. SL. NO. 07. | 176/SWSD | 22/04/2022 | 180 | S.K. BANIK | 126 | 0 | 0 | 35
31 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 0 | 100
32 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and Boundary Wall at Jhaguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 1203/SWSD | 10/08/2023 | 45 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.45 | 0 | 0 | 100
33 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Infrastructure Cost for PACHKELGURI, T/W No. I, under MATIGARA CCC [APPLICATION NO. 100000084014 , Reference ID : 860275184] | BP/23-24/286 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 27.56 | 0 | 0 | 0
34 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-D) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 10. | 2436/SWSD | 21/03/2022 | 1561 | U.K CONSTRUCTIONS | 73.9 | 0 | 0 | 65
35 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-E) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 09. | 868/SWSD | 21/07/2022 | 985 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 81.94 | 0 | 0 | 70
36 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Acceptance cum work order "Construction of Pump House (3 NOS) (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. Rising Main and Boundary Wall at Pauchakelguri ,Khopalasi and Jhauguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | 604/SWSD | 06/03/2024 | 280 | M/S JAYDEV JHA | 28.86 | 0 | 0 | 60
37 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1524/NMD | 03/09/2024 | 408 | ALPHA ENTERPRISE | 11.91 | 0 | 0 | 75
38 | DARJEELING | Northern Mechanical | AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME. , SM/09828 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME ,TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 547/NMD | 15/05/2023 | 688 | ALPHA ENTERPRISE | 23.49 | 0 | 0 | 90
39 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | SHIFTING OF EXISTING TRANSFORMER ALONG WITH 11 KV HOTH LINE. ( REF ID: 860242115 AND APPLICATION ID : 100000052425 ) |  | 22/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.85 | 0 | 0 | 0
40 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-112 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 62.77 | 0 | 0 | 0
41 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 12.12 | 0 | 0 | 0
42 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-E) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04 | 2080/SWSD | 03/02/2022 | 75 | HIMADRI DAM & CO. | 70.68 | 0 | 0 | 50
43 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | 2077/SWSD | 03/02/2022 | 60 | SUDIP BASAK | 66.67 | 0 | 0 | 52
44 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Soil Investigation of Salbari PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | 392/SSD | 20/07/2022 | 20 | SUBIR CH. CHOWDHURY | 1.03 | 0 | 0 | 100
45 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
46 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1330/SWSD | 14/09/2022 | 25 | M/S K. R. S. CONSTRUCTION | 15.45 | 0 | 0 | 0
47 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Construction of 300 cu.m. capacity RCC Elevated Reservoir, 20 mtrs. staging height at the head works site including rising main and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of SALBARI CHHAT, PRATHAM KHANDA, PANCHANAI, NUNU BAIRAGI, MAHATRAM, UDAYSING MOUZA'S (Partially) of SALBARI and adjoining mouza's Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 06. | 2202/SWSD | 17/02/2022 | 180 | SUBIR CH. CHOWDHURY | 125.67 | 0 | 0 | 100
48 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. | 2534/SWSD | 29/03/2022 | 12 | RUPA PRASAD | 1.48 | 0 | 0 | 100
49 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Repair and renovation of the Head Work site Pump House (3.65 m X 2.45 m) size and boundary wall at Head work site allied with additional works like shifting of Rising Main and drain under Augmentation of SALBARI W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, PHE Dte. | 53/SWSD | 10/04/2023 | 30 | SUBIR CH. CHOWDHURY | 9.84 | 0 | 0 | 75
50 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Material Requisition To Resource Division | 2176/SWSD | 11/02/2022 | 0 | Resource Division | 73.29 | 0 | 0 | 0
51 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Material Requisition To Resource Division | 1446/SWSD | 29/09/2022 | 0 | Resource Division | 9.7 | 0 | 0 | 0
52 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Hiring 1 no. diesel consumed luxury vehicle on monthly basis preferably Maxi Cab (with A/C) for Deputy Superintending Engineer, NBC-I, PHE Dte. | BP-2022-23-132 | 20/02/2023 | 0 | OM TRAVELS | 1.95 | 0 | 0 | 0
53 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
54 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Hiring of 1(one) no. Mariti van (non A/C) for the office of the Superintending Engineer, NBC-I , PHE Dte. period from Septenber,October & November 2022 | BP-2022-23-114 | 09/02/2023 | 0 | RUPA PRASAD | 0.8 | 0 | 0 | 0
55 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | 2079/SWSD | 03/02/2022 | 40 | BUDDHADEV NAG | 30.7 | 0 | 0 | 60
56 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | 2078/SWSD | 03/02/2022 | 60 | M/S G.C. CONSTRUCTION & CO. | 65.37 | 0 | 0 | 80
57 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Acceptance cum work order for construction of 4th Tubewell Pump House (3.60 m X 2.40 m) allied with rising main and boundary wall under Augmentation of Salbari W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | 1793/SWSD | 29/09/2023 | 352 | M/S UNIQUE13 | 14.26 | 0 | 0 | 70
58 | DARJEELING | Northern Mechanical | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | New Service Connection Charge for SALBARI, T.W. No. IV under MATIGARA CCC [APPLICATION NO. 4003194765 ; Reference ID : 403046874] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0 | 0
59 | DARJEELING | Northern Mechanical | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1395/NMD | 09/08/2023 | 512 | M/S SAJAHAN CHOWDHURY | 12.99 | 0 | 0 | 100
60 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , SM/09830 | Augmentation | Acceptance Cum Work Order for Repair and Renovation of the 2nd & 3rd Pump House (3.65 m X 2.45 m) site allied with additional works under Augmentation of Salbari W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | 2036/SWSD | 06/11/2023 | 473 | SEBU CHAKRABORTY | 6.38 | 0 | 0 | 90
61 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Connect ion under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Sch eme for Pokhriabong Bazar from Nursery Fatak Source under Jorebanglow- Sukhiapokhri Block Darjeeling" | BP-2022-23-54 | 20/05/2022 | 0 | RISHI KESH THAKURI | 7.36 | 0 | 0 | 0
62 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan M is si on.an d Jal Swapno Programme for Pipe Water Supply Sche me Scheme for 5th mile upper Kotwali Gaon. from Boka Jhora Source under Jorebanglow- Sukhiapokhri Block Darj eeling" | BP-2022-23-41 | 06/05/2022 | 0 | KAMAKHYA ENTERPRISES | 3.63 | 0 | 0 | 0
63 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Funct ional House hold Tap Connection under Jal Jeevan Mission an d Jal Swapno Programme for Pipe Water Supply Sc heme for Mazidhura Lower Parment Busty from Bhir Khola Sou rc e under Jorebanglow- Sukhiapokhri Block Darjeelin g under Darjeeling Division PH ED, GTA." | BP-2022-23-111 | 12/08/2022 | 0 | KAMAKHYA ENTERPRISES | 3.68 | 0 | 0 | 0
64 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jee van Mission and Jal Swapno Pro gramme for Pipe Water Supply Scheme for Lepcha Tribal Gaon Pokhriabong Busty from Gardinay Sim Source under Jorebanglow- Sukhiapokhri Block Darjeeling" | BP-2022-23-171 | 20/10/2022 | 0 | RISHI KESH THAKURI | 3.13 | 0 | 0 | 0
65 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under JAL Jeeva n Mission and Jal Swapno Programme for Pipe Water Su pply Scheme for Chamong Maleteneya And Pari Gaon from Paa Khola and Kera Bari Source under Jorebangiow Sukhiapokhri Block Darjeeling" | BP-2022-23-105 | 08/08/2022 | 0 | RISHI KESH THAKURI | 3.54 | 0 | 0 | 0
66 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Conne ct ion under Jal Jee van Missi on and Jal Swapno Programme for Prpe Water Supply Sch eme for Tar zum under Jorebanglow Sukhiapokhri Block Darjeeling" | BP-2022-23-90 | 14/07/2022 | 0 | SONAM TAMANG | 4.1 | 0 | 0 | 0
67 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functionai Household Tap Connection under Jal Jeevan Mission and Jal Swapno Pro grarnme for Pipe Water Supply Sch eme for Pokhriabong Busty No 4. from Ghimiray Jhora an Thulung Pakha Source under Jorebanglow - Sukhiapokhi" | BP-2022-23-170 | 20/10/2022 | 0 | RISHI KESH THAKURI | 2.56 | 0 | 0 | 0
68 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Scheme for Chotta Pubong ward No 3 & 4 from Singadevi Khela Source Under Jorebanglow - Su khiapokhri Block Dar je elin g under Darje eling Division PHED, GTA." | BP-2022-23-49 | 20/05/2022 | 0 | KIRAN NIROLA | 3.11 | 0 | 0 | 0
69 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | "Jai Jeevan Mi ssion and Jal Swapno Programme for Pipe Water Su pply Scheme for Minzu Pussimbing from Bethany Khop Source under Jorebanglow Sukhiapokhri Block Darjeeling ." | BP-2022-23-53 | 20/05/2022 | 0 | KESHAR CHETTRI | 4.91 | 0 | 0 | 0
70 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0 | 0
71 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0 | 0
72 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | Providing Functional Household Tap Connection under Jal jeevan Mission and Jal Swapno Programrne for Pipe Water Supply Scheme for upper Sirubari and Beech Gaon. Sungma T .E from Bara ReyangKhola Source under Jorebanglow Sukhiapokhri Block Darjeeling | 114/EE/DD/PHED | 10/02/2021 | 120 | SONAM TAMANG | 11.12 | 0 | 0 | 0
73 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] , SM/10259 | Retrofitting | Providing Fun ctional Household Tap Connection under Jal .Jeevan Mission and Jal Swapno Programme for Pipe Water Supp ly Scheme for Bhutia Gaon Plundung from Khodaydhura Khola Source unde r Jorebanglow- Sukhia.pokhri Block Darj eeling | 117/EE/DD/PHED | 10/02/2021 | 120 | ROMAN SHERPA | 3.69 | 0 | 0 | 0
74 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Kharibari W/S Scheme at Kharibari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 01. | 818/SWSD | 13/08/2021 | 21 | ENVIROTECH SOLUTIONS | 3.08 | 0 | 0 | 100
75 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Soil Investigation of Kharibari Zone -II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block. | 387/SSD | 20/07/2022 | 20 | G. TECH INDIA | 1.03 | 0 | 0 | 100
76 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-105 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 49.61 | 0 | 0 | 0
77 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 19.19 | 0 | 0 | 0
78 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
79 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement as per Model Approved Drawing at Tubewell site for different Water Supply Scheme under Siliguri W/S Division, P. H. Engineering Dte. (Name of Scheme : Kharibari Zone-I & II PWSS (Two Nos.) | 334/SWSD | 08/05/2023 | 45 | SWAPAN CHANDRA DAS | 11.67 | 0 | 0 | 100
80 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Material Requisition To Resource Division | 2175/SWSD | 11/02/2022 | 0 | Resource Division | 51.57 | 0 | 0 | 0
81 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Material Requisition To Resource Division | 1451/SWSD | 29/09/2022 | 0 | Resource Division | 26.79 | 0 | 0 | 0
82 | DARJEELING | Northern Mechanical | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | New Service Connection Charge for GURUDAYALJOTE W/S Scheme, T/W No. I, Zone-I under KHARIBARI CCC, [APPLICATION NO. 4003055480, Reference ID : 402933291] | BP/22-23/122 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0 | 0
83 | DARJEELING | Northern Mechanical | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | New Service Connection Charge for PWD MORE W/S Scheme, T/W No. I, Zone-II under KHARIBARI CCC, [APPLICATION NO. 4003055466, Reference ID : 402933292] | BP/22-23/122 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0 | 0
84 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Hiring of vehicle for the office of the Siliguri Sub Division PHE Dte. Assistant Engineer | BP-2023-24-120 | 19/10/2023 | 0 | SUDIP BASAK | 0.74 | 0 | 0 | 0
85 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
86 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Construction of 300 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Connection (FHTC) and allied works at distribution pipe line of Kharibari Zone -II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 01. | 911/SWSD | 25/07/2022 | 891 | ARUN KUMAR SHRIVASTAVA | 240.16 | 0 | 0 | 2
87 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising main and distribution system (Paret-A) allied with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme and allied works Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | 872/SWSD | 21/07/2022 | 1160 | PALLAB BHOWAL | 232.84 | 0 | 0 | 20
88 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Laying distribution system (Part-B) and allied works with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 15. | 873/SWSD | 21/07/2022 | 85 | PALLAB BHOWAL | 91 | 0 | 0 | 73
89 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | 2931/SWSD | 30/10/2024 | 45 | ARUN KUMAR SHRIVASTAVA | 49.08 | 0 | 0 | 0
90 | DARJEELING | Northern Mechanical | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIBARI ZONE - I (TW No. I) and ZONE - II (TW No. I) PIPED WATER SUPPLY SCHEME , in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 493/NMD | 28/04/2023 | 30 | SARKAR ELECTRIC | 22.33 | 0 | 0 | 80
91 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KHARIBARI ZONE - I & ZONE - II PIPED WATER SUPPLY SCHEME , SM/10073 | Augmentation | Sinking of Tubewell By Reverse Rotary Method at 2nd site(KESORDOBA) in replacsmenil of damaged Tube well,KHARIBARI PWSS (ZONE-II) Block: Khoribari, Dist: Darjeeling Under Siliguri W/S Division P.H.E.Dte | 2533/swsd | 18/09/2024 | 151 | NARENDRA KUMAR | 8.71 | 0 | 0 | 85
92 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.05 | 0 | 0 | 0
93 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Khoprail sakha under Kurseong Sub-Division PHED. GTA | BP-2022-23-113 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.83 | 0 | 0 | 0
94 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. | BP-2022-23-19 | 20/04/2022 | 0 | SURAJ LAMA | 6.2 | 0 | 0 | 0
95 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Providing Functional Household Tap Conne ction under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Mandir Busty, Giddhapa har underKurseong Sub-Division PHED, GTA | BP-2022-23-122 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 6.08 | 0 | 0 | 0
96 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Providing Functional HouseholdTap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for for Hilay Jhora and Manju ak number Dara under Kurseong Sub-Division PHED, GTA | BP-2022-23-112 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.7 | 0 | 0 | 0
97 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] , SM/10263 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
98 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Chamta W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 04. | 831/SWSD | 13/08/2021 | 21 | ENVIROTECH SOLUTIONS | 1.97 | 0 | 0 | 100
99 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-113 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 32.46 | 0 | 0 | 0
100 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.52 | 0 | 0 | 0
101 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height including laying distribution system, 400 Nos. FHTC (Part-A) for Chamta and adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | 274/SWSD | 06/05/2022 | 180 | ANUP BASU | 170.09 | 0 | 0 | 0
102 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Laying distribution system of pipeline (Part-B) at Chamta and adjoining mouzas Water Supply Scheme withinMatigara block under Siliguri Sub Division, P.H.E. Dte. (Part-B). (2ND CALL). Sl. No. 01. | 874/SWSD | 21/07/2022 | 85 | DEBASHIS SINHA | 109.33 | 0 | 0 | 75
103 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Laying distribution system of pipeline at Jhauguri at Chamta and adjoining mouzas Water Supply Scheme under Matigara block under Siliguri Sub Division, P.H.E Dte.(Part E). Sl. No. 17. | 860/SWSD | 21/07/2022 | 75 | BISWADEEP CONSTRUCTION | 71.84 | 0 | 0 | 92
104 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Material Requisition To Resource Division | 2177/SWSD | 11/02/2022 | 0 | Resource Division | 43.55 | 0 | 0 | 0
105 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Material Requisition To Resource Division | 1454/SWSD | 29/09/2022 | 0 | Resource Division | 14.43 | 0 | 0 | 0
106 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
107 | DARJEELING | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. I under MATIGARA CCC, [APPLICATION NO. 4003058415, Reference ID : 402932670] | BP/22-23/124 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
108 | DARJEELING | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. II under MATIGARA CCC, [APPLICATION NO. 4003049182, Reference ID : 402926291] | BP/22-23/124 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
109 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Laying distribution system of pipeline (Part-C) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-C). (2ND CALL). Sl. No. 02. | 875/SWSD | 21/07/2022 | 75 | M/S UTPAL CHAKRABORTY & CO. | 78.93 | 0 | 0 | 70
110 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Laying distribution system of pipeline (Part-D) at Chamta & adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-D). Sl. No. 13. | 871/SWSD | 21/07/2022 | 80 | NARENDRA KUMAR | 89.17 | 0 | 0 | 80
111 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 0 | 100
112 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Laying distribution system of pipeline (Part-E) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-E). (2ND CALL) Sl. No. 03. | 876/SWSD | 21/07/2022 | 1043 | SUBIR CH. CHOWDHURY | 104.02 | 0 | 0 | 92
113 | DARJEELING | Northern Mechanical | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 109/NMD | 03/02/2023 | 30 | MAA ENTERPRISES | 10.96 | 0 | 0 | 100
114 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , SM/10107 | Augmentation | Soil Investigation of Champta PWSS for Construction of 350 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | 391/SSD | 20/07/2022 | 20 | G. MITRA & ASSOCIATES | 1.03 | 0 | 0 | 90
115 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Bairatisal W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 06. | 833/SWSD | 13/08/2021 | 25 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 0 | 100
116 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-111 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.2 | 0 | 0 | 0
117 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.3 | 0 | 0 | 0
118 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1328/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.46 | 0 | 0 | 88
119 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1330/SWSD | 14/09/2022 | 25 | M/S K. R. S. CONSTRUCTION | 15.45 | 0 | 0 | 0
120 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Material Requisition To Resource Division | 1453/SWSD | 29/09/2022 | 0 | Resource Division | 27.72 | 0 | 0 | 0
121 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Material Requisition To Resource Division | 130/SWSD | 13/04/2022 | 0 | Resource Division | 14.63 | 0 | 0 | 0
122 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Material Requisition To Resource Division | 2173/SWSD | 11/02/2022 | 0 | Resource Division | 34.95 | 0 | 0 | 0
123 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Hiring 1 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (WITH AIR CONDITION ) fore office of the Executive Engineer, Siliguri W/S division PHE Dte. for the period from 01.09.2021 to 28.02.2022 | BP-2022-23-119 | 20/02/2023 | 0 | SUBIR CH. CHOWDHURY | 1.5 | 0 | 0 | 0
124 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
125 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | New Service Connection Charge for AUG BAIRATISAL,T/W No. II,ZONE-II under SHIVMANDIR CCC [APPLICATION NO. 4003312875 , Reference ID : 403140527] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.31 | 0 | 0 | 0
126 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | New Service Connection Charge for AUG OF BAIRATISAL, T/W No. I, ZONE-II, under SHEVMANDIR CCC [APPLICATION NO. 4003312877 , Reference ID : 403140528] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.29 | 0 | 0 | 0
127 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Construction of 550 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying Rising Main, laying distribution pipeline with Functional household tap connection (FHTC), construction of 2 (two) nos. Pump House (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos tube well (ODEX-165 method) and boundary wall for BAIRATISAL PWSS (Zone-II), Block Matigara Dist. Darjeeling under Siliguri W/S Division, PHE | 1204/SWSD | 11/08/2023 | 767 | BRM DEVELOPERS | 527.89 | 0 | 0 | 20
128 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - II PIPED WATER SUPPLY SCHEME , SM/10108 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - II (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 111/NMD | 03/02/2023 | 910 | CHOWDHURY AND BASU ENTERPRISE | 20.36 | 0 | 0 | 100
129 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin , SM/09078 | Retrofitting | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | 386/SSD | 20/07/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 0 | 100
130 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin , SM/09078 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of July (16/07/24 to 26/07/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-129 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.32 | 0 | 0 | 0
131 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme for Dhulia,Singbhita,Dakua,Tharuvita,Dagdhu Mouza of Dhulia Piped W/S Scheme at Kharibari Block under Siliguri Sub Division, P.H.Engineerin , SM/09078 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August(20/08/24 to 29/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-128 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.35 | 0 | 0 | 0
132 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | PIPED WATER SUPPLY SCHEME FOR KOLBONG UNDER JAL SWAPNO PROGRAMME. (BLOCK-DARJEELING-PULBAZAR) | 610/NKWSMD | 26/05/2022 | 180 | HEMRAJ NIROLA | 80.89 | 0 | 0 | 0
133 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 | 681/NKWSMD | 31/05/2022 | 365 | THE ELECTRIC SPHERE | 2.47 | 0 | 0 | 45
134 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 0 | 0 | 95
135 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | (Continuation) Engagement of 01 (one) no. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Superintending Engineer, GTA, P.H.E. Dte from 01.06.2023 to 31.07.2023. | 378/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.39 | 0 | 0 | 100
136 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | (Continuation) Engagement of 02 (Two) nos. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2023 to 31.07.2023. | 377/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0 | 0 | 100
137 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/09/2023. | 848/NKWSMD | 28/07/2023 | 62 | THE ELECTRIC SPHERE | 0.93 | 0 | 0 | 100
138 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | Material Requisition To Resource Division | 1271/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
139 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong , SM/10834 | New | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | 851/NKWSMD | 28/07/2023 | 123 | THE ELECTRIC SPHERE | 0.87 | 0 | 0 | 90
140 | DARJEELING | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. , SM/10622 | Disaster | Permanent restoration and repair of pipeline track due to Landside triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Thockchu towards Delo Middle Army lake (Betweeen Chain No - 158 to 159) (Betweeen Chain No - 185 to 186) & (Chain No - 360&352) under Neorakhola W/S & Mtc. Division, P.H. E. Dte, Kalimpong | 109/NKWSMD | 13/04/2022 | 180 | JUSTINE BHUTIA | 97.16 | 0 | 0 | 100
141 | DARJEELING | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. , SM/10622 | Disaster | Permanent restoration of pipeline and pipeline track protection work on the eastern and the western side of the Lava lake by Jhora training along with relaying of pipeline of 406.4 mm (O.D) MSERW pipeline damaged due to incessant rainfall of monsoon under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1956/NKWSMD | 20/12/2022 | 180 | BHUTIA AND SONS | 97.78 | 0 | 0 | 50
142 | DARJEELING | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. , SM/10622 | Disaster | Permanent restoration of approach stair including providing chequrred tiles, concrete pavers and protection walls in the shade area and protection walls on hill side and valley side of the approach road to open ground reservoir at Lava along with laying of pipe line of 406.4 mm (O.D) MSERW pipeline at of Lava OGR, Lava, Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1959/NKWSMD | 20/12/2022 | 180 | THUPDEN BHUTIA | 74.36 | 0 | 0 | 50
143 | DARJEELING | Neorakhola W/S & Mtc.Div. | Permanent restoration and repair of pipeline and pipeline track due to landslide triggered by incessant rainfall on 19.10.2021 & 20.10.2021 from Neora Source to Thokchu and Thokchu to Delo Middle lake, under Neorakhola Water Supply & Mtc. Division. P.H.E. , SM/10622 | Disaster | Permanent restoration of Guard Shed, brick boundry walls and chain link fencing along Lava Gorubathan road along with laying of pipe line of 406.4 mm (O.D) MSERW along with fitting of valves at outlet head works site of Lava OGR, Lava. Kalimpong under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 1957/NKWSMD | 20/12/2022 | 180 | THUPDEN BHUTIA | 78.38 | 0 | 0 | 100
144 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. , SM/11394 | Retrofitting | Material Requisition To Resource Division | 1909/NKWSMD | 15/12/2022 | 0 | Resource Division | 8.41 | 0 | 0 | 0
145 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. , SM/11394 | Retrofitting | Material Requisition To Resource Division | 2593/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.41 | 0 | 0 | 0
146 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. , SM/11394 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Teesta Valley, GP - Rungli, Block - Rungli Rungliot. | 952/NKWSMD | 12/07/2022 | 658 | NAVRATNA CONSTRUCTION CO | 167.77 | 0 | 0 | 92
147 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12366 | New | Material Requisition To Resource Division | 2556/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.37 | 0 | 0 | 0
148 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12366 | New | Material Requisition To Resource Division | 2071/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0 | 0
149 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12366 | New | Material Requisition To Resource Division | 2723/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.37 | 0 | 0 | 0
150 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12366 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR ROLAK KHASMAHAL & LONKU KHASMAHAL UNDER KURSEONG BLOCK DISTRICT-DARJEELING UNDER KURSEONG DIVISION. | 656/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 83.76 | 0 | 0 | 0
151 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rolak Khasmahal & Lonku Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12366 | New | Surface water based Rolak Khasmahal & Lonku Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District. | 2494/NKWSMD | 09/02/2023 | 1405 | VINAYAK CONSTRUCTION | 1016.14 | 0 | 0 | 100
152 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Material Requisition To Resource Division | 2024/SWSD | 16/12/2022 | 0 | Resource Division | 17.86 | 0 | 0 | 0
153 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | 857/SWSD | 21/07/2022 | 30 | TUSHAR KANTI SEAL | 29.64 | 0 | 0 | 90
154 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
155 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. | 308/SSD | 13/08/2020 | 0 | SUDIP BASAK | 0.88 | 0 | 0 | 0
156 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Material Requisition To Resource Division | 1467/SWSD | 29/09/2022 | 0 | Resource Division | 20.24 | 0 | 0 | 0
157 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Continuation order for hiring of 1 (one) no. Maxi Cab with engine capacity less than or Equal to 2000 CC (with Air Condition) for the office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022 (for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte.) | BP-2022-23-118 | 20/02/2023 | 0 | HIMADRI DAM | 1.45 | 0 | 0 | 0
158 | DARJEELING | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | New Service Connection Charge for CHOTO DILSARAMJOTE W/S Scheme, T/W No. III, Zone-II under UTTAR RAMDHAN CCC, [APPLICATION NO. 4003055461, Reference ID : 402933290] | BP/22-23/137 | 01/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.54 | 0 | 0 | 0
159 | DARJEELING | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | New Service Connection Charge for UTTAR RAMDHAN, ZONE-I,T/W -I, under NAXALBARI CCC, [APPLICATION NO. 4003079475, Reference ID : 402958536] | BP/22-23/137 | 01/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
160 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | 856/SWSD | 21/07/2022 | 100 | PALLAB BHOWAL | 162.34 | 0 | 0 | 30
161 | DARJEELING | Northern Mechanical | AUGMENTATION OF UTTAR RAMDHAN ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10477 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR RAMDHAN WATER SUPPLY SCHEME, (ZONE-I) TW No. I AND II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 106/NMD | 03/02/2023 | 30 | S.P. ENTERPRISE | 32.98 | 0 | 0 | 50
162 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Material Requisition To Resource Division | 2041/SWSD | 16/12/2022 | 0 | Resource Division | 111.41 | 0 | 0 | 0
163 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Sinking of 01(one) No Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd Tube well site for Augmentation of Dumriguri Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2166/SWSD | 30/12/2022 | 10 | M/S K. R. S. CONSTRUCTION | 8.14 | 0 | 0 | 100
164 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Repairing Of Damaged Pipe Line alongwith House Connections at Airport More Sansad, Lokhnath nagar, Bhujiyapani under Dumriguri Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 962/SWSD | 24/07/2023 | 15 | U.K CONSTRUCTIONS | 4.47 | 0 | 0 | 100
165 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Material Requisition To Resource Division | 1459/SWSD | 29/09/2022 | 0 | Resource Division | 19.64 | 0 | 0 | 0
166 | DARJEELING | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | New Service Connection Charge for DUMRIGURI, TW No. I, (REJU) BAGDOGRA CCC [APPLICATION NO.4003151289 , Reference ID : 403013234] | BP/23-24/28 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
167 | DARJEELING | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1475/NMD | 17/08/2023 | 30 | RAJEEV RANJAN OJHA | 23 | 0 | 0 | 30
168 | DARJEELING | Northern Mechanical | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Infrastructure Cost for DUMRIGURI (REJU) , under BAGDOGRA CCC , [APPLICATION NO. 100000094733, Reference ID : 860287023] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.72 | 0 | 0 | 0
169 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Work Order for Repairing of 350 Cu.M. R.C.C Elevated Reservoir, 20 mtrs. Staging Height at the Head Work Site, Laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), Construction of one number pump house (3.00 X 3.60m), Sinking of 01 (one) no tubewell (ODEX-165 method) and Boundary wall for Dumriguri PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri Water Supply Division, P.H.E. Dte. | 1978/SWSD | 26/10/2023 | 767 | DRISHTI CONSTRUCTION | 529.56 | 0 | 0 | 80
170 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , SM/10476 | Augmentation | Acceptance cum Work Order for Additional Work (F.H.T.C , Paverblock Pavement etc ), under JJM/Jal Swapna in connection with rejuvenation of DAMDAMA PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | 1233/SWSD | 24/04/2025 | 45 | KAMAL GHOSH | 4.73 | 0 | 0 | 0
171 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA , SM/10798 | New | Material Requisition To Resource Division | 2068/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.04 | 0 | 0 | 0
172 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Santa Bhawan & Rajbari Lower under Kurseong Sub Division ,PHED,GTA , SM/10798 | New | SURFACE WATER BASED SANTA BHAWAN & RAJBARI LOWER PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | 1117/NKWSMD | 05/08/2022 | 1195 | BOBBY PRADHAN | 117.24 | 0 | 0 | 50
173 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA , SM/10805 | New | Material Requisition To Resource Division | 1066/NKWSMD | 13/09/2023 | 0 | Resource Division | 0.42 | 0 | 0 | 0
174 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Mani Khope under Kurseong Sub Division ,PHED,GTA , SM/10805 | New | SURFACE WATER BASED MANI KHOPE PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 1749/NKWSMD | 25/11/2022 | 265 | ROSHAN BISWAKARMA | 78.65 | 0 | 0 | 100
175 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA , SM/10807 | New | Material Requisition To Resource Division | 1317/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
176 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA , SM/10807 | New | Material Requisition To Resource Division | 1258/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0 | 0
177 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA , SM/10807 | New | SURFACE WATER BASED LAPCHER (ROHINI) PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 603/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 63.44 | 0 | 0 | 100
178 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA , SM/10803 | New | Material Requisition To Resource Division | 1315/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.57 | 0 | 0 | 0
179 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA , SM/10803 | New | Material Requisition To Resource Division | 2056/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.57 | 0 | 0 | 0
180 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Marchebung under Kurseong Sub Division ,PHED,GTA , SM/10803 | New | SURFACE WATER BASED MARCHEBUNG PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | 602/NKWSMD | 26/05/2022 | 622 | ROSHAN BISWAKARMA | 60.38 | 0 | 0 | 100
181 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA , SM/10828 | New | Material Requisition To Resource Division | 2062/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.46 | 0 | 0 | 0
182 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA , SM/10828 | New | Material Requisition To Resource Division | 2812 | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0 | 0
183 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA , SM/10828 | New | Piped Water Supply Scheme for Lower Lonku under Kurseong Sub-Division, P.H.E.D. GTA. | 831/NKWSMD | 30/06/2022 | 607 | BIKRAM RAI | 79.8 | 0 | 0 | 100
184 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Lonku under Kurseong Sub Division ,PHED,GTA , SM/10828 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | 2410/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 2.17 | 0 | 0 | 0
185 | DARJEELING | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - PHANSIDEWA , DISTRICT - DARJEELING , SM/10824 | New | Material Requisition To Resource Division | 1460/SWSD | 29/09/2022 | 0 | Resource Division | 4.89 | 0 | 0 | 0
186 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11317 | Retrofitting | Material Requisition To Resource Division | 1293/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.87 | 0 | 0 | 0
187 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull ( Gorkha Busty habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11317 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull (Gorkha Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | 835/NKWSMD | 30/06/2022 | 1260 | SAMIR THAPA | 10.11 | 0 | 0 | 80
188 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS , SM/11855 | New | WATER SUPPLY SCHEME FOR SUKHIA POKHARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW BLOCK UNDER DARJEELING DISTRICT. | 1525/NKWSMD | 17/10/2022 | 960 | SUMAN PRADHAN | 317.2 | 0 | 0 | 100
189 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SUKHIYAPOKHRI PWSS , SM/11855 | New | Additional Work for Providing FHTC under Jal Jeevan Mission for balance Household at Maneybhanjang Forest Village Gram Panchayat: Sukhia Simana Block: Jorebunglow Sukhiapokhri. | 1082/NKWSMD | 19/09/2023 | 210 | MOHAN MUKHIA | 55.31 | 0 | 0 | 75
190 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11943 | New | Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme in Kurseong Under Darjeeling District. | 2081/NKWSMD | 10/01/2023 | 348 | SUNRISE ENTERPRISES | 185.86 | 0 | 0 | 100
191 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11943 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Kurseong Division, P.H.E.D., GTA. | 160/AE-II/NKWSMD | 10/01/2024 | 357 | MS JAGANNATH PRASAD | 12.44 | 0 | 0 | 100
192 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MONTIVIOT TEA GARDEN FROM KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11943 | New | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 0 | 100
193 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11344 | New | Material Requisition To Resource Division | 1319/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0 | 0
194 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11344 | New | Material Requisition To Resource Division | 2066/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.74 | 0 | 0 | 0
195 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11344 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0 | 0
196 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11344 | New | PWS Scheme at Aringalae with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 955/NKWSMD | 12/07/2022 | 790 | LAL BAHADUR THAPA | 27.77 | 0 | 0 | 75
197 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Material Requisition To Resource Division | 2032/SWSD | 16/12/2022 | 0 | Resource Division | 1.97 | 0 | 0 | 0
198 | DARJEELING | Central Drilling | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
199 | DARJEELING | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Quotation Charges New service Connection at Purba Madati PWSS under NMD,PHE Dte. Application No - 4003339413 Ref Id- 403162854 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0 | 0
200 | DARJEELING | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Charges for New Service connection at Purba Madati PWSS,TW No- II under NMD , PHEW Dte. Application No- 4003498842 Ref ID- 403286657 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.19 | 0 | 0 | 0
201 | DARJEELING | Northern Mechanical | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1479/NMD | 17/08/2023 | 805 | RIPON DAS | 23.26 | 0 | 0 | 90
202 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , SM/12034 | Augmentation | Construction of 2 (two) Nos. Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size toilet, Rig bore 2 (two) Nos. big dia deep T/W by Odex-165 method of drilliig, boundary wall at 2 (two) sites. laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum/hr. at SATHBIL PASCHIM MADATI Mouza and 20 cu.m./hr opposite of MADATI HIGH SCHOOL) required platform and drain etc. for Rejuvenation at PURBA MADATI Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, P.H.E. Dte. | 1372/SWSD | 18/08/2023 | 948 | M/S G.C. CONSTRUCTION & CO. | 117.74 | 0 | 0 | 35
203 | DARJEELING | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Pathar Hirhirar Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 307/SSD | 09/06/2022 | 20 | SUBHANKAR GHOSH | 3.09 | 0 | 0 | 100
204 | DARJEELING | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Material Requisition To Resource Division | 2044/SWSD | 16/12/2022 | 0 | Resource Division | 30.96 | 0 | 0 | 0
205 | DARJEELING | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Construction of 200 Cu.M. capacity RCC Elevated Reservoir of 20 mtr. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells by ODEX-165, construction of pump houses with toilet, boundary wall at head works 2nd tubewell & 3rd Tubewell sites with necessary interconnection, providing FHTC with platform with other allied works under Jal Jeevan Mission for PATHAR HIRHIRAR CHHAT piped W/S scheme of Phansidewa Block under Siliguri Sub Division PHE Dte. ( Sl No. 08) | 859/SWSD | 12/07/2023 | 1131 | SUBIR CH. CHOWDHURY | 403.68 | 0 | 0 | 70
206 | DARJEELING | Siliguri W/S Division | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Material Requisition To Resource Division | 68/SWSD | 10/01/2024 | 0 | Resource Division | 8.57 | 0 | 0 | 0
207 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299733 ; Reference ID : 403131317] | BP/23-24/224 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.72 | 0 | 0 | 0
208 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | New Service Connection Charge for PATHAR HIRHIRAR CHHAT , T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313525, Reference ID : 403145696] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.79 | 0 | 0 | 0
209 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300848 ; Reference ID : 403131314] | BP/23-24/225 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.46 | 0 | 0 | 0
210 | DARJEELING | Central Drilling | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
211 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHAR HIRHIRAR CHHAT PIPED WATER SUPPLY SCHEME, TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1644/NMD | 29/09/2023 | 562 | PADMA ENGINEERING CO. | 20.85 | 0 | 0 | 90
212 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
213 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
214 | DARJEELING | Northern Mechanical | Pathar Hirhirar Chhat Piped Water Supply Scheme , SM/13508 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
215 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , SM/12038 | Augmentation | Material Requisition To Resource Division | 2028/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0 | 0
216 | DARJEELING | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , SM/12038 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 164/NMD | 17/02/2023 | 30 | MAA BHABOTARINE ENTERPRISE | 10.76 | 0 | 0 | 70
217 | DARJEELING | Northern Mechanical | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , SM/12038 | Augmentation | New Service Connection Charge for rrjuvenation of Dhulia PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144973 ; Reference ID : 403013028] | BP/23-24/11 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
218 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , SM/12038 | Augmentation | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under Jal Jeevan Mission in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri W/S Division, PHD Dte | 2536/SWSD | 18/09/2024 | 137 | KAMAL GHOSH | 7.7 | 0 | 0 | 80
219 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , SM/12038 | Augmentation | Acceptance cum Work Order for IMPROVEMENT OF EXISTING PIPELINE & FHTC DUE TO ROAD & DRAIN CONSTRUCTION at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under JJM/Jal Swapna in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri Sub Division, PHD Dte. | 1236/SWSD | 24/04/2025 | 30 | KAMAL GHOSH | 16.83 | 0 | 0 | 0
220 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 192 numbers of school under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte , SM/11356 | School | Creating gravity based Provision Of Drinking water from spring water source for 192 Numbers of School in Darjeeling Pulvazar Block under the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 959/NKWSMD | 12/07/2022 | 300 | HARI PRASAD CHETTRI | 620.25 | 0 | 0 | 0
221 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Plungdung Health Centre under Jorebunglow-Sukhiapokhri Block (Part-A) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 980/NKWSMD | 12/07/2022 | 30 | KIRAN NIROLA | 3.85 | 0 | 0 | 0
222 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Pulungdung Health Centre under Jorebunglow-Sukhiapokhri Block (Part-B) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 983/NKWSMD | 12/07/2022 | 30 | KAMAKHYA ENTERPRISES | 2.53 | 0 | 0 | 0
223 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Simana Sub- Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 971/NKWSMD | 12/07/2022 | 30 | KAMAKHYA ENTERPRISES | 2.53 | 0 | 0 | 0
224 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Chamong-Health Centre and Nagari Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 982/NKWSMD | 12/07/2022 | 30 | KIRAN NIROLA | 4.8 | 0 | 0 | 0
225 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Rangbhang Tarsing Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 979/NKWSMD | 12/07/2022 | 30 | NAVRATNA CONSTRUCTION CO | 1.87 | 0 | 0 | 0
226 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Dara Gaon Primary Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 981/NKWSMD | 12/07/2022 | 30 | KIRAN NIROLA | 3.85 | 0 | 0 | 0
227 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Dooteria Kallej Valley Health Centre & Rangbull Health Centre under Jorebunglow-Sukhiapokhri in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 978/NKWSMD | 12/07/2022 | 30 | NAVRATNA CONSTRUCTION CO | 4.26 | 0 | 0 | 100
228 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden , SM/11938 | New | Material Requisition To Resource Division | 2072/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0 | 0
229 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden , SM/11938 | New | Material Requisition To Resource Division | 322/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.69 | 0 | 0 | 0
230 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Rohini Tea Garden , SM/11938 | New | SURFACE WATER BASED ROHINI TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 100/NKWSMD | 28/04/2023 | 180 | RUKMANI ENGINEERING WORKS | 324.1 | 0 | 0 | 80
231 | DARJEELING | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Material Requisition To Resource Division | 1952/SWSD | 07/12/2022 | 0 | Resource Division | 13.74 | 0 | 0 | 0
232 | DARJEELING | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR BANSGAON KISMAT PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 255/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.31 | 0 | 0 | 100
233 | DARJEELING | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Issue of fuel for office Executive Engineer and Assistant Engineer Siliguri W/S Division PHE Dte. | BP-2023-24-141 | 15/12/2023 | 0 | SONA PETROL PUMP | 0.2 | 0 | 0 | 0
234 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR BANSGAON KISMAT (ZONE-I) TW No. I and II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1645/NMD | 29/09/2023 | 30 | SARKAR ELECTRIC | 20.65 | 0 | 0 | 85
235 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] | BP/23-24/274 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.16 | 0 | 0 | 0
236 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320186, Reference ID : 403148656] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.11 | 0 | 0 | 0
237 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No.I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003320164, Reference ID : 403149648] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0 | 0
238 | DARJEELING | Central Drilling | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
239 | DARJEELING | Siliguri W/S Division | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Construction Of 150 Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection ,rising main ,pump house (3 nos),IEP (2 nos.),Boundry wall, tube well and soil investigation test under Jal Jeevan Mission of UTTAR BANSGAON KISMAT Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | 976/SWSD | 25/07/2023 | 963 | MANAS KUMAR SAHA | 391.69 | 0 | 0 | 12
240 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
241 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
242 | DARJEELING | Northern Mechanical | Augmentation of Uttar Bansgaon Kismat Piped Water Supply Scheme , SM/13433 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
243 | DARJEELING | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | Material Requisition To Resource Division | 2035/SWSD | 16/12/2022 | 0 | Resource Division | 16.3 | 0 | 0 | 0
244 | DARJEELING | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BURAGANJ & JATUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 253/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.22 | 0 | 0 | 100
245 | DARJEELING | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003291407 ; Reference ID : 403123844] | BP/23-24/203 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.06 | 0 | 0 | 0
246 | DARJEELING | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003291396 ; Reference ID : 403123842] | BP/23-24/202 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
247 | DARJEELING | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
248 | DARJEELING | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
249 | DARJEELING | Siliguri W/S Division | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | Construction of Pump House 2 Nos., Rig bore 2 Nos. big dia T/W by Odex- 165 method, boundary walls, laying distribution system (HDPE pipe), rising main, providing FHTC & supplying fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (20 m cum/hr) and allied works at Augmentation of Buraganj & Jatru PWSS at Kharibari block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | 335/SWSD | 08/05/2023 | 635 | DEBRAJ ENTERPRISE | 228.26 | 0 | 0 | 100
250 | DARJEELING | Northern Mechanical | Augmentation of Buraganja & Jatru Piped Water Supply Scheme , SM/13393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BURAGANJA and JATRU PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1647/NMD | 29/09/2023 | 641 | SANJIB SAHA | 11.85 | 0 | 0 | 100
251 | DARJEELING | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME , SM/16162 | New | Material Requisition To Resource Division | 203/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.03 | 0 | 0 | 0
252 | DARJEELING | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME , SM/16162 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR LATPANCHAR FOREST, UNDER JAL JEEVAN MISSION | BP-2024-25-281 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.3 | 0 | 0 | 0
253 | DARJEELING | Neorakhola W/S & Mtc.Div. | LATPANICHAR PIPED WATER SUPPLY SCHEME , SM/16162 | New | WATER SUPPLY SCHEME FOR LATPANICHAR FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | 120/NKWSMD | 28/04/2023 | 905 | MS. SURYA I PVT. LTD COMPANY | 239.52 | 0 | 0 | 80
254 | DARJEELING | Northern Mechanical | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1666/NMD | 29/09/2023 | 30 | MAA ENTERPRISES | 10.31 | 0 | 0 | 0
255 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Material Requisition To Resource Division | 204/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0 | 0
256 | DARJEELING | Central Drilling | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
257 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 0 | 50
258 | DARJEELING | Northern Mechanical | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | New Service Connection Charge for BIRSING, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003300023 ; Reference ID : 403131327] | BP/23-24/228 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0 | 0
259 | DARJEELING | Central Drilling | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
260 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Acceptance cum Work order Laying distribution system along with boring of new tubewells by ODEX-165, construction of pump houses, boundary walls at 3rd and 4th tubewell site and other allied works inconnection with Augmentation of BIRSING Piped Water Supply Scheme at Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. | 3324/SWSD | 09/12/2024 | 403 | M/S G.C. CONSTRUCTION & CO. | 53.95 | 0 | 0 | 12
261 | DARJEELING | Northern Mechanical | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
262 | DARJEELING | Northern Mechanical | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Installation of two tank chlorination system at BIRSING and other adjacent water supply scheme UNDER JJM under NAXALBARI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. | 82/SMSD | 07/02/2025 | 10 | CHOWDHURY AND BASU ENTERPRISE | 1.26 | 0 | 0 | 0
263 | DARJEELING | Northern Mechanical | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0 | 0
264 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , SM/15271 | Augmentation | Laying of additional pipeline installation of FHTC and Others allied Works at command area of Augmentation of Birsing Piped Water Supply Scheme inconnection with JJM under Siliguri W/S Division P.H.E. Dte.. | 2537/SWSD | 18/09/2024 | 151 | NARAYAN CH GHOSH | 4.81 | 0 | 0 | 100
265 | DARJEELING | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1660/NMD | 29/09/2023 | 30 | M/S ANJALI ENTERPRISE | 10.08 | 0 | 0 | 0
266 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Material Requisition To Resource Division | 2231/SWSD | 06/01/2023 | 0 | Resource Division | 1.97 | 0 | 0 | 0
267 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Material Requisition To Resource Division | 1800/SWSD | 30/09/2023 | 0 | Resource Division | 0.85 | 0 | 0 | 0
268 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | 3155/SWSD | 25/11/2024 | 30 | PALLAB BHOWAL | 26.07 | 0 | 0 | 0
269 | DARJEELING | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Charges for New service Connection at Bhalomanshi TW-II Under NMD,PHE Dte. Application No- 4003425977 Ref. ID- 403232535 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.54 | 0 | 0 | 0
270 | DARJEELING | Central Drilling | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
271 | DARJEELING | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
272 | DARJEELING | Northern Mechanical | AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , SM/15273 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
273 | DARJEELING | Neorakhola W/S & Mtc.Div. | LODHAMA PIPED WATER SUPPLY SCHEME. , SM/15872 | New | Material Requisition To Resource Division | 329/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
274 | DARJEELING | Neorakhola W/S & Mtc.Div. | LODHAMA PIPED WATER SUPPLY SCHEME. , SM/15872 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
275 | DARJEELING | Neorakhola W/S & Mtc.Div. | LODHAMA PIPED WATER SUPPLY SCHEME. , SM/15872 | New | WATER SUPPLY SCHEME FOR LODHOMA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 88/NKWSMD | 27/04/2023 | 600 | KAMAL AND COMPANY | 157.57 | 0 | 0 | 80
276 | DARJEELING | Neorakhola W/S & Mtc.Div. | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme , SM/16142 | New | Material Requisition To Resource Division | 759/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.38 | 0 | 0 | 0
277 | DARJEELING | Neorakhola W/S & Mtc.Div. | JAMADAR BHITA KHASMAHAL PART-II Piped Water Supply Scheme , SM/16142 | New | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 0 | 70
278 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | Material Requisition To Resource Division | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 7.53 | 0 | 0 | 0
279 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | Material Requisition To Resource Division | 1188/NKWSMD | 06/10/2023 | 0 | Resource Division | 7.53 | 0 | 0 | 0
280 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | payment for wbsedcl | BP-2023-24-478 | 28/01/2024 | 0 | WBSEDCL | 6.1 | 0 | 0 | 0
281 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | payment for wbsedcl | BP-2023-24-477 | 28/01/2024 | 0 | WBSEDCL | 4.54 | 0 | 0 | 0
282 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | WATER SUPPLY SCHEME FOR PANIGHATA PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 110/NKWSMD | 28/04/2023 | 900 | YAMA CONSTRUCTIONS LLP | 282.78 | 0 | 0 | 85
283 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANIGHATA Piped Water Supply Scheme , SM/16144 | New | ADDITIONAL WORK FOR PANIGHATA PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT DARJEELING, KURSEONG DIVISION PHED-GTA. | 161/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 52.49 | 0 | 0 | 80
284 | DARJEELING | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Jogibhita Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 411/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0 | 0
285 | DARJEELING | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Material Requisition To Resource Division | 209/SWSD | 25/04/2023 | 0 | Resource Division | 23.71 | 0 | 0 | 0
286 | DARJEELING | Central Drilling | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
287 | DARJEELING | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Material Requisition To Resource Division | 81/SWSD | 10/01/2024 | 0 | Resource Division | 6.67 | 0 | 0 | 0
288 | DARJEELING | Northern Mechanical | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Infrastructure Cost for JOGIBHITA T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323751, Reference ID : 403152325] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.32 | 0 | 0 | 0
289 | DARJEELING | Northern Mechanical | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Infrastructure Cost for JOGIBHITA T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323752, Reference ID : 403152314] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.1 | 0 | 0 | 0
290 | DARJEELING | Central Drilling | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
291 | DARJEELING | Siliguri W/S Division | JOGIBHITA PIPED WATER SUPPLY SCHEME , SM/15928 | New | Part Work order for 150 cu.m capacity R.C.C. elevated reservoir, 20 mtrs staging height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos), IEP, boundary wall and tubewell under Jal Jeevan Mission for Jogibhita Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 1979/SWSD | 26/10/2023 | 979 | M/S UTPAL CHAKRABORTY & CO. | 271.29 | 0 | 0 | 25
292 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DAMDAMA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15857 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
293 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME , SM/15894 | New | Material Requisition To Resource Division | 204/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.59 | 0 | 0 | 0
294 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM FOREST PIPED WATER SUPPLY SCHEME , SM/15894 | New | WATER SUPPLY SCHEME FOR MAHAL DHIRAM FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 122/NKWSMD | 28/04/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 250.28 | 0 | 0 | 85
295 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. , SM/15895 | New | Material Requisition To Resource Division | 441/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.15 | 0 | 0 | 0
296 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. , SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM - 15895] | BP-2024-25-234 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
297 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. , SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM NO - 15895] | BP-2024-25-235 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
298 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sevok Hill Forest area under Kurseong Block. , SM/15895 | New | WATER SUPPLY SCHEME FOR SEVOK HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 434/NKWSMD | 06/06/2023 | 605 | SRINIWAS AGARWAL | 216.18 | 0 | 0 | 85
299 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16352 | New | Material Requisition To Resource Division | 247/NKWSMD | 12/05/2023 | 0 | Resource Division | 4.4 | 0 | 0 | 0
300 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16352 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0 | 0
301 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN,IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16352 | New | WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 107/NKWSMD | 28/04/2023 | 605 | SRINIWAS AGARWAL | 690.58 | 0 | 0 | 100
302 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/16629 | New | Material Requisition To Resource Division | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 1.77 | 0 | 0 | 0
303 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR ALOOBARI PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/16629 | New | WATER SUPPLY SCHEME FOR ALOOBARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. | 115/NKWSMD | 28/04/2023 | 840 | P. D. COMPANY | 577.74 | 0 | 0 | 100
304 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Continuation of Hiring of 1 (one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E. Dte. from 01.09.2022 to 30.11.2022 (With Engine Capacity less than or equal to 2000 CC) (Vehicle no. WB 76A4921) | 439/SSD | 31/08/2022 | 91 | SUDIP BASAK | 0.44 | 0 | 0 | 100
305 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 245/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.87 | 0 | 0 | 100
306 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Material Requisition To Resource Division | 2199/SWSD | 04/01/2023 | 0 | Resource Division | 31.91 | 0 | 0 | 0
307 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Material Requisition To Resource Division | 1799/SWSD | 30/09/2023 | 0 | Resource Division | 33.55 | 0 | 0 | 0
308 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 0 | 50
309 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION AND ASSISTANT ENGINEER PHE DTE | BP-2023-24-147 | 09/01/2024 | 0 | SONA PETROL PUMP | 0.53 | 0 | 0 | 0
310 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA, T/W No. I, ZONE-II, under KHARIBARI CCC, [APPLICATION NO. 4003319471, Reference ID : 403145974] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0 | 0
311 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA Zone-III,TW- I under KHARIBARI CCC | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.5 | 0 | 0 | 0
312 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte. | BP-2023-24-154 | 09/01/2024 | 0 | SUDIP BASAK | 0.99 | 0 | 0 | 0
313 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | New Service Connection Charge for BARSADBHITA, T/W No. II, ZONE- II, under KHARIBARI CCC, [APPLICATION NO. 4003319623, Reference ID : 403147073] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.54 | 0 | 0 | 0
314 | DARJEELING | Central Drilling | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
315 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site (Zn-II) including distribution system all zones (HDPE) with Rising Main, Rig bore 3 nos. big dia T/W by Odex-165 method (Zn-II, III), Providing Functional Household Connection (FHTC), Pump House 3 Nos., Blower Room, IEP (Zone-III-30, Zn-II 30) cu.m/hr, Boundary Walls, Soil Testing & all repair works at Zone-I & Zn-II and allied works for Augmentation of BARSADVITA PWSS Kharibari block under Siliguri Sub Division, P.H.E. Dte. | 1192/SWSD | 10/08/2023 | 753 | RAMESH AGARWAL | 572.07 | 0 | 0 | 60
316 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
317 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
318 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
319 | DARJEELING | Northern Mechanical | AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME , SM/15924 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BARSADBHITA PIPED, (Zone-II) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1577/NMD | 08/09/2023 | 530 | DIPALI CONSTRUCTION | 25.01 | 0 | 0 | 100
320 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PIPED WATER SUPPLY SCHEME , SM/15653 | New | Material Requisition To Resource Division | 2893/NKWSMD | 29/03/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
321 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PIPED WATER SUPPLY SCHEME , SM/15653 | New | Piped Water Supply Scheme for Sukna under Kurseong Division. Scheme Code - 15653 TSM/017746 | BP-2024-25-98 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0 | 0
322 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PIPED WATER SUPPLY SCHEME , SM/15653 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PWSS TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | 2874/NKWSMD | 23/03/2023 | 635 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 241.94 | 0 | 0 | 43
323 | DARJEELING | Neorakhola W/S & Mtc.Div. | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. , SM/15878 | New | Material Requisition To Resource Division | 152/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.37 | 0 | 0 | 0
324 | DARJEELING | Neorakhola W/S & Mtc.Div. | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. , SM/15878 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
325 | DARJEELING | Neorakhola W/S & Mtc.Div. | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. , SM/15878 | New | ADDITIONAL WORK FOR NAMLA BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-DARJEELING PULBAZAR DISTRICT-DARJEELING. | 2357/NKWSMD | 19/12/2024 | 60 | SAGARMATHA CONSTRUCTION CO. | 10.39 | 0 | 0 | 0
326 | DARJEELING | Neorakhola W/S & Mtc.Div. | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. , SM/15878 | New | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 0 | 100
327 | DARJEELING | Neorakhola W/S & Mtc.Div. | NAMLA BUSTY PIPED WATER SUPPLY SCHEME. , SM/15878 | New | WATER SUPPLY SCHEME FOR NAMLA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 119/NKWSMD | 28/04/2023 | 728 | SAGARMATHA CONSTRUCTION CO. | 228.41 | 0 | 0 | 80
328 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/18282 | New | Material Requisition To Resource Division | 815/NKWSMD | 24/07/2023 | 0 | Resource Division | 7.71 | 0 | 0 | 0
329 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/18282 | New | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 719/NKWSMD | 18/07/2023 | 1036 | SRINIWAS AGARWAL | 1473.72 | 0 | 0 | 65
330 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18633 | New | PAYMENT FOR WBSEDCL | BP-2023-24-533 | 26/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0 | 0
331 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18633 | New | PAYMENT FOR WBSEDCL | BP-2023-24-531 | 26/02/2024 | 0 | WBSEDCL | 6.19 | 0 | 0 | 0
332 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18633 | New | PAYMENT FOR WBSEDCL | BP-2023-24-532 | 26/02/2024 | 0 | WBSEDCL | 5.88 | 0 | 0 | 0
333 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18633 | New | WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 883/NKWSMD | 03/08/2023 | 365 | GARGO TRADERS | 1359.83 | 0 | 0 | 80
334 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN(GAYABARI),IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18633 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 591/NKWSMD | 29/04/2025 | 180 | ALLIED INSTRUMENTS | 55.54 | 0 | 0 | 0
335 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING , SM/18635 | New | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 31/11/2023. | 1153/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.94 | 0 | 0 | 0
336 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING , SM/18635 | New | PAYMENT FOR WBSEDCL | BP-2023-24-536 | 26/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0 | 0
337 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING , SM/18635 | New | WATER SUPPLY SCHEME FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 884/NKWSMD | 03/08/2023 | 975 | GARGO TRADERS | 1832.72 | 0 | 0 | 75
338 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY FOR SOURENA TEA ESTATE,IN MIRIK BLOCK UNDER DARJEELING , SM/18635 | New | ADDITIONAL WORK FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK: UNDER DARJEELING DISTRICT.UNDER KURSEONG DIVISION PHED-GTA. | 593/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 64.04 | 0 | 0 | 0
339 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS , SM/18724 | New | Material Requisition To Resource Division | 962/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.29 | 0 | 0 | 0
340 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS , SM/18724 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 2351/NKWSMD | 19/12/2024 | 180 | THUPDEN BHUTIA | 117.43 | 0 | 0 | 0
341 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PWSS , SM/18724 | New | WATER SUPPLY SCHEME FOR TUKDAH,LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 935/NKWSMD | 16/08/2023 | 365 | THUPDEN BHUTIA | 1654.3 | 0 | 0 | 80
342 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte | 1029/SWSD | 26/07/2023 | 60 | PANKAJ KUNDU | 4.58 | 0 | 0 | 0
343 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-F) | 1033/SWSD | 26/07/2023 | 45 | S.K. BANIK | 9.71 | 0 | 0 | 0
344 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | 1024/SWSD | 26/07/2023 | 60 | SHREYANSH AUTOMOBILE | 7.63 | 0 | 0 | 0
345 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | 1026/SWSD | 26/07/2023 | 60 | M/S SHIB ENTERPRISE | 7.72 | 0 | 0 | 0
346 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 3rd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte. | 1030/SWSD | 26/07/2023 | 60 | CHOWDHURY & BASU ENTERPRISE | 4.74 | 0 | 0 | 0
347 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | 1027/SWSD | 26/07/2023 | 60 | S.K. BANIK | 7.63 | 0 | 0 | 0
348 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Sche me (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-D). | 1233/SWSD | 14/08/2023 | 45 | ROYAL ENTERPRISE | 9.81 | 0 | 0 | 0
349 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | 1736/SWSD | 22/09/2023 | 45 | ABHIJIT CHANDA | 21.28 | 0 | 0 | 0
350 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Work Order for laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-II) Part-A under JJM Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | 1730/SWSD | 21/09/2023 | 90 | ARUN KUMAR SHRIVASTAVA | 111.73 | 0 | 0 | 0
351 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped water Supply Scheme (Zone-II) with Matigara Block under Siliguri Sub Division, P.H.E. Dte. | 1830/SWSD | 03/10/2023 | 45 | KULENDRA NATH BARMAN | 19.02 | 0 | 0 | 0
352 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-B) | 1883/SWSD | 09/10/2023 | 30 | M/S S.P. BISWAS | 4.85 | 0 | 0 | 0
353 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance Cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-C) | 2050/SWSD | 07/11/2023 | 30 | CHOWDHURY & BASU ENTERPRISE | 4.85 | 0 | 0 | 0
354 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance Cum Work Order for Construction of boundary wall at head work site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara block under Siliguri Sub Division, PHE Dte. | 2034/SWSD | 06/11/2023 | 60 | SANJIB SAHA | 18.35 | 0 | 0 | 0
355 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance Cum Work Order for Providing Functional Household Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, PHE Dte. | 2035/SWSD | 06/11/2023 | 45 | M/S DIBYA CONSTRUCTION | 19.86 | 0 | 0 | 0
356 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PIPED KALKUT WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 261/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.68 | 0 | 0 | 100
357 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Material Requisition To Resource Division | 2285 | 11/12/2023 | 0 | Resource Division | 4.28 | 0 | 0 | 0
358 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Material Requisition To Resource Division | 1801/SWSD | 30/09/2023 | 0 | Resource Division | 142.4 | 0 | 0 | 0
359 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site at KALKUT Piped W/S Scheme (Zone-2) and FHTC Part-J under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | 1226/SWSD | 14/08/2023 | 535 | BUDDHADEV NAG | 164.68 | 0 | 0 | 1
360 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | 1735/SWSD | 22/09/2023 | 45 | ABHIJIT CHANDA | 21.28 | 0 | 0 | 31
361 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME, (ZONE-II) TW NO I, II, III AND (ZONE-III) TW NO I, II, III in the district of DARJEELING under Northern Mechanical Division, PHE Dte. | 1665/NMD | 29/09/2023 | 30 | ORIENTAL ENGINEERING CO. | 57.97 | 0 | 0 | 30
362 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for providing functional house hold tap connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-I). | 1779/SWSD | 12/07/2024 | 45 | SWAPAN CHANDRA DAS | 19.86 | 0 | 0 | 0
363 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of pump house with toilet at Head Works site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigaraa Block under Siliguri Sub Division, P.H.E. Dte. | 1028/SWSD | 26/07/2023 | 60 | PANKAJ KUNDU | 5.63 | 0 | 0 | 90
364 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Charges for new service connection at T.W No-III,zone-II of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0 | 0
365 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | New Service Connection Charge for KALKUT, T/W No. I, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302654 ; Reference ID : 403132349] | BP/23-24/279 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.49 | 0 | 0 | 0
366 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Charges for new service connection at T.W No-I,zone-III of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.35 | 0 | 0 | 0
367 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | FUEL FOR OFFICE VECHILE OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION PHE DTE | BP-2023-24-161 | 29/01/2024 | 0 | SONA PETROL PUMP | 0.3 | 0 | 0 | 0
368 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | New Service Connection Charge for KALKUT, T/W No. II, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302722 ; Reference ID : 4003132350] | BP/23-24/278 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.36 | 0 | 0 | 0
369 | DARJEELING | Central Drilling | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
370 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | 1023/SWSD | 26/07/2023 | 615 | S.G.CONSTRUCTION | 7.63 | 0 | 0 | 0
371 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, Rising main and laying distribution system Part-A at KALKUT Piped W/S Scheme (Zone-I) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | 1404/SWSD | 21/08/2023 | 497 | M/S G.C. CONSTRUCTION & CO. | 152.43 | 0 | 0 | 90
372 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Laying distribution system Part-B and allied works at Kalkut Piped W/S Scheme (Zone-I) undere JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. | 1373/SWSD | 18/08/2023 | 310 | DEBASHIS SINHA | 226.29 | 0 | 0 | 60
373 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-III) under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, PHE Dte | 1241/SWSD | 16/08/2023 | 1013 | MANAS KUMAR SAHA | 358.73 | 0 | 0 | 29
374 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-3 Command area of Augmentation of Kalkut PWSS in connection with JJM under Siliguri W/S Division P.H.E.Dte. | 483/SWSD | 12/02/2025 | 30 | DEBASHIS SINHA | 15.2 | 0 | 0 | 0
375 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Construction of 550 cu.m. capacity R.C.C. Elevated, 20 mtrs. Staging height at the head works site and FHTC (Part-C) at KALKUT Piped W/S Scheme (Zone-3) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. (SL No.01) | 2616/SWSD | 23/09/2024 | 225 | BUDDHADEV NAG | 205.05 | 0 | 0 | 60
376 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Work order for Laying distribution system at Kalkut Piped Water Supply Scheme (Zone-II) Part-B under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | 2026/SWSD | 06/08/2024 | 180 | NARENDRA KUMAR | 128.48 | 0 | 0 | 30
377 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) under Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part A). | 1403/SWSD | 08/05/2025 | 60 | SAFTI PRIVATE LIMITED | 53.44 | 0 | 0 | 0
378 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
379 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
380 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-1 Command area of Augmentation of Kalkut PWSS inconnection with JJM under Siliguri W/S Division P.H.E.Dte. | 243/SWSD | 22/01/2025 | 30 | M/S G.C. CONSTRUCTION & CO. | 15.2 | 0 | 0 | 0
381 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) under Augmentation of Kalkut PWSS (Zone-II) under Matigara Block in connection with JJM under Siliguri W/S Division P.H.E.Dte. | 1239/SWSD | 24/04/2025 | 30 | BUDDHADEV NAG | 36.69 | 0 | 0 | 0
382 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum Work Order for Construction of Pump House, Boundary wall, IEP and Blower room and allied work for Augmentation Kalkut Zone-1within Matigara block in connection with JJM under Siliguri W/S Division PHE Dte. | 1349/SWSD | 02/05/2025 | 45 | BRM DEVELOPERS | 28.42 | 0 | 0 | 0
383 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
384 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) within Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part ¿ B). | 1094/SWSD | 11/04/2025 | 60 | SAFTI PRIVATE LIMITED | 58.79 | 0 | 0 | 0
385 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-II) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | 1025/SWSD | 26/07/2023 | 60 | A.B. GANAPATI CONSTRUCTION | 7.63 | 0 | 0 | 75
386 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-E) | 1032/SWSD | 26/07/2023 | 1027 | S.G.CONSTRUCTION | 9.71 | 0 | 0 | 100
387 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-A). | 1031/SWSD | 26/07/2023 | 675 | A.B. GANAPATI CONSTRUCTION | 4.85 | 0 | 0 | 100
388 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME , SM/18385 | Augmentation | Acceptance cum work order for construction of pump house (3.6 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, PHE Dte. | 102/SWSD | 15/01/2024 | 383 | ARATI SAHA | 4.82 | 0 | 0 | 88
389 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS , SM/13623 | New | Material Requisition To Resource Division | 2720/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.02 | 0 | 0 | 0
390 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS , SM/13623 | New | Material Requisition To Resource Division | 263/NKWSMD | 20/02/2024 | 0 | Resource Division | 2.17 | 0 | 0 | 0
391 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHAL DIRAM TEA GARDEN PWSS , SM/13623 | New | WATER SUPPLY SCHEME FOR MAHAL DIRAM TEA GARDEN PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 2655/NKWSMD | 28/02/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 212.76 | 0 | 0 | 85
392 | DARJEELING | Neorakhola W/S & Mtc.Div. | KANKIBONG PWSS , SM/18992 | New | WATER SUPPLY SCHEME FOR KANKIBONG PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 1290/NKWSMD | 17/10/2023 | 365 | SAGARMATHA CONSTRUCTION CO. | 785.44 | 0 | 0 | 10
393 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18820 | New | Material Requisition To Resource Division | 1174/NKWSMD | 05/10/2023 | 0 | Resource Division | 3.2 | 0 | 0 | 0
394 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18820 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.08.2024 to 31.08.2024. | 1346/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
395 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18820 | New | WATER SUPPLY SCHEME FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 1100/NKWSMD | 21/09/2023 | 365 | VINAYAK CONSTRUCTION | 1970.49 | 0 | 0 | 50
396 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR KALEJ VALLEY PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18820 | New | ADDITIONAL WORK FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA. | 654/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 142.77 | 0 | 0 | 0
397 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | Material Requisition To Resource Division | 52/NKWSMD | 09/01/2024 | 0 | Resource Division | 13.36 | 0 | 0 | 0
398 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | i)Hydrological study of Rungdong Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-I ii) Hydrological study of Jamboni River under Water Supply Scheme for Darjeeling Pulbazar Pumping-II iii) Hydrological study of Jhepi Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-III iv)Hydrological study of Balason Khola River (locally khown as Rangbhang Khola) under Water Supply Scheme for Mangarjung Tea Garden and other three villages (MVS), Block- Jorebunglow Sukhiapokhari. v) Hydrological study of Rangbhang River (Khola) Pumping water Supply Scheme for Mirik Municipal Town and EN-Route villages District- Darjeeling (under AMRUT) | BP-2024-25-179 | 01/08/2024 | 0 | JADAVPUR UNIVERSITY | 17.51 | 0 | 0 | 0
399 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | 414/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0 | 0
400 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | 413/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0 | 0
401 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - II SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | 134/NKWSMD | 28/01/2025 | 546 | SSN DEVELOPERS | 8170.65 | 0 | 0 | 15
402 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months for G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | 146/NKWSMD | 31/01/2025 | 150 | YAMA CONSTRUCTIONS LLP | 0.83 | 0 | 0 | 0
403 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | 942/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0 | 0
404 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-II PWSS , SM/18659 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | 943/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0 | 0
405 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS , SM/18792 | New | Material Requisition To Resource Division | 53/NKWSMD | 09/01/2024 | 0 | Resource Division | 9.98 | 0 | 0 | 0
406 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS , SM/18792 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
407 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS , SM/18792 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites),GLRs,Chlorine cum switch room , Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - III SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | 1653/NKWSMD | 11/09/2024 | 546 | YATERI CONSTRUCTIONS,JV OF YAMA CONSTRUCTIONS LLP(LEAD PARTNER),AROGYA ENT & BALAJI CONS. | 6744.68 | 0 | 0 | 40
408 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS , SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/08/2024 to 31/01/2025. Note: With effect from the date of issuing work order. | 1349/NKWSMD | 31/07/2024 | 180 | SUJIT DEB | 0.99 | 0 | 0 | 100
409 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING PULBAZAR PUMPING-III PWSS , SM/18792 | New | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | 147/NKWSMD | 31/01/2025 | 150 | SUJIT DEB | 0.83 | 0 | 0 | 0
410 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kashiram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 255/SSD | 17/05/2022 | 20 | ENVIROTECH SOLUTIONS | 4.05 | 0 | 0 | 100
411 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Material Requisition To Resource Division | 2291/SWSD | 11/12/2023 | 0 | Resource Division | 1.63 | 0 | 0 | 0
412 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Material Requisition To Resource Division | 1805/SWSD | 30/09/2023 | 0 | Resource Division | 7 | 0 | 0 | 0
413 | DARJEELING | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KASHIRAM PIPED WATER SUPPLY SCHEME, TW No.- I,II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1653/NMD | 29/09/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 23 | 0 | 0 | 0
414 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Material Requisition To Resource Division | 78/SWSD | 10/01/2024 | 0 | Resource Division | 22.19 | 0 | 0 | 0
415 | DARJEELING | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Quotation Charges New service Connection at Kashiram PWSS,TW-III under NMD,PHE Dte. Application No - 4003458955 Ref Id- 403256880 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 20.61 | 0 | 0 | 0
416 | DARJEELING | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | New Service Connection Charge for KASHIRAM , T/W No. II under PHANSIDAWA CCC, [APPLICATION NO. 4003317760, Reference ID : 403145866] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.26 | 0 | 0 | 0
417 | DARJEELING | Northern Mechanical | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | New Service Connection Charge for KASHIRAM , T/W No. I under PHANSIDAWA CCC, [APPLICATION NO. 4003317755, Reference ID : 403145742] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.28 | 0 | 0 | 0
418 | DARJEELING | Central Drilling | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
419 | DARJEELING | Siliguri W/S Division | KASHIRAM PIPED WATER SUPPLY SCHEME , SM/18613 | New | Construction of 350 cu.m. Capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main,construction of 3 nos. Big dia rig bore tube well by ODEX-165, Pump House, Iron Elemination Plant, Boundary Wall including Functiopnal Household Tap Connection at KASHIRAM Piped Water Supply Scheme (Zone I & II) undere Phansidewa block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte | 1366/SWSD | 18/08/2023 | 606 | UNIBRO INFRASERV PRIVATE LIMITED | 676.79 | 0 | 0 | 35
420 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) , SM/18647 | New | Material Requisition To Resource Division | 972/NKWSMD | 21/08/2023 | 0 | Resource Division | 10.32 | 0 | 0 | 0
421 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) , SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 1 - Sonada Khasmahal part 1] | 915/NKWSMD | 11/08/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1177.68 | 0 | 0 | 80
422 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) , SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 2 - Sonada Khasmahal part 2] | 916/NKWSMD | 11/08/2023 | 605 | M/S. ASHOK KUMAR PERIWAL | 1167.7 | 0 | 0 | 80
423 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) , SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 3 - Rongmook ceder (part), Oaks (part) & Ringtong tea garden (part)] | 917/NKWSMD | 11/08/2023 | 365 | TIKARAM SHARMA | 1263.3 | 0 | 0 | 85
424 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) , SM/18648 | New | Material Requisition To Resource Division | 975/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.24 | 0 | 0 | 0
425 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) , SM/18648 | New | SURFACE WATER BASED RANGMOOK CEDER TEA GARDEN (PART) AND OAKS TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN JOREBUNGLOW SUKHIAPOKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.DTE. | 912/NKWSMD | 11/08/2023 | 1025 | M/S. ASHOK KUMAR PERIWAL | 2166.21 | 0 | 0 | 80
426 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden , SM/18649 | New | Material Requisition To Resource Division | 967/NKWSMD | 21/08/2023 | 0 | Resource Division | 2.14 | 0 | 0 | 0
427 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden , SM/18649 | New | FOREST PAYMENT |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
428 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden , SM/18649 | New | FOREST PAYMENT | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0 | 0
429 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden , SM/18649 | New | SURFACE WATER BASED TINDHARIA & NARBUNG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSOENG BLOCK. | 919/NKWSMD | 11/08/2023 | 605 | SUNIT DEEP RAI | 1161.89 | 0 | 0 | 100
430 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden , SM/18649 | New | ADDITIONAL WORK FOR TINDHARIA & NORBUNG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED. | 496/NKWSMD | 09/04/2025 | 90 | SUNIT DEEP RAI | 17.57 | 0 | 0 | 0
431 | DARJEELING | Neorakhola W/S & Mtc.Div. | BHIRGAON DHARGAON PWSS , SM/18714 | New | WATER SUPPLY SCHEME FOR BHIRGAON DHARAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 893/NKWSMD | 07/08/2023 | 180 | RINZI SHERPA | 152.77 | 0 | 0 | 60
432 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block , SM/07425 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Bairbhita Habitation Bairvita Madanjote village Atal Habitation Atal village Nimubhita chat Habitation Nimuvita, village Minghara chat Habitation Minghar chhat of Damdama Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 04 | 1525/SWSD | 22/02/2021 | 25 | ARUN KUMAR SHRIVASTAVA | 20.95 | 0 | 0 | 75
433 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block , SM/07425 | Retrofitting | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Damdama, Grammani, Grammanir Chhat of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | 2364/SWSD | 08/03/2022 | 20 | DEBOL,S ENTERPRISE | 9.63 | 0 | 0 | 100
434 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Damdama Piped water Supply Scheme at Naxalbari Block , SM/07425 | Retrofitting | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Mingharer Chhat, Nimubhitar Chhat, Atal of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | 2363/SWSD | 08/03/2022 | 25 | ARUN KUMAR SHRIVASTAVA | 19.04 | 0 | 0 | 100
435 | DARJEELING | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) , SM/07046 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapno under Shyamdhan and adjoining mouas WS Scheme command area at Badra and Balijhora and laying wash out pipeline from 2nd T W IEP upto nearest culvert and also laying HDPE piped at Shyamdhan command area of the Shyamdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte. SL. NO. 07. | 1219/SWSD | 01/11/2021 | 20 | M/S SHIVAJI ROY | 12.99 | 0 | 0 | 100
436 | DARJEELING | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) , SM/07046 | Retrofitting | Providing functional household tap connection FHTC and laying 90 mm OD HDPE pipe from house of Dulal Biswas to house of Sunil Sikdar and house of Kalipada Mondal to Zamatulla SSK at village Shyamdhan and habitation Shyamdhan and allied worksw of the Shyamdhan piped WS scheme under Siliguri Sub Division PHE Dte Kharibari block. SL. NO. 08. | 1830/SWSD | 13/01/2022 | 15 | BUDDHADEV NAG | 6.5 | 0 | 0 | 100
437 | DARJEELING | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) , SM/07046 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
438 | DARJEELING | Siliguri W/S Division | roviding Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Shyamdhan, Saheburam, Badora and Balahi Jhora village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-A) , SM/07046 | Retrofitting | Material Requisition To Resource Division | 1672/SWSD | 28/12/2021 | 0 | Resource Division | 0.05 | 0 | 0 | 0
439 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Chayan Sing and Bhogbhita village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-B) , SM/07048 | Retrofitting | Laying 15 mm O.D. HDPE and 15 mm dia G.I. Pipe (excess quantity estimate) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapno under command area (village-Shyamdhan habitation-Shyamdhan (Part-B) of Shyamdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | 304/SWSD | 10/05/2022 | 25 | SHIVNATH DEY | 1.55 | 0 | 0 | 100
440 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Chayan Sing and Bhogbhita village of Shyamdhan and adjoining Mouza Piped water Supply Scheme (Part-B) , SM/07048 | Retrofitting | Shifting of LT POLE FOR CONSTRUCTION OF PHE WATER TANK | BP-2022-23-142 | 16/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.19 | 0 | 0 | 0
441 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Pelku (JL No-71) & Thiknikata (JL No.-74) Mouzas of Kawakhali Pipe water Supply Scheme , SM/07213 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection under Jal Jeevan Mission Programme for PELKU (JL No. 71) and TIKNIKATA (JL No. 74) mouzas of KAWAKHALI Piped Water Supply Scheme at Matigara block under Siliguri W/S Division, P.H.E. Dte.(1st CALL) | 1196/SWSD | 10/08/2023 | 75 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 74.02 | 0 | 0 | 0
442 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme , SM/07215 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
443 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme , SM/07215 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapna Programme for Purba Bansgaon Village of PURBA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART A | 696/SWSD | 02/08/2021 | 35 | AKASH ENTERPRISE | 30.21 | 23.08 | 76.4 | 100
444 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme , SM/07215 | Retrofitting | Laying of new PVC line at along with other repairing works at Matigara Habitation, Purba Bansgaon water supply scheme Phansidewa Block, Siliguri W/S Division,P.H.E Dte | 512/SSD | 16/11/2022 | 10 | SHIVNATH DEY | 0.36 | 0 | 0 | 100
445 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Bansgaon village of Purba Bansgaon Piped water Supply Scheme , SM/07215 | Retrofitting | Material Requisition To Resource Division | 1667/SWSD | 28/12/2021 | 0 | Resource Division | 2.13 | 0 | 0 | 0
446 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission & Jal Swapno Programme for bharatsing & Putimari of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. | 708/SWSD | 03/08/2021 | 90 | M/S UTPAL CHAKRABORTY & CO. | 21.03 | 0 | 0 | 100
447 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Additional work in connection with Providing FHTC under Jal Jeevan Mission and Jal Swapno Programme for Bharatsing and Putimari of Lalman Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | 2362/SWSD | 08/03/2022 | 15 | M/S UTPAL CHAKRABORTY & CO. | 6.9 | 0 | 0 | 0
448 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Hiring of I (one) nos Disel Motor CAB on monthly besis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..With effect from 25.08.2023 to 24.02.2024 .Total 184 days. | 1427/SWSD | 24/08/2023 | 184 | BUDDHADEV NAG | 0.88 | 0 | 0 | 100
449 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Further continuation order for hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.01.2024 to 31.07.2024 for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte. i.e. 07 (seven) months. | 2398/SWSD | 16/12/2023 | 213 | HIMADRI DAM | 1.03 | 0 | 0 | 0
450 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVWE ENGINEER SILIGURI W/S DIVISION PHE DTE | BP-2023-24-184 | 13/03/2024 | 0 | SONA PETROL PUMP | 1.4 | 0 | 0 | 0
451 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Continuation order of Hiring of I (one) nos Diesel Motor CAB on monthly basis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..for the month of 25/02/2024 to 22/08/2024 | 225/SWSD | 30/01/2024 | 180 | BUDDHADEV NAG | 0.88 | 0 | 0 | 0
452 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bharat Singh(JL No .- 102) & Putimari (JL-100) Mouza of Lalman Piped water Supply Scheme , SM/07216 | Retrofitting | Continuation order of Hiring of 01 (one) nos Disel Motor CAB on monthly basis for the Assistant Engineer-II, Office of the Executive Engineer under Siliguri W/S Division, P.H.E. Dte. for the month of 01.09.2024 to 28.02.2025. | 2161/SWSD | 21/08/2024 | 180 | BUDDHADEV NAG | 0.88 | 0 | 0 | 0
453 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme , SM/07217 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapno Programme for Rupandighi and Sahananda village of Guabari Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. (Part B). | 1008/SWSD | 11/12/2020 | 30 | UJJWAL ROY | 35.77 | 32.75 | 47.8 | 100
454 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme , SM/07217 | Retrofitting | Providing functional house hold tap connection under Jal Swapno programme for Guabari village of Guabari piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. No. 05. | 1827/SWSD | 13/01/2022 | 30 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 23.24 | 0 | 0 | 30
455 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme , SM/07217 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
456 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Guabari Piped water Supply Scheme , SM/07217 | Retrofitting | Material Requisition To Resource Division | 1669/SWSD | 28/12/2021 | 0 | Resource Division | 1.87 | 0 | 0 | 0
457 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme , SM/07035 | Retrofitting | Providing Functional House hold Tap Connection under Jal Swapna Programme for Madhya Bansgaon of MADHYA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART C | 692/SWSD | 02/08/2021 | 45 | M/S G.C. CONSTRUCTION & CO. | 38.43 | 0 | 0 | 0
458 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme , SM/07035 | Retrofitting | Providing Functional House hold Tap Connection under Jal Swapna Programme for Madhya Bansgaon of MADHYA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART D | 693/SWSD | 02/08/2021 | 35 | KAMAL GHOSH | 30.83 | 0 | 0 | 35
459 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-II) Piped water Supply Scheme , SM/07035 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
460 | DARJEELING | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME , SM/09426 | New | Material Requisition To Resource Division | 637/NKWSMD | 23/02/2022 | 0 | Resource Division | 2.36 | 0 | 0 | 0
461 | DARJEELING | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME , SM/09426 | New | FOREST PAYMENT | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0 | 0
462 | DARJEELING | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME , SM/09426 | New | FOREST PAYMENT |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
463 | DARJEELING | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME , SM/09426 | New | LOHAGARH WATER SUPPLY SCHEME FROM MANAY KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DARJEELING | 459/NKWSMD | 14/01/2022 | 2404 | SHREE VAISHNO ENTERPRISES | 153.57 | 0 | 0 | 80
464 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division , SM/10765 | Retrofitting | Material Requisition To Resource Division | 2575/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.84 | 0 | 0 | 0
465 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division , SM/10765 | Retrofitting | Material Requisition To Resource Division | 1261/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.84 | 0 | 0 | 0
466 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Connection Piped water supply scheme for SOOM 2nd Division , SM/10765 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Soom 2nd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009296 SM Code-SM/08936 | 555/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.91 | 0 | 0 | 100
467 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield , SM/10772 | Retrofitting | Material Requisition To Resource Division | 1362/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.59 | 0 | 0 | 0
468 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield , SM/10772 | Retrofitting | Material Requisition To Resource Division | 2614/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.59 | 0 | 0 | 0
469 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with retrofitting for PWS scheme for Dhupi Gari Bloomfield , SM/10772 | Retrofitting | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Dhupi gare, Bloomfield, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009472 SM Code-SM/08930 | 497/NKWSMD | 24/05/2022 | 222 | KIRAN SUBBA | 13.14 | 0 | 0 | 100
470 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. , SM/10261 | Retrofitting | Providing Functional household Tap Connection under JJM & JSP Programme for 8th & 9th M ile , Peshoke Road GP Lamahatta under DARJEELING Division PHED, GTA | BP-2022-23-50 | 20/05/2022 | 0 | KIRAN NIROLA | 5.7 | 0 | 0 | 0
471 | DARJEELING | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. , SM/10261 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0 | 0
472 | DARJEELING | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. , SM/10261 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0 | 0
473 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. , SM/10789 | New | Material Requisition To Resource Division | 2374/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.8 | 0 | 0 | 0
474 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. , SM/10789 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-129 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
475 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR SEPTIGURI KHELAGHAR TEA GARDEN UNDER BLOCK KURSEONG DISTRICT OF DARJEELING. , SM/10789 | New | WATER SUPPLY SCHEME FOR TWO NOS OF VILLAGES UNDER BLOCK KURSEONG DISTRICT OF DARJEELING [TSM NO - 10476 / 10473] 1. Septiguri Khelaghar tea garden 2. Pairikumari | 608/NKWSMD | 26/05/2022 | 240 | M/S KAMAK ENGINEERS AND CO. | 199.42 | 0 | 0 | 100
476 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) , SM/11378 | Retrofitting | Material Requisition To Resource Division | 1895/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.4 | 0 | 0 | 0
477 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) , SM/11378 | Retrofitting | Providing Functional Household Tap Connection by Strengthening mainline under Jal Jeevan Mission and Jal Swapno Programme for P.W.S Scheme at Sukhia Bazar, G.P - Sukhia Simana, Block - Jorebungalow Sukhia. | 938/NKWSMD | 12/07/2022 | 60 | KAMAKHYA ENTERPRISES | 33.83 | 0 | 0 | 0
478 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) , SM/11378 | Retrofitting | Material Requisition To Resource Division | 2577/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.4 | 0 | 0 | 0
479 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) , SM/11379 | Retrofitting | Material Requisition To Resource Division | 1906/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.48 | 0 | 0 | 0
480 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) , SM/11379 | Retrofitting | Material Requisition To Resource Division | 1268/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.48 | 0 | 0 | 0
481 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) , SM/11379 | Retrofitting | Material Requisition To Resource Division | 2590/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.48 | 0 | 0 | 0
482 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/ Jal swapno Programme from existing PWSS at Marybong (Tar Dhura & Gairee Goan) , SM/11379 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Marybong GP - Lingia Marybong, Block - Jorebungalow Sukhia. | 943/NKWSMD | 12/07/2022 | 903 | MANI KUMAR CHHETRI | 18.47 | 0 | 0 | 100
483 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung , SM/11389 | Retrofitting | Material Requisition To Resource Division | 1908/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.39 | 0 | 0 | 0
484 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung , SM/11389 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Bijuwa Gaon Pulundung GP - Pulundung, Block - Jorebungalow Sukhia | 939/NKWSMD | 12/07/2022 | 60 | KIRAN NIROLA | 12.21 | 0 | 0 | 0
485 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung , SM/11389 | Retrofitting | Material Requisition To Resource Division | 2591/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.39 | 0 | 0 | 0
486 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung , SM/11389 | Retrofitting | Material Requisition To Resource Division | 1267/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.39 | 0 | 0 | 0
487 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA , SM/10825 | New | Material Requisition To Resource Division | 2061/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.94 | 0 | 0 | 0
488 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA , SM/10825 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
489 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA , SM/10825 | New | Surface Water Based Upper Mamring Piped Water Supply Scheme to accmmodate FHTC in Kurseong Block within Darjeeling District under Kurseong Sub-Division, P.H.E.D-G.T.A | 836/NKWSMD | 30/06/2022 | 90 | AJAY RAI | 89.52 | 0 | 0 | 85
490 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11314 | Retrofitting | Material Requisition To Resource Division | 1290/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.77 | 0 | 0 | 0
491 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney ( North shibkhola habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11314 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney (North Shibkhola habitation) under Kurseong Sub-Division P.H.E.D GTA. | 838/NKWSMD | 30/06/2022 | 60 | SONAM LAMA | 9.28 | 0 | 0 | 45
492 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. , SM/11325 | Retrofitting | Material Requisition To Resource Division | 1300/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0 | 0
493 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation)under Kurseong Sub-Division PHED, GTA. , SM/11325 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation) under Kurseong Sub-Division PHED, GTA. | 797/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 9.35 | 0 | 0 | 100
494 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11329 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Malotar T.E. Mahanadi GP Block - Kurseong Block | 810/NKWSMD | 30/06/2022 | 60 | NARESH RAI | 17.84 | 0 | 0 | 0
495 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Malotar Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11329 | Retrofitting | Material Requisition To Resource Division | 1303/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.96 | 0 | 0 | 0
496 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. , SM/11300 | Retrofitting | Material Requisition To Resource Division | 1313/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
497 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. , SM/11300 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for Piped Water Supply Scheme at Chandraman Gaon Gram Panchyat Paila Goan S D- 2 Block- Mirik TSM No. 009302 | 805/NKWSMD | 30/06/2022 | 915 | MS. SURYA I PVT. LTD COMPANY | 18.95 | 0 | 0 | 100
498 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Krishi kunj , SM/11308 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Krish Kunj: Gram Panchyat Duptin 10, Block - Mirik TSM No. 009481 | 807/NKWSMD | 30/06/2022 | 60 | BIKASH LAMA | 5.52 | 0 | 0 | 0
499 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling , SM/11309 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Chotta Tingling: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009480 | 787/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.72 | 0 | 0 | 100
500 | DARJEELING | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. , SM/11339 | New | Material Requisition To Resource Division | 1886/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.6 | 0 | 0 | 0
501 | DARJEELING | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. , SM/11339 | New | Material Requisition To Resource Division | 2605/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.6 | 0 | 0 | 0
502 | DARJEELING | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. , SM/11339 | New | ADDITIONAL WORK FOR SINGLA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKHIAPOKRI DISTRICT-DARJEELING. | 495/NKWSMD | 09/04/2025 | 180 | DAJUBHAI CONSTRUCTION | 88.19 | 0 | 0 | 0
503 | DARJEELING | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. , SM/11339 | New | PIPED WATER SUPPLY SCHEME FROM SINGLA TEA GARDEN UNDER DARJEELING DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, G.T.A | 1289/NKWSMD | 08/09/2022 | 995 | VINAYAK CONSTRUCTION | 280.33 | 0 | 0 | 100
504 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/11889 | New | Material Requisition To Resource Division | 1892/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.64 | 0 | 0 | 0
505 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/11889 | New | Material Requisition To Resource Division | 2611/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
506 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/11889 | New | Rangaroong T.G water supply scheme Under Jal Jeewan Mission Detail - (SW No. : SW/111753/2022) | "BP-2024-25-293 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.38 | 0 | 0 | 0
507 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/11889 | New | WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING.(TSM/012508) | 1529/NKWSMD | 18/10/2022 | 830 | KUNCHAN JUNGA ENTERPRISES | 272.77 | 0 | 0 | 100
508 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/11889 | New | Additional work for Rageroong Tea Estate for water supply scheme under Darjeeling Division,PHED-GTA. | 862/NKWSMD | 31/07/2023 | 790 | KUNCHAN JUNGA ENTERPRISES | 30.33 | 0 | 0 | 100
509 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme , SM/07038 | Retrofitting | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Swapno Programme for Lalman mouza (Part) of Lalman W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 07. | 1009/SWSD | 10/09/2021 | 15 | SEBU CHAKRABORTY | 4.84 | 0 | 0 | 100
510 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme , SM/07038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal SWapno Programme for Lalman Mouza (Part) of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. (Part-A) | 706/SWSD | 03/08/2021 | 120 | RAJEEV RANJAN OJHA | 32.5 | 13.11 | 40.33 | 43
511 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Lalman (CT) (JL 96) Mouza of Lalman Piped water Supply Scheme , SM/07038 | Retrofitting | Issue of fuel for Office of the Executive Engineer and Assistant Engineers of Siliguri W/S Division, PHE Dte. from 17th March 2024 to 30th May 2024 | BP-2024-25-41 | 08/07/2024 | 0 | SONA PETROL PUMP | 1.87 | 0 | 0 | 0
512 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , SM/12037 | Augmentation | Material Requisition To Resource Division | 2031/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0 | 0
513 | DARJEELING | Northern Mechanical | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , SM/12037 | Augmentation | New Service Connection Charge for Rejuvenation of Paschim Madati, TW No. I, BIDHANNAGAR CCC, [APPLICATION NO. 4003143720, Reference ID : 803008623] | BP/23-24/08 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
514 | DARJEELING | Northern Mechanical | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , SM/12037 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 529/NMD | 10/05/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 11.64 | 0 | 0 | 90
515 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , SM/12037 | Augmentation | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum./hr) required platform and drain etc. for rejuvenation of Paschim Madati Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, PHE Dte. in the dist. of Darjeeling. | 2366/SWSD | 24/01/2023 | 799 | AKASH ENTERPRISE | 67.76 | 0 | 0 | 100
516 | DARJEELING | Siliguri W/S Division | REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , SM/12037 | Augmentation | Acceptance cum Work Order for Improvement of Existing FHTC with existing pipelines for Rejuvenation of Paschim Madati PWSS under Jal Jeeban Mission (JJM) at Phansidewa Block within Siliguri Sub- Division, PHE Dte. | 1241/SWSD | 24/04/2025 | 30 | AKASH ENTERPRISE | 16.03 | 0 | 0 | 0
517 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/11953 | New | Material Requisition To Resource Division | 1897/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.25 | 0 | 0 | 0
518 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/11953 | New | Material Requisition To Resource Division | 2578/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.25 | 0 | 0 | 0
519 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/11953 | New | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024. | 386/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 0 | 100
520 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/11953 | New | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCEME FOR TAMSANG TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING (TSM/011759). | 648/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 23.02 | 0 | 0 | 0
521 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TAMSANG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/11953 | New | Water Supply Scheme for Tamsang Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. | 1562/NKWSMD | 21/10/2022 | 845 | VINAYAK CONSTRUCTION | 736.38 | 0 | 0 | 100
522 | DARJEELING | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Material Requisition To Resource Division | 2037/SWSD | 16/12/2022 | 0 | Resource Division | 13.5 | 0 | 0 | 0
523 | DARJEELING | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 254/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.77 | 0 | 0 | 100
524 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | New Service Connection Charge for RANGALI, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208340 ; Reference ID : 403057204] | BP/23-24/95 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.16 | 0 | 0 | 0
525 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | New Service Connection Charge for RANGALI, T/W I, under KHARIBARI CCC [APPLICATION NO. 4003208350 ; Reference ID : 403057203] | BP/23-24/95 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.11 | 0 | 0 | 0
526 | DARJEELING | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Construction of l00 cu.m. capacity RCC Elevated Reseervoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of 2 (two) nos. pump house (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and soil investigation at H/W site for RANGALI PWSS, block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, PHE Dte. | 2918/SWSD | 24/03/2023 | 739 | M/S BIRAT CONSTRUCTION | 217.11 | 0 | 0 | 10
527 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
528 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
529 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
530 | DARJEELING | Siliguri W/S Division | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall at H/W & 2nd T/W Site Augmentation RANGALI PWSS SCHEME Block Kharibari under Siliguri W/S Division PHE Dte. | 1361/SWSD | 05/05/2025 | 30 | S.G.CONSTRUCTION | 18.14 | 0 | 0 | 0
531 | DARJEELING | Northern Mechanical | Augmentation of Rangali Piped Water Supply Scheme , SM/13429 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1646/NMD | 29/09/2023 | 498 | TAPAN BISWAS | 10.99 | 0 | 0 | 100
532 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , SM/14834 | Augmentation | Material Requisition To Resource Division | 206/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0 | 0
533 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , SM/14834 | Augmentation | Quotation Charges for New Service Connection at Bairagi PWSS,TW-I under NMD PHE Dte. Application No- 4003340167 Ref ID- 403162856 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.69 | 0 | 0 | 0
534 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , SM/14834 | Augmentation | Laying distribution of HDPE pipe line, sluice valve chamber, construction of boundary wall including drain & paver block pathway for Augmentation at Bairagi Water Supply Scheme, 2nd tubewell site of Khoribari block under Siliguri Sub Division, P.H.E. Dte. | 644/SWSD | 15/06/2023 | 690 | M/S SHIVAJI ROY | 22.4 | 0 | 0 | 40
535 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , SM/14834 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1389/NMD | 09/08/2023 | 581 | M/S ANJALI ENTERPRISE | 12.38 | 0 | 0 | 100
536 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Material Requisition To Resource Division | 153/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.42 | 0 | 0 | 0
537 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Gravity Base Water Supply Scheme for Senchal-I under Jal Jeevan Mission Detail - (SW No. : SW/145710/2023) | BP-2024-25-452 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.7 | 0 | 0 | 0
538 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission Detail - (SW No. : SW/145713/2023) WEST BENGAL , DARJEELING |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0 | 0
539 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Gravity Based water supply scheme for Senchal-2 under JAl JEEWAN MISSION. Detail - (SW No. : SW/145709/2023) |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0 | 0
540 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission | BP-2024-25-454 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0 | 0
541 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | Gravity based water supply scheme for Senchal - 2 under JAL JEEWAN MISSION DETAILS (SW/145709/2023) | BP-2024-25-456 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0 | 0
542 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/13956 | New | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | 118/NKWSMD | 28/04/2023 | 974 | SUMAN THAKURI | 483 | 0 | 0 | 70
543 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14528 | New | Material Requisition To Resource Division | 326/NKWSMD | 24/05/2023 | 0 | Resource Division | 4.87 | 0 | 0 | 0
544 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14528 | New | PAYMENT FOR WBSEDCL | BP-2023-24-503 | 17/02/2024 | 0 | WBSEDCL | 5.5 | 0 | 0 | 0
545 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GOPAL DHARA TEA GARDEN PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14528 | New | WATER SUPPLY SCHEME FOR GOPALDHARA TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 223/NKWSMD | 10/05/2023 | 842 | GREENPRO ENGINEERING | 1051.51 | 0 | 0 | 100
546 | DARJEELING | Neorakhola W/S & Mtc.Div. | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME , SM/16159 | New | Material Requisition To Resource Division | 443/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.38 | 0 | 0 | 0
547 | DARJEELING | Neorakhola W/S & Mtc.Div. | LR BANSBOTAY & LR LINGSAY BONG PIPED WATER SUPPLY SCHEME , SM/16159 | New | Water Supply Scheme For Lower Bansbotay & Lower Lingsay Bong Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. | 415/NKWSMD | 05/06/2023 | 180 | HARI PRASAD CHETTRI | 287.97 | 0 | 0 | 80
548 | DARJEELING | Central Drilling | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | 563/CDD | 07/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 0
549 | DARJEELING | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | New Service Connection Charge for OMI, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300005 ; Reference ID : 403131330] | BP/23-24/227 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0 | 0
550 | DARJEELING | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | New Service Connection Charge for OMI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299978 ; Reference ID : 403131329] | BP/23-24/226 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.15 | 0 | 0 | 0
551 | DARJEELING | Central Drilling | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
552 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | Acceptance cum work order for laying of rising main, distribution system of pipeline, construction of pump houses, boundary wall, sinking of Rig bore deep tube well by Odex-165 method of drilling, development of land and other allied works for Augmentation of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Dist-Darjeeling. | 1734/SWSD | 22/09/2023 | 551 | NARAYAN CH GHOSH | 65.91 | 0 | 0 | 80
553 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with AUGMENTATION of OMI PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | 1234/SWSD | 24/04/2025 | 30 | NARAYAN CH GHOSH | 2.72 | 0 | 0 | 0
554 | DARJEELING | Northern Mechanical | AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , SM/15270 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1672/NMD | 29/09/2023 | 395 | M/S MATRI CONSTRUCTION | 10.37 | 0 | 0 | 100
555 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME , SM/15272 | Augmentation | Material Requisition To Resource Division | 207/SWSD | 25/04/2023 | 0 | Resource Division | 0.79 | 0 | 0 | 0
556 | DARJEELING | Northern Mechanical | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME , SM/15272 | Augmentation | New Service Connection Charge for GUABARI, T/W No. I, under PHANSIDAWA CCC, [APPLICATION NO. 4003325453, Reference ID : 403153288] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.39 | 0 | 0 | 0
557 | DARJEELING | Northern Mechanical | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME , SM/15272 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1438/NMD | 10/08/2023 | 752 | S.D. CONCERN | 10.38 | 0 | 0 | 90
558 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME , SM/15272 | Augmentation | Part work order for construction the boring of ODEX 165 tubewell, laying distribution, iron elimination plant, pump house, boundary wall, TW all complete under Augmentation of Guabari Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub division, P.H.E. Dte. | 676/SWSD | 14/03/2024 | 746 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 52.8 | 0 | 0 | 45
559 | DARJEELING | Northern Mechanical | AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME , SM/15272 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
560 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme , SM/16123 | New | Material Requisition To Resource Division | 757/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.77 | 0 | 0 | 0
561 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme , SM/16123 | New | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 0 | 100
562 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK Piped Water Supply Scheme , SM/16123 | New | WATER SUPPLY SCHEME FOR RIMBICK PIPED WATER SUPPLY SCHEME IN DARJEELING-PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 681/NKWSMD | 12/07/2023 | 781 | NIMA SHERPA | 699.58 | 0 | 0 | 90
563 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHAINPURAY PIPED WATER SUPPLY SCHEME , SM/15881 | New | Material Requisition To Resource Division | 755/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.86 | 0 | 0 | 0
564 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHAINPURAY PIPED WATER SUPPLY SCHEME , SM/15881 | New | WATER SUPPLY SCHEME FOR CHAINPURAY PIPED WATER SUPPLY SUPPLY IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 680/NKWSMD | 12/07/2023 | 797 | VAISHNO CONSTRUCTION | 80.25 | 0 | 0 | 100
565 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. , SM/15874 | New | Material Requisition To Resource Division | 243/NKWSMD | 12/05/2023 | 0 | Resource Division | 1.08 | 0 | 0 | 0
566 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. , SM/15874 | New | Strengthening of mainline of water supply scheme at Majua (Singhbumdera) under Darjeeling Division, PHED-GTA. | 861/NKWSMD | 31/07/2023 | 60 | RISHI KESH THAKURI | 28.53 | 0 | 0 | 100
567 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAJUA PIPED WATER SUPPLY SCHEME. , SM/15874 | New | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 124/NKWSMD | 28/04/2023 | 360 | DENDUP BHUTIA AND COMPANY | 255.41 | 0 | 0 | 100
568 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16533 | New | Material Requisition To Resource Division | 155/NKWSMD | 03/05/2023 | 0 | Resource Division | 4.98 | 0 | 0 | 0
569 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16533 | New | WATER SUPPLY SCHEME FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 117/NKWSMD | 28/04/2023 | 815 | VINAYAK CONSTRUCTION | 1144.27 | 0 | 0 | 5
570 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MAKAI BARI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16533 | New | ADDITIONAL WORK FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA | 652/NKWSMD | 05/05/2025 | 90 | MAGMA CONSORTIUM | 30.47 | 0 | 0 | 0
571 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) , SM/16386 | New | Material Requisition To Resource Division | 2772/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.03 | 0 | 0 | 0
572 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR NAHORI TEA GARDEN ( BALASOM) (PART) , SM/16386 | New | SURFACE WATER BASED NAHORI TEA GARDEN (BALASOM) (PART) PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | 2736/NKWSMD | 03/03/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 659.52 | 0 | 0 | 85
573 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16145 | New | Material Requisition To Resource Division | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.84 | 0 | 0 | 0
574 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16145 | New | WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK KURSEONG UNDER DISTRICT DARJEELING. | 683/NKWSMD | 12/07/2023 | 420 | M/S S S CONSTRUCTION | 417.8 | 0 | 0 | 50
575 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16145 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 820/NKWSMD | 09/06/2025 | 60 | M/S S S CONSTRUCTION | 14.61 | 0 | 0 | 0
576 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/15647 | New | Material Requisition To Resource Division | 2892/NKWSMD | 29/03/2023 | 0 | Resource Division | 6.38 | 0 | 0 | 0
577 | DARJEELING | Kurseong Division | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/15647 | New | Work Order for proposals to frame and put up for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong under Kurseong division, PHED,GTA | 515/EE/KD/PHED | 22/11/2023 | 10 | HILL GROUND CONSULTANCY | 0.96 | 0 | 0 | 100
578 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA. SCHEME CODE - 15647 TSM/017747 | "BP-2024-25-100 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0 | 0
579 | DARJEELING | Neorakhola W/S & Mtc.Div. | SUKNA PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/15647 | New | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | 2873/NKWSMD | 23/03/2023 | 695 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 488.43 | 0 | 0 | 52
580 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. , SM/18638 | New | Material Requisition To Resource Division | 958/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.92 | 0 | 0 | 0
581 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. , SM/18638 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
582 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. , SM/18638 | New | SURFACE WATER BASED NORTH & SOUTH SHIBKHOLA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | 910/NKWSMD | 11/08/2023 | 570 | AROGYA ENTERPRISES | 1336.08 | 0 | 0 | 95
583 | DARJEELING | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS , SM/18728 | New | Material Requisition To Resource Division | 961/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0 | 0
584 | DARJEELING | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS , SM/18728 | New | PROVIDING FHTC UNDER JAL JEEVAN MISSION FOR BALANCE HOUSEHOLD AT 9TH MILE (MAMTA PARK LAMAHATTA) PESHOKE ROAD, LAMAHATTA UNDER DARJEELING DIVISION, P.H.E DEPTT, GTA | 934/NKWSMD | 16/08/2023 | 60 | PUSHKAR GURUNG | 13.64 | 0 | 0 | 100
585 | DARJEELING | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS , SM/18728 | New | WATER SUPPLY SCHEME FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 949/NKWSMD | 17/08/2023 | 1095 | VINAYAK CONSTRUCTION | 956.42 | 0 | 0 | 80
586 | DARJEELING | Neorakhola W/S & Mtc.Div. | PESHOK TEA GARDEN PWSS , SM/18728 | New | ADDITIONAL WORK FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-RANGLI RANGLIOT DISTRICT-DARJEELING. | 649/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 74.02 | 0 | 0 | 0
587 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 262/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 0 | 100
588 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | Material Requisition To Resource Division | 1802/SWSD | 30/09/2023 | 0 | Resource Division | 59.09 | 0 | 0 | 0
589 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | New Service Connection Charge for AUG. OF KAWAKHALI, T/W No. III, under PHANSIDEWA CCC, [APPLICATION NO. 4003317469, Reference ID : 403145877] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0 | 0
590 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | New Service Connection Charge for AUG KAWAKHALI, T/W No.II, under PHANSIDAWA CCC, [APPLICATION NO. 4003320218, Reference ID : 403148651] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.1 | 0 | 0 | 0
591 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | New Service Connection Charge for AUG KAWAKHALI, T/W No. I, under PHANSIDAWA CCC, [APPLICATION NO. 4003320233, Reference ID : 403148653] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.61 | 0 | 0 | 0
592 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I, II and (Zone-III) TW-I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1439/NMD | 10/08/2023 | 604 | ALPHA ENTERPRISE | 47.79 | 0 | 0 | 75
593 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site (Zone-II), including Rising Mains, Distribution System Providing Functional household Tapn Connection (FHTC), Iron Elimination Plant (IEP) with Blower Room, Boundary wall & Soil Investigation at H/W site (Zone-II) for Augmentation of KAWAKHALI (Zone-I, II & III) Piped Water Supply Scheme Block : Matigara under Siliguri W/S Division, P.H.E. Dte | 1230/SWSD | 14/08/2023 | 687 | FAIRDEAL ASSOCIATES | 827.38 | 0 | 0 | 25
594 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | ACCEPTANCE CUM WORK ORDER FOR CONSTRUCTION OF BOUNDARY WALL AT EXISTING PUMP HOUSE (two nos)FOR KAWA KHALI W/S SCHEME UNDER SILIGURI WATER SUPPLY DIVISION PHE DTE.(CONSIDERING A LENGTH OF 70 METRE) | 193/SWSD | 16/01/2025 | 45 | RAJEEV RANJAN OJHA | 8.04 | 0 | 0 | 0
595 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
596 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | CONSTRUCTION OF PATHWAY & LAND DEVOLOPMENT FOR KAWAKHALI ZONE-I , II & III PIPED WATER SUPPLY SCHEME (H/W SITE & 2ND T/W SITE) BLOCK MATIGARA DISTRICT : DARJEELING UNDER SILIGURI W/S DIVISION P.H.E.Dte | 2846/SWSD | 23/10/2024 | 30 | FAIRDEAL ASSOCIATES | 19.13 | 0 | 0 | 0
597 | DARJEELING | Northern Mechanical | AUGMENTATION OF KAWAKHALI(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18386 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 34/NMD | 06/01/2025 | 30 | PRATIK ROY | 9.2 | 0 | 0 | 0
598 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection under JSP Programme for PWS scheme at Kataray forest Busty , SM/11302 | Retrofitting | Providing Functional household tap connection with retrofitting the existing distribution networks under Jal Swapno Programme for PWS scheme at Kataray forest Busty Gram Panchyat-Soureni-II, Block- Mirik TSM No. 009305 | 785/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.66 | 0 | 0 | 100
599 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS , SM/18827 | New | Material Requisition To Resource Division | 51/NKWSMD | 09/01/2024 | 0 | Resource Division | 22.53 | 0 | 0 | 0
600 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS , SM/18827 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for Water Supply Scheme for Darjeeling Pulbazar Pumping - I Spring Water Supply Scheme followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | 1567/NKWSMD | 03/09/2024 | 546 | DARA ENGINEERING & INFRASTRUCTURES PRIVATE LIMITED | 15881.1 | 0 | 0 | 5
601 | DARJEELING | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS , SM/18827 | New | (Continuation) Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate for the period from January 2025 to June 2025. | 2412/NKWSMD | 31/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0 | 0
602 | DARJEELING | Neorakhola W/S & Mtc.Div. | AUGMENTATION OF SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/18878 | Augmentation | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 0 | 30
603 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN , SM/18651 | New | Material Requisition To Resource Division | 971/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.21 | 0 | 0 | 0
604 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN , SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | BP-2024-25-220 | 28/08/2024 | 0 | WBSEDCL | 5.43 | 0 | 0 | 0
605 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN , SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | BP-2024-25-88 | 08/07/2024 | 0 | WBSEDCL | 17.08 | 0 | 0 | 0
606 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN , SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | 921/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1126.3 | 0 | 0 | 90
607 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN , SM/18651 | New | ADDITIONAL WORK FOR SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK P.H.E-GTA. | 639/NKWSMD | 05/05/2025 | 180 | SHAKTI CONSTRUCTION | 87.36 | 0 | 0 | 0
608 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. , SM/18652 | New | Material Requisition To Resource Division | 968/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0 | 0
609 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. , SM/18652 | New | SURFACE WATER BASED SINGEL TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | 914/NKWSMD | 11/08/2023 | 815 | M/S. ASHOK KUMAR PERIWAL | 958.42 | 0 | 0 | 80
610 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | Material Requisition To Resource Division | 2060/SWSD | 16/12/2022 | 0 | Resource Division | 65.06 | 0 | 0 | 0
611 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 0 | 100
612 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | FURTHER ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2023 TO 31.08.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. 6 (SIX) MONTHS. | 2642/SWSD | 01/03/2023 | 184 | HIMADRI DAM | 0.88 | 0 | 0 | 100
613 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | Material Requisition To Resource Division | 1458/SWSD | 29/09/2022 | 0 | Resource Division | 6.05 | 0 | 0 | 0
614 | DARJEELING | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON, T/W No. I, ZONE-I, under PHANSIDEWA CCC [APPLICATION NO. 4003305873 ; Reference ID : 403135372] | BP/23-24/275 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.96 | 0 | 0 | 0
615 | DARJEELING | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON , T/W No. II , ZONE-I, under PHANSIDAWA CCC, [APPLICATION NO. 4003317696, Reference ID : 403145882] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.53 | 0 | 0 | 0
616 | DARJEELING | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | New Service Connection Charge for MADHYA BANSGAON , T/W No. I , ZONE-II, under PHANSIDAWA CCC, [APPLICATION NO. 4003317715, Reference ID : 403145870] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0 | 0
617 | DARJEELING | Central Drilling | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
618 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | Construction of 150 cu.m. Overhead reservoir, 2 nos. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation of MADHYA BANSGAON (Zone-I) Piped Water Supply Scheme and Construction of 350 cu.m. overhead reservoir, 1 no. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation work of MADHYA BANSGAON (Zone-II) Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 1130/SWSD | 07/08/2023 | 482 | UNIBRO INFRASERV PRIVATE LIMITED | 869.38 | 0 | 0 | 19
619 | DARJEELING | Northern Mechanical | AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME , SM/10724 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II and (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1652/NMD | 29/09/2023 | 702 | M/S SWAPAN BANERJEE | 22.53 | 0 | 0 | 100
620 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA , SM/18917 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
621 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA , SM/18917 | New | WATER SUPPLY SCHEME FOR MALDIRAM FOREST PART, ST MARYS PART, UPPER LANKU & UPPER ROLAK PART, SIMRING TEA GARDEN PART, CHANDU BUSTY GIDHE PAHAR PART PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 1746/NKWSMD | 19/09/2024 | 365 | DAJUBHAI CONSTRUCTION | 861.59 | 0 | 0 | 80
622 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for mahipal and Bandargachh village of Bandargachh Piped water Supply Scheme , SM/07042 | Retrofitting | Issue of fuel for office vehicles of Executive Engineer and Assistant Engineers of Siliguri W/S Division and Siliguri Sub division, PHE Dte. for the period form 01.06.2024 to 13.07.2024 | BP-2024-25-62 | 02/08/2024 | 0 | SONA PETROL PUMP | 0.98 | 0 | 0 | 0
623 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Badang, Pakridhuka, Sapti and Jayantyika 318 Nos house hold) of Purba Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | 1080/SWSD | 18/12/2020 | 35 | SUBIR CH. CHOWDHURY | 30.22 | 24.34 | 80.53 | 100
624 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 0.56 | 0 | 0 | 0
625 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Material Requisition To Resource Division | 1670/SWSD | 28/12/2021 | 0 | Resource Division | 1.42 | 0 | 0 | 0
626 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
627 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Providing functional house hold tasp connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapno) under command area (Habitation Badang Jayantika Sapti Alim Ganj & Chowdhury Gachh) due to Y.D.U of Purba Madati Piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | 1828/SWSD | 13/01/2022 | 25 | BIMAN DUTTA | 10.38 | 0 | 0 | 20
628 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Purba Madati Piped water Supply Scheme (Part-B) , SM/07043 | Retrofitting | Continuation order for Supply of 01 (one) no. Maxi Cab with Engine Capacity less than or equal to 2000 C.C. with Air Condition on hire basis (for monthly hiring) including driver under Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. (With valid Taxi permit and other necessary documents as per norms of Zonal R.T.O) For 03 (three months) with effect from 01.01.2025 to 31.03.2025. | 3610/SWSD | 31/12/2024 | 90 | S S CONSTRUCTIONS | 0.47 | 0 | 0 | 0
629 | DARJEELING | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Jeevan Mission & Jal Swapno Programme in 5 Habitation ( Ghaiter Busrty, Gurira Zote , Nagar Zote, NDDP Busty , Taluk Zote ) at Village Guria of , SM/09203 | Augmentation | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
630 | DARJEELING | Siliguri W/S Division | STANDALONE MINI PIPED WATER SUPPLY SCHEME IN THE VILLAGES LESS THAN 100 HOUSEHOLD BLOCK - KHARIBARI, NAXALBARI, MATIGARA, DIST - DARJEELIND , SM/10470 | New | Material Requisition To Resource Division | 1461/SWSD | 29/09/2022 | 0 | Resource Division | 6.01 | 0 | 0 | 0
631 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 18.84 | 0 | 0 | 0
632 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-114 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 64.05 | 0 | 0 | 0
633 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | 36/SWSD | 07/04/2022 | 100 | VIJAY KUMAR ARORA | 198.7 | 0 | 0 | 95
634 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) of Distribution Pipeline (Part-D) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | 35/SWSD | 07/04/2022 | 90 | ANUP BASU | 123.58 | 0 | 0 | 0
635 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | `Continuation of Hiring of 1(one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E Dte. from 1.03.2022 to 31.08.2022 (with Engine Capacity less than or equal to 2000 CC) Vehicle no. WB76A 4921) | 112/SSD | 28/02/2022 | 184 | SUDIP BASAK | 0.88 | 0 | 0 | 100
636 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 28.02.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. SIX MONTHS. | 1236/SWSD | 31/08/2022 | 181 | HIMADRI DAM | 0.88 | 0 | 0 | 100
637 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Constuction of Pump House (3.6*3.0m) at Kalam 3rd site under Augmentation of Kalam piped water supply scheme under Matigara Block Darjeeling district in connection with Jal jeevan Mission under Siliguri Sub-division,P.H.E Dte | 268/SSD | 05/06/2023 | 45 | K.K.GHOSH & CO. | 4.75 | 0 | 0 | 100
638 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Material Requisition To Resource Division | 2178/SWSD | 11/02/2022 | 0 | Resource Division | 84.79 | 0 | 0 | 0
639 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Material Requisition To Resource Division | 1447/SWSD | 29/09/2022 | 0 | Resource Division | 13.8 | 0 | 0 | 0
640 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | New Service Connection Charge for KALAM, T/W II, under SHIVMANDIR CCC [APPLICATION NO. 4003119079 ; Reference ID : 402986632] | BP/23-24/03 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
641 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | New Service Connection Charge for KALAM, T/W III, under SHIVMANDIR CCC [APPLICATION NO. 4003119111 ; Reference ID : 402986652] | BP/23-24/03 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0 | 0
642 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
643 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) at Distribution Pipeline (Part-C) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | 2081/SWSD | 03/02/2022 | 336 | KAMAL GHOSH | 63.4 | 0 | 0 | 92
644 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 0 | 100
645 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Construction of Pump House(3.6 X 3.0 m), at Kalam 4th Site under Augmentation of Kalam piped water supply Scheme under Matigara Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | 194/SSD | 04/05/2023 | 45 | K.K.GHOSH & CO. | 4.75 | 0 | 0 | 95
646 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , TW No II & III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 551/NMD | 15/05/2023 | 30 | SARKAR ELECTRIC | 23.37 | 0 | 0 | 100
647 | DARJEELING | Northern Mechanical | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Supply & delivery of CIDF Specials Under JJM project at Kalam W/S Scheme in the dist of Darjeeling. | 383/SMSD | 07/03/2024 | 7 | B.B. CONCERNED | 0.9 | 0 | 0 | 100
648 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Acceptance cum work order for construction of blower room, iron elimination plant, boundary wall at Kalam Piped Water Supply Scheme under Matigara block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | 35/SWSD | 08/01/2024 | 754 | SUBIR CH. CHOWDHURY | 63.98 | 0 | 0 | 60
649 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , SM/09829 | Augmentation | Work Order for Construction of 200 Cu.M capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site including rising mains and distribution system (Part-A) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Kalam & adjoining mouza's water supply scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. | 2354/SWSD | 15/12/2023 | 807 | SHRI ANNAPURNA DISTRIBUTORS | 156.84 | 0 | 0 | 50
650 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal swapno programme for Mirjangla,Mirjnaglar Chhat, Birsing, Fakna Mouza of Birsing Piped W/S Scheme at Naxalbari Block under Siliguri Sub Division, P.H.E Dte. ( Phase-II ) , SM/09079 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Birsing mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 11. | 1221/SWSD | 01/11/2021 | 35 | M/S MATRI CONSTRUCTION | 31.13 | 0 | 0 | 100
651 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal swapno programme for Mirjangla,Mirjnaglar Chhat, Birsing, Fakna Mouza of Birsing Piped W/S Scheme at Naxalbari Block under Siliguri Sub Division, P.H.E Dte. ( Phase-II ) , SM/09079 | Retrofitting | Providing Functional House hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Fakna mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte SL. NO. 06. | 1218/SWSD | 01/11/2021 | 20 | U.K CONSTRUCTIONS | 14.99 | 0 | 0 | 80
652 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-108 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 230.79 | 0 | 0 | 0
653 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 1.32 | 0 | 0 | 0
654 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Laying distribution system (Part-F) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-F) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | 2433/SWSD | 21/03/2022 | 45 | BUDDHADEV NAG | 49.84 | 0 | 0 | 60
655 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Soil Investigation of Lahugaon Z II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | 390/SSD | 20/07/2022 | 20 | D.P. ENTERPRISE | 1.03 | 0 | 0 | 100
656 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Soil Investigation of Lahugaon Z I PWSS for Construction of 400 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | 389/SSD | 20/07/2022 | 20 | M/S PRANTIK ASSOCIATES | 1.02 | 0 | 0 | 100
657 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Material Requisition To Resource Division | 2169/SWSD | 11/02/2022 | 0 | Resource Division | 313.89 | 0 | 0 | 0
658 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Material Requisition To Resource Division | 1449/SWSD | 29/09/2022 | 0 | Resource Division | 25.7 | 0 | 0 | 0
659 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
660 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. | BP-2023-24-41 | 28/07/2023 | 0 | SUDIP BASAK | 2.24 | 0 | 0 | 0
661 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | HIRING OF 1 (ONE) NO. WELL MAINTAINED DIESEL CONSUMED LUXURY CAB ON MONTHLY HIRED BASIS PREFERABLY MAXI CAB (A/C) WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC FOR OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHER ZONE, P.H.E. DTE. VIVEKANANDA BHAWAN (2ND FLOOR) HILL CART ROAD, SILIGURI (FOR ASSISTANT CHIEF ENGINEER, NORTHERN ZONE (CIVIL), P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 31.10.2022 i.e. 2 (TWO) MONTHS. | BP-2022-23-131 | 20/02/2023 | 0 | OM TRAVELS | 1.08 | 0 | 0 | 0
662 | DARJEELING | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | New Service Connection Charge for LAHUGAON, KUMARTULI, T.W. No. I under BIDHANNAGAR CCC, [APPLICATION NO. 4003194405, Reference ID : 403046890] | BP/23-24/74 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0 | 0
663 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Acceptance cum work order "Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and two nos Pump House (3600mm x 2400mm x 3300mm height) with toilet (2100mm x 1350mm) sanitary and plumbing arrangement along with verandah (3975mm x 1500mm) having plinth height 600m m. and construction of Boundary Wall at Three Different Site Pump House Site and Iron Elemination Plant Under Lohugaon (Z-II) at Lahugaon (Z-II) Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | 603/SWSD | 06/03/2024 | 667 | SHYAMAL NATH | 68.77 | 0 | 0 | 60
664 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Supplying. Fabrication, Erection of IRON ELEMINATION PLANT at Lohugaon (Z-1) and construction of Blower Room at pump house site at Lohugaon water Supply Scheme Under Siliguri Sub division, P.H.E DTE. | 2532/SWSD | 13/09/2024 | 30 | PALLAB BHOWAL | 15.2 | 0 | 0 | 0
665 | DARJEELING | Central Drilling | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | 560/CDD | 06/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 10
666 | DARJEELING | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Charges for additional quotation For lahugaon PWSS (Near Kumar tuli),Z-II,Tw-II under NMD PHE dte. Application no- 4003320704 Ref ID- 403147041 For Additional Quotation Application ID- 100000114620 Ref ID- 860308530 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.88 | 0 | 0 | 0
667 | DARJEELING | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Infrastructure Cost for LAHUGAON T/W No.II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320700, Reference ID : 403147042] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
668 | DARJEELING | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Infrastructure Cost for LAHUGAON T/W No. II, ZONE-II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320704, Reference ID : 403147041] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.35 | 0 | 0 | 0
669 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Laying distribution system (Part-B) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-B) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | 2430/SWSD | 21/03/2022 | 1427 | SUBIR CH. CHOWDHURY | 64.88 | 0 | 0 | 65
670 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Laying distribution system (Part-C) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-C) of Lahugaon (Zone-1) and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | 2431/SWSD | 21/03/2022 | 1382 | AKASH ENTERPRISE | 53.99 | 0 | 0 | 60
671 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Laying distribution system (Part-D) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-D) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | 2432/SWSD | 21/03/2022 | 50 | M/S FULBARI CONSTRUCTION CO. | 53.41 | 0 | 0 | 65
672 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Construction of 400 cu.m. capacity RCC Over Head Reservoir, 20 mtrs Staging height and rising mains with laying distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Lohugaon (Zone-I) and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. Sl. No. 07. | 867/SWSD | 21/07/2022 | 1218 | PALLAB BHOWAL | 159.67 | 0 | 0 | 70
673 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Construction of 300 cum capacity Over Head Reservoir, Laying Distribution System with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewells (H/W, 2nd & 3rd sites) by ODEX-165 method of drilling under Augmentation of Lohugaon (Zone-II) piped water supply scheme under Jal Swapna/JJM works within Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. | 2376/SWSD | 24/01/2023 | 829 | FAIRDEAL ASSOCIATES | 400.24 | 0 | 0 | 70
674 | DARJEELING | Northern Mechanical | AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME , SM/10025 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME, TW No. III (Zone-I), TW-I and II (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1480/NMD | 17/08/2023 | 776 | ANUP BASU | 34.42 | 0 | 0 | 70
675 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA , SM/11396 | New | Material Requisition To Resource Division | 2566/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.65 | 0 | 0 | 0
676 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA , SM/11396 | New | SURFACE WATER BASED SHIVAKHOLA FOREST PAGLA JHORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITH IN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | 2082/NKWSMD | 10/01/2023 | 180 | SWAD CONSTRUCTION | 168.21 | 0 | 0 | 100
677 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Shiva Khola Forest under Kurseong Sub - Division, PHED, GTA , SM/11396 | New | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SHIVKHOLA FOREST PAGLAJHORA PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA. | 499/NKWSMD | 09/04/2025 | 90 | SWAD CONSTRUCTION | 55.85 | 0 | 0 | 0
678 | DARJEELING | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Rupsing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 268/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.73 | 0 | 0 | 100
679 | DARJEELING | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Material Requisition To Resource Division | 2053/SWSD | 16/12/2022 | 0 | Resource Division | 45.28 | 0 | 0 | 0
680 | DARJEELING | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Material Requisition To Resource Division | 1463/SWSD | 29/09/2022 | 0 | Resource Division | 6.38 | 0 | 0 | 0
681 | DARJEELING | Northern Mechanical | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RUPSING PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1657/NMD | 29/09/2023 | 30 | TALUKDER ENTERPRISE | 11.5 | 0 | 0 | 50
682 | DARJEELING | Siliguri W/S Division | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head work site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of one number pump house (5.40 X 3.60 m), one number pump house (3.00 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of two (2) nos. tube well (ODEX-165 method), soil investigation at HW site and boundary wall for Rupsing PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri W/S Division, PHE Dte. | 84/SWSD | 10/01/2024 | 240 | YAMA CONSTRUCTIONS LLP | 255.16 | 0 | 0 | 0
683 | DARJEELING | Central Drilling | RUPSING PIPED WATER SUPPLY SCHEME , SM/11776 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
684 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source of school (31 nos) under Mirik Block in the District of Darjeeling under Neorakhola water supply & Mtc Division, P.H.E Dte. , SM/10784 | School | Creating gravity based Provision Of Drinking water from spring water source for 31 numbers of school under Mirik- Block in the District of Darjeeling Under Neorakhola water Supply Division, Kalimpong PHE Dte TSM No. 009893 | 580/NKWSMD | 26/05/2022 | 360 | INTERIOR'S NEST | 94.19 | 0 | 0 | 50
685 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA , SM/10826 | New | Material Requisition To Resource Division | 2839/NKWSMD | 17/03/2023 | 0 | Resource Division | 1.03 | 0 | 0 | 0
686 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA , SM/10826 | New | SURFACE WATER BASED MIDDLE MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT, UNDER KURSEONG DIVISION, P.H.E-GTA. | 1121/NKWSMD | 05/08/2022 | 1151 | PREM CHANDRA RAI | 96.87 | 0 | 0 | 100
687 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA , SM/10827 | New | Material Requisition To Resource Division | 2060/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.21 | 0 | 0 | 0
688 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA , SM/10827 | New | SURFACE WATER BASED LOWER MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 609/NKWSMD | 26/05/2022 | 948 | NAVRATNA CONSTRUCTION CO | 125.37 | 0 | 0 | 80
689 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Thulung Gaon , SM/10830 | New | Material Requisition To Resource Division | 1321/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
690 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Thulung Gaon , SM/10830 | New | PIPED WATER SUPPLY SCHEME FOR THULUNG GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 612/NKWSMD | 26/05/2022 | 60 | SEWARO CONSTRUCTION COMPANY | 75.88 | 0 | 0 | 95
691 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. , SM/10832 | New | Material Requisition To Resource Division | 1884/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
692 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. , SM/10832 | New | PIPED WATER SUPPLY SCHEME FOR POKHRIABONG BUSTY NO. 5 UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 628/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 85.92 | 0 | 0 | 100
693 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. , SM/10832 | New | Material Requisition To Resource Division | 2571/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0 | 0
694 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. , SM/10832 | New | Material Requisition To Resource Division | 1367/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
695 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. , SM/11315 | Retrofitting | Material Requisition To Resource Division | 1323/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0 | 0
696 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. , SM/11315 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | 801/NKWSMD | 30/06/2022 | 60 | PRASANT NIROLA | 19.84 | 0 | 0 | 100
697 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA , SM/11328 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Rajbari Tindharay Gayabari-II GP Block - Kurseong Block | 812/NKWSMD | 30/06/2022 | 60 | HIMALI CONSTRUCTION COMPANY | 22.13 | 0 | 0 | 100
698 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Rajbari under Kurseong-Sub Division, PHED, GTA , SM/11328 | Retrofitting | Material Requisition To Resource Division | 1302/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.36 | 0 | 0 | 0
699 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11942 | New | Material Requisition To Resource Division | 700/NKWSMD | 22/03/2024 | 0 | Resource Division | 1.52 | 0 | 0 | 0
700 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11942 | New | Water Supply Scheme for Spring Sidi Tea Garden village Piped Water Supply Scheme In Kurseong Under Darjeeling District. | 2644/NKWSMD | 24/02/2023 | 770 | HIMALAYAN CONSTRUCTION | 217.45 | 0 | 0 | 100
701 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SPRING SIDI TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/11942 | New | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SPRING SIDI PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA | 776/NKWSMD | 28/05/2025 | 60 | HIMALAYAN CONSTRUCTION | 11.53 | 0 | 0 | 0
702 | DARJEELING | Neorakhola W/S & Mtc.Div. | Augmentation of source and provding FHTC at Bijanbari Bazaar , SM/11375 | Augmentation | Augmentation of source and provding FHTC at Bijanbari Bazar under Jal Swapno Programme for Balance household at Bijanbari Bazar, Gram panchyat- Bijanabari, Block- Bijanbari-Pullbazaar TSM No. 009478 | 804/NKWSMD | 30/06/2022 | 60 | PROSENJIT BASAK | 35.85 | 0 | 0 | 85
703 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Goethals Siding and Upper Kharay Busty with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11352 | New | PWS Scheme at Gothals Siding and Upper Kharay Busty with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 1445/NKWSMD | 28/09/2022 | 60 | NIPENDRA TAMANG | 31.04 | 0 | 0 | 30
704 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/11361 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Anganwadi Centre in Mirik Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 1111/NKWSMD | 05/08/2022 | 180 | KAMAKHYA CONSTRUCTION | 97.78 | 0 | 0 | 0
705 | DARJEELING | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Material Requisition To Resource Division | 2046/SWSD | 16/12/2022 | 0 | Resource Division | 13.77 | 0 | 0 | 0
706 | DARJEELING | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 251/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.8 | 0 | 0 | 100
707 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | New Service Connection Charge for HATIDOBA, T/W No. I, under KHORIBARI CCC [APPLICATION NO. 4003296374 ; Reference ID : 403127440] | BP/23-24/223 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.71 | 0 | 0 | 0
708 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | New Service Connection Charge for HATIDOBA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003321646, Reference ID : 403147923] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0 | 0
709 | DARJEELING | Siliguri W/S Division | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Laying Rising Main, laying distribution pipe line with Functional Household Tap Connection (FHTC), construction of two number Pump Houses (5.40 X 3.60 M), Iron Elimination Plant (IEP) with Blower Room and sinking of 2 (two) Nos. Tube well (ODEX-165 method) for HATIDOBA PWSS, Block - Kharibari, Dist. Darjeeling under Siliguri W/S Division P.H.E. Dte. | 654/SWSD | 15/06/2023 | 775 | M/S DOLPHIN CONSTRUCTION CO | 178.07 | 0 | 0 | 25
710 | DARJEELING | Central Drilling | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
711 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
712 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
713 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
714 | DARJEELING | Northern Mechanical | Augmentation of Hatidoba Piped Water Supply Scheme , SM/13428 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1643/NMD | 29/09/2023 | 713 | M/S SIMARR | 11.92 | 0 | 0 | 100
715 | DARJEELING | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Material Requisition To Resource Division | 2043/SWSD | 16/12/2022 | 0 | Resource Division | 14.57 | 0 | 0 | 0
716 | DARJEELING | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ARJUN MAHAL PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 249/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.83 | 0 | 0 | 100
717 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | New Service Connection Charge for ARJUN MAHAL, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193675, Reference ID : 403046163] | BP/23-24/77 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
718 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | New Service Connection Charge for ARJUN MAHAL, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208346 ; Reference ID : 403057205] | BP/23-24/94 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
719 | DARJEELING | Siliguri W/S Division | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of two numbers pump house (5.40 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and boundary wall for ARJUNMAHAL PWSS, Block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte. | 58/SWSD | 10/04/2023 | 120 | M/S UTPAL CHAKRABORTY & CO. | 180.13 | 0 | 0 | 30
720 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ARJUNMAHAL PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1649/NMD | 29/09/2023 | 30 | M/S UTPAL CHAKRABORTY & CO. | 11.85 | 0 | 0 | 100
721 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Quotation For New service Connection at Arjun Mahal Piped Water Supply Scheme, PH-II under Northern Mechanical Division ,PHE dte. siliguri. APPLICATION NO:- 4003208346 Reference ID :- 403057205 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
722 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
723 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
724 | DARJEELING | Northern Mechanical | Augmentation of Arjunmahal Piped Water Supply Scheme , SM/13395 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
725 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS , SM/14418 | New | Material Requisition To Resource Division | 2559/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
726 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS , SM/14418 | New | Material Requisition To Resource Division | 2717/NKWSMD | 03/03/2023 | 0 | Resource Division | 6.78 | 0 | 0 | 0
727 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS , SM/14418 | New | WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | 2521/NKWSMD | 15/02/2023 | 545 | GARGO TRADERS | 1596.98 | 0 | 0 | 85
728 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS , SM/14418 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
729 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY FOR PULUNGDONG KHASMAHAL PWSS , SM/14418 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. | 590/NKWSMD | 29/04/2025 | 90 | M/S BRM DEVELOPERS | 35.22 | 0 | 0 | 0
730 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14530 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1592/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
731 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14530 | New | WATER SUPPLY SCHEME FOR PUSSINGBONG PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 1279/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 1586.35 | 0 | 0 | 95
732 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR PUSSINBONG TEA GARDEN PWSS IN JORE BUNGLOW-SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14530 | New | ADDITIONAL WORK FOR PUSSINGBONG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING | 632/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 45.26 | 0 | 0 | 0
733 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS , SM/15224 | New | Material Requisition To Resource Division | 765/NKWSMD | 19/07/2023 | 0 | Resource Division | 5.61 | 0 | 0 | 0
734 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PWSS , SM/15224 | New | WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. | 685/NKWSMD | 12/07/2023 | 605 | GARGO TRADERS | 2047.06 | 0 | 0 | 50
735 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Material Requisition To Resource Division | 203/SWSD | 25/04/2023 | 0 | Resource Division | 0.79 | 0 | 0 | 0
736 | DARJEELING | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1664/NMD | 29/09/2023 | 30 | THE BANERJEE CONCERN | 10.22 | 0 | 0 | 0
737 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Acceptance cum Work Order for Construction the boring of ODEX-165 tubewell, laying distribution, iron elimination plant under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, PHE Dte. | 2033/SWSD | 06/11/2023 | 45 | BUDDHADEV NAG | 55.04 | 0 | 0 | 17
738 | DARJEELING | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | New Service Connection Charge for PURBA BANSGAON , T/W No. II, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320129, Reference ID : 403147638] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0 | 0
739 | DARJEELING | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | New Service Connection Charge for PURBA BANSGAON , T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320146, Reference ID : 403147647] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.49 | 0 | 0 | 0
740 | DARJEELING | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510209 Ref ID- 403289913 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.77 | 0 | 0 | 0
741 | DARJEELING | Northern Mechanical | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510161 Ref ID- 403289908 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0 | 0
742 | DARJEELING | Central Drilling | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
743 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Sinking of Rig bored Tubewell by Odex-165 method of drilling & Erection of Iron Elimination Plant of 40 Cum/Hr at 4th TW Site and Construction of Pump House ( 5.40M X 3.65M ) Size with sanitary & plumbing arrangement including Boundary wall along with other anciellary works at 3rd T/W Site for Augmentation of Purba Basgaon Piped Water Supply Scheme within Phansidewa Block under Siliguri W/S Division, related to Jal Jeevan Mission (JJM) | 350/SWSD | 30/01/2025 | 45 | BUDDHADEV NAG | 33.94 | 0 | 0 | 0
744 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , SM/15274 | Augmentation | Acceptance cum work order for construction of pump house, boundary wall, drain under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 1811/SWSD | 03/10/2023 | 695 | AKASH ENTERPRISE | 32.21 | 0 | 0 | 100
745 | DARJEELING | Neorakhola W/S & Mtc.Div. | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) , SM/15892 | New | Material Requisition To Resource Division | 213/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.82 | 0 | 0 | 0
746 | DARJEELING | Neorakhola W/S & Mtc.Div. | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) , SM/15892 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0 | 0
747 | DARJEELING | Neorakhola W/S & Mtc.Div. | KALIJHORA BAZAR PWSS (UPPER-LOWER BARA SITTON) , SM/15892 | New | WATER SUPPLY SCHEME FOR KALIJHORA BAZAR PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 125/NKWSMD | 28/04/2023 | 810 | GREEN VALLEY CONSTRUCTION | 155.27 | 0 | 0 | 82
748 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | Material Requisition To Resource Division | 209/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.98 | 0 | 0 | 0
749 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
750 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | Providing Functional Household Tap Connection under Jal Jeevan Mission for Balance Household at upper Kolbong in connection with Dangia under Darjeeling Division, P.H.E-G.T.A. | 164/NKWSMD | 30/01/2024 | 120 | TULSI NIROLA | 23.65 | 0 | 0 | 100
751 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2024 TO 30.04.2024. | 1576/NKWSMD | 29/12/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 0 | 100
752 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | Material Requisition To Resource Division | 163/NKWSMD | 30/01/2024 | 0 | Resource Division | 0.22 | 0 | 0 | 0
753 | DARJEELING | Neorakhola W/S & Mtc.Div. | DANGIA PIPED WATER SUPPLY SCHEME , SM/15896 | New | WATER SUPPLY SCHEME FOR DANGIA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 183/NKWSMD | 04/05/2023 | 240 | HARI PRASAD CHETTRI | 480.88 | 0 | 0 | 55
754 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15630 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
755 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. , SM/15650 | New | Material Requisition To Resource Division | 2777/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.44 | 0 | 0 | 0
756 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-109 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 31.44 | 0 | 0 | 0
757 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 10.86 | 0 | 0 | 0
758 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying distribution system (Part-F) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-F) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | 2440/SWSD | 21/03/2022 | 40 | M/S ASHIRBAD ENTERPRISE | 33.08 | 0 | 0 | 60
759 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 0 | 100
760 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 02 | 862/SWSD | 21/07/2022 | 75 | M/S UTPAL CHAKRABORTY & CO. | 82.68 | 0 | 0 | 83
761 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 04. | 864/SWSD | 21/07/2022 | 35 | SHIVNATH DEY | 25.22 | 0 | 0 | 90
762 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | 536/SWSD | 16/06/2022 | 35 | SHIVNATH DEY | 25.22 | 0 | 0 | 0
763 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 0 | 100
764 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Material Requisition To Resource Division | 1445/SWSD | 29/09/2022 | 0 | Resource Division | 12.16 | 0 | 0 | 0
765 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Material Requisition To Resource Division | 2171/SWSD | 11/02/2022 | 0 | Resource Division | 42.81 | 0 | 0 | 0
766 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
767 | DARJEELING | Northern Mechanical | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | New Service Connection Charge for AUGUMENTATION OF THAKURGANJ,T/W No - I W/S Scheme, under BIDHANNAGAR CCC, [APPLICATION NO. 4003058220, Reference ID : 402933259] | BP/22-23/156 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
768 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying distribution system (Part-E) Erection of Iron Elimination Plant allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-E) at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | 2439/SWSD | 21/03/2022 | 75 | M/S DEBRAJ ENTERPRISE | 85.61 | 0 | 0 | 85
769 | DARJEELING | Northern Mechanical | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 107/NMD | 03/02/2023 | 30 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 0 | 100
770 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Construction of 350 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging Height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Thakurganj at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL.NO. 01. | 273/SWSD | 06/05/2022 | 1122 | HIMADRI DAM & CO. | 158.69 | 0 | 0 | 60
771 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Construction of Pump House with toilet, plinth protection etc. installation of IEP and Boundary Wall at Thakurganj of THAKURGANJ Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 646/SWSD | 15/06/2023 | 226 | HIMADRI DAM & CO. | 49.26 | 0 | 0 | 35
772 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Acceptance cum Work Order for Additional Work for functional house hold tap connection (FHTC) at Agumentation Thakurganj and Adjoining Mouzas water Supply Scheme under Phansidewa Block under Siliguri Sub Division , P.H.E. Dte. | 1238/SWSD | 24/04/2025 | 30 | VIJAY KUMAR ARORA | 13.11 | 0 | 0 | 0
773 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , SM/09827 | Augmentation | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) and rising main at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 03. | 863/SWSD | 21/07/2022 | 1200 | AKASH ENTERPRISE | 122.09 | 0 | 0 | 2
774 | DARJEELING | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Purba Bansgaon Chakla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 412/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.69 | 0 | 0 | 0
775 | DARJEELING | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Material Requisition To Resource Division | 212/SWSD | 25/04/2023 | 0 | Resource Division | 23.82 | 0 | 0 | 0
776 | DARJEELING | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Material Requisition To Resource Division | 83/SWSD | 10/01/2024 | 0 | Resource Division | 12.11 | 0 | 0 | 0
777 | DARJEELING | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326724, Reference ID : 403152618] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.12 | 0 | 0 | 0
778 | DARJEELING | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. I, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326733, Reference ID : 403152619] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0 | 0
779 | DARJEELING | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Additional Charges for New Service Connection at Purba Bansgaon Chakla PWSS ,Zone-II,TW-II under NMD PHEdte. Ref ID- 860316628 Application ID- 100000122188 | BP/24-25/245 | 26/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.22 | 0 | 0 | 0
780 | DARJEELING | Central Drilling | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
781 | DARJEELING | Siliguri W/S Division | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos.), IEP, boundary wall and tubewell under Jal Jeevan Mission of PURBA BANSGAON CHAKLA Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte | 1148/SWSD | 08/08/2023 | 420 | UNIBRO INFRASERV PRIVATE LIMITED | 497.64 | 0 | 0 | 10
782 | DARJEELING | Northern Mechanical | PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME ( ZONE- I & II ) , SM/15929 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1582/NMD | 08/09/2023 | 723 | M/S SAJAHAN CHOWDHURY | 34.01 | 0 | 0 | 70
783 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/15876 | New | Material Requisition To Resource Division | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 7.38 | 0 | 0 | 0
784 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/15876 | New | WATER SUPPLY SCHEME FOR PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 682/NKWSMD | 12/07/2023 | 455 | RAMESH AGARWAL | 701.65 | 0 | 0 | 50
785 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME. , SM/15876 | New | Additional estimate for water supply scheme for Pumong Tea Garden piped water supply scheme in rangli-rangliot Block under Darjeeling District. | 983/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 48.79 | 0 | 0 | 100
786 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. , SM/15877 | New | Material Requisition To Resource Division | 327/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.21 | 0 | 0 | 0
787 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. , SM/15877 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024 | 385/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
788 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEWARI BOTAY PIPED WATER SUPPLY SCHEME. , SM/15877 | New | WATER SUPPLY SCHEME FOR CHEWARIBOTAY PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 261/NKWSMD | 15/05/2023 | 120 | NIMA SHERPA | 132.89 | 0 | 0 | 100
789 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARBATIA KHASMAHAL PWSS , SM/18189 | New | Material Requisition To Resource Division | 211/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.77 | 0 | 0 | 0
790 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARBATIA KHASMAHAL PWSS , SM/18189 | New | WATER SUPPLY SCHEME FOR BARBATIA KHASMAHAL PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 182/NKWSMD | 04/05/2023 | 330 | MS. SURYA I PVT. LTD COMPANY | 194.76 | 0 | 0 | 95
791 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Toryak Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/19033 | New | Surface water based Toryak Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District | 1328/NKWSMD | 03/11/2023 | 365 | SHAKTI CONSTRUCTION | 1230.38 | 0 | 0 | 100
792 | DARJEELING | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS , SM/18721 | New | Material Requisition To Resource Division | 976/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.58 | 0 | 0 | 0
793 | DARJEELING | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS , SM/18721 | New | WATER SUPPLY SCHEME FOR GINGLAM & GIELLE TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 907/NKWSMD | 11/08/2023 | 415 | RAMESH AGARWAL | 1031.49 | 0 | 0 | 100
794 | DARJEELING | Neorakhola W/S & Mtc.Div. | GINGLAM & GIELIE TEA GARDEN PWSS , SM/18721 | New | Additional Estimate for Water Supply Scheme for Ginglam & Gielle Tea Garden Piped Water Supply Scheme in Rangli-Rangliot Block under Darjeeling District. (SM/18721) | 985/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 32.15 | 0 | 0 | 100
795 | DARJEELING | Neorakhola W/S & Mtc.Div. | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10817 | New | Material Requisition To Resource Division | 2368/NKWSMD | 03/02/2023 | 0 | Resource Division | 6.09 | 0 | 0 | 0
796 | DARJEELING | Neorakhola W/S & Mtc.Div. | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10817 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-294 | 02/11/2023 | 0 | WBSEDCL | 2.71 | 0 | 0 | 0
797 | DARJEELING | Neorakhola W/S & Mtc.Div. | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10817 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-293 | 02/11/2023 | 0 | WBSEDCL | 5.02 | 0 | 0 | 0
798 | DARJEELING | Neorakhola W/S & Mtc.Div. | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10817 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 0 | 100
799 | DARJEELING | Neorakhola W/S & Mtc.Div. | SIMULBARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/10817 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
800 | DARJEELING | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS , SM/18729 | New | Piped Water Supply Scheme for Rongchong and Labda under Kurseong Division. Scheme code - 18729 TSM/018103 | BP-2024-25-97 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.04 | 0 | 0 | 0
801 | DARJEELING | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS , SM/18729 | New | WATER SUPPLY SCHEME FOR RANGCHONG & LABDA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT | 936/NKWSMD | 16/08/2023 | 605 | VINAYAK CONSTRUCTION | 1186.16 | 0 | 0 | 100
802 | DARJEELING | Neorakhola W/S & Mtc.Div. | RONGCHONG AND LABDA PWSS , SM/18729 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR RONGCHONG AND LABDA IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION. PHED/GTA. | 655/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 107.78 | 0 | 0 | 0
803 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) , SM/18730 | New | Material Requisition To Resource Division | 1285/NKWSMD | 17/10/2023 | 0 | Resource Division | 6.92 | 0 | 0 | 0
804 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) , SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-I) (MARGARET HOPE) | 1207/NKWSMD | 10/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1076.48 | 0 | 0 | 90
805 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) , SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-II) (MARGARET HOPE) | 1286/NKWSMD | 17/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1084.55 | 0 | 0 | 80
806 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) , SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-III) | 1287/NKWSMD | 17/10/2023 | 365 | TIKARAM SHARMA | 973.97 | 0 | 0 | 85
807 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra , SM/10561 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Home Dara(Tower Dara) Gram Panchyat -Relling , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009299 SM Code-SM/08927 GO2223000391PH | 258/NKWSMD | 10/05/2022 | 60 | M/S DIVYA ENTERPRISES | 13.79 | 0 | 0 | 0
808 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Tower Danra , SM/10561 | Retrofitting | Material Requisition To Resource Division | 1258/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.68 | 0 | 0 | 0
809 | DARJEELING | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS , SM/18336 | New | WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 850/NKWSMD | 27/07/2023 | 715 | HIMALAYAN CONSTRUCTION | 921.25 | 0 | 0 | 85
810 | DARJEELING | Neorakhola W/S & Mtc.Div. | SITTONG KHASMAHAL PWSS , SM/18336 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 775/NKWSMD | 28/05/2025 | 180 | HIMALAYAN CONSTRUCTION | 122.95 | 0 | 0 | 0
811 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Material Requisition To Resource Division | 1809/SWSD | 30/09/2023 | 0 | Resource Division | 193.96 | 0 | 0 | 0
812 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part D) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12. | 855/SWSD | 21/07/2022 | 25 | SWAPAN CHANDRA DAS | 24.77 | 0 | 0 | 40
813 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part B) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | 853/SWSD | 21/07/2022 | 30 | PRADIP GUHA | 26.69 | 0 | 0 | 40
814 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part C) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 11 | 854/SWSD | 21/07/2022 | 25 | M/S SHIVAJI ROY | 18.45 | 0 | 0 | 40
815 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Soil investigation of Shyamdhan Zone- I PWSS for Construction of 300 cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | 435/SSD | 12/09/2023 | 20 | GEOCON INDIA | 1.03 | 0 | 0 | 100
816 | DARJEELING | Central Drilling | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
817 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Soil investigation of Shyamdhan Zone- II PWSS for Construction of 200 Cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | 436/SSD | 12/09/2023 | 20 | MABCO CONSULTANT | 1.03 | 0 | 0 | 100
818 | DARJEELING | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. II, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320230, Reference ID : 403147069] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0 | 0
819 | DARJEELING | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. III, ZONE-I under KHARIBARI CCC, [APPLICATION NO. 4003320066, Reference ID : 403147080] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.42 | 0 | 0 | 0
820 | DARJEELING | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | New Service Connection Charge for SHYAMDHAN, T/W No. I, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320289, Reference ID : 403147077] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.07 | 0 | 0 | 0
821 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Construction of 300 Cu.M. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd TW site and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan (ZONE-I) Piped Water Supply Scheme (PART-A), Kharibari block under Siliguri Sub Division.P.H.E.Dte. | 1049/SWSD | 28/07/2023 | 787 | M/S BIRAT CONSTRUCTION | 319.92 | 0 | 0 | 40
822 | DARJEELING | Northern Mechanical | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III ,& (Zone-II) TW-I,II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1394/NMD | 09/08/2023 | 753 | WEST BENGAL ENGINEERING CO. | 34.92 | 0 | 0 | 90
823 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Construction of Pump House 2 Nos. (3.65 X 2.45, Zn-II 2nd and 3rd T/W Zn-I) size with (1.20 X 2.10 M) size toilet, plinth protection, 3 nos. Boundary Wall and IEP (40 cu.m/hr. Zn-II H/W, 20 cu.m/hr Zn-I H/W) Supplying, fabrication eretion on suitable RCC foundation and Commissioning with 3 (three) month trial run of pressure type Iron Removal Plant with Blower cum Compressure Room 2 nos. (Zn-II and I, H/W) with required size platform, surface drain at SHYAMDHAN Piped Water Supply Scheme at kharibari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 1414/SWSD | 22/08/2023 | 541 | KOHINOOR ALAM | 84.29 | 0 | 0 | 40
824 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | Work order for Construction of 200 cu.m capacity R.C.C. Elevated Reservoir, 20 mtrs. staging height at the head work site including pump house (H/W site), rising main and distribution system with providing household tap connection (FHTC), construction of rig bored big dia deep tubewells (H/W & 2nd sites) by ODEX-165 method of drilling and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan Piped Water Supply Scheme (Zone-II), Kharibari block under Siliguri Sub Division, P.H.E. Dte. | 107/SWSD | 15/01/2024 | 580 | M/S YOUNG ASSOCIATES | 329.38 | 0 | 0 | 35
825 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME , SM/18421 | Augmentation | CONSTRUCTION OF BOUNDARY WALL, DRAIN, PATHWAY INCLUDING LAND DEVELOPMENT AT HEAD WORK SITE OF SHYAMDHAN ZONE-II AND RENOVATION OF BOUNDARY WALLS, PUMP HOUSES AT H/W SITE AND 2ND SITE OF SHYAMDHAN ZONE-I INCLUDING WASHOUT LINES ICW AUGMENTATION OF SHYAMDHAN PWSS RELATED TO JAL JEEVAN MISSION (JJM) AT KHARIBARI BLOCK WITHIN SILIGURI W/S DIVISION, PHE DTE. | 2845/SWSD | 23/10/2024 | 330 | D S ENTERPRISE | 43.07 | 0 | 0 | 30
826 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA , SM/11337 | Retrofitting | Material Requisition To Resource Division | 1310/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.44 | 0 | 0 | 0
827 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Gitangay under Kurseong-Sub Division, PHED, GTA , SM/11337 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Gitangay T.E. Mahanadi GP Block - Kurseong Block | 803/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 11.87 | 0 | 0 | 100
828 | DARJEELING | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Material Requisition To Resource Division | 1807/SWSD | 30/09/2023 | 0 | Resource Division | 18.81 | 0 | 0 | 0
829 | DARJEELING | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANDILA JHAR PIPED WATER SUPPLY SCHEME, TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1671/NMD | 29/09/2023 | 460 | SAIKAT SINHA | 11.58 | 0 | 0 | 100
830 | DARJEELING | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Material Requisition To Resource Division | 76/SWSD | 10/01/2024 | 0 | Resource Division | 9.49 | 0 | 0 | 0
831 | DARJEELING | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Infrastructure Cost for MANDILA JHAR T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322508, Reference ID : 403149170] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.46 | 0 | 0 | 0
832 | DARJEELING | Northern Mechanical | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Infrastructure Cost for MANDILA JHAR T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322513, Reference ID : 403149165] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.51 | 0 | 0 | 0
833 | DARJEELING | Central Drilling | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
834 | DARJEELING | Siliguri W/S Division | Mandila Jhar Piped Water Supply Scheme. , SM/18784 | New | Work Order for Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height at the head work site including distribution system (HDPE) with rising main, Rig bore 2 nos. big dia T/W by Odex-165 method, providing functional household tap connection (FHTC), pump house 2 nos., blower room, IEP 60 cu.m./hr., boundary walls, soil testing and allied works at Mandilajhar PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 1812/SWSD | 03/10/2023 | 393 | KRISHNA TRADING CO. | 509.14 | 0 | 0 | 60
835 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Material Requisition To Resource Division | 2033/SWSD | 16/12/2022 | 0 | Resource Division | 15.89 | 0 | 0 | 0
836 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 247/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.53 | 0 | 0 | 100
837 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1478/NMD | 17/08/2023 | 30 | SAIKAT SINHA | 12.5 | 0 | 0 | 100
838 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | New Service Connection Charge for ORD TERAI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003291503 ; Reference ID : 403124697] | BP/23-24/222 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.07 | 0 | 0 | 0
839 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | New Service Connection Charge for ORD TERAI, T/W No. II under NAXALBARI CCC [APPLICATION NO. 4003312826 , Reference ID : 4031141988] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
840 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 17/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0 | 0
841 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
842 | DARJEELING | Northern Mechanical | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
843 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12749 | Augmentation | Construction of 200 cum capacity RCC Elevated Reservoir, 20 mtrs. Staging height at the head works site along with distribution system rising main, iron elimination plant, pump houses, boundary walls, functional house hold tap connection (FHTC), soil investigation and other allied works under Jal Jeevan Mission (JJM) for Augmentation of ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | 2655/SWSD | 02/03/2023 | 841 | VIJAY KUMAR ARORA | 209.89 | 0 | 0 | 65
844 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Ghusuru Piped water Supply Scheme at Naxalbari Block , SM/07423 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for BHAKTARAM UTTAM CHAND UTTAM CHANDER CHHAT HODUVITA and MUDIR JANGAL mouza of GHUSURU Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte SL. NO. 03 | 1215/SWSD | 01/11/2021 | 45 | ARUN KUMAR SHRIVASTAVA | 36.04 | 0 | 0 | 100
845 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Providing functional household tap connection under Jal Jeevan Mission & Jal Swapno programme for Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | 1637/SWSD | 28/12/2021 | 15 | KAMAL GHOSH | 4.31 | 0 | 0 | 100
846 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal Swapno Programme for Kawakhali Piped Water Supply Scheme at Matigar Block under Siliguri Sub-Division, P.H.E. Dte. | 707/SWSD | 03/08/2021 | 120 | DEBASHIS SINHA | 34.96 | 0 | 0 | 100
847 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Additional work of providing functional household tap connection under Jal jeevan Mission and Jal Swapno for Kawakhali piped water supply scheme at Matigara Block under Siliguri Sub division,P.H.Engineering Dte. | 508/SSD | 16/11/2022 | 15 | DEBASHIS SINHA | 1.1 | 0 | 0 | 0
848 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Minor repairing works in connection with functional household tap connection at Kawakhali piped W/S Scheme at Matigara Blockunder siliguri sub division,P.H.E Dte | 543/SSD | 19/12/2022 | 15 | KAMAL GHOSH | 0.77 | 0 | 0 | 100
849 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12 | 996/SWSD | 08/09/2021 | 15 | S.G.CONSTRUCTION | 4.71 | 0 | 0 | 0
850 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Kawakhali (JL No-75) Mouza of Kawakhali Piped water Supply Scheme , SM/07033 | Retrofitting | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Bairagi Piped Water Supply Scheme at Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | 1002/SWSD | 09/09/2021 | 15 | M/S ROYAL ENTERPRISE | 4.71 | 0 | 0 | 100
851 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Continuation order for hiring of 1 (one) no. well maintained diesel consumed luxury cab on monthly hired basis preferably MAXI CAB (A/C) with engine capacity less than or equal to 2000 CC for office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte., Vivekananda Bhawan (2nd floor) Hill Cart Road, Siliguri (for Assistant Chief Engineer, Northern Zone (Civil), P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022. | 2269/SWSD | 24/02/2022 | 6 | OM TRAVELS | 0.88 | 0 | 0 | 100
852 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Material Requisition To Resource Division | 2025/SWSD | 16/12/2022 | 0 | Resource Division | 134.96 | 0 | 0 | 0
853 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1329/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.47 | 0 | 0 | 100
854 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART ROAD, SILIGURI FOR THE PERIOD FROM 01.10.2022 TO 28.02.2023 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.) i.e. 5 (FIVE) MONTHS. | 1435/SWSD | 28/09/2022 | 153 | PINKI DAM | 0.74 | 0 | 0 | 100
855 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Material Requisition To Resource Division | 1456/SWSD | 29/09/2022 | 0 | Resource Division | 13.34 | 0 | 0 | 0
856 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | New Service Connection Charge for BAIRATISAL,ZONE-I TW No. I, SHIVMANDIR CCC, [APPLICATION NO.4003158519, Reference ID : 403021368] | BP/23-24/29 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0 | 0
857 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, PHE DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART, ROAD, SILIGURI FOR THE PERIOD FROM 01.04.2022 TO 30.09.2022 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.). (i.e. 6 months) | BP-2022-23-120 | 20/02/2023 | 0 | PINKI DAM | 1.72 | 0 | 0 | 0
858 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Construction of 350 Cum. capacity R.C.C Elevated Reservoir , 20 Mtrs. Staging Height at the head works site including Rising Main, distribution system and providing functional household tap connection (FHTC) & IEP, boundary wall and sub soil investigation for Augmentation of BAIRATISAL & ADJ. Mouza's (Zone-I) Water Supply Scheme under Matigara block under Siliguri W/S Division, P.H.E. Dte. | 652/SWSD | 15/06/2023 | 1077 | FAIRDEAL ASSOCIATES | 476.26 | 0 | 0 | 70
859 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
860 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , SM/10469 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1491/NMD | 17/08/2023 | 442 | M/S MATRI CONSTRUCTION | 12.5 | 0 | 0 | 100
861 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Naxalbari W/S Scheme at Naxalbari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 02. | 819/SWSD | 13/08/2021 | 25 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 0 | 100
862 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Material Requisition To Resource Division | 2042/SWSD | 16/12/2022 | 0 | Resource Division | 131.38 | 0 | 0 | 0
863 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Construction of Pump House (3.65 X 2.45) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. at Kamala zone of Naxalbari Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. SL. NO. 07. | 307/SWSD | 10/05/2022 | 50 | S.G.CONSTRUCTION | 4.15 | 0 | 0 | 100
864 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supplying, fabrication, erection on subitable RCC foundation and commissioning with 3 (three) months trial run of pressure type Iron Removal Plant with bower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E. Plant with surface drain of required length at Budhkaran Zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 15 cu.m./hr.). SL. NO. 13. | 2437/SWSD | 21/03/2022 | 45 | SUBIR CH. CHOWDHURY | 13.81 | 0 | 0 | 0
865 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dayaram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | 283/SSD | 26/05/2022 | 60 | SHREYANSH AUTOMOBILE | 4.17 | 0 | 0 | 100
866 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Chhota Maniram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | 281/SSD | 26/05/2022 | 60 | A.B. GANAPATI CONSTRUCTION | 4.17 | 0 | 0 | 100
867 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Rathkhola Bhimram Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 15 Cu.M./hr.) Sl. No. 08. | 851/SWSD | 21/07/2022 | 45 | DEBRAJ ENTERPRISE | 13.82 | 0 | 0 | 0
868 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Dhakna Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 20 Cu.M./hr.) Sl. No. 09. | 852/SWSD | 21/07/2022 | 45 | SUBIR CH. CHOWDHURY | 14.66 | 0 | 0 | 0
869 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supplying, fabrication, erection on suitable RCC foundation and commissioning with 3(three) months trial run of pressure type Iron Removal Plant with blower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Tutaram zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 30 cu.m./hr.) SL. NO. 11. | 542/SWSD | 16/06/2022 | 45 | MAA ENTERPRISE | 16.52 | 0 | 0 | 0
870 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. | 2534/SWSD | 29/03/2022 | 12 | RUPA PRASAD | 1.48 | 0 | 0 | 100
871 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dhakna zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | 282/SSD | 26/05/2022 | 60 | M/S S.P. BISWAS | 4.18 | 0 | 0 | 100
872 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Rathkhola - Bhimram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | 280/SSD | 26/05/2022 | 60 | M/S S.P. BISWAS | 4.18 | 0 | 0 | 60
873 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Material Requisition To Resource Division | 1455/SWSD | 29/09/2022 | 0 | Resource Division | 53.04 | 0 | 0 | 0
874 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | New Service Connection Charge for RATHKHOLA BHIMRAM W/S Scheme, T/W No. III, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049742, Reference ID : 402926292] | BP/22-23/125 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
875 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | New Service Connection Charge for NAXALBARI PWSS (DHAKNA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105319 ; Reference ID : 402974350] | BP/23-24/04 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
876 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Hiring of Vehicle for the office of the Assistant Engineer under Siliguri Sub-division ,P.H.E dte | BP-2022-23-109 | 18/01/2023 | 0 | SUDIP BASAK | 0.38 | 0 | 0 | 0
877 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | New Service Connection Charge for CHHOTO MONIRAM KALUAJOTE W/S Scheme, T/W No. II, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049226, Reference ID : 402926293] | BP/22-23/125 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
878 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | New Service Connection Charge for NAXALBARI PWSS (KAMALA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105316 ; Reference ID : 402974351] | BP/23-24/04 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
879 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Kamala (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Tutaram Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 15. | 38/SWSD | 07/04/2022 | 377 | ARUN KUMAR SHRIVASTAVA | 137.11 | 0 | 0 | 60
880 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying Distribution System and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Dayaram (Part), Kamala (Part) & Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kamala Zone) within Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | 869/SWSD | 21/07/2022 | 170 | NARAYAN CH GHOSH | 69.9 | 0 | 0 | 90
881 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dayaram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 02. | 847/SWSD | 21/07/2022 | 198 | M/S G.C. CONSTRUCTION & CO. | 83.65 | 0 | 0 | 2
882 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dhakna Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 04. | 848/SWSD | 21/07/2022 | 70 | BUDDHADEV NAG | 67.02 | 0 | 0 | 100
883 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supply installation commissioning and trial operation of electro mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE -I and II ( Rathkhola Bhimram, Kamola Jote Budhkaran) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 2161/SWSD | 29/11/2023 | 30 | CHOWDHURY & BASU ENTERPRISE | 34.09 | 0 | 0 | 90
884 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Chhoto Maniram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Chhota Maniram Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 06. | 850/SWSD | 21/07/2022 | 75 | UJJWAL ROY | 81.01 | 0 | 0 | 100
885 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1327/SWSD | 14/09/2022 | 99 | NORTH EAST CO-OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 46.37 | 0 | 0 | 100
886 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 112/NMD | 03/02/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 32.88 | 0 | 0 | 100
887 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Bengaijote Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 03. | 2074/SWSD | 13/01/2023 | 85 | KAMIRUL SK & CO | 91.79 | 0 | 0 | 100
888 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Balanced work of laying distribution system along with pump connection in connection with Augmentation of Naxalbari piped water supply scheme (chhota Maniram ZOne) under Naxalbari Block, Darjeeling District under siliguri Sub-division ,P.H.E Dte. | 523/SSD | 18/12/2023 | 31 | UJJWAL ROY | 1.91 | 0 | 0 | 100
889 | DARJEELING | Northern Mechanical | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Quotation Charges New service Connection at Naxalbari PWSS,TW-VI, Near Budhkaran under NMD,PHE Dte. Application No - 4003462594 Ref Id- 403258323 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.34 | 0 | 0 | 0
890 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno programme at Budhkaran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Budhkaran Zone) within Naxalbari block, Darjeeling dist. under Siliguri Sub Division, PHE Dte. SL. NO. 16. | 2438/SWSD | 21/03/2022 | 1412 | DEBRAJ ENTERPRISE | 92.59 | 0 | 0 | 81
891 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) Kamala (Part) and Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kalibari Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 16. | 859/SWSD | 21/07/2022 | 1086 | PALLAB BHOWAL | 129.79 | 0 | 0 | 90
892 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Rathkhola Bhimram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 15. | 858/SWSD | 21/07/2022 | 233 | M/S G.C. CONSTRUCTION & CO. | 90 | 0 | 0 | 50
893 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and providing functional household tap connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) & Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kotia Zone) under Naxalbari block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | 1405/SWSD | 21/08/2023 | 573 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 127.6 | 0 | 0 | 70
894 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Budhkraran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Roypara Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 17. | 37/SWSD | 07/04/2022 | 1365 | SUBIR CH. CHOWDHURY | 138.01 | 0 | 0 | 100
895 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME , SM/10183 | Augmentation | CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60 M) SIZE WITH SANITARY & PLUMBING ARRANGEMENT AS PER MODEL APPROVED DRAWING AT BUDHKARAN TUBEWELL SITE FOR NAXALBARI PIPED WATER SUPPLY SCHEME UNDER SILIGURI W/S DIVISION, P. H. ENGINEERING DTE. | 2540/SWSD | 18/09/2024 | 106 | NARAYAN CH GHOSH | 5.83 | 0 | 0 | 100
896 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M , SM/10687 | School | Creating gravity based Provision Of Drinking water from spring water source for 79 numbers of school under Kurseong Sub-Division in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte TSM No. 009890 | 255/NKWSMD | 06/05/2022 | 180 | GARGO TRADERS | 211.58 | 0 | 0 | 0
897 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M , SM/10687 | School | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR 93 NOS OF SCHOOL, 23 NOS OF ICDS CENTRES, 11 NOS OF HEALTH CENTRES, 8 NOS OF GRAM PANCHAYAT IN UNDER RANGLI RANGLIOT BLOCK IN THE DISTRICT OF DARJEELING UNDER NEORAKHOLA WATER SUPPLY DIVISION ,KALIMPONG PHE DTE. TSM No. 009891 | 254/NKWSMD | 06/05/2022 | 180 | GARGO TRADERS | 320.59 | 0 | 0 | 100
898 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M , SM/10687 | School | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2024 TO 30/06/2024 (3 MONTHS). | 705/NKWSMD | 27/03/2024 | 92 | NIM TSHERING LEPCHA | 3.19 | 0 | 0 | 0
899 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating Gravity based provision of Drinking water Spring water source of school (93 nos), ICDS Centres(23 nos), Health Centres,(11 Nos) Gram panchayat(8 Nos) in under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply & M , SM/10687 | School | Additional works in various institutes in connection with creating gravity based provision of drinking water from spring water source for 15 number of schools, 06 no of ICDS Centers, 02 Number of Health Centers, 01 Number of Gram Panchayat under Rangli Rangliot Block in the District of Darjeeling under Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate. | 1177/NKWSMD | 18/08/2022 | 30 | GARGO TRADERS | 4.85 | 0 | 0 | 100
900 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. , SM/10835 | New | Material Requisition To Resource Division | 1883/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.49 | 0 | 0 | 0
901 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. , SM/10835 | New | Material Requisition To Resource Division | 2592/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.49 | 0 | 0 | 0
902 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. , SM/10835 | New | Material Requisition To Resource Division | 1366/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.49 | 0 | 0 | 0
903 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. , SM/10835 | New | PIPED WATER SUPPLY SCHEME FOR MURMIDANG, KOM BUSTY & LOWER KOLBONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 1119/NKWSMD | 05/08/2022 | 180 | AMRIT KUMAR SUBBA | 107.92 | 0 | 0 | 50
904 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Murmidang, Kom Busty & lower Kolbung. , SM/10835 | New | Balance work for water supply scheme for Murmudang, Kom Busty, & Lower Kolbong under Jal Jeevan Mission & JSP programme under Pull Bijanbari Block PHED-GTA. | 880/NKWSMD | 03/08/2023 | 60 | AMRIT KUMAR SUBBA | 96.3 | 0 | 0 | 50
905 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II , SM/11383 | Retrofitting | Material Requisition To Resource Division | 1905/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.94 | 0 | 0 | 0
906 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II , SM/11383 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Relling-I & II, GP - Rungli, Block - Bijanbari Pullbazar | 1443/NKWSMD | 28/09/2022 | 60 | SUMAN PRADHAN | 60.32 | 0 | 0 | 100
907 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II , SM/11383 | Retrofitting | Material Requisition To Resource Division | 2589/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.94 | 0 | 0 | 0
908 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. , SM/11385 | Retrofitting | Material Requisition To Resource Division | 1903/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.05 | 0 | 0 | 0
909 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. , SM/11385 | Retrofitting | Material Requisition To Resource Division | 2615/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0 | 0
910 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection for balance household under Jal Jeewan Mission/Jal Swapno Programme at Vir Goan & Dhar Goan. , SM/11385 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bhir Gaon & Dhar Gaon Gram, GP - Majua, Block - Bijanbari Pulbazar. | 944/NKWSMD | 12/07/2022 | 120 | SUVASH RAI | 40.11 | 0 | 0 | 100
911 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. , SM/11386 | Retrofitting | Material Requisition To Resource Division | 1904/NKWSMD | 15/12/2022 | 0 | Resource Division | 2.92 | 0 | 0 | 0
912 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. , SM/11386 | Retrofitting | Material Requisition To Resource Division | 2616/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.92 | 0 | 0 | 0
913 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. , SM/11386 | Retrofitting | Material Requisition To Resource Division | 1364/NKWSMD | 21/09/2022 | 0 | Resource Division | 2.92 | 0 | 0 | 0
914 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. , SM/11386 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for balance household at Sumbuck & Kankeybong, GP - Jhepi, Block - Bijanbari Pulbazar. | 951/NKWSMD | 12/07/2022 | 180 | SACHIN PRADHAN | 114.36 | 0 | 0 | 100
915 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. , SM/11387 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 6th Mile Bazar Gram GP - Rampuria & Mineral Spring, Block - Pull Bijanbari | 947/NKWSMD | 12/07/2022 | 60 | PUSHKAR GURUNG | 29.98 | 0 | 0 | 0
916 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. , SM/11387 | Retrofitting | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. | BP-2023-24-40 | 11/05/2023 | 0 | KASHYAP COMPUTERS | 0.34 | 0 | 0 | 0
917 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. , SM/11387 | Retrofitting | computer operator payment | BP-2023-24-193 | 30/09/2023 | 0 | KASHYAP COMPUTERS | 0.51 | 0 | 0 | 0
918 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. , SM/11387 | Retrofitting | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | 18/04/2023 | 0 | KASHYAP COMPUTERS | 0.85 | 0 | 0 | 0
919 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA , SM/10802 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
920 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA , SM/10802 | New | SURFACE WATER BASED GHAYABARI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 605/NKWSMD | 26/05/2022 | 1010 | NAVRATNA CONSTRUCTION CO | 125.67 | 0 | 0 | 90
921 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ghayabari under Kurseong Sub Division ,PHED,GTA , SM/10802 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
922 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Creating gravity based Provision Of Drinking water from spring water source for 79 numbers of school under Kurseong Sub-Division in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte TSM No. 009890 | 255/NKWSMD | 06/05/2022 | 180 | GARGO TRADERS | 211.58 | 0 | 0 | 0
923 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Hiring of vehicle for the office of Superintending Engineer, G.T.A-Circle, P.H. Engineering Directorate for the period of 6(Six) months, other than GTA Area. Note: With effect from date of issuing work order. | 2230/NKWSMD | 31/01/2023 | 180 | SUJIT DEB | 0.99 | 0 | 0 | 25
924 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR 93 NOS OF SCHOOL, 23 NOS OF ICDS CENTRES, 11 NOS OF HEALTH CENTRES, 8 NOS OF GRAM PANCHAYAT IN UNDER RANGLI RANGLIOT BLOCK IN THE DISTRICT OF DARJEELING UNDER NEORAKHOLA WATER SUPPLY DIVISION ,KALIMPONG PHE DTE. TSM No. 009891 | 254/NKWSMD | 06/05/2022 | 180 | GARGO TRADERS | 320.59 | 0 | 0 | 100
925 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area. Note: With effect from the date of issuing work order. | 860/NKWSMD | 31/07/2023 | 180 | SUJIT DEB | 0.99 | 0 | 0 | 50
926 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | 170/NKWSMD | 31/01/2024 | 180 | SUJIT DEB | 0.99 | 0 | 0 | 0
927 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months for G.T.A Area. Note: With effect from the date of issuing work order. | 859/NKWSMD | 31/07/2023 | 184 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0 | 100
928 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Additional works in various Schools in connection with creating gravity based provision of drinking water from spring water source for 21 number of schools under Kurseong Sub Division in the District of Darjeeling under Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate. | 1178/NKWSMD | 18/08/2022 | 30 | GARGO TRADERS | 4.84 | 0 | 0 | 100
929 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of March. | BP-2024-25-170 | 01/08/2024 | 0 | PAWAN TAMANG | 0.17 | 0 | 0 | 0
930 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of August. | BP-2024-25-163 | 01/08/2024 | 0 | PAWAN TAMANG | 0.11 | 0 | 0 | 0
931 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of October. | BP-2024-25-165 | 01/08/2024 | 0 | PAWAN TAMANG | 0.12 | 0 | 0 | 0
932 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of January. | BP-2024-25-168 | 01/08/2024 | 0 | PAWAN TAMANG | 0.12 | 0 | 0 | 0
933 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of September. | BP-2024-25-164 | 01/08/2024 | 0 | PAWAN TAMANG | 0.14 | 0 | 0 | 0
934 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of February. | BP-2024-25-169 | 01/08/2024 | 0 | PAWAN TAMANG | 0.18 | 0 | 0 | 0
935 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of December. | BP-2024-25-167 | 01/08/2024 | 0 | PAWAN TAMANG | 0.17 | 0 | 0 | 0
936 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong , SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of November. | "BP-2024-25-166 | 01/08/2024 | 0 | PAWAN TAMANG | 0.15 | 0 | 0 | 0
937 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | Material Requisition To Resource Division | 2373/NKWSMD | 03/02/2023 | 0 | Resource Division | 4.21 | 0 | 0 | 0
938 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-292 | 02/11/2023 | 0 | WBSEDCL | 0.46 | 0 | 0 | 0
939 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-291 | 02/11/2023 | 0 | WBSEDCL | 0.36 | 0 | 0 | 0
940 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | Material Requisition To Resource Division | 1781/NKWSMD | 23/09/2024 | 0 | Resource Division | 0.54 | 0 | 0 | 0
941 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | payment for wbsedcl | BP-2023-24-475 | 28/01/2024 | 0 | WBSEDCL | 4.15 | 0 | 0 | 0
942 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | payment for wbsedcl | BP-2023-24-476 | 28/01/2024 | 0 | WBSEDCL | 5.49 | 0 | 0 | 0
943 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 0 | 100
944 | DARJEELING | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme , SM/10818 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
945 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11318 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram TE (Dilaram Bazar habitation) under Kurseong Sub-Division PHED, GTA. | 791/NKWSMD | 30/06/2022 | 60 | JIWAN TAMANG | 5.96 | 0 | 0 | 0
946 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram Tea Estate ( Dilaram Bazar habitation ) under Kurseong Sub-Division PHED, GTA. , SM/11318 | Retrofitting | Material Requisition To Resource Division | 1294/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
947 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. , SM/11321 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | 793/NKWSMD | 30/06/2022 | 60 | NAVRATNA CONSTRUCTION CO | 14.52 | 0 | 0 | 98
948 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. , SM/11321 | Retrofitting | Material Requisition To Resource Division | 1296/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.19 | 0 | 0 | 0
949 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div , SM/11323 | Retrofitting | Material Requisition To Resource Division | 1298/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.66 | 0 | 0 | 0
950 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div , SM/11323 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation) under Kurseong Sub-Division PHED, GTA. | 802/NKWSMD | 30/06/2022 | 60 | PHURBA RUMBA | 20.05 | 0 | 0 | 100
951 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA , SM/11327 | Retrofitting | Material Requisition To Resource Division | 1301/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.83 | 0 | 0 | 0
952 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Cricket Bazar under Kurseong Sub-Division, PHED, GTA , SM/11327 | Retrofitting | Providing Functional household Tap connection under Jal Jeevan Mission & JSP Programme including Retrofitting work for PWS scheme for Cricket Bazar Tindharay Mahanadi GP Block - Kurseong Block. | 795/NKWSMD | 30/06/2022 | 610 | BIKASH TAMANG | 12.59 | 0 | 0 | 1
953 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA , SM/11335 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Bagmara Mahanadi GP Block - Kurseong Block. | 1110/NKWSMD | 05/08/2022 | 60 | MS. SURYA I PVT. LTD COMPANY | 9.17 | 0 | 0 | 0
954 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Bagmara Busty under Kurseong-Sub Division, PHED, GTA , SM/11335 | Retrofitting | Material Requisition To Resource Division | 1314/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.36 | 0 | 0 | 0
955 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA , SM/11336 | Retrofitting | Material Requisition To Resource Division | 1309/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.63 | 0 | 0 | 0
956 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for 14th Mile and Pagla Jhora Busty under Kurseong-Sub Division, PHED, GTA , SM/11336 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for 14 Mile Mahanadi GP Block - Kurseong Block | 800/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 10.87 | 0 | 0 | 100
957 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11954 | New | Material Requisition To Resource Division | 1898/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.32 | 0 | 0 | 0
958 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11954 | New | Material Requisition To Resource Division | 2574/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.32 | 0 | 0 | 0
959 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11954 | New | WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 1530/NKWSMD | 18/10/2022 | 840 | VINAYAK CONSTRUCTION | 318.85 | 0 | 0 | 100
960 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11351 | New | Material Requisition To Resource Division | 2069/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0 | 0
961 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11351 | New | Material Requisition To Resource Division | 530/NKWSMD | 13/06/2023 | 0 | Resource Division | 2.05 | 0 | 0 | 0
962 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11351 | New | PWS Scheme at 3 Nos Montiviote TE with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 984/NKWSMD | 12/07/2022 | 60 | PRASANT NIROLA | 17.52 | 0 | 0 | 100
963 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/12128 | New | Material Requisition To Resource Division | 1891/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.68 | 0 | 0 | 0
964 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/12128 | New | Material Requisition To Resource Division | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.68 | 0 | 0 | 0
965 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/12128 | New | permission fro laying 80mm dia GI Pipeline along the hill side of Darjeeling Ghoom Bhanjang Bijanbari Road | BP-2022-23-426 | 30/03/2023 | 0 | NEORAKHOLA W/S & MTC. DIV. | 10.35 | 0 | 0 | 0
966 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MARIABONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/12128 | New | Proposed Gravity Based Water Supply Scheme for Mariabong Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. | 1451/NKWSMD | 29/09/2022 | 1000 | GARGO TRADERS | 973.62 | 0 | 0 | 100
967 | DARJEELING | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | Material Requisition To Resource Division | 2029/SWSD | 16/12/2022 | 0 | Resource Division | 1.97 | 0 | 0 | 0
968 | DARJEELING | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | Material Requisition To Resource Division | 1808/SWSD | 30/09/2023 | 0 | Resource Division | 9.89 | 0 | 0 | 0
969 | DARJEELING | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | New Service Connection Charge for rrjuvenation of Ghusuri PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144975 ; Reference ID : 403013463] | BP/23-24/10 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
970 | DARJEELING | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | New Service Connection Charge for Rejuvenation of Ghusuri PWSS, TW No. II, NAXALBARI CCC [APPLICATION NO. 4003144980 ; Reference ID : 403013029] | BP/23-24/10 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
971 | DARJEELING | Northern Mechanical | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 549/NMD | 15/05/2023 | 30 | M/S B.ENTERPRISE | 23.18 | 0 | 0 | 100
972 | DARJEELING | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | Laying distribution system along with boring of new tubewells, construction of pump house, boundary walls at 3rd and 4th tubewell site and providing FHTC at Uttam Chand, Hoda Bhitar Chhat, Uttam Chander Chhat, Mudir Jangal, Satbhaiya, Ghusuru, Raghuram, Raghuramer Chhat, Bhaktaram mouza in connection with rejuvenation of GHUSURU PIPED WATER SUPPLY SCHEME under JJM at Naxalbari block, Darjeeling District under Siliguri Sub Division, PHE Dte. | 2365/SWSD | 24/01/2023 | 90 | SUBIR CH. CHOWDHURY | 142.14 | 0 | 0 | 91
973 | DARJEELING | Siliguri W/S Division | REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , SM/12036 | Augmentation | Acceptance cum work order for Construction of 250 Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site of Ghusuru Piped Water Supply Scheme under Naxalbari Block under Siliguri Sub Division, P.H.E. Dte. | 3026/SWSD | 13/11/2024 | 618 | M/S G.C. CONSTRUCTION & CO. | 89.68 | 0 | 0 | 25
974 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 87 Nos of School under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong. , SM/11355 | School | Creating gravity based Provision Of Drinking water from spring water source for 87 Numbers of School in Jorebungalow-Sukhiapokhri Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. | 933/ NKWSMD | 12/07/2022 | 240 | NAVRATNA CONSTRUCTION CO | 232.24 | 0 | 0 | 60
975 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate , SM/11360 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 101 Numbers of Anganwadi Centre under Jorebungalow-Sukhiapokhri Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, Kalimpong P.H.Engineering Directorate. | 928/NKWSMD | 12/07/2022 | 240 | HARI PRASAD CHETTRI | 310.44 | 0 | 0 | 0
976 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source for 16 Numbers of Aganwadi Centers in Block- Kurseong, under the District of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte,. , SM/11362 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 16 (Sixteen) Numbers of Anganwadi Centers in Kurseong Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong. | 948/ NKWSMD | 12/07/2022 | 60 | MS JAGANNATH PRASAD | 37.03 | 0 | 0 | 50
977 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Mohorgaon Tea Garden Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | 289/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 3.3 | 0 | 0 | 100
978 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Material Requisition To Resource Division | 2050/SWSD | 16/12/2022 | 0 | Resource Division | 24.61 | 0 | 0 | 0
979 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Material Requisition To Resource Division | 2303/SWSD | 12/12/2023 | 0 | Resource Division | 2.72 | 0 | 0 | 0
980 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Material Requisition To Resource Division | 62/SWSD | 09/01/2024 | 0 | Resource Division | 6.3 | 0 | 0 | 0
981 | DARJEELING | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No.II, under MATIGARA CCC, [APPLICATION NO. 4003316001, Reference ID : 403143726] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.06 | 0 | 0 | 0
982 | DARJEELING | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Infrastructure Cost for MOHORGAON T/W-III, under PRADHAN NAGAR CCC , [APPLICATION NO. 4003337401, Reference ID : 403161193] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0 | 0
983 | DARJEELING | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No. I, under MATIGARA CCC, [APPLICATION NO. 4003315986, Reference ID : 403143724] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.4 | 0 | 0 | 0
984 | DARJEELING | Central Drilling | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
985 | DARJEELING | Northern Mechanical | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,IIand (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1651/NMD | 29/09/2023 | 30 | M/S SAJAHAN CHOWDHURY | 23.8 | 0 | 0 | 100
986 | DARJEELING | Siliguri W/S Division | MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/12751 | New | Work Order for Construction of 200 cu.m capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main, Construction of 3 nos Big dia rig bore tube well by ODEX 165, Pump House (5.4 X 3.60 m), Iron Elemination Plant, Boundary Wall including Functional Household Tap Connection at MOHORGAON TEA GARDEN Piped Water Supply Scheme (Zone I & II) under Matigara Block, Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | 1977/SWSD | 26/10/2023 | 885 | EASHAN POLYMERS PRIVATE LIMITED | 492.88 | 0 | 0 | 35
987 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13957 | New | Material Requisition To Resource Division | 2551/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.08 | 0 | 0 | 0
988 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13957 | New | WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 2148/NKWSMD | 20/01/2023 | 240 | M/S. ASHOK KUMAR PERIWAL | 390.86 | 0 | 0 | 50
989 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13958 | New | Material Requisition To Resource Division | 2584/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0 | 0
990 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13958 | New | WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 2004/NKWSMD | 23/12/2022 | 912 | ABHINAY CHETTRI | 306.39 | 0 | 0 | 100
991 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/12983 | New | Material Requisition To Resource Division | 2595/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.26 | 0 | 0 | 0
992 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/12983 | New | Material Requisition To Resource Division | 571/NKWSMD | 22/06/2023 | 0 | Resource Division | 7.02 | 0 | 0 | 0
993 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/12983 | New | Continuation Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 | 1469/NKWSMD | 01/12/2023 | 62 | THE ELECTRIC SPHERE | 0.41 | 0 | 0 | 0
994 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/12983 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST UNDER KURSEONG DIVISION. SCHEME CODE - 12983 TSM/012820 | BP-2024-25-96 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 8.41 | 0 | 0 | 0
995 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JORE BUNGLOW SUKHIA POKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/12983 | New | WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | 2472/NKWSMD | 06/02/2023 | 1005 | M/S. ASHOK KUMAR PERIWAL | 1198.11 | 0 | 0 | 85
996 | DARJEELING | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | Material Requisition To Resource Division | 2021/SWSD | 15/12/2022 | 0 | Resource Division | 2.39 | 0 | 0 | 0
997 | DARJEELING | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Manja Tea Garden Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 312/SSD | 14/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.28 | 0 | 0 | 100
998 | DARJEELING | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. I under NAXALBARI CCC, [APPLICATION NO. 4003194643, Reference ID : 403046929] | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.19 | 0 | 0 | 0
999 | DARJEELING | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. III under NAXALBARI CCC, [APPLICATION NO. 4003194667, Reference ID : 403046932] | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
1000 | DARJEELING | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | New Service Connection Charge for MANJHA T.G., T.W. No. II under NAXALBARI CCC, [APPLICATION NO. 4003194663, Reference ID : 403046923] | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
1001 | DARJEELING | Northern Mechanical | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ,(Zone-I) TW No. I and (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1210/NMD | 26/07/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 23.21 | 0 | 0 | 100
1002 | DARJEELING | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | Material Requisition To Resource Division | 87/SWSD | 10/01/2024 | 0 | Resource Division | 3.3 | 0 | 0 | 0
1003 | DARJEELING | Siliguri W/S Division | MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/13440 | New | Laying distribution system along with construction of pump houses with toilet, boundary walls at tube well sites, laying of rising main, providing FHTC with platform and other allied works under Jal Jeevan Mission (JJM) for MANJHA TEA GARDEN Piped Water Supply Scheme under Naxalbari block, Darjeeling District under Siliguri Sub Division, P.H.E. Dte. | 2504/SWSD | 10/02/2023 | 324 | BUDDHADEV NAG | 154.25 | 0 | 0 | 90
1004 | DARJEELING | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Material Requisition To Resource Division | 2048/SWSD | 16/12/2022 | 0 | Resource Division | 16.99 | 0 | 0 | 0
1005 | DARJEELING | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF HANSQUA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 258/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.01 | 0 | 0 | 100
1006 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | New Service Connection Charge for HANSQUA TEA GARDEN, T.W. No. I under BAGDOGRA CCC, [APPLICATION NO. 4003194521, Reference ID : 403046887] | BP/23-24/76 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.64 | 0 | 0 | 0
1007 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF HANSQUA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1668/NMD | 29/09/2023 | 30 | M/S SIMARR | 10.31 | 0 | 0 | 100
1008 | DARJEELING | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | QUOTATION IVO SHIFTING OF A PART OF HNSQUA 11 KV FEEDER EMANETED FRAM BAGDOGRA 33/11 KV SUBSTATION IN THE AREA OF PHE DTE HANSQUA WATER PUMP HOUSE | BP-2023-24-146 | 03/01/2024 | 0 | WBSEDCL | 2.59 | 0 | 0 | 0
1009 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | "New Service Connection Charge for HANSQUA TEA GARDEN TW-I " APPLICATION NO.4003194521 Reference ID : 403046887 | BP/24-25/99 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0 | 0
1010 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | New Service Connection Charge for HANSQUA TEA GARDEN, T/W No. II, under BAGDOGRA CCC [APPLICATION NO. 4003291262 ; Reference ID : 403123837] | BP/23-24/201 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.1 | 0 | 0 | 0
1011 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Infrastructure Cost for HANSQUA, T/W No. I, under KADAMTALA CCC, [APPLICATION NO. 100000095265, Reference ID : 860287415] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.59 | 0 | 0 | 0
1012 | DARJEELING | Siliguri W/S Division | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Construction of 100 cu.m. capacity R.C.C. Elevated Reservoir of 20 Mtrs. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells by ODEX-165 method, construction of pump house with toilet, boundary wall at head works and 2nd tubewell site with necessary interconnection, providing FHTC with platform and other allied works under Jal Jeevan Mission for Augmentation of HANSQUA TEA GARDEN Piped WS Scheme of Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 2919/SWSD | 24/03/2023 | 882 | SUBIR CH. CHOWDHURY | 296.64 | 0 | 0 | 90
1013 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
1014 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
1015 | DARJEELING | Northern Mechanical | Augmentation of Hansqua Tea Garden area Piped Water Supply Scheme , SM/13391 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
1016 | DARJEELING | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Material Requisition To Resource Division | 2045/SWSD | 16/12/2022 | 0 | Resource Division | 16.3 | 0 | 0 | 0
1017 | DARJEELING | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BAGULAHAGI & BHATTAGACHH PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 250/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.92 | 0 | 0 | 100
1018 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319706, Reference ID : 403147081] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.67 | 0 | 0 | 0
1019 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319825, Reference ID : 403147074] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.77 | 0 | 0 | 0
1020 | DARJEELING | Central Drilling | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1021 | DARJEELING | Siliguri W/S Division | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Laying Rising main, laying distribution pipeline with functional household Tap connection (FHTC), construction of two number pump house (5.40 X 3.60 m), Iron Elimination plant (IEP) with Blower Room and sinking of 2 (two) Nos.Tube Well (ODEX- 165 method) and boundary wall for BAGULAHAGI and BHATTAGACHH PWSS Block - Kharibari, Dist : Darjeeling under Siliguri Sub Division , P.H.E. Dte. Sl No 07. | 867/SWSD | 14/07/2023 | 120 | NARENDRA KUMAR | 197.75 | 0 | 0 | 25
1022 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0 | 0
1023 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
1024 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1025 | DARJEELING | Northern Mechanical | Augmentation of Bagulahagi & Bhattagachh Piped Water Supply Scheme , SM/13392 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAGULAHAGI and BHATTAGACHH PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte | 1667/NMD | 29/09/2023 | 531 | MALAY KUMAR SAHA | 11.86 | 0 | 0 | 100
1026 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME , SM/16157 | New | Material Requisition To Resource Division | 244/NKWSMD | 12/05/2023 | 0 | Resource Division | 0.77 | 0 | 0 | 0
1027 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME , SM/16157 | New | TAKDAH FOREST WATER SUPPLY SCHEME UNDER JAL JEEWAN MISSION | BP-2024-25-283 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 7 | 0 | 0 | 0
1028 | DARJEELING | Neorakhola W/S & Mtc.Div. | TUKDAH FOREST PIPED WATER SUPPLY SCHEME , SM/16157 | New | WATER SUPPLY SCHEME FOR TUKDAH FOREST PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 108/NKWSMD | 28/04/2023 | 1347 | RAMESH AGARWAL | 108.34 | 0 | 0 | 95
1029 | DARJEELING | Neorakhola W/S & Mtc.Div. | KOLBONG KHASMAHAL PWSS , SM/15840 | New | Material Requisition To Resource Division | 324/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.88 | 0 | 0 | 0
1030 | DARJEELING | Neorakhola W/S & Mtc.Div. | KOLBONG KHASMAHAL PWSS , SM/15840 | New | WATER SUPPLY SCHEME FOR KOLBONG KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK : RANGLI RANGLIOT, DISTRICT: DARJEELING. | 189/NKWSMD | 04/05/2023 | 772 | SRINIWAS AGARWAL | 212.21 | 0 | 0 | 100
1031 | DARJEELING | Neorakhola W/S & Mtc.Div. | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. , SM/15909 | New | Material Requisition To Resource Division | 444/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.74 | 0 | 0 | 0
1032 | DARJEELING | Neorakhola W/S & Mtc.Div. | Up & Lr SUMBUK PIPED WATER SUPPLY SCHEME. , SM/15909 | New | Water Supply Scheme For Upper & Lower Sumbuk Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. | 418/NKWSMD | 05/06/2023 | 360 | HARI PRASAD CHETTRI | 278.38 | 0 | 0 | 100
1033 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden , SM/16474 | New | Material Requisition To Resource Division | 2773/NKWSMD | 10/03/2023 | 0 | Resource Division | 3.01 | 0 | 0 | 0
1034 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden , SM/16474 | New | SURFACE WATER BASED MAHARANI TEA GARDEN PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | 2737/NKWSMD | 03/03/2023 | 805 | SRINIWAS AGARWAL | 440.47 | 0 | 0 | 65
1035 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Maharani Tea Garden , SM/16474 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAHARANI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 636/NKWSMD | 05/05/2025 | 120 | SURAJMULL PRABHUDAYAL | 16.26 | 0 | 0 | 100
1036 | DARJEELING | Neorakhola W/S & Mtc.Div. | BIJANBARI PIPED WATER SUPPLY SCHEME. , SM/15869 | New | Material Requisition To Resource Division | 325/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.84 | 0 | 0 | 0
1037 | DARJEELING | Neorakhola W/S & Mtc.Div. | BIJANBARI PIPED WATER SUPPLY SCHEME. , SM/15869 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1038 | DARJEELING | Neorakhola W/S & Mtc.Div. | BIJANBARI PIPED WATER SUPPLY SCHEME. , SM/15869 | New | WATER SUPPLY SCHEME FOR BIJANBARI PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 89/NKWSMD | 27/04/2023 | 817 | VAISHNO CONSTRUCTION | 339.14 | 0 | 0 | 90
1039 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GUABARI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15628 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1040 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15626 | Solarisation | Quotation Charges for Net Metering connection at Bhalamanshi Piped Water Supply Scheme under PHE Dte. Application no- 4003471161 Consumer ID- 402322812 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1041 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15626 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1042 | DARJEELING | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS , SM/16771 | New | Material Requisition To Resource Division | 151/NKWSMD | 03/05/2023 | 0 | Resource Division | 0.47 | 0 | 0 | 0
1043 | DARJEELING | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS , SM/16771 | New | Material Requisition To Resource Division | 212/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.47 | 0 | 0 | 0
1044 | DARJEELING | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS , SM/16771 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SINGALILA UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PUL BIJANBARI BLOCK. | 2368/NKWSMD | 20/12/2024 | 90 | RINZI SHERPA | 29 | 0 | 0 | 0
1045 | DARJEELING | Neorakhola W/S & Mtc.Div. | SINGALILA FOREST PWSS , SM/16771 | New | WATER SUPPLY SCHEME FOR SINGALILA FOREST PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 87/NKWSMD | 27/04/2023 | 858 | NIMA SHERPA | 364.9 | 0 | 0 | 100
1046 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals , SM/15661 | New | Material Requisition To Resource Division | 2770/NKWSMD | 10/03/2023 | 0 | Resource Division | 4.4 | 0 | 0 | 0
1047 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals , SM/15661 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1048 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals , SM/15661 | New | PWS Scheme For St Marys and Geothals | BP-2024-25-458 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.52 | 0 | 0 | 0
1049 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals , SM/15661 | New | SURFACE WATER BASED ST. MARYS AND GOETHALS PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK. | 2670/NKWSMD | 01/03/2023 | 180 | SITA SHARMA | 300.54 | 0 | 0 | 60
1050 | DARJEELING | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. , SM/18723 | New | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 0 | 100
1051 | DARJEELING | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. , SM/18723 | New | Ground Water Reservoir of 20 ML At Sepoydhura Near Woodcut Under Kurseong Division, P.H.E.D-GTA. | 1288/NKWSMD | 17/10/2023 | 928 | INTERIOR'S NEST | 2445.49 | 0 | 0 | 35
1052 | DARJEELING | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. , SM/18723 | New | Augmentation for ground water Reservoir of capacity 20 ML at Sepoydhura (Near Woodcut) Kurseong under PHED, Kusseong Sub- Division, GTA. | 824/NKWSMD | 09/06/2025 | 365 | INTERIOR'S NEST | 411.05 | 0 | 0 | 0
1053 | DARJEELING | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS , SM/18316 | New | Material Requisition To Resource Division | 760/NKWSMD | 19/07/2023 | 0 | Resource Division | 9.95 | 0 | 0 | 0
1054 | DARJEELING | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS , SM/18316 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1055 | DARJEELING | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS , SM/18316 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1595/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
1056 | DARJEELING | Neorakhola W/S & Mtc.Div. | HUM TUKDAH KHASMAHAL PWSS , SM/18316 | New | WATER SUPPLY SCHEME FOR HUM TUKDAH KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 674/NKWSMD | 12/07/2023 | 515 | RAMESH AGARWAL | 1210.81 | 0 | 0 | 100
1057 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Gharia Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | 298/SSD | 01/06/2022 | 20 | SUBHANKAR GHOSH | 3.03 | 0 | 0 | 100
1058 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Work order construction of 200 cu.m capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site, laying rising main, laying distribution pipe line with functional household tap connection (FHTC), construction of pump house (5.40 X 3.60m) and pump house (3.60 X 3.00m) without sanitary and plumbing arrangement, iron elemination plant (IEP) with blower room and soil investigation at H/W site for Bara Gharia PWSS, block Matigara, Dist - Darjeeling under Siliguri W/S Division, P.H.E. Dte. | 1731/SWSD | 21/09/2023 | 225 | CAPITAL ENGINEERS | 338.72 | 0 | 0 | 0
1059 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Material Requisition To Resource Division | 1376/SWD | 21/09/2022 | 0 | Resource Division | 6.69 | 0 | 0 | 0
1060 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Material Requisition To Resource Division | 2055/SWSD | 16/12/2022 | 0 | Resource Division | 54.77 | 0 | 0 | 0
1061 | DARJEELING | Siliguri W/S Division | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Material Requisition To Resource Division | 2289/SWSD | 11/12/2023 | 0 | Resource Division | 5 | 0 | 0 | 0
1062 | DARJEELING | Northern Mechanical | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PIPED WATER SUPLY SCHEME, TW No.- I AND II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1656/NMD | 29/09/2023 | 30 | M/S PARITOSH BHOWMICK AND CO. | 11.49 | 0 | 0 | 50
1063 | DARJEELING | Central Drilling | BARA GHARIA PIPED WATER SUPLY SCHEME , SM/11774 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1064 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme , SM/07034 | Retrofitting | Additional laying of 90mm dia pipeline for FHTC Jal swapno programme of Madhya Bansgaon w/s scheme under Siliguri subdivision, PHE. Dte | 2064/SWSD | 11/01/2023 | 30 | NARENDRA KUMAR | 4.42 | 0 | 0 | 100
1065 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Madhya Basngaon (Part-I) Piped water Supply Scheme , SM/07034 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division. Month of september 2024 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-109 | 04/10/2024 | 0 | SONA PETROL PUMP | 0.32 | 0 | 0 | 0
1066 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection Under Jal Jeevan Mission & Jal Swpna Programme for Samar Nagar& Debidanga area of Kalkut Mouza, Uttar Palash and Dakshin Palash area of Palash Mouza and Kalabari Mouza ( Part ) of Kalkut Piped W/S Scheme at , SM/08296 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection under JAl Swapno Programme for Uttar Palash & Dakshin Palash area of Palash mouza of Kalkut Piped Water Supply Scheme at Matigar Block under Siliguri Sub-Division, P.H.E. Dte. | 711/SWSD | 03/08/2021 | 40 | ARUN KUMAR SHRIVASTAVA | 19.62 | 0 | 0 | 100
1067 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth , SM/10766 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009297 SM Code-SM/08931 | 524/NKWSMD | 25/05/2022 | 60 | RAMESH PRADHAN AND CO. | 6.23 | 0 | 0 | 100
1068 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection at PWS scheme for Bhotay Goth , SM/10766 | Retrofitting | Material Requisition To Resource Division | 1264/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.22 | 0 | 0 | 0
1069 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Continuation order for hiring of 1 (one) no. well maintained diesel consumed luxury cab on monthly hired basis preferably MAXI CAB (A/C) with engine capacity less than or equal to 2000 CC for office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte., Vivekananda Bhawan (2nd floor) Hill Cart Road, Siliguri (for Assistant Chief Engineer, Northern Zone (Civil), P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022. | 2269/SWSD | 24/02/2022 | 6 | OM TRAVELS | 0.88 | 0 | 0 | 100
1070 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Material Requisition To Resource Division | 2012/SWSD | 14/12/2022 | 0 | Resource Division | 7.18 | 0 | 0 | 0
1071 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-106 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.99 | 0 | 0 | 0
1072 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.4 | 0 | 0 | 0
1073 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 1328/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.46 | 0 | 0 | 88
1074 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Laying distribution system (Part-A) at Tari habitation for Augmentation of Bairatisal and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. Sl. No. 12. | 870/SWSD | 21/07/2022 | 85 | M/S G.C. CONSTRUCTION & CO. | 92.37 | 0 | 0 | 90
1075 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Soil Investigation of Bairatisal Zone III PWSS for Construction of 600 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | 393/SSD | 20/07/2022 | 20 | SUBIR CH. CHOWDHURY | 1.03 | 0 | 0 | 100
1076 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Material Requisition To Resource Division | 2174/SWSD | 11/02/2022 | 0 | Resource Division | 112.07 | 0 | 0 | 0
1077 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Material Requisition To Resource Division | 1452/SWSD | 29/09/2022 | 0 | Resource Division | 28.55 | 0 | 0 | 0
1078 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. II, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058171, Reference ID : 402932779] | BP/22-23/123 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
1079 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
1080 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. I, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058151, Reference ID : 402932775] | BP/22-23/123 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
1081 | DARJEELING | Northern Mechanical | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - III (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 110/NMD | 03/02/2023 | 30 | B.B. CONCERNED | 23.55 | 0 | 0 | 100
1082 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BAIRATISAL ZONE - III PIPED WATER SUPPLY SCHEME , SM/10097 | Augmentation | Construction of 600 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising mains, distribution system, pump house (3.65 X 2.45) size, IEP, boundary wall and providing Functional Household Tap Connection (FHTC) for augmentation of BAIRATISAL and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. SL. NO. B. | 970/SWSD | 01/08/2022 | 1095 | M/S KAMAK ENGINEERS & CO | 584.1 | 0 | 0 | 90
1083 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission an.d Jal Swapno Programme for Piped Water Supply Scheme for D.B Road Ekta Valley Lowe r Sonada GP II under Kurseong Sub-Division PHED, GTA | BP-2022-23-26 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.46 | 0 | 0 | 0
1084 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Water Supply Scheme for Upper Pachang lower Sonada GP-II under Kurseong Sub-Division P HED, GTA | BP-2022-23-15 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 4.67 | 0 | 0 | 0
1085 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Longview T.E, St. Mary - Ill GP under Kurseong Sub-Divisi on PHED, GTA | BP-2022-23-39 | 06/05/2022 | 0 | SURAJ LAMA | 21.74 | 0 | 0 | 0
1086 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Pankhabari & sorroundingarea St Mary's GP-Ill under Kurseong Sub-Division PHED, GTA. | BP-2022-23-18 | 20/04/2022 | 0 | SURAJ LAMA | 9.17 | 0 | 0 | 0
1087 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
1088 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programe for Piped Water Supply Scheme for Upper Prashanti Gram & Chatakpur Upper Sonada GP under Kurseong Sub-Division PHED, | BP-2022-23-24 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.92 | 0 | 0 | 0
1089 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Wat¿r Supply Scheme for Ringtong godam dhura gorabari margret's hope GP under Kurseong Sub-Division P HED, GTA | BP-2022-23-14 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 5.35 | 0 | 0 | 0
1090 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for upper Sirubari, Ghyabari GP I under Kurseong Sub-Division PHED, GTA | BP-2022-23-123 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 14.53 | 0 | 0 | 0
1091 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. | BP-2022-23-20 | 20/04/2022 | 0 | SURAJ LAMA | 6.21 | 0 | 0 | 0
1092 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Material Requisition To Resource Division | 2563/NKWSMD | 17/02/2023 | 0 | Resource Division | 12.04 | 0 | 0 | 0
1093 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | Engagement of 1no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna , |  | 27/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0 | 0
1094 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (9 Nos.) under GTA. [Volume No-III] , SM/10262 | Retrofitting | computer operator payment | BP-2023-24-192 | 30/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0 | 0
1095 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Material Requisition To Resource Division | 1291/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.35 | 0 | 0 | 0
1096 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Material Requisition To Resource Division | 2372/NKWSMD | 03/02/2023 | 0 | Resource Division | 2.35 | 0 | 0 | 0
1097 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-126 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1098 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-122 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1099 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-123 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1100 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-125 | 28/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1101 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-124 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1102 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | Mini Piped Water Supply Scheme for South Sukna and Choklong under Kurseong Division. Scheme Code - 10788 TSM/010472 | "BP-2024-25-99 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.91 | 0 | 0 | 0
1103 | DARJEELING | Neorakhola W/S & Mtc.Div. | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER BLOCK KURSEONG & MIRIK, DISTRICT OF DARJEELING , SM/10788 | New | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER KURSEONG, MIRIK BLOCK, DISTRICT OF DARJEELING. [TSM NO -10472] 1. Sukna Forest(Sukna Forest South). 2. Choklong Forest. 3. Panighata(panighata 14 number ward, 10 number line). 4. PanthabariForest(Naya Basti 1). 5. Panthabari Forest(Naya Basti 3). | 607/NKWSMD | 26/05/2022 | 1203 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 242.87 | 0 | 0 | 100
1104 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. , SM/10833 | New | Material Requisition To Resource Division | 1882/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
1105 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. , SM/10833 | New | Piped Water Supply Scheme for Jhepi & Gurdung under Jal Jeevan Mission and Jal Swapno Programme. | 818/NKWSMD | 30/06/2022 | 240 | VINAYAK CONSTRUCTION | 303.13 | 0 | 0 | 100
1106 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. , SM/10833 | New | Material Requisition To Resource Division | 2570/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.9 | 0 | 0 | 0
1107 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. , SM/10833 | New | Material Requisition To Resource Division | 1365/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
1108 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate , SM/10239 | School | Creating gravity based Provision Of Drinking water from spring water source for 45 Numbers of school under Darjeeling Pulbazar Block in the district of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte | 753/NKWSMD | 28/02/2022 | 90 | NIMA SHERPA | 143.7 | 0 | 0 | 0
1109 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source to sourceless schools under different Blocks viz Mirik,Kurseong,Darjeeling-Pulbazar,Jorebunglow-Sukhiapokhri & Rangli-Rangliot in the District of Darjeeling Under Neorakhola Wate , SM/10239 | School | Creating gravity based Provision Of Drinking water from spring water source for 34 Numbers of school under Kurseong Sub-Division, Rongli Rangit Block & Sukia Pokhri Jorebungalow Block in the district of Darjeeling, under Neorakhola water Suppply Division, Kalimpong PHE Dte | 745/NKWSMD | 28/02/2022 | 90 | RUPLAL GOLLAY | 85.5 | 0 | 0 | 0
1110 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar , SM/11382 | Retrofitting | Material Requisition To Resource Division | 1911/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.54 | 0 | 0 | 0
1111 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar , SM/11382 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Manebhanjyang Bazar, Panchyat - Sukhia Simana Block - Jorebungalow Sukhia. | 946/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 48.83 | 0 | 0 | 0
1112 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) , SM/10773 | Retrofitting | Material Requisition To Resource Division | 1901/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.86 | 0 | 0 | 0
1113 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) , SM/10773 | Retrofitting | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Upper & Lower Barbotia, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009473 SM Code-SM/08932 | 498/NKWSMD | 24/05/2022 | 60 | PROSENJIT BASAK | 18.21 | 0 | 0 | 100
1114 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting for PWS scheme at Barbotia (Lower and Upper) , SM/10773 | Retrofitting | Material Requisition To Resource Division | 2580/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.86 | 0 | 0 | 0
1115 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creation of gravity based provision of drinking water from spring water source of anganwadi(119 nos) centers under Darjeeling pulbazar block in the district of Darjeeling under Neorakhola water supply & maintenance division, P.H.E. Directorate , SM/10796 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 119 nos of Anganwadi centers under Darjeeling Pulbazar Block in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte TSM No. 009892 | 253/NKWSMD | 06/05/2022 | 180 | NIMA SHERPA | 334.99 | 0 | 0 | 0
1116 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA , SM/10810 | New | SURFACE WATER BASED RONG TONG 12 MILE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 600/NKWSMD | 26/05/2022 | 825 | NARAYAN THAPA | 83.04 | 0 | 0 | 51
1117 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Rong Tong 12 Mile under Kurseong Sub Division ,PHED,GTA , SM/10810 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
1118 | DARJEELING | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. , SM/10815 | New | Material Requisition To Resource Division | 2375/NKWSMD | 03/02/2023 | 0 | Resource Division | 9.18 | 0 | 0 | 0
1119 | DARJEELING | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. , SM/10815 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-296 | 02/11/2023 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
1120 | DARJEELING | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. , SM/10815 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-295 | 02/11/2023 | 0 | WBSEDCL | 6.14 | 0 | 0 | 0
1121 | DARJEELING | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. , SM/10815 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
1122 | DARJEELING | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. , SM/10815 | New | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 0 | 0 | 100
1123 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II , SM/10822 | Retrofitting | Material Requisition To Resource Division | 1269/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0 | 0
1124 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional household tap connection with pipeline retrofitting for PWS scheme at Lingsaybong, Lodhuma-II , SM/10822 | Retrofitting | :Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Linseybong, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009471 SM Code-SM/08926 | 629/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.59 | 0 | 0 | 70
1125 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12179 | New | Material Requisition To Resource Division | 2581/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.75 | 0 | 0 | 0
1126 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12179 | New | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK: JORE BUNGALOW SUKHIAPOKHRI, DISTRICT: DARJEELING UNDER DARJEELING DIVISION, P.H.E-GTA. | 647/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 22.9 | 0 | 0 | 0
1127 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12179 | New | WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING | 1622/NKWSMD | 03/11/2022 | 815 | VINAYAK CONSTRUCTION | 633.65 | 0 | 0 | 100
1128 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis , SM/11322 | Retrofitting | Material Requisition To Resource Division | 1297/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.07 | 0 | 0 | 0
1129 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis , SM/11322 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden (Khundrukey Busty, Lower Chimney, Majuwa Busty, Mohan Majuwa, Titney Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | 794/NKWSMD | 30/06/2022 | 960 | MS JAGANNATH PRASAD | 11.97 | 0 | 0 | 55
1130 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA , SM/11330 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Kalimati Mahanadi GP Block - Kurseong Block | 814/NKWSMD | 30/06/2022 | 60 | SWAD CONSTRUCTION | 12.14 | 0 | 0 | 0
1131 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Kalimati Busty under Kurseong-Sub Division, PHED, GTA , SM/11330 | Retrofitting | Material Requisition To Resource Division | 1304/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0 | 0
1132 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional households Tap connection under JSP Programme for PWS Scheme Soureni Bazar , SM/11306 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme fro Soureni Bazar: Gram Panchyat- Soureni-I, Block -Mirik TSM No. 009309 | 782/NKWSMD | 30/06/2022 | 60 | KAMAL PRADHAN | 22.21 | 0 | 0 | 100
1133 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution networks retrofitting under JSP Programme for PWS Scheme for Chowandhura , SM/11311 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme at Chowandhura Gram Panchyat Soureni-I Block Mirik TSM No. 009303 | 789/NKWSMD | 30/06/2022 | 915 | KAMAL PRADHAN | 11.04 | 0 | 0 | 100
1134 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING , SM/11856 | New | Material Requisition To Resource Division | 762/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.62 | 0 | 0 | 0
1135 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING , SM/11856 | New | ADDITIONAL WORK FOR PULUNGDUNG TEA ESTATE PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING. | 2349/NKWSMD | 19/12/2024 | 90 | SATHI CONSTRUCTION COMPANY | 47.86 | 0 | 0 | 0
1136 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PULUNGDUNG TEA ESTATE PWSS BLOCK- JORE BUNGALOW- SUKHIYAPOKHRI, DISTRICT- DARJEELING , SM/11856 | New | PULUNGDONG TEA ESTATE VILLAGE WATER SUPPLY SCHEME UNDER JOREBUNGLOW SUKHIAPOKHARI BLOCK. | 677/NKWSMD | 12/07/2023 | 180 | SATHI CONSTRUCTION COMPANY | 239.24 | 0 | 0 | 100
1137 | DARJEELING | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Hetmuri Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 287/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 3.54 | 0 | 0 | 100
1138 | DARJEELING | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Material Requisition To Resource Division | 2056/swsd | 16/12/2022 | 0 | Resource Division | 23.32 | 0 | 0 | 0
1139 | DARJEELING | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Construction of 200 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Main construction of 4 nos big dia rig bore tube well by ODEX - 165, Pump House (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plant , Boundary Wall including Functional Household Tap Connection at HETMURI Piped Water Supply Scheme (ZONE I , II & III) under Phansidewa Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | 1212/SWSD | 11/08/2023 | 867 | K.R.ENTERPRISE | 577.26 | 0 | 0 | 10
1140 | DARJEELING | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HETMURI PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II, (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1576/NMD | 08/09/2023 | 30 | ALPHA ENTERPRISE | 31.45 | 0 | 0 | 0
1141 | DARJEELING | Central Drilling | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
1142 | DARJEELING | Siliguri W/S Division | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Material Requisition To Resource Division | 75/SWSD | 10/01/2024 | 0 | Resource Division | 11.05 | 0 | 0 | 0
1143 | DARJEELING | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | New Service Connection Charge for HETMURII, T/W No. I, under PHANSIDEWAI CCC [APPLICATION NO. 4003293269 , Reference ID : 403129587] | BP/23-24/259 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.57 | 0 | 0 | 0
1144 | DARJEELING | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | New service connection at Hetmuri Z-II ,TW-II under NMD, PHE dte. Application No- 4003425299 Ref. Id- 403230924 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.45 | 0 | 0 | 0
1145 | DARJEELING | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | New Service Connection Charge for HETMURII, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO. 4003293284 , Reference ID : 403129595] | BP/23-24/258 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5 | 0 | 0 | 0
1146 | DARJEELING | Northern Mechanical | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | New service connection at Hetmuri Z-II ,TW-I under NMD, PHE dte. Application No- 4003425334 Ref. Id- 403230933 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.63 | 0 | 0 | 0
1147 | DARJEELING | Central Drilling | HETMURI PIPED WATER SUPPLY SCHEME , SM/12750 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1148 | DARJEELING | Neorakhola W/S & Mtc.Div. | Augmentation of source for lower Takbia , SM/11374 | Augmentation | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.09.2024 to 31.10.2024. | 1551/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 0 | 100
1149 | DARJEELING | Neorakhola W/S & Mtc.Div. | Augmentation of source for lower Takbia , SM/11374 | Augmentation | Augmentation of source for lower takbia under Jal Swapno Programme for Goke-1, Block-Bijanbari-Pullbazar TSM No. 009479 | 806/NKWSMD | 30/06/2022 | 60 | SAILESH RAI | 23.93 | 0 | 0 | 65
1150 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11891 | New | Material Requisition To Resource Division | 1890/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.04 | 0 | 0 | 0
1151 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11891 | New | Material Requisition To Resource Division | 2610/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.04 | 0 | 0 | 0
1152 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/11891 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. | 1146/NKWSMD | 29/09/2022 | 665 | GARGO TRADERS | 852.89 | 0 | 0 | 95
1153 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11345 | New | Material Requisition To Resource Division | 1318/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.32 | 0 | 0 | 0
1154 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Forest Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11345 | New | PWS Scheme at Forest Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 956/NKWSMD | 12/07/2022 | 970 | RAMESH THAPA | 23.61 | 0 | 0 | 100
1155 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Material Requisition To Resource Division | 1949/SWSD | 07/12/2022 | 0 | Resource Division | 11.72 | 0 | 0 | 0
1156 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Continuation order for Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte | 1834/SWSD | 25/11/2022 | 182 | SUDIP BASAK | 0.89 | 0 | 0 | 0
1157 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Acceptance cum Work order Construction of boundary wall at head work site allied with Functional Household Tap Connection (FHTC) for Augmentation Trihana Tea Garden Area PWSS under Naxalbari Block under Siliguri Water Supply Division ,P.H.E,Dte.. | 1690/SWSD | 19/09/2023 | 45 | S.K. BANIK | 30.58 | 0 | 0 | 40
1158 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 248/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.5 | 0 | 0 | 100
1159 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | New Service Connection Charge for TRIHANA TEA GARDEN, under NAXALBARI CCC, [APPLICATION NO. 4003079478, Reference ID : 402958535] | BP/22-23/145 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
1160 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | New Service Connection Charge for TRIHANA W/S SCHEME, T/W II, under NAXALBARI CCC, [APPLICATION NO. 4003210228, Reference ID : 403058760] | BP/23-24/142 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.75 | 0 | 0 | 0
1161 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Sinking of 02(Two) Nos. Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at Tube Well Sites for Augmentation of TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2092/SWSD | 22/12/2022 | 25 | SUBHADEEP ENTERPRISE | 16.28 | 0 | 0 | 100
1162 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Construction of 2 Nos. Pump House (5.4 X 3.60) size, boundary wall allied with laying of rising main, distribution system & providing functional household tap connection (FHTC) for Augmentation TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | 1675/SWSD | 10/11/2022 | 75 | S.K. BANIK | 94.26 | 0 | 0 | 80
1163 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Supplementary work for supply & delivery of column pipe & cable for AUGMENTATION OF TRIHANA TEA GARDEN,TW-I in the dist of Darjeeling under Northern Mechanical Division., PHE Dte. | 366/SMSD | 06/12/2023 | 10 | MAA ENTERPRISES | 1.23 | 0 | 0 | 100
1164 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Supply & delivery of Column pipe under JJM project at Trihana Tea Garden PWSS in the dist of Darjeeling under Northern Mechanical Division, PHE Dte. | 421/SMSD | 19/12/2023 | 10 | B.B. CONCERNED | 0.94 | 0 | 0 | 100
1165 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 108/NMD | 03/02/2023 | 30 | MAA ENTERPRISES | 11.55 | 0 | 0 | 80
1166 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 17/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0 | 0
1167 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1168 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
1169 | DARJEELING | Northern Mechanical | AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/12748 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1753/NMD | 31/10/2023 | 460 | SUBODH KUMAR BANIK | 11.07 | 0 | 0 | 100
1170 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Material Requisition To Resource Division | 2049/SWSD | 16/12/2022 | 0 | Resource Division | 30.25 | 0 | 0 | 0
1171 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Fulbari Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | 413/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.85 | 0 | 0 | 0
1172 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Material Requisition To Resource Division | 2294/SWSD | 11/12/2023 | 0 | Resource Division | 0.31 | 0 | 0 | 0
1173 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Supply and Delivery of C.I.D.F special ( 90 degree Bend) for using pumping machinery installation purpose at FULBARI W/S/S under JJM in the dist. of Siliguri under, Northern Mechanical Division ,PHE Dte. | 424/SMSD | 20/12/2023 | 376 | THE BANERJEE CONCERN | 0.44 | 0 | 0 | 100
1174 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 0 | 55
1175 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Material Requisition To Resource Division | 60/SWSD | 09/01/2024 | 0 | Resource Division | 5.67 | 0 | 0 | 0
1176 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003293292 ; Reference ID : 403125589] | BP/23-24/204 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.87 | 0 | 0 | 0
1177 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003293300 ; Reference ID : 403125590] | BP/23-24/205 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.93 | 0 | 0 | 0
1178 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. V, under KHARIBARI CCC, [APPLICATION NO. 4003320539, Reference ID : 403147071] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.01 | 0 | 0 | 0
1179 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. III, under KHARIBARI CCC [APPLICATION NO.4003303307 ; Reference ID : 403132403] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.85 | 0 | 0 | 0
1180 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. VI, under KHARIBARI CCC, [APPLICATION NO. 4003320625, Reference ID : 403147079] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.94 | 0 | 0 | 0
1181 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | New Service Connection Charge for FULBARI, T/W No. IV, under KHARIBARI CCC, [APPLICATION NO. 4003320577, Reference ID : 403147082] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.35 | 0 | 0 | 0
1182 | DARJEELING | Central Drilling | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1183 | DARJEELING | Siliguri W/S Division | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Laying distribution system along with construction of pump house with toilet (2 nos. at each zone), boundary walls ( 2 nos.at each zone ), boring of new tubewells by ODEX-165 ( 2 nos.at each zone) , providing FHTC With platform & other allied works under Jal Jeevan Mission Programme for FULBARI Piped water supply Scheme (zone-I,II & III ) under Kharibari Block ,Darjeeling District , under Siliguri Sub Division ,P.H.E.Dte. | 651/SWSD | 15/06/2023 | 960 | AKASH ENTERPRISE | 341.56 | 0 | 0 | 80
1184 | DARJEELING | Northern Mechanical | FULBARI PIPED WATER SUPPLY SCHEME ( ZONE-I, II& III) , SM/13509 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for FULBARI PIPED WATER SUPPLY SCHEME( ZONE-I) TW No. I, II, (ZONE-II) TW No. I , II and (ZONE-III) TW No. I , II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1659/NMD | 29/09/2023 | 754 | DAS ENTERPRISE | 57.06 | 0 | 0 | 100
1185 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 244/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 0 | 100
1186 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Material Requisition To Resource Division | 2047/SWSD | 16/12/2022 | 0 | Resource Division | 26.07 | 0 | 0 | 0
1187 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 0 | 50
1188 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Infrastructure Cost for BUDHARUGAON T/W No. II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322531, Reference ID : 403149186] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0 | 0
1189 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Infrastructure Cost for BUDHARUGAON T/W No. II, ZONE-III, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322541, Reference ID : 403149161] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5 | 0 | 0 | 0
1190 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Construction of Pump House 2 Nos. (5.4 X 3.6) with toilet (2.1 X 1.2), Rig bore 2 Nos. Big Dia T/W by Odex-165 method, Boundary Walls, Laying distribution system (HDPE pipe), Rising Main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (25 cu.m./hr. for Zone-II & 50 cu.m./hr. for Zone-III), all repair works Zone-I and allied works at Augmentation of BUDHARUGAON PWSS at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 655/SWSD | 15/06/2023 | 1125 | NETWAY SOLUTION | 371.47 | 0 | 0 | 16
1191 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , TW No I (Zone-II) and TW No. I (Zone-III) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1378/NMD | 09/08/2023 | 721 | NIRMAN | 23.67 | 0 | 0 | 30
1192 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0 | 0
1193 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
1194 | DARJEELING | Northern Mechanical | AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , SM/13467 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1195 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | Material Requisition To Resource Division | 2198/SWSD | 04/01/2023 | 0 | Resource Division | 124.88 | 0 | 0 | 0
1196 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | Material Requisition To Resource Division | 2286/SWSD | 11/12/2023 | 0 | Resource Division | 5.18 | 0 | 0 | 0
1197 | DARJEELING | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | New Service Connection Charge for MATIGARAHAT, T/W No.I,ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316052, Reference ID : 403143727] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.19 | 0 | 0 | 0
1198 | DARJEELING | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | New Service Connection Charge for MATIGARAHAT, T/W No. II, ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316072, Reference ID : 403143728] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0 | 0
1199 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | Construction Of 500 -1no & & 600 -1 No & 450 -1 No Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site ( Zn-I, Zn-II & Zn-III) including distribution system (UPVC) with Rising Main,Providing Functional Household Connection (FHTC) , Pump House 4 Nos, ,Boundary Walls , Horizontal boring and allied works for Augmentation of MATIGARAHAT PWSS, Matigara block under Siliguri Sub Division.P.H.E.Dte. | 1082/SWSD | 02/08/2023 | 730 | SRINIWAS AGARWAL | 2266.88 | 0 | 0 | 70
1200 | DARJEELING | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I and (Zone-III) TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1583/NMD | 08/09/2023 | 754 | ANUP BASU | 50.02 | 0 | 0 | 25
1201 | DARJEELING | Northern Mechanical | AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME. , SM/14517 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 34/NMD | 06/01/2025 | 30 | PRATIK ROY | 9.2 | 0 | 0 | 0
1202 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | Material Requisition To Resource Division | 770/NKWSMD | 19/07/2023 | 0 | Resource Division | 10.27 | 0 | 0 | 0
1203 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 675/NKWSMD | 12/07/2023 | 425 | YAMA CONSTRUCTIONS LLP | 2035.87 | 0 | 0 | 75
1204 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | PAYMENT FOR WBSEDCL | BP-2023-24-506 | 17/02/2024 | 0 | WBSEDCL | 10.62 | 0 | 0 | 0
1205 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | payment for WBSEDCL | BP-2023-24-505 | 17/02/2024 | 0 | WBSEDCL | 4.8 | 0 | 0 | 0
1206 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | BP-2024-25-171 | 30/07/2024 | 0 | WBSEDCL | 0.95 | 0 | 0 | 0
1207 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14529 | New | PAYMENT FOR WBSEDCL | BP-2023-24-507 | 17/02/2024 | 0 | WBSEDCL | 0.96 | 0 | 0 | 0
1208 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/14532 | New | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 362/NKWSMD | 29/05/2023 | 365 | YAMA CONSTRUCTIONS LLP | 1365.56 | 0 | 0 | 90
1209 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/14532 | New | Material Requisition To Resource Division | 532/NKWSMD | 13/06/2023 | 0 | Resource Division | 6.53 | 0 | 0 | 0
1210 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/14532 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1211 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/14532 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 408/NKWSMD | 26/03/2025 | 90 | NIM TSHERING LEPCHA | 35.96 | 0 | 0 | 0
1212 | DARJEELING | Neorakhola W/S & Mtc.Div. | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME , SM/16160 | New | Material Requisition To Resource Division | 210/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.21 | 0 | 0 | 0
1213 | DARJEELING | Neorakhola W/S & Mtc.Div. | RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME , SM/16160 | New | WATER SUPPLY SCHEME FOR RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME IN DARJEELING PHULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 121/NKWSMD | 28/04/2023 | 240 | MS. SURYA I PVT. LTD COMPANY | 196.43 | 0 | 0 | 70
1214 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/15884 | New | Material Requisition To Resource Division | 797/NKWSMD | 20/07/2023 | 0 | Resource Division | 3.43 | 0 | 0 | 0
1215 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/15884 | New | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 0 | 70
1216 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR JAMADARBHITA KHASMAHAL(PART-1) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/15884 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR JAMADARBHITTA KHASMAHAL (PART-1 & 2) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 592/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 45.62 | 0 | 0 | 0
1217 | DARJEELING | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. , SM/15873 | New | Material Requisition To Resource Division | 813/NKWSMD | 24/07/2023 | 0 | Resource Division | 6.67 | 0 | 0 | 0
1218 | DARJEELING | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. , SM/15873 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR GOKE UNDER PULL BIJANIARI BLOCK DARJEELING DIVISION, PHED TO ACCOMMODATE FHTC IN PULL BIJANBARI BLOCK | 2331/NKWSMD | 17/12/2024 | 180 | MS. SURYA I PVT. LTD COMPANY | 66.7 | 0 | 0 | 0
1219 | DARJEELING | Neorakhola W/S & Mtc.Div. | GOKE PIPED WATER SUPPLY SCHEME. , SM/15873 | New | WATER SUPPLY SCHEME FOR GOKE-I PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT | 1293/NKWSMD | 17/10/2023 | 365 | VAISHNO CONSTRUCTION | 839.28 | 0 | 0 | 68
1220 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Debiganja Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | 261/SSD | 17/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.48 | 0 | 0 | 0
1221 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Material Requisition To Resource Division | 2232/SWSD | 06/01/2023 | 0 | Resource Division | 23.09 | 0 | 0 | 0
1222 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Material Requisition To Resource Division | 1803/SWSD | 30/09/2023 | 0 | Resource Division | 31.55 | 0 | 0 | 0
1223 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Material Requisition To Resource Division | 80/SWSD | 10/01/2024 | 0 | Resource Division | 13 | 0 | 0 | 0
1224 | DARJEELING | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-II under NMD PHE dte. Application no- 4003456575 Ref ID- 403252077 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
1225 | DARJEELING | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-I under NMD PHE dte. Application no- 4003456573 Ref ID- 403252078 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.08 | 0 | 0 | 0
1226 | DARJEELING | Central Drilling | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1227 | DARJEELING | Siliguri W/S Division | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump House 2 Nos., Blower Room, I.E.P. 50 cu.m./hr, Boundary Walls, Soil Testing and allied works at DEBIGANJA PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. . (3rd Call) | 1411/SWSD | 22/08/2023 | 548 | SANJEEV KUMAR | 430.31 | 0 | 0 | 25
1228 | DARJEELING | Northern Mechanical | DEBIGANJA PIPED WATER SUPPLY SCHEME , SM/15925 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DEBIGANJA PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1662/NMD | 29/09/2023 | 641 | PRATIK ROY | 12.92 | 0 | 0 | 90
1229 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DEBURAM PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15858 | Solarisation | Quotation Charges for Net Metering connection at DEBURAM Piped Water Supply Scheme under PHE Dte. APPLICATION NO - 4003519945 CONSUMER ID- 402256105 | BP/24-25/244 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1230 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DEBURAM PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15858 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1231 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT OMI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15859 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1232 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16534 | New | Preparation of Re-draft of proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 03 (three) number of scheme under JJM (Jal Jeevan Mission). | 1594/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.57 | 0 | 0 | 100
1233 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16534 | New | AUGMENTATION OF LEFT OUT HABITATION OF CART ROAD GHAYABARI-II G.P. UNDER KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 494/NKWSMD | 09/04/2025 | 180 | SHAKTI CONSTRUCTION | 93.45 | 0 | 0 | 0
1234 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR LIZZIEPUR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/16534 | New | WATER SUPPLY SCHEME FOR LIZZIPUR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 1291/NKWSMD | 17/10/2023 | 365 | SHAKTI CONSTRUCTION | 1461.53 | 0 | 0 | 100
1235 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District , SM/16535 | New | Material Requisition To Resource Division | 154/NKWSMD | 03/05/2023 | 0 | Resource Division | 6.37 | 0 | 0 | 0
1236 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District , SM/16535 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1237 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme for Mahanadi tea Garden in Kurseong block under Darjeeling District , SM/16535 | New | WATER SUPPLY SCHEME FOR MAHANADI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 92/NKWSMD | 27/04/2023 | 605 | VINAYAK CONSTRUCTION | 1041.6 | 0 | 0 | 100
1238 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA BANSGAON PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15629 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1239 | DARJEELING | Neorakhola W/S & Mtc.Div. | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. , SM/16238 | New | Material Requisition To Resource Division | 776/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.26 | 0 | 0 | 0
1240 | DARJEELING | Neorakhola W/S & Mtc.Div. | KARMAT BUSTY PIPED WATER SUPPLY SCHEME. , SM/16238 | New | WATER SUPPLY SCHEME FOR KARMAT BUSTY PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 712/NKWSMD | 17/07/2023 | 300 | SRINIWAS AGARWAL | 128.73 | 0 | 0 | 100
1241 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT , SM/16627 | New | Material Requisition To Resource Division | 278/NKWSMD | 17/05/2023 | 0 | Resource Division | 4.55 | 0 | 0 | 0
1242 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR SOURINI BASTY PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT , SM/16627 | New | ADDITIONAL WORK FOR SAURINI BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-MIRIK DISTRICT-DARJEELING, KURSEONG DIVISION PHE-GTA. | 594/NKWSMD | 29/04/2025 | 90 | ALLIED INSTRUMENTS | 22.62 | 0 | 0 | 0
1243 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DANGARVITA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15627 | Solarisation | Quotation Charges for Net Metering connection at DANGARBHITA Piped Water Supply Scheme under PHE Dte. APPLICATION NO - 4003519940 CONSUMER ID- 402256106 | BP/24-25/244 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1244 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT DANGARVITA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15627 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1245 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15631 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1246 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Budharugaon village of Budharugaon Piped water Supply Scheme , SM/07041 | Retrofitting | Providing Functional Household Tap Connection under Jal Swapna Programme for Budharugaon of BUDHARUGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub-Division PHE Dte PART A | 691/SWSD | 02/08/2021 | 50 | SUDIP BASAK | 41.87 | 0 | 0 | 100
1247 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHANADI FOREST PIPED WATER SUPPLY SCHEME , SM/15648 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1248 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHANADI FOREST PIPED WATER SUPPLY SCHEME , SM/15648 | New | Piped Water Supply Scheme for Mahanadi Forest under Kurseong Division. Scheme Code - 15648 TSM/017745 | BP-2024-25-95 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 15.27 | 0 | 0 | 0
1249 | DARJEELING | Neorakhola W/S & Mtc.Div. | MAHANADI FOREST PIPED WATER SUPPLY SCHEME , SM/15648 | New | PIPED WATER SUPPLY SCHEME FOR MAHANADI FOREST TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | 439/NKWSMD | 07/06/2023 | 830 | RUKMANI ENGINEERING WORKS | 157.77 | 0 | 0 | 100
1250 | DARJEELING | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15655 | New | Material Requisition To Resource Division | 205/NKWSMD | 10/05/2023 | 0 | Resource Division | 4.29 | 0 | 0 | 0
1251 | DARJEELING | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15655 | New | PAYMENT FOR WBSEDCL | BP-2024-25-56 | 07/06/2024 | 0 | WBSEDCL | 51.83 | 0 | 0 | 0
1252 | DARJEELING | Neorakhola W/S & Mtc.Div. | PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15655 | New | SURFACE WATER BASED PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION IN MIRIK BLOCK. | 116/NKWSMD | 28/04/2023 | 1193 | SRINIWAS AGARWAL | 677.35 | 0 | 0 | 90
1253 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Barapathuram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 407/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.99 | 0 | 0 | 100
1254 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART ROAD, SILIGURI FOR THE PERIOD FROM 01.03.2023 TO 31.07.2023 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.) i.e. 5 (FIVE) MONTHS. | 2645/SWSD | 01/03/2023 | 153 | PINKI DAM | 0.74 | 0 | 0 | 40
1255 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Material Requisition To Resource Division | 2200/SWSD | 04/01/2023 | 0 | Resource Division | 85.16 | 0 | 0 | 0
1256 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 0 | 55
1257 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Material Requisition To Resource Division | 59/SWSD | 09/01/2024 | 0 | Resource Division | 22.92 | 0 | 0 | 0
1258 | DARJEELING | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-II under PHASIDAWA CCC [APPLICATION NO. 4003340843 ; Reference ID : 403163867] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.55 | 0 | 0 | 0
1259 | DARJEELING | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | New Service Connection Charge for BARA PATHURAM, T/W No. I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321578, Reference ID : 403148659] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0 | 0
1260 | DARJEELING | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-I under PHASIDAWA CCC [APPLICATION NO. 4003340866 , Reference ID : 403163866] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0 | 0
1261 | DARJEELING | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | New Service Connection Charge for BARA PATHURAM, T/W No. II, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321619, Reference ID : 403148640] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0 | 0
1262 | DARJEELING | Central Drilling | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1263 | DARJEELING | Siliguri W/S Division | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Construction of 250 cu.m. (1 No.) & 150 Cum (2Nos) capacity R.C.C Elevated Reservoir , 20 Mtrs. Stagging Height at the head work site ( Zn-l,Zn-ll & Zn-lll) including distribution system (HDPE) with Rising Main , Rig bore 6 nos big dia T/W by ODEX-165method, Providing Functional Household Connection (FHTC) , Construction of 6 nos. Pump Houses, 3 Nos. Blower Rooms, Boundary walls, Installation of I.E. Plants (Capacity 30,50 & 30 cu.m./hr), Horizontal boring, Soil Testing and allied works at BARA PATHURAM Piped WS Scheme within Phansidewa block, under Siliguri Sub Division, P.H.E. Dte. | 1131/SWSD | 07/08/2023 | 807 | UNIBRO INFRASERV PRIVATE LIMITED | 1076.34 | 0 | 0 | 30
1264 | DARJEELING | Northern Mechanical | BARA PATHURAM PIPED WATER SUPPLY SCHEME ( ZONE-I , II & III ) , SM/18321 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA PATHURAM PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I, II, (ZONE-II) TW No. I, II and (ZONE-III) TW No. I, II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1655/NMD | 29/09/2023 | 712 | ALPHA ENTERPRISE | 45.3 | 0 | 0 | 24
1265 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Providing Functional Household Tap Connection unde.r Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Makaibari Tea Estate under Kurseong Sub-DIvision PHED, GTA | BP-2022-23-21 | 20/04/2022 | 0 | NIPENDRA TAMANG | 10.07 | 0 | 0 | 0
1266 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Selim Hill T .E.under Kurseong Division PHED), GTA | BP-2022-23-13 | 11/04/2022 | 0 | SWAD CONSTRUCTION | 7.27 | 0 | 0 | 0
1267 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sittong-1 & Sittong-111 under Kurseong Sub-Division PHED, GTA. | BP-2022-23-25 | 20/04/2022 | 0 | BIKRAM RAI | 21.12 | 0 | 0 | 0
1268 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
1269 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Schem e for Dudhia Bazaar & its sorrounding area under Kurseong Sub-Division PHED, G1A | BP-2022-23-37 | 20/04/2022 | 0 | SUN SHINE GROUP | 19.39 | 0 | 0 | 0
1270 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] , SM/10264 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.73 | 0 | 0 | 0
1271 | DARJEELING | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS , SM/18722 | New | Material Requisition To Resource Division | 963/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.35 | 0 | 0 | 0
1272 | DARJEELING | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS , SM/18722 | New | ADDITIONAL WORK FOR SAMALBONG PIPED WATER SUPPLY SCHEME UNDER BLOCK-PULBAZAR DISTRICT-DARJEELING. | 596/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 98.47 | 0 | 0 | 0
1273 | DARJEELING | Neorakhola W/S & Mtc.Div. | SAMALBONG PWSS , SM/18722 | New | WATER SUPPLY SCHEME FOR SAMALBONG PIPED WATER SUPPLY SCHEME DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 937/NKWSMD | 16/08/2023 | 605 | GARGO TRADERS | 1200.76 | 0 | 0 | 80
1274 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS , SM/11854 | New | Material Requisition To Resource Division | 1889/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.41 | 0 | 0 | 0
1275 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS , SM/11854 | New | Material Requisition To Resource Division | 2572/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.41 | 0 | 0 | 0
1276 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MOLATEY AND AVONGROVE TEA GARDEN PWSS , SM/11854 | New | WATER SUPPLY SCHEME FOR MOLATEY AND AVONGRAVE TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI UNDER DARJEELING DISTRICT | 1452/NKWSMD | 29/09/2022 | 850 | SHAKTI CONSTRUCTION | 926.69 | 0 | 0 | 99
1277 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE , SM/18588 | New | Material Requisition To Resource Division | 970/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0 | 0
1278 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE , SM/18588 | New | PAYMENT FOR WBSEDCL | BP-2023-24-657 | 23/03/2024 | 0 | WBSEDCL | 11.34 | 0 | 0 | 0
1279 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE , SM/18588 | New | SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST & ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | 913/NKWSMD | 11/08/2023 | 545 | INTERIOR'S NEST | 2568.72 | 0 | 0 | 75
1280 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE , SM/18588 | New | ADDITIONAL WORK FOR SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST AND ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | 829/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 93.84 | 0 | 0 | 0
1281 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE , SM/18588 | New | Balance work for Surface water based Purba & Paschim Phuguri Tea Garden Phuguri Forest and its Surrounding under Kurseong Division, P.H.E-GTA. | 874/NKWSMD | 16/06/2025 | 365 | INTERIOR'S NEST | 312.15 | 0 | 0 | 0
1282 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18601 | New | WATER SUPPLY SCHEME FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 879/NKWSMD | 03/08/2023 | 365 | YAMA CONSTRUCTIONS LLP | 2563.35 | 0 | 0 | 50
1283 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18601 | New | Material Requisition To Resource Division | 174/NKWSMD | 08/02/2024 | 0 | Resource Division | 12.22 | 0 | 0 | 0
1284 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME ACHHALAL HATTA PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18601 | New | ADDITIONAL WORK FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT DARJEELING. | 2203/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 114.92 | 0 | 0 | 80
1285 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden , SM/18640 | New | Material Requisition To Resource Division | 959/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.46 | 0 | 0 | 0
1286 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden , SM/18640 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1287 | DARJEELING | Northern Mechanical | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MEHERULLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1580/NMD | 08/09/2023 | 30 | B.B. CONCERNED | 34.74 | 0 | 0 | 70
1288 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Meherulla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 403/SSD | 27/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
1289 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Material Requisition To Resource Division | 1806/SWSD | 30/09/2023 | 0 | Resource Division | 77.11 | 0 | 0 | 0
1290 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 0 | 55
1291 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Material Requisition To Resource Division | 82/SWSD | 10/01/2024 | 0 | Resource Division | 10.77 | 0 | 0 | 0
1292 | DARJEELING | Central Drilling | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1293 | DARJEELING | Siliguri W/S Division | MEHERULLA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/18614 | New | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (4 nos.), IEP, Bounary wall, tubewell and soil investigation under Jal Jeevan Mission at MEHERULLA Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 545/SWSD | 01/03/2024 | 390 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 626.06 | 0 | 0 | 25
1294 | DARJEELING | Neorakhola W/S & Mtc.Div. | DAWAIPANI & TUKDAH TEA GARDEN PWSS , SM/18752 | New | Material Requisition To Resource Division | 999/NKWSMD | 24/08/2023 | 0 | Resource Division | 8.16 | 0 | 0 | 0
1295 | DARJEELING | Neorakhola W/S & Mtc.Div. | DAWAIPANI & TUKDAH TEA GARDEN PWSS , SM/18752 | New | ADDITIONAL WORK FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 650/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 130.55 | 0 | 0 | 0
1296 | DARJEELING | Neorakhola W/S & Mtc.Div. | DAWAIPANI & TUKDAH TEA GARDEN PWSS , SM/18752 | New | WATER SUPPLY SCHEME FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 988/NKWSMD | 23/08/2023 | 815 | VINAYAK CONSTRUCTION | 992.81 | 0 | 0 | 100
1297 | DARJEELING | Neorakhola W/S & Mtc.Div. | Augmentation of Nipania Piped Water Supply Scheme. , SM/18881 | Augmentation | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 0 | 30
1298 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) , SM/07047 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Uttar Ramdhan habitation Projote of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | 1013/SWSD | 11/12/2020 | 35 | NARENDRA KUMAR | 32.96 | 0 | 0 | 0
1299 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) , SM/07047 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Antaram village habitation Vulka Bajarur Chhat village habitation Bazarir chat Bhulka and Gandagal village habitation Barodil Saram and Chhoto Dil saran of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | 1009/SWSD | 11/12/2020 | 30 | M/S DEBRAJ ENTERPRISE | 24.49 | 5.42 | 55.93 | 100
1300 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) , SM/07047 | Retrofitting | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 0 | 100
1301 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Gandagal, Bajarur Chat, Antaram and Bhulka Village of Uttar Ramdhan & adjoining mouza Piped water Supply Scheme (Part-A) , SM/07047 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | 1011/SWSD | 11/12/2020 | 40 | M/S DEBRAJ ENTERPRISE | 37.92 | 22 | 32.21 | 100
1302 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ranidanga & Shaibhita village of Ranidanga-Rangapani Piped water Supply Scheme , SM/07036 | Retrofitting | FURTHER CONTINUATION HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2023 TO 31.08.2023 (FOR EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. 06 (Six) months. | 2576-31(A)/SWSD | 23/02/2023 | 181 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 0 | 100
1303 | DARJEELING | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D , SM/09204 | Augmentation | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | 386/SSD | 20/07/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 0 | 100
1304 | DARJEELING | Siliguri W/S Division | Rejuvenation and retrofitting for Providing Functional House Hold Tap Connection ( FHTC ) in connection with Jal Jeevan Mission & Jal Swapno Programme under command area of Kharibari piped w/s scheme at Kharibari Block under Siliguri W/S Division, P.H.E D , SM/09204 | Augmentation | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | 2931/SWSD | 30/10/2024 | 45 | ARUN KUMAR SHRIVASTAVA | 49.08 | 0 | 0 | 0
1305 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village , SM/10764 | Retrofitting | Material Requisition To Resource Division | 1263/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1306 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retroffting for Piped water supply scheme at Ramam Forest Village , SM/10764 | Retrofitting | Providing Functional household tap connection under JJM & JSP Programme for PWS Scheme Raman Forest Village Source mahabir Jhora Gram Panchyat -Srikhola, Block Darjeeling - Pullbazaar. TSM No. 009295 SM Code-SM/08925 | 492/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 20.35 | 0 | 0 | 100
1307 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta , SM/10768 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Gorkata Gram Panchyat -Goke-II , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009301 SM Code-SM/08933 | 494/NKWSMD | 24/05/2022 | 60 | MS D.R ENTERPRISES | 24.24 | 0 | 0 | 100
1308 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with distribution pipeline retrofitting at PWS scheme for Gorukatta , SM/10768 | Retrofitting | Material Requisition To Resource Division | 1259/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.78 | 0 | 0 | 0
1309 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan , SM/10769 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Lamagoan, Gram Panchyat -Kaijiliya, Block Bijanbari -PullBazar. TSM No. 009097 SM Code-SM/04601 | 525/NKWSMD | 25/05/2022 | 60 | M/S DIVYA ENTERPRISES | 18.55 | 0 | 0 | 0
1310 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting for Piped water supply scheme at Upper Lamagoan , SM/10769 | Retrofitting | Material Requisition To Resource Division | 1272/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.47 | 0 | 0 | 0
1311 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village , SM/10770 | Retrofitting | Material Requisition To Resource Division | 1262/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.24 | 0 | 0 | 0
1312 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with pipeline retrofitting for PWS at Gorkhey Forest Village , SM/10770 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Gorkhey Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009469 SM Code-SM/08929 | 495/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 16.74 | 0 | 0 | 100
1313 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Kankeybong GP Lodhoma under Darjeellng Division PHED GTA" | BP-2022-23-34 | 20/04/2022 | 0 | SACHIN PRADHAN | 13.66 | 0 | 0 | 0
1314 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household d Tap Connection under JJM & JSP Programme for PWS Scheme for Lungtham Happy Valley under Darjeeling Division PHED GTA" | BP-2022-23-35 | 20/04/2022 | 0 | SAMDEN DUKPA | 6.07 | 0 | 0 | 0
1315 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Gairigoan Fatingtar GP Lodhoma II under Darjeeling Division PHED GTA | BP-2022-23-23 | 20/04/2022 | 0 | BIRAJ RAI | 6.44 | 0 | 0 | 0
1316 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connecti on under JJM & JSP Pro gramme for PWS Scheme for Bijanbari Bazar GP Pull Bijnabari under Darjeeling Division PHED GTA" | BP-2022-23-52 | 20/05/2022 | 0 | AROGYA ENTERPRISES | 24.75 | 0 | 0 | 0
1317 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Providing Functional Household Tap Connection und er JJM & JSP Programme for PWS Schem e for Lama goan GP Jhepi Kaijiliya under Darjeeling Division PHED GTA | BP-2022-23-16 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 9.27 | 0 | 0 | 0
1318 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Tukvar TG GP Tukvar under Darjeeling Division PHED GTA" | BP-2022-23-51 | 20/05/2022 | 0 | VINAYAK CONSTRUCTION | 47.99 | 0 | 0 | 0
1319 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Relling Bhibaray & Lr Relling GP Relling under Darjeeling Division PHED GTA" | BP-2022-23-17 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 8.03 | 0 | 0 | 0
1320 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Singhbhumdera GP Mazua under Darjeeling Division PHED GTA" | BP-2022-23-22 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 13.75 | 0 | 0 | 0
1321 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Providing Functional Household Tap ·connection under JJM & JSP Programme for PWS Scheme for Samsu (Lower) Relling GP under Darjeeling Division PHED GTA | BP-2022-23-27 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 4.03 | 0 | 0 | 0
1322 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" | BP-2022-23-33 | 20/04/2022 | 0 | PASSANG TAMANG | 3.13 | 0 | 0 | 0
1323 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
1324 | DARJEELING | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional .Household Tap Connection under JJM & JSP Programme for PWS Scheme for Takbia (Lower ) GP Goke 1 under Darjeeling Division PHED GTA" | BP-2022-23-36 | 20/04/2022 | 0 | SAILESH RAI | 7.3 | 0 | 0 | 0
1325 | DARJEELING | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0 | 0
1326 | DARJEELING | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0 | 0
1327 | DARJEELING | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. , SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" | 110/EE/DD/PHED | 10/02/2021 | 120 | PASSANG TAMANG | 5.58 | 0 | 0 | 0
1328 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. , SM/10790 | New | Material Requisition To Resource Division | 2370/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.81 | 0 | 0 | 0
1329 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped water supply Scheme for Pairikumari under Kurseong Block in the District of Darjeeling. , SM/10790 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-130 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1330 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. , SM/10836 | New | Material Requisition To Resource Division | 1881/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
1331 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. , SM/10836 | New | Material Requisition To Resource Division | 2569/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0 | 0
1332 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. , SM/10836 | New | PIPED WATER SUPPLY SCHEME FOR DARAGOAN LEKHARGA UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 613/NKWSMD | 26/05/2022 | 60 | SUNIL SHARMA | 58.05 | 0 | 0 | 100
1333 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. , SM/10836 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR DARAGOAN UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PULL BIJANBARI BLOCK | 967/NKWSMD | 03/07/2025 | 60 | SUNIL SHARMA | 6.93 | 0 | 0 | 0
1334 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal jeewan Mission/Jal swapno Mission for balance household at Fatingtar , SM/11384 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Fatinagar Gram, G.P. - Lodhama-I, Block - Bijanbari Pulbazar. | 849/NKWSMD | 27/07/2023 | 60 | BIJAY CHETTRI | 25.37 | 0 | 0 | 100
1335 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar , SM/11392 | Retrofitting | Material Requisition To Resource Division | 1910/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.85 | 0 | 0 | 0
1336 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar , SM/11392 | Retrofitting | Material Requisition To Resource Division | 2618/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.85 | 0 | 0 | 0
1337 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar , SM/11392 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Takdah Bazar GP - Takdah Block - Rungli Rungliot. | 950/NKWSMD | 12/07/2022 | 253 | NAVRATNA CONSTRUCTION CO | 150.61 | 0 | 0 | 100
1338 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/11395 | New | Material Requisition To Resource Division | 328/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.74 | 0 | 0 | 0
1339 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Upper Mamring Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/11395 | New | Surface water based Upper Mamring Khasmahal in Kurseong Block within Darjeeling District. | 186/NKWSMD | 04/05/2023 | 870 | PREM CHANDRA RAI | 267.92 | 0 | 0 | 85
1340 | DARJEELING | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme , SM/12269 | New | Material Requisition To Resource Division | 1885/NKWSMD | 15/12/2022 | 0 | Resource Division | 16.58 | 0 | 0 | 0
1341 | DARJEELING | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme , SM/12269 | New | Material Requisition To Resource Division | 2604/NKWSMD | 17/02/2023 | 0 | Resource Division | 16.58 | 0 | 0 | 0
1342 | DARJEELING | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme , SM/12269 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2023 TO 31.12.2023 | 1023/NKWSMD | 31/08/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 0 | 100
1343 | DARJEELING | Neorakhola W/S & Mtc.Div. | Choongtoong & Lizahill Tea Garden water supply scheme , SM/12269 | New | CHOONGTOONG & LIZAHILL TEA GARDEN WATER SUPPLY SCHEME UNDER DARJEELING DIVISION I, PHED, GTA | 1447/NKWSMD | 29/09/2022 | 300 | SUDESH RAYA MAJHI | 1203.75 | 0 | 0 | 80
1344 | DARJEELING | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dakhshin Bagdogra Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 278/SSD | 25/05/2022 | 20 | SUBHANKAR GHOSH | 3.09 | 0 | 0 | 100
1345 | DARJEELING | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Material Requisition To Resource Division | 1462/SWSD | 29/09/2022 | 0 | Resource Division | 7.47 | 0 | 0 | 0
1346 | DARJEELING | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Material Requisition To Resource Division | 2054/SWSD | 16/12/2022 | 0 | Resource Division | 65.62 | 0 | 0 | 0
1347 | DARJEELING | Northern Mechanical | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Quotation for new service connection at T.W No-I of DAKSHIN BAGDOGRA PWSS in the dist. Darjeeling | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.06 | 0 | 0 | 0
1348 | DARJEELING | Central Drilling | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1349 | DARJEELING | Siliguri W/S Division | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Construction of 200 cu.m. Capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of pump house (5.40 X 3.6 m) and pump house (3.60 X 3.00 m) with sanitary and plumbing arrangement, iron elimination plant (IEP) with blower room and soil investingation at head work site for DAKSHIN BAGDOGRA PWSS, Block Naxalbari Dist. Darjeeling under Siliguri W/S Division, PHE Dte | 1200/SWSD | 10/08/2023 | 966 | NETWAY SOLUTION | 332.54 | 0 | 0 | 30
1350 | DARJEELING | Northern Mechanical | DAKSHIN BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/11773 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at DAKSHIN BAGDOGRA PWSS for T/W No. II in the district of Darjeeling under Northern Mechanical Division, P.H.E. Dte. | 583/NMD | 07/02/2025 | 30 | SAIKAT SINHA | 12.1 | 0 | 0 | 0
1351 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA , SM/10804 | New | Material Requisition To Resource Division | 2567/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.94 | 0 | 0 | 0
1352 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Ratna Dyang under Kurseong Sub Division ,PHED,GTA , SM/10804 | New | SURFACE WATER BASED RATNA DYANG PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA, DISTRICT DARJEELING. | 1988/NKWSMD | 23/12/2022 | 180 | KUMAR CHHETRI | 75.55 | 0 | 0 | 100
1353 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA , SM/10809 | New | Material Requisition To Resource Division | 2602/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.89 | 0 | 0 | 0
1354 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA , SM/10809 | New | SURFACE WATER BASED JOGMAYA TEA ESTATE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | 2083/NKWSMD | 10/01/2023 | 180 | MS CHAMLING CONSTRUCTION | 66.72 | 0 | 0 | 80
1355 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singbuli factory gaon , SM/10831 | New | Material Requisition To Resource Division | 1322/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.3 | 0 | 0 | 0
1356 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singbuli factory gaon , SM/10831 | New | PIPED WATER SUPPLY SCHEME FOR SINGBULLI FACTORY GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | 611/NKWSMD | 26/05/2022 | 60 | M/S JAI BHAWANI CONSTRUCTION CO | 63.19 | 0 | 0 | 97
1357 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling , SM/10819 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-128 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1358 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling , SM/10819 | New | Quotation of wbsedcl for electrical service connection | BP-2023-24-127 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1359 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling , SM/10819 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-290 | 02/11/2023 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1360 | DARJEELING | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling , SM/10819 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 0 | 100
1361 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/12178 | New | Material Requisition To Resource Division | 1887/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.74 | 0 | 0 | 0
1362 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/12178 | New | Material Requisition To Resource Division | 2606/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.74 | 0 | 0 | 0
1363 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TUMSUNG KHASMAHAL PWSS BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/12178 | New | Proposed Gravity Based Water Supply Scheme for Tumsung Khasmahal PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. | 1494/NKWSMD | 14/10/2022 | 1000 | ALLIED INSTRUMENTS | 587.51 | 0 | 0 | 100
1364 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. , SM/11324 | Retrofitting | Material Requisition To Resource Division | 1299/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.61 | 0 | 0 | 0
1365 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. , SM/11324 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | 796/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 27.69 | 0 | 0 | 100
1366 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail , SM/11305 | Retrofitting | Continuation Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. | 1141/NKWSMD | 29/09/2023 | 182 | S S CONSTRUCTIONS | 0.99 | 0 | 0 | 100
1367 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail , SM/11305 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation for work for PWS Scheme for Dara Goan, Khoprail: Gram Panchyat -Soureni-II, Block Mirik TSM No. 009308 | 783/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 12.59 | 0 | 0 | 100
1368 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Bada kothi , SM/11310 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for bada Kothi: Gram Panchyat Soureni- II, Block - Mirik TSM No. 009482 SM Code-SM/08949 | 781/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 3.78 | 0 | 0 | 100
1369 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11331 | Retrofitting | Material Requisition To Resource Division | 1305/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.91 | 0 | 0 | 0
1370 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11331 | Retrofitting | Providing Functional household Tap Connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Ghoomti T.E. Mahanadi GP Block Kurseong | 811/NKWSMD | 30/06/2022 | 60 | MS CHAMLING CONSTRUCTION | 26.4 | 0 | 0 | 100
1371 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA , SM/11333 | Retrofitting | Material Requisition To Resource Division | 1307/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.68 | 0 | 0 | 0
1372 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sivitar under Kurseong-Sub Division, PHED, GTA , SM/11333 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Sivitar T.E. Mahanadi GP Block - Kurseong Block | 798/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 24.02 | 0 | 0 | 100
1373 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singtam Tea Garden , SM/11338 | New | Material Requisition To Resource Division | 767/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.82 | 0 | 0 | 0
1374 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED , SM/19038 | New | SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E. DTE. | 3/NKWSMD | 03/01/2024 | 455 | YAMA CONSTRUCTIONS LLP | 5612.47 | 0 | 0 | 95
1375 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED , SM/19038 | New | ADDITIONAL WORK FOR SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION P.H.E DTE. | 2347/NKWSMD | 19/12/2024 | 365 | YAMA CONSTRUCTIONS LLP | 1156.69 | 0 | 0 | 75
1376 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme , SM/07218 | Retrofitting | Providing functional house hold tap connection (FHTC) in connection with jal Jeevan Mission ( JJM and Jal Swapna Programme ) for Bairagi Village of Bairagi piped water supply scheme at Kharibari | 1275/SWSD | 14/08/2020 | 1826 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 32.19 | 29.04 | 90.19 | 0
1377 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme , SM/07218 | Retrofitting | Providing functional house hold tap connection under Jal Swapno programme for Bairagi village of Duba & Gayen village of Bairagi piped water supply scheme at Khoribari block under Siliguri Sub Division, PHE Dte. SL. No. 04. | 1826/SWSD | 13/01/2022 | 45 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 35.33 | 0 | 0 | 100
1378 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bairagi Piped water Supply Scheme , SM/07218 | Retrofitting | Material Requisition To Resource Division | 1668/SWSD | 28/12/2021 | 0 | Resource Division | 2.68 | 0 | 0 | 0
1379 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Material Requisition To Resource Division | 2059/SWSD | 16/12/2022 | 0 | Resource Division | 23.85 | 0 | 0 | 0
1380 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 241/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.76 | 0 | 0 | 100
1381 | DARJEELING | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , TW No I (Zone-I) and TW No. I (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1650/NMD | 29/09/2023 | 30 | SUBHRANGSHU GUHARAJA | 11.58 | 0 | 0 | 50
1382 | DARJEELING | Central Drilling | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
1383 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Repairing Of Damaged House Connection Under Lalman Water Supply Scheme Under Siliguri Sub Division, Phe Dte. | 1948/SWSD | 16/10/2023 | 10 | SEBU CHAKRABORTY | 1.62 | 0 | 0 | 100
1384 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 0 | 50
1385 | DARJEELING | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT LALMON T.W NO:- IV UNDER NMD, PHE DTE. | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.53 | 0 | 0 | 0
1386 | DARJEELING | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | New Service Connection Charge for LALMAN (AUG), T/W-I, under BAGDOGRA CCC, [APPLICATION NO. 4003347057, Reference ID : 403169281] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.29 | 0 | 0 | 0
1387 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Laying of pipeline for distribution system, rising main, construction of Pump House, Installation of I.E. Plant with blower room construction of boundary wall for Zone-I & Zone-II for Augmentation of LALMAN W/S Scheme under Siliguri W/S Division, P.H.E. Dte. | 649/SWSD | 15/06/2023 | 240 | S.G.CONSTRUCTION. | 453.84 | 0 | 0 | 65
1388 | DARJEELING | Central Drilling | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1389 | DARJEELING | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1390 | DARJEELING | Northern Mechanical | AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , SM/12807 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0 | 0
1391 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | Material Requisition To Resource Division | 2030/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0 | 0
1392 | DARJEELING | Northern Mechanical | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1477/NMD | 17/08/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 12.44 | 0 | 0 | 0
1393 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | Material Requisition To Resource Division | 2234/SWSD | 06/01/2023 | 0 | Resource Division | 0.98 | 0 | 0 | 0
1394 | DARJEELING | Siliguri W/S Division | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | Acceptance cum work order for Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia Deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and Supplying, Fabrication, Erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (20 cu.m./hour) required platform and drain etc. for Rejuvenation of Dangarvita Piped Water Supply Scheme at Kharibari block under under Siliguri Sub Division.P.H.E.Dte.in the dist. of Darjeeling. | 3025/SWSD | 13/11/2024 | 90 | BUDDHADEV NAG | 66.21 | 0 | 0 | 0
1395 | DARJEELING | Central Drilling | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
1396 | DARJEELING | Northern Mechanical | REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , SM/12035 | Augmentation | New Service Connection Charge for DANGARVITA, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003321689, Reference ID : 403147924] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.46 | 0 | 0 | 0
1397 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11346 | New | Material Requisition To Resource Division | 2063/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
1398 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Milan Dhura Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11346 | New | PWS Scheme at Milan Dhura, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 958/NKWSMD | 12/07/2022 | 970 | NABIN RAI | 20.04 | 0 | 0 | 100
1399 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11349 | New | Piped Water Supply Scheme at Chimney Simanatar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED-GTA, Darjeeling. | 986/NKWSMD | 23/08/2023 | 60 | PHURBA RUMBA | 77.11 | 0 | 0 | 0
1400 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Chimney Simanatar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11349 | New | Material Requisition To Resource Division | 1000/NKWSMD | 24/08/2023 | 0 | Resource Division | 1.08 | 0 | 0 | 0
1401 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/11952 | New | Material Requisition To Resource Division | 1893/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.72 | 0 | 0 | 0
1402 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/11952 | New | Material Requisition To Resource Division | 2573/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.72 | 0 | 0 | 0
1403 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS, BLOCK- JORE BUNGLOW, SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/11952 | New | WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. | 1620/NKWSMD | 03/11/2022 | 545 | GARGO TRADERS | 874.98 | 0 | 0 | 90
1404 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -I, under Jorebunglow-Sukhiapokhri Block (Part-I ) in the District of Darjeeling Under Neorakhola Water Supply & Mnt.Division, P.H.E. Directorate, Kalimpong. | 973/NKWSMD | 12/07/2022 | 30 | KAMAKHYA ENTERPRISES | 4.84 | 0 | 0 | 0
1405 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Plungdung Gram Panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, under Neorakhola Water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 972/NKWSMD | 12/07/2022 | 30 | KAMAKHYA ENTERPRISES | 4.12 | 0 | 0 | 0
1406 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -II, under Jorebunglow-Sukhiapokhri Block (Part-II) in the District of Darjeeling Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 974/NKWSMD | 12/07/2022 | 30 | MS EKTA CONSTRUCTION AND CO | 3.19 | 0 | 0 | 0
1407 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision of Drinking water from spring water source for Paragari Tumsong Gram Panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 975/NKWSMD | 12/07/2022 | 30 | MS EKTA CONSTRUCTION AND CO | 2.53 | 0 | 0 | 0
1408 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -III, under Jorebunglow-Sukhiapokhri Block (Part-3) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 976/NKWSMD | 12/07/2022 | 30 | MS EKTA CONSTRUCTION AND CO | 4.79 | 0 | 0 | 0
1409 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong , SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -III, under Jorebunglow-Sukhiapokhri Block (Part-3) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | 977/NKWSMD | 12/07/2022 | 30 | NAVRATNA CONSTRUCTION CO | 4.12 | 0 | 0 | 0
1410 | DARJEELING | Siliguri W/S Division | Khoklong Piped Water Supply Scheme , SM/13437 | New | Material Requisition To Resource Division | 2038/SWSD | 16/12/2022 | 0 | Resource Division | 12.83 | 0 | 0 | 0
1411 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOKLONG PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1674/NMD | 29/09/2023 | 30 | B.B. CONCERNED | 11.43 | 0 | 0 | 70
1412 | DARJEELING | Siliguri W/S Division | Khoklong Piped Water Supply Scheme , SM/13437 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED KHOKLONG PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | 259/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.02 | 0 | 0 | 100
1413 | DARJEELING | Siliguri W/S Division | Khoklong Piped Water Supply Scheme , SM/13437 | New | Material Requisition To Resource Division | 79/SWSD | 10/01/2024 | 0 | Resource Division | 1.08 | 0 | 0 | 0
1414 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Infrastructure development cost for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115666 Reference ID : 860308376 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.39 | 0 | 0 | 0
1415 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Power Service connection charges at T.W No-II of Khoklong PWSS under Northern Mechanical Division dist. Darjeeling CONSUMER ID:- 403230623 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.9 | 0 | 0 | 0
1416 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | New Service Connection Charge for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003460490 Reference ID : 403255264 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
1417 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | New Service Connection Charge for KHOKLONG, T/W No.I, under MATIGARA CCC, [APPLICATION NO. 4003316039, Reference ID : 403143725] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.35 | 0 | 0 | 0
1418 | DARJEELING | Central Drilling | Khoklong Piped Water Supply Scheme , SM/13437 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1419 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
1420 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
1421 | DARJEELING | Northern Mechanical | Khoklong Piped Water Supply Scheme , SM/13437 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
1422 | DARJEELING | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Material Requisition To Resource Division | 2034/SWSD | 16/12/2022 | 0 | Resource Division | 15.33 | 0 | 0 | 0
1423 | DARJEELING | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 256/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.65 | 0 | 0 | 100
1424 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | New Service Connection Charge for GANGARAM TEA GARDEN, T/W I, under BAGDOGRA CCC [APPLICATION NO. 4003221633, Reference ID : 403068165] | BP/23-24/122 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
1425 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF GANGARAM TEA GARDEN AREA PIPED WATER SUPPLY SCHEM , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1375/NMD | 09/08/2023 | 30 | NIRMAN | 20.9 | 0 | 0 | 0
1426 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | New Service Connection Charge for GANGARAM TG, T/W No. II (AUG), under BAGDOGRA CCC [APPLICATION NO. 4003263578, Reference ID : 403103790] | 23-24/173&174 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.75 | 0 | 0 | 0
1427 | DARJEELING | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Construction of 100 Cu.M. capacity R.C.C. Elevated Reservoir of 20 Mtrs. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells, construction of pump houses with toilet, boundary wall at head works and 2nd tubewell site with necessary interconnection, providing FHTC with platform and other allied works under Jal Jeevan Mission for Augmentation of GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME of Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | 670/SWSD | 16/06/2023 | 771 | RAJEEV RANJAN OJHA | 224.95 | 0 | 0 | 70
1428 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
1429 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0 | 0
1430 | DARJEELING | Northern Mechanical | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
1431 | DARJEELING | Siliguri W/S Division | Augmentation of Gangaram Tea Garden area Piped Water Supply Scheme , SM/13394 | Augmentation | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with Augmentation of Gangaram PIPED WATER SUPPLY SCHEME under Phansidewa block, Darjeeling District under Siliguri W/S Division, PHD Dte. | 1237/SWSD | 24/04/2025 | 30 | RAJEEV RANJAN OJHA | 11.94 | 0 | 0 | 0
1432 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme , SM/16143 | New | Material Requisition To Resource Division | 58/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
1433 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme , SM/16143 | New | WATER SUPPLY SCHEME FOR PANTHABARI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 32/NKWSMD | 17/04/2023 | 90 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.41 | 0 | 0 | 100
1434 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme , SM/16143 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-412 | 12/01/2024 | 0 | WBSEDCL | 0.82 | 0 | 0 | 0
1435 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme , SM/16143 | New | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | 2411/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 1.45 | 0 | 0 | 0
1436 | DARJEELING | Neorakhola W/S & Mtc.Div. | PANTHABARI FOREST Piped Water Supply Scheme , SM/16143 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
1437 | DARJEELING | Neorakhola W/S & Mtc.Div. | HATTA PIPED WATER SUPPLY SCHEME. , SM/15883 | New | Material Requisition To Resource Division | 442/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
1438 | DARJEELING | Neorakhola W/S & Mtc.Div. | HATTA PIPED WATER SUPPLY SCHEME. , SM/15883 | New | Water Supply Scheme For Hatta Piped Water Supply Scheme in Darjeeling Pulbazar Block under Darjeeling District. | 413/NKWSMD | 05/06/2023 | 938 | SAGARMATHA CONSTRUCTION CO. | 278.82 | 0 | 0 | 80
1439 | DARJEELING | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. , SM/15885 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1440 | DARJEELING | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. , SM/15885 | New | WATER SUPPLY SCHEME FOR MANEDARA PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 437/NKWSMD | 07/06/2023 | 690 | ALLIED INSTRUMENTS | 413.06 | 0 | 0 | 50
1441 | DARJEELING | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. , SM/15885 | New | Additional estimate for water supply scheme for Manedara piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. (SM/15885) | 981/NKWSMD | 18/06/2024 | 60 | ALLIED INSTRUMENTS | 13.06 | 0 | 0 | 100
1442 | DARJEELING | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. , SM/15885 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
1443 | DARJEELING | Neorakhola W/S & Mtc.Div. | MANEDARA PIPED WATER SUPPLY SCHEME. , SM/15885 | New | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 0 | 100
1444 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BIRSING PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15856 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1445 | DARJEELING | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kuchia Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 410/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 4.2 | 0 | 0 | 0
1446 | DARJEELING | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Material Requisition To Resource Division | 213/SWSD | 25/04/2023 | 0 | Resource Division | 23.24 | 0 | 0 | 0
1447 | DARJEELING | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Material Requisition To Resource Division | 2292/SWSD | 11/12/2023 | 0 | Resource Division | 1.05 | 0 | 0 | 0
1448 | DARJEELING | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUCHIA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, & (Zone-II) TW-I, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1670/NMD | 29/09/2023 | 30 | DIAMOND ELECTRICAL WORKS | 11.6 | 0 | 0 | 60
1449 | DARJEELING | Siliguri W/S Division | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Material Requisition To Resource Division | 77/SWSD | 10/01/2024 | 0 | Resource Division | 9.93 | 0 | 0 | 0
1450 | DARJEELING | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | New Service Connection Charge for KUCHIA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319982, Reference ID : 403147083] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.61 | 0 | 0 | 0
1451 | DARJEELING | Northern Mechanical | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Quotation For New Service Connection charges under KUCHIA PWSS Tw-I under NMD PHE dte. Application no- 4003455839 Ref ID-403251521 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
1452 | DARJEELING | Central Drilling | KUCHIA PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15908 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1453 | DARJEELING | Neorakhola W/S & Mtc.Div. | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme , SM/16385 | New | Material Requisition To Resource Division | 761/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.74 | 0 | 0 | 0
1454 | DARJEELING | Neorakhola W/S & Mtc.Div. | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme , SM/16385 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1455 | DARJEELING | Neorakhola W/S & Mtc.Div. | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme , SM/16385 | New | WATER SUPPLY SCHEME FOR SORIANG KHASMAHAL & TAKLING BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK- RANGLI RANGLIONT ; DISTRICT- DARJEELING. | 676/NKWSMD | 12/07/2023 | 515 | SRINIWAS AGARWAL | 531.05 | 0 | 0 | 100
1456 | DARJEELING | Neorakhola W/S & Mtc.Div. | SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme , SM/16385 | New | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 0 | 100
1457 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/16628 | New | Material Requisition To Resource Division | 251/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.42 | 0 | 0 | 0
1458 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/16628 | New | PAYMENT FOR WBSEDCL | BP-2023-24-656 | 23/03/2024 | 0 | WBSEDCL | 18.95 | 0 | 0 | 0
1459 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR DUPTIN BUSTY,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/16628 | New | WATER SUPPLY SCHEME FOR DUPTIN BUSTY PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 104/NKWSMD | 28/04/2023 | 758 | SHAKTI CONSTRUCTION | 830.5 | 0 | 0 | 100
1460 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT TARBANDHA PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15632 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1461 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (GUNAWAR) (PART) , SM/15649 | New | SURFACE WATER BASED RINGTONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 1289/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 605.39 | 0 | 0 | 50
1462 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden , SM/15652 | New | Material Requisition To Resource Division | 2771/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.37 | 0 | 0 | 0
1463 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden , SM/15652 | New | GRAVITY BASED WATER SUPPLYSCHEME FORUNDER SELIM HILL UNDER JAL JEEWAN MISSION | "BP-2024-25-289 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.2 | 0 | 0 | 0
1464 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden , SM/15652 | New | SURFACE WATER BASED SELIM HILL TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK | 2756/NKWSMD | 09/03/2023 | 365 | SHAKTI CONSTRUCTION | 910.25 | 0 | 0 | 85
1465 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Material Requisition To Resource Division | 2039/SWSD | 16/12/2022 | 0 | Resource Division | 15.3 | 0 | 0 | 0
1466 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme , SM/13438 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED NICHITPUR PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | 260/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.05 | 0 | 0 | 100
1467 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Material Requisition To Resource Division | 2302/SWSD | 12/12/2023 | 0 | Resource Division | 2.75 | 0 | 0 | 0
1468 | DARJEELING | Northern Mechanical | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NICHITPUR PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1673/NMD | 29/09/2023 | 30 | M/S UTPAL CHAKRABORTY & CO. | 11.43 | 0 | 0 | 85
1469 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Material Requisition To Resource Division | 71/SWSD | 10/01/2024 | 0 | Resource Division | 1.29 | 0 | 0 | 0
1470 | DARJEELING | Northern Mechanical | Nichitpur Piped Water Supply Scheme , SM/13438 | New | New Service Connection Charge for NICHITPUR, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003299652, Reference ID : 403130074] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.95 | 0 | 0 | 0
1471 | DARJEELING | Northern Mechanical | Nichitpur Piped Water Supply Scheme , SM/13438 | New | New Service Connection Charge for NICHINTAPUR, T/W No. I, under MATIGARA CCC [APPLICATION NO. 4003299595 ; Reference ID : 403130071] | BP/23-24/276 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.83 | 0 | 0 | 0
1472 | DARJEELING | Central Drilling | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1473 | DARJEELING | Siliguri W/S Division | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Laying distribution pipeline and Rising Main allied with construction of 2 nos. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.65 m), Iron Elimination Plant (10 cu.m/hr.), Boundary Wall including FHTC at NICHITPUR Piped Water Supply Scheme under Matigara Block, Darjeeling Dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | 643/SWSD | 15/06/2023 | 696 | U.K CONSTRUCTIONS | 108.96 | 0 | 0 | 30
1474 | DARJEELING | Northern Mechanical | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0 | 0
1475 | DARJEELING | Northern Mechanical | Nichitpur Piped Water Supply Scheme , SM/13438 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1476 | DARJEELING | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS , SM/18725 | New | Material Requisition To Resource Division | 966/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.07 | 0 | 0 | 0
1477 | DARJEELING | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS , SM/18725 | New | WATER SUPPLY SCHEME FOR BADAMTAM TEA GARDEN PWSS IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 947/NKWSMD | 17/08/2023 | 815 | ASHIRWAD CONSTRUCTION CO. | 1087.52 | 0 | 0 | 100
1478 | DARJEELING | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS , SM/18725 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1590/NKWSMD | 29/12/2023 | 10 | MANOMITA CIVIL ENGINEERING CONSULTANCY PVT LTD | 0.95 | 0 | 0 | 100
1479 | DARJEELING | Neorakhola W/S & Mtc.Div. | BADAMTAM TEA GARDEN PWSS , SM/18725 | New | ADDITIONAL WORK FOR BADAMTAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK: DARJEELING PULBAZAR DISTRICT DARJEELNG UNDER DARJEELING DIVISION PHED GTA. | 817/NKWSMD | 05/06/2025 | 90 | ASHIRWAD CONSTRUCTION CO | 29.04 | 0 | 0 | 0
1480 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18317 | New | Material Requisition To Resource Division | 1189/NKWSMD | 06/10/2023 | 0 | Resource Division | 5.08 | 0 | 0 | 0
1481 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18317 | New | PAYMENT FOR WBSEDCL | BP-2023-24-534 | 26/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
1482 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18317 | New | PAYMENT FOR WBSEDCL | BP-2023-24-535 | 26/02/2024 | 0 | WBSEDCL | 4.83 | 0 | 0 | 0
1483 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18317 | New | WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 671/NKWSMD | 12/07/2023 | 635 | YAMA CONSTRUCTIONS LLP | 1111.51 | 0 | 0 | 100
1484 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN,IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/18317 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 160/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 98.42 | 0 | 0 | 100
1485 | DARJEELING | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS , SM/18726 | New | Material Requisition To Resource Division | 965/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.65 | 0 | 0 | 0
1486 | DARJEELING | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS , SM/18726 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/18726) | 2352/NKWSMD | 19/12/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 19.15 | 0 | 0 | 0
1487 | DARJEELING | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS , SM/18726 | New | WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 946/NKWSMD | 17/08/2023 | 866 | KUNCHAN JUNGA ENTERPRISES | 1046.33 | 0 | 0 | 85
1488 | DARJEELING | Neorakhola W/S & Mtc.Div. | LEBONG & MINERAL TEA GARDEN PWSS , SM/18726 | New | Additional work for Piped Water Supply Scheme for Lebong & Mineral Tea Garden (SM/18726) under Darjeeling Division, PHED, GTA | 984/NKWSMD | 18/06/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 49.4 | 0 | 0 | 0
1489 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD , SM/18727 | New | Material Requisition To Resource Division | 998/NKWSMD | 24/08/2023 | 0 | Resource Division | 10.36 | 0 | 0 | 0
1490 | DARJEELING | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD , SM/18727 | New | RUNGBUL & HILL CART ROAD PIPED WATER SUPPLY SCHEME UNDER KURSEONG DIVISION. | 987/NKWSMD | 23/08/2023 | 755 | GARGO TRADERS | 1927.74 | 0 | 0 | 95
1491 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.92 | 0 | 0 | 0
1492 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | BP-2021-22-107 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 162.17 | 0 | 0 | 0
1493 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying distribution system (Part-D) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 11. | 2442/SWSD | 21/03/2022 | 40 | AKASH ENTERPRISE | 41.47 | 0 | 0 | 80
1494 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying distribution system (Part-E) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 12. | 2443/SWSD | 21/03/2022 | 60 | KAMAL GHOSH | 60.01 | 0 | 0 | 0
1495 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 06. | 538/SWSD | 16/06/2022 | 40 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0 | 0
1496 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 06. | 866/SWSD | 21/07/2022 | 40 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0 | 0
1497 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 05. | 537/SWSD | 16/06/2022 | 45 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0 | 0
1498 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Sinking of 04(four) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different Zones (as mentioned in ANNEXURE-A) of Uttar Bagdogra Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2164/SWSD | 30/12/2022 | 30 | K.R.ENTERPRISE | 32.57 | 0 | 0 | 0
1499 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying distribution system (Part-C) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 10. | 2441/SWSD | 21/03/2022 | 50 | NARAYAN CH GHOSH | 57.37 | 0 | 0 | 60
1500 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 05. | 865/SWSD | 21/07/2022 | 45 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0 | 0
1501 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 0 | 100
1502 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MARUTI VAN (NON A/C) FOR THE SUPERINTENDING ENGINEER, NORTH BENGAL CIRCLE-I, P.H.E. DTE. PERIOF FROM 01.04.2023 TO 30.04.2023 i.e. 1 (ONE) MONTHS. VEHICLE NO. WB 73 B/1911. | 2987/SWSD | 28/03/2023 | 31 | RUPA PRASAD | 0.12 | 0 | 0 | 100
1503 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Material Requisition To Resource Division | 2170/SWSD | 11/02/2022 | 0 | Resource Division | 225.89 | 0 | 0 | 0
1504 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Material Requisition To Resource Division | 1450/SWSD | 29/09/2022 | 0 | Resource Division | 9.68 | 0 | 0 | 0
1505 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
1506 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Construction of 400 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants ,Boundary Walls including Functional Household Tap Connections for Augmentation of UTTAR BAGDOGRA Piped Water Supply Scheme (Zone - I & II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | 1155/SWSD | 09/08/2023 | 960 | MAHADEO PRASAD AGARWAL & CO | 495.4 | 0 | 0 | 0
1507 | DARJEELING | Northern Mechanical | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III, IV and (Zone-II) TW-I,III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1584/NMD | 08/09/2023 | 30 | SUMON ELECTRICAL | 46.7 | 0 | 0 | 75
1508 | DARJEELING | Northern Mechanical | AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME , SM/10026 | Augmentation | Electric quotation for new service connection at t.w no- i,z-ii of Uttar Bagdogra w/s scheme, in the dist. Darjeeling. | BP/24-25/217 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.91 | 0 | 0 | 0
1509 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE , SM/18639 | New | Material Requisition To Resource Division | 960/NKWSMD | 21/08/2023 | 0 | Resource Division | 11.68 | 0 | 0 | 0
1510 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE , SM/18639 | New | PAYMENT FOR WBSEDCL | BP-2023-24-504 | 26/02/2024 | 0 | WBSEDCL | 7.09 | 0 | 0 | 0
1511 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE , SM/18639 | New | SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | 911/NKWSMD | 11/08/2023 | 365 | INTERIOR'S NEST | 1516.55 | 0 | 0 | 65
1512 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE , SM/18639 | New | ADITIONAL WORK FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | 830/NKWSMD | 09/06/2025 | 180 | MAA DURGA ENTERPRISE | 54.17 | 0 | 0 | 0
1513 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE , SM/18639 | New | STRENGHTENING OF LAYING DISTRIBUTION SYSTEM FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION,PHE.DTE. | 831/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 253.18 | 0 | 0 | 0
1514 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme , SM/07030 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Barsadvita habitation Adhikari Barsadvita and village Mayanaguri habitation Moynaguri of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, P.H.E. Dte. | 1014/SWSD | 11/12/2020 | 40 | VIJAY KUMAR ARORA | 33.45 | 28.95 | 86.55 | 100
1515 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme , SM/07030 | Retrofitting | Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission JJM and Jal Swapna under Command area village Maynaguri habitation Pitha bachi Ramchndra village Kelabari habitation Damravita Kalabari and village Alokjhari habitation Surya Mohan of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | 1015/SWSD | 11/12/2020 | 40 | M/S G.C. CONSTRUCTION & CO. | 35.14 | 7.44 | 21.16 | 20
1516 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Barsadvita and adjoining Mouzas Piped water Supply Scheme , SM/07030 | Retrofitting | Issue of fuel for office vehicles of Executive Engineer Siliguri W/S division PHE Dte. | BP-2023-24-196 | 28/03/2024 | 0 | SONA PETROL PUMP | 0.35 | 0 | 0 | 0
1517 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING , SM/19177 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
1518 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANGARJUNG TEA GARDEN & OTHER 3 VILLAGES PWSS(MVS),BLOCK: JORE BUNGALOW-SUKHIAPOKHRI,DISTRICT: DARJEELING , SM/19177 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR MANGARJUNG AND OTHER 3 VILLAGES followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | 1612/NKWSMD | 09/09/2024 | 546 | GARGO TRADERS | 8505.63 | 0 | 0 | 25
1519 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block , SM/07426 | Retrofitting | Laying of new pipe line inconnection with providing functional household tap connection (FHTC) at OMI village of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 07. | 333/SWSD | 18/05/2022 | 10 | UJJWAL ROY | 4.39 | 0 | 0 | 100
1520 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block , SM/07426 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Mahasing Habitation Fokira jote Mahasing village Deomani Habitation Deomani village Nandalal Habitation Jaban jote and Mouri jote of OMI Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte (3rd CALL) | 694/SWSD | 02/08/2021 | 30 | S.K. BANIK | 27.18 | 0 | 0 | 100
1521 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Omi Piped water Supply Scheme at Naxalbari Block , SM/07426 | Retrofitting | Laying bye-pass pipeline along with construction of boundary wall, development of land at head work site of OMI & adjoining w/s scheme under Siliguri Sub Division PHE Dte. | 1429/SWSD | 14/08/2020 | 0 | S.K. BANIK | 24.87 | 0 | 0 | 75
1522 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Matidhar Bijmillini T.E and Pathoria Habitation of Paschim Madati Piped water Supply Scheme (Part - A) , SM/07031 | Retrofitting | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Motidhar Bijmillini T E Part A of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | 1081/SWSD | 18/12/2020 | 40 | M/S G.C. CONSTRUCTION & CO. | 33.72 | 0 | 0 | 85
1523 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Dhakpara village of Budharugaon Piped water Supply Scheme , SM/07214 | Retrofitting | Supply of 01 (one) no. Maxi Cab with Engine Capacity less than or equal to 2000 C.C. with Air Condition on hire basis (for monthly hiring) including driver under Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. (With valid Taxi permit and other necessary documents as per norms of Zonal R.T.O) For 06 (six months) with effect from 01.07.2024 to 31.12.2024. | 1656/SWSD | 28/06/2024 | 180 | S S CONSTRUCTIONS | 0.95 | 0 | 0 | 0
1524 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Dhakpara village of Budharugaon Piped water Supply Scheme , SM/07214 | Retrofitting | Acceptance cum Work Order for Providing of Functional Household Tap Connection (FHTC) at Budharugaon & Dhakpara Mouza's under under Jal Jeevan & Jal Swapno programme of Budharugaon Water Supply Scheme under Phansidewa Block under Siliguri W/S Division , P.H.E. Dte. | 1240/SWSD | 24/04/2025 | 45 | SUBIR CH. CHOWDHURY | 54.23 | 0 | 0 | 0
1525 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u , SM/08295 | Retrofitting | Survey for existing water source electric connection nature of building etc. of schools,AWCs,health centres within different blocks under Siliguri Sub-Division,P.H.E Dte. | 544/SSD | 19/12/2022 | 15 | ROYAL ENTERPRISE | 1.02 | 0 | 0 | 100
1526 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u , SM/08295 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C.on hire basis including driver for Assistant Engineer-I , Siliguri W/S Division, P.H.E. Dte. Dist. Darjeeling (with valid Taxi permit ). | 284/SWSD | 06/02/2024 | 182 | SUDIP BASAK | 0.88 | 0 | 0 | 0
1527 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under jal Jeevan Mission & Jal Swapno Programme for Sukanta Nagar, Upper Bagdogra, Uttar Bagdogra, Adarsha Nagar,Gadadhar Pally, Hochimin Nagar, Jyoti Nagar, Lal Busty & Vivekananda Palli Village Habitation u , SM/08295 | Retrofitting | Further continuation order for hiring of 01 (one) no maxi cab with engine capacity less than or equal to 2000 CC with air condition for the Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte for the period from 01.09.2023 to 31.12.2023 (For Executive Engineer, Siliguri W/S Division, P.H.E. Dte. i.e 04 (four) months. | 1492/SWSD | 31/08/2023 | 122 | SUBIR CH. CHOWDHURY | 0.59 | 0 | 0 | 0
1528 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division , SM/10767 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom 3rd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009298 SM Code-SM/08938 | 493/NKWSMD | 24/05/2022 | 60 | MS JAGANNATH PRASAD | 14.04 | 0 | 0 | 98
1529 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection at PWS scheme for Soom 3rd Division , SM/10767 | Retrofitting | Material Requisition To Resource Division | 1260/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.8 | 0 | 0 | 0
1530 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village , SM/10771 | Retrofitting | Material Requisition To Resource Division | 1902/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.14 | 0 | 0 | 0
1531 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village , SM/10771 | Retrofitting | Material Requisition To Resource Division | 2576/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.14 | 0 | 0 | 0
1532 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village , SM/10771 | Retrofitting | Material Requisition To Resource Division | 1265/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.14 | 0 | 0 | 0
1533 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection with retrofitting of pipeline for PWS scheme at Samadhen Forest Village , SM/10771 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including augmentation & extension for PWS Scheme for Samadhin Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009470 SM Code-SM/08924 | 496/NKWSMD | 24/05/2022 | 60 | SUNIL SHARMA | 13.76 | 0 | 0 | 50
1534 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna , SM/11380 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 3rd Mile Simkuna Gram GP - Rungbull, Block - Jorebungalow Sukhia. | 941/NKWSMD | 12/07/2022 | 60 | BIMLA GURUNG | 9.29 | 0 | 0 | 0
1535 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan mission / Jal sapno Programme from existing scheme at 3rd mile , Simkuna , SM/11380 | Retrofitting | Material Requisition To Resource Division | 2619/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
1536 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden , SM/11381 | Retrofitting | Material Requisition To Resource Division | 1907/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.2 | 0 | 0 | 0
1537 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden , SM/11381 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Pokhriabong Turzum Panchyat - Pokhriabong-II Block - Jorebungalow Sukhia. | 945/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 67.07 | 0 | 0 | 100
1538 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden , SM/11381 | Retrofitting | Material Requisition To Resource Division | 2617/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.2 | 0 | 0 | 0
1539 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden , SM/11381 | Retrofitting | Material Requisition To Resource Division | 1363/NKWSMD | 21/09/2022 | 0 | Resource Division | 3.2 | 0 | 0 | 0
1540 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional household tap connection under Jal Jeewan Mission/ Jal Swapno Programme at New Fallodi Tea Garden ( Mandir Goan) , SM/11390 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at New Fallodi Tea Garden GP - Soureni I, Block-Mirik. | 942/ NKWSMD | 12/07/2022 | 60 | ROHIT KUMAR DEWAN | 9.11 | 0 | 0 | 90
1541 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA , SM/11399 | New | Material Requisition To Resource Division | 321/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
1542 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Lower Mamring under Kurseong Sub - Division, PHED, GTA , SM/11399 | New | Surface water based Lower Mamring Khasmahal in Kurseong Block within Darjeeling District. | 187/NKWSMD | 04/05/2023 | 690 | PREM CHANDRA RAI | 356.26 | 0 | 0 | 85
1543 | DARJEELING | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed M.M TERAI Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 272/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.35 | 0 | 0 | 100
1544 | DARJEELING | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | Material Requisition To Resource Division | 2026/SWSD | 16/12/2022 | 0 | Resource Division | 1.45 | 0 | 0 | 0
1545 | DARJEELING | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | Material Requisition To Resource Division | 1464/SWSD | 29/09/2022 | 0 | Resource Division | 2.16 | 0 | 0 | 0
1546 | DARJEELING | Siliguri W/S Division | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | Construction of Pump House (5.4 X 3.65) size, Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling, boundary wall allied with laying of rising main, distribution system and providing functional household tap connection (FHTC) under JJM for M.M. TERAI PIPED WATER SUPPLY SCHEME within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | 2094/SWSD | 22/12/2022 | 75 | SUDIP BASAK | 88.33 | 0 | 0 | 60
1547 | DARJEELING | Northern Mechanical | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | New Service Connection Charge for M.M TERAI, T/W No. I under NAXALBARI CCC [APPLICATION NO. 4003312828 ; Reference ID : 403142027] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.57 | 0 | 0 | 0
1548 | DARJEELING | Northern Mechanical | M.M.TERAI PIPED WATER SUPPLY SCHEME , SM/11775 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for M.M.TERAI PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1314/NMD | 04/08/2023 | 562 | HARAGOURI ENTERPRISE | 11.5 | 0 | 0 | 100
1549 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA , SM/10800 | New | Material Requisition To Resource Division | 2587/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.81 | 0 | 0 | 0
1550 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA , SM/10800 | New | SURFACE WATER BASED NAYA KAMAN PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 1653/NKWSMD | 04/11/2022 | 1062 | ABHINAY CHETTRI | 86.11 | 0 | 0 | 80
1551 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Naya Kaman under Kurseong Sub Division ,PHED,GTA , SM/10800 | New | ADDITIONAL WORK FOR SURFACE WATER BASED NAYA KAMAN PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE-GTA. | 498/NKWSMD | 09/04/2025 | 60 | ABHINAY CHETTRI | 19.79 | 0 | 0 | 0
1552 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA , SM/10801 | New | Material Requisition To Resource Division | 2838/NKWSMD | 17/03/2023 | 0 | Resource Division | 0.92 | 0 | 0 | 0
1553 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindhuria Goliapakha under Kurseong Sub Division ,PHED,GTA , SM/10801 | New | SURFACE WATER BASED TINDHURIA GOLIAPAKHA PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | 1118/NKWSMD | 05/08/2022 | 270 | PREM CHANDRA RAI | 99.95 | 0 | 0 | 90
1554 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, , SM/11316 | Retrofitting | Material Requisition To Resource Division | 1292/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.31 | 0 | 0 | 0
1555 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare ( Gorabari Margetshop GP ) under Kurseong Sub-Division PHED, , SM/11316 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare (Gorabari Margetshop GP) under Kurseong Sub-Division PHED, GTA. | 792/NKWSMD | 30/06/2022 | 1360 | SAMIR THAPA | 6.78 | 0 | 0 | 70
1556 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11334 | Retrofitting | Material Requisition To Resource Division | 1308/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.51 | 0 | 0 | 0
1557 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sepoydhura Tea Estate under Kurseong-Sub Division, PHED, GTA , SM/11334 | Retrofitting | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Seepoydhura T.E. Mahanadi GP Block - Kurseong Block. | 813/NKWSMD | 30/06/2022 | 90 | HIMALI CONSTRUCTION COMPANY | 26.66 | 0 | 0 | 100
1558 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/11944 | New | WATER SUPPLY SCHEME FOR POKHRIBONG KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | 1619/NKWSMD | 03/11/2022 | 180 | YAMA CONSTRUCTIONS LLP | 897.18 | 0 | 0 | 0
1559 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/11944 | New | Material Requisition To Resource Division | 964/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.58 | 0 | 0 | 0
1560 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/11944 | New | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-I, P.H.E.D., GTA | 159/AE-II/NKWSMD | 10/01/2024 | 15 | MADAN KUMAR CHHETRI | 23.94 | 0 | 0 | 100
1561 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR POKHARIBONG KHASMAHAL PWSS IN JORE BUNGLOW SUKHIAPIOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/11944 | New | Additional work piped water supply scheme for Pokhriabong Busty No. 5 under Jal Jiwan Mission and Jal Swapno Programme. | 940/NKWSMD | 16/08/2023 | 510 | RISHI KESH THAKURI | 12.62 | 0 | 0 | 100
1562 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. , SM/12367 | New | Material Requisition To Resource Division | 2561/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.11 | 0 | 0 | 0
1563 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Longview Tea Garden under Kurseong Sub - Division, PHED, GTA. , SM/12367 | New | SURFACE WATER BASED LONGVIEW PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | 2471/NKWSMD | 06/02/2023 | 455 | SHAKTI CONSTRUCTION | 1742.62 | 0 | 0 | 100
1564 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | Material Requisition To Resource Division | 2594/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.35 | 0 | 0 | 0
1565 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | Material Requisition To Resource Division | 2070/NKWSMD | 05/01/2023 | 0 | Resource Division | 10.71 | 0 | 0 | 0
1566 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | FOREST PAYMENT |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
1567 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | forest payment | BP-2023-24-601 | 18/03/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.28 | 0 | 0 | 0
1568 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | Surface water based Barasitting Khasmahal & Selpu Khasmahal PWSS to accommodate FHTC in Kurseong Block within Darjeeling District | 2362/NKWSMD | 01/02/2023 | 585 | YAMA CONSTRUCTIONS LLP | 1751.75 | 0 | 0 | 100
1569 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Barasit Tong Khasmahal & Selphu Khasmahal under Kurseong Sub - Division, PHED, GTA. , SM/12368 | New | ADDITIONAL WORK FOR SURFACE WATER BASED BARASITTONG KHASMAHAL & SELPU KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | 2205/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 246.9 | 0 | 0 | 80
1570 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Material Requisition To Resource Division | 2058/SWSD | 16/12/2022 | 0 | Resource Division | 23.57 | 0 | 0 | 0
1571 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , (Zone-II) TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1377/NMD | 09/08/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 10.6 | 0 | 0 | 0
1572 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 242/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.19 | 0 | 0 | 100
1573 | DARJEELING | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | 563/CDD | 07/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 0
1574 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Renovation of the pump House and Others allied Works at Mandalaguri (H/W) site of Mandalaguri Piped Water Supply Scheme under Siliguri W/S Division P.H.E. Dte. | 2538/SWSD | 18/09/2024 | 45 | K.K.GHOSH & CO. | 3.2 | 0 | 0 | 0
1575 | DARJEELING | Central Drilling | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 0 | 10
1576 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | New Service Connection Charge for MANDALAGURI, T/W-I, under MATIGARA CCC, [APPLICATION NO. 4003340645, Reference ID : 403163196] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.1 | 0 | 0 | 0
1577 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Installation of two tank chlorination system at MANDALAGURI and other adjacent water supply scheme UNDER JJM under MATIGARA Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. | 81/SMSD | 07/02/2025 | 10 | CHOWDHURY AND BASU ENTERPRISE | 1.1 | 0 | 0 | 0
1578 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , SM/12799 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0 | 0
1579 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11350 | New | PWS Scheme at Pokhari Tar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 957/NKWSMD | 12/07/2022 | 60 | PHURBA RUMBA | 25.37 | 0 | 0 | 0
1580 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11350 | New | Material Requisition To Resource Division | 1320/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.22 | 0 | 0 | 0
1581 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. , SM/11350 | New | Material Requisition To Resource Division | 2067/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0 | 0
1582 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Adalpur Dwitiyo Khanda Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | 288/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 2.82 | 0 | 0 | 100
1583 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Material Requisition To Resource Division | 2051/SWSD | 16/12/2022 | 0 | Resource Division | 31.66 | 0 | 0 | 0
1584 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Material Requisition To Resource Division | 1375/SWSD | 21/09/2022 | 0 | Resource Division | 10.86 | 0 | 0 | 0
1585 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Material Requisition To Resource Division | 2288/SWSD | 11/12/2023 | 0 | Resource Division | 3.57 | 0 | 0 | 0
1586 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 0 | 50
1587 | DARJEELING | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | New Service Connection Charge for BARAADALPUR, T/W No. I, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299617 ; Reference ID : 403130073] | BP/23-24/280 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
1588 | DARJEELING | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. II, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300577 ; Reference ID : 403130594] | BP/23-24/221 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0 | 0
1589 | DARJEELING | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. I, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300574 ; Reference ID : 403130566] | BP/23-24/220 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.47 | 0 | 0 | 0
1590 | DARJEELING | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | New Service Connection Charge for BARAADALPUR, T/W No. II, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299635 ; Reference ID : 403130072] | BP/23-24/277 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.16 | 0 | 0 | 0
1591 | DARJEELING | Central Drilling | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1592 | DARJEELING | Siliguri W/S Division | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Construction of 200 Cu.M & 150 cum capacity RCC Elevated Reservoir each of 20 mtrs Staging Height at the head works sites,laying rising main,Laying distribution pipeline with Functional Household Tap Connection (FHTC), construction of Two number pump houses(5.40 X 3.60 m),Two number pump houses (3.00 X 3.60 m), Iron Elimination Plant (IEP) with Blower room ,Sinking of four (4) nos Tube well (ODEX-165 method),Soil Investigation at H/W sites and Boundary wall for BARA ADALPUR DWITYA KHANDA PWSS (ZONE I & II) Block:Matigara,Dist: Darjeeling under Siliguri W/S Division, P.H.E. Dte | 1150/SWSD | 08/08/2023 | 783 | MAHADEO PRASAD AGARWAL & CO | 510.38 | 0 | 0 | 80
1593 | DARJEELING | Northern Mechanical | BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME , SM/11786 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1579/NMD | 08/09/2023 | 694 | CHOWDHURY AND BASU ENTERPRISE | 23.46 | 0 | 0 | 100
1594 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional Household tap connection from existing PWSS at Khaling dhura & Vah Tukbar( Bhutta Kheti) , SM/13352 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Khalingdhura & Vahtukvar TG (Bhuttakheti) GP - Rangit-I, Block - Bijanbari Pullbazar | 1617/NKWSMD | 03/11/2022 | 1060 | MANI KUMAR CHHETRI | 48.48 | 0 | 0 | 85
1595 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Material Requisition To Resource Division | 2057/SWSD | 16/12/2022 | 0 | Resource Division | 45.97 | 0 | 0 | 0
1596 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 243/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.34 | 0 | 0 | 100
1597 | DARJEELING | Central Drilling | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | 560/CDD | 06/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0 | 10
1598 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Laying distribution of pipeline, construction of boundary wall, pump house, installation of I.E.Plant ,Providing functional House hold Tap Connection (FHTC) at ( Zone -I) , ( Zone-II ) & ( Zone-III ) for augmentation of Mangalsing PWSS under JJM within Naxalbari block under Siliguri WS Division, PHE Dte. Sl No. 09 | 868/SWSD | 14/07/2023 | 180 | M/S DOLPHIN CONSTRUCTION CO | 396.62 | 0 | 0 | 40
1599 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , (Zone-III) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1384/NMD | 09/08/2023 | 30 | BONANZA ENTERPRISE | 12.99 | 0 | 0 | 100
1600 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Laying New HDPE Pipe Line Under Mangalsingh Pwss From Second Tubewell Site To Sebdullhajote Mouza ( Kanu Sanyal Basti) , Under Siliguri Sub Division, Under Siliguri W/S Division | 1949/SWSD | 16/10/2023 | 15 | NARAYAN CH GHOSH | 7.12 | 0 | 0 | 95
1601 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Shifting of existing pipeline to new pipeline ,house connection along with laying of additional pipeline at Sebdella Mouza and Mangalsingh Mouza under Mangalsingh Water supply scheme under Siliguri w/s Division, PHE Dte | 2535/SWSD | 18/09/2024 | 30 | NARAYAN CH GHOSH | 4.92 | 0 | 0 | 100
1602 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | New Service Connection Charge for MANGALSING, T/W No. I,ZONE-II under NAXALBARI CCC [APPLICATION NO. 4003289754 ; Reference ID : 403122959] |  | 22/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0 | 0
1603 | DARJEELING | Northern Mechanical | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0 | 0
1604 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , SM/12773 | Augmentation | Acceptance cum work order for Repair and Renovation of Boundary wall( Zn-II ) ,Approach road & Drain (Zn-III) , Boosting Pump Connection(Zn-I) and allied works for the Augmentation of Mangalsing Piped Water Supply Scheme in connection with JJM under Siliguri W/S Division P.H.E. Dte. | 1235/SWSD | 24/04/2025 | 45 | NARAYAN CH GHOSH | 8.25 | 0 | 0 | 0
1605 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/13041 | New | Material Requisition To Resource Division | 1899/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.24 | 0 | 0 | 0
1606 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/13041 | New | Material Requisition To Resource Division | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.24 | 0 | 0 | 0
1607 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR SAMRIK TEA GARDEN (SIMRIPANI) PWSS. BLOCK JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT- DARJEELING. , SM/13041 | New | Water Supply Scheme for Samarik Pani Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. | 1560/NKWSMD | 21/10/2022 | 965 | SRINIWAS AGARWAL | 1158.25 | 0 | 0 | 95
1608 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/13955 | New | Material Requisition To Resource Division | 2555/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.48 | 0 | 0 | 0
1609 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/13955 | New | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT.(SM/13955) | BP-2024-25-450 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.58 | 0 | 0 | 0
1610 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. , SM/13955 | New | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. | 2152/NKWSMD | 20/01/2023 | 1065 | VINAYAK CONSTRUCTION | 229.98 | 0 | 0 | 80
1611 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13959 | New | Material Requisition To Resource Division | 2583/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.02 | 0 | 0 | 0
1612 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13959 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1613 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR BAMONPOKHRI FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13959 | New | Water Supply Scheme for Bamon Pokhari Forest Piped Water Supply Scheme in Kurseong Block Under Darjeeling District | 1879/NKWSMD | 14/12/2022 | 980 | ROSHAN BISWAKARMA | 211.2 | 0 | 0 | 60
1614 | DARJEELING | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Material Requisition To Resource Division | 2040/SWSD | 16/12/2022 | 0 | Resource Division | 16.12 | 0 | 0 | 0
1615 | DARJEELING | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF SONA CHANDI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 257/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.56 | 0 | 0 | 100
1616 | DARJEELING | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Material Requisition To Resource Division | 69/SWSD | 10/01/2024 | 0 | Resource Division | 2.56 | 0 | 0 | 0
1617 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | New Service Connection Charge for SONA CHANDI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319753, Reference ID : 403147078] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.2 | 0 | 0 | 0
1618 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | New Service Connection Charge for SONA CHANDI, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319880, Reference ID : 403147076] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0 | 0
1619 | DARJEELING | Siliguri W/S Division | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Construction of Pump House 2 nos, Rig bord 2 nos big dia T/W by Odex -165 method, Boundary walls, Laying distribution system (HDPE pipe), rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (Three) month trial run IEP (25 cum/hr) and allied works for Augmentation of Sona Chandi PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | 09/SWSD | 05/04/2023 | 105 | A.K.CONSTRUCTION | 115.86 | 0 | 0 | 60
1620 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sona Chandi Piped Water Supply Scheme, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1476/NMD | 17/08/2023 | 776 | T S CONSTRUCTION | 24.83 | 0 | 0 | 90
1621 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
1622 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
1623 | DARJEELING | Northern Mechanical | Sona Chandi Piped Water Supply Scheme , SM/13436 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1624 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | Material Requisition To Resource Division | 2557/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.43 | 0 | 0 | 0
1625 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | Material Requisition To Resource Division | 2714/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.43 | 0 | 0 | 0
1626 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | 1591/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
1627 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months). | 1457/NKWSMD | 30/11/2023 | 62 | THE ELECTRIC SPHERE | 0.79 | 0 | 0 | 100
1628 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 30/11/2023 (2 Months). | 1139/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0 | 0 | 100
1629 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | Water Supply Scheme For Ghoom Pahar Forest under JAL JEEWAN MISSION within Jorebunglow Sukhia Pokhri Block,District-Darjeeling Detail - (SW No. : SW/140971/2023) | BP-2024-25-291 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.45 | 0 | 0 | 0
1630 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. | 2519/NKWSMD | 15/02/2023 | 815 | GARGO TRADERS | 1586.68 | 0 | 0 | 85
1631 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
1632 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/14148 | New | External Water Supply Works at 10 Bedded Hospital, Ghoom, Darjeeling, GTA | 1507/NKWSMD | 06/12/2023 | 210 | DHIRAJ TAMANG | 17.88 | 0 | 0 | 100
1633 | DARJEELING | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Singijhor Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 409/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.6 | 0 | 0 | 0
1634 | DARJEELING | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Material Requisition To Resource Division | 2201/SWSD | 04/01/2023 | 0 | Resource Division | 74.03 | 0 | 0 | 0
1635 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Supply and Delivery of C.I.D.F specials for using pumping machinery installation purpose at SINGIJHORA W/S/S under JJM in the dist. of Siliguri under, Northern Mechanical Division ,PHE Dte. | 425/SMSD | 20/12/2023 | 377 | SARKAR ELECTRIC | 0.58 | 0 | 0 | 100
1636 | DARJEELING | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Material Requisition To Resource Division | 58/SWSD | 09/01/2024 | 0 | Resource Division | 22.63 | 0 | 0 | 0
1637 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New Service Connection Charge for SINGIJHOR Zone-II,TW- II under BAGDOGRA CCC | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.76 | 0 | 0 | 0
1638 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New Service Connection Charge for SINGIJHORA, T/W No.I, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326146, Reference ID : 403152620] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
1639 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New service connection at singijhora PWSS,Z-I,TW-II under NMD PHE Dte. Application no- 4003417642 Ref id- 403224817 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.19 | 0 | 0 | 0
1640 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New Service Connection Charge for SINGIJHOR Zone-II,TW- I under BAGDOGRA CCC | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.12 | 0 | 0 | 0
1641 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New Service Connection Charge for SINGIJHORA, T/W No.II, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326171, Reference ID : 403152622] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0 | 0
1642 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | New service connection at singijhora PWSS,Z-I,TW-I under NMD PHE Dte. Application no- 4003417637 Ref id- 403224816 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.08 | 0 | 0 | 0
1643 | DARJEELING | Central Drilling | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1644 | DARJEELING | Siliguri W/S Division | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Construction of 300 - 1 No. & 150 - 2 Nos. cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site (Zone - I, II & III) including distribution system (HDPE) with Rising Main, Rig bore 6 Nos. big dia T/W by Odex-165 method, Providing Functional Household Tap Connection (FHTC), Pump House 6 Nos., Blower Room 3 Nos., IEP 70, 35 & 35 cu.m./hr, Boundary Walls, Horizontal Boring, Soil Testing and allied works at SINGHIJHOR PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 1147/SWSD | 08/08/2023 | 693 | UNIBRO INFRASERV PRIVATE LIMITED | 1080.94 | 0 | 0 | 50
1645 | DARJEELING | Northern Mechanical | SINGIJHOR PIPED WATER SUPPLY SCHEME ( ZONE-I, II & III) , SM/14150 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIJHOR PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I and II, (ZONE-II) TW No. I and II, (ZONE-III) TW No. I and II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1654/NMD | 29/09/2023 | 701 | M/S P.P. ELECTRICALS | 45.94 | 0 | 0 | 75
1646 | DARJEELING | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16161 | New | Material Requisition To Resource Division | 208/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.42 | 0 | 0 | 0
1647 | DARJEELING | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16161 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/16161) | 2353/NKWSMD | 19/12/2024 | 180 | HARI PRASAD CHETTRI | 53.29 | 0 | 0 | 0
1648 | DARJEELING | Neorakhola W/S & Mtc.Div. | RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/16161 | New | WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 101/NKWSMD | 28/04/2023 | 999 | HARI PRASAD CHETTRI | 258.75 | 0 | 0 | 70
1649 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Material Requisition To Resource Division | 201/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0 | 0
1650 | DARJEELING | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1663/NMD | 29/09/2023 | 30 | SARKAR ELECTRIC | 10.38 | 0 | 0 | 100
1651 | DARJEELING | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | New Service Connection Charge for TARBANDHA, T/W No. II, under BAGDOGRA CCC, [APPLICATION NO.4003308985, Reference ID : 403137427] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0 | 0
1652 | DARJEELING | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | New Service Connection Charge for TARBANDHA, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] | BP/23-24/273 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.33 | 0 | 0 | 0
1653 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Laying distribution system along with boring of new tubewells by ODEX-165, construction of pump houses, boundary walls at 3rd and 4th tubewell site, installation of I.E.P. at both sites and other allied works in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte. | 336/SWSD | 08/05/2023 | 620 | UJJWAL ROY | 90.32 | 0 | 0 | 75
1654 | DARJEELING | Central Drilling | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1655 | DARJEELING | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0 | 0
1656 | DARJEELING | Northern Mechanical | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0 | 0
1657 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , SM/15269 | Augmentation | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) & other allied works(laying of pipeline , cleaning the chokage of pipe line and ferrule , repair of pump house , Drain and boundary wall) in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte | 484/SWSD | 12/02/2025 | 301 | UJJWAL ROY | 17.38 | 0 | 0 | 90
1658 | DARJEELING | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME , SM/15880 | New | Material Requisition To Resource Division | 2776/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.06 | 0 | 0 | 0
1659 | DARJEELING | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME , SM/15880 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAMOHAN UNDER JAL JEEVAN MISSION. | BP-2024-25-287 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.7 | 0 | 0 | 0
1660 | DARJEELING | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME , SM/15880 | New | SURFACE WATER BASED RANGMOHAN PWSS TO ACCOMODATE FHTC IN MIRIK BLOCK | 2669/NKWSMD | 01/03/2023 | 670 | MAHENDRA ADHIKARI | 304.14 | 0 | 0 | 85
1661 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Material Requisition To Resource Division | 202/SWSD | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0 | 0
1662 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Material Requisition To Resource Division | 2293/SWSD | 11/12/2023 | 0 | Resource Division | 1.88 | 0 | 0 | 0
1663 | DARJEELING | Northern Mechanical | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for LOHASING Piped Water Supply Scheme, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1669/NMD | 29/09/2023 | 30 | ALPHA ENTERPRISE | 12.03 | 0 | 0 | 0
1664 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - I) | 109/SWSD | 15/01/2024 | 112 | CAPITAL ENGINEERS | 161.7 | 0 | 0 | 0
1665 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - II) | 3485/SWSD | 19/12/2024 | 60 | CAPITAL ENGINEERS | 87.1 | 0 | 0 | 0
1666 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Lohasing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 402/SSD | 25/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.64 | 0 | 0 | 30
1667 | DARJEELING | Siliguri W/S Division | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Material Requisition To Resource Division | 72/SWSD | 10/01/2024 | 0 | Resource Division | 7.61 | 0 | 0 | 0
1668 | DARJEELING | Northern Mechanical | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | New Service Connection Charge for LOHASING, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003301385 ; Reference ID : 403131311] | BP/23-24/229 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.31 | 0 | 0 | 0
1669 | DARJEELING | Central Drilling | LOHASING PIPED WATER SUPPLY SCHEME , SM/15926 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1670 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Material Requisition To Resource Division | 2212/SWSD | 05/01/2023 | 0 | Resource Division | 11.92 | 0 | 0 | 0
1671 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Material Requisition To Resource Division | 2287/SWSD | 11/12/2023 | 0 | Resource Division | 4.4 | 0 | 0 | 0
1672 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Material Requisition To Resource Division | 1804/SWSD | 30/09/2023 | 0 | Resource Division | 11.72 | 0 | 0 | 0
1673 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dhemal Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 319/SSD | 20/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.4 | 0 | 0 | 30
1674 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Material Requisition To Resource Division | 73/SWSD | 10/01/2024 | 0 | Resource Division | 9.99 | 0 | 0 | 0
1675 | DARJEELING | Central Drilling | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1676 | DARJEELING | Siliguri W/S Division | DHEMAL PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/15927 | New | Construction of Pump House with toilet , laying distribution system, Rising Main, boring of deep tube well by ODEX-165 method, construction of Blower Room with IEP, Boundary Wall at H/W and second tube well site with necessary interconnection and providng FHTC and other allied work under Jal Jeevan Mission for DHEMAL Piped Water Supply Scheme Block : Naxalbari under Siliguri W/S Division, P.H.E. Dte. | 1225/SWSD | 14/08/2023 | 871 | K.R.ENTERPRISE | 349.22 | 0 | 0 | 10
1677 | DARJEELING | Neorakhola W/S & Mtc.Div. | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme , SM/16384 | New | Material Requisition To Resource Division | 323/NKWSMD | 24/05/2023 | 0 | Resource Division | 2.37 | 0 | 0 | 0
1678 | DARJEELING | Neorakhola W/S & Mtc.Div. | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme , SM/16384 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1679 | DARJEELING | Neorakhola W/S & Mtc.Div. | TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme , SM/16384 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TAKLING KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 631/NKWSMD | 05/05/2025 | 60 | SRINIWAS AGARWAL | 12.88 | 0 | 0 | 0
1680 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA MUNGWA PIPED WATER SUPPLY SCHEME , SM/15893 | New | Additional estimate for water supply scheme for Bara Mungwa piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. | 980/NKWSMD | 18/06/2024 | 60 | GARGO TRADERS | 12.72 | 0 | 0 | 100
1681 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA MUNGWA PIPED WATER SUPPLY SCHEME , SM/15893 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
1682 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA MUNGWA PIPED WATER SUPPLY SCHEME , SM/15893 | New | WATER SUPPLY SCHEME FOR BARA MUNGWA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 438/NKWSMD | 07/06/2023 | 690 | GARGO TRADERS | 455.08 | 0 | 0 | 100
1683 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME , SM/15897 | New | Material Requisition To Resource Division | 445/NKWSMD | 07/06/2023 | 0 | Resource Division | 3.46 | 0 | 0 | 0
1684 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME , SM/15897 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1685 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME , SM/15897 | New | Water Supply Scheme for Pubong Khasmahal Piped Water Supply Scheme In Rangli Rangliot Block Under Darjeeling District. | 411/NKWSMD | 05/06/2023 | 447 | RAMESH AGARWAL | 513.34 | 0 | 0 | 100
1686 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME , SM/15897 | New | Additional work for Water supply Pubong Khasmahal Piped Water Supply Scheme Block Rangli-Rangliot District: Darjeeling. | 967/NKWSMD | 14/06/2024 | 60 | RAMESH AGARWAL | 14.12 | 0 | 0 | 95
1687 | DARJEELING | Neorakhola W/S & Mtc.Div. | PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME , SM/15897 | New | Gravity Based Water Supply Scheme For Pubong Thulokhola under JAL JEEWAN MISSION under RR Block, District- Darjeeling Detail - (SW No. : SW/140500/2023) | BP-2024-25-285 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.35 | 0 | 0 | 0
1688 | DARJEELING | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. , SM/15868 | New | Material Requisition To Resource Division | 242/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.87 | 0 | 0 | 0
1689 | DARJEELING | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. , SM/15868 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
1690 | DARJEELING | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. , SM/15868 | New | WATER SUPPLY SCHEME FOR LAMAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 221/NKWSMD | 10/05/2023 | 515 | TULSI NIROLA | 679.13 | 0 | 0 | 50
1691 | DARJEELING | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. , SM/15868 | New | Additional Estimate for Construction of platform at Lamagaon Piped Water Supply Scheme under Pulbazar Bijanbari Block, PHED, Darjeeling Division, GTA. | 976/NKWSMD | 18/06/2024 | 60 | TULSI NIROLA | 32.99 | 0 | 0 | 100
1692 | DARJEELING | Neorakhola W/S & Mtc.Div. | LAMAGAON PIPED WATER SUPPLY SCHEME. , SM/15868 | New | Providing Functional Household tap Connection under JJM & JSP Programme for Balance Household at Jhepi & Gurdung in Lamagaon under Darjeeling Division : PHED-GTA. | 878/NKWSMD | 03/08/2023 | 350 | NARAYAN SUBBA | 33.7 | 0 | 0 | 100
1693 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme , SM/16141 | New | Material Requisition To Resource Division | 202/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.46 | 0 | 0 | 0
1694 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme , SM/16141 | New | WATER SUPPLY SCHEME FOR CHEGRA KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 184/NKWSMD | 04/05/2023 | 540 | GREEN VALLEY CONSTRUCTION | 323.03 | 0 | 0 | 50
1695 | DARJEELING | Neorakhola W/S & Mtc.Div. | CHEGRA KHASMAHAL Piped Water Supply Scheme , SM/16141 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2024 TO 31.10.2024. | 1537/NKWSMD | 30/08/2024 | 61 | QRT SECURITY AND MANPOWER SERVICE | 0.39 | 0 | 0 | 80
1696 | DARJEELING | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. , SM/15879 | New | Material Requisition To Resource Division | 446/NKWSMD | 07/06/2023 | 0 | Resource Division | 4.21 | 0 | 0 | 0
1697 | DARJEELING | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. , SM/15879 | New | Laying of additional pipeline for Augmentation scheme for Bijanbari Bazar under Darjeeling Division: PHED-GTA. | 877/NKWSMD | 03/08/2023 | 60 | TULSI NIROLA | 40.01 | 0 | 0 | 50
1698 | DARJEELING | Neorakhola W/S & Mtc.Div. | RELLING PIPED WATER SUPPLY SCHEME. , SM/15879 | New | WATER SUPPLY SCHEME FOR RELLING PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 426/NKWSMD | 06/06/2023 | 365 | NIMA SHERPA | 857.26 | 0 | 0 | 55
1699 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18634 | New | Material Requisition To Resource Division | 974/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.01 | 0 | 0 | 0
1700 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18634 | New | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | BP-2024-25-87 | 08/07/2024 | 0 | WBSEDCL | 7.65 | 0 | 0 | 0
1701 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PWSS,IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. , SM/18634 | New | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | 892/NKWSMD | 07/08/2023 | 545 | M/S BALAJI CONSTRUCTIONS | 1180.95 | 0 | 0 | 96
1702 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | Material Requisition To Resource Division | 2233/SWSD | 06/01/2023 | 0 | Resource Division | 199.97 | 0 | 0 | 0
1703 | DARJEELING | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1578/NMD | 08/09/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 34.71 | 0 | 0 | 85
1704 | DARJEELING | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | New Service Connection Charge for AUG. OF RANIDANGA RANGAPANI, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003314400 ; Reference ID : 403144139] | BP/23-24/281 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.2 | 0 | 0 | 0
1705 | DARJEELING | Northern Mechanical | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | New Service Connection Charge for RANIDANGA RANGAPANI (AUG), T under PHANSIDEWA CCC , [APPLICATION NO. 4003282303, Reference ID : 403118284] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.85 | 0 | 0 | 0
1706 | DARJEELING | Central Drilling | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1707 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME , SM/18637 | Augmentation | Construction of 2 Nos. 250 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants , Boundary Walls including Functional Household Tap Connections for Augmentation of RANIDANGA AND RANGAPANI Piped Water Supply Scheme (Zone -I and Zone - II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | 1240/SWSD | 16/08/2023 | 535 | THE MAHADEV CONSTRUCTION | 1148.16 | 0 | 0 | 42
1708 | DARJEELING | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme , SM/09449 | New | HATTA WATER SUPPLY SCHEME FROM PAL MAJUA KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT- DARJEELING. | 621/NKWSMD | 21/02/2022 | 150 | HARI PRASAD CHETTRI | 303.02 | 0 | 0 | 100
1709 | DARJEELING | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme , SM/09449 | New | Material Requisition To Resource Division | 828/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
1710 | DARJEELING | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme , SM/09449 | New | Material Requisition To Resource Division | 1266/NKWSMD | 05/09/2022 | 0 | Resource Division | 1.91 | 0 | 0 | 0
1711 | DARJEELING | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme , SM/09449 | New | Additional work for Hatta water supply scheme under Darjeeling Pulbazar Block, P.H.E. Dte. Darjeeling Division, G.T.A. | 1530/NKWSMD | 14/12/2023 | 270 | MADAN KUMAR CHHETRI | 9.15 | 0 | 0 | 100
1712 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/18821 | New | ADDITIONAL WORK FOR PUBUNG PIPED WATER SUPPLY SCHEME UNDER BLOCK- JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING | 630/NKWSMD | 05/05/2025 | 90 | MAHAKAL ENTERPRISES | 28.61 | 0 | 0 | 95
1713 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVETY BASED WATER SUPPLY SCHEME FOR PUBONG PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/18821 | New | WATER SUPPLY SCHEME FOR PUBONG PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DISTRICT DARJEELING. | 1372/NKWSMD | 22/11/2023 | 605 | SHAKTI CONSTRUCTION | 1221.09 | 0 | 0 | 100
1714 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18822 | New | Material Requisition To Resource Division | 1172/NKWSMD | 05/10/2023 | 0 | Resource Division | 14.44 | 0 | 0 | 0
1715 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18822 | New | Preparation of draft proposal including preparation of maps in KML file , DGPS Map ,SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 02 (two) number of scheme under JJM (Jal Jeevan Mission). | 1596/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 0 | 100
1716 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18822 | New | WATER SUPPLY SCHEME FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | 1099/NKWSMD | 21/09/2023 | 455 | VINAYAK CONSTRUCTION | 3433.58 | 0 | 0 | 50
1717 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR DOOTERIA PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI - I, DISTRICT : DARJEELING , SM/18822 | New | ADDITIONAL WORK FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING, KURSEONG DIVISION PHED/GTA. | 653/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 263.39 | 0 | 0 | 0
1718 | DARJEELING | Neorakhola W/S & Mtc.Div. | AUGMENTATION OF GARIDHORA (M.BARI) TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/18880 | Augmentation | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 0 | 30
1719 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block , SM/07428 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 5.53 | 0 | 0 | 0
1720 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block , SM/07428 | Retrofitting | Material Requisition To Resource Division | 895/SWSD | 24/08/2021 | 0 | Resource Division | 5.77 | 0 | 0 | 0
1721 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block , SM/07428 | Retrofitting | Resources payment for Different Water Supply Scheme | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0 | 0
1722 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block , SM/07428 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of OCTOBER(18/10/24 to 29/10/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-127 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.26 | 0 | 0 | 0
1723 | DARJEELING | Siliguri W/S Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal swapno Programme for Dumriguri-3, Airportmore, Asok Nagar & College Para Habitation of Dumriguri Piped W/S Supply Scheme ( Part-A ) at Naxalbari Block , SM/07428 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August (01/08/24 to 13/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-126 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.34 | 0 | 0 | 0
1724 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) , SM/07032 | Retrofitting | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Pathoria Ramprasad Sing Rup Sing and Sat of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | 1082/SWSD | 18/12/2020 | 30 | M/S G.C. CONSTRUCTION & CO. | 28.59 | 0 | 0 | 89
1725 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) , SM/07032 | Retrofitting | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0 | 0
1726 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Ramprasad Sing, Rup Sing and SAT Habitation of Paschim Madati Piped water Supply Scheme (Part - B) , SM/07032 | Retrofitting | Material Requisition To Resource Division | 1671/SWSD | 28/12/2021 | 0 | Resource Division | 3.17 | 0 | 0 | 0
1727 | DARJEELING | Siliguri W/S Division | Providing Functional House hold Tap Connecton under Jal Jeevan & Jal Swapno programme for Bansgaon village of Purba Bansgaon Piped water Supply Scheme , SM/07040 | Retrofitting | Providing functional household tap connection under Jal Swapno Programme for Bansgaon village of Purba Bansgaon Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. (Part-B). | 1007/SWSD | 11/12/2020 | 30 | KAMAL GHOSH | 37.26 | 35.86 | 96.26 | 100
1728 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME , SM/09427 | New | Material Requisition To Resource Division | 1880/NKWSMD | 15/12/2022 | 0 | Resource Division | 10.08 | 0 | 0 | 0
1729 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME , SM/09427 | New | Material Requisition To Resource Division | 2568/NKWSMD | 17/02/2023 | 0 | Resource Division | 10.08 | 0 | 0 | 0
1730 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME , SM/09427 | New | Material Requisition To Resource Division | 1270/NKWSMD | 05/09/2022 | 0 | Resource Division | 10.06 | 0 | 0 | 0
1731 | DARJEELING | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME , SM/09427 | New | RIMBICK WATER SUPPLY SCHEME FROM PARTHAM KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT-DARJEELING | 8/NKWSMD | 04/04/2022 | 180 | NIMA SHERPA | 598.72 | 0 | 0 | 95
1732 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] , SM/10258 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for upper and lower Majuwa, Rangbhang from GairiBass and Gairi Jhora source under Jorebunglo w Su khiapo lhri Block under Darjeeling PHED" | BP-2022-23-89 | 14/07/2022 | 0 | MOHAN MUKHIA | 4.34 | 0 | 0 | 0
1733 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] , SM/10258 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan M ission and Jal Swapno Pro gramme for Pip e Water Supply Scheme for Sukhia Pokhri Bajar and adjoining area (Augmentation, Extension and Reparing) Darjeeling Div ision.P HED.G .T.A" | BP-2022-23-32 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 41.26 | 0 | 0 | 0
1734 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] , SM/10258 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0 | 0
1735 | DARJEELING | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] , SM/10258 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0 | 0
1736 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (2 Nos.) under GTA. [Volume No-II] , SM/10258 | Retrofitting | RESTORATION OF ROAD SIDE DRAIN UNDER PWD | BP-2022-23-234 | 20/12/2022 | 0 | PWD | 3.95 | 0 | 0 | 0
1737 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Material Requisition To Resource Division | 2023/SWSD | 16/12/2022 | 0 | Resource Division | 52.56 | 0 | 0 | 0
1738 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 0 | 100
1739 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Material Requisition To Resource Division | 1457/SWSD | 29/09/2022 | 0 | Resource Division | 2.35 | 0 | 0 | 0
1740 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Temporary hiring 01 (one) nos. maxi cab with driver for official screening cum enquiry at Kalimpong in favour of Deputy Superintending Engineer, North Bengal Circle-I PHE Dte.& his team | BP-2023-24-64 | 28/09/2023 | 0 | SUDIP BASAK | 0.07 | 0 | 0 | 0
1741 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Construction of rig bore big dia deep tube well 4 (four) nos. by ODEX-165 method of drilling of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 648/SWSD | 15/06/2023 | 30 | BUDDHADEV NAG | 30.05 | 0 | 0 | 75
1742 | DARJEELING | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, under PHANSIDEWA CCC [APPLICATION NO. 4003289610 ; Reference ID : 403124950] | BP/23-24/200 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
1743 | DARJEELING | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, T/W No. III, under PHANSIDEWAI CCC [APPLICATION NO.4003294308 ; Reference ID : 403128805] | BP/23-24/218 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.3 | 0 | 0 | 0
1744 | DARJEELING | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | New Service Connection Charge for BANDARGACHA, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO.4003298928 ; Reference ID : 403128850] | BP/23-24/219 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0 | 0
1745 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Construction of Pump House (4 Nos.) (5.4 X 3.60) size with (1.35 X 2.10 m) size with toilet. Plinth protection etc. installation of IEP and boundary wall at Zone-II, Zone-III, Zone-IV & Zone-V of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | 647/SWSD | 15/06/2023 | 1021 | BUDDHADEV NAG | 91.93 | 0 | 0 | 30
1746 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Construction of 250 cu.m. capacity R.C.C. Overhead Reservoir, 20 mtrs. Staging height including laying distribution system and allied with providing functional household tap connection (FHTC) at distribution pipeline of BANDARGACHH and adjoining mouza's water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. A. | 817/SWSD | 19/07/2022 | 1321 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 441.79 | 0 | 0 | 25
1747 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Acceptance cum Work Order for Additional Laying distribution system for (Z-V) allied with functional house hold tap connection (FHTC) at Augmentation of Bandargachh and Adjoining Mouzas Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | 1243/SWSD | 24/04/2025 | 45 | SHRI ANNAPURNA DISTRIBUTORS | 48.42 | 0 | 0 | 0
1748 | DARJEELING | Northern Mechanical | AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME , SM/10714 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1752/NMD | 31/10/2023 | 530 | SUBODH KUMAR BANIK | 32.74 | 0 | 0 | 100
1749 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay , SM/10780 | Retrofitting | Material Requisition To Resource Division | 1256/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0 | 0
1750 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection with pipeline retrofitting under JSP Programme for PWSS for Upper Bansbotay , SM/10780 | Retrofitting | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Bansbotay, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009477 SM Code-SM/08923 | 592/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.66 | 0 | 0 | 100
1751 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden , SM/10837 | New | Material Requisition To Resource Division | 1257/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.98 | 0 | 0 | 0
1752 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden , SM/10837 | New | PIPED WATER SUPPLY SCHEME FOR 4th DIVISION: PHUBTSHERING TEA GARDEN UNDER JAL SWAPNO PROGRAMME. | 614/NKWSMD | 26/05/2022 | 814 | KAMAKHYA ENTERPRISES | 92.66 | 0 | 0 | 100
1753 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden , SM/10837 | New | WBSEDCL4003424527 | BP-2024-25-447 | 28/11/2024 | 0 | WBSEDCL | 0 | 0 | 0 | 0
1754 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection existing PWSS at Bunkulung , SM/11391 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bungkulung G.P - Dhuptin, Block-Mirik. | 940 /NKWSMD | 12/07/2022 | 716 | KAMAL PRADHAN | 27.91 | 0 | 0 | 98
1755 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam , SM/11393 | Retrofitting | Material Requisition To Resource Division | 766/NKWSMD | 19/07/2023 | 0 | Resource Division | 8.61 | 0 | 0 | 0
1756 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam , SM/11393 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Glenburn Singritam, Gram Panchayat - Singritam, Block - Rangli Rangliot. | 686/NKWSMD | 12/07/2023 | 269 | PUSHKAR GURUNG | 166.03 | 0 | 0 | 92
1757 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Lower Bish Acre, Ghayabari. , SM/11397 | New | Material Requisition To Resource Division | 2585/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.49 | 0 | 0 | 0
1758 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Lower Bish Acre, Ghayabari. , SM/11397 | New | Material Requisition To Resource Division | 2073/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
1759 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Lower Bish Acre, Ghayabari. , SM/11397 | New | WATER SUPPLY SCHEME FOR GAYABARI BISHACRE (LOWER) UNDER DARJEELING DISTRICT. | 2002/NKWSMD | 23/12/2022 | 930 | KAMAL PRADHAN | 65.73 | 0 | 0 | 100
1760 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. , SM/11398 | New | Material Requisition To Resource Division | 2560/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.39 | 0 | 0 | 0
1761 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. , SM/11398 | New | SURFACE WATER BASED PUNKHABARI PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | 2351/NKWSMD | 01/02/2023 | 700 | SHAKTI CONSTRUCTION | 298.42 | 0 | 0 | 100
1762 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Punkhabari under Kurseong Sub - Division, PHED, GTA. , SM/11398 | New | Augmentation of Surface Water Based Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kurseong Block in Functional Household Tap Connection in Kurseong Block within Darjeeling District under Kurseong Division, PHED-G.T.A. | 1167/NKWSMD | 04/07/2024 | 210 | SHAKTI CONSTRUCTION | 36.03 | 0 | 0 | 100
1763 | DARJEELING | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , SM/11777 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bhujia Banir Chhat Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 275/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.35 | 0 | 0 | 100
1764 | DARJEELING | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , SM/11777 | New | Material Requisition To Resource Division | 2027/SWSD | 16/12/2022 | 0 | Resource Division | 2.18 | 0 | 0 | 0
1765 | DARJEELING | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , SM/11777 | New | Laying distribution system along with boring of new tubewell, construction of pump house, boundary wall and providing FHTC under JJM/Jal Swapna for BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri Sub Division, P.H.E. Dte. | 2093/SWSD | 22/12/2022 | 75 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 91.05 | 0 | 0 | 0
1766 | DARJEELING | Siliguri W/S Division | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , SM/11777 | New | Material Requisition To Resource Division | 1465/SWSD | 29/09/2022 | 0 | Resource Division | 4.02 | 0 | 0 | 0
1767 | DARJEELING | Northern Mechanical | BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , SM/11777 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1379/NMD | 09/08/2023 | 30 | TAPAN BISWAS | 11.64 | 0 | 0 | 70
1768 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Bisacre Sub-Center, Soureni-II G.P. under Mirik- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 926/NKWSMD | 12/07/2022 | 30 | SUN SHINE GROUP | 2.67 | 0 | 0 | 0
1769 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Thurbo Sub-Center and Okaity Sub-Center in Paila Gaon School Dara-II G.P, under Mirik- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 966/NKWSMD | 12/07/2022 | 30 | SUN SHINE GROUP | 4.84 | 0 | 0 | 0
1770 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source Duptin Primary Health Centers, Duptin G.P, under Mirik- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 965/NKWSMD | 12/07/2022 | 30 | SUN SHINE GROUP | 3.26 | 0 | 0 | 98
1771 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Pahila Gaon Sub-Center,Paila Gaon School Dara-II G.P,under Mirik- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 967/NKWSMD | 12/07/2022 | 30 | SUN SHINE GROUP | 3.29 | 0 | 0 | 98
1772 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Mirik- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10795 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Duptin Sub-Center, under Mirik- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 964/NKWSMD | 12/07/2022 | 30 | SUN SHINE GROUP | 3.84 | 0 | 0 | 98
1773 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Chunabatti Sub-Center and Ghayabari Primary Health Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 968/NKWSMD | 12/07/2022 | 30 | KAMAKHYA CONSTRUCTION | 4.2 | 0 | 0 | 100
1774 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Ghayabari Sub-Center and Mahanadi Sub-Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 969/NKWSMD | 12/07/2022 | 30 | KAMAKHYA CONSTRUCTION | 4.44 | 0 | 0 | 100
1775 | DARJEELING | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source of Health Centers (6 nos) under Kurseong- Block in the District of Darjeeling , Under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. , SM/10785 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source to Singell Sub-Center & Giddah Pahar Sub-Center, under Kurseong- Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E Directorate, Kalimpong. | 970/NKWSMD | 12/07/2022 | 30 | KAMAKHYA CONSTRUCTION | 4.25 | 0 | 0 | 100
1776 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA , SM/10799 | New | SURFACE WATER BASED KOPCHI GAON PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 601/NKWSMD | 26/05/2022 | 778 | HIMALI CONSTRUCTION COMPANY | 47.25 | 0 | 0 | 100
1777 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Kopchey Gaon under Kurseong Sub Division ,PHED,GTA , SM/10799 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.11.2024 to 31.12.2024. | 2047/NKWSMD | 28/10/2024 | 65 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
1778 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA , SM/10806 | New | Material Requisition To Resource Division | 1316/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0 | 0
1779 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA , SM/10806 | New | Material Requisition To Resource Division | 2057/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0 | 0
1780 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA , SM/10806 | New | SURFACE WATER BASED LOWER CHISOPANI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 606/NKWSMD | 26/05/2022 | 930 | NARESH RAI | 69.92 | 0 | 0 | 100
1781 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA , SM/10808 | New | Material Requisition To Resource Division | 1259/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.47 | 0 | 0 | 0
1782 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA , SM/10808 | New | SURFACE WATER BASED TINDHARIA TEA ESTATE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 604/NKWSMD | 26/05/2022 | 240 | KARUNAMAYA ENTERPRISES | 108.97 | 0 | 0 | 80
1783 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA , SM/10808 | New | ADDITIONAL WORK FOR TINDHARIA TEA ESTATE WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED | 497/NKWSMD | 09/04/2025 | 180 | SUNIT DEEP RAI | 65.5 | 0 | 0 | 0
1784 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Material Requisition To Resource Division | 2371/NKWSMD | 03/02/2023 | 0 | Resource Division | 3.6 | 0 | 0 | 0
1785 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-385 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0 | 0
1786 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-384 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0 | 0
1787 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-383 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0 | 0
1788 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-382 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0 | 0
1789 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Quotation of WBSEDCL for electrical service connection | BP-2023-24-381 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0 | 0
1790 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
1791 | DARJEELING | Neorakhola W/S & Mtc.Div. | BARA CHENGA PIPED WATER SUPPLY SCHEME , SM/10816 | New | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 0 | 0 | 100
1792 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA , SM/10829 | New | Material Requisition To Resource Division | 59/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.5 | 0 | 0 | 0
1793 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA , SM/10829 | New | ADDITIONAL WORK FOR SURFACE WATER BASED TOROYOK KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION ((FHTC) IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | 638/NKWSMD | 05/05/2025 | 90 | SURAJMULL PRABHUDAYAL | 22.11 | 0 | 0 | 100
1794 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. , SM/11320 | Retrofitting | Material Requisition To Resource Division | 1295/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.44 | 0 | 0 | 0
1795 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. , SM/11320 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty (Lower kharaya and upper Kharaya Busty habitaion) under Kurseong Sub-Division PHED, GTA. | 799/NKWSMD | 30/06/2022 | 60 | SAI ENTERPRISE | 16.5 | 0 | 0 | 100
1796 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III , SM/11301 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme for including augmentatin work for PWS scheme for okaity ward no. 03 Gram panchyat PGSD-I, Block-Mirik TSM No. 009304 | 784/NKWSMD | 30/06/2022 | 60 | ROSHAN BISWAKARMA | 7.58 | 0 | 0 | 0
1797 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection Programme for PWSS scheme at Okaity Ward No-III , SM/11301 | Retrofitting | Material Requisition To Resource Division | 1312/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.28 | 0 | 0 | 0
1798 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon , SM/11304 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Ektis Goan: Gram Panchyat-Paila Goan School Dara-I, Block- Mirik TSM No. 009307 SM Code-SM/08942 | 786/NKWSMD | 30/06/2022 | 60 | PUSHKAR GURUNG | 20.13 | 0 | 0 | 0
1799 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional households Tap Connection under JSP Programme for PWS Scheme Ektish Gaon , SM/11304 | Retrofitting | Material Requisition To Resource Division | 1311/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.27 | 0 | 0 | 0
1800 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing functional household Tap connection under JSP Programme for PWS Scheme Manju Dara Gaon , SM/11307 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Manju Dara Gaon: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009483 SM Code-SM/08950 | 780/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 5.33 | 0 | 0 | 100
1801 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA , SM/11332 | Retrofitting | Material Requisition To Resource Division | 1306/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.5 | 0 | 0 | 0
1802 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA , SM/11332 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong Sub-Division P.H.E.D GTA. | 837/KWSMD | 30/06/2022 | 60 | MS JAGANNATH PRASAD | 23.75 | 0 | 0 | 100
1803 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING , SM/11890 | New | Material Requisition To Resource Division | 1888/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.24 | 0 | 0 | 0
1804 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING , SM/11890 | New | Material Requisition To Resource Division | 2607/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.24 | 0 | 0 | 0
1805 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUM TEA GARDEN PWSS. BLOCK- JORE BUNGALOW- SUKHIAPOKHRI, DISTRICT DARJEELING , SM/11890 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUN TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | 1449/NKWSMD | 29/09/2022 | 850 | SRINIWAS AGARWAL | 748.35 | 0 | 0 | 99
1806 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12736 | New | Material Requisition To Resource Division | 1896/NKWSMD | 15/12/2022 | 0 | Resource Division | 6.1 | 0 | 0 | 0
1807 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12736 | New | Material Requisition To Resource Division | 2612/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.1 | 0 | 0 | 0
1808 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR MIM TEA GARDEN PWSS, BLOCK : JORE BUNGALOW SUKHIAPOKHRI, DISTRICT : DARJEELING , SM/12736 | New | Water Supply Scheme for MIM Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. | 1618/NKWSMD | 03/11/2022 | 360 | GARGO TRADERS | 1270.33 | 0 | 0 | 95
1809 | DARJEELING | Neorakhola W/S & Mtc.Div. | Providing household tap connection from existing scheme at Museykhola & Dokan Dhura , SM/11818 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Musey Khola Gaon, Dokan Dhura. School Dhura Gram Panchayat - Maneydanra, Block - Rungli Rungliot. | 1306/NKWSMD | 31/10/2023 | 792 | JANG BAHADUR GURUNG | 46.23 | 0 | 0 | 100
1810 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11347 | New | Material Requisition To Resource Division | 2064/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.59 | 0 | 0 | 0
1811 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Jholy Busty,Latpanchor Sittong III GP with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11347 | New | PWS Scheme at Jholy Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 954/NKWSMD | 12/07/2022 | 60 | BIRU KHAWAS | 38.21 | 0 | 0 | 100
1812 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. , SM/11353 | New | Material Requisition To Resource Division | 2065/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1813 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. , SM/11353 | New | PWS Scheme at Sittong - III Naspatti Gaon with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | 953/NKWSMD | 12/07/2022 | 240 | MS. SURYA I PVT. LTD COMPANY | 62.8 | 0 | 0 | 82
1814 | DARJEELING | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bansgaon Mangachh Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | 267/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.23 | 0 | 0 | 100
1815 | DARJEELING | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Material Requisition To Resource Division | 1951/SWSD | 07/12/2022 | 0 | Resource Division | 2.58 | 0 | 0 | 0
1816 | DARJEELING | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Laying distribution system allied with functional house hold tap connection (FHTC) including boring of new tube well and Iron elimination plant under JJM at BANSGAON MANGACHH and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | 2656/SWSD | 02/03/2023 | 105 | CUBES 'N' PYRAMIDS | 119.4 | 0 | 0 | 10
1817 | DARJEELING | Siliguri W/S Division | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Material Requisition To Resource Division | 1466/SWSD | 29/09/2022 | 0 | Resource Division | 1.33 | 0 | 0 | 0
1818 | DARJEELING | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | New Service Connection Charge for BANSGAON MANGACHH, T.W. No. I under PHANSIDEWA CCC, [APPLICATION NO. 4003194676, Reference ID : 403046883] | BP/23-24/75 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.07 | 0 | 0 | 0
1819 | DARJEELING | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Additional Charges For New service connection At BANSHGAON MANGACHH Water Supply scheme Under NMD, PHE Dte. Application No -4003194676 Ref ID- 403046883 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0 | 0 | 0 | 0
1820 | DARJEELING | Northern Mechanical | BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , SM/11785 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1376/NMD | 09/08/2023 | 784 | M/S DILIP MITRA | 10.61 | 0 | 0 | 90
1821 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/13571 | New | Material Requisition To Resource Division | 2746/NKWSMD | 06/03/2023 | 0 | Resource Division | 7.15 | 0 | 0 | 0
1822 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/13571 | New | WATER SUPPLY SCHEME FOR MOONDA KOTTE TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | 2734/NKWSMD | 03/03/2023 | 545 | SRINIWAS AGARWAL | 1366.07 | 0 | 0 | 70
1823 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR MOONDA KOTEE TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING. , SM/13571 | New | ADDITIONAL WORK FOR MOONDA KOTHI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING UNDER KURSEONG DIVISION PHED GTA. | 635/NKWSMD | 05/05/2025 | 90 | SRINIWAS AGARWAL | 38.65 | 0 | 0 | 0
1824 | DARJEELING | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Material Requisition To Resource Division | 2036/SWSD | 16/12/2022 | 0 | Resource Division | 15.11 | 0 | 0 | 0
1825 | DARJEELING | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF CHUCHUR MUCHUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | 252/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.71 | 0 | 0 | 100
1826 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. II under KHARIBARI CCC, [APPLICATION NO. 4003193651, Reference ID : 403046162] | BP/23-24/78 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0 | 0
1827 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193712, Reference ID : 403046161] | BP/23-24/78 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0 | 0
1828 | DARJEELING | Siliguri W/S Division | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Construction of Pump House 2 Nos. Rig Bord 2 nos. big dia T/W by Odex-165 method, Boundary walls, Laying distribution system HDPE pipe, rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (three) month trial run IEP (20 cu.m./hr) and allied works for Augmentation of Chuchur Muchur PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | 2576/SWSD | 23/02/2023 | 105 | UJJWAL ROY | 142.67 | 0 | 0 | 95
1829 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHUCHUR MUCHUR PWSS , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 644/NMD | 29/05/2023 | 30 | PRATIK ROY | 23.35 | 0 | 0 | 100
1830 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0 | 0
1831 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0 | 0
1832 | DARJEELING | Northern Mechanical | Augmentation of Chuchur Muchur Piped Water Supply Scheme , SM/13427 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1833 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/13042 | New | Material Requisition To Resource Division | 1894/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.56 | 0 | 0 | 0
1834 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/13042 | New | Material Requisition To Resource Division | 2608/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.56 | 0 | 0 | 0
1835 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/13042 | New | WATER SUPPLY SCHEME FOR PARMAGURI KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | 1454/NKWSMD | 29/09/2022 | 300 | MADAN SHARMA | 1011.5 | 0 | 0 | 99
1836 | DARJEELING | Neorakhola W/S & Mtc.Div. | GRAVITY BASED WATER SUPPLY SCHEME FOR PARAMAGURI KHASMAHAL PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI , DISTRICT : DARJEELING , SM/13042 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.08.2024 to 31.08.2024 | 1347/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.2 | 0 | 0 | 100
1837 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Material Requisition To Resource Division | 208/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0 | 0
1838 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | CONSTRUCTION OF HOUSE HOLD TAP CONNECTION (FHTC) AT DIFFERENT MOUZAS UNDER DIFFERENT PIPED WATER SUPPLY SCHEME (PART -C) IN CONNECTION WITH JAL JEEVAN MISSION UNDER SILIGURI W/S DIVISION P.H.E Dte. | 364./SSD | 10/08/2023 | 45 | SEBU CHAKRABORTY | 0.98 | 0 | 0 | 100
1839 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Construction of household tap connection (FHTC)at different mouzas under different piped water supply scheme (Part A) in connection with Jal Jeevan Mission under Siliguri W/S Division P.H.E DTE. | 364/SSD | 10/08/2023 | 45 | SEBU CHAKRABORTY | 0.98 | 0 | 0 | 100
1840 | DARJEELING | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Quotation for new service connection at Damdama w/s scheme T.W N0_ I in the dist. Darjeeling | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.81 | 0 | 0 | 0
1841 | DARJEELING | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1381/NMD | 09/08/2023 | 602 | ASHWIRBAD WOOD CRAFT | 10.38 | 0 | 0 | 85
1842 | DARJEELING | Siliguri W/S Division | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Acceptance cum work order for Laying of rising main, distribution system of pipe line, construction of pump house, boundary wall, sinking of rig bore deep tube well by ODEX-165 method of drilling, development of land and othar works for Augmentation of Damdama nPiped W/S Scheme within Naxalbari Block under Siliguri Sub Division, P.H.E. Dte. | 1903/SWSD | 11/10/2023 | 535 | K.K.GHOSH & CO. | 31.94 | 0 | 0 | 85
1843 | DARJEELING | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0 | 0
1844 | DARJEELING | Northern Mechanical | AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME , SM/14835 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0 | 0
1845 | DARJEELING | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Khunia Pukhari Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | 264/SSD | 18/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.87 | 0 | 0 | 0
1846 | DARJEELING | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Material Requisition To Resource Division | 210/SWSD | 25/04/2023 | 0 | Resource Division | 29.44 | 0 | 0 | 0
1847 | DARJEELING | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME, TW No.- I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1581/NMD | 08/09/2023 | 30 | S.G.TECHNICAL SERVICES | 13.8 | 0 | 0 | 0
1848 | DARJEELING | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Material Requisition To Resource Division | 70/SWSD | 10/01/2024 | 0 | Resource Division | 17.92 | 0 | 0 | 0
1849 | DARJEELING | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | New Service Connection Charge for KHUNIA PUKHORI, T/W No. I, under KADAMTALA CCC, [APPLICATION NO. 4003320147, Reference ID : 403147072] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.72 | 0 | 0 | 0
1850 | DARJEELING | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | New Service Connection Charge for KHUNIA PUKHORI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003320195, Reference ID : 403147070] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.82 | 0 | 0 | 0
1851 | DARJEELING | Northern Mechanical | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Additional Charges For New service connection at Khunia Pukhori pwss TW-II under NMD PHE Dte. Application no- 4003320195 Ref id- 860301418 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
1852 | DARJEELING | Central Drilling | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1853 | DARJEELING | Siliguri W/S Division | KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME , SM/14846 | New | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump Houses 2 Nos., Blower Room, IEP 70 cu.m./hr., Boundary Walls, Soil Testing and allied works at KHUNIA PUKHARI PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. | 1211/SWSD | 11/08/2023 | 782 | THE TEESTA CONSTRUCTION | 667.04 | 0 | 0 | 70
1854 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13960 | New | Material Requisition To Resource Division | 2603/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.22 | 0 | 0 | 0
1855 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13960 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1856 | DARJEELING | Neorakhola W/S & Mtc.Div. | DETAILED PROJECT REPORT FOR WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/13960 | New | WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 2003/NKWSMD | 23/12/2022 | 180 | SRINIWAS AGARWAL | 280.33 | 0 | 0 | 80
1857 | DARJEELING | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dalkajhar Forest Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 273/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.26 | 0 | 0 | 100
1858 | DARJEELING | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Material Requisition To Resource Division | 2052/SWSD | 16/12/2022 | 0 | Resource Division | 0.87 | 0 | 0 | 0
1859 | DARJEELING | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Material Requisition To Resource Division | 61/SWSD | 09/01/2024 | 0 | Resource Division | 0.94 | 0 | 0 | 0
1860 | DARJEELING | Northern Mechanical | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Quotation for new service Connection at T.W No- I of Dalkajhar Forest w/s scheme. | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
1861 | DARJEELING | Siliguri W/S Division | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Laying of distribution pipeline and Rising Main allied with construction of 1 no. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.60 m), Iron Elimination Plant (10 cu.m./hr.), Boundary Wall including FHTC at DALKAJHAR FOREST Piped Water Supply Scheme under Naxalbari block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division,, P.H.E. Dte. | 1041/SWSD | 27/07/2023 | 900 | SUDIP BASAK | 59.15 | 0 | 0 | 50
1862 | DARJEELING | Northern Mechanical | DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , SM/13439 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1374/NMD | 09/08/2023 | 604 | SAIKAT SINHA | 10.66 | 0 | 0 | 100
1863 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/14149 | New | Material Requisition To Resource Division | 2558/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.83 | 0 | 0 | 0
1864 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/14149 | New | Material Requisition To Resource Division | 2715/NKWSMD | 03/03/2023 | 0 | Resource Division | 5.83 | 0 | 0 | 0
1865 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/14149 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1866 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/14149 | New | WATER SUPPLY SCHEME FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 2520/NKWSMD | 15/02/2023 | 1275 | VINAYAK CONSTRUCTION | 1768.52 | 0 | 0 | 85
1867 | DARJEELING | Neorakhola W/S & Mtc.Div. | PROJECT REPORT FOR WATER SUPPLY SCHEME FOR GIDDA PAHAR PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. , SM/14149 | New | ADDITIONAL WORK FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME UNDER BLOCK KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED-GTA. | 651/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 61.66 | 0 | 0 | 0
1868 | DARJEELING | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS , SM/15910 | New | Material Requisition To Resource Division | 812/NKWSMD | 24/07/2023 | 0 | Resource Division | 3.42 | 0 | 0 | 0
1869 | DARJEELING | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS , SM/15910 | New | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.09.2024 to 31.10.2024. | 1550/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 0 | 100
1870 | DARJEELING | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS , SM/15910 | New | WATER SUPPLY SCHEME FOR BLOOMFIELD PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | 720/NKWSMD | 18/07/2023 | 540 | HARI PRASAD CHETTRI | 369.22 | 0 | 0 | 100
1871 | DARJEELING | Neorakhola W/S & Mtc.Div. | BLOOMFIELD TEA GARDEN PWSS , SM/15910 | New | Additional work of Piped Water Supply Scheme for Bloomfield Tea Garden Piped Water Supply Scheme in Pulbazar Block under Darjeeling District. | 966/NKWSMD | 14/06/2024 | 198 | HARI PRASAD CHETTRI | 59.7 | 0 | 0 | 100
1872 | DARJEELING | Neorakhola W/S & Mtc.Div. | RESHOP BAZAR PIPED WATER SUPPLY SCHEME , SM/15882 | New | Material Requisition To Resource Division | 214/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.11 | 0 | 0 | 0
1873 | DARJEELING | Neorakhola W/S & Mtc.Div. | RESHOP BAZAR PIPED WATER SUPPLY SCHEME , SM/15882 | New | WATER SUPPLY SCHEME FOR RESHOP BAZAR PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | 123/NKWSMD | 28/04/2023 | 605 | VAISHNO CONSTRUCTION | 416.96 | 0 | 0 | 100
1874 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BAIRAGI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15855 | Solarisation | Quotation Charges for Net Metering connection at BAIRAGI Piped Water Supply Scheme under PHE Dte. APPLICATION NO - 4003519948 CONSUMER ID- 402256109 | BP/24-25/244 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1875 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BAIRAGI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15855 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1876 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/16532 | New | Material Requisition To Resource Division | 248/NKWSMD | 12/05/2023 | 0 | Resource Division | 7.85 | 0 | 0 | 0
1877 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR OKATIY TEA GARDEN PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/16532 | New | WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | BP-2024-25-172 | 01/08/2024 | 0 | WBSEDCL | 50.95 | 0 | 0 | 0
1878 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15860 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1879 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kilaram Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | 251/SSD | 12/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.36 | 0 | 0 | 0
1880 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Material Requisition To Resource Division | 205/SWSD | 25/04/2023 | 0 | Resource Division | 67.51 | 0 | 0 | 0
1881 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Material Requisition To Resource Division | 2290/SWSD | 11/12/2023 | 0 | Resource Division | 2.9 | 0 | 0 | 0
1882 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging height at head works site, laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), construction of three numbers Pump House (5.40 m X 3.60 m), 2 (two) nos. Iron Elimination Plant (IEP) with Blower Room Sinking of 3 (three) nos. Tube Well (ODEX-165 method) and Boundary Wall for KILARAM PWSS (Zone-I & II), Block Naxalbari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte | 1159/SWSD | 09/08/2023 | 240 | RAMESH KUMAR AGARWAL & CO | 645.57 | 0 | 0 | 55
1883 | DARJEELING | Siliguri W/S Division | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Material Requisition To Resource Division | 74/SWSD | 10/01/2024 | 0 | Resource Division | 13.27 | 0 | 0 | 0
1884 | DARJEELING | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. I, under NAXALBARI CCC, [APPLICATION NO. 4003313640, Reference ID : 403145711] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.56 | 0 | 0 | 0
1885 | DARJEELING | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003313623, Reference ID : 403145716] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0 | 0
1886 | DARJEELING | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | New Service Connection Charge for KILARAM, T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313552, Reference ID : 403145729] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0 | 0
1887 | DARJEELING | Central Drilling | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1888 | DARJEELING | Northern Mechanical | KILARAM PIPED WATER SUPPLY SCHEME ( ZONE-I & II ) , SM/16753 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KILARAM PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II and (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | 1658/NMD | 29/09/2023 | 460 | B.B. CONCERNED | 27.15 | 0 | 0 | 100
1889 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden , SM/15651 | New | Material Requisition To Resource Division | 2727/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.33 | 0 | 0 | 0
1890 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden , SM/15651 | New | Material Requisition To Resource Division | 2778/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.33 | 0 | 0 | 0
1891 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden , SM/15651 | New | SURFACE WATER BASED SEPOYDHURA (ST MARYS -I) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | 2706/NKWSMD | 02/03/2023 | 760 | SHAKTI CONSTRUCTION | 442.13 | 0 | 0 | 90
1892 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Sepoy Dhura Tea Garden , SM/15651 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOY DHURA TEA GARDEN IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | 633/NKWSMD | 05/05/2025 | 180 | MS CHAMLING CONSTRUCTION | 66.89 | 0 | 0 | 0
1893 | DARJEELING | Neorakhola W/S & Mtc.Div. | MONGPOO CINKONA PLANTATION, ROLAK & LONKU KHASMAHAL PWSS , SM/17191 | New | MONGPOO CINKONA PLANTATION PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME. | 98/NKWSMD | 28/04/2023 | 830 | VAISHNO CONSTRUCTION | 230.27 | 0 | 0 | 100
1894 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Edenvale Tea Garden , SM/18710 | New | Material Requisition To Resource Division | 1298/NKWSMD | 30/10/2023 | 0 | Resource Division | 0.67 | 0 | 0 | 0
1895 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Edenvale Tea Garden , SM/18710 | New | SURFACE WATER BASED EDENVALE TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | 894/NKWSMD | 07/08/2023 | 180 | YAMA CONSTRUCTIONS LLP | 139.48 | 0 | 0 | 50
1896 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11348 | New | Material Requisition To Resource Division | 2813/NKWSMD | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0 | 0
1897 | DARJEELING | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. , SM/11348 | New | PIPED WATER SUPPLY SCHEME AT LOWER SIRUBARI WITH FUNCTIONAL HOUSEHOLD TAP CONNECTION UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME UNDER KURSEONG DIVISION PHED-GTA, DARJEELING. | 1748/NKWSMD | 25/11/2022 | 60 | BITIS PRADHAN AND BROTHERS | 24.69 | 0 | 0 | 100
1898 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/18636 | New | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | 882/NKWSMD | 03/08/2023 | 365 | SHAKTI CONSTRUCTION | 1026.53 | 0 | 0 | 100
1899 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT , SM/18636 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MALUTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | 637/NKWSMD | 05/05/2025 | 60 | SURAJMULL PRABHUDAYAL | 13.02 | 0 | 0 | 100
1900 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST , SM/18559 | New | Material Requisition To Resource Division | 969/NKWSMD | 21/08/2023 | 0 | Resource Division | 4.73 | 0 | 0 | 0
1901 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST , SM/18559 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1902 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST , SM/18559 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOYDHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST UNDER KURSEONG DIVISION, PHED-GTA | 634/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 59.3 | 0 | 0 | 95
1903 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST , SM/18559 | New | SURFACE WATER BASED SEPOYDHURA (D.R.) TEA GARDEN, KHARIA BUSTY CHAITAPANI TEA GARDEN & BAMAN DHURA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | 920/NKWSMD | 11/08/2023 | 645 | SHAKTI CONSTRUCTION | 1345.85 | 0 | 0 | 50
1904 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14147 | New | Material Requisition To Resource Division | 245/NKWSMD | 12/05/2023 | 0 | Resource Division | 5.91 | 0 | 0 | 0
1905 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14147 | New | PAYMENT FOR WBSEDCL | BP-2023-24-530 | 26/02/2024 | 0 | WBSEDCL | 6.32 | 0 | 0 | 0
1906 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14147 | New | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MANJUA FOREST SOURINI-II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 595/NKWSMD | 29/04/2025 | 60 | ALLIED INSTRUMENTS | 13.7 | 0 | 0 | 0
1907 | DARJEELING | Neorakhola W/S & Mtc.Div. | WATER SUPPLY SCHEME FOR MANJUA FOREST PWSS IN MIRIK BLOCK UNDER DARJEELING DISTRICT. , SM/14147 | New | WATER SUPPLY SCHEME FOR MANJUA FOREST SOURENI -II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | 109/NKWSMD | 28/04/2023 | 635 | MAA MANASA VYAPAAR | 1093.84 | 0 | 0 | 50
1908 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal , SM/18650 | New | Material Requisition To Resource Division | 973/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0 | 0
1909 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal , SM/18650 | New | PAYMENT FOR WBSEDCL | BP-2023-24-658 | 23/03/2024 | 0 | WBSEDCL | 12.27 | 0 | 0 | 0
1910 | DARJEELING | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal , SM/18650 | New | SURFACE WATER BASED MIRIK KHASMAHAL (P) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | 918/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1224.81 | 0 | 0 | 90
1911 | DARJEELING | Neorakhola W/S & Mtc.Div. | AUGMENTATION OF PAIRIKUMARI PIPED WATER SUPPLY SCHEME , SM/18879 | Augmentation | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 0 | 30
1912 | DARJEELING | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15854 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | 783/NMD | 14/07/2023 | 869 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
1913 | DARJEELING | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE , SM/18534 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
1914 | DARJEELING | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE , SM/18534 | New | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 5 Mouzas in Kurseong Block within Darjeeling District under Kurseong Division, P.H.E.D- GTA. | 100/NKWSMD | 15/01/2024 | 765 | INTERIOR'S NEST | 2672.64 | 0 | 0 | 35
1915 | DARJEELING | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE , SM/18534 | New | ADDITIONAL WORK FOR GROUND WATER RESERVOIR HAVING CAPACITY OF 20 ML AT DURPIN LAKE TO ACCOMMODATE 5 MOUZAS IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | 826/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 318.4 | 0 | 0 | 0
1916 | DARJEELING | Neorakhola W/S & Mtc.Div. | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. , SM/11729 | Support-MIS | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. | BP-2022-23-285 | 17/01/2023 | 0 | IONET | 3.92 | 0 | 0 | 0
1917 | DARJEELING | Neorakhola W/S & Mtc.Div. | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. , SM/11729 | Support-MIS | DPR for Supply, Delivery and Installation of Desktops Computers, UPS, Scanner, Printer, etc. through Gem portal for Office of the Executive Engineer under Kurseong Division, PHE Dte. | BP-2022-23-286 | 17/01/2023 | 0 | IONET | 6.74 | 0 | 0 | 0
1918 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | SUPPLY FOR brother Multifunction MachinesMfm, On Site OEM Warranty 3 Year |  | 19/04/2023 | 0 | IONET | 1.07 | 0 | 0 | 0
1919 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | SUPPLY FOR Canon Multifunction Machines Mfm, On Site OEM Warranty 3 Year | BP-2023-24-36 | 10/05/2023 | 0 | IONET | 1.24 | 0 | 0 | 0
1920 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | SUPPLY FOR hp Multifunction Machines Mfm, On Site OEM Warranty 5 Year | BP-2023-24-37 | 10/05/2023 | 0 | IONET | 0.93 | 0 | 0 | 0
1921 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | supply for brother Multifunction Machines Mfm, On Site OEM Warranty 3 Year | BP-2023-24-39 | 10/05/2023 | 0 | IONET | 0.42 | 0 | 0 | 0
1922 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | SUPPLY FOR brother Multifunction MachinesMfm, On Site OEM Warranty 3 Year | BP-2023-24-35 | 10/05/2023 | 0 | IONET | 1.01 | 0 | 0 | 0
1923 | DARJEELING | Neorakhola W/S & Mtc.Div. | Supply Delivery and Installation of computer & peripheral for official use under the office of Executive Engineer Darjeeling Division: PHED:GTA , SM/12737 | Support-MIS | SUPPLY FOR hp Intel Core i5 11500 16 GB/ 1000 GB HDD/ Windows 10 Professional | BP-2023-24-38 | 10/05/2023 | 0 | EASY DAY ENTERPRISE | 4.82 | 0 | 0 | 0
1924 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687779926941, dated 18-01-2023] | BP/23-24/52&53 | 11/07/2023 | 0 | IONET | 3.6 | 0 | 0 | 0
1925 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687782155228, dated 28-02-2023] | BP/23-24/25 | 01/06/2023 | 0 | IONET | 0.93 | 0 | 0 | 0
1926 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687791085337, dated 06-02-2023] | BP/23-24/52 | 11/07/2023 | 0 | IONET | 4.54 | 0 | 0 | 0
1927 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687703978456, dated 01-03-2023] | BP/23-24/23 | 01/06/2023 | 0 | IONET | 0.24 | 0 | 0 | 0
1928 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687791255110, dated 12-02-2023] | BP/23-24/24 | 01/06/2023 | 0 | EASY DAY ENTERPRISE | 4.82 | 0 | 0 | 0
1929 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687765279624, dated 02-04-2023] | BP/23-24/23 | 01/06/2023 | 0 | IONET | 0.84 | 0 | 0 | 0
1930 | DARJEELING | Northern Mechanical | Supply, Delivery and Installation of Computer & peripherals for official use under Office Of the CE(M/E), N.Z. , Office Of the SE , MC-IV & Office of the EE, NMD , PHE Dte . , SM/14065 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals for official use under Office of the CE(M/E), N.Z., Office of the SE, MC-IV & Office of the EE, NMD, PHE Dte. [Sanction No: 511687702043447, dated 26-02-2023] | BP/23-24/23 | 01/06/2023 | 0 | IONET | 2.47 | 0 | 0 | 0
1931 | DARJEELING | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Siliguri Mahakuma Parishad (SMP) Darjeeling District. , SM/09029 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Siliguri District. | 4689/RS | 17/08/2022 | 365 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 85.07 | 0 | 0 | 75
1932 | DARJEELING | Neorakhola W/S & Mtc.Div. | Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). , SM/18270 | Support-Admin-HRD | Expression of Interest Cum Request for Proposal for Selection of consulting agency for Setting up of District Project Management Unit (DPMU) for Darjeeling (Hills) District under Jal Jeevan Mission (JJM). | 846/NKWSMD | 27/07/2023 | 397 | RADIANT | 45.14 | 0 | 0 | 100
1933 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, l'reparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2023-24-310 | 08/11/2023 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 40.36 | 0 | 0 | 0
1934 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, l'reparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2023-24-309 | 08/11/2023 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 132.52 | 0 | 0 | 0
1935 | DARJEELING | Kurseong Division | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area | 136/KD/PHED/GTA | 26/02/2021 | 1451 | RADIANT | 500 | 0 | 0 | 85
1936 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area | BP-2023-24-595 | 15/03/2024 | 0 | RADIANT | 63.8 | 0 | 0 | 0
1937 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, l'reparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2024-25-107 | 10/07/2024 | 0 | SAMARTH INFRA TECH SERVICES PRIVATE LIMITED | 34.15 | 0 | 0 | 0
1938 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, l'reparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | "BP-2023-24-660 | 28/03/2024 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 30 | 0 | 0 | 0
1939 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area | BP-2023-24-516 | 20/02/2024 | 0 | RADIANT | 23.08 | 0 | 0 | 0
1940 | DARJEELING | Resource | Preparation of piped network supply system which includes route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection, Preparation and supply of CAD-GIS/ layout of plan of the zone wise Co , SM/19010 |  | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. | 1997/RS | 03/11/2021 | 180 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
1941 | DARJEELING | Siliguri W/S Division | Operational Charges of Darjeeling District Laboratory related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19317 | Support-WQMSP | Training for skilling of manpower to generate employment opportuinities and to support implementation of Jal Swapno Programme in collaboration with PHED & Department of Technical Eduction, Training & Skill Development (TETSD) for 4 (four) Nos. Block (Matigara, Naxalbari, Phansidewa & Kharibari) of Siliguri Sub Division under Siliguri W/S Division, P.H.E. Dte. (for 7 days Training). SL. NO. 11 | 275/SWSD | 06/05/2022 | 7 | TALUKDAR ENTERPRISE | 4.91 | 0 | 0 | 50
1942 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation and Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-200 and 201 | 08/11/2022 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 24.64 | 0 | 0 | 0
1943 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2022-23-86 | 30/06/2022 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 97 | 0 | 0 | 0
1944 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area | BP-2022-23-115 | 12/08/2022 | 0 | RADIANT | 61.53 | 0 | 0 | 0
1945 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2022-23-124 | 30/08/2022 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 49.12 | 0 | 0 | 0
1946 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of DPR in line with the technical requirement of jal jiwan mission in GTA area | BP-2022-23-84 | 30/06/2022 | 0 | RADIANT | 19.77 | 0 | 0 | 0
1947 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation & Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2022-23-150 | 30/09/2022 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 47 | 0 | 0 | 0
1948 | DARJEELING | Neorakhola W/S & Mtc.Div. | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data and JJM compliant data collection ,Preparation and supply of Geo reference drawing (CAD-GIS)/ layout of plan of the zone-wise Command area of water distribution and transmission network (WD&TN) showing all requisite design (physical) features, Preparation and Submission of DPR booklet of PWSS all complete in consultation with PHED including clearance from SLSSC and SLSSFC including preparation of Bid Document in various uncovered habitations of Jore Bunglow Sukhiapokhri and other blocks of Hills in Darjeeling District Tentative number of DPR-51 Nos | BP-2022-23-198 | 08/11/2022 | 0 | SAMARTH INFRA TECH SERVICES PVT. LTD. | 72 | 0 | 0 | 0
1949 | DARJEELING | Resource | Preparation of piped network supply system which includes Route survey using DGPS/Drone/Total Station etc . & all related field work for technical data and JJM compliant data collection ,Preparation and supply of CAD-GIS/ layout of plan of the zone-wise C , SM/10732 | Support-M&E | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. | 1997/RS | 03/11/2021 | 180 | NABCONS PRIVATE LIMITED | 5500 | 0 | 0 | 80
1950 | DARJEELING | Neorakhola W/S & Mtc.Div. | Collection of Drinking Water Samples from various spot sources, PWSS, Schools, Anganwadis, Health Centres and Springs under Darjeeling Hills for water testing at Sindhap sub-district laboratory Darjeeling managed by Neorakhola water supply and maintenance , SM/15668 | Support-WQMSP | COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, P.H.ENGINEERING DIRECTORATE, KALIMPONG. | 2728/NKWSMD | 03/03/2023 | 366 | NIM TSHERING LEPCHA | 12.75 | 0 | 0 | 70
1951 | DARJEELING | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . , SM/06627 | Support-WQMSP | Supply of Labortory Instruments/Equipments for Darjeeling District Laboratory at Fulbari under Siliguri W/S Division, PHE Dte. | 2837/SWSD | 17/03/2023 | 15 | LAB SOLUTION | 0.95 | 0 | 0 | 100
1952 | DARJEELING | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . , SM/06627 | Support-WQMSP | Continuation order for Supply of Chemical, Consumables for Darjeeling District Laboratories under Siliguri Water Supply Division, PHE Dte. | 3360/SWSD | 11/12/2024 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.32 | 0 | 0 | 0
1953 | DARJEELING | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . , SM/06627 | Support-WQMSP | Continuation Order for Supply of Chemicals, Consumables for Darjeeling District Laboratories under Siliguri Water Supply Division PHE Dte. | 656/SWSD | 12/03/2024 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.22 | 0 | 0 | 0
1954 | DARJEELING | Siliguri W/S Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual Maintenance of Computer, Printer & etc. required for smooth running of the District Laboratory of Fulbari WTP . , SM/06627 | Support-WQMSP | Running of District Laboratory for Physical,Chemical and Bacteiological test of water sample under Scheme, dist Darjeeling under Siliguri W/S division, PHE Dte. 1st sept 2021 to 31st August 2022. | 939/SWSD | 14/08/2020 | 0 | TALUKDAR ENTERPRISE | 8.67 | 0 | 0 | 0
1955 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | Supply, delivery & installation of laptop HP-440g9/i7/12th/16gb I TB SSD/MINI 11PRO/14 INCHI for office of the Assistant Engineer Siliguri Siliguri w/s Division PHE Dte. | BP-2023-24-63 | 22/09/2023 | 0 | FRIENDS SOLUTION ENTERPRISES | 0.89 | 0 | 0 | 0
1956 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | SUPPLY OF DESKTOP COMPUTER 9 NOS ( CYNIX GENEX 1X3030 DESKYOP CORE i5 AND 9 NOS LED MONITOR ) FOR OFFICE OF THE EXECUTIVE ENGINEER SILIGURI W/S DIVISION PHE DTE. | BP-2023-24-131 | 29/11/2023 | 0 | JINTECH SOLUTION LTD | 3.89 | 0 | 0 | 0
1957 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | Procurement of 10 nos. HP AMD Ryzen 5 14 Inch Laptop from IONET through GEM. | BP-2024-25-86 | 11/09/2024 | 0 | IONET | 4.78 | 0 | 0 | 0
1958 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | Procurement of 1 no. Brother Multifunction Machines Mfm from Easy Day Enterprise through GEM. | BP-2024-25-81 | 02/09/2024 | 0 | EASY DAY ENTERPRISE | 0.43 | 0 | 0 | 0
1959 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | Procurement of 3 nos. Brother Multifunction Machines (Mfm) Printer from Easy Day Enterprise Through GEM. | BP-2024-25-80 | 02/09/2024 | 0 | EASY DAY ENTERPRISE | 0.76 | 0 | 0 | 0
1960 | DARJEELING | Siliguri W/S Division | Supply Delivery and Installation of Computer & Peripherals for official use for Office of the Executive Engineer, Siliguri W/S Division, under G.T.A Circle, PHE Dte. , SM/17179 | Support-MIS | Procurement of 13 nos. Brother Laser Mono Computer Printers for A4 paper size from IONET through GEM. | BP-2024-25-79 | 02/09/2024 | 0 | IONET | 1.81 | 0 | 0 | 0
Total | [9 empty] | 1027586.38 | 243.12 | 0.02