## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme , SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Pradhanpara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 221/JD | 12/02/2021 | 30 | RAGHU DAS | 23.09 | 0 | 0 | 1
2 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme , SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Sajnapara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 1543/JD | 31/12/2020 | 75 | RAGHU DAS | 39.54 | 35.7 | 99.99 | 1
3 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme , SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 6.88 | 100 | 1
4 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme , SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 23.53 | 100 | 1
5 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Sajnapara Mouza under Sajnapara Piped Water Supply Scheme , SM/06959 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | 61/RWS | 09/02/2021 | 15 | NEW KUNDU ENTERPRISE | 4.09 | 4.09 | 100 | 1
6 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 1549/JD | 31/12/2020 | 60 | CALCON CONSTRUCTIONS | 40.32 | 0 | 0 | 0
7 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 563/JSSD | 01/02/2021 | 15 | NARAYAN CHANDRA ADHIKARY | 4.44 | 4.43 | 99.61 | 0
8 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 1550/JD | 31/12/2020 | 30 | PARAMJYOTI ENTERPRISE | 12.27 | 12.26 | 99.89 | 1
9 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna of Khathiar line, Girza line and Chamru line within the command area of Jogesh Ch. T.G. PWSS at Mal Block under Jalpaiguri Division, P.H.E. Dte. (Part-C) | 730/JD | 17/03/2022 | 21 | SANDIP BANIK | 17.59 | 0 | 0 | 1
10 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 93/JD | 10/01/2022 | 60 | TECHNO CRACY | 4.65 | 0 | 0 | 100
11 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 94/JD | 10/01/2022 | 60 | DEBABRATA SARKAR | 4.64 | 0 | 0 | 100
12 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Sinking of 250 mm x 150mm dia 3rd tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 977/JD | 20/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 0 | 0 | 1
13 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Sinking of 250 mm x 150mm dia 4th tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 985/JD | 21/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 0 | 0 | 1
14 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 0 | 1
15 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 101/NMD | 03/02/2023 | 21 | BLUE PINE | 2.91 | 0 | 0 | 100
16 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | New Service Connection Charge for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 4003123385, Reference ID : 402994381] | BP/23-24/16 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
17 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Infrastructure Cost for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 100000076675, Reference ID : 860268405] | BP/23-24/16 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0 | 0
18 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Infrastructure Cost for MALLICK SOVA, T/W IV, under DHUPGURI CCC [APPLICATION NO. 100000076670 , Reference ID : 860268400] | BP/23-24/27 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0 | 0
19 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | New Service Connection Charge for MALLICK SOVA, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] | BP/23-24/55 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
20 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1127/NMD | 12/09/2022 | 30 | BLUE PINE | 8.26 | 0 | 0 | 100
21 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1126/NMD | 12/09/2022 | 30 | DAS CONSTRUCTION | 8.25 | 0 | 0 | 91
22 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 100/NMD | 03/02/2023 | 21 | M/S ROYAL ENTERPRISE | 2.91 | 0 | 0 | 100
23 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Laying Rising Main at 5th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 124/JD | 28/04/2023 | 14 | PINTU DAS | 5.01 | 0 | 0 | 100
24 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0090/2023-2024 ,Dt - 31/01/2024 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.28 | 0 | 0 | 0
25 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Fuel,lubricants charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0001/2023-2024 ,Dt - 30/04/24 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.29 | 0 | 0 | 0
26 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :004/2024-2025 ,Dt - 31/07/2024 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0 | 0
27 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
28 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mallicksova Piped water Supply Scheme , SM/09485 | Augmentation | Laying Rising Main at 4th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 125/JD | 28/04/2023 | 645 | M/S KARMAKAR CONSTRACTION | 6.14 | 0 | 0 | 100
29 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Purba Daukimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 1258/JD | 10/08/2021 | 15 | RABINDRANATH DUTTA | 4.81 | 0 | 0 | 0
30 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna at Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | 130/JD | 14/01/2022 | 21 | RABINDRANATH DUTTA | 4.84 | 0 | 0 | 1
31 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Laying distribution system with FHTC work for Augmentation of Purba Daukimari Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E. Dte. (Part-A) | 333/JD | 02/02/2022 | 120 | SUKES BASU MAJUMDAR | 328.7 | 0 | 0 | 1
32 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Division, P.H.E. Dte. | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0 | 0 | 0
33 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | IEP MAYNAGURI ZONE II | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0 | 0
34 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | REJUNATION 2ND TUBE WELL SITE CHALSA | BP-2021-22-422 | 25/03/2022 | 0 | SUKUMAR KUNDU | 0.94 | 0 | 0 | 0
35 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | IEP FOR MAYNAGURI PWSS | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0 | 0
36 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | b-wall for kharija berubari pwsss | BP-2021-23-4 | 21/04/2022 | 0 | GANAPATI ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.41 | 0 | 0 | 0
37 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Construction of 250 CuM. Capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) for the Head Works Site and other related works including pump connection of different pump for Augmentation of Purba Daukimari Piped Water Supply Scheme of Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | 196/JD | 21/01/2022 | 180 | PRADIP SAHA | 75.21 | 0 | 0 | 1
38 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Laying of Paver Block with development of approach pathway as a restoration work due to delivery main and Rising main laying for Augmentation of Purba Daukimari Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | 445/JD. | 08/06/2023 | 21 | TARAKESWAR PRASAD | 4.59 | 0 | 0 | 0
39 | JALPAIGURI | Northern Mechanical | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAUKIMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1248/NMD | 31/07/2023 | 30 | MAA ENTERPRISES | 10.87 | 0 | 0 | 0
40 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Chanadipa Mouza of Dakshin Salbari W/S/S Under Jalpaiguri Division ,P.H.E. Dte. | 157/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 0 | 0 | 0
41 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Sinking of 1 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Daukimari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 441/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.92 | 0 | 0 | 100
42 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | 156/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 0 | 0 | 0
43 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Laying Distribution System including road boaring, Supplying and fitting fixing specials, Jeffy Coupling and other miscelleneous works for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | 1555/JD | 01/11/2023 | 30 | B.M CONSTRUCTION | 14.3 | 0 | 0 | 100
44 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Laying Distribution System including culvert crossing and road restoration for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | 1553/JD | 01/11/2023 | 21 | B.M CONSTRUCTION | 9.41 | 0 | 0 | 100
45 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | Material Requisition To Resource Division | 556/JD | 01/03/2022 | 0 | Resource Division | 17.98 | 0 | 0 | 0
46 | JALPAIGURI | Northern Mechanical | Augmentation of Purba Daukimari Piped Water Supply Scheme , SM/09560 | Augmentation | New Service Connection Charge for AUGMENTATION OF DAUKIMARI PWSS, TW no I, under DHUPGURI CCC APPLICATION NO. 4003391338 Reference ID : 403203884 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.32 | 0 | 0 | 0
47 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | PREPARATION OF DPR DAKHIN CHAKMOULANI | BP-2021-22-490 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.56 | 0 | 0 | 0
48 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0 | 0 | 0
49 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Continuation Order for the work ¿Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub- Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)¿ from 01.10.2022 to 31.12.2022. | 248/JSSD | 28/09/2022 | 93 | TANMOY CHOUDHURY | 0.46 | 0 | 0 | 0
50 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Sinking of 1 No. 250mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 871/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 8 | 0 | 0 | 100
51 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Dakshin Chalk Moulani P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1066/JSSD | 24/01/2022 | 20 | ASIS ENTERPRISE | 1.83 | 0 | 0 | 0
52 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1109/W/JSSD | 27/01/2022 | 45 | M/S M G CONSTRUCTION | 4.76 | 0 | 0 | 100
53 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Construction of Rig approach for Installation of tubewell 3rd Tube Well site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | 85/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 0.81 | 0 | 0 | 100
54 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | SUPPLY OF SHARP TONNER CARTRIDGE | BP-2022-23-404 | 17/01/2023 | 0 | QUATTRON | 0.17 | 0 | 0 | 0
55 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | hire chages | BP-2022-23-438 | 03/02/2023 | 0 | LOKNATH CONSTRUCTION | 0.52 | 0 | 0 | 0
56 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | ETDS | BP-2022-23-406 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.13 | 0 | 0 | 0
57 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | ETDS | BP-2022-23-405 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.08 | 0 | 0 | 0
58 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | FUEL SUPPLY | BP-2022-23-403 | 17/01/2023 | 0 | FILL & SMILE | 1.71 | 0 | 0 | 0
59 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jal Swapna / JJM for Augmentation of Dakhin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 211/JD | 24/01/2022 | 60 | UNIBRO INFRASERV PRIVATE LIMITED | 426.83 | 0 | 0 | 80
60 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | 566/JSSD | 05/03/2024 | 30 | GOURAV CONSTRUCTION CO. | 4.03 | 0 | 0 | 90
61 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site OHR Aug. of Dakshin Chak Moulani PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | 230/JSSD | 10/09/2024 | 10 | SADHAN KARMAKAR | 0.64 | 0 | 0 | 0
62 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN CHAK MOULANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1383/NMD | 09/08/2023 | 30 | M/S ROYAL ENTERPRISE | 10.32 | 0 | 0 | 60
63 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Dakshin Chakmoulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 83/JSSD | 22/07/2022 | 20 | CHANDAN GHOSH | 4.56 | 0 | 0 | 100
64 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | New Service Connection Charge for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 4003266328, Reference ID : 403105517] | 23-24/153&162 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
65 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Infrastructure Cost for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 100000093179, Reference ID : 860284829] | 23-24/153&162 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.87 | 0 | 0 | 0
66 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1437/JD | 05/10/2023 | 667 | M/S. D.K. DEY & CO.. | 91.09 | 0 | 0 | 35
67 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme , SM/09561 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Dakshin Chak Moulani PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | 671/JD | 16/07/2024 | 625 | M/S S. G. ENTERPRISE | 19.97 | 0 | 0 | 80
68 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Restoration of damaged DI Pipeline at Kathapara Piped W/S at Dhupguri Development Block Under Jalpaiguri Division PHE Dte. | 1320/JD | 16/06/2022 | 15 | SADHAN KARMAKAR | 0.96 | 0 | 0 | 1
69 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Kathapara at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 2411/JD | 19/12/2022 | 30 | SAUMENDU DUTTA | 8.61 | 0 | 0 | 0
70 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Construction of Boundary wall with ancillary works for the Pump House No. 1 Premises of the Bhatia para Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1196/JD | 06/11/2020 | 30 | RABINDRANATH DUTTA | 4.99 | 0 | 0 | 100
71 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Soil Investigation for the work of Construction of R.C.C. Over Head Reservoir for the Head Works Site of Augmentation of Kathapara P.W.S.S. under Jalpaiguri Division.P.H.E.Dte. | 1693/JD | 06/09/2022 | 21 | MOYTEC | 0.97 | 0 | 0 | 100
72 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Shifting and Laying of Parallel pipeline in place of partially damaged pipeline for widening and strengthening BRO Road from Chamurchi to Banerhat more including minor retrofitting works to the Division line under Haritalguri T.G. P.W.S.S. command area under Jalpaiguri Division, P.H.E.Dte. | 1553/JD | 05/08/2022 | 21 | NARAYAN CHANDRA SAHA | 25.32 | 0 | 0 | 0
73 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Land Developmrent at Head Works site under Jabramali Piped Water Supply Scheme whithin Jalpaiguri Division, P.H.E. Dte. | 645/RWS | 21/10/2022 | 15 | M/S RATAN KUMAR DAS GUPTA AND CO | 2.59 | 0 | 0 | 0
74 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site for Kathapara PWSS i.c.w. Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 299/JD | 10/02/2023 | 45 | ABHIK BHOWMIK | 4.64 | 0 | 0 | 100
75 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | TEMPORARY HIRING OF ONE MAXI CAB WITH DRIVER | BP-2023-24-251 | 21/07/2023 | 0 | RUPA PRASAD | 0.34 | 0 | 0 | 0
76 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation |  | BP-2023-24-252 | 21/07/2023 | 0 | APIKUL ALI | 0.35 | 0 | 0 | 0
77 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | New Service Connection Charge for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147726, Reference ID : 403014087] | BP/23-24/17 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
78 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | supply for fuel | BP-2023-24-250 | 21/07/2023 | 0 | FILL & SMILE | 0.58 | 0 | 0 | 0
79 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Infrastructure Cost for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077916, Reference ID : 860269056] | BP/23-24/17 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.38 | 0 | 0 | 0
80 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Construction of 400 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing at Head Works site for Augmentation of Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 734/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 82.2 | 0 | 0 | 75
81 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2027/JD | 19/11/2024 | 20 | ABHIK BHOWMIK | 2.41 | 0 | 0 | 0
82 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Material Requisition To Resource Division | 58/JD | 09/04/2024 | 0 | Resource Division | 18.24 | 0 | 0 | 0
83 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0003/2024-2025 ,Dt - 30/06/24 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.35 | 0 | 0 | 0
84 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Fuel ,lubrication charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0002/2024-2025 ,Dt - 31/05/24 |  | 16/08/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.51 | 0 | 0 | 0
85 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-I) | 1746/JD | 08/09/2022 | 1058 | SCEC BOENTER KDAS JOINT VENTURE | 76.15 | 0 | 0 | 15
86 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Laying Rising Main of 3rd Tube Well site of Kathapara PWSS, in connection with Rejuvenation of Kathapara Piped Water Supply Scheme under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 1850/JD | 15/12/2023 | 383 | ABHIK BHOWMIK | 4.73 | 0 | 0 | 100
87 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd TW Site for Kathapara PWSS i.c.w. JJM under Jalpaiguri Division, PHE Dte. | 2427/JD | 24/12/2024 | 261 | ABHIK BHOWMIK | 11.54 | 0 | 0 | 80
88 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
89 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Laying Distribution System for Augmentation of Kathapara Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 972/JD | 20/04/2022 | 1199 | SCEC BOENTER KDAS JOINT VENTURE | 430.18 | 0 | 0 | 60
90 | JALPAIGURI | Northern Mechanical | Augmentation of Kathapara Piped Water Supply Scheme , SM/09563 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KATHAPARA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 341/NMD | 29/03/2023 | 491 | TAPAN BISWAS | 10.9 | 0 | 0 | 100
91 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Sinking of 2 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 442/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 15.63 | 0 | 0 | 1
92 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Shifting and repairing of damaged/chokage pipe line due to development, widening of roads and agricultural land related to L.D.S. within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1799/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.85 | 0 | 0 | 0
93 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Permanent restoration of G.I. lines across the small stream in two places along with others ancillary works related to distribution system, strengthening of valve chambers due to strengthening of village/PWD roads and culvert works in various places within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division,P.H.E. Dte.Jalpaiguri Division, P.H.E.Dte. | 1800/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.5 | 0 | 0 | 0
94 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 104/JD | 11/01/2022 | 60 | LOKNATH CONSTRUCTION | 4.65 | 0 | 0 | 1
95 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 105/JD | 11/01/2022 | 60 | PRITAM DUTTA | 4.65 | 0 | 0 | 1
96 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.04 | 0 | 0 | 0
97 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Infrastructure Cost for PURBO MAGURMARI, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 100000086997, Reference ID : 860278198] | BP/23-24/108 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.63 | 0 | 0 | 0
98 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0 | 0
99 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 4003018663, Reference ID : 402928488] | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
100 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 4003018653, Reference ID : 402927251] | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
101 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 30
102 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
103 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1125/NMD | 12/09/2022 | 1023 | UTTAM PAUL | 8.01 | 0 | 0 | 60
104 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 82/NMD | 27/01/2023 | 736 | MIHIR SARKAR | 8 | 0 | 0 | 100
105 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 103/NMD | 03/02/2023 | 729 | MIHIR SARKAR | 2.27 | 0 | 0 | 100
106 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Magurmari Piped Water Supply Scheme. , SM/09564 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 104/NMD | 03/02/2023 | 817 | UTTAM PAUL | 2.27 | 0 | 0 | 100
107 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Construction of 100 cum OHR as per departmental design & drawing switch room, laying distribution system sinking of tube well etc. supply of potable drinking water to Manabari Tea Garden in relation with CHAA Sundari Project Piped Water Supply Scheme Block. Nagrakata Dist. Jalpaiguri. | 321/JD | 25/02/2021 | 120 | RANJIT SINGH BENIWAL | 72.76 | 0 | 0 | 0
108 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at MANABARI TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block MAL, district Jalpaiguri. | 355/NMD | 23/05/2022 | 30 | S.P. ENTERPRISE | 14.27 | 0 | 0 | 0
109 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Land development of H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 207/JSSD | 14/09/2022 | 30 | M/S A.B.G. CONSTRUCTION | 1.41 | 0 | 0 | 100
110 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Infrastructure Cost for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO.100000066241 ; Reference ID : 860255931] | BP/22-23/133 | 10/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.12 | 0 | 0 | 0
111 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | New Service Connection Charge for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO. 4003043871 ; Reference ID : 402922125] | BP/22-23/133 | 10/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
112 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Infrastructure development cost for new service connection at Manabari TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 100000118548 Reference ID : 860312788 | BP/24-25/246 | 02/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.44 | 0 | 0 | 0
113 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | New Service Connection Charge for MANABARI TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 4003491173 Reference ID : 403275174 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
114 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Manabari Tea Garden in relation with Chaa Sundari Project. , SM/08579 | New | Sinking of One No. Tube Well by ODEX-165 Method of drilling and Construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement for direct boosting under the command area of Manabari Chaa Sundari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1293/JD | 05/09/2024 | 90 | RANJEET SINGH BENIWAL | 13.9 | 0 | 0 | 100
115 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LDS FHTC GHASMARI | BP-2021-22-499 | 29/03/2022 | 0 | M/S R.N. TRADERS | 56.2 | 0 | 0 | 0
116 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 4th Tubewell site for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 164/JD | 19/01/2023 | 45 | KAUSHIK SEN | 10.78 | 0 | 0 | 0
117 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Rising Main Connections (at 4th TW site) including other necessary arrangement for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. | 167/RWS | 28/02/2023 | 14 | SAPTASWA SARKAR | 1.58 | 0 | 0 | 1
118 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN BERUBARI PWSS,TW No IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 365/NMD | 29/03/2023 | 30 | SARKAR ELECTRIC | 11.14 | 0 | 0 | 70
119 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Sinking of Shallow Tubewell for the Contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | 42/DSD | 14/07/2023 | 10 | SARKAR ELECTRIC | 0.08 | 0 | 0 | 0
120 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tube well (BDTW) by the Reverse Rotary Circulation method of drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | 43/DSD | 14/07/2023 | 10 | SARKAR ELECTRIC | 0.79 | 0 | 0 | 0
121 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) | 672/JD | 10/07/2023 | 184 | APIKUL ALI | 0.88 | 0 | 0 | 30
122 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-D). | 343/JD | 03/02/2022 | 90 | SUKES BASU MAJUMDAR | 177.1 | 0 | 0 | 100
123 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Material Requisition To Resource Division | 560/JD | 01/03/2022 | 0 | Resource Division | 53.75 | 0 | 0 | 0
124 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | FUEL AND LUBRICANTS FOR THE VEHICLES UNDER JALPAIGURI | BP-2023-24-416 | 06/10/2023 | 0 | FILL & SMILE | 2.41 | 0 | 0 | 0
125 | JALPAIGURI | Northern Mechanical | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | New Service Connection Charge for DAKSHIN BERUBARI, T/W IV, under HALDIBARI CCC, [APPLICATION NO. 4003215403, Reference ID : 403062802] | BP/23-24/123 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
126 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | supply of 1(one) Maxi cab with engine capacity less than or equal to 2000c.c on hire basis including driver for the Executive Engineer ,planing & Design Division-III, P.H.E. Dte., silliguri | BP-2023-24-467 | 17/10/2023 | 0 | SHREYANSH AUTO MOBILE | 1.14 | 0 | 0 | 0
127 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | SUPPLY OF FUEL & LUBRICANT FOR THE VEHICLE RUNNING UNDER JALPAIGURI RWS FOR THE MONTH OF OCTOBER-2023 | BP-2023-24-508 | 29/11/2023 | 0 | FILL & SMILE | 0.22 | 0 | 0 | 0
128 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | FUEL BILL | BP-2023-24-491 | 08/11/2023 | 0 | FILL & SMILE | 0.32 | 0 | 0 | 0
129 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | SUPPLY OF FUEL FOR THEB HIRED VEHICLES UNDER JALPAIGURI DIVISION AND SUB DIVISION | BP-2023-24-375 | 19/09/2023 | 0 | FILL & SMILE | 0.7 | 0 | 0 | 0
130 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-B). | 340/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 162.92 | 0 | 0 | 100
131 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) | 683/JD | 11/07/2023 | 184 | RAKESH SARKAR | 0.88 | 0 | 0 | 50
132 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 0 | 0 | 100
133 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Sinking of 250 mm X 150 mm dia tube well by Reverse Rotary method of drilling at 4th Site of A Dakshin Berubari PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division. | 1591/JD | 23/10/2024 | 30 | NARESH SEN | 9.11 | 0 | 0 | 0
134 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 337/JD | 02/02/2022 | 120 | M/S RATAN KUMAR DAS GUPTA AND CO | 143.72 | 0 | 0 | 100
135 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Material Requisition To Resource Division | 2213/JD | 01/12/2024 | 0 | Resource Division | 30.21 | 0 | 0 | 0
136 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-C). | 341/JD | 03/02/2022 | 1468 | M/S A.B.G. CONSTRUCTION | 174.6 | 0 | 0 | 100
137 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-A). | 347/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 175.44 | 0 | 0 | 100
138 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-F). | 346/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 197.49 | 0 | 0 | 100
139 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 0 | 0 | 14
140 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Additional work of OHR including IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Dakshin Berubari Pipe Water Supply Scheme under Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | 128/JD | 16/01/2025 | 440 | M/S RATAN KUMAR DAS GUPTA AND CO | 78.71 | 0 | 0 | 85
141 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-E). | 344/JD | 03/02/2022 | 749 | R.S CONSTRUCTION | 177.82 | 0 | 0 | 100
142 | JALPAIGURI | Jalpaiguri Division | Augmentation of Dakshin Berubari Water Supply Scheme. , SM/10086 | Augmentation | Construction of different components for Rejuvenation of Jogesh Chandra Tea Garden PWSS I.e. TW, Pump Houses, Rising Main, Boundary wall etc. at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 1541/JD | 26/10/2023 | 163 | M/S KARMAKAR CONSTRUCTION | 22.42 | 0 | 0 | 100
143 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2238/JD | 29/12/2021 | 60 | ABHIJIT SARKAR | 11.44 | 0 | 0 | 1
144 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-I) PWSS UNDER CDD, PHE DTE. | 753/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 0 | 0 | 0
145 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 206/NMD | 04/04/2022 | 21 | R.K.ENTERPRISES | 2.77 | 0 | 0 | 0
146 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 463/CMSD-II (D) | 25/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0 | 0 | 0
147 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 10M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 464/CMSD-II (D) | 25/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.42 | 0 | 0 | 0
148 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-II) PWSS UNDER CDD, PHE DTE. | 754/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 0 | 0 | 0
149 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200KM FOR 20 M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-III) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 472/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0 | 0 | 0
150 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-III) PWSS UNDER CENTRAL DRILLING DIVISION, PHE DTE. | 755/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 0 | 0 | 0
151 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS ( 1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 471/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0 | 0 | 0
152 | JALPAIGURI | Central Drilling | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | ADDITIONAL TRANSPORTATION OF BENTONITE AFTER 200 KM FOR (4X3)=12 MT BENTONITE AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 473/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.3 | 0 | 0 | 0
153 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BAIKUR PWSS, at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 540/NMD | 08/07/2022 | 30 | SARKAR ELECTRIC | 8.31 | 0 | 0 | 0
154 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BAIKUR PWSS, at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 443/NMD | 14/06/2022 | 21 | BONANZA ENTERPRISE | 2.76 | 0 | 0 | 0
155 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 279/NMD | 26/04/2022 | 30 | INDTECH ASSOCIATES | 8.74 | 0 | 0 | 0
156 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 207/NMD | 04/04/2022 | 21 | MALAY KUMAR SAHA | 2.77 | 0 | 0 | 0
157 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | New Service Connection Charge for T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
158 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Installation of Infrastructure IRO NSC application T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052276 ; Reference ID : 860241546] | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0 | 0
159 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | New Service Connection Charge for T/W No. IV of BAIKUR JORPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
160 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Installation of Infrastructure IRO NSC application T/W No. III of BAIKUR GOURGRAM HELAPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052275 ; Reference ID : 860241545] | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0 | 0
161 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LDS MOGALKATA T.G PWSS | BP-2021-22-554 | 31/03/2022 | 0 | DULAL CHOUDHURY | 10.11 | 0 | 0 | 0
162 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | TUBE WELL BILL | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0 | 0
163 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | AUG LATAGURI ZONE III | BP-2021-22-552 | 31/03/2022 | 0 | RAGHU DAS | 22.91 | 0 | 0 | 0
164 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-III) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 324/JD | 02/02/2022 | 90 | CALCON CONSTRUCTIONS | 218.39 | 0 | 0 | 50
165 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2223/JD | 27/12/2021 | 60 | DREAM CONSTRUCTION | 11.43 | 0 | 0 | 1
166 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 275/JD | 22/11/2022 | 15 | DREAM CONSTRUCTION | 6.32 | 0 | 0 | 0
167 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Minor Repairing work for Pump House & construction of CC path for Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 191/JD | 20/01/2023 | 15 | DREAM CONSTRUCTION | 2.55 | 0 | 0 | 0
168 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2023 to 31/10/2023 | 44/JSSD | 27/04/2023 | 183 | MRITYUNJAY SIKDAR | 0.88 | 0 | 0 | 34
169 | JALPAIGURI | Northern Mechanical | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 280/NMD | 26/04/2022 | 30 | M/S P.P. ELECTRICALS | 8.74 | 0 | 0 | 0
170 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Additional pipeline works for Augmentation of Baikur (Part-I) Piped Water Supply Scheme. | 1861/JD | 20/09/2022 | 30 | PRADIP KR SEN | 18 | 0 | 0 | 1
171 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. | 2014/JD | 01/11/2022 | 45 | M/S R.N. TRADERS | 17.88 | 0 | 0 | 100
172 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. | 137/JD | 17/01/2023 | 45 | SADHAN KARMAKAR | 17.86 | 0 | 0 | 100
173 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Material Requisition To Resource Division | 557/JD | 01/03/2022 | 0 | Resource Division | 1.82 | 0 | 0 | 0
174 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | PROVIDING INSPECTION VEHICLE FOR OFFICIAL USE OF THE OFFICE OF THE EXECUTIVE ENGINEER,JALPAIGURI DIVISION, P.H.E. Dte. | BP-2023-24-426 | 10/10/2023 | 0 | SADHAN KARMAKAR | 0.16 | 0 | 0 | 0
175 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | supply of 1(one) Maxi cab on hire basis including driver for the office of the Executive Engineer , planning & Design Division -III,P.H.E. Dte. Silliguri | BP-2023-24-515 | 06/12/2023 | 0 | SHREYANSH AUTO MOBILE | 1.15 | 0 | 0 | 0
176 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-II) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 323/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.83 | 0 | 0 | 1
177 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 0 | 0 | 100
178 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-I) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 322/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.8 | 0 | 0 | 100
179 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Laying of Additional 75 mm dia pipeline for providing FHTC for Augmentation of Baikur PWSS for Part-VI area. | 1876/JD | 20/12/2023 | 21 | PRADIP KR SEN | 13.08 | 0 | 0 | 100
180 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Material Requisition To Resource Division | 2219/JD | 01/12/2024 | 0 | Resource Division | 44.19 | 0 | 0 | 0
181 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-IV) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 325/JD | 02/02/2022 | 90 | NARAYAN CHANDRA SAHA | 221.81 | 0 | 0 | 1
182 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-V) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 326/JD | 02/02/2022 | 719 | MINTU CHAKRABORTY | 220.34 | 0 | 0 | 100
183 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | Additional Laying Distribution System and Providing Functional House Hold Tap Connection at Baikur (Part-V) PWSS Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 483/JD | 11/03/2025 | 296 | DREAM CONSTRUCTION | 19.67 | 0 | 0 | 85
184 | JALPAIGURI | Jalpaiguri Division | Augmentation of Baikur Piped Water Supply Scheme. , SM/10089 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-VI) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. | 327/JD | 02/02/2022 | 799 | M/S S.G. CONSTRUCTION | 213.61 | 0 | 0 | 100
185 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 290/JD | 23/02/2021 | 20 | PARESH CHANDRA ROY | 12.8 | 0 | 0 | 1
186 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 296/JD | 24/02/2021 | 30 | M/S SIBU DEY AND CO. | 24.41 | 0 | 0 | 1
187 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of existing LDS under the command area of Khalaigram Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | 1990/JD | 03/12/2021 | 30 | M/S R.N. TRADERS | 47.9 | 0 | 0 | 1
188 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | shifting of pipe line khalaigram |  | 05/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0 | 0
189 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | SHIFTING OF PIPE LINE FOR KHALAIGRAM PWSS | BP-2021-22-77 | 08/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0 | 0
190 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | fhtc khalaigram | BP-2021-22-94 | 13/11/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0 | 0
191 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | FHTC KHALAIGRAM |  | 29/10/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0 | 0
192 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Khalaigram Piped Water Supply Scheme at Dhupguri Block , SM/07892 | Retrofitting | IEP FOR RAIPUR T.G | BP-2021-22-24 | 26/04/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 2.39 | 0 | 0 | 0
193 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | Material Requisition To Resource Division | 1110/JD | 24/08/2023 | 0 | Resource Division | 14.91 | 0 | 0 | 0
194 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | Material Requisition To Resource Division | 1843/JD | 15/12/2023 | 0 | Resource Division | 8.21 | 0 | 0 | 0
195 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-II, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1255/NMD | 31/07/2023 | 30 | RMD TRADING | 21.74 | 0 | 0 | 60
196 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003460802 Reference ID : 403255266 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.3 | 0 | 0 | 0
197 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO I, under DHUPGURI CCC APPLICATION NO. 4003460793 Reference ID : 403255267 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.21 | 0 | 0 | 0
198 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | Construction of different components of MADHYA BORAGARI ZONE-II PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division, P.H.E DTE. | 2345/JD | 04/11/2025 | 210 | BISWANATH GHOSH | 327.82 | 0 | 0 | 0
199 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/13682 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Barogari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1958/JD | 18/09/2025 | 45 | DEBASISH DEY | 29.65 | 0 | 0 | 0
200 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Material Requisition To Resource Division | 159/JD | 28/04/2023 | 0 | Resource Division | 62.06 | 0 | 0 | 0
201 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Construction of Boundary Wall at 2nd site of GAUGRAM PWSS in connection with Jal Jeevan Mission at Block - MAYNAGURI under Jalpaiguri Division, P.H.E.Dte. | 152/RWS | 15/02/2024 | 30 | JAGORAN SARKAR | 5.23 | 0 | 0 | 100
202 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
203 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Material Requisition To Resource Division | 2040/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0 | 0
204 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | New Service Connection Charge for GOURGRAM, T/W No. I under BHOTPATTY CCC [APPLICATION NO. 4003305799 ; Reference ID : 403134434] | BP/23-24/294 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.37 | 0 | 0 | 0
205 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | New Service Connection Charge for Gourgram, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375840 Reference ID : 403191702 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0 | 0
206 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
207 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Construction of different components of Gaurgram PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal JeevanMission at Block- Maynaguri under Jalpaiguri Division , P.H.E Dte. | 787/JD | 27/03/2023 | 1062 | M/S S.G. CONSTRUCTION | 346.83 | 0 | 0 | 100
208 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAURGRAM PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1329/NMD | 08/08/2023 | 678 | DIPALI CONSTRUCTION | 22.21 | 0 | 0 | 100
209 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Gaurgram PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 633/JD | 28/03/2025 | 45 | RABINDRA NATH DUTTA | 34.39 | 0 | 0 | 0
210 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
211 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
212 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
213 | JALPAIGURI | Northern Mechanical | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
214 | JALPAIGURI | Jalpaiguri Division | GAURGRAM PIPED WATER SUPPLY SCHEME , SM/13701 | New | Construction of Boundary Wall at H/W Site including Rising main interconnection of Gaurgram PWSS in connection with Jal Jeevan Mission at Block ¿ Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 2408/JD | 19/02/2024 | 407 | SUBRATA DAS | 15.36 | 0 | 0 | 100
215 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Material Requisition To Resource Division | 1107/JD | 24/08/2023 | 0 | Resource Division | 25.88 | 0 | 0 | 0
216 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | New Service Connection Charge for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4400307494, Reference ID : 403056595] | BP/23-24/87 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
217 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | New Service Connection Charge for SAKATI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212055, Reference ID : 403060258] | BP/23-24/105 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0 | 0
218 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Infrastructure Cost for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086241, Reference ID : 860277651] | BP/23-24/87 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
219 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHAKATI PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 463/NMD | 25/04/2023 | 30 | SUMON ELECTRICAL | 22.07 | 0 | 0 | 100
220 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Material Requisition To Resource Division | 2002/JD | 08/01/2024 | 0 | Resource Division | 7.26 | 0 | 0 | 0
221 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
222 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Construction of different components of Shakati PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | 753/JD | 24/03/2023 | 902 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 346.92 | 0 | 0 | 95
223 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Installation of two tank chlorination system at SHAKATI and other adjacent water supply scheme UNDER JJM under JALPAIGURI SADAR Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 79/SMSD | 07/02/2025 | 15 | SUMON ELECTRICAL | 1.57 | 0 | 0 | 0
224 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Construction of Boundary Wall ,Foot Path,Drain, at 2nd site of Shakati PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 489/RWS | 29/05/2025 | 30 | MS DEBABRATA SARKAR | 6.24 | 0 | 0 | 0
225 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
226 | JALPAIGURI | Jalpaiguri Division | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Shakati PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 468/JD | 11/03/2025 | 40 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 17.67 | 0 | 0 | 0
227 | JALPAIGURI | Northern Mechanical | SHAKATI PIPED WATER SUPPLY SCHEME , SM/13704 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
228 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Material Requisition To Resource Division | 151/JD | 28/04/2023 | 0 | Resource Division | 105.47 | 0 | 0 | 0
229 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AMGURI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 271/NMD | 21/03/2023 | 30 | TALUKDER ENTERPRISE | 22.92 | 0 | 0 | 100
230 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Construction of Boundary Wall at 2nd Pump House site Including raising main and interconnection of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 165/RWS | 15/02/2024 | 30 | DEEP CONSTRUCTION | 6.17 | 0 | 0 | 100
231 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Material Requisition To Resource Division | 2056/JD | 09/01/2024 | 0 | Resource Division | 14.62 | 0 | 0 | 0
232 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266414, Reference ID : 403108583] | 23-24/155&163 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.24 | 0 | 0 | 0
233 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | New Service Connection Charge for AMGURI, T/W No. II, under MAYNAGURI CCC [APPLICATION NO. 4003297950 , Reference ID : 403128266] | BP/23-24/217 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0 | 0
234 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Balance Laying Distribution System and Providing Functional Household Tap Connection in connection with Jal Jeevan Mission at Amguri PWSS in Maynaguri Block under Jalpaiguri Division, PHE Dte. | 45/JD | 09/01/2025 | 416 | B. M CONSTRUCTION | 70.87 | 0 | 0 | 60
235 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
236 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
237 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
238 | JALPAIGURI | Northern Mechanical | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
239 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 985/JD | 14/08/2024 | 15 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
240 | JALPAIGURI | Jalpaiguri Division | AMGURI PIPED WATER SUPPLY SCHEME , SM/13706 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 2631/JD | 07/03/2024 | 45 | B.M CONSTRUCTION | 16.14 | 0 | 0 | 100
241 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Charerbari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 634/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 0 | 0 | 1
242 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941281 , Reference ID : 402831979] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
243 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053963 ; Reference ID : 860243613] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.92 | 0 | 0 | 0
244 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941279 ; Reference ID : 402831974] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
245 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053962 ; Reference ID : 860243612] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0 | 0
246 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 857/NMD | 18/07/2022 | 30 | DAWA DUKPA | 7.87 | 0 | 0 | 80
247 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 568/NMD | 14/07/2022 | 21 | SUNLIT | 2.16 | 0 | 0 | 50
248 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. | 1578/JD | 12/08/2022 | 45 | NEW KUNDU ENTERPRISE | 14.43 | 0 | 0 | 0
249 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. | 1563/JD | 10/08/2022 | 45 | A.P CONSTRUCTION | 14.45 | 0 | 0 | 0
250 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Minor Repairing work for OHR, Pump Houses, Boundary walls, Blower Room, IEP etc. for Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 605/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.69 | 0 | 0 | 0
251 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2213/JD | 27/12/2021 | 60 | JAYA SARKAR | 11.42 | 0 | 0 | 1
252 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2212/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 0 | 0 | 1
253 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 858/NMD | 18/07/2022 | 30 | SUBHRANGSHU GUHARAJA | 7.87 | 0 | 0 | 0
254 | JALPAIGURI | Northern Mechanical | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 569/NMD | 14/07/2022 | 21 | SUDIP DUTTA | 2.16 | 0 | 0 | 0
255 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2012/JD | 01/11/2022 | 15 | M/S DEY & ROY CHOUDHURY | 3.7 | 0 | 0 | 1
256 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Construction of Approach road by Paver Block inside the Reservior Compound at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 603/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.92 | 0 | 0 | 100
257 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Material Requisition To Resource Division | 1059/JD | 24/08/2023 | 0 | Resource Division | 3.24 | 0 | 0 | 0
258 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Charerbari piped water supply scheme. , SM/09458 | Augmentation | Drainage arrangement for back wash water from Iron Elemation Plant at 3rd & 4th tube well site of Charerbari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 387/RWS | 25/04/2023 | 14 | PRITAM DUTTA | 2.73 | 0 | 0 | 100
259 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I,PHE Dte. | BP-2023-24-517 | 07/12/2023 | 0 | RUPA PRASAD | 0.62 | 0 | 0 | 0
260 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHARMMAPUR PWSS, TW NO I and II (ZONE-I) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1256/NMD | 31/07/2023 | 459 | M/S UTPAL CHAKRABORTY & CO. | 21.53 | 0 | 0 | 100
261 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
262 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Construction of Boundary Wall at 2nd site of Dharamapur Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 154/RWS | 15/02/2024 | 287 | ARATI CONSTRUCTION | 7.29 | 0 | 0 | 100
263 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Material Requisition To Resource Division | 2037/JD | 09/01/2024 | 0 | Resource Division | 6.57 | 0 | 0 | 0
264 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
265 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | New Service Connection Charge for DHARMAPUR, T/W No. II, ZONE-I under BHOTPATTY CCC [APPLICATION NO. 4003305854 ; Reference ID : 403134431] | BP/23-24/288 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.12 | 0 | 0 | 0
266 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | New Service Connection Charge for DHARMAPUR, T/W No. I, ZONE-I under BHOTPATTY CCC [APPLICATION NO. 4003305851 ; Reference ID : 403134433] | BP/23-24/287 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0 | 0
267 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Construction of Different components of Dharmapur Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. I.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE Dte. | 96/JD | 25/04/2023 | 857 | GLOBAL POWER & CONSTRUCTION CO. | 314.13 | 0 | 0 | 70
268 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 2460/JD | 23/02/2024 | 768 | ARUP SARKAR | 22.91 | 0 | 0 | 0
269 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmmapur Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2330./JD | 12/12/2024 | 639 | BISWAJIT BHADURI | 41.39 | 0 | 0 | 70
270 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
271 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
272 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
273 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/14826 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
274 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Material Requisition To Resource Division | 1098/JD | 24/08/2023 | 0 | Resource Division | 49.85 | 0 | 0 | 0
275 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Material Requisition To Resource Division | 1887/JD | 20/12/2023 | 0 | Resource Division | 16.42 | 0 | 0 | 0
276 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANICHERA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1488/NMD | 17/08/2023 | 30 | M/S PARITOSH BHOWMICK AND CO. | 37.96 | 0 | 0 | 70
277 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Additional Works in connection with supply, installation, commissioning and trial operation of electro mechanical components along with copper own line voltage corrector for RANICHERA T.G PWSS in the Dist. of JALPAIGURI under Northern Mechanical Division PHE Dte. | 1061/HQ/NMD | 21/06/2024 | 7 | M/S PARITOSH BHOWMICK AND CO. | 0.89 | 0 | 0 | 100
278 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266404, Reference ID : 403105524] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
279 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093888, Reference ID : 860285548] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
280 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093890, Reference ID : 860285650] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
281 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | New Service Connection Charge for RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003482909 Reference ID : 403269953 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
282 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266407, Reference ID : 403105523] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
283 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
284 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093887, Reference ID : 860285547] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.25 | 0 | 0 | 0
285 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266411, Reference ID : 403105529] | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
286 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Infrastructure development cost for new service connection at RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000117729 Reference ID : 860312409 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.39 | 0 | 0 | 0
287 | JALPAIGURI | Northern Mechanical | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
288 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Balance Laying Distribution System with providing Functional Household Tap Connection (FHTC) including sinking of One No Additional Tube Well by ODEX-165 method of drilling, construction of Pump House (3.60m x 2.40m) with sanitary plumbing arrangement, Boundary Wall and direct boosting for 5th site in the command area of Ranichera Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 460/JD | 11/03/2025 | 142 | GOEL CONSTRUCTION CO. | 80.53 | 0 | 0 | 90
289 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Construction of different components of Ranichera Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 845/JD | 28/07/2023 | 704 | GOEL CONSTRUCTION CO. | 517.13 | 0 | 0 | 95
290 | JALPAIGURI | Jalpaiguri Division | RANICHERA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14885 | New | Construction of Different balance component for Ranichera Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2749/JD | 14/03/2024 | 474 | GOEL CONSTRUCTION CO. | 86.19 | 0 | 0 | 100
291 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN DANGAPARA PWSS, ZONE-I, TW no I, II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1315/NMD | 04/08/2023 | 547 | DIAMOND ELECTRICAL WORKS | 21.72 | 0 | 0 | 80
292 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Material Requisition To Resource Division | 2031/JD | 09/01/2024 | 0 | Resource Division | 9.97 | 0 | 0 | 0
293 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
294 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | New Service Connection Charge for DAKSHIN DANGAPARA ZONE-I, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003397121 Reference ID : 403208946 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0 | 0
295 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | New Service Connection Charge for DAKSHIN DANGAPARA ZONE-I, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003397683 Reference ID : 403208960 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0 | 0
296 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Construction of different components of Dakshin Dangapara PWSS Zone- I i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. | 375/A/JD | 30/05/2023 | 763 | PARESH CHANDRA GUHA | 384.43 | 0 | 0 | 100
297 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 2163/JD | 27/11/2024 | 287 | PARESH CHANDRA GUHA | 49.63 | 0 | 0 | 0
298 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
299 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
300 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
301 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-I PIPED WATER SUPPLY SCHEME , SM/14887 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
302 | JALPAIGURI | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME , SM/15132 | Retrofitting | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Arji Maria Kamala Pukhari PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) | 432/JD. | 08/06/2023 | 28 | GOUTAM DAS | 55.33 | 0 | 0 | 100
303 | JALPAIGURI | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME , SM/15132 | Retrofitting | Installation of 2 Nos of Iron Elimination Plant (20m3/hr.) including construction of 2 nos of Blower room (3.60MX3.00M) Size & concrete platform , drain, valve chamber etc at 3rd and 4th Site of Arji maria kamala pukhari piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2175/JD | 22/01/2024 | 60 | R.S CONSTRUCTION | 28.19 | 0 | 0 | 100
304 | JALPAIGURI | Jalpaiguri Division | RETROFITTING OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME , SM/15132 | Retrofitting | Laying Washout line at 4th Site and Replacement of damaged higher dia pipeline at Arjimaria Kamalapukuri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri District, PHE Dte. | 2169/JD | 30/10/2025 | 153 | SOUVIK SAHA | 14 | 0 | 0 | 100
305 | JALPAIGURI | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | Material Requisition To Resource Division | 2047/JD | 09/01/2024 | 0 | Resource Division | 4.67 | 0 | 0 | 0
306 | JALPAIGURI | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | Material Requisition To Resource Division | 52/JD | 09/04/2024 | 0 | Resource Division | 12.25 | 0 | 0 | 0
307 | JALPAIGURI | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-I, under POWER HOUSE CCC, [APPLICATION NO. 4003352320, Reference ID : 403172860] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
308 | JALPAIGURI | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-II, under POWER HOUSE CCC, [APPLICATION NO. 4003352332, Reference ID : 403172862] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.85 | 0 | 0 | 0
309 | JALPAIGURI | Jalpaiguri Division | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | Construction of different components of Chotachand Fapri PWSS i.e, TW, Pump House, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | 221/JD | 03/05/2023 | 1062 | NARENDRA KUMAR | 196.33 | 0 | 0 | 45
310 | JALPAIGURI | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHOTA FAPRI PWSS, AT TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1275/NMD | 02/08/2023 | 761 | M/S BHOWMICK & CO. | 20.44 | 0 | 0 | 70
311 | JALPAIGURI | Northern Mechanical | CHHOTA FAPRI WATER SUPPLY SCHEME , SM/14494 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
312 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
313 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Balance work of Distribution Network and Functional Household Tap Connection (FHTC) of Rangamati Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 2273/JD | 05/12/2024 | 60 | LAKSHMI IRON | 26.64 | 0 | 0 | 0
314 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Material Requisition To Resource Division | 2019/JD | 09/01/2024 | 0 | Resource Division | 12.63 | 0 | 0 | 0
315 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 100000098979 , Reference ID : 860290249] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
316 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No.II, under MAL CCC [APPLICATION NO. 100000099050 , Reference ID : 860290250] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.28 | 0 | 0 | 0
317 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 4003325220 , Reference ID : 403151422] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
318 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. II, under MAL CCC [APPLICATION NO. 4003325230 , Reference ID : 403151421] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
319 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Infrastructure development cost for new service connection at RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 100000110603 Reference ID : 860303203 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0 | 0
320 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
321 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | New Service Connection Charge for RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 4003437136 Reference ID : 403237579 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
322 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Construction of different components of Rangamati Tea Garden PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 940/JD | 08/08/2023 | 718 | M/S SARKAR ENTERPRISE | 360.92 | 0 | 0 | 22
323 | JALPAIGURI | Northern Mechanical | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANGAMATI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1486/NMD | 17/08/2023 | 899 | M/S UTPAL CHAKRABORTY & CO. | 36.59 | 0 | 0 | 50
324 | JALPAIGURI | Jalpaiguri Division | RANGAMATI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14880 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Rangamati Tea Garden PWSS i.e. Tube Well, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 894/JD | 08/05/2025 | 90 | UMA CONSTRUCTION | 41.93 | 0 | 0 | 0
325 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Material Requisition To Resource Division | 155/JD | 28/04/2023 | 0 | Resource Division | 41.26 | 0 | 0 | 0
326 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Construction of Boundary Wall at 2nd Pump House site of Kaoagap PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 831/RWS | 28/08/2024 | 30 | TAPASH MOHANTA | 7.46 | 0 | 0 | 0
327 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
328 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Material Requisition To Resource Division | 2028/JD | 09/01/2024 | 0 | Resource Division | 6.06 | 0 | 0 | 0
329 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | New Service Connection Charge for KAOAGAP, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003356525 Reference ID : 403175897 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
330 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
331 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | New Service Connection Charge for KAOAGAP, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376062 Reference ID : 403191649 | BP/24-25/121 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0 | 0
332 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Construction of different components of Kaoagap PWSS i.e. TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. .C.W. Jal Jeevan Mission at Block:- Maynaguri under Jalpaiguri Division PHE Dte. | 777/JD | 27/03/2023 | 1101 | M/S RATAN KUMAR DAS GUPTA AND CO | 412.26 | 0 | 0 | 80
333 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Kaoagap PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2428/JD | 24/12/2024 | 464 | ALICK DUTTA | 34.87 | 0 | 0 | 0
334 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
335 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
336 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
337 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
338 | JALPAIGURI | Northern Mechanical | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KAOAGAP PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 269/NMD | 21/03/2023 | 711 | MIHIR SARKAR | 21.61 | 0 | 0 | 100
339 | JALPAIGURI | Jalpaiguri Division | KAOAGAP PIPED WATER SUPPLY SCHEME , SM/14199 | New | Pilling of Eucalyptus-bullah at all around the excavated Reservoir foundation trenches for increasing of bearing capacity of the sub soil of proposed 150 CuM RCC Over Head Reservoir of Kaoagap Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 2417/JD | 23/12/2024 | 20 | M/S RATAN KUMAR DAS GUPTA AND CO | 37.42 | 0 | 0 | 100
340 | JALPAIGURI | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Material Requisition To Resource Division | 1108/JD | 24/08/2023 | 0 | Resource Division | 9.53 | 0 | 0 | 0
341 | JALPAIGURI | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Material Requisition To Resource Division | 1845/JD | 15/12/2023 | 0 | Resource Division | 8.44 | 0 | 0 | 0
342 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | New Service Connection Charge for CHARCHARABARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003365758 Reference ID : 403183039 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0 | 0
343 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | New Service Connection Charge for CHARCHARABARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003364338 Reference ID : 403181777 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.23 | 0 | 0 | 0
344 | JALPAIGURI | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Construction of different components of Char Charabari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Dhupguri under Jalpaiguri Division, P.H.E.Dte. | 243JD | 08/05/2023 | 732 | SRINIWAS AGARWAL | 328.17 | 0 | 0 | 50
345 | JALPAIGURI | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Balance work of distribution system and Functional House Hold Tap Connection (FHTC) including Construction of Boundary wall, drain, footpath at 2 nd site of Charchara Bari PWSS at Banarhat Block under Jalapiguri Division PHE. Dte. | 2345/JD | 12/12/2024 | 60 | SRINIWAS AGARWAL | 70.88 | 0 | 0 | 0
346 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
347 | JALPAIGURI | Jalpaiguri Division | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Char Chara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 634/JD | 28/03/2025 | 45 | JITENDRA NATH ROY | 30.36 | 0 | 0 | 0
348 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
349 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
350 | JALPAIGURI | Northern Mechanical | CHAR CHARABARI PIPED WATER SUPPLY SCHEME , SM/16042 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHARCHARABARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1208/NMD | 26/07/2023 | 615 | M/S CHANDRANATH MUKHERJEE | 22.17 | 0 | 0 | 100
351 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MALLICKSOVA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15616 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
352 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MALLICKSOVA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15616 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
353 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 0 | 0 | 1
354 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Material Requisition To Resource Division | 1114/JD | 24/08/2023 | 0 | Resource Division | 9.67 | 0 | 0 | 0
355 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Material Requisition To Resource Division | 1837/JD | 15/12/2023 | 0 | Resource Division | 5.41 | 0 | 0 | 0
356 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM SALBARI PWSS, ZONE-I, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1311/NMD | 04/08/2023 | 30 | DIAMOND ELECTRICAL WORKS | 21.32 | 0 | 0 | 50
357 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003417554 Reference ID : 403224815 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.9 | 0 | 0 | 0
358 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003420142 Reference ID : 403226820 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.31 | 0 | 0 | 0
359 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Paschim Salbari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 635/JD | 28/03/2025 | 45 | GOURAB GUHA ROY | 22.72 | 0 | 0 | 0
360 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
361 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
362 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
363 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Construction of different balance component of PASCHIM SALBARI ZONE-I PWSS i.e. Pump Houses, water distribution Network, OHR, Rising Main, FHTC etc.in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E Dte. | 2346/JD | 04/11/2025 | 120 | MD HAKIMUDDIN | 227.97 | 0 | 0 | 0
364 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/15915 | New | Construction of different components of Paschim Salbari Zone- I PWSS i.e.TW, Pump Houses , Water distribution Network, OHR, RISING MAIN, FTHC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division , P.H.E Dte. | 239/JD | 08/05/2023 | 427 | JAYANTA GHOSH | 242.01 | 0 | 0 | 12
365 | JALPAIGURI | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AIBHIL PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1313/NMD | 04/08/2023 | 630 | UTTAM PAUL | 24.24 | 0 | 0 | 90
366 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | Material Requisition To Resource Division | 2073/JD | 10/01/2024 | 0 | Resource Division | 5.79 | 0 | 0 | 0
367 | JALPAIGURI | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 100000095978 ; Reference ID : 860287638] | BP/23-24/255 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0 | 0
368 | JALPAIGURI | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | Infrastructure Cost for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 100000095977 ; Reference ID : 860287637] | BP/23-24/257 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10 | 0 | 0 | 0
369 | JALPAIGURI | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 4003293341 ; Reference ID : 403125586] | BP/23-24/256 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
370 | JALPAIGURI | Northern Mechanical | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | New Service Connection Charge for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 4003293345 ; Reference ID : 403125584] | BP/23-24/254 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
371 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Aibhil Tea Garden Area Piped Water Supply Scheme , SM/17185 | Augmentation | Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling with 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Aibhil Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 366/JD | 26/05/2023 | 632 | BARUN KUMAR DUTTA | 96.31 | 0 | 0 | 100
372 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Material Requisition To Resource Division | 1081/JD | 24/08/2023 | 0 | Resource Division | 40.23 | 0 | 0 | 0
373 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Distribution System and Functional Household Tap Connection (FHTC) for Paharpur Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 739/JD | 26/07/2024 | 614 | GOUTAM DAS | 108.29 | 0 | 0 | 60
374 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
375 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Material Requisition To Resource Division | 2005/JD | 08/01/2024 | 0 | Resource Division | 20.68 | 0 | 0 | 0
376 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341737, Reference ID : 403171420] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.18 | 0 | 0 | 0
377 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033441732, Reference ID : 403172479] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.37 | 0 | 0 | 0
378 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Construction of different components of Paharpur Zone - I Piped Water Supply Scheme i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | 1820/JD | 14/12/2023 | 535 | UNIBRO INFRASERV PRIVATE LIMITED | 616.92 | 0 | 0 | 80
379 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-I, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 487/NMD | 12/02/2024 | 659 | SUMON ELECTRICAL | 23.55 | 0 | 0 | 100
380 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
381 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PAHARPUR ZONE - I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 487/RWS | 29/05/2025 | 30 | GURUKUL INFOTECH | 4.32 | 0 | 0 | 0
382 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
383 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-I PIPED WATER SUPPLY SCHEME , SM/19097 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
384 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain , Land Development etc. at HW Site for Kumarpara PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 1296/JD | 05/09/2024 | 60 | M/S BOSE ENTERPRISE | 22.73 | 0 | 0 | 0
385 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Material Requisition To Resource Division | 2052/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0 | 0
386 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Material Requisition To Resource Division | 57/JD | 09/04/2024 | 0 | Resource Division | 31.48 | 0 | 0 | 0
387 | JALPAIGURI | Northern Mechanical | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003435868 Reference ID : 403237472 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0 | 0
388 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
389 | JALPAIGURI | Northern Mechanical | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376595 Reference ID : 403191665 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.49 | 0 | 0 | 0
390 | JALPAIGURI | Northern Mechanical | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | New Service Connection Charge for KUMARPARA, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376070 Reference ID : 403191653 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.13 | 0 | 0 | 0
391 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Construction of different components of Kumarpara PWSS i.e, TW, Pump Houses, Water distribution network , OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | 945/JD | 08/08/2023 | 966 | SCEC BOENTER KDAS JOINT VENTURE | 601.28 | 0 | 0 | 25
392 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 3rd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 839/RWS | 29/08/2024 | 412 | SUKUMAR KUNDU | 7.46 | 0 | 0 | 90
393 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 2nd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 803/RWS | 20/08/2024 | 377 | RANA DEY | 7.43 | 0 | 0 | 70
394 | JALPAIGURI | Jalpaiguri Division | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Balance Laying Distribution System including Providing Functional Household Tap Connection in connection with JJM under Kumarpara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 467/JD | 11/03/2025 | 50 | M/S BOSE ENTERPRISE | 40.13 | 0 | 0 | 0
395 | JALPAIGURI | Northern Mechanical | Kumarpara Piped Water Supply Scheme. , SM/18491 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUMARPARA PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1342/NMD | 08/08/2023 | 785 | DAS ENTERPRISE | 32.55 | 0 | 0 | 70
396 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Construction of different components of Basusuba Zone- II PWSS i.e . TW, Pump House, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division , P.H.E. Dte. | 851/JD | 28/07/2023 | 180 | R.S CONSTRUCTION | 303.82 | 0 | 0 | 0
397 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Material Requisition To Resource Division | 1083/JD | 24/08/2023 | 0 | Resource Division | 60.79 | 0 | 0 | 0
398 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
399 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Material Requisition To Resource Division | 2075/JD | 10/01/2024 | 0 | Resource Division | 17.38 | 0 | 0 | 0
400 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
401 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 100000105734 Reference ID : 860297934 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0 | 0
402 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391439 Reference ID : 403203861 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
403 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391480 Reference ID : 403203860 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
404 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105733 Reference ID : 860297933 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.19 | 0 | 0 | 0
405 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Infrastructure development cost for new service connection at BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105735 Reference ID : 860297935 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
406 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 4003391463 Reference ID : 403203857 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
407 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Construction of different components of Basusuba Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | 846/JD | 28/07/2023 | 1131 | R.S CONSTRUCTION | 368.89 | 0 | 0 | 40
408 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BASUSUBA PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1385/NMD | 09/08/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 40.19 | 0 | 0 | 100
409 | JALPAIGURI | Jalpaiguri Division | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Construction of different components of Basusuba (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | 850/JD. | 28/07/2023 | 1131 | R.S CONSTRUCTION | 200.42 | 0 | 0 | 37
410 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
411 | JALPAIGURI | Northern Mechanical | BASUSUBA PIPED WATER SUPPLY SCHEME , SM/18359 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
412 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Material Requisition To Resource Division | 1079/JD | 24/08/2023 | 0 | Resource Division | 42.92 | 0 | 0 | 0
413 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Construction of different components of Patkata Zone- II Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | 1707/JD | 04/12/2023 | 462 | M/S KAMAK ENGINEERS AND CO. | 650.27 | 0 | 0 | 65
414 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 437/SMSD | 28/03/2024 | 7 | M/S PALIDEB ENGINEERING WORKS | 0.73 | 0 | 0 | 0
415 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Material Requisition To Resource Division | 2000/JD | 08/01/2024 | 0 | Resource Division | 26.02 | 0 | 0 | 0
416 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W-II under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003341677 Reference ID : 403172273 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.2 | 0 | 0 | 0
417 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W-III under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003365627 Reference ID : 403187095 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
418 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | New Service Connection Charge for PATKATA, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341680, Reference ID : 403172795] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.12 | 0 | 0 | 0
419 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1440/NMD | 10/08/2023 | 813 | SUMON ELECTRICAL | 36.33 | 0 | 0 | 70
420 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 114/JD | 16/01/2025 | 40 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 23.77 | 0 | 0 | 0
421 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 741/JD | 26/07/2024 | 614 | PRADIP SAHA | 152.08 | 0 | 0 | 60
422 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
423 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 486/RWS | 29/05/2025 | 30 | EDIFICE ENTERPRISE | 8.05 | 0 | 0 | 0
424 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-II PIPED WATER SUPPLY SCHEME , SM/18360 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
425 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of YOUNGTONG T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte | 1080/JD | 15/10/2020 | 45 | ASHIT KUMAR SINGHA | 26.73 | 17.81 | 66.62 | 0
426 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | PROVIDING FHTC AT YOUNGTONG T.G PWSS | 1102 | 22/01/2021 | 0 | M/S.PAMPA CONSTRACTION | 4.49 | 0 | 0 | 0
427 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | iep for young tong t.g pwss | 291 | 05/09/2021 | 0 | ASHIT KUMAR SINGHA | 3.74 | 0 | 0 | 0
428 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | ADDITIONAL LDS FOR YOUNGTONG T.G PWSS | 338/21-22 | 01/10/2021 | 0 | M/S PAMPA CONSTRUCTION | 0.75 | 0 | 0 | 0
429 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | supply stesonarry | BP-2021-23-169 | 29/09/2022 | 0 | NEW KUNDU ENTERPRISE | 0.03 | 0 | 0 | 0
430 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | fhtc mohit nagar | BP-2021-22-168 | 29/09/2022 | 0 | M/S DEY & ROY CHOUDHURY | 1.14 | 0 | 0 | 0
431 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte.(Phase-I) | 07/JSSD | 13/04/2021 | 20 | R.S CONSTRUCTION | 4.13 | 4.12 | 100 | 0
432 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme , SM/06846 | Retrofitting | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte.(Phase-II). | 09/JSSD | 13/04/2021 | 20 | M/S PAMPA CONSTRUCTION | 3.52 | 3.5 | 100 | 0
433 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dakshin Altagram Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 51/JD | 08/01/2021 | 60 | UMWELT ENGINEER PRIVATE LIMITED | 38.7 | 33.23 | 85.85 | 1
434 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Paschim Mullickpara Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 41/JD | 06/01/2021 | 60 | BALAJI UDDYOG | 36.46 | 15.26 | 41.85 | 1
435 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Maynatali Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 310/JD | 26/02/2021 | 30 | SANJIT SAHA | 22.93 | 0 | 0 | 1
436 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | fhtc for khalaigram pwss | 348 | 13/09/2021 | 0 | PARESH CHANDRA GUHA | 12 | 0 | 0 | 0
437 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | RETROFITTING OF DISTRIBUTION PIPE LINE DAKSHIN DANGA PARAMOUZA | BP-2021-22-444 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0 | 0
438 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | FHTC DAKSHIN DANGA PARA | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0 | 0
439 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mainatali Mouza under Mainatali Piped Water Supply Scheme , SM/07303 | Retrofitting | Construction of Drain, Plinth Protection, Guard wall including Land Development at H/W site and stand posts for samsing T.G W/S/S under Jalpaiguri Division P.H.E.Dte. | 1009/W/JSSD | 10/01/2022 | 20 | SUBIR GHOSH | 4.65 | 0 | 0 | 1
440 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) | 1536/JD | 31/12/2020 | 30 | PRADIP SAHA | 15.67 | 15.6 | 99.52 | 1
441 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Argimaria Kamalapokori Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). | 469/RWS | 15/10/2020 | 30 | PINTU DAS | 4.73 | 0 | 0 | 1
442 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) | 1494/JD | 22/12/2020 | 45 | R.S CONSTRUCTION | 23.66 | 0 | 0 | 1
443 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Retrofitting works at related to FHTC for Arjimaria Kamalapukuri Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 67/RWS | 12/02/2021 | 10 | R.S CONSTRUCTION | 4.17 | 0 | 0 | 1
444 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-D) | 1545/JD | 31/12/2020 | 45 | R.S CONSTRUCTION | 28.69 | 28.94 | 100 | 1
445 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 0 | 0 | 1
446 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | providing FHTC for arajimaria Kamla Pukhari | BP-2021-22-238 | 23/02/2022 | 0 | R.S CONSTRUCTION | 4.94 | 0 | 0 | 0
447 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion of Arjimaria Kamalapokhori W/S Scheme in connection with JJM under Jalpaiguri Division, PHE Dte (Part-G). | 707/JD | 13/07/2023 | 30 | M/S R.K SINGHA & SONS | 30.55 | 0 | 0 | 90
448 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna including retrofitting of existing LDS under the command area of Dabgram-II piped Water Supply Scheme (South Zone) at Rajganj Block under Jalpaiguri Division, PHE Dte. Phase-I | 1250/JD | 11/11/2020 | 21 | ASIM GUPTA . | 4.32 | 3.04 | 100 | 0
449 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme , SM/06936 | Retrofitting | Repairing of Pipe Line With Other allied works related to Pipeline Under Luksaan Bazaar water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 612/JSSD | 18/02/2021 | 20 | MONOTOSH ROY | 4.9 | 4.86 | 100 | 0
450 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 745/JD | 13/05/2021 | 20 | GOURAB GUHA ROY | 14.13 | 0 | 0 | 1
451 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 1069/JD | 02/07/2021 | 21 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0 | 1
452 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- V) | 1441/JD | 09/09/2021 | 30 | RAGHU DAS | 31.64 | 0 | 0 | 1
453 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | 1340 /JD | 23/08/2021 | 30 | MONTOSH GHOSH | 30.21 | 0 | 0 | 1
454 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | ambarifalakata fhtc | BP-2021-22-98 | 16/11/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0 | 0
455 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | AMBARIFALAKATA FHTC | BP-2021-22-88 | 01/11/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0 | 0
456 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | fhtc for ambari falakata |  | 21/10/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0 | 0
457 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | LDS AMBARI FALAKATA PWSS |  | 29/10/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0 | 0
458 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi T.G. piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-D) | BP-2021-22-271 | 22/02/2022 | 0 | R.S CONSTRUCTION | 5.04 | 0 | 0 | 0
459 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC SAMSING TG | BP-2022-23-116 | 18/08/2022 | 0 | PINTU DAS | 4.75 | 0 | 0 | 0
460 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC AMBARI FALAKATA | BP-2021-22-329 | 28/02/2022 | 0 | SAPTASWA SARKAR | 21.58 | 0 | 0 | 0
461 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC PATKIDAHA | BP-2021-22-544 | 31/03/2022 | 0 | PRABIR SHOME | 5.89 | 0 | 0 | 0
462 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi Tea Garden piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-C) | BP-2021-22-272 | 22/02/2022 | 0 | R.S CONSTRUCTION | 13.45 | 0 | 0 | 0
463 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | RETROFITTING WORK FOR DAKSHIN SHALBARI | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0 | 0
464 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC KILKOTE | BP-2022-23-118 | 18/08/2022 | 0 | VEDATRAYEE AND CO. | 1.11 | 0 | 0 | 0
465 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC DAKSHIN SALBARI | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0 | 0
466 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC RAIPUR T.G | BP-2021-22-549 | 31/03/2022 | 0 | ANUP KUMAR KUNDU | 2.19 | 0 | 0 | 0
467 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC FOR LUKSHAN BAZAR . | BP-2022-23-89 | 02/08/2022 | 0 | ANUP SARKAR | 24.13 | 0 | 0 | 0
468 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC BARADIGHI WORK | BP-2022-23-115 | 17/08/2022 | 0 | PRIYABRATA KARMAKAR | 4.6 | 0 | 0 | 0
469 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | AMBARI FALAKATA | BP-2021-22-186 | 14/01/2022 | 0 | RAGHU DAS | 31.53 | 0 | 0 | 0
470 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC JOGESH CH T.G | BP-2021-22-535 | 31/03/2022 | 0 | SANDIP BANIK | 19.98 | 0 | 0 | 0
471 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | FHTC PURBADURAMARI | BP-2021-22-465 | 27/03/2022 | 0 | SIBU DEY | 28.4 | 0 | 0 | 0
472 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting with Jal Sapna under the command area of Husludanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-E) | 1906/JD | 27/09/2022 | 25 | SWAPAN SAHA | 17.2 | 0 | 0 | 0
473 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Falakata Piped Water Supply Scheme at Rajganj Block , SM/08036 | Retrofitting | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 0 | 0 | 20
474 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06954 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Caron T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. | 1548/JD | 31/12/2020 | 45 | SANDIP BANIK | 28.61 | 28.61 | 99.99 | 0
475 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06954 | Retrofitting | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 0 | 0 | 1
476 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Retrofitting works including FHTC at Shubhachandi, Futkibari Including FHTC for Garalbari Zone ¿ II . W/S/S under Jalpaiguri Division , P.H.E. Dte | 818/RWS | 30/11/2021 | 15 | BISWAJIT BHADURI | 4.38 | 0 | 0 | 1
477 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Garalbari Zone-I W/S Scheme under Jalpaiguri Division PHE Dte. (Part-E) | 545/JD | 28/02/2022 | 21 | RABINDRANATH DUTTA | 15.82 | 0 | 0 | 1
478 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | FHTC BHANDANI | BP-2022-23-71 | 04/07/2022 | 0 | DULAL CHOUDHURY | 3.34 | 0 | 0 | 0
479 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | IEP GORAL BARI | BP-2021-22-319 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.85 | 0 | 0 | 0
480 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REP OF PUMP HOUSE FOR GORALBARI PWSS | BP-2022-23-128 | 23/08/2022 | 0 | BISWAJIT BHADURI | 0.42 | 0 | 0 | 0
481 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REJ, GORALBARI | BP-2021-22-139 | 14/12/2021 | 0 | BISWAJIT BHADURI | 2.66 | 0 | 0 | 0
482 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REJ. GORALBARI PWSS | BP-2021-22-136 | 14/12/2021 | 0 | RANJIT KARMAKAR | 4.88 | 0 | 0 | 0
483 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REPAIRING & RENOVATION OHR GORALBARI ZONE -II | BP-2021-22-539 | 31/03/2022 | 0 | BISWAJIT BHADURI | 3.76 | 0 | 0 | 0
484 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REP OF PUMP HOUSE FOR GORALBARI PWSS | BP-2022-23-127 | 25/08/2022 | 0 | ASIT PAUL | 0.48 | 0 | 0 | 0
485 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | FHTC GORALBARI PWSS | bp2022-23-52 | 08/06/2022 | 0 | BISWAJIT BHADURI | 14.47 | 0 | 0 | 0
486 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | IEP GORALBARI | BP-2021-22-322 | 28/02/2022 | 0 | DREAM CONSTRACTION | 3.85 | 0 | 0 | 0
487 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REPAIRING H/W GORALBARI ZONE -II | BP-2021-22-538 | 31/03/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0 | 0
488 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REPAIRING & MAINTENANCE GORALBARI WSS | BP-2021-22-537 | 31/03/2022 | 0 | PRADIP SAHA | 4.2 | 0 | 0 | 0
489 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | FHTC GORALBARI ZONE-I | BP-2021-22-548 | 31/03/2022 | 0 | RABINDRANATH DUTTA | 14.9 | 0 | 0 | 0
490 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | rep. and renovetion of garalbari zone-ii | BP-2021-22-17 | 26/04/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0 | 0
491 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | LDS FHTC AUG BAIKUR PART V | BP-2021-22-438 | 26/03/2022 | 0 | MINTU CHAKRABORTY | 78.25 | 0 | 0 | 0
492 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | REJ. GORALBARI PWSS | BP-2021-22-138 | 14/12/2021 | 0 | BISWAJIT BHADURI | 3.12 | 0 | 0 | 0
493 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | IEP GORAL BARI | BP-2021-22-323 | 28/02/2022 | 0 | RAGHU DAS | 3.87 | 0 | 0 | 0
494 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | RE OF PUMP HOUSE B-WAAL FOR GORALBARI PWSS | bp2022-23 | 25/08/2022 | 0 | PRADIP SAHA | 0.47 | 0 | 0 | 0
495 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Sinking of 3 No. 250 mm x 150 mm x 132 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Goralbari Piped Water Supply Scheme (I, II, III) under Jalpaiguri Division P.H.E. Dte. | 1217/JD | 26/05/2022 | 30 | JAYANTA GHOSH | 22.7 | 0 | 0 | 0
496 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Pradhan Para, Choudhury Para, Haripukuri, Uttar & Dakshin Danga para, Jamuri bari and Camperhat within Garalbari Zone-II W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. | 539/JD | 25/02/2022 | 30 | BISWAJIT BHADURI | 29.32 | 0 | 0 | 100
497 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Sarkar Para, along PWD Road, Pranabananda Para, Baruapara, Moulani, Konpakri, Berubari More, Dangapara, Dhapganj etc. within Garalbari Zone-III W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division, PHE Dte. | 538/JD | 25/02/2022 | 60 | ASIM GUPTA | 92.47 | 0 | 0 | 1
498 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Retrofitting at Barodhighi,CWC Road, Baroghoria, Koharapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. | 1890/JD | 22/09/2022 | 30 | MONOJ GHOSH | 26.94 | 0 | 0 | 100
499 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Infrastructure Cost for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 100000078007, Reference ID : 860269067] | BP/23-24/73 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 23.18 | 0 | 0 | 0
500 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | New Service Connection Charge for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 4003154244, Reference ID : 403015424] | BP/23-24/73 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
501 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | New Service Connection Charge for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003119639, Reference ID : 403023006] | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
502 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | New Service Connection Charge for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003132474, Reference ID : 403012261] | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
503 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Infrastructure Cost for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000079173, Reference ID : 860270383] | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0 | 0
504 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Infrastructure Cost for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000077688, Reference ID : 860269318] | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.89 | 0 | 0 | 0
505 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 3 Nos. 20.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc for Rejuvenation of Garalbari water supply scheme (for Zone-I, Zone-II & Zone-III) under Jalpaiguri Division PHE Dte. | 678/JD | 16/03/2023 | 45 | D. S. ENTERPRISE | 53.46 | 0 | 0 | 100
506 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Rising Main Connections(3 Nos.) including other necessary arrangement for Rejuvenation of Goralbari Piped Water Supply Scheme( Zone-I, Zone-II & Zone-III) under Jalpaiguri Division, P.H.E.Dte. | 290/RWS | 29/03/2023 | 21 | BAJRANG ENTERPRISE | 5.97 | 0 | 0 | 100
507 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GARALBARI PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 342/NMD | 29/03/2023 | 30 | SUMON ELECTRICAL | 31.97 | 0 | 0 | 100
508 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Repair works of O.H.R. Pump Houses and Boundary walls .at Goralbari Zone-III Piped Water Supply Scheme Under Jalpaiguri Division PHE Dte. (2nd Call) | 814/RWS | 14/07/2023 | 21 | TAPASH MOHANTA | 4.33 | 0 | 0 | 100
509 | JALPAIGURI | Northern Mechanical | Rejuvenation of Goralbari Piped Water Supply Scheme , SM/09390 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
510 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | 665/JD | 09/03/2022 | 30 | STAR CONSTRUCTION | 9.34 | 0 | 0 | 1
511 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | 666/JD | 09/03/2022 | 30 | BONANZA ENTERPRISE | 9.34 | 0 | 0 | 1
512 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Retrofitting works in connection with Functional Household Tap Connection for Sitaguri of Ambari Falakata Water Supply Scheme i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | 297/JD | 10/02/2023 | 14 | RAGHU DAS | 2.53 | 0 | 0 | 1
513 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Material Requisition To Resource Division | 1103/JD | 24/08/2023 | 0 | Resource Division | 2.95 | 0 | 0 | 0
514 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000076455, Reference ID : 860267595] |  | 07/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
515 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000076457, Reference ID : 860267597] |  | 07/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
516 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 4003135787 ; Reference ID : 403001372] | BP/23-24/30 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
517 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135750 ; Reference ID : 403001370] | BP/23-24/30 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
518 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076455 ; Reference ID : 860267595] | BP/23-24/45 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
519 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000087936, Reference ID : 860279647] | BP/23-24/145 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.92 | 0 | 0 | 0
520 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 100000076457 ; Reference ID : 860267597] | BP/23-24/45 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
521 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000087938, Reference ID : 860279649] | BP/23-24/145 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.1 | 0 | 0 | 0
522 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 0 | 0 | 20
523 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 51/NMD | 24/01/2023 | 30 | BONANZA ENTERPRISE | 11.68 | 0 | 0 | 100
524 | JALPAIGURI | Northern Mechanical | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 50/NMD | 24/01/2023 | 30 | SAIKAT SINHA | 11.68 | 0 | 0 | 100
525 | JALPAIGURI | Central Drilling | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Providing drilling crews for construction of Tube Well (250mmX150mmX 127 Mtrs depth) by Utilizing Departmental Machineries for Ambari Falakata W/S Scheme (T/W-II ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | 1777/CDD | 02/01/2023 | 450 | PADMA ENGINEERING & CO. | 12.19 | 0 | 0 | 100
526 | JALPAIGURI | Central Drilling | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ambari Falakata W/S Scheme (T/W-I ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | 1343/CDD | 13/09/2023 | 180 | PADMA ENGINEERING & CO. | 16.67 | 0 | 0 | 100
527 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2313/JD | 07/02/2024 | 30 | SOUVIK SAHA | 8.28 | 0 | 0 | 100
528 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 4th tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2314/JD | 07/02/2024 | 30 | ARUP SARKAR | 8.34 | 0 | 0 | 100
529 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Construction of boundary wall with gate,drain and pathway including laying pipe line for 5th tubewell at Amabari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . | 1214 | 24/12/2024 | 30 | KANAI LAL SEN | 0 | 0 | 0 | 0
530 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Ambari Falakata Piped Water Supply Scheme , SM/09487 | Augmentation | Providing Functional Household Tap Connection (FHTC) in Connection with Jal Jeevan Mission under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | 472/JD | 20/06/2024 | 20 | SUBIR GHOSH | 63.03 | 0 | 0 | 0
531 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of CHAKIAVITA piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 754/JD | 13/05/2021 | 21 | ANUP SARKAR | 23.75 | 0 | 0 | 1
532 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 1339/JD | 23/08/2021 | 30 | PRADIP SAHA | 30.16 | 0 | 0 | 1
533 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- III) | 1404/JD | 03/09/2021 | 30 | SAPTASWA SARKAR | 30.86 | 0 | 0 | 1
534 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC ENGO |  | 01/10/2021 | 0 | BIMAN DAS | 2.2 | 0 | 0 | 0
535 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | RETREOFITTING WORK FOR BOAL MARI |  | 29/10/2021 | 0 | KANAI LAL SEN | 9.37 | 0 | 0 | 0
536 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC CHAKIAVITA |  | 29/10/2021 | 0 | PRADIP SAHA | 25.87 | 0 | 0 | 0
537 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | RETROFITTING WORK FOR ARAGI GORALBARI |  | 29/10/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0 | 0
538 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC CHAKIAVITA | BP-2021-22-112 | 16/11/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0 | 0
539 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC CHAKIAVITA | BP-2021-22-109 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.37 | 0 | 0 | 0
540 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | RETROFITTING WORK FOR ARAJI GORALBARI PWSS |  | 29/10/2021 | 0 | SAPTASWA SARKAR | 11.02 | 0 | 0 | 0
541 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | fhtc chakiavita | BP-2021-22-95 | 16/11/2021 | 0 | KANAI LAL SEN | 4.59 | 0 | 0 | 0
542 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | CHAKIAVITA FHTC | BP-2021-22-111 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.86 | 0 | 0 | 0
543 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | fhtc chakiavita | BP-2021-22-96 | 16/11/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0 | 0
544 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Retrofitting works in connection with Functional House Hold Tap connection under "JAL SWAPNA" for Baniapara of Chakiavita Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | 1827/JD | 18/11/2021 | 21 | JAYDEB SAHA | 11.32 | 0 | 0 | 1
545 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna within the area of Chakiavita and Kamarvita village under the command area of Chakiavita piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | 2045/JD | 07/12/2021 | 21 | BARUN KUMAR DUTTA | 39.68 | 0 | 0 | 1
546 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | CHAKIAVITA | BP-2021-22-116 | 03/12/2021 | 0 | SAPTASWA SARKAR | 3.98 | 0 | 0 | 0
547 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC RIABARI | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0 | 0
548 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC JITI | BP-2021-22-280 | 23/02/2022 | 0 | CALCON CONSTRUCTIONS | 22.07 | 0 | 0 | 0
549 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC RIABARI TG PWSS (PHASE-II) | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0 | 0
550 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC BHANGAMALI WSS | BP-2021-22-496 | 29/03/2022 | 0 | RABINDRANATH DUTTA | 16.94 | 0 | 0 | 0
551 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC NAKHATI T.G PWSS | BP-2021-22-348 | 08/03/2022 | 0 | R.S CONSTRUCTION | 4.81 | 0 | 0 | 0
552 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC JOGESH CHANDRA T.G PWSS | BP-2021-22-357 | 09/03/2022 | 0 | M/S SURAJIT DEY AND CO. | 28.14 | 0 | 0 | 0
553 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC CHAKIAVITA | BP-2021-22-167 | 14/01/2022 | 0 | SAPTASWA SARKAR | 29.39 | 0 | 0 | 0
554 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC BARADIGHI PWSS | BP-2021-22-476 | 28/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 41.29 | 0 | 0 | 0
555 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC MADHYA KHUTTIMARI | BP-2021-22-280 | 23/02/2022 | 0 | KAMALESH SEN | 9.42 | 0 | 0 | 0
556 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | CONST RCC JURANTI T.G | BP[-2021-22-463 | 27/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 3.43 | 0 | 0 | 0
557 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | FHTC AWC IN MAYNAGURI BLOCK | BP-2021-22-502 | 30/03/2022 | 0 | DREAM CONSTRUCTION | 4.84 | 0 | 0 | 0
558 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Chakiavita Piped Water Supply Scheme at Rajganj Block , SM/08285 | Retrofitting | Retrofitting works related to FHTC inconnection with Jalsapna at different locations of Chanadipa and Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | 163/RWS | 28/02/2022 | 15 | NARAYAN SARKAR | 4.47 | 0 | 0 | 1
559 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Maintenance O.H.R.Boundary walls and pump house for rejuvenation of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte. | 212/RWS | 11/03/2022 | 30 | NARAYAN CHAKRABORTY | 4.8 | 0 | 0 | 1
560 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 42/JD | 04/01/2022 | 60 | NARESH SEN | 11.16 | 0 | 0 | 0
561 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 73/JD | 06/01/2022 | 60 | NARESH SEN | 11.21 | 0 | 0 | 0
562 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Sinking of 2 No. 300 mm x 200 mm x 123 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Boalmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1231/JD | 02/06/2022 | 30 | JAYANTA GHOSH | 17.43 | 0 | 0 | 0
563 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Material Requisition To Resource Division | 1101/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0 | 0
564 | JALPAIGURI | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Infrastructure Cost for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO.100000073857, Reference ID : 860264957] | BP/22-23/167 | 28/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.92 | 0 | 0 | 0
565 | JALPAIGURI | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | New Service Connection Charge for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4003078086, Reference ID : 402978692] | BP/22-23/167 | 28/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
566 | JALPAIGURI | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Infrastructure Cost for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC | BP/23-24/02 | 18/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.15 | 0 | 0 | 0
567 | JALPAIGURI | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | New Service Connection Charge for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC | BP/23-24/02 | 18/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
568 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Boalmari water supply scheme under Jalpaiguri Division PHE Dte. | 624/JD | 13/03/2023 | 45 | KANAI LAL SEN | 33.83 | 0 | 0 | 100
569 | JALPAIGURI | Northern Mechanical | Rejuvenation of Boalmari piped water supply scheme. , SM/09462 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BOALMARI PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 336/NMD | 29/03/2023 | 30 | DEY ENTERPRISE(MALDA) | 20.32 | 0 | 0 | 100
570 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 4th tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. | 1447/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 0 | 0 | 0
571 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. | 1442/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 0 | 0 | 0
572 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2010/JD | 01/11/2022 | 15 | ABHIJIT SARKAR | 5.77 | 0 | 0 | 1
573 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2217/JD | 27/12/2021 | 60 | PINTU DAS | 11.44 | 0 | 0 | 1
574 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2216/JD | 27/12/2021 | 60 | BARUN KUMAR DUTTA | 11.45 | 0 | 0 | 1
575 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 204/NMD | 04/04/2022 | 21 | M/S ANJALI ENTERPRISE | 2.16 | 0 | 0 | 0
576 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 205/NMD | 04/04/2022 | 21 | PRATIK ROY | 2.16 | 0 | 0 | 0
577 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 277/NMD | 26/04/2022 | 30 | M/S PARITOSH BHOWMICK AND CO. | 8.37 | 0 | 0 | 0
578 | JALPAIGURI | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-I) PWSS UNDER CDD, PHE DTE. | 722/ CDD | 05/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.57 | 0 | 0 | 0
579 | JALPAIGURI | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-II) PWSS UNDER CDD, PHE DTE. | 739/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.57 | 0 | 0 | 0
580 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 278/NMD | 26/04/2022 | 30 | SUMON ELECTRICAL | 8.35 | 0 | 0 | 0
581 | JALPAIGURI | Central Drilling | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | ADDITIONAL MOBILISATION OF ALL MACHINERIES & ACCESSORIES INCLUDING LOADING & UNLOADING FROM STORE TO DRILLING SITE DWARIKAMARI (TW-I) PWSS. | 457/CMSD-II (D) | 08/10/2021 | 10 | PADMA ENGINEERING & CO. | 0.46 | 0 | 0 | 0
582 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | TUBE WELL BILL | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0 | 0
583 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | New Service Connection Charge for T/W No. IV of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932370, Reference ID : 402825217 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
584 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932367, Reference ID : 402825216 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
585 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Infrastructure cost for New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 100000052514, Reference ID : 860241674 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0 | 0
586 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Shifting of Pipeline damaged due to construction of Rest area and Truck lay bye by the NHAI in between Maynaguri BDO Office and Tekatuli for Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1739/JD | 08/09/2022 | 21 | BARUN KUMAR DUTTA | 6.49 | 0 | 0 | 1
587 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) | 2285JD | 31/12/2021 | 30 | SUBRATA GOSWAMI | 17.42 | 0 | 0 | 1
588 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | 1734/HQ/NMD | 30/10/2023 | 92 | UTTAM PAUL | 0.95 | 0 | 0 | 100
589 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Charges for shifting of LTOH Line for Dwarikamari P/H -I site under MAYNAGURI CCC APPLICATION NO. 100000120271 Reference ID : 860314461 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.01 | 0 | 0 | 0
590 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/02/2024 to 30/04/2024 = 3 Months. | 430/HQ/NMD | 31/01/2024 | 90 | UTTAM PAUL | 0.95 | 0 | 0 | 100
591 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/05/2024 to 31/07/2024 = 3 Months. | 827/HQ/NMD | 30/04/2024 | 92 | UTTAM PAUL | 0.95 | 0 | 0 | 100
592 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/08/2024 to 31/10/2024 = 3 Months. | 1306/HQ/NMD | 31/07/2024 | 92 | UTTAM PAUL | 0.95 | 0 | 0 | 0
593 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/02/2025 to 30/04/2025 = 3 Months. | 115/HQ/NMD | 17/01/2025 | 90 | UTTAM PAUL | 0.45 | 0 | 0 | 0
594 | JALPAIGURI | Northern Mechanical | Rejuvenation of Dwarikamari piped water supply scheme. , SM/09459 | Augmentation | Hiring of Maxi Cab vehicle (Non-Air conditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/05/2025 to 31/07/2025 = 3 Months. | 1047/HQ/NMD | 30/04/2025 | 92 | UTTAM PAUL | 0.45 | 0 | 0 | 0
595 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-II) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 397/JD | 10/02/2022 | 45 | SUKES BASU MAJUMDAR | 39.13 | 0 | 0 | 1
596 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Sinking of 2 No. 300 mm x 200 mm x 128 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1393/JD | 05/07/2022 | 21 | B.M CONSTRUCTION | 19.95 | 0 | 0 | 1
597 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Construction of Rig approach with partial land development for 1st site & 2nd site under Maynaguri piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. | 562/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 3.56 | 0 | 0 | 1
598 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying of new pipe line beside diversion of PWD road (damaged by PWD for connection of sasan road culvert under Maynaguri Water Supply Scheme (Zone-I). | 563/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 1.16 | 0 | 0 | 1
599 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 441/NMD | 14/06/2022 | 21 | M/S P.P. ELECTRICALS | 2.99 | 0 | 0 | 0
600 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 440/NMD | 14/06/2022 | 21 | UTTAM PAUL | 2.99 | 0 | 0 | 0
601 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 537/NMD | 08/07/2022 | 30 | ALPHA ENTERPRISE | 8.6 | 0 | 0 | 0
602 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 538/NMD | 08/07/2022 | 30 | B.B. CONCERNED | 8.6 | 0 | 0 | 0
603 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 | 07/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.73 | 0 | 0 | 1
604 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Bleaching Powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 | 13/RWS | 03/11/2022 | 92 | BHOWMIK ENTERPRISES | 0.4 | 0 | 0 | 0
605 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Bleaching powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 | 11/RWS | 04/01/2022 | 90 | SADHAN KARMAKAR | 0.4 | 0 | 0 | 1
606 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Alam) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte 01.01.2022 to 31.03.2022 | 10/RWS | 04/01/2022 | 90 | A.P CONSTRUCTION | 0.24 | 0 | 0 | 1
607 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 | 09/RWS | 04/01/2022 | 90 | PROFULLA GHOSH | 0.26 | 0 | 0 | 1
608 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 2nd Tube well site of Augmentation Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2208/JD | 27/12/2021 | 60 | PRIYABRATA KARMAKAR | 11.45 | 0 | 0 | 1
609 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | CONST RCC KHALAIGRAM | BP-2021-22-555 | 31/03/2022 | 0 | DULAL CHOUDHURY | 4.48 | 0 | 0 | 0
610 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | SOIL TEST MAYNAGURI PWSS | BP-2021-22-484 | 29/03/2022 | 0 | PRIYA ASSOCITED | 1.69 | 0 | 0 | 0
611 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | LAYING OF NEW PIPE LINE CHAMURCHI BAZAR W/S/S | BP-2021-22-556 | 31/03/2022 | 0 | NARAYAN CHANDRA SAHA | 13.02 | 0 | 0 | 0
612 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | supply of fuel | BP-2022-23-375 | 18/11/2022 | 0 | FILL & SMILE | 0.29 | 0 | 0 | 0
613 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | New Service Connection Charge for T/W No.I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 4002930314, Reference ID : 402824634 | BP/2022-23/22 | 28/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
614 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | New Service Connection Charge for T/W No. II of MAYNAGURI NEAR DHARMASHALA under MAYNAGURI CCC, APPLICATION NO. 4002932365, Reference ID : 402825215 | BP/2022-23/22 | 28/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
615 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-II, of MAYNAGURI NEAR DHARMASAKA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057038 , Reference ID : 860246648] | BP/2022-23/29 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
616 | JALPAIGURI | Northern Mechanical | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Infrastructure cost for New Service Connection Charge for T/W No. I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 100000052512, Reference ID : 860241672 | BP/2022-23/20 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.65 | 0 | 0 | 0
617 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | KAYING OF PIPELINE FOR MADHABDANGA PWSS | BP-2021-22-404 | 23/03/2022 | 0 | M/S SIBU DEY AND CO. | 2.65 | 0 | 0 | 0
618 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | LDS FHTC RAMSAI PART - II | BP-2021-22-427 | 25/03/2022 | 0 | ASHIT KUMAR SINGHA | 64.85 | 0 | 0 | 0
619 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-B) | 641/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 3.27 | 0 | 0 | 0
620 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-A) | 640/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 4 | 0 | 0 | 0
621 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MAYNAGURI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 205/JD | 24/01/2022 | 120 | SUKES BASU MAJUMDAR | 97.41 | 0 | 0 | 1
622 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Construction of Boundary wall, Pump House and Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60M x 3.00M) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri division, P.H.E. Dte. | 1392/JD | 05/07/2022 | 30 | SUKES BASU MAJUMDAR | 77.4 | 0 | 0 | 1
623 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of different Chemicals (Alam) for I.E.P at Head Work site under Maynaguri W/S/S for 3 months under Jalpaiguri Division P.H.E. Dte. Period from - 01.01.2022 to 31.03.2022 | 08/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.67 | 0 | 0 | 1
624 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Extension of pipe lines at different locations and provision of a new by pass line near NBSTC Bus Depot to facilitate FHTC L.c.w. JJM under Augmentation of Maynaguri Water Supply Scheme, under Jalpaiguri Division, P.H.E. Dte. | 331/RWS | 10/04/2023 | 14 | ARUP SARKAR | 2.96 | 0 | 0 | 100
625 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Material Requisition To Resource Division | 178/JD | 21/01/2022 | 0 | Resource Division | 69.48 | 0 | 0 | 0
626 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | SUPPLY OF ALL TYPES OF PETROLEUM PRODUCTS | BP-2023-24-112 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 1.03 | 0 | 0 | 0
627 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | SUPPLY OF DIFFERENT STATINARY ITEMS FOR OFFICE USE UNDER JALPAIGURI DIVISION P.H.E DTE. | BP-2023-24-548 | 20/12/2023 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 3.53 | 0 | 0 | 0
628 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Rising Main Connection for Augmentation of Maynaguri (Zone-I) piped Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri | 243/JD | 04/02/2023 | 30 | ARATI CONSTRUCTION | 3.57 | 0 | 0 | 100
629 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Replacement of old damaged pipe by new HDPE Pipe line at Sahidgarh area, Ward no. 15 under Augmentation of Maynaguri Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 333/RWS | 10/04/2023 | 21 | SUKES BASU MAJUMDAR | 4.95 | 0 | 0 | 100
630 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Material Requisition To Resource Division | 2210/JD | 01/12/2024 | 0 | Resource Division | 44.3 | 0 | 0 | 0
631 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | SUPPLY OF DIFFERENT STATIONARY ITEMS FOR OFFICE USE UNDER JALPAIGURI R.W.S SUB DIVISION, P.H.E. Dte. | BP-2023-24-573 | 09/01/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.21 | 0 | 0 | 0
632 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | BP-2023-24-575 | 09/01/2024 | 0 | SOUMEN GHOSH | 0.68 | 0 | 0 | 0
633 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of Fuel Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. | BP-2024-25-242 | 26/07/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0 | 0
634 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | SUPPLY OF FUEL (DIESEL) FOR VEHICLES FOR P.H.E JALPAIGURI | BP-2023-24-563 | 05/01/2024 | 0 | FILL & SMILE | 2.6 | 0 | 0 | 0
635 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of Fuel & lubricant for EXECUTIVE ENGINEER , P.H.E Dte. JALPAIGURI | BP-2023-24-578 | 10/01/2024 | 0 | FILL & SMILE | 0.83 | 0 | 0 | 0
636 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | FUEL BILL FOR GOVT. VEHICLE FOR THE MONTH OF NOVEMBER-2023 | BP-2023-24-571 | 09/01/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0 | 0
637 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | BP-2023-24-574 | 09/01/2024 | 0 | APIKUL ALI | 0.37 | 0 | 0 | 0
638 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-241 | 26/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
639 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying Distribution System and Functional House Hold Tap Connection for Augmentation of Maynaguri (Zone-II) Piped Water Supply Scheme. Block- Maynaguri. District - Jalpaiguri. | 226/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.94 | 0 | 0 | 100
640 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying Distribution System and Functional House Hold Connection for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme Block- Maynaguri, Dist. Jalpaiguri. | 225/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.12 | 0 | 0 | 100
641 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Laying Distribution line crossing through Bridge and main distribution connections at Augmentation of Maynaguri Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 814/RWS | 22/08/2024 | 30 | M/S SURAJIT DEY AND CO. | 8.68 | 0 | 0 | 100
642 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Continuation work order for "Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01/02/2025 to 31/07/2025)" | 76/RWS | 30/01/2025 | 181 | ASHIM SARKAR | 0.88 | 0 | 0 | 32
643 | JALPAIGURI | Jalpaiguri Division | Augmentation of Maynaguri Piped Water Supply Scheme. , SM/10042 | Augmentation | Providing Five Hydrant, improvement of drainage system of IEP, shifting of pipeline, repair of raod dameged due to leakage of pipeline including other ancillary work in connection with Jal Jeevan Mission under Maynaguri (Zone-l) Water Supply Scheme at block-Maynaguri under Jalpaiguri Division, PHE Dte. | 163/RWS | 15/02/2024 | 234 | B.M CONSTRUCTION | 9.81 | 0 | 0 | 100
644 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Nagaisuree Tea Garden under Jalpaiguri Division, P.H.E. Dte. | 869/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 0 | 0 | 0
645 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059931, Reference ID : 860249351] | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.16 | 0 | 0 | 0
646 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964334, Reference ID :402851949] | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
647 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059480, Reference ID : 860249200] | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
648 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964306, Reference ID :402851943] | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
649 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 71/NMD | 27/01/2023 | 30 | TALUKDER ENTERPRISE | 11.31 | 0 | 0 | 100
650 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 217/JSSD | 16/09/2022 | 60 | ARUP SARKAR | 4.65 | 0 | 0 | 100
651 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 216/JSSD | 16/09/2022 | 60 | BAJRANG ENTERPRISE | 4.65 | 0 | 0 | 0
652 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 72/NMD | 27/01/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 10.76 | 0 | 0 | 80
653 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/09858 | Augmentation | Retrofitting works for laying Distribution System of Rejuvenation of Nagaisuree T.G. Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 767/JD | 23/03/2022 | 1145 | SADHAN KARMAKAR | 64.75 | 0 | 0 | 60
654 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Replacement of existing defunct sluice valve for Gairkata Water Supply Scheme at Banarhat Development block under Jalpaiguri Division, PHE Dte. | 127/JD | 28/04/2023 | 7 | SHANTI CONSTRUCTION | 1.66 | 0 | 0 | 100
655 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Material Requisition To Resource Division | 554/JD | 01/03/2022 | 0 | Resource Division | 14.26 | 0 | 0 | 0
656 | JALPAIGURI | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W I, under DHUPGURI CCC [APPLICATION NO. 4003208335 ; Reference ID : 403057217] | BP/23-24/93 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
657 | JALPAIGURI | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W II, under DHUPGURI CCC [APPLICATION NO. 4003208338 ; Reference ID : 403057218] | BP/23-24/93 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
658 | JALPAIGURI | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003196195, Reference ID : 403048167] | BP/23-24/70 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.42 | 0 | 0 | 0
659 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Laying Distribution System including providing CI/DI Rising Main connection and providing FHTC in connection with JJM for Augmentation of Gairkata Piped Water Supply Scheme at Banarhat Block under Jalpaiguri Division, PHE Dte. | 695/JD | 17/03/2023 | 730 | M/S R.N. TRADERS | 333.21 | 0 | 0 | 8
660 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Gairkata PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | 455/JD | 18/02/2022 | 21 | MAA ENTERPRISES | 7.93 | 0 | 0 | 100
661 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation Gairkata P.W.S.S under Jalpaiguri Division P.H.E Dte. | 1191/JD | 20/05/2022 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.65 | 0 | 0 | 100
662 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd Tube Well Site of Gairkata Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 2057/JD | 25/11/2024 | 401 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 8.51 | 0 | 0 | 60
663 | JALPAIGURI | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
664 | JALPAIGURI | Northern Mechanical | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0 | 0
665 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Rejuvenation of different components of PWSS of Over Head Reservoir site at Gairkata Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1974/JD | 03/01/2024 | 515 | APEX ENGINEERING | 22.45 | 0 | 0 | 50
666 | JALPAIGURI | Jalpaiguri Division | Augmentation of Gairkata Piped Water Supply Scheme , SM/09860 | Augmentation | Rejuvenation of 2nd Tube Well Site, 3rd Tube Well Site and Head Work Site Pump House at Gairkata Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2390/JD | 19/12/2024 | 103 | BISHAL DAS | 2.48 | 0 | 0 | 100
667 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Minor Repairing of Distribution System along with FHTC works under Jalswapna Programme along with other retrofitting works ,chokage removal alog ,repairing of partially damaged C.I.D.F delivery main with other ancillary works within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division, P.H.E.Dte.(Phase-V) | 1806/JD | 14/09/2022 | 21 | JAYDEB SAHA | 4.84 | 0 | 0 | 1
668 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Laying of New Pipeline adjacent to the National Highway for implementation of Jalswapa programme along with minor retrofitting works(laying of parallel line)within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | 1448/JD | 20/07/2022 | 15 | JAYDEB SAHA | 4.85 | 0 | 0 | 1
669 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Infrastructure Cost for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 100000083812 ; Reference ID : 860275312] | BP/23-24/96 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.2 | 0 | 0 | 0
670 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | New Service Connection Charge for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 4003193586 ; Reference ID : 403045949] | BP/23-24/96 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
671 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Construction of One no Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Rejuvenation of Debpara TG Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1268/JD | 13/09/2023 | 45 | BOSE ENTERPRISE | 17.67 | 0 | 0 | 20
672 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DEBPARA TG PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1392/NMD | 09/08/2023 | 30 | UTTAM PAUL | 12.15 | 0 | 0 | 60
673 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Rejuvenation of old demage distribution system and other allied work related to pipe line at gara line area of Devpara PWSS in conection with Jal Jeevan Mission Block - Banarhat under Jalpaiguri Division, PHE Dte. | 1652/JD | 29/10/2024 | 20 | JAYDEB SAHA | 10.16 | 0 | 0 | 70
674 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Material Requisition To Resource Division | 2066/JD | 25/11/2024 | 0 | Resource Division | 0.67 | 0 | 0 | 0
675 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Laying distribution system with for Rejuvenation of Debpara T.G. Piped water Supply Scheme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | 1348/JD | 26/09/2023 | 529 | JAYDEB SAHA | 30.19 | 0 | 0 | 70
676 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/11812 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | 1520/JD | 16/10/2023 | 562 | ROY ENGINEERS | 41.28 | 0 | 0 | 100
677 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Damdim Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-II) | 186/JSSD | 31/08/2022 | 30 | BIMAN DAS | 4.83 | 0 | 0 | 0
678 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari-Kranti Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-III) | 162/JSSD | 24/08/2022 | 30 | BIMAN DAS | 4.77 | 0 | 0 | 0
679 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Oodlabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. | 1070/JSSD | 25/01/2022 | 20 | SHINE ENGINEERING CONSULTANT | 1.83 | 0 | 0 | 1
680 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Repairing Over Head Reservoir (OHR) with 2 Nos Pump House Head Works Boundary Wall and other ancillary works related to H/W site at Oodlabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 165/JD | 20/01/2022 | 45 | U TURN CONSTRUCTION | 18.63 | 0 | 0 | 0
681 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Sinking of 3 Nos. Deep Rig Bored Tube well by Odex - 165 Method of drilling for Augmentation of Oodlabari (Zone-II) Piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. | 2527/JD | 30/12/2022 | 30 | MS S R CONSTRUCTION CO | 16.6 | 0 | 0 | 0
682 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Bagrakote Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-I) | 191/JSSD | 02/09/2022 | 30 | BIMAN DAS | 3.83 | 0 | 0 | 100
683 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction of Pump House (3.60m X2.40 m) size including Sanitary and Plumbing works at 3rd Tube-Well site for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PH.E. Dte. | 100/JSSD | 25/07/2022 | 45 | BIMAN DAS | 4.75 | 0 | 0 | 100
684 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Material Requisition To Resource Division | 1088/JD | 24/08/2023 | 0 | Resource Division | 100.49 | 0 | 0 | 0
685 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 4003145975, Reference ID : 403012266] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
686 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 100000077680, Reference ID : 860269310] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.16 | 0 | 0 | 0
687 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 4003145978, Reference ID : 403012265] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
688 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 100000077681, Reference ID : 860269311] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
689 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | New Service Connection Charge for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 4003145968, Reference ID : 403012267] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
690 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Infrastructure Cost for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 10000077682, Reference ID : 860269312] | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.4 | 0 | 0 | 0
691 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
692 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Laying Water Distribution Network for Node No 200 to 130 Along the NH-17 from Ghish to Chell River for Augmentation of Odlabari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. | 2312./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 16.84 | 0 | 0 | 0
693 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction of Pump House (3.60mx2.40m) size including sanitary and plumbing works at 2nd Tube well site for Augmentation of Oolabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. | .1051/JSSD | 24/01/2022 | 45 | BIMAN DAS | 4.75 | 0 | 0 | 100
694 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 80/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 0 | 0 | 100
695 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 81/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 0 | 0 | 100
696 | JALPAIGURI | Northern Mechanical | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ODLABARI PWSS, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 373/NMD | 29/03/2023 | 30 | B.B. CONCERNED | 37.59 | 0 | 0 | 95
697 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 1259/JD | 13/09/2023 | 21 | PRITAM DUTTA | 11.83 | 0 | 0 | 100
698 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Facelifting and Interior furnishing works for Establishment Section and computer Room in ground floor at PHE Division Office under Jal;paiguri Division,P.H.E.Dte. | 504/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 10.3 | 0 | 0 | 100
699 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Sinking of One No Big dia tube well (200mm x 150mm) by Modified DTH - ODEX method of drilling at H/W Site in Augmentation of Oodlabari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2751/JD | 14/03/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 0 | 0 | 100
700 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction approach with paver block inside the premises and land development at H/W site for Augmentation of Oodlabari(Zone-I) piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 565/JSSD | 05/03/2024 | 30 | SUBHANKAR DEY | 2.76 | 0 | 0 | 100
701 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Material Requisition To Resource Division | 2220/JD | 01/12/2024 | 0 | Resource Division | 20.62 | 0 | 0 | 0
702 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 881/JD | 05/04/2022 | 1214 | CALCON CONSTRUCTIONS | 234.41 | 0 | 0 | 75
703 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 880/JD | 05/04/2022 | 1367 | M/S SURAJIT DEY AND CO. | 275.87 | 0 | 0 | 70
704 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction approach with paver block inside the premises and land development at HW site of Aug. of Oodlabari PWSS (Z-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 101/JSSD | 30/05/2025 | 30 | PRIYABRATA KARMAKAR | 6.59 | 0 | 0 | 0
705 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Oodlabari (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte | 1067/JD | 28/04/2022 | 979 | TARAKESWAR PRASAD | 84.41 | 0 | 0 | 70
706 | JALPAIGURI | Jalpaiguri Division | Augmentation of Odlabari Piped Water Supply Scheme , SM/13790 | Augmentation | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block -Mal under Jalpaiguri Division, P.H.E.Dte. | 264/JSSD | 25/09/2024 | 30 | PRITAM DUTTA | 2.47 | 0 | 0 | 100
707 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Material Requisition To Resource Division | 145/JD | 28/04/2023 | 0 | Resource Division | 14.77 | 0 | 0 | 0
708 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
709 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Balance work in connection with Laying distribution system along with providing FHTC at Zone I , II & III of Neora Majhiali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E. Dte. | 2315./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 55.21 | 0 | 0 | 0
710 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Material Requisition To Resource Division | 2030/JD | 09/01/2024 | 0 | Resource Division | 9.41 | 0 | 0 | 0
711 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
712 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "INFRA COST IRO NSC for NEORA MAJHIALI,ZIII TW NO-I,METELI CCC " APPLICATION NO.100000108813 Reference ID : 860301243 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.58 | 0 | 0 | 0
713 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 100000104809 Reference ID : 860297129 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
714 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z1 TW NO-I, MAL CCC APPLICATION NO. 100000104807 Reference ID : 860297127 " | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.11 | 0 | 0 | 0
715 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 4003377495 Reference ID : 403192837 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
716 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-II, MAL CCC " APPLICATION NO. 4003377487 Reference ID : 403192832 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
717 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Infrastructure Cost for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 100000095976 ; Reference ID : 860287636] | BP/23-24/231 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.58 | 0 | 0 | 0
718 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-I, MAL CCC " APPLICATION NO. 4003377483 Reference ID : 403192834 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
719 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | New Service Connection Charge for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 4003293335 ; Reference ID : 403125585] | BP/23-24/230 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
720 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z-I TW NO-II, MAL CCC " APPLICATION NO. 100000104808 Reference ID : 860297128 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0 | 0
721 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-I, MAL CCC " APPLICATION NO. 100000104910 Reference ID : 860297130 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0 | 0
722 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,Z II TW NO-I, MAL CCC " APPLICATION NO. 4003377491 Reference ID : 403192835 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
723 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | "New Service Connection Charge for NEORA MAJHIALI,ZIII TW NO-I, METELI CCC " APPLICATION NO.4003416347 Reference ID : 403224096 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
724 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Construction of Different components of Neora Majhiali (Zone-I, II and III) PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Matiali under Jalpaiguri Division, PHE Dte. | 244/JD | 08/05/2023 | 696 | SRINIWAS AGARWAL | 424.24 | 0 | 0 | 55
725 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEORA MAJHIALI PWSS, TW NO I,II,III,IV,V AND VI in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1338/NMD | 08/08/2023 | 570 | CHOWDHURY AND BASU ENTERPRISE | 73.75 | 0 | 0 | 60
726 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
727 | JALPAIGURI | Northern Mechanical | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
728 | JALPAIGURI | Jalpaiguri Division | NEORA MAJHIALI PIPED WATER SUPPLY SCHEME , SM/13900 | New | Sinking of 3 (three) nos. Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Neora Majhiali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2333/JD | 08/02/2024 | 419 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 61.43 | 0 | 0 | 100
729 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHARMMAPUR PWSS, TW NO I and II (ZONE-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1257/NMD | 31/07/2023 | 30 | M/S BHOWMICK & CO. | 21.55 | 0 | 0 | 100
730 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 2461/JD | 23/02/2024 | 45 | PINTU DAS | 14.74 | 0 | 0 | 10
731 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmapur Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 2267/JD | 04/12/2024 | 45 | SOMNATH ROY | 32.43 | 0 | 0 | 0
732 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Construction of Boundary Wall at 2nd site of Dharamapur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 153/RWS | 15/02/2024 | 286 | SANKAR DAS | 5.32 | 0 | 0 | 100
733 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
734 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Material Requisition To Resource Division | 2048/JD | 09/01/2024 | 0 | Resource Division | 6.84 | 0 | 0 | 0
735 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
736 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | New Service Connection Charge for DHARMAPUR, T/W No. I, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305834 ; Reference ID : 403134445] | BP/23-24/289 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.07 | 0 | 0 | 0
737 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | New Service Connection Charge for DHARMAPUR, T/W No. II, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305839 ; Reference ID : 403134438] | BP/23-24/290 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.96 | 0 | 0 | 0
738 | JALPAIGURI | Jalpaiguri Division | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Construction of different components of Dharmapur (Zone-II) PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc I.c.w. Jal Jeevan Mission at Block :- Maynaguri under Jalpaiguri Division, PHE Dte. | 95/JD | 25/04/2023 | 921 | K.R. ENTERPRISE | 322.05 | 0 | 0 | 70
739 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
740 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
741 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
742 | JALPAIGURI | Northern Mechanical | DHARMMAPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/14882 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
743 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Material Requisition To Resource Division | 1076/JD | 24/08/2023 | 0 | Resource Division | 32.73 | 0 | 0 | 0
744 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIPUCHHAPUR PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1437/NMD | 10/08/2023 | 30 | S.P. ENTERPRISE | 27.2 | 0 | 0 | 80
745 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
746 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Material Requisition To Resource Division | 2039/JD | 09/01/2024 | 0 | Resource Division | 11.29 | 0 | 0 | 0
747 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 100000104478 Reference ID : 860297008 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.67 | 0 | 0 | 0
748 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 4003352325 Reference ID : 403172833 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
749 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 4003352328 Reference ID : 403172832 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
750 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 100000104479 Reference ID : 860297009 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.89 | 0 | 0 | 0
751 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Nipucchapur TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 175/JSSD | 25/07/2025 | 30 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 7.59 | 0 | 0 | 0
752 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Construction of different components of Nipuchhapur PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 242/JD | 08/05/2023 | 821 | M/S SURAJIT DEY AND CO. | 335.86 | 0 | 0 | 60
753 | JALPAIGURI | Jalpaiguri Division | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Nipucchapur TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | 2266/JD | 04/12/2024 | 483 | MALAY BHOWMIK | 49.56 | 0 | 0 | 0
754 | JALPAIGURI | Northern Mechanical | NIPUCHHAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15296 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
755 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Providing Functional Household Tap connection (FHTC) at Paharer Hat in connection with JJM at Arji Garalbari Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P.H.E. Dte.(Part-I) | 600/JD | 09/03/2023 | 21 | RANJIT KARMAKAR | 4.85 | 0 | 0 | 100
756 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Construction of Pump House (3.60M X 2.40M) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Arji Garalbari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 169/JD | 19/01/2023 | 30 | ABHIJIT SARKAR | 10.88 | 0 | 0 | 100
757 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Retrofitting works related to FHTC at Barokamat, Dhaurapara for Argi Garalbari W/S Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) | 392/RWS | 25/04/2023 | 14 | BISWAJIT BHADURI | 3.54 | 0 | 0 | 100
758 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | New Service Connection Charge for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 4003103534 ; Reference ID : 402988696] | BP/23-24/33 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
759 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
760 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] | BP/23-24/47 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0 | 0
761 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | New Service Connection Charge for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 4003099007 ; Reference ID : 402983422] | BP/23-24/115 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
762 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Infrastructure Cost for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 100000074333 ; Reference ID : 860264763] | BP/23-24/115 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
763 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Rising Main Connections(at 3rd TW site) including other necessary arrangement for Rejuvenation of Araji Garalbari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. | 289/RWS | 29/03/2023 | 14 | ALICK DATTA | 1.81 | 0 | 0 | 100
764 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Construction of different components for Rejuvenation of Arji Garalbari PWSS i.e. TW, Pump Houses, IEP, Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri sadar under Jalpaiguri Division, P.H.E.Dte | 434/JD. | 08/06/2023 | 568 | ASIM GUPTA | 40.15 | 0 | 0 | 40
765 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI Piped Water Supply Scheme, TW No.- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 812/NMD | 20/07/2023 | 30 | M/S ANJALI ENTERPRISE | 11.53 | 0 | 0 | 100
766 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI PWSS,at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 813/NMD | 20/07/2023 | 30 | SARKAR ELECTRIC | 11.71 | 0 | 0 | 100
767 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site for Rejuvenation of Araji Garalbari water supply scheme under Jalpaiguri Division PHE Dte. | 941/JD | 08/08/2023 | 45 | LOKNATH CONSTRUCTION | 17.31 | 0 | 0 | 100
768 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
769 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ARJI GARALBARI PWSS , SM/15030 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
770 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Material Requisition To Resource Division | 1053/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0 | 0
771 | JALPAIGURI | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGARHAT PWSS, TW NO- I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1220/NMD | 26/07/2023 | 584 | GURUKRIPA ENTERPRISE | 11.5 | 0 | 0 | 80
772 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Laying distribution system for balanced DI pipeline from Ranirhat More towards Dhupguri for Bhangarhat PWSS at Maynaguri Block under Jalapaiguri Division, PHE Dte. | 2454/JD | 23/02/2024 | 14 | DIPAK KUMAR CHAKRABORTY | 11.62 | 0 | 0 | 100
773 | JALPAIGURI | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | New Service Connection Charge for REJUVENATION OF BHANGARHAT, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376107 Reference ID : 403191657 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0 | 0
774 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Balance Laying Distribution System including Providing FHTC and other allied work related to pipe line at Bhangerhat PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 103/JD | 15/01/2025 | 300 | ARATI CONSTRUCTION | 34.03 | 0 | 0 | 0
775 | JALPAIGURI | Northern Mechanical | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
776 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Bhangarhat Piped Water Supply Scheme , SM/15032 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhangarhat PWSS , in connection with Rejuvenation of Bhangarhat PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 349/JD | 24/05/2023 | 726 | DIPAK KUMAR CHAKRABORTY | 36.26 | 0 | 0 | 100
777 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Material Requisition To Resource Division | 1368/JD | 27/09/2023 | 0 | Resource Division | 22.35 | 0 | 0 | 0
778 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
779 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Kranti block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1294/RWS | 29/11/2023 | 30 | SUKES BASU MAJUMDAR | 2.34 | 0 | 0 | 100
780 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Material Requisition To Resource Division | 2018/JD | 09/01/2024 | 0 | Resource Division | 12.97 | 0 | 0 | 0
781 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | New Service Connection Charge for Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 4003373951 Reference ID : 403190123 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
782 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Infrastructure development cost for new service connection at Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 100000103006 Reference ID : 860295356 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
783 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | New Service Connection Charge for PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 4003373939 Reference ID : 403190122 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
784 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Infrastructure development cost for new service connection at PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 100000112283 Reference ID : 860304193 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0 | 0
785 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Construction of different components of Purba Dolaigaon PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | 355/JD | 24/05/2023 | 861 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 423.12 | 0 | 0 | 50
786 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Balance Laying Distribution Network including Construction of Additional Components of Purba Dolaigaon PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | 487/JD | 11/03/2025 | 60 | DEBASISH DEY | 47.56 | 0 | 0 | 0
787 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
788 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at PURBA DOLAIGAON PWSS for T/W No. I and II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 586/NMD | 07/02/2025 | 144 | S.P. ENTERPRISE | 23.88 | 0 | 0 | 80
789 | JALPAIGURI | Jalpaiguri Division | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Purba Dolaigaon PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | 480/RWS | 29/05/2025 | 30 | ADITRI ENTERPRISE | 8.36 | 0 | 0 | 0
790 | JALPAIGURI | Northern Mechanical | PURBA DOLAIGAON PIPED WATER SUPPLY SCHEME , SM/14881 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Kranti Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 56/HQ/NMD | 06/01/2025 | 7 | SUMON ELECTRICAL | 0.31 | 0 | 0 | 0
791 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 170/RWS | 28/02/2023 | 21 | SAHA CONSTRUCTION | 4.91 | 0 | 0 | 1
792 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | "Restoration of DI pipeline earlier damaged under Paschim Salbari Water Supply Scheme (Zone-1) under Jalpaiguri Division PHE Dte. " | 554/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 3.28 | 0 | 0 | 0
793 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Emergency repairing of pipe line damaged due to rural road construction and provision for laying of Gas pipe line at different location under Paschim Salbari (Zone - I) Water Supply Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) | 812/RWS | 14/07/2023 | 21 | SAHA CONSTRUCTION | 2.99 | 0 | 0 | 100
794 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM SALBARI PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 572/NMD | 17/05/2023 | 30 | M/S JIT ENTERPRISE | 23.04 | 0 | 0 | 50
795 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-II) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. | 284/RWS | 29/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 4.94 | 0 | 0 | 100
796 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of PASCHIM SALBARI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1059/HQ/NMD | 21/06/2024 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0 | 0 | 100
797 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | New Service Connection Charge for Reju. of Paschim Salbari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003531577 Reference ID : 403306437 | BP/24-25/246 | 02/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0 | 0
798 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Construction of different components for Rejuvenation of Paschim Salbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 129/JD | 28/04/2023 | 734 | NARAYAN CHANDRA SAHA | 112.5 | 0 | 0 | 50
799 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
800 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
801 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PASCHIM SALBARI PWSS , SM/15076 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
802 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Emergency restoration work of pucca road that was damaged during pipe laying at Uttar Dangapara & Dakshin Sakoajhora Piped Water Supply Scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | 122/JD | 28/04/2023 | 14 | PARESH CHANDRA GUHA | 3.91 | 0 | 0 | 100
803 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Material Requisition To Resource Division | 1056/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
804 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | 2000/JD | 19/05/2023 | 60 | NARESH SEN | 19.29 | 0 | 0 | 15
805 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 100000111357 Reference ID : 860303377 | BP/24-25/143 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.74 | 0 | 0 | 0
806 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 4003441947 Reference ID : 403241902 | BP/24-25/143 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
807 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Providing FHTC with LDS for direct boosting and Installation of Sluice Valve at different strategic point in connection with JJM of Uttar Dangapara and Dakshin Sakoajhora Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 124/JD | 16/01/2025 | 50 | SUNIL ROY | 26.06 | 0 | 0 | 0
808 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
809 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
810 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
811 | JALPAIGURI | Northern Mechanical | Rejuvenation of Uttar Danga Para & Dakshin Sakojhora Piped Water Supply Scheme , SM/15078 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1212/NMD | 26/07/2023 | 584 | TAPAN BISWAS | 11.07 | 0 | 0 | 100
812 | JALPAIGURI | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Material Requisition To Resource Division | 165/JD | 28/04/2023 | 0 | Resource Division | 36.86 | 0 | 0 | 0
813 | JALPAIGURI | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Material Requisition To Resource Division | 1509/JD | 13/10/2023 | 0 | Resource Division | 16.29 | 0 | 0 | 0
814 | JALPAIGURI | Jalpaiguri Division | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Construction of different components of Samarnagar Pwss (Zone-I and II) i.e.TW,Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc. under Jal Jeevan Mission at Block-Rajganj under Jalpaiguri Division,P.H.E. Dte. | 714/JD | 20/03/2023 | 180 | SANTALALL & BROTHERS | 431.94 | 0 | 0 | 52
815 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | New Service Connection Charge for SAMAR NAGAR, T/W-III, PRADHAN NAGAR CCC APPLICATION NO. 4003420228 Reference ID : 403226828 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.37 | 0 | 0 | 0
816 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. I, under PRADHAN NAGAR CCC [APPLICATION NO.4003283650 ; Reference ID : 403118307] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.87 | 0 | 0 | 0
817 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | New Service Connection Charge for SAMARNAGAR, T/W /W No. II, under PRADHAN NAGAR CCC [APPLICATION NO.4003283658 , Reference ID : 403118308] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.41 | 0 | 0 | 0
818 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | New Service Connection Charge for new service connection at SAMAR NAGAR, T/W-IV, PRADHAN NAGAR CCC APPLICATION NO. 4003420236 Reference ID : 403226827 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.67 | 0 | 0 | 0
819 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
820 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
821 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, AT TW NO-I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 368/NMD | 29/03/2023 | 764 | B.B. CONCERNED | 30.72 | 0 | 0 | 100
822 | JALPAIGURI | Northern Mechanical | SAMAR NAGAR PIPED WATER SUPPLY SCHEME , SM/14200 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1750/NMD | 31/10/2023 | 548 | B.B. CONCERNED | 10.36 | 0 | 0 | 100
823 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Material Requisition To Resource Division | 146/JD | 28/04/2023 | 0 | Resource Division | 32.86 | 0 | 0 | 0
824 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintenance as when as required at t/w no-I (zone-II) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 434/SMSD | 28/03/2024 | 7 | SAHA ENTERPRISE | 0.73 | 0 | 0 | 0
825 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-III) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 435/SMSD | 28/03/2024 | 7 | SARKAR ELECTRIC | 0.73 | 0 | 0 | 0
826 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Material Requisition To Resource Division | 2043/JD | 09/01/2024 | 0 | Resource Division | 23.97 | 0 | 0 | 0
827 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000121879 ; Reference ID : 860316809 | BP/24-25/245 | 26/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.08 | 0 | 0 | 0
828 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for new service connection at PANIKOURI, T/W-I, ZONE-II, BELAKOBA CCC APPLICATION NO. 4003372650 Reference ID : 403188995 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0 | 0
829 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-I, ZONE-I, under BELAKOBA CCC APPLICATION NO. 4003372565 Reference ID : 403188998 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
830 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000108541 Reference ID : 860300421 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.59 | 0 | 0 | 0
831 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-II, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372528 Reference ID : 403188999 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0 | 0
832 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKAURI ,ZONE:-III, T/W-I, under BELAKOBA CCC APPLICATION NO. 4003321772 Reference ID : 403174731 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8 | 0 | 0 | 0
833 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- II, under BELAKOBA CCC, [APPLICATION NO. 4003321779, Reference ID : 403171726] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0 | 0
834 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKAURI, T/W-III, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372640 Reference ID : 403189001 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.08 | 0 | 0 | 0
835 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- III, under BELAKOBA CCC, [APPLICATION NO. 4003321780, Reference ID : 403171055] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.24 | 0 | 0 | 0
836 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | New Service Connection Charge for PANIKOURI, ZONE-I, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003377413 Reference ID : 403192847 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.59 | 0 | 0 | 0
837 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PANI KAURI (ZONE-I,II and III) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1512/NMD | 24/08/2023 | 800 | ORIENTAL ENGINEERING CO. | 98.07 | 0 | 0 | 75
838 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Construction of different components of Panikauri PWSS Zone-I,II and III PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block -Rajganj under Jalpaiguri Division, P.H.E. Dte. | 1764/JD | 08/12/2023 | 481 | UNIBRO INFRASERV PRIVATE LIMITED | 822.43 | 0 | 0 | 25
839 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | 823/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0 | 0
840 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.04.2025 to 30.04.2025) | 109-HQ/JD | 28/03/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0 | 0
841 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at Zone- I (H/W Site , 2 nd TW site) Zone_II,(H/W Site,2nd TW Site,3rd TW Site) and Zone-III (H/W Site,2nd TW site, 3rd TW site ) of PANIKAURI piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. inconnection with JJM. | 2152/JD | 17/10/2025 | 75 | KAMAL GHOSH | 113.94 | 0 | 0 | 0
842 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | 1502/JD | 30/06/2025 | 31 | PRADIP SAHA | 0.4 | 0 | 0 | 0
843 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
844 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Sub-Soil Investigation of proposed 150 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 85-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
845 | JALPAIGURI | Jalpaiguri Division | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 86-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
846 | JALPAIGURI | Northern Mechanical | PANI KAURI PIPED WATER SUPPLY SCHEME , SM/14241 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 433/SMSD | 28/03/2024 | 7 | B.B. CONCERNED | 0.73 | 0 | 0 | 100
847 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SAJNAPARA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15620 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
848 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SAJNAPARA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15620 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
849 | JALPAIGURI | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Material Requisition To Resource Division | 157/JD | 28/04/2023 | 0 | Resource Division | 12.08 | 0 | 0 | 0
850 | JALPAIGURI | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Material Requisition To Resource Division | 1840/JD | 15/12/2023 | 0 | Resource Division | 4.51 | 0 | 0 | 0
851 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SONAKHULI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1253/NMD | 31/07/2023 | 30 | GOENKA ENTERPRISE | 20.65 | 0 | 0 | 60
852 | JALPAIGURI | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Sonakhuli Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2332./JD | 12/12/2024 | 45 | ABHIJIT SARKAR | 20.17 | 0 | 0 | 0
853 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 100000110438 Reference ID : 860302768 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.53 | 0 | 0 | 0
854 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Infrastructure development cost for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 100000110437 Reference ID : 860302767 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.17 | 0 | 0 | 0
855 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 4003424435 Reference ID : 403230061 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
856 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | New Service Connection Charge for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 4003424430 Reference ID : 403230062 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
857 | JALPAIGURI | Jalpaiguri Division | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Construction of different components of Sonakhuli PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte | 39/JD | 13/04/2023 | 812 | JAYANTA GHOSH | 196.47 | 0 | 0 | 11
858 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
859 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
860 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
861 | JALPAIGURI | Northern Mechanical | SONAKHULI PIPED WATER SUPPLY SCHEME , SM/15744 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
862 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Material Requisition To Resource Division | 1077/JD | 24/08/2023 | 0 | Resource Division | 35.1 | 0 | 0 | 0
863 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Material Requisition To Resource Division | 1886/JD | 20/12/2023 | 0 | Resource Division | 13.79 | 0 | 0 | 0
864 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Material Requisition To Resource Division | 1508/JD | 13/10/2023 | 0 | Resource Division | 13.79 | 0 | 0 | 0
865 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit). | 383/A/JD | 01/06/2023 | 183 | RUPA PRASAD | 0.88 | 0 | 0 | 50
866 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2023 to 31.05.2024)". | 1677/JD | 24/11/2023 | 182 | RUPA PRASAD | 0.88 | 0 | 0 | 100
867 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
868 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | New Service Connection Charge for new service connection at PAHARPUR, T/W-I, ZONE-II, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003427350 Reference ID : 403231842 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.78 | 0 | 0 | 0
869 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Construction of different components of Paharpur Zone - II PWSS i.e TW, pump houses,water distribution network, OHR, Rising Main, FHTC etc. at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | 130/JD | 28/04/2023 | 706 | GARGO TRADERS | 459.33 | 0 | 0 | 50
870 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-II, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 811/NMD | 20/07/2023 | 774 | M/S RATAN KUMAR DASGUPTA AND CO. | 21.52 | 0 | 0 | 60
871 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Balance Work of Distribution System for Paharpur Zone - II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | 945/JD | 07/08/2024 | 240 | PRIYABRATA KARMAKAR | 24.12 | 0 | 0 | 95
872 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
873 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
874 | JALPAIGURI | Northern Mechanical | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
875 | JALPAIGURI | Jalpaiguri Division | PAHARPUR ZONE-II PIPED WATER SUPPLY SCHEME , SM/16779 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Paharpur Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 116/JD | 16/01/2025 | 40 | JAGORAN SARKAR | 19.18 | 0 | 0 | 100
876 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GATIA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15609 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
877 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GATIA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15609 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
878 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KARBALA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15613 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
879 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KARBALA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15613 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
880 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT JOGESH CHANDRA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15600 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
881 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT JOGESH CHANDRA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15600 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
882 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Material Requisition To Resource Division | 1885/JD | 20/12/2023 | 0 | Resource Division | 12.09 | 0 | 0 | 0
883 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
884 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 735/JD | 26/07/2024 | 75 | PROVA CONSTRUCTION | 103.17 | 0 | 0 | 0
885 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.11.2023 to 31.03.2024) | 1601/JD | 08/11/2023 | 152 | SOMNATH ROY | 0.94 | 0 | 0 | 100
886 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
887 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.04.2024 to 30.08.2024) | 2946/JD | 28/03/2024 | 152 | SOMNATH ROY | 0.93 | 0 | 0 | 100
888 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Material Requisition To Resource Division | 2017/JD | 19/11/2024 | 0 | Resource Division | 36.79 | 0 | 0 | 0
889 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-226 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0 | 0
890 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 78 3405) | BP-2024-25-227 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0 | 0
891 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341713, Reference ID : 403171394] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.36 | 0 | 0 | 0
892 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-228 | 15/07/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0 | 0
893 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341706, Reference ID : 403171321] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.99 | 0 | 0 | 0
894 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 78 3405) | BP-2024-25-225 | 15/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
895 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Supply of Fuel (Diesel) of Vehicle No. WB 25 K 9449 for the Month of July 2024. | BP-2024-25-311 | 20/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
896 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Supply of different stationary items for office use under Jalpaiguri R.W.S Sub Division, P.H.E Dte. | BP-2024-25-121 | 05/06/2024 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 0.25 | 0 | 0 | 0
897 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Construction of different components of Barapatina Nutanbus Zone-I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | 352/JD | 05/06/2023 | 667 | JAYANTA GHOSH | 379.06 | 0 | 0 | 70
898 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Barapatina Nutanbus Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 118/JD | 16/01/2025 | 40 | ALOKE DEY | 18.75 | 0 | 0 | 0
899 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
900 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 485/RWS | 29/05/2025 | 30 | DEEP CONSTRUCTION | 8.05 | 0 | 0 | 0
901 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
902 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | 1735/JD | 31/07/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 0 | 100
903 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | 2001/JD | 25/09/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 0 | 50
904 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | 2404/JD | 19/11/2025 | 30 | AJIJUL HAQUE | 0.4 | 0 | 0 | 0
905 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-I PIPED WATER SUPPLY SCHEME , SM/15971 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARAPATINA NUTANBUS PWSS, ZONE-I, TW no I , II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1280/NMD | 02/08/2023 | 761 | SARKAR ELECTRIC | 22.03 | 0 | 0 | 100
906 | JALPAIGURI | Northern Mechanical | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme , SM/17181 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GATIA TEA GARDEN PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1803/NMD | 31/10/2023 | 30 | SANJIB SAHA | 20.9 | 0 | 0 | 0
907 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme , SM/17181 | Augmentation | Material Requisition To Resource Division | 1060/JD | 24/08/2023 | 0 | Resource Division | 3.73 | 0 | 0 | 0
908 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Gatia Tea Garden Area Piped Water supply Scheme , SM/17181 | Augmentation | Sinking of One No Big Dia Tube Well by Modified DTH - ODEX method for 3rd tube well site at Rejuvenation of Gatia Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2154/JD | 17/10/2025 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 16.63 | 0 | 0 | 100
909 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Porapara piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-E) | 748/JD | 13/05/2021 | 30 | DEBASISH DEY | 30 | 0 | 0 | 1
910 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Providing Functional House hold tap Connection (FHTC ) in connection with Jaldhara/ Jalsapna under the command area of PORAPARA W/S/S at Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) | 674/RWS | 27/09/2021 | 15 | SUKES BASU MAJUMDAR | 4.98 | 0 | 0 | 0
911 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PORAPARA Water Supply Scheme at Sadar Block under under Jalpaiguri Division, PHE Dte. (PART-F) | 1334/JD | 23/08/2021 | 15 | B.M CONSTRUCTION | 14.64 | 8 | 54.63 | 1
912 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | FHTC PORA PARA PWSS |  | 01/10/2021 | 0 | B.M CONSTRUCTION | 8 | 0 | 0 | 0
913 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Retrofitting work related to FHTC in connection to Jalswapna at Haldibari Bypass, Najir Para under Pora para Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. | 644/RWS | 21/10/2022 | 20 | B.M CONSTRUCTION | 4.34 | 0 | 0 | 0
914 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | PORA PARA | BP-2021-22-117 | 03/12/2021 | 0 | SUKES BASU MAJUMDAR | 4.56 | 0 | 0 | 0
915 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna, retrofitting of LDS and rising main connection of 3rd tube well & 4th Tube well site under Porapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-I) | 1298/JD | 14/06/2022 | 60 | B.M CONSTRUCTION | 91.26 | 0 | 0 | 0
916 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Porapara PWSS at block- Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. | 1973/JD | 03/01/2024 | 21 | B.M CONSTRUCTION | 21.19 | 0 | 0 | 100
917 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Porapara Piped Water Supply Scheme at Jalpaiguri Block , SM/08035 | Retrofitting | Material Requisition To Resource Division | 2218/JD | 01/12/2024 | 0 | Resource Division | 36.07 | 0 | 0 | 0
918 | JALPAIGURI | Northern Mechanical | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF JALAPARA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 335/NMD | 29/03/2023 | 30 | MUSTAFI CONCERN | 21.8 | 0 | 0 | 0
919 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Retrofiting works i.c.w.FHTC under Jalsapna including repair of damaged pipe lines during road construction at different areas under Dakshin Salbari Piped W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | 553/RWS | 01/09/2022 | 30 | NEW KUNDU ENTERPRISE | 3.16 | 0 | 0 | 1
920 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Laying Distribution System for Augmentation of Jalapara Piped Water Supply Scheme at Nagrakata & Dhupguri Block under Jalpaiguri Division, PHE Dte | 1413/JD | 03/10/2023 | 90 | BOSE ENTERPRISE | 256.04 | 0 | 0 | 25
921 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Construction of different balance components of Jalapara PWSS in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | 2757/JD | 15/03/2024 | 746 | ANUP KUMAR KUNDU | 88.77 | 0 | 0 | 5
922 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Material Requisition To Resource Division | 54/JD | 09/04/2024 | 0 | Resource Division | 114.02 | 0 | 0 | 0
923 | JALPAIGURI | Northern Mechanical | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | New Service Connection Charge for AUGMENTATION OF JALAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003418441 Reference ID : 403225407 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.58 | 0 | 0 | 0
924 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Construction of 250 CuM Over Head Reservoir (OHR) (Staging height 20 Mtr.) as per departmental design and drawing for Augmentation of Jalapara Piped Water Supply Scheme at Block - Dhupguri in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | 700/JD | 13/07/2023 | 859 | M/S. D.K. DEY & CO.. | 78.88 | 0 | 0 | 20
925 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Jalapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2375/JD | 18/12/2024 | 177 | BALARAM GHOSH & SONS | 2.88 | 0 | 0 | 90
926 | JALPAIGURI | Jalpaiguri Division | Augmentation of Jalapara Piped Water Supply Scheme , SM/10043 | Augmentation | Construction of Pump House (5.40 m X 3.60 m) size with sanitary & plumbing arrangement at head works site for Jalapara PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 126/JD | 28/04/2023 | 614 | EDIFICE ENTERPRISE | 5.91 | 0 | 0 | 100
927 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-C) | 1034/SWSD | 26/07/2023 | 45 | ROYAL ENTERPRISE | 10.03 | 0 | 0 | 0
928 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Laying distribution system, rising main, construction of pump house and tubewells along with other allied works inconnection with Jal Jeevan Mission of Augmentation PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte | 1140/SWSD | 07/08/2023 | 150 | UNIBRO INFRASERV PRIVATE LIMITED | 181.57 | 0 | 0 | 0
929 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-B) | 1232/SWSD | 14/08/2023 | 30 | SHREYANSH AUTOMOBILE | 4.95 | 0 | 0 | 0
930 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA PASCHIM DHANTALA (ZONE-II and III) PWSS, ZONE-II, TW No I,II AND ZONE-III,TW NO- I in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 1485/NMD | 17/08/2023 | 30 | SARKAR ELECTRIC | 34.22 | 0 | 0 | 70
931 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-A) | 1413/SWSD | 22/08/2023 | 30 | SANJAY KUMAR BHADRA | 4.95 | 0 | 0 | 0
932 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Laying distribution system, rising main, construction of pump house and boundary wall, installation of Iron Elimination Plant, repairing of OHR, pump house and boundary wall, sinking of tubewell along with other allied works in connection with Jal Jeevan Mission Programme for Augmentation of PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-I) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte | 1367/SWSD | 18/08/2023 | 240 | UNIBRO INFRASERV PRIVATE LIMITED | 549.31 | 0 | 0 | 0
933 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Providing Functional Household Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme for Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-I) at Rajganj Block Under Siliguri W/S Division, P.H.E. Dte. | 2049/SWSD | 07/11/2023 | 45 | S.G.CONSTRUCTION | 11.87 | 0 | 0 | 0
934 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Material Requisition To Resource Division | 2213/SWSD | 05/01/2023 | 0 | Resource Division | 76.69 | 0 | 0 | 0
935 | JALPAIGURI | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PURBA PASCHIM DHANTALA PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE | 263/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.6 | 0 | 0 | 30
936 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME , SM/18355 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
937 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Material Requisition To Resource Division | 148/JD | 28/04/2023 | 0 | Resource Division | 76.45 | 0 | 0 | 0
938 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
939 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Material Requisition To Resource Division | 2071/JD | 10/01/2024 | 0 | Resource Division | 22.22 | 0 | 0 | 0
940 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 100000105736 Reference ID : 860297936 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.88 | 0 | 0 | 0
941 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105710 Reference ID : 860298010 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.1 | 0 | 0 | 0
942 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391522 Reference ID : 403203856 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
943 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105737 Reference ID : 860297937 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.44 | 0 | 0 | 0
944 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391518 Reference ID : 403203858 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
945 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | New Service Connection Charge for CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 4003391511 Reference ID : 403203859 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
946 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Construction of different components of changmarihat Zone-I PWSS i.e TW, Pump House , Water distribution Network , OHR , Boundary wall , RISING MAIN , FHTC etc . In connection with Jal Jeevan Mission at Block kranti under Jalpaiguri Division , P.H.E Dte. | 849/JD. | 28/07/2023 | 1062 | S & P ENTERPRISE | 398.61 | 0 | 0 | 25
947 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Construction of different components of Changmarihat Zone-II PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | 848/JD. | 28/07/2023 | 1062 | S & P ENTERPRISE | 367.87 | 0 | 0 | 65
948 | JALPAIGURI | Jalpaiguri Division | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Construction of different components of Changmarihat Zone-III PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | 847/JD | 28/07/2023 | 1062 | S & P ENTERPRISE | 234.9 | 0 | 0 | 10
949 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHENGMARIHAT PWSS, TW no I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1333/NMD | 08/08/2023 | 602 | ORIENTAL ENGINEERING CO. | 38.65 | 0 | 0 | 100
950 | JALPAIGURI | Northern Mechanical | CHENGMARIHAT PIPED WATER SUPPLY SCHEME , SM/18358 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
951 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). | 34/RWS | 28/01/2021 | 15 | NARAYAN SARKAR | 4.82 | 0 | 0 | 0
952 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) | 1072/JD | 02/07/2021 | 30 | SAHA CONSTRUCTION | 23.05 | 0 | 0 | 1
953 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-II) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) | 1073/JD | 02/07/2021 | 30 | BISWAJIT BHADURI | 27.41 | 0 | 0 | 0
954 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under Arji Garalbari piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. (Part ¿ E) | 521/RWS | 30/07/2021 | 15 | RANJIT KARMAKAR | 4.75 | 0 | 0 | 0
955 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Over Hauling of the Iron Elimination plant at H/W site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte | 684/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 0 | 1
956 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Reparing and renovation of Boundary walls ( 2nd site ),pump house , including O.H.R for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte Jalpaiguri. | 681/RWS | 27/09/2021 | 30 | BISWAJIT BHADURI | 4.67 | 0 | 0 | 1
957 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under garalbari Zone- iii piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. ( part - c) | 479/RWS | 23/07/2021 | 15 | NARAYAN SARKAR | 2.53 | 0 | 0 | 0
958 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Over Hauling of the Iron Elimination plant at 2nd site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte | 682/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 0 | 0
959 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-H) | 2036/JD | 07/12/2021 | 21 | J.M. CONSTRUCTION | 13.14 | 0 | 0 | 0
960 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-G) | 2035/JD | 07/12/2021 | 21 | SOMNATH ROY | 17.26 | 0 | 0 | 0
961 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | RETROFITTING WORKS GORALBARI ZONE II | BP-2021-22-413 | 23/03/2022 | 0 | BISWAJIT BHADURI | 2.21 | 0 | 0 | 0
962 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC GORALBARI | BP-2021-22-450 | 26/03/2022 | 0 | BISWAJIT BHADURI | 27 | 0 | 0 | 0
963 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | RETROFITTING WORKS FHTC GORALBARI ZONE II | BP-2021-22- 414 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.84 | 0 | 0 | 0
964 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC GORALBARI | BP-2021-22-146 | 14/01/2022 | 0 | SAHA CONSTRUCTION | 23.03 | 0 | 0 | 0
965 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC DABGRAM | BP-2021-22-282 | 23/02/2022 | 0 | NARAYAN CHAKRABORTY | 24.81 | 0 | 0 | 0
966 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC SONGACHI T.GG | BP-2021-22-2291 | 23/02/2022 | 0 | M/S M.B. DESIGN | 15.73 | 0 | 0 | 0
967 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | fhtc charer bari | BP-2021-22-337 | 03/03/2022 | 0 | NEW KUNDU ENTERPRISE | 2.44 | 0 | 0 | 0
968 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | retrofittinbg work for kajaldighi | BP-2021-22-237 | 22/02/2022 | 0 | R.S CONSTRUCTION | 4.54 | 0 | 0 | 0
969 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | providing fhtc yong tong t.g | BP-2021-22-236 | 23/02/2022 | 0 | ASHIT KUMAR SINGHA | 8.71 | 0 | 0 | 0
970 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC GORALBARI | BP-2021-22-145 | 14/01/2022 | 0 | M/S SIBU DEY AND CO. | 37.86 | 0 | 0 | 0
971 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FROVIDING FHTC FOR SAMSING T.G | BP-2021-22-258 | 22/02/2022 | 0 | M/S. D.K. DEY & CO.. | 29.06 | 0 | 0 | 0
972 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC GORALBARI | BP-2021-22-160 | 14/01/2022 | 0 | NARAYAN SARKAR | 2.6 | 0 | 0 | 0
973 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC PURBA MAGURMARI | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0 | 0
974 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC NAYASYLI | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0 | 0
975 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | fhtc bhangarhat | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0 | 0
976 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | water sup[ply arrangement for angawari center | BP-2021-22-277 | 22/02/2022 | 0 | R.S CONSTRUCTION | 18.98 | 0 | 0 | 0
977 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | IEP GORALBARI | BP-2021-22-324 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.87 | 0 | 0 | 0
978 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | fhtc rej nagrakata | BP-2021-22-338 | 03/03/2022 | 0 | ANUP KUMAR KUNDU | 28.29 | 0 | 0 | 0
979 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | retrofitting work for goralbari pwss | BP-2021-22-253 | 22/02/2022 | 0 | NEW KUNDU ENTERPRISE | 1.33 | 0 | 0 | 0
980 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC PURBA MAGURMARI | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0 | 0
981 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | PROVIDING FHTC PORAPARA | BP-2021-22-270 | 22/02/2022 | 0 | DEBASISH DEY | 5.57 | 0 | 0 | 0
982 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing fhtc for boalmari pwss | BP-2021-22-254 | 22/02/2022 | 0 | KANAI LAL SEN | 3.62 | 0 | 0 | 0
983 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | FHTC GORALBARI | BP-2021-22-448 | 26/03/2022 | 0 | ASHIM GUPTA | 62.4 | 0 | 0 | 0
984 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Garalbari Zone ¿ I . W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ C ) | 874/RWS | 08/12/2021 | 10 | SAPTASWA SARKAR | 2.71 | 0 | 0 | 0
985 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal sapna under the command area of Garalbari zone - I. Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte ( Part - D ) | 172/RWS | 03/03/2022 | 15 | SAHA CONSTRUCTION | 3.41 | 0 | 0 | 0
986 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Retrofitting works related to FHTC at Baraghaoria, Bhutiakhola for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte | 164/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 2.21 | 0 | 0 | 0
987 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Retrofitting works related to FHTC at Nijbari,Hazari Para,Ambari,Harinagar for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte | 161/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 4.85 | 0 | 0 | 0
988 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Retrofiting works at Tariapara, Barua para, Nawa para, Khansaheb para related to FHTC for Garalbari Zone ¿I WSS under Jalpaiguri Division , P.H.E. Dte. | 171/RWS | 03/03/2022 | 15 | SAPTASWA SARKAR | 3.84 | 0 | 0 | 0
989 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Retrofitting work related to FHTC at Balipara, Hazaripara and adjacent area within Garalbari zone-II W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | 1552/JD | 05/08/2022 | 21 | BISWAJIT BHADURI | 18.01 | 0 | 0 | 0
990 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Krishimandi, Petrol pump and adjacent area within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-L) | 1862/JD | 20/09/2022 | 25 | ASIM GUPTA | 15.65 | 0 | 0 | 1
991 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 0 | 0 | 0
992 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 0 | 0 | 100
993 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Goralbari Piped Water Supply Scheme , SM/08038 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-F) | 1074/JD | 02/07/2021 | 45 | M/S SIBU DEY AND CO. | 36.93 | 0 | 0 | 0
994 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block , SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Engo T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 561/JSSD | 01/02/2021 | 15 | JOYDEB SAHA | 4.64 | 4.64 | 99.98 | 0
995 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block , SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-C) | 63/JSSD | 13/05/2021 | 15 | BIMAN DAS | 2.34 | 0 | 0 | 0
996 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block , SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-D) | 59/JSSD | 12/05/2021 | 15 | PRITAM DUTTA | 1.87 | 1.73 | 92.49 | 0
997 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block , SM/07301 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-B) | 68/JSSD | 19/05/2021 | 15 | NABIN PRODHAN | 2.35 | 0 | 0 | 0
998 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Engo Tea Garden Piped Water Supply Scheme at Matiali Block , SM/07301 | Retrofitting | Preparation of D.P.R. (consultancy work) in connection with Augmentation of Matially PWSS (Matially block) under Jalpaiguri Division PHED | .93/JSSD | 10/06/2021 | 30 | SUBHANKAR GHOSH | 1.99 | 0 | 0 | 0
999 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PURBA MAGURMARI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 291/JD | 23/02/2021 | 30 | A.P CONSTRUCTION | 24.41 | 0 | 0 | 1
1000 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 1075/JD | 02/07/2021 | 30 | ARATI CONSTRUCTION | 24.34 | 0 | 0 | 1
1001 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna at Purba Magurmari and Paschim Magurmari village under the command area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 1690/JD | 28/10/2021 | 30 | ANUP SARKAR | 24.44 | 0 | 0 | 1
1002 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Purba Magurmari and Paschim Magurmari and Jhar Magurmari village under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | 2044/JD | 07/12/2021 | 21 | ARATI CONSTRUCTION | 39.59 | 0 | 0 | 1
1003 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | fhtc for purba magurmari pwss |  | 21/10/2021 | 0 | MONOJ GHOSH | 16.71 | 0 | 0 | 0
1004 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | FHTC PURBA MAGURMARI | BP-2021-22-90 | 01/11/2021 | 0 | MANOJ GHOSH | 16.71 | 0 | 0 | 0
1005 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | fhtc for purba magurmari pwsws |  | 21/10/2021 | 0 | ARATI CONSTRUCTION | 17.45 | 0 | 0 | 0
1006 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works at various mouza under command area of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | 1291/JD | 14/06/2022 | 21 | ARATI CONSTRUCTION | 4.8 | 0 | 0 | 1
1007 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Material Requisition To Resource Division | 2205/JD | 01/12/2024 | 0 | Resource Division | 28.93 | 0 | 0 | 0
1008 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Laying of Distribution System along with Functional Household Tap Connection (Phase-VI) in connection with Jal Jeevan Mission under Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 628/JD | 13/03/2023 | 765 | SANKAR DAS | 43.78 | 0 | 0 | 60
1009 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block , SM/07891 | Retrofitting | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 30
1010 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Water Supply Arrangement for Anganwadi Center in different location within Maynaguri Block (Other than PWSS) under Jalpaiguri Division, P.H.E. Dte. | 2043/JD | 07/12/2021 | 21 | R.S CONSTRUCTION | 23.13 | 0 | 0 | 0
1011 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Rungamuttee Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. | 245/JD | 27/01/2022 | 60 | B.M CONSTRUCTION | 95.02 | 0 | 0 | 0
1012 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing drinking water arrangement in (all type) / Health Centre under Matialy Block(Phase-II) under Mal Sub-Division under Jalpaiguri Division, P.H.E. Dte. | 1056/JSSD | 24/01/2022 | 15 | ALICK DUTTA | 4.31 | 0 | 0 | 0
1013 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Drinking water arrangement in AWC/School (all type) Health Centre under Matialy Block (Phase - I) under Mal Sub-Division, under Jalpaiguri Division, P.H.E. Dte. | 1045/JSSD | 24/01/2022 | 15 | DREAM CONSTRUCTION | 4.65 | 0 | 0 | 0
1014 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) in connection for Jal sapna in AWC,Govt.School & others institution under the command area of different piped Water Supply Scheme in Maynaguri Block under Jalpaiguri Division , P.H.E. Dte ( PHASE-II ) | 177/RWS | 03/03/2022 | 15 | DREAM CONSTRUCTION | 4.84 | 0 | 0 | 0
1015 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Functional House Hold Tap Connection in connection with Jalswapna in School ICDS Centre and Health Centre at various water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. | 996/JSSD | 05/01/2022 | 15 | ALICK DUTTA | 4.49 | 0 | 0 | 0
1016 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Oodlabari Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. | 129/JD | 14/01/2022 | 60 | M/S R.N. TRADERS | 94.96 | 0 | 0 | 0
1017 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centres other than PWSS in different Location Within Chengmari Gram Panchayet under Jalpaiguri Division, P.H.E. Dte.(Phase-II) | 1062/JSSD | 24/01/2022 | 30 | DINABANDHU ROY | 4.57 | 0 | 0 | 0
1018 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking Water Supply Arrangement in Anganwadi Centers in other than PWSS different location within Tesimla Gram Panchayat under Jalpaiguri Division, P.H.E. Dte. | 736/JD | 17/03/2022 | 45 | PROSENJIT BASAK | 62.1 | 0 | 0 | 0
1019 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  | 15/03/2022 | 0 | SUKES BASU MAJUMDAR | 92 | 0 | 0 | 0
1020 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ANGANWADI SADAR BLOCK | BP-2021-22-411 | 23/03/2022 | 0 | SUKES BASU MAJUMDAR | 21.02 | 0 | 0 | 0
1021 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | ANGANWADI CENTER | BP-2022-23-132 | 25/08/2022 | 0 | ALICK DUTTA | 4.34 | 0 | 0 | 0
1022 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | DRINKING WATER SUPPLY ANGANWADI RUNGAMUTTE GP | BP-2021-22-397 | 22/03/2022 | 0 | B.M CONSTRUCTION | 94.71 | 0 | 0 | 0
1023 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  | 15/03/2022 | 0 | RAGHU DAS | 4.99 | 0 | 0 | 0
1024 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  | 15/03/2022 | 0 | M/S R.N. TRADERS | 92.97 | 0 | 0 | 0
1025 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | LDS FHTC BHUSKADANGA | BP-2021-22-529 | 30/03/2022 | 0 | MRINMOY KANTI DUTTA | 13.77 | 0 | 0 | 0
1026 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  | 15/03/2022 | 0 | GOUTAM DAS | 4.99 | 0 | 0 | 0
1027 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGE MENT FOR ANGANWADI CENTER |  | 15/03/2022 | 0 | PRADIP SAHA | 4.99 | 0 | 0 | 0
1028 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | DRINKING WATER SUPPLY ARRANGEMENT AWC UNDER TISIMLA GP | BP-2021-22-30 | 28/04/2022 | 0 | PROSENJIT BASAK | 11.61 | 0 | 0 | 0
1029 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | DRINKING WATER SUPPLY ARRANGEMENT FOR AWC WITH IN ODLABARI G.P | BP-2021-22-11 | 25/04/2022 | 0 | M/S R.N. TRADERS | 82.53 | 0 | 0 | 0
1030 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | WATER SUPPLY ARRANGEMENT FOR ANGANWADI CENTER | BP-2022-23-133 | 25/08/2022 | 0 | ALICK DUTTA | 4.28 | 0 | 0 | 0
1031 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at different Institutions within Jalpaiguri Sadar Block in connection with Jalsapna under Jalpaiguri Division , P.H.E. Dte . | 162/RWS | 28/02/2022 | 30 | BISWAJIT BHADURI | 4.79 | 0 | 0 | 0
1032 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Tap water supply connection in connection related to Jalswapna in school, ICDS Centre and Health Centre at Oodlbari, Syli T.G. Aibhil TG. Karbala TG & Malbazar Municipality Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 988/JSSD | 03/01/2022 | 15 | SOUVIK SAHA | 4.64 | 0 | 0 | 0
1033 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking water supply arrangement in anganwadi centers other than PWSS in different location within Chapadanga Gram Panchayet under Jalpaiguri Division, P.H.E. Dte. (Phase-I) | 1058/JSSD | 24/01/2022 | 15 | D. S. ENTERPRISE | 4.56 | 0 | 0 | 0
1034 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Repairing of Rig Bore Tubewell/Tara Tubewell/Hand Pump Tubewell of different School and Anganwadi Centres under Mal & Kranti Block under Jalpaiguri Division, P.H.E. Dte. | 364/JD | 20/02/2023 | 14 | RAGHU DAS | 1.63 | 0 | 0 | 0
1035 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Providing Functional Household Tap Connection (FHTC) at Anganwadis, Health Centres and Schools in connection with Jal Swapna under the command area of different piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) | 1993/JD | 03/12/2021 | 15 | SAPTASWA SARKAR | 19.19 | 0 | 0 | 0
1036 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Drinking water supply arrangement in anganwadi Centres other than PWSS in different location within Chapadanga Gram Panchayet under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | 1063/JSSD | 24/01/2022 | 20 | N.M. CONSTRUCTION | 4.57 | 0 | 0 | 0
1037 | JALPAIGURI | Jalpaiguri Division | Water Supply Arrangement for Anganwadi Centre having Electric Power Connection and within the command area of PWSS (Phase-I). , SM/08965 | Anganwadi | Dringking water supply arrangement in Anganwadi Center other than PWSS in different location Chengmari Gram Panchayat under Jalpaiguri Division PHE.Dte (PHASE - I) | 1110/W/JSSD | 27/01/2022 | 20 | GOURAB GUHA ROY | 4.57 | 0 | 0 | 0
1038 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. , SM/08581 | New | Material Requisition To Resource Division | 2104/JD | 25/11/2024 | 0 | Resource Division | 3.02 | 0 | 0 | 0
1039 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. , SM/08581 | New | New Service Connection Charge for RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, T/W-II, under BANARHAT CCC APPLICATION NO. 4003418390 Reference ID : 403225711 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.64 | 0 | 0 | 0
1040 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. , SM/08581 | New | New Service Connection Charge for RED BANK TEA GARDEN (CHAA SUNDARI), T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333225 , Reference ID : 403157470] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.76 | 0 | 0 | 0
1041 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. , SM/08581 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block - DHUPGURI, district Jalpaiguri. | 357/NMD | 23/05/2022 | 1166 | M/S BHOWMICK & CO. | 12.59 | 0 | 0 | 90
1042 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Red Bank Tea Garden in relation with Chaa Sundari Project. , SM/08581 | New | Construction of Different Components of Supply Of Potable Drinking Water To Red Bank Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 2331/JD | 08/02/2024 | 449 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 90.89 | 0 | 0 | 75
1043 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Construction of Boundary wall including repairing of Pump House at 2nd Site for Kharija Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1438/JD | 09/09/2021 | 30 | PROFULLA GHOSH | 9.74 | 0 | 0 | 0
1044 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | SOIL INVESTIGATION WORK AUGMENTATION KHARIJA BERUBARI (ZONE -I) PWSS | BP-2021-22-353 | 08/03/2022 | 0 | GEOCON INDIA | 2.03 | 0 | 0 | 0
1045 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | SOIL INVESTIGATION | BP-2021-22-316 | 28/02/2022 | 0 | MOYTEC | 2.03 | 0 | 0 | 0
1046 | JALPAIGURI | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Augmentation of KharijaBerubari PWSS (Zone-I), Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. | 1411/NMD | 13/12/2022 | 30 | ALPHA ENTERPRISE | 11.43 | 0 | 0 | 0
1047 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Material Requisition To Resource Division | 559/JD | 01/03/2022 | 0 | Resource Division | 96.47 | 0 | 0 | 0
1048 | JALPAIGURI | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | New Service Connection Charge for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003207489, Reference ID : 403056596] | BP/23-24/86 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1049 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER | BP-2023-24-545 | 18/12/2023 | 0 | FILL & SMILE | 0.54 | 0 | 0 | 0
1050 | JALPAIGURI | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | New Service Connection Charge for NANDANPUR,KHARIJA BERUBARI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212076, Reference ID : 403060257] | BP/23-24/103 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
1051 | JALPAIGURI | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Infrastructure Cost for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086246, Reference ID : 860277656] | BP/23-24/86 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0 | 0
1052 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | SUPPLY OF DIFFERENT STATIONARY FOR OFFICE USE | BP-2023-24-363 | 13/09/2023 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 4.59 | 0 | 0 | 0
1053 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Distribution System and Functional Household Tap Connection for Augmentation of Kharija Berubari Zone-II Piped Water Supply Scheme Block - Jalpaiguri District - Jalpaiguri. | 1099/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 554.56 | 0 | 0 | 90
1054 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement and Boundary Wall, Foot Path, Drain of 2nd Site at Kharija - I Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1369/JD | 13/09/2024 | 566 | ALICK DUTTA | 12.67 | 0 | 0 | 65
1055 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF KHARIJA BERUBARI PIPED WATER SUPPLY SCHEME (ZONE-II), Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 335/JD | 02/02/2022 | 120 | NARAYAN CHANDRA SAHA | 97.85 | 0 | 0 | 100
1056 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Construction of 400 m3 OHR as per Departmental Design & Drawing & Pump House (3.60m x 2.40m) internal size with sanitary & Plumbing arrangement at Head Work site for AUGMENTATION OF KHARIJA BERUBARI (Zone-I) Piped Water Supply Scheme Block- Jalpaiguri, District : Jalpaiguri. | 1845//JD | 15/09/2022 | 180 | SUKES BASU MAJUMDAR | 87.97 | 0 | 0 | 100
1057 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Sinking of 250mm x 150mm dia tube wells by Reverse Rotary method of drilling for Augmentation of Kharija Berubari Zone-I PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division (H/W and 2nd Site) | 848/JD | 06/04/2023 | 30 | SHYAMAL KUMARSAHA | 17.39 | 0 | 0 | 100
1058 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.01.2024 to 29.02.2024) | 2121/JD | 17/01/2024 | 60 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 50
1059 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Supply of different forms for office use under jalpaiguri Division, P.H.E. Dte. | 2721/JD | 12/03/2024 | 7 | SUBRATA ART PRESS | 0.7 | 0 | 0 | 100
1060 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.03.2024 to 30.04.2024)" | 2488/JD | 27/02/2024 | 60 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
1061 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Material Requisition To Resource Division | 2215/JD | 01/12/2024 | 0 | Resource Division | 35.61 | 0 | 0 | 0
1062 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | SUPPLY OF ONE MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 C.C. ON HIRE BESIS INCLUDING DRIVER UNDER OFFICE OF THE ASSISTANT ENGINEER ,JALPAIGURI SADAR SUB DIVISION , P.H.E Dte. | BP-2023-24-592 | 16/01/2024 | 0 | MRITYUNJAY SIKDAR | 0.54 | 0 | 0 | 0
1063 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. | BP-2023-24-591 | 16/01/2024 | 0 | FILL & SMILE | 1.02 | 0 | 0 | 0
1064 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Distribution system and functional household tap connection for Augmentation of Kharija Berubari Zone-I piped Water Supply Scheme Block- Jalapiguri, District - Jalpaiguri. | 1066/JD | 28/04/2022 | 1283 | M/S R.N. TRADERS | 605.44 | 0 | 0 | 85
1065 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Construction of IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Kharija Berubari - II Pipe Water Supply Scheme under Jalpaiguri Sadar Block Within Jalpaiguri PHE Division, Jalpaiguri. | 1176/JD | 23/08/2024 | 586 | NARAYAN CHANDRA SAHA | 72.2 | 0 | 0 | 80
1066 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Sinking of Additional 1 No Tube Well by Reverse Rotary Method including construction Pump House, Boundary Wall and installation of Iron Elimination Plant (IEP) and Inter Connection work at Gosaimore under Nagar Berubari GP of Augmentation of Kharija Berubari Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, PHE Dte. | 678/JD | 04/04/2025 | 120 | KANAI LAL SEN | 38.97 | 0 | 0 | 0
1067 | JALPAIGURI | Northern Mechanical | Augmentation of Kharija-Berubari Water Supply Scheme. , SM/10088 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIJA BERUBARI PWSS, ZONE-I, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1272/NMD | 02/08/2023 | 638 | SANJIB SAHA | 23.13 | 0 | 0 | 100
1068 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Carron T.G piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 470/JSSD | 05/10/2021 | 15 | SANDIP BANIK | 4.63 | 0 | 0 | 0
1069 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0 | 0 | 0
1070 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.04.2023 to 30.04.2023. | 503/JSSD | 30/03/2023 | 30 | TANMOY CHOUDHURY | 0.15 | 0 | 0 | 0
1071 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0 | 0 | 0
1072 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Supply of fuel | BP-2023-24-117 | 01/06/2023 | 0 | FILL & SMILE | 0.66 | 0 | 0 | 0
1073 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Construction of Boundary wall with gate, drain and pathway for 4th tube well site at Caron T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1042/JSSD | 24/01/2022 | 20 | SK. MOBIN HUSSAIN | 3.75 | 0 | 0 | 0
1074 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Caron Tea Garden under Jalpaiguri Division, P.H.E. Dte. | 870/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 0 | 0 | 100
1075 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Construction of Pump House (3.60 M X 2.40 M)size with sanitary & plumbing arrangement at 3rd Tube-Well site for Caron T.G.PWSS under Jalpaiguri Division P.H.E.Dte. | 1027/W/JSSD | 31/01/2022 | 1021 | SARKAR ASSOCIATES | 4.64 | 0 | 0 | 100
1076 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at CARRON Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. | 112/JSSD | 27/07/2022 | 15 | SANDIP BANIK | 4.75 | 0 | 0 | 100
1077 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Material Requisition To Resource Division | 2096/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0 | 0
1078 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Infrastructure Cost for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000098886, Reference ID : 860291136] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.52 | 0 | 0 | 0
1079 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | New Service Connection Charge for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 4003352267, Reference ID : 403172839] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
1080 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Infrastructure Cost for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 100000101246, Reference ID : 860293456] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0 | 0
1081 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | New Service Connection Charge for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 4003320133, Reference ID : 403147059] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
1082 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CARON TG PWSS, TW No III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1811/NMD | 31/10/2023 | 30 | M/S B.ENTERPRISE | 30.99 | 0 | 0 | 80
1083 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Caron T.G. P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | 1011/W/JSSD | 27/01/2022 | 1071 | GOURAB GUHA ROY | 3.76 | 0 | 0 | 100
1084 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Construction of different components of rejuvenation of Carron Tea Garden PWSS at 4th TW site i.e. Steel staging OHR, Water Distribution Network, FHTC, interconnection, etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 939/JD | 07/08/2024 | 603 | SANKAR DAS | 15.03 | 0 | 0 | 90
1085 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
1086 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Caron Tea Garden Mouza , SM/09859 | Augmentation | Laying Rising Main for Rejuvenation of Carron Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 800/JD.. | 29/03/2023 | 614 | TECHNO CRACY | 2.84 | 0 | 0 | 100
1087 | JALPAIGURI | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Material Requisition To Resource Division | 161/JD | 28/04/2023 | 0 | Resource Division | 131.96 | 0 | 0 | 0
1088 | JALPAIGURI | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Material Requisition To Resource Division | 2058/JD | 09/01/2024 | 0 | Resource Division | 8.7 | 0 | 0 | 0
1089 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | New Service Connection Charge for Dakshin Putimari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003388138 Reference ID : 403201474 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0 | 0
1090 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | New Service Connection Charge for Dakshin Putimari, T/W-I under BHOTPATTY CCC APPLICATION NO. 4003378682 Reference ID : 403193481 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0 | 0
1091 | JALPAIGURI | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
1092 | JALPAIGURI | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Construction of different components of Dakshin Putimari PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN , FHTC etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. | 778/JD | 27/03/2023 | 1102 | ASHIT KUMAR SINGHA | 363.4 | 0 | 0 | 45
1093 | JALPAIGURI | Jalpaiguri Division | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Additional work for Laying pipe line at Dakshin Putimari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 1171/JD | 23/08/2024 | 586 | PAMPA CONSTRUCTION | 20.26 | 0 | 0 | 65
1094 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
1095 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
1096 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1097 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1098 | JALPAIGURI | Northern Mechanical | DAKHSIN PUTIMARI PIPED WATER SUPPLY SCHEME , SM/13700 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN PUTIMARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 333/NMD | 29/03/2023 | 856 | RIPON DAS | 21.5 | 0 | 0 | 100
1099 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Material Requisition To Resource Division | 176/JD | 28/04/2023 | 0 | Resource Division | 16.8 | 0 | 0 | 0
1100 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 100000082758, Reference ID : 860274518] | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.77 | 0 | 0 | 0
1101 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 4003177288, Reference ID : 403033824] | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1102 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 100000082757, Reference ID : 860274517] | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
1103 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 4003177279, Reference ID : 403033822] | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1104 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1105 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Material Requisition To Resource Division | 2035/JD | 09/01/2024 | 0 | Resource Division | 7.13 | 0 | 0 | 0
1106 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
1107 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | "ADDITIONAL INFRA COST IRO NSC for UTTAR DHUPJHORA TW-II,METELI CCC " APPLICATION NO.100000115577 Reference ID : 860310307 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0 | 0
1108 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Construction of Different Components of Uttar Dhupjhora PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | 716/JD | 20/03/2023 | 835 | BOSE ENTERPRISE | 231.68 | 0 | 0 | 50
1109 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
1110 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Construction of IEP and Blower Room of Uttar Dhupjhora PWSS in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. | 2329./JD | 12/12/2024 | 264 | BOSE ENTERPRISE | 17.26 | 0 | 0 | 20
1111 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
1112 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0 | 0
1113 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1114 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR DHUPJHORA PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1277/NMD | 02/08/2023 | 607 | M/S SWAPAN BANERJEE | 24.39 | 0 | 0 | 100
1115 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UTTAR DHUPJHORA , SM/13988 | New | Laying of Distribution pipeline at the uncovered portions within the command area of Uttar Dhupjhora Piped W/S Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. | 258/JSSD | 25/09/2024 | 83 | TANMOY CHOUDHURY | 4.63 | 0 | 0 | 100
1116 | JALPAIGURI | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Material Requisition To Resource Division | 1116/JD | 24/08/2023 | 0 | Resource Division | 23.05 | 0 | 0 | 0
1117 | JALPAIGURI | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Material Requisition To Resource Division | 1841/JD | 15/12/2023 | 0 | Resource Division | 11.08 | 0 | 0 | 0
1118 | JALPAIGURI | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Dhupguri block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1293/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
1119 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003332348 , Reference ID : 403156800] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0 | 0
1120 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328084 , Reference ID : 403153544] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.26 | 0 | 0 | 0
1121 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003332367 , Reference ID : 403156921] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.73 | 0 | 0 | 0
1122 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR ALTAGRAM PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1371/NMD | 09/08/2023 | 754 | M/S SAJAHAN CHOWDHURY | 33.24 | 0 | 0 | 95
1123 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
1124 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
1125 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
1126 | JALPAIGURI | Northern Mechanical | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1127 | JALPAIGURI | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Balance work of Distribution System for Uttar Altagram Piped Water Supply Scheme within Dhupguri Block under Jalpaiguri Division, PHE Dte. | 2002/JD | 25/09/2025 | 90 | KAMAL DAS | 72.36 | 0 | 0 | 60
1128 | JALPAIGURI | Jalpaiguri Division | UTTAR ALTAGRAM PIPED WATER SUPPLY SCHEME , SM/13899 | New | Construction of different components of Uttar Altagram PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | 351/JD | 24/05/2023 | 534 | SUKES BASU MAJUMDAR | 446.33 | 0 | 0 | 100
1129 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Material Requisition To Resource Division | 1879/JD | 20/12/2023 | 0 | Resource Division | 11.14 | 0 | 0 | 0
1130 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Material Requisition To Resource Division | 162/JD | 28/04/2023 | 0 | Resource Division | 103.77 | 0 | 0 | 0
1131 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E. Dte. (Part-A) | 692/JD | 19/07/2024 | 120 | B.M CONSTRUCTION | 50.78 | 0 | 0 | 100
1132 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. (Part- B) | 1533/JD | 01/10/2024 | 45 | SUKES BASU MAJUMDAR | 66.83 | 0 | 0 | 100
1133 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003388992 Reference ID : 403201630 |  | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
1134 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | New Service Connection Charge for MADHYA DAUKIMARI, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003256198, Reference ID : 403097555] | 23-24/169&172 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.83 | 0 | 0 | 0
1135 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Infrastructure Cost for MADHYA DAUKIMARI , T/W-I, under DHUPGURI CCC [APPLICATION NO. 4003269038 , Reference ID : 403107836] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0 | 0
1136 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Additional New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 100000103797 Reference ID : 860296017 |  | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1137 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Balance Laying Distribution System and Sinking of Additional Tube Well by Reverse Rotary including construction of Pump House and laying Rising Main etc. in connection with Jal Jeevan Mission of Madhya Daukimari PWSS at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | 456/JD | 10/03/2025 | 387 | B. M CONSTRUCTION | 71.85 | 0 | 0 | 0
1138 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
1139 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
1140 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
1141 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1142 | JALPAIGURI | Jalpaiguri Division | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Construction of different components of Madhya Daukimari PWSS i.e TW, Pump Houses, Water Distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Banarhat under Jalpaiguri Division , P.H.E Dte. | 28/JD | 10/04/2023 | 783 | SUKES BASU MAJUMDAR | 506.72 | 0 | 0 | 100
1143 | JALPAIGURI | Northern Mechanical | MADHYA DAUKIMARI PIPED WATER SUPPLY SCHEME , SM/13898 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA DAUKIMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1252/NMD | 31/07/2023 | 551 | PADMA ENGINEERING CO. | 24.51 | 0 | 0 | 100
1144 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Retrofitting works in connection with FHTC works for the habitation of Dangar Bari , Fokkorer Bari , near Chandrakanta School & Providing balanced Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangamali Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. | 1418/JD | 14/07/2022 | 15 | MRINMOY KANTI DUTTA | 4.62 | 0 | 0 | 1
1145 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGAMALI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1436/NMD | 10/08/2023 | 479 | SAIKAT SINHA | 11.5 | 0 | 0 | 80
1146 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | New Service Connection Charge for BHANGAMALI (REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401391 Reference ID : 403212005 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
1147 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1148 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1149 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc for Rejuvenation of Bhangamali Piped Water Supply Scheme at Dhupguri Block in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | 389/A/JD | 01/06/2023 | 671 | VIBEKANANDA DEY | 35.66 | 0 | 0 | 90
1150 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANGAMALI PIPED WATER SUPPLY SCHEME , SM/15096 | Augmentation | Balance Laying Distribution System with Providing FHTC, Overhauling of I.E.P. and other allied works related to Pipeline in connection with Jal Jeevan Mission at Bhangamali Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2026/JD | 19/11/2024 | 242 | MRINMOY KANTI DUTTA | 14.23 | 0 | 0 | 20
1151 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Material Requisition To Resource Division | 1080/JD | 24/08/2023 | 0 | Resource Division | 25.38 | 0 | 0 | 0
1152 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAJOLDOBA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1387/NMD | 09/08/2023 | 570 | SUBODH KUMAR BANIK | 27.14 | 0 | 0 | 70
1153 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1154 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.05.2024 to 30.06.2024)" | 143/JD | 29/04/2024 | 61 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
1155 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Material Requisition To Resource Division | 2025/JD | 09/01/2024 | 0 | Resource Division | 12.26 | 0 | 0 | 0
1156 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | New Service Connection Charge for GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003425397 Reference ID : 403230604 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1157 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORK SITES OF DIFFERENT PWSS AT NAGRAKATA ,MATIALI , AND MAL BLOCK UNDER JALPAIGURI |  | 22/11/2024 | 0 | DR. AMBARISH GHOSH | 17.82 | 0 | 0 | 0
1158 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000110462 Reference ID : 860303002 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0 | 0
1159 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | New Service Connection Charge for GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003425403 Reference ID : 403230603 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1160 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000110463 Reference ID : 860303003 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0 | 0
1161 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Construction of different components of Gajoldoba Tea Garden Piped Water Supply Scheme i.e, TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | 422/A/JD | 07/06/2023 | 938 | M/S SIBU DEY AND CO. | 262.74 | 0 | 0 | 20
1162 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Gajoldoba TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | 2038/JD | 21/11/2024 | 90 | M/S SIBU DEY AND CO. | 83.02 | 0 | 0 | 50
1163 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Protective Boulder Work, Land Development and approach road inside the premises at H/W Site for Gajaldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | 2429/JD | 24/12/2024 | 45 | M/S SIBU DEY AND CO. | 23.79 | 0 | 0 | 50
1164 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1165 | JALPAIGURI | Northern Mechanical | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1166 | JALPAIGURI | Jalpaiguri Division | GAJALDOBA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15297 | New | Sub-Soil Investigation of proposed 300 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Gajaldoba Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 88-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
1167 | JALPAIGURI | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Material Requisition To Resource Division | 1072/JD | 24/08/2023 | 0 | Resource Division | 27.2 | 0 | 0 | 0
1168 | JALPAIGURI | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Material Requisition To Resource Division | 2021/JD | 09/01/2024 | 0 | Resource Division | 8.08 | 0 | 0 | 0
1169 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | New Service Connection Charge for WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003460294 Reference ID : 403254628 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1170 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000114552 Reference ID : 860309142 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.95 | 0 | 0 | 0
1171 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000114551 Reference ID : 860309141 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
1172 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | New Service Connection Charge for WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003460295 Reference ID : 403254629 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1173 | JALPAIGURI | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Construction of different components of Washabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 395/A/JD | 05/06/2023 | 844 | S.S. CONSTRUCTION | 269.38 | 0 | 0 | 65
1174 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for WASHABARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1330/NMD | 08/08/2023 | 755 | SANJIB SAHA | 24.81 | 0 | 0 | 50
1175 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1176 | JALPAIGURI | Northern Mechanical | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1177 | JALPAIGURI | Jalpaiguri Division | WASHABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14886 | New | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 3rd & 4th tube well site of Washabari Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 2317/JD | 11/12/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 0 | 0 | 100
1178 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Retrofitting works & other ancillary works related to FHTC at different places of Jabramali PWSS under Jalpaiguri Division, P.H.E. Dte. | 629/JD | 13/03/2023 | 30 | DREAM CONSTRUCTION | 12.41 | 0 | 0 | 100
1179 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Material Requisition To Resource Division | 1050/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0 | 0
1180 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JABRAMALI PWSS, TW NO-III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1215/NMD | 26/07/2023 | 30 | SUNLIT | 22.15 | 0 | 0 | 0
1181 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Drainage line for IEP & other ancillary works at Head work site of JABRAMALI PWSS under Jalpaiguri Divisiopn PHE Dte. | 1281/RWS | 28/11/2023 | 20 | RAGHU DAS | 3.04 | 0 | 0 | 100
1182 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of JABRAMALI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1055/HQ/NMD | 21/06/2024 | 7 | B.B. CONCERNED | 0.73 | 0 | 0 | 100
1183 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | New Service Connection Charge for JABRAMALI(REJU), T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003397114 Reference ID : 403208952 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0 | 0
1184 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | New Service Connection Charge for JABRAMALI(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003397105 Reference ID : 403208949 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
1185 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JABRAMALI PIPED WATER SUPPLY SCHEME , SM/15109 | Augmentation | Construction of different components of Rejuvenation of Jabramali PWSS i.e. TW, Pump Houses, Water distribution Network, Boundary wall, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 1435/JD | 05/10/2023 | 910 | RAGHU DAS | 83.33 | 0 | 0 | 80
1186 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/15033 | Augmentation | New Service Connection Charge for REJUVENATION OF CHAUHADDI PWSS, TW NO IV, under DHUPGURI CCC APPLICATION NO. 4003460809 Reference ID : 403255219 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.39 | 0 | 0 | 0
1187 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/15033 | Augmentation | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 0 | 30
1188 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/15033 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
1189 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/15033 | Augmentation | Construction of different components of Rejuvenation Chauhaddi PWSS i.e. TW, Pump Houses, Water distribution Network, , RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | 350/JD | 24/05/2023 | 395 | HARIPADA BANERJEE | 61.11 | 0 | 0 | 100
1190 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/15033 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHAUHADDI PWSS at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1637/NMD | 25/09/2024 | 188 | SUMON ELECTRICAL | 11.73 | 0 | 0 | 80
1191 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Samsing T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte. | 1304/JD | 24/11/2020 | 60 | LOKNATH CONSTRUCTIOIN | 32.08 | 0 | 0 | 1
1192 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | Material Requisition To Resource Division | 1070/JD | 24/08/2023 | 0 | Resource Division | 19.77 | 0 | 0 | 0
1193 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | Balance work of Water Distribution Network in Chalsa Zone-I in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 1938/JD | 02/01/2024 | 30 | ALICK DUTTA | 17.21 | 0 | 0 | 50
1194 | JALPAIGURI | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | "INFRA COST IRO NSC for (REJU) SAMSOING TG TW NO-III, METELI CCC " APPLICATION NO.100000107272 Reference ID : 860298682 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.79 | 0 | 0 | 0
1195 | JALPAIGURI | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | " New Service Connection Charge for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.4003402758 Reference ID : 403213197 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1196 | JALPAIGURI | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | " New Service Connection Charge for (REJU) SAMSING TG TW NO-III, METELI CCC " APPLICATION NO.4003402763 Reference ID :403213198 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1197 | JALPAIGURI | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | "INFRA COST IRO NSC for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.100000108221 Reference ID : 860300681 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.82 | 0 | 0 | 0
1198 | JALPAIGURI | Northern Mechanical | Rejuvenation of Samsing Tea Garden Area Piped Water Supply Scheme , SM/15301 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAMSING TG AREA PWSS, TW no III,IV,V,VI,VII in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1810/NMD | 31/10/2023 | 732 | M/S P.P. ELECTRICALS | 56.9 | 0 | 0 | 50
1199 | JALPAIGURI | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Material Requisition To Resource Division | 149/JD | 28/04/2023 | 0 | Resource Division | 13.53 | 0 | 0 | 0
1200 | JALPAIGURI | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Material Requisition To Resource Division | 2011/JD | 09/01/2024 | 0 | Resource Division | 2.64 | 0 | 0 | 0
1201 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 4003352329 Reference ID : 403172831 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1202 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 100000102151 Reference ID : 860294701 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.83 | 0 | 0 | 0
1203 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 4003352331 Reference ID : 403172836 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1204 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 100000102150 Reference ID : 860294700 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0 | 0
1205 | JALPAIGURI | Jalpaiguri Division | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Construction of Different Components of Dakshin Kantadighi Kumarpara PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Mal under | 754/JD | 24/03/2023 | 817 | B RAI CONSTRUCTION COMPANY | 134.73 | 0 | 0 | 50
1206 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
1207 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1208 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1209 | JALPAIGURI | Northern Mechanical | DAKSHIN KANTADIGHI KUMARPARA PIPED WATER SUPPLY SCHEME , SM/14908 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN KANTADIGHI KUMARPARA PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 1274/NMD | 02/08/2023 | 549 | GOENKA ENTERPRISE | 24.41 | 0 | 0 | 80
1210 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Material Requisition To Resource Division | 1084/JD | 24/08/2023 | 0 | Resource Division | 47.75 | 0 | 0 | 0
1211 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MAUAMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1433/NMD | 10/08/2023 | 541 | RAJEEV RANJAN OJHA | 20.68 | 0 | 0 | 50
1212 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Material Requisition To Resource Division | 2059/JD | 10/01/2024 | 0 | Resource Division | 7.17 | 0 | 0 | 0
1213 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
1214 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | New Service Connection Charge for UTTAR MOUAMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003401393 Reference ID : 403212002 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0 | 0
1215 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | New Service Connection Charge for UTTAR MAUAMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376055 Reference ID : 403191647 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.2 | 0 | 0 | 0
1216 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Construction of different components of Uttar Mouamari PWSS i.e TW, Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc,i.c.w.Jal Jeevan Mission at Block-Maynaguri under Jalpaiguri Division,P.H.E.Dte. | 699/JD | 13/07/2023 | 993 | M/S SIBU DEY AND CO. | 250.23 | 0 | 0 | 60
1217 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Construction of Boundary Wall with gate, drain, Land Development and pathway and Laying Pipe line at H/W site of Uttar Mouamari Piped Water Supply Scheme under Jalpaiguri Division PHE, DTE. | 1298/JD | 05/09/2024 | 191 | M/S SIBU DEY AND CO. | 24 | 0 | 0 | 85
1218 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
1219 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
1220 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1221 | JALPAIGURI | Northern Mechanical | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1222 | JALPAIGURI | Jalpaiguri Division | UTTAR MAUAMARI PIPED WATER SUPPLY SCHEME , SM/14914 | New | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at 2 nd site of uttar Mouamari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 801/RWS | 20/08/2024 | 193 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.47 | 0 | 0 | 100
1223 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldigi Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | 442/RWS | 09/10/2020 | 30 | M/S.PAMPA CONSTRACTION | 4.73 | 0 | 0 | 0
1224 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KAJALDIGI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-C). | 1276/JD | 18/11/2020 | 90 | NISHITH RANJAN KARMAKAR | 39.12 | 39.1 | 99.96 | 0
1225 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) | 1085/JD | 05/07/2021 | 20 | GOUTAM DAS | 10.27 | 0 | 0 | 0
1226 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | fhtc jiti |  | 05/10/2021 | 0 | CALCON CONSTRUCTIONS | 17.1 | 0 | 0 | 0
1227 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | PROVIDING HOUSE CONNECYTION AT KAJALDIGHI PWSS | 1055 | 11/01/2021 | 0 | R.S CONSTRUCTION | 4.44 | 0 | 0 | 0
1228 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | FHTC LATAGURI, MOULANI, KRANTI GP | BP-2021-22-467 | 28/03/2022 | 0 | SAHA CONSTRUCTION | 2.2 | 0 | 0 | 0
1229 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | FHTC KAJALDIGHI | BP-2021-22-131 | 14/12/2021 | 0 | R.S CONSTRUCTION | 4.71 | 0 | 0 | 0
1230 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | FHTC KAJAL DIGHI | BP-2021-22-133 | 14/12/2021 | 0 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0 | 0
1231 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme , SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-D). | 74/RWS | 19/02/2021 | 15 | R.S CONSTRUCTION | 4.76 | 4.75 | 100 | 0
1232 | JALPAIGURI | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Material Requisition To Resource Division | 153/JD | 28/04/2023 | 0 | Resource Division | 38.37 | 0 | 0 | 0
1233 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for MANTABARI BFP SCHOOL, SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003227613, Reference ID : 403072694] | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
1234 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W IIZONE II under BELAKOBA CCC, [APPLICATION NO. 4003200012, Reference ID : 403051284] | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
1235 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SHINGIVISA NEAR MASJID, SIMULGURI,ZONE II, T/W III, under BELAKOBA CCC, [APPLICATION NO. 4003227623, Reference ID : 403072705] | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.49 | 0 | 0 | 0
1236 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219227, Reference ID : 403065768] | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.74 | 0 | 0 | 0
1237 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SIMULGURI,ZONE II, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219239, Reference ID : 403065766] | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.14 | 0 | 0 | 0
1238 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W II,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200017, Reference ID : 403051285] | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.04 | 0 | 0 | 0
1239 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | New Service Connection Charge for SIMULGURI, T/W I,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200020, Reference ID : 403051286] | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.5 | 0 | 0 | 0
1240 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-III, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 366/NMD | 29/03/2023 | 30 | M/S P.P. ELECTRICALS | 21.77 | 0 | 0 | 100
1241 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-I,TW NO I,II AND ZONE-II, TW NO- I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 466/NMD | 25/04/2023 | 30 | WEST BENGAL ENGINEERING CO. | 61.4 | 0 | 0 | 100
1242 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Additional work in connection with Supply, installation, commissioning and trial operation of electro-mechanical components for SIMULGURI PWSS, at TW no I (Z-I),and TW NO I,II,III (Z-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 693/SMSD | 14/06/2024 | 7 | WEST BENGAL ENGINEERING CO. | 0.87 | 0 | 0 | 100
1243 | JALPAIGURI | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Material Requisition To Resource Division | 2045/JD | 09/01/2024 | 0 | Resource Division | 18.16 | 0 | 0 | 0
1244 | JALPAIGURI | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Construction of different components of Simulguri PWSS Zone-I, II and III i.e. TW, Pump Houses, Water distribution , Water distribution Network , OHR, Rising Main , FHTC etc. Block - Rajganj under Jalpaiguri Division, P.H.E Dte. | 823/JD | 30/03/2023 | 733 | S.S. CONSTRUCTION | 709.21 | 0 | 0 | 75
1245 | JALPAIGURI | Jalpaiguri Division | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Construction of Boundary wall with gate, Drain, Land development ,Pathway at H/W Site & 2nd T/W site at Zone-I, H/W site , 2nd T/W & 3rd T/W site at Zone-II and H/W Site & 2nd T/W site at Zone-III including balance portion of laying distribution system with providing FHTC at SIMULGURI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E Dte. | 571/JD | 25/03/2025 | 372 | NEW KUNDU ENTERPRISE | 165.71 | 0 | 0 | 55
1246 | JALPAIGURI | Northern Mechanical | SIMULGURI PIPED WATER SUPPLY SCHEME , SM/14240 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1247 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
1248 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Material Requisition To Resource Division | 2032/JD | 09/01/2024 | 0 | Resource Division | 8.53 | 0 | 0 | 0
1249 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
1250 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | New Service Connection Charge for Dakshin Dangapara,Zone-II T/W-II under BHOTPATTY CCC APPLICATION NO. 4003374101 Reference ID : 403190146 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.25 | 0 | 0 | 0
1251 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | New Service Connection Charge for Dakshin Dangapara,Zone-II T/W-I under BHOTPATTY CCC APPLICATION NO. 4003374121 Reference ID : 403190147 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.26 | 0 | 0 | 0
1252 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Construction of different components of Dakshin Dangapara PWSS Zone- II i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. | 296/JD | 15/05/2023 | 903 | M/S SURAJIT DEY AND CO. | 375.71 | 0 | 0 | 60
1253 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 109/JD | 16/01/2025 | 45 | M/S SURAJIT DEY AND CO. | 48.72 | 0 | 0 | 0
1254 | JALPAIGURI | Jalpaiguri Division | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Construction of Boundary Wall at H/W site of Dakhindangapara Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE DTE. | 1172/JD | 23/08/2024 | 528 | M/S SURAJIT DEY AND CO. | 23.37 | 0 | 0 | 80
1255 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
1256 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
1257 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1258 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1259 | JALPAIGURI | Northern Mechanical | DAKSHIN DANGAPARA ZONE-II PIPED WATER SUPPLY SCHEME , SM/16181 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN DANGAPARA PIPED WATER SUPPLY SCHEME , ZONE-II, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1391/NMD | 09/08/2023 | 630 | GOENKA ENTERPRISE | 21.78 | 0 | 0 | 100
1260 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15610 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1261 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15610 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1262 | JALPAIGURI | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Material Requisition To Resource Division | 156/JD | 28/04/2023 | 0 | Resource Division | 16.82 | 0 | 0 | 0
1263 | JALPAIGURI | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Material Requisition To Resource Division | 1882/JD | 20/12/2023 | 0 | Resource Division | 4.11 | 0 | 0 | 0
1264 | JALPAIGURI | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Construction of different components of Bhemtia PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E Dte. | 02/JD | 06/04/2023 | 947 | SCEC BOENTER KDAS JOINT VENTURE | 209.41 | 0 | 0 | 30
1265 | JALPAIGURI | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
1266 | JALPAIGURI | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
1267 | JALPAIGURI | Northern Mechanical | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
1268 | JALPAIGURI | Jalpaiguri Division | BHEMTIA PIPED WATER SUPPLY SCHEME , SM/16676 | New | Sub-Soil Investigation including liquefaction due to close proximity of railway track near the proposed 100 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Bhemtia Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 93-HQ/JD | 17/03/2025 | 20 | R.B TESTING | 0.98 | 0 | 0 | 0
1269 | JALPAIGURI | Northern Mechanical | PURBA DOBBARI PIPED WATER SUPPLY SCHEME , SM/16776 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA DOBBARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1344/NMD | 08/08/2023 | 30 | S.D. CONCERN | 6.11 | 0 | 0 | 0
1270 | JALPAIGURI | Jalpaiguri Division | PURBA DOBBARI PIPED WATER SUPPLY SCHEME , SM/16776 | New | Material Requisition To Resource Division | 2054/JD | 09/01/2024 | 0 | Resource Division | 0.18 | 0 | 0 | 0
1271 | JALPAIGURI | Jalpaiguri Division | PURBA DOBBARI PIPED WATER SUPPLY SCHEME , SM/16776 | New | Construction of different components of Purba Dobbari PWSS i.e. TW, Pump Houses, Water distribution Network, Stand alone Mini OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 946/JD | 08/08/2023 | 693 | SOMNATH ROY | 38.25 | 0 | 0 | 70
1272 | JALPAIGURI | Northern Mechanical | PURBA DOBBARI PIPED WATER SUPPLY SCHEME , SM/16776 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1273 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15607 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1274 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15607 | Solarisation | Quotation charges for Application for Net Metering connection at Debpara TG Piped Water Supply Scheme under NMD ,PHE Dte APPLICATION NO - 4003455550 CONSUMER ID- 401971102 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
1275 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DEBPARA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15607 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1276 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF DOMOHINI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15596 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1277 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF DOMOHINI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15596 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1278 | JALPAIGURI | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAR TANDU PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1336/NMD | 08/08/2023 | 30 | THE BANERJEE CONCERN | 24.53 | 0 | 0 | 0
1279 | JALPAIGURI | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1280 | JALPAIGURI | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Construction of Boundary Wall at H/W site of Upper Tendu Forest (M) PWSS in connection with Jal Jeevan Mission at Block Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 295/JSSD | 27/09/2023 | 45 | NISHITH RANJAN KARMAKAR | 7.99 | 0 | 0 | 100
1281 | JALPAIGURI | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Tandu Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 474/JD | 21/06/2024 | 45 | PRADIP SAHA | 15.98 | 0 | 0 | 100
1282 | JALPAIGURI | Jalpaiguri Division | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Sinking of 2 (Two) Nos. Big Dia Tube well by Modified DTH - ODEX Method at 1st & 2nd tube well site of Chhar Tandu and adjacent area Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 1415/JD | 20/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 0 | 0 | 100
1283 | JALPAIGURI | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
1284 | JALPAIGURI | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
1285 | JALPAIGURI | Northern Mechanical | CHHAR TANDU PIPED WATER SUPPLY SCHEME , SM/15964 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1286 | JALPAIGURI | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1287 | JALPAIGURI | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | Material Requisition To Resource Division | 2014/JD | 09/01/2024 | 0 | Resource Division | 7.02 | 0 | 0 | 0
1288 | JALPAIGURI | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | New Service Connection Charge for TESIMLA, TW NO-II, MAL CCC APPLICATION NO. 4003352318 Reference ID : 403172835 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1289 | JALPAIGURI | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | New Service Connection Charge for TESIMLA, TW NO-I, MAL CCC APPLICATION NO. 4003352315 Reference ID : 403172834 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1290 | JALPAIGURI | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | Infrastructure development cost for new service connection at TESIMLA,, TW NO-I & II, MAL CCC APPLICATION NO. 100000102139 Reference ID : 860293899 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.86 | 0 | 0 | 0
1291 | JALPAIGURI | Jalpaiguri Division | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Tesimala PWSS i.e. Tube Well, Pump House, Boundary Wall in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 104/JD | 15/01/2025 | 70 | APEX ENGINEERING | 39.7 | 0 | 0 | 0
1292 | JALPAIGURI | Northern Mechanical | TESIMALA PIPED WATER SUPPLY SCHEME , SM/15970 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TESIMLA PWSS, TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1299/NMD | 03/08/2023 | 576 | SUMON ELECTRICAL | 23.05 | 0 | 0 | 100
1293 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II , SM/18094 | Augmentation | Material Requisition To Resource Division | 1057/JD | 24/08/2023 | 0 | Resource Division | 4.7 | 0 | 0 | 0
1294 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II , SM/18094 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Maynatali PWSS , in connection with Rejuvenation of Maynatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 405/A/JD | 06/06/2023 | 792 | ABHIJIT SARKAR | 47.88 | 0 | 0 | 25
1295 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme Phase-II , SM/18094 | Augmentation | Providing FHTC and Installation of Sluice Valve at different strategic point in connection with JJM of Mainatali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) | 466/JD | 11/03/2025 | 385 | ARUP SARKAR | 24.16 | 0 | 0 | 0
1296 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of BHANDANI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-II | 42/JD | 06/01/2021 | 90 | DULAL CHOUDHURY | 38.46 | 6.2 | 21.8 | 1
1297 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Bhandani piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | 49/JD | 07/01/2021 | 60 | ASIM GUPTA | 39.45 | 39.42 | 99.91 | 1
1298 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | FHTC BHANDANI PWSS |  | 04/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0 | 0
1299 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | FHTC BHANDABNI PWSS |  | 01/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0 | 0
1300 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | providing fhtc for Mathachulka pwss | 281 | 26/09/2021 | 0 | DEEP CONSTRUCTION | 4.67 | 0 | 0 | 0
1301 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhandani Piped Water Supply Scheme at Dhupguri Block , SM/06958 | Retrofitting | FHTC BHANDANI | BP-2022-23-66 | 04/07/2022 | 0 | DULAL CHOUDHURY | 8.03 | 0 | 0 | 0
1302 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Construction of different components of Salugara PWSS zone-I i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | 1258/JD | 13/09/2023 | 180 | S. N. POLYMERS PVT. LTD. | 346.56 | 0 | 0 | 35
1303 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Material Requisition To Resource Division | 1102/JD | 24/08/2023 | 0 | Resource Division | 65.27 | 0 | 0 | 0
1304 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Material Requisition To Resource Division | 1507/JD | 13/10/2023 | 0 | Resource Division | 32.56 | 0 | 0 | 0
1305 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Infrastructure Cost for SALUGARA , T/W-II, ZONE-II under POWER HOUSE CCC [APPLICATION NO. 4003341484 , Reference ID : 403163817] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
1306 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of September 2024. | BP-2024-25-484 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1307 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of October 2024. | BP-2024-25-549 | 17/12/2024 | 0 | FILL & SMILE | 0.16 | 0 | 0 | 0
1308 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-II,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334683, Reference ID : 403158637] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.7 | 0 | 0 | 0
1309 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334689, Reference ID : 403158907] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.17 | 0 | 0 | 0
1310 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. II, under POWER HOUSE CCC , [APPLICATION NO. 4003334685, Reference ID : 403158908] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.9 | 0 | 0 | 0
1311 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of August 2024. | BP-2024-25-448 | 03/10/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0 | 0
1312 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SALUGARA PWSS, ZONE-I AND II, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1474/NMD | 17/08/2023 | 868 | CHOWDHURY AND BASU ENTERPRISE | 43.27 | 0 | 0 | 85
1313 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
1314 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19/08/2024 to 18/02/2025) | 1025/JD | 16/08/2024 | 184 | AJIJUL HAQUE | 0.88 | 0 | 0 | 0
1315 | JALPAIGURI | Jalpaiguri Division | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19.02.2025 to 31.03.2025) | 53/HQ/JD | 18/02/2025 | 41 | AJIJUL HAQUE | 0.2 | 0 | 0 | 0
1316 | JALPAIGURI | Northern Mechanical | SALUGARA PIPED WATER SUPPLY SCHEME , SM/18625 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1317 | JALPAIGURI | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | Material Requisition To Resource Division | 1842/JD | 15/12/2023 | 0 | Resource Division | 21.75 | 0 | 0 | 0
1318 | JALPAIGURI | Jalpaiguri Division | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | Material Requisition To Resource Division | 55/JD | 09/04/2024 | 0 | Resource Division | 108.57 | 0 | 0 | 0
1319 | JALPAIGURI | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328083 ; Reference ID : 403153545] | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0 | 0
1320 | JALPAIGURI | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328082 , Reference ID : 403153543] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.97 | 0 | 0 | 0
1321 | JALPAIGURI | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | New Service Connection Charge for DAKSHIN JHARALTA, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003356729 Reference ID : 403176999 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.35 | 0 | 0 | 0
1322 | JALPAIGURI | Northern Mechanical | Dakshin Jharalta Piped Water Supply Scheme. , SM/18835 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN JHARALTA PWSS,at TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1805/NMD | 31/10/2023 | 701 | PADMA ENGINEERING CO. | 34.35 | 0 | 0 | 95
1323 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme , SM/06960 | Retrofitting | CONST OF OHR FOR DABGRAM SOUTH ZONE PWSS | 448/21-22 | 04/10/2021 | 0 | PARESH CHANDRA GUHA | 1.57 | 0 | 0 | 0
1324 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme , SM/06960 | Retrofitting | FHTC PATKIDAHA | BP-2021-22-441 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0 | 0
1325 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Altagram & Paschim Altagram Mouza under Mainatali Piped Water Supply Scheme , SM/06960 | Retrofitting | FHTC PATKIDAHA | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0 | 0
1326 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme , SM/06961 | Retrofitting | PROVIDING FHTC UNDER PORA PARA | 1044 | 11/01/2021 | 0 | SUKES BASU MAJUMDAR | 4.45 | 0 | 0 | 0
1327 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dakshin Dangapara & Dambari Mouza Under Patkidaha Piped Water Supply Scheme , SM/06961 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dambari Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 1541/JD | 31/12/2020 | 45 | KULDIP KAPOOR | 24.3 | 16.07 | 75.43 | 80
1328 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Chrarbari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). | 466/RWS | 15/10/2020 | 30 | M/S.DEY & ROY CHOUDHURY | 4.71 | 4.42 | 93.87 | 0
1329 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHARERBARI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-B) | 1284/JD | 18/11/2020 | 45 | RAGHU DAS | 15.22 | 0 | 0 | 0
1330 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-D) | 1552/JD | 31/12/2020 | 45 | NEW KUNDU ENTERPRISE | 27.7 | 27.51 | 99.34 | 1
1331 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | providing fhtc for charer bari pwss |  | 01/10/2021 | 0 | NEW KUNDU ENTERPRISE | 2.02 | 0 | 0 | 0
1332 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | FHTC CHARERBARI WSS | BP-2021-22-415 | 23/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0 | 0
1333 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | FHTC DWARIKAMARI | BP-2021-22-524 | 30/03/2022 | 0 | SUBRATA GOSWAMI | 8.41 | 0 | 0 | 0
1334 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) | 100/JD | 18/01/2021 | 45 | SANKAR DAS | 21.16 | 0 | 0 | 100
1335 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) | 222/JD | 12/02/2021 | 45 | M/S DEY & ROY CHOUDHURY | 24.4 | 0 | 0 | 40
1336 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Restoration work in connection with FHTC works for the habitation of Bideshi Para,Chobarbari, Thonthonerbari and Dakshin Ghutkara under Charerbari W/S/S under Jalpaiguri Division , P.H.E. Dte | 176/RWS | 03/03/2022 | 15 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0 | 0
1337 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (Part-F) | 91/JD | 14/01/2021 | 45 | KAMALESH SEN | 20.95 | 0 | 0 | 100
1338 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme , SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with under the command area of Charerbari Water Supply Scheme at Managuri Block under Jalpaiguri Division, P.H.E. Dte. (PHASE - G) | 650/RWS | 21/10/2022 | 20 | NEW KUNDU ENTERPRISE | 2.42 | 0 | 0 | 100
1339 | JALPAIGURI | Siliguri W/S Division | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme , SM/07028 | Retrofitting | Further continuation order for hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.09.2023 to 31.12.2023 (for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte. i.e. 04 (four) months. | 1428/SWSD | 24/08/2023 | 122 | HIMADRI DAM | 0.59 | 0 | 0 | 0
1340 | JALPAIGURI | Siliguri W/S Division | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Purba Paschim Dhantala Piped water Supply Scheme , SM/07028 | Retrofitting | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of september(20/09/24 to 27/09/24) & october ( 01/10/24 to 04/10/24)and 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | BP-2024-25-125 | 11/11/2024 | 0 | SONA PETROL PUMP | 0.42 | 0 | 0 | 0
1341 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06957 | Retrofitting | hire charge | BP-2021-22-208 | 29/09/2022 | 0 | RAKESH SARKAR | 0.34 | 0 | 0 | 0
1342 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06957 | Retrofitting | car hire charge | BP-2021-22-207 | 29/09/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0 | 0
1343 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hila Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06957 | Retrofitting | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JALDHARA /JAL SAPNA UNDER THE COMMAND AREA OF HILLA T.G. AREA PIPED WATER SUPPLY SCHEME AT NAGRAKATA BLOCK UNDER JALPAIGURI DIVISION, PHE DTE. | 149/JD | 19/01/2022 | 30 | SCEC BOENTER KDAS JOINT VENTURE | 26.95 | 0 | 0 | 100
1344 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 4003023651 ; Reference ID : 402902659] | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
1345 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Installation of Infrastructure COST at CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 100000064277 ; Reference ID : 860253067] | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.12 | 0 | 0 | 0
1346 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | CHAMURCHI BAZAR | BP-2022-2023-42 | 24/05/2022 | 0 | RANA DEY | 3.83 | 0 | 0 | 0
1347 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. II, Zone I under BANARHAT CCC [APPLICATION NO. 4003019807 ; Reference ID : 402902658] | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
1348 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Resistivity Test for Four Nos.Tube Well for Chamurchi Tea Garden area Augmentation Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 142/JD | 18/01/2022 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0 | 0 | 0
1349 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of rig approach road for the various zone of augmentation Chamurchi T.G.PWSS under Jalpaiguri Division,P.H.E.Dte. | 1500/JD | 27/07/2022 | 15 | PARAMJYOTI ENTERPRISE | 1.77 | 0 | 0 | 0
1350 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Chamurchi T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | 1853/JD | 16/09/2022 | 45 | PARAMJYOTI ENTERPRISE | 4.65 | 0 | 0 | 0
1351 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TG PWSS, ZONE-I, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1449/NMD | 21/12/2022 | 30 | SARKAR ELECTRIC | 26.26 | 0 | 0 | 100
1352 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Shifting of Rising main due to widening and Construction of New Culvert at Hatinala and other ancillary works related to the Rising main inside the Head works site of Chamurchi Bazar P.W.S.S. under Jalpaiguri Division, P.H.E.Dte. | 1807/JD | 14/09/2022 | 21 | RANA DEY | 3.57 | 0 | 0 | 0
1353 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Special repairing of RCC Over Head Reservoir for Chamurchi Bazar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte.. | 284/JD | 02/02/2022 | 60 | SUKES BASU MAJUMDAR | 8.29 | 0 | 0 | 1
1354 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 327/DSD | 07/02/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0 | 0 | 0
1355 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 313/DSD | 24/01/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0 | 0 | 0
1356 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 315/DSD | 25/01/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0 | 0 | 0
1357 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of 200 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) and other related works at Zone - I of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | 1540/JD | 04/08/2022 | 180 | SAPTASWA SARKAR | 63.69 | 0 | 0 | 100
1358 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 346/DSD | 22/02/2022 | 15 | SAHA ENTERPRISE | 0.16 | 0 | 0 | 0
1359 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Two nos Pump House with restoration of Sanitary Plumbing System including repairing of C.W.R. raising of valve chamber height and making of Cement Concrete Pathway at Chamurchi Forest Busty Head Works Site under Augmentation of Chamurchi T.G. Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1808/JD | 14/09/2022 | 21 | M/S KARMAKAR CONSTRACTION | 4.17 | 0 | 0 | 100
1360 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 64/DSD | 23/05/2022 | 15 | M/S ROYAL ENTERPRISE | 0.71 | 0 | 0 | 0
1361 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 29/DSD | 21/04/2022 | 15 | SAHA ENTERPRISE | 0.71 | 0 | 0 | 0
1362 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | 152/DSD | 26/07/2022 | 7 | SUMON ELECTRICAL | 0.41 | 0 | 0 | 0
1363 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | 183/DSD | 18/08/2022 | 7 | SUMON ELECTRICAL | 0.41 | 0 | 0 | 0
1364 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-I) udner Jalpaiguri Division P.H.E. Dte. | 967/JD | 20/04/2022 | 90 | NARAYAN CHANDRA SAHA | 85.51 | 0 | 0 | 100
1365 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Material Requisition To Resource Division | 1105/JD | 24/08/2023 | 0 | Resource Division | 160.42 | 0 | 0 | 0
1366 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Sinking of two nos. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at Siv Mandir area of Chamurchi zone-II under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | 802/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 33.1 | 0 | 0 | 54
1367 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TEA GARDEN (CHAMURCHI BAZAR and CHAMURCHI FOREST BUSTY and LABOUR COLONY) PWSS, ZONE-II, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1380/NMD | 09/08/2023 | 30 | THE BANERJEE CONCERN | 26.24 | 0 | 0 | 40
1368 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 14.01.2024) | 1982/JD | 03/01/2024 | 182 | APIKUL ALI | 0.88 | 0 | 0 | 30
1369 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.01.2024) | 1983/JD | 03/01/2024 | 182 | RAKESH SARKAR | 0.88 | 0 | 0 | 30
1370 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 15.07.2024 to 14.10.2024) | 561/JD | 03/07/2024 | 92 | APIKUL ALI | 0.44 | 0 | 0 | 0
1371 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-III) under Jalpaiguri Division P.H.E. Dte. | 864/JD | 01/04/2022 | 1007 | M/S. D.K. DEY & CO.. | 63.77 | 0 | 0 | 100
1372 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 360/DSD | 02/03/2022 | 15 | SAHA ENTERPRISE | 0.16 | 0 | 0 | 100
1373 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Laying of Individual D.I. Rising Main Including common manifold from 1st Tube Well to 2nd Tube Well and to Head Works site including internal connection of 1st and 2nd Tube Well site with Functional Household Tap Connection in connection with Jal Jeevan Mission under Augmentation of Chamurchi T.G. Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division, P.H.E. Dte. | 627/JD | 13/03/2023 | 45 | SANKAR DAS | 47.49 | 0 | 0 | 50
1374 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Sinking of one no. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at chunavati chamurchi Zone-III under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | 801/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 16.55 | 0 | 0 | 80
1375 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Additional work in connection Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of CHAMURCHI TG (Z-I) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 228/HQ/NMD | 15/09/2023 | 15 | SARKAR ELECTRIC | 1.44 | 0 | 0 | 100
1376 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of Two Nos Boundary Wall (at OHR site and alternate 1 st tube well Site) including construction of surface drain,making of pathway,Land development work,with supplying fitting fixing CIDF pipe,modification of pump house and constructionof rest rooms with construction of culvert along with scouring prevention work on the approach way including development of approach way with other allied works for the various site within the command area of augmentation of Chamurchi T.G. Area P.W.S.S.Zone - I under Jalpaiguri Division,P.H.E.Dte. | 1819/JD | 14/12/2023 | 45 | SAPTASWA SARKAR | 64.94 | 0 | 0 | 100
1377 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of 3rd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | 2303/JD | 07/02/2024 | 45 | DITIPRIYA CHOWDHURY | 4.9 | 0 | 0 | 100
1378 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of 2nd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement for at airtel site of Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | 2304/JD | 07/02/2024 | 45 | MAA SHANTI BUILDERS | 4.9 | 0 | 0 | 100
1379 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 2nd tube well site of Chamurchi Piped Water Supply Scheme (Zone-III, Chunabhati) of Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 932/JD | 07/08/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 17.61 | 0 | 0 | 100
1380 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Material Requisition To Resource Division | 2222/JD | 01/12/2024 | 0 | Resource Division | 21.08 | 0 | 0 | 0
1381 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. I, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333005 , Reference ID : 403157463] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 16 | 0 | 0 | 0
1382 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 76 9978 for the Month of July 2024. | BP-2024-25-338 | 30/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1383 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. II, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333013 , Reference ID : 403157465] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0 | 0
1384 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | New Service Connection Charge for CHAMURCHI (CHUNABHATI) ZONE:-III, T/W-III, under BANARHAT CCC APPLICATION NO. 4003418431 Reference ID : 403225913 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.07 | 0 | 0 | 0
1385 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | 1423/JD | 15/07/2022 | 1357 | M/S A.B.G. CONSTRUCTION | 151.77 | 0 | 0 | 10
1386 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Providing Functional Household Tap Connection (Phase - II ) in connection with Jal Jeevan Mission for Augmentation of Chamurchi T.G. P.W.S.S (Zone -III) under Jalpaiguri Division, P.H.E. Dte. | 1463/JD | 06/10/2023 | 697 | MALAY BHOWMIK | 27.18 | 0 | 0 | 50
1387 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of Boundary Wall at 3rd T/W site of Chamurchi Tea Garden Piped W/S scheme (Zone-II, Gumpha Line) along with pipeline repairing and other allied works in connection with JJM at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | 2156/JD | 29/10/2025 | 30 | DITIPRIYA CHOWDHURY | 11.72 | 0 | 0 | 0
1388 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of different components i.e. Head Work Site Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement, Boundary wall and Laying rising Main at Shiv Mandir area of Chamurchi zone - II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri Division, P.H.E. Dte. | 2330/JD | 08/02/2024 | 329 | M/S. SURYA I PVT. LTD COMPANY | 10.7 | 0 | 0 | 100
1389 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Construction of 300 Cu.M. R.C.C. Over Head Reservoir of 20 Mtr. Staging Height for zone - II of Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2493/JD | 28/02/2024 | 340 | LOPCHAN ENTERPRISE | 90.95 | 0 | 0 | 100
1390 | JALPAIGURI | Northern Mechanical | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHAMURCHI ZONE III, TW NO III (CHUNABHATI) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1638/NMD | 25/09/2024 | 249 | SARKAR ELECTRIC | 14.04 | 0 | 0 | 100
1391 | JALPAIGURI | Jalpaiguri Division | Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labor Colony) Piped Water Supply Scheme. , SM/08876 | Augmentation | Laying of rising main along with pump connection and allied works at Augmentation of Chamurchi Tea Garden Piped W/S Scheme (Zone-III) in connection with JJM at Banarhat Block, under Jalpaiguri Division, P.H.E. Dte. | 260/JSSD | 25/09/2024 | 15 | DITIPRIYA CHOWDHURY | 4.26 | 0 | 0 | 100
1392 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 210/NMD | 04/04/2022 | 21 | SAIKAT SINHA | 1.92 | 0 | 0 | 0
1393 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.45 | 0 | 0 | 0
1394 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.48 | 0 | 0 | 0
1395 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4002964712, Reference ID : 402852793] | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
1396 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | REJ. ARAJIMARIA KAMLA PUKARI PWSS | BP-2021-22-137 | 14/12/2021 | 0 | R.S CONSTRUCTION | 5.05 | 0 | 0 | 0
1397 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 400296685, Reference ID : 402852995] | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0 | 0
1398 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1013/NMD | 28/07/2022 | 21 | MAA ENTERPRISES | 1.87 | 0 | 0 | 0
1399 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 0 | 0 | 1
1400 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2229/JD | 27/12/2021 | 60 | SABITA ENTERPRISE | 11.43 | 0 | 0 | 1
1401 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. III, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 859/NMD | 18/07/2022 | 30 | THE BANERJEE CONCERN | 7.61 | 0 | 0 | 100
1402 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Rejuvenation of Arji Maria Kamala Pukhari PWSS, Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. | 1363/NMD | 02/12/2022 | 30 | SARKAR ELECTRIC | 11.59 | 0 | 0 | 0
1403 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Material Requisition To Resource Division | 1086/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0 | 0
1404 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 386/JD | 10/02/2022 | 60 | SUSANTA GHOSH | 11.44 | 0 | 0 | 100
1405 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. IV, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 860/NMD | 18/07/2022 | 30 | M/S UTPAL CHAKRABORTY & CO. | 7.6 | 0 | 0 | 100
1406 | JALPAIGURI | Northern Mechanical | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1014/NMD | 28/07/2022 | 21 | M/S ANJALI ENTERPRISE | 1.89 | 0 | 0 | 100
1407 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Construction Of approach roads for Arjimaria Kamala Pokhari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(3rd & 4thSite) | 166/RWS | 28/02/2023 | 14 | R.S CONSTRUCTION | 1.61 | 0 | 0 | 1
1408 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Araji Maria Kamala Pukhari piped water supply scheme. , SM/09518 | Augmentation | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Araji Maria Kamala Pukhari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. | 288/RWS | 29/03/2023 | 21 | JAYDEB SAHA | 3.54 | 0 | 0 | 100
1409 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Emergency reparing and laying of distribution system near Gadi khana parallel to the Hatinala and indian oil pipeline in connection with for augmentation of Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | 681/JD | 16/03/2023 | 21 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 5.54 | 0 | 0 | 100
1410 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Emergent minor repairing of Pump House and Chlorine room with Construction of Toilet and Sanitary plumbing system located near Banarhat Thana and repairing works of Pump House near Banarhat Panchayat Office with other ancillary works for Augmentation of Banarhat Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1305/JD | 14/06/2022 | 21 | SANKAR DAS | 3.54 | 0 | 0 | 100
1411 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Material Requisition To Resource Division | 1096/JD | 24/08/2023 | 0 | Resource Division | 106.7 | 0 | 0 | 0
1412 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] |  | 20/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1413 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] | BP/23-24/31 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1414 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] | BP/23-24/46 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0 | 0
1415 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] |  | 20/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0 | 0
1416 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Infrastructure Cost for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] | BP/23-24/114 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0 | 0
1417 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | New Service Connection Charge for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 4003103095 ; Reference ID : 402976411] | BP/23-24/114 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1418 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Laying distribution system with Rising Main Connection, of Banarhat Bazar ( Zone-I) Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | 2518/JD | 30/12/2022 | 1099 | PRADIP SAHA | 68.1 | 0 | 0 | 70
1419 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Laying distribution system with Rising Main Connection of Banarhat Bazar (Zone-II) Piped water supply Scheme, at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-A) | 2051/JD | 02/11/2022 | 842 | GLOBAL POWER & CONSTRUCTION CO. | 108.22 | 0 | 0 | 41
1420 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing and Boundary Wall with land development at Head Works site for Augmentation of Banarhat Bazar (zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2486/JD | 28/12/2022 | 150 | PRADIP SAHA | 107.22 | 0 | 0 | 95
1421 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Banerhat Bazar PWSS at TW-IV (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 313/DSD | 06/03/2023 | 10 | M/S MATRI CONSTRUCTION | 0.49 | 0 | 0 | 100
1422 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Laying of Rising Main Connection between Head works Pump House site and Tube Well site including Internal Pump Connection along with Construction of Pump House for Zone-I of Augmentation of Banarhat PWSS i.c.w. Jal Jeevan Mission at under Jalpaiguri Division, P.H.E. Dte. | 569/JD | 03/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 9.04 | 0 | 0 | 100
1423 | JALPAIGURI | Northern Mechanical | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANERHAT BAZAR PWSS, AT TW no IV (ZONE-I) AND AT TW NO I (ZONE-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 372/NMD | 29/03/2023 | 30 | ANIMA ENTERPRISE | 20.46 | 0 | 0 | 100
1424 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Construction of Pump House (5.40m x 3.60m) internal size with sanitary & plumbing arrangement at Head work site and Providing Functional Household Tap Connection (FHTC) for Augmentation of Banarhat Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division, P.H.E.Dte. | 1851/JD | 15/12/2023 | 262 | SOUVIK SAHA | 10.02 | 0 | 0 | 100
1425 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation of Banerhat Bazar Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division P.H.E. Dte. | 2459/JD | 23/02/2024 | 192 | PRADIP SAHA | 19.04 | 0 | 0 | 100
1426 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Augmentation of Banerhat Bazar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2335/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 0 | 0 | 100
1427 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Interconnection work to connect Pump House, reservoir and distribution network and other allied work of Banarhat Bazar zone- II piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 2752/JD | 14/03/2024 | 15 | PRADIP SAHA | 18.08 | 0 | 0 | 100
1428 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Construction of Approach Culvert at Head Work Site of Banarhat Bazar Zone-II PWSS in Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | 1273 | 03/09/2024 | 30 | PRADIP SAHA | 8.67 | 0 | 0 | 100
1429 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Minor Repairing of Overhead Reservoir, Boundary Wall and Pathway and Allied Works under Augmentation of Banarhat Bazar Zone - I in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | 1266/JD | 02/09/2024 | 30 | PRADIP SAHA | 8.05 | 0 | 0 | 100
1430 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Material Requisition To Resource Division | 2211/JD | 01/12/2024 | 0 | Resource Division | 24.1 | 0 | 0 | 0
1431 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Shifting and Extension of pipeline for widening and strengthening of B.R.O Road From Chamurchi More to Moraghat More along with other L.D.S. Repairing and other anciellary works related to L.D.S. within the command area of Augmentation of Banerhat Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 1949/JD | 13/10/2022 | 902 | SANKAR DAS | 8.96 | 0 | 0 | 100
1432 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation Banerhat Bazar Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | 421/JD | 12/06/2024 | 30 | PRADIP SAHA | 19.04 | 0 | 0 | 60
1433 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | 1520/JD | 16/10/2023 | 562 | ROY ENGINEERS | 41.28 | 0 | 0 | 100
1434 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Construction of Pump Houses, Boundary wall (2nd Site), Drain, & Pathway etc. at Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | 2281/JD | 05/12/2024 | 59 | PRADIP SAHA | 27.89 | 0 | 0 | 100
1435 | JALPAIGURI | Jalpaiguri Division | Augmentation of Banerhat Bazar Piped Water Supply Scheme , SM/10044 | Augmentation | Laying of Pipeline for Crossing Culvert, including supply of CIDF specials and other allied works at Grassmore Tea Garden Piped Water Supply Scheme, in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | 2013/JD | 18/11/2024 | 131 | PRADIP SAHA | 2.93 | 0 | 0 | 100
1436 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasaily T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 560/JSSD | 01/02/2021 | 15 | PRIYABRATA KARMAKAR | 4.84 | 4.83 | 99.88 | 0
1437 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasailya T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 13/JD | 04/01/2021 | 45 | GOUTAM DAS | 26.22 | 26.12 | 99.63 | 0
1438 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06956 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0 | 0 | 0
1439 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAYASAILYA T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | 752/JD | 13/05/2021 | 1183 | GAP ENGINEERS ENTERPRISE | 22.63 | 0 | 0 | 90
1440 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 16.59 | 100 | 0
1441 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Shifting of pipeline due to widening and strengthening of PWD road from Jhak Para Petrol Pump towards Head Work Site Pump House at Kranti zone- I Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 993/JSSD | 03/01/2022 | 20 | NARAYAN CHANDRA ADHIKARY | 3.96 | 0 | 0 | 0
1442 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying of pipeline near at Debijhora High School towards Kranti Bazar including Jhora Crossing under Kranti Zone-II Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 992/JSSD | 03/01/2022 | 15 | NARAYAN CHANDRA ADHIKARY | 2.5 | 0 | 0 | 0
1443 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Emergent restoration of pipeline at Kodalkati area under Kranti GP and construction of periferial boundary including retaining structure at H/W Site for Augmentation of Kranti zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1033/JD | 27/04/2022 | 30 | D. S. ENTERPRISE | 29.73 | 0 | 0 | 0
1444 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | LDS FHTC AUG MONDALGHAT | BP-2021-22-462 | 27/03/2022 | 0 | M/S R.N. TRADERS | 38.53 | 0 | 0 | 0
1445 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | New Service Connection Charge for KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 400295553, Reference ID : 402862646] | BP/22-23/94 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1446 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | DPR PREPARATION FOR ANGRABHASA PWSS | BP-2021-22-547 | 31/03/2022 | 0 | SUBHANKAR GHOSH | 1.05 | 0 | 0 | 0
1447 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Installation of Infrastructure COST at KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 100000059310, Reference ID : 860248970] | BP/22-23/94 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
1448 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | LDS FHTC PURBA DURAMARI | BP-2021-22-493 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 46.78 | 0 | 0 | 0
1449 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) | 207/JD | 24/01/2022 | 60 | M/S A.B.G. CONSTRUCTION | 239.47 | 0 | 0 | 70
1450 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) | 209/JD | 24/01/2022 | 90 | M/S SIBU DEY AND CO. | 130.99 | 0 | 0 | 0
1451 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Emergent Laying Distribution System for inter connection to main line at Bhujari Para and Cana bridge at Kranti zone-II P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1050/JSSD | 24/01/2022 | 15 | BARUN KUMAR DUTTA | 4.71 | 0 | 0 | 0
1452 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Kranti (Zone-II) Piped Water supply scheme under Jalpaiguri Division P.H.E. Dte. | 914/JD | 07/04/2022 | 120 | M/S A.B.G. CONSTRUCTION | 468.36 | 0 | 0 | 70
1453 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No. WB71B-8742) | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 0.15 | 0 | 0 | 0
1454 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0 | 0 | 1
1455 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-C) | 210/JD | 24/01/2022 | 90 | BOSE ENTERPRISE | 156.83 | 0 | 0 | 80
1456 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 410/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 0 | 0 | 0
1457 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Emergent repairing of 3rd T/W site Pump House with Sanitary and Plumbing arrangement for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 253/JD | 10/05/2023 | 21 | NARAYAN CHANDRA ADHIKARY | 2.34 | 0 | 0 | 100
1458 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Construction of Guard Wall at pond side for existing Boundary Wall and joining the pipeline at Kodalkati for Augmentation of Kranti Zone - II Piped Water Scheme under Jalpaiguri Division, P.H.E. Dte. | 291/JSSD | 26/09/2023 | 30 | D. S. ENTERPRISE | 1.55 | 0 | 0 | 100
1459 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | supply of fuel | BP-2022-23-557 | 29/03/2023 | 0 | FILL & SMILE | 0.36 | 0 | 0 | 0
1460 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | fuel charges | BP-2022-23-469 | 23/02/2023 | 0 | FILL & SMILE | 0.8 | 0 | 0 | 0
1461 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1462 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | 567/JSSD | 05/03/2024 | 30 | KOHINOOR ISLAM | 3.22 | 0 | 0 | 70
1463 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Construction of Boundary wall including Rising main Interconnection of Existing 2nd TW Site of Augmentation of Kranti Zone-I PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | 1526/JD | 01/10/2024 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.61 | 0 | 0 | 0
1464 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 411/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 0 | 0 | 100
1465 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Construction of approach for Head Works Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 361/JD | 20/02/2023 | 7 | LOKNATH CONSTRUCTION | 0.61 | 0 | 0 | 100
1466 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KRANTI PWSS, ZONE-II ,TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 340/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 10.18 | 0 | 0 | 90
1467 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Supplying and Installation of 45 nos. Display Board at different piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 497/JSSD | 02/01/2024 | 30 | GOUTAM DAS | 7.17 | 0 | 0 | 100
1468 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | New Service Connection Charge for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 4003266348, Reference ID : 403105518] | 23-24/154&171 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1469 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Infrastructure Cost for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 100000093177, Reference ID : 860284827] | 23-24/154&171 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.78 | 0 | 0 | 0
1470 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
1471 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Construction of Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at 2(two) Nos. Head Works sites for Augmentation works of Kranti (Zone-I and II) Piped Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, P.H.E. Dte. | 797/JD. | 24/07/2023 | 982 | MD HAKIMUDDIN | 291.65 | 0 | 0 | 50
1472 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-II Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | 571/JSSD | 05/03/2024 | 378 | SIDDHARTHA KAR | 8.44 | 0 | 0 | 85
1473 | JALPAIGURI | Jalpaiguri Division | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Balance work of Rising Main, Internal Delivery & Iron Elimination Plant (IEP) connection for Zone-II under Augmentation of Kranti Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 892/JD | 08/05/2025 | 20 | BIMAN DAS | 14.85 | 0 | 0 | 0
1474 | JALPAIGURI | Northern Mechanical | Augmentation of Kranti Piped water supply Scheme , SM/09994 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KRANTI PWSS, ZONE-I ,TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 339/NMD | 29/03/2023 | 675 | SAIKAT SINHA | 10.85 | 0 | 0 | 80
1475 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 435/NMD | 14/06/2022 | 21 | SANJIB SAHA | 2.77 | 0 | 0 | 0
1476 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2191/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.17 | 0 | 0 | 1
1477 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2189/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.5 | 0 | 0 | 1
1478 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 437/NMD | 14/06/2022 | 21 | SAIKAT SINHA | 2.39 | 0 | 0 | 0
1479 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | New Service Connection Charge for BHAGATPUR T.G. W/S SCHEME, T/W No. II, Zone-I, [APPLICATION NO. 4002950622, Reference ID : 402840877] | BP/22-23/44 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.56 | 0 | 0 | 0
1480 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Proposal for Approval W.O & E.O for New Three Phase Connection Work MII.R.O BHAGATPOORN DEEPA LINE, TW NO. 02 at BHAGATPUR T.G., [APPLICATION NO. 100000055158, Reference ID : 860244738] | BP/22-23/44 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0 | 0
1481 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Infrustructure cost for New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053301,Reference ID : 402838302 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0 | 0
1482 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | shifting of pipe line pwd nagrakata | 342/22-23 | 15/09/2022 | 0 | PRADIP SAHA | 0.04 | 0 | 0 | 0
1483 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053303,Reference ID : 402830565 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0 | 0
1484 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002953412,Reference ID : 860244395 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.06 | 0 | 0 | 0
1485 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002939102,Reference ID : 860242791 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0 | 0
1486 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC , APPLICATION NO. 4002939096 , Reference ID : 860242793 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.05 | 0 | 0 | 0
1487 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Infrastructure cost for New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000055565, Reference ID : 860244395 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0 | 0
1488 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Laying distribution system with Rising Main Connection, of Bhagatpur Piped water Supply Scheme , Zone-II at Nagrakata Block under Jalpaiguri Division. P.H.E.Dte. | 212/JD | 24/01/2022 | 60 | LOKNATH CONSTRUCTION | 93.12 | 0 | 0 | 100
1489 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Resistivity Test for Four Nos.Tube Well for Bhagatpur Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1938/JD | 29/11/2021 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0 | 0 | 0
1490 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Carrying out Development works and Yield Test for a RBTW (BDTW) at Shyamdhan W/S Scheme (H/W Site) & (2nd Site), Replacement TW, G.P.- Raniganj Panisali, Block - Kharibari, Dist- Darjeeling and Bhagatpur TG PWSS (Zone-I), TW-I (H/W Site) & TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri and Naxalbari RH W/S Scheme, Block - Naxalbari, Dist- Darjeeling, under Northern Mechanical Division, P.H.E., Dte. | 262/DSD | 22/12/2021 | 21 | ALPHA ENTERPRISE | 0.53 | 0 | 0 | 100
1491 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. I in the dist. of Jalpaiguri under under Northern Mechanical Division, P.H. Engineering Dte. | 436/NMD | 14/06/2022 | 21 | BLUE PINE | 2.39 | 0 | 0 | 70
1492 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Bhagatpur T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | 1855/JD | 16/09/2022 | 45 | ADITRI ENTERPRISE | 4.65 | 0 | 0 | 1
1493 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 867/NMD | 20/07/2022 | 30 | ANUP BASU | 10.29 | 0 | 0 | 0
1494 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 535/NMD | 08/07/2022 | 30 | RIPON DAS | 9.99 | 0 | 0 | 100
1495 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Bhagatpur T.G. P.W.S.S. zone-II under Jalpaiguri Division P.H.E.Dte. | 1854/JD | 16/09/2022 | 45 | RANA DEY | 4.65 | 0 | 0 | 1
1496 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Construction of approach road including development of the approach way for the Head works site of Bhagatpur T.G. Piped water supply Scheme Zone -II under Jalpaiguri Division, P.H.E. Dte. | 1798/JD | 14/09/2022 | 21 | ASIT PAUL | 2.84 | 0 | 0 | 0
1497 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 434/NMD | 14/06/2022 | 21 | MIHIR SARKAR | 2.77 | 0 | 0 | 70
1498 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 533/NMD | 08/07/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 10.3 | 0 | 0 | 50
1499 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1500 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Laying distribution system and construction of Boundary Wall ,Foot Path, Drain at HW site of Bhagatpur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 427/JD | 13/06/2024 | 30 | LOKNATH CONSTRUCTION | 34.67 | 0 | 0 | 45
1501 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling at TW-II (2nd Site) under Bhagatpur TG PWSS (Zone-II), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 257/DSD | 17/12/2021 | 15 | RUDOLF DIESEL ENGINEERING SERVICE | 0.49 | 0 | 0 | 100
1502 | JALPAIGURI | Northern Mechanical | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 534/NMD | 08/07/2022 | 30 | SUBODH KUMAR BANIK | 10.02 | 0 | 0 | 100
1503 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Material Requisition To Resource Division | 2060/JD | 10/01/2024 | 0 | Resource Division | 11.74 | 0 | 0 | 0
1504 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Construction of 150 Cu.M. Capacity R.C.C. Over Head Reservoir of 17 Mtr. Staging Height, Construction of One No Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site Zone-II of Bhagatpur PWSS under Jalpaiguri Division, P.H.E. Dte. | 1055/JD | 27/04/2022 | 1161 | LOKNATH CONSTRUCTION | 63.09 | 0 | 0 | 50
1505 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Providing Functional Household Tap Connection in connection with Jal Jeeven Mission under Bhagatpur Piped Water Supply Scheme Zone-II Command area under Jalpaiguri Division P.H.E. Dte. (Phase-I) | 2458/JD | 22/12/2022 | 952 | UDAYAN BOSE | 23.71 | 0 | 0 | 100
1506 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Restoration of existing damaged pipeline near railway crossing at Jhahaji line in connection with Jal Jeevan Mission under Bhagatpur Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | 428/JD | 13/06/2024 | 657 | LOKNATH CONSTRUCTION | 25.24 | 0 | 0 | 25
1507 | JALPAIGURI | Jalpaiguri Division | Bhagatpur Tea Garden Area Piped Water Supply Scheme. , SM/09975 | New | Rising Main and FHTC at Bhagatpur PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 1953/JD | 18/09/2025 | 195 | ADITRI ENTERPRISE | 14.59 | 0 | 0 | 30
1508 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Material Requisition To Resource Division | 1109/JD | 24/08/2023 | 0 | Resource Division | 25.74 | 0 | 0 | 0
1509 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-I, TW no I, II, III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1372/NMD | 09/08/2023 | 30 | EASTERN INDIA SALES & SERVICE | 43.5 | 0 | 0 | 45
1510 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Material Requisition To Resource Division | 2004/JD | 08/01/2024 | 0 | Resource Division | 13.46 | 0 | 0 | 0
1511 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003376713 Reference ID : 403191839 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0 | 0
1512 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003378751 Reference ID : 403193482 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.36 | 0 | 0 | 0
1513 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-III, under DHUPGURI CCC APPLICATION NO. 4003390202 Reference ID : 403202832 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.73 | 0 | 0 | 0
1514 | JALPAIGURI | Jalpaiguri Division | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Boragari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 110/JD | 16/01/2025 | 45 | BISWANATH GHOSH | 47.44 | 0 | 0 | 0
1515 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
1516 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
1517 | JALPAIGURI | Northern Mechanical | MADHYA BAROGARI ZONE-I PIPED WATER SUPPLY SCHEME , SM/13681 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
1518 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | Commissioning of Baradighi Tea Garden Area Piped water supply Scheme under Jalpaiguri Division P.H.E. Dte. | 173/JSSD | 25/08/2022 | 60 | PRIYABRATA KARMAKAR | 4.59 | 0 | 0 | 0
1519 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | Material Requisition To Resource Division | 171/JD | 28/04/2023 | 0 | Resource Division | 3.55 | 0 | 0 | 0
1520 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | Material Requisition To Resource Division | 2044/JD | 09/01/2024 | 0 | Resource Division | 1.29 | 0 | 0 | 0
1521 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-279 | 01/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1522 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
1523 | JALPAIGURI | Jalpaiguri Division | BARA DIGHI PIPED WATER SUPPLY SCHEME , SM/13703 | New | Construction of different components of BaraDighi PWSS i.e. TW, Pump Houses, Water distribution Network,OHR,RISING MAIN,FHTC etc. i.c.w Jal Jeevan Mission at Block-Matiali under Jalpaiguri Division,P.H.E.Dte. | 775/JD | 27/03/2023 | 1099 | RAGHU DAS | 107.46 | 0 | 0 | 90
1524 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Material Requisition To Resource Division | 163/JD | 28/04/2023 | 0 | Resource Division | 44.06 | 0 | 0 | 0
1525 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Construction of different components of Dhumpara (N) (Zone-I & II) PWSS i.e, TW Pump House , Water distribution Network, OHR, RISING MAIN , FHTC etc. I.c.w Jal Jeevan Mission at Block - Nagrakata Under Jalpaiguri Divison P.H.E Dte. | 262/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 471.75 | 0 | 0 | 33
1526 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHUMPARA PWSS , Zone-I (TW No. I, II) and Zone-II (TW No- I, II and III) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1340/NMD | 08/08/2023 | 30 | A.G. ENTERPRISE | 60.95 | 0 | 0 | 50
1527 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0 | 0 | 0
1528 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1529 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 0
1530 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 70
1531 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2023 to 31/01/2025 | 326/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 0
1532 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 570/JSSD | 05/03/2024 | 45 | ARUP SARKAR | 8.23 | 0 | 0 | 100
1533 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Material Requisition To Resource Division | 2055/JD | 09/01/2024 | 0 | Resource Division | 14.08 | 0 | 0 | 0
1534 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-487 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1535 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. I, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321209 ; Reference ID : 403147529] | BP/23-24/299 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.95 | 0 | 0 | 0
1536 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. III, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321422 ; Reference ID : 403147798] | BP/23-24/301 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
1537 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | New Service Connection Charge for DHUMPARA, T/W No. II, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321417 ; Reference ID : 403147621] | BP/23-24/300 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
1538 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
1539 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-297 | 14/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1540 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2024 to 31/01/2025 | 325/1/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 0
1541 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Continuation work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/02/2025 to 30/04/2025(Vehicle No WB 71B 9430) | 416/JSSD | 28/01/2025 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 0
1542 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
1543 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
1544 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR DHUMPARA N , SM/13987 | New | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
1545 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Material Requisition To Resource Division | 1074/JD | 24/08/2023 | 0 | Resource Division | 47.59 | 0 | 0 | 0
1546 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1547 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Neoranadi TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | 2275/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 67.08 | 0 | 0 | 0
1548 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Material Requisition To Resource Division | 2013/JD | 09/01/2024 | 0 | Resource Division | 8.43 | 0 | 0 | 0
1549 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | New Service Connection Charge for NEORA NADI, T/W No. II, under MAL CCC [APPLICATION NO. 4003302999 , Reference ID : 403132352] | BP/23-24/237 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1550 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | New Service Connection Charge for NEORA NODI TEA GARDEN, T/W No. I under MAL CCC [APPLICATION NO. 4003256029 ; Reference ID : 403097550] | BP/23-24/239 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1551 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Infrastructure Cost for NEORA NADI, T/W No. II, under MAL CCC [APPLICATION NO. 100000096819 , Reference ID : 860287689] | BP/23-24/236 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0 | 0
1552 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
1553 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Infrastructure Cost for NEORA NODI TEA GARDEN, T/W No. I under MAL CCC [APPLICATION NO. 100000091998 ; Reference ID : 860283908] | BP/23-24/238 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.37 | 0 | 0 | 0
1554 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Neoranadi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 174/JSSD | 25/07/2025 | 30 | ADWIJA CONSTRUCTION | 7.51 | 0 | 0 | 0
1555 | JALPAIGURI | Jalpaiguri Division | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Construction of different components of Neoranadi Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 238/JD | 08/05/2023 | 878 | PRASENJIT BASAK | 286.38 | 0 | 0 | 100
1556 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1557 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1558 | JALPAIGURI | Northern Mechanical | NEORA NADI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15115 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEORA NADI PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1806/NMD | 31/10/2023 | 459 | S.P. ENTERPRISE (KOLKATA) | 24.79 | 0 | 0 | 100
1559 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Providing Functional Household Tap Connection in connection with Jalswapna with retrofitting work for Mahalaxmi Colony, Lataguri for Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 0 | 0 | 0
1560 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Soil Investigation work for 350 CuM Over Head Reservoir for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. | 1069/JSSD | 25/01/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.83 | 0 | 0 | 1
1561 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Providing Functional House hold Tap connection in connection with Jalswapna with retroffiting work for Mahalaxmi Colony, Lataguri for Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 0 | 0 | 1
1562 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Minor repairing and renovation of 3rd T/W site and H/W site Pump Houses at Lataguri Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 987/JSSD | 03/01/2022 | 20 | D. S. ENTERPRISE | 2.63 | 0 | 0 | 0
1563 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1564 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone-II under KRANTI CCC , [APPLICATION NO. 100000059309, Reference ID : 860248969] |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0 | 0
1565 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. I, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1566 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4100000054083, Reference ID : 860243703] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0 | 0
1567 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone I under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0 | 0
1568 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II, Zone II under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1569 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. I, Zone-III under KRANTI CCC , [APPLICATION NO. 100000059308, Reference ID : 860248968] |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
1570 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II,Zone I under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1571 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0 | 0
1572 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4002941867, Reference ID : 402838302] | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0 | 0
1573 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of approach for Head Works Site for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 360/JD | 20/02/2023 | 7 | RAGHU DAS | 0.56 | 0 | 0 | 0
1574 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Laying of Rising Main from 1st, 2nd & 3rd Tube Well site to OHR for Augmentation of Lataguri (Zone-I) PWSS in connection with Jal Jeevan Mission at Block -Kranti under Jalpaiguri Division, P.H.E.Dte. | 277/JSSD | 21/09/2023 | 30 | ARUP SARKAR | 6.5 | 0 | 0 | 0
1575 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size including sanitary and Plumbing Works at 3rd tube well site for Augmentation of Lataguri (zone-II) PWSS under Jalpaiguri Division, PHE Dte. | 1066/JSSD | 24/02/2022 | 45 | ROY CONSTRUCTION | 4.76 | 0 | 0 | 1
1576 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Emergent Laying of diverted line damaged by excavator due to construction of Market Complex at Lataguri Bazar and replacing the damaged GI line at Lal Setu at Lataguri Water Supply Scheme under Jalpaiguri Division PHE Dte. | 990/JSSD | 03/01/2022 | 10 | LOKNATH CONSTRUCTION | 1.47 | 0 | 0 | 100
1577 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size including sanitary plumbing works at 2nd tube well site for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. | 1054/JSSD | 24/01/2022 | 45 | KABYA ENTERPRISE | 4.76 | 0 | 0 | 100
1578 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Soil Investigation work for 300 CuM Over Head Reservoir Augmentation of Lataguri (Zone-III) PWSS, under Jalpaiguri Division, PHE Dte. | 1067/JSSD | 24/01/2022 | 20 | MABCO CONSULTANT | 1.83 | 0 | 0 | 1
1579 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte. | 1031/JD | 26/04/2022 | 180 | RAGHU DAS | 96.77 | 0 | 0 | 1
1580 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Rig approach for Installation of tubewell of Head Works, 2nd Tubewell and 3rd Tube Well site for Augmentation of Lataguri Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | 86/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 1.46 | 0 | 0 | 1
1581 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Emergent Laying of pipeline at Purba Lataguri Station Para and repairing old stand post (broken)due to widening and strengthening of PWD lataguri-Kranti Road at Lataguri Water Supply Scheme under Jalpaiguri Division,PHE Dte. | 87/JSSD | 22/07/2022 | 10 | KAMALESH SEN | 1.11 | 0 | 0 | 1
1582 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Repairing of 2nd Pump House, office-cum-godown, IEP platform and construction of drain with earth filling in H/W site and ancillary works with over hauling of 3-unit IEP plant for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1946/JD | 13/10/2022 | 21 | D. S. ENTERPRISE | 18.91 | 0 | 0 | 0
1583 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/06/2023 to 31/07/2023. | 558/RWS | 31/05/2023 | 61 | APIKUL ALI | 0.29 | 0 | 0 | 100
1584 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Material Requisition To Resource Division | 1066/JD | 24/08/2023 | 0 | Resource Division | 342.41 | 0 | 0 | 0
1585 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070391, Reference ID : 860261321] | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.57 | 0 | 0 | 0
1586 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003078500, Reference ID : 402950395] | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1587 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070390, Reference ID : 860261320] | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.94 | 0 | 0 | 0
1588 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS | BP-2023-24-111 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 2.85 | 0 | 0 | 0
1589 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - III W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003071675, Reference ID : 402950393] | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
1590 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | SUPPLY OF 1(ONE) MAXI CAB WITH ENGINE CAPACITY MORE THAN 2000C.C ON HIRE BASIS INCLUDING DRIVER FOR ASSISTANT ENGINEER (SADAR), JALPAIGURI SADAR SUB DIVISION, P.H.E. DTE. DIST-JALPAIGURI (WITH VALID PERMIT) | BP-2023-24-292 | 10/08/2023 | 0 | MANIK RAY | 0.25 | 0 | 0 | 0
1591 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1899/JD | 26/09/2022 | 90 | CALCON CONSTRUCTIONS | 267.26 | 0 | 0 | 80
1592 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0 | 0 | 0
1593 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1594 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 0
1595 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0 | 70
1596 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-III) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte | 1922/JD | 28/09/2022 | 180 | J.M. CONSTRUCTION | 84.24 | 0 | 0 | 100
1597 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 78/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 0 | 0 | 100
1598 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no II, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 56/NMD | 24/01/2023 | 30 | SUDIP DUTTA | 10.71 | 0 | 0 | 60
1599 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 73/NMD | 27/01/2023 | 278 | MUSTAFI CONCERN | 10.7 | 0 | 0 | 100
1600 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 55/NMD | 24/01/2023 | 30 | SUMON ELECTRICAL | 10.74 | 0 | 0 | 90
1601 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 57/NMD | 24/01/2023 | 30 | INDRANI ENTERPRISE | 10.74 | 0 | 0 | 100
1602 | JALPAIGURI | Northern Mechanical | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 54/NMD | 24/01/2023 | 30 | S.P. ENTERPRISE | 10.73 | 0 | 0 | 80
1603 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Lataguri (Zone-III) in connection with PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | 281/JSSD | 26/09/2023 | 30 | GOPRO CONSTRUCTION | 3.62 | 0 | 0 | 100
1604 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Rising Line Connection with wash line and balance work in Head Works site at Augmentation of Lataguri(zone-II) PWSS under Jalpaiguri Division,P.H.E.Dte. | 506/JSSD | 02/01/2024 | 30 | RAGHU DAS | 9.22 | 0 | 0 | 100
1605 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Rejuvenation of different components of PWSS of Over Head Reservoir site at Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 423/JD | 12/06/2024 | 45 | APEX ENGINEERING | 22.45 | 0 | 0 | 100
1606 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 79/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 0 | 0 | 100
1607 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Balance work for Laying Distribution System with Providing FHTC for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.¿. Dte. | 298/JSSD | 03/10/2024 | 15 | CALCON CONSTRUCTIONS | 8.06 | 0 | 0 | 100
1608 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Material Requisition To Resource Division | 2216/JD | 01/12/2024 | 0 | Resource Division | 30.66 | 0 | 0 | 0
1609 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | SUPPLY OF FUEL(DISEL) FOR THE VEHICLE NO. WB-78-3405 FOR THE MONTH OF FEBRUARY2024 FOR THE OFFICE USE OF THE ASSISTANT ENGINEER ,SADAR SUB DIVISION, UNDER EXECUTIVE ENGINEER ,JALPAIGURI DIVISION. | BP-2024-25-15 | 12/04/2024 | 0 | FILL & SMILE | 0.25 | 0 | 0 | 0
1610 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-499 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
1611 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 877/JD | 05/04/2022 | 1367 | SCEC BOENTER KDAS JOINT VENTURE | 237.94 | 0 | 0 | 88
1612 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 3rd & 4th TW including Rising main for Augmentation of Lataguri PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 1417/JD | 20/09/2024 | 236 | M/S SIBU DEY AND CO. | 40.12 | 0 | 0 | 40
1613 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Balance work in HW site at Zone-III of Augmentation of Lataguri PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 455/JD | 10/03/2025 | 30 | J.M. CONSTRUCTION | 16.72 | 0 | 0 | 0
1614 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Construction of Pump House (3.6x2.4) m with Land Development, Boundary Wall, approach, Retrofitting work of Lataguri Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte | 1331/JD | 23/08/2021 | 1472 | R.K. SINGHA & SONS | 15.94 | 0 | 0 | 100
1615 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | 1433/JD | 05/10/2023 | 373 | ARUP SARKAR | 15.64 | 0 | 0 | 100
1616 | JALPAIGURI | Jalpaiguri Division | Augmentation of Lataguri Piped Water Supply Scheme , SM/13278 | Augmentation | Extension of Main Distribution Line to Connect the Overhead Reservoir and Laying Pipeline for Direct Boosting for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. | 568/JSSD | 05/03/2024 | 407 | ARUP SARKAR | 7.33 | 0 | 0 | 100
1617 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Tunbari Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1762/JD | 08/12/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 0 | 100
1618 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Material Requisition To Resource Division | 1091/JD | 24/08/2023 | 0 | Resource Division | 35.62 | 0 | 0 | 0
1619 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Material Requisition To Resource Division | 1888/JD | 20/12/2023 | 0 | Resource Division | 9.92 | 0 | 0 | 0
1620 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Construction of different components of Tunbari Tea Garden (P) PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block ¿ Mal under Jalpaiguri Division, P.H.E.Dte. | 265/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 304.78 | 0 | 0 | 70
1621 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TUNBARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1388/NMD | 09/08/2023 | 30 | M/S CHANDRANATH MUKHERJEE | 25.75 | 0 | 0 | 80
1622 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1623 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Malbazar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1291/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
1624 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 100000102137 Reference ID : 860293897 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0 | 0
1625 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | New Service Connection Charge for TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 4003299893 Reference ID : 403130044 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1626 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | New Service Connection Charge for TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 4003299902 Reference ID : 403130042 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1627 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 100000102138 Reference ID : 860293898 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.32 | 0 | 0 | 0
1628 | JALPAIGURI | Jalpaiguri Division | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Laying distribution system with other allied works in connection with Jal Jeevan Mission at Tunbari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 105/JSSD | 30/05/2025 | 45 | GURUKUL INFOTECH | 4.97 | 0 | 0 | 0
1629 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1630 | JALPAIGURI | Northern Mechanical | TUNBARI TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/14883 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1631 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BAIKUR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15580 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1632 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BAIKUR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15580 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1633 | JALPAIGURI | Jalpaiguri Division | RETROFITTING OF MAHITNAGAR PWSS , SM/15131 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion of Mohitnagar W/S Scheme in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (PART-J) | 1269/JD | 13/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 63.37 | 0 | 0 | 90
1634 | JALPAIGURI | Jalpaiguri Division | RETROFITTING OF MAHITNAGAR PWSS , SM/15131 | Retrofitting | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Mahit Nagar PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) | 433/JD. | 08/06/2023 | 28 | RAGHU DAS | 52.95 | 0 | 0 | 98
1635 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Material Requisition To Resource Division | 1049/JD | 24/08/2023 | 0 | Resource Division | 2.45 | 0 | 0 | 0
1636 | JALPAIGURI | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | New Service Connection Charge for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 4003220150, Reference ID : 403066255] | BP/23-24/107 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1637 | JALPAIGURI | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Infrastructure Cost for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 100000088108, Reference ID : 860279669] | BP/23-24/107 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.96 | 0 | 0 | 0
1638 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | FUEL BILL | BP-2023-24-433 | 11/10/2023 | 0 | FILL & SMILE | 0.53 | 0 | 0 | 0
1639 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.08.2023 to 31.01.2024) | 877/RWS | 31/07/2023 | 184 | ASHIM SARKAR | 0.88 | 0 | 0 | 20
1640 | JALPAIGURI | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SONGACHI TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1332/NMD | 08/08/2023 | 30 | ASHWIRBAD WOOD CRAFT | 12.01 | 0 | 0 | 90
1641 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.02.2024 to 31.07.2024) | 93/RWS | 29/01/2024 | 182 | ASHIM SARKAR | 0.88 | 0 | 0 | 50
1642 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Construction of deep tube well by ODEX-195 method of drilling for Songachi T.G. Piped Water Supply Scheme, Block- Matiali, Dist- Jalpaiguri. | 1592/JD | 17/08/2022 | 21 | R.S CONSTRUCTION | 9.32 | 0 | 0 | 100
1643 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-296 | 14/08/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
1644 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of July 2024 | BP-2024-25-295 | 14/08/2024 | 0 | FILL & SMILE | 0.2 | 0 | 0 | 0
1645 | JALPAIGURI | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
1646 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Sinking of 2 (Two) Nos Additional Tube Well by ODEX-165 method including Construction of different components i.e. Pump Houses, Boundary Walls, Rising Mains etc. for 4th and 5th site of Songachi Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. | 630/JD | 28/03/2025 | 60 | PINAKI MITRA | 36.19 | 0 | 0 | 0
1647 | JALPAIGURI | Northern Mechanical | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1648 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF SONGACHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/15077 | Augmentation | Construction of different components of Rejuvenation of Songachi T.G. PWSS i.e pump houses, water distribution network, Boundary wall, Rising main, FHTC etc. in connection with JJM at Block - Matiali under jalpaiguri Division P.H.E.Dte. | 441/JD. | 08/06/2023 | 662 | PINAKI MITRA | 34.93 | 0 | 0 | 100
1649 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KURTI TEA GARDEN PWSS(TW No- I, II and III), in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1804/NMD | 31/10/2023 | 30 | SARKAR ELECTRIC | 37.45 | 0 | 0 | 0
1650 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Material Requisition To Resource Division | 167/JD | 28/04/2023 | 0 | Resource Division | 56.03 | 0 | 0 | 0
1651 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Construction of different components of Kurti Tea Garden (Zone-I, II and III) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 263/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 308.54 | 0 | 0 | 0
1652 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Material Requisition To Resource Division | 2038/JD | 09/01/2024 | 0 | Resource Division | 6.64 | 0 | 0 | 0
1653 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
1654 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
1655 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR KURTI TEA GARDEN , SM/16492 | New | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
1656 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Material Requisition To Resource Division | 1370/JD | 27/09/2023 | 0 | Resource Division | 87.93 | 0 | 0 | 0
1657 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN HANSKHALI PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1487/NMD | 17/08/2023 | 30 | HARA PROSAD DAS | 40.27 | 0 | 0 | 80
1658 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1659 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Material Requisition To Resource Division | 2016/JD | 09/01/2024 | 0 | Resource Division | 17.2 | 0 | 0 | 0
1660 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 4003445776 Reference ID : 403244353 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1661 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 100000112205 Reference ID : 860304705 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0 | 0
1662 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 4003445808 Reference ID : 403244351 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1663 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 100000112206 Reference ID : 860304706 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.16 | 0 | 0 | 0
1664 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 4003445819 Reference ID : 403244352 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
1665 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 100000112207 Reference ID : 860304707 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.52 | 0 | 0 | 0
1666 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Construction of different components of Dakshin Hanskhali PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E.Dte. | 799/JD. | 24/07/2023 | 1135 | M/S. D.K. DEY & CO.. | 465.94 | 0 | 0 | 45
1667 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Construction of Boundary Wall, Land Development, Pathway, Surface Drain etc. at H/W site of Dakshin Hanskhali PWSS i.c.w. Jal Jeevan Mission at block- Kranti under Jalpaiguri Division, PHE Dte. | 484/JD | 11/03/2025 | 45 | M/S. D.K. DEY & CO.. | 21.14 | 0 | 0 | 0
1668 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 3rd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | 481/RWS | 29/05/2025 | 30 | GOURAV CONSTRUCTION CO. | 6.98 | 0 | 0 | 0
1669 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
1670 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Balance Laying Distribution Network and Providing Functional Household Tap connection (FHTC) including Construction of additional components of Dakshin Hanskhali PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | 465/JD | 11/03/2025 | 60 | M/S. D.K. DEY & CO.. | 74.53 | 0 | 0 | 0
1671 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
1672 | JALPAIGURI | Jalpaiguri Division | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | 482/RWS | 29/05/2025 | 30 | M/S. D.K. DEY & CO.. | 8.36 | 0 | 0 | 0
1673 | JALPAIGURI | Northern Mechanical | DAKSHIN HANSKHALI PIPED WATER SUPPLY SCHEME , SM/15335 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
1674 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MADHABDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15615 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
1675 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MADHABDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15615 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1676 | JALPAIGURI | Northern Mechanical | KHUKLUNG PIPED WATER SUPPLY SCHEME , SM/15953 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUKHLUNG PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1492/NMD | 17/08/2023 | 30 | SANJIB SAHA | 6.09 | 0 | 0 | 0
1677 | JALPAIGURI | Jalpaiguri Division | KHUKLUNG PIPED WATER SUPPLY SCHEME , SM/15953 | New | Material Requisition To Resource Division | 2001/JD | 08/01/2024 | 0 | Resource Division | 0.73 | 0 | 0 | 0
1678 | JALPAIGURI | Jalpaiguri Division | KHUKLUNG PIPED WATER SUPPLY SCHEME , SM/15953 | New | Construction of different components of Khuklung Mini PWSS ie. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Dhupguri Block, under Jalpaiguri Division, P.H.E.Dte. | 1265/JD | 13/09/2023 | 656 | DEBASISH DEY | 63.25 | 0 | 0 | 90
1679 | JALPAIGURI | Jalpaiguri Division | HAIHAIPATHAR PWSS , SM/16852 | New | Material Requisition To Resource Division | 1085/JD | 24/08/2023 | 0 | Resource Division | 28.59 | 0 | 0 | 0
1680 | JALPAIGURI | Jalpaiguri Division | HAIHAIPATHAR PWSS , SM/16852 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1681 | JALPAIGURI | Jalpaiguri Division | HAIHAIPATHAR PWSS , SM/16852 | New | Sinking of 2 (Two) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of Hai Hai Pather PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 2311./JD | 11/12/2024 | 70 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 34.93 | 0 | 0 | 0
1682 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HAIHAIPATHAR PWSS, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1490/NMD | 17/08/2023 | 30 | ANIMA ENTERPRISE | 25.32 | 0 | 0 | 100
1683 | JALPAIGURI | Jalpaiguri Division | HAIHAIPATHAR PWSS , SM/16852 | New | Material Requisition To Resource Division | 2022/JD | 09/01/2024 | 0 | Resource Division | 14.2 | 0 | 0 | 0
1684 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | Infrastructure Cost for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 100000092012 ; Reference ID :860283912] | BP/23-24/251 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.17 | 0 | 0 | 0
1685 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | New Service Connection Charge for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 4003255985 ; Reference ID :403097549] | BP/23-24/250 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1686 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | New Service Connection Charge for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 4003255959 ; Reference ID :403097548] | BP/23-24/252 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1687 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | Additional Quotation for Infrastructure development cost for new service connection at Hai Hai Pather, TW NO-II, MAL CCC APPLICATION NO. 100000103229 Reference ID : 860295639 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.78 | 0 | 0 | 0
1688 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | Infrastructure Cost for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 100000091999 ; Reference ID :860283909] | BP/23-24/253 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0 | 0
1689 | JALPAIGURI | Northern Mechanical | HAIHAIPATHAR PWSS , SM/16852 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
1690 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT YOUNGTONG TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15625 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1691 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT YOUNGTONG TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15625 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1692 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT KUMLAI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15601 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1693 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT KUMLAI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15601 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1694 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA DURAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15603 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
1695 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT PURBA DURAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15603 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
1696 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site to sukhanii zone - II (H/W site T/W ) under Jalpaiguri Division PHE Dte. Part B ( Left & Right) | 291/JD | 13/03/2020 | 60 | SADHAN KARMAKAR | 9.7 | 0 | 0 | 1
1697 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 511/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 0 | 1
1698 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 512/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 0 | 1
1699 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 842/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 0 | 0 | 1
1700 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 843/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 0 | 0 | 1
1701 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site for " SUKHANI ZONE-II WATER SUPPLY SCHEME ( H/ W SITE T/W )" under Jalpaiguri Divition , P.H.E. Dte. Part-"A" (Front Side) | 248/JD | 03/03/2020 | 60 | SUBRATA GOSWAMI | 14.17 | 0 | 0 | 1
1702 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 2nd Tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 514/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 0 | 0 | 1
1703 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III head work site at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 513/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 0 | 0 | 1
1704 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | EXT PIPE LINE SUKHANI ZONE - II | BP-2021-22-503 | 30/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
1705 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | CONST 250 M3 B/WALL BARADIGHI T.G | BP-2021-22-471 | 28/03/2022 | 0 | BOSE ENTERPRISE | 49.78 | 0 | 0 | 0
1706 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002950741,Reference ID : 860244518 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1707 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Infrastructure IRO NSC Application 4002960888 at Nawapara, Chaulhati under UMCCC ¿ Sukhani , Zone-III, T/W No. III, [APPLICATION NO. 100000057238, Reference ID : 860246418] | BP/22-23/57 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0 | 0
1708 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951589,Reference ID : 860244513 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1709 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | TUBE WELL SUKHANI ZONE-II | BP-2021-22-479 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 6.93 | 0 | 0 | 0
1710 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056935 , Reference ID : 860245495] | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
1711 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054732,Reference ID : 402840892 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.89 | 0 | 0 | 0
1712 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056936 , Reference ID : 860245496] | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
1713 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | LDS PURBA DAUKIMARI PWSS | BP-2022-23-45 | 24/05/2022 | 0 | SUKES BASU MAJUMDAR | 58.14 | 0 | 0 | 0
1714 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Infrastructure COST at SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 100000058353, Reference ID : 860248265] | BP/22-23/60 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
1715 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | LDS BARADIGHI TG PWSS | BP-2021-22-475 | 31/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 7.66 | 0 | 0 | 0
1716 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054733,Reference ID : 402840890 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0 | 0
1717 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054738,Reference ID : 402840893 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
1718 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951616,Reference ID : 860244512 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1719 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | SINKING OF 300MM X 200MM DIA 3RD T/WELL SUKHANI PWSS ZONE-II | BP-2021-22-479 | 29/03/2022 | 0 | B.M CONSTRUCTION | 6.93 | 0 | 0 | 0
1720 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | LDS FHTC DAKHIN CHAK MAULANI | BP-2021-22-472 | 28/03/2022 | 0 | UNIBRO INFRASERV PRIVATE LIMITED | 21.09 | 0 | 0 | 0
1721 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for Sukhani , Zone-III, T/W No. III near Nawapara, [APPLICATION NO. 4002960888, Reference ID : 402852055] | BP/22-23/57 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1722 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957097 , Reference ID : 402849241] | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1723 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 4002974096, Reference ID :402863303] | BP/22-23/60 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1724 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957084 , Reference ID : 402849240] | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1725 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Distribution System including FHTC for Augmentation of Sukani Piped Water Supply Scheme Zone-III at Rajganj Block Jalpaiguri Division PHE Dte. | 1101/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 668.61 | 0 | 0 | 1
1726 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1196/JD | 20/05/2022 | 45 | SHYAMAL KUMARSAHA | 4.64 | 0 | 0 | 0
1727 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1200/JD | 20/05/2022 | 45 | M/S A.P. DEVELOPERS | 4.65 | 0 | 0 | 0
1728 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site (ZONE-I) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT ¿ JALPAIGURI. | 1273/JD | 07/06/2022 | 45 | M/S SURAJIT DEY AND CO. | 29.51 | 0 | 0 | 0
1729 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1010/NMD | 28/07/2022 | 21 | ANUP BASU | 2.77 | 0 | 0 | 0
1730 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1197/JD | 20/05/2022 | 45 | UNIQUE CONSTRUCTION | 4.64 | 0 | 0 | 0
1731 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1007/NMD | 28/07/2022 | 21 | DAWA DUKPA | 2.39 | 0 | 0 | 0
1732 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no IIin the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1059/NMD | 24/08/2022 | 30 | ABHISEK ENGINEERING CONCERN | 8.26 | 0 | 0 | 100
1733 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1108/NMD | 07/09/2022 | 30 | M/S P.P. ELECTRICALS | 8.26 | 0 | 0 | 100
1734 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0 | 0 | 0
1735 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Continuation order for the work of "Providing guarding arrangement at Stack Yard under Resource Division at the Head Work Site of SUKHANI PWSS (ZONE-I) under Jalpaiguri Division P.H.E. Dte. for the period from 01/08/2022 to 31/07/2023." | 1504/A/JD | 28/07/2022 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.62 | 0 | 0 | 0
1736 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd TubeWell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS zone -III at Rajganj Block under Jalpaiguri Division P.H.E. Dte | 766/JD | 23/03/2022 | 21 | M/S KARMAKAR CONSTRACTION | 8.09 | 0 | 0 | 1
1737 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1201/JD | 20/05/2022 | 45 | KABYA ENTERPRISE | 4.64 | 0 | 0 | 100
1738 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1004/NMD | 28/07/2022 | 21 | SUMON ELECTRICAL | 2.79 | 0 | 0 | 100
1739 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1198/JD | 20/05/2022 | 45 | DILIP SINGHA | 4.65 | 0 | 0 | 1
1740 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-II zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1433/JD | 18/07/2022 | 15 | MOYTEC | 2.25 | 0 | 0 | 100
1741 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1373/JD | 30/06/2022 | 45 | PARESH CHAND GHOSH ROY | 4.64 | 0 | 0 | 1
1742 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1005/NMD | 28/07/2022 | 21 | CHOWDHURY AND BASU ENTERPRISE | 2.79 | 0 | 0 | 100
1743 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. II, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1009/NMD | 28/07/2022 | 21 | SARKAR ELECTRIC | 2.79 | 0 | 0 | 100
1744 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Support 300 mm DI pipe line near Fatapukur and construction 1 no. stand post and other ancillary works at Sukani Zone I under Rajganj block under Jalpaiguri Division PHE Dte. | 1809/JD | 14/09/2022 | 21 | R.K. SARKAR | 1.8 | 0 | 0 | 1
1745 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at 3rd Tube Well site for Sukhani Piped Water Supply Scheme Zone-II at Rajganj block under Jalpaiguri division PHE Dte. | 449/JD. | 08/06/2023 | 45 | JAGORAN SARKAR | 4.9 | 0 | 0 | 100
1746 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) for Augmentation at 3rd tubewell site Sukani (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1358/JD | 26/09/2023 | 45 | D. S. ENTERPRISE | 18.23 | 0 | 0 | 100
1747 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Material Requisition To Resource Division | 1097/JD | 24/08/2023 | 0 | Resource Division | 208.46 | 0 | 0 | 0
1748 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Distribution System for Augmentation of Sukani Piped Water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 1102/JD | 12/05/2022 | 1420 | M/S A.B.G. CONSTRUCTION | 886.96 | 0 | 0 | 78
1749 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Distribution System with FHTC for Augmentation of Sukhani Piped Water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 1229/JD | 01/06/2022 | 240 | MINTU CHAKRABORTY | 746.92 | 0 | 0 | 88
1750 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-1) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | 709/JD | 13/07/2023 | 629 | MRINMOY KANTI DUTTA | 29.51 | 0 | 0 | 55
1751 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Fitting fixing DI specials along with laying distribution for Augmentation of Sukhani Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri. | 948/JD | 08/08/2023 | 60 | MINTU CHAKRABORTY | 82.49 | 0 | 0 | 45
1752 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessary connections for Augmentation of Sukhani Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajgang Block under Jalpaiguri Division, PHE Dte. | 1270/JD | 13/09/2023 | 810 | SANJIT SAHA | 30.41 | 0 | 0 | 55
1753 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0 | 0 | 20
1754 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-III) PIPED WATER SUPPLY SCHEME. | 1519/JD | 16/10/2023 | 481 | M/S. SURYA I PVT. LTD COMPANY | 147.2 | 0 | 0 | 68
1755 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Fitting fixing DI specials along with laying distribution and Pump House (5.40m x 3.60 m) at Head work site for Augmentation of Sukhani Piped water supply scheme Zone-III at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | 2391/JD | 16/02/2024 | 20 | BANSBERIA CONSTRUCTION CO. | 96.25 | 0 | 0 | 0
1756 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying pipe line for H/W Site at Sukani zone III PWSS site piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2329/JD | 08/02/2024 | 45 | LOPCHAN ENTERPRISE | 18.11 | 0 | 0 | 0
1757 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2308/JD | 07/02/2024 | 30 | M/S A.P. DEVELOPERS | 7.76 | 0 | 0 | 0
1758 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2452/JD | 23/02/2024 | 30 | M/S SAHA ENTERPRISE | 8.31 | 0 | 0 | 0
1759 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-II) PIPED WATER SUPPLY SCHEME . | 2392/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 145.22 | 0 | 0 | 0
1760 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd tube well site ( ZONE-II) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT - JALPAIGURI | 1272/JD | 07/06/2022 | 90 | MINTU CHAKRABORTY | 17.91 | 0 | 0 | 100
1761 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1006/NMD | 28/07/2022 | 21 | M/S SAJAHAN CHOWDHURY | 2.41 | 0 | 0 | 100
1762 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1103/NMD | 07/09/2022 | 30 | BONANZA ENTERPRISE | 8.26 | 0 | 0 | 100
1763 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1104/NMD | 07/09/2022 | 967 | SANJIB SAHA | 8.26 | 0 | 0 | 100
1764 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (750 cum) at Sukhani Zone-III under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1424/JD | 15/07/2022 | 15 | M S PRANTIK ASSOCIATES | 2.22 | 0 | 0 | 100
1765 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-I zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1400/JD | 11/07/2022 | 15 | AGAC | 2.26 | 0 | 0 | 100
1766 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1106/NMD | 07/09/2022 | 30 | M/S ROYAL ENTERPRISE | 8.12 | 0 | 0 | 100
1767 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1105/NMD | 07/09/2022 | 30 | TAPAN BISWAS | 8.09 | 0 | 0 | 70
1768 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | 780/JD | 27/03/2023 | 21 | ASIT PAUL | 19.36 | 0 | 0 | 100
1769 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | 1264/JD | 13/09/2023 | 45 | A P CONSTRUCTION | 31.69 | 0 | 0 | 100
1770 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at 4th Tubewell site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | 1359/JD | 26/09/2023 | 45 | SANDIP BANIK | 17.65 | 0 | 0 | 100
1771 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2309/JD | 07/02/2024 | 30 | D. S. ENTERPRISE | 7.78 | 0 | 0 | 100
1772 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2310/JD | 07/02/2024 | 30 | JAGORAN SARKAR | 8.51 | 0 | 0 | 100
1773 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukhani (zone-III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2311/JD | 07/02/2024 | 30 | R.K. SINGHA & SONS | 8.42 | 0 | 0 | 100
1774 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Shifting AC pipes ,Coumpound clearing, Cutting trees and other ancillary works at Sukani zone -II under Sukani piped water supply scheme under Jalpaiguri water supply Division PHE Dte. | 2453/JD | 23/02/2024 | 14 | NEW KUNDU ENTERPRISE | 2.83 | 0 | 0 | 100
1775 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | HDD Boring with MS pipe and other ancillary work at post office more of rajganj and fatapukur to belakoba road of sukani pwss under jalpaiguri division PHE Dte. | 937/JD | 07/08/2024 | 60 | SANKAR DAS | 34.63 | 0 | 0 | 100
1776 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Shifting AC pipes, Coumpound clearing ,Cutting trees ,Land development ,inter connection of IEP and other ancillary works at Sukani zone -II Head work site under Sukani piped water supply scheme under Jalpaiguri Division, PHE Dte. | 2635/JD | 07/03/2024 | 15 | A P CONSTRUCTION | 6.53 | 0 | 0 | 100
1777 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Interconnection work for Iron Elimination Plant to Rising main, Construction Platform land development and other ancillary works at Sukani zone I and zone II in connection with Jal Jeevan Mission at sukani PWSS at Rajganj Block,under Jalpaiguri Division PHE,Dte. | 2633/JD | 07/03/2024 | 15 | D. S. ENTERPRISE | 12.81 | 0 | 0 | 100
1778 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Boundary Wall with drain, land development including interconnection work at Augmentation of Sukani PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 1414/JD | 20/09/2024 | 30 | D. S. ENTERPRISE | 10.17 | 0 | 0 | 100
1779 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Material Requisition To Resource Division | 2221/JD | 01/12/2024 | 0 | Resource Division | 88.05 | 0 | 0 | 0
1780 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Infrastructure Cost for SUKHANI,T/W-I,ZONE-III under MAL CCC [APPLICATION NO. 100000101510, Reference ID : 860293810] | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2 | 0 | 0 | 0
1781 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-3) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | 1263/JD | 13/09/2023 | 931 | ANUP KUMAR KUNDU | 40.53 | 0 | 0 | 0
1782 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-4) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | 1262/JD | 13/09/2023 | 705 | BILTU DAS | 40.83 | 0 | 0 | 50
1783 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-2) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | 1434/JD | 05/10/2023 | 786 | SUBRATA GOSWAMI | 29.29 | 0 | 0 | 40
1784 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 750 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKANI (ZONE I) PIPED WATER SUPPLY SCHEME IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK: RAJGANJ UNDER JALPAIGURI DIVISION, P.H.E DTE. | 2411/JD | 19/02/2024 | 548 | AMINUL HOQUE | 207.67 | 0 | 0 | 50
1785 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone- III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 08/01/JD | 15/03/2024 | 30 | PARESH CHAND GHOSH ROY | 8.32 | 0 | 0 | 100
1786 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of Different Component like Pump House, Tube Well, IEP, Boundary wall and ancillary work at Mogradangi of Sukani PWSS (Zone-I) of Raiganj Block under Jalpaiguri Division, PHE, Dte. | 2729/JD | 13/03/2024 | 748 | D. S. ENTERPRISE | 54.2 | 0 | 0 | 20
1787 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant (IEP) with Construction of Blower Room, Drain, Road including necessary connections and other ancillary work at Zone-I 4th Site of Sukani Piped Water Supply Scheme in connection with Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, PHE Dte. | 2503/JD | 09/12/2025 | 120 | D. S. ENTERPRISE | 25.17 | 0 | 0 | 0
1788 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1107/NMD | 07/09/2022 | 937 | M/S PARITOSH BHOWMICK AND CO. | 8.26 | 0 | 0 | 100
1789 | JALPAIGURI | Northern Mechanical | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. I, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1008/NMD | 28/07/2022 | 978 | B.B. CONCERNED | 2.79 | 0 | 0 | 100
1790 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-III) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | 804/JD | 29/03/2023 | 734 | JITENDRA NATH ROY | 13.79 | 0 | 0 | 100
1791 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-III) under Jalpaiguri Division, PHE Dte. | 1267/JD | 13/09/2023 | 688 | ASHIT KUMAR SINGHA | 52.24 | 0 | 0 | 100
1792 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Interconnection work between M.S. and D.I. Pipe, construction valve chamber including filling at Sukani and other ancillary works at Ambari Falakata PWSS at Rajganj Block under Jalpaiguri Division, PHE Dte. | 130/JD | 16/01/2025 | 20 | SANKAR DAS | 17.53 | 0 | 0 | 90
1793 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sukani Piped Water Supply Scheme , SM/09995 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone-III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 420/JD | 12/06/2024 | 343 | PARESH CHANDRA GHOSH ROY | 8.32 | 0 | 0 | 100
1794 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Material Requisition To Resource Division | 1112/JD | 24/08/2023 | 0 | Resource Division | 122.36 | 0 | 0 | 0
1795 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Material Requisition To Resource Division | 1506/JD | 13/10/2023 | 0 | Resource Division | 15.68 | 0 | 0 | 0
1796 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Construction of Boundary Wall at 3rd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division PHE, DTE. | 1299/JD | 05/09/2024 | 60 | M/S KARMAKAR CONSTRUCTION | 10.93 | 0 | 0 | 0
1797 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Brahmapur PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2335./JD | 12/12/2024 | 60 | SANDIP BANIK | 61.25 | 0 | 0 | 0
1798 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Construction of Boundary Wall at 2nd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 802/RWS | 20/08/2024 | 30 | TECHNO CRACY | 7.49 | 0 | 0 | 0
1799 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 0 | 100
1800 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Material Requisition To Resource Division | 2053/JD | 09/01/2024 | 0 | Resource Division | 15.68 | 0 | 0 | 0
1801 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | New Service Connection Charge for Brahmapur, T/W-III under BHOTPATTY CCC APPLICATION NO. 4003377837 Reference ID : 403192843 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.64 | 0 | 0 | 0
1802 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | New Service Connection Charge for Brahmapur, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375994 Reference ID : 403191703 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.64 | 0 | 0 | 0
1803 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BRAHAMPURI PWSS, TW no I, II and III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 267/NMD | 21/03/2023 | 895 | DAS ENTERPRISE | 32.59 | 0 | 0 | 65
1804 | JALPAIGURI | Jalpaiguri Division | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Construction of different components of Brahmapur PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 1670/JD | 24/11/2023 | 495 | NARAYAN CHANDRA SAHA | 597.49 | 0 | 0 | 50
1805 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
1806 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0 | 0
1807 | JALPAIGURI | Northern Mechanical | BRAHMAPUR PIPED WATER SUPPLY SCHEME , SM/13705 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
1808 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
1809 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Material Requisition To Resource Division | 2063/JD | 10/01/2024 | 0 | Resource Division | 43.48 | 0 | 0 | 0
1810 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- V, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341726, Reference ID : 403171912] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0 | 0
1811 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- VI, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341729, Reference ID : 403172439] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0 | 0
1812 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I, T/W-I under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003351968 Reference ID : 403174734 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0 | 0
1813 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003341662 Reference ID : 403174732 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.96 | 0 | 0 | 0
1814 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-II, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003338890 Reference ID : 403162909 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0 | 0
1815 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Supply of Fuel (Petrol) of Vehicle No. WB 49 K 9449 for the Month of August 2024. | BP-2024-25-365 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0 | 0
1816 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | New Service Connection Charge for SATKHAMAR, T/W- IV, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341723, Reference ID : 403171803] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
1817 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
1818 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of September 2024. | BP-2024-25-486 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0 | 0
1819 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of different components of Satkhamar Zone- II Piped Water Supply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | 1705/JD | 04/12/2023 | 850 | M/S A.B.G. CONSTRUCTION | 590.4 | 0 | 0 | 90
1820 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site Satkhamar - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, PHE Dte. | 1174/JD | 23/08/2024 | 587 | M/S A.B.G. CONSTRUCTION | 31.86 | 0 | 0 | 0
1821 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 737/JD | 26/07/2024 | 524 | ASIM GUPTA | 166.13 | 0 | 0 | 100
1822 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 738/JD | 26/07/2024 | 615 | ANUP KUNDU CONSTRUCTION CO | 142.74 | 0 | 0 | 95
1823 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
1824 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of Iron Elemination Plant (IEP) including interconnection work and washout line at H/W site in Zone-II Satkhamar PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 46/JD | 09/01/2025 | 240 | M/S M.B. DESIGN | 43.97 | 0 | 0 | 80
1825 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - II of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 490/RWS | 29/05/2025 | 30 | CHANDAN GHOSH | 5.77 | 0 | 0 | 0
1826 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - I of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 491/RWS | 29/05/2025 | 308 | SUKES BASU MAJUMDAR | 6.1 | 0 | 0 | 100
1827 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Laying Additional Distribution line with providing and installation of Sluice Valve and Specials at Zone-I of Satkhamar Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | 2108/JD | 15/10/2025 | 168 | SUKES BASU MAJUMDAR | 32.96 | 0 | 0 | 100
1828 | JALPAIGURI | Northern Mechanical | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SATKHAMAR PWSS, ZONE - I (TW NO I, II, III) AND ZONE - II (TW NO I, II, III) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1552/NMD | 04/09/2023 | 605 | M/S BHOWMICK & CO. | 64.9 | 0 | 0 | 100
1829 | JALPAIGURI | Jalpaiguri Division | Satkhamar Piped Water Supply Scheme. , SM/18760 | New | Construction of different components of Sathkhamar Zone- I Piped Water Suply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | 1671/JD | 24/11/2023 | 523 | SUKES BASU MAJUMDAR | 735.05 | 0 | 0 | 10
1830 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Construction of different components of Singimari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 1349/JD | 26/09/2023 | 548 | M/S R.N. TRADERS | 724.62 | 0 | 0 | 15
1831 | JALPAIGURI | Northern Mechanical | Singimari Piped Water Supply Scheme. , SM/18761 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIMARI PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1751/NMD | 31/10/2023 | 579 | M/S PARITOSH BHOWMICK AND CO. | 32.98 | 0 | 0 | 50
1832 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, Land Development etc. at 2nd TW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 1152/RWS | 03/12/2024 | 30 | PRABIR SHOME | 9.14 | 0 | 0 | 0
1833 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain etc. at HW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 1297/JD | 05/09/2024 | 60 | KAMAL DAS | 20.16 | 0 | 0 | 0
1834 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Material Requisition To Resource Division | 2042/JD | 09/01/2024 | 0 | Resource Division | 17.33 | 0 | 0 | 0
1835 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Material Requisition To Resource Division | 56/JD | 09/04/2024 | 0 | Resource Division | 21.92 | 0 | 0 | 0
1836 | JALPAIGURI | Northern Mechanical | Singimari Piped Water Supply Scheme. , SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376114 Reference ID : 403191660 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.73 | 0 | 0 | 0
1837 | JALPAIGURI | Northern Mechanical | Singimari Piped Water Supply Scheme. , SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003376577 Reference ID : 403191663 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0 | 0
1838 | JALPAIGURI | Northern Mechanical | Singimari Piped Water Supply Scheme. , SM/18761 | New | New Service Connection Charge for SINGIMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003379454 Reference ID : 403196948 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.38 | 0 | 0 | 0
1839 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Balance Laying Distribution System including providing Functional Household Tap Connection in connection with JJM under Singimari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 127/JD | 16/01/2025 | 60 | SWAPAN SAHA | 34.8 | 0 | 0 | 0
1840 | JALPAIGURI | Jalpaiguri Division | Singimari Piped Water Supply Scheme. , SM/18761 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 985/JD | 14/08/2024 | 15 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
1841 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHIKARPUR BHANDARPUR PWSS at TW NO I,II,III (ZONE-I,II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1404/NMD | 21/08/2024 | 30 | ALPHA ENTERPRISE | 68.61 | 0 | 0 | 0
1842 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Rajganj block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1292/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
1843 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Motherboard and Power Supply Unit for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1844 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Toner for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1845 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Motherboard, RAM and Printer Relay Unit for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1846 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453990 Reference ID : 403250073 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.38 | 0 | 0 | 0
1847 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of RAM, Logic Board, Pickup Roller and Teflon for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1848 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Printer Logic Board and Pickup Roller for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1849 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-I, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453987 Reference ID : 403250072 | BP/24-25/204 | 12/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0 | 0
1850 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Motherboard, RAM, Pickup Roller and Toner for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1851 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Printer Power Supply, Teflon for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1852 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Printer Teflon, Toner for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1853 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of SSD, Hard Disk and Printer Power Supply Board for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1854 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-II, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430829 Reference ID : 403234010 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.73 | 0 | 0 | 0
1855 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Brother 263 Toner, 88A Toner, 110A Toner, Keyboard and Mouse for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1856 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Motherboard, Toner and Printer Fuser Unit for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1857 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Brother Toner and SMPS for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1858 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430831 Reference ID : 403234013 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.26 | 0 | 0 | 0
1859 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Toner and Mouse for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.08 | 0 | 0 | 0
1860 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of 88A Compatible Toner for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.07 | 0 | 0 | 0
1861 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Motherboard, SSD & Keyboard and Mouse for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1862 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Logic Board, Power Supply and Teflon for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1863 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003430808 Reference ID : 403234012 | BP/24-25/204 | 12/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.58 | 0 | 0 | 0
1864 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Magnetic Relay, Logic Board and Pickup Roller for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1865 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of SSD, Motherboard, Processor, SMPS and Mouse for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1866 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Toner, SSD and Ink for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1867 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Processor, RAM, SMPS and SSD for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.06 | 0 | 0 | 0
1868 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. II, under BELAKOBA CCC APPLICATION NO. 4003430834 Reference ID : 403234011 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
1869 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Logic Board, Magnetic Relay and Teflon for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1870 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Supply of Toner and Desktop RAM for Office use. | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0 | 0
1871 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
1872 | JALPAIGURI | Northern Mechanical | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Installation of two tank chlorination system at SHIKARPUR and other adjacent water supply scheme UNDER JJM under RAJGANJ Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 80/SMSD | 07/02/2025 | 15 | CHOWDHURY AND BASU ENTERPRISE | 1.57 | 0 | 0 | 0
1873 | JALPAIGURI | Jalpaiguri Division | Sikarpur Piped Water Supply Scheme. , SM/18836 | New | Construction of different components of Shikarpur Bhandarpur Zone - I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. | 2623/JD | 07/03/2024 | 908 | ASHIT KUMAR SINGHA | 682.9 | 0 | 0 | 85
1874 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Material Requisition To Resource Division | 1884/JD | 20/12/2023 | 0 | Resource Division | 14.51 | 0 | 0 | 0
1875 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0 | 0 | 20
1876 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
1877 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 0 | 90
1878 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Material Requisition To Resource Division | 2016/JD | 19/11/2024 | 0 | Resource Division | 156.48 | 0 | 0 | 0
1879 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of October 2024. | BP-2024-25-525 | 29/11/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0 | 0
1880 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003351981, Reference ID : 403172665] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.85 | 0 | 0 | 0
1881 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341742, Reference ID : 403172228] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0 | 0
1882 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Construction of different components of Barapatina Nutanbus Zone-II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | 408/A/JD | 07/06/2023 | 705 | UNIBRO INFRASERV PRIVATE LIMITED | 434.44 | 0 | 0 | 70
1883 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 736/JD | 26/07/2024 | 524 | MOTI INDUSTRIES | 128.89 | 0 | 0 | 85
1884 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at BARAPATINA NATUNBUS PWSS for T/W No. I and II, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 582/NMD | 07/02/2025 | 30 | SARKAR ELECTRIC | 23.55 | 0 | 0 | 0
1885 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
1886 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
1887 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Barapatina Nutanbus Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 895/JD | 08/05/2025 | 40 | PRADIP KUMAR SHIL | 18.52 | 0 | 0 | 0
1888 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 484/RWS | 29/05/2025 | 307 | JAYA SARKAR | 8.04 | 0 | 0 | 0
1889 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
1890 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | 820/JD | 30/04/2025 | 61 | SUKES BASU MAJUMDAR | 0.8 | 0 | 0 | 0
1891 | JALPAIGURI | Jalpaiguri Division | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | 1499/JD | 30/06/2025 | 31 | SUKES BASU MAJUMDAR | 0.4 | 0 | 0 | 0
1892 | JALPAIGURI | Northern Mechanical | BARAPATINA NUTANBUS ZONE-II PIPED WATER SUPPLY SCHEME , SM/16041 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
1893 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/19175 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHENGMARI TG AREA PWSS, TW no 1 to 9 in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1817/NMD | 01/11/2023 | 30 | CONCORD ENGINEERING | 103.77 | 0 | 0 | 0
1894 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/19175 | Augmentation | Construction of Intake Well for Sub-Surface Water Source at River Bed of Diana under Nagrakata Block of Jalpaiguri District i.c.w Chengmari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2495/JD | 28/02/2024 | 21 | GOUTAM DAS | 37.37 | 0 | 0 | 100
1895 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF CHENGMARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/19175 | Augmentation | Surveying, Planning, Designing, Construction, Supply and installation and commissioning of surface (River) based water treatment unit to yield 1430 KLD drinking water (Phase-I) on EPC- Turnkey basis for Augmentation of Chengmari Tea Garden Pipe Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1590/JD | 23/10/2024 | 504 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 936.29 | 0 | 0 | 0
1896 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | Material Requisition To Resource Division | 1063/JD | 24/08/2023 | 0 | Resource Division | 8.3 | 0 | 0 | 0
1897 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | Material Requisition To Resource Division | 2067/JD | 10/01/2024 | 0 | Resource Division | 6.28 | 0 | 0 | 0
1898 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | " New Service Connection Charge for (REJU) SATHKAYA TG TW NO-III, METELI CCC " APPLICATION NO.4003401332 Reference ID : 403212025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1899 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | "INFRA COST IRO NSC for (REJU) SATHKAYA TG TW NO-IV, METELI CCC " APPLICATION NO.100000107273 Reference ID : 860298683 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.43 | 0 | 0 | 0
1900 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | "INFRA COST IRO NSC for (REJU) SATHKAYA TG TW NO-III, METELI CCC " APPLICATION NO.100000107270 Reference ID : 860298680 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.07 | 0 | 0 | 0
1901 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | " New Service Connection Charge for (REJU) SATHKAYA TG TW NO-IV, METELI CCC " APPLICATION NO.4003401337 Reference ID : 403212023 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1902 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 0 | 0 | 14
1903 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SATHKAYA TEA GARDEN AREA PWSS, TW NO III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1434/NMD | 10/08/2023 | 30 | SUBODH KUMAR BANIK | 24.25 | 0 | 0 | 95
1904 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sathkaya Tea Garden Area Piped Water Supply Scheme , SM/18713 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0 | 0
1905 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Construction of different components of Nowapara PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN , FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Divison , P.H.E Dte. | 1775/JD | 08/12/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 686.37 | 0 | 0 | 0
1906 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Material Requisition To Resource Division | 1106/JD | 24/08/2023 | 0 | Resource Division | 28.96 | 0 | 0 | 0
1907 | JALPAIGURI | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NOWAPARA PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1472/NMD | 17/08/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 32.15 | 0 | 0 | 0
1908 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Material Requisition To Resource Division | 2033/JD | 09/01/2024 | 0 | Resource Division | 22.38 | 0 | 0 | 0
1909 | JALPAIGURI | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | New Service Connection Charge for NAWAPARA, TW NO-I, NJP GB CCC APPLICATION NO. 4003354727 Reference ID : 403174711 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
1910 | JALPAIGURI | Northern Mechanical | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
1911 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.06.2024 to 30.11.2024)". | 347/JD | 31/05/2024 | 183 | RUPA PRASAD | 0.88 | 0 | 0 | 100
1912 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | 822/JD | 30/04/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 0 | 0
1913 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | 821/JD | 30/04/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0 | 0
1914 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | 1501/JD | 30/06/2025 | 31 | AJIJUL HAQUE | 0.4 | 0 | 0 | 0
1915 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Nowapara Piped Water Supply Scheme Block - Rajganj under Jalpaiguri Division, PHE Dte. | 893/JD | 08/05/2025 | 328 | SAHA CONSTRUCTION | 75.34 | 0 | 0 | 0
1916 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | 1500/JD | 30/06/2025 | 31 | MD AMIRUL ISLAM | 0.4 | 0 | 0 | 0
1917 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | 1731/JD | 31/07/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0 | 0
1918 | JALPAIGURI | Jalpaiguri Division | NOWAPARA PIPED WATER SUPPLY SCHEME , SM/18503 | New | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 0 | 100
1919 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Dwarikamari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | 476/RWS | 15/10/2020 | 30 | GOUTAM DAS | 4.84 | 0 | 0 | 0
1920 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | Providing FHTC under Dwarikamari WSS | 1053 | 11/01/2021 | 0 | BARUN KUMAR DUTTA | 4.43 | 0 | 0 | 0
1921 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | PROVIDING FHTC AT DWARIKAMARI PWSS | 1189 | 02/02/2021 | 0 | GOUTAM DAS | 4.83 | 0 | 0 | 0
1922 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | PREPARATION OF DPR FOR SOUTH BERUBARI PWSS | 440/21-22 | 04/10/2021 | 0 | SUBHANKAR GHOSH | 2.32 | 0 | 0 | 0
1923 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) | 1497/JD | 22/12/2020 | 30 | GOUTAM DAS | 21.72 | 19.54 | 90.47 | 1
1924 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | Laying Distribution System Mogalkata Tea Garden Area Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-K) | 1655/JD | 08/10/2021 | 15 | PRABIR SHOME | 9.87 | 0 | 0 | 0
1925 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Dwarikamari Piped Water Supply Scheme , SM/06841 | Retrofitting | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 0 | 0 | 100
1926 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Madabdanga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | 471/RWS | 15/10/2020 | 30 | ALICK DUTTA | 4.72 | 4.74 | 100 | 1
1927 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madabdanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) | 48/JD | 07/01/2021 | 60 | M/S SIBU DEY AND CO. | 39.4 | 0 | 0 | 0
1928 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madab danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) | 1537/JD | 31/12/2020 | 60 | ANUP SARKAR | 32.76 | 29.66 | 90.54 | 1
1929 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | PROVIDING FHTC AT MADHABDANGA PWSS | 1054 | 11/01/2021 | 0 | BHOWMIK ENTERPRISES | 4.41 | 0 | 0 | 0
1930 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | PROVIDING FHTC FOR JURANTI T.G PWSS |  | 04/10/2021 | 0 | NARAYAN CH SAHA & SONS | 18.42 | 0 | 0 | 0
1931 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | FHTC MADHAB DANFGA | BP-2021-22-234 | 23/02/2022 | 0 | ANUP SARKAR | 3.99 | 0 | 0 | 0
1932 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | CONST SULICE VALVE CHEMBER FOR DAKSHIN SHALBARI PWSS | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
1933 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | RETROFITTING WORK MADHAB DANGA PWSS | BP-2021-22-405 | 23/03/2022 | 0 | ANUP SARKAR | 2.25 | 0 | 0 | 0
1934 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | CONST. SLUICE VALVE DAKSHIN SALBARI | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
1935 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | FHTC MADHYA KHUTTIMARI | BP-2021-22-369 | 16/03/2022 | 0 | ALOKE DEY | 16.81 | 0 | 0 | 0
1936 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | Construction of store below OHR , plinth protection and construction of valve chamber etc. including through reparing of pipe line with cleaning to provide water facility near Jalpesh more under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte | 870/RWS | 08/12/2021 | 15 | M/S SURAJIT DEY AND CO. | 4.85 | 0 | 0 | 0
1937 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme , SM/06938 | Retrofitting | Retrofitting works in connection with FHTC at Kadamtala, Indira More and Baman para under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte | 849/RWS | 03/12/2021 | 10 | ANUP SARKAR | 2.25 | 0 | 0 | 0
1938 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06953 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Hope T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. | 30/JD | 05/01/2021 | 75 | UMWELT ENGINEER PRIVATE LIMITED | 43.55 | 0 | 0 | 0
1939 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06953 | Retrofitting | FHTC FOR BHANGARHAT PWSS | 376/21-22 | 20/09/2021 | 0 | MRINMOY KANTI DUTTA | 23.75 | 0 | 0 | 0
1940 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06953 | Retrofitting | fuel bill | BP-2023-24-30 | 12/04/2023 | 0 | FILL & SMILE | 1.9 | 0 | 0 | 0
1941 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block , SM/06953 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangarhat piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 1076/JD | 02/07/2021 | 30 | DIPANKAR DUTTA | 24.38 | 23.18 | 100 | 0
1942 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of PORAPARA W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 270/NMD | 22/04/2022 | 21 | SUBHRANGSHU GUHARAJA | 2.77 | 0 | 0 | 0
1943 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 473/JD | 22/02/2022 | 60 | SOMNATH ROY | 11.28 | 0 | 0 | 1
1944 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | New Service Connection Charge for TW-III of Porapara (Reju) under UKILPARA MASKALAIBARI CCC, APPLICATION NO. 4002893861, Reference ID : 402797316 | BP/2022-23/18 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.96 | 0 | 0 | 0
1945 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Installation of Infrastructure IRO NSC Application 4002893861 at PORAPARA for T/W No. III W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050876, Reference ID : 860240746] | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.85 | 0 | 0 | 0
1946 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF PORAPARA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 353/NMD | 23/05/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.18 | 0 | 0 | 90
1947 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Construction of Guard Shed including supply and installation of 300 dia Sluice valve and chamber and the other allied works under Porapara Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 555/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.81 | 0 | 0 | 0
1948 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Laying new pipe line from Canal near OHR to Taltala near Haldibari Road to facilitate Functional Household Tap Connection in connection with JJM under Porapara Piped Water Supply Scheme under Jalpaiguri | 682/JD | 16/03/2023 | 30 | B.M CONSTRUCTION | 14.92 | 0 | 0 | 0
1949 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall gate, drain and pathway for 4th Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 913/JD | 07/04/2022 | 60 | JAYDEB SAHA | 11.2 | 0 | 0 | 100
1950 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Rectrofting and reparing of pipe line, IEP and other allied works at Fakir Para, Bairagi danga, Brahatal Para due to widening and new construction of road by P.W.D. under Porapara Water Supply Scheme Jalpaiguri Division PHE Dte | 561/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.82 | 0 | 0 | 1
1951 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Construction of Rig approach with partial land development for 3rd tube well site under Porapara piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. | 564/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 4.32 | 0 | 0 | 1
1952 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Pora Para water supply scheme under Jalpaiguri Division PHE Dte. | 1932/JD | 29/09/2022 | 45 | SUKES BASU MAJUMDAR | 16.22 | 0 | 0 | 0
1953 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Sinking of Tubewell at 4th Tube Well site for Rejuvenation of Porapara PWSS in connection with JJM at block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. | 1517/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 9.79 | 0 | 0 | 100
1954 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Construction of C.C. pathway repairing drain and boundary wall etc. at Head work site campus of Porapara W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | 559/RWS | 01/09/2022 | 30 | SOMNATH ROY | 2.22 | 0 | 0 | 1
1955 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Infrastructure Cost for PORAPARA , T/W IV, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000079172, Reference ID : 860270382] | BP/23-24/44 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.66 | 0 | 0 | 0
1956 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | New Service Connection Charge for PORAPARA, T/W V under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003205927, Reference ID : 403055575] | BP/23-24/83 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.6 | 0 | 0 | 0
1957 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | New Service Connection Charge for PORAPARA , T/W IV, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003163097, Reference ID : 403023007] | BP/23-24/44 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
1958 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tube well (BDTW) by the Reverse Rotary Circulation method of drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | 67/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.77 | 0 | 0 | 100
1959 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Sinking of Shallow Tubewell for the Contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | 65/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.07 | 0 | 0 | 100
1960 | JALPAIGURI | Northern Mechanical | Rejuvenation of Porapara piped water supply scheme. , SM/09463 | Augmentation | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | 66/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.95 | 0 | 0 | 100
1961 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Retrofitting works in connection with FHTC of Natun para , Borobari and Malar Math under Uttar Bhuskadanga W/S/S under Jalpaiguri Division , P.H.E Dte | 743/RWS | 08/10/2021 | 15 | BALARAM GHOSH | 2.86 | 0 | 0 | 0
1962 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | UTTAR BHUSKA DANGA | BP-2021-22-114 | 03/12/2021 | 0 | BALARAM GHOSH | 4.8 | 0 | 0 | 0
1963 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-K) | 643/RWS | 21/10/2022 | 20 | J.M. CONSTRUCTION | 3.73 | 0 | 0 | 0
1964 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Construction of cement concrete drain , pathway , store below OHR and culvert etc. at H/W site campus of Dakshin Salbari W/S/S under Jalpaiguri Division , P.H.E Dte. | 679/RWS | 27/09/2021 | 30 | R.S CONSTRUCTION | 4.85 | 0 | 0 | 1
1965 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Retrofitting works in connection with FHTC works for the habitation of Monosha Mandir para & Bura Amtolar Gali under Bhuskadanga W/S/S under Jalpaiguri Division P.H.E. Dte. | 307/RWS | 28/04/2022 | 15 | BALARAM GHOSH | 0.77 | 0 | 0 | 0
1966 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone- III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-J) | 642/RWS | 21/10/2022 | 20 | SOMNATH ROY | 4.82 | 0 | 0 | 0
1967 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/02/2023 to 31/05/2023. | 72/RWS | 31/01/2023 | 120 | APIKUL ALI | 0.59 | 0 | 0 | 100
1968 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF UTTAR BHUSKADANGA & GARTALI JALPESH PIPED WATER SUPPLY SCHEME, under Jalpaiguri Division P.H.E. Dte. | 976/JD | 20/04/2022 | 120 | UNIBRO INFRASERV PRIVATE LIMITED | 57.66 | 0 | 0 | 100
1969 | JALPAIGURI | Jalpaiguri Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITH RETROFITTING OF UTTAR BHUSKADANGA AND GARTALI JALPESH PIPED WATER SUPPLY SCHEME UNDER JAL SWAPNA UNDER JALPAIGURI DIVISION, PHE DTE. , SM/09099 | Retrofitting | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF UTTAR BHUSKADANGA PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI | 254/JD | 31/01/2022 | 1246 | MRINMOY KANTI DUTTA | 79.88 | 0 | 0 | 90
1970 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Mohit Nagar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Part-G) | 537/JD | 25/02/2022 | 30 | M/S DEY & ROY CHOUDHURY | 21.77 | 0 | 0 | 0
1971 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2194/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.56 | 0 | 0 | 0
1972 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2190/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.32 | 0 | 0 | 0
1973 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 352/NMD | 23/05/2022 | 30 | ALPHA ENTERPRISE | 9.18 | 0 | 0 | 0
1974 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 268/NMD | 22/04/2022 | 21 | S.P. ENTERPRISE | 2.77 | 0 | 0 | 0
1975 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 269/NMD | 22/04/2022 | 21 | SARKAR ELECTRIC | 2.77 | 0 | 0 | 0
1976 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Restoration of pipe line at different places including construction of sluice valve chamber with supply of sluice valv etc.at head work site campus under Mohitnagar W/S/S under Jalpaiguri Division , P.H.E. Dte | 306/RWS | 28/04/2022 | 15 | M/S DEY & ROY CHOUDHURY | 4.83 | 0 | 0 | 1
1977 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 39/JD | 04/12/2021 | 60 | NARESH SEN | 11.12 | 0 | 0 | 1
1978 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | DEV LAND & REPAIRING SANITARY & PLUMBING ARRANGEMENT | BP-2021-22-506 | 30/03/2022 | 0 | SANDIP BANIK | 4.55 | 0 | 0 | 0
1979 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Installation of Infrastructure IRO NSC Application 4002923185 at T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0 | 0
1980 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Installtion of Infrastructure IRO NSC application 4002923192 at T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.09 | 0 | 0 | 0
1981 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | FHTC SAMSING | BP-2021-22-235 | 16/02/2022 | 0 | SUJAN LAMA | 4.79 | 0 | 0 | 0
1982 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | New Service Connection Charge for T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002923185, Reference ID : 402817973] | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0 | 0
1983 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | New Service Connection Charge for T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO.4002923192, Reference ID : 402817972] | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0 | 0
1984 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | LDS FHTC LIKSAN BAZAR (ZONE - III) | BP-2021-22515 | 30/03/2022 | 0 | ALICK DUTTA | 13.19 | 0 | 0 | 0
1985 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) | 601/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.84 | 0 | 0 | 100
1986 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-H) | 599/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.51 | 0 | 0 | 100
1987 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Providing Guard wall including additional part of Boundary wall at 3rd Tubewell Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 743/JD | 23/03/2023 | 15 | SAUMENDU DUTTA | 1.76 | 0 | 0 | 0
1988 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0 | 0 | 100
1989 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 351/NMD | 23/05/2022 | 30 | M/S SAJAHAN CHOWDHURY | 9.19 | 0 | 0 | 0
1990 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Renovation of Boundary wall including Approach Road, Earth filling, Valve Chambers at Head Work Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1813/JD | 14/09/2022 | 21 | M/S DEY & ROY CHOUDHURY | 8.1 | 0 | 0 | 1
1991 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0 | 0 | 1
1992 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Retrofitting at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. | 602/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.33 | 0 | 0 | 100
1993 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Rising Main Connections (at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Mohit Nagar Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. | 165/RWS | 28/02/2023 | 21 | SOUVIK SAHA | 3.28 | 0 | 0 | 100
1994 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0 | 0 | 1
1995 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Material Requisition To Resource Division | 1117/JD | 24/08/2023 | 0 | Resource Division | 3.55 | 0 | 0 | 0
1996 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 25.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Mohitnagar water supply scheme under Jalpaiguri Division PHE Dte. | 132/JD | 17/01/2023 | 45 | R.S CONSTRUCTION | 30.33 | 0 | 0 | 100
1997 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Retrofitting at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. | 598/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 4.79 | 0 | 0 | 100
1998 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-III, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | 283/DSD | 03/01/2022 | 7 | SUMON ELECTRICAL | 0.95 | 0 | 0 | 100
1999 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Carrying out Surging, Development and Y.T. works for a Rig Bored Big Dia Tube well (BDTW) by reverse rotary method of drilling for Rejuvenation of Porapara PWSS TW-III, Rejuvenation of Mahitnagar PWSS TW-III & IV, Rejuvenation of Arji Maria Kamala Pukhari PWSS TW-III & IV, Block - Jalpaiguri, Dist.- Jalpaiguri under different water supply scheme under Northern Mechanical Division, P.H.E. Dte. | 311/DSD | 21/01/2022 | 21 | UTTAM PAUL | 0.73 | 0 | 0 | 100
2000 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mohitnagar piped water supply scheme. , SM/09519 | Augmentation | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. | 330/DSD | 08/02/2022 | 7 | S.P. ENTERPRISE | 0.95 | 0 | 0 | 100
2001 | JALPAIGURI | Jalpaiguri Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER JALPAIGURI DISTRICT , SM/10775 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 9 (nine) villages under different blocks having less than 100 households under Jalpaiguri district in connection with Jal Swapna | 1226/JD | 01/06/2022 | 30 | M/S NANDY ENTERPRISE | 355.27 | 0 | 0 | 0
2002 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation of Jurantee Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 05/JSSD | 16/05/2022 | 45 | RAJAT GHOSH | 4.65 | 0 | 0 | 0
2003 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Sinking of Two Nos. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Jurantee Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 737/JD | 17/03/2022 | 30 | ASHIS DUTTA | 13.5 | 0 | 0 | 100
2004 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Laying Distribution System of Rejuvenation of Jurantee Tea Garden Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 2456/JD | 22/12/2022 | 30 | SANDIP BANIK | 71.54 | 0 | 0 | 100
2005 | JALPAIGURI | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084451, Reference ID : 860276312] | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0 | 0
2006 | JALPAIGURI | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000085207, Reference ID : 860276427] | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.19 | 0 | 0 | 0
2007 | JALPAIGURI | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197409, Reference ID : 403049081] | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2008 | JALPAIGURI | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197405, Reference ID : 403049083] | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2009 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Construction of boundary wall with gate,drain and pathway for 3rd tube-well site of Rejuvenation of Jurantee tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 62/JSSD | 19/07/2022 | 20 | ARINDAM CHATTERJEE | 3.88 | 0 | 0 | 100
2010 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Juranteeee TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 252/JD | 10/05/2023 | 45 | SARKAR CONSTRUCTION | 4.64 | 0 | 0 | 100
2011 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Jurantee Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2628/JD | 07/03/2024 | 45 | ASIT PAUL | 5.61 | 0 | 0 | 100
2012 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
2013 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) at Juranti TG PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | 115/JSSD | 03/06/2025 | 30 | ASIT PAUL | 9.61 | 0 | 0 | 100
2014 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Rejuvenation of Juranti Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 348/JD | 24/05/2023 | 678 | ASIT PAUL | 73.94 | 0 | 0 | 38
2015 | JALPAIGURI | Northern Mechanical | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JURANTI PWSS, TW no III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1373/NMD | 09/08/2023 | 540 | S.S. ENTERPRISES | 27.5 | 0 | 0 | 100
2016 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme , SM/10069 | Augmentation | Restoration work of damaged road due to laying of pipeline and other allied works under Rejuvenation of Juranti Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 298/JSSD | 27/09/2023 | 338 | SANDIP BANIK | 9.64 | 0 | 0 | 100
2017 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Hila Tea Garden Area Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 562/NMD | 14/07/2022 | 21 | ALPHA ENTERPRISE | 2.99 | 0 | 0 | 0
2018 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | FHTC HILLA T.G PWSS | BP-2021-22-473 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 19.05 | 0 | 0 | 0
2019 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-I] | BP/22-23/59 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0 | 0
2020 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | SUPPLY INSTALATION COMMISSIONING AND TRIAL OPERATION OF HILA T.G PWSS | BP-2021-22-483 | 29/03/2022 | 0 | S P ENTERPRISE | 8.09 | 0 | 0 | 0
2021 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  | 16/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0 | 0
2022 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | EARTH FILLING WORK H/W DAKSHIN SALBARI WSS | BP-2021-22-534 | 31/03/2022 | 0 | R.S CONSTRUCTION | 4.66 | 0 | 0 | 0
2023 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | RECONNECTION OF PIPE LINE RETROFITTING HILLA T.G WSS | BP-2021-22-474 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 17.01 | 0 | 0 | 0
2024 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 100000058117, Reference ID : 860247827] | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
2025 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  | 26/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0 | 0
2026 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-II] | BP/22-23/58 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.71 | 0 | 0 | 0
2027 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 4002969966, Reference ID :402856020] | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2028 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 4002969959 ; Reference ID :402856023] | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2029 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 75/NMD | 27/01/2023 | 30 | GURUKRIPA ENTERPRISE | 11.38 | 0 | 0 | 0
2030 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Construction of Boundary wall at 3rd Tube well site for Hila T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. | 552/JSSD | 29/01/2021 | 30 | SAHA CONSTRUCTION | 4.55 | 0 | 0 | 1
2031 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hila Tea Garden under Jalpaiguri Division, P.H.E. Dte. | 561/JD | 01/03/2022 | 30 | ASHIS DUTTA | 13.22 | 0 | 0 | 1
2032 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Construction of Pump House (3.60 m X 2.40m size with sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Water Supply Scheme for HILA Tea Garden under Jalpaiguri Division,P.H.E Dte. | 1105/W/JSSD | 27/01/2022 | 45 | TECHNOCRACY ELECTRICAL CONTRACTOR & GENERAL ORDER SUPPLIER | 4.64 | 0 | 0 | 1
2033 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 4th tube-well site of Rejuvenation of Piped Water Supply Scheme for HILA under Jalpaiguri Division,P.H.E. Dte. | 1364/JSSD | 19/04/2022 | 20 | GOPAL DEY | 3.89 | 0 | 0 | 100
2034 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 5th tube well site for Hila TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 215/JSSD | 16/09/2022 | 60 | U TURN CONSTRUCTION | 4.65 | 0 | 0 | 100
2035 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Retrofitting works for Laying Distribution System of Rejuvenation of water supply scheme for Hilla Tea Garden Mouza under Jalpaiguri Division, P.H.E. Dte | 733/JD | 22/03/2023 | 30 | PROFULLA GHOSH | 32.91 | 0 | 0 | 100
2036 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Construction of peripherial drain with Land development and RBT at 4th tubewell site of Hila Tea Garden in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 254/JD | 10/05/2023 | 14 | GOPAL DEY | 1.19 | 0 | 0 | 100
2037 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Retrofitting works of 3rd Pump House site at Hila Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 503/JSSD | 02/01/2024 | 30 | SCEC BOENTER AND KDAS JOINT VENTURE | 6.04 | 0 | 0 | 0
2038 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 6th tube well site of Rejuvenation of Hila Tea Garden Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 1389/JD | 18/09/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0 | 0
2039 | JALPAIGURI | Northern Mechanical | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 76/NMD | 27/01/2023 | 30 | HARA PROSAD DAS | 12.38 | 0 | 0 | 70
2040 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Hila Tea Garden area piped water supply scheme , SM/10070 | Augmentation | Providing Functional Household Tap Connection 261Nos. in Connection with Jal Jeevan Mission Hila Tea Garden Piped Water Supply Scheme Under Jalpaiguri Division, P.H.E.Dte. | 564/JSSD | 05/03/2024 | 30 | SAHA CONSTRUCTION | 9.52 | 0 | 0 | 100
2041 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2225/JD | 27/12/2021 | 60 | ARATI CONSTRUCTION | 11.44 | 0 | 0 | 1
2042 | JALPAIGURI | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCHEME (TW-II), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 473/CDD | 25/05/2022 | 30 | PADMA ENGINEERING & CO. | 10.64 | 0 | 0 | 0
2043 | JALPAIGURI | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG M/C & ACCESSORIES INCLUDING LOADING & UNLOADING FROM MADHYA KHAGRABARI TW-II SITE TO UTTARTAJPUR W/S SCH, UNDER CDD, PHE DTE. | 186/CMSD-I | 10/06/2022 | 7 | PADMA ENGINEERING & CO. | 0.8 | 0 | 0 | 0
2044 | JALPAIGURI | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOT CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCH (TW-I), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 472/CDD | 25/05/2022 | 30 | PADMA ENGINEERING & CO. | 10.64 | 0 | 0 | 0
2045 | JALPAIGURI | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0 | 0 | 0
2046 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941289, Reference ID : 402831971] | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2047 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941293, Reference ID : 402831977] | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2048 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Providing car on daily hire basis @12.00/Km for official use of the office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte | BP-2022-23-155 | 02/09/2022 | 0 | RAKESH SARKAR | 0.19 | 0 | 0 | 0
2049 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059497, Reference ID : 860245057] | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
2050 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | LDS REJ NAGRAKATA | BP-2021-22-517 | 30/03/2022 | 0 | UDAYAN BOSE | 6.91 | 0 | 0 | 0
2051 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059498, Reference ID : 860245058] | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.04 | 0 | 0 | 0
2052 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 223/JD | 24/01/2022 | 60 | SOMNATH ROY | 11.44 | 0 | 0 | 0
2053 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 856/NMD | 18/07/2022 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 7.87 | 0 | 0 | 80
2054 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri Division PHE Dte. | 680/JD | 16/03/2023 | 45 | M/S RATAN KUMAR DAS GUPTA AND CO | 16.43 | 0 | 0 | 80
2055 | JALPAIGURI | Central Drilling | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | 1350/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.38 | 0 | 0 | 0
2056 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MADHYA KHAGRABARI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 186/JD | 21/01/2022 | 120 | M/S A.B.G. CONSTRUCTION | 108.63 | 0 | 0 | 1
2057 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PH.E Dte Jalpaiguri (with valid Taxi permit). Period from 01/10/2022 to 31/01/2023 | 616/RWS | 29/09/2022 | 122 | APIKUL ALI | 0.59 | 0 | 0 | 1
2058 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Work of DI Pipe (Raising main), Drain, Chamber, flower block & other ancillary works at 4th site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | 816/RWS | 14/07/2023 | 14 | ARATI CONSTRUCTION | 2.65 | 0 | 0 | 100
2059 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Construction of pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2224/JD | 23/12/2021 | 60 | SOMNATH ROY | 11.44 | 0 | 0 | 100
2060 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Material Requisition To Resource Division | 179/JD | 21/01/2022 | 0 | Resource Division | 127.45 | 0 | 0 | 0
2061 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Material Requisition To Resource Division | 551/JD | 01/03/2022 | 0 | Resource Division | 27.35 | 0 | 0 | 0
2062 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | SUPPLY OF FUEL | BP-2022-23-545 | 25/03/2023 | 0 | FILL & SMILE | 0.3 | 0 | 0 | 0
2063 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | SUPPLY OF FUEL | BP-2022-23-544 | 25/03/2023 | 0 | FILL & SMILE | 0.25 | 0 | 0 | 0
2064 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 564/NMD | 14/07/2022 | 21 | SUBODH KUMAR BANIK | 2.19 | 0 | 0 | 100
2065 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri | 135/JD | 17/01/2023 | 45 | M/S SURAJIT DEY AND CO. | 16.44 | 0 | 0 | 100
2066 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | 817/RWS | 14/07/2023 | 14 | SOMNATH ROY | 2.65 | 0 | 0 | 100
2067 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | ADDITIONAL WORK FOR LAYING & DISTRIBUTION SYSTEM IN MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI. | 1895/JD | 20/12/2023 | 15 | JAYA SARKAR | 9 | 0 | 0 | 100
2068 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Material Requisition To Resource Division | 2214/JD | 01/12/2024 | 0 | Resource Division | 22.14 | 0 | 0 | 0
2069 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-C`). | 213/JD | 24/01/2022 | 1142 | NARAYAN CHANDRA SAHA | 169.95 | 0 | 0 | 75
2070 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-B). | 189/JD | 21/01/2022 | 1530 | M/S A.B.G. CONSTRUCTION | 181.29 | 0 | 0 | 100
2071 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-A). | 194/JD | 21/01/2022 | 1166 | M/S A.B.G. CONSTRUCTION | 173.57 | 0 | 0 | 100
2072 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 855/NMD | 18/07/2022 | 867 | GOENKA ENTERPRISE | 7.87 | 0 | 0 | 100
2073 | JALPAIGURI | Northern Mechanical | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 563/NMD | 14/07/2022 | 871 | MUSTAFI CONCERN | 2.16 | 0 | 0 | 100
2074 | JALPAIGURI | Jalpaiguri Division | Augmentation of Madhya Khagrabari Water Supply Scheme. , SM/10028 | Augmentation | Restoration works of Damaged pipe line due to culvert construction of Green tough cold storage at Madhya Khagrabari PWSS under Jalpaiguri Division P.H.E. Dte. | 815/RWS | 22/08/2024 | 20 | SOMNATH ROY | 0.55 | 0 | 0 | 100
2075 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-A). | 342/JD | 03/02/2022 | 90 | M/S R.N. TRADERS | 158.04 | 0 | 0 | 1
2076 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for MondalghatP/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 | 400/RWS | 30/06/2021 | 184 | UNITED CONSTRUCTION | 2.01 | 0 | 0 | 1
2077 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | providing drainage system for mondalghat pwss | BP-2021-23-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0 | 0
2078 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | PROVIDING DRAINAGE SYSTEM FOR MONDALGHAT PWSS | BP-2021-22-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0 | 0
2079 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | SOIL TEST FOR MANDALGHAT | BP-2021-22 | 22/03/2022 | 0 | R.B TESTING | 2.02 | 0 | 0 | 0
2080 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | FHTC GRASS MORE | BP-2021-22-25 | 26/04/2022 | 0 | M/S R.N. TRADERS | 7.08 | 0 | 0 | 0
2081 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | CONSTRUCTION 550 M3 AUG MANDALGHAT PWSS | BP-2021-22-391 | 17/03/2022 | 0 | R.N.TRADER'S | 51.64 | 0 | 0 | 0
2082 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MANDALGHAT PWSS, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 336/JD | 02/02/2022 | 120 | M/S R.N. TRADERS | 110.23 | 0 | 0 | 1
2083 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Construction of boundary wall with drain for 3rd site of Mondal ghat piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 648/RWS | 21/10/2022 | 30 | ALICK DUTTA | 4.84 | 0 | 0 | 100
2084 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Repair work of Pump house , bath room of H/W site & ancilliary works at Mondalghat PWSS under Jalpaiguri Division. | 285/RWS | 29/03/2023 | 14 | M/S UNITED CONSTRUCTION | 1.53 | 0 | 0 | 100
2085 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Construction of valve chember & Blower room(3.60MX3.00M ) Size for Iron Elimination Plant at Head Work Site of Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 390/RWS | 25/04/2023 | 14 | SWAPAN SAHA | 4.8 | 0 | 0 | 100
2086 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Material Requisition To Resource Division | 550/JD | 01/03/2022 | 0 | Resource Division | 60.75 | 0 | 0 | 0
2087 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Reparing of pump houses & construction of Boundary wall at 2nd site for Mandalghat W/S/S under Jalpaiguri Division , P.H.E Dte | 820/RWS | 30/11/2021 | 30 | ALICK DUTTA | 4.83 | 0 | 0 | 99
2088 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Construction of Boundary wall and land development at Head Work Site for Mandalghat Water Supply Scheme under Jalpaiguri Division P.H.E. Dte | 1442/JD | 09/09/2021 | 30 | M/S UNITED CONSTRUCTION | 10.53 | 0 | 0 | 100
2089 | JALPAIGURI | Northern Mechanical | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALGHAT PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1250/NMD | 31/07/2023 | 30 | M/S ANJALI ENTERPRISE | 11.6 | 0 | 0 | 100
2090 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Mandolghat PWSS under JJM work at Jalpaiguri sadar Block under PHE Dte., Jalpaiguri Division | 1082/RWS | 19/09/2023 | 30 | TIRTHANKAR CHOWDHURY | 9.24 | 0 | 0 | 100
2091 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Material Requisition To Resource Division | 2212/JD | 01/12/2024 | 0 | Resource Division | 23.36 | 0 | 0 | 0
2092 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Material Requisition To Resource Division | 2095/JD | 25/11/2024 | 0 | Resource Division | 70.02 | 0 | 0 | 0
2093 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-D). | 339/JD | 03/02/2022 | 1518 | BISWANATH GHOSH | 150.63 | 0 | 0 | 60
2094 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-B). | 345/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 195.6 | 0 | 0 | 85
2095 | JALPAIGURI | Jalpaiguri Division | Augmentation of Mondalghat Water Supply Scheme. , SM/10087 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site for Augmentation Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 402/JD | 11/02/2022 | 357 | M/S R.N. TRADERS | 27.54 | 0 | 0 | 100
2096 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2226/JD | 27/12/2021 | 60 | JITENDRA NATH ROY | 11.44 | 0 | 0 | 1
2097 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for Barnish P/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 | 408/RWS | 30/06/2021 | 184 | JITENDRA NATH ROY | 0.86 | 0 | 0 | 1
2098 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under BARNES PWSS, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 444/NMD | 14/06/2022 | 21 | TALUKDER ENTERPRISE | 2.16 | 0 | 0 | 0
2099 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-I) PWSS UNDER CDD, PHE DTE. | 756/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 0 | 0 | 0
2100 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-II) PWSS UNDER CDD, PHE DTE. | 757/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 0 | 0 | 0
2101 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2227/JD | 27/12/2021 | 60 | SADHAN KARMAKAR | 11.45 | 0 | 0 | 1
2102 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 596/CMSD-II (D) | 07/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0 | 0
2103 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION AFTER 200 KM FOR BENTONITE AND OTHERS FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | 607/CMSD-II (D) | 10/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.68 | 0 | 0 | 0
2104 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. | 597/CMSD-II (D) | 07/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.92 | 0 | 0 | 0
2105 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 0 | 0 | 0
2106 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0 | 0 | 0
2107 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941261, Reference ID : 402831975] | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2108 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | BARNESH PWSS | BP-2021-22- | 24/03/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 16.99 | 0 | 0 | 0
2109 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059398, Reference ID : 860248698] | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
2110 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059561, Reference ID : 860249301] | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0 | 0
2111 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | SOIL INVESTIGATION AUG BARNES PWSS | BP-2021-22-398 | 22/03/2022 | 0 | M S PRANTIK ASSOCIATES | 2.02 | 0 | 0 | 0
2112 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941264, Reference ID : 402831973] | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2113 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | PREPARATION OF DPR ODLABARI PWSS | BP-2021-22-492 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.94 | 0 | 0 | 0
2114 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 854/NMD | 18/07/2022 | 30 | SAIKAT SINHA | 7.87 | 0 | 0 | 100
2115 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-D). | 331/JD | 02/02/2022 | 90 | SUKES BASU MAJUMDAR | 155.8 | 0 | 0 | 1
2116 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Barnes W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 567/NMD | 14/07/2022 | 21 | S.D. CONCERN WORKSHOP | 2.16 | 0 | 0 | 0
2117 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte | 185/JD | 21/01/2022 | 120 | ASHIT KUMAR SINGHA | 141.66 | 0 | 0 | 1
2118 | JALPAIGURI | Northern Mechanical | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW No. III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 541/NMD | 08/07/2022 | 30 | SUMON ELECTRICAL | 7.86 | 0 | 0 | 100
2119 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Retrofitting works related to FHTC at different places of Barnes PWSS under Jalpaiguri Division, P.H.E. Dte. | 731/JD | 22/03/2023 | 30 | ASHIT KUMAR SINGHA | 17.49 | 0 | 0 | 100
2120 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Extention of pipe line at different places of Barnes PWSS under Jalpiaiguri Division,P.H.E.Dte. | 803/JD | 29/03/2023 | 21 | R.S CONSTRUCTION | 10.28 | 0 | 0 | 100
2121 | JALPAIGURI | Central Drilling | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
2122 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Material Requisition To Resource Division | 558/JD | 01/03/2022 | 0 | Resource Division | 124.02 | 0 | 0 | 0
2123 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS | BP-2023-24-109 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.55 | 0 | 0 | 0
2124 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | supply of one maxi cab on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar sub Division,P.H.E Dte. | BP-2023-24-428 | 11/10/2023 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
2125 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-C). | 330/JD | 02/02/2022 | 90 | R.S CONSTRUCTION | 170.45 | 0 | 0 | 100
2126 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-B). | 329/JD | 02/02/2022 | 90 | ASHIT KUMAR SINGHA | 146.7 | 0 | 0 | 80
2127 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site of Augmentation Barnish piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 409/JD | 15/02/2022 | 45 | ASHIT KUMAR SINGHA | 26.37 | 0 | 0 | 20
2128 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Construction of boundary wall with gate,drain, Pipe line,rising line, Approach road & other ancillary works for OHR site of Barnish piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 60/JD | 18/04/2023 | 30 | ASHIT KUMAR SINGHA | 25.62 | 0 | 0 | 100
2129 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Work of DI Pipe (Raising main), Pathway, Drain,Chember,flower block,Partial land Development , approach & other ancillary works at 4th site of Barnish Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | 388/RWS | 25/04/2023 | 14 | JITENDRA NATH ROY | 5.18 | 0 | 0 | 100
2130 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Barnish piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | 335/RWS | 10/04/2023 | 14 | SADHAN KARMAKAR | 3.21 | 0 | 0 | 100
2131 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 4th T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. | 1266/JD | 13/09/2023 | 45 | ASHIT KUMAR SINGHA | 16.44 | 0 | 0 | 100
2132 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 3rd T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. | 2519/JD | 30/12/2022 | 45 | GIYASUDDIN SEKH | 16.44 | 0 | 0 | 100
2133 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | Material Requisition To Resource Division | 2204/JD | 01/12/2024 | 0 | Resource Division | 24.92 | 0 | 0 | 0
2134 | JALPAIGURI | Jalpaiguri Division | Augmentation of Barnes Water Supply Scheme. , SM/10090 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-A). | 328/JD | 02/02/2022 | 1304 | ASHIT KUMAR SINGHA | 163.38 | 0 | 0 | 100
2135 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Shifting of DI pipeline due to widening of road of Purba Salbari Area Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte | 1534/JD | 02/08/2022 | 15 | ABHIJIT SARKAR | 1.52 | 0 | 0 | 1
2136 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Repairing of 2 nos. of Pump House (Head Work site & 2nd site) ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement and other allied works at Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 251/JD | 19/02/2021 | 30 | ABHIJIT SARKAR | 4.85 | 0 | 0 | 1
2137 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | CONST H/W BHANGARHAT WSS | BP-2021-22-516 | 30/03/2022 | 0 | SAHA CONSTRUCTION | 4.83 | 0 | 0 | 0
2138 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Purba Salbari PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | 349/JD | 22/02/2022 | 21 | ABHIJIT SARKAR | 7.97 | 0 | 0 | 0
2139 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation Purba Salbari P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 1802/JD | 14/09/2022 | 21 | ABHIJIT SARKAR | 4.65 | 0 | 0 | 0
2140 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Material Requisition To Resource Division | 553/JD | 01/03/2022 | 0 | Resource Division | 39.86 | 0 | 0 | 0
2141 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | FUEL BILL | BP-2022-23-350 | 09/12/2022 | 0 | FILL & SMILE | 0.62 | 0 | 0 | 0
2142 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | New Service Connection Charge for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018659, Reference ID : 402928489] | BP/22-23/128 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2143 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Infrastructure Cost for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 100000066802, Reference ID : 860257022] | BP/22-23/128 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0 | 0
2144 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of Laying Distribution System for Rejuvenation of Purba Salbari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte | 879/JD | 05/04/2022 | 210 | M/S GARGO TRADERS | 417.6 | 0 | 0 | 64
2145 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA SALBARI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1124/NMD | 12/09/2022 | 30 | DIAMOND ELECTRICAL WORKS | 8.02 | 0 | 0 | 100
2146 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing for Rejuvenation of Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1964/JD | 18/10/2022 | 180 | SAHA CONSTRUCTION | 69.07 | 0 | 0 | 60
2147 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA SALBARI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 105/NMD | 03/02/2023 | 21 | DIAMOND ELECTRICAL WORKS | 2.27 | 0 | 0 | 100
2148 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Laying Rising Main at 3rd Tubewell site of Purba Salbari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 323/JD | 18/05/2023 | 14 | ABHIJIT SARKAR | 4.59 | 0 | 0 | 80
2149 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Construction of different components of Rejuvenation of Purba Salbari PWSS i.e. RISING MAIN, Boundary wall etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 986/JD | 14/08/2024 | 595 | SAHA CONSTRUCTION | 29.57 | 0 | 0 | 50
2150 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purbba Salbari Piped Water Supply Scheme , SM/09861 | Augmentation | Balance Laying Distribution System with Providing Functional House Hold Tap Connection in connection with JJM at Purbba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | 677/JD | 04/04/2025 | 45 | A P CONSTRUCTION | 36.26 | 0 | 0 | 0
2151 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Repairing of Pump House (2nd T/W Site) and extension of pipeline repairing of pipeline under Purba Batabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 169/JSSD | 13/08/2020 | 30 | BIMAN DAS | 4.77 | 0 | 0 | 0
2152 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of boundary wall with gate, drain, culvert, Pipe line for H/W site of Purba Batabari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1332/JD | 23/08/2021 | 30 | R.S CONSTRUCTION | 15.53 | 0 | 0 | 0
2153 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Sinking of 1 No. 250mm x 150mm x 132m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 872/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 7.8 | 0 | 0 | 0
2154 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | AUG PURBA BATABARI | BP-2021-22-169 | 14/01/2022 | 0 | BIMAN DAS | 4.36 | 0 | 0 | 0
2155 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | RESTORATION OF PIPE LINE PURBA BATABARI PWSS | BP-2021-22-508 | 30/03/2022 | 0 | BIMAN DAS | 2.99 | 0 | 0 | 0
2156 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | PROVIDING DRINKING ARRANGEMENT AWC MAL SUB-DIVISION | BP-2021-22-541 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 4.61 | 0 | 0 | 0
2157 | JALPAIGURI | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | New Service Connection Charge for PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 4002964283, Reference ID :402851945] | BP/22-23/91 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2158 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | SINKING OF TUBEWELL FOR LATAGURI | BP-2021-22-542 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 7.63 | 0 | 0 | 0
2159 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | PREPARATION OF DPR PURBA BATABARI PWSS | BP-2021-22-489 | 29/03/2022 | 0 | SUBHANKAR GHOSH | 1.57 | 0 | 0 | 0
2160 | JALPAIGURI | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Installation of Infrastructure COST at PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 100000059481, Reference ID : 860249201] | BP/22-23/91 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
2161 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | RENOVATION OF B-WALL SOUTH BERUBARI | BP-2022-2023-46 | 24/05/2022 | 0 | A.P CONSTRUCTION | 2.2 | 0 | 0 | 0
2162 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Restoration of pipeline at Purba Batabari PWSS (damaged part) under Jalpaiguri Division, P.H.E. Dte. | 991/JSSD | 03/01/2022 | 10 | BIMAN DAS | 2.99 | 0 | 0 | 0
2163 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of paver block approach road with land development, inside drain etc. and fixing R.B.T. in boundary wall at H/W Site for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 134/JD | 14/01/2022 | 15 | SUNIL ROY | 4.46 | 0 | 0 | 0
2164 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Purba Batabari PWSS in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | 388/JSSD | 09/11/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 3.64 | 0 | 0 | 0
2165 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. | 1108/W/JSSD | 27/01/2022 | 45 | N S CONSTRUCTION & SUPPLIER | 4.75 | 0 | 0 | 100
2166 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 84/JSSD | 22/07/2022 | 20 | N S CONSTRUCTION & SUPPLIER | 4.57 | 0 | 0 | 100
2167 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Diviion, P.H.E. Dte. | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0 | 0 | 0
2168 | JALPAIGURI | Northern Mechanical | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BATABARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 74/NMD | 27/01/2023 | 30 | M/S MATRI CONSTRUCTION | 10.98 | 0 | 0 | 100
2169 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of Sluice valve Chamber and GI line over culvert for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1931/JD | 29/11/2021 | 15 | SUNIL ROY | 1.63 | 0 | 0 | 0
2170 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | HIRE CHARGES | BP-2022-23-344 | 09/12/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0 | 0
2171 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | HIRE CHARGES | BP-2022-23-344 | 09/12/2022 | 0 | RAKESH SARKAR | 0.33 | 0 | 0 | 0
2172 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 499/JSSD | 02/01/2024 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 0 | 0 | 0 | 0
2173 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 499/JSSD | 02/01/2024 | 30 | TIRTHANKAR CHOWDHURY | 2.8 | 0 | 0 | 0
2174 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2175 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Supplying and Installation of 24 nos. Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | 89/JSSD | 20/06/2024 | 10 | GURUKUL INFOTECH | 4.46 | 0 | 0 | 100
2176 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Supplying and Installation of 77 nos Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division PHE Dte | 88/JSSD | 20/06/2024 | 10 | GOUTAM DAS | 14.3 | 0 | 0 | 100
2177 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jalswapna for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) | 667/JD | 09/03/2022 | 1394 | BOSE ENTERPRISE | 221.99 | 0 | 0 | 90
2178 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 793/JD | 24/07/2023 | 180 | TIRTHANKAR CHOWDHURY | 91.24 | 0 | 0 | 70
2179 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Purba Batabari PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 108/JD | 16/01/2025 | 60 | M/S. S.D. ENTERPRISE | 19.96 | 0 | 0 | 0
2180 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Providing Sluice Valves at Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 331/JSSD | 10/09/2024 | 7 | SWAPAN SAHA | 0.55 | 0 | 0 | 100
2181 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | 1734/JD | 31/07/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0 | 0
2182 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | 2405/JD | 19/11/2025 | 30 | APIKUL ALI | 0.4 | 0 | 0 | 0
2183 | JALPAIGURI | Jalpaiguri Division | Augmentation of Purbba Batabari Piped Water Supply Scheme , SM/09864 | Augmentation | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | 2000/JD | 25/09/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0 | 0
2184 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | LDS BARADIGHI | BP-2021-22-528 | 30/03/2022 | 0 | GOUTAM DAS | 4.52 | 0 | 0 | 0
2185 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | LDS FHTC AUG KRANTI (ZONE -I) | BP-2021-22-527 | 30/03/2022 | 0 | M/S SIBU DEY AND CO. | 9.39 | 0 | 0 | 0
2186 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM at various House hold and Govt. Aided Educational/ Health Institute under the command area of Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (Phase-III) | 1300/JD | 14/06/2022 | 15 | SAHA CONSTRUCTION | 2.15 | 0 | 0 | 0
2187 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Repairing of Damaged distribution line due to drain construction by T.G. authority, Land development, re modification of distribution main along with other ancillary works within the command area of rejuvenation of Kathalguri T.G. P.W.S.S. under Jalpaiguri Division, P.H.E.Dte.and I.E.Plant etc. under Jalpaiguri Division, P.H.E.Dte. (from 01.08.2022 to 31.01.2023) | 1805/JD | 14/09/2022 | 21 | RABINDRANATH DUTTA | 4.83 | 0 | 0 | 0
2188 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Resistivity test at two alternative Site and two reserved sites for sinking of Tube Well at Zone-II for Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme and at Two Sites for Rejuvenation of Khthalguri T.G. P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | 1856/JD | 16/09/2022 | 21 | PARAMJYOTI ENTERPRISE | 1.25 | 0 | 0 | 0
2189 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Kathalguri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 107/JD | 11/01/2022 | 60 | JITENDRA NATH ROY | 4.65 | 0 | 0 | 100
2190 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Construction of 200 Cu.M. capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site and other related works including pump connection of different pump for Rejuvenation of Kathalguri Tea Garden area piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 352/JD | 03/03/2022 | 180 | NEW KUNDU ENTERPRISE | 81.56 | 0 | 0 | 100
2191 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Shifting of existing pipeline of Khalaigram W/S Scheme between the Khalaigram Khetifullbari P.W.D. Road under Jalpaiguri Division P.H.E. Dte. (PART - A) | 423/JD | 04/06/2020 | 90 | LOKNATH CONSTRUCTION | 28.18 | 0 | 0 | 0
2192 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 0 | 0 | 1
2193 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | New Service Connection Charge for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003103082 ; Reference ID : 402976414] | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2194 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | New Service Connection Charge for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 4003103099 ; Reference ID : 402976404] | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2195 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Infrastructure Cost for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 100000073456 ; Reference ID : 860265206] | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0 | 0
2196 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Infrastructure Cost for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO.100000074460 ; Reference ID : 860265550] | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.72 | 0 | 0 | 0
2197 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KATHALGURI TG PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 337/NMD | 29/03/2023 | 30 | SUBODH KUMAR BANIK | 29.9 | 0 | 0 | 60
2198 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Construction of Pump House (5.40m x 3.60m) with sanitary & plumbing arrangement including Rising Main & interconnections at Head Work site for Augmentation of Kathalguri Water Supply Scheme at Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. | 2305/JD | 07/02/2024 | 45 | NEW KUNDU ENTERPRISE | 7.39 | 0 | 0 | 100
2199 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Construction of Foot Path, Drain including rising main interconnections at HW site of Kathalguri PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | 2634/JD | 07/03/2024 | 21 | NEW KUNDU ENTERPRISE | 13.52 | 0 | 0 | 100
2200 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2201 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kathalguri Tea Garden Piped water Supply Scheme , SM/09392 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | 1520/JD | 16/10/2023 | 562 | ROY ENGINEERS | 41.28 | 0 | 0 | 100
2202 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Sinking of 183 mm x 125mm dia tube well by ODEX-165 method of drilling for Rejuvenation of Mainatali PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 198/JD | 21/01/2022 | 30 | M/S BABUN BISWAS | 7.89 | 0 | 0 | 100
2203 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Mainatali P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 95/JD | 10/01/2022 | 60 | ABHIJIT SARKAR | 4.65 | 0 | 0 | 100
2204 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | New Service Connection Charge for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147727, Reference ID : 403014098] | BP/23-24/18 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2205 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Infrastructure Cost for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077915, Reference ID : 860269055] | BP/23-24/18 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.27 | 0 | 0 | 0
2206 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Laying Rising Main at 3rd Tubewell site of Mainatali PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 324/JD | 18/05/2023 | 14 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.64 | 0 | 0 | 50
2207 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Construction of Blower Room & IEP (40m3/hr.) of Mainatali PWSS, in connection with Rejuvenation of Mainatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E Dte. | 1778/JD | 08/12/2023 | 60 | D. S. ENTERPRISE | 16.9 | 0 | 0 | 75
2208 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | New Service Connection Charge for MAINATALI, T/W-IV, under DHUPGURI CCC, [APPLICATION NO. 4003336981, Reference ID : 403161218] |  | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0 | 0
2209 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | New Service Connection Charge for Rejuvenation of Mainatali, T/W-IV under DHUPGURI CCC APPLICATION NO. 4003336981 Reference ID :- 403161218 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0 | 0
2210 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Additional New Service Connection Charge for REJUVENATION OF MAINATALI PWSS, at TW NO IV, under DHUPGURI CCC APPLICATION NO. 100000113878 Reference ID : 860306078 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.74 | 0 | 0 | 0
2211 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
2212 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MAINATALI PWSS, at TW NO III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 392/NMD | 29/03/2023 | 734 | BLUE PINE | 24.99 | 0 | 0 | 100
2213 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mainatali Piped Water Supply Scheme , SM/09565 | Augmentation | Construction of Boundary Wall, IEP Washout, Pathway, Drain etc. at 3rd TW Site for Mainatali PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 2314./JD | 11/12/2024 | 100 | ABHIJIT SARKAR | 9.55 | 0 | 0 | 100
2214 | JALPAIGURI | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Construction of Different Components of Chhaophali PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. | 138/JD | 28/04/2023 | 180 | RANJEET SINGH BENIWAL | 131.18 | 0 | 0 | 50
2215 | JALPAIGURI | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Material Requisition To Resource Division | 1115/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0 | 0
2216 | JALPAIGURI | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAOAPHALI PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1273/NMD | 02/08/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 24.43 | 0 | 0 | 75
2217 | JALPAIGURI | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Construction of Boundary Wall with approach road at H/W site including rising main and interconnections of Chhaophali PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | 2412/JD | 19/02/2024 | 45 | RANJEET SINGH BENIWAL | 19.17 | 0 | 0 | 0
2218 | JALPAIGURI | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Laying of Rising Main along with pump connection for commissioning of the scheme and remaining part of laying distribution system with providing FHTC at Chhaoaphali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E.Dte. | 1531/JD | 01/10/2024 | 30 | PRIYABRATA KARMAKAR | 18.45 | 0 | 0 | 100
2219 | JALPAIGURI | Jalpaiguri Division | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Material Requisition To Resource Division | 2041/JD | 09/01/2024 | 0 | Resource Division | 2.85 | 0 | 0 | 0
2220 | JALPAIGURI | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Infrastructure Cost for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 100000097045 , Reference ID : 860289125] | BP/23-24/271 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.12 | 0 | 0 | 0
2221 | JALPAIGURI | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | New Service Connection Charge for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 4003292351 , Reference ID : 403124700] | BP/23-24/270 | 23/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2222 | JALPAIGURI | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
2223 | JALPAIGURI | Northern Mechanical | CHHAOAPHALI PIPED WATER SUPPLY SCHEME , SM/13901 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
2224 | JALPAIGURI | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Material Requisition To Resource Division | 152/JD | 28/04/2023 | 0 | Resource Division | 26.83 | 0 | 0 | 0
2225 | JALPAIGURI | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Material Requisition To Resource Division | 1838/JD | 15/12/2023 | 0 | Resource Division | 2.62 | 0 | 0 | 0
2226 | JALPAIGURI | Jalpaiguri Division | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Construction of different components of Gadang Pratham Khanda PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 779/JD | 27/03/2023 | 180 | M/S. DOLPHIN CONSTRUCTION CO. | 222.91 | 0 | 0 | 20
2227 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS , T/W-I under DHUPGURI CCC, APPLICATION NO. 4003412908 Reference ID : 403221510 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.3 | 0 | 0 | 0
2228 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS, TW no II, under DHUPGURI CCC APPLICATION NO. 4003290916 Consumer ID : 403123851 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
2229 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
2230 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
2231 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
2232 | JALPAIGURI | Northern Mechanical | GADANG PRATHAM KHANDA PIPED WATER SUPPLY SCHEME , SM/14665 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GADANG PRATHAM KHANDA PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1471/NMD | 17/08/2023 | 593 | S.P. ENTERPRISE (KOLKATA) | 20.63 | 0 | 0 | 100
2233 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Material Requisition To Resource Division | 166/JD | 28/04/2023 | 0 | Resource Division | 15.92 | 0 | 0 | 0
2234 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Construction of different components of Paschim Baragila PWSS i.e. TW, pump Houses, Water distribution network, OHR, RISING MAIN, FHTC etc. under Jal Jeeban Mission at Block - Maynaguri under Jalpaiguri Divission, P.H.E. Dte. | 776/JD | 27/03/2023 | 180 | TIRTHANKAR CHOWDHURY | 234.57 | 0 | 0 | 75
2235 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM BARAGILA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 272/NMD | 21/03/2023 | 30 | S.P. ENTERPRISE | 20.63 | 0 | 0 | 80
2236 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 2496/JD | 28/02/2024 | 45 | TIRTHANKAR CHOWDHURY | 16.53 | 0 | 0 | 0
2237 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Paschimbaragila PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2334./JD | 12/12/2024 | 45 | PRITAM DUTTA | 21.76 | 0 | 0 | 0
2238 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Material Requisition To Resource Division | 2050/JD | 09/01/2024 | 0 | Resource Division | 2.89 | 0 | 0 | 0
2239 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | New Service Connection Charge for PASCHIM BOROGILA, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266412, Reference ID : 403105853] | 23-24/156&164 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.99 | 0 | 0 | 0
2240 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2241 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | New Service Connection Charge for PASCHIM BOROGILA, T/W No. II, under MAYNAGURI CCC, [APPLICATION NO. 4003266398, Reference ID : 403105500] | 23-24/156&164 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
2242 | JALPAIGURI | Jalpaiguri Division | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 167/RWS | 15/02/2024 | 358 | EDIFICE ENTERPRISE | 7.52 | 0 | 0 | 100
2243 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
2244 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0 | 0
2245 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
2246 | JALPAIGURI | Northern Mechanical | PASCHIM BARAGILA PIPED WATER SUPPLY SCHEME , SM/14667 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
2247 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Retroffitting works, repairing of 2 nos pump house 2 nos boundary wall, repairing of Rising main line and other allied works at Chilaoni TG Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 607/JD | 09/03/2023 | 30 | SUJAN LAMA | 29.35 | 0 | 0 | 0
2248 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 0 | 1
2249 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Material Requisition To Resource Division | 1069/JD | 24/08/2023 | 0 | Resource Division | 15.45 | 0 | 0 | 0
2250 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Infrastructure Cost for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 100000066825, Reference ID : 860257225] | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0 | 0
2251 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | New Service Connection Charge for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964337, Reference ID : 402851946] | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2252 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Infrastructure Cost for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC W/S Scheme, , [APPLICATION NO. 100000066826, Reference ID : 860257226] | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
2253 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | New Service Connection Charge for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964336, Reference ID : 402851948] | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2254 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 3rd tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. | 74/JSSD | 22/07/2022 | 45 | SUJAN LAMA | 4.65 | 0 | 0 | 100
2255 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 4th tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. | 75/JSSD | 22/07/2022 | 45 | SUJOY CHOWDHURY | 4.65 | 0 | 0 | 100
2256 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHILOUNI TG AREA PWSS, TW no III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 477/NMD | 26/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 22.76 | 0 | 0 | 100
2257 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Matiali block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1286/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 0 | 0 | 100
2258 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chilouni Tea Garden Area Piped Water Supply Scheme , SM/15114 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0 | 0
2259 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Material Requisition To Resource Division | 1054/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0 | 0
2260 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Providing FHTC Including Restoration of Existing FHTC in the Command Area of Bhandani PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 2398/JD | 19/12/2024 | 30 | SANJIT SAHA | 6.96 | 0 | 0 | 0
2261 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Bhandani PWSS , in connection with Rejuvenation of Bhandani PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 703/JD | 13/07/2023 | 628 | GOURAB GUHA ROY | 36.18 | 0 | 0 | 55
2262 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Laying distribution system along with ancillary works for Rejuvenation of Bhandani Piped water supply scheme in connection with Jal Jeevan mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 422/JD | 12/06/2024 | 323 | SANJIT SAHA | 29.06 | 0 | 0 | 50
2263 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
2264 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
2265 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2266 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BHANDANI PIPED WATER SUPPLY SCHEME , SM/15094 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANDANI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 594/NMD | 18/05/2023 | 837 | M/S ROYAL ENTERPRISE | 11.45 | 0 | 0 | 100
2267 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DIANA TG(D) PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 369/NMD | 29/03/2023 | 30 | THE BANERJEE CONCERN | 24.35 | 0 | 0 | 0
2268 | JALPAIGURI | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Material Requisition To Resource Division | 150/JD | 28/04/2023 | 0 | Resource Division | 15.68 | 0 | 0 | 0
2269 | JALPAIGURI | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Material Requisition To Resource Division | 1830/JD | 15/12/2023 | 0 | Resource Division | 5.95 | 0 | 0 | 0
2270 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Infrastructure Cost for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 100000083813 ; Reference ID : 860275313] | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.15 | 0 | 0 | 0
2271 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | New Service Connection Charge for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 4003193588 ; Reference ID : 403045950] | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2272 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Infrastructure Cost for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 100000083815 ; Reference ID : 860275315] | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.32 | 0 | 0 | 0
2273 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | New Service Connection Charge for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 4003193593 ; Reference ID : 403045952] | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2274 | JALPAIGURI | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2275 | JALPAIGURI | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Construction of Boundary Wall, Drain, Footpath including Balance Portion of Distribution Network and other Allied Works related to Pipe Line at Diana Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | 2012/JD | 18/11/2024 | 30 | VISHAL ENTERPRISES | 9.7 | 0 | 0 | 0
2276 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
2277 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
2278 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0 | 0
2279 | JALPAIGURI | Jalpaiguri Division | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No. WB71B-8742) (From 01.04.2025 to 30.04.2025) | 108-HQ/JD | 28/03/2025 | 31 | RAKESH SARKAR | 0.15 | 0 | 0 | 0
2280 | JALPAIGURI | Northern Mechanical | DIANA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/15261 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2281 | JALPAIGURI | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Material Requisition To Resource Division | 169/JD | 28/04/2023 | 0 | Resource Division | 12.25 | 0 | 0 | 0
2282 | JALPAIGURI | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Material Requisition To Resource Division | 1834/JD | 15/12/2023 | 0 | Resource Division | 7.44 | 0 | 0 | 0
2283 | JALPAIGURI | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2284 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 4003254880 ; Reference ID : 403095717] | BP/23-24/246 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2285 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 4003254888 ; Reference ID : 403095711] | BP/23-24/248 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2286 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 100000091681 ; Reference ID : 860283231] | BP/23-24/247 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.26 | 0 | 0 | 0
2287 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 100000091682 ; Reference ID : 860283232] | BP/23-24/249 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.71 | 0 | 0 | 0
2288 | JALPAIGURI | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Construction of different components of Lakhipara Tea Garden PWSS i.e. TW, Pump House, Water distribution Network, OHR , Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division , P.H.E Dte. | 824/JD | 30/03/2023 | 1007 | S.S. CONSTRUCTION | 297.96 | 0 | 0 | 60
2289 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
2290 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
2291 | JALPAIGURI | Jalpaiguri Division | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (From 01.04.2025 to 30.04.2025) | 110-HQ/JD | 28/03/2025 | 31 | AJIJUL HAQUE | 0.15 | 0 | 0 | 0
2292 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0 | 0
2293 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2294 | JALPAIGURI | Northern Mechanical | LAKSHMI PARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15262 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for LAKSHMIPARA TG PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1369/NMD | 09/08/2023 | 419 | GEETA CONSTRUCTION | 24.87 | 0 | 0 | 100
2295 | JALPAIGURI | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Material Requisition To Resource Division | 2049/JD | 09/01/2024 | 0 | Resource Division | 7.47 | 0 | 0 | 0
2296 | JALPAIGURI | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Material Requisition To Resource Division | 53/JD | 09/04/2024 | 0 | Resource Division | 13.2 | 0 | 0 | 0
2297 | JALPAIGURI | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-I, POWER HOUSE CCC APPLICATION NO. 4003352414 Consumer ID : 403172861 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.99 | 0 | 0 | 0
2298 | JALPAIGURI | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-II, Powe House CCC APPLICATION NO. 4003352425 Reference ID : 403172863 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.71 | 0 | 0 | 0
2299 | JALPAIGURI | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Construction of different components of Kholachand Fapri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. under Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | 266/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 262.01 | 0 | 0 | 35
2300 | JALPAIGURI | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOLACHAND FAPRI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1276/NMD | 02/08/2023 | 608 | P.K.ENGINEERING | 22.11 | 0 | 0 | 50
2301 | JALPAIGURI | Northern Mechanical | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
2302 | JALPAIGURI | Jalpaiguri Division | KHOLACHAND FAPRI PIPED WATER SUPPLY SCHEME , SM/15263 | New | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Kholachand Fapri Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 87-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
2303 | JALPAIGURI | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme , SM/15099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PALASBARI TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1482/NMD | 17/08/2023 | 30 | SUDIP DUTTA | 10.76 | 0 | 0 | 0
2304 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme , SM/15099 | Augmentation | Construction of Boundary Wall Surface, Drain, Pathway with related ancillary work at Head Works site of Palashbari Tea Garden Area PWSS under Jalpaiguri Division, P.H.E. Dte. | 839/JD | 31/03/2022 | 30 | DULAL CHOUDHURY | 28.53 | 0 | 0 | 1
2305 | JALPAIGURI | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme , SM/15099 | Augmentation | New Service Connection Charge for REJU PALASHBARI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 400333017 , Reference ID : 403157467] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
2306 | JALPAIGURI | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme , SM/15099 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
2307 | JALPAIGURI | Northern Mechanical | Rejuvenation of Palasbari Tea Garden Area Piped Water Supply Scheme , SM/15099 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2308 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Sinking of one No. tube well (250mm x 200mm) by Reverse Rotary Method of Drilling and Construction of Pump House (5.40m x 3.60m) and Iron Elimination Plant for direct boosting arrangement for Augmentation of Porapara Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 988/JD | 14/08/2024 | 120 | SADHAN KARMAKAR | 38.03 | 0 | 0 | 0
2309 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Construction of different components for Rejuvenation of Porapara PWSS I.e. TW, Pump Houses, Boundary wall IEP, Rising main etc. at Block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. | 1003/JD | 17/05/2023 | 45 | B.M CONSTRUCTION | 51.2 | 0 | 0 | 100
2310 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1298/NMD | 03/08/2023 | 30 | M/S ANJALI ENTERPRISE | 12.62 | 0 | 0 | 100
2311 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1251/NMD | 31/07/2023 | 30 | TAPAN BISWAS | 10.86 | 0 | 0 | 100
2312 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Emergency extension and reparing of pipe line to facilite FHTC at different location Pora Para Water Supply Scheme under Jalpaiguri Division, PHE Dte. Under JJM. | 1282/RWS | 28/11/2023 | 20 | B.M CONSTRUCTION | 6.16 | 0 | 0 | 100
2313 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Sadar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1290/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 0 | 0 | 100
2314 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Material Requisition To Resource Division | 2208/JD | 01/12/2024 | 0 | Resource Division | 24.23 | 0 | 0 | 0
2315 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Supply of Different Stationary Items for Office Use under Jalpaiguri RWS Sub Division. PHE Dte. | BP-2024-25-515 | 14/11/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.23 | 0 | 0 | 0
2316 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 479/RWS | 29/05/2025 | 30 | JAYDEB SAHA | 7.95 | 0 | 0 | 100
2317 | JALPAIGURI | Northern Mechanical | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2318 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF PORA PARA PWSS , SM/15101 | Augmentation | Construction of different balance components of Rejuvenation of Porapara PWSS in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. | 2494/JD | 28/02/2024 | 428 | SUKES BASU MAJUMDAR | 74.69 | 0 | 0 | 100
2319 | JALPAIGURI | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Material Requisition To Resource Division | 1082/JD | 24/08/2023 | 0 | Resource Division | 8.97 | 0 | 0 | 0
2320 | JALPAIGURI | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Material Requisition To Resource Division | 2024/JD | 09/01/2024 | 0 | Resource Division | 2.81 | 0 | 0 | 0
2321 | JALPAIGURI | Jalpaiguri Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Construction of different components of Khasjangal-I PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Mal under Jalpaiguri Division. | 942/JD | 08/08/2023 | 721 | A. K. INDUSTRIES | 133.2 | 0 | 0 | 30
2322 | JALPAIGURI | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHAS JANGAL PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 1473/NMD | 17/08/2023 | 684 | NIRMAN | 25.2 | 0 | 0 | 50
2323 | JALPAIGURI | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2324 | JALPAIGURI | Northern Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME , SM/14907 | New | Installation of two tank chlorination system at P.H No.-I under KHAS JANGAL PWSS of JJM in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 112/HQ/NMD | 17/01/2025 | 7 | SARKAR ELECTRIC | 0.16 | 0 | 0 | 0
2325 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME , SM/15338 | Augmentation | Material Requisition To Resource Division | 1071/JD | 24/08/2023 | 0 | Resource Division | 41.27 | 0 | 0 | 0
2326 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME , SM/15338 | Augmentation | Construction of different components of Augmentation of Angrabhasa PWSS i.e. TW, Pump Houses, Boundary Walls. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 1436/JD | 05/10/2023 | 60 | M/S ROY & SARKAR CONSTRUCTION | 27.72 | 0 | 0 | 35
2327 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME , SM/15338 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Nagrakata block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1287/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 0 | 0 | 100
2328 | JALPAIGURI | Northern Mechanical | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME , SM/15338 | Augmentation | New service connection charge for (reju) Angrabhasa PWSS tw-IV Application No-4003418417 Reference Id-403225912 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9 | 0 | 0 | 0
2329 | JALPAIGURI | Northern Mechanical | Rejuvenation of ANGRABHASA WATER SUPPLY SCHEME , SM/15338 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ANGRABHASA PWSS at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 656/NMD | 15/03/2024 | 472 | SAIKAT SINHA | 12.6 | 0 | 0 | 100
2330 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ELLENBURY TEA GARDEN PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1334/NMD | 08/08/2023 | 30 | SUBODH KUMAR BANIK | 21.95 | 0 | 0 | 0
2331 | JALPAIGURI | Jalpaiguri Division | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2332 | JALPAIGURI | Jalpaiguri Division | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 3rd tube well site of Ellenbari Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 2318/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0 | 0
2333 | JALPAIGURI | Jalpaiguri Division | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Material Requisition To Resource Division | 2020/JD | 09/01/2024 | 0 | Resource Division | 4.28 | 0 | 0 | 0
2334 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Infrastructure development cost for new service connection at ELLENBARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000109307 Reference ID : 860301267 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.76 | 0 | 0 | 0
2335 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | New Service Connection Charge for ELLENBARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003424572 Reference ID : 403230052 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2336 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Infrastructure development cost for new service connection at ELLENBARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109308 Reference ID : 860301268 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.19 | 0 | 0 | 0
2337 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | New Service Connection Charge for ELLENBARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424570 Reference ID : 403230051 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2338 | JALPAIGURI | Jalpaiguri Division | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Construction of different components of Ellenburry Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 939/JD | 08/08/2023 | 966 | NARENDRA KUMAR | 175.96 | 0 | 0 | 55
2339 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2340 | JALPAIGURI | Northern Mechanical | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
2341 | JALPAIGURI | Jalpaiguri Division | ELLENBURY TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15980 | New | Balance laying Distribution Network and Providing Functional House Hold Tap Connection including TW, Pump House, Boundary Wall of Ellenbari Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 2511/JD | 10/12/2025 | 60 | NARENDRA KUMAR | 40.39 | 0 | 0 | 0
2342 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJOHRA TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1812/NMD | 31/10/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 29.21 | 0 | 0 | 60
2343 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2344 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Sinking of one no. Tube Well by Modified DTH - ODEX big dia tube well 200x150 mm dia for Pathorjhora piped water supply scheme i.c.w. Jal jeevan Mission at Mal Block under Jalpaiguri Division, P.H.E. Dte | 1357/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.54 | 0 | 0 | 100
2345 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Sinking of 2 (Two) Nos Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Patharjohra Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2750/JD | 14/03/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.26 | 0 | 0 | 100
2346 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Drilling of 200mm Big Dia Tube Well by Modified DTH-ODEX method at 2nd tube well site of Pathorjhora Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | 588/A/AE/JSSD/CAMP | 18/03/2024 | 2 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 4.36 | 0 | 0 | 100
2347 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Material Requisition To Resource Division | 2062/JD | 10/01/2024 | 0 | Resource Division | 6.09 | 0 | 0 | 0
2348 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 100000100929, Reference ID : 860293129] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.03 | 0 | 0 | 0
2349 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 4003344810, Reference ID : 403166839] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2350 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | New Service Connection Charge for PATHORJHORA TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003482918 Reference ID : 403269952 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2351 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Infrastructure development cost for new service connection at PATHORJHORA TG, TW NO-III,, OODLABARI CCC APPLICATION NO. 100000117770 Reference ID : 860312410 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.61 | 0 | 0 | 0
2352 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 4003343265, Reference ID : 403165544] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2353 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 100000101095, Reference ID : 860293135] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.24 | 0 | 0 | 0
2354 | JALPAIGURI | Jalpaiguri Division | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Construction of different components of Patharjhora Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 346/JD. | 23/05/2023 | 180 | SRINIWAS AGARWAL | 208.93 | 0 | 0 | 62
2355 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJHORA TG PWSS at TW No. III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1841/NMD | 05/11/2024 | 30 | CHOWDHURY AND BASU ENTERPRISE | 14.14 | 0 | 0 | 70
2356 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2357 | JALPAIGURI | Northern Mechanical | PATHARJOHRA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15978 | New | Additional Works in connection with Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJOHRA TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 817/HQ/NMD | 25/03/2025 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.54 | 0 | 0 | 0
2358 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2359 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Sinking of 1 (One) No Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Meanglass Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1416/JD | 20/09/2024 | 20 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 20.88 | 0 | 0 | 0
2360 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Sinking of Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling for one no. tube well at Meenglass Tea Garden Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1761/JD | 08/12/2023 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.46 | 0 | 0 | 100
2361 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Material Requisition To Resource Division | 2072/JD | 10/01/2024 | 0 | Resource Division | 6.75 | 0 | 0 | 0
2362 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
2363 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | New Service Connection Charge for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266406, Reference ID : 403105525] | 23-24/158&166 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2364 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | New Service Connection Charge for MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424052 Reference ID : 403230050 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2365 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Infrastructure development cost for new service connection at MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109304 Reference ID : 860301264 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.47 | 0 | 0 | 0
2366 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Infrastructure Cost for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093891, Reference ID : 860285651] | 23-24/158&166 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0 | 0
2367 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2368 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
2369 | JALPAIGURI | Jalpaiguri Division | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Construction of different components of Menglass Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 40/JD | 13/04/2023 | 605 | SANDIP BANIK | 206.82 | 0 | 0 | 100
2370 | JALPAIGURI | Northern Mechanical | MENGLASS TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15990 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MENGLASS TEA GARDEN PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1393/NMD | 09/08/2023 | 631 | M/S SAJAHAN CHOWDHURY | 24.55 | 0 | 0 | 100
2371 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR NAGRAKATA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15611 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2372 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR NAGRAKATA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15611 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2373 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF NAGRAKATA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15619 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2374 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF NAGRAKATA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15619 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2375 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BASILARDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15907 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
2376 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BASILARDANGA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15907 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2377 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SAOGAON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15623 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2378 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SAOGAON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15623 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2379 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.4003385771 Reference ID : 403199268 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2380 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.4003386376 Reference ID : 403200294 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2381 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105525 Reference ID : 860297575 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.24 | 0 | 0 | 0
2382 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.100000105522 Reference ID : 860297572 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.99 | 0 | 0 | 0
2383 | JALPAIGURI | Northern Mechanical | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1319/NMD | 04/08/2023 | 574 | EASTERN INDIA SALES & SERVICE | 20.6 | 0 | 0 | 70
2384 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF BATABARI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/16773 | Augmentation | Construction of different components of Rejuvenation of Batabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. | 1347/JD | 26/09/2023 | 568 | SABITA ENTERPRISE | 127.56 | 0 | 0 | 52
2385 | JALPAIGURI | Jalpaiguri Division | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2386 | JALPAIGURI | Jalpaiguri Division | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Material Requisition To Resource Division | 2015/JD | 09/01/2024 | 0 | Resource Division | 4.08 | 0 | 0 | 0
2387 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Infrastructure Cost for SISOBARI TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093882, Reference ID : 860285542] | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.31 | 0 | 0 | 0
2388 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | New Service Connection Charge for SISOBARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266400, Reference ID : 403105526] | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2389 | JALPAIGURI | Jalpaiguri Division | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
2390 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | New Service Connection Charge for SISOBARI TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266403, Reference ID : 403105522] | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2391 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Infrastructure Cost for SISOBARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093881, Reference ID : 860285541] | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
2392 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
2393 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
2394 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2395 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
2396 | JALPAIGURI | Northern Mechanical | Sisubari Tea Garden Piped Water Supply Scheme , SM/16778 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SISUBARI TEA GARDEN AREA PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1335/NMD | 08/08/2023 | 543 | GOENKA ENTERPRISE | 24.28 | 0 | 0 | 100
2397 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF CHARERBARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15606 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
2398 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF CHARERBARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15606 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2399 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Construction of different components of Chapgar (Zone-I & II) PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block -Maynaguri under Jalpaiguri Division, P.H.E Dte. | 944/JD | 08/08/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 488 | 0 | 0 | 34
2400 | JALPAIGURI | Northern Mechanical | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHAPGAR PWSS, Zone-I,II at TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1343/NMD | 08/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 43.76 | 0 | 0 | 0
2401 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Facelifting and Interior furnishing works for Junior Engineer Room-2 and Estimating Section under Jal;paiguri Division,P.H.E.Dte. | 502/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.66 | 0 | 0 | 100
2402 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Facelifting and Interior furishing works for Junior Engineer Room-1 and DPMU Room under Jalpaiguri Division, PHE Dte. | 501/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.65 | 0 | 0 | 100
2403 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Material Requisition To Resource Division | 2061/JD | 10/01/2024 | 0 | Resource Division | 9.79 | 0 | 0 | 0
2404 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of October 2024 | BP-2024-25-520 | 25/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
2405 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-519 | 25/11/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
2406 | JALPAIGURI | Northern Mechanical | Chapgar Piped Water Supply Scheme. , SM/18492 | New | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-II under MAYNAGURI CCC APPLICATION NO. 4003379456 Reference ID : 403196953 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
2407 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-495 | 07/10/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
2408 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of August 2024 | BP-2024-25-363 | 13/09/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
2409 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2410 | JALPAIGURI | Northern Mechanical | Chapgar Piped Water Supply Scheme. , SM/18492 | New | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376095 Reference ID : 403191643 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.54 | 0 | 0 | 0
2411 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of September 2024 | BP-2024-25-494 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
2412 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-362 | 13/09/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
2413 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-270 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
2414 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of April 2024 | BP-2024-25-233 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
2415 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of June 2024 | BP-2024-25-232 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
2416 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R. W.S Sub-Division P.HE. Dte. for 6 month (Period from 01/08/2024 to 31/01/2025) | 709/RWS | 31/07/2024 | 184 | ASHIM SARKAR | 0.88 | 0 | 0 | 0
2417 | JALPAIGURI | Jalpaiguri Division | Chapgar Piped Water Supply Scheme. , SM/18492 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 985/JD | 14/08/2024 | 15 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
2418 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Domohani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-V) | 2008/JD | 01/11/2022 | 30 | ALOKE DEY | 40.21 | 0 | 0 | 1
2419 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Providing Functional Household Tap Connection (FHTC) with retrofitting works in connection with Jaldhara / Jal Sapna under the command area of Domohani Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, P.H.E Dte. (Phase-IV) | 939/JD | 18/04/2022 | 45 | PRADIP KR SEN | 4.85 | 0 | 0 | 1
2420 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | fhtc domohani | BP-2021-23-1 | 21/04/2022 | 0 | PRADIP KR SEN | 4.57 | 0 | 0 | 0
2421 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | DPR PREPARATION | BP-2021-22-262 | 16/02/2022 | 0 | SUBHANKAR GHOSH | 2.37 | 0 | 0 | 0
2422 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | FHTC MOGOLKATA T.G PWSS | BP-2021-22-498 | 29/03/2022 | 0 | PROFULLA GHOSH | 30.06 | 0 | 0 | 0
2423 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | LDS INDONG T.G | BP-2021-22-546 | 31/03/2022 | 0 | KANAI LAL SEN | 16.3 | 0 | 0 | 0
2424 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | SINKING REJ CHOUHADDI | BP-2021-22-545 | 31/03/2022 | 0 | J.M. CONSTRUCTION | 7 | 0 | 0 | 0
2425 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Laying Distribution System for Augmentation of Domohani Piped Water Supply Scheme at Moynaguri Block under Jalpaiguri Division, PHE Dte | 661/JD | 09/03/2022 | 90 | SUKES BASU MAJUMDAR | 335.53 | 0 | 0 | 1
2426 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Shifting of pipeline in connection with PWD road widning work from Domohani PWSS at Moynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 975/JD | 20/04/2022 | 45 | PROVA CONSTRUCTION | 38.07 | 0 | 0 | 0
2427 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Renovation of front side boundary wall and construction of shade over front door of the pump house and ancillary works of the 2nd tube well site of Domohani Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | 1803/JD | 14/09/2022 | 21 | M/S SURAJIT DEY AND CO. | 2.41 | 0 | 0 | 0
2428 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Construction of Pump (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement at 3rd tube well site of Augmentation Domohoni W/S Scheme under Jalpaiguri Division , P.H.E Dte. | 1193/JD | 20/05/2022 | 45 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.65 | 0 | 0 | 100
2429 | JALPAIGURI | Central Drilling | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 123 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DOMOHANI PWSS, JALPAIGURI DISTRICT, CDD, PHE DTE. | 1775/CDD | 02/01/2023 | 30 | PADMA ENGINEERING & CO. | 11.99 | 0 | 0 | 0
2430 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Material Requisition To Resource Division | 54/JD | 05/01/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
2431 | JALPAIGURI | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Infrastructure Cost for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084156, Reference ID : 860276006] | BP/23-24/68 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.96 | 0 | 0 | 0
2432 | JALPAIGURI | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | New Service Connection Charge for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003107329, Reference ID : 402974759] | BP/23-24/68 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2433 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Domohani piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 1066/JD | 02/07/2021 | 21 | PRADIP KR SEN | 4.82 | 0 | 0 | 0
2434 | JALPAIGURI | Northern Mechanical | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of DOMOHANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 266/NMD | 21/03/2023 | 30 | HARAGOURI ENTERPRISE | 10.12 | 0 | 0 | 50
2435 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Construction of Boundary wall, Blower Room, IEP of 3rd Pump House & Providing FHTC of Domohani PWSS, in connection with Augmentation of Domohani PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 1554/JD | 01/11/2023 | 60 | B.M CONSTRUCTION | 67.78 | 0 | 0 | 100
2436 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Rejuvenation of different components of Head Work Site of Domohani PWSS under Jalpaiguri Division, PHE Dte. | 1972/JD | 03/01/2024 | 45 | SUKES BASU MAJUMDAR | 39.34 | 0 | 0 | 100
2437 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Engagement of Block Level Staff (Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Maynaguri block in Connection with JJM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. (2nd Call) | 256/RWS | 07/03/2024 | 30 | B.M CONSTRUCTION | 3.11 | 0 | 0 | 100
2438 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Material Requisition To Resource Division | 2099/JD | 25/11/2024 | 0 | Resource Division | 80.22 | 0 | 0 | 0
2439 | JALPAIGURI | Central Drilling | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | 244/S&WSD | 30/12/2024 | 184 | NEMAI CHANDRA NAIYA | 0.87 | 0 | 0 | 0
2440 | JALPAIGURI | Jalpaiguri Division | Augmentation of Domohani Piped Water Supply Scheme , SM/09345 | Augmentation | Sinking of One No. tube Well (250mm x 200mm) by Reverse Rotary Method of Drilling and others components for boosting in Augmentation of Domohoni Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2629/JD | 07/03/2024 | 782 | M/S PRAFULLA GHOSH | 52.42 | 0 | 0 | 50
2441 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2627/JD | 07/03/2024 | 45 | SWAPAN SAHA | 23.15 | 0 | 0 | 0
2442 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | 2498/JD | 28/02/2024 | 45 | M/S BOSE ENTERPRISE | 22.62 | 0 | 0 | 0
2443 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 151/RWS | 15/02/2024 | 30 | DEBABRATA SARKAR | 6.97 | 0 | 0 | 100
2444 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | 150/RWS | 15/02/2024 | 30 | SOUVIK SAHA | 7.24 | 0 | 0 | 100
2445 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of Boundary Wall, Foot Path, Drain, pipeline for washout at 2nd Tubewell site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. (2nd Call) | 257/RWS | 07/03/2024 | 30 | UCO LABOUR CO-OPERATIVE SOCIETY LTD. | 7.24 | 0 | 0 | 100
2446 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Material Requisition To Resource Division | 51/JD | 09/04/2024 | 0 | Resource Division | 64.27 | 0 | 0 | 0
2447 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Material Requisition To Resource Division | 2036/JD | 09/01/2024 | 0 | Resource Division | 37.59 | 0 | 0 | 0
2448 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003356521 Reference ID : 403175893 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.98 | 0 | 0 | 0
2449 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Supply mobil to vehicle no WB 71 A 5774 | BP-2024-25-271 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0 | 0
2450 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of May 2024 | BP-2024-25-191 | 08/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
2451 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305811 ; Reference ID : 403134435] | BP/23-24/292 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
2452 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305806 ; Reference ID : 403134432] | BP/23-24/291 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.26 | 0 | 0 | 0
2453 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2454 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305829 ; Reference ID : 403134442] | BP/23-24/295 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.59 | 0 | 0 | 0
2455 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305819 ; Reference ID : 403134444] | BP/23-24/293 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
2456 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003356527 Reference ID : 403175900 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.3 | 0 | 0 | 0
2457 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of different components of Saptibari (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 1350/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 571.97 | 0 | 0 | 90
2458 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Construction of different components of Saptibari (Zone-III) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | 1352/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 432.29 | 0 | 0 | 79
2459 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Balance Work of Distribution System for Saptibari Zone- II Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | 987/JD | 14/08/2024 | 360 | MONOJ GHOSH | 59.77 | 0 | 0 | 85
2460 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Balance Work of Distribution System for Saptibari Zone- III Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | 1534/JD | 01/10/2024 | 243 | KAMALESH SEN | 52.66 | 0 | 0 | 90
2461 | JALPAIGURI | Jalpaiguri Division | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Balance Work of Distribution System for Saptibari Zone-I Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | 486/JD | 11/03/2025 | 120 | DIPAK KUMAR CHAKRABORTY | 71.83 | 0 | 0 | 0
2462 | JALPAIGURI | Northern Mechanical | Saptibari Piped Water Supply Scheme. , SM/18759 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAPTIBARI PWSS, ZONE-I,II,III AT TW NO I,II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 1553/NMD | 04/09/2023 | 575 | EASTERN INDIA SALES & SERVICE | 67.81 | 0 | 0 | 100
2463 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 744/JD | 13/05/2021 | 30 | KAMALESH SEN | 23.73 | 0 | 0 | 1
2464 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-IV. | 1257/JD | 10/08/2021 | 15 | ALICK DUTTA | 4.81 | 0 | 0 | 1
2465 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 1337/JD | 23/08/2021 | 30 | DULAL CHOUDHURY | 30.23 | 0 | 0 | 0
2466 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 1065/JD | 02/07/2021 | 21 | GANAPATI CO-OP LABOUR CONT. & CONST. SOCIETY LTD. | 4.83 | 0 | 0 | 1
2467 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- V) | 1444/JD | 09/09/2021 | 30 | ALOKE DEY | 30.23 | 0 | 0 | 1
2468 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | fhtc madhyakhuttimari | BP-2021-22-107 | 16/11/2021 | 0 | KAMALESH SEN | 11.92 | 0 | 0 | 0
2469 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | fhtc madhya khuttimari pwss | BP-2021-22-106 | 16/11/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0 | 0
2470 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | FHTC MADHYAKHUTTIMARI PWSS |  | 29/10/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0 | 0
2471 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block , SM/08078 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 746/JD | 13/05/2021 | 20 | RABINDRANATH DUTTA | 13.97 | 0 | 0 | 1
2472 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-D) | 1279/JD | 18/11/2020 | 30 | NEW KUNDU ENTERPRISE | 14.38 | 0 | 0 | 1
2473 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-C) | 1278/JD | 18/11/2020 | 60 | SANDIP BANIK | 28.51 | 0 | 0 | 1
2474 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | PROVIDING FHTC FOR AMBARI T.G PWSS | 1077 | 14/01/2021 | 0 | SAHA CONSTRUCTION | 4.03 | 0 | 0 | 0
2475 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | PROVIDING FHTC AT AMBARI T.G PWSS | 1123 | 22/01/2021 | 0 | SANDIP BANIK | 28.5 | 0 | 0 | 0
2476 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | PRIVIDING FHTC AT AMBARI T.G PWWSS | 919 | 04/01/2021 | 0 | SANDIP BANIK | 4.21 | 0 | 0 | 0
2477 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | LDS FOR PURBA DURAMARI PWSS | 08 | 07/05/2021 | 0 | SANJIT SAHA | 8.91 | 0 | 0 | 0
2478 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | RETROFITTING WORK & OTHER ANCILLARY WORK RELATED FHTC FOR AMBARI T.G PWSS | 1589 | 21/03/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0 | 0
2479 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | Providing FHTC Ambari TG Part D | 1124 | 22/01/2021 | 0 | NEW KUNDU ENTERPRISE | 11.95 | 0 | 0 | 0
2480 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | Retrofitting works & other ancillary works related to FHTC at different places of Ambari TG PWSS.under Jalpaiguri Division P.H.E. Dte. | 1589 | 23/04/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0 | 0
2481 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme , SM/06837 | Retrofitting | FHTC SADAR BLOCK ZONE II | BP-2021-22- 412 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.92 | 0 | 0 | 0
2482 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of BOALMARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | 1105/JD | 20/10/2020 | 90 | UMWEL ENGINEER PRIVATE LIMITED | 39.23 | 5.96 | 15.2 | 1
2483 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Boalmari Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | 475/RWS | 15/10/2020 | 30 | KABYA ENTERPRISE | 4.7 | 0 | 0 | 1
2484 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | FHTC BOALMARI |  | 01/10/2021 | 0 | KANAI LAL SEN | 22.04 | 0 | 0 | 0
2485 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Retrofitting Boalmari WSS |  | 26/10/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0 | 0
2486 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Providing house connection under Boalmari Water Supply Scheme at Sadar Block under Jalpaiguri Division P.H.E.Dte. | 296/RWS | 20/04/2021 | 15 | DEBABRATA GHOSH | 4.44 | 0 | 0 | 0
2487 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Providing functional household tap connection (FHTC) with Jalsapna including Retrofitting works under the command area of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte.(Part ¿ F) | 182/RWS | 04/03/2022 | 15 | KANAI LAL SEN | 4.51 | 0 | 0 | 0
2488 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme , SM/06838 | Retrofitting | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri.(3rd Call) | 971/RWS | 18/08/2023 | 200 | KANAI LAL SEN | 3.13 | 0 | 0 | 100
2489 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 30.12 | 100 | 1
2490 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Providing Functional House hold tap Connection (FHTC)in connection with Jaldhara/ Jalsapna a t Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ H) | 685/RWS | 27/09/2021 | 15 | NARAYAN CHAKRABORTY | 4.25 | 0 | 0 | 1
2491 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Providing Functional House hold tap Connection(FHTC) In connection with Jaldhara/ Jalsapna at Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) | 683/RWS | 27/09/2021 | 15 | BISWAJIT BHADURI | 3.4 | 0 | 0 | 1
2492 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Reparing & renovation of Boundary wall, approach At H/W site for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte | 699/RWS | 27/09/2021 | 30 | ASIT PAUL | 4.84 | 0 | 0 | 1
2493 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 6.58 | 100 | 1
2494 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Retrofitting works related to FHTC at Kamar para, Taltala line , Purba Madati para, Purba Kamar Para for Argi Garalbari . W/S/S under Jalpaiguri Division , P.H.E. Dte | 817/RWS | 30/11/2021 | 10 | BISWAJIT BHADURI | 4.85 | 0 | 0 | 1
2495 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | FHTC PURBAMAGURMARI PWSS | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0 | 0
2496 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | FHTC PURBAMAGUR MARI PWSS | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0 | 0
2497 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | FHTC NAYASAILYA T.G PWSS | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0 | 0
2498 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | FHTC ENGO T.G PWSS | BP-2021-22-464 | 27/03/2022 | 0 | NABIN PRODHAN | 2.26 | 0 | 0 | 0
2499 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme , SM/06840 | Retrofitting | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement of Rejuvenation Garalbari . W/S/S ( zone - I ) 3rd T/W site under Jalpaiguri Division , P.H.E. Dte. | 869/RWS | 08/12/2021 | 30 | ABHIJIT SARKAR | 4.65 | 0 | 0 | 0
2500 | JALPAIGURI | Jalpaiguri Division | Funtional Household Tap Connection (FHTC) under Jaldhara Jal Sapna under command area of Red Bank Garden Piped Water Supply Scheme , SM/06843 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retroftting of existing LDS under the command area of Red Bank Tea Garden area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- II) | 1295/JD | 23/11/2020 | 90 | M/S R.N. TRADERS | 39.75 | 0 | 0 | 1
2501 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | RETROFITTING WORK RELATED FHTC FOR BOALMARI PWSS | 1563 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.21 | 0 | 0 | 0
2502 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | providing fhtc for maynatali pwss | 357/21-22 | 16/09/2021 | 0 | SANJIT SAHA | 19.92 | 0 | 0 | 0
2503 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | LDS FOR D-SHALBARI PWSS | 336/21-22 | 04/10/2021 | 0 | ROY & SARKAR CONSTRUCTION | 5.85 | 0 | 0 | 0
2504 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | RETROFITTING WORK AT BOALMARI PWSS | 1564 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.34 | 0 | 0 | 0
2505 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 12.25 | 100 | 0
2506 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/06844 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NGAISUREE T.G. Area piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte.(Phase-II). | 1273/JD | 18/11/2020 | 1625 | SADHAN KARMAKAR | 43.64 | 0 | 0 | 100
2507 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC SATHKAYA TG PWSS |  | 04/10/2021 | 0 | LOKNATH CONSTRUCTION | 22.44 | 0 | 0 | 0
2508 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC CHALAUNI | BP-2021-22-240 | 22/02/2022 | 0 | BILTU DAS | 10.56 | 0 | 0 | 0
2509 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC JABRAMALI | BP-2021-22-332 | 28/02/2022 | 0 | SUKES BASU MAJUMDAR | 12.67 | 0 | 0 | 0
2510 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC BHANGARHAT PWSS | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0 | 0
2511 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC DAKSHIN SALBARI PWSS | BP-2021-22-402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0 | 0
2512 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC MOHIT NAGAR | BP-2021-22-252 | 16/02/2022 | 0 | ANUP KUMAR KUNDU | 20.15 | 0 | 0 | 0
2513 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC DAKSHIN SALBARI PWSS | BP-2021-22402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0 | 0
2514 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | fhtc matiali bazar | BP-2021-22-233 | 23/02/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.39 | 0 | 0 | 0
2515 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC MOHIT NAGAR PWSS | BP-2021-22-550 | 31/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.24 | 0 | 0 | 0
2516 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC MOHITNAGAR | BP-2022-2023-41 | 24/05/2022 | 0 | M/S DEY & ROY CHOUDHURY | 7.1 | 0 | 0 | 0
2517 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC DABGRAM-II | BP-2021-22-410 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 52.17 | 0 | 0 | 0
2518 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | FHTC BATABARI T.G | BP-2021-22-264 | 22/02/2022 | 0 | PRIYABRATA KARMAKAR | 7.52 | 0 | 0 | 0
2519 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | NH Road(4 Lane) crossing through underpass at Assam More .i.c.w. FHTC of Mohit Nagar W/S Scheme under Jalpaiguri Division P.H.E. Dte. | 646/RWS | 21/10/2022 | 30 | M/S DEY & ROY CHOUDHURY | 3.86 | 0 | 0 | 0
2520 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Sebagram In connection with Jaldhara/ Jal Sapna under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) | 1081/RWS | 19/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 6.68 | 0 | 0 | 100
2521 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mahitnagar Piped Water Supply Scheme at Jalpaiguri Block , SM/08037 | Retrofitting | Thorough repairing and overhauling of the Iron Elimination Plant (double Unit) at Mohitnagar Water Supply Scheme (H/W Site), under Jalpaiguri Division P.H.E. Dte. | 1083/RWS | 19/09/2023 | 15 | M/S DEY & ROY CHOUDHURY | 5.41 | 0 | 0 | 100
2522 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 566/JSSD | 01/02/2021 | 15 | ALICK DUTTA | 4.61 | 0 | 0 | 0
2523 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 1547/JD | 31/12/2020 | 75 | SCEC BOENTER KDAS JOINT VENTURE | 42.4 | 19.16 | 45.19 | 0
2524 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06955 | Retrofitting | RETROFITTING WORK FOR FHTC FOR JABRAMALI PWSS | 124/21-22 | 07/07/2021 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 13.89 | 0 | 0 | 0
2525 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block , SM/06955 | Retrofitting | ADD BILL | 536/21-22 | 17/11/2021 | 0 | GENESIS ADVERTISING PVT LTD | 2.89 | 0 | 0 | 0
2526 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Providing Functional Household Tap Connection in connection with Jal Swapna under the command area of Sajnapara Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | 1801/JD | 14/09/2022 | 21 | RAGHU DAS | 4.37 | 0 | 0 | 1
2527 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sajnapara P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 97/JD | 10/01/2022 | 60 | DEEP CONSTRUCTION | 4.65 | 0 | 0 | 0
2528 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | New Service Connection Charge for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147721, Reference ID : 403014075] | BP/23-24/15 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2529 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Infrastructure Cost for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077914, Reference ID : 860269054] | BP/23-24/15 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.52 | 0 | 0 | 0
2530 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | New Service Connection Charge for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] |  | 04/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2531 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Infrastructure Cost for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076670, Reference ID : 860268400] |  | 04/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0 | 0
2532 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAJNAPARA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 371/NMD | 29/03/2023 | 30 | M/S MATRI CONSTRUCTION | 11.25 | 0 | 0 | 100
2533 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Fuel ,Lubricant ,Gear Oil & steering oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0063/2023-2024 , Dt. 31.10.2023 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.24 | 0 | 0 | 0
2534 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | fuel Charges for Government Inspection Vehicle under NMD PHE Dte. Invoice No- 0033/2023-24 ,Dt. 1.07.2023 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.06 | 0 | 0 | 0
2535 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Fuel, Lubricant & coolant charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 00047/2023-2024 , Dt. 31.08.2023 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.21 | 0 | 0 | 0
2536 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Fuel & Lubricant oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0069/2023-2024 , Dt. 30.11.2023 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.32 | 0 | 0 | 0
2537 | JALPAIGURI | Northern Mechanical | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2538 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Sajnapara Piped Water Supply Scheme , SM/09391 | Augmentation | Sinking of five nos Tube Well by Odex- 165 method of drilling at different Tube Well site in connection with jal jeevan mission under Augmentation/Rejuvenation of Kathalguri TG PWSS (Two Nos), Devpara TG PWSS (One No), Banarhat Bazar PWSS (One No), Sajna Para PWSS (One No) under Jalpaiguri Division, P.H.E. Dte. | 1520/JD | 16/10/2023 | 562 | ROY ENGINEERS | 41.28 | 0 | 0 | 100
2539 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply, delivery & installation of 30 KVA Servo Motor operated Copper wound line voltage corrector Chakiabhita W/S Scheme, TW No. I in the dist. of Jalpaiguri under NMD PHE Dte. | 1905/NMD | 07/01/2021 | 30 | MAA DURGA CONCERN | 3.03 | 0 | 0 | 0
2540 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | 453/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 0 | 0 | 1
2541 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | 452/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 0 | 0 | 1
2542 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Infrustructure cost for New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054735,Reference ID : 402843365 | BP/2022-23/31 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0 | 0
2543 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | RETROFITTING WORKS SAMSING T.G | BP-2021-22-518 | 30/03/2022 | 0 | SUJAN LAMA | 11.66 | 0 | 0 | 0
2544 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951612,Reference ID : 860244515 | BP/2022-23/31 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2545 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 143/JD | 18/01/2022 | 60 | PRIYABRATA KARMAKAR | 4.65 | 0 | 0 | 0
2546 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0 | 0 | 1
2547 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0 | 0 | 0
2548 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 131/JD | 14/01/2022 | 60 | SUKUMAR KUNDU | 4.65 | 0 | 0 | 100
2549 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAKIABHITA (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 99/NMD | 03/02/2023 | 21 | CHOWDHURY AND BASU ENTERPRISE | 2.52 | 0 | 0 | 100
2550 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | New Service Connection Charge for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135861 ; Reference ID : 403001371] | BP/23-24/06 | 03/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0 | 0
2551 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply of fuel against vehicle WB-71B-3112 under Assistant Engineer Jalpaiguri Sadar Sub-Division PHE Dte for the month April 2023 | BP-2023-24-116 | 01/06/2023 | 0 | FILL & SMILE | 0.26 | 0 | 0 | 0
2552 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Infrastructure Cost for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076456 ; Reference ID : 860267596] | BP/23-24/06 | 03/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0 | 0
2553 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAKIABHITA (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1121/NMD | 12/09/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 7.95 | 0 | 0 | 100
2554 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHAKIABHITA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 52/NMD | 24/01/2023 | 30 | M/S B.ENTERPRISE | 11.67 | 0 | 0 | 100
2555 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2306/JD | 07/02/2024 | 30 | SUKUMAR KUNDU | 8.82 | 0 | 0 | 100
2556 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2307/JD | 07/02/2024 | 30 | PRIYABRATA KARMAKAR | 9.03 | 0 | 0 | 100
2557 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chakiavita Piped Water Supply Scheme , SM/09482 | Augmentation | Supplying, Erecting, Installation and Commissioning of Iron Elimination Plant (I.E.P.) (15 cum 2 Unit) at 3rd site and 4th site of Chakiavita Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division PHE Dte. | 1776/JD | 08/12/2023 | 437 | SANDIP BANIK | 25.78 | 0 | 0 | 100
2558 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) at Indong T.G. Area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1068/JSSD | 25/01/2022 | 20 | MOYTEC | 2.02 | 0 | 0 | 0
2559 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Sinking of Two No. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method, at Indong TG area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 1313/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 0 | 0
2560 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Soil investigation work for 200 CUM Over head reservoir (OHR) at Indong TG |  | 27/09/2022 | 0 | MOYTEC | 1.01 | 0 | 0 | 0
2561 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964293, Reference ID :402851944] | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2562 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964298, Reference ID :402851947] | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2563 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059407, Reference ID : 860248997] | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0 | 0
2564 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059409, Reference ID : 860248999] | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0 | 0
2565 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Construction of Pump House (3.60m x 2.40m) size with Sanitary & Plumbing arrangement at 2nd Tube well site for Indong T.G. area of P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1043/JSSD | 24/01/2022 | 45 | ABHISEK KUNDU | 4.63 | 0 | 0 | 0
2566 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Construction of boundary wall with gate, drain and pathway for 2nd tubewell site of Indong Tea Garden Area piped water supply scheme under Jalpaiguri Division P.H.E. Dte. | 1039/JSSD | 21/01/2022 | 20 | BISWAJIT MANDAL | 3.76 | 0 | 0 | 0
2567 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement at Head Works Site for Indong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 856/JD | 01/04/2022 | 60 | SUJOY CHOWDHURY | 5.61 | 0 | 0 | 0
2568 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 77/NMD | 27/01/2023 | 30 | B.B. CONCERNED | 10.86 | 0 | 0 | 100
2569 | JALPAIGURI | Northern Mechanical | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 78/NMD | 27/01/2023 | 30 | ALPHA ENTERPRISE | 10.86 | 0 | 0 | 100
2570 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Material Requisition To Resource Division | 1064/JD | 28/04/2022 | 0 | Resource Division | 37.54 | 0 | 0 | 0
2571 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Material Requisition To Resource Division | 175/JD | 28/04/2023 | 0 | Resource Division | 14.68 | 0 | 0 | 0
2572 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Laying distribution system (Phase - II) & Rising Main for Ingdong Tea Garden piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. | 705/JD | 13/07/2023 | 21 | KANAI LAL SEN | 21.42 | 0 | 0 | 100
2573 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Construction of 200 Cum OHR as per Departmental Design & Drawing for INDONG Tea Garden Area Piped Water Supply Scheme Block : Matiali District- Jalpaiguri. | 472/JD | 21/02/2022 | 180 | M/S SIBU DEY AND CO. | 54.95 | 0 | 0 | 100
2574 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Material Requisition To Resource Division | 2065/JD | 10/01/2024 | 0 | Resource Division | 7.61 | 0 | 0 | 0
2575 | JALPAIGURI | Jalpaiguri Division | Indong Tea Garden Area Piped Water Supply Scheme. , SM/08873 | New | Laying distribution system including Providing Functional Household Tap Connection in connection with Jal Swapna for Indong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. | 690/JD | 15/03/2022 | 1236 | KANAI LAL SEN | 112.93 | 0 | 0 | 90
2576 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-III) | 570/JSSD | 01/02/2021 | 15 | ARUP SARKAR | 4.39 | 0 | 0 | 0
2577 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of MATHACHULKA T.G Area piped Water Supply Scheme at Matially Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | 654/JSSD | 25/02/2021 | 15 | DEEP CONSTRUCTION | 4.69 | 0 | 0 | 0
2578 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household Tap Connection(FHTC) in connection with Jaldhara/Jal Swapna under Command area of Mathachulka Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,PHE Dte(Phase-I) | 510/JSSD | 03/11/2021 | 15 | DEEP CONSTRUCTION | 4.65 | 0 | 0 | 0
2579 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 453JSSD | 30/12/2020 | 15 | DEEP CONSTRUCTION | 4.6 | 0 | 0 | 0
2580 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA pipe water Supply schme at Matialy Block under Jalpaiguri Division, P.H.E Dte.(Phase-IX) | 76/JSSD | 22/07/2022 | 15 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.84 | 0 | 0 | 0
2581 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA (Gobra Busty & Salbari Part) at Mathachulka pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. | 163/JSSD | 24/08/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.78 | 0 | 0 | 0
2582 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka (Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase-VIII) | .1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 0 | 0 | 0
2583 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka ( Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase - VIII) | 1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 0 | 0 | 0
2584 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Retrofitting works related to Functional Household Tap Connection(FHTC) inconnection with JJM/Jalswapna under command area of MATHACHULKA (GOBRABUSTY,UPORDHARA areas) pipe water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. | 93/JSSD | 22/07/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 3.61 | 0 | 0 | 0
2585 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Mathachulka Tea Garden Piped Water Supply Scheme at Metiali Block , SM/08284 | Retrofitting | Construction of valve and valve Chamber at different location under command area of MATHACHULKA pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. | 96/JSSD | 22/07/2022 | 30 | DEEP CONSTRUCTION | 1.97 | 0 | 0 | 0
2586 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | FHTC GRASSMORE T.G PWSS | BP-2021-22-469 | 28/03/2022 | 0 | SWAPAN SAHA | 9.59 | 0 | 0 | 0
2587 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | FHTC MALLICKSOVA PWSS | BP-2021-22-466 | 27/03/2022 | 0 | BOSE ENTERPRISE | 65.35 | 0 | 0 | 0
2588 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) | 193/JD | 21/01/2022 | 60 | BOSE ENTERPRISE | 172.88 | 0 | 0 | 1
2589 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | 882/JD | 05/04/2022 | 60 | M/S NANDY ENTERPRISE | 182.16 | 0 | 0 | 0
2590 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 0 | 0 | 100
2591 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Partial Retrofitting work for Riabari T.G.Area with repairing of rising main, including damaged/Chokage line repairing due to local developmnet works, direct Pumping arrangement from 2nd pump within the command area of Riabari T.G. P.W.S.S. under Jalsapna programme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | 1742/JD | 08/09/2022 | 21 | SAPTASWA SARKAR | 15.65 | 0 | 0 | 1
2592 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 0 | 0 | 0
2593 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Material Requisition To Resource Division | 180/JD | 21/01/2022 | 0 | Resource Division | 2.99 | 0 | 0 | 0
2594 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Mallicksova piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. , SM/09100 | Retrofitting | Material Requisition To Resource Division | 2206/JD | 01/12/2024 | 0 | Resource Division | 26.77 | 0 | 0 | 0
2595 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of KAJALDIGHI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 268/NMD | 21/03/2023 | 30 | INDTECH ASSOCIATES | 21.38 | 0 | 0 | 0
2596 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Sinking of 250mm x 150mm dia Two nos tube well by Reverse Rotary method of drilling for Augmentation at 3rd & 4th Tube well site of Kajaldighi PWSS within Maynaguri Block under PHE Dte. Jalpaiguri Division. | 850/JD | 06/04/2023 | 45 | M/S S. G. ENTERPRISE | 16.86 | 0 | 0 | 100
2597 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164175, Reference ID : 403024433] | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2598 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084435, Reference ID : 860276015] | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0 | 0
2599 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084436, Reference ID : 860276016] | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0 | 0
2600 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164171, Reference ID : 403024432] | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2601 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. | 1562/JD | 08/08/2022 | 936 | DEBASISH DEY | 13.78 | 0 | 0 | 80
2602 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2215/JD | 27/12/2021 | 60 | M/S TRINATH CONSTRUCTION AND CO. | 11.44 | 0 | 0 | 100
2603 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2214/JD | 27/12/2021 | 60 | SUBIR GHOSH | 11.45 | 0 | 0 | 100
2604 | JALPAIGURI | Northern Mechanical | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of KAJALDIGI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1060/HQ/NMD | 21/06/2024 | 7 | SARKAR ELECTRIC | 0.75 | 0 | 0 | 100
2605 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline at Kajaldighi Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 476/RWS | 29/05/2025 | 30 | M/S TRINATH CONSTRUCTION AND CO. | 4.03 | 0 | 0 | 0
2606 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Construction of approach Road for 3rd & 4th site for Kajaldighi Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 477/RWS | 29/05/2025 | 30 | M/S S. G. ENTERPRISE | 0.5 | 0 | 0 | 0
2607 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kajaldighi piped water supply scheme. , SM/09457 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. | 1740/JD | 08/09/2022 | 997 | SAHA CONSTRUCTION | 14.44 | 0 | 0 | 100
2608 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Replacing Old Damaged Pipeline With Laying New UPVC Pipeline Due To Construction of Rural Road at Angravasa Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 56 /JSSD | 12/05/2021 | 30 | ROY & SARKAR CONSTRUCTION | 3.76 | 0 | 0 | 1
2609 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Continuation Work order for the work of Annual Maintenance of pipe line and other misc. work related to pipe line including maintenance of I.E.Plant (if any)for Angravasa T.G. PWSS under Jalpaiguri Division, P.H.E Dte. period from 15/07/2021 to 31/12/2021. | 162 /JSSD | 15/07/2021 | 170 | ROY & SARKAR CONSTRUCTION | 2.23 | 0 | 0 | 1
2610 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Soil investigation work for 200 Cum over head Reservoir (OHR)for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. | 1183/W/JSSD | 08/03/2022 | 20 | G MITRA & ASSOCIATES | 2 | 0 | 0 | 0
2611 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Material Requisition To Resource Division | 555/JD | 01/03/2022 | 0 | Resource Division | 52.27 | 0 | 0 | 0
2612 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | New Service Connection Charge for PUMP HOUSE IN ANGRABHASA w/s scheme under BANARHAT CCC, [APPLICATION NO. 4002813842, Reference ID : 422058156] | BP/23-24/32 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0 | 0
2613 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Construction of Pump House (3.60 m x2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division. | 1242/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 0 | 0 | 0
2614 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1262/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.8 | 0 | 0 | 0
2615 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Angrabhasa Piped Water Supply Scheme Block- Dhupguri, District - Jalpaiguri. | 1554/JD | 05/08/2022 | 1336 | SWAPAN SAHA | 54.69 | 0 | 0 | 100
2616 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Laying Rising Main for Augmenmtation of Angrabhasa piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 798/JD.. | 29/03/2023 | 14 | M/S ROY & SARKAR CONSTRUCTION | 6.39 | 0 | 0 | 70
2617 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Sinking of 1 No. 250 mm x 200 mm x 147 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for the Augmentation of Angrabhasa piped water supply scheme under Jalpaiguri Division P.H.E. Dte. | 840/JD | 31/03/2022 | 21 | MALAY BHOWMIK | 8.83 | 0 | 0 | 100
2618 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | New Service Connection Charge for ANGRABHASA, T/W No.III, under BANARHAT CCC, [APPLICATION NO. 4003323154, Reference ID : 403149195] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.34 | 0 | 0 | 0
2619 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Laying of dedicated pipeline along with commissioning of Augmentation of Angrabhasa Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. | 99/JSSD | 30/05/2025 | 30 | RAGHU DAS | 12.42 | 0 | 0 | 0
2620 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 878/JD | 05/04/2022 | 1368 | M/S R.N. TRADERS | 282.14 | 0 | 0 | 1
2621 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Construction of boundary wall with gate, drain and pathway for 3rd tubewell Site for Augmentation of Angrabhasa PWSS, under Jalpaiguri Division, P.H.E. Dte. | .99/JSSD | 22/07/2022 | 864 | CHANDAN GHOSH | 4.78 | 0 | 0 | 100
2622 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF ANGRABHASA PIPED WATER SUPPLY SCHEME. , SM/10071 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ANGRABHASA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 363/NMD | 29/03/2023 | 690 | M/S ROYAL ENTERPRISE | 10.1 | 0 | 0 | 100
2623 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Repairing of 2 nos of Pump House (1st site & 2nd site ), 2Nos boundary wall (1st site & 2nd site) and other Allied works at Jiti TG Piped Water Supply Scheme under Jalpaiguri Division .P.H.E. Dte. | 90/JSSD | 22/07/2022 | 15 | SOUVIK SAHA | 4.7 | 0 | 0 | 0
2624 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | SINKING 250MX150 MM DIA PURBASALBARI PWSS | BP-2021-22- 470 | 28/03/2022 | 0 | ABHIJIT SARKAR | 7.92 | 0 | 0 | 0
2625 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | lds jabarmali pwss | BP-2021-22-170 | 29/09/2022 | 0 | BOSE ENTERPRISE | 2.43 | 0 | 0 | 0
2626 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | RETROFITTING WORKS BHANGARHAT PWSS | BP-2021-22-500 | 29/03/2022 | 0 | MRINMOY KANTI DUTTA | 1.55 | 0 | 0 | 0
2627 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Sinking of Tow Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Jiti Tea Garden under Jalpaiguri Division, P.H.E. Dte. | 1222/JD | 31/05/2022 | 30 | M/S BABUN BISWAS | 13.84 | 0 | 0 | 0
2628 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of JITI pipe water supply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E Dte. | 82/JSSD | 22/07/2022 | 20 | ARUP SARKAR | 4.85 | 0 | 0 | 100
2629 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Retrofitting works and installation of valerelated to Functional Household Tap Connection(FHTC)inconnection with JJM/Jalswapna under command area of Jiti pipe watersupply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | 94/JSSD | 22/07/2022 | 30 | ARUP SARKAR | 3.25 | 0 | 0 | 100
2630 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Material Requisition To Resource Division | 1374/JD | 27/09/2023 | 0 | Resource Division | 9.21 | 0 | 0 | 0
2631 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Construction of Pump House (3.60 M x 2.40 M) size with sanitary & Plumbing arrangement at 3rd Tube well site for Jiti T.G. PWSS under Jalpaiguri Division, | 1055/JSSD | 24/01/2022 | 45 | ADWIJA CONSTRUCTION | 4.64 | 0 | 0 | 100
2632 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Construction of boundary wall with gate drain and pathway for 3rd tube well site of Jiti T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1044/JSSD | 24/01/2022 | 20 | ADWIJA CONSTRUCTION | 3.76 | 0 | 0 | 100
2633 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Sinking of 2 Nos. Big dia Tube Well by Modified DTH-ODEX method at 3rd & 4th tube well site in connection with Jal Jeevan Mission of JITI Tea Garden piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1356/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 32.57 | 0 | 0 | 100
2634 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 100000099256 ; Reference ID : 860291236] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0 | 0
2635 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 4003330215 ; Reference ID : 403155155] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2636 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | New Service Connection Charge for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 403330231 ; Reference ID : 403155154] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2637 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 100000099255 ; Reference ID : 860291235] | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.56 | 0 | 0 | 0
2638 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Laying Rising Main for Rejuvenation of Jiti Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 801/JD.. | 29/03/2023 | 914 | KSMC CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION | 2.48 | 0 | 0 | 100
2639 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
2640 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of Jiti Tea Garden Mouza , SM/09865 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JITI T.G. PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 367/NMD | 29/03/2023 | 690 | MIHIR SARKAR | 25.02 | 0 | 0 | 90
2641 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1232/JD | 02/06/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 0 | 0 | 1
2642 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 2nd tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1218/JD | 26/05/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 0 | 0 | 1
2643 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 4002966831, Reference ID :402856022] | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2644 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 4002969971, Reference ID :402856021] | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2645 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 100000056975, Reference ID : 860246285] | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
2646 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 100000058118, Reference ID : 860247828] | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.79 | 0 | 0 | 0
2647 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with Sanitary & Plumbing arrangement at Head works site for Augmentation of Luksan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1080/JD | 29/04/2022 | 60 | MONOTOSH ROY | 5.61 | 0 | 0 | 1
2648 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- I) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 818/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 0 | 0 | 1
2649 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 817/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 0 | 0 | 1
2650 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-11) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte | 1182/W/JSSD | 08/03/2022 | 20 | M K KAYAL & ASSOCIATES | 2.02 | 0 | 0 | 0
2651 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-1) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte | 1184/W/JSSD | 08/03/2022 | 20 | MABCO CONSULTANT | 2.02 | 0 | 0 | 0
2652 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 1st tube-well site for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 1263/JSSD | 25/03/2022 | 20 | JAYA SARKAR | 4.79 | 0 | 0 | 100
2653 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 100000072620, Reference ID : 860263640] | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.27 | 0 | 0 | 0
2654 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 100000072602, Reference ID : 860263632] | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0 | 0
2655 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 4003095902, Reference ID : 402966241] | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2656 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 4003097549, Reference ID : 402966979] | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2657 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS | BP-2023-24-110 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 4.99 | 0 | 0 | 0
2658 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-II Block- Nagrakata, District - Jalpaiguri. | 735/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 55.08 | 0 | 0 | 100
2659 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Sinking of Big Dia 2nd Tube well by Modified DTH - ODEX Method at 1st tube well site of Augmentation of Luksan Bazar Piped Water Supply Scheme of (zone-I) of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 2319/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0 | 100
2660 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | -Interconnection work including FHTC with allied works at Augmentation of Looksan Bazar Piped W/S Scheme ( zone-I & III) in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E.Dte. | 267/JSSD | 25/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 2.25 | 0 | 0 | 0
2661 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Balance work in connection with Laying Rising Main for Augmentation of Luksan Bazar (Zone -I ,Zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 263/JSSD | 25/09/2024 | 99 | MONTOSH GHOSH | 2.78 | 0 | 0 | 100
2662 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Pump House (3.60 m x 2.40 m ) size with sanitary & plumbing arrangement at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme for under Jalpaiguri Division. | 1243/JSSD | 25/03/2022 | 45 | KABYA ENTERPRISE | 4.64 | 0 | 0 | 100
2663 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at Lukshan Bazar (Zone-III) for Augmentation of Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. | 1244/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 0 | 0 | 100
2664 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Lukshan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 1261/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.79 | 0 | 0 | 100
2665 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Laying Rising Main for Augmenmtation of Luksan Bazar (Zone -I ,zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 797/JD.. | 29/03/2023 | 599 | MONTOSH GHOSH | 7.71 | 0 | 0 | 100
2666 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 547/JD | 28/02/2022 | 30 | ALICK DUTTA | 21.58 | 0 | 0 | 15
2667 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Pump House (3.60m x 2.40m) size including sanitary & plumbing works at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-II) Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. | 1245/JSSD | 25/03/2022 | 45 | DEBABRATA SARKAR | 4.65 | 0 | 0 | 100
2668 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Emergent repair of damage pipe line and FHTC at Lukshan Bazar (Zone-III) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 498/JSSD | 02/01/2024 | 30 | ALICK DUTTA | 4.81 | 0 | 0 | 100
2669 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Balance work for construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement at 2nd T/W site for Augmentation of Lukshan Bazar (Zone - II) Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. | 505/JSSD | 02/01/2024 | 335 | ARUP SARKAR | 2.75 | 0 | 0 | 100
2670 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 548/JD | 28/02/2022 | 1312 | GAP ENGINEERS ENTERPRISES | 79.03 | 0 | 0 | 75
2671 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LUKSAN BAZAR PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 163/NMD | 17/02/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 41.3 | 0 | 0 | 80
2672 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Redevelopment of Boundary Wall with gate, drain and pathway for Existing tubewell (2nd site as per new drawing) site for Augmentation of Luksan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 959/JD | 09/08/2024 | 602 | ALICK DUTTA | 22.33 | 0 | 0 | 75
2673 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Construction of Boundary Wall at Head Work (OHR) site of Augmentation of Luksan Bazar (Zone-II) i.c.w. Jal Jeevan Mission at block Nagrakata in Jalpaiguri Division, PHE Dte. | 960/JD | 09/08/2024 | 601 | ALICK DUTTA | 12.36 | 0 | 0 | 0
2674 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Land development works at the Zone-II H/W Site along with pump connection and other allied works at Augmentation of Luksan Bazar Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. | 257/JSSD | 25/09/2024 | 464 | ARUP SARKAR | 2.61 | 0 | 0 | 0
2675 | JALPAIGURI | Northern Mechanical | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
2676 | JALPAIGURI | Jalpaiguri Division | AUGMENTATION OF LUKSAN BAZAR PWSS , SM/11814 | Augmentation | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar Water Supply Scheme (Zone-II). | 1315/JD | 16/06/2022 | 1021 | ANUP SARKAR | 90.22 | 0 | 0 | 100
2677 | JALPAIGURI | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | Material Requisition To Resource Division | 164/JD | 28/04/2023 | 0 | Resource Division | 13.57 | 0 | 0 | 0
2678 | JALPAIGURI | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | Material Requisition To Resource Division | 1881/JD | 20/12/2023 | 0 | Resource Division | 6.62 | 0 | 0 | 0
2679 | JALPAIGURI | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | Supply and Delivery at site of UPVC pipe of 250mm dia for tube well of Uttar Khuttimari PWSS under Jalpaiguri Division, PHE Dte. | 2456/JD | 23/02/2024 | 7 | UNIBRO INFRASERV PRIVATE LIMITED | 2.46 | 0 | 0 | 0
2680 | JALPAIGURI | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356873, Reference ID : 403176987] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
2681 | JALPAIGURI | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 100000101600, Reference ID : 860292660] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3 | 0 | 0 | 0
2682 | JALPAIGURI | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101602, Reference ID : 860292662] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0 | 0
2683 | JALPAIGURI | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 4003356966, Reference ID : 403176985] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
2684 | JALPAIGURI | Jalpaiguri Division | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | Providing Balance Functional Household Tap Connection (FHTC) in the command area of Uttar Kuttimari PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 485/JD | 11/03/2025 | 25 | KABYA ENTERPRISE | 12.58 | 0 | 0 | 0
2685 | JALPAIGURI | Northern Mechanical | UTTAR KHUTTIMARI PIPED WATER SUPPLY SCHEME , SM/14660 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR KHUTTIMARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 464/NMD | 25/04/2023 | 798 | MALAY KUMAR SAHA | 22.13 | 0 | 0 | 100
2686 | JALPAIGURI | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Material Requisition To Resource Division | 147/JD | 28/04/2023 | 0 | Resource Division | 32.33 | 0 | 0 | 0
2687 | JALPAIGURI | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Material Requisition To Resource Division | 1828/JD | 15/12/2023 | 0 | Resource Division | 14.29 | 0 | 0 | 0
2688 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003214185, Reference ID : 403062249] | BP/23-24/106 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.66 | 0 | 0 | 0
2689 | JALPAIGURI | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2690 | JALPAIGURI | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Construction of different components of Gairkhata Tea Garden (D) PWSS i.e. T.W. Pump House, Water Distribution Network, OHR, Rising Main,FHTC etc. In connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | 677/JD | 16/03/2023 | 455 | SUKES BASU MAJUMDAR | 448.24 | 0 | 0 | 100
2691 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAIRKHATA TEA GARDEN (D) PWSS, at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1194/NMD | 21/07/2023 | 30 | SARKAR ELECTRIC | 40.62 | 0 | 0 | 100
2692 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Additional works in connection with supply, installation and commissioning and trial operation of electromechanical accessories of W/S system at GAIRKATA W/S scheme for T.W No. -I, II & III in the dist. of Jalpaiguri. | 01/DSD | 04/01/2024 | 7 | SARKAR ELECTRIC | 0.93 | 0 | 0 | 100
2693 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Fuel, Lubricant Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007(A)/2024-2025 , Dt - 31/10/2024 Vechile no - WB73B/7824 for the month of october 2024 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.1 | 0 | 0 | 0
2694 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0006/2024-2025 , Dt - 30/09/2024 Vechile no - WGX4997 for the month of september 2024 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.2 | 0 | 0 | 0
2695 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007/2024-2025 , Dt - 31/10/2024 Vechile no - WGX4997 for the month of OCtober 2024 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.09 | 0 | 0 | 0
2696 | JALPAIGURI | Jalpaiguri Division | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Construction of Boundary Wall, Rising Main, Laying Distribution System at 3rd Tube Well Site and Providing Functional Household Tap Connection of Sajnapara around Gairkata Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, PHE Dte. | 459/JD | 11/03/2025 | 143 | ALOKE DEY | 56.41 | 0 | 0 | 20
2697 | JALPAIGURI | Northern Mechanical | GAIRKHATA TEA GARDEN (D) PIPED WATER SUPPLY SCHEME , SM/14664 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of GAIRKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 338/NMD | 29/03/2023 | 795 | M/S ROYAL ENTERPRISE | 10.24 | 0 | 0 | 100
2698 | JALPAIGURI | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Material Requisition To Resource Division | 1093/JD | 24/08/2023 | 0 | Resource Division | 27.95 | 0 | 0 | 0
2699 | JALPAIGURI | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Material Requisition To Resource Division | 1829/JD | 15/12/2023 | 0 | Resource Division | 14.72 | 0 | 0 | 0
2700 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 4003193569 ; Reference ID : 403045945] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2701 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 4003193576 ; Reference ID : 403045947] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2702 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 100000083811 ; Reference ID : 860275311] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.38 | 0 | 0 | 0
2703 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
2704 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 100000083810 ; Reference ID : 860275310] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0 | 0
2705 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 4003193581 ; Reference ID : 403045948] | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2706 | JALPAIGURI | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
2707 | JALPAIGURI | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Gendrapara Tea Garden Piped Water Supply Scheme Block - Banarhat under Jalpaiguri Division, PHE Dte. | 125/JD | 16/01/2025 | 50 | SANJIT SAHA | 56.46 | 0 | 0 | 0
2708 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
2709 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
2710 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0 | 0
2711 | JALPAIGURI | Jalpaiguri Division | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Construction of different components of Gendrapara Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Banerhat under Jalpaiguri Division | 717/JD | 20/03/2023 | 880 | ANUGRAH CONSTRUCTION PVT. LTD. | 424.78 | 0 | 0 | 60
2712 | JALPAIGURI | Northern Mechanical | GENDRAPARA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14666 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GENDRAPARA TG (D) PWSS, TW NO I, II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1254/NMD | 31/07/2023 | 428 | SUNRISE ENGINEERING CORPORATION | 36.78 | 0 | 0 | 100
2713 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Material Requisition To Resource Division | 160/JD | 28/04/2023 | 0 | Resource Division | 2.08 | 0 | 0 | 0
2714 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | New Service Connection Charge for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 4003177258 ; Reference ID : 403033825] | BP/23-24/97 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2715 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Infrastructure Cost for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 100000082756 ; Reference ID : 860274516] | BP/23-24/97 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0 | 0
2716 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Construction of Different components of Upper Tandu Forest (M) i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Nagrakata under Jalpaiguri Division, PHE Dte. | 676/JD | 16/03/2023 | 180 | NISHITH RANJAN KARMAKAR | 96 | 0 | 0 | 100
2717 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UPPER TENDU FOREST PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 364/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 12.05 | 0 | 0 | 100
2718 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Material Requisition To Resource Division | 2057/JD | 09/01/2024 | 0 | Resource Division | 2.22 | 0 | 0 | 0
2719 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
2720 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
2721 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR UPPER TENDU FOREST , SM/13989 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2722 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Construction of Hume Pipe Culvert along with approach way development at 2 nd Pump House Site of Grassmore T.G. Piped water supply Scheme under Jalpaiguri Division,P.H.E.Dte. | 1434/JD | 18/07/2022 | 15 | DEEP CONSTRUCTION | 1.18 | 0 | 0 | 1
2723 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Remaining part of Laying Distribution System (PART-C ) for Grassmore T.G. AREA P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | 1266/JD | 18/11/2020 | 60 | ASHIT KUMAR SINGHA | 61.96 | 0 | 0 | 1
2724 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Construction of different components of Rejuvenation Of Grassmore Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 413/A/JD | 07/06/2023 | 60 | JAYDEB SAHA | 30.89 | 0 | 0 | 90
2725 | JALPAIGURI | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GRASSMORE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1346/NMD | 08/08/2023 | 30 | BONANZA ENTERPRISE | 11.36 | 0 | 0 | 100
2726 | JALPAIGURI | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Infrastructure Cost for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 100000096116 ; Reference ID : 860288226] | BP/23-24/241 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.21 | 0 | 0 | 0
2727 | JALPAIGURI | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | New Service Connection Charge for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 4003285470 ; Reference ID : 403120243] | BP/23-24/240 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2728 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Direct boosting arrangement from 2 nd Pump to the Nandu more to Ghasmari Road area due to low tail end pressure along with leftout distribution system and FHTC at Grassmore T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 794/JD | 24/07/2023 | 617 | SUNIL ROY | 11.3 | 0 | 0 | 100
2729 | JALPAIGURI | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
2730 | JALPAIGURI | Northern Mechanical | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2731 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Grassmore Tea Garden Area Piped Water Supply Scheme , SM/15130 | Augmentation | Construction of Boundary wall, Footpath, Drain at Grassmore Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 2011/JD | 18/11/2024 | 30 | PRADIP SAHA | 6.96 | 0 | 0 | 100
2732 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Material Requisition To Resource Division | 1883/JD | 20/12/2023 | 0 | Resource Division | 15.62 | 0 | 0 | 0
2733 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Material Requisition To Resource Division | 1369/JD | 27/09/2023 | 0 | Resource Division | 23.28 | 0 | 0 | 0
2734 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | New Service Connection Charge for PATKATA, ZONE-III, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341668, Reference ID : 403171646] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0 | 0
2735 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2736 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | New Service Connection Charge for new service connection at PATKATA, T/W-II, ZONE-III, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003426181 Reference ID : 403231210 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0 | 0
2737 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Construction of different components of Patkata Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc In connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, P.H.E.Dte. | 398/A/JD | 06/06/2023 | 1037 | GARGO TRADERS | 434.09 | 0 | 0 | 70
2738 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1217/NMD | 26/07/2023 | 737 | MALAY KUMAR SAHA | 24.37 | 0 | 0 | 70
2739 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-III PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 117/JD | 16/01/2025 | 440 | PRADIP KUMAR SEN | 26.83 | 0 | 0 | 90
2740 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Balance Work of Distribution System for Patkata Zone- III Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | 957/JD | 09/08/2024 | 601 | JAYA SARKAR | 49.34 | 0 | 0 | 80
2741 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-III PIPED WATER SUPPLY , SM/14878 | New | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site of PATKATA ZONE - III PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 488/RWS | 29/05/2025 | 30 | PARESH CHANDRA GHOSH ROY | 5.49 | 0 | 0 | 0
2742 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme , SM/15298 | Augmentation | Material Requisition To Resource Division | 1095/JD | 24/08/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2743 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme , SM/15298 | Augmentation | Sinking of Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling for Karbala Tea Garden Pipe Water Supply Scheme in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | 1355/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.38 | 0 | 0 | 100
2744 | JALPAIGURI | Northern Mechanical | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme , SM/15298 | Augmentation | New Service Connection Charge for REJU KARBALA TEA GARDEN, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333217 , Reference ID : 403157469] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.61 | 0 | 0 | 0
2745 | JALPAIGURI | Northern Mechanical | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme , SM/15298 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KARBALA TG PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1328/NMD | 08/08/2023 | 967 | AHALYA ENGINEERING WORKS | 23.83 | 0 | 0 | 60
2746 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Karbala Tea Garden Piped Water Supply Scheme , SM/15298 | Augmentation | Construction of different components of Rejuvenation of Karbala Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | 41/JD | 13/04/2023 | 750 | MALAY BHOWMIK | 110.9 | 0 | 0 | 100
2747 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Laying of Pipe line in uncovered area including installation of Sluice Valves at different strategic point within the command area of Mogolkata T.G. P.W.S.S. at Dhupguri Block under Jalpaiguri Division. P.H.E. Dte. | 1694/JD | 06/09/2022 | 21 | DIPAK KUMAR CHAKRABORTY | 4.1 | 0 | 0 | 1
2748 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Material Requisition To Resource Division | 1099/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0 | 0
2749 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Providing FHTC including retrofitting works near Totapara Bazar for Mogalkata Piped Water Supply Scheme at Banarhat Block in under Jalpaiguri Division, PHE Dte. | 1971/JD | 03/01/2024 | 20 | JITENDRA NATH ROY | 12.57 | 0 | 0 | 100
2750 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | New Service Connection Charge for REJUVENATION OF MOGALKATA TG, T/W-III, under BANARHAT CCC APPLICATION NO. 4003374000 Reference ID : 403189743 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.02 | 0 | 0 | 0
2751 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
2752 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2753 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main, Water Distribution Network etc. of Mogalkata Tea Garden PWSS , in connection with Rejuvenation of Mogalkata Tea Garden PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | 411/A/JD | 07/06/2023 | 729 | JAYA SARKAR | 27.08 | 0 | 0 | 100
2754 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MOGALKATA TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1435/NMD | 10/08/2023 | 418 | SAIKAT SINHA | 11.5 | 0 | 0 | 100
2755 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mogalkata Tea Garden Area Piped Water Supply Scheme , SM/15075 | Augmentation | Construction of Boundary Wall, footpath, drain including Rising Main and other allied works at Mogalkata PWSS in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, PHE Dte. | 2409./JD | 20/12/2024 | 223 | JAYA SARKAR | 10.73 | 0 | 0 | 90
2756 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Providing Functional Household Tap Connection in connection with Jaldhara/Jalswapna near factory line and allied areas for Barodighi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 362/JD | 20/02/2023 | 14 | PRIYABRATA KARMAKAR | 6.38 | 0 | 0 | 1
2757 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Providing Functional Household Tap Connection (150 nos) in connection with JJM near Dipu line, Mangla line, Bhouka line and allied areas for Barodighi T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 613/JD | 09/03/2023 | 15 | PRIYABRATA KARMAKAR | 7.12 | 0 | 0 | 1
2758 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Material Requisition To Resource Division | 1089/JD | 24/08/2023 | 0 | Resource Division | 5.42 | 0 | 0 | 0
2759 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BARADIGHI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1211/NMD | 26/07/2023 | 30 | ASHWIRBAD WOOD CRAFT | 11.45 | 0 | 0 | 0
2760 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Conctruction of approach road with paver block inside the premises and outside approach, R.B.T fixing in boundary wall and inside drain at H/W site for Barodighi TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | 612/JD | 09/03/2023 | 21 | BOSE ENTERPRISE | 13.4 | 0 | 0 | 100
2761 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARADIGHI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1896/NMD | 30/11/2023 | 30 | S.P. ENTERPRISE | 11.3 | 0 | 0 | 100
2762 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | New Service Connection Charge for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 4003279994 ; Reference ID :403115813] | BP/23-24/234 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2763 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Infrastructure Cost for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 100000094585 ; Reference ID :860286265] | BP/23-24/235 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.51 | 0 | 0 | 0
2764 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0 | 0
2765 | JALPAIGURI | Northern Mechanical | Rejuvenation of Baradighi Tea Garden Area Piped Water Supply Scheme , SM/15059 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
2766 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Construction of Approach Culvert with Guard Wall at H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. | 359/JD | 20/02/2023 | 21 | M/S A.B.G. CONSTRUCTION | 2.93 | 0 | 0 | 100
2767 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Construction of G. I. line & concrete block & piller for culvert for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 802/JD | 29/03/2023 | 21 | M/S A.B.G. CONSTRUCTION | 3.02 | 0 | 0 | 100
2768 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Material Requisition To Resource Division | 1064/JD | 24/08/2023 | 0 | Resource Division | 19.68 | 0 | 0 | 0
2769 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MANABARI TEA GARDEN PWSS, AT TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1341/NMD | 08/08/2023 | 30 | S.P. ENTERPRISE | 20.63 | 0 | 0 | 0
2770 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Rejuvenation of Manabari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2332/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 0 | 0 | 100
2771 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Infrastructure development cost for new service connection at REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000118549 Reference ID : 860312789 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
2772 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | New Service Connection Charge for REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003491167 Reference ID : 403275173 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
2773 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Construction of different components of Rejuvenation of Manabari Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 937/JD | 08/08/2023 | 754 | TARAKESWAR PRASAD | 97.86 | 0 | 0 | 60
2774 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
2775 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
2776 | JALPAIGURI | Northern Mechanical | Rejuvenation for Manabari Tea Garden , SM/15082 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
2777 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Material Requisition To Resource Division | 170/JD | 28/04/2023 | 0 | Resource Division | 15.65 | 0 | 0 | 0
2778 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | New Service Connection Charge for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 4003164169, Reference ID : 403024436] | BP/23-24/104 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2779 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Infrastructure Cost for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 100000084433, Reference ID : 860276013] | BP/23-24/72 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.09 | 0 | 0 | 0
2780 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Infrastructure Cost for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 100000088138, Reference ID : 860278838] | BP/23-24/104 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.26 | 0 | 0 | 0
2781 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | New Service Connection Charge for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 4003164173, Reference ID : 403024437] | BP/23-24/72 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2782 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Construction of different components of Uttar Marichbari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | 773/JD | 27/03/2023 | 710 | UNIBRO INFRASERV PRIVATE LIMITED | 182.48 | 0 | 0 | 80
2783 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MARICHBARI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1370/NMD | 09/08/2023 | 389 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 20.62 | 0 | 0 | 100
2784 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 166/RWS | 15/02/2024 | 30 | PINTU DAS | 6.14 | 0 | 0 | 100
2785 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Material Requisition To Resource Division | 2046/JD | 09/01/2024 | 0 | Resource Division | 5.49 | 0 | 0 | 0
2786 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2787 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Construction of Boundary Wall at H/W site including rising main and interconnections of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. | 2174/JD | 22/01/2024 | 679 | SUBRATA GOSWAMI | 15.52 | 0 | 0 | 100
2788 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
2789 | JALPAIGURI | Northern Mechanical | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
2790 | JALPAIGURI | Jalpaiguri Division | UTTAR MARICHBARI PIPED WATER SUPPLY SCHEME , SM/14919 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-C of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 985/JD | 14/08/2024 | 15 | LIMRA SOCIAL WELFARE SOCIETY | 4.63 | 0 | 0 | 100
2791 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF CHAMURCHI FOREST BUSTY WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15584 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2792 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF CHAMURCHI FOREST BUSTY WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15584 | Solarisation | Quotation charges for Application for Net Metering connection at Chamurchi Piped Water Supply Scheme under NMD ,PHE Dte APPLICATION NO - 4003455325 CONSUMER ID- 422179293 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
2793 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF CHAMURCHI FOREST BUSTY WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15584 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2794 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Material Requisition To Resource Division | 1371/JD | 27/09/2023 | 0 | Resource Division | 48.31 | 0 | 0 | 0
2795 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. | 740/JD | 26/07/2024 | 150 | M/S SIBU DEY AND CO. | 118.85 | 0 | 0 | 60
2796 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 436/SMSD | 28/03/2024 | 7 | M/S ANJALI ENTERPRISE | 0.73 | 0 | 0 | 0
2797 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Material Requisition To Resource Division | 2076/JD | 10/01/2024 | 0 | Resource Division | 26.02 | 0 | 0 | 0
2798 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
2799 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | New Service Connection Charge for PATKATA, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341718, Reference ID : 403171608] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.15 | 0 | 0 | 0
2800 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | New Service Connection Charge for PATKATA, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033417720, Reference ID : 403172408] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.09 | 0 | 0 | 0
2801 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | New Service Connection Charge for PATKATA, ZONE-I, TW NO-III, MASKALAIBARI CCC APPLICATION NO. 4003483369 Reference ID : 403270691 | BP/24-25/217 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.61 | 0 | 0 | 0
2802 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1279/NMD | 02/08/2023 | 761 | M/S BHOWMICK & CO. | 35.98 | 0 | 0 | 60
2803 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Construction of different components of Patkata Zone- I Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. | 1706/JD | 04/12/2023 | 637 | GARGO TRADERS | 546.65 | 0 | 0 | 60
2804 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 112/JD | 16/01/2025 | 440 | DINABANDHU ROY | 17.84 | 0 | 0 | 0
2805 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
2806 | JALPAIGURI | Northern Mechanical | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2807 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. | 483/RWS | 29/05/2025 | 30 | PINTU DAS | 7.76 | 0 | 0 | 0
2808 | JALPAIGURI | Jalpaiguri Division | PATKATA ZONE-I PIPED WATER SUPPLY SCHEME , SM/15339 | New | Construction of Boundary Wall, Foot Path, Drain including Iron Elemination Plant and interconnection work at 3rd site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 2497/JD | 09/12/2025 | 120 | KANAI LAL SEN | 21.13 | 0 | 0 | 0
2809 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 0 | 0 | 1
2810 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Material Requisition To Resource Division | 1113/JD | 24/08/2023 | 0 | Resource Division | 9.93 | 0 | 0 | 0
2811 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Material Requisition To Resource Division | 1880/JD | 20/12/2023 | 0 | Resource Division | 4.77 | 0 | 0 | 0
2812 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | New Service Connection Charge for PASCHIM SALBARI ,ZONE:-II, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003379309 Reference ID : 403193837 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.77 | 0 | 0 | 0
2813 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | New Service Connection Charge for PASCHIM SALBARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003289711 Consumer ID : 403122966 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0 | 0
2814 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Construction of diferent components of Paschim Salbari Zone-II pwss i.e TW, Pump Houses, water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E.Dte. | 264/JD | 10/05/2023 | 1057 | ANUP SARKAR | 213 | 0 | 0 | 35
2815 | JALPAIGURI | Jalpaiguri Division | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Paschim Salbari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2333./JD | 12/12/2024 | 475 | ANUP SARKAR | 18.22 | 0 | 0 | 100
2816 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0 | 0
2817 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
2818 | JALPAIGURI | Northern Mechanical | PASCHIM SALBARI ZONE-II PIPED WATER SUPPLY SCHEME , SM/16040 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM SALBARI PWSS, ZONE-II, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1209/NMD | 26/07/2023 | 699 | THE BANERJEE CONCERN | 21.54 | 0 | 0 | 100
2819 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SYLI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15621 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2820 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF SYLI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15621 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2821 | JALPAIGURI | Northern Mechanical | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1213/NMD | 26/07/2023 | 30 | MAA ENTERPRISES | 11.18 | 0 | 0 | 0
2822 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | Material Requisition To Resource Division | 1055/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0 | 0
2823 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | Rejuvenation work for Pump House & Additional Backwash line for Uttar Bhuskadanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 155/RWS | 15/02/2024 | 30 | MRINMOY KANTI DUTTA | 6.13 | 0 | 0 | 100
2824 | JALPAIGURI | Northern Mechanical | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | New Service Connection Charge for UTTAR BHUSKADANGA(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401398 Reference ID : 403211999 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.97 | 0 | 0 | 0
2825 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | Laying Additional pipeline to improve the water distribution network for Uttar Bhuskadanga Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 631/JD | 28/03/2025 | 218 | MRINMOY KANTI DUTTA | 23.85 | 0 | 0 | 0
2826 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS , SM/16937 | Augmentation | Construction of different components for Rejuvenation of Uttar Bhuskadanga & Gartali Jalpesh PWSS i.e. TW, Pump House, IEP, Rising Main etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division PHE Dte. | 401/A/JD | 06/06/2023 | 622 | KAMALESH SEN | 42.76 | 0 | 0 | 100
2827 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | SOIL INVESTIGATION WORK FOR BAGRAKOTE T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI | 852/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 0 | 0 | 1
2828 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Sinking of 3 Nos. Tubewell by ODEX-165 method for Bagrakote W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | 1516/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 20.54 | 0 | 0 | 100
2829 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Material Requisition To Resource Division | 1940/JD | 02/12/2021 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2830 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Material Requisition To Resource Division | 172/JD | 28/04/2023 | 0 | Resource Division | 82.59 | 0 | 0 | 0
2831 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093885, Reference ID : 860285545] | BP/23-24/151 | 05/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0 | 0
2832 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266408, Reference ID : 403105530] | BP/23-24/150 | 05/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2833 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of 400 CuM Capacity R.C.C. Over Head Reservoir (OHR) of 20 Mtr Staging Height at Bagrakote Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 2410/JD | 19/02/2024 | 180 | D.C RAKSHIT AND SONS INDIA PRIVATE LTD. | 106.62 | 0 | 0 | 0
2834 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of Boundary wall, drain and pathway for 2nd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 134/JD | 17/01/2023 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.01 | 0 | 0 | 100
2835 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 1674/JD | 24/11/2023 | 45 | KAPIL MANI BRAHMAN | 11.66 | 0 | 0 | 100
2836 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Emergency water supply arrangement to the dengue effected area related to Bagrakote water supply Scheme for 45 days . ( from 29.06.2022 to 12.08.2022) | 437/RWS | 07/07/2022 | 45 | SWAPAN SAHA | 4.47 | 0 | 0 | 0
2837 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Material Requisition To Resource Division | 2068/JD | 10/01/2024 | 0 | Resource Division | 14.15 | 0 | 0 | 0
2838 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093883, Reference ID : 860285543] | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.39 | 0 | 0 | 0
2839 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093777, Reference ID : 860285647] | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
2840 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266397, Reference ID : 403105521] | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
2841 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Laying Distribution system and functional household tap connection for Bagrakote Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. | 351/JD | 03/02/2022 | 1305 | M/S GARGO TRADERS | 184.25 | 0 | 0 | 60
2842 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(2nd Site) .(4th Call) | 1274/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 0.8 | 0 | 0 | 100
2843 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. .(H/W Site) .(4th Call) | 1275/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 1.37 | 0 | 0 | 100
2844 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Bagrakote T.G. W/S/S under Jalpaiguri Division , P.H.E. Dte. | 825/RWS | 30/11/2021 | 1187 | BIMAN DAS | 4.65 | 0 | 0 | 100
2845 | JALPAIGURI | Northern Mechanical | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BAGRAKOTE TEA GARDEN AREA PWSS,at TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1481/NMD | 17/08/2023 | 503 | SUBHRA ENTERPRISE | 41.17 | 0 | 0 | 100
2846 | JALPAIGURI | Jalpaiguri Division | Bagrakote Tea Garden Area Piped Water Supply Scheme. , SM/08874 | New | Construction of Pump House (5.40m x 3.60m) Head work site with sanitary & plumbing arrangement including Rising main interconnection and restoration work at Bagrakote Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2486/JD | 27/02/2024 | 429 | GARGO TRADERS | 15.46 | 0 | 0 | 100
2847 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KILKOTE TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15614 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2848 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KILKOTE TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15614 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2849 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHANGARHAT PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15598 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2850 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHANGARHAT PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15598 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2851 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GRASSMORE TEA GARDEN AREA PIPED WATER SUPPLY UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15599 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
2852 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT GRASSMORE TEA GARDEN AREA PIPED WATER SUPPLY UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15599 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
2853 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (North Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | 1552/JD | 01/11/2023 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 414.28 | 0 | 0 | 0
2854 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Material Requisition To Resource Division | 1827/JD | 14/12/2023 | 0 | Resource Division | 121.48 | 0 | 0 | 0
2855 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Material Requisition To Resource Division | 1104/JD | 24/08/2023 | 0 | Resource Division | 184.96 | 0 | 0 | 0
2856 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Retrofittings works including Functional House Hold Tap connection under JJM for Dabgram Water Supply Scheme ( Central Zone ) under Jalpaiguri Division , P.H.E. Dte. | 796/JD | 24/07/2023 | 21 | NARENDRA KUMAR | 36.22 | 0 | 0 | 100
2857 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of September 2024. | BP-2024-25-496 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0 | 0
2858 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of August 2024. | BP-2024-25-552 | 17/12/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0 | 0
2859 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VII, under SUBHASPALLY CCC APPLICATION NO. 4003412903 Reference ID : 403221491 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.6 | 0 | 0 | 0
2860 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412861 Reference ID : 403221492 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0 | 0
2861 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 71 B 8742 for the Month of July 2024. | BP-2024-25-341 | 30/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
2862 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of September 2024. | BP-2024-25-550 | 17/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
2863 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE , T/W-V , Bhoot Para, Thakur Nagar, Behind GC Tiles under SUBHASPALLY CCC APPLICATION NO. 4003511149 , Reference ID : 403289730 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.61 | 0 | 0 | 0
2864 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412817 Reference ID : 403221494 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.57 | 0 | 0 | 0
2865 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of August 2024. | BP-2024-25-368 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0 | 0
2866 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-IV, under SUBHASPALLY CCC APPLICATION NO. 4003412749 Reference ID : 403221493 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.23 | 0 | 0 | 0
2867 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of October 2024. | BP-2024-25-548 | 17/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0 | 0
2868 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Different stationary for office under Jalpaiguri Division, PHE Dte. | BP-2024-25-84 | 17/05/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0 | 0
2869 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of October 2024. | BP-2024-25-551 | 17/12/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0 | 0
2870 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Thorough repair and overhauling of the IEP reparing Pump House and other ancillary work at Dabgram Central zone at Dabgram -II G.P. under Dabgram piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 795/JD | 24/07/2023 | 861 | NARENDRA KUMAR | 6.8 | 0 | 0 | 0
2871 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (Central Zone) i.e. TW, Pump Houses, Water Distribution Network, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block, Rajganj under Jalpaiguri Division, P.H.E. Dte. | 936/JD | 08/08/2023 | 779 | MAA MANASA VYAPAAR | 708.57 | 0 | 0 | 43
2872 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DABGRAM-II (CENTRAL ZONE,SOUTH ZONE,NORTH ZONE) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1513/NMD | 24/08/2023 | 930 | ALPHA ENTERPRISE | 143.91 | 0 | 0 | 60
2873 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Construction of different components of Dabgram PWSS (South Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | 1708/JD | 04/12/2023 | 759 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 526.38 | 0 | 0 | 45
2874 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/08/2024 to 09/02/2025) | 963/JD | 09/08/2024 | 184 | RABINDRA NATH DUTTA | 0.88 | 0 | 0 | 0
2875 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.07.2024 to 13.01.2025) | 649/JD | 11/07/2024 | 184 | RAKESH SARKAR | 0.88 | 0 | 0 | 0
2876 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2024 to 31.05.2025)". | 2201/JD | 30/11/2024 | 182 | RUPA PRASAD | 0.88 | 0 | 0 | 0
2877 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.01.2025 to 28.02.2025) | 04/HQ/JD | 13/01/2025 | 46 | RAKESH SARKAR | 0.23 | 0 | 0 | 0
2878 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 01/04/2025 to 30/04/2025) | 107-HQ/JD | 28/03/2025 | 31 | RABINDRA NATH DUTTA | 0.15 | 0 | 0 | 0
2879 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation Order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | 212/JD | 29/01/2025 | 181 | SOUMEN GHOSH | 0.88 | 0 | 0 | 0
2880 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/02/2025 to 31/03/2025) | 41/HQ/JD | 09/02/2025 | 50 | RABINDRA NATH DUTTA | 0.25 | 0 | 0 | 0
2881 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of "Supply of 1 (One) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit) (w.e.f. 01.06.2025 to 30.11.2025)." | 983/JD | 26/05/2025 | 184 | RUPA PRASAD | 0.88 | 0 | 0 | 0
2882 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | 1496/JD | 30/06/2025 | 31 | BISWANATH GHOSH | 0.4 | 0 | 0 | 0
2883 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 01.03.2025 to 31.03.2025) | 70/HQ/JD | 28/02/2025 | 31 | RAKESH SARKAR | 0.15 | 0 | 0 | 0
2884 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte.(For the period from01/05/2025 to 30/06/2025) | 817/JD | 30/04/2025 | 61 | BISWANATH GHOSH | 0.8 | 0 | 0 | 0
2885 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | 818/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0 | 0
2886 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | 1998/JD | 25/09/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0 | 0
2887 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | 2428/JD | 25/11/2025 | 30 | PRADIP SAHA | 0.4 | 0 | 0 | 0
2888 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | 1732/JD | 31/07/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0 | 0
2889 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DABGRAM-II PIPED WATER SUPPLY SCHEME , SM/18283 | Augmentation | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 0 | 100
2890 | JALPAIGURI | Jalpaiguri Division | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme , SM/06842 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAKHATI T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte | 1118/JD | 02/11/2020 | 60 | R.S CONSTRUCTION | 38.19 | 10 | 26.18 | 0
2891 | JALPAIGURI | Jalpaiguri Division | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme , SM/06842 | Retrofitting | fhtc nakhati |  | 05/10/2021 | 0 | R.S CONSTRUCTION | 10 | 0 | 0 | 0
2892 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- IV) | 1405/JD | 03/09/2021 | 30 | RABINDRANATH DUTTA | 23.6 | 9.77 | 41.41 | 1
2893 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | 1338/JD | 23/08/2021 | 30 | ASIT PAUL | 30.22 | 22.15 | 73.3 | 1
2894 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Chauhaddi piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | 1256/JD | 10/08/2021 | 15 | HARIPADA BANERJEE | 4.81 | 0 | 0 | 1
2895 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 0 | 0 | 1
2896 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | fhtc chauhaddi |  | 05/10/2021 | 0 | ASIT PAUL | 22.15 | 0 | 0 | 0
2897 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | fhtc chauhaddi |  | 06/10/2021 | 0 | RABINDRANATH DUTTA | 9.77 | 0 | 0 | 0
2898 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | FHTC GORALBARI | BP-2021-22-454 | 27/03/2022 | 0 | SAPTASWA SARKAR | 2.69 | 0 | 0 | 0
2899 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | HDPE UTTAR ANGRAVASA PWSS | BP-2021-22-461 | 27/03/2022 | 0 | ROY & SARKAR CONSTRUCTION | 4.89 | 0 | 0 | 0
2900 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | RETRO FITTING WOR FOR GORALBARI ZONE -I | BP-2021-22-455 | 27/03/2022 | 0 | SAPTASWA SARKAR | 3.67 | 0 | 0 | 0
2901 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | FHTC KAMARVITA VILLAGE RAJGANJ BLOCK | BP-2021-22-444 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 3.63 | 0 | 0 | 0
2902 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | FHTC GORALBARI ZONE - I | BP-2021-22-453 | 27/03/2022 | 0 | SAHA CONSTRUCTION | 3.49 | 0 | 0 | 0
2903 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC)under Jaldhara Jal Sapna under comand area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block , SM/07893 | Retrofitting | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works under Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | 1292/JD | 14/06/2022 | 15 | ASIT PAUL | 1.69 | 0 | 0 | 0
2904 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2192/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.97 | 0 | 0 | 0
2905 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Construction of Pump House (3.60m x 2.40m) size with sanitary and plumbing arrangement at 2nd Tube well site for Ghasmari PWSS under Jalpaiguri Division, P.H.E. Dte. | 1071/JSSD | 25/01/2022 | 45 | ARUP SARKAR | 4.65 | 0 | 0 | 0
2906 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Construction of Boundary wall with gate drain and pathway for 2nd tube well site of Ghasmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1061/JSSD | 24/01/2022 | 20 | PRITAM DUTTA | 3.76 | 0 | 0 | 0
2907 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 267/NMD | 22/04/2022 | 21 | GURUKRIPA ENTERPRISE | 2.16 | 0 | 0 | 0
2908 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Rig approach for Installation of tube well at Ghasmari Piped water supply Scheme head works site & 2nd site under Jalpaiguri Division, P.H.E.Dte. | 97/JSSD | 22/07/2022 | 30 | ALICK DUTTA | 1.22 | 0 | 0 | 0
2909 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | CONST OF OHR FOR UTTAR DANGAPRA DAKSHIN SAKOAJHORA PWSS | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0 | 0
2910 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | New Service Connection Charge for TW-II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921741, Reference ID : 402816204] | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0 | 0
2911 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Maintainance of Jalpaiguri division office including RWS/ Sadar Sub-Division | BP-2022-23-180 | 15/09/2022 | 0 | SUKUMAR KUNDU | 1.64 | 0 | 0 | 0
2912 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | supply of fuel | BP-2022-23-262 | 17/11/2022 | 0 | FILL & SMILE | 0.98 | 0 | 0 | 0
2913 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | New Service Connection Charge for TW-I of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921737, Reference ID : 402816203] | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.85 | 0 | 0 | 0
2914 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | New Service Connection Charge for R.O. PHE Pump House No. I & II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 100000050449, Reference ID : 860240039] | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0 | 0
2915 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | supply of fuel | BP-2022-23-261 | 17/11/2022 | 0 | FILL & SMILE | 1.26 | 0 | 0 | 0
2916 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | CONST 250 MM CAPACITY UTTAR DANGA PARA & DAKSHIN SAKOJHORA | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0 | 0
2917 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Installation of R.B.T fixing in boundary wall and other allied works at 2nd site for Ghasmari TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | 183/JSSD | 29/08/2022 | 30 | PRITAM DUTTA | 1.78 | 0 | 0 | 100
2918 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 283/NMD | 26/04/2022 | 30 | M/S BHOWMICK & CO. | 8.67 | 0 | 0 | 100
2919 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Material Requisition To Resource Division | 173/JD | 28/04/2023 | 0 | Resource Division | 17.75 | 0 | 0 | 0
2920 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | HIRE CHARGES | BP-2022-23-348 | 09/12/2022 | 0 | APIKUL ALI | 0.29 | 0 | 0 | 0
2921 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | fuel charges | BP-2022-23-439 | 06/02/2023 | 0 | FILL & SMILE | 0.29 | 0 | 0 | 0
2922 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 266/NMD | 22/04/2022 | 21 | M/S PALIDEB ENGINEERING WORKS | 2.16 | 0 | 0 | 100
2923 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 282/NMD | 26/04/2022 | 30 | DEY ENTERPRISE (BALLY) | 8.67 | 0 | 0 | 100
2924 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Material Requisition To Resource Division | 2064/JD | 10/01/2024 | 0 | Resource Division | 4.8 | 0 | 0 | 0
2925 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Construction of 150 CUM Capacity R.C.C. Elevated Reservoir, 20 Mtrs staging Height including pump house (5.4x3.6) size, Boundary wall and Drain for GHASMARI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte | 708/JD | 13/07/2023 | 612 | M/S R.N. TRADERS | 76.58 | 0 | 0 | 85
2926 | JALPAIGURI | Jalpaiguri Division | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Laying distribution system with Rising Main Connection and Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Ghasmari Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte. | 208/JD | 24/01/2022 | 1123 | M/S R.N. TRADERS | 118.35 | 0 | 0 | 100
2927 | JALPAIGURI | Northern Mechanical | Ghasmari Piped Water Supply Scheme. , SM/08868 | New | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling, at Ghasmari PWSS, TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | 356/DSD | 28/02/2022 | 15 | S.P. ENTERPRISE | 0.49 | 0 | 0 | 100
2928 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Madhya Khattiamri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 96/JD | 10/01/2022 | 60 | ALICK DUTTA | 4.65 | 0 | 0 | 0
2929 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Madhya Khattimari PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 197/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 0 | 0 | 1
2930 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | New Service Connection Charge for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123382, Reference ID : 402998142] | BP/23-24/09 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2931 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Infrastructure Cost for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076479, Reference ID : 860267199] | BP/23-24/09 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.22 | 0 | 0 | 0
2932 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Laying Rising Main at 3rd Tubewell site of Madhya Khuttimari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 325/JD | 18/05/2023 | 14 | CHOWDHURY CONSTRUCTION | 4.63 | 0 | 0 | 10
2933 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MADHYA KHUTTIMARI PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 391/NMD | 29/03/2023 | 30 | M/S DILIP MITRA | 11.07 | 0 | 0 | 100
2934 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhya Khutttimari Piped Water Supply Scheme , SM/09483 | Augmentation | Laying of higher dia. pipeline within the Command Area of Madhya Khuttimary and adjoining mouzas Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 2163/JD | 30/10/2025 | 75 | BILTU DAS | 152.02 | 0 | 0 | 0
2935 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Sinking of 1 No. 250mm x 150mm x 135 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 348/JD | 03/02/2022 | 30 | J.M. CONSTRUCTION | 7.85 | 0 | 0 | 1
2936 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chauhaddi P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 106/JD | 11/01/2022 | 60 | J.M. CONSTRUCTION | 4.65 | 0 | 0 | 1
2937 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Repairing of damaged line near Harinkhwa School with other ancillary repairing work related to the Laying Distribution System at Chauhaddi P.W.S.S. under Jalpaiguri Division, | 166/JD | 20/01/2022 | 21 | HARIPADA BANERJEE | 3.68 | 0 | 0 | 1
2938 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | FUEL BILL | BP-2022-23-137 | 25/08/2022 | 0 | FILL & SMILE | 0.74 | 0 | 0 | 0
2939 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | BOUNDARY WALL 2ND T/WELL SITE RED BANK T.G | BP-2021-22- 459 | 27/03/2022 | 0 | DEEP CONSTRUCTION | 3.58 | 0 | 0 | 0
2940 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Repairing of choakaged and damaged branch lines due to road development and widening of near by area of Garialtari within the command area of Chauhaddi and adjoining mouzas Piped Water Supply Scheme under Jalpaiguri Division. P.H.E.Dte. | 1435/JD | 18/07/2022 | 21 | HARIPADA BANERJEE | 4.84 | 0 | 0 | 0
2941 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0 | 0 | 0
2942 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Providing Functional Household Tap Connection (Phase - VI) in connection with Jal Jeevan Mission for Rejuvenation of Chouhaddi and adjoining Mouzas P.W.S.S under Jalpaiguri Division, P.H.E. Dte. | 626/JD | 13/03/2023 | 30 | SOMNATH ROY | 17.57 | 0 | 0 | 0
2943 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Retrofitting works in connection with Rejuvination of Chauhaddi PWSS for FHTC work of Jal Swapna at Dhupguri Block under Jalpaiguri Division, PHE Dte. | 971/JD | 20/04/2022 | 90 | SCEC BOENTER KDAS JOINT VENTURE | 168.05 | 0 | 0 | 1
2944 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Construction of Pathway inside the Head Works Site of Chauhaddi and adjoining mouzas .P.W.S.S. under Jalpaiguri Division,P.H.E.Dte. | 1468/JD | 25/07/2022 | 21 | HARIPADA BANERJEE | 3.53 | 0 | 0 | 100
2945 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0 | 0 | 0
2946 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | New Service Connection Charge for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018642, Reference ID : 402927988] | BP/22-23/129 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2947 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Infrastructure Cost for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066801, Reference ID : 860257021] | BP/22-23/129 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.81 | 0 | 0 | 0
2948 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAUHADDI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1122/NMD | 12/09/2022 | 30 | SUMON ELECTRICAL | 8.14 | 0 | 0 | 100
2949 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAUHADDI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 102/NMD | 03/02/2023 | 21 | SUMON ELECTRICAL | 2.94 | 0 | 0 | 100
2950 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0091/2023-2024 ,Dt - 29/02/24 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.41 | 0 | 0 | 0
2951 | JALPAIGURI | Northern Mechanical | Rejuvenation of Chauhaddi Piped Water Supply Scheme , SM/09484 | Augmentation | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0092/2023-2024 ,Dt - 31/03/24 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0 | 0
2952 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Khalaigram P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | 1851/JD | 16/09/2022 | 45 | MANAB BAKSHI | 4.65 | 0 | 0 | 0
2953 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Sinking of 250 mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Khalaigram PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | 199/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 0 | 0 | 1
2954 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Infrastructure Cost for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066803, Reference ID : 860257023] | BP/22-23/130 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.24 | 0 | 0 | 0
2955 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | New Service Connection Charge for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018666, Reference ID : 402928492] | BP/22-23/130 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0 | 0
2956 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | ADDITIONAL WORK Infrastructure Cost for KHALAIGRAM, T/W III, under DHUPGURI CCC [APPLICATION NO. 100000090647, Reference ID : 860281557] | BP/23-24/124 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.64 | 0 | 0 | 0
2957 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for KHALAIGRAM (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1123/NMD | 12/09/2022 | 30 | S.P. ENTERPRISE (KOLKATA) | 8.13 | 0 | 0 | 100
2958 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under KHALAIGRAM (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1400/NMD | 09/12/2022 | 30 | S.D. CONCERN | 2.91 | 0 | 0 | 100
2959 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Laying Rising Main at 3rd Tube Well site of Khalaigram PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | 123/JD | 28/04/2023 | 14 | PRIYABRATA KARMAKAR | 8.33 | 0 | 0 | 80
2960 | JALPAIGURI | Northern Mechanical | Rejuvenation of Khalaigram Piped Water Supply Scheme , SM/09486 | Augmentation | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
2961 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | 2193/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.42 | 0 | 0 | 0
2962 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Model estimate for construction of pump house ( 3.60 m X 2.40 m) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Kumlai T.G . W/S/S under Jalpaiguri Division , P.H.E. Dte | 875/RWS | 08/12/2021 | 30 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.65 | 0 | 0 | 1
2963 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 438/NMD | 14/06/2022 | 21 | TAPAN BISWAS | 2.39 | 0 | 0 | 0
2964 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | RENOVATION B/W H/W SOUTH BERUBARI WSS | BP-2021-22-540 | 31/03/2022 | 0 | A.P CONSTRUCTION | 19.8 | 0 | 0 | 0
2965 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 4002922582, Reference ID : 402818172] | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.32 | 0 | 0 | 0
2966 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCI [APPLICATION NO. 4002922585, Reference ID : 402817968] | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.88 | 0 | 0 | 0
2967 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Infrastructure cost for New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050873, Reference ID : 860240743] | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0 | 0
2968 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Infrastructure cost for New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050872, Reference ID : 860240742] | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.59 | 0 | 0 | 0
2969 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 439/NMD | 14/06/2022 | 21 | M/S B.ENTERPRISE | 2.37 | 0 | 0 | 0
2970 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | SOIL INVESTIGATION WORK FOR KUMLAI T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI | 853/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 0 | 0 | 0
2971 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Construction of 150 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing RCC including pipe connection and cost of pipes, specials, Construction of Pump House (5.4m x 3.60 m) & Boundary wall at H/W site Kumlai Tea Garden Area Piped Water Supply Scheme, Block- Mal, Dist. Jalpaiguri. Under Jalpaiguri Division P.H.E. Dte. | 252/JD | 31/01/2022 | 150 | SANDIP BANIK | 64.43 | 0 | 0 | 1
2972 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Carrying out Development works and Yield Test for a BDTW at Kumlai TG W/S Scheme, TW-I & II, Bhagatpur TG PWSS (Zone-II), TW-I & II, Ghasmari PWSS, TW-I & II , Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | 328/DSD | 07/02/2022 | 21 | M/S ANJALI ENTERPRISE | 0.63 | 0 | 0 | 100
2973 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 861/NMD | 18/07/2022 | 30 | PRATIK ROY | 9.2 | 0 | 0 | 100
2974 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Providing Functional Household Tap Connection (FHTC) in connection for Jaldhara/Jal Sapna under the command area of Jabramali piped Water Supply Scheme at MATIALI Block under Jalpaiguri Division, PHE Dte. (Part-E) | 565/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 2.65 | 0 | 0 | 0
2975 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Construction of boundary wall Path way, block drain for 2 nd site of kumlai T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Die. | 647/RWS | 21/10/2022 | 20 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.83 | 0 | 0 | 1
2976 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0 | 0 | 1
2977 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Material Requisition To Resource Division | 174/JD | 28/04/2023 | 0 | Resource Division | 21.11 | 0 | 0 | 0
2978 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | PAYMENT FOR FUEL BILL | BP-2023-24-315 | 18/08/2023 | 0 | FILL & SMILE | 3.34 | 0 | 0 | 0
2979 | JALPAIGURI | Northern Mechanical | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 536/NMD | 08/07/2022 | 30 | RAJEEV RANJAN OJHA | 9.62 | 0 | 0 | 70
2980 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Laying Distribution system and functional household tap connection for Kumlai Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. | 192/JD | 21/01/2022 | 60 | R.S CONSTRUCTION | 116.87 | 0 | 0 | 70
2981 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Rising main connection for Kumlai TG PWSS including supply of Sluice valve/ Jeffy coupling ,C.I.D.F. Specials etc. under Jalpaiguri Division P.H.E. Dte. | 27/JD | 05/01/2023 | 21 | ADITRI ENTERPRISE | 4.81 | 0 | 0 | 100
2982 | JALPAIGURI | Jalpaiguri Division | Kumlai Tea Garden Area Piped Water Supply Scheme. , SM/08875 | New | Material Requisition To Resource Division | 2066/JD | 10/01/2024 | 0 | Resource Division | 6.1 | 0 | 0 | 0
2983 | JALPAIGURI | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Binnaguri (Rajganj Block) W/S Scheme at T/W No. I & II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 208/NMD | 04/04/2022 | 21 | BONANZA ENTERPRISE | 4.78 | 0 | 0 | 0
2984 | JALPAIGURI | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BINNAGURI (AUG) W/S Scheme, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 442/NMD | 14/06/2022 | 21 | MALAY KUMAR SAHA | 2.77 | 0 | 0 | 0
2985 | JALPAIGURI | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | PROVIDING ADDITIONAL BENTONITE & OTHER ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI W/S SCH UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 408/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0 | 0 | 0
2986 | JALPAIGURI | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | ADDITIONAL WORK FOR DRILLING BOLDER/SAND STONE ZONE AT AUG. OF BINNAGURI W/S SCH, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 407/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.97 | 0 | 0 | 0
2987 | JALPAIGURI | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 395/CMSD-II (D) | 01/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.53 | 0 | 0 | 0
2988 | JALPAIGURI | Central Drilling | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | PROVIDING DRILLING CREWS INCLUDING OTHERS MATERIALS & WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 100 MTR DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | 394/CMSD-II (D) | 01/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.3 | 0 | 0 | 0
2989 | JALPAIGURI | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | New Service Connection Charge for T/W No. V of MORAGHAT TEA GARDEN NEAR HOSPITAL W/S Scheme under BANRHAT CCC [APPLICATION NO.4002888889, Reference ID : 402788875] | BP/2022-23/14 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
2990 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Laying distribution system for Augmentation of Binnaguri Piped water Supply Scheme at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | 332/JD | 02/02/2022 | 120 | M/S NANDY ENTERPRISE | 458.51 | 0 | 0 | 1
2991 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Supply of Sluice valve C.I. Specials at Binnaguri for laying of DI line from OHR to UPVC Pipe line in connection with Augmentation of Binnaguri W/S Scheme under Jalpaiguri Division, PHE Dte. | 389/RWS | 25/04/2023 | 14 | B.M CONSTRUCTION | 3.31 | 0 | 0 | 0
2992 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Construction of Boundary Wall with gate, drain for 3rd Tube well site of Binnaguri Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | 444/JD. | 08/06/2023 | 21 | ETHERIA EDIFICE (OPC) PVT. LTD. | 5.29 | 0 | 0 | 0
2993 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission under the command area of Binnaguri (Fulbari-II) for Augmentation of Binnaguri Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | 1852/JD | 15/12/2023 | 45 | SUNIL ROY | 17.04 | 0 | 0 | 0
2994 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) with sanitary & plumbing arrangement at 3rd Tube well site for Binnaguri (Fulbari) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 133/JD | 17/01/2023 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 0 | 0 | 100
2995 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Installation of Iron Elimination Plant (capacity-50m3/hr.) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT JALPAIGURI | 165/JD | 19/01/2023 | 45 | KANAI LAL SEN | 19.8 | 0 | 0 | 100
2996 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | SUPPLY OF FUEL | BP-2022-23-522 | 15/03/2023 | 0 | FILL & SMILE | 0.33 | 0 | 0 | 0
2997 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Extra Laying of Water Distribution System, construction of valve chamber and other ancillary works for Augmentation of Binnaguri PWSS at Binnaguri at Block - Rajganj under Jalpaiguri Division, PHE Dte. | 706/JD | 13/07/2023 | 21 | M/S KARMAKAR CONSTRUCTION | 29.75 | 0 | 0 | 80
2998 | JALPAIGURI | Northern Mechanical | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BINNAGURI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 53/NMD | 24/01/2023 | 30 | SUNLIT | 10.1 | 0 | 0 | 100
2999 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Repairing of OHR and repairing valve chamber & other ancillary works Binnaguri Head Work site under Binnaguri Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. | 1228/JD | 11/09/2023 | 21 | KANAI LAL SEN | 6.87 | 0 | 0 | 100
3000 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Repairing of pump house, boundary wall, land development and construction of drain, repairing valve chamber & other ancillary works at Augmentation of Binnaguri head works site under Binnaguri piped water supply scheme under Jalpaiguri Division PHE,Dte. | 1934/JD | 02/01/2024 | 21 | GOPRO CONSTRUCTION | 4.2 | 0 | 0 | 100
3001 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Material Requisition To Resource Division | 2102/JD | 25/11/2024 | 0 | Resource Division | 101.9 | 0 | 0 | 0
3002 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | SUPPLY OF FUEL (DIESEL) FOR VEHICLES UNDER JALPAIGURI DIVISION PHE DTE. FOR THE MONTH OF DECEMBER 2023 AND JANUARY 2024 | BP-2023-24-665 | 22/02/2024 | 0 | FILL & SMILE | 1.9 | 0 | 0 | 0
3003 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Installation of Iron Elimination Plant (Capacity 20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd Tubewell site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT - JALPAIGURI. | 136/JD | 17/01/2023 | 45 | SUBIR GHOSH | 14.72 | 0 | 0 | 0
3004 | JALPAIGURI | Jalpaiguri Division | Augmentation of Binnaguri Piped Water Supply Scheme , SM/09344 | Augmentation | Laying of Water Distribution System and other ancillary works for Augmentation of Binnaguri PWSS at Block-Rajganj under Jalpaiguri Division, P.H.E. Dte. (Part-A) | 2408./JD | 20/12/2024 | 224 | M/S KARMAKAR CONSTRUCTION | 40.9 | 0 | 0 | 100
3005 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Augmentation of Shikarpur PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | 440/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.23 | 0 | 0 | 1
3006 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (350 cum) at Shikarpur under Shikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1411/JD | 12/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 0 | 0 | 1
3007 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Thorough repair and overhauling of the Iron Elimination Plant installed at Shikarpur Water Supply Scheme, under Jalpaiguri Division P.H.E. Dte. | 1797/JD | 14/09/2022 | 21 | KANAI LAL SEN | 3.04 | 0 | 0 | 1
3008 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site of Shikarpur PWSS i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | 298/JD | 10/02/2023 | 45 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 4.69 | 0 | 0 | 1
3009 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Construction of Room and other ancillary work at Belakoba primary school near H/W site for Shikarpur piped water supply schemer at Rajganj block under Jalpaiguri division PHE Dte. | 447/JD. | 08/06/2023 | 45 | DEBABRATA SARKAR | 2.94 | 0 | 0 | 100
3010 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Dismantiling old IEP, old Pump house and filling old CWR and other ancillary works at Sikarpur under Sikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 446/JD. | 08/06/2023 | 14 | GOUTAM DAS | 6 | 0 | 0 | 100
3011 | JALPAIGURI | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | New Service Connection Charge for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO. 4003114721 ; Reference ID : 402982646] | BP/22-23/170 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3012 | JALPAIGURI | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Infrastructure Cost for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO.100000074416 ; Reference ID : 860265926] | BP/22-23/170 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0 | 0
3013 | JALPAIGURI | Northern Mechanical | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHIKARPUR PWSS, at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 362/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 11.07 | 0 | 0 | 100
3014 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Shikarpur piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2315/JD | 07/02/2024 | 30 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.28 | 0 | 0 | 100
3015 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Rejuvenation work for Pump houses and laying UPVC pipe line at H/W site of Augmentation of Shikarpur Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 519/JD | 27/06/2024 | 115 | KANAI LAL SEN | 7.02 | 0 | 0 | 100
3016 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Construction of Boundary Wall with gate, drain, land development, pathway including interconnection work and laying pipe line at Augmentation of Shikarpur PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 1530/JD | 01/10/2024 | 76 | GOUTAM DAS | 16.48 | 0 | 0 | 100
3017 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | VEHICLE BILL |  | 25/01/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
3018 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | FUEL BILL | BP-2023-24-631 | 06/02/2024 | 0 | FILL & SMILE | 0.82 | 0 | 0 | 0
3019 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | VEHICLE DRIVER |  | 25/01/2024 | 0 | RAKESH SARKAR | 0.37 | 0 | 0 | 0
3020 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Providing Functional Household Tap Connection (FHTC) for Augmentation of Shikarpur Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | 1933/JD | 02/01/2024 | 45 | JAYA SARKAR | 17.09 | 0 | 0 | 0
3021 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Laying of Water Distribution System with Functional Household Tap Connection (FHTC) including construction valve chamber and other ancillary works in connection with Jal Jeevan Mission for Augumentation of Shikarpur Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division, P. H. E. Dte. | 2622/JD | 07/03/2024 | 600 | SCEC BOENTER AND KDAS JOINT VENTURE | 559.19 | 0 | 0 | 59
3022 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.07.2025 to 29.11.2025) | 1495/JD | 30/06/2025 | 152 | SOMNATH ROY | 0.94 | 0 | 0 | 0
3023 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIUR CAPACITY 350 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SHIKARPUR PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT:JALPAIGURI, UNDER JALPAIGURI DIVISION, P.H.E. DTE. | 733/JD | 17/03/2022 | 1046 | GOUTAM DAS | 83.34 | 0 | 0 | 100
3024 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Rejuvenation of different components of Over Head Reservoir site at Augmentation of Sikarpur Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1777/JD | 08/12/2023 | 435 | GOUTAM DAS | 12.9 | 0 | 0 | 100
3025 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Supply, Installation, erecting and commissioning of Iron Elimination Plant including construction of Blower Room (3.6MX3.0M) for Augmentation at 3rd tube well site of Shikarpur Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 875/JD | 01/08/2023 | 624 | SADHAN KARMAKAR | 17.83 | 0 | 0 | 100
3026 | JALPAIGURI | Jalpaiguri Division | Augmentation of Shikarpur Piped Water Supply Scheme , SM/09562 | Augmentation | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 0 | 100
3027 | JALPAIGURI | Central Drilling | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250 MM X 150 MM) BY DEPARTMENTAL RIG MACHINE FOR MAYNAGURI BLOCK TW-II UNDER CENTRAL DRILLING DIVISION, PHE DTE. | 781 /CDD | 08/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.42 | 0 | 0 | 0
3028 | JALPAIGURI | Central Drilling | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR MAYNAGURI BLOCK TW-I UNDER CDD, PHE DTE. | 780/ CDD | 08/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.42 | 0 | 0 | 0
3029 | JALPAIGURI | Central Drilling | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0 | 0 | 0
3030 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053937 ; Reference ID : 860243607] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.4 | 0 | 0 | 0
3031 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | New Service Connection Charge for TW-IV of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941284 ; Reference ID : 402831976] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3032 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Infrastructure cost for New Service Connection Charge for W-III of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053961 ; Reference ID : 860243611] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.85 | 0 | 0 | 0
3033 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | New Service Connection Charge for TW-III of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941282 ; Reference ID : 402831978] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3034 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Madhabdanga Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 566/NMD | 14/07/2022 | 21 | GEETA CONSTRUCTION | 2.16 | 0 | 0 | 0
3035 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Retrofitting works including Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Madhab Danga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-F) | 1898/JD | 26/09/2022 | 21 | ANUP SARKAR | 6.48 | 0 | 0 | 0
3036 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Retro fitting works due to FHTC in connection and other ancillary works for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. | 400/JD | 24/02/2023 | 15 | M/S SIBU DEY AND CO. | 1.64 | 0 | 0 | 0
3037 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Providing Functional Household Tap Connection(FHTC) in connection for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. | 399/JD | 24/02/2023 | 21 | M/S SIBU DEY AND CO. | 4.75 | 0 | 0 | 1
3038 | JALPAIGURI | Central Drilling | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCHEME (TW0II) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | 1077/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 0 | 0 | 0
3039 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2210/JD | 27/12/2021 | 60 | M/S KARMAKAR CONSTRACTION | 12.24 | 0 | 0 | 1
3040 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2211/JD | 21/12/2021 | 60 | NISHITH RANJAN KARMAKAR | 12.26 | 0 | 0 | 0
3041 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHABDANGA PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 852/NMD | 18/07/2022 | 30 | M/S BHOWMICK & CO. | 8 | 0 | 0 | 0
3042 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Madhabdanga Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 565/NMD | 14/07/2022 | 21 | R.K.ENTERPRISES | 2.16 | 0 | 0 | 0
3043 | JALPAIGURI | Central Drilling | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Supply & Delivery of lubricant for drilling work at Madhabdanga PWSS, Dist-Jalpaiguri and other PWSS under CDD, PHE Dte. | 262/CMSD-I(D) | 27/06/2022 | 15 | UTTAM KUMAR CHATTERJEE | 4.47 | 0 | 0 | 0
3044 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHABDANGA PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 853/NMD | 18/07/2022 | 30 | MAA ENTERPRISES | 7.99 | 0 | 0 | 98
3045 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Madhabdanga piped water supply scheme under Jalpaiguri Division PHE Dte. | 1593/JD | 18/08/2022 | 45 | M/S SIBU DEY AND CO. | 14.4 | 0 | 0 | 100
3046 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 4th site of Mathab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | 391/RWS | 25/04/2023 | 14 | NISHITH RANJAN KARMAKAR | 2.62 | 0 | 0 | 100
3047 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. | 334/RWS | 10/04/2023 | 14 | M/S KARMAKAR CONSTRACTION | 2.62 | 0 | 0 | 1
3048 | JALPAIGURI | Northern Mechanical | Rejuvenation of Madhabdanga piped water supply scheme. , SM/09456 | Augmentation | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0 | 0
3049 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 844/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 0 | 0 | 1
3050 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | 1020/JD | 26/04/2022 | 21 | NARESH SEN | 8.09 | 0 | 0 | 1
3051 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of Pump House (3.60 m x 2.40 m ) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-ii Water Supply Scheme under Jalpaiguri Division , P.H.Engineering Dte. | 1195/JD | 20/05/2022 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 0 | 0 | 1
3052 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1012/NMD | 28/07/2022 | 21 | M/S RATAN KUMAR DASGUPTA AND CO. | 2.77 | 0 | 0 | 0
3053 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Installation of Infrastructure COST at SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060680, Reference ID : 860250380] | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.1 | 0 | 0 | 0
3054 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | New Service Connection Charge for SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002969126, Reference ID :402855384] | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.66 | 0 | 0 | 0
3055 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | New Service Connection Charge for SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002970357, Reference ID :402858305] | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3056 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Installation of Infrastructure COST at SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060668, Reference ID : 860250378] | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0 | 0
3057 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | 1194/JD | 20/05/2022 | 45 | MANAB BAKSHI | 4.65 | 0 | 0 | 0
3058 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1109/NMD | 07/09/2022 | 30 | MALAY KUMAR SAHA | 8.26 | 0 | 0 | 100
3059 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0 | 0 | 0
3060 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of different stationary for office use under Jalpaiguri division, P.H.E. Dte. as per annexure- I. | 358/JD | 17/02/2023 | 7 | SUBRATA ART PRESS | 1.64 | 0 | 0 | 1
3061 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | 1020/JD | 21/08/2023 | 45 | M/S M.B. DESIGN | 33.17 | 0 | 0 | 0
3062 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-II under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1413/JD | 13/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 0 | 0 | 1
3063 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-I under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | 1414/JD | 13/07/2022 | 15 | M.K. KAYAL & ASSOCIATES | 2.26 | 0 | 0 | 1
3064 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of different stationary for office use under Jalpaiguri Division, P.H.E. Dte. as per Annexure- I. | 357/JD | 17/02/2023 | 7 | JAGRITI PRESS | 1.71 | 0 | 0 | 1
3065 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 400 CUM AND 20 M STAGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPARMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE I) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ DISTRICT:JALPAIGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | 876/JD | 05/04/2022 | 180 | UMWELT ENGINEER PRIVATE LIMITED | 94.23 | 0 | 0 | 100
3066 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Material Requisition To Resource Division | 1233/JD | 12/09/2023 | 0 | Resource Division | 41 | 0 | 0 | 0
3067 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I, PHE Dte. For the month of june to august 2023 | BP-2023-24-418 | 06/10/2023 | 0 | RUPA PRASAD | 1.03 | 0 | 0 | 0
3068 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | ADDITIONAL Infrastructure Cost for SANYASHI KATA, ZONE-I,T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000091299, Reference ID : 860282879] | BP/23-24/143 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0 | 0
3069 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | 2128/JD | 18/01/2024 | 182 | MD AMIRUL ISLAM | 0.88 | 0 | 0 | 30
3070 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | CONSTRUCTION OF RCC OVERHEAD RESERVOUR CAPACITY 550 CUM AND 20 M STAGING HEIGHT INCLUDING AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE- II) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT,JALPAIGURI | 2393/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 113.02 | 0 | 0 | 0
3071 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Laying distribution system with FHTC for Augmentation of Sannyasikata Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | 1228/JD | 01/06/2022 | 120 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.85 | 0 | 0 | 100
3072 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Laying distribution system for Augmentation of Sannyasikata Piped water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | 1100/JD | 12/05/2022 | 90 | UMWELT ENGINEER PRIVATE LIMITED | 540.04 | 0 | 0 | 100
3073 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 1011/NMD | 28/07/2022 | 21 | M/S CHANDRANATH MUKHERJEE | 2.18 | 0 | 0 | 100
3074 | JALPAIGURI | Northern Mechanical | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1067/NMD | 29/08/2022 | 30 | DEY ENTERPRISE(MALDA) | 8.01 | 0 | 0 | 100
3075 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-II under Jalpaiguri Division, PHE Dte. | 1353/JD | 26/09/2023 | 45 | RAGHU DAS | 48.86 | 0 | 0 | 100
3076 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell Site at Sannyasikata Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2312/JD | 07/02/2024 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.81 | 0 | 0 | 100
3077 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying Pipe line for H/W Site at Sannyasikata Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 2630/JD | 07/03/2024 | 294 | SADHAN KARMAKAR | 26.72 | 0 | 0 | 85
3078 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Interconnection of Iron Elimination Plant to Rising Main, and other Ancillary Works at Sannyasikata Zone-II Head Work Site at Sannyasikata PWSS Rajganj Block, under Jalpaiguri Division P.H.E. Dte. | 1285/JD | 03/09/2024 | 30 | RAGHU DAS | 8.11 | 0 | 0 | 100
3079 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Material Requisition To Resource Division | 2207/JD | 01/12/2024 | 0 | Resource Division | 39.29 | 0 | 0 | 0
3080 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of October 2024. | BP-2024-25-524 | 29/11/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0 | 0
3081 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of Fuel (Diesel) ofVehicle No. WB 71 A 5131 for the Month of August 2024. | BP-2024-25-370 | 13/09/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3082 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of September 2024. | BP-2024-25-482 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3083 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Supply of Fuel (Diesel) of Vehicle No WB 71 A 5131 for the Month of July 2024. | BP-2024-25-333 | 28/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3084 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-I) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | 840/JD | 04/04/2023 | 697 | ARUP SARKAR | 10.16 | 0 | 0 | 50
3085 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of Different Component of water supply work and other ancillary work at Kalinagar Hospital More at Sannyasikata Zone-II under Sannyasikata PWSS of Rajganj Block under Jalpaiguri Division PHE, Dte. | 2756/JD | 15/03/2024 | 550 | SHREE KRISHNA ENTERPRISE | 75.06 | 0 | 0 | 75
3086 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.07.2024 to 21.01.2025) | 659/JD | 12/07/2024 | 184 | MD AMIRUL ISLAM | 0.88 | 0 | 0 | 0
3087 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Construction of boundary wall with gate,drain and pathway and laying pipe line for Sannyasikata zone II H/W Site at Sannyasikata PWSS Site piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1419/JD | 20/09/2024 | 147 | PRABIR SHOME | 18.38 | 0 | 0 | 0
3088 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.03.2025 to 31.03.2025) | 71/HQ/JD | 28/02/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0 | 0
3089 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.01.2025 to 28.02.2025) | 15/HQ/JD | 20/01/2025 | 38 | MD AMIRUL ISLAM | 0.19 | 0 | 0 | 0
3090 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | 62/JD | 18/04/2023 | 928 | RANJIT KARMAKAR | 31.21 | 0 | 0 | 100
3091 | JALPAIGURI | Jalpaiguri Division | Augmentation of Sannyasikata Piped Water Supply Scheme , SM/09996 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | 1432/JD | 05/10/2023 | 510 | M/S M.B. DESIGN | 33.17 | 0 | 0 | 85
3092 | JALPAIGURI | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Material Requisition To Resource Division | 168/JD | 28/04/2023 | 0 | Resource Division | 23.28 | 0 | 0 | 0
3093 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 439/SMSD | 28/03/2024 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0 | 0 | 0
3094 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | 440/SMSD | 28/03/2024 | 7 | S.P. ENTERPRISE | 0.73 | 0 | 0 | 0
3095 | JALPAIGURI | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Material Requisition To Resource Division | 2051/JD | 09/01/2024 | 0 | Resource Division | 13.02 | 0 | 0 | 0
3096 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-I, under FULBARIHAT CCC APPLICATION NO. 4003359104 Reference ID : 403178079 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
3097 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | New Service Connection Charge for MAHANVITA,ZONE-II,T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003365271 Reference ID : 403182689 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0 | 0
3098 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Additional New Service Connection Charge for MOHANBHITA, T/W-III, ZONE-I,under FULBARI CCC APPLICATION NO. 4003338759 Reference ID : 860296643 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0 | 0
3099 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Infrastructure Cost for MOHONVITA, ZONE-II T/W-I, under FULBARI CCC [APPLICATION NO. 4003338806 , Reference ID : 403162021] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.89 | 0 | 0 | 0
3100 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003359089 Reference ID : 403178078 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0 | 0
3101 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Additional New Service Connection Charge for MOHANBHITA, T/W-I, ZONE-II,under FULBARI CCC APPLICATION NO. 4003338806 Reference ID : 860296639 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0 | 0
3102 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Infrastructure Cost for MOHONVITA, ZONE-I T/W-III, under FULBARI CCC [APPLICATION NO. 4003338759 , Reference ID : 403161865] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0 | 0
3103 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MAHANBHITA PWSS, ZONE-I AND II, TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 467/NMD | 25/04/2023 | 982 | M/S P.P. ELECTRICALS | 73.36 | 0 | 0 | 95
3104 | JALPAIGURI | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Construction of different components of Mahanbhita (Zone-I and II) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc under Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division, P.H.E. Dte. | 367/JD | 26/05/2023 | 965 | MINTU CHAKRABORTY | 512 | 0 | 0 | 40
3105 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
3106 | JALPAIGURI | Jalpaiguri Division | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Construction of boundary wall with gate, drain, Land development and pathway including laying pipe line at Mahanbhita Zone-I (HW site & 2nd site) and Mahanbhita Zone-II (HW site, 2nd site and 3rd site) of Mahanbhita piped water supply scheme i.c.w. JJM under Jalpaiguri Division, P.H.E. Dte. | 270/JD | 07/02/2025 | 75 | SANKAR DAS | 80.69 | 0 | 0 | 30
3107 | JALPAIGURI | Northern Mechanical | MAHANBHITA PIPED WATER SUPPLY SCHEME , SM/13702 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3108 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Emergent repairing of Over Head Reservior(OHR) at Syli Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 346/JD | 16/02/2023 | 30 | RAGHU DAS | 4.12 | 0 | 0 | 1
3109 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Material Requisition To Resource Division | 1094/JD | 24/08/2023 | 0 | Resource Division | 9.89 | 0 | 0 | 0
3110 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Sinking of 2 Nos. Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling i.c.w Rejuvenation of Syli Tea Garden Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, PHE Dte. | 1354/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 40.77 | 0 | 0 | 60
3111 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Supply and Delivery of C.I special for as when as required at T/W No-I of SYLI TG and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1058/HQ/NMD | 21/06/2024 | 7 | BONANZA ENTERPRISE | 0.73 | 0 | 0 | 100
3112 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | New Service Connection Charge for REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003343252 Reference ID : 403165542 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3113 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | New Service Connection Charge for REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003343254 Reference ID : 403165543 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3114 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000101047 Reference ID : 860293437 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0 | 0
3115 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000101048 Reference ID : 860293438 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0 | 0
3116 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Construction of different components of Rejuvenation of Syli Tea Garden PWSS i.e TW, Pump Houses, Boundary Walls, Water Distribution Network(convertion), Rising Main etc in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division,P.H.E Dte. | 128/JD | 28/04/2023 | 654 | SAHA CONSTRUCTION | 104.75 | 0 | 0 | 90
3117 | JALPAIGURI | Northern Mechanical | Rejuvenation of Syli Tea Garden Area Piped Water Supply Scheme , SM/15117 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SYLI TG PWSS, TW no III & IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1489/NMD | 17/08/2023 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 23.84 | 0 | 0 | 80
3118 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME , SM/15089 | Augmentation | Construction of different components of Rejuvenation of Ambari Falakata PWSS ie. TW, Pump Houses, Water distribution Network, IEP etc. in connection with Jal Jeevan Mission at Rajganj Block, under Jalpaiguri Division, P.H.E.Dte. | 429/JD. | 08/06/2023 | 663 | KANAI LAL SEN | 82.62 | 0 | 0 | 85
3119 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME , SM/15089 | Augmentation | Overhauling and Reconditioning of The IEP (2 Unit) other Ancillary Works at Ambari Falakata H/W Site at Block Rajganj, under Jalpaiguri Division, P.H.E. Dte. | 1292/JD | 04/09/2024 | 30 | BAJRANG ENTERPRISE | 12.02 | 0 | 0 | 100
3120 | JALPAIGURI | Northern Mechanical | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME , SM/15089 | Augmentation | New Service Connection Charge for AMBARI FALAKATA, T/WNO. V under FULBARIHAT CCC APPLICATION NO. 4003385989 Reference ID : 403199279 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.12 | 0 | 0 | 0
3121 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF AMBARI FALAKATA PIPED WATER SUPPLY SCHEME , SM/15089 | Augmentation | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Ambari Falakata P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | 158/JD | 19/01/2022 | 60 | MAA ENTERPRISES | 4.65 | 0 | 0 | 100
3122 | JALPAIGURI | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | Material Requisition To Resource Division | 2211/SWSD | 05/01/2023 | 0 | Resource Division | 31.37 | 0 | 0 | 0
3123 | JALPAIGURI | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PORJHAR PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE | 264/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 2.77 | 0 | 0 | 30
3124 | JALPAIGURI | Northern Mechanical | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | New Service Connection Charge for PORAJHAR, T/W No. II, under SHIVMANDIR CCC [APPLICATION NO. 4003332377 , Reference ID : 403156964] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.14 | 0 | 0 | 0
3125 | JALPAIGURI | Northern Mechanical | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | New Service Connection Charge for PORAJHAR, T/W No. I, under SHIVMANDIR CCC [APPLICATION NO. 4003332364 , Reference ID : 403156961] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.78 | 0 | 0 | 0
3126 | JALPAIGURI | Siliguri W/S Division | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | Laying distribution system,risingmain,installation of iron elemination plant, pump houses ,boundary walls ,functional house hold tap connection (FHTC) and other allied works under Jal Jeevan Mission (JJM) for Augmentation of PORJHAR Piped Water Supply Scheme under Rajganj Block under Siliguri Sub Division, P.H.E. Dte. | 1158/SWSD | 09/08/2023 | 874 | AKASH ENTERPRISE | 356.29 | 0 | 0 | 90
3127 | JALPAIGURI | Northern Mechanical | Augmentation of Porjhar Pipe Water Supply Scheme , SM/15302 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PORJHAR PWSS,ZONE-I,TW NO-I AND ZONE-II,TW NO-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1316/NMD | 04/08/2023 | 606 | S.D. CONCERN WORKSHOP | 23.48 | 0 | 0 | 100
3128 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Material Requisition To Resource Division | 1067/JD | 24/08/2023 | 0 | Resource Division | 17.44 | 0 | 0 | 0
3129 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at MATHACHULKA Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. | 92/JSSD | 22/07/2022 | 15 | DEBABRATA SARKAR | 4.62 | 0 | 0 | 100
3130 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Construction of different components of Rejuvenation of Mathachulka PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. | 701/JD | 13/07/2023 | 539 | M/S. D.K. DEY & CO.. | 77.02 | 0 | 0 | 85
3131 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Material Requisition To Resource Division | 2069/JD | 10/01/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
3132 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | "New Service Connection Charge fo MATHACHULKA PWSS TW NO-III, METELI CCC " APPLICATION NO.4003386724 Reference ID : 403200293 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3133 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | "INFRA COST IRO NSC POLECASE for MATHACHULKA TW-IV(NEW MASJID),METELI CCC " Reference No-860314555 Application No-100000120355 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
3134 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | "New Service Connection Charge for MATHACHULKA TW-IV(NEW MASJID),METELI CCC Reference ID:403285589 Application Id:4003505421 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3135 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | "INFRA COST IRO NSC for (REJU) MATHACHULKA TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105524 Reference ID : 860297574 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.59 | 0 | 0 | 0
3136 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0 | 0
3137 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Balance work in connection with Laying Distribution System at Mathachulka Piped Water Supply Scheme in connection with Jal Jeevan Mission at Matiali Block under Jalpaiguri Division, PHE Dte. | 2166/JD | 30/10/2025 | 30 | DEEP CONSTRUCTION | 24.8 | 0 | 0 | 0
3138 | JALPAIGURI | Northern Mechanical | Rejuvenation of Mathachulka Piped Water Supply Scheme , SM/15098 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MATHACHULKA PWSS, TW no III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1214/NMD | 26/07/2023 | 736 | MUSTAFI CONCERN | 22.13 | 0 | 0 | 100
3139 | JALPAIGURI | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Material Requisition To Resource Division | 1073/JD | 24/08/2023 | 0 | Resource Division | 17.26 | 0 | 0 | 0
3140 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIDAM JHORA TEA GARDEN PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 1312/NMD | 04/08/2023 | 789 | MERCURY ENGINEERING COMPANY | 24.55 | 0 | 0 | 70
3141 | JALPAIGURI | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3142 | JALPAIGURI | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Nidam Jhora Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2334/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 0 | 0 | 100
3143 | JALPAIGURI | Jalpaiguri Division | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Material Requisition To Resource Division | 2023/JD | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0 | 0
3144 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Infrastructure development cost for new service connection at NIDAM JHORA TG, TW NO-I & II, MAL CCC APPLICATION NO. 100000104805 Reference ID : 860297125 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.19 | 0 | 0 | 0
3145 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | New Service Connection Charge for NIDAM JHORA TG, TW NO-I, MAL CCC APPLICATION NO. 4003299874 Reference ID : 403130047 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3146 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | New Service Connection Charge for NIDAM JHORA TG, TW NO-II, MAL CCC APPLICATION NO. 4003299885 Reference ID : 403130043 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3147 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
3148 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3149 | JALPAIGURI | Northern Mechanical | NIDAM JHORA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14911 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3150 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS , SM/15071 | Augmentation | Land devlopment at 2nd site under Raipur T.G. Piped Water Supply Scheme under Jalpiaiguri Division,P.H.E.Dte. | 286/RWS | 29/03/2023 | 10 | NEW KUNDU ENTERPRISE | 0.98 | 0 | 0 | 100
3151 | JALPAIGURI | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS , SM/15071 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF RAIPUR TEA GARDEN PWSS,at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1544/NMD | 01/09/2023 | 30 | SAIKAT SINHA | 12.42 | 0 | 0 | 100
3152 | JALPAIGURI | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS , SM/15071 | Augmentation | New Service Connection Charge for RAIPUR TEA GARDEN,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003343597 Reference ID : 403174733 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.87 | 0 | 0 | 0
3153 | JALPAIGURI | Northern Mechanical | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS , SM/15071 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
3154 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF RAIPUR TEA GARDEN AREA PWSS , SM/15071 | Augmentation | Construction of different components of Rejuvenation of Raipur T.G. PWSS i.e TW, pump houses,water distribution network, Boundary wall, Rising main, etc in connection with JJM at Block - Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | 385/JD | 01/06/2023 | 639 | NEW KUNDU ENTERPRISE | 49.45 | 0 | 0 | 100
3155 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 169/RWS | 28/02/2023 | 21 | NEW KUNDU ENTERPRISE | 2.99 | 0 | 0 | 100
3156 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DAKSHIN SALBARI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1218/NMD | 26/07/2023 | 30 | SUDIP DUTTA | 11.49 | 0 | 0 | 0
3157 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Material Requisition To Resource Division | 1068/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0 | 0
3158 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Construction of C.C. drain (extension) at front side of head work site along the road to drain out over flow water of OHR under Dakshin Salbari Water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 386/RWS | 25/04/2023 | 14 | NEW KUNDU ENTERPRISE | 2.41 | 0 | 0 | 100
3159 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Laying of Wash out line and distribution line over jhora at Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 518/JD | 27/06/2024 | 14 | NEW KUNDU ENTERPRISE | 1.9 | 0 | 0 | 100
3160 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF DAKSHIN SALBARI,T/W-III, GAIRKATA CCC APPLICATION NO. 100000110784 Reference ID : 860303154 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.33 | 0 | 0 | 0
3161 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Fuel,lubricant, stearing oil charges for Government inspection vehicle,NMD,PHE,Dte Invoice no-0059/2023-2024, Dt-30/09/23 |  | 22/08/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.3 | 0 | 0 | 0
3162 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF DAKSHIN SALBARI,T/W-III, GAIRKATA CCC APPLICATION NO. 4003438171 Reference ID : 403238894 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
3163 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Construction of different components for Rejuvenation of Dakshin Shalbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Banarhat under Jalpaiguri Division, P.H.E.Dte. | 437/JD. | 08/06/2023 | 784 | RABINDRANATH DUTTA | 56.71 | 0 | 0 | 70
3164 | JALPAIGURI | Northern Mechanical | REJUVENATION OF DAKSHIN SALBARI PWSS , SM/15087 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3165 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Material Requisition To Resource Division | 154/JD | 28/04/2023 | 0 | Resource Division | 17.1 | 0 | 0 | 0
3166 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Material Requisition To Resource Division | 2003/JD | 08/01/2024 | 0 | Resource Division | 6.23 | 0 | 0 | 0
3167 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-I, under HALDIBARI CCC , [APPLICATION NO. 4003341115, Reference ID : 403164679] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.66 | 0 | 0 | 0
3168 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0 | 0
3169 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Infrastructure Cost for BINNAGURI T/W-II, under HALDIBARI CCC , [APPLICATION NO. 4003341205, Reference ID : 403165171] | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.38 | 0 | 0 | 0
3170 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0 | 0
3171 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0 | 0
3172 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Balance Laying Distribution System and Functional Household Tap Connection for Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. | 482/JD | 11/03/2025 | 333 | BISWANATH GHOSH | 18.65 | 0 | 0 | 0
3173 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3174 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Construction of different components of Binnaguri PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. | 751/JD | 24/03/2023 | 725 | BISWANATH GHOSH | 226.15 | 0 | 0 | 100
3175 | JALPAIGURI | Northern Mechanical | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BINNAGURI(JALPAIGURI SADAR BLOCK) PWSS, TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1310/NMD | 04/08/2023 | 728 | UTTAM PAUL | 22.21 | 0 | 0 | 100
3176 | JALPAIGURI | Jalpaiguri Division | BINNAGURI PIPED WATER SUPPLY SCHEME , SM/14198 | New | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site of Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, PHE Dte. | 1175/JD | 23/08/2024 | 60 | BISWANATH GHOSH | 27.55 | 0 | 0 | 100
3177 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Material Requisition To Resource Division | 1078/JD | 24/08/2023 | 0 | Resource Division | 38.3 | 0 | 0 | 0
3178 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS at TW NO I,II, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 654/NMD | 15/03/2024 | 382 | SUBHRANGSHU GUHARAJA | 23.9 | 0 | 0 | 50
3179 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3180 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Material Requisition To Resource Division | 2074/JD | 10/01/2024 | 0 | Resource Division | 8.03 | 0 | 0 | 0
3181 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 100000109538 Reference ID : 860301298 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | 0
3182 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 4003426904 Reference ID : 403231622 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3183 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 4003477836 Reference ID : 403266830 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3184 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 4003477826 Reference ID : 403266831 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3185 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 100000117355 Reference ID : 860311645 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0 | 0
3186 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 100000117353 Reference ID : 860311643 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.85 | 0 | 0 | 0
3187 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | New Service Connection Charge for BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 4003426943 Reference ID : 403231623 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3188 | JALPAIGURI | Northern Mechanical | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 100000109544 Reference ID : 860302004 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0 | 0
3189 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Construction of differet components of Baragharia Zone-II PWSS i.e TW, Pump Houses, Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. in connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E Dte. | 357/JD. | 25/05/2023 | 180 | M.S ENTERPRISE | 166.28 | 0 | 0 | 65
3190 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Construction of differet components of Baragharia Zone-I PWSS i.e TW, Pump Houses , Water distribution Network, OHR, Boundary Wall , RISING MAIN , FHTC etc. in connection with Jal Jeevan Mission at Block Kranti under Jalpaiguri Division , P.H.E Dte. | 356/JD | 25/05/2023 | 860 | M.S ENTERPRISE | 246.82 | 0 | 0 | 40
3191 | JALPAIGURI | Jalpaiguri Division | BARA GHARIA PIPED WATER SUPPLY SCHEME , SM/15967 | New | Construction of Additional Components for uncovered TANTY PARA AREA of BARAGHARIA PWSS i.e. TW, Pump House ,Boundary Wall, Water distribution Network ,FHTC, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | 570/JD | 25/03/2025 | 75 | SADHAN KARMAKAR | 113.85 | 0 | 0 | 0
3192 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MATHACHULKA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15617 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
3193 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MATHACHULKA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15617 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3194 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MOHITNAGAR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15618 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
3195 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF MOHITNAGAR PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15618 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3196 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF WATER SUPPLY SCHEME OF JITI TEA GARDEN UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15622 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
3197 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF WATER SUPPLY SCHEME OF JITI TEA GARDEN UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15622 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3198 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DWARIKAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15608 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
3199 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF DWARIKAMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15608 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3200 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | Balance work of Laying pipeline & providing FHTC with allied works at Haritalguri Piped Water Supply Scheme in connection with JJM within Banarhat Block under Jalpaiguri Division, PHE Dte. | 2425/JD | 24/12/2024 | 45 | M/S ROY & SARKAR CONSTRUCTION | 32.68 | 0 | 0 | 0
3201 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Banarhat block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | 1288/RWS | 28/11/2023 | 30 | SUKES BASU MAJUMDAR | 3.11 | 0 | 0 | 100
3202 | JALPAIGURI | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | New Service Connection Charge for HARITALGURI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003332995 , Reference ID : 403157461] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0 | 0
3203 | JALPAIGURI | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
3204 | JALPAIGURI | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3205 | JALPAIGURI | Northern Mechanical | Rejuvenation of Haritalguri Tea Garden Area Piped Water Supply Scheme , SM/16772 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HARITALGURI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1390/NMD | 09/08/2023 | 542 | SUBHRA ENTERPRISE | 11.7 | 0 | 0 | 100
3206 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15605 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
3207 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15605 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3208 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KAJALDIGHI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15612 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
3209 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF KAJALDIGHI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15612 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3210 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | "INFRA COST IRO NSC for (REJU) ENGO TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.100000105521 Reference ID : 860297571 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.14 | 0 | 0 | 0
3211 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | "INFRA COST IRO NSC for (REJU)ENGO TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105439 Reference ID : 860297569 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.71 | 0 | 0 | 0
3212 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | "New Service Connection Charge for(REJU)ENGO TG PWSS TW NO-III, METELI CCC " APPLICATION NO.4003385947 Reference ID : 403199267 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3213 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | "New Service Connection Charge for(REJU)ENGO TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.4003385787 Reference ID : 403199269 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3214 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | Construction of different components of Rejuvenation of Engo Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Metiali under Jalpaiguri Division, P.H.E.Dte. | 442/JD. | 08/06/2023 | 604 | GOUTAM DAS | 46.29 | 0 | 0 | 100
3215 | JALPAIGURI | Northern Mechanical | REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , SM/17681 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ENGO TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1396/NMD | 09/08/2023 | 570 | SARKAR ELECTRIC | 24.64 | 0 | 0 | 100
3216 | JALPAIGURI | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Material Requisition To Resource Division | 1839/JD | 15/12/2023 | 0 | Resource Division | 12.71 | 0 | 0 | 0
3217 | JALPAIGURI | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003249150, Reference ID : 403091826] | BP/23-24/170 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.88 | 0 | 0 | 0
3218 | JALPAIGURI | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | New Service Connection Charge for BARAGHARIA, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003248664, Reference ID : 403090252] | BP/23-24/170 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0 | 0
3219 | JALPAIGURI | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Construction of different components of Baragharia PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | 93/JD | 25/04/2023 | 1096 | SCEC BOENTER KDAS JOINT VENTURE | 431.11 | 0 | 0 | 75
3220 | JALPAIGURI | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Providing FHTC in the command area of Baragharia PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, PHE Dte. | 111/JD | 16/01/2025 | 45 | SWAPAN SAHA | 22.58 | 0 | 0 | 0
3221 | JALPAIGURI | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
3222 | JALPAIGURI | Jalpaiguri Division | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Balance work for Laying Distribution System at Baragharia Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Dhupguri under Jalpaiguri Division, PHE Dte. | 2167/JD | 30/10/2025 | 30 | S. DUTTA | 26.33 | 0 | 0 | 0
3223 | JALPAIGURI | Northern Mechanical | BARAGHARIA Piped Water Supply Scheme. , SM/17649 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS,at TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1331/NMD | 08/08/2023 | 406 | B.B. CONCERNED | 24.52 | 0 | 0 | 100
3224 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Material Requisition To Resource Division | 1373/JD | 27/09/2023 | 0 | Resource Division | 39.87 | 0 | 0 | 0
3225 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0 | 0 | 70
3226 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3227 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0 | 0 | 0
3228 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Material Requisition To Resource Division | 2026/JD | 09/01/2024 | 0 | Resource Division | 20.96 | 0 | 0 | 0
3229 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344833, Reference ID : 403166837] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3230 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of Fuel bill for the Month of August'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-563 | 20/12/2024 | 0 | FILL & SMILE | 0.24 | 0 | 0 | 0
3231 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101170, Reference ID : 860293440] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.67 | 0 | 0 | 0
3232 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3233 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of Fuel bill for the Month of JuLY,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-416 | 01/10/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
3234 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 4003299833 , Reference ID : 403130048] | BP/23-24/266 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3235 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of Fuel bill for the Month of June,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-418 | 01/10/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0 | 0
3236 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Infrastructure Cost for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 100000096849 , Reference ID : 860287699] | BP/23-24/269 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.91 | 0 | 0 | 0
3237 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344844, Reference ID : 403166840] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3238 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101049, Reference ID : 860293439] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0 | 0
3239 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Infrastructure Cost for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 100000096848 , Reference ID : 860287698] | BP/23-24/267 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0 | 0
3240 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | New Service Connection Charge for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 4003299838 , Reference ID : 403130049] | BP/23-24/268 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3241 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Construction of different components of New Clenco T.G. (P) (Zone-I & II) PWSS i.e. TW, Pump Housese,Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | 798/JD. | 24/07/2023 | 601 | MD HAKIMUDDIN | 554.35 | 0 | 0 | 100
3242 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0 | 0 | 50
3243 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0 | 0 | 0
3244 | JALPAIGURI | Jalpaiguri Division | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Sinking of 3 (Three) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of New Clenco TG PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 2432/JD | 24/12/2024 | 373 | MD HAKIMUDDIN | 53.54 | 0 | 0 | 100
3245 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0 | 0
3246 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
3247 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3248 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3249 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Additional Works in connection with Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 690/HQ/NMD | 28/02/2025 | 7 | ANUP BASU | 0.91 | 0 | 0 | 0
3250 | JALPAIGURI | Northern Mechanical | NEW CALENCO TEA GARDEN (P) PIPED WATER SUPPLY SCHEME , SM/18357 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1586/NMD | 08/09/2023 | 754 | ANUP BASU | 52.66 | 0 | 0 | 70
3251 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Sinking of Deep Tube well by Odex - 165 Method of drilling at 3rd tube well site for Rejuvenation of Nayasily Tea Garden Piped water Supply scheme under Jalpaiguri Division, P.H.E. Dte." | 837/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.61 | 0 | 0 | 0
3252 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Sinking of Deep Tube Well by Odex -165 Method of drilling at 4th tube well site for Rejuvenation of Nayasily Tea Garden Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte." | 838/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.62 | 0 | 0 | 0
3253 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) for Nayasaily T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. | .1065/JSSD | 24/01/2022 | 20 | R.B TESTING | 2.01 | 0 | 0 | 100
3254 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Construction of Boundary Wall with gate, drain, and pathway for 3rd tube-well site of Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. | 1260/JSSD | 25/03/2022 | 20 | ROY CONSTRUCTION | 4.79 | 0 | 0 | 100
3255 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Providing Tap Water Supply Connection in Connection with Jaldhara /Jalswapna in School, ICDS Centre and Health Centre at Hope TG,Naya Sily TG, Jiti TG,Nagrakata & Nagrakata TG Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,P.H.E. Dte. | 88/JSSD | 22/07/2022 | 10 | GOUTAM DAS | 3.64 | 0 | 0 | 0
3256 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Construction of Pump House (3.60 m x 2.40m) size with sanitary and plumbing arrangement at 3rd tubewell site for Rejuvenation of Water Supply of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 24/JSSD | 21/06/2022 | 45 | SANJIT SARKAR | 4.76 | 0 | 0 | 100
3257 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Construction of boundary wall with gate, drain and pathway for 4th tube-well site for Rejuvenation of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 64/JSSD | 19/07/2022 | 20 | N.M. CONSTRUCTION | 4.77 | 0 | 0 | 100
3258 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) size including sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Nayasaily Tea Garden Water Supply Scheme for under Jalpaiguri Division, P.H.E Dte. | 63/JSSD | 19/07/2022 | 45 | N.M. CONSTRUCTION | 4.75 | 0 | 0 | 100
3259 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Infrastructure Cost for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072608, Reference ID : 860263638] | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.51 | 0 | 0 | 0
3260 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Infrastructure Cost for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072600, Reference ID : 860263630] | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0 | 0
3261 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | New Service Connection Charge for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097516, Reference ID : 402966975] | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3262 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | New Service Connection Charge for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003098584, Reference ID : 402967280] | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3263 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | 200 Cum OHR as per Departmental Design & Drawing for Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme Block- Nagrakata, District - Jalpaiguri. | 1081/JD | 29/04/2022 | 180 | SABITA ENTERPRISE | 55.26 | 0 | 0 | 100
3264 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAYASAILY TEA GARDEN PWSS,TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 334/NMD | 29/03/2023 | 30 | HARA PROSAD DAS | 21.5 | 0 | 0 | 70
3265 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Balance work in connection with providing Functional Household Tap Connection (FHTC) i.c.w. Jal Jeevan Mission under the command area of Rejuvenation of Nayasayli T.G. Area Piped W/S Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. (Phase-IV). | 1527/JD | 01/10/2024 | 20 | GAP ENGINEERS ENTERPRISES | 14.48 | 0 | 0 | 90
3266 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Replacement of UPVC pipeline with other allied works at Jungle Busty area i.c.w. Rejuvenation of Nayasaili Piped W/S Scheme under JJM at Nagrakata BLOCK, under Jalpaiguri Division,P.H.E.Dte. | 266/JSSD | 25/09/2024 | 38 | NEW KUNDU ENTERPRISE | 2.24 | 0 | 0 | 100
3267 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Material Requisition To Resource Division | 2110/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0 | 0
3268 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Sinking of a Rig Bored Tubewell by ODEX-165 method of drilling along with pump connection and other allied works at Champaguri Bazar area (5th TW Site) in connection with Jal Jeevan Mission of Rejuvenation of Naya Saily TG Piped Water Supply Scheme, Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | 463/JD | 11/03/2025 | 30 | NARESH SEN | 10.09 | 0 | 0 | 0
3269 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Balance work in connection with laying rising main with other allied works for Rejuvenation of Nayasayli Tea Garden Piped W/S Scheme under JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. | 259/JSSD | 25/09/2024 | 280 | GOLDEN KEY ENTERPRISE | 7.07 | 0 | 0 | 75
3270 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
3271 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nayasaily Tea Garden PWSS Piped water Supply Scheme , SM/09863 | Augmentation | Laying Rising Main for Rejuvenation of Nayasaily Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. | 799/JD.. | 29/03/2023 | 553 | GOLDEN KEY ENTERPRISE | 2.66 | 0 | 0 | 100
3272 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | fhtc basilardanga |  | 21/10/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0 | 0
3273 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | FHTC BASILARDANGA | BP-2021-22-87 | 01/11/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0 | 0
3274 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | fhtc basilar danga |  | 05/10/2021 | 0 | PARESH CHANDRA GUHA | 15 | 0 | 0 | 0
3275 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | FHTC PALASBARI PWSS | BP-2021-22-553 | 30/03/2022 | 0 | SANKAR DAS | 4.73 | 0 | 0 | 0
3276 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | FHTC BHANGARHAT PWSS | BP-2021-22-497 | 29/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 10.33 | 0 | 0 | 0
3277 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Basilardanga Piped Water Supply Scheme , SM/08077 | Retrofitting | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 0 | 0 | 100
3278 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme , SM/06845 | Retrofitting | PROVIDING FHTC FOR BHANGAMALI PWSS | 1195 | 04/02/2021 | 0 | MRINMOY KANTI DUTTA | 14.66 | 0 | 0 | 0
3279 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme , SM/06845 | Retrofitting | BHANGAMALI | BP-2021-22-203 | 19/01/2022 | 0 | MRINMOY KANTI DUTTA | 14.38 | 0 | 0 | 0
3280 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme , SM/06845 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0 | 0 | 1
3281 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme , SM/06845 | Retrofitting | Retrofitting works in connection with FHTC works along with PWD road from Prodhan Para to Putimari and different places at Bhangamali under Bhangamali Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1811/JD | 18/11/2021 | 15 | RABINDRANATH DUTTA | 17.81 | 0 | 0 | 1
3282 | JALPAIGURI | Siliguri W/S Division | Providing Functional House hold Tap Connection under Jal Jeevan & Jal Swapno programme for Porjhar Piped water Supply Scheme. , SM/07044 | Retrofitting | Continuation order for Hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte. Vivekananda Bhawan (2nd floor), Hill Cart Road, Siliguri for the period from 01.01.2024 to 31.07.2024 for Chief Engineer (Civil), Northern Zone, P.H.E. Dte. i.e.07 (seven) months. | 2396/SWSD | 16/12/2023 | 213 | PINKI DAM | 1.03 | 0 | 0 | 0
3283 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | Construction of boundary wall with gate,drain, Pipe line for H/W site of KILLKOTE T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 202/JD | 10/02/2021 | 30 | M/S SURAJIT DEY AND CO. | 14.94 | 0 | 0 | 0
3284 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | INSTALLATION IRON ELIMINATION PLANT | BP-2021-22-519 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.1 | 0 | 0 | 0
3285 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | soil test for kilkote | bp2022-23- | 14/06/2022 | 0 | G. TECH INDIA | 2.03 | 0 | 0 | 0
3286 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | CONST OF RISING MAIN CONNECTION FOR KILKOTE T.G | bp2022-23-49 | 07/06/2022 | 0 | GOUR KUMAR MITRA | 4.8 | 0 | 0 | 0
3287 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | RETRO FITTING WORK HOPE | BP-2021-22-327 | 28/02/2022 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 0.7 | 0 | 0 | 0
3288 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | CONST BLOWER ROOM PURBA DURAMARI WSS | BP-2021-22-520 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.78 | 0 | 0 | 0
3289 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | FHTC KILKOTE | BP-2021-22-328 | 28/02/2022 | 0 | M/S SURAJIT DEY AND CO. | 11.92 | 0 | 0 | 0
3290 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | SOIL INVESTIGATION WORK KILKOTE T.G | BP-2021-22-436 | 26/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0 | 0
3291 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | SOIL INVESTIGATION BHUSKA DANGA PWSS | BP-2021-22-424 | 25/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0 | 0
3292 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Kilkote Tea Garden Piped Water Supply Scheme. , SM/09461 | Augmentation | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 0 | 0 | 100
3293 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Basilardanga Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 642/JD | 08/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 0 | 0 | 1
3294 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Basilardanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 2011/JD | 01/11/2022 | 15 | SANKAR DAS | 6.64 | 0 | 0 | 1
3295 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2218/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 0 | 0 | 1
3296 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 850/NMD | 18/07/2022 | 30 | S.P. ENTERPRISE | 7.74 | 0 | 0 | 0
3297 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 851/NMD | 18/07/2022 | 30 | M/S ANJALI ENTERPRISE | 7.6 | 0 | 0 | 0
3298 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 570/NMD | 14/07/2022 | 21 | GURUKRIPA ENTERPRISE | 1.87 | 0 | 0 | 0
3299 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | 571/NMD | 14/07/2022 | 21 | HARAGOURI ENTERPRISE | 1.87 | 0 | 0 | 0
3300 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2219/JD | 27/12/2021 | 60 | PARESH CHANDRA ROY | 11.45 | 0 | 0 | 1
3301 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053960 ; Reference ID : 860243610] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.06 | 0 | 0 | 0
3302 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053938 ; Reference ID : 860243608] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.92 | 0 | 0 | 0
3303 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941265 ; Reference ID : 402831972] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3304 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Infrastructure cost for New Service Connection Charge for TW-III, of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057050 , Reference ID : 860246650] | BP/2022-23/30 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.57 | 0 | 0 | 0
3305 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941268 ; Reference ID : 402831980] | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3306 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 3rd tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. | 1603/JD | 18/08/2022 | 45 | SANDIP BANIK | 13.65 | 0 | 0 | 0
3307 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | 146/HQ/NMD | 31/07/2023 | 92 | UTTAM PAUL | 0.95 | 0 | 0 | 0
3308 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Reparing on OHR , pump house , IEP Room , boundary wall , construction of pathway , & other ancillary works for Basilardanga piped W/S/S under Jalpaiguri Division , P.H.E. Dte | 178/RWS | 03/03/2022 | 30 | PARESH CHANDRA GUHA | 4.85 | 0 | 0 | 0
3309 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. | 2067/JD | 04/11/2022 | 45 | R.S CONSTRUCTION | 13.65 | 0 | 0 | 100
3310 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 0 | 0 | 100
3311 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Retrofitting works & other ancillary works related to FHTC at different places of Basilardanga PWSS under Jalpaiguri Division, P.H.E. Dte. | 368/JD | 20/02/2023 | 15 | DIPAK KUMAR CHAKRABORTY | 1.81 | 0 | 0 | 0
3312 | JALPAIGURI | Northern Mechanical | Rejuvenation of Basilardanga piped water supply scheme. , SM/09460 | Augmentation | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte | 21/HQ/NMD | 20/04/2023 | 91 | UTTAM PAUL | 0.95 | 0 | 0 | 100
3313 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at DHARANIPUR TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block NAGRAKATA, district Jalpaiguri. | 356/NMD | 23/05/2022 | 30 | SUBODH KUMAR BANIK | 16.28 | 0 | 0 | 0
3314 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.100000110436 Reference ID : 860302766 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0 | 0
3315 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT " APPLICATION NO.4003435519 Reference ID : 403236673 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
3316 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG " APPLICATION NO.100000110433 Reference ID : 860302763 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.31 | 0 | 0 | 0
3317 | JALPAIGURI | Northern Mechanical | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.4003435908 Reference ID : 403236934 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
3318 | JALPAIGURI | Jalpaiguri Division | Supply of potable drinking water to Dharanipur Tea Garden in relation with Chaa Sundari Project. , SM/08578 | New | Construction of Different Components of Supply Of Potable Drinking Water To Dharanipur Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 2755/JD | 15/03/2024 | 413 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 71.04 | 0 | 0 | 55
3319 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | LDS BHUJARI PARA KRANTI ZONE II | BP-2021-22-439 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 4.7 | 0 | 0 | 0
3320 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Sinking of 2 No. 250 mm x 150 mm x 123 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Augmentation of Ramsai Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 633/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.35 | 0 | 0 | 0
3321 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 217/JD | 24/01/2022 | 60 | GOURAB GUHA ROY | 11.44 | 0 | 0 | 100
3322 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 2228/JD | 27/12/2021 | 60 | SANKAR DAS | 11.45 | 0 | 0 | 100
3323 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Laying Distribution System ( node 2-4-287-288-289-290-291-292 & node 5-134) for Augmentation of Ramsai Piped Water Supply Scheme under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. Block-Maynaguri. District- Jalpaiguri. | 730/JD | 22/03/2023 | 45 | R.S CONSTRUCTION | 25.64 | 0 | 0 | 100
3324 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Material Requisition To Resource Division | 181/JD | 21/01/2022 | 0 | Resource Division | 31.71 | 0 | 0 | 0
3325 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Material Requisition To Resource Division | 552/JD | 01/03/2022 | 0 | Resource Division | 28.13 | 0 | 0 | 0
3326 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | New Service Connection Charge for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164167, Reference ID : 403024435] | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3327 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Infrastructure Cost for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084431, Reference ID : 860276011] | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.71 | 0 | 0 | 0
3328 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Infrastructure Cost for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084158, Reference ID : 860276008] | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0 | 0
3329 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | New Service Connection Charge for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164165, Reference ID : 403024434] | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3330 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of RAMSAI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1057/HQ/NMD | 21/06/2024 | 7 | SUMON ELECTRICAL | 0.73 | 0 | 0 | 100
3331 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Construction of Boundary wall at H/W Site & 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF RAMSAI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | 187/JD | 21/01/2022 | 120 | PARESH CHANDRA GUHA | 108.89 | 0 | 0 | 100
3332 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-II) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT - JALPAIGURI. | 206/JD | 24/01/2022 | 90 | ASHIT KUMAR SINGHA | 221.07 | 0 | 0 | 100
3333 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Installation of Iron Elimination Plant (35 m3/hr) including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain...etc at H/W Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | 2268/JD | 21/11/2022 | 585 | M/S A.B.G. CONSTRUCTION | 29.33 | 0 | 0 | 100
3334 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Material Requisition To Resource Division | 2217/JD | 01/12/2024 | 0 | Resource Division | 20.02 | 0 | 0 | 0
3335 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF RAMSAI (PART-III) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT, JALPAIGURI. | 191/JD | 21/01/2022 | 1319 | M/S R.N. TRADERS | 187.78 | 0 | 0 | 100
3336 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-I) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT ¿ JALPAIGURI. | 190/JD | 21/01/2022 | 1118 | PARESH CHANDRA GUHA | 203.47 | 0 | 0 | 100
3337 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | 2015/JD | 01/11/2022 | 927 | M/S R.N. TRADERS | 14.7 | 0 | 0 | 100
3338 | JALPAIGURI | Jalpaiguri Division | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. | 140/JD | 17/01/2023 | 850 | R.S CONSTRUCTION | 14.7 | 0 | 0 | 60
3339 | JALPAIGURI | Northern Mechanical | Augmentation of Ramsai Water Supply Scheme. , SM/10033 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RAMSAI PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 270/NMD | 21/03/2023 | 346 | M/S PARITOSH BHOWMICK AND CO. | 20.2 | 0 | 0 | 100
3340 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Providing Functional Household Tap Connection in connection with Jalswapna near 18 no. line 15 no. line and allied areas for Hope T.G. PWSS under Jalpaiguri Division, PHE Dte. (Part-B) | 1049/JSSD | 24/01/2022 | 15 | GOUTAM DAS | 4.75 | 0 | 0 | 0
3341 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hope Tea Garden under Jalpaiguri Division, P.H.E. Dte. | 1467/JD | 25/07/2022 | 30 | PROSENJIT BASAK | 13.84 | 0 | 0 | 0
3342 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Repairing of 2 nos. of pump house (1st site & 2nd site) 3 nos. Boundary wall (Head work site, 1st site & 2nd site) with sanitary & plumbing arrangement and other allied works at Hope T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 1065/JSSD | 24/02/2022 | 30 | GOUTAM DAS | 4.08 | 0 | 0 | 0
3343 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Urgent Retrofitting works at LW Bungalow back side under Hope T.G. Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 187/JSSD | 31/08/2022 | 30 | NARAYAN CHANDRA ADHIKARY | 1.91 | 0 | 0 | 0
3344 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Disconnecting illegeal connections and street stand posts with repairing of distribution line at Rejuvenation of Chalsa (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 363/JD | 20/02/2023 | 14 | ALICK DATTA | 2.91 | 0 | 0 | 100
3345 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Construction of 2 nos. Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement and 2 nos. boundary wall with gate,drain and pathway for 3rd & 4th tubewell site of Hope TG piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | 632/JD | 13/03/2023 | 60 | PRADIP KUMAR SHIL | 16.98 | 0 | 0 | 100
3346 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | EMERGENT REPAIRING OF PIPE LINE INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER HOPE TG PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE. | 299/JSSD | 27/09/2023 | 45 | GOUTAM DAS | 3.37 | 0 | 0 | 100
3347 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Infrastructure Cost for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072368, Reference ID : 860263628] | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0 | 0
3348 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | New Service Connection Charge for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097490, Reference ID : 402966973] | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3349 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | New Service Connection Charge for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003097475, Reference ID : 402966977] | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3350 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Infrastructure Cost for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072607, Reference ID : 860263637] | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.56 | 0 | 0 | 0
3351 | JALPAIGURI | Northern Mechanical | Rejuvenation of Water Supply Scheme of HopeTea Garden Mouza , SM/09862 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HOPE T.G PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 465/NMD | 25/04/2023 | 30 | M/S P.P. ELECTRICALS | 21.6 | 0 | 0 | 100
3352 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Retrofitting works related with Jal swapna / JJM for Mateli Bazar area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | 1053 /JSSD | 24/01/2022 | 15 | GOURAB GUHA ROY | 3.1 | 0 | 0 | 0
3353 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Urgent Retrofitting works at Prem Nagar & Thakur line under Meteli Bazar Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. | 175/JSSD | 25/08/2022 | 30 | SUJAN LAMA | 3.14 | 0 | 0 | 1
3354 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 139//JD | 17/01/2023 | 30 | M/S KARMAKAR CONSTRACTION | 14.88 | 0 | 0 | 0
3355 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 138/JD | 17/01/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.88 | 0 | 0 | 0
3356 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1586/JD | 06/11/2023 | 45 | M/S SUNSHINE | 5.61 | 0 | 0 | 0
3357 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Providing Household Tap Connection 846 Nos. in connection with Jal Jeevan Mission at Mateli Bazar Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1669/JD | 24/11/2023 | 30 | DIPAK KUMAR CHAKRABORTY | 30.54 | 0 | 0 | 0
3358 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Meteli Bazar Zone-II area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1582/JD | 03/11/2023 | 180 | UNIVERSAL ENTERPRISES | 73.78 | 0 | 0 | 0
3359 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Providing Functional Household Tap Connection in Connection with Jaldhara/Jal Swapna near Jyoti Colony for Matiali Bazar Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 89/JSSD | 22/07/2022 | 10 | GOURAB GUHA ROY | 4.53 | 0 | 0 | 100
3360 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 849/JD | 06/04/2023 | 45 | M/S YADAV CONSTRUCTION | 5.44 | 0 | 0 | 100
3361 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | New Service Connection Charge for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO.4003117038, Reference ID : 403006108] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3362 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Infrastructure Cost for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO. 100000075619, Reference ID : 860267309] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.93 | 0 | 0 | 0
3363 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | New Service Connection Charge for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO.4003117033, Reference ID : 403006110] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3364 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Infrastructure Cost for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO. 100000076010, Reference ID : 860267310] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0 | 0
3365 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Infrastructure Cost for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO. 100000075618, Reference ID : 860267308] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.28 | 0 | 0 | 0
3366 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | New Service Connection Charge for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO.4003117034, Reference ID : 403006109] | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3367 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Sinking of One No. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 457/JD | 18/02/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 6.38 | 0 | 0 | 100
3368 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Sinking of Two Nos. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 456/JD | 18/02/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 12.75 | 0 | 0 | 100
3369 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Emergent repairing of HW site & 1st site Pump House with Sanitary and plumbing arrangement for Augmentation of Mateli Bazar(Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 283/JSSD | 26/09/2023 | 366 | M/S YADAV CONSTRUCTION | 6.32 | 0 | 0 | 100
3370 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Restoration work of damaged road due to lying of pipeline, GI works and other allied works under Rejuvenatioin of Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 496/JSSD | 02/01/2024 | 30 | NARAYAN CHAKRABORTY | 8.47 | 0 | 0 | 100
3371 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Sinking of 3 Nos. Big Dia Tube well by Modified DTH - ODEX Method at 6th, 7th & 8th tube well site of Rejuvenation of Mateli Bazar (Zone- I & II) Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 931/JD | 07/08/2024 | 45 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 52.84 | 0 | 0 | 100
3372 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF METELI BAZAR PWSS, ZONE-I, TW No II AND ZONE-II,TW NO- I and II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | 370/NMD | 29/03/2023 | 946 | ASHUTOSH DAS AND CO. | 38.04 | 0 | 0 | 30
3373 | JALPAIGURI | Northern Mechanical | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0 | 0
3374 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Providing Functional Water Tap Connection including laying pipeline in the command area of Metelibazar PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. | 104/JSSD | 30/05/2025 | 30 | SUJAN LAMA | 4.83 | 0 | 0 | 100
3375 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF METELIBAZAR PWSS , SM/11813 | Augmentation | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division P.H.E.Dte. | 1030/JD | 26/04/2022 | 1158 | NARAYAN CHAKRABORTY | 97.34 | 0 | 0 | 100
3376 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Material Requisition To Resource Division | 1087/JD | 24/08/2023 | 0 | Resource Division | 9.2 | 0 | 0 | 0
3377 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 100000104920 Reference ID : 860296940 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.8 | 0 | 0 | 0
3378 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT(REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO.100000104806 Reference ID : 860297126 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.52 | 0 | 0 | 0
3379 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO. 4003377480 Reference ID : 403192836 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3380 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 4003377472 Reference ID : 403192833 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3381 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
3382 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3383 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Construction of different components of Rejuvenation of Nakhati Tea Garden PWSS i.e TW, Pump Houses, Boundary Wall, Water Distribution Network (Conversion ), Rising main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division , P.H.E Dte. | 358/JD. | 25/05/2023 | 617 | D. S. ENTERPRISE | 66.52 | 0 | 0 | 40
3384 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAKHATI TEA GARDEN AREA PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1484/NMD | 17/08/2023 | 622 | PRATIK ROY | 24.25 | 0 | 0 | 100
3385 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nakhati Tea Garden Area Piped Water Supply Scheme , SM/15116 | Augmentation | Balance work, Construction of approaches to Pump House area and Land development inside PH area under Rejuvenation of Nakhati TG in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 122/JD | 16/01/2025 | 45 | ADITRI ENTERPRISE | 17.85 | 0 | 0 | 100
3386 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Minor repairing of Two nos. Pump House with Construction of Toilet and Sanitary Plumbing System located at head work site including Land Development work at 2nd Pummp house site and adjacent area along with ancillary work of Augmentation of Bhatiapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 1306/JD | 14/06/2022 | 21 | RABINDRANATH DUTTA | 3.93 | 0 | 0 | 100
3387 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 135 mtrs. Depth) by utilising Departmental machineries for Bhatipara PWSS, Dhupguri block under Jalpaiguri District, CDD PHE Dte. | 1776/CDD | 20/01/2023 | 30 | PADMA ENGINEERING & CO. | 12.61 | 0 | 0 | 100
3388 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | 132/CMSD-II(D) | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.72 | 0 | 0 | 100
3389 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-I) HW, Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | 131/CMSD-II(D) | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.79 | 0 | 0 | 100
3390 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing drilling crews for construction of Tube Well (250 mm x 150 mm x 88 mtrs depth) by SUPER RR Rig machine for Bhatiyapara PWSS Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | 219/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 4.64 | 0 | 0 | 100
3391 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing Tube Well materials conforming to IS : 12818 : 2010 with other works at site for construction of Tube well for Bhatiyapara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | 221/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 2.64 | 0 | 0 | 100
3392 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing additional Tubewell materials conforming to IS: 12818:2010 with other works at site for construction of Tubewell for Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | 133/CMSD-II | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.87 | 0 | 0 | 100
3393 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 130 mtrs. Depth) by utilising Departmental machineries for Bhatiapara W/S Scheme (Z-II,TW-III), Nagrakata block under Jalpaiguri District, CDD PHE Dte. | 875/CDD | 11/07/2023 | 30 | PADMA ENGINEERING & CO. | 13.53 | 0 | 0 | 100
3394 | JALPAIGURI | Central Drilling | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing strainer conforming to IS : 12818 : 2010 with other materials & works at site for construction of Tube well at Bhatipara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | 220/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 2.13 | 0 | 0 | 100
3395 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Material Requisition To Resource Division | 1065/JD | 24/08/2023 | 0 | Resource Division | 7.18 | 0 | 0 | 0
3396 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying Distribution System for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme (Part A & D) at Nagrakata Block Under Jalpaiguri Division, PHE Dte. | 1948/JD | 13/10/2022 | 120 | JAYANTA GHOSH | 241.53 | 0 | 0 | 60
3397 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-B) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | 2060/JD | 03/11/2022 | 21 | SAPTASWA SARKAR | 74.86 | 0 | 0 | 100
3398 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-II )Piped water Supply Scheme (Part-E) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | 1959/JD | 17/10/2022 | 21 | M/S SIBU DEY AND CO. | 81.95 | 0 | 0 | 95
3399 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | 2013/JD | 01/11/2022 | 21 | NEW KUNDU ENTERPRISE | 58.51 | 0 | 0 | 96
3400 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-I under Jalpaiguri Division, PHE Dte. | 1260/JD | 13/09/2023 | 719 | NARAYAN CHAKRABORTY | 56.64 | 0 | 0 | 6
3401 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Bhatia Para (Zone-II) Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | 1970/JD | 03/01/2024 | 21 | RABINDRANATH DUTTA | 18.51 | 0 | 0 | 0
3402 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3403 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara ( Zone-II ) Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | 2004/JD | 28/10/2022 | 21 | GOURAB GUHA ROY | 33.43 | 0 | 0 | 100
3404 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Material Requisition To Resource Division | 2209/JD | 01/12/2024 | 0 | Resource Division | 31.51 | 0 | 0 | 0
3405 | JALPAIGURI | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356887, Reference ID : 403176984] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0 | 0
3406 | JALPAIGURI | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-III, under BANARHAT CCC APPLICATION NO. 4003373992 Reference ID : 403189742 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0 | 0
3407 | JALPAIGURI | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101603, Reference ID : 860292663] | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.21 | 0 | 0 | 0
3408 | JALPAIGURI | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003373981 Reference ID : 403189738 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.13 | 0 | 0 | 0
3409 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of 450 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 240/JD | 08/05/2023 | 721 | JAYANTA GHOSH | 140.51 | 0 | 0 | 60
3410 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-II under Jalpaiguri Division, PHE Dte. | 1261/JD | 13/09/2023 | 718 | RANA DEY | 90.44 | 0 | 0 | 50
3411 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of 2nd Tube well site Boundary wall, Drain, Pathway and Laying of Rising main at Zone-I of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 268/JD | 07/02/2025 | 328 | RANA DEY | 9.33 | 0 | 0 | 0
3412 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of BHATIAPARA (ZONE-I) Piped Water Supply Scheme (PART-A) at Banarhut Block under Jalpaiguri Division, P.H.E Dte | 569/JD | 25/03/2025 | 372 | ANUP SARKAR | 146.75 | 0 | 0 | 0
3413 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of 3rd site Tube well Boundary wall, Drain, Pathway and Laying of Rising main at Zone-II of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 269/JD | 07/02/2025 | 147 | RANA DEY | 9.24 | 0 | 0 | 0
3414 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Laying distribution system for Augmentation of Bhatiapara (Zone-II ) Piped water Supply Scheme(Part-B) at Nagrakata Block under Jalpaiguri Division. P.H.E. Dte. | 1889/JD | 22/09/2022 | 1073 | RANA DEY | 65.49 | 0 | 0 | 97
3415 | JALPAIGURI | Jalpaiguri Division | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-I) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 1346/JD | 26/09/2023 | 462 | D. S. ENTERPRISE | 109.4 | 0 | 0 | 100
3416 | JALPAIGURI | Northern Mechanical | Augmentation of Bhatipara Water Supply Scheme , SM/13277 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BHATIAPARA PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte.. | 1895/NMD | 30/11/2023 | 444 | M/S P.P. ELECTRICALS | 32.53 | 0 | 0 | 85
3417 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Material Requisition To Resource Division | 158/JD | 28/04/2023 | 0 | Resource Division | 2.39 | 0 | 0 | 0
3418 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Construction of different components of Tandu PWSS i.e TW Pump Houses, Water distribution Network, OHR,RISING MAIN,FHTC etc. i.c.w JAL JEEVAN MISSION at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | 755/JD | 24/03/2023 | 1015 | PRADIP SAHA | 114.12 | 0 | 0 | 35
3419 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TANDU PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1339/NMD | 08/08/2023 | 30 | BLUE PINE | 12.03 | 0 | 0 | 100
3420 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Material Requisition To Resource Division | 2029/JD | 09/01/2024 | 0 | Resource Division | 2.44 | 0 | 0 | 0
3421 | JALPAIGURI | Jalpaiguri Division | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3422 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Infrastructure Cost for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 100000096118 ; Reference ID : 860288228] | BP/23-24/233 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0 | 0
3423 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | New Service Connection Charge for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 4003285461 ; Reference ID : 403120244] | BP/23-24/232 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0 | 0
3424 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0 | 0
3425 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0 | 0
3426 | JALPAIGURI | Northern Mechanical | PIPE WATER SUPPLY SCHEME FOR TANDU , SM/13990 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3427 | JALPAIGURI | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Material Requisition To Resource Division | 1375/JD | 27/09/2023 | 0 | Resource Division | 18.27 | 0 | 0 | 0
3428 | JALPAIGURI | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Material Requisition To Resource Division | 1836/JD | 15/12/2023 | 0 | Resource Division | 5.33 | 0 | 0 | 0
3429 | JALPAIGURI | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Construction of different components of Niranjan Pat PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 406/JD | 06/06/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 231.81 | 0 | 0 | 65
3430 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115928 Reference ID : 860309778 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0 | 0
3431 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003470466 Reference ID : 403261884 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
3432 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 4003470493 Reference ID : 403261885 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
3433 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 100000115926 Reference ID : 860309776 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.91 | 0 | 0 | 0
3434 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0 | 0
3435 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
3436 | JALPAIGURI | Jalpaiguri Division | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Niranjanpat Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 632/JD | 28/03/2025 | 45 | TIRTHANKAR CHOWDHURY | 24.06 | 0 | 0 | 0
3437 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
3438 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3439 | JALPAIGURI | Northern Mechanical | NIRANJANPAT WATER SUPPLY SCHEME , SM/13991 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIRANJANPATH PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1995/NMD | 21/12/2023 | 497 | ABHISEK ENGINEERING CONCERN | 20.45 | 0 | 0 | 100
3440 | JALPAIGURI | Northern Mechanical | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ANANDAPUR TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1317/NMD | 04/08/2023 | 30 | ABHISEK ENGINEERING CONCERN | 27.18 | 0 | 0 | 0
3441 | JALPAIGURI | Jalpaiguri Division | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Material Requisition To Resource Division | 1372/JD | 27/09/2023 | 0 | Resource Division | 27.51 | 0 | 0 | 0
3442 | JALPAIGURI | Jalpaiguri Division | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3443 | JALPAIGURI | Northern Mechanical | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3444 | JALPAIGURI | Northern Mechanical | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0 | 0
3445 | JALPAIGURI | Jalpaiguri Division | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Construction of different Components of ANANDAPUR T.G. PWSS i.e. 2 Nos Tube well, 2 Nos Pump house, Iron Elimination plant, 2 Nos Boundary Wall, Blower Room, Water distribution Network, 350 Cum OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. | 2153/JD | 17/10/2025 | 210 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 481.86 | 0 | 0 | 0
3446 | JALPAIGURI | Jalpaiguri Division | ANANDAPUR TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/14884 | New | Sub-Soil Investigation of proposed 350 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Anandapur Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 89-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0 | 0
3447 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Sinking of 2 Nos Deep Rig Bored Tube Well by ODEX-195 method of drilling with 2 Nos Pump House(3.6m X 2.4m) and Boundary Wall including Pump House to distribution Line Connection for Rejuvenation of Chalsa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 614/JD | 30/06/2023 | 30 | S. N. POLYMERS PVT. LTD. | 40.47 | 0 | 0 | 35
3448 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Retrofitting and Repairing work related to Laying Distribution System in Mangal Bar market area at Chalsa Rejuvenation Water Supply Scheme under Jalpaiguri Division, PHE DTE. | 1072/W/JSSD | 25/01/2022 | 20 | DEEP CONSTRUCTION | 4.14 | 0 | 0 | 0
3449 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084427, Reference ID : 860276303] | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.14 | 0 | 0 | 0
3450 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197396, Reference ID : 403049082] | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3451 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | New Service Connection Charge for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197399, Reference ID : 403049084] | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3452 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Infrastructure Cost for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000084429, Reference ID : 860276310] | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0 | 0
3453 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3454 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Material Requisition To Resource Division | 2034/JD | 09/01/2024 | 0 | Resource Division | 6.65 | 0 | 0 | 0
3455 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Construction of different components of Chalsa Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Matiali under Jalpaiguri Division. | 24/JD | 10/04/2023 | 905 | PRASENJIT BASAK | 195.5 | 0 | 0 | 90
3456 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0 | 0
3457 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3458 | JALPAIGURI | Jalpaiguri Division | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) of Chalsa Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. | 2157/JD | 29/10/2025 | 30 | PRASENJIT BASAK | 14.85 | 0 | 0 | 0
3459 | JALPAIGURI | Northern Mechanical | CHALSA TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/15264 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHALSA TEA GARDEN (ZONE-I,II) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1278/NMD | 02/08/2023 | 574 | MASSK ENGINEERING WORKS | 24.55 | 0 | 0 | 100
3460 | JALPAIGURI | Jalpaiguri Division | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | Relaying of Rising Main from Head Works Site to Pump House No.-II due to the Damage of HDPE Pipeline at Riabari T.G PWSS under Jalpaiguri Division, P.H.E. | 2403/JD | 20/12/2024 | 20 | SAPTASWA SARKAR | 1.32 | 0 | 0 | 0
3461 | JALPAIGURI | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | New Service Connection Charge for REJU RIA BARI TEA GARDEN, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003333061 , Reference ID : 403157468] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.73 | 0 | 0 | 0
3462 | JALPAIGURI | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
3463 | JALPAIGURI | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3464 | JALPAIGURI | Jalpaiguri Division | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | Construction of different components of Rejuvenation Of Riabari Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | 375/JD | 30/05/2023 | 999 | SAPTASWA SARKAR | 71.77 | 0 | 0 | 50
3465 | JALPAIGURI | Northern Mechanical | Rejuvanation of Riabari Tea Garden Area Piped Water Supply Scheme , SM/15103 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF RIABARI TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1483/NMD | 17/08/2023 | 534 | KARMAKAR CONSTRUCTION | 10.76 | 0 | 0 | 85
3466 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Construction of drain, development of land, Painting works of 250 Cu.M. capacity R.C.C. Elevated Reservoir, Pump House & Boundary Wall at Head works site for YongTong TG Piped Water Supply Scheme under Jalpaiguri Divition , P.H.E. Dte. | 606/JD | 09/03/2023 | 30 | PAMPA CONSTRUCTION | 6.2 | 0 | 0 | 0
3467 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Material Requisition To Resource Division | 1100/JD | 24/08/2023 | 0 | Resource Division | 14.64 | 0 | 0 | 0
3468 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of YongTong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 500/JSSD | 02/01/2024 | 30 | D. S. ENTERPRISE | 2.34 | 0 | 0 | 100
3469 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 0 | 100
3470 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.4003401347 Reference ID : 403212024 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3471 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.4003419056 Reference ID : 403225904 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3472 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.100000108225 Reference ID : 860300685 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.74 | 0 | 0 | 0
3473 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.100000108223 Reference ID : 860300683 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0 | 0
3474 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0 | 0
3475 | JALPAIGURI | Northern Mechanical | Rejuvenation of Yongtong Tea Garden Area Pipe Water Supply Scheme , SM/15299 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF YONGTONG TEA GARDEN AREA PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1318/NMD | 04/08/2023 | 696 | RMD TRADING | 24.24 | 0 | 0 | 100
3476 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Laying Distribution System (Part-L) along with 120 nos FHTC related to Rejuvenation of Nagrakata PWSS in connection with Jal Jeevan Mission at Block-Nagrakata under under Jalpaiguri Division, P.H.E. Dte. | 294/JSSD | 27/09/2023 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.68 | 0 | 0 | 60
3477 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | EMERGENT REPAIRING OF PIPE LINE, R.B.T FIXING IN BOUNDARY WALL, INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER NAGRAKATA T.G. PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE | 301/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 5.37 | 0 | 0 | 100
3478 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Commissioning of Rejuvenation of Nagrakata Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. (Phase-I) | 300/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 9.59 | 0 | 0 | 100
3479 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Material Requisition To Resource Division | 1058/JD | 24/08/2023 | 0 | Resource Division | 11.54 | 0 | 0 | 0
3480 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.100000107213 Reference ID : 860298383 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.41 | 0 | 0 | 0
3481 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.4003390273 Reference ID : 403202824 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3482 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.4003390283 Reference ID : 403202825 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3483 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.100000107214 Reference ID : 860298384 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.32 | 0 | 0 | 0
3484 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Construction of different components for Rejuvenation of Nagrakata Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | 438/JD. | 08/06/2023 | 573 | NARAYAN CHANDRA SAHA | 85.68 | 0 | 0 | 90
3485 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGRAKATA TG PWSS, TW no III & IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 668/NMD | 15/03/2024 | 472 | DEY ENTERPRISE(MALDA) | 24.07 | 0 | 0 | 95
3486 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagrakata Tea Garden Area Piped Water Supply Scheme , SM/15300 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0 | 0
3487 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Retro fitting works due to FHTC in connection for JJM under the command area of Huslu Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. | 675/JD | 16/03/2023 | 15 | M/S ROY & SARKAR CONSTRUCTION | 2.92 | 0 | 0 | 0
3488 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Material Requisition To Resource Division | 1048/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0 | 0
3489 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HASLURDANGA PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1382/NMD | 09/08/2023 | 30 | BLUE PINE | 20.22 | 0 | 0 | 100
3490 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Supply and Delivery of C.I special as when as required at T/W No-I of HASLUDANGA and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. | 1056/HQ/NMD | 21/06/2024 | 7 | B.B. CONCERNED | 0.73 | 0 | 0 | 100
3491 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | New Service Connection Charge for HUSLUDANGA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003356512 Reference ID : 403175904 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0 | 0
3492 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | New Service Connection Charge for HUSLUDANGA, T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003356517 Reference ID : 403175891 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.84 | 0 | 0 | 0
3493 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0 | 0
3494 | JALPAIGURI | Northern Mechanical | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3495 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF HASLURDANGA PIPED WATER SUPPLY SCHEME , SM/15031 | Augmentation | Construction of different components of Rejuvination of Haslurdanga PWSS i.e. TW, Pump Houses, Water distribution Network , Boundary wall , RISING MAIN , etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. | 388/A/JD | 01/06/2023 | 588 | BISWAJIT BHADURI | 82.64 | 0 | 0 | 100
3496 | JALPAIGURI | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Material Requisition To Resource Division | 1092/JD | 24/08/2023 | 0 | Resource Division | 60.02 | 0 | 0 | 0
3497 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN KANTADIGHI KUMARPARA TEA GARDEN PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1994/NMD | 21/12/2023 | 436 | SUBODH KUMAR BANIK | 25.51 | 0 | 0 | 70
3498 | JALPAIGURI | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Material Requisition To Resource Division | 2012/JD | 09/01/2024 | 0 | Resource Division | 15.28 | 0 | 0 | 0
3499 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 4003303019 , Reference ID : 403132354] | BP/23-24/261 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3500 | JALPAIGURI | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3501 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 4003303022 , Reference ID : 403132353] | BP/23-24/262 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3502 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 100000096844 , Reference ID : 860287694] | BP/23-24/263 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0 | 0
3503 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 4003303010 , Reference ID : 403132351] | BP/23-24/264 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0 | 0
3504 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 100000096846 , Reference ID : 860287696] | BP/23-24/265 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
3505 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 100000096843 , Reference ID : 860287693] | BP/23-24/260 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.14 | 0 | 0 | 0
3506 | JALPAIGURI | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Construction of different components of Kantadighi Kumarpara T.G. PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 247/JD | 10/05/2023 | 875 | S.S. CONSTRUCTION | 465.21 | 0 | 0 | 20
3507 | JALPAIGURI | Jalpaiguri Division | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Balance works Distribtion System and Functional Household Tap Connection (FHTC) including Different Components of Kantadighi Kumar Para TG PWSS i.e. TW, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. | 2037/JD | 21/11/2024 | 496 | SAPTASWA SARKAR | 82.16 | 0 | 0 | 40
3508 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0 | 0
3509 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3510 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3511 | JALPAIGURI | Northern Mechanical | KANTADIGHI KUMARPARA TEA GARDEN , SM/14879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KANTADIGHI KUMAPARA TG PWSS at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 655/NMD | 15/03/2024 | 231 | BONANZA ENTERPRISE | 12.34 | 0 | 0 | 100
3512 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 3rd Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-A) | 335/JD | 22/05/2023 | 30 | BAJRANG ENTERPRISE | 7.79 | 0 | 0 | 100
3513 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Material Requisition To Resource Division | 1052/JD | 24/08/2023 | 0 | Resource Division | 23.38 | 0 | 0 | 0
3514 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 4th Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-B) | 1414/JD | 03/10/2023 | 30 | ARUP SARKAR | 7.02 | 0 | 0 | 100
3515 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 0 | 100
3516 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 5th & 6th tube well site of Nagaisuree Tea Garden Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | 1361/JD | 11/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 0 | 0 | 100
3517 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Providing Inspection Vehicle WB-71B-9586 for JJM on daily basis @12.00/Km for Official use of the Assistant Engineer, Jalpaiguri Sadar-Sub Division P.H.E. Dte (OCT 2023 TO DEC 2023) | BP-2023-24-637 | 09/02/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0 | 0
3518 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at REJUVENATION OF NAGAISUREE TEA GARDEN PWSS for T/W No. V and VI in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. | 587/NMD | 07/02/2025 | 30 | ALPHA ENTERPRISE | 27.14 | 0 | 0 | 0
3519 | JALPAIGURI | Northern Mechanical | Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme , SM/15060 | Augmentation | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0 | 0
3520 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Material Requisition To Resource Division | 1061/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0 | 0
3521 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JOGESH CHANDRA TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1345/NMD | 08/08/2023 | 481 | SAIKAT SINHA | 11.35 | 0 | 0 | 50
3522 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Infrastructure development cost for new service connection at Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 100000103458 Reference ID : 860295868 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0 | 0
3523 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | New Service Connection Charge for Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 4003373903 Reference ID : 403190124 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3524 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3525 | JALPAIGURI | Northern Mechanical | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3526 | JALPAIGURI | Jalpaiguri Division | REJUVENATION OF JOGESH CHANDRA TEA GARDEN AREA PWSS , SM/15068 | Augmentation | Construction of different components for Rejuvenation of Jogesh Chandra Tea Garden PWSS I.e. TW, Pump Houses, Rising Main, Boundary wall etc. at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | 1541/JD | 26/10/2023 | 163 | M/S KARMAKAR CONSTRUCTION | 22.42 | 0 | 0 | 100
3527 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | 1936/JD | 29/11/2021 | 15 | PRABIR SHOME | 3.75 | 0 | 0 | 1
3528 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Dakhsin Dangapara Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | 940/JD | 18/04/2022 | 15 | SUKES BASU MAJUMDAR | 1.25 | 0 | 0 | 100
3529 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E.Dte. | 1852/JD | 16/09/2022 | 21 | SADHAN KARMAKAR | 2.8 | 0 | 0 | 1
3530 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Restoration of damaged DI pipeline at Patkidaha Piped W/S Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | 1312/JD | 15/06/2022 | 15 | M/S SIBU DEY AND CO. | 1.82 | 0 | 0 | 100
3531 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Material Requisition To Resource Division | 1062/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
3532 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Retrofitting of distribution pipeline network within Dambari Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | 1935/JD | 29/11/2021 | 15 | KULDIP KAPOOR | 1.47 | 0 | 0 | 100
3533 | JALPAIGURI | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PATKIDAHA PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 476/NMD | 26/04/2023 | 30 | BONANZA ENTERPRISE | 11.5 | 0 | 0 | 100
3534 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Retrofittings of distribution pipeline network within Dambari Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri development Block under Jalpaiguri Division, P.H.E.Dte. | 1786/JD | 08/12/2023 | 21 | KULDIP KAPOOR | 4.3 | 0 | 0 | 100
3535 | JALPAIGURI | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | New Service Connection Charge for REJU PATKIDHAHA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328075 , Reference ID : 403153542] | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0 | 0
3536 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Construction of Boundary Wall, Pathway, Drain, Providing FHTC, IEP Washout etc. at 3rd TW Site for Patkidaha PWSS icw JJM under Jalpaiguri Division, PHE Dte. | 1529/JD | 01/10/2024 | 273 | SADHAN KARMAKAR | 15.77 | 0 | 0 | 40
3537 | JALPAIGURI | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
3538 | JALPAIGURI | Northern Mechanical | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3539 | JALPAIGURI | Jalpaiguri Division | Rejuvenation for Patkidaha Piped Water Supply Scheme , SM/15085 | Augmentation | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Patkidaha PWSS , in connection with Rejuvenation of Patkidaha PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | 374/JD | 30/05/2023 | 666 | SADHAN KARMAKAR | 47.23 | 0 | 0 | 20
3540 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | Material Requisition To Resource Division | 1051/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0 | 0
3541 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | New Service Connection Charge for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 4003460491 Reference ID : 403255265 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0 | 0
3542 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | Infrastructure development cost for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 100000115667 Reference ID : 860308377 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.66 | 0 | 0 | 0
3543 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | Construction of different components of Rejuvenation of Purba Duramari PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | 334/JD | 22/05/2023 | 728 | MONTOSH GHOSH | 41.09 | 0 | 0 | 100
3544 | JALPAIGURI | Northern Mechanical | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PURBA DURAMARI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1219/NMD | 26/07/2023 | 676 | BONANZA ENTERPRISE | 11.5 | 0 | 0 | 100
3545 | JALPAIGURI | Jalpaiguri Division | Rejuvenation of Purba Duramari Piped Water Supply Scheme , SM/15326 | Augmentation | Balance Laying Water Distribution Network including Providing Functional Household Tap Connection (FHTC) of Purba Duramari PWSS in connection with Jal Jeevan Mission at Block-Banarhat under Jalpaiguri Division, P.H.E. Dte. | 2320/JD | 11/12/2024 | 171 | DEEP CONSTRUCTION | 13.08 | 0 | 0 | 100
3546 | JALPAIGURI | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Material Requisition To Resource Division | 1111/JD | 24/08/2023 | 0 | Resource Division | 20.09 | 0 | 0 | 0
3547 | JALPAIGURI | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Material Requisition To Resource Division | 1844/JD | 15/12/2023 | 0 | Resource Division | 8.57 | 0 | 0 | 0
3548 | JALPAIGURI | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Jhar Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | 2268/JD | 04/12/2024 | 45 | J.M. CONSTRUCTION | 32.13 | 0 | 0 | 0
3549 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | New Service Connection Charge for JHAR SHALBARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003364367 Reference ID : 403181756 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.75 | 0 | 0 | 0
3550 | JALPAIGURI | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Construction of different components of Jhar Salbari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | 139/JD | 28/04/2023 | 795 | ALLIED INSTRUMENTS | 310.52 | 0 | 0 | 10
3551 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for JHAR SALBARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1207/NMD | 26/07/2023 | 829 | SUBODH KUMAR BANIK | 20.26 | 0 | 0 | 60
3552 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0 | 0
3553 | JALPAIGURI | Jalpaiguri Division | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Sinking of 3rd Tube well by Reverse Rotary Method of drilling inlucing Construction of Pump House (3.6m x 2.4m) and Laying Rising main for Jhar Salbari PWSS under Dhupguri Block icw Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | 454/JD | 10/03/2025 | 50 | M/S S. G. ENTERPRISE | 17.55 | 0 | 0 | 0
3554 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0 | 0
3555 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
3556 | JALPAIGURI | Northern Mechanical | JHAR SHALBARI PIPED WATER SUPPLY SCHEME , SM/15742 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0 | 0
3557 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SONGACHHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15624 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
3558 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT SONGACHHI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15624 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3559 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15604 | Solarisation | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1215/HQ/NMD | 15/07/2024 | 15 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 100
3560 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF ARJI MARIA KAMALA PUKHARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15604 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3561 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHAGATPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15597 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | 1214/HQ/NMD | 15/07/2024 | 15 | SARKAR ELECTRIC | 4.11 | 0 | 0 | 100
3562 | JALPAIGURI | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHAGATPUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. , SM/15597 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | 1631/NMD | 27/09/2023 | 855 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 93
3563 | JALPAIGURI | Jalpaiguri Division | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Material Requisition To Resource Division | 1075/JD | 24/08/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
3564 | JALPAIGURI | Jalpaiguri Division | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Material Requisition To Resource Division | 1835/JD | 15/12/2023 | 0 | Resource Division | 0.71 | 0 | 0 | 0
3565 | JALPAIGURI | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | New Service Connection Charge for PRAYAGPUR PWSS, TW NO I, BANARHAT CCC. APPLICATION NO. 4003506434 Reference ID : 403286480 | BP/24-25/244 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.66 | 0 | 0 | 0
3566 | JALPAIGURI | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PRAYAGPUR PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1249/NMD | 31/07/2023 | 763 | KARMAKAR CONSTRUCTION | 10.96 | 0 | 0 | 90
3567 | JALPAIGURI | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0 | 0
3568 | JALPAIGURI | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0 | 0
3569 | JALPAIGURI | Northern Mechanical | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0 | 0
3570 | JALPAIGURI | Jalpaiguri Division | PRAYAGPUR (D) MINI PIPED WATER SUPPLY SCHEME , SM/14224 | New | Construction of different components of Prayagpur (D) Mini PWSS TW, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | 436/JD. | 08/06/2023 | 754 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 64.63 | 0 | 0 | 10
3571 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme , SM/06847 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of JURANTI T.G. Area piped Water Supply Scheme at Metiali Block under Jalpaiguri Division, PHE Dte. (PART-B) | 1277/JD | 18/11/2020 | 90 | NARAYAN CHANDRA SAHA | 43.68 | 0 | 0 | 80
3572 | JALPAIGURI | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Juranti T.G Area Piped Water Supply Scheme , SM/06847 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PALASHBARI TEA GARDEN area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | 1280/JD | 18/11/2020 | 45 | SANKAR DAS | 16.96 | 16.94 | 100 | 0
3573 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0 | 0
3574 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Damdim TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. | 2274/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 91.26 | 0 | 0 | 0
3575 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Estimate for Balance work of Water Distribution Network in Damdim Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 569/JSSD | 05/03/2024 | 30 | PRABIR SHOME | 9.05 | 0 | 0 | 100
3576 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Material Requisition To Resource Division | 2017/JD | 09/01/2024 | 0 | Resource Division | 12.02 | 0 | 0 | 0
3577 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Material Requisition To Resource Division | 2071/JD | 25/11/2024 | 0 | Resource Division | 38.02 | 0 | 0 | 0
3578 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000098645, Reference ID : 860290455] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0 | 0
3579 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No.I, under ODLABARI CCC, [APPLICATION NO. 4003325562, Reference ID : 403151430] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3580 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000098644, Reference ID : 860290454] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0 | 0
3581 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003325572, Reference ID : 403151429] | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3582 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3583 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Construction of different components of Damdim Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 1257/JD | 13/09/2023 | 607 | PRASENJIT BASAK | 297.11 | 0 | 0 | 40
3584 | JALPAIGURI | Jalpaiguri Division | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Damdim TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | 100/JSSD | 30/05/2025 | 306 | JAYA SARKAR | 6.37 | 0 | 0 | 0
3585 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3586 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3587 | JALPAIGURI | Northern Mechanical | DAMDIM TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18711 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAMDIM TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1441/NMD | 10/08/2023 | 479 | DILIP MAHATO | 25.34 | 0 | 0 | 100
3588 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme , SM/07304 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Patkidaha and Jakhaikona Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte | 209/JD | 11/02/2021 | 30 | PRABIR SHOME | 21.88 | 0 | 0 | 1
3589 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme , SM/07304 | Retrofitting | PROVIDING FHTC FOR PURBA MAGURMARI PWSS | 192/21-22 | 02/08/2021 | 0 | A.P CONSTRUCTION | 25.1 | 0 | 0 | 0
3590 | JALPAIGURI | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Patkidaa & Jakhaikona Mouza under Patkidaha Piped Water Supply Scheme , SM/07304 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 10.76 | 100 | 1
3591 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Material Requisition To Resource Division | 1090/JD | 24/08/2023 | 0 | Resource Division | 24.92 | 0 | 0 | 0
3592 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0 | 0 | 70
3593 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-I) PWSS i.e. OHR,TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. of North Bengal Circle-I, PHE Dte. | 936/JD | 07/08/2024 | 300 | SUJIT KUMAR SAHA | 183.05 | 0 | 0 | 0
3594 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0 | 0 | 0
3595 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.07.2024 to 31.08.2024)" | 531/JD | 28/06/2024 | 61 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
3596 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Material Requisition To Resource Division | 2070/JD | 10/01/2024 | 0 | Resource Division | 17.24 | 0 | 0 | 0
3597 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Material Requisition To Resource Division | 2029/JD | 19/11/2024 | 0 | Resource Division | 108.92 | 0 | 0 | 0
3598 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Infrastructure Cost for ODLABARI TEA GARDEN,T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093886, Reference ID : 860285546] | 23-24/160&168 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0 | 0
3599 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 78 3405) | BP-2024-25-97 | 22/05/2024 | 0 | FILL & SMILE | 0.36 | 0 | 0 | 0
3600 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of Fuel bill for the Month of October'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-560 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0 | 0
3601 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-531 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3602 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-269 | 30/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0 | 0
3603 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-533 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3604 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | New Service Connection Charge for ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424001 Reference ID : 403230049 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0 | 0
3605 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | New Service Connection Charge for ODLABARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266395, Reference ID : 403105528] | 23-24/160&168 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.91 | 0 | 0 | 0
3606 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of fuel (Diesel) for vehicle no. WB-71B-9430 for the month of February-2024 | BP-2024-25-64 | 14/05/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3607 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 76 7338) | BP-2024-25-529 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3608 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of Fuel bill for the Month of April,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-183 | 28/06/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0 | 0
3609 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of Fuel bill for the Month of November'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-561 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0 | 0
3610 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 78 3405) | BP-2024-25-98 | 22/05/2024 | 0 | FILL & SMILE | 0.28 | 0 | 0 | 0
3611 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 78 3405) | BP-2024-25-523 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3612 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 76 7338) | BP-2024-25-522 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3613 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 78 3405) | BP-2024-25-530 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3614 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month January'2024 (Vehicle No. WB 71 B 9430) | BP-2024-25-240 | 26/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0 | 0
3615 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0 | 0
3616 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Infrastructure development cost for new service connection at ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109306 Reference ID : 860301266 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.48 | 0 | 0 | 0
3617 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 78 3405) | BP-2024-25-532 | 13/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
3618 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (Petrol) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9586) | BP-2024-25-559 | 20/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3619 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 78 3405) | BP-2024-25-497 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0 | 0
3620 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of Fuel bill for the Month of March,2024 Vide Vehicle no-WB71B9586 under Jalpaiguri Sadar Sub-Division, PHE Dte | BP-2024-25-182 | 28/06/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0 | 0
3621 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of Engine oil, Gear Oil and Kool plus Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte | BP-2024-25-181 | 28/06/2024 | 0 | FILL & SMILE | 0.07 | 0 | 0 | 0
3622 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 78 3405) | BP-2024-25-294 | 14/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0 | 0
3623 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Construction of different components of Oodlabari Tea Garden (Zone-II) PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. | 800/JD. | 24/07/2023 | 892 | GHANASHYAM SARKAR | 281.55 | 0 | 0 | 40
3624 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ODLABARI TEA GARDEN PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | 1585/NMD | 08/09/2023 | 754 | CHOWDHURY AND BASU ENTERPRISE | 42.08 | 0 | 0 | 68
3625 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0 | 0 | 50
3626 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission. Period from 01/08/2024 to 31/01/2025. | 125/JSSD | 18/07/2024 | 184 | APIKUL ALI | 0.88 | 0 | 0 | 0
3627 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0 | 0 | 0
3628 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM From 01.09.2024 to 28.02.2025 (Vehicle No.: - WB 76 9978) | 206/JSSD | 30/08/2024 | 182 | APIKUL ALI | 0.88 | 0 | 0 | 0
3629 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. (Vehicle No-WB 71B 9586) w.e.f. 1.02.2025-31.07.2025. | 434/JSSD | 31/01/2025 | 181 | DHIRAJ BISWAS | 0.88 | 0 | 0 | 30
3630 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | 824/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0 | 0 | 100
3631 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0 | 0
3632 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation work of " Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission". Period from 01.02.2025 to 31.07.2025. (Vichle No. WB 78 3405) | 418/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0 | 0 | 0
3633 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st February 2025 to 31st July 2025) | 417/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0 | 0 | 0
3634 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | 1498/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 0 | 100
3635 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | 1503/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 0 | 100
3636 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | 819/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0 | 0 | 100
3637 | JALPAIGURI | Northern Mechanical | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0 | 0
3638 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Construction approach with paver block inside the premises and land ment at HW site & 2nd TW Site of Oodlabari TG (Z-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | 170/JSSD | 24/07/2025 | 30 | SUBHANKAR DEY | 6.57 | 0 | 0 | 0
3639 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation Order for the Work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.11.2024 to 31.12.2024)" | 1797/JD | 30/10/2024 | 61 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
3640 | JALPAIGURI | Jalpaiguri Division | ODLABARI TEA GARDEN PIPED WATER SUPPLY SCHEME , SM/18356 | New | Continuation Order for the Work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.09.2024 to 31.10.2024)" | 1215/JD | 28/08/2024 | 61 | GURUKUL INFOTECH | 3.16 | 0 | 0 | 100
3641 | JALPAIGURI | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16508 | Support-WQMSP | Procurement of Chemicals, Consumables for 04 No's laboratories under Jalpaiguri Division PHE Dte. | 721/JD | 20/03/2023 | 30 | ARUNALOY SCIENTIFIC HOUSE | 9.87 | 0 | 0 | 100
3642 | JALPAIGURI | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16508 | Support-WQMSP | Procurement of necessary Chemicals and consumables for regular & NABL related water sample testing purpose of Laboratories under Jalpaiguri Division. PHE. Dte.for one month. | 734/RWS | 02/08/2024 | 31 | ARUNALOY SCIENTIFIC HOUSE | 0.97 | 0 | 0 | 100
3643 | JALPAIGURI | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16508 | Support-WQMSP | Honorarium of the LAB personnel & Maintenance Charge of The Laboratory for October, November & December 2023 from Office memo No-RWO/L/05 Date-19/12/2023 and Govt Memo no-PHE/WSSO/112/2827-2844 date-07/12/2015 for draft Mou regarding the agreement between NGO managing water testing laboratory & PHED,Govt. of west Bengal and ORDER no-27552-27581/MC/LABS/000007/2021 Date-14/12/2022 for Enhancement of Monthly remuneration of lab personal and fund thereto | BP-2023-24-662 | 20/02/2024 | 0 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
3644 | JALPAIGURI | Jalpaiguri Division | PROCUREMENT OF CHEMICALS - GLASSWARE & MAINTENANCE OF COMPUTER OF PHED & NGO MANAGED LABORATORIES RELATED TO WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16508 | Support-WQMSP | Work of Operation of Chalsa Laboratory at Chalsa PWSS premises for Physical, Chemical and Bacteriological test of water sample under Jalpaiguri Division, PHE Dte. From 1st February 2023 to 31st January 2024. | 865/JD | 01/08/2023 | 366 | SUKES BASU MAJUMDAR | 5.22 | 0 | 0 | 100
3645 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory , SM/08681 | Support-WQMSP | Estimate for procurement of miscellenious items for Jalpaiguri District water testing laboratory for developing the NABL set up under Jalpaiguri Division P.H.E Dte. | 848/RWS | 03/12/2021 | 7 | ARUNALOY SCIENTIFIC HOUSE | 3.12 | 0 | 0 | 0
3646 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory , SM/08681 | Support-WQMSP | Improvement of Lab rooms & ancilliary works at Dhupguri Sub District Lab & excess works of Chalsa Sub District Lab under Jalpaiguri Division , P.H.E. Dte. | 873/RWS | 08/12/2021 | 10 | NEW KUNDU ENTERPRISE | 3.79 | 0 | 0 | 0
3647 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory , SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Chalsa Sub- District Water Testing Laboratory under Jalpaiguri Division, P.H.E. Dte. | 1263/RWS | 22/11/2023 | 10 | SWAPAN SAHA | 0.1 | 0 | 0 | 100
3648 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory , SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Dhupguri Sub-District Laboratory under Jalpaiguri Division, P.H.E.Dte. | 1262/RWS | 22/11/2023 | 10 | SWAPAN SAHA | 0.1 | 0 | 0 | 100
3649 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals, Glassware and Instrument equipment for NABL Accreditation of Jalpaiguri District Laboratory , SM/08681 | Support-WQMSP | Installation of NABL specified signboard at the entrance of Jalpaiguri District Water Testing Laboratory under Jalpaiguri Division, P.H.E.Dte. | 1261/RWS | 22/11/2023 | 10 | SWAPAN SAHA | 0.1 | 0 | 0 | 100
3650 | JALPAIGURI | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities related to FHTC under JJM Support Activities at Jalpaiguri District. , SM/09018 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Jalpaiguri District | 4688/RS | 17/08/2022 | 365 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 105.71 | 0 | 0 | 75
3651 | JALPAIGURI | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P , SM/19171 | Support-IEC | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. | 942/JD | 07/08/2024 | 10 | BALARAM GHOSH & SONS | 2.21 | 0 | 0 | 100
3652 | JALPAIGURI | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P , SM/19171 | Support-IEC | Execution of Special Community Mobilization and Community Ownership Drive through printing & Supply IEC Leaflets & Banner for distribution on FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water, Water Quality issues, water conservation and WASH related issues as per guideline of JJM and preparation of web based Digital (A/V) awareness generation cum training material (Bengali) with voice over showcasing IEC and HRD initiative at Jalpaiguri District under Jalpaiguri Division, PHE Dte, Govt. of West Bengal. | 1639/JD | 17/07/2025 | 92 | SHOUMMYODIP & CO | 13.33 | 0 | 0 | 0
3653 | JALPAIGURI | Jalpaiguri Division | Orientation and Mass Awareness Generation ( IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues under Jal Jeevan Mission (JJM) Support Activities at Jalpaiguris District under Jalpaiguri Division. P , SM/19171 | Support-IEC | Execution of Special Community Mobilization and Community Ownership Drive through Tableau (Mobile IEC Van), Street Play and Miking on JJM / FHTC; Save Water; Water Conservation, illegal pumping & connection; safe handling & storage of safe water; Quality issues and other WASH related issues as per guideline of JJM at Jalpaiguri District under Jalpaiguri Division, PHE Dte, Govt. of West Bengal. | 1638/JD | 17/07/2025 | 92 | DEBNATH BROTHERS | 26.91 | 0 | 0 | 0
3654 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS and annual maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06615 | Support-WQMSP | Supply of water testing/reagents of Jalpaiguri district laboratory under Jalpaiguri Division P.H.E.Dte. | 126/RWS | 17/03/2020 | 10 | ARUNALOY SCIENTIFIC HOUSE | 4.86 | 0 | 0 | 0
3655 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS and annual maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06615 | Support-WQMSP | Estimate for procurement of Chemicals, Consumables for 04 No's laboratories under Jalpaiguri Division PHE Dte. | 512/RWS | 08/08/2022 | 15 | M/S PAMPA CONSTRUCTION | 3.06 | 0 | 0 | 0
3656 | JALPAIGURI | Jalpaiguri Division | Procurement of Chemicals & Consumables, Glassware for Laboratories, Consumables for OMAS and annual maintenance contract of Computer, Printer, UPS & other peripherals for Laboratories. , SM/06615 | Support-WQMSP | Procurement of necessary Consumables (having 2 years shelve life from date of supply), Glasswares, Plasticwares etc. for Regular & NABL related water sample testing purpose for 4 No Laboratories (including 1 No NGO Managed) under Jalpaiguri Division, PHE Dte. for 12 months. | 1295/JD | 05/09/2024 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 11.66 | 0 | 0 | 100
3657 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | Purchase of 09 (nine) nos. of Laptop under Jalpaiguri Division PHEDTE. | 2218/JD | 11/12/2022 | 1 | PINCHA COMPUTER | 4.99 | 0 | 0 | 0
3658 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | Purchase of 09 (Nine) Nos. of Desktop and 09 (Nine) Nos. of Monitor under Jalpaiguri Division, PHE Dte. | 2284/JD | 23/11/2022 | 1 | PINCHA COMPUTER | 4.71 | 0 | 0 | 0
3659 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | Purchase of 01 (One) no of Scanner under Jalpaiguri division, PHE Dte | 2285/JD | 23/11/2022 | 1 | PINCHA COMPUTER | 0.33 | 0 | 0 | 0
3660 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | PURCHASE OF 9 LAPTOP | BP-2022-23-425 | 01/02/2023 | 0 | PINCHA COMPUTER | 4.99 | 0 | 0 | 0
3661 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | PURCHASE OF 9 NOS COMPUTER AND MONITOR | BP-2022-23-426 | 01/02/2023 | 0 | PINCHA COMPUTER | 4.71 | 0 | 0 | 0
3662 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | PURCHASE OF 1NO. SCANNER | BP-2022-23-424 | 01/02/2023 | 0 | PINCHA COMPUTER | 0.33 | 0 | 0 | 0
3663 | JALPAIGURI | Jalpaiguri Division | SUPPLY DELIVERY AND INSTALLATION OF COMPUTER & OTHER PERIPHERAL DEVICES FOR OFFICIAL USE UNDER OFFICE OF SUPERINTENDING ENGINEER NORTH BENGAL CIRCLE-I & EXECUTIVE ENGINEER, JALPAIGURI DIVISION P.H.E. DTE. , SM/11170 | Support-MIS | supply of Hp multifunction machine | BP-2022-23-512 | 10/03/2023 | 0 | TRANSCON ELECTRONICS PVT. LTD. | 1.15 | 0 | 0 | 0
3664 | JALPAIGURI | Jalpaiguri Division | DRINKING WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KITS (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION , SM/13679 | Support-WQMSP | FTK test by ASHA Workers | BP-2023-24-600 | 16/01/2024 | 0 | DISTRICT HEALTH AMP FAMILY WELFARE SAMITY | 9.05 | 0 | 0 | 0
3665 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order Honorarium for of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 4 Months from 01/08/2022 to 30/11/2022 | 476/RWS | 25/07/2022 | 123 | R.S CONSTRUCTION | 3.08 | 0 | 0 | 0
3666 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Further Continuation order Honorarium for of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 4 Months from 01/12/2022 to 31/03/2023 | 658/RWS | 07/11/2022 | 120 | R.S CONSTRUCTION | 2.8 | 0 | 0 | 0
3667 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Work of Running Dhupguri Laboratory at Dhupguri PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte.for 4 Months from 01-10-2022 to 31.01.2023. | 617/RWS | 29/09/2022 | 122 | SUKES BASU MAJUMDAR | 1.08 | 0 | 0 | 100
3668 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Further Continuation order Honorarium fur of Running District Laboratory staff for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division office P.H.E. Dte.for 3 Months from 01/04/2023 to 30/06/2023 | 308/RWS | 31/03/2023 | 91 | R.S CONSTRUCTION | 2.1 | 0 | 0 | 100
3669 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Work of Running Chalsa Laboratory at Chalsa PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 4 Months from 01-10-2022 to 31-01-2023 | 618/RWS | 29/09/2022 | 122 | SUKES BASU MAJUMDAR | 1.08 | 0 | 0 | 100
3670 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Work of Running Dhupguri Laboratory at Dhupguri zone - ii PWSS Premises for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 6 Months from 01-02-2023 to 31-07-2023. | 74/RWS | 31/01/2023 | 181 | SUKES BASU MAJUMDAR | 1.69 | 0 | 0 | 100
3671 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Work of Running Chalsa Laboratory at Chalsa PWSS Premie for physical, chemical and Bacteriological test of water sample under Jalpaiguri Division P.H.E. Dte. for 6 Months from 01-02-2023 to 31-07-2023. | 73/RWS | 31/01/2023 | 181 | SUKES BASU MAJUMDAR | 1.69 | 0 | 0 | 100
3672 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Organizing the updating and synchronization of different data related with laboratory, PWSS etc. in connection with Jalswapna under Jalpaiguri division PHE Dte. for 2 Months from 01/05/2023 to 30/06/2023 | 435/RWS | 28/04/2023 | 61 | R.S CONSTRUCTION | 0.27 | 0 | 0 | 100
3673 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Continuation order for Organizing the updating and synchronization of different data related with laboratory, PWSS etc. in connection with Jalswapna under Jalpaiguri division PHE Dte. for 3 Months from 01/05/2023 to 30/06/2023 | 435/RWS | 28/04/2023 | 61 | R.S CONSTRUCTION | 0.27 | 0 | 0 | 100
3674 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Festival bonus for laboratory personnel for the financial year 2022-2023 | BP-2023-24-395 | 29/09/2023 | 0 | RAJGANJ WELLFEAR ORGANISATION | 0.16 | 0 | 0 | 0
3675 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | HONORARIUM OF THE LAB PERSONNEL & MAINTAINENCE CHARGE OF THE LAB FOR THE MONTH OF APRIL MAY JUNE 2023 | BP-2023-24-224 | 17/07/2023 | 0 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
3676 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | T.A of transportation of referral sample of Dist lab of Jalpaiguri and other Sub Dist labs & N.G.O .managed lab of Jalpaiguri to Mangal Pandey Referral lab. | BP-2023-24-329 | 25/08/2023 | 0 | SUJIT BASU | 0.06 | 0 | 0 | 0
3677 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Honorarium of the lab personnel and maintenance charge of the laboratory for January, February & March of Rajganj Welfare Organization,P.O- Rajganj,Dist-Jalpaiguri(Government of West Bengal Supported Rural Drinking Water Testing Laboratory) Registration No-S/83259,ESTD-1992 Ref No-RWO/L/06 Dated-27.03.2024 | BP-2024-25-65 | 14/05/2024 | 0 | RAJGANJ WELLFEAR ORGANISATION | 1.54 | 0 | 0 | 0
3678 | JALPAIGURI | Jalpaiguri Division | OPERATIONAL CHARGES OF PHED MANAGED LABORATORIES RELATED TO WATE QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/16509 | Support-WQMSP | Work of Operation for Dhupguri Laboratory at Dhupguri Zone-II PWSS premises Physical, Chemical and Bacteriological test of water sample under Jalpaiguri Division, PHE Dte. From 1st February 2023 to 31st January 2024. | 864/JD | 01/08/2023 | 366 | B.M CONSTRUCTION | 5.01 | 0 | 0 | 100
Total | [9 empty] | 152612.11 | 662.06 | 0.43